## June-14
Local Government Engineering Department
Construction of Large Bridge on Upazila & Union road project
Monthly Progress Report
Progress -July/2014
DPP Sl. No. | Name of District | Name of Upazila | Name of Scheme | Length (m) | No of Span | Estimated cost (TK.) | Contract Amount (TK.) | Name of Contractor | Date of work order | Date of completion as per work order | Actual date of completion | Pile (no) |  |  | Pile Cap (no)
[12 empty] | Total | Completed | Rest | Total | Completed | Rest
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Chapai Nawabganj | Shibganj | Construction of 85.00m long RCC Bridge on Shahabazpur UP Office - Telkupee Hat Road via Chalkpara BOP & Mondaltola Road, ID. No. 170883029 under Shibganj Upazila in Chapai Nawabganj District. (Package No-PD,CLBUURP,W-151). | 85 | 5 | 17788447 | 17770897.66 | Moyen Khan & Abdul Mannan JV | 24/8/2010 | 26/3/2012 | 19-3-2012 | 56 | 56 | - | 6 | 6 | -
2 | Chapai Nawabganj | Sadar | Construction of 546.600m long PC Girder Bridge over Mohananda river on Namosankorbati G.C - Dhulauri G.C via Saheber Ghat under Chapai Nawabganj Sadar Upazila Package No. LBC/CNG/PQ/01 . | 546.6 | 13 | 497924000 | 497924000 | WMCG-NAVANA JV | 2011-01-03 | 9/9/2013 (Ex. Date of W/O 09/06/14) |  | 165 | 165 | - | 14 | 14 | -
|  |  | 45.00m Bridge in the Same Road (Ch. 184m) | 45 | 3 | [6 empty] | 52 | 52 | - | 4 | 4 | -
|  |  | 48.00m Bridge in the Same Road (Ch. 2190m) | 48 | 4 | [6 empty] | 56 | 56 | - | 5 | 5 | -
3 | DO | DO | Execution of the works of (Bridge/Road Lighing work) 546.60m long Bridge and its approach road of Namosankarbati G,c to Dhulauri G,C over Mohananda river |  |  | 50847005 | 50847005 | NAVANA Construction | 26-2-14 | 2015-04-03
Sub-Total = |  |  |  | 724.6 |  | 566559452 | 566541902.66
Abutment & Pier (no) |  |  | Girder (no) |  |  | Slab (no) |  |  | Approach (m) |  |  | Physical progress (%) | Fund Released (In Lac) | Fund Spent (In Lac) | Remarks
Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest
19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
6 | 6 | - | 10 | 10 | - | 5 | 5 | - | 100m | 100m | - | 100% | 4671.95 | 176.8711 | Final Bill
14 | 14 | - | 52 | 51 | 1 | 13 | 10 | 3 | 1800 | 1400m WBM+1400m Earth work | 400m | 89% |  | 4435.42
4 | 4 | - | 12 | 12 | - | 3 | 3 | 0
5 | 5 | - | Slab Bridge | Slab Bridge | - | 4 | 4 | -
[12 empty] | 12% |  | 59.6589
Sub-Total = | [12 empty] | 4671.95 | 4671.95
Grand Total = |  |  |  | 724.6 |  | 566559452 | 566541902.66 | [5 empty] | 4671.95 | 4671.95
|  |  | Accountant |  |  | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
|  |  | LGED |  |  | LGED |  |  |  | LGED |  |  |  | LGED
|  |  | Chapai Nawabgaj |  |  | Chapai Nawabgaj |  |  |  | Chapai Nawabgaj |  |  |  | Chapai Nawabgaj
Fund Released |  | 4671.95 | Lac
Fund Spend |  | 4671.95 | Lac
Fund Balance |  | 0 | Lac

## July-14
Local Government Engineering Department
Construction of Large Bridge on Upazila & Union road project
Monthly Progress Report
Progress -July/2014
DPP Sl. No. | Name of District | Name of Upazila | Name of Scheme | Length (m) | No of Span | Estimated cost (TK.) | Contract Amount (TK.) | Name of Contractor | Date of work order | Date of completion as per work order | Actual date of completion | Pile (no) |  |  | Pile Cap (no)
[12 empty] | Total | Completed | Rest | Total | Completed | Rest
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Chapai Nawabganj | Shibganj | Construction of 85.00m long RCC Bridge on Shahabazpur UP Office - Telkupee Hat Road via Chalkpara BOP & Mondaltola Road, ID. No. 170883029 under Shibganj Upazila in Chapai Nawabganj District. (Package No-PD,CLBUURP,W-151). | 85 | 5 | 17788447 | 17770897.66 | Moyen Khan & Abdul Mannan JV | 24/8/2010 | 26/3/2012 | 19-3-2012 | 56 | 56 | - | 6 | 6 | -
2 | Chapai Nawabganj | Sadar | Construction of 546.600m long PC Girder Bridge over Mohananda river on Namosankorbati G.C - Dhulauri G.C via Saheber Ghat under Chapai Nawabganj Sadar Upazila Package No. LBC/CNG/PQ/01 . | 546.6 | 13 | 497924000 | 497924000 | WMCG-NAVANA JV | 2011-01-03 | 9/9/2013 (Ex. Date of W/O 09/06/14) |  | 165 | 165 | - | 14 | 14 | -
|  |  | 45.00m Bridge in the Same Road (Ch. 184m) | 45 | 3 | [6 empty] | 52 | 52 | - | 4 | 4 | -
|  |  | 48.00m Bridge in the Same Road (Ch. 2190m) | 48 | 4 | [6 empty] | 56 | 56 | - | 5 | 5 | -
3 | DO | DO | Execution of the works of (Bridge/Road Lighing work) 546.60m long Bridge and its approach road of Namosankarbati G,c to Dhulauri G,C over Mohananda river |  |  | 50847005 | 50847005 | NAVANA Construction | 26-2-14 | 2015-04-03
Sub-Total = |  |  |  | 724.6 |  | 566559452 | 566541902.66
Abutment & Pier (no) |  |  | Girder (no) |  |  | Slab (no) |  |  | Approach (m) |  |  | Physical progress (%) | Fund Released (In Lac) | Fund Spent (In Lac) | Remarks
Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest
19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
6 | 6 | - | 10 | 10 | - | 5 | 5 | - | 100m | 100m | - | 100% | 5071.95 | 176.8711 | Final Bill
14 | 14 | - | 52 | 52 | 0 | 13 | 13 | 0 | 1800 | 1400m WBM+1400m Earth work | 400m | 92% |  | 4465.74
4 | 4 | - | 12 | 12 | - | 3 | 3 | 0
5 | 5 | - | Slab Bridge | Slab Bridge | - | 4 | 4 | -
[12 empty] | 20% |  | 106.47
Sub-Total = | [12 empty] | 5071.95 | 4749.0811
Grand Total = |  |  |  | 724.6 |  | 566559452 | 566541902.66 | [5 empty] | 5071.95 | 4749.0811
|  |  | Accountant |  |  | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
|  |  | LGED |  |  | LGED |  |  |  | LGED |  |  |  | LGED
|  |  | Chapai Nawabgaj |  |  | Chapai Nawabgaj |  |  |  | Chapai Nawabgaj |  |  |  | Chapai Nawabgaj
Fund Released |  | 5071.95 | Lac
Fund Spend |  | 4749.0811 | Lac
Fund Balance |  | 322.8689 | Lac