## Progress
Sylhet Division Rural Infrastructure Improvement Project ( SDRIIP)
Monthly Progress Report ( Physical & Financial)
District:- Habigonj
Reporting Month:January/2015
Sl. No. | Package No. | Road ID | Name of Scheme with location (Chainage) | Quantity |  | Estimated Coat (Tk) |  |  | Tender receiving date | Name of Contractor | Date of Contract | Contract Amount (Tk) | Physical Progress | Date of Completion | Payment made (Tk) |  | Remarks
|  |  |  | Road (Km) | Stru. (M) | Road | Structure | Total | [6 empty] | Road | Structure
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Bahubal
1 | SDRIIP/Habi/W-27 | 636054026 | Imp. Of Mokkandi-Modhupur road.at ch. 00-500m. | 0.5 | 0 | 1570543 | 0 | 1570543 | 06.02.12 | M/S.Ruman Const. | 21.03.12 | 1492015 | 100% | 30.10-13 | 1492006 | 0 | Final
2 | SDRIIP/Habi/W-28 | 636054040 | Imp. Of Joypur Akra-Raghurampur-Izzatnagar road. At ch. 00-500m. | 0.5 | 0 | 1570543 | 0 | 1570543 | 06.02.12 | M/S.Chowdhury Ent. | 29.03.12 | 1492015 | 100% | 05.09.12 | 1492016 | 0 | Final
3 | SDRIIP/Habi/W-29 | 636054027 | Imp. Of Karimpur (Daripur Mosque)-Faizabad Hills road. At ch. 00-500m | 0.5 | 0 | 1570543 | 0 | 1570543 | 06.02.12 | Md.Shahidur Rahman | 21.03.12 | 1492015 | 100% | 28.08.12 | 1491965 | 0 | Final
4 | SDRIIP/Habi/W-30 | 636053008 | Imp. Of Bahubal UP office-Manikabazar via Goharua Primary school road. at ch. 2000-2500 | 0.5 | 0 | 2152829 | 0 | 2152829 | 06.02.12 | Nurujjaman Chwo. | 03.04.12 | 2045187 | 100% | 16.06.13 | 2045162 | 0 | Final
5 | SDRIIP/Habi/W-41 | 636053011 | Imp. Of Putijuri UP office-Mirzapur UP Office (Srimangal) road at ch. 1500-2500 m. | 1 | 0 | 3996190 | 0 | 3996190 | 21.03.12 | M/S. R.K Enterprise | 19.04.12 | 3796380 | 100% | 21.01.13 | 3737231 | 0 | Final
6 | SDRIIP/Habi/W-42 | 636053001 | A) Imp. Of Snanghat UP office-Raisgnj bazar road.& Brick toe wall at ch. 00-800 m. B) Const. Of 3x4.50x5.00m RCC box culvert on Snanghat UP office-Raisgnj bazar road. at ch.700m. | 0.8 | 13.5 | 3936190 | 1957888 | 5894078 | 21.03.12 | M/S.Ahmed Enterprise | 08.04.12 | 5737087 | 75% | 30.11.13 | 3400000 | 0 | Letter Issued
7 | SDRIIP/Habi/W-43 | 636054012 | Const. Of 1x3.00x3.00m RCC box culvert on Amrita Borchar road. at ch.3150m. | 0 | 3 | 0 | 572289 | 572289 | 21.03.12 | M/S.Haque Enterprise | 08.04.12 | 543674 | 100% | 19.08.12 | 0 | 543141 | Final
8 | SDRIIP/Habi/W-50 | 636054059 | Imp. Of Dhaka Sylhet R&H- Aliachara Kashia Punji road at Ch.00-1000m. | 1 | 0 | 3236219 | 0 | 3236219 | 28.05.12 | Md.Abdul Awal | 25.06.12 | 3074408 | 100% | 30.12.12 | 2569418 | 0 | Final
9 | SDRIIP/Habi/W-87 | 636053011 | Imp. Of Putijuri UP office-Mirzapur (Srimangal) Road at ch. 2440-3440 m. | 1 | 0 | 5142842 | 0 | 5142842 | 30.10.13 | Md.Shishu Miah | 18.11.13 | 4885699 | 100% | 23.06.14 | 4882990 | 0 | Final
10 | SDRIIP/Habi/W-92 | 636053010 | A) Imp. Of Bahubal UP Office-Razapur Bazar Road At Ch 2000-3000m.B) Const. of 2 Nos RCC Box Culvert on the Same Road.At ch. 2350,2500m. | 1 | 3.5 | 5933196 | 0 | 5933196 | 30.10.13 | M/S Chowdhury Enter. | 24.11.13 | 5636536 | 80% | 21.10.14 | 3647459 | 0 | Revised Est.Sent to H/Q
11 | SDRIIP/Habi/W-93 | 636054063 | A) Imp. Of Laskarpur Rail way- Mirpur (1400-2600m. B) Const. of 2 Nos U-Drain on the Same Road At Ch.1700-2000m. | 1.2 | 0 | 4699988 | 0 | 4699988 | 30.10.13 | Md.Kamal Ahmed | 21.11.13 | 4464988 | 100% | 26.06.14 | 4464301 | 0 | Final
12 | SDRIIP/Habi/W-107 | 636053001 | Imp. Of Snanghat UP Office-Raisgonj bazar Road By Earth work At Ch 1800-2900m. | 1.1 | 0 | 975364 | 0 | 975364 | 31.12.13 | M/S Jamal Ent. | 22.01.14 | 926595 | 100% | 28.05.14 | 926250 | 0 | Final
13 | SDRIIP/Habi/W-108 | 636053004 | Imp. Of Satkapon UP Office(Chalitatala) -Bakterpur via Shoaia bazar Road At Ch 8170-91700m. | 1 | 0 | 5227253 | 0 | 5227253 | 31.12.13 | Md. Kabir Ahmed | 23.01.14 | 4965890 | 100% | 24.01.15 | 4371032 | 0 | Final
14 | SDRIIP/Habi/W-109 | 636053008 | Imp. Of Bahubal UP Office-Manika bazar via Goharua Pry. School Road At Ch 2900-4400m. | 1.5 | 0 | 7920456 | 0 | 7920456 | 31.12.13 | M/S.Alam & Brothers | 20.01.14 | 7524432 | 100% | 23.10.14 | 5200000 | 0 | Final
15 | SDRIIP/Habi/W-110 | 636054009 | Imp. Of Boraiuri-Nandanpur bazar Road At Ch 500-1500m. | 1 | 0 | 3884188 | 0 | 3884188 | 31.12.13 | M/S.Razzak Enter. | 23.01.14 | 3689978 | 100% | 20.11.14 | 2113342 | 0 | Final
16 | SDRIIP/Habi/W-111 | 636054012 | A) Imp. Of Amrita-Barchar Road At Ch. 2200-3200m. B) Const. Of 1x3.00x3.00m RCC box culvert on Amrita Borchar road. at ch.3150m. | 1 | 3 | 3880903 | 299493 | 4180396 | 31.12.13 | M/S.Alam & Brothers | 20.01.14 | 3971376 | 95% | 16.11.14 | 2000000 | 0 | Work Final Revised Est.Sent to H/Q
17 | SDRIIP/Habi/W-112 | 636054027 | Imp. Of Karimpur-Faizabad Road At Ch 500-1500m. | 1 | 0 | 3787058 | 0 | 3787058 | 31.12.13 | M/S. Noman Ent. | 23.01.14 | 3597705 | 100% | 20.11.14 | 2000000 | 0 | Final
18 | SDRIIP/Habi/W-131 | 636054009 | Imp. Of Boraiuri-Nandanpur Bazar Road At Ch. 1500-2550m. | 1.05 | 0 | 4313177 | 0 | 4313177 | 08.09.14 | Md.Kamal Ahmed | 01.10.14 | 4097518 | 40% | 01.03.15 | 0 | 0 | work on going
19 | SDRIIP/Habi/W-132 | 636055058 | Imp. Of Shuaiya Bazar Ruail Road At Ch. 00-1000m. | 1 | 0 | 3850258 | 0 | 3850258 | 08.09.14 | Md.Shafiullah | 01.10.14 | 3657745 | 20% | 01.03.15 | 0 | 0 | work on going
20 | SDRIIP/Habi/W-152 | 636054067 | Const. Of 22m RCC Girder Bridge over Kalishiri Khal on Goshai Bazar-Fatepur Road At Ch. 3+910Km | 0 | 22 | 0 | 10673020 | 10673020 | 29.12.14 | M/S. M Alam | 01.02.15 | 10139369 | 5% | 01.02.16 | 0 | 0 | work on going
21 | SDRIIP/Habi/W-155 | 636053001 | Imp. Of Snanghat UP Office-Raisgonj bazar Road At Ch 1800-3200m. | 1 | 0 | 7120180 | 0 | 7120180 |  |  |  | 0 |  |  | 0 | 0 | e-GP. Tender Received Loterry Proc.
22 | SDRIIP/Habi/W-156 | 636053001 | Imp. Of Snanghat UP Office-Raisgonj bazar Road By Earth work At Ch 3265-5565m. | 1.3 | 0 | 1227305 | 0 | 1227305 |  |  |  | 0 |  |  | 0 | 0 | Do
23 | SDRIIP/Habi/W-157 | 636054081 | Imp. Of Biswa Road Bijlee Bridge to Helalpur- Modhupur Road At Ch 00-1000m. | 1 | 0 | 3908838 | 0 | 3908838 |  |  |  | 0 |  |  | 0 | 0 | Do
|  |  | Bahubal Upazila Sub Total = | 19.95 | 45 | 79904063 | 13502690 | 93406753 |  |  |  | 77230612 |  |  | 45833172 | 543141
Nabiganj
1 | SDRIIP/Habi/W-31 | 636773006 | Imp. Of Sakua bazaar-Sherpur-Halimpur road By BC at ch. 2230-3230 m | 1 | 0 | 4630446 | 0 | 4630446 | 06.02.12 | M/S. Eva Traders | 29.03.12 | 4516340 | 100% | 31.05.13 | 4516255 | 0 | Final
2 | SDRIIP/Habi/W-32 | 63674035 | Imp. Of Kayastagram-Debpara bazar road.By BC At ch. 00-1000 m | 1 | 0 | 3176782 | 0 | 3176782 | 06.02.12 | Ranjit kumar Roy | 29.03.12 | 3228245 | 100% | 30.10.13 | 3228231 | 0 | Final
3 | SDRIIP/Habi/W-33 | 63674072 | Imp. Of Kandigaon –Umedganj bazar-Satak road at ch. 1200-2200 m. | 1 | 0 | 3233118 | 0 | 3233118 | 06.02.12 | Md.Abdul Matin | 28.03.12 | 3071462 | 100% | 24.09.12 | 2756715 | 0 | Final
4 | SDRIIP/Habi/W-34 | 636774003 | Imp. Of Salamatpur-Nabiganj-Inathgonj road .By BC At ch. 00-1000 m. | 1 | 0 | 3329994 | 0 | 3329994 | 06.02.12 | Md.Mostafa Ali | 03.04.12 | 3163494 | 100% | 30.04.13 | 3160818 | 0 | Final
5 | SDRIIP/Habi/W-60 | 636774046 | Imp. Of Kazir Bazar-Choto Vakir road .By BC At ch. 00-790 m. | 0.79 | 0 | 3913442 | 0 | 3913442 | 07.11.12 | Md. Kabir Ahmed | 17.12.12 | 3717770 | 100% | 30.10.13 | 3717770 | 0 | Final
6 | SDRIIP/Habi/W-63 | 636774004 | Imp. Of Nabiganj-Habiganj-West Timirpur road .By BC At Ch. 00-1000 m. | 1 | 0 | 3880026 | 0 | 3880026 | 03.04.13 | Md.Abul Kashem Chow. | 21.04.13 | 3686025 | 100% | 25.10.13 | 3493094 | 0 | Final
7 | SDRIIP/Habi/W-64 | 636774059 | Imp. Of Tintalab- Enatabad road At Ch. 1000-2000 m. | 1 | 0 | 4026100 | 0 | 4026100 | 03.04.13 | Md. Imdadur Rahman Mukol | 23.04.13 | 3824795 | 45% | 28.05.15 | 300000 | 0 | work on going
8 | SDRIIP/Habi/W-74 | 636772011 | Imp. Of Sayedpur (Jalalpur)-Gurarai bazar road at Ch. 00-600 m. | 0.6 | 0 | 5206865 | 0 | 5206865 | 17.07.13 | Md. Imdadur Rahman Mukol | 14.08.13 | 4946521 | 100% | 17.05.14 | 4520191 | 0 | Final
9 | SDRIIP/Habi/W-75 | 636773005 | Imp. Of Bangla Bazar- Taherpur-Kailashgonj bazar road at Ch. 1590-2590 m. | 1 | 0 | 5897539 | 0 | 5897539 | 17.07.13 | Rabindra Kumar Paul | 14.08.13 | 5367061 | 100% | 17.05.14 | 5366020 | 0 | Final
10 | SDRIIP/Habi/W-76 | 636773001 | Const. of 42.00m Long RCC Grider Bridge over Shaka Borak river on Nabigonj-Shakua bazar road. At ch.2+600m | 0 | 42 | 0 | 12474365 | 12474365 | 17.07.13 | Md. Golam Faruk | 20.08.13 | 12695845 | 100% | 27.08.14 | 0 | 12658187 | Final
11 | SDRIIP/Habi/W-77 | 636774040 | Imp. Of Bausha Boyalia Bazar road At Ch. 00-700m. | 0.7 | 0 | 3820418 | 0 | 3820418 | 24.09.13 | M/S.Eva Ent. | 03.10.13 | 3629396 | 100% | 08.05.14 | 3503050 | 0 | Final
12 | SDRIIP/Habi/W-82 | 636774003 | Imp. Of Salamotpur Nabiganj-Inathgonj Road at Ch.1000-1610m. | 0.61 | 0 | 2857592 | 0 | 2857592 | 24.09.13 | Lokman Ahmed Khan | 03.10.13 | 2714711 | 100% | 08.04.14 | 2712304 | 0 | Final
13 | SDRIIP/Habi/W-83 | 636773003 | Improvement. Of Goplar Bazar Groth Center | 0 | 0 | 0 | 3488500 | 3488500 | 24.09.13 | M/S.S. Ahmed Traders | 03.10.13 | 3410155 | 100% | 20.06.14 | 0 | 3407781 | Final
14 | SDRIIP/Habi/W-102 | 636773002 | Imp. Of Sayedpur Inathgonj -Kamargoan Road By BC At Ch.428-503 & 753-1678m. | 1 | 0 | 5856617 | 0 | 5856617 | 31.12.13 | M/S.Samin Bricks | 22.01.14 | 5663786 | 100% | 25.10.14 | 5527761 | 0 | Final
15 | SDRIIP/Habi/W-103 | 636773006 | Imp. Of Sakua Bazar-Sherpur-Halimpur Road By BC At Ch.3230-4330m. | 1 | 0 | 6854645 | 0 | 6854645 | 31.12.13 | M/S.Hasan Ent. | 22.01.14 | 6511912 | 95% | 18.12.14 | 3781881 | 0 | Work Final Revised Est.Sent to H/Q
16 | SDRIIP/Habi/W-104 | 636773011 | Imp. Of Kurshi UP HQ-Enatabad-Nabiganj college Road By BC At Ch.00-704 & 2455-2751m. | 1 | 0 | 5458208 | 0 | 5458208 | 31.12.13 | Md.Mohibul Islam Shahin | 23.01.14 | 5185298 | 100% | 26.10.14 | 5182208 | 0 | Final
17 | SDRIIP/Habi/W-105 | 636774035 | Imp. Of Kayestagram-Debpara bazar Road By BC At Ch.1000-1960 m. | 0.96 | 0 | 3951535 | 0 | 3951535 | 31.12.13 | Md.Amjad Hossain | 16.01.14 | 3833522 | 100% | 20.08.14 | 2600000 | 0 | Final
18 | SDRIIP/Habi/W-106 | 636774054 | Imp. Of Nabiganj-Rudragram-Sha Taz uddin Kurashi Mazar Road By BC At Ch.00-1000m | 1 | 0 | 4833545 | 0 | 4833545 | 31.12.13 | Md.Kabir Ahmed | 23.01.14 | 4591866 | 100% | 20.11.14 | 4200000 | 0 | Final
19 | SDRIIP/Habi/W-115 | 636773012 | Imp. Of Madobpur- Hariragar Road At Ch.00-1000m. & 02 Nos Drain Culvert on the same Road At Ch. 80m, 1000m. | 1 | 0 | 4569911 | 0 | 4569911 | 19.02.14 | M/S Nion | 11.03.14 | 4341415 | 100% | 14.10.14 | 4339218 | 0 | Final
20 | SDRIIP/Habi/W-119 | 636775196 | A) Imp. Of Immambari -Borinow road to Khalilpur GPS Road At Ch. 00-1000m. B) Const. of 1x4.50x4.50m RCC box Culvert on the Same Road At Ch. 990m.C) Const. of 5 Nos 5x0.625mx0.600m U-Drainage Culvert on the Same Road At Ch.233m, 256m,274m,412m & 535m. | 1 | 4.5 | 4270996 | 1911410 | 6182406 | 19.03.14 | M/S Moklis Traders | 10.04.14 | 5873850 | 45% | 12.01.15 | 1300000 | 0 | work on going
21 | SDRIIP/Habi/W-122 | 636774018 | A) Imp. Of Nabiganj-Sherpur road- Mukimpur via Sha Sundar Mazar Road At Ch.1550-2600m. B) Const. of 2 Nos Drain Culvert on the Same Road At. Ch.2130m, & 2263m. | 1.5 | 0 | 4682080 | 0 | 4682080 | 08.05.14 | M/S.Kohinur Ent. | 25.05.14 | 4447976 | 50% | 25.02.15 | 1000000 | 0 | work on going
22 | SDRIIP/Habi/W-154 | 636772011 | A) Imp. Of Sayedpur- Gurarai Bazar Road By BC At Ch.600-1600m. | 1 | 0 | 6769718 | 0 | 6769718 | 29.12.14 | M/S. Ahmed Const. | 02.02.15 | 6431232 | 0% | 28.07.15 | 0 | 0 | W/O Issued
23 | SDRIIP/Habi/W-158 | 636775026 | Imp. Of Sayedpur Madrasha Omarpur Uttar Road By BC At Ch.00-1000 m & 03 Nos Drain Culvert on the Same Road At Ch.350m, 450m. | 1 | 0 | 3571635 | 0 | 3571635 |  |  |  | 0 |  |  | 0 | 0 | e-GP. Tender Received Loterry Proc.
24 | SDRIIP/Habi/W-163 | 636774059 | A) Imp. Of Tintalab-Enatabad Road At Ch.00-600m. B) Const. of 1x3.00x3.00 m RCC Box Culvert on the Same Road At. Ch.900m. | 0.6 | 3 | 2077986 | 710224 | 2788210 |  |  |  | 0 |  |  | 0 | 0 | Tender Call Processing
|  |  | Nabiganj Upazila Sub Total = | 20.76 | 49.5 | 96869198 | 18584499 | 115453697 |  |  |  | 104852677 |  |  | 65205516 | 16065968
|  |  | Habiganj-1 Total = | 40.71 | 94.5 | 176773261 | 32087189 | 208860450 |  |  |  | 182083289 |  |  | 111038688 | 16609109
Baniachong
1 | SDRIIP/Habi/W-16 | 636113012 | A) Imp. of Barauri UP Office-Kadupur bazar via Cilarai,Kalainjura bazar road at ch.3630-5630m.& Brick toe wall with Rcc post at ch. 4611m,4671m. B) Const. of 2 vent 3.50x3.50 m. Rcc box culvert on the Same road at ch. 5330m. | 2 | 7 | 8833887 | 1031211 | 9865098 | 17.01.12 | M/S.Rathindra Chandra Roy | 23.02.12 | 9371843 | 100% | 30.10.13 | 8403949 | 967280 | Final
2 | SDRIIP/Habi/W-35(1) | 636114013 | A) Imp.of Habigonj-Baniachong R&H to Sunaru village road at ch. 00-1000m.C) Const. of 2x 1.00x1.00m Box culvert on Habigonj-Baniachong R&H to Sunaru village road at ch. 550m & 670m. | 1 | 2 | 4408469 | 511236 | 4919705 | 03.04.13 | M/S. Bishal Construction | 23.04.13 | 5112133 | 100% | 26.01.14 | 4448794 | 485386 | Final
3 | SDRIIP/Habi/W-36 | 636115020 | Imp. Of Nandipara near Sarafatullah house Nandipara road at ch. 00-750m. & Brick toe wall RCC post ,3 Nos Cross Drain at ch. 85m, 280m & 510m. | 0.75 | 0 | 3860508 | 0 | 3860508 | 21.03.12 | Md.Abul Kashem Chow. | 05.04.12 | 3896563 | 100% | 12.05.13 | 3895553 | 0 | Final
4 | SDRIIP/Habi/W-37 | 636113014 | Imp. Of Ratna bazar-Muradpur UP office road via, Sunampur & Dulalpur road at ch. 00-120m. | 0.12 | 0 | 633713 | 0 | 633713 | 21.03.12 | Hassan Traders | 05.04.12 | 602027 | 100% | 11.10.12 | 453036 | 0 | Final
5 | SDRIIP/Habi/W-38 | 636114012 | Imp. Of Sheker Mohalla- Zingri river road at ch. 00-678.00 m.& Brick toe wall RCC post. | 0.67 | 0 | 4665096 | 0 | 4665096 | 21.03.12 | Ranjit Kumar Roy | 18.04.12 | 4431805 | 100% | 30.05.13 | 4337842 | 0 | Final
6 | SDRIIP/Habi/W-39 | 636115028 | Imp. Of Sharif khani infront of Golap ullah house Vangha road at ch. 00-800m. & Brick toe wall with RCC post. | 0.8 | 0 | 3307282 | 0 | 3307282 | 21.03.12 | M/S.Ahmed Contruction | 18.04.12 | 3141917 | 100% | 30.04.13 | 2849103 | 0 | Final
7 | SDRIIP/Habi/W-46 | 636113013 | Const. of 99.00m PSC Girder Bridge over Satai river on Subidpur UP office-Aowal Mohal bazar via kabirpur, Niamatpur road. At ch.0+800m | 0 | 99 | 0 | 35044350 | 35044350 | 25.09.12 | M.A Enterprise (JV) | 04.12.12 | 40239611 | 100% | 30.12.14 | 0 | 35883839 | Final
8 | SDRIIP/Habi/W-47 (LCS No.1 | 636112004 | Earth Filling work of Habigonj- Baniachong R&H (Khoire par)- Sujatpur road at ch.16325-16655m. | 0.33 | 0 | 476863 | 0 | 476863 |  | Mohammad Ali/ Shafiq Uddin | 18.12.12 | 476863 | 100% | 24.03.13 | 474483 | 0 | Final
9 | SDRIIP/Habi/W-48 LCS No:1 | 636113009 | Earth Filling work of Kagapasha bazar -Kagapasha UP office via Gokrapur road at ch.00-780 km. | 0.78 | 0 | 505394 | 0 | 505394 |  | Jogadish Das / Mifta Chow | 10.04.12 | 505394 | 100% | 15.06.12 | 492552 | 0 | Final
| SDRIIP/Habi/W-48 LCS No:2 | Do | Earth Filling work of Kagapasha bazar -Kagapasha UP office via Gokrapur road at ch.780-1680 km. | 0.9 | 0 | 522241 | 0 | 522241 |  | Ranjit Roy/ Nurujjaman Chow. | 10.04.12 | 522241 | 100% | 15.06.14 | 519738 | 0 | Do
| SDRIIP/Habi/W-48 LCS No:3 | Do | Earth Filling work of Kagapasha bazar -Kagapasha UP office via Gokrapur road at ch.1680-2340 Km. | 0.66 | 0 | 484036 | 0 | 484036 |  | Nazmul Chow/ Bibakanada Das | 10.04.12 | 484036 | 100% | 15.06.12 | 449650 | 0 | Do
| SDRIIP/Habi/W-48 LCS No:4 | Do | Earth Filling work of Kagapasha bazar -Kagapasha UP office via Gokrapur road at ch.2340-2880 km. | 0.54 | 0 | 488867 | 0 | 488867 |  | Anayet jaman/ Rohul Amin Chow | 10.04.12 | 488867 | 100% | 15.06.12 | 476146 | 0 | Do
| SDRIIP/Habi/W-48 LCS No:5 | Do | Earth Filling work of Kagapasha bazar -Kagapasha UP office via Gokrapur road at ch.2880-3320m. | 0.44 | 0 | 405798 | 0 | 405798 |  | Ahmed Hasan Chow / Anas Ali | 10.04.12 | 405798 | 100% | 15.06.12 | 363808 | 0 | Do
10 | SDRIIP/Habi/W-62 |  | Imp. Of Baro Bazar Internal road at Ch 00-336m & Multipurpose Shed. | 0.336 | 0 | 2755650 | 942959 | 3698609 | 13.03.13 | M/S.Shahin Traders | 31.03.13 | 3513698 | 100% | 04.10.13 | 3507030 | 0 | Final
11 | SDRIIP/Habi/W-65 LCS-01 | 636112007 | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 00-840m | 0.84 | 0 | 616045 | 0 | 616045 |  | Pankog kumar Das | 14.03.13 | 615045 | 100% | 15.06.13 | 612354 | 0 | Final
| LCS-02 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 840-1680m | 0.084 | 0 | 574165 | 0 | 574165 |  | Sunil Chandra Das | 14.03.13 | 574165 | 100% | 15.06.13 | 572391 | 0 | Do
| LCS-03 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 1680-2400m | 0.72 | 0 | 613390 | 0 | 613390 |  | Nipandra Chow. | 14.03.13 | 613390 | 100% | 15.06.13 | 610853 | 0 | Do
| LCS-04 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 2400-3210m | 0.81 | 0 | 634688 | 0 | 634688 |  | Joy Hori Boisnib | 14.03.13 | 634688 | 100% | 15.06.13 | 630930 | 0 | Do
| LCS-05 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 3210-3570m | 0.36 | 0 | 557727 | 0 | 557727 |  | Joy Kumar Boisnib | 14.03.13 | 557727 | 100% | 15.06.13 | 554731 | 0 | Do
| LCS-06 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 3570-4020m | 0.45 | 0 | 565827 | 0 | 565827 |  | Ramendra Boisnib | 14.03.13 | 565827 | 100% | 15.06.13 | 562839 | 0 | Do
| LCS-07 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 4020-4650m | 0.63 | 0 | 574015 | 0 | 574015 |  | Madai Boisnib | 14.03.13 | 574015 | 100% | 15.06.13 | 571913 | 0 | Do
| LCS-08 | Do | Earth Filling work of Kadirgonj GC- Paharpur GC via Karcha road at Ch. 4650-5100m | 0.45 | 0 | 564663 | 0 | 564663 |  | Rathindra Boisnub | 14.03.13 | 564663 | 100% | 15.06.13 | 562297 | 0 | Do
12 | SDRIIP/Habi/W-78 | 636114033 & 636113003 | Part-1) (A) Imp. Of Janab Ali Degree College-Habiganj RHD via paragaon road At Ch. 00-600m.(B) Const.of 1vent 3.00x3.00m RCC Box Culvert on the same road At Ch. 420m. Part-2) Imp. Of Khagaura UP office-Uzirpur Bazar Road At Ch.4010-4330m. | 0.92 | 3 | 4709674 | 1079912 | 5789586 | 24.09.13 | M/S Kohinur Ent. | 03.10.13 | 5462169 | 100% | 22.11.14 | 4458679 | 1025897 | Final
13 | SDRIIP/Habi/W-116 | 636112007 | (A) Imp. Of Kadirgonj GC- Paharpur GC via Karcha Road At Ch. 00-1300m. (B) Const.of 03 Nos Drain Culvert 1x1.00x1.00m on Kadir gonj GC- Paharpur GC via Karcha Road At Ch. 375,680&1150m. | 1.3 | 3 | 7131992 | 546658 | 7678650 | 19.02.14 | M/S.Sheikh Ent. | 12.03.04 | 7294718 | 35% | 07.02.15 | 200000 | 0 | work on going
14 | SDRIIP/Habi/W-117 | 636113012 | A) Imp. Of Barauri UP Office-Kadupur bazar via Cilarai,Kalainjura bazar Road At Ch 5630-7096m B) Const. of 03x4.50x4.50m RCC Box Culvert on Barauri UP Office-Kadupur bazar via Cilarai, Kalainjura bazar Road At Ch. 6093m. C) Const. of 01x3.00x3.00m RCC Box Culvert on Barauri UP Office-Kadupur bazar via Cilarai, Kalainjura bazar Road At Ch. 6422m. | 1.466 | 13.5 | 7987777 | 2790075 | 10777852 | 19.02.14 | Md.Shafiullah | 11.03.14 | 10238959 | 40% | 18.03.15 | 0 | 0 | work on going
15 | SDRIIP/Habi/W-149 | 636113013 | Imp. Subidpur UP office- Aowal mohal bazar via Kabirpur, Niamatpur Road At Ch. 1000-2000m. | 1 | 0 | 5179340 | 0 | 5179340 | 20.11.14 | Md. Sheer Ali | 21.12.14 | 4920373 | 0% | 25.06.15 | 0 | 0 | W/O Issued
16 | SDRIIP/Habi/W-150 | 636113015 | Imp. Of Awal mohal bazar- Pukra UP office Road At Ch. 2631-3131m. | 0.5 | 0 | 3367318 | 0 | 3367318 | 20.11.14 | Md. Golam Faruk | 30.12.14 | 3198952 | 20% | 05.07.15 | 0 | 0 | work on going
17 | SDRIIP/Habi/W-151 | 636113004 | A) Imp. Of Subidpur UP Office- Baliakhal (Nagura)- Road At Ch. 325-1325m. B) Const. of 1x2.00 xx 2.00m RCC Box Culvert on the Same Road At Ch. 665m. | 1 | 2 | 5791914 | 827910 | 6619824 | 20.11.14 | M/S. Khohinor Ent. | 28.12.14 | 6288832 | 25% | 05.07.15 | 0 | 0 | work on going
|  |  | Baniachong Upazila Sub Total = | 19.856 | 129.5 | 70216339 | 42774311 | 112990650 |  |  |  | 115296319 |  |  | 40008671 | 38362402
Azmirigonj
1 | SDRIIP/Habi/W-52 | 636023001 | Imp. Of Poschimbagh- Azmiriganj road at Ch. 1200-2200m. | 1 | 0 | 4334000 | 0 | 4334000 | 28.05.12 | M/S. Mortuza Hasan | 29.07.12 | 4876933 | 100% | 30.11.13 | 4263175 | 0 | Final
2 | SDRIIP/Habi/W-53 | 636025042 | Imp. Of Madhobpasa- Sluice gate via Nayahati road at Ch. 00-1200m. | 1.2 | 0 | 4358448 | 0 | 4358448 | 28.05.12 | M/S. Mortuza Hasan | 29.07.12 | 4573462 | 100% | 31.01.13 | 3879988 | 0 | Final
3 | SDRIIP/Habi/W-86 | 636022002 | Imp. Of Azmiriganj-Kakailsew Road By RCC At Ch. 6500-7320m. | 0.82 | 0 | 8748622 | 0 | 8748622 | 30.10.13 | Shamayun Kabir Chow. | 25.11.13 | 8311190 | 70% | 29.08.14 | 5366746 | 0 | work on going
4 | SDRIIP/Habi/W-88 | 636025024 | Imp. Of Nikli-Boldi Road By RCC At Ch.00-1000m. | 1 | 0 | 5093400 | 0 | 5093400 | 30.10.13 | M/S.Samin Bricks | 25.11.13 | 4838730 | 90% | 30.06.14 | 4400000 | 0 | Revised Est. under Processing
5 | SDRIIP/Habi/W-129 | 636022002 | Imp. Of Road From Azmiriganj -Kakailsew Road at Ch. 1000-2000m. | 1 | 0 | 7050114 | 0 | 7050114 | 21.07.14 | Md.Al-Amin | 06.08.14 | 6697607 | 100% | 09.05.15 | 1000000 | 0 | Final
6 | SDRIIP/Habi/W-130 | 636022004 | Imp. Of Road By RCC From Paharpur-Kadirgong Road at Ch. 1000-2000m. | 1 | 0 | 7579081 | 0 | 7579081 | 21.07.14 | Md.Mohibul Islam Shahin | 06.08.14 | 7200127 | 85% | 09.05.15 | 1200000 | 0 | work on going
7 | SDRIIP/Habi/W-138 | 636022002 | Imp. Of Road From Azmiriganj -Kakailsew Road at Ch. 2000-2720m. | 0.72 | 0 | 4858256 | 0 | 4858256 | 28.09.14 | M/S.Mortrza Hasan | 13.10.14 | 4615343 | 20% | 30.06.15 | 0 | 0 | work on going
8 | SDRIIP/Habi/W-147 | 636022004 | Imp. Of Road By RCC from Paharpur GC- Kadirganj GC Road At Ch.2000-2450m. | 0.45 | 0 | 3269880 | 0 | 3269880 | 20.11.14 | Md.Shafiullah | 21.12.14 | 3106386 | 70% | 25.06.15 | 400000 | 0 | work on going
9 | SDRIIP/Habi/W-148 | 636025024 | Imp. Of Nikli-Boldi Road By RCC At Ch.1000-1250m. | 0.25 | 0 | 1231531 | 0 | 1231531 | 20.11.14 | M/S Momun Traders | 28.12.14 | 1169954 | 0% | 02.07.15 | 0 | 0 | W/O Issued
10 | SDRIIP/Habi/W-164 | 636023001 | Imp. Of Poschimbagh- Azmiriganj road at Ch.2200-2660m. | 0.46 | 0 | 3479685 | 0 | 3479685 |  |  |  | 0 |  |  | 0 | 0 | Tender Call Processing
|  |  | Azmirigonj Upazila Sub Total = | 7.9 | 0 | 50003017 | 0 | 50003017 |  |  |  | 45389732 |  |  | 20509909 | 0
|  |  | Habiganj-2 Total = | 27.756 | 129.5 | 120219356 | 42774311 | 162993667 |  |  |  | 160686051 |  |  | 60518580 | 38362402
Sadar
1 | SDRIIP/Habi/W-17 | 636444023 | Const. of 1x2.50x2.50m RCC box culvert on Bhadi village road at ch.10m. | 0 | 2.5 | 0 | 440500 | 440500 | 06.03.12 | Md.Abdul Matin | 06.03.12 | 418475 | 100% | 03.06.12 | 0 | 392542 | Final
2 | SDRIIP/Habi/W-18 | 636443004 | Imp. Of Nizampur UP(Surkipara)-Shaistaganj GC road at ch.00-1100m | 1.1 | 0 | 4663791 | 0 | 4663791 | 06.03.12 | Mahibul Islam Shahin | 12.04.12 | 4430601 | 100% | 30.12.12 | 4430385 | 0 | Final
3 | SDRIIP/Habi/W-19 | 636442008 | Imp of Lakhal R&H to Rajiura via Hurgaon road by Earth work at ch.00-3000m | 3 | 0 | 4973362 | 0 | 4973362 | 06.03.12 | Md.Taj Uddin | 22.03.12 | 4971769 | 100% | 30.01.13 | 4967312 | 0 | Final
4 | SDRIIP/Habi/W-20 | 636443009 | Imp.of Gopaiya UP-Dhuliakhal (DR)-Gopalgonj bazar via Alapur road at ch.3720-4800m | 1.8 | 0 | 5420391 | 0 | 5420391 | 06.03.12 | Md.Kamal Ahmed | 22.03.12 | 5148386 | 100% | 29.12.12 | 4171796 | 0 | Final
5 | SDRIIP/Habi/W-21 | 636444041 | Imp.of Surabai- Lalchand road by BC from ch.2250-3500m. | 1.25 | 0 | 3912269 | 0 | 3912269 | 06.03.12 | Md.Sher Ali | 18.03.12 | 3901790 | 100% | 25.12.12 | 3901748 | 0 | Final
6 | SDRIIP/Habi/W-22 | 636444016 | Imp of Ratanpur R&H -Batshar road at ch.00-1225m | 1.225 | 0 | 4701681 | 0 | 4701681 | 06.03.12 | M/S.Ikra Enterprise | 29.03.12 | 4466596 | 100% | 30.05.13 | 4156148 | 0 | Final
7 | SDRIIP/Habi/W-23 | 636444046 | Imp.of Gopaiya-Pikpara road at ch.800-1115m | 0.315 | 0 | 1056041 | 0 | 1056041 | 06.03.12 | M/S.Ahmed Contruction | 21.03.12 | 1003238 | 100% | 10.02.13 | 1002697 | 0 | Final
8 | SDRIIP/Habi/W-24 | 636443007 | Imp. Of Nurpur (NHW)-Shutang GC-Aminpur road at ch.2312-3212m. | 0.9 | 0 | 3936895 | 0 | 3936895 | 06.03.12 | Md.Akter Hossain | 21.03.12 | 3956824 | 100% | 28.02.13 | 3944571 | 0 | Final
9 | SDRIIP/Habi/W-26 | 636445010 | Construction of 85.00 M Long RCC Girder Bridge over Branch of Borak river at Aliganj Bazar on Abdullahpur-Sayadabad road at ch. 0+100m. | 0 | 85 | 0 | 14421257 | 14421257 | 06.03.12 | M/S. Bismillah Traders | 22.04.12 | 15142000 | 70% | 31.01.14 | 0 | 9867782 | work on going
10 | SDRIIP/Habi/W-44 | 636444003 | Imp. Of Lakhai R&H-Motalib Miah's house- Goalnagar- Kashipur road by Earth work at ch. 00-3800m. | 3.8 | 0 | 2473418 | 0 | 2473418 | 18.04.12 | M/S Hasan Traders | 02.05.12 | 2350300 | 100% | 05.11.12 | 1791686 | 0 | Final
11 | SDRIIP/Habi/W-54 | 636444007 | A) Imp. Police Line-BSCIC road via Tetoiya road by BC at Ch. 780-1510m. B) Imp. Of Gopaya UP- Duliakhal (DR)- Gopalganj bazar via Alapur road by BC at Ch. 00-147m. | 0.877 | 0 | 3190818 | 0 | 3190818 | 28.05.12 | M/S. Razzak Enterprise | 24.06.12 | 3031277 | 100% | 28.12.12 | 2998780 | 0 | Final
12 | SDRIIP/Habi/W-55 | 636444026 | Imp. Of Sharifabad -Aminpur Sluice gate (RD)-Nizampur road at Ch. 475-517m & 650-1650m. | 1.42 | 0 | 3343750 | 0 | 3343750 | 28.05.12 | M/S. M. Jaman Const | 17.06.12 | 3176562 | 100% | 18.06.13 | 3176562 | 0 | Final
13 | SDRIIP/Habi/W-66 | 636443007 | A) Imp. Of Nurpur (NHW)- Shutang GC (Talia Khal) road by Bituminous Carpeting at ch. 7800-8800m. & Brick Toe wall with RCC post. | 1 | 0 | 5550750 | 0 | 5550750 | 03.04.13 | Md.Rahmat Ali | 23.04.13 | 5273168 | 100% | 26.01.14 | 5272844 | 0 | Final
14 | SDRIIP/Habi/W-67 | 636443011 | A) Imp. Of Lakhai R&H-Rajiura UP-Uchail Bazar road by Bituminous Carpeting at ch. 1450-2450m.B) Const. of 1vent 1.50x1.50m RCC Box Culvert on the Same road at Ch.1822 | 1 | 1.5 | 5289852 | 379115 | 5668967 | 03.04.13 | M/S.Mortrza Hasan | 23.04.13 | 5385519 | 50% | 26.01.14 | 1150000 | 0 | work on going
15 | SDRIIP/Habi/W-69 LCSNo:01 | 636445009 | Imp. Of Chargoan-Shikarpur-Kushamkhali (Abdullahpur) road By Earty filling work at Ch. 100- 400m. | 0.3 | 0 | 452574 | 0 | 452574 |  | Shakawat Hossain/ Abul Basar | 23.12.13 | 452574 | 100% | 30.04.14 | 316883 | 0 | Final
| LCS No:02 | Do | Imp. Of Chargoan-Shikarpur-Kushamkhali (Abdullahpur) road By Earty filling work at Ch. 400- 700m. | 0.3 | 0 | 455200 | 0 | 455200 |  | Manik Miah/ Ahad Miah | 23.12.13 | 455200 | 100% | 30.04.14 | 374484 | 0 | Do
| LCS No:03 | Do | Imp. Of Chargoan-Shikarpur-Kushamkhali (Abdullahpur) road By Earty filling work at Ch. 700- 1000m. | 0.3 | 0 | 480349 | 0 | 480349 |  | Nazrul Islam/ Amin Miah | 23.12.13 | 480349 | 100% | 30.04.14 | 387657 | 0 | Do
| LCS No:04 | Do | Imp. Of Chargoan-Shikarpur-Kushamkhali (Abdullahpur) road By Earty filling work at Ch. 1000- 1287m. | 0.287 | 0 | 465889 | 0 | 465889 |  | Abu Shaleha/ Mohibur Rahaman | 23.12.13 | 465889 | 100% | 30.04.14 | 111933 | 0 | Do
| LCS No:05 | Do | Imp. Of Chargoan-Shikarpur-Kushamkhali (Abdullahpur) road By Earty filling work at Ch. 1287- 2100m. | 0.813 | 0 | 421483 | 0 | 421483 |  | Abdul Hannan/ Abdul Shalek | 23.12.13 | 421483 | 100% | 30.04.14 | 332195 | 0 | Do
| LCS No:06 | Do | Imp. Of Chargoan-Shikarpur-Kushamkhali (Abdullahpur) road By Earty filling work at Ch. 2100-3050m. | 0.95 | 0 | 440788 | 0 | 440788 |  | Md.Taiad/ Koram Ali | 23.12.13 | 440788 | 100% | 30.04.14 | 334144 | 0 | Do
16 | SDRIIP/Habi/W-72 | 636443002 | Imp. Of Jagatpur (DR)-Nizampur UP Road at Ch. 1382-2106m. & 4Nos U-Drain Culvert on the Same Road at Ch. 1467,1529,1638 & 2067m. | 0.724 | 0 | 4158257 | 0 | 4158257 | 16.09.13 | M/S.M.A Ahad | 25.11.13 | 3950359 | 100% | 11.09.14 | 3039758 | 0 | Final
17 | SDRIIP/Habi/W-80 | 636444008 | A) Imp. Of Rampur-Gobindopur Road at Ch. 976-1426m. B) Const. of 1Vent1x2.50x2.50M RCC Box Culvert on the Same Road.at Ch.1043m. C) Const of 1Nos U-Drain on the Same Road at Ch. 1333M. | 0.45 | 2.5 | 2204636 | 640728 | 2845364 | 24.09.13 | M/S.M Jaman | 03.10.13 | 2703093 | 100% | 08.04.14 | 2052454 | 525402 | Final
18 | SDRIIP/Habi/W-81 | 636445050 | A) Imp. Of Dariapur-Sujatpur GPS (Nitai Chaik) Road at Ch. 00-1350m. B) Const. of 1Vent1x2.50x2.50M RCC Box Culvert on the Same Road.at Ch.890m. | 1.35 | 2.5 | 4201125 | 548560 | 4749685 | 24.09.13 | Md.Sha. Alam | 10.10.13 | 4512200 | 70% | 14.07.14 | 1976149 | 0 | work on going
19 | SDRIIP/Habi/W-94 | 636444012 | Imp. Of Jatra Barobari - Aminpur (Talikhal) Road at Ch.1260-2274. | 1.14 | 0 | 4295959 | 0 | 4295959 | 30.10.13 | Md.Sultan Mahmud | 28.11.13 | 4081161 | 100% | 16.06.14 | 3723562 | 0 | work Final Revised Sent to H/Q
20 | SDRIIP/Habi/W-95 | 636445002 | Imp. Of Nishapat-Kargahati Road at Ch. 00-1000m. | 1 | 0 | 4518145 | 0 | 4518145 | 30.10.13 | Md.Sultan Mahmud | 28.11.13 | 4292238 | 100% | 16.06.14 | 4271106 | 0 | Final
21 | SDRIIP/Habi/W-97 | 636442008 | A) Imp. Of Lakhai R&H- Rajiura via Hurgaon Road at Ch. 00-1000m.B) Const. of 1 vent 3.50x3.50m RCC Box culvert on the Same Road At Ch. 527m. | 1 | 3.5 | 5961247 | 774338 | 6735585 | 31.12.13 | M/S.Jamal Enterprise | 22.01.14 | 6398805 | 100% | 19.12.14 | 4804640 | 732824 | Final
22 | SDRIIP/Habi/W-98 | 636443003 | Imp. Of Anwarpur (DR)- Richi UP-Gopalgonj Bazar Road at Ch. 7950-8120m. | 0.17 | 0 | 902545 | 0 | 902545 | 31.12.13 | M/S.Misba Uddin | 16.01.14 | 857417 | 100% | 22.05.14 | 856755 | 0 | Final
23 | SDRIIP/Habi/W-99 | 636443007 | Imp. Of Nurpur (NHW)-Shutang GC-Aminpur Road At Ch 6030-7050 m. | 1.2 | 0 | 5533832 | 0 | 5533832 | 31.12.13 | M/S. M. Jaman Construction | 22.01.14 | 5257140 | 100% | 25.10.14 | 4706732 | 0 | Final
24 | SDRIIP/Habi/W-114 |  | Improvement. Of Kotiadi Bazar | 0 | 0 | 0 | 3432528 | 3432528 | 23.01.14 | M/S Mokul Const. | 16.02.14 | 3260901 | 85% | 20.11.14 | 0 | 1800000 | work on going
25 | SDRIIP/Habi/W-118 | 636444006 | A) Imp. Of Dariapur -Etbarpur Road By BC At Ch. 1000-2150.00 & Brick Toe wall RCC post At Ch. 460-500 m, (01) Nos U- Drain At Ch.1110 m, (03) Nos RCC Box Culvert on the Same Road At Ch. 500,1585 & 1666m. | 1.15 | 3 | 4510454 | 1454357 | 5964811 | 19.02.14 | M/S.Islam Trading Co. | 10.03.14 | 5666570 | 90% | 12.12.14 | 1800000 | 0 | BC on going
26 | SDRIIP/Habi/W-124 | 636445031 | Imp. Of Ladia Road to Janiganj via Kazirgaon Community Clinic Road At Ch.00-900m | 0.9 | 0 | 3755500 | 0 | 3755500 | 18.06.14 | M/S.Nishat Ent. | 15.07.14 | 3567724 | 100% | 16.02.15 | 2020917 | 0 | Final
27 | SDRIIP/Habi/W-141 | 636443011 | A) Imp. Of Lakhai R&H-Rajiura UP-Uchail Bazar road by Bituminous Carpeting At Ch. 2450-2851m. B) Const. of 1Nos 1.50x1.50m RCC Box Culvert on the Same road At Ch.2808 | 0.401 | 1.5 | 2355158 | 0 | 2355158 | 20.11.14 | M/S. M. Jaman | 24.12.14 | 2237400 | 0% | 30.06.15 | 0 | 0 | W/O Issued
28 | SDRIIP/Habi/W-142 | 636445027 | Imp. Of Paikpara Rail Gate to Sayedpur High School Road by BC At Ch. 1678-2678m. | 1 | 0 | 4195097 | 0 | 4195097 | 20.11.14 | M/S.Simu Akter | 21.12.14 | 3985342 | 15% | 25.06.15 | 0 | 0 | work on going
29 | SDRIIP/Habi/W-143 | 636444012 | Imp. Of Jatraborobari- Aminpur Road By BC At Ch. 00-1000m | 1 | 0 | 4164392 | 0 | 4164392 | 20.11.14 | Sayed Rukunuzzaman | 23.12.14 | 3956172 | 0% | 28.06.15 | 0 | 0 | W/O Issued
30 | SDRIIP/Habi/W-144 | 636445022 | A) Imp. Of Mojahar High School to Sail jura Road By BC At Ch. 1000-2000m B) Const of 1 Nos 1x2.00x2.00m RCC Box Culvert on the Same Road At Ch. 1724m | 1 | 2 | 3769670 | 569762 | 4339432 | 20.11.14 | Md. Kamal Ahmed | 23.12.14 | 4122460 | 0% | 28.06.15 | 0 | 0 | W/O Issued
31 | SDRIIP/Habi/W-145 | 636445007 | Imp. Of Shahjibazar-Sadurbazar road to Pachim Noagaon Pry. School Road At Ch. 2000-2530m. | 0.53 | 0 | 2587077 | 0 | 2587077 | 20.11.14 | Md. Kazal Miah | 22.12.14 | 2457723 | 15% | 25.06.15 | 0 | 0 | work on going
32 | SDRIIP/Habi/W-146 | 636444026 | A) Imp. Of Sharifabad- Aminpur Road By BC At Ch. 1508-2258m. B) Const. of 2 x4.50x5.00m RCC Box Culvert on the Same Road At Ch. 1853m. | 0.75 | 4.5 | 3098035 | 2024455 | 5122490 | 29.12.14 | M/S.Niyaz uddin Harun | 02.02.15 | 4866365 | 0% | 28.07.15 | 0 | 0 | W/O Issued
|  |  | Sadar Upazila Sub Total = | 34.402 | 108.5 | 111440430 | 24685600 | 136126030 |  |  |  | 131545858 |  |  | 72073898 | 13318550
Lakhai
1 | SDRIIP/Habi/W-25 | 636683001 | Imp. Of Bulla UP office-Mouiuak Fandauk road via Shinghagram road at ch. 2100-3100m | 1 | 0 | 4023835 | 0 | 4023835 | 06.02.12 | Md. Mostafa Ali | 03.04.12 | 3822643 | 100% | 15.06.13 | 3793042 | 0 | Final
2 | SDRIIP/Habi/W-49 | 636683004 | A) Imp. Of Murakari UP office-Zirunda bazar upto RHD road near Bamoi UP office road at ch.6316-7000m.B) Cost. Of 2 Nos 1.00x1.00m RCC box culvert on the same road at ch. 6230 & 6400m. | 0.684 | 2 | 3609650 | 390349 | 3999999 | 18.04.12 | M/S. H.S Enterprise | 17.05.12 | 3799998 | 100% | 20.04.14 | 2460450 | 370832 | Final
3 | SDRIIP/Habi/W-56 | 636682003 | Imp. Of Bulla Bazar-Barponni to Sozatpur BY RCC at Ch. 6330-7200m. | 0.87 | 0 | 3999728 | 0 | 3999728 | 28.05.12 | M/S. Arif Const. | 18.06.12 | 3799741 | 100% | 30.07.13 | 3717663 | 0 | Final
4 | SDRIIP/Habi/W-68 (LCS No-1 | 636685020 | Imp. Of Badikara Fandauk road- Naklauk road By Earty filling work at Ch. 00-1000m | 1 | 0 | 379310 | 0 | 379310 | 25.04.13 | Asadul Haque / Kamrul Hasan | 10.06.13 | 379310 | 100% | 29.09.13 | 378620 | 0 | Final
| SDRIIP/Habi/W-68 (LCS-2) | Do | Imp. Of Badikara Fandauk road- Naklauk road By Earty filling work at Ch. 1000-1400m | 0.4 | 0 | 382758 | 0 | 382758 | 25.04.13 | Muluk Hossain / Moznu | 10.06.13 | 382758 | 100% | 29.09.13 | 382344 | 0 | Do
5 | SDRIIP/Habi/W-84 |  | Const. of Womens Corner Market at Bulla Bazar . | 0 | 0 | 0 | 1950000 | 1950000 | 24.09.13 | M/S.Islam Trading Co. | 03.10.13 | 2009170 | 100% | 30.12.14 | 0 | 1250000 | Final
6 | SDRIIP/Habi/W-96 | 636682002 | Construction of 60.00 M Long RCC Girder Bridge over Balakandi khal on Lukra-Madna Bazar Road at Ch. 7+000km. |  | 60 | 0 | 19995000 | 19995000 | 09.12.13 | Md. Golam Faruk | 30.12.13 | 18995250 | 65% | 05.01.15 | 0 | 7000000 | work on going
7 | SDRIIP/Habi/W-100 | 636683004 | Imp. Of Murakari UP office-Zirunda bazar upto RHD road near Bamoi UP office road At Ch.5316-6316 m. | 1 | 0 | 5860577 | 0 | 5860577 | 31.12.13 | M/S.Ranju Roy | 22.01.14 | 5567547 | 100% | 25.10.14 | 4173673 | 0 | Final
8 | SDRIIP/Habi/W-101 | 636684003 | A) Imp. Of Maintail DC Road-Harinakona Road By BC. At Ch.840-1840 m.B) Const. of 1x3.00x3.00m RCC Box culvert on the Same Road. At Ch. 950m. | 1 | 3 | 4731613 | 699074 | 5430687 | 31.12.13 | M/S. R.I Monju | 23.01.14 | 5159153 | 100% | 26.01.14 | 3235172 | 0 | Final
9 | SDRIIP/Habi/W-121 | 636688003 | Improvement of Madna Bazar Growth Center | 0 | 0 | 0 | 3749639 | 3749639 | 08.05.14 | M/S.Sultan Mahmud | 25.05.14 | 3562157 | 75% | 27.12.14 | 0 | 1050000 | work on going
10 | SDRIIP/Habi/W-159 | 636683004 | Imp. Of Murakari UP office-Zirunda bazar upto RHD road near Bamoi UP office Road By BC At Ch.3750-4816m. | 1.06 | 0 | 8763877 | 0 | 8763877 |  |  |  | 0 |  |  | 0 | 0 | e-GP. Tender Received Loterry Proc.
11 | SDRIIP/Habi/W-160 | 636685033 | Imp. Of Kaliadhara R&H- Tagoria Kalauk Road By BC At Ch.1500-2930m. | 1.43 | 0 | 5685885 | 0 | 5685885 |  |  |  | 0 |  |  | 0 | 0 | Do
12 | SDRIIP/Habi/W-161 | 636684002 | Imp. Of Rarishal - Balashri river Road By BC At Ch.800-1800m. | 1 | 0 | 4212952 | 0 | 4212952 |  |  |  | 0 |  |  | 0 | 0 | Do
|  |  | Lakhai Upazila Sub Total = | 9.444 | 65 | 41650185 | 26784062 | 68434247 |  |  |  | 47477727 |  |  | 18140964 | 9670832
|  |  | Habiganj-3 Total = | 43.846 | 173.5 | 153090615 | 51469662 | 204560277 |  |  |  | 179023585 |  |  | 90214862 | 22989382
Madhabpur
1 | SDRIIP/Habi/W-01 | 636712006 | Imp. of Changer bazar- Chowmuhani road at ch.00-1000m. | 1 | 0 | 4266811 | 0 | 4266811 | 17.1.12 | Md.Akter Hossain | 22.02.12 | 4053470 | 100% | 08.11.12 | 3978693 | 0 | Final
2 | SDRIIP/Habi/W-02 | 636713001 | Imp. of Noypara bazar-Kharki-Bulla bazar road at ch.3850-4505m. | 0.655 | 0 | 3673983 | 0 | 3673983 | 17.1.12 | Md.Mostafa Ali | 22.03.12 | 2329808 | 100% | 05.12.12 | 1814753 | 0 | Final
3 | SDRIIP/Habi/W-03 | 636713008 | A) Imp. of Bahara UP office-Akhara bazar road at ch.1250-2000m. B) Protection work of Bahara UP office-Akhara bazar road at ch.1300-1312m. | 0.75 | 0 | 2767934 | 0 | 2767934 | 17.1.12 | M/S Al-Mina Internation | 29.02.12 | 2629536 | 100% | 15.04.14 | 2591004 | 0 | Final
4 | SDRIIP/Habi/W-04 | 636714038 | Imp.of Bakshair R&H-Durgapur road at ch.1000-2000m. | 1 | 0 | 3142610 | 0 | 3142610 | 17.1.12 | M/S.Chowdh. Enter. | 29.03.12 | 2985479 | 100% | 30.06.13 | 2943670 | 0 | Final
5 | SDRIIP/Habi/W-05 | 636714042 | A) Imp. of Jogodispur-Temunia-Uttar Bajura road at ch.2450-2950m. B) Protection work of Jogodispur-Temunia-Uttar Bajura road at ch.2550-2580m,2585-2625m & 2750-2790m. | 0.5 | 0 | 1122508 | 0 | 1122508 | 17.1.12 | M/S Chowdhury Enter. | 29.02.12 | 1122508 | 100% | 06.12.12 | 1122508 | 0 | Terminated
| SDRIIP/Habi/W-05(1) | 636714042 | Imp. of Jogodispur-Temunia-Uttar Bajura road at ch.2450-2963m. | 0.513 | 0 | 1417526 | 0 | 1417526 | 17.07.13 | M/S.Jamal Enterprise | 19.08.13 | 1346649 | 100% | 22.02.14 | 1346649 | 0 | Final
6 | SDRIIP/Habi/W-06 | 636714098 | Imp. of Etakhola Rail Station-Baikuntha- pur road at ch.00-900 m. | 0.9 | 0 | 2828349 | 0 | 2828349 | 17.1.12 | Md.Abdul Awal | 29.02.12 | 2686931 | 100% | 10.11.12 | 2657076 | 0 | Final
7 | SDRIIP/Habi/W-07 | 636715034 | Imp. of Dhamaghar-Hafizia Madrasha-Debpur Enukaji Bari road at ch.00-500m. | 0.5 | 0 | 1609491 | 0 | 1609491 | 17.1.12 | M/S Ahmed Trading Crop. | 23.02.12 | 1529016 | 100% | 10.11.12 | 1264033 | 0 | Final
8 | SDRIIP/Habi/W-40 | 636714098 | Const. of 2 vent 3.50x3.00m RCC box culvert on Itakhola Rail Station-Bykuntopur tea garden road at ch.900m. | 0 | 7 | 0 | 993307 | 993307 | 21.03.12 | Md. Siraj Uddin Khan | 15.04.12 | 943641 | 100% | 21.10.12 | 0 | 937419 | Final
9 | SDRIIP/Habi/W-45 | 636714047 | A) Imp. Of Chowmohani-Komlanagar-Barjala BDR camp via Gazipur road at ch.00-1000m. B) Protection work of on the same road at ch. 300-313m. | 1 | 0 | 3253847 | 0 | 3253847 | 18.04.12 | M/S Mohammdi Enter. | 10.05.12 | 3091155 | 100% | 24.01.13 | 3016518 | 0 | Final
10 | SDRIIP/Habi/W-73 | 636714120 | Imp. Of Teliapara R&H-Teliapara Smriti Shudha road at Ch.00-1630m & other work. | 1.63 | 0 | 7354162 | 0 | 7354162 |  | Md.Kamal Ahmed | 29.10.13 | 7521740 | 100% | 01.03.15 | 5979891 | 0 | Work Final Vareation Sent to H/Q
11 | SDRIIP/Habi/W-85 |  | Const. of Womens Corner Market at Noapara Bazar. | 0 | 0 | 0 | 2035000 | 2035000 | 24.09.13 | Md.Golam Faruk | 07.10.13 | 1933249 | 100% | 12.04.14 | 0 | 1917392 | Final
12 | SDRIIP/Habi/W-113 | 636712010 | Construction of 36.00m Long RCC Girder Bridge on Andiura R&H-Bulla- Chatian Bazar Road At Ch.6400m. | 0 | 36 | 0 | 15911306 | 15911306 | 23.01.14 | M/S Jamal Ent. | 17.02.14 | 15115740 | 75% | 25.02.15 | 0 | 7086846 | work on going
13 | SDRIIP/Habi/W-120 |  | Const. of Womens Corner Market at Chowmohani Bazar . | 0 | 0 | 0 | 2054007 | 2054007 | 19.03.14 | M/S Mokul Const. | 10.04.14 | 1952250 | 35% | 13.11.14 | 0 | 0 | work on going
14 | SDRIIP/Habi/W-125 | 636712003 | Construction of 20.00m RCC Girder Bridge on Jagodishpur-Temunia-Shahaji Bazar Road At Ch.10+240k.m. | 0 | 20 | 0 | 10454970 | 10454970 | 17.07.14 | M/S. Rathindra Chandra Roy | 10.08.14 | 9932220 | 0% | 17.08.15 | 0 | 0 | Terminated
15 | SDRIIP/Habi/W-133 | 636712006 | A) Imp. Of Cangar bazar-Chowmohani- Road At Ch.986-1970m. B) Const. of Cross Drain on Cangar bazar-Chowmohani- Road At Ch.1800m. | 0.984 | 0 | 3210507 | 0 | 3210507 | 16.09.14 | Md. Kamal Ahmed | 13.10.14 | 3049981 | 0% | 30.06.15 | 0 | 0 | Letter Issued
16 | SDRIIP/Habi/W-134 | 636714052 | A) Imp. Of Barura DC road- Anandagram Pry. School Road At Ch.2237-3237m. B) Const. of 04 (Four) nos Cross Drain on Barura DC road- Anandagram Pry. School Road At Ch 2575m,3047m,2262m & 2811m. | 1 | 0 | 3905011 | 0 | 3905011 | 16.09.14 | M/S. Rani Traders | 13.10.14 | 3709760 | 30% | 30.06.15 | 250000 | 0 | work on going
17 | SDRIIP/Habi/W-135 | 636715074 | A) Imp. Of Cangar bazar to Bishnapur GPS Road At Ch.1000-1825m. B) Const. of Cross Drain on CCangar bazar to Bishnapur GPS Road At Ch.1124m. | 0.825 | 0 | 3276495 | 0 | 3276495 | 16.09.14 | M/S Neon Ent. | 13.10.14 | 3112670 | 0% | 30.06.15 | 0 | 0 | Letter Issued
18 | SDRIIP/Habi/W-136 | 636714016 | Imp. Of Madhabpur R&H- Shahapur bazar via Dighirpur Road At Ch.1480-2495m. | 1.15 | 0 | 4435620 | 0 | 4435620 | 16.09.14 | M/S. Khohinoor Ent. | 13.10.14 | 4213839 | 50% | 16.04.15 | 800000 | 0 | work on going
19 | SDRIIP/Habi/W-137 | 636053010 | Imp. Of Madhabpur R&H- Sultanpur- Gateghar bazar-Shahjahanpur UP Road At Ch.6425-7440.00m. | 1.15 | 0 | 5679551 | 0 | 5679551 | 16.09.14 | Md.Golam Faruk | 13.10.14 | 5395573 | 60% | 19.04.15 | 1483022 | 0 | work on going
|  |  | Madhabpur Upazila Sub Total= | 13.557 | 63 | 51944405 | 31448590 | 83392995 |  |  |  | 78655215 |  |  | 29247817 | 9941657
Chunarughat:
1 | SDRIIP/Habi/W-08 | 636263002 | A) Imp. of Shatiajuri UP office- Ranigaon UP office-Merashi Nuton bazar road at ch.4975-5250m.B) Const. of U-box Drain on the same road at ch.5129m. | 0.2777 | 0 | 1357421 | 0 | 1357421 | 17.1.12 | Md.Abdul Awal | 29.02.12 | 1289549 | 100% | 29.08.12 | 1253631 | 0 | Final
2 | SDRIIP/Habi/W-09 | 636264020 | A) Imp. of Paikpara UP office- Badargazi road at ch.500-1500m. B) Const. of 1x1.00x1.00 m. Rcc box culvert on the Same road at ch. 675m & 1450m. C) Const.of U-box Drain on the Same road at ch.1175m. | 1 | 2 | 3341546 | 459975 | 3801521 | 17.1.12 | M/S Haque Enter. | 29.02.12 | 3611444 | 100% | 30.06.13 | 3609661 | 0 | Final
3 | SDRIIP/Habi/W-10 | 636264021 | A) Imp. of RHD-Ramsree-Durgapure bazar road at ch.3800-4500m. B) Const. of 1x2.00x2.00 m. Rcc box culvert on the Same road at ch. 4350m.C) Const. of 1x.00x1.00 m. Rcc box culvert on the Same road at ch. 4150m.D) Const.of U-box Drain on the Same road at ch.3850m. | 0.7 | 3 | 2410242 | 562887 | 2973129 | 17.1.12 | Md.Siraj uddin Khan | 22.03.12 | 2824472 | 100% | 28.09.12 | 1676394 | 529921 | Final
4 | SDRIIP/Habi/W-11 | 636264053 | Const. of 3x4.00x4.00 m. Rcc box culvert on Pakuria-Battala-Kalanga road.at ch. 4250 m. | 0 | 12 | 0 | 1602137 | 1602137 | 17.1.12 | Md.Dider Hossain | 26.02.12 | 1522030 | 100% | 04.08.12 | 0 | 1517293 | Final
5 | SDRIIP/Habi/W-12 | 636264054 | A) Imp. of R&H-Borokota bazar via Ubahata UP office road at ch.850-1850m. B) Const. of 1x3.00x3.00 m. Rcc box culvert on the same road at ch. 1750m. | 1 | 3 | 3782731 | 619038 | 4401769 | 17.1.12 | M/S. Samin Bricks | 29.02.12 | 4181680 | 100% | 07.08.12 | 3589423 | 588085 | Final
6 | SDRIIP/Habi/W-13 | 636264041 | Imp. of Amtali (Chunarughat Rail Station)- Kalishiri road at ch.1000-1500m. | 0.5 | 0 | 1863564 | 0 | 1863564 | 17.1.12 | M/S Ful Mia & Brother | 23.02.12 | 1770385 | 100% | 30.01.13 | 1755145 | 0 | Final
7 | SDRIIP/Habi/W-14 | 636265064 | A) Imp. of Ladia WAPDA Embakment-Shahid Chunnu bazar via Mohdir kona road at ch.00-1000m.B) Const. of 1x1.00x1.00 m. Rcc box culvert on the Same road at ch. 620m.C) Const. of 1x.200x2.00 m. Rcc box culvert on the Same road at ch. 370m.D) Const.of U-box Drain (05) Nos on the Same road at ch.420,525,725,900 & 930m. | 1 | 3 | 3387903 | 675795 | 4063698 | 17.1.12 | M.A Ahad | 23.02.12 | 3860513 | 100% | 15.11.12 | 3215745 | 641929 | Final
8 | SDRIIP/Habi/W-15 | 636265079 | A) Imp. of Kaunda East side to Katakhila-Gogaura Mominpur via Natun bazar road at ch.00-1150m.B) Const. of 2x1.00x1.00 m. Rcc box culvert on the Same road at ch. 400,1100m.C) Const.of U-box Drain (06)Nos on the Same road at ch250,300,340,550,680 & 1140m. | 1.5 | 2 | 3838255 | 567071 | 4405326 | 17.1.12 | Md. Shafi ullah | 11.03.12 | 4185059 | 100% | 11.09.12 | 3640895 | 538474 | Final
9 | SDRIIP/Habi/W-51 | 636265036 | A) Imp. Of RHD (6No UP office)-Murar Banda Mazar via South Norpati road at Ch.600-1600m. B) Const. of 3Nos U-Box drain on the same road at Ch.1050,1250& 1350m. | 1 | 0 | 3338461 | 0 | 3338461 | 28.05.12 | M/S. Panna Traders | 17.06.12 | 3171538 | 100% | 21.12.12 | 3169380 | 0 | Final
10 | SDRIIP/Habi/W-57 | 636264030 | Imp. Of Deorgach Rail gate- Danchi Ferry Ghat road at Ch.1600-2600m. | 1 | 0 | 4415005 | 0 | 4415005 | 07.11.12 | Md.Kamal Ahmed | 13.12.12 | 4194241 | 100% | 17.06.13 | 4194070 | 0 | Final
11 | SDRIIP/Habi/W-58 | 636264004 | Imp. Of Amo Road Rail gate-Dulna road at Ch.00-1000m. | 1 | 0 | 3937211 | 0 | 3937211 | 07.11.12 | M/S. Sanzida Enterprise | 10.12.12 | 3740351 | 100% | 14.06.13 | 3677565 | 0 | Final
12 | SDRIIP/Habi/W-59 | 636264027 | Imp. Of Gazipur UP office- BDR camp road at Ch.1400-2100m. | 0.7 | 0 | 3013477 | 0 | 3013477 | 07.11.12 | M/S. Samin Bricks | 13.12.12 | 2862790 | 100% | 17.06.13 | 2861103 | 0 | Final
13 | SDRIIP/Habi/W-61 | 636265065 | A) Imp. Of Rakhi WAPDA Embakment- Sahid Chunnu Chow. Bazar via Kaaus road.at Ch. 00-700m.B) Const. of 1 Nos 1x1.00x1.00m RCC box Culvert on the same road at Ch.585m. C) Const. of 2Nos U-drain on the same road at Ch. 300m.690m. | 0.7 | 1 | 3073916 | 302644 | 3376560 | 04.12.12 | Md. Jahirul Islam Selam | 02.01.13 | 3207769 | 100% | 30.04.14 | 2821728 | 286790 | Final
14 | SDRIIP/Habi/W-70 | 636263003 | A) Imp. Of Deurgach UP office (Chunarughat Rail Station)-Amorote Bazar (Rail Station) Road at Ch. 620-1620m B) Const. of 1Nos 1.00x1.00m RCC box culvert on the Same Road.at Ch. 820m | 1 | 1 | 5191263 | 252930 | 5444193 | 30.05.13 | M/S.Bissmillah Ent. | 26.06.13 | 5171983 | 100% | 31.03.14 | 4931621 | 240283 | Final
15 | SDRIIP/Habi/W-71 | 636263009 | A) Imp. Of Paikpara UP office (Satang Bazar)-Shakir Mohammad Road at Ch. 00-1000m B) Const. of 1Nos 1.00x1.00m RCC box culvert on the Same Road.at Ch. 450m C) Const. of 1Nos 1.00x1.50m RCC box culvert on the Same Road.at Ch. 920m | 1 | 2 | 5246020 | 614810 | 5860830 | 30.05.13 | M/S.Sanjida Ent. | 20.06.13 | 5567788 | 100% | 27.03.14 | 4806970 | 500022 | Final
16 | SDRIIP/Habi/W-79 | 636263007 | A) Imp. Of Mirashi UP office-Shahid Chunu Chow. bazar Road at Ch. 1000-1800m B) Const. of 5 Nos U-Drain on the same road. At Ch.1309,1399,1519,1699 &1783m. C) Const. of 1Nos 2.00x1.50m RCC box culvert on the Same Road.at Ch. 1219m. | 0.8 | 3 | 4288395 | 405509 | 4693904 | 24.09.13 | Md.Jahirul Islam Selim | 10.10.13 | 4459207 | 75% | 12.10.14 | 2546275 | 385175 | BC Prep.
17 | SDRIIP/Habi/W-89 | 636264053 | Improvement of Pakuria-Battala-Kalanga Road via Mirashi Road At ch. 6050-7050 m. | 1 | 0 | 4265505 | 0 | 4265505 | 30.10.13 | M.A Ahad | 21.11.13 | 4052229 | 60% | 30.12.14 | 1790000 | 0 | work on going
18 | SDRIIP/Habi/W-90 | 636264030 | A) Imp. Of Deorgach Rail gate- Danchi Ferry Ghat road at Ch.2600-3551m.B) Const. of 2 Nos 1.00x1.00 m RCC box culvert on the Same Road At ch. 2665 & 3158m. | 0.95 | 2 | 3756700 | 471736 | 4228436 | 30.10.13 | M/S Sumon Ent. | 21.11.13 | 4017014 | 100% | 03.11.14 | 3568150 | 447965 | Final
19 | SDRIIP/Habi/W-91 | 636264020 | Imp. of Paikpara UP office- Badargazi road At Ch.1500-2500m. | 1 | 0 | 5198289 | 0 | 5198289 | 3010.13 | Md.Shamayun Kabir Chow. | 21.11.13 | 5152542 | 100% | 26.06.14 | 5152506 | 0 | Final
20 | SDRIIP/Habi/W-123 | 636265135 | Imp. of R&H-Durgapur Bazar-Ulukandi via Ubahata UP Office Road At Ch.00-590m. | 0.59 | 0 | 2686138 | 0 | 2686138 | 08.05.14 | M/S. S.M Cosnt. | 25.05.14 | 2551831 | 20% | 27.12.14 | 0 | 0 | work on going
21 | SDRIIP/Habi/W-126 | 636264004 | Imp. Of Amo Road Rail gate-Dulna road at Ch.1000-2000m. | 1 | 0 | 3863639 | 0 | 3863639 | 21.07.14 | Md. Abdur Rouf | 06.08.14 | 3670455 | 100% | 10.03.15 | 2800000 | 0 | Final
22 | SDRIIP/Habi/W-127 | 636264020 | Imp. of Paikpara UP office- Badargazi road At Ch.2500-3040m. | 0.54 | 0 | 2502228 | 0 | 2502228 | 21.07.14 | Md.Samayun Kabir Chow. | 06.08.14 | 2377116 | 30% | 08.02.15 | 250000 | 0 | work on going
23 | SDRIIP/Habi/W-128 | 636264054 | Imp. of R&H -Borokota Bazar via Ubahata UP office Road At Ch.1850-2598m. | 0.748 | 0 | 3741043 | 0 | 3741043 | 21.07.14 | M/S.Muklis Traders | 06.08.14 | 3553990 | 45% | 10.03.15 | 800000 | 0 | work on going
24 | SDRIIP/Habi/W-139 | 636263009 | Imp. Of Paikpara UP office( Satang Bazar)- Sakir Mohammad Bazar Road At Ch. 1000-2245m | 1.245 | 0 | 6488832 | 0 | 6488832 | 13.11.14 | Syed Rokunuzzaman | 03.12.14 | 6164390 | 15% | 30.06.15 | 0 | 0 | work on going
25 | SDRIIP/Habi/W-140 | 636264053 | Const. of 1x4.50x3.50m RCC Box Culvert on Pakuria Battala-Kalenga via Mirashi Road At Ch. 8500m. | 0 | 4.5 | 0 | 1129187 | 1129187 | 13.11.14 | M/S. Chowdhury Ent. | 03.12.14 | 1072727 | 100% | 15.12.15 | 0 | 0 | Final
26 | SDRIIP/Habi/W-153 | 636264010 | Const. Of 35 m RCC Girder Bridge over Karangi River on Sateajuri-Daragaon Road At Ch. 2+200 m. | 0 | 35 | 0 | 11592270 | 11592270 | 29.12.14 | M/S. Jamal Ent. | 02.02.15 | 11012656 | 0% | 07.02.16 | 0 | 0 | W/O Issued
27 | SDRIIP/Habi/W-162 | 636265068 | Imp. Of Pakuria Battala Rema road- Bularjum Road At Ch. 00-1000m | 1 | 0 | 5016455 | 0 | 5016455 |  |  |  | 0 |  |  | 0 | 0 | Tender Call Processing
|  |  | Chunarughat Upazila Sub Total= | 21.2507 | 73.5 | 90004239 | 19255989 | 109260228 |  |  |  | 99245749 |  |  | 62110262 | 5675937
|  |  | Habiganj-4 Total = | 34.8077 | 136.5 | 141948644 | 50704579 | 192653223 |  |  |  | 177900964 |  |  | 91358079 | 15617594
|  |  | Habiganj District Total= | 147.1197 | 534 | 592031876 | 177035741 | 769067617 |  |  |  | 699693889 |  |  | 353130209 | 93578487

## Fund State
Details fund Allocation Of Summary(SDRIIP)
Total Fund Received |  |  | Payment This Month |  | Cumulative Payment | Fund Lapses (If Any) | Balance
1 |  |  | 2 |  | 3 | 4 | 5(3+4)
456975000 |  |  | 14733696 |  | 446708696 | 0 | 10266304
Details Scheme Samary (SDRIIP)
Constituency Area | Total Scheme | Total Approved Estimated Cost | Total Contracr Amount | Complete Scheme (100%) | On going Scheme
[5 empty] | Progress above 70% | Progress 40% - 70% | Less than 40%
Habiganj-1 | 47 | 208860450 | 182083289 | 31 | 15 | 12 | 33
Habiganj-2 | 27 | 162993667 | 160686051 | 15
Habiganj-3 | 44 | 204560277 | 179023585 | 28
Habiganj-4 | 46 | 192653223 | 177900964 | 30
| 164 | 769067617 | 699693889 | 104 | 15 | 12 | 33
15
Assistant Engineer
LGED,Habiganj
Accountant
LGED,Habiganj
Senior Assistant Engineer
LGED,Habiganj
Executive Engineer
LGED,Habiganj

## Fund reci
SDRIIP FUND ALLOCATION
SL.No | Financial year | Memo | Date | Amount Tk
1 | 2011-2012 | 0 | 0 | 24000000
2 | 2012-2013 | 0 | 0 | 153475000
3 | 2013-2014 | 0 | 0 | 156500000
4 | 2014-2015 | 0 | 0 | 30000000
5 | 2015-2016 | 0 | 0 | 0
363975000