## Jessore
CITY REGION DEVELOPMENT PROJECT (CRDP)
Monthly Progress Report ( Physical & Financial )
Reporting Month : November /2018
District: Jessore
Sl No | Upazila | Package No | Name Of Scheme | Package Decription | Part-A Road Work |  | Part-B Drain Work |  | Part-C Structure |  | Part-D Ghat Work |  | Part-E Deck Work |  | Total Estemated Amount in Lac | Contract Amount in Lac | [5 empty] | Total Revised Contract in Lac | Date of Contract | Date of Completion | Progress | Fund Spent | Remerks |  | UZR |  | UNR |  | VR |  | Drain |  | Ghat |  | Deck
[5 empty] | Km | Estimated Cost in Lac | Km | Estimated Cost in Lac | m | Estimated Cost in Lac | Nos | Estimated Cost in Lac | Nos | Estimated Cost in Lac |  | Road | Drain | Structure | Ghat | Deck | Total | [7 empty] | Km | Amount | Km | Amount | Km | Amount | Km | Amount | No | Amount | No | Amount
1 | Sarsha | CRDP/ LGED/ JESSORE/UC/NCB/2015/ W-01 | Civil works in Navaran, khajura, Salua, Chinatola and Chingra urban center under Jessore district | i) Road in Navaran Urban Center | 1.313 | 180.867 | [8 empty] | 180.867 | 174.6996 |  |  |  |  | 174.6996 |  |  |  | 100% |  |  | 174.6996
|  |  |  | ii) Deck in Navaran Urban Center | [8 empty] | 2 | 38.3607 | 38.3607 |  |  |  |  | 37.0526 | 37.0526 |  |  |  | 100% |  |  | 37.0526
|  |  |  | iii) Drain in Navaran Urban Center |  |  | 1.406 | 239.0085 | [6 empty] | 239.0085 |  | 230.8585 |  |  |  | 230.8585 |  |  |  | 100% |  |  | 230.8585
2 | Bagerpara |  |  | iv) Road in Khajura Urban Center | 1.426 | 176.0396 | [8 empty] | 176.0396 | 170.0368 |  |  |  |  | 170.0368 |  |  |  | 100% |  |  | 170.0368
|  |  |  | v) Drain in Khajurain Urban Center |  |  | 1.163 | 188.5285 | [6 empty] | 188.5285 |  | 182.0999 |  |  |  | 182.0999 |  |  |  | 100% |  |  | 182.0999
3 | Chowgacga |  |  | vi) Road in Salua Urban Center | 0.81 | 71.2534 | [8 empty] | 71.2534 | 68.8237 |  |  |  |  | 68.8237 |  |  |  | 100% |  |  | 68.8237
|  |  |  | vii) Drain in Salua Urban Center |  |  | 0.525 | 92.7876 | [6 empty] | 92.7876 |  | 89.6237 |  |  |  | 89.6237 |  |  |  | 100% |  |  | 89.6237
4 | Monirampur |  |  | viii) Road in Chinatola Urban Center | 0.769 | 56.9171 | [8 empty] | 56.9171 | 54.9763 |  |  |  |  | 54.9763 |  |  |  | 100% |  |  | 54.9763
|  |  |  | iX) Drain in Chinatola Urban Center |  |  | 0.725 | 87.6485 | [6 empty] | 87.6485 |  | 84.6598 |  |  |  | 84.6598 |  |  |  | 100% |  |  | 84.6598
5 | Keshabpur |  |  | x) Road in Chingra Urban center | 0.553 | 63.5727 | [8 empty] | 63.5727 | 61.4049 |  |  |  |  | 61.4049 |  |  |  | 100% |  |  | 61.4049
|  |  |  | xi) Ghat in Chingra Urban center | [6 empty] | 2 | 40.4136 |  |  | 40.4136 |  |  |  | 39.0355 |  | 39.0355 |  |  |  | 100% |  |  | 39.0355
|  |  |  | xii) Drain in Chingra Urban center |  |  | 0.316 | 39.8931 | [6 empty] | 39.8931 |  | 38.5328 |  |  |  | 38.5328 |  |  |  | 100% |  |  | 38.5328
W-01 Package Total= |  |  |  |  | 4.871 | 548.6497 | 4.135 | 647.8663 | 0 | 0 | 2 | 40.4136 | 2 | 38.3607 | 1275.2903 | 529.9414 | 625.7748 | 0 | 39.0355 | 37.0526 | 1231.8043 | 1416.1014 | 18/02/16 | 30/11/16 Ext-20.09.18 | 100% | 1066.3611 |  | 1231.8043
2 | Jhikorgacha | CRDP/ LGED/ JESSORE/UC/NCB/2016/ W-02 | Civil works in Bakra urban center under Package No.- W-02 Jessore district | i) Improvement of Road in Bazar area of Bakra Urban Center | 4.35 | 319.9461 | [8 empty] | 319.9461 | 299.4696 |  |  |  |  | 299.4696 |  |  |  | 100% |  |  | 299.4696
|  |  |  | ii) Improvement of Bakra bazar(Bakra UP)-Matshia bazar Road (3009) | 2.244 | 87.8545 | [8 empty] | 87.8545 | 82.2318 |  |  |  |  | 82.2318 |  |  |  | 100% |  |  | 82.2318 |  |  | 2.244
|  |  |  | iii) Improvement of Hazirbag-Digri bazar Road in/C 8 nos Box culvert. (4025) | 1.9 | 121.4984 |  |  | 5 | [5 empty] | 121.4984 | 113.7225 |  |  |  |  | 113.7225 |  |  |  | 100% |  |  | 113.7225 |  |  |  |  | 1.19
|  |  |  | iv) Improvement of Bakra College More BC road-Daspara Road In/C 4 nos box culvert (4090) | 1.19 | 58.0012 |  |  | 2.5 | [5 empty] | 58.0012 | 54.2891 |  |  |  |  | 54.2891 |  |  |  | 100% |  |  | 54.2891 |  |  |  |  | 0.45
|  |  |  | v) Improvement of Digdana bazar-Digdana Sluice Gate Road in/C 1 no box culvert (5090) | 0.45 | 23.642 |  |  | 0.625 | [5 empty] | 23.642 | 22.1289 |  |  |  |  | 22.1289 |  |  |  | 100% |  |  | 22.1289 |  |  |  |  | 1.2
|  |  |  | vi) Improvement of Bakra Rifuzipara-Bakra Daspara Road In/C 2 nos box culvet (5145) | 1.2 | 63.1603 |  |  | 1.25 | [5 empty] | 63.1603 | 59.118 |  |  |  |  | 59.118 |  |  |  | 100% |  |  | 59.118 |  |  |  |  | 0.9
|  |  |  | vii) Improvement of Roypatan GC Road-Bakra Hazirbag Girls High School Road In/C 2 nos box culvert (5147) | 0.9 | 49.9571 |  |  | 1.25 | [5 empty] | 49.9571 | 46.7598 |  |  |  |  | 46.7598 |  |  |  | 100% |  |  | 46.7598 |  |  |  |  | 0.9
|  |  |  | viii) Improvement of Drain in Bazar area of Bakra Urban Center |  |  | 2.075 | 408.9966 | [6 empty] | 408.9966 |  | 378.793 |  |  |  | 378.793 |  |  |  | 100% |  |  | 378.793 |  |  |  |  | 0
|  |  |  | ix) Construction of RCC Box Culvert (1.6x1.6m) on Hazirbag-Digri baza Road (40250 |  |  |  |  | 1.6 | 4.1685 |  |  |  |  | 4.1685 |  |  | 4.193 |  |  | 4.193 |  |  |  | 100% |  |  | 4.193
W-02 Package Total= |  |  |  |  | 12.234 | 724.0597 | 2.075 | 408.9966 | 12.225 | 4.1685 | 0 | 0 | 0 | 0 | 1137.2248 | 677.7199 | 378.793 | 4.193 | 0 | 0 | 1060.7059 | 1214.7458 | 25/05/16 | 30/11/16 Ext-30.06.18 | 100% | 933.1292 |  | 1060.7059 | 0 | 0 | 2.244 | 0 | 4.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Jhikorgacha | CRDP/ LGED/ JESSORE/UC/NCB/2016/ W-03 | Civil works in Bakra urban center under Package No.- W-03 Jessore district | i) Improvement of Bakra UP-Jhapa (Bridge) Bazar Road (Ch.650-2102m) (ID 3008) | 1.452 | 39.4335 | [8 empty] | 39.4335 | 36.7166 |  |  |  |  | 36.7166 |  |  |  | 100% |  |  | 36.7166 |  |  | 1.452
|  |  |  | ii) Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More Road (Ch.2780-3880) In/C 5 nos Cross Drain (ID 3012) | 1.1 | 86.4005 |  |  | 3.125 | [5 empty] | 86.4005 | 80.4476 |  |  |  |  | 80.4476 |  |  |  | 100% |  |  | 80.4476 |  |  | 1.1
|  |  |  | iii) Improvement of Bakra UP-Digdana bazar Road (Ch.00-3480m) (ID 3023) | 3.48 | 200.0608 | [8 empty] | 200.0608 | 186.2768 |  |  |  |  | 186.2768 |  |  |  | 100% |  |  | 186.2768 |  |  | 3.48
|  |  |  | iv) Improvement of Bakra Dargahdangi More-Khordah via Matshia Road (Ch.00-3910m) In/C 2 nos Cross Drain (ID 4037) | 3.91 | 156.6523 |  |  | 1.25 | [5 empty] | 156.6523 | 145.8591 |  |  |  |  | 145.8591 |  |  |  | 100% |  |  | 145.8591 |  |  |  |  | 3.91
|  |  |  | v) Improvement of Uzzalpur bazar-Khasalnagar-Jhapa Bridge(Shahid Muktijodha Sarak) Road (Ch.1000-3350m) In/C 4 nos Cross Drain (ID 4067) | 2.35 | 153.8737 |  |  | 2.5 | [5 empty] | 153.8737 | 143.2719 |  |  |  |  | 143.2719 |  |  |  | 100% |  |  | 143.2719 |  |  |  |  | 2.35
|  |  |  | vi) Improvement of Alipur GC-Bishnupue GC road via Alipur Charatala More Road (Ch.00-1025m) In/C 4 nos Cross Drain (ID 4091) | 1.025 | 61.7287 |  |  | 2.5 | [5 empty] | 61.7287 | 57.4756 |  |  |  |  | 57.4756 |  |  |  | 100% |  |  | 57.4756 |  |  |  |  | 1.025
|  |  |  | vii) Improvement of Roypatan UZR-Roypatan village Road (Ch.00-510m) In/C 2nos cross drain (ID 5055) | 0.51 | 36.3453 |  |  | 1.25 | [5 empty] | 36.3453 | 33.8411 |  |  |  |  | 33.8411 |  |  |  | 100% |  |  | 33.8411 |  |  |  |  | 0.51
|  |  |  | viii) Improvement of Bilkachua-Bishnupur Road (Ch.2400-3200m) In/C 2 nos cross drain (ID 5056) | 0.8 | 49.7767 |  |  | 1.25 | [5 empty] | 49.7767 | 46.3472 |  |  |  |  | 46.3472 |  |  |  | 100% |  |  | 46.3472 |  |  |  |  | 0.8
|  |  |  | ix) Improvement of Chotopodawlia-Baropodawlia Road (Ch.260-1670m) In/C 2 nos cross drain and Link. Porbopara mosque to Karim Gazibari via arsenic tube wall (Ch.00-200m) [ID 5065] | 1.61 | 82.0187 |  |  | 1.25 | [5 empty] | 82.0187 | 76.3677 |  |  |  |  | 76.3677 |  |  |  | 100% |  |  | 76.3677 |  |  |  |  | 1.61
|  |  |  | x) Improvement of Bakra GC-Alipur Village oad (Ch.00-600m) [ID 5072] | 0.6 | 30.5568 | [8 empty] | 30.5568 | 28.4514 |  |  |  |  | 28.4514 |  |  |  | 100% |  |  | 28.4514 |  |  |  |  | 0.6
|  |  |  | xi) Improvement of Sonakur Rowshon Morol House More-Sonakur Taltala Road (Ch.00-710m) In/C 2 nos cross drain [ID 5094] | 0.71 | 50.8583 |  |  | 1.25 | 6.8583 |  |  |  |  | 57.7166 | 46.61 |  | 7.13 |  |  | 53.74 |  |  |  | 100% |  |  | 53.74 |  |  |  |  | 0.71
|  |  |  | xii) Improvement of Alipur Khan Shaheb's house More-Alipur Charatala More Road (Ch.00-700m) [ID 5138] | 0.7 | 32.9699 | [8 empty] | 32.9699 | 30.6983 |  |  |  |  | 30.6983 |  |  |  | 100% |  |  | 30.6983 |  |  |  |  | 0.7
|  |  |  | xiii) Improvement of Alipur Munshipara More-Hanefpara More Road 9Ch.00-500m) [ID 5139] | 0.5 | 26.5412 | [8 empty] | 26.5412 | 24.7125 |  |  |  |  | 24.7125 |  |  |  | 100% |  |  | 24.7125 |  |  |  |  | 0.5
|  |  |  | xiv) Improvement of Roypaton Sekender's house to the house of Akbar Road (Ch.00-204m) [ID 5329] | 0.24 | 10.406 | [8 empty] | 10.406 | 9.689 |  |  |  |  | 9.689 |  |  |  | 100% |  |  | 9.689 |  |  |  |  | 0.24
|  |  |  | xv) Improvement of Bakra Ziaul More-Alipur Hanefpara via Gazipara Road (Ch.00-900m) In/C 2 nos cross drain [ ID 5352] | 0.9 | 50.3584 |  |  | 1.25 | [5 empty] | 50.3584 | 46.8888 |  |  |  |  | 46.8888 |  |  |  | 100% |  |  | 46.8888 |  |  |  |  | 0.9
|  |  |  | xvi) Improvement of Digdana Pucca road to the house of Muktijodha Chand Ali Road (Ch.00-470m) In/C 5 nos cross drain [ID 5367] | 0.47 | 25.9808 |  |  | 3.125 | [5 empty] | 25.9808 | 24.1907 |  |  |  |  | 24.1907 |  |  |  | 100% |  |  | 24.1907 |  |  |  |  | 0.47
|  |  |  | xvii) Improvement of Khatbaria-Nayra bazar Road (Ch.00-1600m) In/C 4 nos cross drain [ID 4039] | 1.6 | 80.9114 |  |  | 2.5 | [5 empty] | 80.9114 | 75.3367 |  |  |  |  | 75.3367 |  |  |  | 100% |  |  | 75.3367 |  |  |  |  | 1.6
W-03 Package Total= |  |  |  |  | 21.957 | 1174.8729 | 0 | 0 | 21.25 | 6.8583 | 0 | 0 | 0 | 0 | 1181.7312 | 1093.1811 | 0 | 7.13 | 0 | 0 | 1100.3111 | 1265.0532 | 25/05/16 | 30/11/16 Ext-30.06.18 | 100% | 975.3074 |  | 1100.3111 | 0 | 0 | 6.032 | 0 | 15.925 | 0 | 0 | 0 | 0 | 0 | 0 | 0
District Total= |  |  |  |  | 39.062 | 2447.5823 | 6.21 | 1056.8629 | 33.475 | 11.0268 | 2 | 40.4136 | 2 | 38.3607 | 3594.2463 | 2300.8424 | 1004.5678 | 11.323 | 39.0355 | 37.0526 | 3392.8213 | 3895.9003 |  |  | 100% | 2974.7977 |  | 3392.8213 | 0 | 0 | 8.276 | 0 | 20.565 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Sub Asstt Engineet | [11 empty] | Sr. Assitant Engineer | [6 empty] | Monjurul Alam Siddiqui
|  | LGED Jessore | [11 empty] | LGED Jessore | [6 empty] | Exceutive Engineer

## Sheet2
| Q | E/Rate | Cont/Rate | Est Cost | Cont Cost | Q | Est Cost | Cont Cost | Est Cost
2 | 4054.71 | 289.86 | 150.001 | 1175298.2406 | 608210.5547
3 | 4054.71 | 29.75 | 10.001 | 120627.6225 | 40551.1547
4 | 561.375 | 61.54 | 40.001 | 34547.0175 | 22455.5614
5 | 1015.522 | 570.29 | 600.001 | 579142.0414 | 609314.2155
10 | 155 | 137.06 | 120 | 21244.3 | 18600
11 | 280.44 | 2690.32 | 2800.001 | 754473.3408 | 785232.2804
12 | 280.44 | 284.41 | 250.001 | 79759.9404 | 70110.2804
18 | 542 | 299.16 | 320.001 | 162144.72 | 173440.542
22 | 2915.6 | 143.07 | 100.001 | 417134.892 | 291562.9156
25 | 3423.449 | 125.53 | 150.001 | 429745.553 | 513520.7734 | 64.819 | 8136.7291 | 9722.9148
26 | 1 | 20000 | 20000.001 | 20000 | 20000.001 |  | 0 | 0
27 |  | 7000 | 7000.001 | 0 | 0 | 1 | 7000 | 7000.001
28 | 22.642 | 325.38 | 300.001 | 7367.254 | 6792.6226 | 22.642 | 7367.254 | 6792.6226
29 | 229.681 | 6792.64 | 10500.001 | 1560140.3478 | 2411650.7297 | 1.698 | 11533.9027 | 17829.0017
30 | 175846.984 | 82.54 | 65.001 | 14514410.0594 | 11430229.807 | 1659.574 | 136981.238 | 107873.9696
31 | 2641.504 | 18.98 | 15.001 | 50135.7459 | 39625.2015 |  | 0 | 0
32 | 33.75 | 11771.71 | 10000.001 | 397295.2125 | 337500.0338 |  | 0 | 0
33 | 280.77 | 184.1 | 170.001 | 51689.757 | 47731.1808 |  | 0 | 0
34 | 65.938 | 6186.87 | 7000.001 | 407949.8341 | 461566.0659 |  | 0 | 0
35 | 272.469 | 11593.01 | 14000.001 | 3158735.8417 | 3814566.2725 | 7.768 | 90054.5017 | 108752.0078
36 | 523.644 | 12124.8 | 14000.001 | 6349078.7712 | 7331016.5236 | 6.42 | 77841.216 | 89880.0064
37 |  | 15652.4 | 14000.001 | 0 | 0 | 0.268 | 4194.8432 | 3752.0003
38 | 262.539 | 13758.22 | 14000.001 | 3612069.3206 | 3675546.2625 | 2.984 | 41054.5285 | 41776.003
39 |  | 13047.72 | 14000.001 | 0 | 0 | 0.382 | 4984.229 | 5348.0004
40 |  | 121.5 | 80.001 | 0 | 0 | 81.6 | 9914.4 | 6528.0816
41 |  | 9905.68 | 10000.001 | 0 | 0 | 0.548 | 5428.3126 | 5480.0005
42 |  | 171.88 | 100.001 | 0 | 0 | 1.8 | 309.384 | 180.0018
43 |  | 313.94 | 200.001 | 0 | 0 | 32 | 10046.08 | 6400.032
44 | 542 | 910.01 | 690.001 | 493225.42 | 373980.542 |  | 0 | 0
45 | 17050 | 158.45 | 100.001 | 2701572.5 | 1705017.05 |  | 0 | 0
46 | 177.6 | 11058.09 | 9000.001 | 1963916.784 | 1598400.1776 |  | 0 | 0
47 | 100 | 313.48 | 250.001 | 31348 | 25000.1 |  | 0 | 0
48 | 1680 | 181.64 | 100.001 | 305155.2 | 168001.68 |  | 0 | 0
49 | 3832 | 89.66 | 80.001 | 343577.12 | 306563.832 |  | 0 | 0
50 | 527.408 | 687.33 | 500.001 | 362503.3406 | 263704.5274 |  | 0 | 0
51 | 18 | 8331.31 | 5000.001 | 149963.58 | 90000.018 |  | 0 | 0
54 | 1 | 5000 | 5000.001 | 5000 | 5000.001 |  | 0 | 0
55 |  | 2000 | 2000.001 | 0 | 0 | 1 | 2000 | 2000.001
56 | 1 | 400000 | 400000.001 | 400000 | 400000.001 |  | 0 | 0
57 | 30 | 309 | 100.001 | 9270 | 3000.03 |  | 0 | 0
58 | 52 | 1000 | 120.001 | 52000 | 6240.052 |  | 0 | 0
59 | 17.324 | 10766 | 13000.001 | 186510.184 | 225212.0173 |  | 0 | 0
|  |  |  | 40907031.9409 | 37879343.0075 |  | 416846.6188 | 419314.6445