## Jashore
Contract Status of Flood & Disaster Damaged Rural Road Infrastructure Rehabilitation Project (FDDRIRP), FY: 2018-2019
District : |  | Jashore | [14 empty] | Date of Reporting: | 2018-12-01
Sl. No. | Name of Upazila | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Contract's Name | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progr. (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
A. Rehabilitation Road [Strengthening/Widening]
1 | Abhoynagar | W01 | 1 | 241042003 | Nowapara Upazila H/Q (Live Stock Office)- Paira GC via Hospital Road | M/S Motiur Rahaman Nannu JV, 57 Chawlkbazar, Sadar, Faridpur | 0 | 5015 | 5015 | 53491659 | 56000291.61 |  | 2018-10-17 | 2019-05-20 | 20.93% | 20% | - |  |  | 215 | 45
2 | Manirampur | W02 | 1 | 241612011 | Monirampur - Nowapara - Kultia Road |  | 0 | 7000 | 7000 | 67661941 |  |  |  |  | - |  | - | 1st call Re-Tendered. 2nd call on New rate on live, Tender will be received on 18/12/18. |  | 0 | -
3 | Manirampur | W03 | 1 | 241612011 | Monirampur - Nowapara - Kultia Road |  | 7000 | 12410 | 5410 | 62781736 |  |  |  |  | - |  | - | 2nd call, no tender received. Estimate using 2018-19 rate sent to Hqs. Approval not yet received. |  | 0 | -
4 | Manirampur | W04 | 1 | 241613025 | Hazirhat Bazar - Sundaki UP via Kuchlia Bottola Road |  | 0 | 2570 | 2570 | 25891025 |  |  |  |  | - |  | - | APP Send |  | 0 | -
5 | Jessore Sadar | W05 | 1 | 241475176 | Vaina Sardarpara - Rajapur Road | M/S Biswas Construction, 134 Dhaka Road, Puratonkasba, Jashore | 0 | 925 | 925 | 4505069 | 4700138.49 |  | 2018-11-19 | 2019-03-18 | 10.08% | 30% | - |  |  | 119 | 12
6 | Keshabpur | W06 | 1 | 241382002 | Keshabpur-Katakhali, Nehalpur Road |  | 0 | 8000 | 8000 | 84112314 |  |  |  |  | - |  | - | Evaluation under Processed |  | 0 | -
7 | Keshabpur | W07 | 1 | 241382002 | Keshabpur-Katakhali, Nehalpur Road |  | 8000 | 15270 | 7270 | 69023544 |  |  |  |  | - |  | - | Evaluation under Processed |  | 0 | -
|  | W08 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W09 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W10 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W11 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W12 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W13 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W14 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W15 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W16 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W17 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W18 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W19 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W20 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W21 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W22 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W23 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W24 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W25 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W26 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W27 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W28 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W29 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
|  | W30 | [6 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
7 | Sub-Total (A): | 5 |  |  | Not Contacted Amount | 309470560 |  |  | 36.19 | 367467288 | 60700430.1 | 0 | Fin. Pgr. (%) | - |  | 20.77%
B. Rehabilitation Structure [Bridges/Culverts]
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
0 | Sub-Total (B): | 0 |  |  | Not Contacted Amount | 0 |  |  | 0 | 0 | 0 | 0 | Fin. Pgr. (%) | - |  | 0
7 | Grand Total: | 5 |  |  | Not Contacted Amount | 309470560 |  |  |  | 367467288 | 60700430.1 | 0 | Fin. Pgr. (%) | 0 |  | 20.77%
Fund Received: | [5 empty] | Structure | 0 | m | Road | 36.19 | km |  |  |  |  | Cash in Hand: |  | 0
Date: | [17 empty] | Total:
Tk. | [17 empty] | 0
Comments if any:
[12 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  |  | Amount Required upto June'17 (Tk.)
Jessore Sadar
Abhoynagar
Bagher Para
Chaugacha
Jhikargacha
Keshabpur
Manirampur
Sharsha