## Progress jun18
Rangpur Division Rural Infrastructure Improvement Project (RDRIIP) District wise Monthly Progress Report (Physical & Financial).
District : Gaibandha. | [11 empty] | Reporting Month: Up to Jun/2018
Upazila | Approval Date | Package No | Road ID No. | Name of scheme (chainage) | Quantity (Km/m/nos) | Approved Estimated cost (Tk) | Name of Contractor | Contract Amount (Tk) | Date of Contract | Date of completion | Physical Progress (%) | Payment Status |  |  | Remarks
[12 empty] | Final Bill (Tk.) | Payment made (Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16 | 20
1. Improvement of Upazila road:
Sadar | 15.07.2014 | RDRIIP/GAI/ UZ-041 | 132242010 | Improvement of Tulshi Ghat -Pocherbazar GC via Khur Dokomurpur Bazar Road (Ch.5000-5552m). | 0.552 | 4368588 | Md. Shoheb Hossain Mona | 3811387.87 | 11.11.2014 | 11.11.2015 | 100% | 3811387 | 3811387 | 0 | Final bill Paid
Sadar | 03.08.2016 | RDRIIP/GAI/ UZ-096 | 132242013 | Improvement of Gaibandha - Shaghata R&H near Fulbari - Fulchori HQ via Chuniakandi Road (Ch. 00-1100m). | 1.1 | 10575563 | Md. Nuruzzaman, Kurigram. | 10928502.72 | 31.10.2016 | 14.11.2017 | 100% | 10896041 | 10896041 | 0 | Final bill Paid
Sub-Total = |  | 2 |  |  | 1.652 | 14944151 | 2 | 14739890.59 |  |  | 100% | 14707428 | 14707428 | 0
Sadullapur | 12.06.2014 | RDRIIP/GAI/ UZ-010 | 132822005 | Improvement of Dhaperhat GC – Madargonj GC (Dhaperhat – Masargonj FBR road) Road (Ch. 1480-2480m). | 1 | 6977793 | Md. Mahomudun Nobi | 5833150.8 | 11.11.2014 | 30.06.2016 | 100% | 5785739 | 5785739 | 0 | Final bill Paid
Sadullapur | 13.07.2014 | RDRIIP/GAI/ UZ-040 | 132822010 | Improvement of Sadullapur – Pachar Bazar GC Road (Ch. 4575-7263m). | 2.688 | 16658151 | Md. Ferdous Bari | 13579866.66 | 12.11.2014 | 30.06.2016 | 100% | 13565695 | 13565695 | 0 | Final bill Paid
Sadullapur | 05.01.2015 | RDRIIP/DIN/ UZ-059 | 132822004 | Improvement of Jamlarjan – Palashbari Road (2224-4224m). | 2 | 13813541 | Md. Abu Sayid Mahabub. | 12162818.55 | 24.03.2015 | 15.03.2016 | 100% | 12160560 | 12160560 | 0 | Final bill Paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ UZ-105 | 132822005 | Improvement of Dhaperhat GC - Madargonj Pirgonj GC Road (Ch. 2480-4127m). | 1.647 | 12563060 | Md. Ferdous Bari, Sadullapur, Gaibandha. | 12224855.44 | 20.06.2017 | 24.04.2018 | 100% | 12222846 | 12222846 |  | Final bill Paid
Sub-Total = |  | 4 |  |  | 7.335 | 50012545 | 4 | 43800691.45 |  |  | 100% | 43734840 | 43734840 | 0
Palalshbari | 03.11.2014 | RDRIIP/GAI/ UZ-049 | 132672007 | Improvement of Satharpara RHW - Fakirhat GC Road (Ch. 2000-3500m). | 1.5 | 11440377 | Md. Abu Sayid Mahabub. | 12269761.91 | 22.02.2015 | 14.01.2016 | 100% | 12254900 | 12254900 | 0 | Final bill Paid
Palalshbari | 05.07.2015 | RDRIIP/GAI/ UZ-078 | 132672007 | Improvement of Satharpara RHW - Fakirhat GC Road (Ch. 3500-5000m). | 1.5 | 12343838 | Md. Jakir Hossain | 11185609.27 | 18.10.15 | 29.02.2017 | 100% | 11185142 | 11185142 | 0 | Final bill Paid
Palalshbari | 03.08.2016 | RDRIIP/GAI/ UZ -095 | 132672006 | Improvement of Thutiapukur RHW - Pacharbazar GC Road (Ch. 00-1235m). | 1.235 | 12583020 | Md. Abdul Latif Hakkani, Gaibandha. | 12837718.14 | 24.10.2016 | 14.11.2017 | 100% | 12835726 | 12835726
Palalshbari | 07.08.2016 | RDRIIP/GAI/ UZ-098 | 132672010 | Improvement of Dublagari NHW - Dholbanga GC Road via Amlagachi GC Road (Ch.00-1110m). | 1.11 | 9511147 | Md. Shahidul Islam, Gaibandha. | 9978869.86 | 04.12.2017 | 04.12.2017 | 100% | 9625861 | 9625861 | 0 | Final bill Paid
Palalshbari | 23.08.2016 | RDRIIP/GAI/ UZ-100 | 132672009 | Improvement of Komorpur GC - Marihat GC Road via Sahindaha Road (Ch. 1580-4580m). | 2.984 | 24162562 | Md. Abdul Latif Hakkani, Gaibandha. | 25345297.52 | 21.11.2016 | 19.11.2017 | 100% |  | 25344039 |  | Final bill Paid
Palalshbari | 01.01.2017 | RDRIIP/GAI/ UZ-102 | 132672003 | Improvement of Tulshighat GC - Nakihat GC Road (Ch. 25-650m). | 0.625 | 4728832 | Md. Abdul Latif Hakkani, Gaibandha. | 4955788.81 | 25.05.2017 | 25.01.2018 | 100% |  | 4955063 |  | Final bill Paid
Sub-Total = |  | 6 |  |  | 8.954 | 74769776 | 6 | 76573045.51 |  |  | 100% | 45901629 | 76200731 | 0
Gobindaganj | 12.06.2014 | RDRIIP/GAI/ UZ-009 | 132302016 | Improvement of Shagdaha Bridge – Trimohonighat Road (Ch. 5760-6550m & 7260-8470m). | 2 | 12138543 | M/S. SR Traders Thanapara, Gaibandaha | 10950991.36 | 16.09.2014 | 14.09.2015 | 75% |  | 3809933 | 7141058.36
Sub-Total = |  | 1 |  |  | 2 | 12138543 | 1 | 10950991.36 |  |  | 75% | 0 | 3809933 | 7141058.36
Total = |  | 13 |  |  | 19.941 | 151865015 | 13 | 146064618.91 |  |  | 98.08% | 104343897 | 138452932 | 7141058.36
2. Improvement of Union Road:
Sundarganj | 29.11.2015 | RDRIIP/GAI/ UN-210 | 132913003 | Improvement of Ramjiban UP HQ - Dahaband UP HQ (Brac Office) Road (Ch. 4200-5200m). | 1 | 5390911 | RSL Enterprise | 5639066.29 | 08.03.2016 | 01.03.2017 | 100% | 5639000 | 5639000 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ UN-211 | 132913004 | Improvement of Sonaray UP HQ - Naldanga GC (Kishmbazar) Road (Ch. 2800-3800m). | 1 | 5793102 | Md. Motlbur Rahman | 6066482.18 | 08.03.2016 | 01.03.2017 | 100% | 6051845 | 6051845 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ UN-212 | 132913006 | Improvement of Dhopadanga UP -Sreepur UP HQ (Dharmapur FRA) Road (Ch. 1000-3000m). | 2 | 13821170 | M/S Ahsan & Co. | 14477438.67 | 08.03.2016 | 01.03.2017 | 100% | 14463621 | 14463621 |  | Final bill paid
Sundarganj | 04.08.2016 | RDRIIP/GAI/ UN-281 | 132913008 | Improvement of Dharmopur (Sreepur UP H/Q) - Baruarhat Road (Ch. 00-1000m). | 1 | 7284497 | Md. Abdul Latif Hakkani, Gaibandha. | 7643378.99 | 22.11.2016 | 4.12.2017 | 100% | 7633565 | 7633565 |  | Final bill paid
Sundarganj | 04.08.2016 | RDRIIP/GAI/ UN-282 | 132913013 | Improvement of Ramjiban UP HQ -Naldangha GC (Bater Chara) Road (Ch. 00-1000m). | 1 | 6233243 | M/S Shazin Traders | 6538044.91 | 25.10.2016 | 14.11.2017 | 100% | 6537695 | 6537695 |  | Final bill paid
Sundarganj | 04.08.2016 | RDRIIP/GAI/ UN-283 | 132913017 | Improvement of Santiram UP -Pachgasi Model School (Muzamder GC) Road (Ch. 2100-3100m). | 1 | 7037046 | M/S Esa Kabinet, Gaibandha. Nozel C.Man | 7374805.92 | 27.11.2016 | 04.12.2017 | 45% |  | 872453 | 6502352.92
Sub-Total = |  | 6 |  |  | 7 | 45559969 | 6 | 47739216.96 |  |  | 90.83% | 40325726 | 41198179 | 6502352.92
Sadar | 15.07.2014 | RDRIIP/GAI/ UN-037 | 132243016 | Improvement of Gidari UP office - Dariapur GC Road (Ch. 00-1000m). | 1 | 5730258 | Md. Khademul Islam Jewel. | 4936071.89 | 09.09.2014 | 15.07.2015 | 100% | 4936018 | 4936018 |  | Final bill paid
Sadar | 15.07.2014 | RDRIIP/GAI/ UN-071 | 132243004 | Improvement of Badia khali UP office - Chak Barul Bazar Road (Ch. 2950-3850m). | 0.9 | 4854829 | Md. Khademul Islam Jewel | 4154545.48 | 11.11.2014 | 11.11.2015 | 100% | 4154545 | 4154545 |  | Final bill paid
Sadar | 01.10.2014 | RDRIIP/GAI/ UN-072 | 132243014 | Improvement of Badiakhali UP office - FarazKhan Bazar Road (Ch. 2500-3500m). | 1 | 5382612 | Md. Khademul Islam Jewel | 4663777.35 | 11.11.2014 | 11.11.2015 | 100% | 4663777 | 4663777 |  | Final bill paid
Sadar | 06.04.2015 | RDRIIP/GAI/ UN-152 | 132243013 | Improvement of Hasem Bazar – Ghagoa UP Road (Ch. 00-4760m). | 4.76 | 35969395 | KJ-SA (JV) | 37720850 | 10.11.2015 | 29.12.2016 | 100% | 37509075 | 37509075 |  | Final bill paid
Sub-Total = |  | 4 |  |  | 7.66 | 51937094 | 4 | 51475244.72 |  |  | 100% | 51263415 | 51263415 | 0
Sadullapur | 27.02.2014 | RDRIIP/GAI/ UN-013 | 132823005 | Improvement of Kamrapara UP office - Sadullapur Naldanga Road (Ch. 00-1000m). | 1 | 5691572 | Mony Enterprise Polashbari, Gaibandaha. | 5063758.98 | 06.07.2014 | 22.06.2015 | 100% | 5063758 | 5063758 |  | Final bill paid
Sadullapur | 12.06.2014 | RDRIIP/GAI/ UN-042 | 132823002 | Improvement of Moshbsndhi - Mirpur Road (Ch. 4235-5235m). | 1 | 5533374 | Mony Enterprise | 4683248.56 | 07.09.2014 | 10.06.2015 | 100% | 4681491 | 4681491 |  | Final bill paid
Sadullapur | 01.07.2015 | RDRIIP/GAI/ UN-170 | 132823017 | Improvement of Bhatgram U.P office – Nagbari Bazar via Burir Bazar Road (Ch. 00-500m). | 0.5 | 3172927 | Md. Ferdous Bari | 2807380.44 | 18.10.2015 | 30.06.2016 | 100% | 2749665 | 2749665 |  | Final bill paid
Sadullapur | 13.06.2016 | RDRIIP/GAI/ UN-276 | 132823006 | Improvement of Chandiapur Bazar - Rahmatpur GC via Rasulpur bazar Road (Ch. 00-1000m). | 1 | 7306613 | Md. Zahidul Islam | 6828952.81 | 11.11.2016 | 24.10.2017 | 100% | 6532501 | 6532501 |  | Final bill paid
Sub-Total = |  | 4 |  |  | 3.5 | 21704486 | 4 | 19383340.79 |  |  | 100% | 19027415 | 19027415 | 0
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-303 | 132673005 | Improvement of Dholbanga Bazar at Zillbandha-Pabnapur UP office Road (Ch. 910-1414m). | 0.504 | 3230128 | Md. Shahidul Islam, Gaibandha. Kamal | 3386403.94 | 12.06.2017 | 24.04.2018 | 100% |  | 2700000 | 686403.94 |  | 685424
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-305 | 132673002 | Improvement of Kalibari GC at Chinema Hall - Chattra UP Office Road (Ch. 2000-2500m). | 0.5 | 3310770 | Mony Enterprise, Polashbari, Gaibandha. | 3467955.73 | 22.05.2017 | 24.04.2018 | 100% | 3466107 | 3466107 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-306 | 132673022 | Improvement of Monohorpur-UP office to Pabnapur up office Road via Azir beel Road (Ch. 450-950m). | 0.5 | 3318023 | M/S Shazin Traders, Gaibandha. | 3477130.03 | 15.06.2017 | 24.04.2018 | 100% | 3474570 | 3474570 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-307 | 132673020 | Improvement of Kumidpur Bazar - Badiakhali UP office Road (Ch. 145-645m). | 0.5 | 2908919 | Md. Shahidul Islam, Gaibandha.Liton | 3040018.44 | 15.06.2017 | 24.04.2018 | 60% |  | 1762656 | 1277362.44
Sub-Total = |  | 4 |  |  | 2.004 | 12767840 | 4 | 13371508.14 |  |  | 90% | 6940677 | 11403333 | 1963766.38
Gobindaganj | 22.05.2014 | RDRIIP/GAI/ UN-028 | 132303037 | Improvement of Rakhalburuz U.P(at Dargapara) - Dharmapur bazar at Baradaha KazlaChowduri bari via Sarkerpara Road (Ch. 950-1950m). | 1 | 6219447 | NR Traders | 7240913.13 | 14.10.2014 | 25.01.2015 | 100% | 7237334 | 7237334 |  | Final bill paid
Gobindaganj | 22.05.2014 | RDRIIP/GAI/ UN-029 | 132303020 | Improvement of Salmara U.P - Sonatola Upazila via Heatpur(Uzirer Baiguni-Salmara) Road (Ch. 845-1595m). | 0.75 | 5201076 | The Kanak & Kallal Engineering Workshop | 6271445 | 14.10.2014 | 14.07.2015 | 100% | 6135515.62 | 6135515 |  | Final bill paid
Gobindaganj | 22.05.2014 | RDRIIP/GAI/ UN-030 | 132303033 | Improvement of Kamardaha U.P(Fashitola NHW) - Daridahahat Via Ferusha,Nagarvita ( at Niamatpur) Road (Ch. 00-500m). | 0.5 | 2912781 | Shaharul Islam Titu | 3197467.16 | 14.10.2014 | 14.07.2015 | 100% | 3196072 | 3196072 |  | Final bill paid
Gobindaganj | 12.06.2014 | RDRIIP/GAI/ UN-041 | 132303029 | Improvement of Nakaihat – Ratherbazer via Dhankhunia Road (Ch. 5400-6400m). | 1 | 6785333 | Mony Enterprise Polashbari, Gaibandaha. | 6011330.22 | 07.09.2014 | 10.06.2015 | 100% | 5972361 | 5972361 |  | Final bill paid
Gobindaganj | 02.06.2014 | RDRIIP/GAI/ UN-031 | 132303024 | Improvement of Dorbasta U.P – Katakhali Balua Hat Road via Bishubari (Ch. 1783-2783m). | 1 | 7517239 | M/S Ahsan & Co. | 8231136.53 | 14.10.2014 | 15.07.2015 | 100% | 8225830 | 8225830 |  | Final bill paid
Gobindaganj | 02.06.2014 | RDRIIP/GAI/ UN-032 | 132303009 | Improvement of Gumanigonj U.P - Fulpukuria- Bazar at sreepur via Zarippur (Ch. 3040-4805m). | 1.765 | 10539763 | M/S Milu Traders | 11567728.41 | 14.10.2014 | 14.07.2015 | 100% | 11567141.73 | 11567141 |  | Final bill paid
Gobindaganj | 16.06.2014 | RDRIIP/GAI/ UN-045 | 132303016 | Improvement of Kochashahor U.P - Chandpara hat. ( Dharaikandi-Chandpara via UP office) Road (Ch. 00-750m). | 0.75 | 5087358 | M/S Atkur Rahman | 5590876.72 | 11.09.2014 | 20.06.2015 | 100% | 5590076 | 5590076 |  | Final bill paid
Gobindaganj | 03.11.2014 | RDRIIP/GAI/ UN-093 | 132033010 | Improvement of Gumanigonj UP – Daridaha Hat at Niamatpur Road (293 -2293m). | 2 | 12630127 | M/S Sabbir Traders. | 13616063.21 | 22.02.2015 | 14.01.2016 | 100% | 13614648 | 13614648 |  | Final bill paid
Gobindaganj | 24.11.2014 | RDRIIP/GAI/ UN-113 | 132303007 | Improvement of Rajahar UP at Banaswer – Fulpukuria Bazar at UZR Road (2706 -4726m). | 2 | 10919855 | M/S Atikur Rahman | 11984528.16 | 22.03.2015 | 01.03.2016 | 100% | 11983986 | 11983986 |  | Final bill paid
Gobindaganj | 12.04.2015 | RDRIIP/GAI/ UN-159 | 132303035 | Improvement of Rakhalburuz UP at Amtoli – Mohimagonj at Puntair Kanipara more road via Kurarmath Garzan Road (Ch. 3900-4900m). | 1 | 5900897 | M/S Khandakar Enterprise | 6369300.77 | 18.08.2015 | 17.07.2016 | 100% | 6368033 | 6368033 |  | Final bill paid
Gobindaganj | 31.03.2016 | RDRIIP/GAI/ UN-257 | 132913012 | Improvement of Gumaniganj UP - Kamardaha via Gudaraghat Road (Ch. 00-3180m). | 3.18 | 20705544 | M/S Atikur Rahman, Gobindaganj, Gaibandha. | 21638355 | 29.06.2017 | 12.07.2016 | 100% | 21633963 | 21633963 |  | Final bill paid
Gobindaganj | 00.00.2016 | RDRIIP/GAI/ UN-293 | 132303015 | Improvement of Kochashahor UP - Chandpara Hat Road (Ch. 1350-3350m). | 2 | 13337039 | M/S Atikur Rahman, Gobindaganj, Gaibandha. | 13977548.48 | 30.01.2017 | 22.5.18 | 100% | 13968670 | 13968670 |  | Final bill paid
Sub-Total = |  | 12 |  |  | 16.945 | 107756459 | 12 | 115696692.79 |  |  | 100% | 115493630.35 | 115493629 | 0
Saghata | 27.02.2014 | RDRIIP/GAI/ UN-014 | 132883014 | Improvement of Kachua UP - Kamalerpara Road (Ch. 00-1000m). | 1 | 6223534 | M/S. SR Traders Thanapara, Gaibandaha | 5751958.55 | 06.07.2014 | 22.06.2015 | 100% | 5749426 | 5749426 |  | Final bill paid
Saghata | 03.11.2014 | RDRIIP/GAI/ UN-087 | 132883005 | Improvement of Ghuridha UP Office - Bottola Bazar Road (Ch. 00-1400m). | 1.4 | 12856911 | Md. Khademul Islam Jewel. | 13809947.4 | 05.03.2015 | 14.01.2016 | 100% | 13767820 | 13767820 |  | Final bill paid
Saghata | 03.11.2014 | RDRIIP/GAI/ UN-088 | 132883014 | Improvement of Kachua UP - Kamalerpara UP Road (Ch. 1000-1955m, Effective Length = 945m). | 0.945 | 5890348 | Md. Rafiqul Islam | 6331760.61 | 08.03.2015 | 14.01.2016 | 100% | 6327583 | 6327583 |  | Final bill paid
Saghata | 03.11.2015 | RDRIIP/GAI/ UN-199 | 132883002 | Improvement of Padumshahar UP - Bhutmara Hat via Chakdatia Bazar road (Ch. 00-2080m). | 2.08 | 12595176 | Md. Khademul Islam Jewel | 13209673.51 | 30.03.2016 | 01.03.2017 | 75% |  | 7860544 | 5349129.51
Saghata | 03.11.2015 | RDRIIP/GAI/ UN-200 | 132883002 | Improvement of Padamsohor UP - Bhutmara Hat via Chakdatia Bazar Road (Ch. 2080-3080m). | 1 | 6521429 | Md. Khademul Islam Jewel, Gaibandha. | 6837029.3 | 28.04.2016 | 30.03.2017 | 75% |  | 3895659 | 2941370.3
Saghata | 28.02.2017 | RDRIIP/GAI/ UN-304 | 132883014 | Improvement of Kachua UP - Kamalerpara UP Road (Ch. 3650-4150m). | 0.5 | 3237456 | M/S Shazin Traders | 3389342.44 | 05.06.2017 | 24.04.2018 | 75% |  | 2300000 | 2300000
Sub-Total = |  | 6 |  |  | 6.925 | 47324854 | 6 | 49329711.81 |  |  | 87.5% | 25844829 | 39901032 | 10590499.81
Total = |  | 36 |  |  | 44.034 | 287050702 | 36 | 296995715.21 |  |  | 95.28% | 258895692.35 | 278287003 | 19056619.11
3. Improvement of Village Road:
Sundarganj | 23.02.2015 | RDRIIP/GAI/ VR-174 | 132915057 | Improvement of Ramdakua – Shamopraiarpat Govt. Pry. School via Panchanan Madrasha Road (Ch. 400-1400m). | 1 | 5056777 | SR Traders Thanapara, Gaibandaha | 5177941.67 | 24.06.2015 | 10.05.2016 | 100% | 5174559 | 5174559 |  | Final bill paid
Sundarganj | 23.02.2015 | RDRIIP/GAI/ VR-175 | 132915086 | Improvement of Boali - Samas Road (Ch. 1400-2400m). | 1 | 5393265 | M/S. SR Traders Thanapara, Gaibandaha | 5382121.4 | 24.06.2015 | 15.03.2017 | 100% | 5376640 | 5376640 |  | Final bill paid
Sundarganj | 23.02.2015 | RDRIIP/GAI/ VR-176 | 132914037 | Improvement of Baiddanath (RHD) – Sonarai Road (Ch. 00-2162m). | 2.162 | 12826570 | Md. Abdul Latif Hakkani | 12830107.04 | 29.06.2015 | 05.07.2016 | 100% | 12703826 | 12703826 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ VR-247 | 132914056 | Improvement of Sonarai Baburdighi-Bamondanga FRA Road (Ch. 00-1200m). | 1.2 | 8564135 | RSL Enterprise | 8972157.259 | 08.03.2016 | 01.03.2017 | 100% | 8942644 | 8942644 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ VR-248 | 132914016 | Improvement of Bamondanga (Shashan) RHD - Kandi Road (Ch. 00-700m). | 0.7 | 3841418 | Md. Shoheb Hossain Mona, Gaibandha. | 4022130.21 | 20.03.2016 | 01.03.2017 | 100% | 4019576 | 4019576 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ VR-249 | 132915092 | Improvement of Mondolerhat Near Dines House - Pararhatkhola Road (Mondolerhat - Dhopadanga (Orphanage) Road (Ch. 00-700m). | 0.7 | 4221509 | Md. Abdul Latif Hakkani, Bridge Road, Gaibandha. | 4423645.55 | 08.03.2016 | 01.03.2017 | 100% | 4408982 | 4408982 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-371 | 132915117 | Improvement of Sonaroy - Kandhi (Jamaderdigi) Road (Ch. 00-1000m). | 1 | 7771581 | M/S Shazzad Hossain, Gaibandha. | 8131465.97 | 08.01.2017 | 28.5.18 | 100% | 8125028 | 8125028 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-372 | 132915111 | Improvement of Khanpara Pacca more - Kushtary Rajandronath Old Bari Road (Ch. 1000-2314m). | 1.314 | 12047663 | M/S Ahsan & Co, Gaibandha. | 12550851.49 | 31.10.2016 | 14.11.2017 | 100% | 12534519 | 12534519 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-373 | 132915065 | Improvement of Kashim Bazer (UZR) - Motinmiar Hat Road (Ch. 00-1000m). | 1 | 6895479 | Md. Matlubour Rahman, Gaibandha. | 7236970.12 | 04.12.2016 | 04.12.2017 | 100% | 7213887 | 7213887 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-374 | 132914090 | Improvement of Koikuribazar - Bamondanga (Bridge More) Road (Ch. 00-1000m). | 1 | 6088735 | Md. Shoheb Hossain Mona, Gaibandha. | 6385382.89 | 15.01.2017 | 14.01.2018 | 100% | 6375257 | 6375257 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-375 | 132915008 | Improvement of Chaitantola -Sonarai Road (Ch. 00-1130m). | 1.13 | 6796502 | M/S Shazin Traders, Gaibandha. Mamun | 7129076.28 | 25.10.2016 | 14.11.2017 | 70% |  | 5000000 | 2129076.28
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-376 | 132915082 | Improvement of Zuharuler More-Zhina Via Aftab More Road (Ch. 00-953m). | 0.953 | 5814688 | M/S Shawon Construction. | 6096680.37 | 24.10.2016 | 14.11.2017 | 100% | 6086410 | 6086410 |  | Final bill Paid
Sundarganj | 28.02.2017 | RDRIIP/GAI/ VR-450 | 132915121 | Improvement of Bamondanga (R&H) Luxmipur GC road Indrarpar - Sadhur more Mazumderhat GC Road (Ch. 00-1430m). | 1.43 | 10230033 | Md. Shoheb Hossain Mona, Gaibandha. | 10736097.73 | 14.06.2017 | 19.04.2018 | 100% | 10724934 | 10724934 |  | Final bill paid
Sub-Total = |  | 13 |  |  | 14.589 | 95548355 | 13 | 99074627.979 |  |  | 97.69% | 91686262 | 96686262 | 2129076.28
Sadar | 15.07.2014 | RDRIIP/GAI/ VR-080 | 132244028 | Improvement of Kabiler bazar - Lengabazer Road (Ch. 00-800m). | 0.8 | 5247022 | Md. Abu Sayid Mahabub | 4536862.41 | 12.11.2014 | 12.11.2015 | 100% | 4536862 | 4536862 |  | Final bill paid
Sadar | 15.07.2014 | RDRIIP/GAI/ VR-081 | 132244033 | Improvement of R&H (sadullapur) - Narayanpur ghat Road (Ch. 00-500m). | 0.5 | 2906590 | SR Traders | 2493439.87 | 12.11.2014 | 12.11.2015 | 100% | 2493439 | 2493439 |  | Final bill paid
Sadar | 01.10.2014 | RDRIIP/GAI/ VR-110 | 132245044 | Improvement of Kholahati UP Godarhat Haydar Member House-Zamil Member House Road (Ch. 1700m-2700m). | 1 | 5114138 | Md. Abdul Latif Hakkani, Bridge Road, Gaibandha. | 4441818.33 | 06.01.2015 | 31.05.2015 | 100% | 4440992 | 4440992 |  | Final bill paid
Sadar | 07.06.2016 | RDRIIP/GAI/ VR-356 | 132245005 | Improvement of panchjumma Road-Dariapur Kuptola Road (Ch. 00-500m). | 0.5 | 3734188 | M/S Rahman Traders, Gaibandha. | 3520807.86 | 31.10.2016 | 14.11.2017 | 100% | 2852721 | 2852721 |  | Final bill paid
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-442 | 132244086 | Improvement of Tingacher Tool - Radhakisnopu SKS Inn Ofice Road (Ch. 00-1070m). | 1.07 | 6293342 | Md. Khademul Islam Jewel, Gaibandha. | 6563225.22 | 13.06.2017 | 24.04.2018 | 100% | 6563225 | 6563225 |  | Final bill paid
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-444 | 132245065 | Improvement of Chapadha H/O Abdur Nur - Gaibandha Loxmipur Road via Chapadha Community Clinic Road (Ch. 00-500m). | 0.5 | 2798521 | M/S Shazin Traders, Gaibandha. Sizan | 2936692.53 | 05.06.2017 | 24.04.2018 | 100% | 2936673 | 2936673
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-445 | 132245064 | Improvement of Gaibandha - Dinajpur R&H New Bridge - Manash Regulator Road. (Ch. 00-1000m). | 1 | 5521846 | Khandakar Wahedunnabi Rimu. Gaibandha. | 5895489.16 | 25.05.2017 | 24.04.2018 | 100% | 5889522 | 5889522
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-443 | 132244028 | Improvement of Kabiler bazar - Lengabazer Road (Ch. 800-1800m). | 1 | 6291286 | M/S Shazin Traders, Gaibandha. | 6589951.77 | 05.06.2017 | 24.04.2018 | 100% |  | 6100000 | 489951.77 |  | 486136
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-446 | 132245018 | Improvement of Boali - Ramchandrapur road to Radhakrishnapur Road. (Ch. 400-1400m). | 1 | 5961980 | M/S Ahsan & Co. Gaibandha. | 6246399.68 | 22.05.2017 | 24.04.2018 | 100% | 6244386 | 6244386 |  | Final bill paid
Sadar | 27.03.2017 | RDRIIP/GAI/ VR-543 | 132245063 | Improvement of Pearapur GPS - Kabla Sha Mazar via Abbaus Uddin Grave Yeard Road (Ch. 00-1100m). | 1.1 | 7274994.55 | M/S Ahsan & Co. Gaibandha. | 7601217.64 | 19.06.2017 | 26.06.2018 | 100% | 7597260 | 7597260 |  | Final bill paid
Sadar | 03.05.2017 | RDRIIP/GAI/ VR-557 | 132245062 | Improvement of Manik Patni -North Simultari School via South Simultari School Road (Ch. 00-500m). | 0.5 | 2940893.21 | Md.Abu Bakar Siddique, Gaibandha. Sizan | 3082052.12 |  |  | 30% |  |  | 3082052.12 | Problematic | 1580000
|  | 11 |  |  | 8.97 | 54084800.76 | 11 | 53907956.59 |  |  | 93.64% | 43555080 | 49655080 | 3572003.89
Sadullapur | 27.02.2014 | RDRIIP/GAI/ VR-037 | 132825074 | Improvement of Sadullapur - Dhaper hat pacca raod – Khordoruhia Gor Mondop Road (Ch. 355-890m). | 0.535 | 3052186 | M/S Sadin Traders | 2660615.74 | 14.07.2014 | 22.06.2015 | 100% | 2643453 | 2643453 |  | Final bill paid
Sadullapur | 10.07.2014 | RDRIIP/GAI/ VR-079 | 132824060 | Improvement of Enaetpur Bazar – Mohishbandi Bazar road (Enaetpur Srikola road to Principal Tazul Islam House road via Dula Munshi House (Ch. 00-500m). | 0.5 | 2878678 | Md. Mahomudunnabi | 2355098.17 | 30.06.2016 | 30.06.2016 | 100% | 2354816 | 2354816 |  | Final bill paid
Sadullapur | 25.06.2015 | RDRIIP/GAI/ VR-218 | 132825021 | Improvement of Kantanagar Bazar – Wapda Embankment Road (Ch. 00-500m). | 0.5 | 3300291 | Md. Ferdous Bari | 2979597.4 | 18.10.2015 | 30.06.2016 | 100% | 2975740 | 2975740 |  | Final bill paid
Sadullapur | 07.06.2016 | RDRIIP/GAI/ VR-354 | 132824062 | Improvement of Iddrakpur Bazar- Kishamot Sherpur GPS Road (Ch. 00-500m). | 0.5 | 3368852 | M/S Rahman Traders, Gaibandha. | 2936190 | 31.10.2016 | 14.11.2017 | 100% | 2933958 | 2933958 |  | Final bill paid
Sadullapur | 07.06.2016 | RDRIIP/GAI/ VR-355 | 132824007 | Improvement of Kazibari sontola - sarbazar via badlagari Road (Ch. 00-500m). | 0.5 | 3150710 | M/S Rahman Traders, Gaibandha. | 2876323.35 | 31.10.2016 | 14.11.2017 | 100% | 2869600 | 2869600 |  | Final bill paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-431 | 132824015 | Improvement of Dhaperhat Madargonj G.C Rd at Ali Nagar - Madarer ghat Road (Ch. 00-500m). | 0.5 | 3540201 | M/S Md. Farhadul Haque, Gaibandha.Ferdous | 3703503.43 | 12.06.2017 | 24.04.2018 | 75% |  | 2325000 | 1378503.43 |  | 1337077
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-432 | 132824038 | Improvement of Gaibandha - Sadullapur Road - Dakhin Manduar Kheya Ghat via Gorer math Road (Ch. 1727-2727m). | 1 | 6254844 | M/S. Md. Rabiul Alam (Bulbul), Rangpur. | 6536111.2 | 08.06.2017 | 24.04.2018 | 100% | 6535869 | 6535869 |  | Final bill paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-433 | 132824061 | Improvement of Sadullapur - Madargonj GC Road near Brack Office - Choto Doulotpur Pucca road via Choto Doulotpur GPS road (Ch. 00-1000m). | 1 | 6536333 | Md. Mahomudun Nobi, Rangpur. | 6132194.22 | 19.06.2017 | 24.04.2018 | 20% |  | 600000 | 5532194.22 | Problematic | 459000
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-434 | 132824062 | Improvement of Idrackpur Bazar - Khisamot Sheerpur GPS via Isubpur GPS Road (Ch. 00-1508m). | 1.008 | 6502350 | M/S Ahsan & Co. Gaibandha. | 6785260.48 | 22.05.2017 | 24.04.2018 | 100% | 6782749 | 6782749 |  | Final bill paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-435 | 132824027 | Improvement of Idilpur Govt. Pry.school - Area of Palashbari via Mohipur bazar Road (Ch. 00-500m). | 0.5 | 3070522 | M/S Md. Farhadul Haque, Gaibandha. | 3212298.17 | 06.06.2017 | 24.01.2018 | 20% |  | 300000 | 2912298.17 | Problematic
Sub-Total = |  | 10 |  |  | 6.543 | 41654967 | 10 | 40177192.16 |  |  | *******--------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------- | 27096185 | 30321185 | 9822995.82
Palalshbari | 27.02.2014 | RDRIIP/GAI/ VR-036 | 132674043 | Improvement of Harinmari South Bas stand NHW - Hospital via Napiter Bari Road (Ch. 00-560m). | 0.56 | 3112049 | Mony Enterprise Polashbari, Gaibandaha. | 2733547.34 | 06.07.2014 | 22.06.2015 | 100% | 2733547 | 2733547 |  | Final bill paid
Palalshbari | 07.08.2016 | RDRIIP/GAI/ VR-380 | 132674020 | Improvement of Palashbari -Gaibandha Gramin Bank - Shuigram Road (Ch. 00-500m). | 0.5 | 3032171 | M/S Surovi Enterprise | 3179101.1 | 24.10.2016 | 14.11.2017 | 100% | 3177260 | 3177260 |  | Final bill paid
Palalshbari | 07.08.2016 | RDRIIP/GAI/ VR-381 | 132674086 | Improvement of Kishargari Road at Palashbari Karigori College - Ghoraghat Road via Andua Road (Ch. 00-500m). | 0.5 | 3344183 | M/S Surovi Enterprise | 3536788.82 | 24.10.2016 | 14.11.2017 | 100% | 3500106 | 3500106 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-436 | 132674048 | Improvement of South Vogabanpur NHW - Bashudebpur Road (Ch. 00-503m). | 0.503 | 3675941 | M/S BB Traders, Gaibandha. | 3841120.96 | 19.06.2017 | 24.04.2018 | 100% | 3838766 | 3838766 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-437 | 132675114 | Improvement of Bari Horinmari Mouza near Dreamland - Moazem Sorker House Road (Ch. 00-625m). | 0.625 | 3745609 | M/S New Pavel Auto | 3922417.55 | 04.06.2017 | 24.04.2018 | 25% |  | 2516000 | 1406417.55
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-438 | 132674058 | Improvement of Bengulia GPS - Tangra via Mondol Bari Road (Ch. 1000-2000m). | 1 | 6446164 | Md. Farhadul Haque, Gaibandha. | 6742475.56 | 16.05.2017 | 14.04.2018 | 100% | 6738201 | 6738201 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-439 | 132675117 | Improvement of Ghorobandha Chorasta west side of Bridge -Near house of Fazlu Master Purbo Balabamuniya Road (Ch. 00-500m). | 0.5 | 3264414 | Md. Ziaul Alam Dales kamal | 3410559.79 | 06.06.2017 | 24.04.2018 | 100% |  | 2700000 | 710559.79 |  | 610559
Palalshbari | 24.05.2017 | RDRIIP/GAI/ VR-561 | 132674030 | Improvement of Kutirghat Bridge - Kalitala Bazar Road (Ch. 00-500m). | 0.5 | 4739881.39 | M/S Shazin Traders, Gaibandha. | 4974414.92 | 12-10-17 | 18-09-2018 | 35% |  | 1315000 | 3659414.92
Palalshbari | 14.11.2017 | RDRIIP/GAI/ VR-562 | 132675119 | Improvement of Rangpur - Bogra NHW near Sugar Center Ruhul Amin house Road (Ch. 00-190m). | 0.19 | 911803.34 | Wahedunnobi rimu | 911803.34 | 12-5-18 | 14-11-18 | 70% |  | 461982 | 449821.34
Sub-Total = |  | 9 |  |  | 4.878 | 32272215.73 | 9 | 33252229.38 |  |  | 81.11% | 19987880 | 26980862 | 6226213.6
Gobindaganj | 02-06-2014 | RDRIIP/GAI/ VR-053 | 132304207 | Improvement of Kochashahor Kamar bari-Singha road (Ch. 00-1000m). | 1 | 5798328 | M/S Atikur Rahman | 6483470.95 | 14.10.2014 | 20.10.2015 | 100% | 6478719 | 6478719 |  | Final bill paid
Gobindaganj | 02-06-2014 | RDRIIP/GAI/ VR-054 | 132304141 | Improvement of Talikkanupur UP at NHW Samaspara-Jamalpur hat road (Ch. 1680-2680m). | 1 | 5883542 | M/S Shihab Construction | 6460946.52 | 14.10.2014 | 14.07.2015 | 100% | 6459268 | 6459268 |  | Final bill paid
Gobindaganj | 16-06-2014 | RDRIIP/GAI/ VR-058 | 132304214 | Improvement of Ashkur - Farusha raod ( Katabri-Tulot Road to Jugipara poultry Firm) Road (Ch. 00-500m). | 0.5 | 2845181 | M/S Shihab Construction | 2848752.59 | 09.09.2014 | 15.06.2015 | 100% | 2848612 | 2848612 |  | Final bill paid
Gobindaganj | 16-06-2014 | RDRIIP/GAI/ VR-059 | 132304176 | Improvement of Katabari UP at Katgor Madrasha - Polupara Ghat(Ghoraghat Road-Katgor Madrasha Fakirganj Road (Ch. 00-415m). | 0.415 | 2550917 | M/S Salama Traders | 2240474.5 | 09.09.2014 | 15.06.2015 | 100% | 2238151 | 2238151 |  | Final bill paid
Gobindaganj | 19-08-2014 | RDRIIP/DIN/ VR-092 | 132304077 | Improvement of Gopalpur – Puntair road (Ch. 00-1250m) (Effective Length = 1232m). | 1.232 | 7579128 | Md. Abdul Latif Hakkani, Bridge Road, Gaibandha. | 7046581.12 | 28.04.2015 | 28.01.2016 | 100% | 7565571 | 7565571 |  | Final bill paid
Gobindaganj | 12.04.2015 | RDRIIP/DIN/ VR-203 | 132304034 | Improvement of Kamorpur Hindopara – R&H Tatultola Mazar Road (Ch. 00-825m). | 0.825 | 4779180 | Md. Mukitur Rahman Rafi | 5159838.35 | 18.08.2015 | 17.07.2016 | 100% | 5157247 | 5157247 |  | Final bill paid
Gobindaganj | 12.04.2015 | RDRIIP/DIN/ VR-204 | 132304136 | Improvement of NHW Nundaha Bridge - Mirapara Road (Ch. 00-500m). | 0.05 | 3059682 | Md. Mikaddesh Ali Babu | 3301317.91 | 18.08.2015 | 17.07.16 | 100% | 3299839 | 3299839 |  | Final bill paid
Gobindaganj | 23.02.2016 | RDRIIP/GAI/ VR-276 | 132304123 | Improvement of Nakai UP - Horinabari Bazar via Dumargach Road (Ch. 1400-1900m). | 0.5 | 3080024 | M/S Shihab Construction, Gobindaganj, Gaibandha. | 3222108.97 | 17.05.2016 | 30.11.2016 | 100% | 3220305 | 3220305 |  | Final bill paid
Gobindaganj | 23.02.2016 | RDRIIP/GAI/ VR-277 | 132304179 | Improvement of Nasarabad School - Bagunbari Road Chandpara hat (Nashirabad village) Road (Ch. 00-500m). | 0.5 | 2868584 | Shaharul Islam Titu, Gobindaganj, Gaibandha. | 3000487.24 | 22.05.2016 | 30.11.2016 | 100% | 2997903 | 2997903 |  | Final bill paid
Gobindaganj | 10.04.2016 | RDRIIP/GAI/ VR-322 | 132305125 | Improvement of NHW Avairampur - H/O Niru Doctor Road (Ch. 00-1260m). | 1.26 | 8015033 | Md. Rokonuzzaman Prodhan, Gobindaganj, Gaibandha. | 8410279.29 | 25.10.2016 | 14.11.2017 | 100% | 8401299 | 8401299 |  | Final bill paid
Gobindaganj | 18.08.2016 | RDRIIP/GAI/ VR-387 | 132304174 | Improvement of Fulbari UP NHW at Fulbari - Boalia Road (Ch. 00-1385m). | 1.385 | 8661736 | M/S NR Traders, Gobindaganj, Gaibandha. | 9081466.09 | 29.11.2016 | 19.11.2017 | 100% | 9079058 | 9079058 |  | Final bill Paid
Gobindaganj | 24.08.2016 | RDRIIP/GAI/ VR-389 | 132304019 | Improvement of Chitipara at (Charmatha More) - Teghora Road via Satal Para Bhutgari Kishi College Road (Ch. 2500-3000m). | 0.5 | 2866270 | Shaharul Islam Titu, Gobindaganj, Gaibandha. | 3006674.55 | 05.12.2016 | 19.11.2017 | 100% | 3002819.05 | 3002819.05 |  | Final bill Paid
Gobindaganj | 23.10.2016 | RDRIIP/GAI/ VR-393 | 132304152 | Improvement of Kalitola Bazar - Fashitola (Kata) via Golapara Madrasha Road (Ch. 00-1220m). | 1.22 | 7308751 | Md. Mukitur Rahman Rafi, Gobindangan, Gaibandha. | 7661127.1 | 16.01.2017 | 18.01.2018 | 100% | 7657837 | 7657837 |  | Final bill Paid
Gobindaganj | 00.00.2016 | RDRIIP/GAI/ VR-394 | 132304046 | Improvement of Masta - Chaprigonj via Kamardaha School, Clinic Road (Ch. 2825-3825m). | 1 | 6314448 | Md. Atikur Rahman, Gobindaganj, Gaibandha. | 6620203.22 | 30.01.2017 | 6.4.18 | 100% | 7416353 | 7416353 |  | Final bill paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-403 | 132305141 | Improvement of Faiska - Khurshal (Birat road at Feshka - Gonar Parul - Islampur) Road (Ch. 00-1185m). | 1.185 | 8664423 | M/S Khandakar Enterprise, Gobindaganj, Gaibandha. | 8885660.66 | 09.04.2017 | 11.03.2018 | 100% | 8885416 | 8885416 |  | Final bill Paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-441 | 132305282 | Improvement of Jagonathpur Senior Madrasha - Fashitola Pacca Road (at Dharma) (Ch. 00-500m). | 0.5 | 3429862 | M/S. Sabbir Traders, Gobindaganj, Gaibandha. | 3591574.21 | 11.06.2017 | 24.04.2018 | 100% | 3589668 | 3589668 |  | Final bill Paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-457 | 132305168 | Improvement of Shakhahar UP - Fupukuria road - Khurshal Mosque Road (Ch. 00-350m). | 0.35 | 2046580 | Md. Mokaddesh Ali Badu, Gobindaganj, Gaibandha. | 2142502.63 | 31.05.2017 | 15.05.2018 | 100% | 2113971 | 2113971 |  | Final bill paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-458 | 132305009 | Improvement of Bogulagari Eidgha (CARE road) - Satana Balua Road (Ch. 1000-2030m). | 1.03 | 7361931 | Md. Mokaddesh Ali Badu, Gobindaganj, Gaibandha. | 7710655.41 | 17.05.2017 | 24.04.2018 | 100% | 7706750 | 7706750 |  | Final bill paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-459 | 132304027 | Improvement of Fashitola - Kayaganj Road (Ch. 2100-3100m). | 1 | 6483362 | Md. Ziaul Islam Methu | 6789578.63 | 08.06.2017 | 24.04.2018 | 100% | 6778905 | 6778905 |  | Final bill paid
Gobindaganj | 19.03.2017 | RDRIIP/GAI/ VR-523 | 132304150 | Improvement of Guga - Fulpukuria via Kalitola Road (Ch. 600-1250m). | 0.665 | 3931654 | Md. Shaharul Islam Titu, Gobindaganj, Gaibandha. | 4119190.83 | 15.06.2017 | 26.06.2018 | 100% | 4117308 | 4117308 |  | Final bill paid
Gobindaganj | 3 | RDRIIP/GAI/ VR-545 | 132305082 | Improvement of Satailbatail - Bara Sohagi WDB Road (Ch. 715-1500m). | 0.785 | 6844660.29 | M/S Shihab Construction, Gobindaganj, Gaibandha. | 7171734.22 | 05.07.2017 | 05.07.2018 | 100% | 7159507 | 7159507 |  | Final bill paid
Gobindaganj | 03.05.2017 | RDRIIP/GAI/ VR-555 | 132305247 | Improvement of Darbasta - Bogulagari Bazar Road -Kalitola High School via Zabber master house Road (Ch. 00-990m). | 0.99 | 6914151.21 | M/S Khandakar Enterprise. Gobindaganj, Gaibandha. | 7246079.2 | 10.07.2017 | 05.07.2018 | 100% | 7243983 | 7243983 |  | Final bill paid
Gobindaganj | 03.05.2017 | RDRIIP/GAI/ VR-556 | 132305058 | Improvement of Gopinathpur Bridge - Devpur Road via Singiani Govt. Primary School Road (Ch. 00-500m). | 0.5 | 3304399.95 | M/S Milu Traders. Gobindaganj, Gaibandha. | 3460316.24 | 10.07.2018 | 05.07.2019 | 100% | 3459498 | 3459498 |  | final bill paid
Sub-Total = |  | 23 |  |  | 18.392 | 120591827.45 | 23 | 125661020.43 |  |  | 100% | 126877987.05 | 126877987.05 | 0
Saghata | 03.04.2014 | RDRIIP/GAI/ VR-046 | 132885039 | Improvement of Badiakhali – Bonarpara GC – Raghobpur Telian Road (Ch. 00-1765m). | 1.765 | 2294099.98 | Md. Khaliur Rahman | 2294099.98 | 15.07.14 | 22.12.2014 | 100% | 2294099 | 2294099 |  | Final bill paid
Saghata | 13.06.2016 | RDRIIP/GAI/ VR-046(R) | 132885039 | Remaining work of Badiakhali – Bonarpara GC – Raghobpur Telian Road (Ch. 00-1765m). |  | 4918770 | Md. Khaybor Rahman | 5160383.87 | 30.10.2016 | 24.10.2017 | 100% | 5158307 | 5158307 |  | Final bill paid
Saghata | 23.07.2014 | RDRIIP/GAI/ VR-085 | 132884001 | Improvement of Bonarpara Railway stall – Kasiabari Ghat Road (Ch. 00-2190m). | 2.19 | 9794244 | Md. Khademul Islam Jewel | 8404225.32 | 11.11.2014 | 11.11.2015 | 100% | 8402915 | 8402915 |  | Final bill paid
Saghata | 05.11.2014 | RDRIIP/GAI/ VR-115 | 132885122 | Improvement of Bhutmara Bazar – Alai River near H/O Motin Engineer Road (1000 -1250m). | 0.25 | 1699501 | Md. Shamim Ahammed Mondal. | 1826695.36 | 08.03.2015 | 15.10.2015 | 100% | 1826691 | 1826691 |  | Final bill paid
Saghata | 05.11.2014 | RDRIIP/GAI/ VR-116 | 132885160 | Improvement of Bajit Nagar Bazar Charpra Adarsa Gram Road (1000 -1600m). | 0.6 | 3252701 | Md. Sahidul Islam. | 3480257.43 | 05.03.2015 | 14.10.2015 | 100% | 3479466 | 3479466 |  | Final bill paid
Saghata | 24.11.2014 | RDRIIP/GAI/ VR-131 | 132884019 | Improvement of Mandura - Bharatkhali Road (Ch. 00-1830m). | 1.83 | 8345043 | The Kanak & Kallal Engineering Workshop | 8325579 | 28.04.2015 | 28.01.2016 | 100% | 8315746 | 8315746 |  | Final bill paid
Saghata | 11.12.2014 | RDRIIP/GAI/ VR-136 | 132884026 | Improvement of Bonarpara – Saghata - Bilbosta Road (Ch. 1500-2380m). | 0.88 | 3930832 | Md. Rafiqul Islam | 3631640.96 | 15.03.2015 | 30.11.2015 | 100% | 3630906 | 3630906 |  | Final bill paid
Saghata | 06.01.2015 | RDRIIP/GAI/ VR-145 | 132884065 | Improvement of Bangla Bazar - Chorkata Bridge Road (Ch. 585-1085m). | 0.5 | 2488656 | M/S SR Traders | 2307619.72 | 23.04.2015 | 14.01.2016 | 100% | 2305132 | 2305132 |  | Final bill paid
Saghata | 06.01.2015 | RDRIIP/GAI/ VR-146 | 132244038 | Improvement of Buliarber GPS – Kamalerpara – Folia Pucca (Folia - Panchpur (Fokir Para) Road (Ch. 1780-2380m). | 0.6 | 2999848 | M/S SR Traders | 2810785.4 | 23.04.2015 | 15.06.2017 | 75% |  | 1834687 | 976098.4
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-178 | 132884055 | Improvement of Bottola Bazar - Mothorpara (Bottola – Mothorpara west) Road (Ch. 00-500m). | 0.5 | 2886833 | Md Shamim Ahammed Mondol | 2674137.33 | 28.06.2015 | 15.03.2017 | 100% | 2668841 | 2668841 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-179 | 132884022 | Improvement of Mafurjan Road – Badiakhali - Saghata R&H Road (Ch. 00-500m). | 0.5 | 2108297 | Md. Touhidul Islam | 1999515.056 | 28.06.2015 | 10.05.2016 | 100% | 1997940 | 1997940 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-180 | 132884007 | Improvement of Kachua Hat Sluice Gate – Kalapani Embankment Road (Ch. 00-750m). | 0.75 | 3751196 | Md Shamim Ahammed Mondol | 3688869.9 | 23.06.2015 | 10.05.2016 | 100% | 3685695 | 3685695 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-181 | 132884011 | Improvement of Muktinagar – Boanarpara - Bharatkhali Road (Ch. 00-600m). | 0.6 | 2605349 | M/S SR Traders | 2601519.69 | 23.06.2015 | 15.05.2016 | 100% | 2596697 | 2596697 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-182 | 132884008 | Improvement of BWDB Embankment – Bogarvita via Bosonterpara Road (Ch. 00-500m). | 0.5 | 2468084 | Md. Khoybor Rahman | 2365758.77 | 23.06.2015 | 10.05.2016 | 100% | 2363833 | 2363833 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-183 | 132884059 | Improvement of Badiakhali – Jumarbari – Jordoba Road (Ch. 3390-4115m, Effective Length = 717m). | 0.717 | 3919220 | The Kanak & Kallal Engineering Workshop | 4206245.42 | 05.07.2015 | 10.05.2016 | 100% | 4203460 | 4203460 |  | Final bill paid
Saghata | 07.08.2015 | RDRIIP/GAI/ VR-379 | 132884002 | Improvement of House of Mozammel - Bonarpara BRAC office Road (Ch. 00-600m). | 0.6 | 2904478 | SR Traders, Gaibandha. | 3021897.46 | 02.11.2016 | 14.11.2017 | 100% | 3020291 | 3020291 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-447 | 132884010 | Improvement of Beltali Pry.School - Kalapani Bridge Road (Ch. 2820-3850m). | 1.03 | 7476064 | SR Traders, Thana para, Gaibandha. | 7830723.16 | 08.06.2017 | 24.04.2018 | 100% | 7820468 | 7820468
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-448 | 132884036 | Improvement of Sadhur Assram RHD - Padum shahar Malipara Road (Ch. 1500-2000m). | 0.5 | 3193503 | Md. Rafiqul Islam | 3349952.92 | 24.05.2017 | 24.05.2018 | 100% | 3346075 | 3346075 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-449 | 132885185 | Improvement of Poragram main Road - Poragram Mondol bari Jame Mosque Road (Ch. 00-470m). | 0.47 | 2337112 | M/S Shazin Traders, Gaibandha.mirza rafiq | 2446796.16 | 08.06.2017 | 24.04.2018 | 20% |  |  | 2446796.16 | Problematic
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-451 | 132884039 | Improvement of Gorerpara - Kamalerpara Bazar Road (Ch. 00-500m). | 0.5 | 3529192 | Md. Amirul Islam Bablu, Bonarpara, Gaibandha. | 3687953.3 | 05.06.2017 | 24.04.2018 | 75% |  | 1600000 | 2087953.3
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-452 | 132884065 | Improvement of Kachuahat FRB at Bangla bazar - Chorkatha bridge Road (Ch. 1085-1585m). | 0.5 | 3342894 | M/S SR Traders, Thanapara, Gaibandha | 3502045.47 | 08.06.2017 | 24.04.2018 | 35% |  | 1349598 | 2152447.47 | Problematic
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-453 | 132884061 | Improvement of Trimohoni Khayaghat - Ullasonatola bazar Road (Ch. 1800-2300m). | 0.5 | 3138600 | Mirza Rafiqul Alam | 3282003.65 | 08.06.2017 | 24.04.2018 | 40% |  | 285937 | 2996066.65 | Problematic | 1750000
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-454 | 132885170 | Improvement of Kukrahat - Katlamari Bazar Road (Ch. 00-500m). | 0.5 | 2646297 | M/S FRB Enterprise | 2764107.83 | 08.06.2017 | 24.04.2018 | 100% | 2764101 | 2764101 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-455 | 132885196 | Improvement of Mofurjan Foot Bridge - Badiakhali Kazi bari Road (Ch. 00-500m). | 0.5 | 3021437 | Md. Azol Hauq, Gaibandha. | 3157362.99 | 18.05.2017 | 24.04.2018 | 100% | 3157626 | 3156626 |  | Final bill Paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-456 | 132885204 | Improvement of Bati Mousa Bati Bridge - Moimontopur Madrasha Road (Ch. 00-500m). | 0.5 | 3171480 | Md. Amirul Islam Bablu, Bonarpara, Gaibandha. | 3313705.81 | 05.06.2017 | 24.04.2018 | 100% |  | 1900000 | 1413705.81
Saghata | 19.03.2017 | RDRIIP/GAI/ VR-524 | 132885219 | Improvement of Uttar Satalia H/O Sattar - WAPDA Embankment Road (Ch. 00-730m). | 0.73 | 5353815.48 | Md. Farhadul Haque, Gaibandha. | 5610786.1 | 13.06.2017 | 26.06.2018 | 50% |  | 2200000 | 3410786.1
Sub-Total = |  | 26 |  |  | 18.512 | 97577546.46 | 26 | 97744668.056 |  |  | 88.27% | 73038289 | 82207511 | 15483853.89
Fulchari | 03.11.2014 | RDRIIP/GAI/ VR-112 | 132214001 | Improvement of H/O Delwar Hossain - Chunakandi khea ghat Road (Ch. 00-500m). | 0.5 | 4264533 | Md. Shoheb Hossain Mona. | 4582976.52 | 22.02.2015 | 14.10.2015 | 100% | 4575886 | 4575886 |  | Final bill paid
Fulchari | 24.11.2014 | RDRIIP/GAI/ VR-132 | 132214016 | Improvement of Purba salua H/O Mozibar - H/O Osman munsi Road (Ch. 00-500m). | 0.5 | 2841251 | Md. Rashed Khan Manan | 2538201.01 | 11.03.2015 | 30.11.2015 | 100% | 2538200 | 2538200 |  | Final bill paid
Fulchari | 24.11.2014 | RDRIIP/GAI/ VR-133 | 132214019 | Improvement of Kator Govt . Primary school - Purba udakhali H/O Akbar hossain Road (Ch. 600-1100m). | 0.5 | 2515839 | Md. Rashed Khan Manan | 2246895.89 | 11.03.2015 | 30.11.2015 | 100% | 2246895 | 2246895 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-170 | 132214016 | Improvement of Purba Salua H/O Mozibar - H/O Osman munsi Road (Ch. 500-1000m). | 0.5 | 2765005 | Md. Rashed Khan Manan | 2339922.74 | 29.06.2015 | 06.04.2016 | 100% | 2271309 | 2271309 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-171 | 132214019 | Improvement of Kator Govt . Primary school - Purba udakhali H/O Akbar hossain Road (Ch. 00-600m). | 0.6 | 3434284 | Md. Rashed Khan Manan | 2928139.96 | 29.06.2015 | 06.04.2016 | 100% | 2443478 | 2443478 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-172 | 132214002 | Improvement of WAPDA Embankment near Chawdharypara - Mashervita Mosque Road (Ch. 2650-3250m). | 0.6 | 3100970 | Md. Rashed Khan Manan | 2672001.11 | 29.06.2015 | 06.04.2016 | 100% | 2641998 | 2641998 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-173 | 132215102 | Improvement of Singra road - Gonvori Road (Ch. 00-170.00m). | 0.17 | 1087691 | Md. Rashed Khan Manan | 907401.95 | 29.06.2015 | 06.04.2016 | 100% | 901265 | 901265 |  | Final bill paid
Sub-Total = |  | 7 |  |  | 3.37 | 20009573 | 7 | 18215539.18 |  |  | 100% | 17619031 | 17619031 | 0
Total = |  | 99 |  |  | 75.254 | 461739285.4 | 99 | 468033233.775 |  |  | 92.32% | 399860714.05 | 430347918.05 | 37234143.48
Total Road = |  | 148 |  |  | 139.229 | 900655002.4 | 148 | 911093567.895 |  |  | 95.23% | 763100303.4 | 847087853.05 | 63431820.95
4. Construction of Bridge/Culvert on Upazila road:
Saghata | 28.03.2016 | RDRIIP/GAI/ BR-016 | 132882001 | Construction of 39 m Long RCC Girder Bridge on Badiakhali R&H Road - Jumarbari GC Road at Ch.15403m. | 39 | 20074854 | AH-KJ (JV) Gaibandha. | 17079068.11 | 17.07.2016 | 31.12.2017 | 100% | 17018860 | 17018860 |  | Final bill paid
Sub-Total = |  | 1 |  |  | 39 | 20074854 | 1 | 17079068.11 |  |  | 100% | 17018860 | 17018860 | 0
Total = |  | 1 |  |  | 39 | 20074854 | 1 | 17079068.11 |  |  | 100% | 17018860 | 17018860 | 0
5. Construction of Bridge/Culvert on Union road:
Sadar | 21.10.2015 | RDRIIP/GAI/ BR-005 | 132243016 | Construction of 100.00m Long RCC Girder Bridge over Ghagoat River on Gidari UP Office - Dariapur GC (Badshar Ghat) Road at Ch.3465m | 100 | 53658135 | M/S Basundhara R.K Road, Ghoshpara, Kurigram Sadar, Kurigram. | 46693694.09 | 06.03.2016 | 13.07.2017 | 65% |  | 29872574 | 16821120.09
Sub-Total = |  | 1 |  |  | 100 | 53658135 | 1 | 46693694.09 |  |  | 65% | 0 | 29872574 | 16821120.09
Total = |  | 1 |  |  | 100 | 53658135 | 1 | 46693694.09 |  |  | 65% | 0 | 29872574 | 16821120.09
6. Construction of Bridge/Culvert on Village road:
Sundarganj | 30.05.2016 | RDRIIP/GAI/ BR-021 | 132914097 | Construction of 45.00m Long RCC Girder Bridge over Lahangga Channel on Kalitola (RHD) – Bamondangha South rail gate (Bypass) raod at Ch. 700.00m. | 45 | 20975135 | M/S Anisur Rahman Chowdhury & S.M Rashed Hossain JV, Rangpur. | 17722348 | 30.10.2016 | 14.05.2018 | 45% |  | 10046855 | 7675493
Sub-Total = |  | 1 |  |  | 45 | 20975135 | 1 | 17722348 |  |  | 45% | 0 | 10046855 | 7675493
Total = |  | 1 |  |  | 45 | 20975135 | 1 | 17722348 |  |  | 45% | 0 | 10046855 | 7675493
Total Bridge/Culvert = |  | 3 |  |  | 184 | 94708124 | 3 | 81495110.2 |  |  | 70% | 17018860 | 56938289 | 24496613.09
7.Road maintenance works:
Sundarganj | 25.07.2016 | RDRIIP/GAI/ M-027 | 132913001 | Maintenance of Mirgonj Mazipara (More) - Tarapur Road (Ch. 00-3609m). | 3.609 | 10293615 | M/S Ovijatrik Construction, Jamalpur. | 8498099.8 | 02.11.2016 | 24.10.2016 | 100% | 8486155 | 8486155
Sub-Total = |  | 1 |  |  | 3.609 | 10293615 | 1 | 8498099.8 |  |  | 100% | 8486155 | 8486155 | 0
Saghata | 23.10.2014 | RDRIIP/GAI/ M-001 | 132882001 | Maintenance of Badiakhali Bridge R&H – Jumarbari Hat GC Road (Ch. 00-3575m). | 3.575 | 15870180 | Md. Abdul Latif Hakkani. | 17108127.2 | 24.02.2015 | 28.01.2016 | 100% | 17077863 | 17077863 |  | Final bill Paid
Saghata | 23.10.2014 | RDRIIP/GAI/ M-002 | 132882001 | Maintenance of Badiakhali Bridge R&H – Jumarbari Hat GC Road (Ch. 4600-8121m). | 3.521 | 13850254 | Md. Khalilur Rahman. | 14923519.77 | 10.03.2015 | 28.01.2016 | 100% | 14905949 | 14905949 |  | Final bill Paid
Sub-Total = |  | 2 |  |  | 7.096 | 29720434 | 2 | 32031646.97 |  |  | 100% | 31983812 | 31983812 | 0
Fulchari | 26.10.2014 | RDRIIP/GAI/ M-003 | 132212003 | Maintenance of Fulchari Upazila H.Q - Modenerpara R&H Road.(Ch.00-330m & Ch.3611m- 6180m). | 2.899 | 7222580 | Md. Rashed Khan Manan. | 7764259.14 | 03.05.2015 | 29.10.2015 | 100% | 7758295 | 7758295 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 2.899 | 7222580 | 1 | 7764259.14 |  |  | 100% | 7758295 | 7758295 | 0
Gobindaganj | 06.08.2015 | RDRIIP/GAI/ M-004 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 00-3000m). | 3 | 6148462 | Md. Khademul Islam Jewel. | 5372701.65 | 10.11.2015 | 30.05.2016 | 100% | 5372273 | 5372273 |  | Final bill Paid
Gobindaganj | 06.08.2015 | RDRIIP/GAI/ M-005 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 3000-5150m & 7120-7400m). | 2.43 | 6158493 | Md. Khademul Islam Jewel. | 5372676 | 10.11.2015 | 30.05.2016 | 100% | 5283001 | 5283001 |  | Final bill Paid
Gobindaganj | 06.08.2015 | RDRIIP/GAI/ M-006 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 7400-10400m). | 3 | 7323302 | Md. Khademul Islam Jewel. | 6341565.17 | 10.11.2015 | 30.05.2016 | 100% | 6327877 | 6327877 |  | Final bill Paid
Gobindaganj | 23.10.2014 | RDRIIP/GAI/ M-007 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 10400-12750m). | 2.35 | 5987891 | Md. Khademul Islam Jewel. | 5192466.58 | 10.11.2015 | 30.05.2016 | 100% | 5187895 | 5187895 |  | Final bill Paid
Sub-Total = |  | 4 |  |  | 10.78 | 25618148 | 4 | 22279409.4 |  |  | 100% | 22171046 | 22171046 | 0
Sadar | 25.11.2015 | RDRIIP/GAI/ M-014 | 132242001 | Maintenance of Gaibandha - Laxmipur Road (Ch. 00-5500m). | 5.5 | 11519318 | Md. Abdul Latif Hakkani. | 12064159.04 | 08.03.2016 | 01.03.2017 | 100% | 12049125 | 12049125 |  | Final bill Paid
Sadar | 25.11.2015 | RDRIIP/GAI/ M-015 | 132242001 | Maintenance of Gaibandha - Laxmipur Road (Ch. 5500-11760m). | 6.26 | 11660550 | Md. Saidur Rahaman | 12212062.91 | 08.03.2016 | 01.03.2017 | 100% | 12197906 | 12197906 |  | Final bill Paid
Sub-Total = |  | 2 |  |  | 11.76 | 23179868 | 2 | 24276221.95 |  |  | 100% | 24247031 | 24247031 | 0
Total = |  | 10 |  |  | 36.144 | 96034645 | 10 | 94849637.26 |  |  | 100% | 94646339 | 94646339 | 0
8. Off pavement road maintenance (LCS women):
Sundarganj | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi my›`iMÄ Dc‡Rjvaxb 15wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 283.8333 | 17030000 | LCS | 16423371 | 01.07.2015 | 30.06.2017 | 100% | 16423371 | 16423371 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 283.8333 | 17030000 | 1 | 16423371 |  |  | 100% | 16423371 | 16423371 | 0
Sadar | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi m`i Dc‡Rjvaxb 13wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 246.8 | 14808000 | LCS | 11662028 | 01.07.2015 | 30.06.2017 | 67% | 11662028 | 11662028 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 246.8 | 14808000 | 1 | 11662028 |  |  | 167% | 11662028 | 11662028 | 0
Sadullapur | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi mv`yjøvcyi Dc‡Rjvaxb 11wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 209.7667 | 12586000 | LCS | 11180306 | 01.07.2015 | 30.06.2017 | 100% | 11180306 | 11180306 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 209.7667 | 12586000 | 1 | 11180306 |  |  | 267% | 11180306 | 11180306 | 0
Palalshbari | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi cjvkevox Dc‡Rjvaxb 9wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 172.7333 | 10364000 | LCS | 9245133 | 01.07.2015 | 30.06.2017 | 100% | 9245133 | 9245133 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 172.7333 | 10364000 | 1 | 9245133 |  |  | 367% | 9245133 | 9245133 | 0
Gobindaganj | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi ‡Mvwe›`MÄ Dc‡Rjvaxb 17wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 320.8667 | 19252000 | LCS | 18958854 | 01.07.2015 | 30.06.2017 | 100% | 18958854 | 18958854 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 320.8667 | 19252000 | 1 | 18958854 |  |  | 467% | 18958854 | 18958854 | 0
Saghata | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi mvNvUv Dc‡Rjvaxb 10wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 191.25 | 11475000 | LCS | 10800914 | 01.07.2015 | 30.06.2017 | 100% | 10800914 | 10800914 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 191.25 | 11475000 | 1 | 10800914 |  |  | 567% | 10800914 | 10800914 | 0
Fulchari | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi dzjQwo Dc‡Rjvaxb 7wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 135.7 | 8142000 | LCS | 7008190 | 01.07.2015 | 30.06.2017 | 100% | 7008190 | 7008190 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 135.7 | 8142000 | 1 | 7008190 |  |  | 667% | 7008190 | 7008190 | 0
Total = |  | 7 |  |  | 1560.95 | 93657000 | 7 | 85278796 |  |  | 95.29% | 85278796 | 85278796 | 0
10. Tree plantation:
Sadar | 13.07.2014 | RDRIIP/GAI/ TR-003 | 132243014 | Tree Plantation work of Badiakhali UP office – Farazkhan Bazar road (Ch. 1000-2000m). | 1 | 150000 | LCS women | 150000 |  |  | 100% | 150000 | 150000 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 1 | 150000 | 1 | 150000 |  |  | 100% | 150000 | 150000 | 0
Sadullapur | 27.07-2015 | RDRIIP/GAI/TR-031 | 132822004 | Tree Plantation work of Jamlarjan – Thutiapukur via Pachar Bazar GC road (Ch. 1000-2000m). | 1 | 150000 | LCS women | 150000 |  |  | 100% | 150000 | 150000 |  | Final bill Paid
Sadullapur | 27.07.2015 | RDRIIP/GAI/TR-032 | 132822006 | Tree Plantation work of Rahmatpur GC – Majumdarhat GC via Naldanga GC road (Ch. 2000-3000m). | 1 | 150000 | LCS women | 150000 |  |  | 100% | 150000 | 150000 |  | Final bill Paid
Sub-Total = |  | 2 |  |  | 2 | 300000 | 2 | 300000 |  |  | 100% | 300000 | 300000 | 0
Palalshbari | 27.07.2015 | RDRIIP/GAI/TR-033 | 132672001 | Tree Plantation work of Palashbari Upazila H/Q – Fakirhat GC road (Ch. 4700-5900m). | 1.2 | 156900 | LCS women | 156900 |  |  | 100% | 156900 | 156900 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 1.2 | 156900 | 1 | 156900 |  |  | 100% | 156900 | 156900 | 0
Gobindaganj | 08.07.2014 | RDRIIP/GAI/ TR-002 | 132303011 | Tree Plantation work of Gumanigonj UP – Upazila H/Q (Post Office) via Kalikadoba road (Ch. 986-2986m). | 2 | 300828 | LCS women | 300828 |  |  | 100% | 300828 | 300828 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 2 | 300828 | 1 | 300828 |  |  | 100% | 300828 | 300828 | 0
Fulchari | 02-08-2015 | RDRIIP/GAI/ TR-034 | 132214001 | Tree Plantation work of H/O Delwer Hossain – Chunakandi Khea Ghat road (Ch. 00-1400m). | 1.4 | 271600 | LCS women | 271600 |  |  | 100% | 166324.95 | 166324.95 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 1.4 | 271600 | 1 | 271600 |  |  | 100% | 166324.95 | 166324.95 | 0
Total = |  | 6 |  |  | 7.6 | 1179328 | 6 | 1179328 |  |  | 100% | 1074052.95 | 1074052.95 | 0
Total (Tender) = |  | 161 |  |  |  | 1091397771.4 | 161 | 1087438315.355 |  |  | 88.41% | 874765502.4 | 998672481.05 | 87928434.04
Total (LCS woman) = |  | 7 |  |  |  | 93657000 | 7 | 85278796 |  |  | 95.29% | 85278796 | 85278796 | 0
Total (Tree plantation) = |  | 6 |  |  |  | 1179328 | 6 | 1179328 |  |  | 100% | 1074052.95 | 1074052.95 | 0
District Total (All) = |  | 174 |  |  |  | 1186234099.4 | 174 | 1173896439.355 |  |  | 94.56% | 961118351.35 | 1085025330 | 87928434.04 |  | 6908196
[7 empty] | Total Fund Received | [5 empty] | 1085025330
[7 empty] | Balance | [5 empty] | 0

## UP TO DATE
Rangpur Division Rural Infrastructure Improvement Project (RDRIIP) District wise Monthly Progress Report (Physical & Financial).
District : Gaibandha. | [11 empty] | Reporting Month: Up to March 24/2019
Upazila | Approval Date | Package No | Road ID No. | Name of scheme (chainage) | Quantity (Km/m/nos) | Approved Estimated cost (Tk) | Name of Contractor | Contract Amount (Tk) | Date of Contract | Date of completion | Physical Progress (%) | Payment Status |  |  | Remarks
[12 empty] | Final Bill (Tk.) | Payment made (Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 13 | 14 | 15 | 16 | 20
1. Improvement of Upazila road:
Sadar | 15.07.2014 | RDRIIP/GAI/ UZ-041 | 132242010 | Improvement of Tulshi Ghat -Pocherbazar GC via Khur Dokomurpur Bazar Road (Ch.5000-5552m). | 0.552 | 4368588 | Md. Shoheb Hossain Mona | 3811387.87 | 11.11.2014 | 11.11.2015 | 100% | 3811387 | 3811387 | 0 | Final bill Paid
Sadar | 03.08.2016 | RDRIIP/GAI/ UZ-096 | 132242013 | Improvement of Gaibandha - Shaghata R&H near Fulbari - Fulchori HQ via Chuniakandi Road (Ch. 00-1100m). | 1.1 | 10575563 | Md. Nuruzzaman, Kurigram. | 10928502.72 | 31.10.2016 | 14.11.2017 | 100% | 10896041 | 10896041 | 0 | Final bill Paid
Sub-Total = |  | 2 |  |  | 1.652 | 14944151 | 2 | 14739890.59 |  |  | 100% | 14707428 | 14707428 | 0
Sadullapur | 12.06.2014 | RDRIIP/GAI/ UZ-010 | 132822005 | Improvement of Dhaperhat GC – Madargonj GC (Dhaperhat – Masargonj FBR road) Road (Ch. 1480-2480m). | 1 | 6977793 | Md. Mahomudun Nobi | 5833150.8 | 11.11.2014 | 30.06.2016 | 100% | 5785739 | 5785739 | 0 | Final bill Paid
Sadullapur | 13.07.2014 | RDRIIP/GAI/ UZ-040 | 132822010 | Improvement of Sadullapur – Pachar Bazar GC Road (Ch. 4575-7263m). | 2.688 | 16658151 | Md. Ferdous Bari | 13579866.66 | 12.11.2014 | 30.06.2016 | 100% | 13565695 | 13565695 | 0 | Final bill Paid
Sadullapur | 05.01.2015 | RDRIIP/DIN/ UZ-059 | 132822004 | Improvement of Jamlarjan – Palashbari Road (2224-4224m). | 2 | 13813541 | Md. Abu Sayid Mahabub. | 12162818 | 24.03.2015 | 15.03.2016 | 100% | 12160560 | 12160560 | 0 | Final bill Paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ UZ-105 | 132822005 | Improvement of Dhaperhat GC - Madargonj Pirgonj GC Road (Ch. 2480-4127m). | 1.647 | 12563060 | Md. Ferdous Bari, Sadullapur, Gaibandha. | 12224855.44 | 20.06.2017 | 24.04.2018 | 100% | 12222846 | 12222846 |  | Final bill Paid
Sub-Total = |  | 4 |  |  | 7.335 | 50012545 | 4 | 43800690.9 |  |  | 100% | 43734840 | 43734840 | 0
Palalshbari | 03.11.2014 | RDRIIP/GAI/ UZ-049 | 132672007 | Improvement of Satharpara RHW - Fakirhat GC Road (Ch. 2000-3500m). | 1.5 | 11440377 | Md. Abu Sayid Mahabub. | 12269761.91 | 22.02.2015 | 14.01.2016 | 100% | 12254900 | 12254900 | 0 | Final bill Paid
Palalshbari | 05.07.2015 | RDRIIP/GAI/ UZ-078 | 132672007 | Improvement of Satharpara RHW - Fakirhat GC Road (Ch. 3500-5000m). | 1.5 | 12343838 | Md. Jakir Hossain | 11185609.27 | 18.10.15 | 29.02.2017 | 100% | 11185142 | 11185142 | 0 | Final bill Paid
Palalshbari | 03.08.2016 | RDRIIP/GAI/ UZ -095 | 132672006 | Improvement of Thutiapukur RHW - Pacharbazar GC Road (Ch. 00-1235m). | 1.235 | 12583020 | Md. Abdul Latif Hakkani, Gaibandha. | 12837718.14 | 24.10.2016 | 14.11.2017 | 100% | 12835726 | 12835726
Palalshbari | 07.08.2016 | RDRIIP/GAI/ UZ-098 | 132672010 | Improvement of Dublagari NHW - Dholbanga GC Road via Amlagachi GC Road (Ch.00-1110m). | 1.11 | 9511147 | Md. Shahidul Islam, Gaibandha. | 9978869.86 | 04.12.2017 | 04.12.2017 | 100% | 9625861 | 9625861 | 0 | Final bill Paid
Palalshbari | 23.08.2016 | RDRIIP/GAI/ UZ-100 | 132672009 | Improvement of Komorpur GC - Marihat GC Road via Sahindaha Road (Ch. 1580-4580m). | 2.984 | 24162562 | Md. Abdul Latif Hakkani, Gaibandha. | 25345297.52 | 21.11.2016 | 19.11.2017 | 100% | 25344039 | 25344039 |  | Final bill Paid
Palalshbari | 01.01.2017 | RDRIIP/GAI/ UZ-102 | 132672003 | Improvement of Tulshighat GC - Nakihat GC Road (Ch. 25-650m). | 0.625 | 4728832 | Md. Abdul Latif Hakkani, Gaibandha. | 4955788.81 | 25.05.2017 | 25.01.2018 | 100% | 4955063 | 4955063 |  | Final bill Paid
Sub-Total = |  | 6 |  |  | 8.954 | 74769776 | 6 | 76573045.51 |  |  | 100% | 76200731 | 76200731 | 0
Gobindaganj | 12.06.2014 | RDRIIP/GAI/ UZ-009 | 132302016 | Improvement of Shagdaha Bridge – Trimohonighat Road (Ch. 5760-6550m & 7260-8470m). | 2 | 12138543 | M/S. SR Traders Thanapara, Gaibandaha | 10950991.36 | 16.09.2014 | 14.09.2015 | 100% | 3809933 | 3809933 | 761986700% | Remaining Work Estimate Tender Called
Gobindaganj | 30.8.18 | RDRIIP/GAI/ UZ-112 | 132302016 | Improvement of Remaining work Gobindaganj-Gaibandha RHD at Shakdaha Bridge – Banarpara GC UP to Trimohoni ghat Road via Amtoli Bazar Road (Ch. 7220-8500m). | 1.28 | 15763174.15 | Mukitur Rahman Rafi, Gobindaganj, Gaibandha | 15760809.674 | 6.11.18 | 10.6.19 | 25% |  | 3000000 | 12760809.674
Sub-Total = |  | 2 |  |  | 3.28 | 27901717.15 | 2 | 26711801.034 |  |  | 50% | 3809933 | 6809933 | 1061986650%
Total = |  | 14 |  |  | 21.221 | 167628189.15 | 14 | 161825428.034 |  |  | 92.86% | 138452932 | 141452932 | 10619866.5
2. Improvement of Union Road:
Sundarganj | 29.11.2015 | RDRIIP/GAI/ UN-210 | 132913003 | Improvement of Ramjiban UP HQ - Dahaband UP HQ (Brac Office) Road (Ch. 4200-5200m). | 1 | 5390911 | RSL Enterprise | 5639066.29 | 08.03.2016 | 01.03.2017 | 100% | 5639000 | 5639000 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ UN-211 | 132913004 | Improvement of Sonaray UP HQ - Naldanga GC (Kishmbazar) Road (Ch. 2800-3800m). | 1 | 5793102 | Md. Motlbur Rahman | 6066482.18 | 08.03.2016 | 01.03.2017 | 100% | 6051845 | 6051845 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ UN-212 | 132913006 | Improvement of Dhopadanga UP -Sreepur UP HQ (Dharmapur FRA) Road (Ch. 1000-3000m). | 2 | 13821170 | M/S Ahsan & Co. | 14477438.67 | 08.03.2016 | 01.03.2017 | 100% | 14463601 | 14463601 |  | Final bill paid
Sundarganj | 04.08.2016 | RDRIIP/GAI/ UN-281 | 132913008 | Improvement of Dharmopur (Sreepur UP H/Q) - Baruarhat Road (Ch. 00-1000m). | 1 | 7284497 | Md. Abdul Latif Hakkani, Gaibandha. | 7643378.99 | 22.11.2016 | 4.12.2017 | 100% | 7633565 | 7633565 |  | Final bill paid
Sundarganj | 04.08.2016 | RDRIIP/GAI/ UN-282 | 132913013 | Improvement of Ramjiban UP HQ -Naldangha GC (Bater Chara) Road (Ch. 00-1000m). | 1 | 6233243 | M/S Shazin Traders | 6538044.91 | 25.10.2016 | 14.11.2017 | 100% | 6537695 | 6537695 |  | Final bill paid
Sundarganj | 04.08.2016 | RDRIIP/GAI/ UN-283 | 132913017 | Improvement of Santiram UP -Pachgasi Model School (Muzamder GC) Road (Ch. 2100-3100m). | 1 | 7037046 | M/S Esa Kabinet, Gaibandha. Nozel C.Man | 7374805.92 | 27.11.2016 | 30.3.2019 | 45% |  | 2372453 | 5002352.92
Sub-Total = |  | 6 |  |  | 7 | 45559969 | 6 | 47739216.96 |  |  | 90.83% | 40325706 | 42698159 | 5002352.92
Sadar | 15.07.2014 | RDRIIP/GAI/ UN-037 | 132243016 | Improvement of Gidari UP office - Dariapur GC Road (Ch. 00-1000m). | 1 | 5730258 | Md. Khademul Islam Jewel. | 4936071.89 | 09.09.2014 | 15.07.2015 | 100% | 4936018 | 4936018 |  | Final bill paid
Sadar | 15.07.2014 | RDRIIP/GAI/ UN-071 | 132243004 | Improvement of Badia khali UP office - Chak Barul Bazar Road (Ch. 2950-3850m). | 0.9 | 4854829 | Md. Khademul Islam Jewel | 4154545.48 | 11.11.2014 | 11.11.2015 | 100% | 4154545 | 4154545 |  | Final bill paid
Sadar | 01.10.2014 | RDRIIP/GAI/ UN-072 | 132243014 | Improvement of Badiakhali UP office - FarazKhan Bazar Road (Ch. 2500-3500m). | 1 | 5382612 | Md. Khademul Islam Jewel | 4663777.35 | 11.11.2014 | 11.11.2015 | 100% | 4663777 | 4663777 |  | Final bill paid
Sadar | 06.04.2015 | RDRIIP/GAI/ UN-152 | 132243013 | Improvement of Hasem Bazar – Ghagoa UP Road (Ch. 00-4760m). | 4.76 | 35969395 | KJ-SA (JV) | 37720850.25 | 10.11.2015 | 29.12.2016 | 100% | 37509075 | 37509075 |  | Final bill paid
Sub-Total = |  | 4 |  |  | 7.66 | 51937094 | 4 | 51475244.97 |  |  | 100% | 51263415 | 51263415 | 0
Sadullapur | 27.02.2014 | RDRIIP/GAI/ UN-013 | 132823005 | Improvement of Kamrapara UP office - Sadullapur Naldanga Road (Ch. 00-1000m). | 1 | 5691572 | Mony Enterprise Polashbari, Gaibandaha. | 5063758.98 | 06.07.2014 | 22.06.2015 | 100% | 5063758 | 5063758 |  | Final bill paid
Sadullapur | 12.06.2014 | RDRIIP/GAI/ UN-042 | 132823002 | Improvement of Moshbsndhi - Mirpur Road (Ch. 4235-5235m). | 1 | 5533374 | Mony Enterprise | 4683248.56 | 07.09.2014 | 10.06.2015 | 100% | 4681491 | 4681491 |  | Final bill paid
Sadullapur | 01.07.2015 | RDRIIP/GAI/ UN-170 | 132823017 | Improvement of Bhatgram U.P office – Nagbari Bazar via Burir Bazar Road (Ch. 00-500m). | 0.5 | 3172927 | Md. Ferdous Bari | 2807380.44 | 18.10.2015 | 30.06.2016 | 100% | 2749665 | 2749665 |  | Final bill paid
Sadullapur | 13.06.2016 | RDRIIP/GAI/ UN-276 | 132823006 | Improvement of Chandiapur Bazar - Rahmatpur GC via Rasulpur bazar Road (Ch. 00-1000m). | 1 | 7306613 | Md. Zahidul Islam | 6828952.81 | 11.11.2016 | 24.10.2017 | 100% | 6532501 | 6532501 |  | Final bill paid
Sub-Total = |  | 4 |  |  | 3.5 | 21704486 | 4 | 19383340.79 |  |  | 100% | 19027415 | 19027415 | 0
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-303 | 132673005 | Improvement of Dholbanga Bazar at Zillbandha-Pabnapur UP office Road (Ch. 910-1414m). | 0.504 | 3230128 | Md. Shahidul Islam, Gaibandha. Kamal | 3386403.94 | 12.06.2017 | 24.04.2018 | 100% | 3385424 | 3385424 |  | Final bill paid | 685424 | 4070848
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-305 | 132673002 | Improvement of Kalibari GC at Chinema Hall - Chattra UP Office Road (Ch. 2000-2500m). | 0.5 | 3310770 | Mony Enterprise, Polashbari, Gaibandha. | 3467955.73 | 22.05.2017 | 24.04.2018 | 100% | 3466107 | 3466107 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-306 | 132673022 | Improvement of Monohorpur-UP office to Pabnapur up office Road via Azir beel Road (Ch. 450-950m). | 0.5 | 3318023 | M/S Shazin Traders, Gaibandha. | 3477130.03 | 15.06.2017 | 24.04.2018 | 100% | 3474570 | 3474570 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ UN-307 | 132673020 | Improvement of Kumidpur Bazar - Badiakhali UP office Road (Ch. 145-645m). | 0.5 | 2908919 | Md. Shahidul Islam, Gaibandha.Liton | 3040018.44 | 15.06.2017 | 25.12.18 | 100% | 3040018 | 1762656 | 1277362.44
Sub-Total = |  | 4 |  |  | 2.004 | 12767840 | 4 | 13371508.14 |  |  | 100% | 13366119 | 12088757 | 1277362.44
Gobindaganj | 22.05.2014 | RDRIIP/GAI/ UN-028 | 132303037 | Improvement of Rakhalburuz U.P(at Dargapara) - Dharmapur bazar at Baradaha KazlaChowduri bari via Sarkerpara Road (Ch. 950-1950m). | 1 | 6219447 | NR Traders | 7240913.13 | 14.10.2014 | 25.01.2015 | 100% | 7237334 | 7237334 |  | Final bill paid
Gobindaganj | 22.05.2014 | RDRIIP/GAI/ UN-029 | 132303020 | Improvement of Salmara U.P - Sonatola Upazila via Heatpur(Uzirer Baiguni-Salmara) Road (Ch. 845-1595m). | 0.75 | 5201076 | The Kanak & Kallal Engineering Workshop | 6271445 | 14.10.2014 | 14.07.2015 | 100% | 6135515 | 6135515 |  | Final bill paid
Gobindaganj | 22.05.2014 | RDRIIP/GAI/ UN-030 | 132303033 | Improvement of Kamardaha U.P(Fashitola NHW) - Daridahahat Via Ferusha,Nagarvita ( at Niamatpur) Road (Ch. 00-500m). | 0.5 | 2912781 | Shaharul Islam Titu | 3197467.16 | 14.10.2014 | 14.07.2015 | 100% | 3196072 | 3196072 |  | Final bill paid
Gobindaganj | 12.06.2014 | RDRIIP/GAI/ UN-041 | 132303029 | Improvement of Nakaihat – Ratherbazer via Dhankhunia Road (Ch. 5400-6400m). | 1 | 6785333 | Mony Enterprise Polashbari, Gaibandaha. | 6011330.22 | 07.09.2014 | 10.06.2015 | 100% | 5972361 | 5972361 |  | Final bill paid
Gobindaganj | 02.06.2014 | RDRIIP/GAI/ UN-031 | 132303024 | Improvement of Dorbasta U.P – Katakhali Balua Hat Road via Bishubari (Ch. 1783-2783m). | 1 | 7517239 | M/S Ahsan & Co. | 8231136.53 | 14.10.2014 | 15.07.2015 | 100% | 8225830 | 8225830 |  | Final bill paid
Gobindaganj | 02.06.2014 | RDRIIP/GAI/ UN-032 | 132303009 | Improvement of Gumanigonj U.P - Fulpukuria- Bazar at sreepur via Zarippur (Ch. 3040-4805m). | 1.765 | 10539763 | M/S Milu Traders | 11567728.41 | 14.10.2014 | 14.07.2015 | 100% | 11567141 | 11567141 |  | Final bill paid
Gobindaganj | 16.06.2014 | RDRIIP/GAI/ UN-045 | 132303016 | Improvement of Kochashahor U.P - Chandpara hat. ( Dharaikandi-Chandpara via UP office) Road (Ch. 00-750m). | 0.75 | 5087358 | M/S Atkur Rahman | 5590876.72 | 11.09.2014 | 20.06.2015 | 100% | 5590076 | 5590076 |  | Final bill paid
Gobindaganj | 03.11.2014 | RDRIIP/GAI/ UN-093 | 132033010 | Improvement of Gumanigonj UP – Daridaha Hat at Niamatpur Road (293 -2293m). | 2 | 12630127 | M/S Sabbir Traders. | 13616063.21 | 22.02.2015 | 14.01.2016 | 100% | 13614648 | 13614648 |  | Final bill paid
Gobindaganj | 24.11.2014 | RDRIIP/GAI/ UN-113 | 132303007 | Improvement of Rajahar UP at Banaswer – Fulpukuria Bazar at UZR Road (2706 -4726m). | 2 | 10919855 | M/S Atikur Rahman | 11984528.16 | 22.03.2015 | 01.03.2016 | 100% | 11983986 | 11983986 |  | Final bill paid
Gobindaganj | 12.04.2015 | RDRIIP/GAI/ UN-159 | 132303035 | Improvement of Rakhalburuz UP at Amtoli – Mohimagonj at Puntair Kanipara more road via Kurarmath Garzan Road (Ch. 3900-4900m). | 1 | 5900897 | M/S Khandakar Enterprise | 6369300.77 | 18.08.2015 | 17.07.2016 | 100% | 6368033 | 6368033 |  | Final bill paid
Gobindaganj | 31.03.2016 | RDRIIP/GAI/ UN-257 | 132913012 | Improvement of Gumaniganj UP - Kamardaha via Gudaraghat Road (Ch. 00-3180m). | 3.18 | 20705544 | M/S Atikur Rahman, Gobindaganj, Gaibandha. | 21638355 | 29.06.2017 | 12.07.2016 | 100% | 21633963 | 21633963 |  | Final bill paid
Gobindaganj | 00.00.2016 | RDRIIP/GAI/ UN-293 | 132303015 | Improvement of Kochashahor UP - Chandpara Hat Road (Ch. 1350-3350m). | 2 | 13337039 | M/S Atikur Rahman, Gobindaganj, Gaibandha. | 13977548.48 | 30.01.2017 | 22.5.18 | 100% | 13968670 | 13968670 |  | Final bill paid
Sub-Total = |  | 12 |  |  | 16.945 | 107756459 | 12 | 115696692.79 |  |  | 100% | 115493629 | 115493629 | 0
Saghata | 27.02.2014 | RDRIIP/GAI/ UN-014 | 132883014 | Improvement of Kachua UP - Kamalerpara Road (Ch. 00-1000m). | 1 | 6223534 | M/S. SR Traders Thanapara, Gaibandaha | 5751958.55 | 06.07.2014 | 22.06.2015 | 100% | 5749426 | 5749426 |  | Final bill paid
Saghata | 03.11.2014 | RDRIIP/GAI/ UN-087 | 132883005 | Improvement of Ghuridha UP Office - Bottola Bazar Road (Ch. 00-1400m). | 1.4 | 12856911 | Md. Khademul Islam Jewel. | 13809947.4 | 05.03.2015 | 14.01.2016 | 100% | 13767820 | 13767820 |  | Final bill paid
Saghata | 03.11.2014 | RDRIIP/GAI/ UN-088 | 132883014 | Improvement of Kachua UP - Kamalerpara UP Road (Ch. 1000-1955m, Effective Length = 945m). | 0.945 | 5890348 | Md. Rafiqul Islam | 6331760.61 | 08.03.2015 | 14.01.2016 | 100% | 6327583 | 6327583 |  | Final bill paid
Saghata | 03.11.2015 | RDRIIP/GAI/ UN-199 | 132883002 | Improvement of Padumshahar UP - Bhutmara Hat via Chakdatia Bazar road (Ch. 00-2080m). | 2.08 | 12595176 | Md. Khademul Islam Jewel | 13209673.51 | 30.03.2016 | 02.9.18 | 100% | 13200353 | 13200353 |  | Final bill paid
Saghata | 03.11.2015 | RDRIIP/GAI/ UN-200 | 132883002 | Improvement of Padamsohor UP - Bhutmara Hat via Chakdatia Bazar Road (Ch. 2080-3080m). | 1 | 6521429 | Md. Khademul Islam Jewel, Gaibandha. | 6837029.3 | 28.04.2016 | 29.8.18 | 100% | 6830795 | 6830795 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ UN-304 | 132883014 | Improvement of Kachua UP - Kamalerpara UP Road (Ch. 3650-4150m). | 0.5 | 3237456 | M/S Shazin Traders | 3389342.44 | 05.06.2017 | 17.11.18 | 100% | 3387766 | 3387766 |  | Final bill paid
Sub-Total = |  | 6 |  |  | 6.925 | 47324854 | 6 | 49329711.81 |  |  | 100% | 49263743 | 49263743 | 0
Total = |  | 36 |  |  | 44.034 | 287050702 | 36 | 296995715.46 |  |  | 98.47% | 288740027 | 289835118 | 6279715.36
3. Improvement of Village Road:
Sundarganj | 23.02.2015 | RDRIIP/GAI/ VR-174 | 132915057 | Improvement of Ramdakua – Shamopraiarpat Govt. Pry. School via Panchanan Madrasha Road (Ch. 400-1400m). | 1 | 5056777 | SR Traders Thanapara, Gaibandaha | 5177941.67 | 24.06.2015 | 10.05.2016 | 100% | 5174559 | 5174559 |  | Final bill paid
Sundarganj | 23.02.2015 | RDRIIP/GAI/ VR-175 | 132915086 | Improvement of Boali - Samas Road (Ch. 1400-2400m). | 1 | 5393265 | M/S. SR Traders Thanapara, Gaibandaha | 5382121.4 | 24.06.2015 | 15.03.2017 | 100% | 5376640 | 5376640 |  | Final bill paid
Sundarganj | 23.02.2015 | RDRIIP/GAI/ VR-176 | 132914037 | Improvement of Baiddanath (RHD) – Sonarai Road (Ch. 00-2162m). | 2.162 | 12826570 | Md. Abdul Latif Hakkani | 12830107.04 | 29.06.2015 | 05.07.2016 | 100% | 12703826 | 12703826 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ VR-247 | 132914056 | Improvement of Sonarai Baburdighi-Bamondanga FRA Road (Ch. 00-1200m). | 1.2 | 8564135 | RSL Enterprise | 8972157.259 | 08.03.2016 | 01.03.2017 | 100% | 8942644 | 8942644 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ VR-248 | 132914016 | Improvement of Bamondanga (Shashan) RHD - Kandi Road (Ch. 00-700m). | 0.7 | 3841418 | Md. Shoheb Hossain Mona, Gaibandha. | 4022130.21 | 20.03.2016 | 01.03.2017 | 100% | 4019576 | 4019576 |  | Final bill paid
Sundarganj | 29.11.2015 | RDRIIP/GAI/ VR-249 | 132915092 | Improvement of Mondolerhat Near Dines House - Pararhatkhola Road (Mondolerhat - Dhopadanga (Orphanage) Road (Ch. 00-700m). | 0.7 | 4221509 | Md. Abdul Latif Hakkani, Bridge Road, Gaibandha. | 4423645.55 | 08.03.2016 | 01.03.2017 | 100% | 4408982 | 4408982 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-371 | 132915117 | Improvement of Sonaroy - Kandhi (Jamaderdigi) Road (Ch. 00-1000m). | 1 | 7771581 | M/S Shazzad Hossain, Gaibandha. | 8131465.97 | 08.01.2017 | 28.5.18 | 100% | 8125028 | 8125028 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-372 | 132915111 | Improvement of Khanpara Pacca more - Kushtary Rajandronath Old Bari Road (Ch. 1000-2314m). | 1.314 | 12047663 | M/S Ahsan & Co, Gaibandha. | 12550851.49 | 31.10.2016 | 14.11.2017 | 100% | 12534519 | 12534519 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-373 | 132915065 | Improvement of Kashim Bazer (UZR) - Motinmiar Hat Road (Ch. 00-1000m). | 1 | 6895479 | Md. Matlubour Rahman, Gaibandha. | 7236970.12 | 04.12.2016 | 04.12.2017 | 100% | 7213887 | 7213877 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-374 | 132914090 | Improvement of Koikuribazar - Bamondanga (Bridge More) Road (Ch. 00-1000m). | 1 | 6088735 | Md. Shoheb Hossain Mona, Gaibandha. | 6385382.89 | 15.01.2017 | 14.01.2018 | 100% | 6375257 | 6375257 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-375 | 132915008 | Improvement of Chaitantola -Sonarai Road (Ch. 00-1130m). | 1.13 | 6796502 | M/S Shazin Traders, Gaibandha. Mamun | 7129076.28 | 25.10.2016 | 11.12.2018 | 100% | 7128035 | 7128035 |  | Final bill paid
Sundarganj | 03.08.2016 | RDRIIP/GAI/ VR-376 | 132915082 | Improvement of Zuharuler More-Zhina Via Aftab More Road (Ch. 00-953m). | 0.953 | 5814688 | M/S Shawon Construction. | 6096680.37 | 24.10.2016 | 14.11.2017 | 100% | 6086410 | 6086410 |  | Final bill Paid
Sundarganj | 28.02.2017 | RDRIIP/GAI/ VR-450 | 132915121 | Improvement of Bamondanga (R&H) Luxmipur GC road Indrarpar - Sadhur more Mazumderhat GC Road (Ch. 00-1430m). | 1.43 | 10230033 | Md. Shoheb Hossain Mona, Gaibandha. | 10736097.73 | 14.06.2017 | 19.04.2018 | 100% | 10724934 | 10724934 |  | Final bill paid
Sub-Total = |  | 13 |  |  | 14.589 | 95548355 | 13 | 99074627.979 |  |  | 100% | 98814297 | 98814287 | 0
Sadar | 15.07.2014 | RDRIIP/GAI/ VR-080 | 132244028 | Improvement of Kabiler bazar - Lengabazer Road (Ch. 00-800m). | 0.8 | 5247022 | Md. Abu Sayid Mahabub | 4536862.41 | 12.11.2014 | 12.11.2015 | 100% | 4536862 | 4536862 |  | Final bill paid
Sadar | 15.07.2014 | RDRIIP/GAI/ VR-081 | 132244033 | Improvement of R&H (sadullapur) - Narayanpur ghat Road (Ch. 00-500m). | 0.5 | 2906590 | SR Traders | 2493439.87 | 12.11.2014 | 12.11.2015 | 100% | 2493439 | 2493439 |  | Final bill paid
Sadar | 01.10.2014 | RDRIIP/GAI/ VR-110 | 132245044 | Improvement of Kholahati UP Godarhat Haydar Member House-Zamil Member House Road (Ch. 1700m-2700m). | 1 | 5114138 | Md. Abdul Latif Hakkani, Bridge Road, Gaibandha. | 4441818.33 | 06.01.2015 | 31.05.2015 | 100% | 4440992 | 4440992 |  | Final bill paid
Sadar | 07.06.2016 | RDRIIP/GAI/ VR-356 | 132245005 | Improvement of panchjumma Road-Dariapur Kuptola Road (Ch. 00-500m). | 0.5 | 3734188 | M/S Rahman Traders, Gaibandha. | 3520807.86 | 31.10.2016 | 14.11.2017 | 100% | 2852721 | 2852721 |  | Final bill paid
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-442 | 132244086 | Improvement of Tingacher Tool - Radhakisnopu SKS Inn Ofice Road (Ch. 00-1070m). | 1.07 | 6293342 | Md. Khademul Islam Jewel, Gaibandha. | 6563225.22 | 13.06.2017 | 24.04.2018 | 100% | 6563225 | 6563225 |  | Final bill paid
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-444 | 132245065 | Improvement of Chapadha H/O Abdur Nur - Gaibandha Loxmipur Road via Chapadha Community Clinic Road (Ch. 00-500m). | 0.5 | 2798521 | M/S Shazin Traders, Gaibandha. Sizan | 2936692.53 | 05.06.2017 | 24.04.2018 | 100% | 2936673 | 2936673 |  | Final bill paid
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-445 | 132245064 | Improvement of Gaibandha - Dinajpur R&H New Bridge - Manash Regulator Road. (Ch. 00-1000m). | 1 | 5521846 | Khandakar Wahedunnabi Rimu. Gaibandha. | 5895489.16 | 25.05.2017 | 24.04.2018 | 100% | 5889522 | 5889522 |  | Final bill paid
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-443 | 132244028 | Improvement of Kabiler bazar - Lengabazer Road (Ch. 800-1800m). | 1 | 6291286 | M/S Shazin Traders, Gaibandha. | 6589951.77 | 05.06.2017 | 24.04.2018 | 100% | 6586136 | 6586136 |  | Final bill paid | 486136 | 7072272
Sadar | 28.02.2017 | RDRIIP/GAI/ VR-446 | 132245018 | Improvement of Boali - Ramchandrapur road to Radhakrishnapur Road. (Ch. 400-1400m). | 1 | 5961980 | M/S Ahsan & Co. Gaibandha. | 6246399.68 | 22.05.2017 | 24.04.2018 | 100% | 6244386 | 6244386 |  | Final bill paid
Sadar | 27.03.2017 | RDRIIP/GAI/ VR-543 | 132245063 | Improvement of Pearapur GPS - Kabla Sha Mazar via Abbaus Uddin Grave Yeard Road (Ch. 00-1100m). | 1.1 | 7274994.55 | M/S Ahsan & Co. Gaibandha. | 7601217.64 | 19.06.2017 | 26.06.2018 | 100% | 7597260 | 7597260 |  | Final bill paid
Sadar | 03.05.2017 | RDRIIP/GAI/ VR-557 | 132245062 | Improvement of Manik Patni -North Simultari School via South Simultari School Road (Ch. 00-500m). | 0.5 | 2940893.21 | Md.Abu Bakar Siddique, Gaibandha. Sizan | 3082052.12 | 12.07.2017 | 12.9.18 | 100% | 3082052 | 3082052 | 0 | Final bill paid | 1580000
|  | 11 |  |  | 8.97 | 54084800.76 | 11 | 53907956.59 |  |  | 100% | 53223268 | 53223268 | 0
Sadullapur | 27.02.2014 | RDRIIP/GAI/ VR-037 | 132825074 | Improvement of Sadullapur - Dhaper hat pacca raod – Khordoruhia Gor Mondop Road (Ch. 355-890m). | 0.535 | 3052186 | M/S Sadin Traders | 2660615.74 | 14.07.2014 | 22.06.2015 | 100% | 2643453 | 2643453 |  | Final bill paid
Sadullapur | 10.07.2014 | RDRIIP/GAI/ VR-079 | 132824060 | Improvement of Enaetpur Bazar – Mohishbandi Bazar road (Enaetpur Srikola road to Principal Tazul Islam House road via Dula Munshi House (Ch. 00-500m). | 0.5 | 2878678 | Md. Mahomudunnabi | 2355098.17 | 30.06.2016 | 30.06.2016 | 100% | 2354816 | 2354816 |  | Final bill paid
Sadullapur | 25.06.2015 | RDRIIP/GAI/ VR-218 | 132825021 | Improvement of Kantanagar Bazar – Wapda Embankment Road (Ch. 00-500m). | 0.5 | 3300291 | Md. Ferdous Bari | 2979597.4 | 18.10.2015 | 30.06.2016 | 100% | 2975740 | 2975740 |  | Final bill paid
Sadullapur | 07.06.2016 | RDRIIP/GAI/ VR-354 | 132824062 | Improvement of Iddrakpur Bazar- Kishamot Sherpur GPS Road (Ch. 00-500m). | 0.5 | 3368852 | M/S Rahman Traders, Gaibandha. | 2994574.61 | 31.10.2016 | 14.11.2017 | 100% | 2933958 | 2933958 |  | Final bill paid
Sadullapur | 07.06.2016 | RDRIIP/GAI/ VR-355 | 132824007 | Improvement of Kazibari sontola - sarbazar via badlagari Road (Ch. 00-500m). | 0.5 | 3150710 | M/S Rahman Traders, Gaibandha. | 2905907.53 | 31.10.2016 | 14.11.2017 | 100% | 2869600 | 2869600 |  | Final bill paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-431 | 132824015 | Improvement of Dhaperhat Madargonj G.C Rd at Ali Nagar - Madarer ghat Road (Ch. 00-500m). | 0.5 | 3540201 | M/S Md. Farhadul Haque, Gaibandha.Ferdous | 3703503.43 | 12.06.2017 | 24.04.2018 | 100% | 3662077 | 3662077 |  | Final bill paid | 1337077 | 4999154
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-432 | 132824038 | Improvement of Gaibandha - Sadullapur Road - Dakhin Manduar Kheya Ghat via Gorer math Road (Ch. 1727-2727m). | 1 | 6254844 | M/S. Md. Rabiul Alam (Bulbul), Rangpur. | 6536111.2 | 08.06.2017 | 24.04.2018 | 100% | 6535869 | 6535869 |  | Final bill paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-433 | 132824061 | Improvement of Sadullapur - Madargonj GC Road near Brack Office - Choto Doulotpur Pucca road via Choto Doulotpur GPS road (Ch. 00-1000m). | 1 | 6536333 | Md. Mahomudun Nobi, Rangpur. | 6132194.22 | 19.06.2017 | 30.11.18 | 50% |  | 2459000 | 3673194.22 | Problematic | 459000 | 2918000
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-434 | 132824062 | Improvement of Idrackpur Bazar - Khisamot Sheerpur GPS via Isubpur GPS Road (Ch. 00-1508m). | 1.008 | 6502350 | M/S Ahsan & Co. Gaibandha. | 6785260.48 | 22.05.2017 | 24.04.2018 | 100% | 6782749 | 6782749 |  | Final bill paid
Sadullapur | 28.02.2017 | RDRIIP/GAI/ VR-435 | 132824027 | Improvement of Idilpur Govt. Pry.school - Area of Palashbari via Mohipur bazar Road (Ch. 00-500m). | 0.5 | 3070522 | M/S Md. Farhadul Haque, Gaibandha. | 3212298.17 | 06.06.2017 | 15.4.19 | 70% |  | 2000000 | 1212298.17 | Problematic
Sub-Total = |  | 10 |  |  | 6.543 | 41654967 | 10 | 40265160.95 |  |  | 92% | 30758262 | 35217262 | 4885492.39
Palalshbari | 27.02.2014 | RDRIIP/GAI/ VR-036 | 132674043 | Improvement of Harinmari South Bas stand NHW - Hospital via Napiter Bari Road (Ch. 00-560m). | 0.56 | 3112049 | Mony Enterprise Polashbari, Gaibandaha. | 2733547.34 | 06.07.2014 | 22.06.2015 | 100% | 2733547 | 2733547 |  | Final bill paid
Palalshbari | 07.08.2016 | RDRIIP/GAI/ VR-380 | 132674020 | Improvement of Palashbari -Gaibandha Gramin Bank - Shuigram Road (Ch. 00-500m). | 0.5 | 3032171 | M/S Surovi Enterprise | 3179101.1 | 24.10.2016 | 14.11.2017 | 100% | 3177260 | 3177260 |  | Final bill paid
Palalshbari | 07.08.2016 | RDRIIP/GAI/ VR-381 | 132674086 | Improvement of Kishargari Road at Palashbari Karigori College - Ghoraghat Road via Andua Road (Ch. 00-500m). | 0.5 | 3344183 | M/S Surovi Enterprise | 3536788.82 | 24.10.2016 | 14.11.2017 | 100% | 3500106 | 3500106 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-436 | 132674048 | Improvement of South Vogabanpur NHW - Bashudebpur Road (Ch. 00-503m). | 0.503 | 3675941 | M/S BB Traders, Gaibandha. | 3841120.96 | 19.06.2017 | 24.04.2018 | 100% | 3838766 | 3838766 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-437 | 132675114 | Improvement of Bari Horinmari Mouza near Dreamland - Moazem Sorker House Road (Ch. 00-625m). | 0.625 | 3745609 | M/S New Pavel Auto | 3922417.55 | 04.06.2017 | 24.04.2018 | 100% | 3921060 | 3921060 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-438 | 132674058 | Improvement of Bengulia GPS - Tangra via Mondol Bari Road (Ch. 1000-2000m). | 1 | 6446164 | Md. Farhadul Haque, Gaibandha. | 6742475.56 | 16.05.2017 | 14.04.2018 | 100% | 6738201 | 6738201 |  | Final bill paid
Palalshbari | 28.02.2017 | RDRIIP/GAI/ VR-439 | 132675117 | Improvement of Ghorobandha Chorasta west side of Bridge -Near house of Fazlu Master Purbo Balabamuniya Road (Ch. 00-500m). | 0.5 | 3264414 | Md. Ziaul Alam Dales kamal | 3410559.79 | 06.06.2017 | 24.04.2018 | 100% | 3410559 | 3410559 |  |  | 610559 | 4021118
Palalshbari | 24.05.2017 | RDRIIP/GAI/ VR-561 | 132674030 | Improvement of Kutirghat Bridge - Kalitala Bazar Road (Ch. 00-500m). | 0.5 | 4739881.39 | M/S Shazin Traders, Gaibandha. | 4974414.92 | 12-10-17 | 31-3-2019 | 100% | 4974212 | 1315000 | 3659414.92 | Final bill paid
Palalshbari | 14.11.2017 | RDRIIP/GAI/ VR-562 | 132675119 | Improvement of Rangpur - Bogra NHW near Sugar Center Ruhul Amin house Road (Ch. 00-190m). | 0.19 | 911803.34 | Wahedunnobi rimu | 866213.17 | 12-5-18 | 03-9-2018 | 100% | 866132 | 866132 | 0 | Final bill paid
Sub-Total = |  | 9 |  |  | 4.878 | 32272215.73 | 9 | 33206639.21 |  |  | 100% | 33159843 | 29500631 | 3659414.92
Gobindaganj | 02-06-2014 | RDRIIP/GAI/ VR-053 | 132304207 | Improvement of Kochashahor Kamar bari-Singha road (Ch. 00-1000m). | 1 | 5798328 | M/S Atikur Rahman | 6483470.95 | 14.10.2014 | 20.10.2015 | 100% | 6478719 | 6478719 |  | Final bill paid
Gobindaganj | 02-06-2014 | RDRIIP/GAI/ VR-054 | 132304141 | Improvement of Talikkanupur UP at NHW Samaspara-Jamalpur hat road (Ch. 1680-2680m). | 1 | 5883542 | M/S Shihab Construction | 6460946.52 | 14.10.2014 | 14.07.2015 | 100% | 6459268 | 6459268 |  | Final bill paid
Gobindaganj | 16-06-2014 | RDRIIP/GAI/ VR-058 | 132304214 | Improvement of Ashkur - Farusha raod ( Katabri-Tulot Road to Jugipara poultry Firm) Road (Ch. 00-500m). | 0.5 | 2845181 | M/S Shihab Construction | 2848752.59 | 09.09.2014 | 15.06.2015 | 100% | 2848612 | 2848612 |  | Final bill paid
Gobindaganj | 16-06-2014 | RDRIIP/GAI/ VR-059 | 132304176 | Improvement of Katabari UP at Katgor Madrasha - Polupara Ghat(Ghoraghat Road-Katgor Madrasha Fakirganj Road (Ch. 00-415m). | 0.415 | 2550917 | M/S Salama Traders | 2240474.5 | 09.09.2014 | 15.06.2015 | 100% | 2238151 | 2238151 |  | Final bill paid
Gobindaganj | 19-08-2014 | RDRIIP/DIN/ VR-092 | 132304077 | Improvement of Gopalpur – Puntair road (Ch. 00-1250m) (Effective Length = 1232m). | 1.232 | 7579128 | Md. Abdul Latif Hakkani, Bridge Road, Gaibandha. | 7566032.93 | 28.04.2015 | 28.01.2016 | 100% | 7565571 | 7565571 |  | Final bill paid
Gobindaganj | 12.04.2015 | RDRIIP/DIN/ VR-203 | 132304034 | Improvement of Kamorpur Hindopara – R&H Tatultola Mazar Road (Ch. 00-825m). | 0.825 | 4779180 | Md. Mukitur Rahman Rafi | 5159838.35 | 18.08.2015 | 17.07.2016 | 100% | 5157247 | 5157247 |  | Final bill paid
Gobindaganj | 12.04.2015 | RDRIIP/DIN/ VR-204 | 132304136 | Improvement of NHW Nundaha Bridge - Mirapara Road (Ch. 00-500m). | 0.05 | 3059682 | Md. Mikaddesh Ali Babu | 3301317.91 | 18.08.2015 | 17.07.16 | 100% | 3299839 | 3299839 |  | Final bill paid
Gobindaganj | 23.02.2016 | RDRIIP/GAI/ VR-276 | 132304123 | Improvement of Nakai UP - Horinabari Bazar via Dumargach Road (Ch. 1400-1900m). | 0.5 | 3080024 | M/S Shihab Construction, Gobindaganj, Gaibandha. | 3222108.97 | 17.05.2016 | 30.11.2016 | 100% | 3220305 | 3220305 |  | Final bill paid
Gobindaganj | 23.02.2016 | RDRIIP/GAI/ VR-277 | 132304179 | Improvement of Nasarabad School - Bagunbari Road Chandpara hat (Nashirabad village) Road (Ch. 00-500m). | 0.5 | 2868584 | Shaharul Islam Titu, Gobindaganj, Gaibandha. | 3000487.24 | 22.05.2016 | 30.11.2016 | 100% | 2997903 | 2997903 |  | Final bill paid
Gobindaganj | 10.04.2016 | RDRIIP/GAI/ VR-322 | 132305125 | Improvement of NHW Avairampur - H/O Niru Doctor Road (Ch. 00-1260m). | 1.26 | 8015033 | Md. Rokonuzzaman Prodhan, Gobindaganj, Gaibandha. | 8410279.29 | 25.10.2016 | 14.11.2017 | 100% | 8401299 | 8401299 |  | Final bill paid
Gobindaganj | 18.08.2016 | RDRIIP/GAI/ VR-387 | 132304174 | Improvement of Fulbari UP NHW at Fulbari - Boalia Road (Ch. 00-1385m). | 1.385 | 8661736 | M/S NR Traders, Gobindaganj, Gaibandha. | 9081466.09 | 29.11.2016 | 19.11.2017 | 100% | 9079058 | 9079058 |  | Final bill Paid
Gobindaganj | 24.08.2016 | RDRIIP/GAI/ VR-389 | 132304019 | Improvement of Chitipara at (Charmatha More) - Teghora Road via Satal Para Bhutgari Kishi College Road (Ch. 2500-3000m). | 0.5 | 2866270 | Shaharul Islam Titu, Gobindaganj, Gaibandha. | 3006674.55 | 05.12.2016 | 19.11.2017 | 100% | 3002819.05 | 3002819.05 |  | Final bill Paid
Gobindaganj | 23.10.2016 | RDRIIP/GAI/ VR-393 | 132304152 | Improvement of Kalitola Bazar - Fashitola (Kata) via Golapara Madrasha Road (Ch. 00-1220m). | 1.22 | 7308751 | Md. Mukitur Rahman Rafi, Gobindangan, Gaibandha. | 7661127.1 | 16.01.2017 | 18.01.2018 | 100% | 7657837 | 7657837 |  | Final bill Paid
Gobindaganj | 00.00.2016 | RDRIIP/GAI/ VR-394 | 132304046 | Improvement of Masta - Chaprigonj via Kamardaha School, Clinic Road (Ch. 2825-3825m). | 1 | 6314448 | Md. Atikur Rahman, Gobindaganj, Gaibandha. | 7416370 | 30.01.2017 | 6.4.18 | 100% | 7416353 | 7416353 |  | Final bill paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-403 | 132305141 | Improvement of Faiska - Khurshal (Birat road at Feshka - Gonar Parul - Islampur) Road (Ch. 00-1185m). | 1.185 | 8664423 | M/S Khandakar Enterprise, Gobindaganj, Gaibandha. | 8885660.66 | 09.04.2017 | 11.03.2018 | 100% | 8885416 | 8885416 |  | Final bill Paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-441 | 132305282 | Improvement of Jagonathpur Senior Madrasha - Fashitola Pacca Road (at Dharma) (Ch. 00-500m). | 0.5 | 3429862 | M/S. Sabbir Traders, Gobindaganj, Gaibandha. | 3591574.21 | 11.06.2017 | 24.04.2018 | 100% | 3589668 | 3589668 |  | Final bill Paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-457 | 132305168 | Improvement of Shakhahar UP - Fupukuria road - Khurshal Mosque Road (Ch. 00-350m). | 0.35 | 2046580 | Md. Mokaddesh Ali Badu, Gobindaganj, Gaibandha. | 2142502.63 | 31.05.2017 | 15.05.2018 | 100% | 2113971 | 2113971 |  | Final bill paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-458 | 132305009 | Improvement of Bogulagari Eidgha (CARE road) - Satana Balua Road (Ch. 1000-2030m). | 1.03 | 7361931 | Md. Mokaddesh Ali Badu, Gobindaganj, Gaibandha. | 7710655.41 | 17.05.2017 | 24.04.2018 | 100% | 7706750 | 7706750 |  | Final bill paid
Gobindaganj | 28.02.2017 | RDRIIP/GAI/ VR-459 | 132304027 | Improvement of Fashitola - Kayaganj Road (Ch. 2100-3100m). | 1 | 6483362 | Md. Ziaul Islam Methu | 6789578.63 | 08.06.2017 | 24.04.2018 | 100% | 6778905 | 6778905 |  | Final bill paid
Gobindaganj | 19.03.2017 | RDRIIP/GAI/ VR-523 | 132304150 | Improvement of Guga - Fulpukuria via Kalitola Road (Ch. 600-1250m). | 0.665 | 3931654 | Md. Shaharul Islam Titu, Gobindaganj, Gaibandha. | 4119190.83 | 15.06.2017 | 26.06.2018 | 100% | 4117308 | 4117308 |  | Final bill paid
Gobindaganj | 3 | RDRIIP/GAI/ VR-545 | 132305082 | Improvement of Satailbatail - Bara Sohagi WDB Road (Ch. 715-1500m). | 0.785 | 6844660.29 | M/S Shihab Construction, Gobindaganj, Gaibandha. | 7171734.22 | 05.07.2017 | 05.07.2018 | 100% | 7159507 | 7159507 |  | Final bill paid
Gobindaganj | 03.05.2017 | RDRIIP/GAI/ VR-555 | 132305247 | Improvement of Darbasta - Bogulagari Bazar Road -Kalitola High School via Zabber master house Road (Ch. 00-990m). | 0.99 | 6914151.21 | M/S Khandakar Enterprise. Gobindaganj, Gaibandha. | 7246079.2 | 10.07.2017 | 05.07.2018 | 100% | 7243983 | 7243983 |  | Final bill paid
Gobindaganj | 03.05.2017 | RDRIIP/GAI/ VR-556 | 132305058 | Improvement of Gopinathpur Bridge - Devpur Road via Singiani Govt. Primary School Road (Ch. 00-500m). | 0.5 | 3304399.95 | M/S Milu Traders. Gobindaganj, Gaibandha. | 3460316.24 | 10.07.2018 | 05.07.2019 | 100% | 3459498 | 3459498 |  | final bill paid
Sub-Total = |  | 23 |  |  | 18.392 | 120591827.45 | 23 | 126976639.02 |  |  | 100% | 126877987.05 | 126877987.05 | 0
Saghata | 03.04.2014 | RDRIIP/GAI/ VR-046 | 132885039 | Improvement of Badiakhali – Bonarpara GC – Raghobpur Telian Road (Ch. 00-1765m). | 1.765 | 2294099.98 | Md. Khaliur Rahman | 2294099.98 | 15.07.14 | 22.12.2014 | 100% | 2294099 | 2294099 |  | Final bill paid
Saghata | 13.06.2016 | RDRIIP/GAI/ VR-046(R) | 132885039 | Remaining work of Badiakhali – Bonarpara GC – Raghobpur Telian Road (Ch. 00-1765m). |  | 4918770 | Md. Khaybor Rahman | 5160383.87 | 30.10.2016 | 24.10.2017 | 100% | 5158307 | 5158307 |  | Final bill paid
Saghata | 23.07.2014 | RDRIIP/GAI/ VR-085 | 132884001 | Improvement of Bonarpara Railway stall – Kasiabari Ghat Road (Ch. 00-2190m). | 2.19 | 9794244 | Md. Khademul Islam Jewel | 8404225.32 | 11.11.2014 | 11.11.2015 | 100% | 8402915 | 8402915 |  | Final bill paid
Saghata | 05.11.2014 | RDRIIP/GAI/ VR-115 | 132885122 | Improvement of Bhutmara Bazar – Alai River near H/O Motin Engineer Road (1000 -1250m). | 0.25 | 1699501 | Md. Shamim Ahammed Mondal. | 1826695.36 | 08.03.2015 | 15.10.2015 | 100% | 1826691 | 1826691 |  | Final bill paid
Saghata | 05.11.2014 | RDRIIP/GAI/ VR-116 | 132885160 | Improvement of Bajit Nagar Bazar Charpra Adarsa Gram Road (1000 -1600m). | 0.6 | 3252701 | Md. Sahidul Islam. | 3480257.43 | 05.03.2015 | 14.10.2015 | 100% | 3479466 | 3479466 |  | Final bill paid
Saghata | 24.11.2014 | RDRIIP/GAI/ VR-131 | 132884019 | Improvement of Mandura - Bharatkhali Road (Ch. 00-1830m). | 1.83 | 8345043 | The Kanak & Kallal Engineering Workshop | 8325579 | 28.04.2015 | 28.01.2016 | 100% | 8315746 | 8315746 |  | Final bill paid
Saghata | 11.12.2014 | RDRIIP/GAI/ VR-136 | 132884026 | Improvement of Bonarpara – Saghata - Bilbosta Road (Ch. 1500-2380m). | 0.88 | 3930832 | Md. Rafiqul Islam | 3631640.96 | 15.03.2015 | 30.11.2015 | 100% | 3630906 | 3630906 |  | Final bill paid
Saghata | 06.01.2015 | RDRIIP/GAI/ VR-145 | 132884065 | Improvement of Bangla Bazar - Chorkata Bridge Road (Ch. 585-1085m). | 0.5 | 2488656 | M/S SR Traders | 2307619.72 | 23.04.2015 | 14.01.2016 | 100% | 2305132 | 2305132 |  | Final bill paid
Saghata | 06.01.2015 | RDRIIP/GAI/ VR-146 | 132244038 | Improvement of Buliarber GPS – Kamalerpara – Folia Pucca (Folia - Panchpur (Fokir Para) Road (Ch. 1780-2380m). | 0.6 | 2999848 | M/S SR Traders | 2810785.4 | 23.04.2015 | 15.06.2017 | 100% | 2808039 | 2808039 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-178 | 132884055 | Improvement of Bottola Bazar - Mothorpara (Bottola – Mothorpara west) Road (Ch. 00-500m). | 0.5 | 2886833 | Md Shamim Ahammed Mondol | 2674137.33 | 28.06.2015 | 15.03.2017 | 100% | 2668841 | 2668841 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-179 | 132884022 | Improvement of Mafurjan Road – Badiakhali - Saghata R&H Road (Ch. 00-500m). | 0.5 | 2108297 | Md. Touhidul Islam | 1999515.056 | 28.06.2015 | 10.05.2016 | 100% | 1997940 | 1997940 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-180 | 132884007 | Improvement of Kachua Hat Sluice Gate – Kalapani Embankment Road (Ch. 00-750m). | 0.75 | 3751196 | Md Shamim Ahammed Mondol | 3688869.9 | 23.06.2015 | 10.05.2016 | 100% | 3685695 | 3685695 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-181 | 132884011 | Improvement of Muktinagar – Boanarpara - Bharatkhali Road (Ch. 00-600m). | 0.6 | 2605349 | M/S SR Traders | 2601519.69 | 23.06.2015 | 15.05.2016 | 100% | 2596697 | 2596697 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-182 | 132884008 | Improvement of BWDB Embankment – Bogarvita via Bosonterpara Road (Ch. 00-500m). | 0.5 | 2468084 | Md. Khoybor Rahman | 2365758.77 | 23.06.2015 | 10.05.2016 | 100% | 2363833 | 2363833 |  | Final bill paid
Saghata | 26.02.2015 | RDRIIP/GAI/ VR-183 | 132884059 | Improvement of Badiakhali – Jumarbari – Jordoba Road (Ch. 3390-4115m, Effective Length = 717m). | 0.717 | 3919220 | The Kanak & Kallal Engineering Workshop | 4206245.42 | 05.07.2015 | 10.05.2016 | 100% | 4203460 | 4203460 |  | Final bill paid
Saghata | 07.08.2015 | RDRIIP/GAI/ VR-379 | 132884002 | Improvement of House of Mozammel - Bonarpara BRAC office Road (Ch. 00-600m). | 0.6 | 2904478 | SR Traders, Gaibandha. | 3021897.46 | 02.11.2016 | 14.11.2017 | 100% | 3020291 | 3020291 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-447 | 132884010 | Improvement of Beltali Pry.School - Kalapani Bridge Road (Ch. 2820-3850m). | 1.03 | 7476064 | SR Traders, Thana para, Gaibandha. | 7830723.16 | 08.06.2017 | 24.04.2018 | 100% | 7820468 | 7820468
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-448 | 132884036 | Improvement of Sadhur Assram RHD - Padum shahar Malipara Road (Ch. 1500-2000m). | 0.5 | 3193503 | Md. Rafiqul Islam | 3349952.92 | 24.05.2017 | 24.05.2018 | 100% | 3346075 | 3346075 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-449 | 132885185 | Improvement of Poragram main Road - Poragram Mondol bari Jame Mosque Road (Ch. 00-470m). | 0.47 | 2337112 | M/S Shazin Traders, Gaibandha.mirza rafiq | 2446796.16 | 08.06.2017 | 30-11-18 | 75% |  | 1570000 | 876796.16
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-451 | 132884039 | Improvement of Gorerpara - Kamalerpara Bazar Road (Ch. 00-500m). | 0.5 | 3529192 | Md. Amirul Islam Bablu, Bonarpara, Gaibandha. | 3687953.3 | 05.06.2017 | 30.11.18 | 100% |  | 3686439 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-452 | 132884065 | Improvement of Kachuahat FRB at Bangla bazar - Chorkatha bridge Road (Ch. 1085-1585m). | 0.5 | 3342894 | M/S SR Traders, Thanapara, Gaibandha | 3502045.47 | 08.06.2017 | 19.10.18 | 100% | 3500966 | 3500966 | 1079.47 | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-453 | 132884061 | Improvement of Trimohoni Khayaghat - Ullasonatola bazar Road (Ch. 1800-2300m). | 0.5 | 3138600 | Mirza Rafiqul Alam | 3282003.65 | 08.06.2017 | 30.12.18 | 75% |  | 2035937 | 1246066.65 | Problematic | 1750000 | 3785937
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-454 | 132885170 | Improvement of Kukrahat - Katlamari Bazar Road (Ch. 00-500m). | 0.5 | 2646297 | M/S FRB Enterprise | 2764107.83 | 08.06.2017 | 24.04.2018 | 100% | 2764101 | 2764101 |  | Final bill paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-455 | 132885196 | Improvement of Mofurjan Foot Bridge - Badiakhali Kazi bari Road (Ch. 00-500m). | 0.5 | 3021437 | Md. Azol Hauq, Gaibandha. | 3157362.99 | 18.05.2017 | 24.04.2018 | 100% | 3156626 | 3156626 |  | Final bill Paid
Saghata | 28.02.2017 | RDRIIP/GAI/ VR-456 | 132885204 | Improvement of Bati Mousa Bati Bridge - Moimontopur Madrasha Road (Ch. 00-500m). | 0.5 | 3171480 | Md. Amirul Islam Bablu, Bonarpara, Gaibandha. | 3313705.81 | 05.06.2017 | 10.9.18 | 100% | 3310764 | 3310764 |  | Final bill paid
Saghata | 19.03.2017 | RDRIIP/GAI/ VR-524 | 132885219 | Improvement of Uttar Satalia H/O Sattar - WAPDA Embankment Road (Ch. 00-730m). | 0.73 | 5353815.48 | Md. Farhadul Haque, Gaibandha. | 5610786.1 | 13.06.2017 | 20.11.18 | 100% | 5601018 | 5601018 |  | Final bill paid
Sub-Total = |  | 26 |  |  | 18.512 | 97577546.46 | 26 | 97744668.056 |  |  | 98.08% | 88258076 | 95550452 | 2123942.28
Fulchari | 03.11.2014 | RDRIIP/GAI/ VR-112 | 132214001 | Improvement of H/O Delwar Hossain - Chunakandi khea ghat Road (Ch. 00-500m). | 0.5 | 4264533 | Md. Shoheb Hossain Mona. | 4582976.52 | 22.02.2015 | 14.10.2015 | 100% | 4575886 | 4575886 |  | Final bill paid
Fulchari | 24.11.2014 | RDRIIP/GAI/ VR-132 | 132214016 | Improvement of Purba salua H/O Mozibar - H/O Osman munsi Road (Ch. 00-500m). | 0.5 | 2841251 | Md. Rashed Khan Manan | 2538201.01 | 11.03.2015 | 30.11.2015 | 100% | 2538200 | 2538200 |  | Final bill paid
Fulchari | 24.11.2014 | RDRIIP/GAI/ VR-133 | 132214019 | Improvement of Kator Govt . Primary school - Purba udakhali H/O Akbar hossain Road (Ch. 600-1100m). | 0.5 | 2515839 | Md. Rashed Khan Manan | 2246895.89 | 11.03.2015 | 30.11.2015 | 100% | 2246895 | 2246895 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-170 | 132214016 | Improvement of Purba Salua H/O Mozibar - H/O Osman munsi Road (Ch. 500-1000m). | 0.5 | 2765005 | Md. Rashed Khan Manan | 2339922.74 | 29.06.2015 | 06.04.2016 | 100% | 2271309 | 2271309 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-171 | 132214019 | Improvement of Kator Govt . Primary school - Purba udakhali H/O Akbar hossain Road (Ch. 00-600m). | 0.6 | 3434284 | Md. Rashed Khan Manan | 2928139.96 | 29.06.2015 | 06.04.2016 | 100% | 2443478 | 2443478 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-172 | 132214002 | Improvement of WAPDA Embankment near Chawdharypara - Mashervita Mosque Road (Ch. 2650-3250m). | 0.6 | 3100970 | Md. Rashed Khan Manan | 2642001.11 | 29.06.2015 | 06.04.2016 | 100% | 2641998 | 2641998 |  | Final bill paid
Fulchari | 23.02.2014 | RDRIIP/GAI/ VR-173 | 132215102 | Improvement of Singra road - Gonvori Road (Ch. 00-170.00m). | 0.17 | 1087691 | Md. Rashed Khan Manan | 907401.95 | 29.06.2015 | 06.04.2016 | 100% | 901265 | 901265 |  | Final bill paid
Sub-Total = |  | 7 |  |  | 3.37 | 20009573 | 7 | 18185539.18 |  |  | 100% | 17619031 | 17619031 | 0
Total = |  | 99 |  |  | 75.254 | 461739285.4 | 99 | 469361230.985 |  |  | 98.69% | 448710764.05 | 456802918.05 | 10668849.59
Total Road = |  | 149 |  |  | 140.509 | 916418176.55 | 149 | 928182374.479 |  |  | 96.67% | 875903723.05 | 888090968.05 | 27568431.45
4. Construction of Bridge/Culvert on Upazila road:
Saghata | 28.03.2016 | RDRIIP/GAI/ BR-016 | 132882001 | Construction of 39 m Long RCC Girder Bridge on Badiakhali R&H Road - Jumarbari GC Road at Ch.15403m. | 39 | 20074854 | AH-KJ (JV) Gaibandha. | 17079068.11 | 17.07.2016 | 31.12.2017 | 100% | 17018860 | 17018860 |  | Final bill paid
Sub-Total = |  | 1 |  |  | 39 | 20074854 | 1 | 17079068.11 |  |  | 100% | 17018860 | 17018860 | 0
Total = |  | 1 |  |  | 39 | 20074854 | 1 | 17079068.11 |  |  | 100% | 17018860 | 17018860 | 0
5. Construction of Bridge/Culvert on Union road:
Sadar | 21.10.2015 | RDRIIP/GAI/ BR-005 | 132243016 | Construction of 100.00m Long RCC Girder Bridge over Ghagoat River on Gidari UP Office - Dariapur GC (Badshar Ghat) Road at Ch.3465m | 100 | 53658135 | M/S Basundhara R.K Road, Ghoshpara, Kurigram Sadar, Kurigram. | 46693694.09 | 06.03.2016 | 13.07.2017 | 80% |  | 32172574 | 14521120.09
Sub-Total = |  | 1 |  |  | 100 | 53658135 | 1 | 46693694.09 |  |  | 80% | 0 | 32172574 | 14521120.09
Total = |  | 1 |  |  | 100 | 53658135 | 1 | 46693694.09 |  |  | 80% | 0 | 32172574 | 14521120.09
6. Construction of Bridge/Culvert on Village road:
Sundarganj | 30.05.2016 | RDRIIP/GAI/ BR-021 | 132914097 | Construction of 45.00m Long RCC Girder Bridge over Lahangga Channel on Kalitola (RHD) – Bamondangha South rail gate (Bypass) raod at Ch. 700.00m. | 45 | 20975135 | M/S Anisur Rahman Chowdhury & S.M Rashed Hossain JV, Rangpur. | 17722348 | 30.10.2016 | 30.12.18 | 85% |  | 12746855 | 4975493
Sub-Total = |  | 1 |  |  | 45 | 20975135 | 1 | 17722348 |  |  | 85% | 0 | 12746855 | 4975493
Total = |  | 1 |  |  | 45 | 20975135 | 1 | 17722348 |  |  | 85% | 0 | 12746855 | 4975493
Total Bridge/Culvert = |  | 3 |  |  | 184 | 94708124 | 3 | 81495110.2 |  |  | 88.33% | 17018860 | 61938289 | 19496613.09
7.Road maintenance works:
Sundarganj | 25.07.2016 | RDRIIP/GAI/ M-027 | 132913001 | Maintenance of Mirgonj Mazipara (More) - Tarapur Road (Ch. 00-3609m). | 3.609 | 10293615 | M/S Ovijatrik Construction, Jamalpur. | 8498099.8 | 02.11.2016 | 24.10.2016 | 100% | 8486155 | 8486155 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 3.609 | 10293615 | 1 | 8498099.8 |  |  | 100% | 8486155 | 8486155 | 0
Saghata | 23.10.2014 | RDRIIP/GAI/ M-001 | 132882001 | Maintenance of Badiakhali Bridge R&H – Jumarbari Hat GC Road (Ch. 00-3575m). | 3.575 | 15870180 | Md. Abdul Latif Hakkani. | 17108127.2 | 24.02.2015 | 28.01.2016 | 100% | 17077863 | 17077863 |  | Final bill Paid
Saghata | 23.10.2014 | RDRIIP/GAI/ M-002 | 132882001 | Maintenance of Badiakhali Bridge R&H – Jumarbari Hat GC Road (Ch. 4600-8121m). | 3.521 | 13850254 | Md. Khalilur Rahman. | 14923519.77 | 10.03.2015 | 28.01.2016 | 100% | 14905949 | 14905949 |  | Final bill Paid
Sub-Total = |  | 2 |  |  | 7.096 | 29720434 | 2 | 32031646.97 |  |  | 100% | 31983812 | 31983812 | 0
Fulchari | 26.10.2014 | RDRIIP/GAI/ M-003 | 132212003 | Maintenance of Fulchari Upazila H.Q - Modenerpara R&H Road.(Ch.00-330m & Ch.3611m- 6180m). | 2.899 | 7222580 | Md. Rashed Khan Manan. | 7764259.14 | 03.05.2015 | 29.10.2015 | 100% | 7758295 | 7758295 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 2.899 | 7222580 | 1 | 7764259.14 |  |  | 100% | 7758295 | 7758295 | 0
Gobindaganj | 06.08.2015 | RDRIIP/GAI/ M-004 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 00-3000m). | 3 | 6148462 | Md. Khademul Islam Jewel. | 5372701.65 | 10.11.2015 | 30.05.2016 | 100% | 5372273 | 5372273 |  | Final bill Paid
Gobindaganj | 06.08.2015 | RDRIIP/GAI/ M-005 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 3000-5150m & 7120-7400m). | 2.43 | 6158493 | Md. Khademul Islam Jewel. | 5372676 | 10.11.2015 | 30.05.2016 | 100% | 5283001 | 5283001 |  | Final bill Paid
Gobindaganj | 06.08.2015 | RDRIIP/GAI/ M-006 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 7400-10400m). | 3 | 7323302 | Md. Khademul Islam Jewel. | 6341565.17 | 10.11.2015 | 30.05.2016 | 100% | 6327877 | 6327877 |  | Final bill Paid
Gobindaganj | 23.10.2014 | RDRIIP/GAI/ M-007 | 132302001 | Maintenance of Gobindagonj - Mohimagonj Road (Ch. 10400-12750m). | 2.35 | 5987891 | Md. Khademul Islam Jewel. | 5192466.58 | 10.11.2015 | 30.05.2016 | 100% | 5187895 | 5187895 |  | Final bill Paid
Sub-Total = |  | 4 |  |  | 10.78 | 25618148 | 4 | 22279409.4 |  |  | 100% | 22171046 | 22171046 | 0
Sadar | 25.11.2015 | RDRIIP/GAI/ M-014 | 132242001 | Maintenance of Gaibandha - Laxmipur Road (Ch. 00-5500m). | 5.5 | 11519318 | Md. Abdul Latif Hakkani. | 12064159.04 | 08.03.2016 | 01.03.2017 | 100% | 12049125 | 12049125 |  | Final bill Paid
Sadar | 25.11.2015 | RDRIIP/GAI/ M-015 | 132242001 | Maintenance of Gaibandha - Laxmipur Road (Ch. 5500-11760m). | 6.26 | 11660550 | Md. Saidur Rahaman | 12212062.91 | 08.03.2016 | 01.03.2017 | 100% | 12197906 | 12197906 |  | Final bill Paid
Sub-Total = |  | 2 |  |  | 11.76 | 23179868 | 2 | 24276221.95 |  |  | 100% | 24247031 | 24247031 | 0
Total = |  | 10 |  |  | 36.144 | 96034645 | 10 | 94849637.26 |  |  | 100% | 94646339 | 94646339 | 0
8. Off pavement road maintenance (LCS women):
Sundarganj | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi my›`iMÄ Dc‡Rjvaxb 15wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 283.8333 | 17030000 | LCS | 16423371 | 01.07.2015 | 30.06.2017 | 100% | 16423371 | 16423371 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 283.8333 | 17030000 | 1 | 16423371 |  |  | 100% | 16423371 | 16423371 | 0
Sadar | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi m`i Dc‡Rjvaxb 13wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 246.8 | 14808000 | LCS | 11662028 | 01.07.2015 | 30.06.2017 | 67% | 11662028 | 11662028 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 246.8 | 14808000 | 1 | 11662028 |  |  | 67% | 11662028 | 11662028 | 0
Sadullapur | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi mv`yjøvcyi Dc‡Rjvaxb 11wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 209.7667 | 12586000 | LCS | 11180306 | 01.07.2015 | 30.06.2017 | 100% | 11180306 | 11180306 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 209.7667 | 12586000 | 1 | 11180306 |  |  | 100% | 11180306 | 11180306 | 0
Palalshbari | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi cjvkevox Dc‡Rjvaxb 9wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 172.7333 | 10364000 | LCS | 9245133 | 01.07.2015 | 30.06.2017 | 100% | 9245133 | 9245133 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 172.7333 | 10364000 | 1 | 9245133 |  |  | 100% | 9245133 | 9245133 | 0
Gobindaganj | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi ‡Mvwe›`MÄ Dc‡Rjvaxb 17wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 320.8667 | 19252000 | LCS | 18958854 | 01.07.2015 | 30.06.2017 | 100% | 18958854 | 18958854 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 320.8667 | 19252000 | 1 | 18958854 |  |  | 100% | 18958854 | 18958854 | 0
Saghata | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi mvNvUv Dc‡Rjvaxb 10wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 191.25 | 11475000 | LCS | 10800914 | 01.07.2015 | 30.06.2017 | 100% | 10800914 | 10800914 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 191.25 | 11475000 | 1 | 10800914 |  |  | 100% | 10800914 | 10800914 | 0
Fulchari | 14.06.2016 | RDRIIP/GAI/ LCS-56 |  | MvBevÜv †Rjvi dzjQwo Dc‡Rjvaxb 7wU BDwbq‡bi MÖvgxY `yt¯’ gwnjv‡`i Øviv moK iÿYv‡eÿY KvR¦ | 135.7 | 8142000 | LCS | 7008190 | 01.07.2015 | 30.06.2017 | 100% | 7008190 | 7008190 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 135.7 | 8142000 | 1 | 7008190 |  |  | 200% | 7008190 | 7008190 | 0
Total = |  | 7 |  |  | 1560.95 | 93657000 | 7 | 85278796 |  |  | 95.29% | 85278796 | 85278796 | 0
10. Tree plantation:
Sadar | 13.07.2014 | RDRIIP/GAI/ TR-003 | 132243014 | Tree Plantation work of Badiakhali UP office – Farazkhan Bazar road (Ch. 1000-2000m). | 1 | 150000 | LCS women | 150000 |  |  | 100% | 150000 | 150000 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 1 | 150000 | 1 | 150000 |  |  | 100% | 150000 | 150000 | 0
Sadullapur | 27.07-2015 | RDRIIP/GAI/TR-031 | 132822004 | Tree Plantation work of Jamlarjan – Thutiapukur via Pachar Bazar GC road (Ch. 1000-2000m). | 1 | 150000 | LCS women | 150000 |  |  | 100% | 150000 | 150000 |  | Final bill Paid
Sadullapur | 27.07.2015 | RDRIIP/GAI/TR-032 | 132822006 | Tree Plantation work of Rahmatpur GC – Majumdarhat GC via Naldanga GC road (Ch. 2000-3000m). | 1 | 150000 | LCS women | 150000 |  |  | 100% | 150000 | 150000 |  | Final bill Paid
Sub-Total = |  | 2 |  |  | 2 | 300000 | 2 | 300000 |  |  | 100% | 300000 | 300000 | 0
Palalshbari | 27.07.2015 | RDRIIP/GAI/TR-033 | 132672001 | Tree Plantation work of Palashbari Upazila H/Q – Fakirhat GC road (Ch. 4700-5900m). | 1.2 | 156900 | LCS women | 156900 |  |  | 100% | 156900 | 156900 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 1.2 | 156900 | 1 | 156900 |  |  | 100% | 156900 | 156900 | 0
Gobindaganj | 08.07.2014 | RDRIIP/GAI/ TR-002 | 132303011 | Tree Plantation work of Gumanigonj UP – Upazila H/Q (Post Office) via Kalikadoba road (Ch. 986-2986m). | 2 | 300828 | LCS women | 300828 |  |  | 100% | 300828 | 300828 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 2 | 300828 | 1 | 300828 |  |  | 100% | 300828 | 300828 | 0
Fulchari | 02-08-2015 | RDRIIP/GAI/ TR-034 | 132214001 | Tree Plantation work of H/O Delwer Hossain – Chunakandi Khea Ghat road (Ch. 00-1400m). | 1.4 | 271600 | LCS women | 271600 |  |  | 100% | 166324.95 | 166324.95 |  | Final bill Paid
Sub-Total = |  | 1 |  |  | 1.4 | 271600 | 0 | 271600 | 0 | 0 | 1 | 166324.95 | 166324.95 | 0
Total = |  | 6 |  |  | 7.6 | 1179328 | 5 | 1179328 |  |  | 120% | 1074052.95 | 1074052.95 | 0
Total (Tender) = |  | 162 |  |  |  | 1107160945.55 | 162 | 1104527121.939 |  |  | 95% | 987568922.05 | 1044675596.05 | 47065044.54
Total (LCS woman) = |  | 7 |  |  |  | 93657000 | 7 | 85278796 |  |  | 95.29% | 85278976 | 85278976 | 0
Total (Tree plantation) = |  | 6 |  |  |  | 1179328 | 5 | 1179328 |  |  | 120% | 1074052.95 | 1074052.95 | 0
District Total (All) = |  | 175 |  |  |  | 1201997273.55 | 174 | 1190985245.939 |  |  | 103.4% | 1073921951 | 1131028625 | 47065044.54 |  | 6908196
[7 empty] | Total Fund Received | [5 empty] | 1140125382
[7 empty] | Balance | [5 empty] | 9096757