## Gaibandha
Contract Status of Flood & Disaster Damaged Rural Road Infrastructure Rehabilitation Project (FDDRIRP), FY: 2018-2019
District : |  | Gaibandha | [14 empty] | Date of Reporting: | 2026-08-05
Sl. No. | Name of Upazila | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Contract's Name | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progr. (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
A. Rehabilitation Road [Strengthening/Widening]
1 | Shaghata | W01 | 1 | 132882003 | Bonar Para GC (Bonar Para college)-Shankorgonj kheyaghat rd (Nakaihat GC) | M/S Dalia Trading, House No. 40, Road No.1/1, JNC Road, East Gupt apara, Rangpur-5400 | 0 | 3575 | 3575 | 16768998 | 15930548.1 | 4850000 | 2018-07-22 | 2019-05-30 | 941% | 70% | Time Expired |  |  | 312 | 2936
2 | Shaghata | W02 | 1 | 132883001 | Saghata GC-Kachua UP Office via Ullah Sonatala Bazar | Md. Atiqur Rahman Kishamat Malibari, Dariapur, Gaibandha Sadar, Gaibandha | 0 | 2465 | 2465 | 11405463 | 10835189.85 | 3800000 | 2018-07-17 | 2019-01-14 | 1625% | 70% | Time Expired |  |  | 181 | 2941
3 | Gobindaganj | W03 | 1 | 132303020 | Salmara UP - Sonatola Upazila via Heatpur | M/S Dalia Trading, House No. 40, Road No.1/1, JNC Road, East Gupt apara, Rangpur-5400 | 3920 | 5080 | 1160 | 4873986 | 4630286.7 | 4623560 | 2018-07-22 | 2019-03-30 | 1170% | 100% | - | Final Bill Paid |  | 251 | 2936
4 | Sundarganj | W04 | 1 | 132912008 | Bamandangha R&H - Luxmipur GC Via Naldanga G.C & Dhupadangha UP Road.(Sundarganj Upazila part ch.0.00-4.800 & 7.650-10.938)km | Md. Matlubour Rahman, Gaibandha | 0 | 4800 | 4800 | [5 empty] | - |  | - |  |  | 0 | -
[7 empty] | 7650 | 10938 | 3288 | 43262795 | 41235562.578 | 5500000 | 2018-06-08 | 2019-06-30 | 770% | 40% | Time Expired |  |  | 387 | 2980
5 | Sadullapur | W05 | 1 | 132822002 | Sadullapur -Naldanga GC Road | M/S. Md. Rabiul Alam (Bulbul) | 2650 | 6078 | 3428 | [5 empty] | - |  | - |  |  | 0 | -
[7 empty] | 7287 | 10955 | 3668 | 46067785 | 40538436.158 | 10650000 | 2018-08-18 | 2019-07-30 | 840.8% | 35% | Time Expired |  |  | 346 | 2909
6 | Palashbari | W06&W08 | 1 | 132673002 | Kalibari GC at cinema hall-chattra UP office Road [Length=9.50km] | M/S Shihab Construction, Gobindaganj, Gaibandha | 0 | 2000 | 2000 | 2889422 | 2744950 | 1500000 | 2019-01-09 | 2019-05-29 | 1975% | 75% | Time Expired |  |  | 140 | 2765
|  |  | 2 | 132672007 | Satarpara RHW-Fakirhat GC Road | M/S Shihab Construction, Gobindaganj, Gaibandha | 0 | 4750 | 4750 | 7760165 | 7372156.75 | 500000 | 2019-01-09 | 2019-05-29 | 1975% | 25% | Time Expired |  |  | 140 | 2765
|  |  | 3 | 132672009 | Komorpur GC-Marirhat GC Road via sahindaha | M/S Shihab Construction, Gobindaganj, Gaibandha | 0 | 1580 | 1580 | 4785734 | 4546447.3 | 1500000 | 2019-01-09 | 2019-05-29 | 1975% | 100% | - |  |  | 140 | 2765
7 | Sadullapur | W10 | 1 | 132825009 | Sadullapur Naldanga Road - Kismat Khejur via maruadaha | Rabbi Ent. Pirganj, Rangpur | 0 | 1875 | 1875 | 6432417 | 6110796.15 |  | 2019-04-02 | 2019-08-02 | 2198% | 10% | Time Expired |  |  | 122 | 2682
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
7 | Sub-Total (A): | 0 | 9 |  | Not Contacted Amount | 0 |  |  | 32.589 | 144246765 | 133944373.586 | 32923560 | Fin. Pgr. (%) | 24.58% |  | 47.12%
B. Rehabilitation Structure [Bridges/Culverts]
1 | Gobindaganj | BW09 | 1 | 132304129 | Mohimagonj UP - Bishpukur Naya Bazar via Balua | Mokaddes Ali Badu, Gobindaganj, Gaibandha | 130 | 160 | 30 | 22815685 | 22808061.79 |  | 2019-03-25 | 2020-03-02 | 784.3% | 10% | Time Expired |  |  | 343 | 2690
2 | Gobindaganj | BW11 | 1 | 132302014 | Mohimagonj GC-Bonarpra GC (Shaghata) Road | Mokaddes Ali Badu, Gobindaganj, Gaibandha JV | 2160 | 2180 | 20 | 16560415 | 16521439.66 |  | 2019-04-29 | 2020-04-09 | 767.3% | 0% | Time Expired |  |  | 346 | 2655
3 | Gobindaganj | BW12 | 1 | 132303025 | Katabari U.P-Bagulagari hat |  | 2290 | 2320 | 30 | 26164467 |  |  |  |  | - |  | - | NOA |  | 0 | -
4 | Shaghata | BW13 | 1 | 132884060 | Helencha FRB - Bati Road |  | 423 | 443 | 20 | 20148392 |  |  |  |  | - |  | - | Tender receive date 06/05/19 |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
4 | Sub-Total (B): | 2 | 4 |  | Not Contacted Amount | 46312859 |  |  | 100 | 85688959 | 39329501.45 | 0 | Fin. Pgr. (%) | - |  | 0.057992
11 | Grand Total: | 2 | 13 |  | Not Contacted Amount | 46312859 |  |  |  | 229935724 | 173273875.036 | 32923560 | Fin. Pgr. (%) | 19% |  | 37.74% |  |  |  | Apr
Fund Received: | [5 empty] | Structure | 100 | m | Road | 32.589 | km |  |  |  |  | Cash in Hand: |  | 7076440
Date: | 2019-10-15 |  | 2019-03-14 | [14 empty] | Total:
Tk. | 20000000 |  | 20000000 | [14 empty] | 40000000
Comments if any:
[12 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  |  | Amount Required upto June (Tk.)
Gaibandha Sadar
Gobindaganj
Fulchhari
Palashbari
Sadullapur
Shaghata
Sundarganj