## Gaibandha
Contract Status of Rural Road Maintenance (GoB Maintenance), FY: 2018-2019
District : |  | Gaibandha | [14 empty] | Date of Reporting: | 2019-05-05
Sl. No. | Category of Maintenance | e-Tender ID No. Package No. (If any) | Sch. Sl. No. Under Pack. | Road ID No. | Road Name | Name of Contractor | Start Chainage (m) | End Chainage (m) | Effective Length (m) | Gross Estimated Cost (Taka) | Contract Amount (Taka) | Amount Paid (Taka) | Work Start Date (As per Contract) | Work Completion Date (As per Contract) | Elapse Day (%) | Phy. Progr. (%) | Contract Delayed Status | Activity/ Remarks/ Date |  | Stipulated Day | Elapse Day
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Upazila: |  | 1. Gaibandha Sadar
1 | Re-Seal | 233956 | 1 | 132243003 | Shahar Bazar-Shahapara UP office Road | Name : M/S Sadia Enterprise , Gaibandha sadar | 0 | 5850 | 5850 | 8977095 | 8528240.25 | 8526335 | 2018-12-29 | 2019-03-28 | 142.7% | 100% | - | Final Bill Paid |  | 89 | 127
2 | Re-Seal | 233957 | 1 | 132243006 | Shahapara UP office-Mirpur Bazar Road | Emtiaz hakkani, Gaibandha sadar | 0 | 4560 | 4560 | 7295494 | 693019.3 | 6923948 | 2018-12-30 | 2019-03-16 | 165.8% | 100% | - | Final Bill Paid |  | 76 | 126
3 | Re-Seal | 233895 | 1 | 132243015 | Ramchandrapur U.P Office-Tindaha Bazar Road | M/S SHAMIM ENTERPRISE, DAVID COMPANY PARA, POST+ UPAZILA+ DISTRICT: GAIBANDHA | 0 | 790 | 790 | 1838843 | 1746900.85 |  | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - |  |  | 61 | 140
4 | Re-Seal | 233951 | 1 | 132244009 | Kabirerpara-Kazdah Road | M/s Shazin Traders,Gaibandha sadar | 0 | 1000 | 1000 | 3514560 | 3338832 | 3335123 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
5 | Re-Seal | 233950 | 1 | 132244013 | Ramchandrapur-Radhakrisnowpur Road | RSL Ent. Gaibandha sadar | 0 | 1175 | 1175 | 3458609 | 3285678.55 | 3285673 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
6 | Re-Seal | 233897 | 1 | 132244024 | Mirpur Bazar-Majhipara Road | Md. Abdur Razzak Address: Chalkmamrojpur, Khanka Shorif, Gaibandha | 0 | 550 | 550 | 1796249 | 1706436.55 | 800000 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - |  |  | 61 | 141
7 | Re-Seal | 233896 | 1 | 132244063 | Sadar Upazila H/Q-Thansinghpur Kachari Road | Abu Sayed Mahbub, Gaibandha sadar | 0 | 1100 | 1100 | 2051413 | 1948842.35 | 1944426 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
8 | Over-Lay | 233964 | 1 | 132242006 | Laxmipur-Kamarjani Road | M/S. Prodip and Brothers, Prop: Prodip Kumar Sarker, Vill: Sundarganj, Post: Sundarganj, Upazila: Sundarganj, Dist: Gaibandha | 6000 | 9000 | 3000 | 9145762 | 8688473.9 | 7280000 | 2019-01-06 | 2019-04-06 | 132.2% | 100% | - |  |  | 90 | 119
9 | Over-Lay | 233965 | 1 | 132242006 | Laxmipur-Kamarjani Road | Mamun ent. Gaibandha sadar | 9000 | 12500 | 3500 | 10186818 | 9677477.1 | 9670943 | 2018-12-26 | 2019-03-25 | 146.1% | 100% | - | Final Bill Paid |  | 89 | 130
10 | Over-Lay | 233928 | 1 | 132243021 | Malaibari UP office to Nutun Bandar Bazar Road | RSL Ent., Gaibandha sadar | 0 | 1410 | 1410 | 2981754 | 2832666.3 | 2832627 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
11 | Over-Lay | 233927 | 1 | 132245035 | DC Road (Bottola) to Wapda Embankment Road | M/S Nawrin Enterprise Address: Professor Colony, College Road, Gaibandha | 2220 | 2742 | 522 | 1300849 | 1235806.55 | 1214914 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
12 | CO Road | 132317 | 1 | 132242005 | Nurulganj Hat - Fakirer Hat Road | M/s Shafiq Traders, pabna | 0 | 3235 | 3235 | 968323 | 968323 | 961297 | 2018-01-09 | 2018-03-26 | 632.9% | 100% | - |  |  | 76 | 481
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
12 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 26.692 | 53515769 | 44650696.7 | 46775286 | Fin. Pgr. (%) | 104.8% |  | 100%
Upazila: |  | 2. Gobindaganj
1 | Re-Seal | 233939 | 1 | 132303021 | Shibpur U.P(at Baro Tikuri) - Chandpur (at R&H) via Gheedangha hat Road | Mukitur Rahman Rafi, Gobindaganj, gaibandha | 3946 | 6300 | 2354 | 4240026 | 4028024.7 |  | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - |  |  | 59 | 124
2 | Re-Seal | 233940 | 1 | 132303026 | Katabari UP-Bairagir Hat Road via Kathal bari Road | HR Enterprise, Gobindapur, Gobindaganj, Gaibandha | 4300 | 5677 | 1377 | 3066201 | 2912890.95 | 2911531 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - | Final Bill Paid |  | 59 | 124
3 | Re-Seal | 233941 | 1 | 132303039 | Kamdia UP-Bindhara GC Road | M/s Silvee & Shahi Traders, Aligram, Gobindaganj, Gaibandha | 0 | 2272 | 2272 | 4878188 | 4634278.6 | 4634194 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
4 | Re-Seal | 233942 | 1 | 132303040 | Mohimagonj UP Office (at Railway station)- Badiakhali Jumar bari GC (UZR) at Hapania up to Satitola ghat (Gobindagonj part ) Road | Ferdous Bari, Sadullapur | 0 | 1740 | 1740 | 3903522 | 3708345.9 | 3705915 | 2018-12-30 | 2019-03-01 | 206.6% | 100% | - | Final Bill Paid |  | 61 | 126
5 | Re-Seal | 233943 | 1 | 132304044 | Shakahar-Daihara Road | M/s Azad Construction, Gobindaganj, Gaibandha | 0 | 2045 | 2045 | 4769803 | 4531312.5 | 4530002 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - | Final Bill Paid |  | 59 | 124
6 | Re-Seal | 233944 | 1 | 132304141 | Talukkanupur UP at NHW Samaspara-Jamalpur hat Road | HR Enterprise, Gobindapur, Gobindaganj, Gaibandha | 0 | 1275 | 1275 | 4585924 | 4356627.8 |  | 2019-01-01 | 2019-03-01 | 210.2% | 35% | Time Expired |  |  | 59 | 124
7 | Re-Seal | 233945 | 1 | 132305031 | NHW Mugaltuli ( near Petrol pump)- Kamardah Road | Ferdous Bari, Sadullapur | 0 | 2000 | 2000 | 4919832 | 4673840.4 | 4654427 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - | Final Bill Paid |  | 59 | 124
8 | Over-Lay | 233962 | 1 | 132302016 | Gobindaganj-Gaibandha RHD at Shaghata bridge-Bonarpara GC (Up to Trimohani ghat) via Amtoli bazar Road | Ziaul Islam Methu, Gobindaganj, Gaibandha | 1500 | 4200 | 2700 | 5270842 | 5007299.9 |  | 2018-12-30 | 2019-03-17 | 163.6% | 50% | Time Expired |  |  | 77 | 126
9 | Over-Lay | 233909 | 1 | 132303007 | Rajahar U.P (at Banaswar bazar) - Fulpukuria Bazar (at UZR Road) Road | Khademul Islam, Gaibandha | 0 | 986 | 986 | 2071929 | 1968332.55 | 1847434 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - |  |  | 61 | 141
10 | Over-Lay | 233910 | 1 | 132303014 | Kamardaha U.P (NHW)-Choyghoria bazar Road | Khandakar Ent. Gobindaganj, Gaibandha | 5650 | 6650 | 1000 | 2296047 | 2293980.58 | 2292526 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
11 | Over-Lay | 233963 | 1 | 132303018 | Salmara UP (at Raiway station) -Kochashahar Bazar Road | Rezanul Habib rofiq, Gobindaganj, Gaibandha | 0 | 6633 | 6633 | 6197537 | 5887660.15 |  | 2019-01-07 | 2019-03-22 | 159.5% | 40% | Time Expired |  |  | 74 | 118
12 | Over-Lay | 233911 | 1 | 132303031 | Nakai UP (Paikor vita RHD) - Katakhili Balua hat via Jamalpur hat Road | Shahidul Islam ,Gaibandha | 8750 | 9750 | 1000 | 2403553 | 2283375.35 | 2282198 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
13 | Over-Lay | 233912 | 1 | 132304009 | Brinchi-Uthabi Road (at Pera Borogram) Road | Milu Traders, Gobindaganj, Gaibandha | 0 | 1050 | 1050 | 2068808 | 2066739.192 | 2066731 | 2018-12-30 | 2019-03-01 | 206.6% | 100% | - | Final Bill Paid |  | 61 | 126
14 | Over-Lay | 233913 | 1 | 132304041 | Mohimagonj-Ziboinpur School via (H/O maznue Chairman) Road | M/S Aishi traders Address: Gobindaganj,Gaibandha | 0 | 1200 | 1200 | 2252606 | 2250128.133 | 2249434 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - | Final Bill Paid |  | 59 | 124
15 | Over-Lay | 233915 | 1 | 132304047 | Kata-Birt Road at Peara-Panitola hat Road via Gopalpur Road | M/s Eglu Ent.Gobindaganj,Gaibandha | 0 | 770 | 770 | 1565214 | 1564431.393 | 1564387 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
16 | Over-Lay | 233918 | 1 | 132304056 | R&H at Howakhana-Futanir bazer Road | Shemul Ent. Holding# o, Gobindopur jilpar,Gobindogonj.,Gaibandha | 0 | 547 | 547 | 1124192 | 1123124.018 | 1122682 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
17 | Over-Lay | 233919 | 1 | 132304057 | R&H at Chaprigonj-Ghoramara School Via Rousulpur Road | M/s Linkon traders | 2830 | 3330 | 500 | 1373862 | 1372144.673 | 1370982 | 2018-12-30 | 2019-03-01 | 206.6% | 100% | - | Final Bill Paid |  | 61 | 126
18 | Over-Lay | 233921 | 1 | 132304085 | R&H at Chandipur-Birahimpur Rd.via H/O Shidul Chairman Road | Semul Ent. ,Gobindogonj.,Gaibandha | 0 | 500 | 500 | 1516996 | 1515691.383 | 1513325 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
19 | Over-Lay | 233916 | 1 | 132304115 | Bhagdaria Hindowpara-Palashbari via Nachaikochai Road | Shahidul Islam, .,Gaibandha | 0 | 1118 | 1118 | 2763848 | 2625655.6 | 2625027 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
20 | Over-Lay | 233917 | 1 | 132304219 | Kamdia-Punchbibi (UZR) Road - Biala Matrai GC Road via Aligram Road | M/s NR Traders, Gobindogonj.,Gaibandha | 0 | 595 | 595 | 1514949 | 1513358.304 | 1507648 | 2018-12-26 | 2019-02-25 | 213.1% | 100% | - | Final Bill Paid |  | 61 | 130
21 | Over-Lay | 233920 | 1 | 132305068 | Potter bar - Sitalgram Road | Shahidul Islam.,Gaibandha | 0 | 1000 | 1000 | 2090073 | 1985569.35 |  | 2018-12-16 | 2019-02-15 | 229.5% | 30% | Time Expired |  |  | 61 | 140
22 | Over-Lay | 233922 | 1 | 132305071 | Baratickry-Taranipara Rd. Via Para kachua Road | Shamsul Islam., Gobindagajn Gaibandha | 0 | 600 | 600 | 1492843 | 1491648.726 | 1490078 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
23 | Over-Lay | 233926 | 1 | 132305088 | Mogaltoli Girls high school-Rasulpur Road | Bikash Garments, Gobindogonj.,Gaibandha | 660 | 1612 | 952 | 2565904 | 2437608.8 | 2200000 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - |  |  | 61 | 127
24 | CO Road | 171490 | 1 | 132303022 | Mohimagonj Railway Station at (Jirai) - Baria Hat via Buraburi Hat Road | M/s Shazin Traders, .,Gaibandha | 870 | 3325 | 2455 | 3808003 | 3808003 | 3807779 | 2018-04-16 | 2018-06-16 | 629.5% | 100% | - |  |  | 61 | 384
25 | CO Road | 171491 | 1 | 132303023 | Darbasta UP (at Kalitola) - Bogulagari Bazar Road | M/s Anjum Enterprise,Gobindogonj.,Gaibandha | 0 | 5470 | 5470 | 621169 | 621169 | 609531 | 2018-04-28 | 2018-07-28 | 408.8% | 100% | - |  |  | 91 | 372
26 | CO Road | 188326 | 1 | 132304057 | R&H at Chaprigonj - Ghoramara School via Rousulpur Road | M/s Linkon traders, Gobindogonj.,Gaibandha | 0 | 2830 | 2830 | 6541536 | 6541536 | 6540154 | 2018-05-28 | 2018-08-13 | 444.2% | 100% | - |  |  | 77 | 342
27 | CO Road | 188328 | 1 | 132304129 | Mohimaganj UP - Bishpukur Naya Bazar via Balua Road | NR traders, Gobindogonj.,Gaibandha | 0 | 1920 | 1920 | 523102 | 523102 | 503878 | 2018-06-04 | 2018-08-04 | 549.2% | 100% | - |  |  | 61 | 335
28 | CO Road | 171489 | 1 | 132303021 | Shibpur U.P(at Baro Tikuri) - Chandpur (at R&H) via Gheedangha hat Road | M/S Shazin Traders, Gaibandha | 0 | 185 | 185 | 640373 | 640373 | 640373 | 2018-04-16 | 2018-06-24 | 556.5% | 100% | - | Final Bill Paid |  | 69 | 384
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
28 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 47.074 | 81066882 | 78366251.952 | 56670236 | Fin. Pgr. (%) | 72.31% |  | 86.91%
Upazila: |  | 3. Fulchhari
1 | Re-Seal | 233955 | 1 | 132212003 | Fulchari Upazila H/Q-Modonerpara R&H Road | BB Traders, gaibandha sadar | 3610 | 6180 | 2570 | 5102065 | 4846961.75 | 4837773 | 2018-12-29 | 2019-03-14 | 169.3% | 100% | - | Final Bill Paid |  | 75 | 127
2 | Re-Seal | 233888 | 1 | 132213005 | Kanchipara UP H/Q-Ketkir hat Road | Rashed Khan Menon, fulchori | 0 | 1650 | 1650 | 2401044 | 2280991.8 | 2247488 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
3 | Re-Seal | 233889 | 1 | 132214019 | Kator Govt. Primary school-purba udakhali H/O Akbar hossain Road | Ananda chal Ata kol, fulchori | 0 | 1030 | 1030 | 1112315 | 1056699.25 | 1051773 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
4 | Over-Lay | 233906 | 1 | 132214001 | Pachim Salua Mazar shorif( H/O Delwar Hossain )-Chunakandi khea ghat Road | Shamim mondol, saghata | 0 | 428 | 428 | 1677393 | 1593523.35 | 1545306 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
5 | Over-Lay | 233905 | 1 | 132214042 | Fulchari Zila parishad Dakbanglo - Salua Eid gah mat Road | M/S SHANTI TRADERS Address: Vill: Paschimpara, Word No. 02, Gaibandha Sadar, Gaibandha. | 0 | 655 | 655 | 2100331 | 1995314.45 | 1980434 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
6 | CO Road | 171486 | 1 | 132213006 | Urai UP H/Q - WAPDA Embk via Mosamari Bazar Road | SS Engineering,Gaibandha | 500 | 1135 | 635 | 647346 | 647346 | 646767 | 2018-04-29 | 2018-07-12 | 501.4% | 100% | - | Final Bill Paid |  | 74 | 371
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
6 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 6.968 | 13040494 | 12420836.6 | 12309541 | Fin. Pgr. (%) | 99.1% |  | 100%
Upazila: |  | 4. Palashbari
1 | Re-Seal | 233891 | 1 | 132672001 | Palashbari Upazila H/Q-Fakirhat GC Road Road | New Pavel auto, palashbari | 890 | 2390 | 1500 | 2298917 | 2183971.15 |  | 2018-12-15 | 2019-02-14 | 231.1% | 20% | Time Expired |  |  | 61 | 141
2 | Re-Seal | 233892 | 1 | 132673001 | Barishal U.P.Office-Thutiapukur Bazar Road via Bisramgachi Road | M/S. Sangeet Enterprise Address: Nuniagari, Palashbari, Gaibandha | 6500 | 7730 | 1230 | 1183901 | 1124705.95 |  | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - |  |  | 61 | 141
3 | Re-Seal | 233893 | 1 | 132674043 | Road Harinmari South bas stand NHW-Hospital via Napiter Bari Road | Name : M/S AJAD TRADERS Address: Jamalpur, Palashbari, Gaibandha | 0 | 560 | 560 | 518636 | 492704.2 | 492704 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
4 | Re-Seal | 233894 | 1 | 132674058 | Bengulia Govt P/S-Tangra Band Road | Alif Lam Mim, gaibandha | 0 | 1000 | 1000 | 2221553 | 2110475.35 |  | 2018-12-16 | 2019-02-15 | 229.5% | 40% | Time Expired |  |  | 61 | 140
5 | Over-Lay | 233961 | 1 | 132672002 | Godown Bazar ZR-Fakirhat GC Road | M/S RS Traders Address: D.B Road, Gaibandha | 0 | 4680 | 4680 | 5993675 | 5693991.25 | 5691601 | 2019-01-07 | 2019-03-22 | 159.5% | 100% | - | Final Bill Paid |  | 74 | 118
6 | Over-Lay | 233907 | 1 | 132674027 | Palashbari Chowmatha-Goraghat Rd via H/O Satter Road | M/S Mithala Traders Address: Palashbari,gaibandha | 0 | 900 | 900 | 1971082 | 1872527.9 |  | 2018-12-16 | 2019-02-15 | 229.5% | 30% | Time Expired |  |  | 61 | 140
7 | Over-Lay | 233908 | 1 | 132674038 | Gaibandha Palashbari Road-Rangpur Bogra Road | M/S Mithala Traders Address: Palashbari,gaibandha | 0 | 450 | 450 | 1222585 | 1161455.75 |  | 2018-12-16 | 2019-02-15 | 229.5% | 30% | Time Expired |  |  | 61 | 140
8 | Structure Maintenance | 233932 | 1 | 132674108 | Protection work on Moralipur GPS More - Pabnapur Chararhat Bazer NH/O Millat Road | M/S SHANTI TRADERS Address: Vill: Paschimpara, Word No. 02, Gaibandha Sadar, Gaibandha. | 2430 | 2500 | 70 | 402828 | 382686.6 | 381556 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
9 | Re-Hab. Structure | 233933 | 1 | 132674039 | 1.50m x 1.50m box culvert at Pabnatpur MP house-Talukgorabandha via Charerhat Road | BB Traders, gaibandha sadar | 750 |  | -750 | 623925 | 592728.75 | 592672 | 2018-12-09 | 2019-02-08 | 241% | 100% | - | Final Bill Paid |  | 61 | 147
10 | CO Road | 132313 | 1 | 132674036 | Samader Bazar - Basudebpur Bazar Road | M/S Shafiq Traders, Pabna | 0 | 1200 | 1200 | 4202457 | 4202457 | 3850672 | 2018-01-09 | 2018-12-12 | 142.7% | 100% | - | Final Bill Paid |  | 337 | 481
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
10 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 10.84 | 20639559 | 19817703.9 | 11009205 | Fin. Pgr. (%) | 55.55% |  | 74.08%
Upazila: |  | 5. Sadullapur
1 | Re-Seal | 233898 | 1 | 132822004 | Jamlarjan-Thutiapukur Road via Pachar Bazar GC.(Sadullapur Part) Road | Ziaul Islam Dales, gaibandha sadar | 0 | 1022 | 1022 | 1846362 | 1754043.9 |  | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - |  |  | 61 | 141
2 | Re-Seal | 233946 | 1 | 132822009 | Madergonj G.C-Pachar bazar G.C. Road | M/S Ela Traders Address: Kishamot Sherpur, Sadullapur, Gaibandha | 0 | 1900 | 1900 | 4573864 | 4345170.8 |  | 2019-01-01 | 2019-03-01 | 210.2% | 20% | Time Expired |  |  | 59 | 124
3 | Re-Seal | 233958 | 1 | 132823003 | Dhalvanga G.C-Jawlir bazar Kishamat Durgapur Eidgah Maidan Road | M/S Hiru Traders Address: Kachari Bazar Gaibandha | 0 | 3200 | 3200 | 5331831 | 5065239.45 |  | 2019-01-07 | 2019-03-22 | 159.5% | 40% | Time Expired |  |  | 74 | 118
4 | Re-Seal | 233899 | 1 | 132823007 | Ghagar bazar-Faridpur U.P.office Road | Rahed Enterprise Address: Gaibandha | 500 | 1808 | 1308 | 2992292 | 2842677.4 | 2550000 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - |  |  | 61 | 140
5 | Re-Seal | 233947 | 1 | 132824019 | Sadullapur-Naldanga rd from Garmin Bank Road | M/s Shihab Construction, Gobindaganj | 0 | 1045 | 1045 | 3260407 | 3097386.65 | 700000 | 2018-12-30 | 2019-02-28 | 210% | 40% | Time Expired |  |  | 60 | 126
6 | Re-Seal | 233900 | 1 | 132824059 | Sadullapur- Naldanga GC Road at Bottola -Chanderbazar Road | Ziaul Islam Dales, gaibandha sadar | 0 | 1000 | 1000 | 1899199 | 1804239.05 | 1801031 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
7 | Re-Seal | 233948 | 1 | 132824064 | Sadullapur - Madargonj GC Road near Jamalpur up Goespur pucca road Mokbular Etimkhana more to Patilakura road via Goespur Abdus Subahan house Road | Md. Abdur Razzak Address: Chalkmamrojpur, Khanka Shorif, Gaibandha | 0 | 1595 | 1595 | 4956781 | 4708941.95 | 4300000 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - |  |  | 61 | 127
8 | Re-Seal | 233949 | 1 | 132825080 | Sandiapur Clinic More-Rasulpur Bazar via Bosunia Para Grave Yeard Road | Md.Ramjan Ali Address: Ward No. 6, Wapda Para, P.O: Gaibandha-5700, Gaibandha Sadar,Gaibandha. | 0 | 700 | 700 | 3155048 | 2997295.6 | 2916012 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
9 | Over-Lay | 233930 | 1 | 132824063 | Naldanga Ralway Station to Namapara Road | Dipa Medical, gaibandha | 0 | 1115 | 1115 | 2428911 | 2307465.5 | 2050000 | 2018-12-29 | 2019-03-01 | 204.8% | 100% | - |  |  | 62 | 127
10 | Over-Lay | 233929 | 1 | 132825019 | Naldanga Sadullapur Road to Uttar Damudatpur via Nurnobi chairman house Road | Md. Shoheb Mona | 0 | 1504 | 1504 | 2913251 | 2767588.45 | 2766214 | 2018-12-29 | 2019-02-28 | 208.2% | 100% | - | Final Bill Paid |  | 61 | 127
11 | Re-Hab. Road | 233953 | 1 | 132824057 | Enaetpur-Mohisbandi Road at Dhakil Maddrasha - Sadullapur- Madargonj road via choto Daudpur GPS Road | M/S Yanur Traders Address: Kalir Bazar, Fulchori, Gaibandha | 0 | 1400 | 1400 | 4224418 | 4013197.1 |  | 2019-01-01 | 2019-03-01 | 210.2% | 40% | Time Expired |  |  | 59 | 124
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
11 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 15.789 | 37582364 | 35703245.85 | 17083257 | Fin. Pgr. (%) | 47.85% |  | 69.8%
Upazila: |  | 6. Shaghata
1 | Re-Seal | 233936 | 1 | 132883018 | Muktinagor UP-Bangla bazar Road | Abu Sayed Mahbub, Gaibandha sadar | 1866 | 3650 | 1784 | 3544196 | 3366986.2 |  | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - |  |  | 59 | 124
2 | Re-Seal | 233935 | 1 | 132884003 | Thai Kuerpara Pry.School- Kai Chora Road | Md. Atiqur Rahman Address: Kishamat Malibari, Dariapur, Gaibandha Sadar, Gaibandha | 3275 | 5185 | 1910 | 4254075 | 4041371.25 |  | 2019-01-01 | 2019-03-01 | 210.2% | 10% | Time Expired |  |  | 59 | 124
3 | Re-Seal | 233938 | 1 | 132884005 | Gobindapur Mouza-Shimulbari Road | M/s Anaf traders, saghata | 0 | 2250 | 2250 | 4983656 | 4734473.2 | 4260000 | 2018-12-30 | 2019-03-01 | 206.6% | 100% | - |  |  | 61 | 126
4 | Re-Seal | 233937 | 1 | 132884060 | Helencha FRB-Bati Road | Md. Mostafizur Mondal Address: Dublagari, Plashbari, Gaibandha | 0 | 1223 | 1223 | 3310008 | 3144507.6 |  | 2018-12-30 | 2019-02-28 | 210% | 100% | - |  |  | 60 | 126
5 | Re-Seal | 233890 | 1 | 132884066 | Chakdetia bazar-Sannashdaha Pry. School Road | SR Traders, gaibandha | 0 | 1015 | 1015 | 2212876 | 2102232.2 |  | 2018-12-16 | 2019-02-15 | 229.5% | 50% | Time Expired |  |  | 61 | 140
6 | Over-Lay | 233966 | 1 | 132882001 | Badiakhali Bridge R&H-Jumarbari Hat GC Road | Abu Sayed Mahbub, Gaibandha sadar | 8407 | 10748 | 2341 | 7640279 | 7258265.05 |  | 2019-01-01 | 2019-04-01 | 137.8% | 100% | - |  |  | 90 | 124
7 | Over-Lay | 233931 | 1 | 132884069 | Bonarpara Collage-Bharatkhali Hat UZR at Chakchokia-Mukti nagar UP Road | Mirza rofiqul alam , saghata | 0 | 625 | 625 | 2190773 | 2081234.35 | 2079681 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - | Final Bill Paid |  | 59 | 124
8 | Re-Hab. Road | 233934 | 1 | 132884017 | Kalapani Bandth-Dhanaruha Road | Md. Mostafizur Mondal Address: Dublagari, Plashbari, Gaibandha | 0 | 860 | 860 | 2629109 | 2497653.55 | 2200000 | 2018-12-30 | 2019-02-28 | 210% | 100% | - |  |  | 60 | 126
9 | Re-Hab. Road | 233954 | 1 | 132884056 | Badiakhali UZR at panditpara-Bharatkhali UZR at Kalapani Road | M/S NILA ENTERPRISE Address: Village- Dhanaruha, Post- Khamadhanaruha, Upazila- Shaghata, Dist- Gaibandha. | 800 | 1918 | 1118 | 4306803 | 4091462.85 | 3750000 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - |  |  | 59 | 124
10 | CO Road | 132323 | 1 | 132882001 | Badiakhali Bridge R&H - Jumarbari Hat GC Road | Shafiq Traders, Pabna | 5410 | 21872 | 16462 | 4374597 | 4374597 | 3744278 | 2018-01-09 | 2018-05-11 | 394.3% | 100% | - | Final Bill Paid |  | 122 | 481
11 | CO Road | 171483 | 1 | 132882008 | Saghata GC - Mohimagong GC Road | M/s Shazin Traders, .,Gaibandha | 8300 | 9872 | 1572 | 424628 | 424628 | 419328 | 2018-04-16 | 2018-06-16 | 629.5% | 100% | - | Final Bill Paid |  | 61 | 384
12 | CO Road | 158051 | 1 | 132882010 | Bonarpara GC - Gobindogonj - Gaibandha RHD at Sagdha Bridge via Ramnagar Bazar (Saghata part) Road | Sukra Enr. Bogra | 0 | 3652 | 3652 | 21069688 | 21069688 | 0 | 2018-04-07 | 2018-08-07 | 322.1% | 30% | Time Expired |  |  | 122 | 393
13 | CO Road | 188325 | 1 | 132884059 | Badhakhali Jumarbari GCCR - Zordoba Road | M/s Shazin Traders, .,Gaibandha | 1200 | 3390 | 2190 | 2606737 | 2606737 | 2604158 | 2018-05-05 | 2018-08-05 | 396.7% | 100% | - | Final Bill Paid |  | 92 | 365
14 | CO Road | 152528 | 1 | 132885023 | Jumarbari G.C.C.R - Sonatala G.C.C.R Road | Forhadul haque, gaibandha | 0 | 1165 | 1165 | 2333000 | 2333000 | 0 | 2018-02-22 | 2018-04-24 | 716.4% | 100% | - |  |  | 61 | 437
15 | CO Road | 171496 |  | 132883008 | Holdia UP H/Q - Jumarbari H/Q Road | M/S Rohan Traders, Saghata, Gaibandha | 4496 | 6496 | 2000 | 2713668 | 2713668 | 2686866 | 2018-04-16 | 2018-07-10 | 451.8% | 100% | - | Final Bill Paid |  | 85 | 384
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
15 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 40.167 | 68594093 | 66840504.25 | 21744311 | Fin. Pgr. (%) | 32.53% |  | 70.92%
Upazila: |  | 7. Sundarganj
1 | Re-Seal | 233883 | 1 | 132913005 | Mazumderhat GC-Kapashia UP. HQ. Via Lalchamar Bazar Road | M/s Shihab Construction, Gobindaganj | 3850 | 5215 | 1365 | 1579489 | 1500514.55 | 1350000 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - |  |  | 61 | 140
2 | Re-Seal | 233887 | 1 | 132913015 | Dahband UP office-Sundarganj Bazar Road | Abdul Latif Hakkani, gaibandha | 0 | 525 | 525 | 1755238 | 1667476.1 | 1665669 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
3 | Re-Seal | 233885 | 1 | 132914025 | Monmoth(Kalitala)-Taluk Falgacha Road | M/S Rabeya Enterprise Address: Gaibnadha | 1280 | 2015 | 735 | 906231 | 860919.45 | 860001 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
4 | Re-Seal | 233881 | 1 | 132914057 | Ramgonj-Basuhat (Sibrammor) Road | Md. Ferdous Bari, Sadullapur | 0 | 1513 | 1513 | 2179641 | 2346019 | 2100000 | 2019-02-27 | 2019-04-27 | 113.6% | 100% | - | Revised |  | 59 | 67
5 | Re-Seal | 233886 | 1 | 132914087 | Kanchibari UP HQ. (Police Investigation Center)-WAPDA Embankment Road | Prodip Kumar Sarkar, Gaibandha Sadar | 0 | 1150 | 1150 | 1398743 | 1328805.85 | 1284753 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
6 | Re-Seal | 233884 | 1 | 132914100 | Chandipur Pachimpara - Bazra Kanchibari Bazar Road | Zetendra nath Sarkar, Sundarganj | 0 | 840 | 840 | 1611705 | 1531119.75 | 1526915 | 2018-12-15 | 2019-02-14 | 231.1% | 100% | - | Final Bill Paid |  | 61 | 141
7 | Over-Lay | 233960 | 1 | 132912001 | Bamondanga (JMC FRA) Nagarkatgora GC-Bairati hat GC Road | Khademul Islam, Gaibandha | 0 | 2280 | 2280 | 5246536 | 4984209.2 | 4977425 | 2019-01-07 | 2019-03-22 | 159.5% | 100% | - | Final Bill Paid |  | 74 | 118
8 | Over-Lay | 233959 | 1 | 132913002 | Mirganj GC-Zamalerhat (Bamandangha UP H/Q) Road | Lokman ent.sundarganj | 0 | 6460 | 6460 | 13188486 | 12529061.7 |  | 2019-01-16 | 2019-05-15 | 91.6% | 20% | Critical |  |  | 119 | 109
9 | Over-Lay | 233903 | 1 | 132914069 | Kasim Bazar-Sicha Bazar Road | Abu Sayed Mahbub, Gaibandha sadar | 0 | 835 | 835 | 2521303 | 2395237.85 | 2393775 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
10 | Over-Lay | 233904 | 1 | 132914073 | Bamandanga-Rangpur RHD-Kheyaghat Road | Shahidul Islam, .,Gaibandha | 0 | 1000 | 1000 | 2826819 | 2685478.05 | 2680824 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
11 | Over-Lay | 233902 | 1 | 132915071 | Dhubni Bazer-Muzumder Lalchamar Via Near The H/O S. Hazi Road | M/S. Sinthia construction, Prop: Md. Sagir Khan, Vill: Monmoth, Post: Bamondanga, Upazila: Sundarganj, Dist: Gaibandha | 0 | 929 | 929 | 2698314 | 2563398.3 | 2551735 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
12 | Over-Lay | 233901 | 1 | 132915084 | Sonary Hat-Chandra Hat Road | Md. Atiqur rahman, Gaibandha Sadar | 636 | 1138 | 502 | 1268706 | 1205270.7 | 1204155 | 2018-12-16 | 2019-02-15 | 229.5% | 100% | - | Final Bill Paid |  | 61 | 140
13 | Re-Hab. Road | 233952 | 1 | 132913003 | Ramjiban UP. HQ.-Dahaband UP HQ. (Brac Office) Road | Abu Sayed Mahbub, Gaibandha sadar | 5200 | 6400 | 1200 | 4753060 | 4515407 | 4400000 | 2019-01-01 | 2019-03-01 | 210.2% | 100% | - |  |  | 59 | 124
14 | Re-Hab. Road | 203989 | 1 | 132915075 | Mater Hat - Sokher Bazar Via Samas Road | M/s Shazin Traders, .,Gaibandha | 0 | 1517 | 1517 | 3116544 | 2960716.8 | 2959262 | 2018-07-29 | 2018-09-29 | 451.6% | 100% | - | Final Bill Paid |  | 62 | 280
15 | CO Road | 132308 | 1 | 132913005 | Mazumderhat GC - Kapashia UP. HQ. Via Lalchamar Bazar Road | Md. Nuruzzaman Mia, pabna | 0 | 3850 | 3850 | 2032012 | 2032012 | 2028260 | 2018-01-08 | 2018-03-10 | 790.2% | 100% | - | Final Bill Paid |  | 61 | 482
16 | CO Road | 132096 | 1 | 132913012 | Chandipur UP H/Q (Punchpirhat) - Kalir Bazar (Haripur Kheyaghat) | M/s Samsul Alam Gaibandha | 0 | 1730 | 1730 | 194191 | 194191 | 191787 | 2018-01-03 | 2018-03-03 | 825.4% | 100% | - | Final Bill Paid |  | 59 | 487
17 | CO Road | 188329 | 1 | 132914072 | Halhalia (FRB) - Ramgonj hat Road | SR Traders, gaibandha | 0 | 1500 | 1500 | 2453615 | 2453615 | 2446170 | 2018-06-05 | 2018-08-05 | 547.5% | 100% | - | Final Bill Paid |  | 61 | 334
18 | CO Road | 188330 | 1 | 132914089 | Mazumderhat GC Road at Bashawala Bari to Mondol Para via Paramanik House Road | Anisha Traders, gaibandha | 0 | 1127 | 1127 | 2412834 | 2412834 | 2410188 | 2018-06-04 | 2018-08-04 | 549.2% | 100% | - | Final Bill Paid |  | 61 | 335
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
18 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 29.058 | 52143467 | 50166286.3 | 37030919 | Fin. Pgr. (%) | 73.82% |  | 80.02%
District Office
1 | Off-Pavement |  | 1 |  |  | LCS |  |  | 0 | 2670000 | 2670000 | 1494400 | 2018-08-01 | 2019-06-30 | 83.18% | 75% | - |  |  | 333 | 277
2 | On-Pavement | 241141 | 1 |  | Material Supply and purchase of Tools Fuel Labour & others for On-pavement Routine Maintenance under Gaibandha District. | M/S Shashi Enterprise Address: V-Aid Road, Gaibandha |  |  | 0 | 1030000 | 978500 | 0 | 2019-01-06 | 2019-06-10 | 76.77% | 60% | - |  |  | 155 | 119
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
[9 empty] | 0 | [5 empty] | - |  | - |  |  | 0 | -
2 | Sub-Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 0 | 3700000 | 3648500 | 1494400 | Fin. Pgr. (%) | 40.96% |  | 70.98%
100 | Grand Total: | 0 |  |  | Not Contacted Amount | 0 |  |  | 176.588 | 330282628 | 311614025.552 | 204117155 | Fin. Pgr. (%) | 65.5% |  | 81.81% |  |  |  | 28/3
Fund Received: | [15 empty] | Cash in Hand: | 55882845
Date: | 2018-09-13 |  | 2019-03-10 |  | 2019-04-04 | [12 empty] | Total:
Tk. | 80000000 |  | 100000000 |  | 80000000 | [12 empty] | 260000000
Comments if any:
[12 empty] | Tentative Carried Over Amount (Tk.) |  | Cancelled Contract Amount (Tk.) |  |  | Amount Required upto June (Tk.) | Remarks
Re-Seal
Over-Lay
Structure Maintenance
Re-Hab. Road
Re-Hab. Structure
Widening Road
Widening Structure
EM Road
EM Structure
CO Road
CO Structure
Off-Pavement
On-Pavement
1. Gaibandha Sadar
2. Gobindaganj
3. Fulchhari
4. Palashbari
5. Sadullapur
6. Shaghata
7. Sundarganj