## Gaibandha
Construction of 1490m Long PC Girder Bridge Project Monthly Progress Report (Physical & Financial).
District : Gaibandha. | [9 empty] | Reporting Month: Up to March,2019
Upazila | Approval Date | Package No | Name of scheme (chainage) | Approved Estimated cost (Tk) | Name of Contractor | Contract Amount (Tk) | Date of Contract | Date of completion | Physical Progress (%) | Payment Status |  |  | Remarks
[10 empty] | Final Bill (Tk.) | Payment made (Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Sundarganj | 18-7-17 | Sundarganj- W5(Part-1) | Earth work of Connecting Road for 1490.00m Bridge over Tista River- 1. Luxmipur GC-Chilmari Upazila H/Q Via Dharmapur-Panchpir GC Road Road ID No. 132912007 Ch.34-6462m 6462-16955m & 20445-22345m. a. Luxmipur-Mondaler Hat b. Mondaler Hat-Dharmapur c. Dharmapur-Panchpir Bridge Point & d. New Embankment-Cyclone Center Horipur. 2. Shovaganj GC-Panchpir Hat GC Via Belka Bazar Road Road ID No.132912002 Ch.00-5085m. 3. Matherhat GC-Kamarjani GC Sokher Bazar Road Road ID No.132912010. Ch.00-3880m. 4. Belka Chowrasta-Sundarganj Upazila H/Q Via WAPDA Bandh Road Road ID No. 132912012 Ch.00-7770m. 5. Kanchibari UP Office-Panchpir Hat GC Road Road ID No. 132913007 Ch.00-4022m. Panchpir-RHD Via Dhubni. 6. Barurar Hat-WAPDA Bandh Road Road ID No.132914012 Ch.00-1941m. 7. Dharmapur-Panchpir Hat GC Pucca Road Kabejer More Bridge-Baruarar Hat Road Road ID No.132914101 Ch.00-1710m. 8. Bridge Point-Belka WAPDA Bandh Belka Chowrasta Road ID No. 132914103 Ch.00-7443m. 9. Barurar Hat WAPDA Bandh-Changmari High School Road Road ID No.132915069 Ch.00-1300m. under Sundarganj Upazila Dist Gaibandha. | 185731290 | ADL-NT-IH JV, Sharif Mansion, 2nd Floor, 56-57 Motijhell, C/A, Dhaka-1000 | 167158161.001 | 14-11-17 | 14-05-19 | 35% | 0 | 51099235 | 0
Sundarganj | 18-7-17 | Sundarganj- W5(Part-2) | Earth work of Connecting Road for 1490.00m Bridge over Tista River- 1.Luxmipur GC-Panchpir GC (Sadar Part) (Road ID No. 132242014) Ch.00-3625m under Gaibandha Sadar, 2 Dhaperhat GC-Luxmipur GC Via Sadullapur GC Road (Sadullapur Part) (Road ID No. 132822003) Ch.00-22800m under+ Sadullapur Upazila Dist Gaibandha, (APP ID: 57349). | 42608028 | Mohammed Eunus & Brothers (Pvt.) Ltd, AS Tower (8th Floor), Road 01, Plot-553, Hill View R/A, Panchlaish, Chittagang. | 38347225.2 | 16-10-17 | 5-12-2018 | 20% | 0 | 6400765 | 0
Sundarganj |  | Sundarganj- W-01 | Construction of 1490.00m Bridge over Tista River- Luxmipur GC-Chilmari Upazila H/Q Via Dharmapur-Panchpir GC Road Road under Sundarganj Upazila Dist Gaibandha. | [9 empty] | Cancelled & Tender Under Process
|  |  | Land Acquisition | [7 empty] | 69200000
Sub-Total = |  | 3 |  | 228339318 |  | 205505386.201 |  |  |  | 0 | 126700000 | 0
|  |  | Total Fund Received | [7 empty] | 156700000
|  |  | Fund in hand | [7 empty] | 30000000
Accountant |  |  | Sub-Assistant Engineer |  | Assistant Engineer |  |  | Senior Asstt. Engineer |  |  |  | Executive Engineer
LGED, Gaibandha. |  |  | LGED, Gaibandha. |  | LGED, Gaibandha. |  |  | LGED,Gaibandfha. |  |  |  | LGED, Gaibandha.