## Ghagot Lake
Ghagot Lake Development Project Monthly Progress Report (Physical & Financial).
District : Gaibandha. | [9 empty] | Reporting Month: Up to 30-04-2019
Upazila | Approval Date | Package No | Name of scheme (chainage) | Quantity (Km/m/nos) | Approved Estimated cost (Tk) | Name of Contractor | Contract Amount (Tk) | Date of Contract | Work completion Date | Physical Progress (%) | Financial Progress (%) | Total Payment made (Tk) | Payment Made FY 2018-19 | Fund Required
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 11 | 12 | 13 | 14 | 15
Sadar (Gaibandha Pourashava) | 10-1-17 | IGL GP-Re-Ex-01/16-17 | Re-Excavation of Ghagot Lake under Gaibandha Sadar Upazila, Dist: Gaibandha. | 3 | 6456932.68 | Md. Abdul Halim Mondal, Gorosthanpara, Gaibandha. | 5811239.412 | 2017-04-18 | 2018-04-24 | 80% | 72% | 4221439 | 0 | No
Sadar (Gaibandha Pourashava) | 5-10-17 | Ghagot/Bridge-01/17-18 | Construction of 54.00m RCC Long Girder Bridge over Ghagot River at Devid Company Para Ghagot Lake (Ch.1000m). | 54m | 39069245.35 | Niaz Traders-NNBL JV, Dhaka | 35162320.81 | 2018-01-18 | 2019-01-09 | 40% | 36% | 15150000 | 8150000 | No
Sadar (Gaibandha Pourashava) | 5-10-17 | Ghagot/Bridge-02/17-18 | Construction of 45.00m RCC Long Girder Bridge over Ghagot River at Shashanghat Ghat Ghagot Lake (Ch.1800m). | 45m | 39087955.4 | Niaz Traders-NNBL JV, Dhaka | 35179159.86 | 2018-01-18 | 2019-01-09 | 35% | 30% | 12571475 | 7280000 | No
Sadar (Gaibandha Pourashava) | 18-10-17 | Ghagot/ Ghat-01/17-18 | Construction of 4 Nos. Ghat on Ghagot Lake under Gaibandha Sadar Upazila. | 4 Nos. | 13880111 | Md. Saidur Rahman,Godown Road, Gaibandha | 12492099.9 | 2018-02-10 | 2018-12-20 | 100% | 73% | 12473596 | 3286510 | No
Sadar (Gaibandha Pourashava) | 11-1-18 | Ghagot/ Protection Work-01/17-18 | Construction of Slope Protection Work on Ghagot Lake under Gaibandha Pourashava Gaibandha-sadar upazila District Gaibandha | 6.00 km | 73496186 | Niaz Traders-NNBL JV, Dhaka | 73494116.348 | 2018-04-25 | 2019-05-14 | 22% | 7% | 5350000 | 5350000 | No
Total Taka |  |  |  |  | 171990430.43 |  | 162138936.33 |  |  |  |  | 49766510 | 24066510
[6 empty] | Fund Released | [5 empty] | 70605000
[6 empty] | Balance | [5 empty] | 20838490
Accountant |  |  | Sub-Assistant Engineer |  | Assistant Engineer |  | Sr. Assistant Engineer |  |  |  |  | Executive Engineer
LGED, Gaibandha. |  |  | LGED, Gaibandha. |  | LGED, Gaibandha. |  | LGED, Gaibandha. |  |  |  |  | LGED, Gaibandha.