## Sheet3 (2)
Local Government Engineering Department
Construction of Large Bridge on Upazila & Union road Project
Monthly Progress Report
District: Gaibandha | [28 empty] | Repoting month: 05/Feb, 2018
SL. No. | Name of District | Name of Upazila | Name of Scheme | Length (m) | No of Span | Estimated cost(Tk) | Contract Amount(Tk) | Name of Contractor | Date of work order | Date of completion as per work order | Actual date of completion | Pile (no) |  |  | Pile Cap (no) |  |  | Abutment & Pier (no) |  |  | Gider (no) |  |  | Slab (no) |  |  | Approach (m) |  |  | Physical Progress(%) | Fund Released (In lac) | Fund Spent(In lac) | Remarks
[12 empty] | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest |  |  |  |  | 2845.12
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
`1 | Gaibandha | Saghata | Construction of 360.00m PC Girder Bridge over Katakhali River on Bonarpara UP H/Q – Ramnagar Bazar Road at ch.4025m; Road ID No.132883020 under Saghata Upazila, District: Gaibandha. | 360 | 9 | 241245660 | 284513217.54 | M/S Surma Enterprise | 21.11.13 | 30.03.17 | 15.11.17 | 116 | 116 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 36 | 36 | 0 | 9 | 9 | 0 | 1100 | 1100 | 0 | 100 | 4149.82 | 2763.16 | Final |  | 0.97119
2 |  | Gobindaganj | Construction of 238.30m Long Bridge on Katabari UP -Boglabari Hat Road over the Katakhali River at ch.1700m, Road ID No. 132303025 under Gobindaganj Upazila, District: Gaibandha | 238.3 | 7 | 111981319 | 130462227 | Mir Akter-AR (JV) | 15.09.14 | 31.07.17 | 25.5.18 | 88 | 88 | 0 | 8 | 8 | 0 | 8 | 8 | 0 | 21 | 21 | 0 | 7 | 7 | 0 | 1811 | 1500 | 311 | 100 |  | 1298.48 | Final | 1231.59 | 1.0543
3 |  | Fulchari | Construction of 32.00m Long RCC Girder Bridge on Fulchari Upazila H/Q-Gunvary GC Road over Paomary Khal at ch.1141m. Road ID 132212001, Package No. PD/CLBUURP/W-339 | 32 |  | 19096152 | 17186536 | Rafiq Const. Co. (Pvt) Ltd. | 2018-04-03 | 29.04.19 | [19 empty] | 0
4 |  | Fulchari | Construction of 20.00m Long RCC Girder Bridge on Gunvary GC-Badiakhali R&H Road over Goraimary Bill at ch.200m. Road ID 132212002, Package No. PD/CLBUURP/W-340 | 20 |  | 16065341 | 14458806 | Rafiq Const. Co. (Pvt) Ltd. | 2018-04-03 | 29.04.19 | [19 empty] | 30 |  | 45.298
5 |  | Fulchari | Construction of 18.00m Long RCC Girder Bridge on Udakhali UP-Singria Bazar Road over Singria Bill at ch.3610m. Road ID 132213001, Package No. PD/CLBUURP/W-341 | 18 |  | 14029628 | 12626665 | Rafiq Const. Co. (Pvt) Ltd. | 2018-04-03 | 29.04.19 | [19 empty] | 30 |  | 42.89
6 |  | Palashbari | PD/CLBUURP/W-338 Construction of 55.00m Long Bridge on Dublagari National Highway- Dholbhanga CG via Amlagachi GC Road at ch 8050m Road id132672010 under Palashbari Upazila Dist Gaibandha. | 55 | 3 | 39521885 | 39013626.939 | Md. Abdul Latif Hokkani, Gaibandha | 2018-11-09 | 29/3/20 |  | 28 | 0 | 28 | 3 | 0 | 3 |  |  |  | 6 | [8 empty] | 5
7 |  | Sundarganj | PD/CLBUURP/W-337 Construction of 44.00 m Long RCC Girder Bridge on Sudargonj Gaibandha Road-Vurarghat Mirganj at Ch.1000m under Sundarganj upazila. Dist. Gaibandha | 44 | 3 | 31850607.57 | 29965102.038 | RSL Enterprise, Gaibandha | 3.1.19 | 27.11.19
8 |  |  | PD/CLBUURP/W-336 & Construction of 96.00 m Long PC Girder Bridge on Sudargonj Ramdakua Mohila Bazar Road-Ponchanon Madrasha at Ch.320m under Sundarganj upazila. Dist. Gaibandha | 96 |  | 58800313.16 | 59798443.999 | Purakaushal Projukti Ltd.
|  |  | Total= | 863.3 | 22 | 532590905.73 | 588024624.516 | [15 empty] | 0 | 16 | 16 | 0 | 2911 | 2600 | 311 | 265 | 4149.82 | 4149.828 | 0
[25 empty] | Balance | [5 empty] | -0.00802
Accountant | [5 empty] | Sub-Assistant Engineer | [6 empty] | Assistant Engineer | [5 empty] | Senior Asstt. Engineer | [10 empty] | Executive Engineer
LGED, Gaibandha. | [5 empty] | LGED, Gaibandha. | [6 empty] | LGED, Gaibandha. | [5 empty] | LGED,Gaibandfha. | [10 empty] | LGED, Gaibandha.

## Sheet3 (3)
Local Government Engineering Department
Construction of Large Bridge on Upazila & Union road Project
Monthly Progress Report
District: Gaibandha | [28 empty] | Repoting month: 10/April, 2018
SL. No. | Name of District | Name of Upazila | Name of Scheme | Length (m) | No of Span | Estimated cost(Tk) | Contract Amount(Tk) | Name of Contractor | Date of work order | Date of completion as per work order | Actual date of completion | Pile (no) |  |  | Pile Cap (no) |  |  | Abutment & Pier (no) |  |  | Gider (no) |  |  | Slab (no) |  |  | Approach (m) |  |  | Physical Progress(%) | Fund Released (In lac) | Fund Spent(In lac) | Remarks
[12 empty] | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest |  |  |  |  | 2845.12
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
`1 | Gaibandha | Saghata | Construction of 360.00m PC Girder Bridge over Katakhali River on Bonarpara UP H/Q – Ramnagar Bazar Road at ch.4025m; Road ID No.132883020 under Saghata Upazila, District: Gaibandha. | 360 | 9 | 241245660 | 284513217.54 | M/S Surma Enterprise | 21.11.13 | 30.03.17 | 15.11.17 | 116 | 116 | 0 | 10 | 10 | 0 | 10 | 10 | 0 | 36 | 36 | 0 | 9 | 9 | 0 | 1100 | 1100 | 0 | 100 | 4449.82 | 2763.16 | Final |  | 0.97119
2 |  | Gobindaganj | Construction of 238.30m Long Bridge on Katabari UP -Boglabari Hat Road over the Katakhali River at ch.1700m, Road ID No. 132303025 under Gobindaganj Upazila, District: Gaibandha | 238.3 | 7 | 111981319 | 130462227 | Mir Akter-AR (JV) | 15.09.14 | 31.07.17 | 25.5.18 | 88 | 88 | 0 | 8 | 8 | 0 | 8 | 8 | 0 | 21 | 21 | 0 | 7 | 7 | 0 | 1811 | 1500 | 311 | 100 |  | 1298.48 | Final | 1231.59 | 1.0543
3 |  | Fulchari | Construction of 32.00m Long RCC Girder Bridge on Fulchari Upazila H/Q-Gunvary GC Road over Paomary Khal at ch.1141m. Road ID 132212001, Package No. PD/CLBUURP/W-339 | 32 |  | 19096152 | 17186536 | Rafiq Const. Co. (Pvt) Ltd. | 2018-04-03 | 29.04.19 | [19 empty] | 0
4 |  | Fulchari | Construction of 20.00m Long RCC Girder Bridge on Gunvary GC-Badiakhali R&H Road over Goraimary Bill at ch.200m. Road ID 132212002, Package No. PD/CLBUURP/W-340 | 20 |  | 16065341 | 14458806 | Rafiq Const. Co. (Pvt) Ltd. | 2018-04-03 | 29.04.19 | [19 empty] | 30 |  | 45.298
5 |  | Fulchari | Construction of 18.00m Long RCC Girder Bridge on Udakhali UP-Singria Bazar Road over Singria Bill at ch.3610m. Road ID 132213001, Package No. PD/CLBUURP/W-341 | 18 |  | 14029628 | 12626665 | Rafiq Const. Co. (Pvt) Ltd. | 2018-04-03 | 29.04.19 | [19 empty] | 60 |  | 72.89
6 |  | Palashbari | PD/CLBUURP/W-338 Construction of 55.00m Long Bridge on Dublagari National Highway- Dholbhanga CG via Amlagachi GC Road at ch 8050m Road id132672010 under Palashbari Upazila Dist Gaibandha. | 55 | 3 | 39521885 | 39013626.939 | Md. Abdul Latif Hokkani, Gaibandha | 2018-11-09 | 29/3/20 |  | 28 | 0 | 28 | 3 | 0 | 3 |  |  |  | 6 | [8 empty] | 35 |  | 125
7 |  | Sundarganj | PD/CLBUURP/W-337 Construction of 44.00 m Long RCC Girder Bridge on Sudargonj Gaibandha Road-Vurarghat Mirganj at Ch.1000m under Sundarganj upazila. Dist. Gaibandha | 44 | 3 | 31850607.57 | 29965102.038 | RSL Enterprise, Gaibandha | 3.1.19 | 27.11.19 | [19 empty] | 5
8 |  | Sundarganj | PD/CLBUURP/W-336 & Construction of 96.00 m Long PC Girder Bridge on Sudargonj Ramdakua Mohila Bazar Road-Ponchanon Madrasha at Ch.320m under Sundarganj upazila. Dist. Gaibandha | 96 |  | 58800313.16 | 59798443.999 | Purakaushal Projukti Ltd. | 27.3.19 | 3.3.20
|  |  | Total= | 863.3 | 22 | 532590905.73 | 588024624.516 | [15 empty] | 0 | 16 | 16 | 0 | 2911 | 2600 | 311 | 330 | 4449.82 | 4304.828 | 0
[25 empty] | Balance | [5 empty] | 144.992
Accountant | [5 empty] | Sub-Assistant Engineer | [6 empty] | Assistant Engineer | [5 empty] | Senior Asstt. Engineer | [10 empty] | Executive Engineer
LGED, Gaibandha. | [5 empty] | LGED, Gaibandha. | [6 empty] | LGED, Gaibandha. | [5 empty] | LGED,Gaibandfha. | [10 empty] | LGED, Gaibandha.
[7 empty] | 17186536 | 4529802
[7 empty] | 14458806 | 4289000
[7 empty] | 12626665 | 0
[7 empty] | 44272007 | 8818802 | 35453205
[7 empty] | 58.8 | 41.49 | 17.31