## jun 18
Local Government Engineering Department
09(Nine) Bridge Project
Monthly Progress Report
District: Gaibandha | [28 empty] | Repoting month: Jun, 2018
SL. No. | Name of District | Name of Upazila | Name of Scheme | Length (m) | No of Span | Estimated cost(Tk) | Contract Amount(Tk) | Name of Contractor | Date of work order | Date of completion as per work order | Actual date of completion | Pile (no) |  |  | Pile Cap (no) |  |  | Abutment & Pier (no) |  |  | Gider (no) |  |  | Slab (no) |  |  | Approach (m) |  |  | Physical Progress(%) | Fund Released (In lac) | Fund Spent (In lac) | Remarks
[12 empty] | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
`1 | Gaibandha | Saghata | Construction of 195.00m long prestressed Girder Bridge over katakhali River on Folia bazar – Panchpur Road at ch: 500m. Road ID No. 132885049 under Saghata Upazila,Dist: Gaibandha Package No-GAI.W-21 | 195 | 5 | 147585704 | 134165654.09 | M/S Chowdhury Enterprise | 23/11/2015 | 30/11/2017 |  | 56 | 56 | 0 | 6 | 6 | 0 | 6 | 6 | 0 | 15 | 13 | 2 | 5 | 3 | 2 | 666 | 0 | 666 | 75 | 3256.38 | 105482725
2 |  | Saghata | Construction of 273.00m long prestressed Girder Bridge over katakhali River on Barokona FRB – Bangabari kheya Ghat Road at ch: 5000m. Road ID No. 132883003 under Saghata Upazila,Dist: Gaibandha Package No-GAI.W-20 | 273 | 7 | 198661285 | 179981942.213 | SSL Udayan JV,Dhaka | 15.03.16 | 30.11.17 |  | 80 | 80 | 0 | 8 | 6 | 2 | 8 | 6 | 2 | 21 | 8 | 13 | 7 | 2 | 5 | 677 | 0 | 677 | 73 |  | 124327724
3 |  | Saghata | Extension of Approach Road and slope protection work for 195.00m long PC Girder Bridge over Katakhali River on Folia Bazar - Panchapur road at Ch 500m, Road ID No.132885049 under Saghata Upazila, District Gaibandha (Re-tender), Package No. GAI.W-21a | 0 | 0 | 108030579 | 113430694.884 | Md. Moyenuddin (Bashi), Jessore | 2017-09-18 | 2018-12-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2880 | 0 | 2880 | 15 |  | 18820790
4 |  | Saghata | Extension of Approach Road and slope protection work for 273.00m Long PC Girder Bridge over Katakhali River on Barokona FRB - Bangabari Kheya Ghat Road at Ch 5000m, ID No. 132883003 under Saghata Upazila District. Gaibandha (2nd called), Package No. GAI.W-20a | 0 | 0 | 167424485 | 169999999 | NN Builders Ltd, Dhaka | 2017-12-03 | 2019-06-08 |  | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 5100 | 0 | 5100 | 20 |  | 12048775
|  |  | Land Acquisition | [28 empty] | 34958000
|  |  | Total= | 468 | 12 | 346246989 | 314147596.303 |  |  |  |  | 136 | 136 | 0 | 14 | 12 | 2 | 14 | 12 | 2 | 36 | 21 | 15 | 12 | 5 | 7 | 1343 | 0 | 1343 |  |  | 295638014
325638014
30000000
Accountant | [5 empty] | Sub-Assistant Engineer | [6 empty] | Assistant Engineer | [5 empty] | Senior Asstt. Engineer | [10 empty] | Executive Engineer
LGED, Gaibandha. | [5 empty] | LGED, Gaibandha. | [6 empty] | LGED, Gaibandha. | [5 empty] | LGED,Gaibandfha. | [10 empty] | LGED, Gaibandha.

## Feb19
Local Government Engineering Department
09(Nine) Bridge Project
Monthly Progress Report
District: Gaibandha | [28 empty] | Repoting month: 24/Mar, 2019
SL. No. | Name of District | Name of Upazila | Name of Scheme | Length (m) | No of Span | Estimated cost(Tk) | Contract Amount(Tk) | Name of Contractor | Date of work order | Date of completion as per work order | Actual date of completion | Pile (no) |  |  | Pile Cap (no) |  |  | Abutment & Pier (no) |  |  | Gider (no) |  |  | Slab (no) |  |  | Approach (m) |  |  | Physical Progress(%) | Fund Released (In lac) | Fund Spent (In lac) | Remarks
[12 empty] | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest | Total | Completed | Rest
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
`1 | Gaibandha | Saghata | Construction of 195.00m long prestressed Girder Bridge over katakhali River on Folia bazar – Panchpur Road at ch: 500m. Road ID No. 132885049 under Saghata Upazila,Dist: Gaibandha Package No-GAI.W-21 | 195 | 5 | 147585704 | 134165654.09 | M/S Chowdhury Enterprise | 23/11/2015 | 2019-06-02 |  | 56 | 56 | 0 | 6 | 6 | 0 | 6 | 6 | 0 | 15 | 13 | 2 | 5 | 3 | 2 | 666 | 0 | 666 | 90 | 347458000 | 123135089
2 |  | Saghata | Construction of 273.00m long prestressed Girder Bridge over katakhali River on Barokona FRB – Bangabari kheya Ghat Road at ch: 5000m. Road ID No. 132883003 under Saghata Upazila,Dist: Gaibandha Package No-GAI.W-20 | 273 | 7 | 198661285 | 179981942.213 | SSL Udayan JV,Dhaka | 15.03.16 | 2019-05-22 |  | 80 | 80 | 0 | 8 | 6 | 2 | 8 | 6 | 2 | 21 | 8 | 13 | 7 | 2 | 5 | 677 | 0 | 677 | 80 |  | 143598149
3 |  | Saghata | Extension of Approach Road and slope protection work for 195.00m long PC Girder Bridge over Katakhali River on Folia Bazar - Panchapur road at Ch 500m, Road ID No.132885049 under Saghata Upazila, District Gaibandha (Re-tender), Package No. GAI.W-21a | 0 | 0 | 108030579 | 113430694.884 | Md. Moyenuddin (Bashi), Jessore | 2017-09-18 | 2018-12-31 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 2880 | 0 | 2880 | 55 |  | 32357794
4 |  | Saghata | Extension of Approach Road and slope protection work for 273.00m Long PC Girder Bridge over Katakhali River on Barokona FRB - Bangabari Kheya Ghat Road at Ch 5000m, ID No. 132883003 under Saghata Upazila District. Gaibandha (2nd called), Package No. GAI.W20a | 0 | 0 | 167424485 | 169999999 | NN Builders Ltd, Dhaka | 2017-12-03 | 2019-06-08 |  | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 5100 | 0 | 5100 | 35 |  | 37998775
|  |  | Land Acquisition | [28 empty] | 33958000
|  |  | Total= | 468 | 12 | 621702053 | 597578290.187 |  |  |  |  | 176 | 176 | 0 | 14 | 12 | 2 | 14 | 12 | 2 | 36 | 21 | 15 | 12 | 5 | 7 | 9323 | 0 | 9323 | 260 | 347458000 | 371047807
[25 empty] | Fund in hand | [6 empty] | -23589807
Accountant | [5 empty] | Sub-Assistant Engineer | [6 empty] | Assistant Engineer | [5 empty] | Senior Asstt. Engineer | [10 empty] | Executive Engineer
LGED, Gaibandha. | [5 empty] | LGED, Gaibandha. | [6 empty] | LGED, Gaibandha. | [5 empty] | LGED,Gaibandfha. | [10 empty] | LGED, Gaibandha.