## SHOUHARDO-III
SHOUHARDO-III Project Monthly Progress Report (Physical & Financial).
District : Gaibandha. | [10 empty] | Reporting Month: Up to10-April, 2019
Upazila | Approval Date | Package No | Name of scheme (chainage) | Quantity (Km/m/nos) | Approved Estimated cost (Tk) | Name of Contractor | Contract Amount (Tk) | Date of Contract | Date of completion | Physical Progress (%) | Payment Status |  |  | Remarks
[11 empty] | Final Bill (Tk.) | Payment made (Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Sundarganj | 18-10-17 | SHOW/Gai/W-01 | Kanicaritabari Mollapara Govt. Primary School. | 0 | 2710164.42 | M/S. Shazin Traders, Gaibandha | 2104506.99 | 10-01-18 | 14-01-19 | 100% | 0 | 1847682 |  | Final Bil Paid
Sundarganj | 18-9-18 | SHOU III/Gai/W-07 | Construction of School Cum Flood Shelter Kolim Sarkarer Char Govt. Parimary School Under Sundarganj Upazila Dist Gaibandha. | 0 | 2654383 | Md. Shamim Ahammed Mondal, Saghata, Gaibandha | 2521663.85 | 24-12-18 | 4-6-19 | 20% |  |  | 2521663.85
Fulchari | 18-9-18 | SHOU III/Gai/W-06 | Construction of School Cum Flood Shelter Dariar Vita Govt. Parimary School Under Fulchari Upazila Dist Gaibandha. | 0 | 2700175 | Prodip Kumar sarker, Gaibandha | 2565166.25 | 24-12-18 | 4-6-19 | 60% |  |  | 2565166.25
Sadullapur | 22-10-18 | SHOU III/GAI/W-15. | a Rehabilitation of road from Kantanagar - Luxmipur road at Vuttu Army shouse to Uttar Hat Bamuni Agriculture Sales Centre under Sadullapur Upazila Dist Gaibandha.b Rehabilitation of 03Three Nos. 0.625x0.600m drainage culvert U-drain on the same road at ch.111m 155m & 305m.c Construction of 3.00x2.50m RCC Box Culvert at ch.715m on the same road. under Sadullapur Upazila Dist Gaibandha. | 1.055 | 10095930 | M/s Mafi Construction, Sadullapur | 9591133.5 | 06-10-18 | 14-6-19 | 100% |  | 8000000 | 1591133.5
| Grand Total= |  |  | 1.055 | 18160652.42 |  | 16782470.59 |  |  |  | 0 | 9847682 | 6677963.6
[6 empty] | Fund Received | [5 empty] | 8000000
[6 empty] | Balance | [5 empty] | -1847682
Accountant |  |  | Sub-Assistant Engineer |  | Assistant Engineer |  |  | Senior Assistant Engineer |  |  |  |  | Executive Engineer
LGED, Gaibandha. |  |  | LGED, Gaibandha. |  | LGED, Gaibandha. |  |  | LGED, Gaibandha. |  |  |  |  | LGED, Gaibandha.