## UMC
Government of the People's Republic of Bangladesh
LocalGovernment Engineering Department
Construction of upazila Muktijuddha complex Project
Agargaon, Sher-E-Bangla Nagar,Dhaka-1207
Status on Implementation of Scheme
Monthly Progress Report
Name of District: Gaibandha | [12 empty] | Repoting Month:24/Mar, 2019
Sl. No | Upazila | Package No | Scheam Name | Estimated Cost(in Tk) | Name of Contractor | Contract Amount | Rivesed Contract Amount | Contract Agreement date | Contract completion date | Actual Completion date | Physical Progress (%) | Fund Received | Fund Spent this month | Total Fund Spent | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
1 | Palashbari | UMC/GAI/PAL/14/C-107 | Construction of Moktijoddha Complex Bhaban under Palashbari Upazila, District: Gaibandha | 24665000 | Md. Saidur Rahman | 262.95 | - | 21/05/14 | 2015-11-17 | 2018-06-20 | 100% | 113800000 |  | 26042712 | Final Bill Paid
2 | Sadullapur | UMC/GAI/PAL/15/C-208 | Construction of Moktijoddha Complex Bhaban under Sadullapur Upazila, District: Gaibandha | 23217179 | Md. Saidur Rahman | 198.27 |  | 29/03/16 | 28/3/17 |  | 100% |  |  | 19100695
3 | Sundaganj | UMC/GAI/SUN/15/C-238 | Construction of Upazila Muktijodha Complex Bhaban at Sundarganj Upazila under Gaibandha District | 21812654 | Md. Saidur Rahman | 185.66 |  | 26/07/16 | 24/05/17 |  | 100% |  |  | 18038310
4 | Gobindaganj | CUMCP/GAI/GOB/16/C-275 | Construction of Upazila Muktijoddha Complex Bhaban at Gobindaganj Upazila under Gaibandha District. | 18888168 | M/S Nasif construction | 155.29 |  | 19.02.17 | 20.03.18 | 2018-06-06 | 100% |  |  | 15529228 | Final Bill Paid
5 | Saghata | CUMCP/GAI/SAG/16/C-290 | Construction of Upazila Muktijoddha Complex Bhaban at Saghata Upazila under Gaibandha District. | 19507936 | Md. Saidur Rahman | 175.57 |  | 05.07.17 | 30.07.18 |  | 100% |  |  | 16624838
6 | Fulchari | CUMCP/GAI/FUL/16/C-293 | Construction of Upazila Muktijoddha Complex Bhaban at fulchariUpazila under Gaibandha District. | 19035398 | Md. Saidur Rahman | 171.32 |  | 05.07.17 | 30.07.18 |  | 100% |  |  | 16304569
7 | Sadar |  | Construction of Upazila Muktijoddha Complex Bhaban at Sadar Upazila under Gaibandha District. | [11 empty] | Land acquisition under process
|  |  | Total | 127126335 |  | 1149.06 | [5 empty] | 113800000 | 0 | 111640352
| Accountant |  |  | Sub-Assist. Engineer |  | Assistant Engineer |  |  |  |  | Sr.Assistant Engineer |  |  | Executive Engineer
| LGED,Gaibandha |  |  | LGED,Gaibandha |  | LGED, Gaibandha. |  |  |  |  | LGED, Gaibandha |  |  | LGED, Gaibandha