## Gaibandha
Monthly Progress Report
Project Name : Construction of Town and Union Land Office across the Country under Ministry of Land.
Reporting Month : 18- Apr, 2019
District Name : Gaibandha. | [10 empty] | Division Name : Rangpur
Sl. No. | Upazila | Package No. | Name of Work | Number of Land Office | Estimated Cost (Tk.) | Date of Contract | Contract Price (Tk) | Contractor Name | Start Date | Completion Date | Phy. Prog. (%) | Payment Made (Tk) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 | 11 | 12 | 13
1 | Gaibandha-Sadar | TULO/GBD/W-01 | Construction of Union Land Office at Boali (with 152m Boundary Wall & Barbed Wire) and Tulsighat (with 180m Boundary Wall & Barbed Wire) under Gaibandha Sadar Upazila Dist Gaibandha. | 2 | 9512000 | 2018-02-25 | 8560800 | Dhaly Construction Ltd, Dhaka | 2018-03-03 | 2018-12-28 | 70% & 0% | 600000
2 | Palashbari | TULO/GBD/W-02 | Construction of Union Land Office at Matherhat (with 180m Boundary Wall & Barbed Wire) and Kishorgari (with 103m Boundary Wall & Barbed Wire) under Palashbari Upazila Dist Gaibandha | 2 | 9397000 | .04-3-18 | 8457300 | Dhaly Construction Ltd, Dhaka | 2018-03-10 | 2019-01-04 | 0% & 70% | 1050000
3 | Saghata | TULO/GBD/W-03 | Construction of Union Land Office at Saghata (with 135m Boundary Wall & Barbed Wire) and Padum Sahar (with 104m Boundary Wall & Barbed Wire) under Saghata Upazila Dist Gaibandha | 2 | 9358000 | 2018-02-13 | 8422200 | M/S. Masuma Begum, Bogra | 2018-02-19 | 2019-12-31 | 0% & 85% | 2502793
4 | Gobindaganj | TULO/GBD/W-04 | Construction of Union Land Office at Mohimaganj With 160m Boundary Wall and Taluk kanupur With 160m Boundary Wall under Gobindaganj Upazila Dist Gaibandha under Construction of Town & Union Land Office across the Country Project. | 2 | 10833000 | 2018-03-25 | 10826564 | Md. Atikur Rahman, Gobindaganj, Gaibandha | 2018-03-31 | 2019-02-03 | 90% & 90% | 7331000
5 | Sadullapur | TULO/GBD/W-05 | Construction of Union Land Office at Dhaperhat With 160m Boundary Wall and Vat Gram With 160m Boundary Wall under Sadullpur Upazila Dist Gaibandha under Construction of Town & Union Land Office across the Country Project. | 2 | 10221000 | 2018-04-03 | 10218000 | Md. Saidur Rahman, Godown Road, Gaibandha | 2018-04-09 | 2019-02-03 | 80% & 80% | 5250000
6 | Sundarganj | TULO/GBD/W-06 | Construction of Union Land Office at Belka With 93m Boundary Wall and Chandipur With 160m Boundary Wall under Sundarganj Upazila Dist Gaibandha under Construction of Town & Union Land Office across the Country Project. | 2 | 9947000 | 2018-03-19 | 8952499 | M/S. Zebin Enterprise, 24/B, BC Shahid Minar Road, Kalyanpur, Mirpur, Dhaka. | 2018-03-25 | 2019-02-03 | 30% & 30% | 1050000
|  |  | Total= | 12 | 59268000 |  | 55437363 |  |  |  |  | 17783793
| Total Fund Received : |  | 22500000
| Total Fund Spent : |  | 10683793
| Balance : |  | 11816207
| Signature of Accountant |  |  | Signature of SAE |  |  | Signature of Sr. Assistant Engineer |  |  |  | Signature of Executive Engineer
| LGED, Gaibandha |  |  | LGED, Gaibandha |  |  | LGED, Gaibandha |  |  |  | LGED, Gaibandha