## Ghagot Lake
Village Road Rehab. Project Monthly Progress Report (Physical & Financial).
District : Gaibandha. | [9 empty] | Reporting Month: Up to 10-03-2019
Upazila | Approval Date | Package No | Name of scheme (chainage) | Quantity (Km/m/nos) | Approved Estimated cost (Tk) | Name of Contractor | Contract Amount (Tk) | Work Start Date | Completion Date | Physical Progress (%) | Financial Progress (%) | Payment made (Tk) | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  | 11 | 12 | 13 | 14
Saghata | 2019-01-07 | e-Tender/LGED/Gai/VRRP/18-19/W-01 | A. Rehabilitation of Saghata-Gaibandha R&H Road at Jharavarsha-Ghuridaha U.P. Office Road Ch. 00m-1490m under Saghata Upazila. Dist. Gaibandha. Road ID132884063. B. Rehabilitation of Bonarpara Saghatta Road-Bilbosta Road Ch. 00m-325m under Saghata Upazila. Dist. Gaibandha. Road ID132884026 | 1.815 | 6153429 | Md. Shamim Ahammed Mondal | 5845757.55 | 2019-03-17 | 2019-05-31 | 0 | 0
Saghata | 7-1-19 | e-Tender/LGED/Gai/VRRP/18-19/W-02 | A. Rehibilation of Thoikorer para H/O Samad Member-WAPDA Embankment Road Ch. 00-1300m under Saghata Upazila. Dist. Gaibandha. Road ID.132884041. B. Rehibilation of Falia-Panchpur Road Ch. 700m-1930m under Saghata Upazila. Dist. Gaibandha. Road ID.132885049 | 2.53 | 9722367 | M. S. S Engineering & Construction, Rangpur | 9236248.65 | 2019-03-11 | 2019-05-10 | 0% | 0% | 0
Sadullapur | 7-1-19 | e-Tender/LGED/Gai/VRRP/18-19/W-03 | Rehabilitation of Mohishbandhi Hat-Rahmatpur GC via Rasulpur Hat Road Ch. 00-530m under Sadullapur Upazila. Dist. Gaibandha. Road ID.132824023 | 0.53 | 1943783 | Md. Shamsul Alam, Gaibandha | 1846593.85 | 2019-03-19 | 2019-05-18 | 0% | 0%
Fulchari |  | e-Tender/LGED/Gai/VRRP/18-19/W-04 | Rehabilitation of Purba Salua H/O Mozibar - H/O Osman Munsi Purba Salua from Ch. 00-1014m.ID132214016 under Fulchari Upazila Dist Gaibandha.
Sundarganj |  | e-Tender/LGED/Gai/VRRP/18-19/W-05 | Rehabilitation of Bolai Samas Road from Ch.00-689m. ID132915086 under Sundarganj Upazila Dist Gaibandha.
Palashbari |  | e-Tender/LGED/Gai/VRRP/18-19/W-06 | Rehabilitation of Mostafujer Abu Talab House to Moraripur Nururzzan House from Ch.00-285m. ID132675070 under Palashbari Upazila Dist Gaibandha.
Total Taka |  |  |  |  | 17819579 |  | 16928600.05 |  |  |  |  | 0
Fund Released
[6 empty] | Balance | [5 empty] | 0
Accountant |  |  | Sub-Assistant Engineer |  | Assistant Engineer |  | Sr. Assistant Engineer |  |  |  |  | Executive Engineer
LGED, Gaibandha. |  |  | LGED, Gaibandha. |  | LGED, Gaibandha. |  | LGED, Gaibandha. |  |  |  |  | LGED, Gaibandha.