## Khulna
KHULNA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Terokhada
1 | 247942001- Sachiadah RHD Road - Nagarkandi GC via Patla GC Road (Ch: 6370m - 10084m) by BC | KDRIDP/Khul/W-01/2016-17 | 3.71 | 0 | 0 | 245.93 | 2017-05-22 | M/s Ziaul Traders | 2017-07-03 | 240.91 | 60% | 2018-08-31 |  | 119.32 | -119.32 | 49.53% | Salvage Tk. 26,86,784.00
2 | 247942006- Improvement of Ajogara R&H-Sheakpura GC Road (Ch:1881-2508m) | KDRIDP/Khul/W-70/2017-18 | 0.63 | 0 | 0 | 43.017 | 2018-06-05 | [7 empty] | 0 | #DIV/0! | Salvage Tk. 15,515.00
3 | 247942010-Nalamara R&H - Katenga GC via Abnali Rd. | [13 empty] | 0 | #DIV/0!
Dighalia
4 | 247402001 - Improvement of Daulatpur-Senhati - Magirghati road (Ch: 5955 - 8717m). | KDRIDP/Khul/W-07/2016-17 | 2.76 | 0 | 0 | 102.72 | 2017-07-27 | Mir Construction | 2017-09-10 | 96.29 | 50% | 2018-07-30 |  | 41.75 | -41.75 | 43.36% | Salvage Tk. 4,81,962.00
Batiaghata
5 | 247122003-Baroaria hat-Banikhali GC via Sundarmahal Rd. | [13 empty] | 0 | #DIV/0!
6 | 247122004-Hatbatihat-Koiyahat Rd. | [13 empty] | 0 | #DIV/0!
7 | 247122005-Hatbatihat-Koiyahat via Bagulardanga Rd. | [13 empty] | 0 | #DIV/0!
8 | 247122007-Katianangla-Roypur via Sukdara Bazar , Baro Bhuiyan & Kechrabad Rd. | [13 empty] | 0 | #DIV/0!
9 | 247122009-Sachibunia-Nijkhamar Rd. | [13 empty] | 0 | #DIV/0!
Dacope
10 | 247172001-Khona R&H-Garikhali GC (Paikgacha) via Batbunia G.C Road | [13 empty] | 0 | #DIV/0!
11 | 247172002 - Improvement of Dacope (Chunkuri Kheya Ghat) - Nalian GC via Kalinagar GC Road (Ch: 12891m - 15891m) | KDRIDP/Khul/W-61/2017-18 | 3 | 0 | 0 | 276.695 | [10 empty] | Re Tender
12 | 247172002- Improvement of Dacope (chundri kheya ghat)- Nalian GC via Kalinagor GC road (Ch: 15891m-18891m) | KDRIDP/Khul/W-66/2017-18 | 3 | 0 | 0 | 289.398
13 | 247172002 - Improvement of Dacope (Chunkuri Kheya Ghat) - Nalian GC via Kalinagar GC Road (Ch: 18891m - 21891m) | KDRIDP/Khul/W-54/2017-18 | 3 | 0 | 0 | 258.22 | 2018-02-26 | M/s Ziaul Trader | 2018-04-19 | 283.748 | 0% | 2019-04-25 |  |  | 0 | 0%
14 | 247172003-Chalna (Poddergong)-Khutakhali GC Road. | [13 empty] | 0 | #DIV/0!
15 | 247172004 - Improvement of Kalinagar GC - Khutakhali (Bajua) GC Road (Ch: 7500m -10133m) | KDRIDP/Khul/W-55/2017-18 | 2.633 | 0 | 0 | 224.09 | 2018-02-26 | M/s Ziaul Trader | 2018-04-19 | 246.266 | 0% | 2019-04-25 |  |  | 0 | 0%
16 | 247172004- Improvement of Kalinagar GC- Khutakhali (Bajua) GC road (Ch: 2517m-5000m) | KDRIDP/Khul/W-65/2017-18 | 2.483 | 0 | 0 | 259.708 | [8 empty] | 0 | #DIV/0!
17 | 247172004- Improvement of Kalinagar GC- Khutakhali (Bajua) GC road (Ch: 316m- 2517m) | KDRIDP/Khul/W-64/2017-18 | 2.201 | 0 | 0 | 229.457 | [8 empty] | 0 | #DIV/0!
Paikgacha
17 | 247642006-Kopilmuni GC-Samukpota bazar-Katamari bazar-Jamtala bazar-Baroaria GC(Paikgacha portion) . | [13 empty] | 0 | #DIV/0!
18 | 247642011 - Improvement of Paikgacha GC - Laskarhat- Fulbari Hat- Boroaria GC road (Ch: 1028m-1372m, 1756m-4550m & 6161m-8420m ) | KDRIDP/Khul/W-67/2017-18 | 5.297 | 0 | 0 | 442.458 | [8 empty] | 0 | #DIV/0! | Salvage Tk. 12,97,736.00
19 | 247642011 - Improvement of Paikgacha GC - Laskarhat- Fulbari Hat- Boroaria GC road ( Ch: 8540m-12520m) | KDRIDP/Khul/W-68/2017-18 | 3.98 | 0 | 0 | 346.986 | [10 empty] | Salvage Tk. 5,14,291.00
20 | 247642012-Paikgacha GCBaintala bazar - Gilabari GC (Paikgaha potion) road. | [13 empty] | 0 | #DIV/0!
Koyra
21 | 247532005 - Improvement of Islampur R&H - Ghugrakati GC Road (Ch: 00 - 1100m) | KDRIDP/Khul/W-23/2017-18 | 1.1 | 0 | 0 | 85.64 | 2017-09-21 | M/S Sufia Enterprise | 2017-11-13 | 77.07 | 40% | 2018-11-19 |  | 24 | -24 | 31.14% | Salvage Tk. 18,90,615.00
22 | 247532006 R&H Graduate High School-Hayatkhali Bazar road. | [13 empty] | 0 | #DIV/0!
23 | 247532010-Jagir Mahal Bazar-Gilabari GC | [13 empty] | 0 | #DIV/0!
24 | 247532011-Bamia R&H-Baskhali-Malikhali-Boga Bazar-Narayanpur Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 33.794 | 0 | 0 | 2804.319 |  |  |  | 944.284 | 30% |  | 0 | 185.07 | -185.07 | 19.6%
Improvement of Union Road by BC
Rupsha
1 | 247753004-Ghatbhog UP-Dhopakhola-Doba Bazer Road | [13 empty] | 0 | #DIV/0!
2 | 247753008-Naihati UP Office (R&H)-Lockpur GC Road. | [13 empty] | 0 | #DIV/0!
Terokhada
3 | 247943001-Ajogara UP office-Kola Bazar via Sreepur bazar Road.(Start From Agaroamtala R&H) Rd. | [13 empty] | 0 | #DIV/0!
4 | 247943004-Improvement of Barasat UP Office to Bilduria hat via Arpangasia Road (Ch:2910-4457m) | KDRIDP/Khul/W-71/2017-18 | 1.55 | 0 | 0 | 100.016 | 2018-06-05 | [7 empty] | 0 | #DIV/0! | Salvage Tk. 63,818.00
Dighalia
5 | 247403002-Shenhati GC-Shenhati UP road | [13 empty] | 0 | #DIV/0!
6 | 247403005-Digholia UP-Deara-Formizekhana | [13 empty] | 0 | #DIV/0!
7 | 247403008-Jogipola UP-Rangpur UP road | [13 empty] | 0 | #DIV/0!
8 | 247403013 - Improvement of Barakpur UP Complex-Haripada Mat-Ghoshgati Bazer Road by BC. CH -(2240m- 3340m) | KDRIDP/Khul/W-73/2017-18 | 1.1 | 0 | 0 | 76.8 | [8 empty] | 0 | #DIV/0! | Salvage Tk. 7,34,171.00
Batiaghata
9 | 247123003-Batiaghata UP at Hetalbunia - Mailmara Hat Road. | [13 empty] | 0 | #DIV/0!
10 | 247123005-Balaidanga UP-Koria hat Road. | [13 empty] | 0 | #DIV/0!
11 | 247123007- Improvement of jalma UP OFFice- Tetultola Hat Road. (CH: 1200-2500m) | KDRIDP/Khul/W-41/2017-18 | 1.3 | 0 | 0 | 80.01 | 2018-02-13 | Sk.Idris ALI | 2018-03-25 | 87.79 | 20% | 2018-11-20 |  | 30.09 | -30.09 | 34.27%
12 | 247123008-Amripur UP-Phultala hat rd. | [13 empty] | 0 | #DIV/0!
13 | 247123010- Improvement of Gangarampur CH-(00-3950m) | KDRIDP/Khul/W-43/2017-18 | 3.95 | 0 | 0 | 268 | 2018-06-20 | [7 empty] | 0 | #DIV/0!
14 | 247123011-Improvement of Bhanderkote UP Office - Purbo Halia Hat Road. (CH: 562-3000m) | KDRIDP/Khul/W-40/2017-18 | 2.438 | 0 | 0 | 145.84 | 2018-02-13 | Sk.Idris ALI | 2018-03-19 | 160.315 | 0% | 2019-02-10 |  |  | 0 | 0%
15 | 247123001-Jalma UP Office - Krishna Nagor Poultry Firm. | [13 empty] | 0 | #DIV/0!
16 | 247123014-Sukdara bazar – Surkhali UP office via gaoghara khoral | [13 empty] | 0 | #DIV/0!
Dacope
17 | 247173002 (a) Banisanta UP Office - Banisanta Bazar Road (Ch: 900m - 1725m & 4293m - 5666m) by BC & (b) Construction of 04 Nos (0.625m x 0.900m) U-Type Drain Culvert at Ch: 960m, 5420m, 5563m & 5758m on the same road. | KDRIDP/Khul/W-04/2016-17 | 2.198 | 0 | 0 | 139.99 | 2017-05-22 | M/s Ziaul Traders | 2017-07-03 | 139.78 | 30% | 2018-08-31 |  | 38.3 | -38.3 | 27.4% | Salvage Tk. 11,28,632.00
18 | 247173006-Dacope UP office-Bajua UP office Road. | [13 empty] | 0 | #DIV/0!
19 | 247173007-Kailashgong UP - Loudobe UP (Near Horintana bridge) Road. | [13 empty] | 0 | #DIV/0!
20 | 247173009 - Improvement of Pankhali UP Office (Khatail Bridge) - Moukhali Bazar Via Kabiraj bari Road (Ch: 1402 - 4175m) | KDRIDP/Khul/W-56/2017-18 | 2.773 | 0 | 0 | 222.24 | 2018-06-20 | [7 empty] | 0 | #DIV/0!
Koyra
21 | 247533001 - Improvement of Koyra UP- 4 No. Koyra Bazar Road (Ch: 2890 - 3770m) | KDRIDP/Khul/W-22/2017-18 | 0.88 | 0 | 0 | 55.83 | 2017-09-21 | Md. Bodruddoja | 2017-11-13 | 58.56 | 10% | 2018-11-19 |  |  | 0 | 0% | Salvage Tk. 6,43,104.00
22 | 247533005 - Improvement of Uttar Bedkashi UP - Barobari Bazar - Pukurpar Bazar Road (Ch: 1900- 3158m) | KDRIDP/Khul/W-21/2017-18 | 1.258 | 0 | 0 | 98.53 | 2017-09-21 | Foysal Traders | 2017-11-13 | 103.42 | 30% | 2018-11-19 |  | 26.019 | -26.019 | 25.16% | Salvage Tk. 4,33,440.00
23 | 247533006 - Improvement of Amadi UP - Amadi Bazar Road (Ch: 875 - 2140m) | KDRIDP/Khul/W-24/2017-18 | 1.265 | 0 | 0 | 80.09 | 2017-09-21 | S.M Salah uddin | 2017-11-13 | 79.19 | 65% | 2018-11-19 |  | 47.83 | -47.83 | 60.4% | Salvage Tk. 8,36,506.00
24 | 247533011-Bagali Up-Boga Bazar Rd. | [13 empty] | 0 | #DIV/0!
Paikgacha
25 | 247643001-Garaikhali Gc-Amurkata Bazar | [13 empty] | 0 | #DIV/0!
26 | 247643002-Garaikhali Gc-Gangrakhi Bazar | [13 empty] | 0 | #DIV/0!
27 | 247643004-Lata UP -Chowmohoni bazar Rd. | [13 empty] | 0 | #DIV/0!
28 | 247643005-Mamudkati College more(Goaldanga) Akamgong Bazar via Horidhali UP Office Road. | [13 empty] | 0 | #DIV/0!
29 | 247643006-Sashtitala Bazar-Raruli UP Office road | [13 empty] | 0 | #DIV/0!
30 | 247643007-Gadaipur U.P Office(New Molongi bazer)Andermanik Bazar Via Rashid mia kheyaghat | [13 empty] | 0 | #DIV/0!
31 | 247643008-Fulbari bazar-Darunmollick road | [13 empty] | 0 | #DIV/0!
Dumuria
32 | 247303002 - (a) Kanchannagar Bazar - Magurkhali UP - Magurkhali Bazar Road (Ch: 1557 - 5350m) by BC & (b) Construction of 02 Nos (0.625m x 0.600m) U-Type Drain Culvert at Ch: 2475m & 3082m on the same road. | KDRIDP/Khul/W-05/2016-17 | 3.79 | 0 | 0 | 206.97 | 2017-05-22 | Md. Noor Hossain | 2017-07-03 | 200.48 | 60% | 2018-07-09 |  | 116.848 | -116.848 | 58.28% | Salvage Tk. 2,19,703.00
33 | 247303006-Salua bazar-Raghunathpur Bazar via Rangpur UP Office Road. | [13 empty] | 0 | #DIV/0!
34 | 247303008-Gutudia UP Office-Kanchannagar bazar via Bhandarpara UP Office Road. | [13 empty] | 0 | #DIV/0!
35 | 247303009-(a) Improvement of Dunuria (Chingra) -Sovna UP –Sovna Westpara bazar (Teligati Ghat) Road (Ch: 00- 317m & 1625-5225m) (b) Rehabe. of 01 No. RCC Box Culvert at Ch: 2874m & Construction of 12 Nos Different sizes U-Type Drain culvert at Ch: 4590m, 4828m, 5160m, 1682m, 2611m, 3072m, 4270m, 2325m, 3598m, 3770m, 3940m & 4180m on the same road. | KDRIDP/Khul/W-20/2016-17 | 3.917 | 0 | 0 | 264.16 | 2017-11-09 | FT& BB JV | 2017-10-30 | 256.02 | 30% | 2018-11-05 |  | 50.916 | -50.916 | 19.89% | Salvage Tk. 43,14,618.00
36 | 247303010-Shovna UP-Zialtala Bazar Road | [13 empty] | 0 | #DIV/0!
37 | 247303011-Kathalia bazar-Magurikhali UP via Pashchim Patibunia road | [13 empty] | 0 | #DIV/0!
38 | 247303015-Kharnia UP-Sovna westpara bazar road | [13 empty] | 0 | #DIV/0!
39 | 247303017- Improvement of Gutudia UP –Salua Bazar Road (Ch: 00 - 3900m) | KDRIDP/Khul/W-18/2016-17 | 3.9 | 0 | 0 | 282.33 | 2017-11-09 | M/s Ziaul Traders | 2017-10-31 | 295.74 | 60% | 2018-11-06 |  | 168.809 | -168.809 | 57.08% | Salvage Tk. 80,60,627.00
40 | 247303016-Chuknagar Eidgah(R&H)-Atlia UP-Chuknagar GC-Narnia(R&H) | [13 empty] | 0 | #DIV/0!
41 | 247303020-Improvement of Mathertala Bazar-Magurkhali UP Office via Hatitana More Road (Ch: 700 - 4000m) | KDRIDP/Khul/W-19/2016-17 | 3.3 | 0 | 0 | 240.06 | 2017-11-09 | M/S Rupa Enterprise | 2017-10-31 | 230.96 | 45% | 2018-11-05 |  | 84.116 | -84.116 | 36.42% | Salvage Tk. 23,98,533.00
42 | 247303022-Sahos UP-Moikhali bazar Rd. | [13 empty] | 0 | #DIV/0!
43 | 247303023-Basundiadanga Bazar - Magurkhali UP Office Rd. | [13 empty] | 0 | #DIV/0!
44 | 247303024-Shahos UP Office (Kumarghata Amtala more)- Kadamtala Koyaghat Bazar via KDC Pry. School Rd. | [13 empty] | 0 | #DIV/0!
45 | 247303002-Kanchannagar Bazar-Magurkhali UP - Magurkhali Bazzar road. | [11 empty] | 0 | 0 | 0 | #DIV/0! | Duplicate as SL. No. 32
Phultala
46 | 247693006-Damodar UP-Alka Transmeter bazar via Damodar Kolony & Alka Dakkin para. | [13 empty] | 0 | #DIV/0!
Total |  |  | 33.619 | 0 | 0 | 2260.866 |  |  |  | 1612.255 | 35% |  | 0 | 562.928 | -562.928 | 34.92%
Improvement of Village Road by BC
Rupsha
1 | 247754024 - Rupsha Bagerhat Noman School - Tilokhat via Khider Box House - Janata Market Road (Ch: 2216m - 5986m) by BC & (b) Construction of 02 Nos (1.00m x 1.00m) U-Type Drain Culvert at Ch: 2105m & 2959m on the same road. | KDRIDP/Khul/W-03/2016-17 | 3.77 | 0 | 0 | 192.88 | 2017-05-22 | Md. Noor Hossain | 2017-07-03 | 187.25 | 60% | 2018-07-09 |  | 117.36 | -117.36 | 62.68% | Salvage Tk. 60,06,901.00
2 | 247754025-Jabusa-Bhangonpar-Jabusa h/s-Khayghat Rd. | [13 empty] | 0 | #DIV/0!
3 | 247755009-Gilatala-S.Bahirdia Thana boundary Rd. | [13 empty] | 0 | #DIV/0!
4 | 247755019-Shealihat-Nornia WAPDA Rd. | [13 empty] | 0 | #DIV/0!
5 | 247755111 - Improvement of Alipur collage-shahabuddin sikder house - Bhabanipur School road (ch: 00-1750m) | KDRIDP/Khul/W-09/2016-17 | 1.75 | 0 | 0 | 102.87 | 2017-11-09 | M/S Mizan Enterprise | 2017-09-10 | 97.32 | 70% | 2018-09-30 |  | 59.74 | -59.74 | 61.39% | Salvage Tk. 10,87,735.00
6 | 247755206 - Improvement of Deara Paulpara - Agrodut Field via Chairman House Road (Ch: 240 -1043m) [Rupsa] [Salvage Cost of this package is Tk 683664.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-32/2017-18 | 0.803 | 0 | 0 | 51.3 | 2018-02-13 | M/S Totul & Co | 2018-03-15 | 51.297 | 30% | 2019-02-05 |  | 22.347 | -22.347 | 43.56%
7 | 247755290 - Improvement of Narikali Raton dey house - Chara Battala Via Bablu sheik house road (Ch. 500-1000m) | KDRIDP/Khul/W-08/2016-17 | 0.5 | 0 | 0 | 23.88 | 2017-11-09 | M/s Ziaul Traders | 2018-01-11 | 25.03 | 10% | 2018-08-06 |  |  | 0 | 0% | Salvage Tk. 1,53,369.00
8 | 247755387-Alaipur -Sheikhpura FRB- Narikeli Rabindranath house-Kachatala Bazar Rd. | [13 empty] | 0 | #DIV/0!
9 | 247755450-TSB UP Goalbathan R&H Road-Noor Mohammad Fakir house to driver Wadud Kazi house | [13 empty] | 0 | #DIV/0!
10 | 247755396 - Improvement of Uttar Khajadanga Main Road - Arafat House via Mosjid to Rafiqul Shop Road (Ch: 00 - 900m) [Rupsa] [Salvage Cost of this package is Tk 709542.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-33/2017-18 | 0.9 | 0 | 0 | 58.38 | 2017-12-28 | M/S Totul & Co | 2018-03-15 | 61.29 | 0% | 2019-02-05 |  |  | 0 | 0%
11 | 247755440-(a) Improvement of Elaipur Khorshed Ali house-Shobedali house road via Motair Chairman house Road (Ch: 00-725m) by BC (b) Construction of 02 Nos 0.600m x 0.600m U-Type Drain culvert at Ch: 165m & 265m on the same road. | KDRIDP/Khul/W-14/2016-17 | 0.725 | 0 | 0 | 51.26 | 2017-11-09 | M/s Ziaul Traders | 2018-01-11 | 53.72 | 30% | 2018-10-19 |  | 32.173 | -32.173 | 59.89% | Salvage Tk. 4,04,987.00
12 | 247755441-(a) Improvement of Elaipur Primary School-Rupsha Mongla (R&H) road via Motair Chairman house Road (Ch: 00-555m) by BC (b) Construction of 05 Nos 0.600m x 0.600m U-Type Drain culvert at Ch: 210m, 340m, 370m, 451m & 540m on the same road. | KDRIDP/Khul/W-15/2016-17 | 0.55 | 0 | 0 | 38.406 | 2017-11-09 | M/s Ziaul Traders | 2018-01-11 | 40.25 | 30% | 2018-06-08 |  | 13.53 | -13.53 | 33.61% | Salvage Tk. 4,27,750.00
13 | 247755060 - Improvement of Kazdia Bazar - Kazdia Eid Gah - Bari Sk's House Road (Ch: 00 -1290m) [Rupsa] [Salvage Cost of this package is Tk 1777999.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-36/2017-18 | 1.29 | 0 | 0 | 91.3 | 2017-10-24 | M.A Jalil Khan | 2017-12-10 | 95.41 | 30% | 2018-10-20 |  | 25 | -25 | 26.2% | Salvage Tk. 17,77,999.00
14 | 247755162 -Improvement of Rupali Sea Food - Gupiar Khal via Shahjahan Graders House to Al - Aksa Koborkhana Road (Ch: 00 - 520m) [Rupsa] [Salvage Cost of this package is Tk 158397.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-35/2017-18 | 0.52 | 0 | 0 | 32.57 | 2017-12-28 | M/S Totul & Co | 2018-03-25 | 34.85 | 0% | 2018-12-31 |  |  | 0 | 0%
15 | 247755047 - Mahabub House - Siddique Sheikh House (Ch: 00-480m) road. | KDRIDP/Khul/W-13/2016-17 | 0.48 | 0 | 0 | 30.95 | 2017-10-24 | M/s. Milon Treders | 2017-12-10 | 30.7 | 30% | 2018-09-16 |  |  | 0 | 0%
Terokhada
16 | 247944005 - Gazipur - Harikhali via Nebudia Road (Ch: 00 - 1268m) by BC | KDRIDP/Khul/W-02/2016-17 | 1.268 | 0 | 0 | 69.12 | 2017-05-22 | M/s Ziaul Traders | 2017-07-03 | 67.73 | 40% | 2018-08-31 |  | 16 | -16 | 23.62% | Salvage Tk. 5,95,379.00
17 | 247944008-Mokampur village Road. | [13 empty] | 0 | #DIV/0!
18 | 247944012-Atlia Bazar Parokhali Adampur FRB Road. | [13 empty] | 0 | #DIV/0!
19 | 247944017-Patla Karoria-Induhati FRB Road. | [13 empty] | 0 | #DIV/0!
20 | 247944021-Improvement of Terokhada R&H- Nebudia road (Ch:500-1475m& 1970-2665m) | KDRIDP/Khul/W-72/2017-18 | 1.67 | 0 | 0 | 121.946 | [8 empty] | 0 | #DIV/0! | Salvage Tk. 5,41,506.00
21 | 247944022-Harikhali(Manrartali) R&H-Gazipur Road. | [13 empty] | 0 | #DIV/0!
22 | 247944025-NebudiaR&H Bridge to Nalamara R&H Bridge road Via Kagdi | [13 empty] | 0 | #DIV/0!
23 | 247944028-Isamti WDB Iate - Isamoti kuti shop rd | [13 empty] | 0 | #DIV/0!
24 | 247945064-South Modhupur Khalpar road | [13 empty] | 0 | #DIV/0!
25 | 247945105-Sachiadh Dhali house-Diliproy house road | [13 empty] | 0 | #DIV/0!
26 | 247945153-Naliarchar Modhyapara - Oliar Mollah more Rd. | [13 empty] | 0 | #DIV/0!
Dighalia
27 | 247404033 - Improvement of Teligati Pakar Matha to Rajapur Ghat road (Ch: 00 - 1630m). | KDRIDP/Khul/W-06/2016-17 | 1.63 | 0 | 0 | 54.91 | 2017-07-27 | S.M Salah uddin | 2017-09-10 | 50.62 | 100% | 2018-09-30 | 50.56 | 50.56 | 0 | 99.88% | Final (Salvage Tk. 2,00,716.00)
28 | 247404035- Improvement of Brahmmagati Sutirkul to Lakhohati Bazar road Ch (500m-1365m) | KDRIDP/Khul/W-44/2017-18 | 0.865 | 0 | 0 | 56.94 | 2018-01-31 | M/S Zaman Enterprise | 2018-03-22 | 62.468 | 0% | 2019-03-28 |  |  | 0 | 0%
29 | 247404037- Improvement of Maheshdia to Katla Via Ambaria Road CH-( 00-2690) | KDRIDP/Khul/W-46/2017-18 | 2.69 | 0 | 0 | 180.54 | 2018-02-01 | M/S Rafique Enterprise | 2018-03-11 | 188.21 | 0% | 2019-03-17 |  |  | 0 | 0%
30 | 247404072-Chandanimahal Vottacharja Bazar - Katabon Picnic Corner Via KITCMill,MoslemBayati AdGolam Ali Sk. Sk Para Jame Mosque, HumaunMember, Vuipara & Puja Mondir Road. | [13 empty] | 0 | #DIV/0!
31 | 247404062-Senhati Katanipara Hoglar More - Bativita Ashraf House H/O Koykobad Rd. | [13 empty] | 0 | #DIV/0!
32 | 247404107 - Improvement of jangushia Fakirpara Chara Battalar More Par Mochomdapur Hari Mondir via Bagmara shop/Khokon road CH -( 240m- 1055m) | KDRIDP/Khul/W-45/2017-18 | 0.815 | 0 | 0 | 59.376 | 2018-06-05 | [7 empty] | 0 | #DIV/0!
Batiaghata
33 | 247124008-Joypur hat-Shadaler hat via Amripur Pry.School Rd. | [13 empty] | 0 | #DIV/0!
34 | 247124014-Manobshebaloy-Choyghoria box culvert Rd. | [13 empty] | 0 | #DIV/0!
35 | 247124019-Dhadua Pry.School-Joypur Hela Battala Rd. | [13 empty] | 0 | #DIV/0!
36 | 247124034-Shimana - Badamtala Hat Road. | [13 empty] | 0 | #DIV/0!
37 | 247124036- Improvement of Bagmara Harintana CH- (940m- 2150m) | KDRIDP/Khul/W-42/2017-18 | 1.21 | 0 | 0 | 82.61 | 2018-01-31 | M/S F. K construction | 2018-03-25 | 86.74 | 15% | 2019-03-31 |  |  | 0 | 0%
38 | 247124041-Choyghoria R&H-Rupsha bridge Rd | [13 empty] | 0 | #DIV/0!
39 | 247124042-Chourangi hat- Sholmari Ghat Rd | [13 empty] | 0 | #DIV/0!
40 | 247124046 - Improvement of Katianangla Sluicegate - Baronpara via Kayemkhola Hula Road (Ch: 5650 - 6315m) | KDRIDP/Khul/W-26/2017-18 | 0.665 | 0 | 0 | 39.43 | 2017-09-21 | M/S Sufia Enterprise | 2017-11-13 | 35.49 | 30% | 2018-08-19 |  | 9 | -9 | 25.36% | Salvage Tk. 3,35,504.00
41 | 247124053 - Improvement of Nirala Tablig Mosque - Rupsha Bridge Approach Road via Nirala & Shabujbag Residential area Road (Ch: 00 - 880m) [Batiaghata] | KDRIDP/Khul/W-31/2017-18 | 0.88 | 0 | 0 | 98.09 | 2017-09-25 | M/S Sufia Enterprise | 2017-11-13 | 89.93 | 0% | 2018-11-19 |  |  |  |  | Salvage Tk. 3.77.663.00
42 | 247124061-Nirala Kobor KhanaTo Rupsha Bipas Rd | [13 empty] | 0 | #DIV/0!
43 | 247125056-Parbatiaghata - Shailamari Khayaghat Rd | [13 empty] | 0 | #DIV/0!
44 | 247125058- Hatbati mot - Saaliamari Khayghat Rd | [13 empty] | 0 | #DIV/0!
45 | 247125158-Bunarabad BWDP-near H/Q Sharil- Banarabad H/Q. Afjal M | [13 empty] | 0 | #DIV/0!
46 | 247125159-Hoglabuni WAPDA-Bunaradad Durga Mondir | [13 empty] | 0 | #DIV/0!
47 | 247125160-Gariardanga Collage- Gariardanga Moth | [13 empty] | 0 | #DIV/0!
48 | 247124016-Noailtala Hat - Shialidanga Hat Road. | [13 empty] | 0 | #DIV/0!
49 | 247124052- (a) Improvement of Harintana Jabber Sarak road (Ch: 00 - 442m) by BC [247124052] (b) Construction of 01 No. 0.600m x 0.600m U-drain Culvert at Ch: 103m on the same road. | KDRIDP/Khul/W-17/2016-17 | 0.442 | 0 | 0 | 20.97 | 2017-11-10 | M/s Ziaul Traders | 2018-01-11 | 21.98 | 20% | 2018-08-06 |  |  | 0 | 0% | Salvage Tk. 1,79,262.00
Dacope
50 | 247174006 - Improvement of Yasin School near Hoglabunia Khalergora road (Ch: 1500 - 1806m) [Dacope] | KDRIDP/Khul/W-27/2017-18 | 0.306 | 0 | 0 | 24.49 | 2017-09-21 | S.M Salah uddin | 2017-11-13 | 23.61 | 30% | 2018-11-19 |  |  | 0 | 0% | Salvage Tk. 1,42,024.00
51 | 247174007 - Lodobe Bazar to Buridabur via Kalikabati Prymari School Road Ch - (2500m- 5000m) | KDRIDP/Khul/W-57/2017-18 | 2.5 | 0 | 0 | 189.465 | 2018-06-05 | [7 empty] | 0 | #DIV/0!
52 | 247174010-Batbunia GC to Laxmikhala Bazar Via Kachari Bari road. | [13 empty] | 0 | #DIV/0!
53 | 247174028-Khajuria WDB Gora N/H/O Krisnopada to Dhangmari Biswanat P/School via Binapani GPS Road. | [13 empty] | 0 | #DIV/0!
54 | 247174032-Laxmikhola Khatail Bridge to Laxmikhola CARE Pucca Road via Moukhali N/H/O Seromone Mondal Road. | [13 empty] | 0 | #DIV/0!
55 | 247175035-Kailashgong Bhutiamari Bazer to Kailashgong Denash Mondal house via Bangabandhu H/School & Dolkhola Hospital Road. | [13 empty] | 0 | #DIV/0!
56 | 247174011-Batbunia GC to Mozamnagor School (Bazar) Road Via Binakpani P/School Road. | [13 empty] | 0 | #DIV/0!
57 | 247174020-(a) Improvement of Shatghoria H/O Oma Sarkar –Shaharabad H/O Kalam Halder via H/O Momen Sheikh road (Ch: 00 - 2850m) by BC [247174020] (b) Construction of 01 No. 2.00m x 2.00m RCC Box Culvert at Ch: 1023m on the same road. (b) Construction of 07 No. 0.625 x 0.900m U-drain Culvert at Ch: 870m, 1260m, 1460m, 1770m, 1890m, 2240m & 2350m on the same road. | KDRIDP/Khul/W-16/2016-17 | 2.85 | 0 | 0 | 201.27 | 2017-11-09 | AT&NE JV | 2017-11-13 | 201.09 | 25% | 2018-11-19 |  |  | 0 | 0% | Salvage Tk. 4,87,108.00
Koyra
58 | 247534002-R & H Kalna-Dashalia Khya Ghat Road | [13 empty] | 0 | #DIV/0!
59 | 247534003 - Improvement R&H - Deara - Rongbag UZR Road (Ch: 00 - 2270m) [Koira] [Salvage Cost of this package is Tk 3624706.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-37/2017-18 | 2.27 | 0 | 0 | 163.109 | 2018-06-05 | [7 empty] | 0 | #DIV/0! | Salvage Tk. 36,24,706.00
60 | 247534012-Ghorilal FRB-Golkhali Pry. School road | [13 empty] | 0 | #DIV/0!
61 | 247534023 - Improvement of Harihorpur Parimary School - Binapani CARE Road (Ch: 00 - 975m) [Koira] | KDRIDP/Khul/W-25/2017-18 | 0.975 | 0 | 0 | 66.81 | 2017-09-21 | M/S Sufia Enterprise | 2017-11-13 | 60.13 | 0% | 2018-11-19 |  |  | 0 | 0% | Salvage Tk. 5,86,565.00
62 | 247534024-Holdibunia UZR .-Charamukha Road | [13 empty] | 0 | #DIV/0!
63 | 247534028-Hatiardanga Surikhali-Chowmohona Bazar(Koyra Portion) | [13 empty] | 0 | #DIV/0!
64 | 247534029-R&H Road-Mosjidkur | [13 empty] | 0 | #DIV/0!
65 | 247534036-Dewliar Hat-Kashirabad BC Road via Uttar Chack Madrasha | [13 empty] | 0 | #DIV/0!
66 | 247534080- Improvement of khirul BC road-Basepara BC road.(CH: 680-1563m) | KDRIDP/Khul/W-39/2017-18 | 0.883 | 0 | 0 | 54.42 | 2018-06-05 | [7 empty] | 0 | #DIV/0!
67 | 247534058-Chandipur R&H Khirul Lunch Ghat | [13 empty] | 0 | #DIV/0!
68 | 247534057- Improvement R&H Hatiardanga Culvert Surikhali Bazar via Patnikhali Road (Ch: 2060-2522m, 2522-3500m & 4450-5300m) [Koira] [Salvage Cost of this package is Tk 683306.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-38/2017-18 | 2.29 | 0 | 0 | 132.33 | 2018-02-26 | Foysal Traders | 2018-04-08 | 141.59 | 30% | 2019-04-14 |  | 38 | -38 | 26.84% | Salvage Tk. 6,83,306.00
69 | 255575218- Beltala Pucca road-Hanif Biswas house road. | [13 empty] | 0 | #DIV/0!
70 | 255575217-Ramchandrapur Mosur Biswas house to cannel road. | [13 empty] | 0 | #DIV/0!
71 | 247534005-Uttar Chowkuni-Purbo Chowkoni Regd. Pry. School. | [13 empty] | 0 | #DIV/0!
72 | 247534070-Hatiardanga Culvert-Patnikhali Foot Bridge | [13 empty] | 0 | #DIV/0!
73 | 247535048-Channirchok Girl's School- Kataltola khal road. | [13 empty] | 0 | #DIV/0!
74 | 247534035-Hudabonia-Channichok (Culvert-Rashipara) road. | [13 empty] | 0 | #DIV/0!
75 | 2475535017-Hudda -Banikhali road -Sonil Master H/o. | [13 empty] | 0 | #DIV/0!
76 | 247535113-Kalna Amzad Molla H/O road -Hossain Hawlder H/O road. | [13 empty] | 0 | #DIV/0!
77 | 247535079-2 No Koyra R&H (Habibur Shope-Majherite BC via Nolpara road. | [13 empty] | 0 | #DIV/0!
78 | 1 No. Koyra BC Road-H/O Anser Gazi | [13 empty] | 0 | #DIV/0!
Phultala
79 | 247694010-Pura Buttala Road. | [13 empty] | 0 | #DIV/0!
80 | 247694032 - Improvement of Paygram Kashba Shikir hat CH - ( 00m- 641m) | KDRIDP/Khul/W-47/2017-18 | 0.641 | 0 | 0 | 39.779 | 2018-06-05 | [7 empty] | 0 | #DIV/0!
81 | 247694084 - Improvement Satiani Bazar - Jamira GC Road (Ch: 1085 - 1325m) | KDRIDP/Khul/W-28/2017-18 | 0.24 | 0 | 0 | 14.15 | 2017-09-25 | M/S Sufian Enterprise | 2017-11-03 | 13.73 | 100% | 2018-08-20 |  | 4.79 | -4.79 | 34.89% | Salvage Tk. 3,28,628.00
82 | 247694090-Damotar GPS-Korai Comp. Factory Rd. | [13 empty] | 0 | #DIV/0!
83 | 247694099 - Improvement of Phultala Rail Station - Phultala Thana H/Q Road (Ch: 627 - 1818m) | KDRIDP/Khul/W-30/2017-18 | 1.191 | 0 | 0 | 64.209 | 2017-09-25 | Md. Ziaul Haque. | 2017-11-13 | 59.71 | 50% | 2018-09-27 |  | 25.824 | -25.824 | 43.25% | Salvage Tk. 5,60,209.00
84 | 247694102 - Improvement of Muktisory Mazar- Bejerdanga Bazar road (Ch: 605 - 750m). | KDRIDP/Khul/W-12/2016-17 | 0.145 | 0 | 0 | 8.25 | 2017-10-27 | M/S Rupa Enterprise | 2017-09-10 | 8.005 | 100% | 2018-04-25 | 7.827 | 7.827 | 0 | 97.78% | Final (Salvage Tk. 5,60,209.00)
85 | 247694105 - Improvement of Bejerdanga-Rabindra Complex upto Shikirhat road (Ch: 1320- 2520m). | KDRIDP/Khul/W-10/2016-17 | 1.2 | 0 | 0 | 70.49 | 2017-10-27 | M/S Rupa Enterprise | 2017-09-10 | 66.61 | 100% | 2018-07-25 |  | 38.179 | -38.179 | 57.32% | Salvage Tk. 7,51,308.00
86 | 247694109-Pro.Safiullas/H - Alka gate road. | [13 empty] | 0 | #DIV/0!
87 | 247694117 - Improvement of Bejerdanga Rail Station - Bejerdanga Primary School Volapata UZR Road (Ch: 1550 - 2640m) | KDRIDP/Khul/W-29/2017-18 | 1.09 | 0 | 0 | 63.715 | 2017-09-25 | Md. Ziaul Haque. | 2017-11-13 | 61.8 | 10% | 2018-09-27 |  |  | 0 | 0%
88 | 247694118-Bejerdanga rail station Dhakuria primary school - Bejerdanga school road. | [13 empty] | 0 | #DIV/0!
89 | 247694080 - Improvement of Shirmoni Bazar-Dakatia Beel via Imam Bari road (Ch: 2040 - 2430m). | KDRIDP/Khul/W-11/2016-17 | 0.39 | 0 | 0 | 23.86 | 2017-10-27 | M/S Rupa Enterprise | 2017-09-10 | 22.54 | 100% | 2018-04-25 | 22.49 | 22.49 | 0 | 99.78% | Final (Salvage Tk. 2,66,250.00)
Dumuria
90 | 247304002-Khornia-Pachpota Rd | [13 empty] | 0 | #DIV/0!
91 | 247304009- Moikhali UZR (Fotik Shop)-Banda Bazar Rd | [13 empty] | 0 | #DIV/0!
92 | 247304013- Zelerdanga RHD-Vhanderpur UP Rd | [13 empty] | 0 | #DIV/0!
93 | 247304021 Improvement of Ula Hazibunia road- Kanchan nagar Bazar Road CH - ( 2307m - 2530m) | KDRIDP/Khul/W-52/2017-18 | 0.223 | 0 | 0 | 15.73 | 2018-02-01 | Bishowajit Kundu | 2018-03-25 | 16.86 | 100% | 2018-12-31 | 16.858 | 16.858 | 0 | 99.99% | Final
94 | 247304023 Improvement Alapur R&H Baduria Bazar Road (Ch: 1375m-2685m) and (3673m-3923m) | KDRIDP/Khul/W-62/2017-18 | 1.56 | 0 | 0 | 216.96 | 2018-03-29 | M/S Amin & Co. | 2018-05-28 | 216.198 | 0% | 2019-04-02 |  |  | 0 | 0%
95 | 247304028-Vhandarpara UP (Vanda bazar)-Dhanibunia bazar UZR Road. | [13 empty] | 0 | #DIV/0!
96 | 247305488- Improvement of Rangpur Goramipara via Mallik house Road Ch-( 0.00- 1555m) | KDRIDP/Khul/W-53/2017-18 | 1.555 | 0 | 0 | 125.865 | 2018-06-05 | [7 empty] | 0 | #DIV/0! | Salvage Tk. 13,01,215.0
97 | 247304027-Chuknagar petrol pump-Baduria bazar Road. | [13 empty] | 0 | #DIV/0!
98 | 247304032-Zelerdanga R&H-Kuloty-Bakultala Bazar -Falymary Bastar Mill Rd. | [13 empty] | 0 | #DIV/0!
99 | 247304033-Daulatpur-Shahpur UZR-Thukri bazar Rd. | [13 empty] | 0 | #DIV/0!
100 | 247304056-Ranai R&H palbari WAPDA | [13 empty] | 0 | #DIV/0!
101 | 247304085 - Improvement of Shibpur - Zialtala Bazar via Gosai Bari Road (Ch: 800m - 1432m) | KDRIDP/Khul/W-63/2017-18 | 0.632 | 0 | 0 | 49.487 | 2018-02-26 | Bishowajit Kundu | 2018-04-19 | 48.88 | 30% | 2019-01-25 |  | 11.019 | -11.019 | 22.54%
102 | 247305126 - Improvement of Mirzapur- Kharia road (Ch. 0.00m- 1390m). | KDRIDP/Khul/W-69/2017-18 | 1.39 | 0 | 0 | 104.999 |  | Bishowajit Kundu | 2018-06-07 | 109.09 |  | 2019-06-13 |  |  | 0 | 0% | Salvage Tk. 6,45,305.00
103 | 247305078 - Improvement of Salua Maloapara road CH - (00- 467m) | KDRIDP/Khul/W-49/2017-18 | 0.467 | 0 | 0 | 44.86 | 2018-01-31 | Bishowajit Kundu | 2018-03-25 | 44.277 | 70% | 2018-12-31 |  | 26.9 | -26.9 | 60.75% | Salvage Tk. 3,29,948.00
104 | 247305149 - Improvement of Chingra- Gabtola Road CH - ( 00m-2230m) | KDRIDP/Khul/W-50/2017-18 | 2.23 | 0 | 0 | 146.02 | 2018-06-05 | [7 empty] | 0 | #DIV/0!
105 | 247304061-Khukia south para-Uttarpara | [13 empty] | 0 | #DIV/0!
106 | 247305197-Udayan School- Baladuni Primary School road | [13 empty] | 0 | #DIV/0!
107 | 247304051-Checuri Police Camp-Bakultalr more | [13 empty] | 0 | #DIV/0!
108 | 247304045-Adarsha gram R&H Golna Razzak Dr. house Bhadurpur | [13 empty] | 0 | #DIV/0!
109 | 247305125-Golna South para rd | [13 empty] | 0 | #DIV/0!
110 | 247305207-Ranai Village Road | [13 empty] | 0 | #DIV/0!
111 | 247305266-Tipna Viaalage road (Tipna Sk.-Community Clinic | [13 empty] | 0 | #DIV/0!
112 | 247305013-Sahahapur-Fokir bari road | [13 empty] | 0 | #DIV/0!
113 | 247305017-Anduli Sahapara | [13 empty] | 0 | #DIV/0!
114 | 247305191-Anduli grmeen tower-beel Dakatia | [13 empty] | 0 | #DIV/0!
115 | 247305195-Komrai Madrasha-Komiail Primary School | [13 empty] | 0 | #DIV/0!
116 | 247305234-Anduli R&H Palut house to Shahajan Shaik house | [13 empty] | 0 | #DIV/0!
117 | 247305238 Improvement of Ragunatpur Rishebari Road CH - (00m- 575m) | KDRIDP/Khul/W-51/2017-18 | 0.575 | 0 | 0 | 42.778 | 2018-02-01 | Bishowajit Kundu | 2018-03-25 | 42.14 | 40% | 2018-12-31 |  | 14.4 | -14.4 | 34.17%
118 | 247305243-Thukra Bazar to Rupa Rampur Village road | [13 empty] | 0 | #DIV/0!
119 | 247305158-Rudaghora Bazar-Gholder para | [13 empty] | 0 | #DIV/0!
120 | 247305215-Rudaghora Soial RD | [13 empty] | 0 | #DIV/0!
121 | 247305252-Dumuria Miksimil (R&H) Hassanpur-Joardar para | [13 empty] | 0 | #DIV/0!
122 | 247305376-Hasanpur Joarder bari Mosque-Abdulla Jordar bari road | [13 empty] | 0 | #DIV/0!
123 | 247304061-Khukia Southpara -Uttarpara | [13 empty] | 0 | #DIV/0!
124 | 247305075-Gajendrapur-bazar UNR Gajendrapur Uttarpara (Jorakhal wazad sheik house) | [13 empty] | 0 | #DIV/0!
125 | 247305220-Gajendrapur Village road (Nowsher Master house Telepukur-Vadra Bari | [13 empty] | 0 | #DIV/0!
126 | 247305279-Gozendrapur khabari-Hajibunia road (Madrasha via saheb ali sheik house – Musa Shop) | [13 empty] | 0 | #DIV/0!
127 | 247305280-Gozendrapur Dakhin para road | [13 empty] | 0 | #DIV/0!
128 | 247304079-Catcatia –Akra WAPDA | [13 empty] | 0 | #DIV/0!
129 | 247305203-Kalikapur Goldarpara -jhaltola | [13 empty] | 0 | #DIV/0!
130 | 247304037-Baliakhali Bazar-Hamkura Bazar-Thukra Bazar | [13 empty] | 0 | #DIV/0!
131 | 247305147-Shahos Kazirulla -Patibunia Road | [13 empty] | 0 | #DIV/0!
132 | 247305165-Purba Bilpabla Rayermohal- Pasim Bilpubla Road | [13 empty] | 0 | #DIV/0!
133 | 247305404-Hazibunia Dakhin para- Kanchannagor Road | [13 empty] | 0 | #DIV/0!
134 | 247305037- Bayar sing - Adharmani via AKBK School Road | [13 empty] | 0 | #DIV/0!
135 | 247305136-Mathertala Bazar - Chittramari Purbapara via Gajalia Road | [13 empty] | 0 | #DIV/0!
136 | 247305262-Dumuria Miximil R&H -Dumuria College ( Khulna - Satkhira R&H) Road | [13 empty] | 0 | #DIV/0!
137 | 247305048-Chucknagor Bazar - Chakundia Sardar Bari Road | [13 empty] | 0 | #DIV/0!
138 | 247304038-Mathertala Bazar - Badurgacha Mahasasan Road | [13 empty] | 0 | #DIV/0!
Paikgacha
139 | 247644001-Ramnathpur-Taltala road. | [13 empty] | 0 | #DIV/0!
140 | 247644003-Mothbaria R&H-Ghosal road. | [13 empty] | 0 | #DIV/0!
141 | 247644006-Habibnagar madrasha-Samukpota bazar road. | [13 empty] | 0 | #DIV/0!
142 | 247644010-Betbuni-Amurkata road. | [13 empty] | 0 | #DIV/0!
143 | 247644014-Paikgacha GC-Samukpota Bazar road. | [13 empty] | 0 | #DIV/0!
144 | 247644015 - Improvement of Paikgacha GC - Laskar Hat road . ( Ch: 0.00 - 1400m ) | KDRIDP/Khul/W-60/2017-18 | 1.4 | 0 | 0 | 89.09 | 2018-01-30 | M/S Ziaul Traders | 2018-03-25 | 97.91 | 0% | 2019-03-31 |  |  | 0 | 0%
145 | 247644013-Improvement of Gorikhali - Kumkhali BB road Gorikhali Almin road via South Kumkhali Master Shibpodo Model H/Q Bridge Road. ( Ch: 1324m-3000m) | KDRIDP/Khul/W-58/2017-18 | 1.676 | 0 | 0 | 104.91 | 2018-01-30 | M/S Ziaul Traders | 2018-03-25 | 115.3 | 30% | 2019-03-31 |  |  | 0 | 0%
146 | 247645146 - Improvement of Patkalkhali Bridge Kathtola BC road. (Ch: 0.00m-1110m) | KDRIDP/Khul/W-59/2017-18 | 1.11 | 0 | 0 | 69.95 | 2018-01-30 | M/S Zaman Enterprise | 2018-03-22 | 76.78 | 0% | 2019-03-28 |  |  | 0 | 0% | NoA Issued
147 | 247644048-Goraikhali-Hathair Danga via Knakhali Govt.Pri.School( West Side of Khal) to kanakhali Bridge. | [13 empty] | 0 | #DIV/0!
Total |  |  | 53.212 | 0 | 0 | 3584.724 |  |  |  | 2706.535 | 36.39% |  | 97.735 | 551.997 | -454.262 | 20.39%
Improvement of Village Road by HBB
Rupsha
1 | 247755118 - Improvement of Alaipur - Anandanagar FRB Putimari - Peara Village Jami Mosque - Chandunsree H/O Khalid Howlader Road by HBB (Ch: 00 - 2500m) [Rupsa] [Salvage Cost of this package is Tk 623967.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-34/2017-18 | 2.5 | 0 | 0 | 98.9 | 2017-10-24 | M/s Amin & Co. | 2017-12-05 | 89.01 | 5% | 2018-12-11 |  |  | 0 | 0% | Salvage Tk. 6,23,967.00
Terokhada
2 | 247944023- Improvement of Bhujinia(start from Ajogara R&H) to Promodnagar road by HBB (Ch:2630-4630m) | KDRIDP/Khul/W-70/2017-18 | 2 | 0 | 0 | 73.8 | 2018-06-05 | [7 empty] | 0 | #DIV/0!
3 | 247944007-Development Of WAPDA Embankment –Kaibarta Shisa Road | [13 empty] | 0 | #DIV/0!
4 | 247944009-Development of South Bnk of Laskerpur Khal Road | [13 empty] | 0 | #DIV/0!
5 | 247944023-Development of Bhujnia (start from Ajogara R&H ) to promodangar via kalinagar road | [13 empty] | 0 | #DIV/0!
6 | 247944024-Development of chaglada Bazar –Kusla Primary School road | [13 empty] | 0 | #DIV/0!
7 | 247945009-Development of Bipara Ajogara CARE road. | [13 empty] | 0 | #DIV/0!
8 | 247945014-Development of Rostom Ajogara road. | [13 empty] | 0 | #DIV/0!
9 | 247945018-Development of Biri Ajogara-North para road. | [13 empty] | 0 | #DIV/0!
10 | 247945024-Develpment of Kharbireya road. | [13 empty] | 0 | #DIV/0!
11 | 247945027-Development of Anandanagar-Goara Ferry Ghat road. | [13 empty] | 0 | #DIV/0!
12 | 247945029-Development of Anadanagar Madrasha road. | [13 empty] | 0 | #DIV/0!
Dacope
13 | 247174002-Rajnagar Channir chalk P/School-JoynagorBazar road. | [13 empty] | 0 | #DIV/0!
Paikgacha
14 | 247644020-Barigari house at Soladana UZR-Amurkata Bazar Rd. | [13 empty] | 0 | #DIV/0!
Dumuria
15 | 247305104 - Improvement of Line Bilpabla (Rayer Mohol Sluice gate) - Uttar Bilpabla - Shikderpara - Junction mor Road (Ch: 715m- 3550m) By HBB | KDRIDP/Khul/W-48/2017-18 | 2.835 | 0 | 0 | 149.96 | 2018-01-31 | M/S Ziaul Traders | 2018-03-25 | 157.357 | 5% | 2019-03-31 |  |  | 0 | 0%
16 | 247305495-UZR- Ramkrishnapur Sosan Rd. | [13 empty] | 0 | #DIV/0!
17 | 247304129-Line Beelpabla (rayermahol Sluice Gate) Uttar Beelpabla | [13 empty] | 0 | #DIV/0!
18 | 247305330-Kaya Bridge Gutudia Pubopara WDBD Sluice gate (WDBD) | [13 empty] | 0 | #DIV/0!
19 | 247305071-Sahas Mirpara road. | [13 empty] | 0 | #DIV/0!
20 | 247305440-Kunar Ghata (Anis Shop) Kundibari ropad. | [13 empty] | 0 | #DIV/0!
21 | 247305090-Mechaghona-Bahadurpur Rd | [13 empty] | 0 | #DIV/0!
22 | 247305091-Mechaghona Rd | [13 empty] | 0 | #DIV/0!
23 | 247305293-Noakati-Ramakhali Khal road. | [13 empty] | 0 | #DIV/0!
Koyra
24 | 247532006- R&H Graduate High School-Hayatkhali Bazar road. | [13 empty] | 0 | #DIV/0!
25 | 247533009- Moheshawripur UP-Baniakhali Bazar via Noyani road. | [13 empty] | 0 | #DIV/0!
26 | 247534055- R & H Islampur-UZR Narayanpur Launch Ghat Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 7.335 | 0 | 0 | 322.66 |  |  |  | 246.367 | 5% |  | 0 | 0 | 0 | 0%
Construction of Bridge on Upazila Road (7.30m width)
Dacope
1 | 247172011-Const. of RCC Bridge at Chalna GC (Gashtala) -Goraikhali GC via Laxmikhola & Mozamnagarhat Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Rupsha
1 | 247755494-Construction of 40.00 m long PSC Gider Bridge on Taltala Rampaul-Alaipur Sheikhpur FRB(Paulghat) road at ch-1000m. | KDRIDP/Khul/B-01/2017-18 | 0 | 40 | 0 | 288.187 | [8 empty] | 0 | #DIV/0!
Terokhada
2 | 247943001-Const. of RCC Bridge at Azogara UP Office- Kola Bazar via Dreepur Bazar Road | [13 empty] | 0 | #DIV/0!
Dighalia
3 | 247404037-Construction of 20m. Span RCC Bridge on Maheshdia to Katla | [13 empty] | 0 | #DIV/0!
Paikgacha
4 | 247644012-Const. of RCC Bridge on Vedamari-Sonkordana Rd | [13 empty] | 0 | #DIV/0!
5 | 247645008-Const. of RCC Bridge on Katipara Bazar-Charitable Dispensary Road. | [13 empty] | 0 | #DIV/0!
Koyra
6 | 247534070 -Const. of RCC Bridge on Hatiar Danga Culvert to Patnikhali Foot Bridge iva majar chalk mondir | [13 empty] | 0 | #DIV/0!
Dumuria
7 | 247303007-Construction of 30m Long Bridge on Ula Bazar-Sarafpur UP Office (Baniakhali GC) Road. | [13 empty] | 0 | #DIV/0!
8 | 247303008-Construction of 8.00m long Bridge/Culvert on Gutudia UP Office-Kanchannagar bazar via Bhandarpara UP Office Road | [13 empty] | 0 | #DIV/0!
9 | 247303022-Construction of 60m Long Bridge on Sahos UP-Moikhali bazar Rd. | [13 empty] | 0 | #DIV/0!
10 | 247305102-Construction of 72m Long Bridge on Kulati Badurgacha bazar Rd. | [13 empty] | 0 | #DIV/0!
11 | 247305413-Construction of 93m Long Bridge on Tipna-Singa Rd. | [13 empty] | 0 | #DIV/0!
Batiaghata
12 | 247124007-Construction of bridge on Kismot Phultala-Bayardanga Road over Kharia river. | [13 empty] | 0 | #DIV/0!
13 | 247124053-Construction of bridge on Nirala Tablig Mosque-Rupsha Bridge Approach Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
14 | 24124046-Katianagla sluice gate - Baron para via Kayemkhola hula Road khoria river. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 40 | 0 | 288.187 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Maintenance
Rupsha
1 | 247752001-Thana H/Q-Alaipurhat- Sheikhpura GC Road. | [13 empty] | 0 | #DIV/0!
2 | 247753004-Ghatbhog UP- Dhopakhala -Doba Bazar Rd. | [13 empty] | 0 | #DIV/0!
3 | 247755184-Pithabhog school-Sheikpur FRB via Munsur Paik- Jagodis Tagur house Rd. | [13 empty] | 0 | #DIV/0!
4 | 247755290-Narikali Raton dey house-Chara Battala via Bablu Sheikh house Rd. | [13 empty] | 0 | #DIV/0!
Dighalia
5 | 2474052001-Daulatpur -Senhati -Magirgahati Rd. | [13 empty] | 0 | #DIV/0!
6 | 247403002-Shenhati GC -Shenhati UP via Chandanimahal Ferryghat -Charerhat Kheyaghat (Katabon Picnim Corner) Road. | [13 empty] | 0 | #DIV/0!
7 | 247403007-Jabdipur Main Road via UP Office -R&H Road. | [13 empty] | 0 | #DIV/0!
8 | 247403008-Jogipole UP Office -Rangpur UP Rd. | [13 empty] | 0 | #DIV/0!
9 | 247403010-Aronghata UP -Lata Kamarbari UP Office (Digholia Portion) | [13 empty] | 0 | #DIV/0!
10 | 247404024-Old BITroad:Fulbarigate RHD-Labrotary high shool ViaArafat JameMosqueKhanabari High Schol | [13 empty] | 0 | #DIV/0!
11 | 247404038-Dighalia FWC on RHD -Panigati-Pather Bazar GC | [13 empty] | 0 | #DIV/0!
12 | 247404033-Teligati Pakar Matha to Rajapur Ghat road. | [13 empty] | 0 | #DIV/0!
Batiaghata
13 | 247122005-Hatbatihat-Koiyahat via Bagulardanga Rd. | [13 empty] | 0 | #DIV/0!
Koyra
14 | 247533003-Koyra UP-Suti Bazar Rd. | [13 empty] | 0 | #DIV/0!
15 | 247534057-R&H Hatiardanga Culvert-Surikhali Bazar road via Patnikhali Rd. | [13 empty] | 0 | #DIV/0!
Paikgacha
16 | 247642012-Paikgacha GC-Baintala Bazar-Bagularchack Bazar-Surikhali Bazar-Gilabari GC Rd. | [13 empty] | 0 | #DIV/0!
17 | 247644084-Horidashkati Play Ground Horidhali UP Paikgacha GC-Samukpota bazar Rd. | [13 empty] | 0 | #DIV/0!
Dumuria
18 | 247302003-Khornia GC - Rudhaghora UP - Boruna GC Rd. | [13 empty] | 0 | #DIV/0!
19 | 247302008-Mostafar more RHD-Rajbandh-Kaiya GC Rd. | [13 empty] | 0 | #DIV/0!
20 | 247303001-Magurghona UP Office (RHD Road) -Uttor Magurghona Karim Box Bazar Rd via Magurghona Union H/S Road. | [13 empty] | 0 | #DIV/0!
21 | 247303017-Gutudia UP-Salua Bazar Rd. | [13 empty] | 0 | #DIV/0!
22 | 247304116-Faloymari Baster mill-Bakultala-Pashkhali Sluice gate Rd. | [13 empty] | 0 | #DIV/0!
23 | 247304013-Zalardanga RHD-Bhadurpara UP road. | [13 empty] | 0 | #DIV/0!
Phultala
24 | 247693001-Atra Gilatala UP-Palpara Bazar | [13 empty] | 0 | #DIV/0!
25 | 247694079-Shiromoni Tank Road. | [13 empty] | 0 | #DIV/0!
26 | 247694080-Shiromoni Bazar -Dakatia Bill via Emambari Rd. | [13 empty] | 0 | #DIV/0!
27 | 247694055-Easterngate GC-Moshiali Firing Spot | [13 empty] | 0 | #DIV/0!
28 | 247694081-Shiromoni Bazar-Shiromoni Dakhin Para | [13 empty] | 0 | #DIV/0!
29 | 247694023 - Periodic Maintenance of Jugnipasha School Road Via Jugnipasha Mosque Road (Ch: 00m - 985m) | KDRIDP/Khul/M-01/2017-18 | 0.985 | 0 | 0 | 24.118 | 2018-02-26 | M/S Ruma Traders | 2018-04-26 | 24.118 | 0% | 2019-02-21 |  |  | 0 | 0%
30 | 247694096-Phultala Health Complex-Phultala Railstation | [13 empty] | 0 | #DIV/0!
31 | 247695146-Mosiali Sarif House - Fakirpara Amjed Hossen GPS | [13 empty] | 0 | #DIV/0!
Total |  |  | 0.985 | 0 | 0 | 24.118 |  |  |  | 24.118 | 0% |  | 0 | 0 | 0 | 0%
GC-Hat
Rupsha
1 | Construction of Alaipur Bazar | KDRIDP/Khul/GC-01/2017-18 | 0 | 0 | 1 | 22.35 | 2018-01-30 | M/A Amirun Enterprise | 2018-03-25 | 20.11 | 0% | 2018-12-31 |  |  | 0 | 0%
Dacope
2 | Kalinagar GC | [13 empty] | 0 | #DIV/0!
Dumuria
3 | Construction of Khornia Growth Center | KDRIDP/Khul/GC-02/2017-18 | 0 | 0 | 1 | 20.8 | 2018-01-30 | M/S Amin & Co. | 2018-03-11 | 18.72 | 0% | 2018-12-17 |  |  | 0 | 0%
4 | Construction of Kathalia Bazar Growth Center | KDRIDP/Khul/GC-03/2017-18 | 0 | 0 | 1 | 21.02 | 2018-01-30 | M/S Amin & Co. | 2018-03-11 | 18.92 | 40% | 2018-12-17 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 3 | 64.17 |  |  |  | 57.75 | 13.33% |  | 0 | 0 | 0 | 0%
Landing/ Riverghat
Rupsha
1 | Construction of Rupsa Riverghat (Ferryghat). | KDRIDP/Khul/G-14/2017-18 | 0 | 0 | 1 | 30.2 | [8 empty] | 0 | #DIV/0! | Re Tender
Dacope
2 | Pankhalighat | [13 empty] | 0 | #DIV/0!
Paikgacha
3 | Soladana BazarGhat | [13 empty] | 0 | #DIV/0!
Dumuria
4 | Construction of Kanchanagar Kheya Ghat | KDRIDP/Khul/G-06/2017-18 | 0 | 0 | 1 | 35.56 | [8 empty] | 0 | #DIV/0!
5 | Construction of Jabra Bazar Kheya Ghat | KDRIDP/Khul/G-07/2017-18 | 0 | 0 | 1 | 27.86 |  |  |  |  | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 3 | 93.62 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Tree Plantation
Rupsha
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Terokhada
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Dighalia
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Batiaghata
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Dacope
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Koyra
6 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Paikgacha
7 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Dumuria
8 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Phultala
9 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 128.945 | 40 | 6 | 9442.664 |  |  |  | 5591.309 | 11.97% |  | 97.735 | 1299.995 | -1202.26 | 23.25%
|  |  | 128.945 | 40 | 6 | 9442.664 |  |  |  | 5591.309 | 6.789% |  | 97.735 | 1299.995 | -1202.26 | 23.25%

## Dacope
Dacope
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 247172001-Khona R&H-Garikhali GC (Paikgacha) via Batbunia G.C Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 247172002 - Improvement of Dacope (Chunkuri Kheya Ghat) - Nalian GC via Kalinagar GC Road (Ch: 12891m - 15891m) | KDRIDP/Khul/W-61/2017-18 | 3 | 0 | 0 | 276.695 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | Re Tender
3 | 247172002- Improvement of Dacope (chundri kheya ghat)- Nalian GC via Kalinagor GC road (Ch: 15891m-18891m) | KDRIDP/Khul/W-66/2017-18 | 3 | 0 | 0 | 289.398 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0
4 | 247172002 - Improvement of Dacope (Chunkuri Kheya Ghat) - Nalian GC via Kalinagar GC Road (Ch: 18891m - 21891m) | KDRIDP/Khul/W-54/2017-18 | 3 | 0 | 0 | 258.22 | 2018-02-26 | M/s Ziaul Trader | 2018-04-19 | 283.748 | 0% | 2019-04-25 | 0 | 0 | 0 | 0% | 0
5 | 247172003-Chalna (Poddergong)-Khutakhali GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 247172004 - Improvement of Kalinagar GC - Khutakhali (Bajua) GC Road (Ch: 7500m -10133m) | KDRIDP/Khul/W-55/2017-18 | 2.633 | 0 | 0 | 224.09 | 2018-02-26 | M/s Ziaul Trader | 2018-04-19 | 246.266 | 0% | 2019-04-25 | 0 | 0 | 0 | 0% | 0
7 | 247172004- Improvement of Kalinagar GC- Khutakhali (Bajua) GC road (Ch: 2517m-5000m) | KDRIDP/Khul/W-65/2017-18 | 2.483 | 0 | 0 | 259.708 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 247172004- Improvement of Kalinagar GC- Khutakhali (Bajua) GC road (Ch: 316m- 2517m) | KDRIDP/Khul/W-64/2017-18 | 2.201 | 0 | 0 | 229.457 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
9 | 247173002 (a) Banisanta UP Office - Banisanta Bazar Road (Ch: 900m - 1725m & 4293m - 5666m) by BC & (b) Construction of 04 Nos (0.625m x 0.900m) U-Type Drain Culvert at Ch: 960m, 5420m, 5563m & 5758m on the same road. | KDRIDP/Khul/W-04/2016-17 | 2.198 | 0 | 0 | 139.99 | 2017-05-22 | M/s Ziaul Traders | 2017-07-03 | 139.78 | 30% | 2018-08-31 | 0 | 38.3 | -38.3 | 27.4% | Salvage Tk. 11,28,632.00
10 | 247173006-Dacope UP office-Bajua UP office Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 247173007-Kailashgong UP - Loudobe UP (Near Horintana bridge) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 247173009 - Improvement of Pankhali UP Office (Khatail Bridge) - Moukhali Bazar Via Kabiraj bari Road (Ch: 1402 - 4175m) | KDRIDP/Khul/W-56/2017-18 | 2.773 | 0 | 0 | 222.24 | 2018-06-20 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
13 | 247174006 - Improvement of Yasin School near Hoglabunia Khalergora road (Ch: 1500 - 1806m) [Dacope] | KDRIDP/Khul/W-27/2017-18 | 0.306 | 0 | 0 | 24.49 | 2017-09-21 | S.M Salah uddin | 2017-11-13 | 23.61 | 30% | 2018-11-19 | 0 | 0 | 0 | 0% | Salvage Tk. 1,42,024.00
14 | 247174007 - Lodobe Bazar to Buridabur via Kalikabati Prymari School Road Ch - (2500m- 5000m) | KDRIDP/Khul/W-57/2017-18 | 2.5 | 0 | 0 | 189.465 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247174010-Batbunia GC to Laxmikhala Bazar Via Kachari Bari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247174028-Khajuria WDB Gora N/H/O Krisnopada to Dhangmari Biswanat P/School via Binapani GPS Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247174032-Laxmikhola Khatail Bridge to Laxmikhola CARE Pucca Road via Moukhali N/H/O Seromone Mondal Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 247175035-Kailashgong Bhutiamari Bazer to Kailashgong Denash Mondal house via Bangabandhu H/School & Dolkhola Hospital Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 247174011-Batbunia GC to Mozamnagor School (Bazar) Road Via Binakpani P/School Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 247174020-(a) Improvement of Shatghoria H/O Oma Sarkar –Shaharabad H/O Kalam Halder via H/O Momen Sheikh road (Ch: 00 - 2850m) by BC [247174020] (b) Construction of 01 No. 2.00m x 2.00m RCC Box Culvert at Ch: 1023m on the same road. (b) Construction of 07 No. 0.625 x 0.900m U-drain Culvert at Ch: 870m, 1260m, 1460m, 1770m, 1890m, 2240m & 2350m on the same road. | KDRIDP/Khul/W-16/2016-17 | 2.85 | 0 | 0 | 201.27 | 2017-11-09 | AT&NE JV | 2017-11-13 | 201.09 | 25% | 2018-11-19 | 0 | 0 | 0 | 0% | Salvage Tk. 4,87,108.00
Improvement of Village Road by HBB
21 | 247174002-Rajnagar Channir chalk P/School-JoynagorBazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
22 | 247172011-Const. of RCC Bridge at Chalna GC (Gashtala) -Goraikhali GC via Laxmikhola & Mozamnagarhat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
23 | Kalinagar GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Landing/ Riverghat
24 | Pankhalighat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
25 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 26.944 | 0 | 0 | 2315.023 |  |  |  | 894.494 | 3.4% |  | 0 | 38.3 | -38.3 | 4.282%

## Batiaghata
Batiaghata
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 247122003-Baroaria hat-Banikhali GC via Sundarmahal Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 247122004-Hatbatihat-Koiyahat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 247122005-Hatbatihat-Koiyahat via Bagulardanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 247122007-Katianangla-Roypur via Sukdara Bazar , Baro Bhuiyan & Kechrabad Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 247122009-Sachibunia-Nijkhamar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
6 | 247123003-Batiaghata UP at Hetalbunia - Mailmara Hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 247123005-Balaidanga UP-Koria hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 247123007- Improvement of jalma UP OFFice- Tetultola Hat Road. (CH: 1200-2500m) | KDRIDP/Khul/W-41/2017-18 | 1.3 | 0 | 0 | 80.01 | 2018-02-13 | Sk.Idris ALI | 2018-03-25 | 87.79 | 20% | 2018-11-20 | 0 | 30.09 | -30.09 | 34.27% | 0
9 | 247123008-Amripur UP-Phultala hat rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247123010- Improvement of Gangarampur CH-(00-3950m) | KDRIDP/Khul/W-43/2017-18 | 3.95 | 0 | 0 | 268 | 2018-06-20 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 247123011-Improvement of Bhanderkote UP Office - Purbo Halia Hat Road. (CH: 562-3000m) | KDRIDP/Khul/W-40/2017-18 | 2.438 | 0 | 0 | 145.84 | 2018-02-13 | Sk.Idris ALI | 2018-03-19 | 160.315 | 0% | 2019-02-10 | 0 | 0 | 0 | 0% | 0
12 | 247123001-Jalma UP Office - Krishna Nagor Poultry Firm. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 247123014-Sukdara bazar – Surkhali UP office via gaoghara khoral | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
14 | 247124008-Joypur hat-Shadaler hat via Amripur Pry.School Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247124014-Manobshebaloy-Choyghoria box culvert Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247124019-Dhadua Pry.School-Joypur Hela Battala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247124034-Shimana - Badamtala Hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 247124036- Improvement of Bagmara Harintana CH- (940m- 2150m) | KDRIDP/Khul/W-42/2017-18 | 1.21 | 0 | 0 | 82.61 | 2018-01-31 | M/S F. K construction | 2018-03-25 | 86.74 | 15% | 2019-03-31 | 0 | 0 | 0 | 0% | 0
19 | 247124041-Choyghoria R&H-Rupsha bridge Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 247124042-Chourangi hat- Sholmari Ghat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 247124046 - Improvement of Katianangla Sluicegate - Baronpara via Kayemkhola Hula Road (Ch: 5650 - 6315m) | KDRIDP/Khul/W-26/2017-18 | 0.665 | 0 | 0 | 39.43 | 2017-09-21 | M/S Sufia Enterprise | 2017-11-13 | 35.49 | 30% | 2018-08-19 | 0 | 9 | -9 | 25.36% | Salvage Tk. 3,35,504.00
22 | 247124053 - Improvement of Nirala Tablig Mosque - Rupsha Bridge Approach Road via Nirala & Shabujbag Residential area Road (Ch: 00 - 880m) [Batiaghata] | KDRIDP/Khul/W-31/2017-18 | 0.88 | 0 | 0 | 98.09 | 2017-09-25 | M/S Sufia Enterprise | 2017-11-13 | 89.93 | 0% | 2018-11-19 | 0 | 0 | 0 | 0% | Salvage Tk. 3.77.663.00
23 | 247124061-Nirala Kobor KhanaTo Rupsha Bipas Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 247125056-Parbatiaghata - Shailamari Khayaghat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 247125058- Hatbati mot - Saaliamari Khayghat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 247125158-Bunarabad BWDP-near H/Q Sharil- Banarabad H/Q. Afjal M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 247125159-Hoglabuni WAPDA-Bunaradad Durga Mondir | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 247125160-Gariardanga Collage- Gariardanga Moth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 247124016-Noailtala Hat - Shialidanga Hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 247124052- (a) Improvement of Harintana Jabber Sarak road (Ch: 00 - 442m) by BC [247124052] (b) Construction of 01 No. 0.600m x 0.600m U-drain Culvert at Ch: 103m on the same road. | KDRIDP/Khul/W-17/2016-17 | 0.442 | 0 | 0 | 20.97 | 2017-11-10 | M/s Ziaul Traders | 2018-01-11 | 21.98 | 20% | 2018-08-06 | 0 | 0 | 0 | 0% | Salvage Tk. 1,79,262.00
Construction of Bridge on Union Road/Village Road (5.50m width)
31 | 247124007-Construction of bridge on Kismot Phultala-Bayardanga Road over Kharia river. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 247124053-Construction of bridge on Nirala Tablig Mosque-Rupsha Bridge Approach Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 24124046-Katianagla sluice gate - Baron para via Kayemkhola hula Road khoria river. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
34 | 247122005-Hatbatihat-Koiyahat via Bagulardanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
35 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 10.885 | 0 | 0 | 734.95 |  |  |  | 482.245 | 2.429% |  | 0 | 39.09 | -39.09 | 8.106%

## Rupsha
Rupsha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 4 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 247753004-Ghatbhog UP-Dhopakhola-Doba Bazer Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 247753008-Naihati UP Office (R&H)-Lockpur GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
3 | 247754024 - Rupsha Bagerhat Noman School - Tilokhat via Khider Box House - Janata Market Road (Ch: 2216m - 5986m) by BC & (b) Construction of 02 Nos (1.00m x 1.00m) U-Type Drain Culvert at Ch: 2105m & 2959m on the same road. | KDRIDP/Khul/W-03/2016-17 | 3.77 | 0 | 0 | 192.88 | 2017-05-22 | Md. Noor Hossain | 2017-07-03 | 187.25 | 60% | 2018-07-09 | 0 | 117.36 | -117.36 | 62.68% | Salvage Tk. 60,06,901.00
4 | 247754025-Jabusa-Bhangonpar-Jabusa h/s-Khayghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 247755009-Gilatala-S.Bahirdia Thana boundary Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 247755019-Shealihat-Nornia WAPDA Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 247755111 - Improvement of Alipur collage-shahabuddin sikder house - Bhabanipur School road (ch: 00-1750m) | KDRIDP/Khul/W-09/2016-17 | 1.75 | 0 | 0 | 102.87 | 2017-11-09 | M/S Mizan Enterprise | 2017-09-10 | 97.32 | 70% | 2018-09-30 | 0 | 59.74 | -59.74 | 61.39% | Salvage Tk. 10,87,735.00
8 | 247755206 - Improvement of Deara Paulpara - Agrodut Field via Chairman House Road (Ch: 240 -1043m) [Rupsa] [Salvage Cost of this package is Tk 683664.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-32/2017-18 | 0.803 | 0 | 0 | 51.3 | 2018-02-13 | M/S Totul & Co | 2018-03-15 | 51.297 | 30% | 2019-02-05 | 0 | 22.347 | -22.347 | 43.56% | 0
9 | 247755290 - Improvement of Narikali Raton dey house - Chara Battala Via Bablu sheik house road (Ch. 500-1000m) | KDRIDP/Khul/W-08/2016-17 | 0.5 | 0 | 0 | 23.88 | 2017-11-09 | M/s Ziaul Traders | 2018-01-11 | 25.03 | 10% | 2018-08-06 | 0 | 0 | 0 | 0% | Salvage Tk. 1,53,369.00
10 | 247755387-Alaipur -Sheikhpura FRB- Narikeli Rabindranath house-Kachatala Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 247755450-TSB UP Goalbathan R&H Road-Noor Mohammad Fakir house to driver Wadud Kazi house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 247755396 - Improvement of Uttar Khajadanga Main Road - Arafat House via Mosjid to Rafiqul Shop Road (Ch: 00 - 900m) [Rupsa] [Salvage Cost of this package is Tk 709542.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-33/2017-18 | 0.9 | 0 | 0 | 58.38 | 2017-12-28 | M/S Totul & Co | 2018-03-15 | 61.29 | 0% | 2019-02-05 | 0 | 0 | 0 | 0% | 0
13 | 247755440-(a) Improvement of Elaipur Khorshed Ali house-Shobedali house road via Motair Chairman house Road (Ch: 00-725m) by BC (b) Construction of 02 Nos 0.600m x 0.600m U-Type Drain culvert at Ch: 165m & 265m on the same road. | KDRIDP/Khul/W-14/2016-17 | 0.725 | 0 | 0 | 51.26 | 2017-11-09 | M/s Ziaul Traders | 2018-01-11 | 53.72 | 30% | 2018-10-19 | 0 | 32.173 | -32.173 | 59.89% | Salvage Tk. 4,04,987.00
14 | 247755441-(a) Improvement of Elaipur Primary School-Rupsha Mongla (R&H) road via Motair Chairman house Road (Ch: 00-555m) by BC (b) Construction of 05 Nos 0.600m x 0.600m U-Type Drain culvert at Ch: 210m, 340m, 370m, 451m & 540m on the same road. | KDRIDP/Khul/W-15/2016-17 | 0.55 | 0 | 0 | 38.406 | 2017-11-09 | M/s Ziaul Traders | 2018-01-11 | 40.25 | 30% | 2018-06-08 | 0 | 13.53 | -13.53 | 33.61% | Salvage Tk. 4,27,750.00
15 | 247755060 - Improvement of Kazdia Bazar - Kazdia Eid Gah - Bari Sk's House Road (Ch: 00 -1290m) [Rupsa] [Salvage Cost of this package is Tk 1777999.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-36/2017-18 | 1.29 | 0 | 0 | 91.3 | 2017-10-24 | M.A Jalil Khan | 2017-12-10 | 95.41 | 30% | 2018-10-20 | 0 | 25 | -25 | 26.2% | Salvage Tk. 17,77,999.00
16 | 247755162 -Improvement of Rupali Sea Food - Gupiar Khal via Shahjahan Graders House to Al - Aksa Koborkhana Road (Ch: 00 - 520m) [Rupsa] [Salvage Cost of this package is Tk 158397.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-35/2017-18 | 0.52 | 0 | 0 | 32.57 | 2017-12-28 | M/S Totul & Co | 2018-03-25 | 34.85 | 0% | 2018-12-31 | 0 | 0 | 0 | 0% | 0
17 | 247755047 - Mahabub House - Siddique Sheikh House (Ch: 00-480m) road. | KDRIDP/Khul/W-13/2016-17 | 0.48 | 0 | 0 | 30.95 | 2017-10-24 | M/s. Milon Treders | 2017-12-10 | 30.7 | 30% | 2018-09-16 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by HBB
18 | 247755118 - Improvement of Alaipur - Anandanagar FRB Putimari - Peara Village Jami Mosque - Chandunsree H/O Khalid Howlader Road by HBB (Ch: 00 - 2500m) [Rupsa] [Salvage Cost of this package is Tk 623967.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-34/2017-18 | 2.5 | 0 | 0 | 98.9 | 2017-10-24 | M/s Amin & Co. | 2017-12-05 | 89.01 | 5% | 2018-12-11 | 0 | 0 | 0 | 0% | Salvage Tk. 6,23,967.00
Construction of Bridge on Union Road/Village Road (5.50m width)
19 | 247755494-Construction of 40.00 m long PSC Gider Bridge on Taltala Rampaul-Alaipur Sheikhpur FRB(Paulghat) road at ch-1000m. | KDRIDP/Khul/B-01/2017-18 | 0 | 40 | 0 | 288.187 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
20 | 247752001-Thana H/Q-Alaipurhat- Sheikhpura GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 247753004-Ghatbhog UP- Dhopakhala -Doba Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 247755184-Pithabhog school-Sheikpur FRB via Munsur Paik- Jagodis Tagur house Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 247755290-Narikali Raton dey house-Chara Battala via Bablu Sheikh house Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
24 | Construction of Alaipur Bazar | KDRIDP/Khul/GC-01/2017-18 | 0 | 0 | 1 | 22.35 | 2018-01-30 | M/A Amirun Enterprise | 2018-03-25 | 20.11 | 0% | 2018-12-31 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
25 | Construction of Rupsa Riverghat (Ferryghat). | KDRIDP/Khul/G-14/2017-18 | 0 | 0 | 1 | 30.2 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Re Tender
Tree Plantation
26 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 13.788 | 40 | 2 | 1113.433 |  |  |  | 786.237 | 11.35% |  | 0 | 270.15 | -270.15 | 34.36%

## Terokhada
Terokhada
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 247942001- Sachiadah RHD Road - Nagarkandi GC via Patla GC Road (Ch: 6370m - 10084m) by BC | KDRIDP/Khul/W-01/2016-17 | 3.71 | 0 | 0 | 245.93 | 2017-05-22 | M/s Ziaul Traders | 2017-07-03 | 240.91 | 60% | 2018-08-31 | 0 | 119.32 | -119.32 | 49.53% | Salvage Tk. 26,86,784.00
2 | 247942006- Improvement of Ajogara R&H-Sheakpura GC Road (Ch:1881-2508m) | KDRIDP/Khul/W-70/2017-18 | 0.63 | 0 | 0 | 43.017 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 15,515.00
3 | 247942010-Nalamara R&H - Katenga GC via Abnali Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 247943001-Ajogara UP office-Kola Bazar via Sreepur bazar Road.(Start From Agaroamtala R&H) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 247943004-Improvement of Barasat UP Office to Bilduria hat via Arpangasia Road (Ch:2910-4457m) | KDRIDP/Khul/W-71/2017-18 | 1.55 | 0 | 0 | 100.016 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 63,818.00
Improvement of Village Road by BC
6 | 247944005 - Gazipur - Harikhali via Nebudia Road (Ch: 00 - 1268m) by BC | KDRIDP/Khul/W-02/2016-17 | 1.268 | 0 | 0 | 69.12 | 2017-05-22 | M/s Ziaul Traders | 2017-07-03 | 67.73 | 40% | 2018-08-31 | 0 | 16 | -16 | 23.62% | Salvage Tk. 5,95,379.00
7 | 247944008-Mokampur village Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 247944012-Atlia Bazar Parokhali Adampur FRB Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 247944017-Patla Karoria-Induhati FRB Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247944021-Improvement of Terokhada R&H- Nebudia road (Ch:500-1475m& 1970-2665m) | KDRIDP/Khul/W-72/2017-18 | 1.67 | 0 | 0 | 121.946 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 5,41,506.00
11 | 247944022-Harikhali(Manrartali) R&H-Gazipur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 247944025-NebudiaR&H Bridge to Nalamara R&H Bridge road Via Kagdi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 247944028-Isamti WDB Iate - Isamoti kuti shop rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 247945064-South Modhupur Khalpar road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247945105-Sachiadh Dhali house-Diliproy house road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247945153-Naliarchar Modhyapara - Oliar Mollah more Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
17 | 247944023- Improvement of Bhujinia(start from Ajogara R&H) to Promodnagar road by HBB (Ch:2630-4630m) | KDRIDP/Khul/W-70/2017-18 | 2 | 0 | 0 | 73.8 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 247944007-Development Of WAPDA Embankment –Kaibarta Shisa Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 247944009-Development of South Bnk of Laskerpur Khal Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 247944023-Development of Bhujnia (start from Ajogara R&H ) to promodangar via kalinagar road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 247944024-Development of chaglada Bazar –Kusla Primary School road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 247945009-Development of Bipara Ajogara CARE road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 247945014-Development of Rostom Ajogara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 247945018-Development of Biri Ajogara-North para road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 247945024-Develpment of Kharbireya road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 247945027-Development of Anandanagar-Goara Ferry Ghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 247945029-Development of Anadanagar Madrasha road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
28 | 247943001-Const. of RCC Bridge at Azogara UP Office- Kola Bazar via Dreepur Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | #DIV/0! | 0
Total |  |  | 10.828 | 0 | 0 | 653.829 |  |  |  | 308.64 | 3.448% |  | 0 | 135.32 | -135.32 | 43.84%

## Dighalia
Dighalia
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 247402001 - Improvement of Daulatpur-Senhati - Magirghati road (Ch: 5955 - 8717m). | KDRIDP/Khul/W-07/2016-17 | 2.76 | 0 | 0 | 102.72 | 2017-07-27 | Mir Construction | 2017-09-10 | 96.29 | 50% | 2018-07-30 | 0 | 41.75 | -41.75 | 43.36% | Salvage Tk. 4,81,962.00
Improvement of Union Road by BC
2 | 247403002-Shenhati GC-Shenhati UP road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 247403005-Digholia UP-Deara-Formizekhana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 247403008-Jogipola UP-Rangpur UP road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 247403013 - Improvement of Barakpur UP Complex-Haripada Mat-Ghoshgati Bazer Road by BC. CH -(2240m- 3340m) | KDRIDP/Khul/W-73/2017-18 | 1.1 | 0 | 0 | 76.8 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 7,34,171.00
Improvement of Village Road by BC
6 | 247404033 - Improvement of Teligati Pakar Matha to Rajapur Ghat road (Ch: 00 - 1630m). | KDRIDP/Khul/W-06/2016-17 | 1.63 | 0 | 0 | 54.91 | 2017-07-27 | S.M Salah uddin | 2017-09-10 | 50.62 | 100% | 2018-09-30 | 50.56 | 50.56 | 0 | 99.88% | Final (Salvage Tk. 2,00,716.00)
7 | 247404035- Improvement of Brahmmagati Sutirkul to Lakhohati Bazar road Ch (500m-1365m) | KDRIDP/Khul/W-44/2017-18 | 0.865 | 0 | 0 | 56.94 | 2018-01-31 | M/S Zaman Enterprise | 2018-03-22 | 62.468 | 0% | 2019-03-28 | 0 | 0 | 0 | 0% | 0
8 | 247404037- Improvement of Maheshdia to Katla Via Ambaria Road CH-( 00-2690) | KDRIDP/Khul/W-46/2017-18 | 2.69 | 0 | 0 | 180.54 | 2018-02-01 | M/S Rafique Enterprise | 2018-03-11 | 188.21 | 0% | 2019-03-17 | 0 | 0 | 0 | 0% | 0
9 | 247404072-Chandanimahal Vottacharja Bazar - Katabon Picnic Corner Via KITCMill,MoslemBayati AdGolam Ali Sk. Sk Para Jame Mosque, HumaunMember, Vuipara & Puja Mondir Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247404062-Senhati Katanipara Hoglar More - Bativita Ashraf House H/O Koykobad Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 247404107 - Improvement of jangushia Fakirpara Chara Battalar More Par Mochomdapur Hari Mondir via Bagmara shop/Khokon road CH -( 240m- 1055m) | KDRIDP/Khul/W-45/2017-18 | 0.815 | 0 | 0 | 59.376 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
12 | 247404037-Construction of 20m. Span RCC Bridge on Maheshdia to Katla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
13 | 2474052001-Daulatpur -Senhati -Magirgahati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 247403002-Shenhati GC -Shenhati UP via Chandanimahal Ferryghat -Charerhat Kheyaghat (Katabon Picnim Corner) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247403007-Jabdipur Main Road via UP Office -R&H Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247403008-Jogipole UP Office -Rangpur UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247403010-Aronghata UP -Lata Kamarbari UP Office (Digholia Portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 247404024-Old BITroad:Fulbarigate RHD-Labrotary high shool ViaArafat JameMosqueKhanabari High Schol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 247404038-Dighalia FWC on RHD -Panigati-Pather Bazar GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 247404033-Teligati Pakar Matha to Rajapur Ghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
21 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 9.86 | 0 | 0 | 531.286 |  |  |  | 397.588 | 7.143% |  | 50.56 | 92.31 | -41.75 | 23.22%

## Dumuria
Dumuria
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 247303002 - (a) Kanchannagar Bazar - Magurkhali UP - Magurkhali Bazar Road (Ch: 1557 - 5350m) by BC & (b) Construction of 02 Nos (0.625m x 0.600m) U-Type Drain Culvert at Ch: 2475m & 3082m on the same road. | KDRIDP/Khul/W-05/2016-17 | 3.79 | 0 | 0 | 206.97 | 2017-05-22 | Md. Noor Hossain | 2017-07-03 | 200.48 | 60% | 2018-07-09 | 0 | 116.848 | -116.848 | 58.28% | Salvage Tk. 2,19,703.00
2 | 247303006-Salua bazar-Raghunathpur Bazar via Rangpur UP Office Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 247303008-Gutudia UP Office-Kanchannagar bazar via Bhandarpara UP Office Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 247303009-(a) Improvement of Dunuria (Chingra) -Sovna UP –Sovna Westpara bazar (Teligati Ghat) Road (Ch: 00- 317m & 1625-5225m) (b) Rehabe. of 01 No. RCC Box Culvert at Ch: 2874m & Construction of 12 Nos Different sizes U-Type Drain culvert at Ch: 4590m, 4828m, 5160m, 1682m, 2611m, 3072m, 4270m, 2325m, 3598m, 3770m, 3940m & 4180m on the same road. | KDRIDP/Khul/W-20/2016-17 | 3.917 | 0 | 0 | 264.16 | 2017-11-09 | FT& BB JV | 2017-10-30 | 256.02 | 30% | 2018-11-05 | 0 | 50.916 | -50.916 | 19.89% | Salvage Tk. 43,14,618.00
5 | 247303010-Shovna UP-Zialtala Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 247303011-Kathalia bazar-Magurikhali UP via Pashchim Patibunia road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 247303015-Kharnia UP-Sovna westpara bazar road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 247303017- Improvement of Gutudia UP –Salua Bazar Road (Ch: 00 - 3900m) | KDRIDP/Khul/W-18/2016-17 | 3.9 | 0 | 0 | 282.33 | 2017-11-09 | M/s Ziaul Traders | 2017-10-31 | 295.74 | 60% | 2018-11-06 | 0 | 168.809 | -168.809 | 57.08% | Salvage Tk. 80,60,627.00
9 | 247303016-Chuknagar Eidgah(R&H)-Atlia UP-Chuknagar GC-Narnia(R&H) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247303020-Improvement of Mathertala Bazar-Magurkhali UP Office via Hatitana More Road (Ch: 700 - 4000m) | KDRIDP/Khul/W-19/2016-17 | 3.3 | 0 | 0 | 240.06 | 2017-11-09 | M/S Rupa Enterprise | 2017-10-31 | 230.96 | 45% | 2018-11-05 | 0 | 84.116 | -84.116 | 36.42% | Salvage Tk. 23,98,533.00
11 | 247303022-Sahos UP-Moikhali bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 247303023-Basundiadanga Bazar - Magurkhali UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 247303024-Shahos UP Office (Kumarghata Amtala more)- Kadamtala Koyaghat Bazar via KDC Pry. School Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 247303002-Kanchannagar Bazar-Magurkhali UP - Magurkhali Bazzar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Duplicate as SL. No. 32
Improvement of Village Road by BC
15 | 247304002-Khornia-Pachpota Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247304009- Moikhali UZR (Fotik Shop)-Banda Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247304013- Zelerdanga RHD-Vhanderpur UP Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 247304021 Improvement of Ula Hazibunia road- Kanchan nagar Bazar Road CH - ( 2307m - 2530m) | KDRIDP/Khul/W-52/2017-18 | 0.223 | 0 | 0 | 15.73 | 2018-02-01 | Bishowajit Kundu | 2018-03-25 | 16.86 | 100% | 2018-12-31 | 16.858 | 16.858 | 0 | 99.99% | Final
19 | 247304023 Improvement Alapur R&H Baduria Bazar Road (Ch: 1375m-2685m) and (3673m-3923m) | KDRIDP/Khul/W-62/2017-18 | 1.56 | 0 | 0 | 216.96 | 2018-03-29 | M/S Amin & Co. | 2018-05-28 | 216.198 | 0% | 2019-04-02 | 0 | 0 | 0 | 0% | 0
20 | 247304028-Vhandarpara UP (Vanda bazar)-Dhanibunia bazar UZR Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 247305488- Improvement of Rangpur Goramipara via Mallik house Road Ch-( 0.00- 1555m) | KDRIDP/Khul/W-53/2017-18 | 1.555 | 0 | 0 | 125.865 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 13,01,215.0
22 | 247304027-Chuknagar petrol pump-Baduria bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 247304032-Zelerdanga R&H-Kuloty-Bakultala Bazar -Falymary Bastar Mill Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 247304033-Daulatpur-Shahpur UZR-Thukri bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 247304056-Ranai R&H palbari WAPDA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 247304085 - Improvement of Shibpur - Zialtala Bazar via Gosai Bari Road (Ch: 800m - 1432m) | KDRIDP/Khul/W-63/2017-18 | 0.632 | 0 | 0 | 49.487 | 2018-02-26 | Bishowajit Kundu | 2018-04-19 | 48.88 | 30% | 2019-01-25 | 0 | 11.019 | -11.019 | 22.54% | 0
27 | 247305126 - Improvement of Mirzapur- Kharia road (Ch. 0.00m- 1390m). | KDRIDP/Khul/W-69/2017-18 | 1.39 | 0 | 0 | 104.999 | 0 | Bishowajit Kundu | 2018-06-07 | 109.09 | 0% | 2019-06-13 | 0 | 0 | 0 | 0% | Salvage Tk. 6,45,305.00
28 | 247305078 - Improvement of Salua Maloapara road CH - (00- 467m) | KDRIDP/Khul/W-49/2017-18 | 0.467 | 0 | 0 | 44.86 | 2018-01-31 | Bishowajit Kundu | 2018-03-25 | 44.277 | 70% | 2018-12-31 | 0 | 26.9 | -26.9 | 60.75% | Salvage Tk. 3,29,948.00
29 | 247305149 - Improvement of Chingra- Gabtola Road CH - ( 00m-2230m) | KDRIDP/Khul/W-50/2017-18 | 2.23 | 0 | 0 | 146.02 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 247304061-Khukia south para-Uttarpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 247305197-Udayan School- Baladuni Primary School road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 247304051-Checuri Police Camp-Bakultalr more | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 247304045-Adarsha gram R&H Golna Razzak Dr. house Bhadurpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 247305125-Golna South para rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 247305207-Ranai Village Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 247305266-Tipna Viaalage road (Tipna Sk.-Community Clinic | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 247305013-Sahahapur-Fokir bari road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 247305017-Anduli Sahapara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 247305191-Anduli grmeen tower-beel Dakatia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 247305195-Komrai Madrasha-Komiail Primary School | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 247305234-Anduli R&H Palut house to Shahajan Shaik house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 247305238 Improvement of Ragunatpur Rishebari Road CH - (00m- 575m) | KDRIDP/Khul/W-51/2017-18 | 0.575 | 0 | 0 | 42.778 | 2018-02-01 | Bishowajit Kundu | 2018-03-25 | 42.14 | 40% | 2018-12-31 | 0 | 14.4 | -14.4 | 34.17% | 0
43 | 247305243-Thukra Bazar to Rupa Rampur Village road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 247305158-Rudaghora Bazar-Gholder para | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 247305215-Rudaghora Soial RD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 247305252-Dumuria Miksimil (R&H) Hassanpur-Joardar para | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 247305376-Hasanpur Joarder bari Mosque-Abdulla Jordar bari road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 247304061-Khukia Southpara -Uttarpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 247305075-Gajendrapur-bazar UNR Gajendrapur Uttarpara (Jorakhal wazad sheik house) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
50 | 247305220-Gajendrapur Village road (Nowsher Master house Telepukur-Vadra Bari | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
51 | 247305279-Gozendrapur khabari-Hajibunia road (Madrasha via saheb ali sheik house – Musa Shop) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
52 | 247305280-Gozendrapur Dakhin para road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
53 | 247304079-Catcatia –Akra WAPDA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
54 | 247305203-Kalikapur Goldarpara -jhaltola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
55 | 247304037-Baliakhali Bazar-Hamkura Bazar-Thukra Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
56 | 247305147-Shahos Kazirulla -Patibunia Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
57 | 247305165-Purba Bilpabla Rayermohal- Pasim Bilpubla Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
58 | 247305404-Hazibunia Dakhin para- Kanchannagor Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
59 | 247305037- Bayar sing - Adharmani via AKBK School Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
60 | 247305136-Mathertala Bazar - Chittramari Purbapara via Gajalia Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
61 | 247305262-Dumuria Miximil R&H -Dumuria College ( Khulna - Satkhira R&H) Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
62 | 247305048-Chucknagor Bazar - Chakundia Sardar Bari Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
63 | 247304038-Mathertala Bazar - Badurgacha Mahasasan Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
64 | 247305104 - Improvement of Line Bilpabla (Rayer Mohol Sluice gate) - Uttar Bilpabla - Shikderpara - Junction mor Road (Ch: 715m- 3550m) By HBB | KDRIDP/Khul/W-48/2017-18 | 2.835 | 0 | 0 | 149.96 | 2018-01-31 | M/S Ziaul Traders | 2018-03-25 | 157.357 | 5% | 2019-03-31 | 0 | 0 | 0 | 0% | 0
65 | 247305495-UZR- Ramkrishnapur Sosan Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
66 | 247304129-Line Beelpabla (rayermahol Sluice Gate) Uttar Beelpabla | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
67 | 247305330-Kaya Bridge Gutudia Pubopara WDBD Sluice gate (WDBD) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
68 | 247305071-Sahas Mirpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
69 | 247305440-Kunar Ghata (Anis Shop) Kundibari ropad. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
70 | 247305090-Mechaghona-Bahadurpur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
71 | 247305091-Mechaghona Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
72 | 247305293-Noakati-Ramakhali Khal road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
73 | 247303007-Construction of 30m Long Bridge on Ula Bazar-Sarafpur UP Office (Baniakhali GC) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
74 | 247303008-Construction of 8.00m long Bridge/Culvert on Gutudia UP Office-Kanchannagar bazar via Bhandarpara UP Office Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
75 | 247303022-Construction of 60m Long Bridge on Sahos UP-Moikhali bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
76 | 247305102-Construction of 72m Long Bridge on Kulati Badurgacha bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
77 | 247305413-Construction of 93m Long Bridge on Tipna-Singa Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
78 | 247302003-Khornia GC - Rudhaghora UP - Boruna GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
79 | 247302008-Mostafar more RHD-Rajbandh-Kaiya GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
80 | 247303001-Magurghona UP Office (RHD Road) -Uttor Magurghona Karim Box Bazar Rd via Magurghona Union H/S Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
81 | 247303017-Gutudia UP-Salua Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
82 | 247304116-Faloymari Baster mill-Bakultala-Pashkhali Sluice gate Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
83 | 247304013-Zalardanga RHD-Bhadurpara UP road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
84 | Construction of Khornia Growth Center | KDRIDP/Khul/GC-02/2017-18 | 0 | 0 | 1 | 20.8 | 2018-01-30 | M/S Amin & Co. | 2018-03-11 | 18.72 | 0% | 2018-12-17 | 0 | 0 | 0 | 0% | 0
85 | Construction of Kathalia Bazar Growth Center | KDRIDP/Khul/GC-03/2017-18 | 0 | 0 | 1 | 21.02 | 2018-01-30 | M/S Amin & Co. | 2018-03-11 | 18.92 | 40% | 2018-12-17 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
86 | Construction of Kanchanagar Kheya Ghat | KDRIDP/Khul/G-06/2017-18 | 0 | 0 | 1 | 35.56 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
87 | Construction of Jabra Bazar Kheya Ghat | KDRIDP/Khul/G-07/2017-18 | 0 | 0 | 1 | 27.86 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
88 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 26.374 | 0 | 4 | 1995.419 |  |  |  | 1655.642 | 5.455% |  | 16.858 | 489.866 | -473.008 | 29.59%

## Phultala
Phultala
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 247693006-Damodar UP-Alka Transmeter bazar via Damodar Kolony & Alka Dakkin para. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
2 | 247694010-Pura Buttala Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 247694032 - Improvement of Paygram Kashba Shikir hat CH - ( 00m- 641m) | KDRIDP/Khul/W-47/2017-18 | 0.641 | 0 | 0 | 39.779 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 247694084 - Improvement Satiani Bazar - Jamira GC Road (Ch: 1085 - 1325m) | KDRIDP/Khul/W-28/2017-18 | 0.24 | 0 | 0 | 14.15 | 2017-09-25 | M/S Sufian Enterprise | 2017-11-03 | 13.73 | 100% | 2018-08-20 | 0 | 4.79 | -4.79 | 34.89% | Salvage Tk. 3,28,628.00
5 | 247694090-Damotar GPS-Korai Comp. Factory Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 247694099 - Improvement of Phultala Rail Station - Phultala Thana H/Q Road (Ch: 627 - 1818m) | KDRIDP/Khul/W-30/2017-18 | 1.191 | 0 | 0 | 64.209 | 2017-09-25 | Md. Ziaul Haque. | 2017-11-13 | 59.71 | 50% | 2018-09-27 | 0 | 25.824 | -25.824 | 43.25% | Salvage Tk. 5,60,209.00
7 | 247694102 - Improvement of Muktisory Mazar- Bejerdanga Bazar road (Ch: 605 - 750m). | KDRIDP/Khul/W-12/2016-17 | 0.145 | 0 | 0 | 8.25 | 2017-10-27 | M/S Rupa Enterprise | 2017-09-10 | 8.005 | 100% | 2018-04-25 | 7.827 | 7.827 | 0 | 97.78% | Final (Salvage Tk. 5,60,209.00)
8 | 247694105 - Improvement of Bejerdanga-Rabindra Complex upto Shikirhat road (Ch: 1320- 2520m). | KDRIDP/Khul/W-10/2016-17 | 1.2 | 0 | 0 | 70.49 | 2017-10-27 | M/S Rupa Enterprise | 2017-09-10 | 66.61 | 100% | 2018-07-25 | 0 | 38.179 | -38.179 | 57.32% | Salvage Tk. 7,51,308.00
9 | 247694109-Pro.Safiullas/H - Alka gate road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247694117 - Improvement of Bejerdanga Rail Station - Bejerdanga Primary School Volapata UZR Road (Ch: 1550 - 2640m) | KDRIDP/Khul/W-29/2017-18 | 1.09 | 0 | 0 | 63.715 | 2017-09-25 | Md. Ziaul Haque. | 2017-11-13 | 61.8 | 10% | 2018-09-27 | 0 | 0 | 0 | 0% | 0
11 | 247694118-Bejerdanga rail station Dhakuria primary school - Bejerdanga school road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 247694080 - Improvement of Shirmoni Bazar-Dakatia Beel via Imam Bari road (Ch: 2040 - 2430m). | KDRIDP/Khul/W-11/2016-17 | 0.39 | 0 | 0 | 23.86 | 2017-10-27 | M/S Rupa Enterprise | 2017-09-10 | 22.54 | 100% | 2018-04-25 | 22.49 | 22.49 | 0 | 99.78% | Final (Salvage Tk. 2,66,250.00)
Maintenance
13 | 247693001-Atra Gilatala UP-Palpara Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 247694079-Shiromoni Tank Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247694080-Shiromoni Bazar -Dakatia Bill via Emambari Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247694055-Easterngate GC-Moshiali Firing Spot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247694081-Shiromoni Bazar-Shiromoni Dakhin Para | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 247694023 - Periodic Maintenance of Jugnipasha School Road Via Jugnipasha Mosque Road (Ch: 00m - 985m) | KDRIDP/Khul/M-01/2017-18 | 0.985 | 0 | 0 | 24.118 | 2018-02-26 | M/S Ruma Traders | 2018-04-26 | 24.118 | 0% | 2019-02-21 | 0 | 0 | 0 | 0% | 0
19 | 247694096-Phultala Health Complex-Phultala Railstation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 247695146-Mosiali Sarif House - Fakirpara Amjed Hossen GPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
21 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 5.882 | 0 | 0 | 308.571 |  |  |  | 256.513 | 21.9% |  | 30.317 | 99.11 | -68.793 | 38.64%

## Koyra
Koyra
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 247532005 - Improvement of Islampur R&H - Ghugrakati GC Road (Ch: 00 - 1100m) | KDRIDP/Khul/W-23/2017-18 | 1.1 | 0 | 0 | 85.64 | 2017-09-21 | M/S Sufia Enterprise | 2017-11-13 | 77.07 | 40% | 2018-11-19 | 0 | 24 | -24 | 31.14% | Salvage Tk. 18,90,615.00
2 | 247532006 R&H Graduate High School-Hayatkhali Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 247532010-Jagir Mahal Bazar-Gilabari GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 247532011-Bamia R&H-Baskhali-Malikhali-Boga Bazar-Narayanpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 247533001 - Improvement of Koyra UP- 4 No. Koyra Bazar Road (Ch: 2890 - 3770m) | KDRIDP/Khul/W-22/2017-18 | 0.88 | 0 | 0 | 55.83 | 2017-09-21 | Md. Bodruddoja | 2017-11-13 | 58.56 | 10% | 2018-11-19 | 0 | 0 | 0 | 0% | Salvage Tk. 6,43,104.00
6 | 247533005 - Improvement of Uttar Bedkashi UP - Barobari Bazar - Pukurpar Bazar Road (Ch: 1900- 3158m) | KDRIDP/Khul/W-21/2017-18 | 1.258 | 0 | 0 | 98.53 | 2017-09-21 | Foysal Traders | 2017-11-13 | 103.42 | 30% | 2018-11-19 | 0 | 26.019 | -26.019 | 25.16% | Salvage Tk. 4,33,440.00
7 | 247533006 - Improvement of Amadi UP - Amadi Bazar Road (Ch: 875 - 2140m) | KDRIDP/Khul/W-24/2017-18 | 1.265 | 0 | 0 | 80.09 | 2017-09-21 | S.M Salah uddin | 2017-11-13 | 79.19 | 65% | 2018-11-19 | 0 | 47.83 | -47.83 | 60.4% | Salvage Tk. 8,36,506.00
8 | 247533011-Bagali Up-Boga Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
7 | 247534002-R & H Kalna-Dashalia Khya Ghat Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 247534003 - Improvement R&H - Deara - Rongbag UZR Road (Ch: 00 - 2270m) [Koira] [Salvage Cost of this package is Tk 3624706.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-37/2017-18 | 2.27 | 0 | 0 | 163.109 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 36,24,706.00
9 | 247534012-Ghorilal FRB-Golkhali Pry. School road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247534023 - Improvement of Harihorpur Parimary School - Binapani CARE Road (Ch: 00 - 975m) [Koira] | KDRIDP/Khul/W-25/2017-18 | 0.975 | 0 | 0 | 66.81 | 2017-09-21 | M/S Sufia Enterprise | 2017-11-13 | 60.13 | 0% | 2018-11-19 | 0 | 0 | 0 | 0% | Salvage Tk. 5,86,565.00
11 | 247534024-Holdibunia UZR .-Charamukha Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 247534028-Hatiardanga Surikhali-Chowmohona Bazar(Koyra Portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 247534029-R&H Road-Mosjidkur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 247534036-Dewliar Hat-Kashirabad BC Road via Uttar Chack Madrasha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247534080- Improvement of khirul BC road-Basepara BC road.(CH: 680-1563m) | KDRIDP/Khul/W-39/2017-18 | 0.883 | 0 | 0 | 54.42 | 2018-06-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247534058-Chandipur R&H Khirul Lunch Ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247534057- Improvement R&H Hatiardanga Culvert Surikhali Bazar via Patnikhali Road (Ch: 2060-2522m, 2522-3500m & 4450-5300m) [Koira] [Salvage Cost of this package is Tk 683306.00 (fixed) which will be paid by contractor] | KDRIDP/Khul/W-38/2017-18 | 2.29 | 0 | 0 | 132.33 | 2018-02-26 | Foysal Traders | 2018-04-08 | 141.59 | 30% | 2019-04-14 | 0 | 38 | -38 | 26.84% | Salvage Tk. 6,83,306.00
18 | 255575218- Beltala Pucca road-Hanif Biswas house road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 255575217-Ramchandrapur Mosur Biswas house to cannel road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 247534005-Uttar Chowkuni-Purbo Chowkoni Regd. Pry. School. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 247534070-Hatiardanga Culvert-Patnikhali Foot Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 247535048-Channirchok Girl's School- Kataltola khal road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 247534035-Hudabonia-Channichok (Culvert-Rashipara) road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 2475535017-Hudda -Banikhali road -Sonil Master H/o. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 247535113-Kalna Amzad Molla H/O road -Hossain Hawlder H/O road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 247535079-2 No Koyra R&H (Habibur Shope-Majherite BC via Nolpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 1 No. Koyra BC Road-H/O Anser Gazi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
28 | 247532006- R&H Graduate High School-Hayatkhali Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 247533009- Moheshawripur UP-Baniakhali Bazar via Noyani road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 247534055- R & H Islampur-UZR Narayanpur Launch Ghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
31 | 247534070 -Const. of RCC Bridge on Hatiar Danga Culvert to Patnikhali Foot Bridge iva majar chalk mondir | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
32 | 247533003-Koyra UP-Suti Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 247534057-R&H Hatiardanga Culvert-Surikhali Bazar road via Patnikhali Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
34 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 10.921 | 0 | 0 | 736.759 |  |  |  | 519.96 | 4.861% |  | 0 | 135.849 | -135.849 | 0.26127

## Paikgacha
Paikgacha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 247642006-Kopilmuni GC-Samukpota bazar-Katamari bazar-Jamtala bazar-Baroaria GC(Paikgacha portion) . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 247642011 - Improvement of Paikgacha GC - Laskarhat- Fulbari Hat- Boroaria GC road (Ch: 1028m-1372m, 1756m-4550m & 6161m-8420m ) | KDRIDP/Khul/W-67/2017-18 | 5.297 | 0 | 0 | 442.458 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Tk. 12,97,736.00
3 | 247642011 - Improvement of Paikgacha GC - Laskarhat- Fulbari Hat- Boroaria GC road ( Ch: 8540m-12520m) | KDRIDP/Khul/W-68/2017-18 | 3.98 | 0 | 0 | 346.986 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage Tk. 5,14,291.00
4 | 247642012-Paikgacha GCBaintala bazar - Gilabari GC (Paikgaha potion) road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 247643001-Garaikhali Gc-Amurkata Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 247643002-Garaikhali Gc-Gangrakhi Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 247643004-Lata UP -Chowmohoni bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 247643005-Mamudkati College more(Goaldanga) Akamgong Bazar via Horidhali UP Office Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 247643006-Sashtitala Bazar-Raruli UP Office road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 247643007-Gadaipur U.P Office(New Molongi bazer)Andermanik Bazar Via Rashid mia kheyaghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 247643008-Fulbari bazar-Darunmollick road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
12 | 247644001-Ramnathpur-Taltala road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 247644003-Mothbaria R&H-Ghosal road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 247644006-Habibnagar madrasha-Samukpota bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 247644010-Betbuni-Amurkata road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 247644014-Paikgacha GC-Samukpota Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 247644015 - Improvement of Paikgacha GC - Laskar Hat road . ( Ch: 0.00 - 1400m ) | KDRIDP/Khul/W-60/2017-18 | 1.4 | 0 | 0 | 89.09 | 2018-01-30 | M/S Ziaul Traders | 2018-03-25 | 97.91 | 0% | 2019-03-31 | 0 | 0 | 0 | 0% | 0
18 | 247644013-Improvement of Gorikhali - Kumkhali BB road Gorikhali Almin road via South Kumkhali Master Shibpodo Model H/Q Bridge Road. ( Ch: 1324m-3000m) | KDRIDP/Khul/W-58/2017-18 | 1.676 | 0 | 0 | 104.91 | 2018-01-30 | M/S Ziaul Traders | 2018-03-25 | 115.3 | 30% | 2019-03-31 | 0 | 0 | 0 | 0% | 0
19 | 247645146 - Improvement of Patkalkhali Bridge Kathtola BC road. (Ch: 0.00m-1110m) | KDRIDP/Khul/W-59/2017-18 | 1.11 | 0 | 0 | 69.95 | 2018-01-30 | M/S Zaman Enterprise | 2018-03-22 | 76.78 | 0% | 2019-03-28 | 0 | 0 | 0 | 0% | NoA Issued
20 | 247644048-Goraikhali-Hathair Danga via Knakhali Govt.Pri.School( West Side of Khal) to kanakhali Bridge. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
21 | 247644020-Barigari house at Soladana UZR-Amurkata Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
22 | 247644012-Const. of RCC Bridge on Vedamari-Sonkordana Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 247645008-Const. of RCC Bridge on Katipara Bazar-Charitable Dispensary Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
24 | 247642012-Paikgacha GC-Baintala Bazar-Bagularchack Bazar-Surikhali Bazar-Gilabari GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 247644084-Horidashkati Play Ground Horidhali UP Paikgacha GC-Samukpota bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Landing/ Riverghat
26 | Soladana BazarGhat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
27 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 13.463 | 0 | 0 | 1053.394 |  |  |  | 289.99 | 1.111% |  | 0 | 0 | 0 | 0%

## Summary
KHULNA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 12 | 5 | 33.794 | 0 | 0 | 944.284 | 185.07 | 30% | 19.6%
Union Road by BC | 14 | 10 | 33.619 | 0 | 0 | 1612.255 | 562.928 | 35% | 34.92%
Village Road by BC | 45 | 37 | 53.212 | 0 | 0 | 2706.535 | 551.997 | 36.39% | 20.39%
Village Road by HBB | 3 | 2 | 7.335 | 0 | 0 | 246.367 | 0 | 5% | 0%
Bridge on Upazila Road |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 1 |  | 0 | 40 | 0 | 0 | 0 | 0% | #DIV/0!
Maintenance | 1 | 1 | 0.985 | 0 | 0 | 24.118 | 0 | 0% | 0%
GC-Hat | 3 | 3 | 0 | 0 | 3 | 57.75 | 0 | 13.33% | 0%
Landing/ Riverghat | 3 |  | 0 | 0 | 3 | 0 | 0 | 0% | #DIV/0!
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 82 | 58 | 128.945 | 40 | 6 | 5591.309 | 1299.995 | 11.97% | 23.25%