## Bagerhat
BAGERHAT
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Sharankhola
1 | 201772004-Amragachia RHD - Banglabazar GC road | [13 empty] | 0 | #DIV/0!
2 | 201772006-Development of Baniakhali GC- Dhansagar RHD Road. Ch 1000 -3805 m. Salvage TK. 1634778.00 | KDRIDP/Bager/W-08/2016-17 | 2.805 | 0 | 0 | 210.72 | 2017-06-08 | M/S Ahamed Steel Industries, Kapuria patty, Mathbaris, Barisal | 2017-07-20 | 219.13 | 80% | 2018-09-02 |  | 153.39 | -153.39 | 70% | 3rd R/A
3 | 201772007-Tafalbari GC-Rasulpur GC-Rajapur GC-Pollanbari RHD Road. | [13 empty] | 0 | #DIV/0!
Morrelgonj
4 | 201602002 - Chingrakhali GC-Daibajnahati GC | [13 empty] | 0 | #DIV/0!
5 | 201602006 - Pollerhat GC-Chingrakhali UP-Zianagar RHD (Morel Part) | [13 empty] | 0 | #DIV/0!
6 | 201602007-Dhansagar RHD-Baniakhali GC Rd | [13 empty] | 0 | #DIV/0!
7 | 201602012 - Khalkula Steel bridge to Chingrakhali bazar via Kachuabunia Rahmatia School | [13 empty] | 0 | #DIV/0!
Mollahat
8 | 201562008-Harida more- Machuarkul Rd. | [13 empty] | 0 | #DIV/0!
9 | 201562009-Gawla-Kodalia Bazar Rd. | [13 empty] | 0 | #DIV/0!
10 | 201562010-Ghoradair -Kachna Road. | [13 empty] | 0 | #DIV/0!
Rampal
11 | 201732007-Bhaga RHD-Kapasdanga-Kaigardashkati-Chalnahat GC (Rampal portion) | [13 empty] | 0 | #DIV/0!
12 | 201732010-Improvement of Balai Bridge-Rampal Road Ch. 0.00m-5100m. Under Rampal Upazila Bagerhat. Road ID No. 201732010 Salvage cost Tk. 3840719.00 | KDRIDP/Bager/W-72/2017-18 | 5.1 | 0 | 0 | 416.04 | 2018-03-06 | M.A. Jalil Khan, Rupsha Stand Road, Khulna. | 2018-04-25 | 456.72 | 0% | 2019-05-02 |  |  | 0 | 0%
13 | 201732013-A) Development of Baliadanga Bus Stand- Vangonpar Road by BC Ch 00-5200 m. B) Construction of 2 nos U-Drain at ch 300 m& 495 m.C Construction of 04 Nos Rcc 3x3 V Box Culvert at ch 2040m3450 m4170 m & 4525 mOn Same Road. Salvage Cost TK. 2101973.00 Fixed | KDRIDP/Bager/W-01/2016-17 | 5.2 | 0 | 0 | 251.31 | 2017-05-15 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-07-03 | 262.62 | 20% | 2018-08-29 |  |  | 0 | 0%
14 | 201732014-Babur bari-Bujbunia Road. | [13 empty] | 0 | #DIV/0!
15 | 201732015-Improvement of Tatulia Bridge - Kadirkhola road Ch1175-2904m by BC. Salvage amount Tk.1486339.00 Fixed | KDRIDP/Bager/W-44/2017-18 | 1.729 | 0 | 0 | 138.038 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 144.56 | 10% | 2018-12-20 |  |  | 0 | 0%
Mongla
16 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 00-4550 m. Salvage cost TK.8984664.00 Fixed | KDRIDP/Bager/W-02/2016-17 | 4.55 | 0 | 0 | 370.91 | 2017-06-14 | MSEBA and AB (JV), 211, Khanjahan Ali, Road, Khulna. | 2017-08-02 | 388.83 | 30% | 2018-08-29 |  | 101.72 | -101.72 | 26.16%
17 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 4550-8340 m. Salvage cost TK.4928783.00 Fixed(2nd Call) | KDRIDP/Bager/W-03/2016-17 | 3.79 | 0 | 0 | 261.14 | 2017-06-14 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-08-02 | 272.72 | 35% | 2018-08-29 |  | 75.06 | -75.06 | 27.52% | 1st R/A
18 | 201582006-Chaterhat GC-Bashtola GC-Joymonigol Road. | [13 empty] | 0 | #DIV/0!
19 | 201582007-Improvement of Digiraj-Jhalmalia Dhigi road. Ch.4040m-7395m. Salvage Cost Tk. 3563628 | KDRIDP/Bager/W-77/2017-18 | 3.355 | 0 | 0 | 277.37 | [8 empty] | 0 | #DIV/0! | New Rate Estimate under preparation
Fakirhat
20 | 201342013 Lokhpur GC-Dhaka Khulna RHD (Nowapara More) | [13 empty] | 0 | #DIV/0!
Total |  |  | 26.529 | 0 | 0 | 1925.528 |  |  |  | 1744.58 | 29.17% |  | 0 | 330.17 | -330.17 | 18.93%
Improvement of Union Road by BC
Bagerhat Sadar
1 | 201083011 Bishnapur UP-Bakerganj bazar.(sadar portion) | [13 empty] | 0 | #DIV/0!
2 | 201083012 Baroipara UP office-Ujalpur bazar via Kafurpura school road. | [13 empty] | 0 | #DIV/0!
3 | 201083017 Improvement of Chulkathi bazar-Betaga UP Road Sadar Portion Ch00-1476. ID No-201083017 Salvage amount tk. 157003. fixed | KDRIDP/Bager/W-35/2017-18 | 1.476 | 0 | 0 | 87.09 | 2017-09-11 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 91.08 | 100% | 2018-07-22 | 91.06 | 91.06 | 0 | 99.98% | Final
4 | 201083018-Bemorta UP(At Fatepur)-Bottala bazar via Bijoypur. | [13 empty] | 0 | #DIV/0!
5 | 201083019-Bishnapur UP-Kandapara GC Rd. | [13 empty] | 0 | #DIV/0!
6 | 201083022-Karapara UP office to Karapara bazar via Magnitala bazar rd.. | [13 empty] | 0 | #DIV/0!
Sharankhola
7 | 201773004-Banglabazar GC-Dhansagar UP Office Rd via Rashid Khan Bridge Road. | [13 empty] | 0 | #DIV/0!
Morrelgonj
8 | 201603002 - Improvement of Baharbunia U.P.-Madrasa Hat Road from Ch. 00m-3020m. Salvage Amount Tk. 5799741.00 | KDRIDP/Bager/W-80/2017-18 | 3.02 | 0 | 0 | 194.94 | [8 empty] | 0 | #DIV/0! | Re-tender dt. 03.04.18
9 | 201603003 - Mazhibari RHD at Badsharhat-Nishanbaria U.P office | [13 empty] | 0 | #DIV/0!
10 | 201603004 - Improvement of Khowla UP office-CARE bazar RHD ch2686-4906m | KDRIDP/Bager/W-51/2017-18 | 2.22 | 0 | 0 | 127.62 | 2017-10-03 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2017-11-28 | 116.71 | 50% | 2018-12-04 |  | 26.6 | -26.6 | 22.79% | 1st R/A
11 | 201603007 - Banagrame Bazar-Hoglapasha U.P. | [13 empty] | 0 | #DIV/0!
12 | 201603009 - Morrelgonj-Upazila H.Q.to Baharbunia Union H.Q. | [13 empty] | 0 | #DIV/0!
13 | 201603010 - Putikhali UP office-Sonakhali bazar | [13 empty] | 0 | #DIV/0!
14 | 201603012 - Hoglabunia UP office-Lakhaner hat via Nager Hat | [13 empty] | 0 | #DIV/0!
15 | 201603017 - Baraikhali UP office-JeoDhara UP via Kalibari bazar | [13 empty] | 0 | #DIV/0!
16 | 201603019 - Improvement of Banagram UP- Shailkhali ch2100-2343m | KDRIDP/Bager/W-52/2017-18 | 0.243 | 0 | 0 | 15.39 | 2017-10-03 | M/S Sher-e-Bangla Traders, Mathbaria, Perojpur | 2017-11-28 | 14.82 | 35% | 2018-12-04 |  |  | 0 | 0%
17 | 201603015-Improvement of Jewdhara UP office -Joybangla bazar Ekramkhali Baytun Akram Hazi Bari Mosque road. Ch: 00-2169m | KDRIDP/Bager/W-56/2017-18 | 2.169 | 0 | 0 | 159.219 | 2017-10-26 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-12-13 | 166.84 | 5% | 2018-12-19 |  |  | 0 | 0%
Fakirhat
18 | 201343005-Singati Bazar-Piljong UP-Balir Dokan-Shambagat RHD. | KDRIDP/Bager/W-25/2017-18 | 1.02 | 0 | 0 | 64.92 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 60.65 | 55% | 2018-07-18 |  | 39.59 | -39.59 | 65.28% | 1st R/A
19 | 201343001-Fakirhat H/Q-Naldah Maubhog UP | [13 empty] | 0 | #DIV/0!
20 | 201343006 Upazila H/Q(Livestock Office)-Satsika-Baliadanga-Rakhalgachi UP (Fakirhat Part | [13 empty] | 0 | #DIV/0!
21 | 201343011 - Mulgor UP-Nalda Moubog UP Road | [13 empty] | 0 | #DIV/0!
Mollahat
22 | 201563004-Improvement of Kodalia U.P Office- Aruadehi hat road ch.1400-3480m | KDRIDP/Bager/W-71/2017-18 | 2.08 | 0 | 0 | 151.85 | 2018-02-07 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-03-21 | 136.66 | 0% | 2019-03-27 |  |  | 0 | 0%
23 | 201563006-Gaula UP-Chanderhat-Faltita Bazar Road. | [13 empty] | 0 | #DIV/0!
24 | 201563007-Kulia Up-Nagarkandi GC Rd. | [13 empty] | 0 | #DIV/0!
25 | 201563008 - Singgati hat-Chunkhola UP H/Q | [13 empty] | 0 | #DIV/0!
26 | 201563009-Mollarkul Bazar-Udyapur UP Road. | [13 empty] | 0 | #DIV/0!
Rampal
27 | 201733002-Gilatale G.C-Bhospatia UP Rd. | [13 empty] | 0 | #DIV/0!
28 | 201733005-Perikhali G.C-Bhojpatia U.P office Rd. | [13 empty] | 0 | #DIV/0!
29 | 201733006-Improvement of Rampa-Bashtoli UP Road Ch.1890m-3695m. Under Rampal Upazila Bagerhat. Road ID No. 201733006 Salvage cost Tk. 264634 | KDRIDP/Bager/W-73/2017-18 | 1.805 | 0 | 0 | 104.937 | [8 empty] | 0 | #DIV/0! | New Rate estimate sent to HQ
30 | 201733007-Uzalkur UP-Baburhat Road | [13 empty] | 0 | #DIV/0!
31 | 201733009-Perikhali GC-Hurka UP | [13 empty] | 0 | #DIV/0!
32 | 201733010-Kaligonj bazar-Mollikarbare UP | [13 empty] | 0 | #DIV/0!
33 | 201733014-Improvement of Rampa UP-Pabantala hat Road Ch.0.00m-2380m & 4646m-5484m .Under Rampal Upozila Bagerhat. Road ID No. 201733014 Salvage cost Tk. 2551146 | KDRIDP/Bager/W-74/2017-18 | 3.218 | 0 | 0 | 210.72 | 2018-03-06 | M/S Ziaul & Brothers, Bhandaria, Pirojpur | 2018-04-24 | 231.3 | 0% | 2019-04-29 |  |  | 0 | 0% | Evaluation under process
Mongla
34 | 201583002-Burirdanga hat-Sonaeiltola UP Rd. | [13 empty] | 0 | #DIV/0!
35 | 201583007-Khulna-Mongla RHD at Goni Bridge- Burirdanga UP Office via Kapalirmeat Rd. | [13 empty] | 0 | #DIV/0!
36 | 201583001-Impropment of Chandpai UP - Chila hat Road. | [13 empty] | 0 | #DIV/0!
Chitalmari
37 | 201143001 - Chitalmari-Hizla UP-Kalatola UP | [13 empty] | 0 | #DIV/0!
38 | 201143006-Chinguri hat-Kalatala UP-Banglabazar Road. | [13 empty] | 0 | #DIV/0!
39 | 201143007 - Saildah hat-Kalatala UP | [13 empty] | 0 | #DIV/0!
Kachua
40 | 201383004-Improvement of Dhopakhali UP-Madertola bazar House Road by BC at Ch.987m-1881m. Salvage Amount Tk. 15,94,676.00 | KDRIDP/Bager/W-84/2017-18 | 0.894 | 0 | 0 | 64.787 | 2018-05-17 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-06-05 | 68.026 |  |  |  |  | 0 | 0%
| 201383009-Improvement of Kachua UP-Talwshwer bazar Road by BC at Ch.00m-1143m & 2961m-3600m. Salvage Amount Tk. 22,87,655.00 |  | 1.782 | 0 | 0 | 123.059 |  |  |  | 129.21 |  |  |  |  | 0 | 0%
41 | 201383005-Improvement of Fatehpur bazar-Gopalpur UP- Fultala bazar Road. Ch4794-5353 m & 6300-7100 m. Salvage Cost Tk. 1345002.00 | KDRIDP/Bager/W-48/2017-18 | 1.359 | 0 | 0 | 83.459 | 2017-12-04 | M/S Sonia Enterprise, Nagerbazar, Bagerhat | 2018-02-05 | 87.15 | 50% | 2019-02-11 |  | 30.44 | -30.44 | 34.93% | 1st R/A
42 | 201383008-Badhal UP-Atharogati bazar Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 21.286 | 0 | 0 | 1387.991 |  |  |  | 1102.446 | 36.88% |  | 91.06 | 187.69 | -96.63 | 17.02%
Improvement of Village Road by BC
Bagerhat Sadar
1 | 201084001-South Khanpur-Taterhat-Ranjeetpur.(start from Ranjeetpur Asrayan) | [13 empty] | 0 | #DIV/0!
2 | 201084011-B.Sc High school-Laksmikhali BWDB-Chaksree(Kalibari) hat road. | [13 empty] | 0 | #DIV/0!
3 | 201084017-Patorpara-Karapra road(Add.CE R&H dept). | [13 empty] | 0 | #DIV/0!
4 | 201084018-Patilakhali-Nataikhali road | [13 empty] | 0 | #DIV/0!
5 | 201084019-Kandapara GC(Parnowapara)-Betkhali bazar-Taleswar bazar road. | [13 empty] | 0 | #DIV/0!
6 | 201084024-Zindapir mazar-Khanjahan Ali mazar with link of nine gambuj mosque. | [13 empty] | 0 | #DIV/0!
7 | 201084038-Haderhat bazar-Bakhergonj bazar via singa kheyaghat WDB road. | [13 empty] | 0 | #DIV/0!
8 | 201084040-Monigonj-Gopalkati-Bishnapur Rd. | [13 empty] | 0 | #DIV/0!
9 | 201084067-Chapatola (H/O Amin)-Jattrapur govt. pri. School | [13 empty] | 0 | #DIV/0!
10 | 201084074-Rakhalgachi UP-Chulkathi bazar via Ranjeetpur. | [13 empty] | 0 | #DIV/0!
11 | 201085010-Doritaluk Rd-Bagmara Road | [13 empty] | 0 | #DIV/0!
12 | 201085288-Chaparkul –Bakarganj bazar via khalispur road. | [13 empty] | 0 | #DIV/0!
13 | 201085039-Bara Bansh Baria road | [13 empty] | 0 | #DIV/0!
14 | 201085044-Bara Bansh High school | [13 empty] | 0 | #DIV/0!
15 | 201084046- Improvement of Jattrapur at UZR- Komorpur via Afra Mowmachi Palon project & Murshidpur Ch00-2151m. Salvage Amount tk.-592374 fixed | KDRIDP/Bager/W-36/2017-18 | 2.151 | 0 | 0 | 127.185 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 133.33 | 100% | 2018-08-30 | 133.31 | 133.31 | 0 | 99.98% | Final
16 | 201084040-Improvement of Monigonj- Gopalkati- Bishnapur Road from Ch. 823m-1658m. Salvage Cost Tk. 1642597.00 | KDRIDP/Bager/W-78/2017-18 | 0.835 | 0 | 0 | 85.79 | [8 empty] | 0 | #DIV/0! | Request sent to HQ for cancellation.
17 | 201085013-Keshobpur Charogram-Kondola-Talswar road. | [13 empty] | 0 | #DIV/0!
18 | 201085191-Improvement of Hakimpur Pry. School-Chandromahel road Ch 995-1845m. Salvage amount tk. 246687.00 fixed | KDRIDP/Bager/W-37/2017-18 | 0.85 | 0 | 0 | 60.78 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 63.72 | 100% | 2018-08-30 | 63.66 | 63.66 | 0 | 99.91% | Final
19 | 201084069-West Saera Bazar-Sree Ghat Bazar via Sadullahpur road. | KDRIDP/Bager/W-16/2016-17 | 0.702 | 0 | 0 | 41.58 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-13 | 43.56 | 100% | 2018-08-19 | 43.553 | 43.553 | 0 | 99.98% | Final
20 | 201085234-Rangeetpur-Southpara via Morralpara Tater hat road. | [13 empty] | 0 | #DIV/0!
21 | 201085238-Development of Ranjitpur- Guchegram- Morolpara- Surjamukhi Club Road. Ch 00-821 m. Salvage Cost Tk.145827.00 | KDRIDP/Bager/W-10/2016-17 | 0.821 | 0 | 0 | 49.28 | 2017-06-14 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-07-26 | 51.69 | 100% | 2018-05-29 | 51.65 | 51.65 | 0 | 99.92% | Final
22 | 201085040- Improvement of PC Dema Pucca Road-Mallik bari Road CH00-350M. Salvage amount 176715.00 fixed | KDRIDP/Bager/W-58/2017-18 | 0.35 | 0 | 0 | 20.11 | 2017-10-26 | M/S S.S. Brothers, 18, Sarker lane, Tootpara, Khulna. | 2017-12-12 | 21.11 | 60% | 2018-06-18 |  |  | 0 | 0%
Kachua
22 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.1278m-3278m. Salvage Amount Tk. 3144409.00 | KDRIDP/Bager/W-85/2017-18 | 2 | 0 | 0 | 190.819 | 2018-05-27 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-06-28 | 199.31 | 5% | 2019-12-04 |  |  | 0 | 0%
23 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.5780m-7564m. Salvage Amount Tk. 297535.00 | KDRIDP/Bager/W-86/2017-18 | 1.784 | 0 | 0 | 134.255 | 2018-05-28 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-07-01 | 140.968 | 0% | 2019-12-07 |  |  |  | 0%
24 | 201384017-Development of Bakultala- Moshni Road. Ch. 2059-3135 m. Salvage Cost. TK.-539470.00 | KDRIDP/Bager/W-20/2016-17 | 1.076 | 0 | 0 | 78.97 | 2017-08-08 | M/S Rupali Construction, Hospital Road, Barisal | 2017-09-11 | 82.5 | 35% | 2018-09-17 |  | 14.39 | -14.39 | 17.44% | 1st R/A
25 | 201384016-Improvement of Kachua-Badamtali Road by BC at Ch.1673m-3173m. Salvage Amount Tk. 904835.00 | KDRIDP/Bager/W-88/2017-18 | 1.5 | 0 | 0 | 145.075 | 2018-05-28 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-07-01 | 152.328 | 10% | 2019-12-07 |  |  | 0 | 0%
26 | 201384044-Improvement of Maliporton School-bishkhali Road. Ch400-1260 m Under Kachua Upazila. Bagerhat. Salvage Cost Tk. 107512.00(Fixed) | KDRIDP/Bager/W-50/2017-18 | 0.86 | 0 | 0 | 63.956 | 2017-11-21 | M/S Robel Enterprise, Madaripur | 2018-01-25 | 66.52 | 40% | 2019-01-30 |  | 13 | -13 | 19.54% | 1st R/A
27 | 201384045-Laraahat-Lararkul | [13 empty] | 0 | #DIV/0!
28 | 201384085-Improvement of Mosni Bazar-Bhuddobhumi Road by BC at Ch.1500m-2566m. Salvage Amount Tk. 7,80,539.00 | KDRIDP/Bager/W-87/2017-18 | 1.066 | 0 | 0 | 94.25 | 2018-05-28 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-07-01 | 98.96 | 0% | 2019-12-07 |  |  | 0 | 0%
| 201384031-Improvement of Mogia-Shirokhali Road by BC at Ch. 510m-1060m. Salvage Amount Tk. 8,59,367.00 |  | 0.55 | 0 | 0 | 36.06 |  |  |  | 37.86 |  |  |  |  | 0 | 0%
29 | 201385032-Afra Battala- Afra Jame Mosque Rd. | [13 empty] | 0 | #DIV/0!
30 | 201384103-Development of Guzarpara- Baleshor River Ghat Road. Ch.558-1540 m. Salvage Cost TK. 211626.00 | KDRIDP/Bager/W-18/2016-17 | 0.982 | 0 | 0 | 68.2 | 2017-07-10 | M/S Sufia Enterprise, Badura Parerhat, Pirojpur. | 2017-08-22 | 71.4 | 100% | 2018-08-29 | 71.39 | 71.39 | 0 | 99.99% | Final
31 | 201384103-Improvement of Guzarpara-Baleshor River Ghat Road Ch.1540m-1767m. Salvage cost Tk. 135904 | KDRIDP/Bager/W-75/2017-18 | 0.227 | 0 | 0 | 15.7 | 2018-01-25 | M/S Upokar Enterprise, LGED, Pirojpur. | 2018-05-01 | 14.8 | 60% | 2019-03-31
32 | 201385014-Development of B. Andermanik S Club - Huchibaga- Andermanik H. School Road. Ch.271-2146 m. Salvage Cost TK. 900690.00 | KDRIDP/Bager/W-17/2016-17 | 1.875 | 0 | 0 | 139.996 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 146.93 | 100% | 2018-08-12 | 146.913 | 146.913 | 0 | 99.99% | Final
33 | 201384100-Improvement of Shibpur- Palpara Road. Ch 00-1359 m. Salvage Cost Tk. 491805.00 (201384078) | KDRIDP/Bager/W-46/2017-18 | 1.359 | 0 | 0 | 90.636 | 2017-12-18 | M/S Khandaker Brothers, Nalcity, Jhalokati. | 2018-01-28 | 96.38 | 40% | 2019-02-03 |  | 11.15 | -11.15 | 11.57% | 1st R/A
34 | 201384019-Madettola-Jobai | [13 empty] | 0 | #DIV/0!
35 | 201384025-Improvement of Protappur-Bokaterkathi Road. Ch00-625 m. Salvage Cost Tk. 330365.00 | KDRIDP/Bager/W-49/2017-18 | 0.625 | 0 | 0 | 69.678 | 2017-10-04 | M/S Masud Enterprise, Kachua, Bagerhat. | 2017-11-13 | 72.73 | 100% | 2018-11-19 | 72.42 | 72.42 | 0 | 99.57% | Final
36 | 201384115-Padonagur masin shop via chato khal to signboard (201384065) | KDRIDP/Bager/W-29/2017-18 | 1.114 | 0 | 0 | 89.598 | 2017-08-22 | Md. Noor Hossain, Mission para, Jessore. | 2017-10-11 | 83.12 | 35% | 2018-07-17 |  |  | 0 | 0%
37 | 201384050-Improvement of Charkati- Baruikhali Shosan Ghat Road. Ch1000-2325 m. Salvage Cost Tk. 460221.00 | KDRIDP/Bager/W-47/2017-18 | 1.325 | 0 | 0 | 83.92 | 2017-10-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2017-11-13 | 88.12 | 100% | 2018-11-19 | 88.11 | 88.11 | 0 | 99.99% | Final
38 | 201384043-Development of Uttar Gopalpur- Kachua Araian Bridge Road. Ch.00-961 m. Salvage Cost TK. 475021.00 | KDRIDP/Bager/W-19/2016-17 | 0.961 | 0 | 0 | 70 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 73.4 | 100% | 2018-08-12 | 73.28 | 73.28 | 0 | 99.84% | Final
39 | 201385059-Atharogati-Sardar Bari House to Ohidkhan road. | [13 empty] | 0 | #DIV/0!
40 | fatepur fultala(paddanagar)via brigde to habibshop | [13 empty] | 0 | #DIV/0!
Sharankhola
41 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Rd | [13 empty] | 0 | #DIV/0!
42 | 201774006: Improvement of Kadamtala Ashar alo Mosjid- Varanirper upgrade GPS Road Ch4885-5885m | KDRIDP/Bager/W-26/2017-18 | 1 | 0 | 0 | 56.797 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 54.46 | 60% | 2018-07-10 |  | 31.8 | -31.8 | 58.39% | 2nd R/A
43 | 201774007: Nalbunia-Baniakhali road | [13 empty] | 0 | #DIV/0!
44 | 201774011-Improvement of Rajapur-Dhansagar Bazar Road by BC at Ch.505m-1875m. Salvage Amount Tk. 2,04,825.00 | KDRIDP/Bager/W-91/2017-18 | 1.37 | 0 | 0 | 89.544 | [8 empty] | 0 | #DIV/0!
| 201774048-Improvement of Rajapur WAPDA-Rajapur GC (Police Fary) Bazar Road by BC at Ch.675m-1450m. Salvage Amount Tk. 4,36,293.00 |  | 0.775 | 0 | 0 | 51.07 | [8 empty] | 0 | #DIV/0!
45 | 201774014-Amtoli-Badhal Road. | [13 empty] | 0 | #DIV/0!
46 | 201774018: Improvement of Golbunia Talukderbari-Motherper Ladenmor Road Ch2900-4300m. Salvage amount -tk.548997.00( fixed) | KDRIDP/Bager/W-27/2017-18 | 1.4 | 0 | 0 | 80.36 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 75.29 | 60% | 2018-07-10 |  | 44.64 | -44.64 | 59.29% | 2nd R/A
47 | 201774022: Jhilbunia-Lakurtala road | [13 empty] | 0 | #DIV/0!
48 | 201774023: Khada -Lakurtala Road | [13 empty] | 0 | #DIV/0!
49 | 201774024: Banglabazar-Tafalbari-Mourashi Road | [13 empty] | 0 | #DIV/0!
50 | 201774025: Improvement of Khada-North Tafalbari-Mourasi Bazar Road by BC at Ch.00m-2000m. Salvage Amount Tk. 3,78,627.00 (2nd Call) | KDRIDP/Bager/W-90/2017-18 | 2 | 0 | 0 | 135.226 | [8 empty] | 0 | #DIV/0!
51 | 201774035:Bakultala - Sonatala Rd | [13 empty] | 0 | #DIV/0!
52 | 201774040: Improvement of Khontakata-Charerper Road by BC at Ch.1640m-3280m. Salvage Amount Tk. 388301.00 | KDRIDP/Bager/W-81/2017-18 | 1.64 | 0 | 0 | 112.27 | 2018-05-29 | M/S Sohana Enterprise, Sharankhola, Bagerhat |  | 117.58 |  |  |  |  | 0 | 0% | NOA issued on 11.06.18
53 | 201775078-Improvement of Rajapur Bayor-Saver Madrasa via Gojen Roy House Road by BC at Ch.00m-1500m. Salvage Amount Tk. 572444.00 | KDRIDP/Bager/W-82/2017-18 | 1.5 | 0 | 0 | 97.406 | 2018-06-11 | M/S Sohana Enterprise, Sharankhola, Bagerhat |  | 102.016 |  |  |  |  | 0 | 0% | NOA issued on 11.06.18
54 | 201774047-Improvement of Taltoli bazer-Nalbunia (Bezitana) bazer Road Ch1500-2505m. Salvage amount -tk.554716.00 (fixed) | KDRIDP/Bager/W-28/2017-18 | 1.005 | 0 | 0 | 62.45 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 58.02 | 60% | 2018-07-10 |  | 34.82 | -34.82 | 60.01% | 2nd R/A
Morrelgonj
55 | 201604011-Chingrakhali-Dharadoha Rd. | [13 empty] | 0 | #DIV/0!
56 | 201604027 - Improvement of Gabagachia-Burujbaria road. Ch 500m-2150m. Salvage Cost Tk.49606.00. | KDRIDP/Bager/W-70/2017-18 | 1.65 | 0 | 0 | 127.54 | 2018-01-25 | Md. Shariful Alam, Fakirhat, Bagerhat | 2018-03-11 | 126.778 | 0% | 2019-03-17 |  |  | 0 | 0%
57 | 201604044 - R&H road (at Saralia wooden bridge)-Kutghata bazar. | [13 empty] | 0 | #DIV/0!
58 | 201604050 - Amtala bazar-Chandipur Highschool via Taltola bazar | [13 empty] | 0 | #DIV/0!
59 | 201604065 - Improvement of Srenikhali- Bashbaria road Paschim Kalikabari- C & B road ch800-2480m. Salvage amount tk.482190.00 fixed | KDRIDP/Bager/W-54/2017-18 | 1.68 | 0 | 0 | 123.3 | 2017-10-04 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-11-28 | 128.23 | 25% | 2018-12-04 |  | 25 | -25 | 19.5% | 1st R/A
60 | 201604069 - Chingrakhali FRB Road-Khalkula-sagorkati | [13 empty] | 0 | #DIV/0!
61 | 201604072 - Improvement of Tulatola RHD near h/o M. Talukder-Uttttarjoka RHD ch4250-5140m. Salvage Amount Tk.502421.00 fixed | KDRIDP/Bager/W-53/2017-18 | 0.89 | 0 | 0 | 51.02 | 2017-10-03 | M/S Faruk Enterprise, Kachua, Bagerhat | 2017-11-19 | 53.54 | 100% | 2018-11-25 | 53.54 | 53.54 | 0 | 100% | Final
62 | 201604074 - Development of Bashbaria R & H to Mongolerhat. CH 00-1260 m. Salvage Cost. TK. 109498.00 | KDRIDP/Bager/W-21/2016-17 | 1.26 | 0 | 0 | 100.49 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-07 | 104.567 | 50% | 2018-08-29 |  | 52.21 | -52.21 | 49.93% | 1st R/A
63 | 201604088 - Panchakaran UP office to Sonakhali bazar | [13 empty] | 0 | #DIV/0!
64 | 201604098 - Chairman Bazar-RHD road via H/O Master Abul Kashem | [13 empty] | 0 | #DIV/0!
65 | 201605121--Daskhali RHD-Shoilkhali Bazar | [13 empty] | 0 | #DIV/0!
66 | 201605095-Kalibari Bazar - Srizon Smriti high School via Mothbaria School Road. | [13 empty] | 0 | #DIV/0!
67 | 201605124-Improvement of Nurul Islam Dakhil Madrasa-Gulishakhali UP office via Sonamuddin Chokidar Bari Road from Ch. 00m-5124m. Salvage Amount Tk. 328810.00. | KDRIDP/Bager/W-79/2017-18 | 5.124 | 0 | 0 | 198.95 | [8 empty] | 0 | #DIV/0! | Re-tender dt. 03.04.18
68 | 201605004-Development of Kalikabari- Guabaria Road. Ch 220 - 2776 m | KDRIDP/Bager/W-09/2016-17 | 2.556 | 0 | 0 | 209.99 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-11 | 217.576 | 15% | 2018-08-29 |  | 8.75 | -8.75 | 4.022% | 1st R/A
69 | 201604140-Improvement of Badshar hat C & B- Hasan Member bari Mazibari road via Tassen Uddin Howlader bari road. Ch00m-2130m. Salvage Cost Tk.172678.00. | KDRIDP/Bager/W-69/2017-18 | 2.13 | 0 | 0 | 153.08 | 2018-01-30 | Sayed Milon, Post office road, Jhalokathi. | 2018-02-20 | 157.599 | 20% | 2019-02-26 |  | 16.17 | -16.17 | 10.26% | 1st R/A
70 | 201605061-Improvement of Sleeper bridge Near RHD North Balvadrapur Shasapara via Tripolli RNGPS ch 00-1482m | KDRIDP/Bager/W-55/2017-18 | 1.482 | 0 | 0 | 104.457 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 108.63 | 20% | 2018-12-20 |  | 17.48 | -17.48 | 16.09% | 1st R/A
71 | 201605124-Improvement of NUrul Islam Dhakil Madrasha Gulishakhali UP Office via Sona Muddin Chokider bari road. | [13 empty] | 0 | #DIV/0!
72 | 201604063-Morrelganj-Bisarighata | [13 empty] | 0 | #DIV/0!
73 | 201605165-W.Kachubunia Primary School Road. | [13 empty] | 0 | #DIV/0!
Fakirhat
74 | 201344004- Khulna Mollahat R&H at Talerpukur pagla deapara | [13 empty] | 0 | #DIV/0!
75 | 201344008-Improvement of Khazura R &H-Bolloppur Road. Ch1194-2650m. Salvage Cost-103999.00(fixed) | KDRIDP/Bager/W-24/2017-18 | 1.456 | 0 | 0 | 84.83 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 79.3 | 45% | 2018-07-18 |  | 36.62 | -36.62 | 46.18%
76 | 201344009-Lockpur Ballata-Bollopur village rd | [13 empty] | 0 | #DIV/0!
77 | 201344013- Shibbari-Dohor Moubog Road | [13 empty] | 0 | #DIV/0!
78 | 201344014- Mollar bazar-Bangopar bazar via Tekatia road | [13 empty] | 0 | #DIV/0!
79 | 201344018 - Betaga bazar-pasur river via Chakuli Pry.school road | [13 empty] | 0 | #DIV/0!
80 | 201344024 - Singati Gilatala road upto C&B Bazer | [13 empty] | 0 | #DIV/0!
81 | 201344026 - Kanarpukur-Deapara Rd | [13 empty] | 0 | #DIV/0!
82 | 201344042 - Singati-Baliadanga road | [13 empty] | 0 | #DIV/0!
83 | 201344061- Nawapara Baloyer Dokan-Syambagat Rd | [13 empty] | 0 | #DIV/0!
84 | 201344088-Kanarpukur-Satshikha Rd | [13 empty] | 0 | #DIV/0!
Chitalmari
85 | 201144020-Kirtankhali - Kharamkhali road (via Khasherhat GC) Road. | [13 empty] | 0 | #DIV/0!
86 | 201144011 - Development of Moidah Shibpur Club- Kaligati Road. Ch 00-878. Salvage Cost TK. 404704.00 | KDRIDP/Bager/W-15/2016-17 | 0.878 | 0 | 0 | 61.46 | 2017-07-10 | M/S S.S. Traders, Tungipara, Gopalgonj | 2017-08-24 | 59.92 | 100% | 2018-08-30 | 59.87 | 59.87 | 0 | 99.92% | Final
87 | 201144023 - Chinguri kheaghat-Krishi Bank-Kalatala road | [13 empty] | 0 | #DIV/0!
88 | 201144032 - Development of Khaserhat- Asoknagar Road. Ch 2300-4595 m. Salvage Cost TK. 433415.00 | KDRIDP/Bager/W-13/2016-17 | 2.295 | 0 | 0 | 147.91 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 143.47 | 60% | 2018-08-29 |  | 91.31 | -91.31 | 63.64% | 1st R/A
89 | 201144033-Development of Shampara- Kudari via Panchpara Hat Road. Ch 1000-2550 m. Salvage Cost TK. 796234.00 | KDRIDP/Bager/W-12/2016-17 | 1.55 | 0 | 0 | 140.03 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 135.17 | 50% | 2018-08-29 |  | 48.34 | -48.34 | 35.76% | 1st R/A
90 | 201144049-Development of Barobaria at RHD Road-Ghola High School-Baroguni bazar Road. Ch 00-1700 m. Salvage Cost TK. 261420.00 | KDRIDP/Bager/W-14/2016-17 | 1.7 | 0 | 0 | 105.59 | 2017-07-10 | Md. Iqbal Hossain, Tungipara, Gopalgonj. | 2017-08-06 | 101.05 | 60% | 2018-08-29 |  | 49.8 | -49.8 | 49.28%
91 | 201145027-Improvement of Hizla Sheikpara- Agakhal RPS Road. Ch 00 -1275m. Salvage Cost TK. 618000.00 | KDRIDP/Bager/W-64/2017-18 | 1.275 | 0 | 0 | 103.13 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-02-06 | 92.82 | 30% | 2019-02-12 |  |  | 0 | 0%
Mongla
92 | 201584014 - Khaserdanga more-Kharkharia-Dewotala bazar | [13 empty] | 0 | #DIV/0!
93 | 201584021-Bashtala bazar-Digraj bazar Rd. | [13 empty] | 0 | #DIV/0!
94 | 201584030 - Chila hat-Monumia High School-Katakhali-Joymoni Battola | [13 empty] | 0 | #DIV/0!
95 | 201584040 - Improvement of Mongla ( Fire brigate)- Malgazi C.S- Moukhali (GCCR).. (Ch:3100.00-4250m). Salvage Cost Tk. 153808.00 | KDRIDP/Bager/W-92/2017-18 | 1.15 | 0 | 0 | 85.497 | [8 empty] | 0 | #DIV/0!
| 201584044 - Improvement of Holdibunia Baliar more-Burburia via malgazi-hid office Road. Ch3300m-4500m. Salvage Cost Tk.2220602.00 |  | 1.2 | 0 | 0 | 88.178 | [8 empty] | 0 | #DIV/0!
96 | 201584045 - Development of Digraj College - Burirdanga FWC Ch. 650-2380 m. Salvage Cost. Tk. 2023367.00 | KDRIDP/Bager/W-11/2016-17 | 1.73 | 0 | 0 | 112.53 | 2017-06-13 | Sardar Jashim, Kharder, Bagerhat | 2017-08-02 | 118.01 | 30% | 2018-08-29 |  | 20.45 | -20.45 | 17.33% | 1st R/A
97 | 201584071 - Sonailtola UP Office - Bokultola | [13 empty] | 0 | #DIV/0!
98 | 201584094 - Madurpalta Govt. Pond Road | [13 empty] | 0 | #DIV/0!
99 | 201584103 - Digraj bazar - Kitunia Bazar Road | [13 empty] | 0 | #DIV/0!
100 | 201584068-Improvement of Kumerkhali Bridge to Narkeltola Bridge to Masmara Village Road. Ch 0.00 -1895 m. Salvage Cost Tk. 4079725.00 | KDRIDP/Bager/W-66/2017-18 | 1.895 | 0 | 0 | 135.11 | 2018-01-24 | M/S Iqbal Enterprise, Mongla, Bagerhat | 2018-03-07 | 141.5 | 60% | 2019-03-13 |  | 77.44 | -77.44 | 54.73% | 1st R/A
Mollahat
101 | 201564022-Kahalpur RHD-Joydehihat | [13 empty] | 0 | #DIV/0!
102 | 201564090 - Improvement of Singati-Capil Bridge Road. Ch 500-920 m Under Mollahat Upazila Bagerhat. | KDRIDP/Bager/W-39/2017-18 | 0.42 | 0 | 0 | 26.66 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 23.996 | 70% | 2018-11-21 |  | 10 | -10 | 41.67% | 1st R/A
103 | 201564005 - Boaliahat-Kahalpur R&H Rd. | [13 empty] | 0 | #DIV/0!
104 | 201564007 - Improvement of Rajpat - Gaola UP Road. Ch 1062-2900 m. Salvage Cost. TK. 1386398.00 | KDRIDP/Bager/W-38/2017-18 | 1.838 | 0 | 0 | 111.297 | 2017-09-28 | M/S Rubel Enterprise, Rajoir, Madaripur | 2017-11-15 | 100.167 | 70% | 2018-11-21 |  | 55.43 | -55.43 | 55.34% | 2nd R/A
105 | 201564013 - Charkuliahat-Takiarkul road. | [13 empty] | 0 | #DIV/0!
106 | 201564016 - Atjuri UP-Kadamtala Kheyaghat | [13 empty] | 0 | #DIV/0!
107 | 201564039 - Boalia RHD-Bhandarkhola hat(Atjuri UP) | [13 empty] | 0 | #DIV/0!
108 | 201564047 - Improvement of Garfa- Girishnagar-Kadamtala Khayaghat Road. Ch 4100-4900 m Under Mollahat Upazila Bagerhat. Salvage Cost. TK. 114374.00 | KDRIDP/Bager/W-40/2017-18 | 0.8 | 0 | 0 | 46.965 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 42.27 | 100% | 2018-11-21 | 42.26 | 42.26 | 0 | 99.98% | Final
109 | 201565009 - Improvement of Chaulturi-Kodalia Bill Road. Ch 880-2255 m | KDRIDP/Bager/W-41/2017-18 | 1.375 | 0 | 0 | 77.9 | 2017-09-27 | Shikder Zahidul Islam, Mollahat, Bagerhat. | 2017-11-15 | 70.11 | 60% | 2018-11-21 |  | 36.42 | -36.42 | 51.95% | 2nd R/A
110 | 201565079 - Shason Sobed Molla House-Jamai More Road | [13 empty] | 0 | #DIV/0!
111 | 201565017 - Kahalpur Alek house-Kutimia house | [13 empty] | 0 | #DIV/0!
112 | 201565018 - Kahalpur Barapukurpar-Kahalpur H/School via Omar Moulana House | [13 empty] | 0 | #DIV/0!
113 | 201565022 - Kahalpur Charpara Road | [13 empty] | 0 | #DIV/0!
114 | 201564096-Uddaypur Uttar kandy Pacca road-Uddaypur Uttar Kandy GPS-Uttar kandy Graveyard with link of H/O Kamal Molla road. | [13 empty] | 0 | #DIV/0!
Rampal
115 | 201734104-Banshtali UP-Solakora | [13 empty] | 0 | #DIV/0!
116 | 201734018-Improvement of Kismat Kumlai-Saguna road Ch00-2080m by BC. Salvage amount Tk.2388545.00Fixed | KDRIDP/Bager/W-45/2017-18 | 2.08 | 0 | 0 | 154.76 | 2017-11-13 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 166.37 | 40% | 2018-12-20 |  | 26.12 | -26.12 | 15.7%
117 | 201734028-Sakurhat-Saguna Rd. | [13 empty] | 0 | #DIV/0!
118 | 201734032-Telikhali-Baruipara Rd. | [13 empty] | 0 | #DIV/0!
119 | 201734038-Development of KataKhali P/S - Dakra Road By HBB. Ch 1000-1650 m. Salvage Cost. TK.454832.00(2nd call) | KDRIDP/Bager/W-05/2016-17 | 0.65 | 0 | 0 | 21.95 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 23.6 | 50% | 2018-08-20 |  |  | 0 | 0% | HBB
120 | 201734042-Development of Dakhin Mollikerber-Dhalipara Road By HBB. Ch 1140- 2950 m Under Rampal Upazila Bagerhat. Road ID No. 201734042. Salvage Cost. TK.333359. (2nd call) | KDRIDP/Bager/W-04/2016-17 | 1.81 | 0 | 0 | 87.88 | [8 empty] | 0 | #DIV/0!
121 | 201734046-Rajnagor-Gorerdanga Road | [13 empty] | 0 | #DIV/0!
122 | 201734066-Foyla-Baburhat. | [13 empty] | 0 | #DIV/0!
123 | 201734068-Amtala bazar-Pabantala Bazar | [13 empty] | 0 | #DIV/0!
124 | 201734129-Development of Nolbunia borun BishasTran Bridge house-Babur bari bus Stand Road By BC. Ch (1915-2385m). Salvage Cost. TK.306072.00 (2nd call) | KDRIDP/Bager/W-07/2016-17 | 0.47 | 0 | 0 | 37.26 | 2017-11-13 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-01-04 | 40.15 | 40% | 2018-10-10 |  | 17.96 | -17.96 | 44.73% | 1st R/A
125 | 201735195-Development of Banga-Gilatola GC-Sorder Bari More-Hospital link Road Ch00-570m under Rampal Upazila District-Bagerhat Road ID No201735195 Salvage amount Tk.164834fixed | KDRIDP/Bager/W-59/2017-18 | 0.57 | 0 | 0 | 35.37 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 37.09 | 0% | 2018-11-06 |  |  | 0 | 0% | HBB
Total |  |  | 75.617 | 0 | 0 | 5174.095 |  |  |  | 4418.015 | 54.67% |  | 899.956 | 1639.256 | -739.3 | 37.1%
Improvement of Village Road by HBB
Kachua
1 | 201384051-Improvement of Bisherkhola-Bottola School Road by HBB at Ch.00m-2533m. Salvage Amount Tk. 845746.00 | KDRIDP/Bager/W-89/2017-18 | 2.533 | 0 | 0 | 162.366 | 2018-05-24 | M/S Rina Enterprise, Fultola, Bagerhat | 2018-06-25 | 161.96 |  |  |  |  | 0 | 0%
Sharankhola
2 | 201774013-Improvement of Purba Khontakata-Nalbunia Road by HBB at Ch.00m-1378m & 2818m-4090m. Salvage Amount Tk. 2312135.00 | KDRIDP/Bager/W-83/2017-18 | 2.65 | 0 | 0 | 111.809 | 2018-05-13 | M/S Chan Enterprise, Puraton Bazar, Bagerhat | 2018-06-18 | 116.84 | 0% | 2019-06-24 |  |  | 0 | 0%
Morrelgonj
3 | 201605021-Mohonpur-Banagramme Rd. | [13 empty] | 0 | #DIV/0!
4 | 201604098-Moslem khan's house - Gharami bari bridge Rd. | [13 empty] | 0 | #DIV/0!
5 | 201604140-Badshar hat C & B - Hasan Member bari (Mazibari) road via Tassen Uddin Howlader bari | [13 empty] | 0 | #DIV/0!
Fakirhat
6 | 201344006-Bahirdia-satbaria road. | [13 empty] | 0 | #DIV/0!
7 | 201344088-Bahirdia UP office to Weast Bahirdia GPS Rd. | [13 empty] | 0 | #DIV/0!
Mongla
8 | 201584030-Chila hat-Monumia High School-Katakhali-Joymoni Battola Rd. | [13 empty] | 0 | #DIV/0!
9 | 201584075- Khulna Mongla RHD Gania Bridge to Burirdanga Up Office via Kapalirmat Road. | [13 empty] | 0 | #DIV/0!
Rampal
10 | 201734046-Development of Rajnagar-Gorerdanga Road By HBB. Ch 1000-1970 m. Salvage Cost. TK.226330.00(2nd Call) | KIDRIDP/Bager/W-06/2016-17 | 0.97 | 0 | 0 | 33.34 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 35.83 | 50% | 2018-08-20 |  | 12 | -12 | 33.49% | 1st R/A
11 | 201734033-Improvement of Modnakhali-Khayghat-East Banstali cyclone shelter road Ch500-2000m by HBB Salvage amount Tk.592188.00 Fixed | KDRIDP/Bager/W-43/2017-18 | 1.5 | 0 | 0 | 67.54 | 2017-09-27 | M/S Ziaul & Brothers, Bhandaria, Perojpur | 2017-11-14 | 67.33 | 90% | 2018-11-20 |  | 61.42 | -61.42 | 91.22% | 1st R/A
12 | 201734139-Srifaltala new market-Veternary hospital via sarner field. | [13 empty] | 0 | #DIV/0!
13 | 201734135-Sreefultola bridge - Jahanjhaia Hospatal Road. | [13 empty] | 0 | #DIV/0!
Chitalmari
14 | 201145133-Improvment of HBB Road at Umajuri Pachimpara road-Umajuri Bottala Hasans House Road Ch00-620m. Salvage Cost Tk.-129789.00(fixed) | KDRIDP/Bager/W-30/2017-18 | 0.62 | 0 | 0 | 26.72 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 26.72 | 100% | 2018-07-22 | 26.58 | 26.58 | 0 | 99.48% | Final
15 | 201145115-Improvement of HBB Road at Baburhat Khayaghat Chursta -Hanif Sheks house road. Ch00-510m | KDRIDP/Bager/W-33/2017-18 | 0.51 | 0 | 0 | 18.42 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-11-21 | 18.42 | 100% | 2018-08-27 | 18.42 | 18.42 | 0 | 100% | Final
16 | 201145114-Improvement of Besharkhola (Bottola)-Bottola Abdul Gazi house road via Sultan Chairman road Ch750-1590m by BC | KDRIDP/Bager/W-42/2017-18 | 0.84 | 0 | 0 | 49.346 | 2017-09-25 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-15 | 44.41 | 100% | 2018-11-21 | 44.23 | 44.23 | 0 | 99.59% | Final
17 | 201145116-Improvement of HBB Road at Bottola Khuria AKub Sheks house Katchuria Baser Gazi house road. Ch00-926m. Salvage Cost. TK. -338716.00 | KDRIDP/Bager/W-34/2017-18 | 0.926 | 0 | 0 | 34.41 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 34.39 | 100% | 2018-07-16 | 34.38 | 34.38 | 0 | 99.97% | Final
18 | 201145121-Improvement of Bottola Bazar (Mozam Mistry Bari)- Khuria Motin House Road Ch00-670 m. Salvage Cost-2,31,118.00 | KDRIDP/Bager/W-23/2017-18 | 0.67 | 0 | 0 | 39.58 | 2017-08-17 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-10-09 | 35.62 | 60% | 2018-07-15 |  | 17.51 | -17.51 | 49.16% | 1st R/A
19 | 201145106-Improvement of Babuana of Shantos pur Lararkul Road Lalrarkul primary School Road By HBB. Ch 00-800 m | KDRIDP/Bager/W-61/2017-18 | 0.8 | 0 | 0 | 56.88 | 2018-05-17 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-06-05 | 59.298 | 30% | 2019-06-10 |  | 16.68 | -16.68 | 28.13% | 1st R/A
20 | 201144024-Improvement of HBB Road at KirtonKhali Santoshpur R&H road. Ch. 2875-3235m. Salvage amount tk.1,91,274.00 (fixed) | KDRIDP/Bager/W-32/2017-18 | 0.36 | 0 | 0 | 13.94 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 13.93 | 70% | 2018-07-16 |  |  | 0 | 0%
21 | 201144006-Improvement of Santospur Uttar LararculSantospur primary School road Road By HBB. Ch 1600-2470 m | KDRIDP/Bager/W-60/2017-18 | 0.87 | 0 | 0 | 51.31 | 2017-12-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 55.9 | 60% | 2018-11-11 |  | 39.33 | -39.33 | 70.36% | 2nd R/A
22 | 201144059-Improvement of HBB Road at Kaligonj Bazar-Bashbaria road. Ch00-1260m. Salvage Cost Tk.-356489.00 | KDRIDP/Bager/W-31/2017-18 | 1.26 | 0 | 0 | 53.938 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 53.94 | 100% | 2018-07-22 | 52.83 | 52.83 | 0 | 97.94% | Final
23 | 201145137-Improvement of Bottola Satghor jame Mosque- Motin Sheikh wooden bridge Road By HBB. Ch 00-570 m | KDRIDP/Bager/W-62/2017-18 | 0.57 | 0 | 0 | 46.11 | 2017-12-26 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-02-05 | 48.34 | 50% | 2018-11-11 |  | 37.05 | -37.05 | 76.64% | 2nd R/A
24 | 201145108-Improvement of Umazuri- Kachuria pry. Regd. School- Kachuuria Road by HBB. Ch 00- 2560 m | KDRIDP/Bager/W-57/2017-18 | 2.56 | 0 | 0 | 147.65 | 2017-10-16 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-16 | 147.64 | 80% | 2018-11-22 |  | 78.39 | -78.39 | 53.1% | 1st R/A
25 | 201144029-Kaligonj-Kachuria Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 17.639 | 0 | 0 | 913.359 |  |  |  | 920.568 | 70.71% |  | 176.44 | 438.82 | -262.38 | 47.67%
Construction of Bridge on Upazila Road (7.30m width)
Sharankhola
1 | 201772004-Construction of 42.00m Long RCC Girder Bridge at Amragachia RHD-Banglabazar GC Road at Ch 4200m | KDRIDP/Bager/B-11/2017-18 | 0 | 42 | 0 | 235.666 | [8 empty] | 0 | #DIV/0!
2 | 201772007-Construction of 22.00m Long RCC Girder Bridge at Tafalbari GC- Rasulpur GC- Rajapur GC- Pollanbari RHD Road at Ch 1215m | KDRIDP/Bager/B-08/2017-18 | 0 | 22 | 0 | 183.14 | [8 empty] | 0 | #DIV/0!
Mollahat
3 | 201552009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | [13 empty] | 0 | #DIV/0!
4 | 201562009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | [13 empty] | 0 | #DIV/0!
5 | 201562009-Construction of 30.00m Long RCC Girder Bridge at Gawla-Kodalia Bazar Road at Ch 3300m. | KDRIDP/Bager/B-12/2017-18 | 0 | 30 | 0 | 215.987 | [8 empty] | 0 | #DIV/0!
Rampal
6 | 201732010-Construction of 60.00m Long RCC Girder Bridge on Balai Bridge-Rampal Road at Ch 3940m | KDRIDP/Bager/B-01/2017-18 | 0 | 60 | 0 | 358.53 | 2018-04-10 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-05-23 | 392.51 | 0% | 2019-05-29 |  |  | 0 | 0%
7 | 201732004-Construction of 30.00m Long RCC Girder Bridge on Foyla hat-Chaksree GC Road at Ch 841m | KDRIDP/Bager/B-06/2017-18 | 0 | 30 | 0 | 192.018 | [8 empty] | 0 | #DIV/0!
Mongla
8 | 201582007-Construction of 28.00m Long PSC Girder Bridge on Digiraj-Jhalmalia Dhigi Road at Ch 3980m | KDRIDP/Bager/B-03/2017-18 | 0 | 28 | 0 | 176 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. |  | 190.38 |  |  |  |  | 0 | 0% | NOA issued on 01.07.18
9 | 201582006-Construction of 90.00m Long PSC Girder Bridge on Chaterhat GC-Banshtola GC-Joymonirghol Baddamary Road at Ch 6600m | KDRIDP/Bager/B-05/2017-18 | 0 | 90 | 0 | 569.596 | 2018-04-18 | M/S Abul Kalam Azad, Patuakhali |  | 624.509 |  |  |  |  | 0 | 0% | NOA issued on 16.05.18
Bagerhat Sadar
10 | 201082012-Construction of 42.00m Long RCC Girder Bridge at Chulkath R&H- Faila GC via Ranjeetpur road Sadar Part Road at Ch 6898m. | KDRIDP/Bager/B-13/2017-18 | 0 | 42 | 0 | 232.74 |  |  |  |  | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 344 | 0 | 2163.677 |  |  |  | 1207.399 | 0% |  | 0 | 0 | 0 | 0%
Construction of Bridge on Union Road/Village Road (5.50m width)
Kachua
1 | 201383005-Construction of RCC Bridge on Fatehpur Bazar-Gopalpur UP -Fultala Bazar Road. | [13 empty] | 0 | #DIV/0!
2 | 201384050-Construction of RCC Box culvert 5.00mx3.50m at Ch. 1762m on Charkati-Baruikhali Shosan Ghat | KDRIDP/Bager/W-76/2017-18 | 0 | 5 | 0 | 13.07 | 2017-12-26 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 11.76 | 100% | 2018-10-11 | 11.76 | 11.76 | 0 | 100% | Final
Sharankhola
2 | 201774020-Construction of 30.00m Long RCC Girder Bridge on South Amragachia-Jibanduari Road at Ch 3500m. | KDRIDP/Bager/B-07/2017-18 | 0 | 30 | 0 | 213.51 | [8 empty] | 0 | #DIV/0!
Morrelgonj
3 | 201603021-Construction of 22.00m Long RCC Girder Bridge on Putikhali U.P.-Panchakaran UP via Gazalia bazar Road at Ch 2738m. | KDRIDP/Bager/B-14/2017-18 | 0 | 22 | 0 | 195.2 | [8 empty] | 0 | #DIV/0!
4 | 201605020-Const. of RCC Bridge on Balavadrapur (Badhal Bazar)- Mohonpur Road. | [13 empty] | 0 | #DIV/0!
5 | 201604098-Const. of RCC Bridge on Moslem khan's house - Gharami bari bridge Road. | [13 empty] | 0 | #DIV/0!
6 | 201603006-Construction of 54.00m Long RCC Girder Bridge on Baharbunia U.P-Shonirjore Bazer Near the House of Talukder Mustafizur Rahman Road at Ch 1191m | KDRIDP/Bager/B-09/2017-18 | 0 | 54 | 0 | 306.29 | 2018-06-04 | MKB-MSE (JV), Nalchity, Jhalakati |  | 325 |  |  |  |  | 0 | 0% | NOA issued on 01.07.18
7 | 201605061-Improvement of Sleeper Bridge near RHD north Balvadrapur Shahapara via Tripolli RNGPS. | [13 empty] | 0 | #DIV/0!
Chitalmari
8 | 201143006-Construction of 17.00m Long RCC Girder Bridge on Chinguri hat-Kalatala UP-Banglabazar Road at Ch 8090m. | KDRIDP/Bager/B-10/2017-18 | 0 | 17 | 0 | 141.19 | 2018-05-09 | M/S Kamrul & Brothers, Gopalgonj | 2018-06-25 | 140.999 | 0% | 2019-07-01 |  |  | 0 | 0%
9 | 201144029-Const. of RCC Box Culvert 1vX1.00X1.00m , 2vX4.00X4.00m & 1vX4.30X3.60m at Kaligonj-Kachuria Road | KDRIDP/Bager/W-63/2017-18 | 0 | 13.3 | 0 | 48.27 | 2017-11-13 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2018-01-04 | 43.44 | 75% | 2019-01-10 |  |  | 0 | 0%
10 | 201145121-Const. of RCC Box Culvert 2vX4.00X4.00m over canal at Bottola Bazar9Mozam Mistry Bari)-Khuria Motin House road. | KDRIDP/Bager/W-65/2017-18 | 0 | 8 | 0 | 23.61 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-01-04 | 21.25 | 100% | 2019-01-10 | 21.18 | 21.18 | 0 | 99.67% | Final
Rampal
9 | 201734069-Gourbamha G.C-Konnadubi kheya ghat | [13 empty] | 0 | #DIV/0!
10 | 201734069-Gourbamha G.C-Konnadubi kheya ghat | [13 empty] | 0 | #DIV/0!
Mongla
11 | 201584044-Construction of 22.00m Long RCC Girder Bridge on Holdibunia (Baliar more)-Burburia via Malgazi-Hid office Road at Ch 2900m | KDRIDP/Bager/B-02/2017-18 | 0 | 22 | 0 | 177.85 | 2018-02-20 | M/S Mizan Enterprise, Madaripur | 2018-04-11 | 184.07 | 5% | 2019-04-17 |  |  | 0 | 0%
12 | 201584035-Construction of 25.00m Long PSC Girder Bridge on Banshtala Bridge Pakhimara Khal-Shikari Houst at Burburia Road at Ch 1510m | KDRIDP/Bager/B-04/2017-18 | 0 | 25 | 0 | 196 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. |  | 212.98 |  |  |  |  | 0 | 0% | NOA issued on 01.07.18
Total |  |  | 0 | 196.3 | 0 | 1314.99 |  |  |  | 939.499 | 56% |  | 32.94 | 32.94 | 0 | 3.506%
Maintenance
Bagerhat Sadar
1 | 201083011-Baroipara UP Office -Haderhat bazar via Kartickdia Bazar Rd. | [13 empty] | 0 | #DIV/0!
2 | 201084002 Periodic Maintenance of Dashani(R&H)-Shatgambuj UZR-via Upazila HQ Road from Ch. 2780m-4540m. | KDRIDP/Bager/M-13/2017-18 | 1.76 | 0 | 0 | 33.68 | 2018-04-26 | M/S A. Samad Traders, Sharankhola, Bagerhat | 2018-05-30 | 31.996 | 0% | 2019-06-05 |  |  | 0 | 0%
| 201084048-Periodic Maintenance of Nonadanga-Krishnanagar Road from Ch. 00m-780m. | KDRIDP/Bager/M-13/2017-18 | 0.78 | 0 | 0 | 11.829 |  |  |  | 11.238 |  |  |  |  | 0 | 0%
| 201084087-Periodic Maintenance of Khanpur UP-Uttor Khanpur UHC Road from Ch. 00m-1420m | KDRIDP/Bager/M-13/2017-18 | 1.42 | 0 | 0 | 29.936 |  |  |  | 28.439 |  |  |  |  | 0 | 0%
3 | 201084005 Periodic Maintenance of Mathabhanga R & H-Sukdara bus stand via Sunagar from Ch. 850m-4212m. | KDRIDP/Bager/M-12/2017-18 | 3.36 | 0 | 0 | 51.24 | 2018-04-26 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-05-23 | 48.678 | 0% | 2019-05-29 |  |  | 0 | 0%
| 201084036 Periodic Maintenance of C & B bazar-Shaawliabag mazar Road at H/O Mayor Mr.Tayyab from Ch. 00m-1339m. | KDRIDP/Bager/M-12/2017-18 | 1.339 | 0 | 0 | 28.446 |  |  |  | 27.024 |  |  |  |  | 0 | 0%
| 201084045 Periodic Maintenance of Bagerhat Pallibidyut DC rd-Polghat-Monigonj ferrighat Road from Ch. 00m-1520m. | KDRIDP/Bager/M-12/2017-18 | 1.52 | 0 | 0 | 25.936 |  |  |  | 24.639 |  |  |  |  | 0 | 0%
4 | 201084082-Nowapara Bazar-Baitpur R&H Road. | [13 empty] | 0 | #DIV/0!
Kachua
5 | 201382008-Periodic Maintenance of Maddham Teligati-Malomgacha-Brhmankathi-Kakarbill Kachua Part from Ch. 00m-2233m | KDRIDP/Bager/M-08/2017-18 | 2.233 | 0 | 0 | 41.037 | 2018-04-03 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-04-26 | 38.98 | 10% | 2018-12-17 |  |  | 0 | 0%
6 | 201383005-Periodic Maintenance of Fatehpur bazar-Gopalpur UP-Fultala bazar Road from Ch. 2584m-4794m & 7100m-8086m. | KDRIDP/Bager/M-09/2017-18 | 3.196 | 0 | 0 | 47.02 | 2018-04-04 | M/S Mou Enterprise, Kharder, Bagerhat | 2018-08-05 | 44.67 | 0% | 2018-12-30 |  |  | 0 | 0%
7 | 201383006.Gopulpur UP-Natunhat Bazar Road | [13 empty] | 0 | #DIV/0!
8 | 201383007.Kachua UP-Natun hat bazar | [13 empty] | 0 | #DIV/0!
9 | 201383008-Periodic Maintenance of Badhal UP-Atharogati bazar Road from Ch. 00m-915m | KDRIDP/Bager/M-10/2017-18 | 0.915 | 0 | 0 | 17.339 | 2018-04-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-04-26 | 16.47 | 10% | 2018-12-17 |  |  | 0 | 0%
10 | 201383010-Dhopakhali UP-Lararhat via Madhopkati Rd. | [13 empty] | 0 | #DIV/0!
11 | 201384013-Periodic Maintenance of Goalmath-Jessordi End Panbaria Road from Ch. 00m-310m | KDRIDP/Bager/M-11/2017-18 | 0.31 | 0 | 0 | 7.273 | [8 empty] | 0 | #DIV/0!
12 | 201384014-Kachua-Badhal FRB to Tagrakhal river Ghat (Football field) Road. | [13 empty] | 0 | #DIV/0!
13 | 201384120.Hazarkhali Bazar-Joygashi Taleshwar Road | [13 empty] | 0 | #DIV/0!
Sharankhola
14 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Road | [13 empty] | 0 | #DIV/0!
15 | 201774016-Periodic Maintenance of Baniakhali GC-Pollanbari RHD via B-Dhansagar Community Clinic Delower house Sharankhola part Road from Ch. 1500m-3500m. | KDRIDP/Bager/M-06/2017-18 | 2 | 0 | 0 | 30.03 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 29.805 | 10% | 2019-01-17 | 29.81 | 29.81 | 0 | 100% | Final
16 | 201774023: Periodic Maintenance of Khada- Lakurtala Road from Ch. 00m-1350m | KDRIDP/Bager/M-07/2017-18 | 1.35 | 0 | 0 | 20.09 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 19.918 | 10% | 2019-01-17 | 18.93 | 18.93 | 0 | 95.04% | Final
17 | 201774024: Banglabazar-Tafalbari-Mourashi Road | [13 empty] | 0 | #DIV/0!
Mollahat
18 | 201552008-Harida More-Machuarkul Rd. | [13 empty] | 0 | #DIV/0!
19 | 201552009-Gawla-Kadalia Bazar Rd. | [13 empty] | 0 | #DIV/0!
20 | 201553007-Kulia UP-Nagarkandi GC R | [13 empty] | 0 | #DIV/0!
21 | 201564020 - Periodic Maintenance of Moupura-Singati Road from Ch. 00m-2500m | KDRIDP/Bager/M-03/2017-18 | 2.5 | 0 | 0 | 41.48 | 2018-02-24 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 37.33 | 80% | 2019-01-11 |  | 30 | -30 | 80.36% | 1st R/A
22 | 201564002 - Periodic Maintenance of Mollarkul hat-Mollarkul Govt. Pry. School Road from Ch. 00m-1000m | KDRIDP/Bager/M-05/2017-18 | 1 | 0 | 0 | 18.47 | 2018-02-25 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 16.62 | 100% | 2019-01-11 | 16.62 | 16.62 | 0 | 100% | Final
23 | 201563005 - Periodic Maintenance of Joydehihat-Kulia U.P Office Road from Ch. 00m-1000m | KDRIDP/Bager/M-01/2017-18 | 1 | 0 | 0 | 22.22 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20 | 100% | 2019-01-11 | 20 | 20 | 0 | 100% | Final
24 | 201564028 - Periodic Maintenance of Mollahat Hospital -Derbolia RHD Road from Ch. 00m-695m | KDRIDP/Bager/M-02/2017-18 | 0.695 | 0 | 0 | 22.75 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20.47 | 0% | 2019-01-11 |  |  | 0 | 0%
25 | 201565017 - Periodic Maintenance of Kahalpur Alek house-Kutimia house Road from Ch. 00m-1150m | KDRIDP/Bager/M-04/2017-18 | 1.15 | 0 | 0 | 17.26 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 15.53 | 30% | 2019-01-11 |  |  | 0 | 0%
Chitalmari
26 | 201143006-Chigurihat -Kalatola UP-BanglabazarRd. | [13 empty] | 0 | #DIV/0!
Rampal
27 | 201732015-Periodic Maintenance of Tatulia bridge-Kadirkhola Road from Ch. 00m-1185m | KDRIDP/Bager/M-14/2017-18 | 1.185 | 0 | 0 | 22.237 | [8 empty] | 0 | #DIV/0!
| 201733009-Periodic Maintenance of Perikhali GC-Hurka UP Road from Ch. 00m-1860m |  | 1.86 | 0 | 0 | 89.992 | [8 empty] | 0 | #DIV/0!
28 | 201733005-Perikhali GC -Bhojpatia UP Office | [13 empty] | 0 | #DIV/0!
29 | 201734054-Ronsan-Mirakhali Road | [13 empty] | 0 | #DIV/0!
30 | 201734104-Banshtali UP-Solakora | [13 empty] | 0 | #DIV/0!
Mongla
31 | 201582007-Digraj-Jholmolia Dhige Rd | [13 empty] | 0 | #DIV/0!
32 | 201583002-Burirdangahat Sonailtala up Office Rd. | [13 empty] | 0 | #DIV/0!
33 | 201583007-Khanjahanalihat RHD Gazir Bridge Road. | [13 empty] | 0 | #DIV/0!
Fakirhat
34 | 201344001-Maintenance of Fakirhat L.S.D Godown-singgaty road. | [13 empty] | 0 | #DIV/0!
35 | 201344009 Lockpur Ballata-Bollopur village road | [13 empty] | 0 | #DIV/0!
36 | 201344024-Maintenance of Singati Gilatala road upto C&B Bazer Road. | [13 empty] | 0 | #DIV/0!
37 | 201344025-Maintenance of Katkhali R&H-Baintala Kheya Ghat Rd. | [13 empty] | 0 | #DIV/0!
Morrelgonj
38 | 201603007 - Banagrame Bazar-Hoglapasha U.P. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
39 | 201604059 - Sannashi Launch ghat-Chairmanbazar-(Sannashi Bazer) Pallimangal C&B road | [13 empty] | 0 | #DIV/0!
Total |  |  | 29.573 | 0 | 0 | 578.265 |  |  |  | 431.807 | 26.92% |  | 85.36 | 115.36 | -30 | 26.72%
GC-Hat
Sharankhola
1 | Construction of Banglabazar Growth Center | KDRIDP/Bager/GC-04/2017-18 | 0 | 0 | 1 | 19.45 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. |  | 18.615 |  |  |  |  | 0 | 0% | NOA issued on 07.03.18
Mollahat
2 | Construction of Nagarkandi Growth Center | KDRIDP/Bager/GC-05/2017-18 | 0 | 0 | 1 | 20.52 | 2018-02-08 | M/S Kamrul & Brothers, Gopalgonj | 2018-04-05 | 18.467 | 0% | 2019-01-11 |  |  | 0 | 0%
Rampal
3 | Construction of Foylahat Growth Center | KDRIDP/Bager/GC-06/2017-18 | 0 | 0 | 1 | 21.55 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-03-28 | 20.889 | 0% | 2019-01-03 |  |  | 0 | 0%
Mongla
4 | Construction of Mithakhali Growth Center | KDRIDP/Bager/GC-07/2017-18 | 0 | 0 | 1 | 19.38 | 2018-02-08 | M/S Sk. Nurul Amin, Mongla, Bagerhat | 2018-03-28 | 20.29 | 0% | 2019-01-31 |  |  | 0 | 0%
Chitalmari
5 | Construction of Saildah Growth Center | KDRIDP/Bager/GC-08/2017-18 | 0 | 0 | 1 | 20.43 | 2018-02-08 | M/S S.S. Traders, Tungipara, Gopalgonj | 2018-03-19 | 18.387 | 20% | 2018-12-26 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 5 | 101.33 |  |  |  | 96.648 | 5% |  | 0 | 0 | 0 | 0%
Landing/ Riverghat
Sharankhola
1 | Rayenda Bandaghataghat | [13 empty] | 0 | #DIV/0!
2 | Construction of Tafalbari GC Ghat | KDRIDP/Bager/G-11/2017-18 | 0 | 0 | 1 | 17.25 | 2017-12-27 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-02-19 | 16.23 | 0% | 2018-11-25 |  |  | 0 | 0% | NOA issued on 22.01.18
3 | Construction of Udaypur Ghat | KDRIDP/Bager/G-09/2017-18 | 0 | 0 | 1 | 24.598 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 22.14 | 0% | 2018-11-12 |  |  | 0 | 0%
4 | Construction of Udaypur Gholarchak Madrasa Ghat | KDRIDP/Bager/G-10/2017-18 | 0 | 0 | 1 | 12.58 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 11.32 | 0% | 2018-11-12 |  |  | 0 | 0%
Morrelgonj
5 | Amtoli Bazar Khal | KDRlDP/Bager/G-01/2017-18 | 0 | 0 | 1 | 17.04 | 2017-11-29 | M/S Shikto Enterprise, Zianagar, Perojpur. | 2018-01-21 | 16.65 | 100% | 2018-10-27 |  | 13 | -13 | 78.08% | 1st R/A
6 | Sannasi Bazar Khal | KDRlDP/Bager/G-03/2017-18 | 0 | 0 | 1 | 25.78 | 2017-11-30 | M/S Shanta & Brothers, Basabati, Bagerhat. | 2018-02-05 | 24.98 | 10% | 2018-11-11 |  |  | 0 | 0%
7 | Bisharighata Bazar Khal | KDRlDP/Bager/G-02/2017-18 | 0 | 0 | 1 | 19.64 | 2018-01-25 | N & S brothers, College Road, Morrelgonj, Bagerhat | 2018-03-07 | 20.3 | 40% | 2018-07-13 |  | 9.4 | -9.4 | 46.31% | 1st R/A
Rampal
8 | Construction of Kaligonj Khaya Ghat | KDRIDP/Bager/G-12/2017-18 | 0 | 0 | 1 | 21.59 | [8 empty] | 0 | #DIV/0!
9 | Construction of Dakra Khaya Ghat | KDRIDP/Bager/G-13/2017-18 | 0 | 0 | 1 | 20.33 | [8 empty] | 0 | #DIV/0!
Mongla
10 | Digraj Kheyaghat | KDRIDP/Bager/G-05/20 17-18 | 0 | 0 | 1 | 17.77 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 17.53 | 0% | 2018-11-06 |  |  | 0 | 0%
11 | Chila Growth Center Ghat | KDRIDP/Bager/G-04/2017-18 | 0 | 0 | 1 | 20.41 | 2017-11-29 | M/S Antar Enterprise, Mongla, Bagerhat. | 2018-02-01 | 20.37 | 30% | 2018-11-06 |  | 8.36 | -8.36 | 41.04%
Chitalmari
12 | Construction of RCC Ghatla at Khaserhat GC | KDRIDP/Bager/G-08/2017-18 | 0 | 0 | 1 | 15.28 | 2017-12-27 | M/S Muzahidul Islam, Gopalgonj | 2018-02-15 | 13.75 | 0% | 2018-10-21 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 11 | 212.268 |  |  |  | 163.27 | 20% |  | 0 | 30.76 | -30.76 | 18.84%
Tree Plantation
Bagerhat Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kachua
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Sharankhola
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Morrelgonj
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Fakirhat
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Mollahat
6 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Chitalmari
7 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Rampal
8 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Mongla
9 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 170.644 | 540.3 | 16 | 13771.503 |  |  |  | 11024.232 | 29.93% |  | 1285.756 | 2774.996 | -1489.24 | 25.17%
|  |  | 170.644 | 540.3 | 16 | 13771.503 |  |  |  | 11024.232 | 15.77% |  | 1285.756 | 2774.996 | -1489.24 | 25.17%

## Mollahat
Mollahat
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201562008-Harida more- Machuarkul Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201562009-Gawla-Kodalia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201562010-Ghoradair -Kachna Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 201563004-Improvement of Kodalia U.P Office- Aruadehi hat road ch.1400-3480m | KDRIDP/Bager/W-71/2017-18 | 2.08 | 0 | 0 | 151.85 | 2018-02-07 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-03-21 | 136.66 | 0% | 2019-03-27 | 0 | 0 | 0 | 0% | 0
5 | 201563006-Gaula UP-Chanderhat-Faltita Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201563007-Kulia Up-Nagarkandi GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201563008 - Singgati hat-Chunkhola UP H/Q | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201563009-Mollarkul Bazar-Udyapur UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 201564022-Kahalpur RHD-Joydehihat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201564090 - Improvement of Singati-Capil Bridge Road. Ch 500-920 m Under Mollahat Upazila Bagerhat. | KDRIDP/Bager/W-39/2017-18 | 0.42 | 0 | 0 | 26.66 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 23.996 | 70% | 2018-11-21 | 0 | 10 | -10 | 41.67% | 1st R/A
11 | 201564005 - Boaliahat-Kahalpur R&H Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201564007 - Improvement of Rajpat - Gaola UP Road. Ch 1062-2900 m. Salvage Cost. TK. 1386398.00 | KDRIDP/Bager/W-38/2017-18 | 1.838 | 0 | 0 | 111.297 | 2017-09-28 | M/S Rubel Enterprise, Rajoir, Madaripur | 2017-11-15 | 100.167 | 70% | 2018-11-21 | 0 | 55.43 | -55.43 | 55.34% | 2nd R/A
13 | 201564013 - Charkuliahat-Takiarkul road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201564016 - Atjuri UP-Kadamtala Kheyaghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201564039 - Boalia RHD-Bhandarkhola hat(Atjuri UP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201564047 - Improvement of Garfa- Girishnagar-Kadamtala Khayaghat Road. Ch 4100-4900 m Under Mollahat Upazila Bagerhat. Salvage Cost. TK. 114374.00 | KDRIDP/Bager/W-40/2017-18 | 0.8 | 0 | 0 | 46.965 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 42.27 | 100% | 2018-11-21 | 42.26 | 42.26 | 0 | 99.98% | Final
17 | 201565009 - Improvement of Chaulturi-Kodalia Bill Road. Ch 880-2255 m | KDRIDP/Bager/W-41/2017-18 | 1.375 | 0 | 0 | 77.9 | 2017-09-27 | Shikder Zahidul Islam, Mollahat, Bagerhat. | 2017-11-15 | 70.11 | 60% | 2018-11-21 | 0 | 36.42 | -36.42 | 51.95% | 2nd R/A
18 | 201565079 - Shason Sobed Molla House-Jamai More Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 201565017 - Kahalpur Alek house-Kutimia house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201565018 - Kahalpur Barapukurpar-Kahalpur H/School via Omar Moulana House | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201565022 - Kahalpur Charpara Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 201564096-Uddaypur Uttar kandy Pacca road-Uddaypur Uttar Kandy GPS-Uttar kandy Graveyard with link of H/O Kamal Molla road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
23 | 201552009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 201562009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201562009-Construction of 30.00m Long RCC Girder Bridge at Gawla-Kodalia Bazar Road at Ch 3300m. | KDRIDP/Bager/B-12/2017-18 | 0 | 30 | 0 | 215.987 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
26 | 201552008-Harida More-Machuarkul Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201552009-Gawla-Kadalia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 201553007-Kulia UP-Nagarkandi GC R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 201564020 - Periodic Maintenance of Moupura-Singati Road from Ch. 00m-2500m | KDRIDP/Bager/M-03/2017-18 | 2.5 | 0 | 0 | 41.48 | 2018-02-24 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 37.33 | 80% | 2019-01-11 | 0 | 30 | -30 | 80.36% | 1st R/A
30 | 201564002 - Periodic Maintenance of Mollarkul hat-Mollarkul Govt. Pry. School Road from Ch. 00m-1000m | KDRIDP/Bager/M-05/2017-18 | 1 | 0 | 0 | 18.47 | 2018-02-25 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 16.62 | 100% | 2019-01-11 | 16.62 | 16.62 | 0 | 100% | Final
31 | 201563005 - Periodic Maintenance of Joydehihat-Kulia U.P Office Road from Ch. 00m-1000m | KDRIDP/Bager/M-01/2017-18 | 1 | 0 | 0 | 22.22 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20 | 100% | 2019-01-11 | 20 | 20 | 0 | 100% | Final
32 | 201564028 - Periodic Maintenance of Mollahat Hospital -Derbolia RHD Road from Ch. 00m-695m | KDRIDP/Bager/M-02/2017-18 | 0.695 | 0 | 0 | 22.75 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20.47 | 0% | 2019-01-11 | 0 | 0 | 0 | 0% | 0
33 | 201565017 - Periodic Maintenance of Kahalpur Alek house-Kutimia house Road from Ch. 00m-1150m | KDRIDP/Bager/M-04/2017-18 | 1.15 | 0 | 0 | 17.26 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 15.53 | 30% | 2019-01-11 | 0 | 0 | 0 | 0% | 0
GC-Hat
34 | Construction of Nagarkandi Growth Center | KDRIDP/Bager/GC-05/2017-18 | 0 | 0 | 1 | 20.52 | 2018-02-08 | M/S Kamrul & Brothers, Gopalgonj | 2018-04-05 | 18.467 | 0% | 2019-01-11 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
35 | Construction of Udaypur Ghat | KDRIDP/Bager/G-09/2017-18 | 0 | 0 | 1 | 24.598 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 22.14 | 0% | 2018-11-12 | 0 | 0 | 0 | 0% | 0
36 | Construction of Udaypur Gholarchak Madrasa Ghat | KDRIDP/Bager/G-10/2017-18 | 0 | 0 | 1 | 12.58 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 11.32 | 0% | 2018-11-12 | 0 | 0 | 0 | 0% | 0
Tree Plantation
37 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 12.858 | 30 | 3 | 810.537 |  |  |  | 535.08 | 16.49% |  | 78.88 | 210.73 | -131.85 | 39.38%

## Fakirhat
Fakirhat
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201342013 Lokhpur GC-Dhaka Khulna RHD (Nowapara More) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
2 | 201343005-Singati Bazar-Piljong UP-Balir Dokan-Shambagat RHD. | KDRIDP/Bager/W-25/2017-18 | 1.02 | 0 | 0 | 64.92 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 60.65 | 55% | 2018-07-18 | 0 | 39.59 | -39.59 | 65.28% | 1st R/A
3 | 201343001-Fakirhat H/Q-Naldah Maubhog UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 201343006 Upazila H/Q(Livestock Office)-Satsika-Baliadanga-Rakhalgachi UP (Fakirhat Part | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 201343011 - Mulgor UP-Nalda Moubog UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 201344004- Khulna Mollahat R&H at Talerpukur pagla deapara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201344008-Improvement of Khazura R &H-Bolloppur Road. Ch1194-2650m. Salvage Cost-103999.00(fixed) | KDRIDP/Bager/W-24/2017-18 | 1.456 | 0 | 0 | 84.83 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 79.3 | 45% | 2018-07-18 | 0 | 36.62 | -36.62 | 46.18% | 0
8 | 201344009-Lockpur Ballata-Bollopur village rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201344013- Shibbari-Dohor Moubog Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201344014- Mollar bazar-Bangopar bazar via Tekatia road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201344018 - Betaga bazar-pasur river via Chakuli Pry.school road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201344024 - Singati Gilatala road upto C&B Bazer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201344026 - Kanarpukur-Deapara Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201344042 - Singati-Baliadanga road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201344061- Nawapara Baloyer Dokan-Syambagat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201344088-Kanarpukur-Satshikha Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
17 | 201344006-Bahirdia-satbaria road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201344088-Bahirdia UP office to Weast Bahirdia GPS Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
19 | 201344001-Maintenance of Fakirhat L.S.D Godown-singgaty road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201344009 Lockpur Ballata-Bollopur village road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201344024-Maintenance of Singati Gilatala road upto C&B Bazer Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 201344025-Maintenance of Katkhali R&H-Baintala Kheya Ghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
23 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 2.476 | 0 | 0 | 149.75 |  |  |  | 139.95 | 4.348% |  | 0 | 76.21 | -76.21 | 54.46%

## Chitalmari
Chitalmari
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 201143001 - Chitalmari-Hizla UP-Kalatola UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201143006-Chinguri hat-Kalatala UP-Banglabazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201143007 - Saildah hat-Kalatala UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
4 | 201144020-Kirtankhali - Kharamkhali road (via Khasherhat GC) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 201144011 - Development of Moidah Shibpur Club- Kaligati Road. Ch 00-878. Salvage Cost TK. 404704.00 | KDRIDP/Bager/W-15/2016-17 | 0.878 | 0 | 0 | 61.46 | 2017-07-10 | M/S S.S. Traders, Tungipara, Gopalgonj | 2017-08-24 | 59.92 | 100% | 2018-08-30 | 59.87 | 59.87 | 0 | 99.92% | Final
6 | 201144023 - Chinguri kheaghat-Krishi Bank-Kalatala road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201144032 - Development of Khaserhat- Asoknagar Road. Ch 2300-4595 m. Salvage Cost TK. 433415.00 | KDRIDP/Bager/W-13/2016-17 | 2.295 | 0 | 0 | 147.91 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 143.47 | 60% | 2018-08-29 | 0 | 91.31 | -91.31 | 63.64% | 1st R/A
8 | 201144033-Development of Shampara- Kudari via Panchpara Hat Road. Ch 1000-2550 m. Salvage Cost TK. 796234.00 | KDRIDP/Bager/W-12/2016-17 | 1.55 | 0 | 0 | 140.03 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 135.17 | 50% | 2018-08-29 | 0 | 48.34 | -48.34 | 35.76% | 1st R/A
9 | 201144049-Development of Barobaria at RHD Road-Ghola High School-Baroguni bazar Road. Ch 00-1700 m. Salvage Cost TK. 261420.00 | KDRIDP/Bager/W-14/2016-17 | 1.7 | 0 | 0 | 105.59 | 2017-07-10 | Md. Iqbal Hossain, Tungipara, Gopalgonj. | 2017-08-06 | 101.05 | 60% | 2018-08-29 | 0 | 49.8 | -49.8 | 49.28% | 0
10 | 201145027-Improvement of Hizla Sheikpara- Agakhal RPS Road. Ch 00 -1275m. Salvage Cost TK. 618000.00 | KDRIDP/Bager/W-64/2017-18 | 1.275 | 0 | 0 | 103.13 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-02-06 | 92.82 | 30% | 2019-02-12 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by HBB
11 | 201145133-Improvment of HBB Road at Umajuri Pachimpara road-Umajuri Bottala Hasans House Road Ch00-620m. Salvage Cost Tk.-129789.00(fixed) | KDRIDP/Bager/W-30/2017-18 | 0.62 | 0 | 0 | 26.72 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 26.72 | 100% | 2018-07-22 | 26.58 | 26.58 | 0 | 99.48% | Final
12 | 201145115-Improvement of HBB Road at Baburhat Khayaghat Chursta -Hanif Sheks house road. Ch00-510m | KDRIDP/Bager/W-33/2017-18 | 0.51 | 0 | 0 | 18.42 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-11-21 | 18.42 | 100% | 2018-08-27 | 18.42 | 18.42 | 0 | 100% | Final
13 | 201145114-Improvement of Besharkhola (Bottola)-Bottola Abdul Gazi house road via Sultan Chairman road Ch750-1590m by BC | KDRIDP/Bager/W-42/2017-18 | 0.84 | 0 | 0 | 49.346 | 2017-09-25 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-15 | 44.41 | 100% | 2018-11-21 | 44.23 | 44.23 | 0 | 99.59% | Final
14 | 201145116-Improvement of HBB Road at Bottola Khuria AKub Sheks house Katchuria Baser Gazi house road. Ch00-926m. Salvage Cost. TK. -338716.00 | KDRIDP/Bager/W-34/2017-18 | 0.926 | 0 | 0 | 34.41 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 34.39 | 100% | 2018-07-16 | 34.38 | 34.38 | 0 | 99.97% | Final
15 | 201145121-Improvement of Bottola Bazar (Mozam Mistry Bari)- Khuria Motin House Road Ch00-670 m. Salvage Cost-2,31,118.00 | KDRIDP/Bager/W-23/2017-18 | 0.67 | 0 | 0 | 39.58 | 2017-08-17 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-10-09 | 35.62 | 60% | 2018-07-15 | 0 | 17.51 | -17.51 | 49.16% | 1st R/A
16 | 201145106-Improvement of Babuana of Shantos pur Lararkul Road Lalrarkul primary School Road By HBB. Ch 00-800 m | KDRIDP/Bager/W-61/2017-18 | 0.8 | 0 | 0 | 56.88 | 2018-05-17 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-06-05 | 59.298 | 30% | 2019-06-10 | 0 | 16.68 | -16.68 | 28.13% | 1st R/A
17 | 201144024-Improvement of HBB Road at KirtonKhali Santoshpur R&H road. Ch. 2875-3235m. Salvage amount tk.1,91,274.00 (fixed) | KDRIDP/Bager/W-32/2017-18 | 0.36 | 0 | 0 | 13.94 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 13.93 | 70% | 2018-07-16 | 0 | 0 | 0 | 0% | 0
18 | 201144006-Improvement of Santospur Uttar LararculSantospur primary School road Road By HBB. Ch 1600-2470 m | KDRIDP/Bager/W-60/2017-18 | 0.87 | 0 | 0 | 51.31 | 2017-12-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 55.9 | 60% | 2018-11-11 | 0 | 39.33 | -39.33 | 70.36% | 2nd R/A
19 | 201144059-Improvement of HBB Road at Kaligonj Bazar-Bashbaria road. Ch00-1260m. Salvage Cost Tk.-356489.00 | KDRIDP/Bager/W-31/2017-18 | 1.26 | 0 | 0 | 53.938 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 53.94 | 100% | 2018-07-22 | 52.83 | 52.83 | 0 | 97.94% | Final
20 | 201145137-Improvement of Bottola Satghor jame Mosque- Motin Sheikh wooden bridge Road By HBB. Ch 00-570 m | KDRIDP/Bager/W-62/2017-18 | 0.57 | 0 | 0 | 46.11 | 2017-12-26 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-02-05 | 48.34 | 50% | 2018-11-11 | 0 | 37.05 | -37.05 | 76.64% | 2nd R/A
21 | 201145108-Improvement of Umazuri- Kachuria pry. Regd. School- Kachuuria Road by HBB. Ch 00- 2560 m | KDRIDP/Bager/W-57/2017-18 | 2.56 | 0 | 0 | 147.65 | 2017-10-16 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-16 | 147.64 | 80% | 2018-11-22 | 0 | 78.39 | -78.39 | 53.1% | 1st R/A
22 | 201144029-Kaligonj-Kachuria Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
23 | 201143006-Construction of 17.00m Long RCC Girder Bridge on Chinguri hat-Kalatala UP-Banglabazar Road at Ch 8090m. | KDRIDP/Bager/B-10/2017-18 | 0 | 17 | 0 | 141.19 | 2018-05-09 | M/S Kamrul & Brothers, Gopalgonj | 2018-06-25 | 140.999 | 0% | 2019-07-01 | 0 | 0 | 0 | 0% | 0
24 | 201144029-Const. of RCC Box Culvert 1vX1.00X1.00m , 2vX4.00X4.00m & 1vX4.30X3.60m at Kaligonj-Kachuria Road | KDRIDP/Bager/W-63/2017-18 | 0 | 13.3 | 0 | 48.27 | 2017-11-13 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2018-01-04 | 43.44 | 75% | 2019-01-10 | 0 | 0 | 0 | 0% | 0
25 | 201145121-Const. of RCC Box Culvert 2vX4.00X4.00m over canal at Bottola Bazar9Mozam Mistry Bari)-Khuria Motin House road. | KDRIDP/Bager/W-65/2017-18 | 0 | 8 | 0 | 23.61 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-01-04 | 21.25 | 100% | 2019-01-10 | 21.18 | 21.18 | 0 | 99.67% | Final
Maintenance
24 | 201143006-Chigurihat -Kalatola UP-BanglabazarRd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
25 | Construction of Saildah Growth Center | KDRIDP/Bager/GC-08/2017-18 | 0 | 0 | 1 | 20.43 | 2018-02-08 | M/S S.S. Traders, Tungipara, Gopalgonj | 2018-03-19 | 18.387 | 20% | 2018-12-26 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
26 | Construction of RCC Ghatla at Khaserhat GC | KDRIDP/Bager/G-08/2017-18 | 0 | 0 | 1 | 15.28 | 2017-12-27 | M/S Muzahidul Islam, Gopalgonj | 2018-02-15 | 13.75 | 0% | 2018-10-21 | 0 | 0 | 0 | 0% | 0
Tree Plantation
27 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 17.684 | 38.3 | 2 | 1345.204 |  |  |  | 1308.864 | 46.38% |  | 257.49 | 635.9 | -378.41 | 48.58%

## Bagerhat Sadar
Bagerhat Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 201083011 Bishnapur UP-Bakerganj bazar.(sadar portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201083012 Baroipara UP office-Ujalpur bazar via Kafurpura school road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201083017 Improvement of Chulkathi bazar-Betaga UP Road Sadar Portion Ch00-1476. ID No-201083017 Salvage amount tk. 157003. fixed | KDRIDP/Bager/W-35/2017-18 | 1.476 | 0 | 0 | 87.09 | 2017-09-11 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 91.08 | 100% | 2018-07-22 | 91.06 | 91.06 | 0 | 99.98% | Final
4 | 201083018-Bemorta UP(At Fatepur)-Bottala bazar via Bijoypur. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 201083019-Bishnapur UP-Kandapara GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201083022-Karapara UP office to Karapara bazar via Magnitala bazar rd.. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
7 | 201084001-South Khanpur-Taterhat-Ranjeetpur.(start from Ranjeetpur Asrayan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201084011-B.Sc High school-Laksmikhali BWDB-Chaksree(Kalibari) hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201084017-Patorpara-Karapra road(Add.CE R&H dept). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201084018-Patilakhali-Nataikhali road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201084019-Kandapara GC(Parnowapara)-Betkhali bazar-Taleswar bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201084024-Zindapir mazar-Khanjahan Ali mazar with link of nine gambuj mosque. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201084038-Haderhat bazar-Bakhergonj bazar via singa kheyaghat WDB road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201084040-Monigonj-Gopalkati-Bishnapur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201084067-Chapatola (H/O Amin)-Jattrapur govt. pri. School | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201084074-Rakhalgachi UP-Chulkathi bazar via Ranjeetpur. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 201085010-Doritaluk Rd-Bagmara Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201085288-Chaparkul –Bakarganj bazar via khalispur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 201085039-Bara Bansh Baria road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201085044-Bara Bansh High school | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201084046- Improvement of Jattrapur at UZR- Komorpur via Afra Mowmachi Palon project & Murshidpur Ch00-2151m. Salvage Amount tk.-592374 fixed | KDRIDP/Bager/W-36/2017-18 | 2.151 | 0 | 0 | 127.185 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 133.33 | 100% | 2018-08-30 | 133.31 | 133.31 | 0 | 99.98% | Final
22 | 201084040-Improvement of Monigonj- Gopalkati- Bishnapur Road from Ch. 823m-1658m. Salvage Cost Tk. 1642597.00 | KDRIDP/Bager/W-78/2017-18 | 0.835 | 0 | 0 | 85.79 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Request sent to HQ for cancellation.
23 | 201085013-Keshobpur Charogram-Kondola-Talswar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 201085191-Improvement of Hakimpur Pry. School-Chandromahel road Ch 995-1845m. Salvage amount tk. 246687.00 fixed | KDRIDP/Bager/W-37/2017-18 | 0.85 | 0 | 0 | 60.78 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 63.72 | 100% | 2018-08-30 | 63.66 | 63.66 | 0 | 99.91% | Final
25 | 201084069-West Saera Bazar-Sree Ghat Bazar via Sadullahpur road. | KDRIDP/Bager/W-16/2016-17 | 0.702 | 0 | 0 | 41.58 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-13 | 43.56 | 100% | 2018-08-19 | 43.553 | 43.553 | 0 | 99.98% | Final
26 | 201085234-Rangeetpur-Southpara via Morralpara Tater hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201085238-Development of Ranjitpur- Guchegram- Morolpara- Surjamukhi Club Road. Ch 00-821 m. Salvage Cost Tk.145827.00 | KDRIDP/Bager/W-10/2016-17 | 0.821 | 0 | 0 | 49.28 | 2017-06-14 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-07-26 | 51.69 | 100% | 2018-05-29 | 51.65 | 51.65 | 0 | 99.92% | Final
28 | 201085040- Improvement of PC Dema Pucca Road-Mallik bari Road CH00-350M. Salvage amount 176715.00 fixed | KDRIDP/Bager/W-58/2017-18 | 0.35 | 0 | 0 | 20.11 | 2017-10-26 | M/S S.S. Brothers, 18, Sarker lane, Tootpara, Khulna. | 2017-12-12 | 21.11 | 60% | 2018-06-18 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Upazila Road (7.30m width)
29 | 201082012-Construction of 42.00m Long RCC Girder Bridge at Chulkath R&H- Faila GC via Ranjeetpur road Sadar Part Road at Ch 6898m. | KDRIDP/Bager/B-13/2017-18 | 0 | 42 | 0 | 232.74 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
30 | 201083011-Baroipara UP Office -Haderhat bazar via Kartickdia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 201084002 Periodic Maintenance of Dashani(R&H)-Shatgambuj UZR-via Upazila HQ Road from Ch. 2780m-4540m. | KDRIDP/Bager/M-13/2017-18 | 1.76 | 0 | 0 | 33.68 | 2018-04-26 | M/S A. Samad Traders, Sharankhola, Bagerhat | 2018-05-30 | 31.996 | 0% | 2019-06-05 | 0 | 0 | 0 | 0% | 0
| 201084048-Periodic Maintenance of Nonadanga-Krishnanagar Road from Ch. 00m-780m. |  | 0.78 | 0 | 0 | 11.829 |  |  |  | 11.238 |  |  | 0 | 0 | 0 | 0% | 0
| 201084087-Periodic Maintenance of Khanpur UP-Uttor Khanpur UHC Road from Ch. 00m-1420m |  | 1.42 | 0 | 0 | 29.936 |  |  |  | 28.439 |  |  | 0 | 0 | 0 | 0% | 0
32 | 201084005 Periodic Maintenance of Mathabhanga R & H-Sukdara bus stand via Sunagar from Ch. 850m-4212m. | KDRIDP/Bager/M-12/2017-18 | 3.36 | 0 | 0 | 51.24 | 2018-04-26 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-05-23 | 48.678 | 0% | 2019-05-29 | 0 | 0 | 0 | 0% | 0
| 201084036 Periodic Maintenance of C & B bazar-Shaawliabag mazar Road at H/O Mayor Mr.Tayyab from Ch. 00m-1339m. |  | 1.339 | 0 | 0 | 28.446 |  |  |  | 27.024 |  |  | 0 | 0 | 0 | 0% | 0
| 201084045 Periodic Maintenance of Bagerhat Pallibidyut DC rd-Polghat-Monigonj ferrighat Road from Ch. 00m-1520m. |  | 1.52 | 0 | 0 | 25.936 |  |  |  | 24.639 |  |  | 0 | 0 | 0 | 0% | 0
33 | 201084082-Nowapara Bazar-Baitpur R&H Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
34 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 17.364 | 42 | 0 | 885.622 |  |  |  | 576.504 | 16.47% |  | 383.233 | 383.233 | 0 | 66.48%

## Kachua
Kachua
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 201383004-Improvement of Dhopakhali UP-Madertola bazar House Road by BC at Ch.987m-1881m. Salvage Amount Tk. 15,94,676.00 | KDRIDP/Bager/W-84/2017-18 | 0.894 | 0 | 0 | 64.787 | 2018-05-17 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-06-05 | 68.026 | 0% | 0 | 0 | 0 | 0 | 0% | 0
| 201383009-Improvement of Kachua UP-Talwshwer bazar Road by BC at Ch.00m-1143m & 2961m-3600m. Salvage Amount Tk. 22,87,655.00 |  | 1.782 | 0 | 0 | 123.059 |  |  |  | 129.21 |  |  | 0 | 0 | 0 | 0% | 0
2 | 201383005-Improvement of Fatehpur bazar-Gopalpur UP- Fultala bazar Road. Ch4794-5353 m & 6300-7100 m. Salvage Cost Tk. 1345002.00 | KDRIDP/Bager/W-48/2017-18 | 1.359 | 0 | 0 | 83.459 | 2017-12-04 | M/S Sonia Enterprise, Nagerbazar, Bagerhat | 2018-02-05 | 87.15 | 50% | 2019-02-11 | 0 | 30.44 | -30.44 | 34.93% | 1st R/A
3 | 201383008-Badhal UP-Atharogati bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
4 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.1278m-3278m. Salvage Amount Tk. 3144409.00 | KDRIDP/Bager/W-85/2017-18 | 2 | 0 | 0 | 190.819 | 2018-05-27 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-06-28 | 199.31 | 5% | 2019-12-04 | 0 | 0 | 0 | 0% | 0
5 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.5780m-7564m. Salvage Amount Tk. 297535.00 | KDRIDP/Bager/W-86/2017-18 | 1.784 | 0 | 0 | 134.255 | 2018-05-28 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-07-01 | 140.968 | 0% | 2019-12-07 | 0 | 0 | 0 | 0% | 0
6 | 201384017-Development of Bakultala- Moshni Road. Ch. 2059-3135 m. Salvage Cost. TK.-539470.00 | KDRIDP/Bager/W-20/2016-17 | 1.076 | 0 | 0 | 78.97 | 2017-08-08 | M/S Rupali Construction, Hospital Road, Barisal | 2017-09-11 | 82.5 | 35% | 2018-09-17 | 0 | 14.39 | -14.39 | 17.44% | 1st R/A
| 201384016-Improvement of Kachua-Badamtali Road by BC at Ch.1673m-3173m. Salvage Amount Tk. 904835.00 | KDRIDP/Bager/W-88/2017-18 | 1.5 | 0 | 0 | 145.075 | 2018-05-28 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-07-01 | 152.328 | 10% | 2019-12-07 | 0 | 0 | 0 | 0% | 0
7 | 201384044-Improvement of Maliporton School-bishkhali Road. Ch400-1260 m Under Kachua Upazila. Bagerhat. Salvage Cost Tk. 107512.00(Fixed) | KDRIDP/Bager/W-50/2017-18 | 0.86 | 0 | 0 | 63.956 | 2017-11-21 | M/S Robel Enterprise, Madaripur | 2018-01-25 | 66.52 | 40% | 2019-01-30 | 0 | 13 | -13 | 19.54% | 1st R/A
8 | 201384045-Laraahat-Lararkul | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201384085-Improvement of Mosni Bazar-Bhuddobhumi Road by BC at Ch.1500m-2566m. Salvage Amount Tk. 7,80,539.00 | KDRIDP/Bager/W-87/2017-18 | 1.066 | 0 | 0 | 94.25 | 2018-05-28 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-07-01 | 98.96 | 0% | 2019-12-07 | 0 | 0 | 0 | 0% | 0
9 | 201384031-Improvement of Mogia-Shirokhali Road by BC at Ch. 510m-1060m. Salvage Amount Tk. 8,59,367.00 |  | 0.55 | 0 | 0 | 36.06 | 0 | 0 | 0 | 37.86 | 0% | 0 | 0 | 0 | 0 | 0% | 0
11 | 201385032-Afra Battala- Afra Jame Mosque Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201384103-Development of Guzarpara- Baleshor River Ghat Road. Ch.558-1540 m. Salvage Cost TK. 211626.00 | KDRIDP/Bager/W-18/2016-17 | 0.982 | 0 | 0 | 68.2 | 2017-07-10 | M/S Sufia Enterprise, Badura Parerhat, Pirojpur. | 2017-08-22 | 71.4 | 100% | 2018-08-29 | 71.39 | 71.39 | 0 | 99.99% | Final
13 | 201384103-Improvement of Guzarpara-Baleshor River Ghat Road Ch.1540m-1767m. Salvage cost Tk. 135904 | KDRIDP/Bager/W-75/2017-18 | 0.227 | 0 | 0 | 15.7 | 2018-01-25 | M/S Upokar Enterprise, LGED, Pirojpur. | 2018-05-01 | 14.8 | 60% | 2019-03-31 | 0 | 0 | 0 | 0% | 0
14 | 201385014-Development of B. Andermanik S Club - Huchibaga- Andermanik H. School Road. Ch.271-2146 m. Salvage Cost TK. 900690.00 | KDRIDP/Bager/W-17/2016-17 | 1.875 | 0 | 0 | 139.996 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 146.93 | 100% | 2018-08-12 | 146.913 | 146.913 | 0 | 99.99% | Final
15 | 201384100-Improvement of Shibpur- Palpara Road. Ch 00-1359 m. Salvage Cost Tk. 491805.00 (201384078) | KDRIDP/Bager/W-46/2017-18 | 1.359 | 0 | 0 | 90.636 | 2017-12-18 | M/S Khandaker Brothers, Nalcity, Jhalokati. | 2018-01-28 | 96.38 | 40% | 2019-02-03 | 0 | 11.15 | -11.15 | 11.57% | 1st R/A
16 | 201384019-Madettola-Jobai | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 201384025-Improvement of Protappur-Bokaterkathi Road. Ch00-625 m. Salvage Cost Tk. 330365.00 | KDRIDP/Bager/W-49/2017-18 | 0.625 | 0 | 0 | 69.678 | 2017-10-04 | M/S Masud Enterprise, Kachua, Bagerhat. | 2017-11-13 | 72.73 | 100% | 2018-11-19 | 72.42 | 72.42 | 0 | 99.57% | Final
18 | 201384115-Padonagur masin shop via chato khal to signboard (201384065) | KDRIDP/Bager/W-29/2017-18 | 1.114 | 0 | 0 | 89.598 | 2017-08-22 | Md. Noor Hossain, Mission para, Jessore. | 2017-10-11 | 83.12 | 35% | 2018-07-17 | 0 | 0 | 0 | 0% | 0
19 | 201384050-Improvement of Charkati- Baruikhali Shosan Ghat Road. Ch1000-2325 m. Salvage Cost Tk. 460221.00 | KDRIDP/Bager/W-47/2017-18 | 1.325 | 0 | 0 | 83.92 | 2017-10-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2017-11-13 | 88.12 | 100% | 2018-11-19 | 88.11 | 88.11 | 0 | 99.99% | Final
20 | 201384043-Development of Uttar Gopalpur- Kachua Araian Bridge Road. Ch.00-961 m. Salvage Cost TK. 475021.00 | KDRIDP/Bager/W-19/2016-17 | 0.961 | 0 | 0 | 70 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 73.4 | 100% | 2018-08-12 | 73.28 | 73.28 | 0 | 99.84% | Final
21 | 201385059-Atharogati-Sardar Bari House to Ohidkhan road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | fatepur fultala(paddanagar)via brigde to habibshop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
23 | 201384051-Improvement of Bisherkhola-Bottola School Road by HBB at Ch.00m-2533m. Salvage Amount Tk. 845746.00 | KDRIDP/Bager/W-89/2017-18 | 2.533 | 0 | 0 | 162.366 | 2018-05-24 | M/S Rina Enterprise, Fultola, Bagerhat | 2018-06-25 | 161.96 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
24 | 201383005-Construction of RCC Bridge on Fatehpur Bazar-Gopalpur UP -Fultala Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201384050-Construction of RCC Box culvert 5.00mx3.50m at Ch. 1762m on Charkati-Baruikhali Shosan Ghat | KDRIDP/Bager/W-76/2017-18 | 0 | 5 | 0 | 13.07 | 2017-12-26 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 11.76 | 100% | 2018-10-11 | 11.76 | 11.76 | 0 | 100% | Final
Maintenance
26 | 201382008-Periodic Maintenance of Maddham Teligati-Malomgacha-Brhmankathi-Kakarbill Kachua Part from Ch. 00m-2233m | KDRIDP/Bager/M-08/2017-18 | 2.233 | 0 | 0 | 41.037 | 2018-04-03 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-04-26 | 38.98 | 10% | 2018-12-17 | 0 | 0 | 0 | 0% | 0
27 | 201383005-Periodic Maintenance of Fatehpur bazar-Gopalpur UP-Fultala bazar Road from Ch. 2584m-4794m & 7100m-8086m. | KDRIDP/Bager/M-09/2017-18 | 3.196 | 0 | 0 | 47.02 | 2018-04-04 | M/S Mou Enterprise, Kharder, Bagerhat | 2018-08-05 | 44.67 | 0% | 2018-12-30 | 0 | 0 | 0 | 0% | 0
28 | 201383006.Gopulpur UP-Natunhat Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 201383007.Kachua UP-Natun hat bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 201383008-Periodic Maintenance of Badhal UP-Atharogati bazar Road from Ch. 00m-915m | KDRIDP/Bager/M-10/2017-18 | 0.915 | 0 | 0 | 17.339 | 2018-04-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-04-26 | 16.47 | 10% | 2018-12-17 | 0 | 0 | 0 | 0% | 0
31 | 201383010-Dhopakhali UP-Lararhat via Madhopkati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 201384013-Periodic Maintenance of Goalmath-Jessordi End Panbaria Road from Ch. 00m-310m | KDRIDP/Bager/M-11/2017-18 | 0.31 | 0 | 0 | 7.273 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 201384014-Kachua-Badhal FRB to Tagrakhal river Ghat (Football field) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 201384120.Hazarkhali Bazar-Joygashi Taleshwar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
35 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 30.526 | 5 | 0 | 1930.523 |  |  |  | 1983.552 | 24.86% |  | 463.873 | 532.853 | -68.98 | 26.86%

## Rampal
Rampal
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201732007-Bhaga RHD-Kapasdanga-Kaigardashkati-Chalnahat GC (Rampal portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201732010-Improvement of Balai Bridge-Rampal Road Ch. 0.00m-5100m. Under Rampal Upazila Bagerhat. Road ID No. 201732010 Salvage cost Tk. 3840719.00 | KDRIDP/Bager/W-72/2017-18 | 5.1 | 0 | 0 | 416.04 | 2018-03-06 | M.A. Jalil Khan, Rupsha Stand Road, Khulna. | 2018-04-25 | 456.72 | 0% | 2019-05-02 | 0 | 0 | 0 | 0% | 0
3 | 201732013-A) Development of Baliadanga Bus Stand- Vangonpar Road by BC Ch 00-5200 m. B) Construction of 2 nos U-Drain at ch 300 m& 495 m.C Construction of 04 Nos Rcc 3x3 V Box Culvert at ch 2040m3450 m4170 m & 4525 mOn Same Road. Salvage Cost TK. 2101973.00 Fixed | KDRIDP/Bager/W-01/2016-17 | 5.2 | 0 | 0 | 251.31 | 2017-05-15 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-07-03 | 262.62 | 20% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
4 | 201732014-Babur bari-Bujbunia Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 201732015-Improvement of Tatulia Bridge - Kadirkhola road Ch1175-2904m by BC. Salvage amount Tk.1486339.00 Fixed | KDRIDP/Bager/W-44/2017-18 | 1.729 | 0 | 0 | 138.038 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 144.56 | 10% | 2018-12-20 | 0 | 0 | 0 | 0% | 0
Improvement of Union Road by BC
6 | 201733002-Gilatale G.C-Bhospatia UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201733005-Perikhali G.C-Bhojpatia U.P office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201733006-Improvement of Rampa-Bashtoli UP Road Ch.1890m-3695m. Under Rampal Upazila Bagerhat. Road ID No. 201733006 Salvage cost Tk. 264634 | KDRIDP/Bager/W-73/2017-18 | 1.805 | 0 | 0 | 104.937 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | New Rate estimate sent to HQ
9 | 201733007-Uzalkur UP-Baburhat Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201733009-Perikhali GC-Hurka UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201733010-Kaligonj bazar-Mollikarbare UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201733014-Improvement of Rampa UP-Pabantala hat Road Ch.0.00m-2380m & 4646m-5484m .Under Rampal Upozila Bagerhat. Road ID No. 201733014 Salvage cost Tk. 2551146 | KDRIDP/Bager/W-74/2017-18 | 3.218 | 0 | 0 | 210.72 | 2018-03-06 | M/S Ziaul & Brothers, Bhandaria, Pirojpur | 2018-04-24 | 231.3 | 0% | 2019-04-29 | 0 | 0 | 0 | 0% | Evaluation under process
Improvement of Village Road by BC
13 | 201734104-Banshtali UP-Solakora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201734018-Improvement of Kismat Kumlai-Saguna road Ch00-2080m by BC. Salvage amount Tk.2388545.00Fixed | KDRIDP/Bager/W-45/2017-18 | 2.08 | 0 | 0 | 154.76 | 2017-11-13 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 166.37 | 40% | 2018-12-20 | 0 | 26.12 | -26.12 | 15.7% | 0
15 | 201734028-Sakurhat-Saguna Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201734032-Telikhali-Baruipara Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 201734038-Development of KataKhali P/S - Dakra Road By HBB. Ch 1000-1650 m. Salvage Cost. TK.454832.00(2nd call) | KDRIDP/Bager/W-05/2016-17 | 0.65 | 0 | 0 | 21.95 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 23.6 | 50% | 2018-08-20 | 0 | 0 | 0 | 0% | HBB
18 | 201734042-Development of Dakhin Mollikerber-Dhalipara Road By HBB. Ch 1140- 2950 m Under Rampal Upazila Bagerhat. Road ID No. 201734042. Salvage Cost. TK.333359. (2nd call) | KDRIDP/Bager/W-04/2016-17 | 1.81 | 0 | 0 | 87.88 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 201734046-Rajnagor-Gorerdanga Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201734066-Foyla-Baburhat. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201734068-Amtala bazar-Pabantala Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 201734129-Development of Nolbunia borun BishasTran Bridge house-Babur bari bus Stand Road By BC. Ch (1915-2385m). Salvage Cost. TK.306072.00 (2nd call) | KDRIDP/Bager/W-07/2016-17 | 0.47 | 0 | 0 | 37.26 | 2017-11-13 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-01-04 | 40.15 | 40% | 2018-10-10 | 0 | 17.96 | -17.96 | 44.73% | 1st R/A
23 | 201735195-Development of Banga-Gilatola GC-Sorder Bari More-Hospital link Road Ch00-570m under Rampal Upazila District-Bagerhat Road ID No201735195 Salvage amount Tk.164834fixed | KDRIDP/Bager/W-59/2017-18 | 0.57 | 0 | 0 | 35.37 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 37.09 | 0% | 2018-11-06 | 0 | 0 | 0 | 0% | HBB
Improvement of Village Road by HBB
24 | 201734046-Development of Rajnagar-Gorerdanga Road By HBB. Ch 1000-1970 m. Salvage Cost. TK.226330.00(2nd Call) | KIDRIDP/Bager/W-06/2016-17 | 0.97 | 0 | 0 | 33.34 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 35.83 | 50% | 2018-08-20 | 0 | 12 | -12 | 33.49% | 1st R/A
25 | 201734033-Improvement of Modnakhali-Khayghat-East Banstali cyclone shelter road Ch500-2000m by HBB Salvage amount Tk.592188.00 Fixed | KDRIDP/Bager/W-43/2017-18 | 1.5 | 0 | 0 | 67.54 | 2017-09-27 | M/S Ziaul & Brothers, Bhandaria, Perojpur | 2017-11-14 | 67.33 | 90% | 2018-11-20 | 0 | 61.42 | -61.42 | 91.22% | 1st R/A
26 | 201734139-Srifaltala new market-Veternary hospital via sarner field. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201734135-Sreefultola bridge - Jahanjhaia Hospatal Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
28 | 201732010-Construction of 60.00m Long RCC Girder Bridge on Balai Bridge-Rampal Road at Ch 3940m | KDRIDP/Bager/B-01/2017-18 | 0 | 60 | 0 | 358.53 | 2018-04-10 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-05-23 | 392.51 | 0% | 2019-05-29 | 0 | 0 | 0 | 0% | 0
29 | 201732004-Construction of 30.00m Long RCC Girder Bridge on Foyla hat-Chaksree GC Road at Ch 841m | KDRIDP/Bager/B-06/2017-18 | 0 | 30 | 0 | 192.018 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
30 | 201734069-Gourbamha G.C-Konnadubi kheya ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 201734069-Gourbamha G.C-Konnadubi kheya ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
32 | 201732015-Periodic Maintenance of Tatulia bridge-Kadirkhola Road from Ch. 00m-1185m | KDRIDP/Bager/M-14/2017-18 | 1.185 | 0 | 0 | 22.237 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 201733009-Periodic Maintenance of Perikhali GC-Hurka UP Road from Ch. 00m-1860m |  | 1.86 | 0 | 0 | 89.992 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 201733005-Perikhali GC -Bhojpatia UP Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 201734054-Ronsan-Mirakhali Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 201734104-Banshtali UP-Solakora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
36 | Construction of Foylahat Growth Center | KDRIDP/Bager/GC-06/2017-18 | 0 | 0 | 1 | 21.55 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-03-28 | 20.889 | 0% | 2019-01-03 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
37 | Construction of Kaligonj Khaya Ghat | KDRIDP/Bager/G-12/2017-18 | 0 | 0 | 1 | 21.59 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | Construction of Dakra Khaya Ghat | KDRIDP/Bager/G-13/2017-18 | 0 | 0 | 1 | 20.33 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
39 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 28.147 | 90 | 3 | 2285.392 |  |  |  | 1878.969 | 7.5% |  | 0 | 117.5 | -117.5 | 6.253%

## Mongla
Mongla
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 00-4550 m. Salvage cost TK.8984664.00 Fixed | KDRIDP/Bager/W-02/2016-17 | 4.55 | 0 | 0 | 370.91 | 2017-06-14 | MSEBA and AB (JV), 211, Khanjahan Ali, Road, Khulna. | 2017-08-02 | 388.83 | 30% | 2018-08-29 | 0 | 101.72 | -101.72 | 26.16% | 0
2 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 4550-8340 m. Salvage cost TK.4928783.00 Fixed(2nd Call) | KDRIDP/Bager/W-03/2016-17 | 3.79 | 0 | 0 | 261.14 | 2017-06-14 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-08-02 | 272.72 | 35% | 2018-08-29 | 0 | 75.06 | -75.06 | 27.52% | 1st R/A
3 | 201582006-Chaterhat GC-Bashtola GC-Joymonigol Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 201582007-Improvement of Digiraj-Jhalmalia Dhigi road. Ch.4040m-7395m. Salvage Cost Tk. 3563628 | KDRIDP/Bager/W-77/2017-18 | 3.355 | 0 | 0 | 277.37 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | New Rate Estimate under preparation
Improvement of Union Road by BC
5 | 201583002-Burirdanga hat-Sonaeiltola UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201583007-Khulna-Mongla RHD at Goni Bridge- Burirdanga UP Office via Kapalirmeat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201583001-Impropment of Chandpai UP - Chila hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 201584014 - Khaserdanga more-Kharkharia-Dewotala bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201584021-Bashtala bazar-Digraj bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201584030 - Chila hat-Monumia High School-Katakhali-Joymoni Battola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201584040 - Improvement of Mongla ( Fire brigate)- Malgazi C.S- Moukhali (GCCR).. (Ch:3100.00-4250m). Salvage Cost Tk. 153808.00 | KDRIDP/Bager/W-92/2017-18 | 1.15 | 0 | 0 | 85.497 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 201584044 - Improvement of Holdibunia Baliar more-Burburia via malgazi-hid office Road. Ch3300m-4500m. Salvage Cost Tk.2220602.00 |  | 1.2 | 0 | 0 | 88.178 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
12 | 201584045 - Development of Digraj College - Burirdanga FWC Ch. 650-2380 m. Salvage Cost. Tk. 2023367.00 | KDRIDP/Bager/W-11/2016-17 | 1.73 | 0 | 0 | 112.53 | 2017-06-13 | Sardar Jashim, Kharder, Bagerhat | 2017-08-02 | 118.01 | 30% | 2018-08-29 | 0 | 20.45 | -20.45 | 17.33% | 1st R/A
13 | 201584071 - Sonailtola UP Office - Bokultola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201584094 - Madurpalta Govt. Pond Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201584103 - Digraj bazar - Kitunia Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201584068-Improvement of Kumerkhali Bridge to Narkeltola Bridge to Masmara Village Road. Ch 0.00 -1895 m. Salvage Cost Tk. 4079725.00 | KDRIDP/Bager/W-66/2017-18 | 1.895 | 0 | 0 | 135.11 | 2018-01-24 | M/S Iqbal Enterprise, Mongla, Bagerhat | 2018-03-07 | 141.5 | 60% | 2019-03-13 | 0 | 77.44 | -77.44 | 54.73% | 1st R/A
Improvement of Village Road by HBB
17 | 201584030-Chila hat-Monumia High School-Katakhali-Joymoni Battola Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201584075- Khulna Mongla RHD Gania Bridge to Burirdanga Up Office via Kapalirmat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
19 | 201582007-Construction of 28.00m Long PSC Girder Bridge on Digiraj-Jhalmalia Dhigi Road at Ch 3980m | KDRIDP/Bager/B-03/2017-18 | 0 | 28 | 0 | 176 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. | 0 | 190.38 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 01.07.18
20 | 201582006-Construction of 90.00m Long PSC Girder Bridge on Chaterhat GC-Banshtola GC-Joymonirghol Baddamary Road at Ch 6600m | KDRIDP/Bager/B-05/2017-18 | 0 | 90 | 0 | 569.596 | 2018-04-18 | M/S Abul Kalam Azad, Patuakhali | 0 | 624.509 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 16.05.18
Construction of Bridge on Union Road/Village Road (5.50m width)
21 | 201584044-Construction of 22.00m Long RCC Girder Bridge on Holdibunia (Baliar more)-Burburia via Malgazi-Hid office Road at Ch 2900m | KDRIDP/Bager/B-02/2017-18 | 0 | 22 | 0 | 177.85 | 2018-02-20 | M/S Mizan Enterprise, Madaripur | 2018-04-11 | 184.07 | 5% | 2019-04-17 | 0 | 0 | 0 | 0% | 0
22 | 201584035-Construction of 25.00m Long PSC Girder Bridge on Banshtala Bridge Pakhimara Khal-Shikari Houst at Burburia Road at Ch 1510m | KDRIDP/Bager/B-04/2017-18 | 0 | 25 | 0 | 196 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. | 0 | 212.98 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 01.07.18
Maintenance
23 | 201582007-Digraj-Jholmolia Dhige Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 201583002-Burirdangahat Sonailtala up Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201583007-Khanjahanalihat RHD Gazir Bridge Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
26 | Construction of Mithakhali Growth Center | KDRIDP/Bager/GC-07/2017-18 | 0 | 0 | 1 | 19.38 | 2018-02-08 | M/S Sk. Nurul Amin, Mongla, Bagerhat | 2018-03-28 | 20.29 | 0% | 2019-01-31 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
27 | Digraj Kheyaghat | KDRIDP/Bager/G-05/20 17-18 | 0 | 0 | 1 | 17.77 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 17.53 | 0% | 2018-11-06 | 0 | 0 | 0 | 0% | 0
28 | Chila Growth Center Ghat | KDRIDP/Bager/G-04/2017-18 | 0 | 0 | 1 | 20.41 | 2017-11-29 | M/S Antar Enterprise, Mongla, Bagerhat. | 2018-02-01 | 20.37 | 30% | 2018-11-06 | 0 | 8.36 | -8.36 | 41.04% | 0
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 17.67 | 165 | 3 | 2507.741 |  |  |  | 2191.189 | 6.552% |  | 0 | 283.03 | -283.03 | 12.92%

## Morrelgonj
Morrelgonj
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201602002 - Chingrakhali GC-Daibajnahati GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201602006 - Pollerhat GC-Chingrakhali UP-Zianagar RHD (Morel Part) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201602007-Dhansagar RHD-Baniakhali GC Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 201602012 - Khalkula Steel bridge to Chingrakhali bazar via Kachuabunia Rahmatia School | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 201603002 - Improvement of Baharbunia U.P.-Madrasa Hat Road from Ch. 00m-3020m. Salvage Amount Tk. 5799741.00 | KDRIDP/Bager/W-80/2017-18 | 3.02 | 0 | 0 | 194.94 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Re-tender dt. 03.04.18
6 | 201603003 - Mazhibari RHD at Badsharhat-Nishanbaria U.P office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201603004 - Improvement of Khowla UP office-CARE bazar RHD ch2686-4906m | KDRIDP/Bager/W-51/2017-18 | 2.22 | 0 | 0 | 127.62 | 2017-10-03 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2017-11-28 | 116.71 | 50% | 2018-12-04 | 0 | 26.6 | -26.6 | 22.79% | 1st R/A
8 | 201603007 - Banagrame Bazar-Hoglapasha U.P. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201603009 - Morrelgonj-Upazila H.Q.to Baharbunia Union H.Q. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201603010 - Putikhali UP office-Sonakhali bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201603012 - Hoglabunia UP office-Lakhaner hat via Nager Hat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201603017 - Baraikhali UP office-JeoDhara UP via Kalibari bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201603019 - Improvement of Banagram UP- Shailkhali ch2100-2343m | KDRIDP/Bager/W-52/2017-18 | 0.243 | 0 | 0 | 15.39 | 2017-10-03 | M/S Sher-e-Bangla Traders, Mathbaria, Perojpur | 2017-11-28 | 14.82 | 35% | 2018-12-04 | 0 | 0 | 0 | 0% | 0
14 | 201603015-Improvement of Jewdhara UP office -Joybangla bazar Ekramkhali Baytun Akram Hazi Bari Mosque road. Ch: 00-2169m | KDRIDP/Bager/W-56/2017-18 | 2.169 | 0 | 0 | 159.219 | 2017-10-26 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-12-13 | 166.84 | 5% | 2018-12-19 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by BC
15 | 201604011-Chingrakhali-Dharadoha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201604027 - Improvement of Gabagachia-Burujbaria road. Ch 500m-2150m. Salvage Cost Tk.49606.00. | KDRIDP/Bager/W-70/2017-18 | 1.65 | 0 | 0 | 127.54 | 2018-01-25 | Md. Shariful Alam, Fakirhat, Bagerhat | 2018-03-11 | 126.778 | 0% | 2019-03-17 | 0 | 0 | 0 | 0% | 0
17 | 201604044 - R&H road (at Saralia wooden bridge)-Kutghata bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201604050 - Amtala bazar-Chandipur Highschool via Taltola bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 201604065 - Improvement of Srenikhali- Bashbaria road Paschim Kalikabari- C & B road ch800-2480m. Salvage amount tk.482190.00 fixed | KDRIDP/Bager/W-54/2017-18 | 1.68 | 0 | 0 | 123.3 | 2017-10-04 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-11-28 | 128.23 | 25% | 2018-12-04 | 0 | 25 | -25 | 19.5% | 1st R/A
20 | 201604069 - Chingrakhali FRB Road-Khalkula-sagorkati | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201604072 - Improvement of Tulatola RHD near h/o M. Talukder-Uttttarjoka RHD ch4250-5140m. Salvage Amount Tk.502421.00 fixed | KDRIDP/Bager/W-53/2017-18 | 0.89 | 0 | 0 | 51.02 | 2017-10-03 | M/S Faruk Enterprise, Kachua, Bagerhat | 2017-11-19 | 53.54 | 100% | 2018-11-25 | 53.54 | 53.54 | 0 | 100% | Final
22 | 201604074 - Development of Bashbaria R & H to Mongolerhat. CH 00-1260 m. Salvage Cost. TK. 109498.00 | KDRIDP/Bager/W-21/2016-17 | 1.26 | 0 | 0 | 100.49 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-07 | 104.567 | 50% | 2018-08-29 | 0 | 52.21 | -52.21 | 49.93% | 1st R/A
23 | 201604088 - Panchakaran UP office to Sonakhali bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 201604098 - Chairman Bazar-RHD road via H/O Master Abul Kashem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201605121--Daskhali RHD-Shoilkhali Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 201605095-Kalibari Bazar - Srizon Smriti high School via Mothbaria School Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201605124-Improvement of Nurul Islam Dakhil Madrasa-Gulishakhali UP office via Sonamuddin Chokidar Bari Road from Ch. 00m-5124m. Salvage Amount Tk. 328810.00. | KDRIDP/Bager/W-79/2017-18 | 5.124 | 0 | 0 | 198.95 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Re-tender dt. 03.04.18
28 | 201605004-Development of Kalikabari- Guabaria Road. Ch 220 - 2776 m | KDRIDP/Bager/W-09/2016-17 | 2.556 | 0 | 0 | 209.99 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-11 | 217.576 | 15% | 2018-08-29 | 0 | 8.75 | -8.75 | 4.022% | 1st R/A
29 | 201604140-Improvement of Badshar hat C & B- Hasan Member bari Mazibari road via Tassen Uddin Howlader bari road. Ch00m-2130m. Salvage Cost Tk.172678.00. | KDRIDP/Bager/W-69/2017-18 | 2.13 | 0 | 0 | 153.08 | 2018-01-30 | Sayed Milon, Post office road, Jhalokathi. | 2018-02-20 | 157.599 | 20% | 2019-02-26 | 0 | 16.17 | -16.17 | 10.26% | 1st R/A
30 | 201605061-Improvement of Sleeper bridge Near RHD North Balvadrapur Shasapara via Tripolli RNGPS ch 00-1482m | KDRIDP/Bager/W-55/2017-18 | 1.482 | 0 | 0 | 104.457 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 108.63 | 20% | 2018-12-20 | 0 | 17.48 | -17.48 | 16.09% | 1st R/A
31 | 201605124-Improvement of NUrul Islam Dhakil Madrasha Gulishakhali UP Office via Sona Muddin Chokider bari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 201604063-Morrelganj-Bisarighata | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 201605165-W.Kachubunia Primary School Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
34 | 201605021-Mohonpur-Banagramme Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 201604098-Moslem khan's house - Gharami bari bridge Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 201604140-Badshar hat C & B - Hasan Member bari (Mazibari) road via Tassen Uddin Howlader bari | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
37 | 201603021-Construction of 22.00m Long RCC Girder Bridge on Putikhali U.P.-Panchakaran UP via Gazalia bazar Road at Ch 2738m. | KDRIDP/Bager/B-14/2017-18 | 0 | 22 | 0 | 195.2 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 201605020-Const. of RCC Bridge on Balavadrapur (Badhal Bazar)- Mohonpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 201604098-Const. of RCC Bridge on Moslem khan's house - Gharami bari bridge Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 201603006-Construction of 54.00m Long RCC Girder Bridge on Baharbunia U.P-Shonirjore Bazer Near the House of Talukder Mustafizur Rahman Road at Ch 1191m | KDRIDP/Bager/B-09/2017-18 | 0 | 54 | 0 | 306.29 | 2018-06-04 | MKB-MSE (JV), Nalchity, Jhalakati | 0 | 325 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 01.07.18
41 | 201605061-Improvement of Sleeper Bridge near RHD north Balvadrapur Shahapara via Tripolli RNGPS. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
42 | 201603007 - Banagrame Bazar-Hoglapasha U.P. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 201604059 - Sannashi Launch ghat-Chairmanbazar-(Sannashi Bazer) Pallimangal C&B road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Landing/ Riverghat
44 | Amtoli Bazar Khal | KDRlDP/Bager/G-01/2017-18 | 0 | 0 | 1 | 17.04 | 2017-11-29 | M/S Shikto Enterprise, Zianagar, Perojpur. | 2018-01-21 | 16.65 | 100% | 2018-10-27 | 0 | 13 | -13 | 78.08% | 1st R/A
45 | Sannasi Bazar Khal | KDRlDP/Bager/G-03/2017-18 | 0 | 0 | 1 | 25.78 | 2017-11-30 | M/S Shanta & Brothers, Basabati, Bagerhat. | 2018-02-05 | 24.98 | 10% | 2018-11-11 | 0 | 0 | 0 | 0% | 0
46 | Bisharighata Bazar Khal | KDRlDP/Bager/G-02/2017-18 | 0 | 0 | 1 | 19.64 | 2018-01-25 | N & S brothers, College Road, Morrelgonj, Bagerhat | 2018-03-07 | 20.3 | 40% | 2018-07-13 | 0 | 9.4 | -9.4 | 46.31% | 1st R/A
Tree Plantation
47 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 24.424 | 76 | 3 | 2129.946 |  |  |  | 1582.22 | 10% |  | 53.54 | 222.15 | -168.61 | 14.04%

## Sharankhola
Sharankhola
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201772004-Amragachia RHD - Banglabazar GC road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201772006-Development of Baniakhali GC- Dhansagar RHD Road. Ch 1000 -3805 m. Salvage TK. 1634778.00 | KDRIDP/Bager/W-08/2016-17 | 2.805 | 0 | 0 | 210.72 | 2017-06-08 | M/S Ahamed Steel Industries, Kapuria patty, Mathbaris, Barisal | 2017-07-20 | 219.13 | 80% | 2018-09-02 | 0 | 153.39 | -153.39 | 70% | 3rd R/A
3 | 201772007-Tafalbari GC-Rasulpur GC-Rajapur GC-Pollanbari RHD Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 201773004-Banglabazar GC-Dhansagar UP Office Rd via Rashid Khan Bridge Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
5 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201774006: Improvement of Kadamtala Ashar alo Mosjid- Varanirper upgrade GPS Road Ch4885-5885m | KDRIDP/Bager/W-26/2017-18 | 1 | 0 | 0 | 56.797 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 54.46 | 60% | 2018-07-10 | 0 | 31.8 | -31.8 | 58.39% | 2nd R/A
7 | 201774007: Nalbunia-Baniakhali road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201774011-Improvement of Rajapur-Dhansagar Bazar Road by BC at Ch.505m-1875m. Salvage Amount Tk. 2,04,825.00 | KDRIDP/Bager/W-91/2017-18 | 1.37 | 0 | 0 | 89.544 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 201774048-Improvement of Rajapur WAPDA-Rajapur GC (Police Fary) Bazar Road by BC at Ch.675m-1450m. Salvage Amount Tk. 4,36,293.00 | 0 | 0.775 | 0 | 0 | 51.07 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201774018: Improvement of Golbunia Talukderbari-Motherper Ladenmor Road Ch2900-4300m. Salvage amount -tk.548997.00( fixed) | KDRIDP/Bager/W-27/2017-18 | 1.4 | 0 | 0 | 80.36 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 75.29 | 60% | 2018-07-10 | 0 | 44.64 | -44.64 | 59.29% | 2nd R/A
10 | 201774022: Jhilbunia-Lakurtala road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201774023: Khada -Lakurtala Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201774024: Banglabazar-Tafalbari-Mourashi Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201774025: Improvement of Khada-North Tafalbari-Mourasi Bazar Road by BC at Ch.00m-2000m. Salvage Amount Tk. 3,78,627.00 (2nd Call) | KDRIDP/Bager/W-90/2017-18 | 2 | 0 | 0 | 135.226 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201774035:Bakultala - Sonatala Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201774040: Improvement of Khontakata-Charerper Road by BC at Ch.1640m-3280m. Salvage Amount Tk. 388301.00 | KDRIDP/Bager/W-81/2017-18 | 1.64 | 0 | 0 | 112.27 | 2018-05-29 | M/S Sohana Enterprise, Sharankhola, Bagerhat | 0 | 117.58 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 11.06.18
16 | 201775078-Improvement of Rajapur Bayor-Saver Madrasa via Gojen Roy House Road by BC at Ch.00m-1500m. Salvage Amount Tk. 572444.00 | KDRIDP/Bager/W-82/2017-18 | 1.5 | 0 | 0 | 97.406 | 2018-06-11 | M/S Sohana Enterprise, Sharankhola, Bagerhat | 0 | 102.016 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 11.06.18
17 | 201774047-Improvement of Taltoli bazer-Nalbunia (Bezitana) bazer Road Ch1500-2505m. Salvage amount -tk.554716.00 (fixed) | KDRIDP/Bager/W-28/2017-18 | 1.005 | 0 | 0 | 62.45 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 58.02 | 60% | 2018-07-10 | 0 | 34.82 | -34.82 | 60.01% | 2nd R/A
Improvement of Village Road by HBB
18 | 201774013-Improvement of Purba Khontakata-Nalbunia Road by HBB at Ch.00m-1378m & 2818m-4090m. Salvage Amount Tk. 2312135.00 | KDRIDP/Bager/W-83/2017-18 | 2.65 | 0 | 0 | 111.809 | 2018-05-13 | M/S Chan Enterprise, Puraton Bazar, Bagerhat | 2018-06-18 | 116.84 | 0% | 2019-06-24 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Upazila Road (7.30m width)
19 | 201772004-Construction of 42.00m Long RCC Girder Bridge at Amragachia RHD-Banglabazar GC Road at Ch 4200m | KDRIDP/Bager/B-11/2017-18 | 0 | 42 | 0 | 235.666 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201772007-Construction of 22.00m Long RCC Girder Bridge at Tafalbari GC- Rasulpur GC- Rajapur GC- Pollanbari RHD Road at Ch 1215m | KDRIDP/Bager/B-08/2017-18 | 0 | 22 | 0 | 183.14 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
21 | 201774020-Construction of 30.00m Long RCC Girder Bridge on South Amragachia-Jibanduari Road at Ch 3500m. | KDRIDP/Bager/B-07/2017-18 | 0 | 30 | 0 | 213.51 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
22 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 201774016-Periodic Maintenance of Baniakhali GC-Pollanbari RHD via B-Dhansagar Community Clinic Delower house Sharankhola part Road from Ch. 1500m-3500m. | KDRIDP/Bager/M-06/2017-18 | 2 | 0 | 0 | 30.03 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 29.805 | 10% | 2019-01-17 | 29.81 | 29.81 | 0 | 100% | Final
24 | 201774023: Periodic Maintenance of Khada- Lakurtala Road from Ch. 00m-1350m | KDRIDP/Bager/M-07/2017-18 | 1.35 | 0 | 0 | 20.09 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 19.918 | 10% | 2019-01-17 | 18.93 | 18.93 | 0 | 95.04% | Final
25 | 201774024: Banglabazar-Tafalbari-Mourashi Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
26 | Construction of Banglabazar Growth Center | KDRIDP/Bager/GC-04/2017-18 | 0 | 0 | 1 | 19.45 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 0 | 18.615 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 07.03.18
Landing/ Riverghat
27 | Rayenda Bandaghataghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | Construction of Tafalbari GC Ghat | KDRIDP/Bager/G-11/2017-18 | 0 | 0 | 1 | 17.25 | 2017-12-27 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-02-19 | 16.23 | 0% | 2018-11-25 | 0 | 0 | 0 | 0% | NOA issued on 22.01.18
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 19.495 | 94 | 2 | 1726.788 |  |  |  | 827.904 | 9.333% |  | 48.74 | 313.39 | -264.65 | 37.85%

## Summary
BAGERHAT
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 7 | 6 | 26.529 | 0 | 0 | 1744.58 | 330.17 | 29.17% | 18.93%
Union Road by BC | 11 | 9 | 21.286 | 0 | 0 | 1102.446 | 187.69 | 36.88% | 17.02%
Village Road by BC | 53 | 47 | 75.617 | 0 | 0 | 4418.015 | 1639.256 | 54.67% | 37.1%
Village Road by HBB | 15 | 15 | 17.639 | 0 | 0 | 920.568 | 438.82 | 70.71% | 47.67%
Bridge on Upazila Road | 8 | 3 | 0 | 344 | 0 | 1207.399 | 0 | 0% | 0%
Bridge on Union Road/Village Road | 9 | 7 | 0 | 196.3 | 0 | 939.499 | 32.94 | 56% | 3.506%
Maintenance | 14 | 13 | 29.573 | 0 | 0 | 431.807 | 115.36 | 26.92% | 26.72%
GC-Hat | 5 | 5 | 0 | 0 | 5 | 96.648 | 0 | 5% | 0%
Landing/ Riverghat | 11 | 9 | 0 | 0 | 11 | 163.27 | 30.76 | 20% | 18.84%
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 133 | 114 | 170.644 | 540.3 | 16 | 11024.232 | 2774.996 | 29.93% | 25.17%