## Satkhira
SATKHIRA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Assasuni
1 | 287042010-Chiledanga RHD - Bangadah GC Paithali Bazer Rd. | [13 empty] | 0 | #DIV/0!
2 | 287042012-Mohishkur RHD - Bashtala bazar via Mohishkur GC Road (Assasuni part). | [13 empty] | 0 | #DIV/0!
3 | 287042013-Protapnagar GC-Pakhimara RHD(Assasuni part). | [13 empty] | 0 | #DIV/0!
Debhata
4 | 287252007-Improvement of Subornabad GC-Bangdah GC Road by BC (Ch. 3240-5240m) with 15nos. 625mmX600mm U-Drain at Ch. 3241m, 3275m, 3352m, 3529m, 3568m, 3678m, 3705m, 3952m, 4093m, 4291m 4539m, 4642m, 4816m, 5032m & 5058m on the Same Road. | KDRIDP/Sat/W-08/2016-17 | 2 | 0 | 0 | 165.74 | 2017-05-22 | M/S Habib Enterprise Satkhira | 2017-06-14 | 173.1 | 35% | 2018-06-20 |  | 56.99 | -56.99 | 32.92% | Salvage Amount Tk. 8,93,628/-
5 | 287252008-Improvement of Bohera Bazar (RHD) - Ellarchor Bazar -Bangdah GC(Sadar) Road by BC (Ch. 6704-8000m) with 3nos. 625mmX600mm U-Drain at Ch.7050m, 7640m & 7775m and 1no. 900mmX900mm U-Drain at Ch. 7700m on the Same Road | KDRIDP/Sat/W-07/2016-17 | 1.296 | 0 | 0 | 87.3 | 2017-05-22 | M/S Joint Bricks Traders Bankal, Satkhira | 2017-07-02 | 84.78 | 90% | 2018-07-08 |  | 76.054 | -76.054 | 89.71%
6 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 8000-9660m | KDRIDP/Sat/W-61/2017-18 | 1.66 | 0 | 0 | 146.46
7 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 9660m-11910m | KDRIDP/Sat/W-62/2017-18 | 2.25 | 0 | 0 | 186.566 | 2018-07-26 | [9 empty] | Salvage amount Tk. 422153.00
Kaligonj
7 | 287472004-Khanpur-Baliadanga GC-Uzirpur GC via Gobindokatihat Rd. | [13 empty] | 0 | #DIV/0!
8 | 287472005-(a) Improvement of Raipur RHD - Noornagar GC Via Sirajpur Hat Road at Ch 600-3385m & (b) Construction of 3 nos. u-PVC Pipe Culvert on the Same Road | KDRIDP/Sat/W-29/2017-18 | 2.785 | 0 | 0 | 233.067 | 2018-07-19 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 4462226.00
9 | 287472006-(a) Improvement of Dudly RHD - Ratanpur GC Road at Ch 00-4200m, (b) Construction of 12 nos. u-PVC Pipe Culvert & (c) Construction of 11nos. 625mmX600mm U-Drain at Ch. 533m, 722m, 789m, 1270m, 1881m, 2177m, 2352m, 2878m, 3117m, 3345m & 4018m on the Same Road | KDRIDP/Sat/W-28/2017-18 | 4.2 | 0 | 0 | 344.03 | 2018-07-19 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 8575180.00
10 | 287472010-Approach of Bashtola bridge | [13 empty] | 0 | #DIV/0!
Tala
11 | 287902001-Improvement of Tala-Kalaroa UP HQ via Dalua GC-Patkelghata GC road Tala Portion road by BC (Ch. 10020-11788m) with 1no. 925mmX900mm U-Drain at Ch. 11160m on the Same Road | KDRIDP/Sat/W-09/2016-17 | 1.94 | 0 | 0 | 160 | 2017-06-08 | M/S Basu Traders Tala, Satkhira | 2017-07-11 | 158.79 | 65% | 2018-07-17 |  | 95.59 | -95.59 | 60.2% | Salvage Amount Tk. 3,08,136/-
12 | 287902004-Jethua GC - Budhata GC Via Horihornagor Bazar Road(Tala portion). | [13 empty] | 0 | #DIV/0!
13 | 287902005-Improvement of Kopilmoni GC-Jatua GC road at Ch. 5465-6429m | KDRIDP/Sat/W-57/2017-18 | 0.964 | 0 | 0 | 78.67 | 2018-04-10 | Uttam Traders, Tala, Satkhira. | 2018-05-21 | 82.43 | 35% |  |  | 25 | -25 | 30.33%
Shyamnagar
14 | 287862002-Improvement of Nowabenki GC - Khanpur R&H via Vetkhali GC road at (Ch. 27100-29000m & Ch. 32300-34100m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 27350m, 27800m & 33200m on the Same Road | KDRIDP/Sat/W-11/2016-17 | 3.7 | 0 | 0 | 321.22 | 2017-10-09 | mewebajv Shyamnagar, Satkhira | 2017-12-03 | 330.37 | 65% |  |  | 199.21 | -199.21 | 60.3% | 1st R/A
15 | 287862005-Pakhimara R&H -Protapnagar GC Road | [13 empty] | 0 | #DIV/0!
Kalaroa
16 | 287432005-Kalaroa GC-Gaira GC via Chandanpur UP Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 20.795 | 0 | 0 | 1723.053 |  |  |  | 829.47 | 58% |  | 0 | 452.844 | -452.844 | 54.59%
Improvement of Union Road by BC
Satkhira Sadar
1 | 287823010-Mahamudpur Bazar-Abaderhat Via Jaghanathpur road. | [13 empty] | 0 | #DIV/0!
2 | 287823020 - Improvement of Ghona Bazar - Kushkhali UPC Bhadra Ziader more road via Aruakhali GPS at ch 1665-2687m and 2687-3914m | KDRIDP/Sat/W-69/2017-18 | 2.25 | 0 | 0 | 170.68 | 2018-06-28 | [7 empty] | 0 | #DIV/0!
3 | 287823022-Agordari UP Office (Abadehat GC ) - Bharukhaki Bazar ( Bharukhali GPS) Road Via Jhitkee | [13 empty] | 0 | #DIV/0!
4 | 287823023-Bali UP office - Raipur Bazar road via Shumundanga | [13 empty] | 0 | #DIV/0!
Assasuni
5 | 287043001-Kadakati UP office - Kadakati GC via Gabtala Bazar road. | [13 empty] | 0 | #DIV/0!
6 | 287043004-Ekshora bazar-Bichotbazar(Anulia UP) Rd. | [13 empty] | 0 | #DIV/0!
7 | 287043008-Dargapur UP Office-Tentulia Bazer Rd. | [13 empty] | 0 | #DIV/0!
8 | 287043010-Paithali Bazar - Sobhnali UP office via Kamalkati kheyaghat road. | [13 empty] | 0 | #DIV/0!
9 | 287043011-Bardal UP office - Kapsanda Bazar via Baintala & Fatikkhali road. | [13 empty] | 0 | #DIV/0!
Debhata
10 | 287253002-Sakhipur UP-Nangla Bazar via Eidgah Chandipur Road | [13 empty] | 0 | #DIV/0!
11 | 287253003-Debhata UP Office-Komorpur Road(Debhata Portion) | [13 empty] | 0 | #DIV/0!
12 | 287253005-Nowapara UP -Bodarhata GC via Chandpur Atapur road. | [13 empty] | 0 | #DIV/0!
Tala
13 | 287903003-Patkelghata GC(R&H) near Pollibiddut-Khalishkhali UP Road. | [13 empty] | 0 | #DIV/0!
14 | 287903006-(a) Improvement of Tala UP Office Hospital-Jatpur GC road by BC (Ch. 1596-5096m) (b) Construction of 6nos. 625mmX600mm U-Drain at Ch. 169m, 2896m, 3396m, 3641m, 3946m & 4616m and (c) Construction of 1no. 925mmX900mm U-Drain at Ch. 2286m on the Same Road | KDRIDP/Sat/W-10/2016-17 | 3.5 | 0 | 0 | 226.07 | 2017-06-12 | Md. Iqbal Jamader, Polashpole, Satkhira | 2017-07-16 | 223.62 | 60% | 2018-05-30 |  | 126.97 | -126.97 | 56.78% | Salvage Amount Tk. 1,39,115/-
15 | 287903013-Khesra UP-Dakshin Sahjadpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
16 | 287903007-Improvement of Magura UP Office-Madra Bazar road at Ch. 1000-2215m | KDRIDP/Sat/ W-56/2017-18 | 1.215 | 0 | 0 | 79.239 | 2018-04-10 | M/S Raka Enterprise, Tala, Satkhira. | 2018-05-21 | 79.235 | 25% | 2019-04-20 |  | 15.293 | -15.293 | 19.3%
| 287903015-Improvement of Islamkati UP Office-Magura Bazar road at Ch. 1000-2215m |  | 0.982 | 0 | 0 | 64.59 |  |  |  | 64.586 |  |  |  | 12.47 | -12.47 | 19.31%
17 | 287903011-Improvement of Nagarghata UP-Pulirhat road at Ch. 00-1670m | KDRIDP/Sat/ W-55/2017-18 | 1.67 | 0 | 0 | 116.069 | 2018-04-10 | Tasnim Enterprise Daulatpur, Khulna |  | 110.265 |  |  |  |  | 0 | 0% | NOA issued on 03.05.18
18 | 287903008-Tetulia UP office(Modonpur R & H) Ghone Bazar via Dewanipara Bazar | [13 empty] | 0 | #DIV/0!
19 | 287903013-Khesra UP-Dakshin Sahjadpur Bazar | [13 empty] | 0 | #DIV/0!
Kalaroa
20 | 287433002-(a) Improvement of Jalalabad UP Koila more - Batra bazar road at (Ch. 5050-6920m) by 25mm BC + 7mm SC (b) Construction of 3nos. 315mm PVC Pipe Drain at Ch. 5290m, 6770m & 6828m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 6190m, 6296m & 6504m on the Same Road. | KDRIDP/Sat/W-17/2016-17 | 1.87 | 0 | 0 | 117.52 | 2017-07-17 | M/S Sarder Bricks Kalaroa, Satkhira | 2017-09-06 | 111.406 | 35% | 2017-07-20 |  | 33.999 | -33.999 | 30.52%
21 | 287433005-Chandanpur UO-Sultanpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
22 | 287433006-(a) Improvement of Chandanpur UP - Hejaldi bazar via Sultanpur bazar road at (Ch. 3600-7270m) by 25mm BC + 7mm SC (b) Construction of 8nos. 315mm PVC Pipe Drain at Ch. 4282m, 4560m, 5014m, 5172m, 5229m, 5278m, 5784m & 6116m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 4828m, 6337m & 6518m on the Same Road. | KDRIDP/Sat/W-16/2016-17 | 3.67 | 0 | 0 | 262.63 | 2017-07-17 | Sk. Sirajul Haque Labsha, Satkhira | 2017-09-06 | 259.999 | 55% | 2018-09-12 |  | 137.55 | -137.55 | 52.9% | Salvage Amount Tk. 9,03,849/-
23 | 287433007-Helatola UP-Kazirhat Bazar Rd. | [13 empty] | 0 | #DIV/0!
24 | 287433008-(a) Improvement of Kushadanga UP (Kalibari more)-Kalatupi nutun bazar via Raita bazar road by BC (Ch. 2952-5675m) (b) Construction of 3nos. PVC Pipe Drain Culvert at Ch. 3384m, 3917m & 5300m, (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 3185m & 3871m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 5615m on the Same Road | KDRIDP/Sat/W-02/2016-17 | 2.72 | 0 | 0 | 169.15 | 2017-05-21 | Sk. Sirajul Haque Labsha, Satkhira | 2017-07-02 | 164.55 | 55% | 2018-07-08 |  | 87.64 | -87.64 | 53.26%
25 | 287433016-Improvement of Damdam Bazar Halatala UP Brojabakas Jamal more road by BC (Ch. 1839-2652m) with 1no. PVC Pipe Drain Culvert at Ch. 315m and 1no. 625mmX600mm U-Drain at Ch. 1843m on the Same Road | KDRIDP/Sat/W-03/2016-17 | 0.81 | 0 | 0 | 54.64 | 2017-05-22 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-07-02 | 53.55 | 60% | 2018-07-08 |  | 32.06 | -32.06 | 59.87%
26 | 287433017-Brojabaksa Bazar-Kushodanga UP Rd. | [13 empty] | 0 | #DIV/0!
27 | 287433021-Bamonkhali Bazar-Jugakhali UP rd. | [13 empty] | 0 | #DIV/0!
Shyamnagar
28 | 287863003-Nakipur-Sirajpur hat road. | [13 empty] | 0 | #DIV/0!
29 | 287863004-Improvement of Iswaripur UP-Harinagar hat via Dhumkali Road by BC (Ch. 00-4090m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 210m, 3305m & 3950m on the Same Road | KDRIDP/Sat/W-04/2016-17 | 4.09 | 0 | 0 | 279.02 | 2017-05-25 | M/S Rabeya Traders Dhaka | 2017-06-14 | 273.53 | 45% | 2018-06-20 |  | 32.875 | -32.875 | 12.02% | Salvage Amount Tk. 38,60,858/-
30 | 287863013-Improvement of Iswaripur UP-Paranpur hat via Ramjannagar Road by BC (Ch. 1900-3475m) | KDRIDP/Sat/W-05/2016-17 | 1.575 | 0 | 0 | 102.54 | 2017-05-22 | M/S Rabeya Traders Dhaka | 2017-06-14 | 95.93 | 10% | 2018-06-20 |  |  | 0 | 0% | Salvage Amount Tk. 13,04,167/-
31 | 287863017-Improvement of Iswaripur UP- Gumantali hat via Golabari Ghat Road by BC at Ch. 2730-4500m. | KDRIDP/Sat/ W-75/2017-18 | 1.77 | 0 | 0 | 144.026 | 2018-07-26 | [7 empty] | 0 | #DIV/0!
32 | 28783012-Noornagar-Kultali Bazar road. | [13 empty] | 0 | #DIV/0!
Kaligonj
33 | 287473002-(a) Improvement of Dudly Bazar (Natun Hat)-Dhalbaria UP via Ratanpur GC Road at Ch 2400-2900m & (b) Construction of 3 nos. u-PVC Pipe Culvert on the Same Road. | KDRIDP/Sat/W-31/2017-18 | 0.5 | 0 | 0 | 33.16 | 2018-01-18 | M/S Sheikh Bricks Kaligonj, Satkira | 2018-03-05 | 33.05 | 20% | 2018-11-11 |  |  | 0 | 0%
34 | 287473017-Improvement of Dakhinsripur UP Bazar-Gobindokati Bazar via Uttarsripur road at Ch. 2745-4350m | KDRIDP/Sat/W-46/2017-18 | 1.605 | 0 | 0 | 107.169 |  | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 109.26 | 65% | 2019-04-21 |  | 70.37 | -70.37 | 64.41%
Total |  |  | 28.227 | 0 | 0 | 1926.503 |  |  |  | 1578.981 | 43% |  | 0 | 549.227 | -549.227 | 34.78%
Improvement of Village Road by BC
Satkhira Sadar
1 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | [13 empty] | 0 | #DIV/0!
2 | 287824004-Bansdah UP Office-Kawan danga Rd. | [13 empty] | 0 | #DIV/0!
3 | 287824009-Dhohakula FRB-Dhohakula R&H (Assasuni) road. | [13 empty] | 0 | #DIV/0!
4 | 287824014-Improvement of Dhuliar- Damarpara WAPDA Embt road Ch.0.00-1000m | KDRIDP/Sat/ W-60/2017-18 | 1 | 0 | 0 | 72.74 | 2018-07-26 | [7 empty] | 0 | #DIV/0! | Salvage amount Tk. 420751.00
5 | 287824023-Taltala R&H to Kaikhali Mistripara road. | [13 empty] | 0 | #DIV/0!
6 | 287824025-Brahmmorajpur Maniktala to Machkhola Hatkhola road. | [13 empty] | 0 | #DIV/0!
7 | 287824028-Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road. | [13 empty] | 0 | #DIV/0!
8 | 287824061-Faizullahpur more (Satkhira-Assasuni R&H) to Fingri UP Office road. | [13 empty] | 0 | #DIV/0!
9 | 287825021-Gobindakati Satrano Battola-Reui Bazar Road. | [13 empty] | 0 | #DIV/0!
10 | 287825016-Bhabanipur more-Toloigacha BDR Camp Road | [13 empty] | 0 | #DIV/0!
11 | 287825060-Babulia FRB-Satkhira city College Road. | [13 empty] | 0 | #DIV/0!
12 | 287825062-Chandpur-Budhata Road | [13 empty] | 0 | #DIV/0!
13 | 287825133-Improvement of Brahmmorajpur Bazar to Chalerdangi RHD Assasuni road Brahmmorajpur Bazar to Baradal Pucca road via Dhulihor Chandra Pukur road at ch. 00-866m | KDRIDP/Sat/W-68/2017-18 | 0.866 | 0 | 0 | 62.69 | 2018-06-25 | [7 empty] | 0 | #DIV/0! | Salvage amount Tk.517797.00
14 | 287825187-Jadia Sheikhpara.GPS road. | [13 empty] | 0 | #DIV/0!
15 | 287825158-Bankal-Bagmari road | [13 empty] | 0 | #DIV/0!
16 | 287825107-Goalpota Hatkhola to Kamardangi Sluice Gate road. | [13 empty] | 0 | #DIV/0!
17 | 287824028-Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road. | [13 empty] | 0 | #DIV/0!
18 | 287824054-R&H poraton Satkhitra Machkhola road. | [13 empty] | 0 | #DIV/0!
Assasuni
19 | 287044018-Badartala-Mozgurkhali Rd. | [13 empty] | 0 | #DIV/0!
20 | 287044089-Agordhari-Gabtala via Kampura rd. | [13 empty] | 0 | #DIV/0!
21 | 287044094-APS Collage-Gokulnagar Road. | [13 empty] | 0 | #DIV/0!
25 | 287045059-Improvement of Agordari Dhalibari- Hazi bari Graveyard via Agordari High School road at ch.00-1330m. | KDRIDP/Sat/W-65/2017-18 | 1.33 | 0 | 0 | 110.796 | 2018-06-25 | [7 empty] | 0 | #DIV/0! | Salvage amount Tk.134268.00
| 287044119-Improvement of Kachua Girls high School- Agordari High School road at ch.00-1380m. |  | 1.38 | 0 | 0 | 107.55 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk.670148.00
| 287044156-Improvement of Agordari west para Mosque- Kadakati GC road at ch.00m-1445m. |  | 1.445 | 0 | 0 | 117.238 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 299347.00
24 | 287045057-Sreeulia R&H-Sreeulia UP Office road. | [13 empty] | 0 | #DIV/0!
26 | 287045066-Natana bazar - Hashkhali GPS via Hashkhali culvert road. | [13 empty] | 0 | #DIV/0!
27 | 287045092-Sreeula foot ball field - Sluce gare via Jela parishad road. | [13 empty] | 0 | #DIV/0!
28 | 287044133-Kurikahunia Makbul Dokanderer Bari - Nakna Gazibari road. | [13 empty] | 0 | #DIV/0!
29 | 287044034-Sriula R&H-Sriula Shashibari Bridge via BD Chow house. | [13 empty] | 0 | #DIV/0!
30 | 287044030-Budhata Bazar to Budhata Pr.School road. | [13 empty] | 0 | #DIV/0!
31 | 287045064-Mohishadanga High school-Ganesher Khey ghat via H-O. Kishor Babu. | [13 empty] | 0 | #DIV/0!
32 | 287044051-Mohistpur- Boyershing khal road. | [13 empty] | 0 | #DIV/0!
33 | 287045126-Badar tola Hazi Jallauddin Collage- Mozjurkhali Pr.School road. | [13 empty] | 0 | #DIV/0!
34 | 287045072-Sreeula Molla Bari Mosque road. | [13 empty] | 0 | #DIV/0!
35 | 287044228-Godaipor-Rautara road. | [13 empty] | 0 | #DIV/0!
Debhata
36 | 287254001-Sekendra R&H-WDB Embankment (Ghariadanga) Rd. | [13 empty] | 0 | #DIV/0!
37 | 287254006-North Parulia R&H-Naziergheer Rd | [13 empty] | 0 | #DIV/0!
38 | 287254021-Konra Pakralala R&H-Kazimoholla Samsuddin M. House Road . | [13 empty] | 0 | #DIV/0!
39 | 287254035-Debhata Parulia UZR-Bhatshala Cyclone Shelter Road. | [13 empty] | 0 | #DIV/0!
40 | 287254037-Sushilgati FRB-Eidgah Sakhipur Road. | [13 empty] | 0 | #DIV/0!
41 | 287254045-Badartola Bazar-Rangashisha Road. | [13 empty] | 0 | #DIV/0!
42 | 287255032-Ratanshapur Babar Ali Shop-Teyor GCCR Road | [13 empty] | 0 | #DIV/0!
43 | 287255175-Improvement of Shakhipur Mosque - Khegurbaria Southpara Mosque road at Ch 00-1135m with 2nos. 625mmX600mm U-Drain at Ch.62m & 560m on the Same Road | KDRIDP/Sat/W-59/2017-18 | 1.135 | 0 | 0 | 92.117 | 2018-04-23 | Md. Shajahan Alam, Kaligonj, Satkhira. | 2018-06-06 | 96.61 | 0% | 2019-06-12 |  |  | 0 | 0% | Salvage Amount Tk. 863133.00
| 287255075-Improvement of Shakhipur Nimay house - Lakhimi Kanta house road at Ch 00-1038m with 3nos. 625mmX600mm U-Drain at Ch.450m, 615m & 892m on the Same Road. |  | 1.038 | 0 | 0 | 81.768 |  |  |  | 85.758 |  |  |  |  | 0 | 0% | Salvage Amount Tk. 1536290.00
44 | 287254033-Subornabad FRB-Darer khal Ferry ghat Via Shasadanga Madrasha). | [13 empty] | 0 | #DIV/0!
45 | 287254043-Improvement of Shakhipur Bazar - Bhatshala UNR WDB Embankment road at Ch 00-6210m | KDRIDP/Sat/W-58/2017-18 | 6.21 | 0 | 0 | 418.94 | 2018-06-25 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 1384326.00
46 | 287255045-Chaltatola-Synnasir chack via roingashisha( WDB) Emabankmnet road. | [13 empty] | 0 | #DIV/0!
47 | 287255153-Parulia Sunial Desh House- Jhal Bagen Road | [13 empty] | 0 | #DIV/0!
48 | 2872555130-pubo kulia bridge tosadesh hachari Rd. | [13 empty] | 0 | #DIV/0!
Tala
49 | 287904004-Improvement of Manikhar-Ghorerdanga Road by 25mm BC+7mm SC (Ch. 00-1494m) with 4nos. 625mmX600mm U-Drain at Ch. 120m, 380m, 916m & 1309m on the Same Road. | KDRIDP/Sat/W-34/2017-18 | 1.494 | 0 | 0 | 105.99 | 2018-07-19 | [7 empty] | 0 | #DIV/0! | NOA issued on 10.05.18
50 | 287904011-Baliadha-Bolarumpur Road. | [13 empty] | 0 | #DIV/0!
51 | 287904018-Khalishkhali-Dalua. | [13 empty] | 0 | #DIV/0!
52 | 287904057-Improvement of Sujansah Bazar R&H-Ghona Road at Ch. 1000-2140m | KDRIDP/Sat/W-70/2017-18 | 1.14 | 0 | 0 | 78.705 | 2018-06-28 | [7 empty] | 0 | #DIV/0!
| 287905031-Improvement of Magura girls school - joynwddin house Road at Ch. 00m - 995m |  | 0.995 | 0 | 0 | 69.59 | [8 empty] | 0 | #DIV/0!
53 | 287904064-Improvement of Sujanshoha Bazar Paranpur Israil house road at Ch. 00-1007m | KDRIDP/SAT/W-37/2017-18 | 1.007 | 0 | 0 | 71.786 | 2018-04-23 | M/S Roshni Enterprise, Tala, Satkhira. | 2018-06-06 | 74.765 | 0% | 2019-06-12 |  |  | 0 | 0%
54 | 287904073-Improvement of Shalika College-Dalua GC road at Ch. 4500-8210m | KDRIDP/Sat/ W-54/2017-18 | 3.71 | 0 | 0 | 246.85 | 2018-04-19 | M/S Basu Traders Tala, Satkhira |  | 255.3 |  |  |  |  | 0 | 0% | Salvage Amount Tk. 186115.00 W/O under process
55 | 287905147-Bathuadanga Primary school - Kalagachi Road | [13 empty] | 0 | #DIV/0!
56 | 287904010-Shahpur R&H – Hazrakati Bazar | [13 empty] | 0 | #DIV/0!
57 | 287904039-Barobila(UZR)- Sarulia Bazar via Barobila GPS | [13 empty] | 0 | #DIV/0!
58 | 287904088-Bhairabnagar R&H- Akrakhola Bazar via Nagarghata UP | [13 empty] | 0 | #DIV/0!
59 | 287905134-Boyardanga UZR - Mokolandokati GPS via Pakshia Durgha Mondir Road | [13 empty] | 0 | #DIV/0!
60 | 287905185-Daibari mor - H/O Intaz Golder via maspara Mosjid Road | [13 empty] | 0 | #DIV/0!
61 | 287905108-Improvement of Majiara (House of Azhar Ali more) Khorerdanga Bazar Road by BC (Ch. 118-2024m) with 1no. 625mmX600mm U-Drain at Ch. 1040m on the Same Road | KDRIDP/Sat/W-06/2016-17 | 1.906 | 0 | 0 | 129.44 | 2017-05-22 | M/S Roshni Enterprise Tala, Satkhira | 2017-06-22 | 126.53 | 100% | 2018-06-28 | 126.47 | 126.47 | 0 | 99.95% | Final (Salvage Amount Tk. 22,97,337.00)
62 | 28790516-Kazidanga H/O-Dr. Aminuddin Gazi-Kharail,Bhabanipur road. | [13 empty] | 0 | #DIV/0!
Kalaroa
63 | 287434006-Improvement of Tin Bot-tala to Satpota bazar Via Nathpur Rd by BC (Ch. 1621-3622m) with 4nos. Pipe Drain Culvert at Ch. 1861m, 2090m, 2206m & 2465m and 1no. 625mmX600mm U-Drain at Ch. 2588m on the Same Road | KDRIDP/Sat/W-01/2016-17 | 2.001 | 0 | 0 | 121.34 | 2017-05-22 | Star Enterprise Munjitpur, Satkhira | 2017-07-02 | 119.46 | 0% | 2018-07-08 |  |  | 0 | 0% | Salvage Amount Tk. 2,24,703/-
64 | 287434028-Improvement of Kesmot Elishpur-Chitla Bottola road at Ch. 2062-3680m | KDRIDP/Sat/ W-49/2017-18 | 1.618 | 0 | 0 | 111.62 | 2018-04-10 | Tasnim Enterprise Daulatpur, Khulna |  | 106.04 |  |  |  |  | 0 | 0% | NOA issued on 03.05.18
65 | 287434053-Improvement of Kalaroa-Saraskati R&H at Hamidpur More-Bamonkhali road at Ch. 1540-3115m | KDRIDP/Sat/ W-53/2017-18 | 1.575 | 0 | 0 | 111.359 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 114.69 | 0% | 2019-06-11 |  |  | 0 | 0% | Salvage Amount Tk. 75036.00
66 | 287434059-(a) Improvement of Brojabaksah jamal More - Jhapagat Pukur road at Ch. 1175m-2605m by 25mm BC+7mm SC (b) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1439m & 2483m on the Same Road | KDRIDP/Sat/W-36/2017-18 | 1.403 | 0 | 0 | 91.18 | 2018-04-23 | M/S Swarnalata Enterprise, Kalaroa, Satkhira. |  | 86.62 |  |  |  |  | 0 | 0% | NOA issued on 10.05.18
67 | 287434057-(a) Improvement of Boyerdanga FRB - N. Kati Charabattala FRB road at (Ch. 00-1995m) by 25mm BC + 7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 746m and (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 15m & 1083m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 1302m on the Same Road | KDRIDP/Sat/W-18/2016-17 | 1.995 | 0 | 0 | 133.75 | 2017-07-17 | Star Enterprise Munjitpur, Satkhira | 2017-09-06 | 129.609 | 5% | 2018-09-12 |  |  | 0 | 0% | Salvage Amount Tk. 4,24,435/-
68 | 287434061-Improvement of Kazirhat Bazar-Bahura Komorpur road at Ch. 2480-3520m | KDRIDP/Sat/ W-51/2017-18 | 1.04 | 0 | 0 | 73.28 | 2018-04-10 | Tasnim Enterprise Daulatpur, Khulna |  | 69.616 |  |  |  |  | 0 | 0% | Salvage Amount Tk. 52529.00 NOA issued on 03.05.18
69 | 287434068-Improvement of Boalia Fakirpara Bazar-Bhadiali Bazar road at Ch. 499-1972m | KDRIDP/Sat/ W-40/2017-18 | 1.473 | 0 | 0 | 97.27 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk.1012925.00
70 | 287434072-Improvement of Bamonkhali Bazar-Batra Bazar road at Ch. 3980-5250m | KDRIDP/Sat/ W-52/2017-18 | 1.27 | 0 | 0 | 81.245 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 81.2 | 0% | 2019-06-11 |  |  | 0 | 0% | Salvage Amount Tk. 21921.00 NOA issued
71 | 287434085-Brikrompur FRB-Hojoldi bazar road. | [13 empty] | 0 | #DIV/0!
72 | 287435004-Improvement of Kayla-Morarikati road at Ch. 2593-4080m | KDRIDP/Sat/ W-50/2017-18 | 1.487 | 0 | 0 | 109.316 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk. 72128.00
73 | 287435018-(a) Improvement of Helatala UP Tile Fectory - Kashpur P/School more road at Ch 1599m - 3114m by 25mm BC+7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 2219m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 1745m, 2076m & 2739m on the Same Road. | KDRIDP/Sat/W-35/2017-18 | 1.515 | 0 | 0 | 100.56 | 2018-04-23 | Md. Rafiqul Islam, Kalaroa, Satkhira. | 2018-06-06 | 95.536 | 0% | 2019-06-12 |  |  | 0 | 0%
74 | 287434093-Ofapur Govt.Primary School to Basantapur Govt. Primary School. | [13 empty] | 0 | #DIV/0!
75 | 287435085-Improvement of Panchpota - Sonabaria bazar road at (Ch. 2944-3500m) by 25mm BC + 7mm SC | KDRIDP/Sat/W-19/2016-17 | 0.556 | 0 | 0 | 34.29 | 2017-07-17 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-09-06 | 33.606 | 35% | 2018-06-12 |  | 10.49 | -10.49 | 31.21%
76 | 287435045-Hulhulia Notun Bazar More-Hulhulia Govt.Primary School road. | [13 empty] | 0 | #DIV/0!
77 | 287434035-Ramkesnopur hat khola more- Nurmohammad Gazi H/O road. | [13 empty] | 0 | #DIV/0!
78 | 287435110-Improvement of Nathpur Khanpukur more - Nathpur Gazipara via Kamarepota road at (Ch. 00-575m) by 25mm BC + 7mm SC (b) Construction of 2nos. 315mm PVC Pipe Drain at Ch. 130m & 375m on the Same Road | KDRIDP/Sat/W-20/2016-17 | 0.575 | 0 | 0 | 35 | 2017-07-17 | G M Enterprise Kalaroa, Satkhira | 2017-09-06 | 36.55 | 60% | 2018-04-30 |  | 21.15 | -21.15 | 57.87%
Shyamnagar
79 | 287864007-Improvement of Iswaripur FWC - Beramollah Hat road at (Ch. 00-3000m) & Construction of 7.0m Long 600mmX600mm U-Drain at Ch. 368m on the Same Road | KDRIDP/Sat/W-12/2016-17 | 3 | 0 | 0 | 182.52 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 187.9 | 45% | 2018-11-25 |  | 71.267 | -71.267 | 37.93% | Salvage Amount Tk. 2,62,483/-
80 | 287864026-Ramjibonpur More-Horinagari Road | [13 empty] | 0 | #DIV/0!
81 | 287864038-ZR at Sonaremore-Fulbari-Chigrikhali road. | [13 empty] | 0 | #DIV/0!
82 | 287864040 Chandipur R&H-Sankarkati hat-Majhergonj hat road. | [13 empty] | 0 | #DIV/0!
83 | 287864048-Improvement of Jotindanagar hat-Manikhali R&H road at Ch. 9180-11180m | KDRIDP/Sat/W-43/2017-18. | 2 | 0 | 0 | 148.917 | 2018-07-26 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 641202.00
84 | 287864062- Munshigonj Bazar-Garrage hat Bridge. | [13 empty] | 0 | #DIV/0!
85 | 287864077 Jadappur Pucca road-Kallyanpur Sluicegate-Chingrikhali road | [13 empty] | 0 | #DIV/0!
86 | 287864102- Improvement of Biramollah hat Kowsar Gazi bari road at (Ch. 1000-2200m) | KDRIDP/Sat/W-15/2016-17 | 1.2 | 0 | 0 | 73.26 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 75.4 | 55% | 2018-11-25 |  | 38.97 | -38.97 | 51.68% | Salvage Amount Tk. 5,06,656/-
87 | 287864102-Improvement of Khagraghat H/O Fazlul Haque- R & H road by BC.Ch0.00m-1100m | KDRIDP/Sat/W-48/2017-18 | 1.1 | 0 | 0 | 76.22 |  | M/S Asa Construction, Shyamnagar, Satkira | 2018-04-22 | 80.03 | 0% | 2019-04-21
88 | 287864119- Badaghata-Anowara khatun Mohila Madrasa via Muktijoddha. | [13 empty] | 0 | #DIV/0!
89 | 287865149- Improvement of Mohendrakata - Badda house road at (Ch. 00-1650m) & Construction of 2nos. 7.0m Long 600mmX600mm U-Drain at Ch. 1100m & 1400m on the Same Road | KDRIDP/Sat/W-13/2016-17 | 1.65 | 0 | 0 | 99.52 | 2017-10-09 | Md. Abdul Hakim Situlpur, Kaligonj | 2017-11-19 | 103.965 | 40% | 2018-10-06 |  | 22.52 | -22.52 | 21.66% | 1st R/A
90 | 287864110-Improvement of Biramollah hat - Ruhit Majhi - Dakin Srifalkati road at (Ch. 1000-2718m) | KDRIDP/Sat/W-14/2016-17 | 1.718 | 0 | 0 | 104.69 | 2017-07-16 | M/S Asha Construction Ishwaripur, Shyamnagar, Satkhira | 2017-09-20 | 109.897 | 60% | 2018-07-22 |  | 62.34 | -62.34 | 56.73% | Salvage Amount Tk. 1,74,989.00
91 | 287864148-Improvement of Padmapukur R&H-Baintala GPS road at Ch. 00-2000m | KDRIDP/Sat/W-42/2017-18. | 2 | 0 | 0 | 85.906 |  | Md. Iqbal Jamader Polashpole, Satkhira | 2018-04-24 | 85.65 | 0% | 2019-04-20 |  |  | 0 | 0%
92 | 28785149-Mohendrokata-Baidda house | [13 empty] | 0 | #DIV/0!
93 | 287864045 - Improvement of Sapkhali - Kaikhali BOP Road by BC at Ch.00m-3000m | KDRIDP/Sat/W-71/2017-18 | 3 | 0 | 0 | 199.436 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk.2092433.00
94 | 287864031-Improvement of Hawalbhangi-Baduria road at CH. 00-2651m | KDRIDP/Sat/ W-75/2017-18 | 2.615 | 0 | 0 | 187.5 | [8 empty] | 0 | #DIV/0!
95 | 287864100-Dumuria Bazr-Parsheemari Kheyaghat road. | [13 empty] | 0 | #DIV/0!
96 | 287865048-Improvement of Jada more-Gani Mollik road at (Ch. 00-1500m) | KDRIDP/Sat/W-21/2017-18 | 1.5 | 0 | 0 | 105.17 | 2017-08-31 | Molla Engineering Workshop Shyamnagar, Satkhira | 2017-10-09 | 109.27 | 20% | 2018-05-25 |  | 7.59 | -7.59 | 6.946% | Salvage Amount Tk. 2,04,581/-
97 | Gorkumarpur Bazar to Diglarait Moszid. | [13 empty] | 0 | #DIV/0!
98 | 287864041-Zr. Moutala-Tajhori hat road. | [13 empty] | 0 | #DIV/0!
99 | 287864105-Ishakur LGED Packa road-Jhasghata Sha Mosque road. | [13 empty] | 0 | #DIV/0!
100 | 287865036- Improvement of Bongshipur-Azad Gazi road at CH. 00-950m | KDRIDP/Sat/ W-38/2017-18 | 0.95 | 0 | 0 | 76.196 | 2018-06-25 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 594005.00
Kaligonj
101 | 287474028-Kushlia G.C.C.-Uttar Sreepur WAPDA Emb.via Chanditala Road. | [13 empty] | 0 | #DIV/0!
102 | 287474053-Kaligonj Upazila Nazimgonj bazar - Bosontopur BOP Via Kaligonj BOP Road. | [13 empty] | 0 | #DIV/0!
103 | 287475001-Gorapota R&H - Maniltala Rd. | [13 empty] | 0 | #DIV/0!
104 | 287475003-(a) Improvement of Nalta RHD Girls School - Nalta College Road at Ch 00-2100m, (b) Construction of 2 nos. u-PVC Pipe Culvert & (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1230m & 1855m on the Same Road. | KDRIDP/Sat/W-32/2017-18 | 2.1 | 0 | 0 | 125.89 | 2018-04-23 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 132.1 | 0% | 2019-05-23 |  |  | 0 | 0%
105 | 287475017-Bhathudanga - Goalkhali Road. | [13 empty] | 0 | #DIV/0!
106 | 287475027-(a) Improvement of Parulgacha pry. School - Radhapada Mondol House (Nengi beel) Road at Ch 00-1080m & (b) Construction of 1nos. 625mmX600mm U-Drain at Ch. 707m on the Same Road | KDRIDP/Sat/W-33/2017-18 | 1.08 | 0 | 0 | 75.907 | 2018-04-23 | Sk. Shahinur Rahman, Kaligonj, Satkhira | 2018-05-29 | 79.28 | 0% | 2019-06-04 |  |  | 0 | 0%
107 | 287475065-Improvement of Moutala GPS-Liakot Ali House Road by BC at Ch.00-2315m | KDRIDP/Sat/W-74/2017-18 | 2.315 | 0 | 0 | 153.927 | 2018-07-26 | [7 empty] | 0 | #DIV/0!
| 287475386-Improvement of Pania Rashid Chokider H/O-Jerongacha hat-Makhun shop road at Ch. 00-2040m |  | 2.04 | 0 | 0 | 133.267 | [8 empty] | 0 | #DIV/0!
108 | 287475071-Moutala Deputy Sb.H.-Kamarpara | [13 empty] | 0 | #DIV/0!
109 | 287475074-Moutala Old Bazar-Jhorukhamar | [13 empty] | 0 | #DIV/0!
110 | 287475118-Improvement of Gobindrakati-Uttar Sreepur road at Ch. 00-1550m | KDRIDP/Sat/W-45/2017-18 | 1.55 | 0 | 0 | 101.059 |  | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 106 | 0% | 2019-04-21 |  |  | 0 | 0%
111 | 287475246 fatapur to nilkanthapurl road. | [13 empty] | 0 | #DIV/0!
112 | 287475409-Uttar Srepur Malipara Eidgah-Dakkin Srepur Bazar via Latif Member House road. | [13 empty] | 0 | #DIV/0!
113 | 2874755065-Moutala Govt. pry. school-Liakot Ali H. | [13 empty] | 0 | #DIV/0!
114 | 287474033-Moutala ZR.-ParamanDakati | [13 empty] | 0 | #DIV/0!
115 | 287475210- (a) Improvement of Pania GPS - M Gobindapur Emam Chowkidar House Via Mirpara Maszid Road by BC at Ch 00-1730m, (b) Construction of 10nos. u-PVC Pipe Culvert & (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1193m & 1469m on the Same Road | KDRIDP/Sat/W-72/2017-18 | 1.73 | 0 | 0 | 118.71 | 2018-07-26 | [7 empty] | 0 | #DIV/0! | Salvage amount Tk. 26,47,028.00
| 287475378-(a) Improvement of Pania Akash Shikari House - West Moutala Khanpara GPS Road at Ch 00-1420m, (b) Construction of 5 nos. u-PVC Pipe Culvert & (c) Construction of 1nos. 625mmX600mm U-Drain at Ch. 1232m on the Same Road |  | 1.42 | 0 | 0 | 96.338 | [8 empty] | 0 | #DIV/0!
116 | 287475057-Improvement of Kaligonj (R&H)-Khazabaria Bridge-Ujzymari road at Ch. 00-1170m | KDRIDP/Sat/W-41/2017-18 | 1.17 | 0 | 0 | 96.49 |  | Molla Engineering Workshop Shyamnagar, Satkhira | 2018-04-15 | 99.337 | 0% | 2019-04-21 |  |  | 0 | 0% | Salvage Amount Tk. 440937.00
117 | 287475058-Dudly Village- Ex.Chariman H/O | [13 empty] | 0 | #DIV/0!
118 | 287475326-Improvement of Charjumina Khaldhar-Notun hat via Powkhali Perojpur Shoshanghat road at Ch. 00-2500m | KDRIDP/Sat/W-47/2017-18 | 2.5 | 0 | 0 | 164.547 |  | Motiur Rahman, Kaligonj, Satkhira | 2018-04-30 | 156.32 | 45% | 2019-03-07 |  | 70 | -70 | 44.78%
119 | 287475364-Laxinathpur Jahid Kazi H/O-Moral para via Laxinathpur bholar H/O. | [13 empty] | 0 | #DIV/0!
120 | 287475387-Norohore kathi Sattar Dr. More via Motola Govt.Pr.School via Boldy para road. | [13 empty] | 0 | #DIV/0!
121 | 287475016 Wapda office to Satpur bridge road. | [13 empty] | 0 | #DIV/0!
122 | 287475115-Chatta pokur(WAPDA Khayghat)via Khartola bazarto via abdul mannan house to iman ali house road. | [13 empty] | 0 | #DIV/0!
123 | 287474003-Thakra shoner bangla Clube-Kolijoga Moktizoda Abdus Sadak H/O. rod. | [13 empty] | 0 | #DIV/0!
124 | 287475022-Improvement of Thakra Chowmoni-Tollakati School via Kulia Dargapur Road by BC at Ch.00-1850m. | KDRIDP/Sat/W-73/2017-18 | 1.85 | 0 | 0 | 127.23 | 2018-07-26 | [7 empty] | 0 | #DIV/0!
| 287475317-Improvement of Sreekola Mohila Madrasha Gate-Sreekhola High School Road by BC at Ch.00-1030m |  | 1.03 | 0 | 0 | 72.359 | [8 empty] | 0 | #DIV/0!
| 287475037-Improvement of Pania School (Ramjan's House -Abdul Moazzem's House via Janakalyan Samiti Road by BC at Ch. 00-800m |  | 0.8 | 0 | 0 | 56.606 | [8 empty] | 0 | #DIV/0!
125 | 287475384-Bashtola Graveyard - Barkhali Dr. Poretosh pokur via Baruni mondir road. | [13 empty] | 0 | #DIV/0!
126 | 287475393-Hogla Ansher Shop- Nengy Sendary School road. | [13 empty] | 0 | #DIV/0!
127 | 287475143-Bastola Bazar via Uzipur bazar via Chandulia Thalna road. | [13 empty] | 0 | #DIV/0!
128 | 287474009-Uksha Likat More-Osman Sk. House. | [13 empty] | 0 | #DIV/0!
129 | 287475365-Namazgar shamsul karighor H/O- Namazgar Govt. Pr.Scool, | [13 empty] | 0 | #DIV/0!
130 | 287475253-Bondokati H/Q Raish Miostry-Nilkonthapur Halima Member road. | [13 empty] | 0 | #DIV/0!
131 | 28475123-Romsh Kormokar H.(Komarpur)-Raridpur Mohammad Ali H/O | [13 empty] | 0 | #DIV/0!
132 | 287475212-Batuadanga Moksed Shop UZR-Katakhali Gulli Bill Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 81.482 | 0 | 0 | 5528.075 |  |  |  | 2837.039 | 21.14% |  | 126.47 | 430.797 | -304.327 | 15.18%
Improvement of Village Road by HBB
Satkhira Sadar
1 | 287824005-Matiadanga Khaya ghat-Khariadanga Road. | [13 empty] | 0 | #DIV/0!
2 | 287824008-Ghona-Vharukhali Sluice gate Road. | [13 empty] | 0 | #DIV/0!
3 | 287824011-Ghona BOP-Gazipur Golam Ali House Road. | [13 empty] | 0 | #DIV/0!
4 | 287824003-Dhulihar puraton Bazar Khola more to Damarpota via Kazir house & Bardal Village road | [13 empty] | 0 | #DIV/0!
5 | 287824007-Vatpara-Gharchala P/School Road | [13 empty] | 0 | #DIV/0!
6 | 287824010-Chandpur bazar-Kulpota WAPDA Embt. Road | [13 empty] | 0 | #DIV/0!
7 | 287824016-Kumorpur R&H-Kumorpur WDB EMB Road. | [13 empty] | 0 | #DIV/0!
8 | 287825041-Nehalpur WDB Emb. to Jugipota (Sukdebpur) Road. | [13 empty] | 0 | #DIV/0!
Assasuni
9 | 287044032-Naktara FRB to Baliakhali WAPDA via Radharati Rd. | [13 empty] | 0 | #DIV/0!
10 | 287044179-Tuardanga Culvert - Bamondanga bridge via Tuardanga Paschimpara Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Debhata
11 | 287254013-Gazirhat- Kalabaria via Borohula Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Upazila Road (7.30m width)
Kaligonj
1 | 287472011-Const. of RCC Bridge on Nazimging GC-Pawkhali RHD Road over Jamuna Khal | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Kaligonj
1 | 287473001-Construction of Bridge on Mothoreshpur UP-Powkhali RHD Road over Jamuna Khal. | [13 empty] | 0 | #DIV/0!
Assasuni
2 | 287043012-Construction of Bridge on Sovnali UP-Nashukhali bazar via paschim Kamalkati Radha Shyamsundar Mandir road. | [13 empty] | 0 | #DIV/0!
3 | 287044188-Construction of Bridge on Gazir hat-Chumuria road over Morischap khal. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Tala
4 | 247904059-Dakin Sahajadpur Launch ghat-Kathipara bazar | [13 empty] | 0 | #DIV/0!
5 | 287864101-Biramolla hat Kawser gazi bari road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Maintenance
Satkhira Sadar
1 | 287822010-Periodic Maintenance of Rasulpur R&H-Baikari UP via Pairadanga-Aruakhali via Mirgidanga road at Ch. 00-4200m | KDRIDP/Sat/ M-01/2017-18 | 4.2 | 0 | 0 | 105.51 | 2018-05-17 | Md. Ashraful Kabir Khokun, Katia, Satkhira |  | 110.785 |  |  |  |  | 0 | 0%
2 | 287823010-Mahamudpur Bazar -Abaderhat via Jaghanathpur Road. | [13 empty] | 0 | #DIV/0!
3 | 287823024-Periodic Maintenance of Kulia Sreerampur Chubaria-Bhamra road at Ch. 00-1000m | KDRIDP/Sat/ M-03/2017-18 | 1 | 0 | 0 | 20.34 | 2018-05-17 | S.M. Shawkat Hossain, Katia, Satkhira |  | 21.35 |  |  |  |  | 0 | 0%
4 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | [13 empty] | 0 | #DIV/0!
5 | 287824004-Bansdah UP Office-Kawandanga Road | [13 empty] | 0 | #DIV/0!
6 | 287824006-Binerpota bridge-Rajnagore Road. | [13 empty] | 0 | #DIV/0!
7 | 287824012-Puraton Satkhira R&H hat-Gobindopur Bazar Road via jiala | [13 empty] | 0 | #DIV/0!
8 | 287824032-Periodic Maintenance of Shaighoria R&H-Akhrakhola Bazar via Satianatala & Battala More road at Ch. 00-2752m | KDRIDP/Sat/ M-02/2017-18 | 2.752 | 0 | 0 | 57.8 | 2018-05-17 | Santa Mahmud, Kamalnagor, Satkhira |  | 60.11 |  |  |  |  | 0 | 0%
9 | 287824032-Shaighoria R&H-Akhrakhola Bazar via Satiantala & Battala more road. | [13 empty] | 0 | #DIV/0!
10 | 287824042-Shaighoria R&H-Babulia Bazar Road | [13 empty] | 0 | #DIV/0!
11 | 287824050-Madabkati-Satani Bazar road | [13 empty] | 0 | #DIV/0!
12 | 287825145-Alipur Jangalar Bridge - Nathuar Danga Road via Kulpura Rd | [13 empty] | 0 | #DIV/0!
Assasuni
13 | 287042001-Assasuni GC-Manikkhali ferryghat Rd. | [13 empty] | 0 | #DIV/0!
14 | 287042010-Chiledanga RHD -Bangdah GC Road via Paithali Bazar Rd. | [13 empty] | 0 | #DIV/0!
15 | 287043002-Khazra UP- Bordol GC Rd. | [13 empty] | 0 | #DIV/0!
16 | 287043008-Dargapur UP Office -Tentulia Bazar Rd. | [13 empty] | 0 | #DIV/0!
17 | 287044088-Gunaharkati Bazar-Mohajanpur Rd. | [13 empty] | 0 | #DIV/0!
18 | 287044089-Agordhari-Gabtola via Humkura Rd. | [13 empty] | 0 | #DIV/0!
Debhata
19 | 287252008-Periodic Maintenance of Bohera Bazar RHD-Ellarchor Bazar-Bangdah GC road at Ch. 00-1735m | KDRIDP/Sat/ M-04/2017-18 | 1.735 | 0 | 0 | 47.5 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 49.39 | 0% | 2018-11-23 |  |  | 0 | 0%
20 | 287254025-Periodic Maintenance of Hadipur R&H-Hadipur Masrasha via Ashkarpur Alimiya Kallyan Sangoshta road at Ch. 1145-2296m | KDRIDP/Sat/ M-05/2017-18 | 1.151 | 0 | 0 | 15.6 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 16.22 | 0% | 2018-11-23 |  |  | 0 | 0%
21 | 287254038-Periodic Maintenance of Parulia R&H-Debhata Parulia GCR via Sakhipur Dhopadanga road at Ch. 00-1045m | KDRIDP/Sat/ M-06/2017-18 | 1.045 | 0 | 0 | 20.519 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 21.33 | 0% | 2018-11-23 |  |  | 0 | 0%
22 | 287255070-Nowapara Nawser house-Bibuti`s house Road. | [13 empty] | 0 | #DIV/0!
Tala
23 | 287902005-Tala-Kopilmoni GC via Jatua GC Rd. | [13 empty] | 0 | #DIV/0!
24 | 287904048-Kanchanpur Eidgah (R & H)-Hizaldanga Bazar Road. | [13 empty] | 0 | #DIV/0!
25 | 287904088-Bhairabnagor R&H Road - Akrakhola Bazar via Nagorghata UP RD | [13 empty] | 0 | #DIV/0!
26 | 287905096-Islamkati Primary School - Vagba House of Abdul Malek Mohalder Road. | [13 empty] | 0 | #DIV/0!
27 | 287904115-Kumira R&H - Magura Bazar Road. | [13 empty] | 0 | #DIV/0!
Kalaroa
28 | 287432003-Baguri Beltala -Chandanpur GC Rd. | [13 empty] | 0 | #DIV/0!
29 | 287432006-Kalaroa- Tala via Dhandia Bazar Rd. | [13 empty] | 0 | #DIV/0!
Shyamnagar
30 | 287862002-Nowabenki GC-Khanpur R&H via Vetkhali GC Rd. | [13 empty] | 0 | #DIV/0!
31 | 287863007-Burigoalini UP-Nildumur hat Masud more via Durgabati Road. | [13 empty] | 0 | #DIV/0!
32 | 287863009-Nakipur GC-Chandipur hat Rd | [13 empty] | 0 | #DIV/0!
33 | 287864074-Soalia Mosque-Kallanpur Sluice gate Road. | [13 empty] | 0 | #DIV/0!
34 | 287864077-Jadabpur Pacca road-Kallanpur Sluice gate Road. | [13 empty] | 0 | #DIV/0!
35 | 287864146-Nurnagar-Ramchandrapur-Habibpur Road | [13 empty] | 0 | #DIV/0!
36 | 287863002 Kasimari UP-Jhapali hat Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
37 | 287864041 ZR at Moutala-Teghori hat Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 11.883 | 0 | 0 | 267.269 |  |  |  | 279.185 | 0% |  | 0 | 0 | 0 | 0%
GC-Hat
Assasuni
1 | Construction of East Nakna Bazar Chairman Bazar GC | KDRIDP/Sat/ GC-09/2017-18 | 0 | 0 | 1 | 20.59 | 2018-04-10 | Md. Abul Hossain Kamalnagar, Satkhira | 2018-05-06 | 20.26 | 0% | 2018-11-12 |  |  | 0 | 0%
Kaligonj
2 | Construction of Bhodrakhali Bazar GC | KDRIDP/Sat/ GC-10/2017-18 | 0 | 0 | 1 | 20.32 | 2018-02-28 | Md. Rafiqul Islam Kaligonj, Satkhira | 2018-04-03 | 20.2 | 0% | 2018-10-09 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 2 | 40.91 |  |  |  | 40.46 | 0% |  | 0 | 0 | 0 | 0%
Landing/ Riverghat
Shyamnagar
1 | Garkunerpur bazar ghat | [13 empty] | 0 | #DIV/0!
Assasuni
2 | Boundhir Khyaghat | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Kaligonj
3 | Construction of Kalikapur ghat | KDRIDP/Khul/G-15/2017-18 | 0 | 0 | 1 | 30.69 | [8 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 1 | 30.69 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Tree Plantation
Satkhira Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Assasuni
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Debhata
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kaligonj
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Tala
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kalaroa
6 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Shyamnagar
7 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 142.387 | 0 | 3 | 9516.5 |  |  |  | 5565.135 | 12.21% |  | 126.47 | 1432.868 | -1306.398 | 25.75%
|  |  | 142.387 | 0 | 3 | 9516.5 |  |  |  | 5565.135 | 5.193% |  | 126.47 | 1432.868 | -1306.398 | 25.75%

## Kaligonj
Kaligonj
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287472004-Khanpur-Baliadanga GC-Uzirpur GC via Gobindokatihat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 287472005-(a) Improvement of Raipur RHD - Noornagar GC Via Sirajpur Hat Road at Ch 600-3385m & (b) Construction of 3 nos. u-PVC Pipe Culvert on the Same Road | KDRIDP/Sat/W-29/2017-18 | 2.785 | 0 | 0 | 233.067 | 2018-07-19 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 4462226.00
3 | 287472006-(a) Improvement of Dudly RHD - Ratanpur GC Road at Ch 00-4200m, (b) Construction of 12 nos. u-PVC Pipe Culvert & (c) Construction of 11nos. 625mmX600mm U-Drain at Ch. 533m, 722m, 789m, 1270m, 1881m, 2177m, 2352m, 2878m, 3117m, 3345m & 4018m on the Same Road | KDRIDP/Sat/W-28/2017-18 | 4.2 | 0 | 0 | 344.03 | 2018-07-19 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 8575180.00
4 | 287472010-Approach of Bashtola bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 287473002-(a) Improvement of Dudly Bazar (Natun Hat)-Dhalbaria UP via Ratanpur GC Road at Ch 2400-2900m & (b) Construction of 3 nos. u-PVC Pipe Culvert on the Same Road. | KDRIDP/Sat/W-31/2017-18 | 0.5 | 0 | 0 | 33.16 | 2018-01-18 | M/S Sheikh Bricks Kaligonj, Satkira | 2018-03-05 | 33.05 | 20% | 2018-11-11 | 0 | 0 | 0 | 0% | 0
6 | 287473017-Improvement of Dakhinsripur UP Bazar-Gobindokati Bazar via Uttarsripur road at Ch. 2745-4350m | KDRIDP/Sat/W-46/2017-18 | 1.605 | 0 | 0 | 107.169 | 0 | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 109.26 | 65% | 2019-04-21 | 0 | 70.37 | -70.37 | 64.41% | 0
Improvement of Village Road by BC
7 | 287474028-Kushlia G.C.C.-Uttar Sreepur WAPDA Emb.via Chanditala Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 287474053-Kaligonj Upazila Nazimgonj bazar - Bosontopur BOP Via Kaligonj BOP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 287475001-Gorapota R&H - Maniltala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287475003-(a) Improvement of Nalta RHD Girls School - Nalta College Road at Ch 00-2100m, (b) Construction of 2 nos. u-PVC Pipe Culvert & (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1230m & 1855m on the Same Road. | KDRIDP/Sat/W-32/2017-18 | 2.1 | 0 | 0 | 125.89 | 2018-04-23 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 132.1 | 0% | 2019-05-23 | 0 | 0 | 0 | 0% | 0
11 | 287475017-Bhathudanga - Goalkhali Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287475027-(a) Improvement of Parulgacha pry. School - Radhapada Mondol House (Nengi beel) Road at Ch 00-1080m & (b) Construction of 1nos. 625mmX600mm U-Drain at Ch. 707m on the Same Road | KDRIDP/Sat/W-33/2017-18 | 1.08 | 0 | 0 | 75.907 | 2018-04-23 | Sk. Shahinur Rahman, Kaligonj, Satkhira | 2018-05-29 | 79.28 | 0% | 2019-06-04 | 0 | 0 | 0 | 0% | 0
14 | 287475065-Improvement of Moutala GPS-Liakot Ali House Road by BC at Ch.00-2315m | KDRIDP/Sat/W-74/2017-18 | 2.315 | 0 | 0 | 153.927 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287475386-Improvement of Pania Rashid Chokider H/O-Jerongacha hat-Makhun shop road at Ch. 00-2040m |  | 2.04 | 0 | 0 | 133.267 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
15 | 287475071-Moutala Deputy Sb.H.-Kamarpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 287475074-Moutala Old Bazar-Jhorukhamar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287475118-Improvement of Gobindrakati-Uttar Sreepur road at Ch. 00-1550m | KDRIDP/Sat/W-45/2017-18 | 1.55 | 0 | 0 | 101.059 | 0 | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 106 | 0% | 2019-04-21 | 0 | 0 | 0 | 0% | 0
18 | 287475246 fatapur to nilkanthapurl road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287475409-Uttar Srepur Malipara Eidgah-Dakkin Srepur Bazar via Latif Member House road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 2874755065-Moutala Govt. pry. school-Liakot Ali H. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287474033-Moutala ZR.-ParamanDakati | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287475210- (a) Improvement of Pania GPS - M Gobindapur Emam Chowkidar House Via Mirpara Maszid Road by BC at Ch 00-1730m, (b) Construction of 10nos. u-PVC Pipe Culvert & (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1193m & 1469m on the Same Road | KDRIDP/Sat/W-72/2017-18 | 1.73 | 0 | 0 | 118.71 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 26,47,028.00
23 | 287475378-(a) Improvement of Pania Akash Shikari House - West Moutala Khanpara GPS Road at Ch 00-1420m, (b) Construction of 5 nos. u-PVC Pipe Culvert & (c) Construction of 1nos. 625mmX600mm U-Drain at Ch. 1232m on the Same Road |  | 1.42 | 0 | 0 | 96.338 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
24 | 287475057-Improvement of Kaligonj (R&H)-Khazabaria Bridge-Ujzymari road at Ch. 00-1170m | KDRIDP/Sat/W-41/2017-18 | 1.17 | 0 | 0 | 96.49 | 0 | Molla Engineering Workshop Shyamnagar, Satkhira | 2018-04-15 | 99.337 | 0% | 2019-04-21 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 440937.00
25 | 287475058-Dudly Village- Ex.Chariman H/O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287475326-Improvement of Charjumina Khaldhar-Notun hat via Powkhali Perojpur Shoshanghat road at Ch. 00-2500m | KDRIDP/Sat/W-47/2017-18 | 2.5 | 0 | 0 | 164.547 | 0 | Motiur Rahman, Kaligonj, Satkhira | 2018-04-30 | 156.32 | 45% | 2019-03-07 | 0 | 70 | -70 | 44.78% | 0
28 | 287475364-Laxinathpur Jahid Kazi H/O-Moral para via Laxinathpur bholar H/O. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287475387-Norohore kathi Sattar Dr. More via Motola Govt.Pr.School via Boldy para road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287475016 Wapda office to Satpur bridge road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287475115-Chatta pokur(WAPDA Khayghat)via Khartola bazarto via abdul mannan house to iman ali house road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 287474003-Thakra shoner bangla Clube-Kolijoga Moktizoda Abdus Sadak H/O. rod. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 287475022-Improvement of Thakra Chowmoni-Tollakati School via Kulia Dargapur Road by BC at Ch.00-1850m. | KDRIDP/Sat/W-73/2017-18 | 1.85 | 0 | 0 | 127.23 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 287475317-Improvement of Sreekola Mohila Madrasha Gate-Sreekhola High School Road by BC at Ch.00-1030m |  | 1.03 | 0 | 0 | 72.359 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
13 | 287475037-Improvement of Pania School (Ramjan's House -Abdul Moazzem's House via Janakalyan Samiti Road by BC at Ch. 00-800m |  | 0.8 | 0 | 0 | 56.606 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
35 | 287475384-Bashtola Graveyard - Barkhali Dr. Poretosh pokur via Baruni mondir road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 287475393-Hogla Ansher Shop- Nengy Sendary School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 287475143-Bastola Bazar via Uzipur bazar via Chandulia Thalna road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 287474009-Uksha Likat More-Osman Sk. House. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 287475365-Namazgar shamsul karighor H/O- Namazgar Govt. Pr.Scool, | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 287475253-Bondokati H/Q Raish Miostry-Nilkonthapur Halima Member road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 28475123-Romsh Kormokar H.(Komarpur)-Raridpur Mohammad Ali H/O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 287475212-Batuadanga Moksed Shop UZR-Katakhali Gulli Bill Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
43 | 287472011-Const. of RCC Bridge on Nazimging GC-Pawkhali RHD Road over Jamuna Khal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
44 | 287473001-Construction of Bridge on Mothoreshpur UP-Powkhali RHD Road over Jamuna Khal. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
45 | Construction of Bhodrakhali Bazar GC | KDRIDP/Sat/ GC-10/2017-18 | 0 | 0 | 1 | 20.32 | 2018-02-28 | Md. Rafiqul Islam Kaligonj, Satkhira | 2018-04-03 | 20.2 | 0% | 2018-10-09 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
46 | Construction of Kalikapur ghat | KDRIDP/Khul/G-15/2017-18 | 0 | 0 | 1 | 30.69 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
47 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 28.675 | 0 | 2 | 2090.766 |  |  |  | 735.547 | 3.023% |  | 0 | 140.37 | -140.37 | 19.08%

## Kalaroa
Kalaroa
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287432005-Kalaroa GC-Gaira GC via Chandanpur UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
2 | 287433002-(a) Improvement of Jalalabad UP Koila more - Batra bazar road at (Ch. 5050-6920m) by 25mm BC + 7mm SC (b) Construction of 3nos. 315mm PVC Pipe Drain at Ch. 5290m, 6770m & 6828m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 6190m, 6296m & 6504m on the Same Road. | KDRIDP/Sat/W-17/2016-17 | 1.87 | 0 | 0 | 117.52 | 2017-07-17 | M/S Sarder Bricks Kalaroa, Satkhira | 2017-09-06 | 111.406 | 35% | 2017-07-20 | 0 | 33.999 | -33.999 | 30.52% | 0
3 | 287433005-Chandanpur UO-Sultanpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 287433006-(a) Improvement of Chandanpur UP - Hejaldi bazar via Sultanpur bazar road at (Ch. 3600-7270m) by 25mm BC + 7mm SC (b) Construction of 8nos. 315mm PVC Pipe Drain at Ch. 4282m, 4560m, 5014m, 5172m, 5229m, 5278m, 5784m & 6116m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 4828m, 6337m & 6518m on the Same Road. | KDRIDP/Sat/W-16/2016-17 | 3.67 | 0 | 0 | 262.63 | 2017-07-17 | Sk. Sirajul Haque Labsha, Satkhira | 2017-09-06 | 259.999 | 55% | 2018-09-12 | 0 | 137.55 | -137.55 | 52.9% | Salvage Amount Tk. 9,03,849/-
5 | 287433007-Helatola UP-Kazirhat Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 287433008-(a) Improvement of Kushadanga UP (Kalibari more)-Kalatupi nutun bazar via Raita bazar road by BC (Ch. 2952-5675m) (b) Construction of 3nos. PVC Pipe Drain Culvert at Ch. 3384m, 3917m & 5300m, (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 3185m & 3871m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 5615m on the Same Road | KDRIDP/Sat/W-02/2016-17 | 2.72 | 0 | 0 | 169.15 | 2017-05-21 | Sk. Sirajul Haque Labsha, Satkhira | 2017-07-02 | 164.55 | 55% | 2018-07-08 | 0 | 87.64 | -87.64 | 53.26% | 0
7 | 287433016-Improvement of Damdam Bazar Halatala UP Brojabakas Jamal more road by BC (Ch. 1839-2652m) with 1no. PVC Pipe Drain Culvert at Ch. 315m and 1no. 625mmX600mm U-Drain at Ch. 1843m on the Same Road | KDRIDP/Sat/W-03/2016-17 | 0.81 | 0 | 0 | 54.64 | 2017-05-22 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-07-02 | 53.55 | 60% | 2018-07-08 | 0 | 32.06 | -32.06 | 59.87% | 0
8 | 287433017-Brojabaksa Bazar-Kushodanga UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 287433021-Bamonkhali Bazar-Jugakhali UP rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
10 | 287434006-Improvement of Tin Bot-tala to Satpota bazar Via Nathpur Rd by BC (Ch. 1621-3622m) with 4nos. Pipe Drain Culvert at Ch. 1861m, 2090m, 2206m & 2465m and 1no. 625mmX600mm U-Drain at Ch. 2588m on the Same Road | KDRIDP/Sat/W-01/2016-17 | 2.001 | 0 | 0 | 121.34 | 2017-05-22 | Star Enterprise Munjitpur, Satkhira | 2017-07-02 | 119.46 | 0% | 2018-07-08 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 2,24,703/-
11 | 287434028-Improvement of Kesmot Elishpur-Chitla Bottola road at Ch. 2062-3680m | KDRIDP/Sat/ W-49/2017-18 | 1.618 | 0 | 0 | 111.62 | 2018-04-10 | Tasnim Enterprise Daulatpur, Khulna | 0 | 106.04 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 03.05.18
12 | 287434053-Improvement of Kalaroa-Saraskati R&H at Hamidpur More-Bamonkhali road at Ch. 1540-3115m | KDRIDP/Sat/ W-53/2017-18 | 1.575 | 0 | 0 | 111.359 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 114.69 | 0% | 2019-06-11 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 75036.00
13 | 287434059-(a) Improvement of Brojabaksah jamal More - Jhapagat Pukur road at Ch. 1175m-2605m by 25mm BC+7mm SC (b) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1439m & 2483m on the Same Road | KDRIDP/Sat/W-36/2017-18 | 1.403 | 0 | 0 | 91.18 | 2018-04-23 | M/S Swarnalata Enterprise, Kalaroa, Satkhira. | 0 | 86.62 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 10.05.18
14 | 287434057-(a) Improvement of Boyerdanga FRB - N. Kati Charabattala FRB road at (Ch. 00-1995m) by 25mm BC + 7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 746m and (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 15m & 1083m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 1302m on the Same Road | KDRIDP/Sat/W-18/2016-17 | 1.995 | 0 | 0 | 133.75 | 2017-07-17 | Star Enterprise Munjitpur, Satkhira | 2017-09-06 | 129.609 | 5% | 2018-09-12 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 4,24,435/-
15 | 287434061-Improvement of Kazirhat Bazar-Bahura Komorpur road at Ch. 2480-3520m | KDRIDP/Sat/ W-51/2017-18 | 1.04 | 0 | 0 | 73.28 | 2018-04-10 | Tasnim Enterprise Daulatpur, Khulna | 0 | 69.616 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 52529.00 NOA issued on 03.05.18
16 | 287434068-Improvement of Boalia Fakirpara Bazar-Bhadiali Bazar road at Ch. 499-1972m | KDRIDP/Sat/ W-40/2017-18 | 1.473 | 0 | 0 | 97.27 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk.1012925.00
17 | 287434072-Improvement of Bamonkhali Bazar-Batra Bazar road at Ch. 3980-5250m | KDRIDP/Sat/ W-52/2017-18 | 1.27 | 0 | 0 | 81.245 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 81.2 | 0% | 2019-06-11 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 21921.00 NOA issued
18 | 287434085-Brikrompur FRB-Hojoldi bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287435004-Improvement of Kayla-Morarikati road at Ch. 2593-4080m | KDRIDP/Sat/ W-50/2017-18 | 1.487 | 0 | 0 | 109.316 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 72128.00
20 | 287435018-(a) Improvement of Helatala UP Tile Fectory - Kashpur P/School more road at Ch 1599m - 3114m by 25mm BC+7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 2219m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 1745m, 2076m & 2739m on the Same Road. | KDRIDP/Sat/W-35/2017-18 | 1.515 | 0 | 0 | 100.56 | 2018-04-23 | Md. Rafiqul Islam, Kalaroa, Satkhira. | 2018-06-06 | 95.536 | 0% | 2019-06-12 | 0 | 0 | 0 | 0% | 0
21 | 287434093-Ofapur Govt.Primary School to Basantapur Govt. Primary School. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287435085-Improvement of Panchpota - Sonabaria bazar road at (Ch. 2944-3500m) by 25mm BC + 7mm SC | KDRIDP/Sat/W-19/2016-17 | 0.556 | 0 | 0 | 34.29 | 2017-07-17 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-09-06 | 33.606 | 35% | 2018-06-12 | 0 | 10.49 | -10.49 | 31.21% | 0
23 | 287435045-Hulhulia Notun Bazar More-Hulhulia Govt.Primary School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 287434035-Ramkesnopur hat khola more- Nurmohammad Gazi H/O road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 287435110-Improvement of Nathpur Khanpukur more - Nathpur Gazipara via Kamarepota road at (Ch. 00-575m) by 25mm BC + 7mm SC (b) Construction of 2nos. 315mm PVC Pipe Drain at Ch. 130m & 375m on the Same Road | KDRIDP/Sat/W-20/2016-17 | 0.575 | 0 | 0 | 35 | 2017-07-17 | G M Enterprise Kalaroa, Satkhira | 2017-09-06 | 36.55 | 60% | 2018-04-30 | 0 | 21.15 | -21.15 | 57.87% | 0
Maintenance
26 | 287432003-Baguri Beltala -Chandanpur GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287432006-Kalaroa- Tala via Dhandia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
28 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 25.578 | 0 | 0 | 1704.15 |  |  |  | 1462.432 | 10.89% |  | 0 | 322.889 | -322.889 | 22.08%

## Satkhira Sadar
Satkhira Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 287823010-Mahamudpur Bazar-Abaderhat Via Jaghanathpur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 287823020 - Improvement of Ghona Bazar - Kushkhali UPC Bhadra Ziader more road via Aruakhali GPS at ch 1665-2687m and 2687-3914m | KDRIDP/Sat/W-69/2017-18 | 2.25 | 0 | 0 | 170.68 | 2018-06-28 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 287823022-Agordari UP Office (Abadehat GC ) - Bharukhaki Bazar ( Bharukhali GPS) Road Via Jhitkee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 287823023-Bali UP office - Raipur Bazar road via Shumundanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
5 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 287824004-Bansdah UP Office-Kawan danga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287824009-Dhohakula FRB-Dhohakula R&H (Assasuni) road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 287824014-Improvement of Dhuliar- Damarpara WAPDA Embt road Ch.0.00-1000m | KDRIDP/Sat/ W-60/2017-18 | 1 | 0 | 0 | 72.74 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 420751.00
9 | 287824023-Taltala R&H to Kaikhali Mistripara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287824025-Brahmmorajpur Maniktala to Machkhola Hatkhola road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287824028-Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287824061-Faizullahpur more (Satkhira-Assasuni R&H) to Fingri UP Office road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 287825021-Gobindakati Satrano Battola-Reui Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287825016-Bhabanipur more-Toloigacha BDR Camp Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 287825060-Babulia FRB-Satkhira city College Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 287825062-Chandpur-Budhata Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287825133-Improvement of Brahmmorajpur Bazar to Chalerdangi RHD Assasuni road Brahmmorajpur Bazar to Baradal Pucca road via Dhulihor Chandra Pukur road at ch. 00-866m | KDRIDP/Sat/W-68/2017-18 | 0.866 | 0 | 0 | 62.69 | 2018-06-25 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.517797.00
18 | 287825187-Jadia Sheikhpara.GPS road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287825158-Bankal-Bagmari road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 287825107-Goalpota Hatkhola to Kamardangi Sluice Gate road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287824028-Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287824054-R&H poraton Satkhitra Machkhola road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
23 | 287824005-Matiadanga Khaya ghat-Khariadanga Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 287824008-Ghona-Vharukhali Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 287824011-Ghona BOP-Gazipur Golam Ali House Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287824003-Dhulihar puraton Bazar Khola more to Damarpota via Kazir house & Bardal Village road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287824007-Vatpara-Gharchala P/School Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 287824010-Chandpur bazar-Kulpota WAPDA Embt. Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287824016-Kumorpur R&H-Kumorpur WDB EMB Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287825041-Nehalpur WDB Emb. to Jugipota (Sukdebpur) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
31 | 287822010-Periodic Maintenance of Rasulpur R&H-Baikari UP via Pairadanga-Aruakhali via Mirgidanga road at Ch. 00-4200m | KDRIDP/Sat/ M-01/2017-18 | 4.2 | 0 | 0 | 105.51 | 2018-05-17 | Md. Ashraful Kabir Khokun, Katia, Satkhira | 0 | 110.785 | 0% | 0 | 0 | 0 | 0 | 0% | 0
32 | 287823010-Mahamudpur Bazar -Abaderhat via Jaghanathpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 287823024-Periodic Maintenance of Kulia Sreerampur Chubaria-Bhamra road at Ch. 00-1000m | KDRIDP/Sat/ M-03/2017-18 | 1 | 0 | 0 | 20.34 | 2018-05-17 | S.M. Shawkat Hossain, Katia, Satkhira | 0 | 21.35 | 0% | 0 | 0 | 0 | 0 | 0% | 0
34 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 287824004-Bansdah UP Office-Kawandanga Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 287824006-Binerpota bridge-Rajnagore Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 287824012-Puraton Satkhira R&H hat-Gobindopur Bazar Road via jiala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 287824032-Periodic Maintenance of Shaighoria R&H-Akhrakhola Bazar via Satianatala & Battala More road at Ch. 00-2752m | KDRIDP/Sat/ M-02/2017-18 | 2.752 | 0 | 0 | 57.8 | 2018-05-17 | Santa Mahmud, Kamalnagor, Satkhira | 0 | 60.11 | 0% | 0 | 0 | 0 | 0 | 0% | 0
39 | 287824032-Shaighoria R&H-Akhrakhola Bazar via Satiantala & Battala more road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 287824042-Shaighoria R&H-Babulia Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 287824050-Madabkati-Satani Bazar road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 287825145-Alipur Jangalar Bridge - Nathuar Danga Road via Kulpura Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
43 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 12.068 | 0 | 0 | 489.76 |  |  |  | 192.245 | 0% |  | 0 | 0 | 0 | 0%

## Tala
Tala
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287902001-Improvement of Tala-Kalaroa UP HQ via Dalua GC-Patkelghata GC road Tala Portion road by BC (Ch. 10020-11788m) with 1no. 925mmX900mm U-Drain at Ch. 11160m on the Same Road | KDRIDP/Sat/W-09/2016-17 | 1.94 | 0 | 0 | 160 | 2017-06-08 | M/S Basu Traders Tala, Satkhira | 2017-07-11 | 158.79 | 65% | 2018-07-17 | 0 | 95.59 | -95.59 | 60.2% | Salvage Amount Tk. 3,08,136/-
2 | 287902004-Jethua GC - Budhata GC Via Horihornagor Bazar Road(Tala portion). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 287902005-Improvement of Kopilmoni GC-Jatua GC road at Ch. 5465-6429m | KDRIDP/Sat/W-57/2017-18 | 0.964 | 0 | 0 | 78.67 | 2018-04-10 | Uttam Traders, Tala, Satkhira. | 2018-05-21 | 82.43 | 35% | 0 | 0 | 25 | -25 | 30.33% | 0
Improvement of Union Road by BC
4 | 287903003-Patkelghata GC(R&H) near Pollibiddut-Khalishkhali UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 287903006-(a) Improvement of Tala UP Office Hospital-Jatpur GC road by BC (Ch. 1596-5096m) (b) Construction of 6nos. 625mmX600mm U-Drain at Ch. 169m, 2896m, 3396m, 3641m, 3946m & 4616m and (c) Construction of 1no. 925mmX900mm U-Drain at Ch. 2286m on the Same Road | KDRIDP/Sat/W-10/2016-17 | 3.5 | 0 | 0 | 226.07 | 2017-06-12 | Md. Iqbal Jamader, Polashpole, Satkhira | 2017-07-16 | 223.62 | 60% | 2018-05-30 | 0 | 126.97 | -126.97 | 56.78% | Salvage Amount Tk. 1,39,115/-
6 | 287903013-Khesra UP-Dakshin Sahjadpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287903007-Improvement of Magura UP Office-Madra Bazar road at Ch. 1000-2215m | KDRIDP/Sat/ W-56/2017-18 | 1.215 | 0 | 0 | 79.239 | 2018-04-10 | M/S Raka Enterprise, Tala, Satkhira. | 2018-05-21 | 79.235 | 25% | 2019-04-20 | 0 | 15.293 | -15.293 | 19.3% | 0
| 287903015-Improvement of Islamkati UP Office-Magura Bazar road at Ch. 1000-2215m |  | 0.982 | 0 | 0 | 64.59 |  |  |  | 64.586 |  |  | 0 | 12.47 | -12.47 | 19.31%
8 | 287903011-Improvement of Nagarghata UP-Pulirhat road at Ch. 00-1670m | KDRIDP/Sat/ W-55/2017-18 | 1.67 | 0 | 0 | 116.069 | 2018-04-10 | Tasnim Enterprise Daulatpur, Khulna | 0 | 110.265 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 03.05.18
9 | 287903008-Tetulia UP office(Modonpur R & H) Ghone Bazar via Dewanipara Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287903013-Khesra UP-Dakshin Sahjadpur Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
11 | 287904004-Improvement of Manikhar-Ghorerdanga Road by 25mm BC+7mm SC (Ch. 00-1494m) with 4nos. 625mmX600mm U-Drain at Ch. 120m, 380m, 916m & 1309m on the Same Road. | KDRIDP/Sat/W-34/2017-18 | 1.494 | 0 | 0 | 105.99 | 2018-07-19 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | NOA issued on 10.05.18
12 | 287904011-Baliadha-Bolarumpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 287904018-Khalishkhali-Dalua. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287904057-Improvement of Sujansah Bazar R&H-Ghona Road at Ch. 1000-2140m | KDRIDP/Sat/W-70/2017-18 | 1.14 | 0 | 0 | 78.705 | 2018-06-28 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 287905031-Improvement of Magura girls school - joynwddin house Road at Ch. 00m - 995m |  | 0.995 | 0 | 0 | 69.59 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
15 | 287904064-Improvement of Sujanshoha Bazar Paranpur Israil house road at Ch. 00-1007m | KDRIDP/SAT/W-37/2017-18 | 1.007 | 0 | 0 | 71.786 | 2018-04-23 | M/S Roshni Enterprise, Tala, Satkhira. | 2018-06-06 | 74.765 | 0% | 2019-06-12 | 0 | 0 | 0 | 0% | 0
16 | 287904073-Improvement of Shalika College-Dalua GC road at Ch. 4500-8210m | KDRIDP/Sat/ W-54/2017-18 | 3.71 | 0 | 0 | 246.85 | 2018-04-19 | M/S Basu Traders Tala, Satkhira | 0 | 255.3 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 186115.00 W/O under process
17 | 287905147-Bathuadanga Primary school - Kalagachi Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287904010-Shahpur R&H – Hazrakati Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287904039-Barobila(UZR)- Sarulia Bazar via Barobila GPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 287904088-Bhairabnagar R&H- Akrakhola Bazar via Nagarghata UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287905134-Boyardanga UZR - Mokolandokati GPS via Pakshia Durgha Mondir Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287905185-Daibari mor - H/O Intaz Golder via maspara Mosjid Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 287905108-Improvement of Majiara (House of Azhar Ali more) Khorerdanga Bazar Road by BC (Ch. 118-2024m) with 1no. 625mmX600mm U-Drain at Ch. 1040m on the Same Road | KDRIDP/Sat/W-06/2016-17 | 1.906 | 0 | 0 | 129.44 | 2017-05-22 | M/S Roshni Enterprise Tala, Satkhira | 2017-06-22 | 126.53 | 100% | 2018-06-28 | 126.47 | 126.47 | 0 | 99.95% | Final (Salvage Amount Tk. 22,97,337.00)
24 | 28790516-Kazidanga H/O-Dr. Aminuddin Gazi-Kharail,Bhabanipur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
25 | 247904059-Dakin Sahajadpur Launch ghat-Kathipara bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287864101-Biramolla hat Kawser gazi bari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
27 | 287902005-Tala-Kopilmoni GC via Jatua GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 287904048-Kanchanpur Eidgah (R & H)-Hizaldanga Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287904088-Bhairabnagor R&H Road - Akrakhola Bazar via Nagorghata UP RD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287905096-Islamkati Primary School - Vagba House of Abdul Malek Mohalder Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287904115-Kumira R&H - Magura Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
32 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 20.523 | 0 | 0 | 1426.999 |  |  |  | 1175.521 | 8.906% |  | 126.47 | 401.793 | -275.323 | 34.18%

## Shyamnagar
Shyamnagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287862002-Improvement of Nowabenki GC - Khanpur R&H via Vetkhali GC road at (Ch. 27100-29000m & Ch. 32300-34100m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 27350m, 27800m & 33200m on the Same Road | KDRIDP/Sat/W-11/2016-17 | 3.7 | 0 | 0 | 321.22 | 2017-10-09 | mewebajv Shyamnagar, Satkhira | 2017-12-03 | 330.37 | 65% | 0 | 0 | 199.21 | -199.21 | 60.3% | 1st R/A
2 | 287862005-Pakhimara R&H -Protapnagar GC Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 287863003-Nakipur-Sirajpur hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 287863004-Improvement of Iswaripur UP-Harinagar hat via Dhumkali Road by BC (Ch. 00-4090m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 210m, 3305m & 3950m on the Same Road | KDRIDP/Sat/W-04/2016-17 | 4.09 | 0 | 0 | 279.02 | 2017-05-25 | M/S Rabeya Traders Dhaka | 2017-06-14 | 273.53 | 45% | 2018-06-20 | 0 | 32.875 | -32.875 | 12.02% | Salvage Amount Tk. 38,60,858/-
5 | 287863013-Improvement of Iswaripur UP-Paranpur hat via Ramjannagar Road by BC (Ch. 1900-3475m) | KDRIDP/Sat/W-05/2016-17 | 1.575 | 0 | 0 | 102.54 | 2017-05-22 | M/S Rabeya Traders Dhaka | 2017-06-14 | 95.93 | 10% | 2018-06-20 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 13,04,167/-
6 | 287863017-Improvement of Iswaripur UP- Gumantali hat via Golabari Ghat Road by BC at Ch. 2730-4500m. | KDRIDP/Sat/ W-75/2017-18 | 1.77 | 0 | 0 | 144.026 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 28783012-Noornagar-Kultali Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 287864007-Improvement of Iswaripur FWC - Beramollah Hat road at (Ch. 00-3000m) & Construction of 7.0m Long 600mmX600mm U-Drain at Ch. 368m on the Same Road | KDRIDP/Sat/W-12/2016-17 | 3 | 0 | 0 | 182.52 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 187.9 | 45% | 2018-11-25 | 0 | 71.267 | -71.267 | 37.93% | Salvage Amount Tk. 2,62,483/-
9 | 287864026-Ramjibonpur More-Horinagari Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287864038-ZR at Sonaremore-Fulbari-Chigrikhali road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287864040 Chandipur R&H-Sankarkati hat-Majhergonj hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287864048-Improvement of Jotindanagar hat-Manikhali R&H road at Ch. 9180-11180m | KDRIDP/Sat/W-43/2017-18. | 2 | 0 | 0 | 148.917 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 641202.00
13 | 287864062- Munshigonj Bazar-Garrage hat Bridge. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287864077 Jadappur Pucca road-Kallyanpur Sluicegate-Chingrikhali road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 287864102- Improvement of Biramollah hat Kowsar Gazi bari road at (Ch. 1000-2200m) | KDRIDP/Sat/W-15/2016-17 | 1.2 | 0 | 0 | 73.26 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 75.4 | 55% | 2018-11-25 | 0 | 38.97 | -38.97 | 51.68% | Salvage Amount Tk. 5,06,656/-
16 | 287864102-Improvement of Khagraghat H/O Fazlul Haque- R & H road by BC.Ch0.00m-1100m | KDRIDP/Sat/W-48/2017-18 | 1.1 | 0 | 0 | 76.22 | 0 | M/S Asa Construction, Shyamnagar, Satkira | 2018-04-22 | 80.03 | 0% | 2019-04-21 | 0 | 0 | 0 | 0% | 0
17 | 287864119- Badaghata-Anowara khatun Mohila Madrasa via Muktijoddha. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287865149- Improvement of Mohendrakata - Badda house road at (Ch. 00-1650m) & Construction of 2nos. 7.0m Long 600mmX600mm U-Drain at Ch. 1100m & 1400m on the Same Road | KDRIDP/Sat/W-13/2016-17 | 1.65 | 0 | 0 | 99.52 | 2017-10-09 | Md. Abdul Hakim Situlpur, Kaligonj | 2017-11-19 | 103.965 | 40% | 2018-10-06 | 0 | 22.52 | -22.52 | 21.66% | 1st R/A
19 | 287864110-Improvement of Biramollah hat - Ruhit Majhi - Dakin Srifalkati road at (Ch. 1000-2718m) | KDRIDP/Sat/W-14/2016-17 | 1.718 | 0 | 0 | 104.69 | 2017-07-16 | M/S Asha Construction Ishwaripur, Shyamnagar, Satkhira | 2017-09-20 | 109.897 | 60% | 2018-07-22 | 0 | 62.34 | -62.34 | 56.73% | Salvage Amount Tk. 1,74,989.00
20 | 287864148-Improvement of Padmapukur R&H-Baintala GPS road at Ch. 00-2000m | KDRIDP/Sat/W-42/2017-18. | 2 | 0 | 0 | 85.906 | 0 | Md. Iqbal Jamader Polashpole, Satkhira | 2018-04-24 | 85.65 | 0% | 2019-04-20 | 0 | 0 | 0 | 0% | 0
21 | 28785149-Mohendrokata-Baidda house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287864045 - Improvement of Sapkhali - Kaikhali BOP Road by BC at Ch.00m-3000m | KDRIDP/Sat/W-71/2017-18 | 3 | 0 | 0 | 199.436 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.2092433.00
23 | 287864031-Improvement of Hawalbhangi-Baduria road at CH. 00-2651m | KDRIDP/Sat/ W-75/2017-18 | 2.615 | 0 | 0 | 187.5 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 287864100-Dumuria Bazr-Parsheemari Kheyaghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 287865048-Improvement of Jada more-Gani Mollik road at (Ch. 00-1500m) | KDRIDP/Sat/W-21/2017-18 | 1.5 | 0 | 0 | 105.17 | 2017-08-31 | Molla Engineering Workshop Shyamnagar, Satkhira | 2017-10-09 | 109.27 | 20% | 2018-05-25 | 0 | 7.59 | -7.59 | 6.946% | Salvage Amount Tk. 2,04,581/-
26 | Gorkumarpur Bazar to Diglarait Moszid. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287864041-Zr. Moutala-Tajhori hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 287864105-Ishakur LGED Packa road-Jhasghata Sha Mosque road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287865036- Improvement of Bongshipur-Azad Gazi road at CH. 00-950m | KDRIDP/Sat/ W-38/2017-18 | 0.95 | 0 | 0 | 76.196 | 2018-06-25 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 594005.00
Maintenance
30 | 287862002-Nowabenki GC-Khanpur R&H via Vetkhali GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287863007-Burigoalini UP-Nildumur hat Masud more via Durgabati Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 287863009-Nakipur GC-Chandipur hat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 287864074-Soalia Mosque-Kallanpur Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 287864077-Jadabpur Pacca road-Kallanpur Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 287864146-Nurnagar-Ramchandrapur-Habibpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 287863002 Kasimari UP-Jhapali hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 287864041 ZR at Moutala-Teghori hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Landing/ Riverghat
38 | Garkunerpur bazar ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
39 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 31.868 | 0 | 0 | 2186.141 |  |  |  | 1451.942 | 8.718% |  | 0 | 434.772 | -434.772 | 29.94%

## Debhata
Debhata
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287252007-Improvement of Subornabad GC-Bangdah GC Road by BC (Ch. 3240-5240m) with 15nos. 625mmX600mm U-Drain at Ch. 3241m, 3275m, 3352m, 3529m, 3568m, 3678m, 3705m, 3952m, 4093m, 4291m 4539m, 4642m, 4816m, 5032m & 5058m on the Same Road. | KDRIDP/Sat/W-08/2016-17 | 2 | 0 | 0 | 165.74 | 2017-05-22 | M/S Habib Enterprise Satkhira | 2017-06-14 | 173.1 | 35% | 2018-06-20 | 0 | 56.99 | -56.99 | 32.92% | Salvage Amount Tk. 8,93,628/-
2 | 287252008-Improvement of Bohera Bazar (RHD) - Ellarchor Bazar -Bangdah GC(Sadar) Road by BC (Ch. 6704-8000m) with 3nos. 625mmX600mm U-Drain at Ch.7050m, 7640m & 7775m and 1no. 900mmX900mm U-Drain at Ch. 7700m on the Same Road | KDRIDP/Sat/W-07/2016-17 | 1.296 | 0 | 0 | 87.3 | 2017-05-22 | M/S Joint Bricks Traders Bankal, Satkhira | 2017-07-02 | 84.78 | 90% | 2018-07-08 | 0 | 76.054 | -76.054 | 89.71% | 0
3 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 8000-9660m | KDRIDP/Sat/W-61/2017-18 | 1.66 | 0 | 0 | 146.46 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0
4 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 9660m-11910m | KDRIDP/Sat/W-62/2017-18 | 2.25 | 0 | 0 | 186.566 | 2018-07-26 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage amount Tk. 422153.00
Improvement of Union Road by BC
5 | 287253002-Sakhipur UP-Nangla Bazar via Eidgah Chandipur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 287253003-Debhata UP Office-Komorpur Road(Debhata Portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287253005-Nowapara UP -Bodarhata GC via Chandpur Atapur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 287254001-Sekendra R&H-WDB Embankment (Ghariadanga) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 287254006-North Parulia R&H-Naziergheer Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287254021-Konra Pakralala R&H-Kazimoholla Samsuddin M. House Road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287254035-Debhata Parulia UZR-Bhatshala Cyclone Shelter Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287254037-Sushilgati FRB-Eidgah Sakhipur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 287254045-Badartola Bazar-Rangashisha Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 287255032-Ratanshapur Babar Ali Shop-Teyor GCCR Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287255175-Improvement of Shakhipur Mosque - Khegurbaria Southpara Mosque road at Ch 00-1135m with 2nos. 625mmX600mm U-Drain at Ch.62m & 560m on the Same Road | KDRIDP/Sat/W-59/2017-18 | 1.135 | 0 | 0 | 92.117 | 2018-04-23 | Md. Shajahan Alam, Kaligonj, Satkhira. | 2018-06-06 | 96.61 | 0% | 2019-06-12 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 863133.00
15 | 287255075-Improvement of Shakhipur Nimay house - Lakhimi Kanta house road at Ch 00-1038m with 3nos. 625mmX600mm U-Drain at Ch.450m, 615m & 892m on the Same Road. |  | 1.038 | 0 | 0 | 81.768 |  |  |  | 85.758 |  |  | 0 | 0 | 0 | 0% | Salvage Amount Tk. 1536290.00
16 | 287254033-Subornabad FRB-Darer khal Ferry ghat Via Shasadanga Madrasha). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287254043-Improvement of Shakhipur Bazar - Bhatshala UNR WDB Embankment road at Ch 00-6210m | KDRIDP/Sat/W-58/2017-18 | 6.21 | 0 | 0 | 418.94 | 2018-06-25 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 1384326.00
18 | 287255045-Chaltatola-Synnasir chack via roingashisha( WDB) Emabankmnet road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18.784 | 287255153-Parulia Sunial Desh House- Jhal Bagen Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19.6245 | 2872555130-pubo kulia bridge tosadesh hachari Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
21 | 287254013-Gazirhat- Kalabaria via Borohula Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
22 | 287252008-Periodic Maintenance of Bohera Bazar RHD-Ellarchor Bazar-Bangdah GC road at Ch. 00-1735m | KDRIDP/Sat/ M-04/2017-18 | 1.735 | 0 | 0 | 47.5 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 49.39 | 0% | 2018-11-23 | 0 | 0 | 0 | 0% | 0
23 | 287254025-Periodic Maintenance of Hadipur R&H-Hadipur Masrasha via Ashkarpur Alimiya Kallyan Sangoshta road at Ch. 1145-2296m | KDRIDP/Sat/ M-05/2017-18 | 1.151 | 0 | 0 | 15.6 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 16.22 | 0% | 2018-11-23 | 0 | 0 | 0 | 0% | 0
24 | 287254038-Periodic Maintenance of Parulia R&H-Debhata Parulia GCR via Sakhipur Dhopadanga road at Ch. 00-1045m | KDRIDP/Sat/ M-06/2017-18 | 1.045 | 0 | 0 | 20.519 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 21.33 | 0% | 2018-11-23 | 0 | 0 | 0 | 0% | 0
25 | 287255070-Nowapara Nawser house-Bibuti`s house Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
26 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 19.52 | 0 | 0 | 1262.51 |  |  |  | 527.188 | 4.808% |  | 0 | 133.044 | -133.044 | 25.24%

## Assasuni
Assasuni
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287042010-Chiledanga RHD - Bangadah GC Paithali Bazer Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 287042012-Mohishkur RHD - Bashtala bazar via Mohishkur GC Road (Assasuni part). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 287042013-Protapnagar GC-Pakhimara RHD(Assasuni part). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 287043001-Kadakati UP office - Kadakati GC via Gabtala Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 287043004-Ekshora bazar-Bichotbazar(Anulia UP) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 287043008-Dargapur UP Office-Tentulia Bazer Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287043010-Paithali Bazar - Sobhnali UP office via Kamalkati kheyaghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 287043011-Bardal UP office - Kapsanda Bazar via Baintala & Fatikkhali road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 287044018-Badartala-Mozgurkhali Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287044089-Agordhari-Gabtala via Kampura rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287044094-APS Collage-Gokulnagar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287045059-Improvement of Agordari Dhalibari- Hazi bari Graveyard via Agordari High School road at ch.00-1330m. | KDRIDP/Sat/W-65/2017-18 | 1.33 | 0 | 0 | 110.796 | 2018-06-25 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.134268.00
| 287044119-Improvement of Kachua Girls high School- Agordari High School road at ch.00-1380m. |  | 1.38 | 0 | 0 | 107.55 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.670148.00
| 287044156-Improvement of Agordari west para Mosque- Kadakati GC road at ch.00m-1445m. |  | 1.445 | 0 | 0 | 117.238 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 299347.00
13 | 287045057-Sreeulia R&H-Sreeulia UP Office road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287045066-Natana bazar - Hashkhali GPS via Hashkhali culvert road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 287045092-Sreeula foot ball field - Sluce gare via Jela parishad road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 287044133-Kurikahunia Makbul Dokanderer Bari - Nakna Gazibari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287044034-Sriula R&H-Sriula Shashibari Bridge via BD Chow house. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287044030-Budhata Bazar to Budhata Pr.School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287045064-Mohishadanga High school-Ganesher Khey ghat via H-O. Kishor Babu. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 287044051-Mohistpur- Boyershing khal road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287045126-Badar tola Hazi Jallauddin Collage- Mozjurkhali Pr.School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287045072-Sreeula Molla Bari Mosque road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 287044228-Godaipor-Rautara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
24 | 287044032-Naktara FRB to Baliakhali WAPDA via Radharati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 287044179-Tuardanga Culvert - Bamondanga bridge via Tuardanga Paschimpara Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
26 | 287043012-Construction of Bridge on Sovnali UP-Nashukhali bazar via paschim Kamalkati Radha Shyamsundar Mandir road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287044188-Construction of Bridge on Gazir hat-Chumuria road over Morischap khal. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
28 | 287042001-Assasuni GC-Manikkhali ferryghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287042010-Chiledanga RHD -Bangdah GC Road via Paithali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287043002-Khazra UP- Bordol GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287043008-Dargapur UP Office -Tentulia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 287044088-Gunaharkati Bazar-Mohajanpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 287044089-Agordhari-Gabtola via Humkura Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
34 | Construction of East Nakna Bazar Chairman Bazar GC | KDRIDP/Sat/ GC-09/2017-18 | 0 | 0 | 1 | 20.59 | 2018-04-10 | Md. Abul Hossain Kamalnagar, Satkhira | 2018-05-06 | 20.26 | 0% | 2018-11-12 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
35 | Boundhir Khyaghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
36 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 4.155 | 0 | 1 | 356.174 |  |  |  | 20.26 | 0% |  | 0 | 0 | 0 | 0%

## Summary
SATKHIRA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 9 | 5 | 20.795 | 0 | 0 | 829.47 | 452.844 | 58% | 54.59%
Union Road by BC | 13 | 10 | 28.227 | 0 | 0 | 1578.981 | 549.227 | 43% | 34.78%
Village Road by BC | 41 | 24 | 81.482 | 0 | 0 | 2837.039 | 430.797 | 21.14% | 15.18%
Village Road by HBB | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Upazila Road | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Maintenance | 6 | 5 | 11.883 | 0 | 0 | 279.185 | 0 | 0% | 0%
GC-Hat | 2 | 2 | 0 | 0 | 2 | 40.46 | 0 | 0% | 0%
Landing/ Riverghat | 1 |  | 0 | 0 | 1 | 0 | 0 | 0% | #DIV/0!
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 72 | 46 | 142.387 | 0 | 3 | 5565.135 | 1432.868 | 12.21% | 25.75%