## Jessore
JESSORE
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Jessore Sadar
1 | 241472009-Rupdia GC-Basundia Moor RHD via Shakarigati Road | KDRIDP/Jess/W-81/2017-18 | 2.71 | 0 | 0 | 224.256 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 17/05/2018
2 | 241472012-Razarhat GC-Hamidpur RHD Road | [13 empty] | 0 | #DIV/0!
3 | 241472013-Jongle Bandle RHD-Basundia GC Road | [13 empty] | 0 | #DIV/0!
4 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch: 7500-9350m. [Salvage Cost Tk. 28,17,772.00 ] | KDRIDP/Jess/W-14/2016-17 | 1.85 | 0 | 0 | 128.13 | 2017-05-29 | M/S Morol Enterprise Balia, Vakutia Bazar, Sadar, Jessore | 2017-12-07 | 128.11 | 50% | 2018-06-19 |  |  | 0 | 0%
5 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch:10416-11460m under Upazila: Sadar, District: Jessore. | KDRIDP/Jess/W-82/2017-18 | 1.044 | 0 | 0 | 78.89 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore |  | 82.83 | 0% | [5 empty] | NOA Date 27/05/2018
Bagherpara
6 | 241092006-Simakhali RHD-Narikelbaria GC Rd. | [13 empty] | 0 | #DIV/0!
7 | 241092011-Dhalgram GC- Maijpara UP to Kalukhali | [13 empty] | 0 | #DIV/0!
8 | 241092014-Improvement of Narikelbaria GC Bunagati GC (Shersha Sarak) Road. From Ch: 700-3270m. [salvage Cost Tk.20,890.00] | KDRIDP/Jess/W-96/2017-18 | 2.57 | 0 | 0 | 199.065 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 21/05/2018
9 | 241092018 Improvement of Narikelbaria GC - Monohorpur Bazar RHD at Joynagor More via Raypur UP (Bagherpara Part) Road. From Ch: 406-4144m,5400-5987m & 6372-7057m. [salvage Cost Tk.95,88,834.00] | KDRIDP/Jess/W-67/2017-18 | 5.01 | 0 | 0 | 396.55 | [8 empty] | 0 | #DIV/0!
Abhoynagar
10 | 241042005-Nowapara Upazila H/Q (Sankerpasha Bazarghat)-Amtala GC via Vatpara Bazar Rd. | [13 empty] | 0 | #DIV/0!
11 | 241042012-Nowapara GC (Shankerpasha Ghat)-Gobra GC via Borni Bazer road From Ch. 293-28450m [Salvage Cost Tk. 56,24,401.00] | KDRIDP/Jess/W-76/2017-18 | 2.552 | 0 | 0 | 199.92 | 2018-02-19 | Md. Abdur Rouf Molla, Bhoakhali, Ratangonj, Narail | 2018-04-18 | 210 | 0% | 2018-01-09 |  |  | 0 | 0%
Jhikargacha
12 | 241232012 : Navaran puraton Bazar-Seordah GC Road. | [13 empty] | 0 | #DIV/0!
13 | 241232015-Jhikargacha Rhana Hospital More-Goaldha Bazar via Padmapukur Kashipur Rd. | [13 empty] | 0 | #DIV/0!
14 | 241232016 : Hazirbag UZR-Matikumra UZR via Hazirbag UPC & MatiKumra Bazar. | [13 empty] | 0 | #DIV/0!
Monirampur
15 | 241612008-Monirampur-Mukterpur Road | [13 empty] | 0 | #DIV/0!
16 | 241612018-Dighirpar-Dumurkhali Bazar Road | [13 empty] | 0 | #DIV/0!
Sarsa
17 | 241902004-Improvement of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra Road From Ch.5064-7300m, 8725-9225m & 12150-15397m. [Salvage Cost Tk.18,35,766.00] | KDRIDP/Jess/W-33/2017-18 | 5.983 | 0 | 0 | 436.357 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 419.76 | 50% | 2018-10-15 |  | 139.79 | -139.79 | 33.3%
Keshabpur
18 | 241382005 Improvement of Chingra-Rajgonj via Trimohani UP (Keshabpur Portation) Road From Ch. 12600-13440m | KDRIDP/Jess/W-99/2017-18 | 0.8 | 0 | 0 | 68.496 | 2018-05-27 | M/S Alom Enterprise Bagda, Keshabpur, Jessore |  | 71.9 | 0% |  |  |  | 0 | 0% | NOA Date 14/06/2018
19 | 241382009 Mongalkot UP-Saraskati bazar | [13 empty] | 0 | #DIV/0!
Total |  |  | 22.519 | 0 | 0 | 1731.664 |  |  |  | 912.6 | 20% |  | 0 | 139.79 | -139.79 | 15.32%
Improvement of Union Road by BC
Jessore Sadar
1 | 241473003-Improvement of Lebutala UP Office-Shyamnagar via Fultola Bazar Road. From Ch:5423-7723m & 9450-10236m. [Salvage Cost. Tk.42,07,378.00] | KDRIDP/Jess/W-54/2017-18 | 3.086 | 0 | 0 | 221.42 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
2 | 241473005-Upashahor UP-Dolennagar Bazar Rd via Kashimpur Rd. | [13 empty] | 0 | #DIV/0!
3 | 241473007-Chanchra UP office-Kuadah Bazar via Sarapol Rd. | [13 empty] | 0 | #DIV/0!
4 | 241473010-Improvement of Chanchra Bazar-Chanchar UP via Vaturia(Jessore Khulna Hogway Beltolarmore Bormonpara Nodermore via Chanchra High School) Road. From Ch:00-1300m. [Salvage Cost. Tk.12,59,686.00] | KDRIDP/Jess/W-101/2017-18 | 1.3 | 0 | 0 | 86.959 | [8 empty] | 0 | #DIV/0!
5 | 241473011-Natunhat-Deara UP office via Dattopara Rd. | [13 empty] | 0 | #DIV/0!
6 | 241473019-Arabpur UP Office-Faridpur Old Bazar Rd. | [13 empty] | 0 | #DIV/0!
7 | 241473020-Haibatpur UP-Ambottola via Kamalpur, Shahabajpur Rd. | [13 empty] | 0 | #DIV/0!
8 | 241473021-Churamonkati UP Office-Khojar Hat Rd (Kashimpur UP) Rd. | [13 empty] | 0 | #DIV/0!
9 | 241473022-Fatehpur UP Office-Bablatola Bazar Rd. | [13 empty] | 0 | #DIV/0!
10 | 241473024-Labutola UP-Andolpota via Agrail, Enayetpur Rd. | [13 empty] | 0 | #DIV/0!
11 | 241473025-Lawjani Bazar-Deeara UP Office via Narangali Bazar Rd. | [13 empty] | 0 | #DIV/0!
12 | 241473030-Ichali UP (Bangda more) - Labutala Bazar via Rajapur (RHD) . | [13 empty] | 0 | #DIV/0!
13 | 241473031-Pulerhat - Arabpur UP (Mondalgati) Road | [13 empty] | 0 | #DIV/0!
14 | 241473001-Improvement of Chowlia Gate-Sutighata Ramnagar UP Office Road. From Ch:2660-4255m. [Salvage Cost. Tk.37,44,628.00] | KDRIDP/Jess/W-68/2017-18 | 1.595 | 0 | 0 | 107.517 | 2018-05-28 | M/S Jamuna Prokousoli, Hatkhola Road, Jessore |  | 112.87 | 0% |  |  |  | 0 | 0% | NOA Date 14/06/2018
Bagherpara
15 | 241093003-Bandabila UP- Puinerhat | [13 empty] | 0 | #DIV/0!
16 | 241093008-Improvement of Joharpur up office-Betalpara Bazar Road. From Ch: 1900-3250m. [salvage Cost Tk.5,096.00] | KDRIDP/Jess/W-97/2017-18 | 1.35 | 0 | 0 | 99.547 | 2018-05-21 | M/S Monir Traders Natun Khayertala, Jessore |  | 104.5 | 0% |  |  |  | 0 | 0% | NOA Date 05/06/2018
| 241093010-Improvement of Raipur UP Office-Vater bazar Road. From Ch: 3611-3997m & 4689-5620m. [salvage Cost Tk.24,19,116.00] |  | 1.317 | 0 | 0 | 87.845 |  |  |  | 92.22 |  |  |  |  | 0 | 0%
17 | 241093013-Vangura RHD.-Dhalgram UP Rd. | [13 empty] | 0 | #DIV/0!
18 | 241093014-Vangura RHD.-Basundia UP Rd. | [13 empty] | 0 | #DIV/0!
19 | 241093017-Simakhali UP- Johurpur UP via Betalpara Bazar, Premchara. | [13 empty] | 0 | #DIV/0!
20 | 241093018-Dhalgram UP- Garerhat Bazar via Antaikhola | [13 empty] | 0 | #DIV/0!
Abhoynagar
21 | 241043002-Improvement of Chengutia Bazar-Sreedharpur UP Office Road From Ch. 1217-3600m | KDRIDP/Jess/W-01/2016-17 | 2.383 | 0 | 0 | 144.16 | 2017-05-15 | Md. Abdur Rouf Molla , Bhoakhali, Ratangonj, Narail | 2017-07-06 | 150.3 | 100% | 2018-04-30 | 150.285 | 150.285 | 0 | 99.99% | Final
22 | 241043004-Nowapara H/Q (Peer Bari Kheya ghat)-Baghutia U.P. Office via Maddhapur Pry.School ,Bogratala Mosque & Chow matha,Vatpara Gramin Bank Road. | [13 empty] | 0 | #DIV/0!
23 | 241043006-Paira U.P.Office-Chalisha U.P.Office (Bagdah Dharmatala Eid-gah) via Kuta madrasha,Bagdah Paschimpara Baltala More Road. | [13 empty] | 0 | #DIV/0!
24 | 241043007-Sundali U.P.Office-Moshihati Bazar Road. | [13 empty] | 0 | #DIV/0!
25 | 241043010-Baghutia UP office-Singari Bazar via Singari Dakhil Madrasha Road. | [13 empty] | 0 | #DIV/0!
26 | BTMC ghat -Barni Bazar via Sreedarpur UP Complex Road. | [13 empty] | 0 | #DIV/0!
Chowgacha
27 | 241113003:( Singahjhully UP Office-Rashtampur bazar via Koyarpara Road.) | [13 empty] | 0 | #DIV/0!
28 | 241113005-Improvement of Nimtala bazar-Pasapole bazar via Pasapole UP Office Road Ch: 3120-3520m & 4020-4120m. | KDRIDP/Jess/W-106/2017-18 | 0.5 | 0 | 0 | 32.407 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
29 | 241113008-Improvement of Shingo jhuli UP-Marua bazar Road. From Ch:3000-3495 m. | KDRIDP/Jess/W-16/2017-18 | 0.495 | 0 | 0 | 28.22 | 2017-08-07 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-02 | 29.57 | 90% | 2018-08-13 |  | 14.83 | -14.83 | 50.15%
30 | 241113012- Improvement of Jogodishpur-Arpara GC Road From Ch: 2025-3525m. | KDRIDP/Jess/W-91/2017-18 | 1.5 | 0 | 0 | 89.331 | 2018-04-18 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore |  | 93.67 | 0% |  |  |  | 0 | 0%
31 | 241113013-Swarupda UP-Sukpukuria U.P Office Rd. | [13 empty] | 0 | #DIV/0!
32 | 241113016-Swarupda UP Office-Kharincha Bazar Road. | [13 empty] | 0 | #DIV/0!
33 | 241113020- Solua GCCR-Pashapole UP Office Road. | [13 empty] | 0 | #DIV/0!
Jhikargacha
34 | 241233001-Improvement of Parbazar-Chutipur bazar (Gongganandapur UP) Road From Ch. 5775 - 9925m | KDRIDP/Jess/W-49/2017-18 | 4.15 | 0 | 0 | 290.13 | 2018-03-13 | M/S Monir Traders Natun Khayertala, Jessore | 2018-04-04 | 316.09 | 15% | 2019-01-13 |  |  | 0 | 0%
35 | 241233002-Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP) Rd. | [13 empty] | 0 | #DIV/0!
36 | 241233004 : Improvement of Lawjani bazar-Jhikargacha Katakhal bazar(Shahid Rafique Sarak) Road From Ch. 00 - 162m & 600-1750m | KDRIDP/Jess/W-47/2017-18 | 1.312 | 0 | 0 | 82.48 | 2017-10-30 | M/S Monir Traders Natun Khayertala, Jessore | 2017-11-30 | 79.39 | 65% | 2018-07-20 |  | 29.32 | -29.32 | 36.93%
37 | 241233006 : Improvement of Seordah GC-Moheshpara Road From Ch. 3750 - 6350m | KDRIDP/Jess/W-48/2017-18 | 2.6 | 0 | 0 | 146.91 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 140.85 | 50% | 2018-03-12 |  | 43.26 | -43.26 | 30.71%
38 | 241233008 : Bakra UP-Jhapa (Bridge) Bazar | [13 empty] | 0 | #DIV/0!
39 | 241233009 : Bakra bazar(Bakra UP)-Matshia bazar. | [13 empty] | 0 | #DIV/0!
40 | 241233012 : Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More. Road From Ch. 6460 - 8350m. [Salvage Cost Tk. 6,982.00] | KDRIDP/Jess/W-83/2017-18 | 1.89 | 0 | 0 | 151.4 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 18/03/2018
41 | 241233013 : Improvement of Magura New Market-Magura UP office Road From Ch. 492 - 1300m [Salvage cost Tk. 2,37,171.00] | KDRIDP/Jess/W-50/2017-18 | 0.81 | 0 | 0 | 54.34 | 2017-10-30 | MD. Humayun Kabir Nobarakpur, Jhikorgacha, Jessore | 2017-11-30 | 49.06 | 100% | 2018-04-22 | 45.885 | 45.885 | 0 | 93.53% | Final
42 | 241233017 : Godkhali UP-Bodhkhana bazar | [13 empty] | 0 | #DIV/0!
43 | 241233018 : Improvement of Barbakpur bazar-Simulia UP Road From Ch. 00-1150m. | KDRIDP/Jess/W-51/2017-18 | 1.15 | 0 | 0 | 75.47 | 2017-10-26 | M/S Jamuna Prokousoli Hatkhola Road, Jessore | 2017-12-12 | 75.17 | 100% | 2018-09-16 | 75.129 | 75.129 | 0 | 99.95% | Final
44 | 241233024 : Shimulia UP-Gorpara GC | [13 empty] | 0 | #DIV/0!
45 | 241233025 : Godkhali bazar-Panishara UP(Borni bazar). | [13 empty] | 0 | #DIV/0!
46 | 241233026 : Shimulia UP-Godkhali bazar. | [13 empty] | 0 | #DIV/0!
47 | 241233027 : Shimulia UP-Navaran UP (at Kalagachi RHD). | [13 empty] | 0 | #DIV/0!
48 | 241233028 : Lawjani Bazar(Jhikargacha UP)-Naranggali bazar(Sadar) | [13 empty] | 0 | #DIV/0!
49 | 241233029 : Jhikargacha GC-Jhikargacha UP(Lawjani Bazar) | [13 empty] | 0 | #DIV/0!
Monirampur
50 | 241613001-Improvement of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 3500-6420m | KDRIDP/Jess/W-03/2016-17 | 2.92 | 0 | 0 | 176.63 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-06-01 | 168.71 | 100% | 2018-04-26 | 168.67 | 168.67 | 0 | 99.98% | Final
51 | 241613002-Chalkidanga Bazar-Rohita UP via Kashimnagar UP Road | [13 empty] | 0 | #DIV/0!
52 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia Road | [13 empty] | 0 | #DIV/0!
53 | 241613006-mprovement of Chalkidanga Bazer-Haridashkati UP via Joypur bazar Road From Ch. 4371-5800m | KDRIDP/Jess/W-44/2017-18 | 1.429 | 0 | 0 | 92.44 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 91.41 | 100% | 2018-07-15 |  | 49.86 | -49.86 | 54.55%
54 | 241613009-Improvement of Nehalpur UP-Hazirhat bazar via Kultia UP Road From Ch. 00-3557m | KDRIDP/Jess/W-04/2016-17 | 3.557 | 0 | 0 | 231.18 | 2017-10-22 | M/S Motinur Rahaman Nannu, 57, Chalk Bazar, Faridpur | 2017-11-16 | 250.7 | 60% | 2018-02-12 |  | 125.52 | -125.52 | 50.07%
55 | 241613011-Improvement of Sundalpur bazar-Haridashkati UP via Salimpur Road From Ch. 9050-10920m. [Salvage Cost Tk. 1,73,331.00] | KDRIDP/Jess/W-103/2017-18 | 1.87 | 0 | 0 | 137.89 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
| 241613019-Improvement of Khanpur UP-Horidaskati UP Road From Ch. 2550-3380m. [Salvage Cost Tk. 13,90,230.00] |  | 0.83 | 0 | 0 | 61.04 | [8 empty] | 0 | #DIV/0!
56 | 241613012-Improvement of Bhojgati UP-Dhakuria UP via Horergati Road From Ch. 1000-4810m. [Salvage Cost Tk. 3,15,834.00] | KDRIDP/Jess/W-79/2017-18 | 3.81 | 0 | 0 | 270.36 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 17/05/2018
57 | 241613013-Improvement of Tangramari-Khedapara U.P.via Jalalpur Road From Ch. 00-2120m. [Salvage Cost Tk. 54,342.00] | KDRIDP/Jess/W-77/2017-18 | 2.12 | 0 | 0 | 151.21 | 2018-05-27 | M/S Biswajit Construction, 9 Rail Road, Jessore |  | 155.72 | 0% |  |  |  | 0 | 0% | NOA Date 14/06/2018
58 | 241613014-Shyamkur Up-Chandipur via Lakkanpur Road | [13 empty] | 0 | #DIV/0!
59 | 241613016-Improvement of Muragacha-Horihornagor U.P.via Modonpur Road From Ch. 1000-2695m. [Salvage Cost Tk. 13,90,230.00] | KDRIDP/Jess/W-45/2017-18 | 1.695 | 0 | 0 | 116.18 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 111.33 | 45% | 2018-09-03 |  |  | 0 | 0%
60 | 241613022-Nangro Bazar - Rashulpur via Jamtala Rd. | [13 empty] | 0 | #DIV/0!
Keshabpur
61 | 241383004 Improvement of Biddanandakati UP-Kabilpur RHD more Via Hasanpur Road From Ch. 00-2760m. [Salvage Cost Tk. 60,56,868.00] | KDRIDP/Jess/W-100/2017-18 | 2.76 | 0 | 0 | 198.925 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 04/07/2018
62 | 241383005 Keshabpur Pilot High School-Gorvanga Bazar | [13 empty] | 0 | #DIV/0!
63 | 241383008 Biddanandakati UP-Jamalgong Bazar Via Parchakra Bazar | [13 empty] | 0 | #DIV/0!
64 | 241383009 Sagardari UP- Kabilpur GPS | [13 empty] | 0 | #DIV/0!
65 | 241383011-Improvement of Panjia UP-Hoder hat Road From Ch. 00-3200m. [Salvage Cost Tk. 47,27,475.00] | KDRIDP/Jess/W-07/2016-17 | 3.2 | 0 | 0 | 229.93 | 2017-08-16 | M/S Mohidul Islam, 13/A Rail Road, Rail Bazar, Jessore | 2017-09-27 | 224.98 | 45% | 2017-08-17 |  |  | 0 | 0%
66 | 241383014-Panjia UP-Burali Bazar Rd. | [13 empty] | 0 | #DIV/0!
67 | 241383018 Improvement of Mangolkot UP-Buruli bazar Road From Ch. 2616-4016m. [Salvage Cost Tk. 25,250.00] | KDRIDP/Jess/W-08/2016-17 | 1.4 | 0 | 0 | 87.96 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-06-14 | 87.77 | 100% | 2018-05-20 | 87.727 | 87.727 | 0 | 99.95% | Final
Sarsa
68 | 241903001-Improvement of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.10665-13520m. [Salvage Cost Tk.21,87,707.00] | KDRIDP/Jess/W-36/2017-18 | 2.855 | 0 | 0 | 171.625 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 165.09 | 60% | 2018-10-15 |  | 104.24 | -104.24 | 63.14%
69 | 241903003-Kuchia More (Ulashi UP)-Dhaldah road | [13 empty] | 0 | #DIV/0!
70 | 241903004-Improvement of Dehi Union H/Q-Shikerpur Bazar via Fulsar Road From Ch.4480-6190m. [Salvage Cost Tk.2,04,049.00] | KDRIDP/Jess/W-34/2017-18 | 1.71 | 0 | 0 | 103.175 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 99.25 | 60% | 2018-10-15 |  | 29.65 | -29.65 | 29.87%
71 | 241903008-Improvement of Benapole G.C-Bahadurpur UP H/Q via Ghiba Road From Ch.2545-7000m | KDRIDP/Jess/W-35/2017-18 | 4.455 | 0 | 0 | 268.13 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 265.08 | 25% | 2018-10-15 |  |  | 0 | 0%
72 | 241903011-Goga Union H /Q-Khalshi bazar via Agrabhulat road. | [13 empty] | 0 | #DIV/0!
73 | 241903016-Bahadurpur Union H/Q-Sharbunghuda Bazar road. | [13 empty] | 0 | #DIV/0!
74 | 241473020 Dehi Union H/Q –Wapda Bazar upto Kashipur Rd | [13 empty] | 0 | #DIV/0!
75 | 241903017-Ulashi Union H/Q-Jamtala Bazar Via Benekhori road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 60.049 | 0 | 0 | 3994.811 |  |  |  | 2863.73 | 55.75% |  | 527.696 | 924.376 | -396.68 | 32.28%
Improvement of Village Road by BC
Jessore Sadar
1 | 241474002-Improvement of Haibathpur -Uttar Lolitadha Road. From Ch:1030-104m & 1180-2560m. [Salvage Cost. Tk.34,666.00] | KDRIDP/Jess/W-95/2017-18 | 1.39 | 0 | 0 | 102.107 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore |  | 107.207 | 0% |  |  |  | 0 | 0% | NOA Date 27/05/2018
2 | 241474003-New Khairtala R&H-Bahadurpur Rd. | [13 empty] | 0 | #DIV/0!
3 | 241474004-Khairrala Seed Office-Boalpur Rd. | [13 empty] | 0 | #DIV/0!
4 | 241474007-Sujalpur Muchipara-Faridpur old Bazar Rd. | [13 empty] | 0 | #DIV/0!
5 | 241474009-Improvement of Gopalpur-Rampur Pry. School Road. From Ch:2000-4105m. [Salvage Cost. Tk.3,68,686.00] | KDRIDP/Jess/W-69/2017-18 | 2.105 | 0 | 0 | 130.835 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
6 | 241474015-Rudropur-Sarapole bazar Rd. | [13 empty] | 0 | #DIV/0!
7 | 241474017-Rupdia Jamtala R&HD- Rustompur Rd. | [13 empty] | 0 | #DIV/0!
8 | 241474020-Basundia bazar-Jogonnathpur Kheaghat Rd. | [13 empty] | 0 | #DIV/0!
9 | 241474021-Deapara-Ghop RHD Rd. | [13 empty] | 0 | #DIV/0!
10 | 241474027-Muroli more R&HD-Kanitala Rd. | [13 empty] | 0 | #DIV/0!
11 | 241474052-Setarampur-Jhumjhumpur Rd. | [13 empty] | 0 | #DIV/0!
12 | 241474055-Dhopakhola RHD-Durgapur Koyetpara Rd. | [13 empty] | 0 | #DIV/0!
13 | 241474056-Taragonj-Ramkrisnapur Rd. | [13 empty] | 0 | #DIV/0!
14 | 241474063-Mondolgaty (Kholadanga)-Arabpur UP Office Rd. | [13 empty] | 0 | #DIV/0!
15 | Patan Paikpara-Chitra Bazar-Bagerpara road. | [13 empty] | 0 | #DIV/0!
16 | Monsefnagar village Biswas para Jame Mosque-Monsefnagar Secendary School rd. | [13 empty] | 0 | #DIV/0!
17 | 241475293 Enayetpur-Teerhat Road. via Kadir Para (H/O Minaz-Manikdihe-Dhaka rd) | [13 empty] | 0 | #DIV/0!
18 | 241475285 Narendropur Pucca Road to Narendropur High School Rd | [13 empty] | 0 | #DIV/0!
19 | 241475292 ahsania mission road | [13 empty] | 0 | #DIV/0!
Bagherpara
20 | 241094005-Indra- Azmeherpur | [13 empty] | 0 | #DIV/0!
21 | 241094010-Improvement of Narikelbaria (Salikha Upazila) – Paschima Das Para More Road. From Ch: 500-1300m | KDRIDP/Jess/W-98/2017-18 | 0.8 | 0 | 0 | 49.66 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 21/05/2018
22 | 241094018-Satiantala bazar to RHD at Dadpur bazar via Sayed Mahmudpur | [13 empty] | 0 | #DIV/0!
23 | 241094020-Khanpur Bazer-Indra Bazer (Khanpur Freedom Fiter Gopal House-Rahaman House) Rd. | [13 empty] | 0 | #DIV/0!
24 | 241094028-Pashima H/O Sariful- Dari Agra via Napte more | [13 empty] | 0 | #DIV/0!
25 | 241094034-Kadamtola- Bandabila hat | [13 empty] | 0 | #DIV/0!
26 | 241095145-Punihar Battala- Sreerampur High School Rd. | [13 empty] | 0 | #DIV/0!
27 | 241095284-Improvement of Kundupara Senbari- Tapan Master house[Inventory Name ;-Narikelbaria Senbari - Narikelbaria North Para via Narikelpara kundupara Mandir] Road. From Ch: 00-710m. | KDRIDP/Jess/W-86/2017-18 | 0.71 | 0 | 0 | 63.405 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 13/03/2018
28 | 241095127 Improvement of Madhyapara Mosque RHD (jessore-Narial)-Joka [Inventory Name ;-RHD Rashid Karimpur H/O Omar Molla Khalshi] Road. From Ch: 00-1696m. [salvage Cost Tk.25,76,452.00] | KDRIDP/Jess/W-93/2017-18 | 1.696 | 0 | 0 | 108.45 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 10/04/2018
29 | 241095285-Khetrapara School -Hablapara Shawkat's House Road. | [13 empty] | 0 | #DIV/0!
Abhoynagar
30 | 241044003-Improvement of Nowapara Betar South Corner R&H-Dumurtala via Dhopadi Road From Ch. 4175-5000m | KDRIDP/Jess/W-02/2016-17 | 0.825 | 0 | 0 | 51.38 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [5th Called]
31 | 241044004-Noapara North Bengal(Bengal Textile)-Gobindapur Thrimohony via Dhopapara primary school Road. | [13 empty] | 0 | #DIV/0!
32 | 241044006-Taltala-Gramtala via Ektarpur Road. | [13 empty] | 0 | #DIV/0!
33 | 241044010-Paira(Kota Eayler More)-Kuta Shoyailer ghat Road. | [13 empty] | 0 | #DIV/0!
34 | 241044018-Nowly Bazar-Hanorgari Ghat via Madhur Dokan Road. | [13 empty] | 0 | #DIV/0!
35 | 241044019-Rajghat R&H-Bakardanga via Gazipur Road. | [13 empty] | 0 | #DIV/0!
36 | 241044023-Bashuari more(UZR)-Suvarara River Ghat via Dighirpar road. | [13 empty] | 0 | #DIV/0!
37 | 241044024-Ichamoti UZR-Peruli Gc Rd. | [13 empty] | 0 | #DIV/0!
38 | 241044026-Arpara UZR(Prembag More)-Zialtala Bazar Road. | [13 empty] | 0 | #DIV/0!
39 | 241044035-Magura Gabukhali Collage-Joyanta via Dholergati school Road. | [13 empty] | 0 | #DIV/0!
40 | 241044036-Chengutia Baruari Mondir-Beel Road. | [13 empty] | 0 | #DIV/0!
41 | 241044043-Nowly High school UZR-Beelkul Totarmatha via Nowly Mollik bari Jame-Mosque & Biswas Bari Road. | [13 empty] | 0 | #DIV/0!
42 | 241044050-Barandi Fakirhat Bazar-Takerghat road via WAPDA Office. | [13 empty] | 0 | #DIV/0!
43 | 241045086-Ranaghati Khayghat - Bhugilhat Mor Rd. | [13 empty] | 0 | #DIV/0!
44 | 241045230-Nowly Biswas para-Mosque road. | [13 empty] | 0 | #DIV/0!
45 | 241045516-Improvement of Nowly Momin Biswas house - Mir Bari Tematha Road From Ch. 00-412m | KDRIDP/Jess/W-104/2017-18 | 0.412 | 0 | 0 | 27.728 | [8 empty] | 0 | #DIV/0!
| 241045613-Improvement of Nowly Golamar Bari more-Tatultala Ghat Road From Ch. 00-500m [Salvage Cost Tk. 1,21,853.00] |  | 0.5 | 0 | 0 | 34.54 | [8 empty] | 0 | #DIV/0!
46 | 241045406-Improvement of Bagutia Palpara Puja mondir- Mojibor house Road From Ch. 00-634m. [Salvage Cost Tk. 50,471.00] | KDRIDP/Jess/W-105/2017-18 | 0.634 | 0 | 0 | 43.15 | [8 empty] | 0 | #DIV/0!
| 241045188-Improvement of Baghutia Bridge-Baghutia Dhakinpara Mosque Road From Ch. 00-1550m. |  | 1.55 | 0 | 0 | 106.627 | [8 empty] | 0 | #DIV/0!
47 | 241044022 Improvement of Abhoynagar Puraton Kheya Ghat-Shibnagor UZR(N/H/O Kalachand) via Bogratala Mosque Road From Ch.584-2560 m. [salvage Cost Tk. 3,17,894.00] | KDRIDP/Jess/W-61/2017-18 | 1.976 | 0 | 0 | 130.88 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 28/02/2018 [3Rd Called]
48 | 241044062 Improvement of Horishpur Reg.Primary school-Magura G.C. via Ramsara chowmatha, shishutala Road From Ch. 2435-4130m. [salvage Cost Tk. 8,78,194.00] | KDRIDP/Jess/W-62/2017-18 | 1.695 | 0 | 0 | 117.66 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 28/02/2018 [3Rd Called]
49 | 241044069-Improvement of Gopinathpur Village-Dokhanpara Abdul Gofur khan shope-Batiul Nure Jame Mosque Road From Ch. 00-775m. [Salvage Cost Tk. 3,85,651.00] | KDRIDP/Jess/W-63/2017-18 | 0.775 | 0 | 0 | 53.47 | 2018-02-05 | B.M Rafiqul Islam, Dariyapur, Narial Sadar, Narial | 2018-03-12 | 57.49 | 0% | 2018-12-13 |  |  | 0 | 0%
50 | 241044066 Improvement of Bhabadha Sluice gate-Zamira UZR. Road From Ch.00-3160m. [Salvage Cost Tk. 71,67,422.00] | KDRIDP/Jess/W-64/2017-18 | 3.16 | 0 | 0 | 208.65 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [2Nd Called]
51 | 241045137 Improvement of Dattagati WAPDA Road near the house of Ashu babu- Dattagati East para Culvert Road From Ch. 00-290m. [Salvage Cost Tk. 6,51,733.00] | KDRIDP/Jess/W-102/2017-18 | 0.29 | 0 | 0 | 19.265 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
| 241044039 Improvement of Takerghat-Kapalia bazar via Bhabadha Sluice gate, College & kalishakul Bazer Road From Ch. 3300-5300m |  | 2 | 0 | 0 | 152.43 | [8 empty] | 0 | #DIV/0!
Chowgacha
52 | 241114011-Guatoli UZR-Narayanpur UZR Rd | [13 empty] | 0 | #DIV/0!
53 | 241114024-Improvement of Goribpur-Moshiuragor Road Ch: 00-875m. [Salvage cost Tk.30.524.00] | KDRIDP/Jess/W-106/2017-18 | 0.875 | 0 | 0 | 56.958 | [8 empty] | 0 | #DIV/0!
54 | 241114025 Improvement of Dhuliani bazar-Shajadpur Road From Ch: 00-184m & 1728-2465m. [Salvage Cost Tk. 3,49,720.00] | KDRIDP/Jess/W-70/2017-18 | 0.921 | 0 | 0 | 71.65 | 2018-05-07 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore |  | 75.225 | 0% |  |  |  | 0 | 0% | NOA Date 27/05/2018
55 | 241114034-Improvement of Mosiurnagor Bazar-Bariali Road Ch: 371-1925m [Salvage cost Tk.13,79,050.00] | KDRIDP/Jess/W-88/2017-18 | 1.554 | 0 | 0 | 101.38 | [8 empty] | 0 | #DIV/0!
56 | 241114037-Dhuliani road-Uzirpur Rd. | [13 empty] | 0 | #DIV/0!
57 | 241114049-Goyra-Mashila Road. | [13 empty] | 0 | #DIV/0!
58 | 241114063-Improvement of Arpara Bazer- Sarfarajpur Bazer via Kandi Road From Ch: 1120-2225m [Salvage cost Tk.6,63,400.00] | KDRIDP/Jess/W-89/2017-18 | 1.105 | 0 | 0 | 69.94 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore |  | 73.4 | 0% |  |  |  | 0 | 0%
59 | 241114030-Improvement of Jahatabmunshir Vhagar Road. From Ch: 00-1000m | KDRIDP/Jess/W-29/2017-18 | 1 | 0 | 0 | 65.85 | 2017-09-06 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-15 | 69.13 | 0% | 2018-04-09 |  |  | 0 | 0%
60 | 241115048-Karincha bazar-Madhabpur Burning Ghat Road. | [13 empty] | 0 | #DIV/0!
61 | 241115140-Dashpakia-Nawdaga Road. | [13 empty] | 0 | #DIV/0!
62 | 241115098-Improvement of Chanda Afra-Raynagor Road. From Ch: 1952-3182m. [Salvage Cost Tk.1,71,976.00 | KDRIDP/Jess/W-28/2017-18 | 1.23 | 0 | 0 | 73.49 | 2017-09-07 | M/S Jahid Hossain Kotchandpur Bus Stand Para, Jhenidah. | 2017-10-16 | 77.14 | 60% | 2018-09-06 |  | 48.5 | -48.5 | 62.87%
63 | 241115098-Improvement of Chanda Afra-Raynagor Road From Ch: 00-520m under. [Salvage Cost Tk. 2,43,822.00] | KDRIDP/Jess/W-84/2017-18 | 0.52 | 0 | 0 | 33.23 | 2018-05-13 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore |  | 34.889 | 0% |  |  |  |  | 0% | NOA Date 27/05/2018
64 | 241115181-Improvement of Batikamari - Bundalitala Road [ Inventory Name: Batikamari Bhanga road- Batikamari village Road ] From Ch: 00-610m | KDRIDP/Jess/W-71/2017-18 | 0.61 | 0 | 0 | 43.865 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [2Nd Called]
65 | 241115030-Improvement of Bergobindapur- Math Road (Bergobindapur-Goalbari via Purbo Para) From Ch: 00-1000m. [Salvage Cost Tk. 3,41,285.00] | KDRIDP/Jess/W-58/2017-18 | 1 | 0 | 0 | 59.4 | 2018-03-12 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-04-18 | 62.45 | 40% | 2019-01-15 |  |  | 0 | 0% | NOA Date 27/03/2018
66 | 241115079-Improvement of DMC Madrasha - Joynarar union Road. From Ch: 00 - 1130m. [Salvage Cost Tk. 4,91,285.00] | KDRIDP/Jess/W-12/2016-17 | 1.13 | 0 | 0 | 69.69 | 2017-05-12 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-08-06 | 72.54 | 15% | 2018-04-30 |  |  | 0 | 0%
67 | 241115079-Improvement of DMC Madrasha - Rainagar union Road From Ch:1130-2100 m. [Salvage Cost Tk.89,458.00] | KDRIDP/Jess/W-52/2017-18 | 0.97 | 0 | 0 | 65.46 | 2018-01-11 | M/D Jahid Hossain Kotchandpur Bus stand para, Jhenidah | 2018-02-07 | 68.73 | 60% | 2018-09-30
68 | 241115078-Improvement of Jhinaikundu-Jamira Road. From Ch: 00-1000m | KDRIDP/Jess/W-30/2017-18 | 1 | 0 | 0 | 57.77 | 2017-07-09 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2017-10-03 | 60.52 | 100% | 2018-02-09 | 60.52 | 60.52 | 0 | 100% | Final
69 | 241115078-Improvement of Jhinaikundu-Jamira Road From Ch: 1000-1535m. [Salvage Cost Tk. 66,223.00] | KDRIDP/Jess/W-74/2017-18 | 0.535 | 0 | 0 | 32.98 | 2018-05-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah |  | 34.627 | 0% |  |  |  | 0 | 0% | NOA Date 27/05/2018
70 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 00-1000m. [Salvage Cost Tk. 2,61,184.00] | KDRIDP/Jess/W-24/2017-18 | 1 | 0 | 0 | 58.5 | 2017-08-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-10 | 60.88 | 0% | 2018-08-20 |  |  | 0 | 0%
71 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 1000-1340m. [Salvage Cost Tk. 19,597.00] | KDRIDP/Jess/W-73/2017-18 | 0.34 | 0 | 0 | 23.4 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 04/07/2018
72 | 241115199-Improvement of Fulsara Purbopara Madrasha- Abed ali house Road. From Ch:00-645 m [Salvage Cost Tk.1,61,285.00] | KDRIDP/Jess/W-17/2017-18 | 0.645 | 0 | 0 | 38.58 | 2017-08-06 | Md. Abdul Halim Kotchanpur, Jhenaidah | 2017-05-10 | 39.4 | 100% | 2018-08-25 | 39.4 | 39.4 | 0 | 100% | Final
73 | 241115207-Improvement of Fulshara Purbopara Village Road. From Ch: 00 - 680m. [Salvage Cost Tk. 8,37,415.00] | KDRIDP/Jess/W-13/2016-17 | 0.68 | 0 | 0 | 42.75 | 2017-05-15 | M/S Mim Enterprise, Gajirhat Road, Puraton Kosba, Jessore | 2017-11-06 | 42.94 | 60% | 2018-04-28 |  | 19.03 | -19.03 | 44.32%
74 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road. From Ch: 00-455m [Salvage Cost Tk. 1,45,870.00] | KDRIDP/Jess/W-26/2017-18 | 0.455 | 0 | 0 | 27.63 | 2017-08-21 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-15 | 28.98 | 90% | 2018-08-27 |  | 16.22 | -16.22 | 55.97%
75 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road From Ch: 455-636m. | KDRIDP/Jess/W-87/2017-18 | 0.181 | 0 | 0 | 11.24 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore |  | 11.8 | 0%
76 | 241115262-Improvement of Araddah Muktijuddah Abdur Sattar Mia House -Sibnagor village via Balidapara GPS Road. From Ch: 00-1140m. [Salvage Cost Tk.1,04,350.00] | KDRIDP/Jess/W-25/2017-18 | 1.14 | 0 | 0 | 68.25 | 2018-02-19 | M/S Sun Enterprise, Chowgacha Bazar, Chowgacha, Jessore |  | 75.015 | 0% |  |  |  | 0 | 0% | NOA Dated 12/03/2018
77 | 241115258-Improvement of Singojhuli Jhautala - Baruhati Road. From Ch: 00-1235m | KDRIDP/Jess/W-18/2017-18 | 1.235 | 0 | 0 | 71.51 | 2017-08-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-09-28 | 74.94 | 100% | 2018-05-31 | 74.64 | 74.64 | 0 | 99.6% | Final
78 | 241115131-Improvement of Dhakinsagor-Charabari via H/O Abdul Bari Road. From Ch: 00-1650m. [Salvage Cost. Tk. 62,601.00] | KDRIDP/Jess/W-22/2017-18 | 1.65 | 0 | 0 | 94.46 | 2017-08-21 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-10-03 | 99.06 | 100% | 2018-05-31 | 98.877 | 98.877 | 0 | 99.82% | Final
79 | 241115060-Improvement of Andulia-Doulatpur Road From Ch: 2327-3350m [Salvage cost Tk.9,77,690.00] | KDRIDP/Jess/W-90/2017-18 | 1.023 | 0 | 0 | 62.158 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 19/04/2018
80 | 241115153-Improvement of Patibila UP - Hayetpur via Uttor Para Road. From Ch: 00-1000m [Salvage Cost Tk.5,65,304.00] | KDRIDP/Jess/W-23/2017-18 | 1 | 0 | 0 | 59.93 | 2017-08-18 | M/S Jamuma Prokousoli hatkhola Road, jessore | 2017-10-02 | 62.8 | 0% | 2018-08-28 |  |  | 0 | 0%
81 | 241115288-Improvement of Afra R&H road near H/O Mokbul via Karamot Ali Road. From Ch: 00-475m. [Salvage Cost Tk.3,08,590.00] | KDRIDP/Jess/W-20/2017-18 | 0.475 | 0 | 0 | 32.38 | 2017-10-19 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 33.54 | 0% | 2018-05-30 |  |  | 0 | 0%
82 | 241115296-Improvement of Durgabor Kathi Amir Ali H/O -Tatul Bari Korban Biswas H/O Road. From Ch: 00-587m. | KDRIDP/Jess/W-21/2017-18 | 0.587 | 0 | 0 | 37.45 | 2017-10-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-11-26 | 38.89 | 0% | 2018-02-06 |  |  | 0 | 0%
83 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid Road. From Ch: 00-1000m | KDRIDP/Jess/W-27/2017-18 | 1 | 0 | 0 | 62.74 | 2017-08-20 | M/S Sarkar Construction Lalbazar, Natore | 2017-10-10 | 64 | 60% | 2018-08-27 |  | 36.13 | -36.13 | 56.45%
84 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid From Ch: 1000-1480m. [Salvage Cost Tk. 1,10,415.00] | KDRIDP/Jess/W-75/2017-18 | 0.48 | 0 | 0 | 30.22 | 2018-02-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-04-03 | 30.61 | 0% | 2018-11-19
85 | 241115292-Improvement of Souila Arpara road near H/O Toffazial-Durabakati H/O Ismail Road. From Ch:00-350 m .[Salvage Cost Tk.1,94,990.00] | KDRIDP/Jess/W-19/2017-18 | 0.35 | 0 | 0 | 21.76 | 2017-10-17 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 21.458 | 0% | 2018-05-30 |  |  | 0 | 0%
86 | 241115269-Improvement of Sayedpur Shek Para Abdur Razzak Shop- Purbo Mat Pucca Road From Ch: 00-1470m. [Salvage Cost Tk. 1,89,585.00] | KDRIDP/Jess/W-72/2017-18 | 1.47 | 0 | 0 | 97.755 | [8 empty] | 0 | #DIV/0!
87 | 241115008-Improvement of Swruppur Hajambari-Bagdanga Road From Ch: 00-2200m. [Salvage Cost Tk. 5,95,622.00] | KDRIDP/Jess/W-60/2017-18 | 2.2 | 0 | 0 | 142.81 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 07/05/2018
88 | 241115014-Improvement of Tazbizpur-Jatrapur Road From Ch: 864-2035m | KDRIDP/Jess/W-59/2017-18 | 1.171 | 0 | 0 | 71.695 | 2018-04-25 | M/S Renu Enterprise Asrom Road Jessore | 2018-05-24 | 75.25 | 0% | 2018-02-24 |  |  | 0 | 0%
89 | 241115286-Improvement of Anderkota Primary school-Panchbaria Beel Tematha BC Road From Ch:00-1075 m | KDRIDP/Jess/W-55/2017-18 | 1.075 | 0 | 0 | 58.92 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 63.028 | 0% | 2019-01-24 |  |  | 0 | 0%
90 | 241115044-Improvement of Baishagari BC Road - Hazrakhana Kadamtala BC Road via Anderkota, Batikamari Road. (Batkamari- Mohespur Road.)Road. From Ch:1500-2680m | KDRIDP/Jess/W-56/2017-18 | 1.18 | 0 | 0 | 70.706 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 75.649 | 0% | 2019-01-15 |  |  | 0 | 0%
91 | 241114026-Improvement of Kongsharipur-Mashila Road. From Ch: 2043-2198m & 4080-5510m | KDRIDP/Jess/W-57/2017-18 | 1.585 | 0 | 0 | 89.53 | 2018-03-12 | MD. Noor Islam. Purbo Barandipara, Jessore | 2018-04-17 | 95.72 | 40% | 2018-09-12 |  |  | 0 | 0% | NOA Date 27/03/2018
92 | 241115271- Sayedpur Altab Mondol House-H/O Thandu Mondol via Mondol Para Jame Mosque Road. | KDRIDP/Jess/W-85/2017-18 | 0.236 | 0 | 0 | 15.95 | [10 empty] | Tender will be Recceived on Dated 04/07/2018
Jhikargacha
93 | 241234009 : Fatepur-Bodhkhana bazar. | [13 empty] | 0 | #DIV/0!
94 | 241234013 : Misrideara UZR Jamtala-Angarpara. | [13 empty] | 0 | #DIV/0!
95 | 241234035 : Improvement of Komarchanda-Nayra bazar Road From Ch. 00 - 925m | KDRIDP/Jess/W-06/2016-17 | 0.925 | 0 | 0 | 55.32 | 2017-07-03 | M/S Mysha Traders, 377/1, South Goran, Sabujbag, Dhaka-1219 | 2017-09-13 | 52.25 | 70% | 2018-05-31 |  | 29.24 | -29.24 | 55.96%
96 | 241234052-Improvement of Digri bazar-Sadipu bazar Road From Ch.00-148 m | KDRIDP/Jess/W-15/2016-17 | 0.148 | 0 | 0 | 10.36 | 2017-07-27 | M/S Bakul Enterprise Pulerhat Bazar, Chanchara, Jessore | 2017-09-25 | 10.33 | 100% | 2018-03-14 | 10.33 | 10.33 | 0 | 100% | Final
97 | 241234071-Gongganandapur UP- Panditpur Rd. | [13 empty] | 0 | #DIV/0!
98 | 241235001 : Bishahari-Atulia UZR. | [13 empty] | 0 | #DIV/0!
99 | 241235012 : Magura UP Office-Magura UZR. | [13 empty] | 0 | #DIV/0!
100 | 241235028 : Nabibnagar RHD-Kamarpara GPS. | [13 empty] | 0 | #DIV/0!
101 | 241235031 : Kawria GPS More-Towra. | [13 empty] | 0 | #DIV/0!
102 | 241235282-Gongadharpur Israil's house-Palla Lutfor's house. | [13 empty] | 0 | #DIV/0!
Monirampur
103 | 241614005-Monirampur College-Debidaspur | [13 empty] | 0 | #DIV/0!
104 | 241614019-Improvement of Komolpur-Tazpur Road From Ch. 00-2000m [Salvage Cost Tk. 21,76,122.00] | KDRIDP/Jess/W-78/2017-18 | 2 | 0 | 0 | 143.17 | 2018-05-12 | Sayed Nahid Hassan Keshabpur Bazar, Keshabpur, Jessore |  | 150.25 | 0% |  |  |  | 0 | 0% | NOA Date 27/05/2018
105 | 241614020-Chandipur-Hanuar Amtala | [13 empty] | 0 | #DIV/0!
106 | 241614025-Improvement of Rajgonj Jamshed mill-Monohorpur Road From Ch. 1540-2106m. [Salvage Cost Tk. 51,999.00] | KDRIDP/Jess/W-41/2017-18 | 0.566 | 0 | 0 | 40.63 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 40.39 | 60% | 2018-05-28 |  | 22.87 | -22.87 | 56.62%
107 | 241614041-Mobarokpur Ghospara-Negura Bazar | [13 empty] | 0 | #DIV/0!
108 | 241614048-Fakirrasta-Keshabpur via Hashadanga | [13 empty] | 0 | #DIV/0!
109 | 241614066-Kharinci-Rohita Shaikpara | [13 empty] | 0 | #DIV/0!
110 | 241614079-Improvement of Kashimpur Battala-Rohita U.P Road From Ch. 1250-3200m. [Salvage Cost Tk. 1,59,608.00] | KDRIDP/Jess/W-80/2017-18 | 1.95 | 0 | 0 | 139.45 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 30/05/2018
111 | 241614100-Subalkati Edgah-Lawkunda Sr.Madrasha | [13 empty] | 0 | #DIV/0!
112 | 241614113-Improvement of Hazrakati Daspara More - Hazrakati Sanapara Road From Ch. 944-1985m. [Salvage Cost Tk. 1,86,215.00] | KDRIDP/Jess/W-42/2017-18 | 1.041 | 0 | 0 | 79.4 | 2017-10-29 | M/S Hira construction Main Road, Monirampur, Jessore | 2017-11-30 | 79.5 | 40% | 2018-05-28 |  | 12.31 | -12.31 | 15.48%
113 | 241615035-Improvement of Parala-Satgati Road From Ch. 00-925m | KDRIDP/Jess/W-05/2016-17 | 0.925 | 0 | 0 | 61.07 | 2017-05-15 | M/S Hira Construction, Main Road Monirampur, Jessore | 2017-05-29 | 60.81 | 100% | 2018-04-28 | 59.575 | 59.575 | 0 | 97.97% | Final
114 | 241615071-Boalia Bazar-Uttarpara | [13 empty] | 0 | #DIV/0!
115 | 241615110-Moshimnagor Charabattala-Vorotpur Road | [13 empty] | 0 | #DIV/0!
116 | 241614076-Improvement of 8 mile(RHD)-Khahimnagor U.P. Road From Ch. 00-1780m. [Salvage Cost Tk. 10,61,912.00] | KDRIDP/Jess/W-38/2017-18 | 1.67 | 0 | 0 | 131.55 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 130.25 | 100% | 2018-07-15 | 130.13 | 130.13 | 0 | 99.91% | Final
117 | 241615398-Improvement of Atghara purbopara - Amjamtola Road From Ch. 00-805m | KDRIDP/Jess/W-39/2017-18 | 0.805 | 0 | 0 | 57.11 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore |  | 59.948 | 0% |  |  |  | 0 | 0% | NOA Date 27/05/2018
118 | 241614060-Improvement of Lakhanpur Mandartala-Gouripur FWC Road From Ch. 00-470m | KDRIDP/Jess/W-40/2017-18 | 0.47 | 0 | 0 | 34.81 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 34.96 | 60% | 2018-05-28 |  | 19 | -19 | 54.35%
119 | Routia UP Bashdebpur bazar Torafdar Bostlay-Bashdebpur Dakil Madrasha & Attimkhana-Mathpara mono molla H/O road. | [13 empty] | 0 | #DIV/0!
120 | 241615185-Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 00-1000m. [Salvage Cost Tk. 83,892.00] | KDRIDP/Jess/W-53/2017-18 | 1 | 0 | 0 | 75.93 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore |  | 79.7 | 0% |  |  |  | 0 | 0% | NOA Date 27/05/2018
121 | 241615185- Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 1000-2095m | KDRIDP/Jess/W-92/2017-18 | 1.095 | 0 | 0 | 77.93 | 2018-04-09 | M/S Sajan Enterprise Chanchara Cheakpost Jessore |  | 81.827 | 40%
122 | 241615336-Parkhaajura-Baroypara more-Garidkhali road. | [13 empty] | 0 | #DIV/0!
Keshabpur
123 | 241384008 Satkira Chira mill-Habspol Madrasha | [13 empty] | 0 | #DIV/0!
124 | 241384022 Dewli more-Dewli non Govt Primary School | [13 empty] | 0 | #DIV/0!
125 | 241384025 Improvement of Dashkohonia Ruhul Amin House-Burili Rishipara Road From Ch. 1000-2705m. [Salvage Cost Tk. 7,35,719.00] | KDRIDP/Jess/W-09/2016-17 | 1.705 | 0 | 0 | 102.65 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-11-06 | 102.39 | 100% | 2018-04-14 | 102.3 | 102.3 | 0 | 99.91% | Final
126 | 241384026 Satbaria Choudary Pond-Begompur more | [13 empty] | 0 | #DIV/0!
127 | 241384030 Protappur – Attonda | [13 empty] | 0 | #DIV/0!
128 | 241384035 Boga-Mohadebpur road | [13 empty] | 0 | #DIV/0!
129 | 241384037 Borenga-Pancharoi | [13 empty] | 0 | #DIV/0!
130 | 241384038 Jhikra-baruihati (Kasta bazar-Sikerpur bazar road) | [13 empty] | 0 | #DIV/0!
131 | 241384043 Boga FRB-Vanderkhola Bazar | [13 empty] | 0 | #DIV/0!
132 | 241384050 Improvement of Bosuntia (Mongolkot bazar)-Baduria via Ramkrishnapur Road From Ch. 480-1125m | KDRIDP/Jess/W-10/2016-17 | 0.645 | 0 | 0 | 42.34 | 2017-05-15 | M/S Joy Enterprise, Keshabpur Bazar, Keshabpur, Jessore | 2017-11-06 | 42.29 | 100% | 2018-04-30 | 42.24 | 42.24 | 0 | 99.88% | Final
133 | 241384051 Jahanpur Jamtala more-Vallukghar Bazar road. | [13 empty] | 0 | #DIV/0!
134 | 241385019 Improvement of Kanderpur-Gater-hat(Bongshir Battala) Road From Ch. 1000-2485m | KDRIDP/Jess/W-11/2016-17 | 1.485 | 0 | 0 | 88.92 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-12-06 | 88.74 | 100% | 2018-04-30 | 88.68 | 88.68 | 0 | 99.93% | Final
135 | 241385022 Baliadanga-Gurvanga | [13 empty] | 0 | #DIV/0!
136 | 241385540-Improvement of Dohori Village C&B - Surindronath Mondal bari Road From Ch. 00-1100m. [Salvage Cost Tk. 6,41,862.00] | KDRIDP/Jess/W-94/2017-18 | 1.1 | 0 | 0 | 72.746 |  | M/S Biswajit Construction, 9 Rail Road, Jessore |  | 76.369 | 0% |  |  |  | 0 | 0% | NOA Date 14/06/2018
| 241385541-Improvement of Gurdaga-Dong ghat H/O Mono Boso Road From Ch. 00-1000m. [Salvage Cost Tk. 79,300.00] |  | 1 | 0 | 0 | 68.33 |  |  |  | 71.73 |  |  |  |  | 0 | 0%
Sarsa
137 | 241904002-Ghiba Uttar para-Sharbunghuda bazar road. | [13 empty] | 0 | #DIV/0!
138 | 241904003-Bagarchara (GC)-Basatpur Bazar rd. | [13 empty] | 0 | #DIV/0!
139 | 241904015-Chandrapur-Belta ghat | [13 empty] | 0 | #DIV/0!
140 | 241904023-Ulashi Debdar Tala-Jirengacha road | [13 empty] | 0 | #DIV/0!
141 | 241904024-Ulashi Bazar Mosjheed R&H-Kannyadah Bazar road. | [13 empty] | 0 | #DIV/0!
142 | 241904026-Kagojpukur-Dubpara road. | [13 empty] | 0 | #DIV/0!
143 | 241904043-Trimohini-Kulpala via Bolidadah road | [13 empty] | 0 | #DIV/0!
144 | 241904046-Naihati-Dehi road. | [13 empty] | 0 | #DIV/0!
145 | 241904047-Saratola High School-Tebaria Mosque via Daridurgapur road. | [13 empty] | 0 | #DIV/0!
146 | 241904048-Sikerpur-Salta road. | [13 empty] | 0 | #DIV/0!
147 | 241904052-Ekjhala Bazar-Kondarpopur road. | [13 empty] | 0 | #DIV/0!
148 | 241904061-Bosotpur Madrasha-Baikola road . | [13 empty] | 0 | #DIV/0!
149 | 241904115-Golapole More-Keshadanga Village Rd. | [13 empty] | 0 | #DIV/0!
150 | 241905198- Improvement of Sibobash Khalil's House-Shalkona Primary School road Via Sahid Shangbadic Shamsur Rahman House Road From Ch.00-1440m [Salvage Cost. Tk. 3,68,361.00] | KDRIDP/Jess/W-37/2017-18 | 1.44 | 0 | 0 | 91.38 | 2017-10-17 | M/S Ashraf Traders Voirob stand, Haspatal Ghat, Khulna | 2017-12-26 | 91.16 | 60% | 2018-11-16 |  | 45.98 | -45.98 | 50.44%
Total |  |  | 74.096 | 0 | 0 | 4865.32 |  |  |  | 3040.202 | 38.15% |  | 706.692 | 955.972 | -249.28 | 31.44%
Improvement of Village Road by HBB
Jessore Sadar
1 | 241474005-Churmankati Rail gate-Dogachia Beel Rd. | [13 empty] | 0 | #DIV/0!
2 | 241474016-Hamidpur Kamar bari-Dhitila Rd. | [13 empty] | 0 | #DIV/0!
Bagherpara
3 | 241095221-Ramkrishnapur Bazar-Silumpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
Abhoynagar
4 | 241044060-Dhulgram Club-Siddipasha U.P.Office(Nowly Bazar) Rd. | [13 empty] | 0 | #DIV/0!
Chowgacha
5 | 241114038-Burinda-Dashpakia Rd. | [13 empty] | 0 | #DIV/0!
Jhikargacha
6 | 241234040-Nawali bazar-Kanarali bazar Rd. | [13 empty] | 0 | #DIV/0!
Monirampur
7 | 241614089-Khedapara U.P.-Kasipur Mandertala Rd. | [13 empty] | 0 | #DIV/0!
Keshabpur
8 | 241384046-Keshabpur UP-Shikerpur bazar Rd. | [13 empty] | 0 | #DIV/0!
Sarsa
9 | 241904105-Improvement of Nizampur Bazar-Bahadurpur Road From Ch.2643-4718m. [Salvage Cost Tk.45,344.00] | KDRIDP/Jess/W-32/2017-18 | 2.075 | 0 | 0 | 75.315 | 2017-10-17 | M/S Asraf Traders, Voirob Road, Haspatal Ghat, Khulna | 2017-12-26 | 75.3 | 85% | 2018-11-16 |  | 61.99 | -61.99 | 82.32%
Total |  |  | 2.075 | 0 | 0 | 75.315 |  |  |  | 75.3 | 85% |  | 0 | 61.99 | -61.99 | 82.32%
Construction of Bridge on Union Road/Village Road (5.50m width)
Jessore Sadar
1 | 241473016-Const. of RCC Bridge on Stiantola Bazar-Ichali UP via Suro Kamergona Road. | [13 empty] | 0 | #DIV/0!
2 | 241473002-Const. of RCC Bridge on Narendrapur UP-Dailala Bazar Road | [13 empty] | 0 | #DIV/0!
Monirampur
3 | 241613020-Const. of RCC Bridge on Dhakuria UP- Gabukhali Bazar Road | [13 empty] | 0 | #DIV/0!
4 | 241614070-Construction of 44.0m RCC Girder Bridge on Fakir Rasta-Pazia Road at Ch.500m | KDRIDP/Jess/W-31/2017-18 | 0 | 44 | 0 | 245.86 | 2017-10-23 | Kamarjani-Brojen-Anowara-JV, Sree Angoan, faridpur | 2017-11-30 | 221.27 | 60% | 2018-02-12 |  | 124.82 | -124.82 | 56.41% | Pair pile & Cap casting complet
5 | 241615002-Const. of RCC Bridge onMujguni-Durgapur | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 44 | 0 | 245.86 |  |  |  | 221.27 | 60% |  | 0 | 124.82 | -124.82 | 56.41%
Maintenance
Jessore Sadar
1 | 241472012-Razarhat GC-Hamidpur RHD Rd. | [13 empty] | 0 | #DIV/0!
2 | 241472014-Churamankati GC-Kayemkhola GC via Bagdanga Jhowdia Bazar Chandutia Rd | KDRIDP/Jess/M-01/2017-18 | 2.805 | 0 | 0 | 120.728 | 2018-04-25 | M/S L Rahaman Enterprise R. N. Road, Jessore |  | 126.76 | 0% |  |  |  | 0 | 0% | NOA Date 20/05/2018
3 | 241472017-Monohorpur Bazar RHD - Narikel Baria GC via Raipur UP ( sadar part) Road. | [13 empty] | 0 | #DIV/0!
4 | 241473002-Narendrapur UP-Daitala Bazar Rd. | [13 empty] | 0 | #DIV/0!
5 | 241473005-Periodic Maintenance of Upashahor UP - Tail kup Bazar Rd. Via Kashimpur, Dighirpar Road From Ch.00-1300m | KDRIDP/Jess/M-21/2017-18 | 1.33 | 0 | 0 | 62.36 | 2018-11-05 | M/S S S Traders Kazi Para, Puraton Koshba, Jessore | 2018-05-28 | 65.469 | 85% | 2019-02-03 |  | 54.885 | -54.885 | 83.83%
6 | 241473007-Chanchra UP Office-Kuadah Bazar via Sarapol Rd. | [13 empty] | 0 | #DIV/0!
7 | 241473008-Bagerhat Bazar-Ramnagar UP Office Rd. | [13 empty] | 0 | #DIV/0!
8 | 241473009-Sannashi Bottala Bazar- Ramnagar UP Office Rd. | [13 empty] | 0 | #DIV/0!
9 | 241473010-Chanchara Bazar -Chanchar UP via Vaturia Rd. | [13 empty] | 0 | #DIV/0!
10 | 241473016-Periodic Maintenance of Satiantola Bazar- (Fulbari More) Ichali UP via Suro, Kamergona Road From Ch.00-2975m | KDRIDP/Jess/M-02/2017-18 | 2.975 | 0 | 0 | 73.158 | 2018-04-22 | M/S Dilip Enterprise, Calectorit Mosjid Market, Jessore |  | 76.808 | 0% |  |  |  | 0 | 0% | NOA Date 16/05/2018
11 | 241473028-Khajura(Bagherpara) GC-Barobazar(Kaligonj) GC Road via Labutola UP Rd. | [13 empty] | 0 | #DIV/0!
12 | 241474010-Periodic Maintenance of Basundia Bazar-Afraghat Ghat Road From Ch.00-2540m. | KDRIDP/Jess/M-04/2017-18 | 2.54 | 0 | 0 | 74.54 | 2018-04-23 | M/S Sharif Rabrul Enterprise Jail Road Ghop, Jessore |  | 78.266 | 0% |  |  |  | 0 | 0% | NOA Date 20/05/2018
13 | 241474012-R&H Rd. at Bijoynagar-Bolpur Ghat Rd. | [13 empty] | 0 | #DIV/0!
14 | 241474026-Periodic Maintenance of Pulerhat Shishu Aparad Centre-Vaturia Road From Ch.00-1400m | KDRIDP/Jess/M-03/2017-18 | 1.4 | 0 | 0 | 84.418 | 2018-04-24 | M/S Harun or Rashid Nowapara Road, Ghop, Jessore |  | 88.45 | 0% |  |  |  | 0 | 0% | NOA Date 20/05/2018
15 | 241474033-Bablatola Taxi Stand-Sarothi Mill Gabtola Rd. | [13 empty] | 0 | #DIV/0!
16 | 241474044-Nutunhat RHD-Bagerhat Rd. | [13 empty] | 0 | #DIV/0!
17 | 241475083-Beltola -Khmalpur Rd. | [13 empty] | 0 | #DIV/0!
Bagherpara
18 | 241092003-Jessore Narail RHD-Dhalgram more- Narikelbaria via Dhalgram Bazar Rd. | [13 empty] | 0 | #DIV/0!
19 | 241092011-Periodic Maintenance of Dhalgram GC.-Maijpara Up to Kalukhali Road From Ch.00-2265m | KDRIDP/Jess/M-26/2017-18 | 2.265 | 0 | 0 | 61.248 | 2018-05-11 | M/S Biswas Construction, 134 Dhaka Road, Puraton Kashba, Jessore |  | 64.206 | 0% |  |  |  | 0 | 0% | NOA Dare 27/05/2018
Abhoynagar
20 | 241042005-Nowapara Upazila H/Q- Amtala GC via Vatpara Bazar Rd. | [13 empty] | 0 | #DIV/0!
21 | 241042009-Alipur RHD-Sundali GC via Rajapur more Ramsaradham, Arpara Clinic more, Harishpur RNGPS Rd. | [13 empty] | 0 | #DIV/0!
22 | 241043001-Noapara HQ(BTMC Ghat)-Borni Bazar via Sreedharpur UP Office | [13 empty] | 0 | #DIV/0!
23 | 241043007-Periodic Maintenance of Sundali U.P.Office-Moshihati Bazar Road From Ch.00-3050m | KDRIDP/Jess/M-07/2017-18 | 3.05 | 0 | 0 | 68.045 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
24 | 241043009-Siddipasha UP Office(Nowly Bazer)-Phultala G.C. via Dhulgram kheya Ghat. | [13 empty] | 0 | #DIV/0!
25 | 241044005-Periodic Maintenance of Taltala Bazar-Dumortala road via Sirajkati,Chalishia Rishipara Chourasta More Road From Ch.00-5310m | KDRIDP/Jess/M-08/2017-18 | 5.31 | 0 | 0 | 162.81 | [8 empty] | 0 | #DIV/0!
26 | 241044017-Hidia Madrasha UZR- Kharoria Bazar Rd. | [13 empty] | 0 | #DIV/0!
27 | 241044039-Takerhat-Kapalia Bazarvia Bhabadha Sluicegate Collage & Kalishakul Bazar Rd. | [13 empty] | 0 | #DIV/0!
28 | 241044063-Rajapur More- Magura Madrasha more UZR via Sishutala Rd | [13 empty] | 0 | #DIV/0!
29 | 241044066-Bhabadha Sluicegate -Zamira UZR Rd. | [13 empty] | 0 | #DIV/0!
Chowgacha
30 | 241112008-Periodic Maintenance of Solua GC-Arpara GC Road From Ch.5500-7325m | KDRIDP/Jess/M-11/2017-18 | 1.825 | 0 | 0 | 60.646 | 2018-04-25 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore |  | 63.678 | 0% |  |  |  | 0 | 0% | NOA Date 20/05/2018
31 | 241112011-Purapara GC-Moheshpur Pucca road | [13 empty] | 0 | #DIV/0!
32 | 241113010-Periodic Maintenance of Debipur-Narayanpur GC Road From Ch.00-1260m. | KDRIDP/Jess/M-12/2017-18 | 1.26 | 0 | 0 | 30.358 | 2018-04-25 | M/S Sheba Traders Chowgacha Bazar, Chowgacha, Jessore |  | 31.87 | 0% |  |  |  | 0 | 0% | NOA Dare 16/05/2018
33 | 241113011-Periodic Maintenance of Chowgacha U.P-Dhuliani Via Bergobindapur Baor Road From Ch.275-1100m. | KDRIDP/Jess/M-13/2017-18 | 0.825 | 0 | 0 | 19.82 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 20.809 | 100% | 2018-11-30 | 20.8 | 20.8 | 0 | 99.96% | Final
34 | 241113014-Periodic Maintenance of Sukpukuria U.P-Andulia bazar Road From Ch.900-3680m | KDRIDP/Jess/M-14/2017-18 | 2.78 | 0 | 0 | 47.95 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
35 | 241113005-Nimtala Bazar-Pasapole Bazar via Pasapole UP Office Rd. | [13 empty] | 0 | #DIV/0!
36 | 241113017-Sukpukria UP Office -Goira Bazar Rd. | [13 empty] | 0 | #DIV/0!
37 | 241113013-Swarupda UP- Sukpukuria UO Office Rd. | [13 empty] | 0 | #DIV/0!
38 | 241114052-Chowgacha -Kabilpur Rd Mashampur more - Masila Bazar Rd | [13 empty] | 0 | #DIV/0!
39 | 241115022-Maligati -Bariali Rd. | [13 empty] | 0 | #DIV/0!
40 | 241114009(Roghonatpur-Dashpakhia bazar Road) | [13 empty] | 0 | #DIV/0!
41 | 241114014-Periodic Maintenance of Purapara Sonali Bank-Ballave pur Road From Ch.820-4900m | KDRIDP/Jess/M-16/2017-18 | 4.08 | 0 | 0 | 109.69 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 117.36 | 100% | 2018-11-30 | 117.36 | 117.36 | 0 | 100% | Final
42 | 241114024(Goribpur-Moshiuragor Road.) | [13 empty] | 0 | #DIV/0!
43 | 241114026(Kongsharipur-Mashila Road). | [13 empty] | 0 | #DIV/0!
44 | 241114028-Periodic Maintenance of Kamlapur More-Mashila Bazar Road From Ch.00-1115m | KDRIDP/Jess/M-15/2017-18 | 1.15 | 0 | 0 | 28.174 | 2018-07-05 | Md. Noor Islam, Purbo Barandipara, Jessore |  | 29.58 | 0% |  |  |  | 0 | 0% | NOA Dare 27/05/2018
45 | 241114044Muktadah-Jagadishpur UP Road..) | [13 empty] | 0 | #DIV/0!
Jhikargacha
46 | 241232015-Jhikargacha Thana Hospital more- Goaldah Bazar via Padmapukur Kashipur Rd. | [13 empty] | 0 | #DIV/0!
47 | 241233001-Parbazar-Chutipur Bazar Rd. | [13 empty] | 0 | #DIV/0!
48 | 241233002-Periodic Maintenance of Navaran Puratan bazar- Chutipur bazar Gongganandapur UP) Road From Ch.9750-14750m | KDRIDP/Jess/M-24/2017-18 | 5 | 0 | 0 | 166.579 | 2018-10-04 | M/S Sarder International Gohata Road, Cityplaza Complex, Jessore |  | 174.89 | 0% |  |  |  | 0 | 0% | NOA Dare 10/05/2018
49 | 241233021-Sankarpur UP-Shamta Bazar RHD Rd. | [13 empty] | 0 | #DIV/0!
50 | 241233024-Periodic Maintenance of Shimulia UP-Gorpara GC Road From Ch.00-2401m. | KDRIDP/Jess/M-25/2017-18 | 2.401 | 0 | 0 | 60.376 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 28/05/2018
Monirampur
51 | 241612011-Monirampur- Noapara -Kultia -Nehalpur Rd. | [13 empty] | 0 | #DIV/0!
52 | 241612014-Periodic Maintenance of Monoharpur Bazar-Chinatola Bazar Road From Ch. 00-3900m [Salvage Cost Tk.5,14,017.00] | KDRIDP/Jess/M-18/2017-18 | 3.9 | 0 | 0 | 147.2 | [8 empty] | 0 | #DIV/0!
53 | 241612015-Sundali Bazar-Dhakuria-Pramebag Gate road | [13 empty] | 0 | #DIV/0!
54 | 241612019-Periodic Maintenance of Nehalpur-Durbadanga-Bajitpur Road From Ch. 2830-8690m. [Salvage Cost Tk.7,61,457.00] | KDRIDP/Jess/M-17/2017-18 | 5.86 | 0 | 0 | 249.06 | 2018-05-16 | M/S Bonantor Trading Corporation Benapol Road Chanchara, Jessore |  | 261.418 | 0% |  |  |  | 0 | 0% | NOA Dare 07/06/2018
55 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia | [13 empty] | 0 | #DIV/0!
56 | 241233002 : Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP). | [13 empty] | 0 | #DIV/0!
57 | 241233005 : Borni bzar(Panishara UP)-Bejiatala bazar. | [13 empty] | 0 | #DIV/0!
58 | 241233006 : Seordah GC-Moheshpara | [13 empty] | 0 | #DIV/0!
59 | 241613018-Fakir Rasta bazar-Chaluahati UP | [13 empty] | 0 | #DIV/0!
60 | 241612016-Lawri (Madrasha) RHD -Khedapara GC Rd. | [13 empty] | 0 | #DIV/0!
61 | 241613001-Periodic Maintenance of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 7580-8703m [Salvage Cost Tk.Tk.1,42,500.00] | KDRIDP/Jess/M-19/2017-18 | 1.123 | 0 | 0 | 26.38 | [8 empty] | 0 | #DIV/0!
62 | 241613010-Periodic Maintenance of Gopalpur Bazar-Kultia U.P.office Road From Ch. 00-4590m [Salvage Cost Tk.4,92,836.00] | KDRIDP/Jess/M-20/2017-18 | 4.59 | 0 | 0 | 122.29 | 2018-03-13 | M/S. Banantor Trading Corporation Benapol Road Chanchara, Jessore | 2018-04-15 | 128.4 | 10% | 2019-01-22 |  |  | 0 | 0%
63 | 24164080-Khedapara-Maragacha via Gangulia Rd. | [13 empty] | 0 | #DIV/0!
Keshabpur
64 | 241382009 Mongalkot UP-Saraskati bazar | [13 empty] | 0 | #DIV/0!
65 | 241383006-Panjia Bazar UP- Monoharnagar Bazar Rd. | [13 empty] | 0 | #DIV/0!
66 | 241383007-Periodic Maintenance of Mongalkot-Panjia via Magurkhali Bazar Road From Ch.2300-3846m | KDRIDP/Jess/M-10/2017-18 | 1.546 | 0 | 0 | 48.335 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 50.75 | 0% | 2019-01-21 |  |  | 0 | 0%
67 | 241383014-Panjia UP- Burali Bazar Rd. | [13 empty] | 0 | #DIV/0!
68 | 241384001-Bhallukghar- Komorpole hat - Bakultala hat Rd. | [13 empty] | 0 | #DIV/0!
69 | 241383010 Bakaborshi Natun hat-Durbadanga UP via Gorvanga Bazar | [13 empty] | 0 | #DIV/0!
70 | 241383016 Periodic Maintenance of Mongalkot UP-Hizaldanga bazar upto Subasni RHD Road From Ch.00-3750m | KDRIDP/Jess/M-22/2017-18 | 3.75 | 0 | 0 | 181.75 | [8 empty] | 0 | #DIV/0!
71 | 241384029 Periodic Maintenance of Raghurampur Trimohoni (Near Reg P/School) -Saraskati Bazar Road From Ch.00-1710m | KDRIDP/Jess/M-09/2017-18 | 1.71 | 0 | 0 | 49.705 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 52.19 | 0% | 2019-01-21 |  |  | 0 | 0%
72 | 241384031 Periodic Maintenance of Kasta-Raghurampur Road From Ch.00-2000m | KDRIDP/Jess/M-23/2017-18 | 2 | 0 | 0 | 69.87 | 2018-05-13 | M/S Biswajit Construction, 9 Rail Road, Jessore |  | 73.358 | 20% |  |  |  | 0 | 0% | Tender will be Recceived on Dated 14/05/2018
Sarsa
73 | 241902004-Periodic Maintenance of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra. Road From Ch.00-2225m,9225-10413m &10886-12150m | KDRIDP/Jess/M-06/2017-18 | 4.677 | 0 | 0 | 203.2 | 2018-02-26 | Abdur Razzaque Navaron Rail Bazar, Sharsha, Jessore | 2018-10-04 | 223.52 | 25% | 2019-09-01 |  |  | 0 | 0%
74 | 241903001-Periodic Maintenance of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.206-2783m,5060-6785m, 8341-9471m &9665-10665m | KDRIDP/Jess/M-05/2017-18 | 6.432 | 0 | 0 | 160.54 | 2018-05-20 | Md. Oahiduzzaman Navaron Rail Bazar, Sarsha, Jessore |  | 168.49 | 0% |  |  |  | 0 | 0% | NOA Date 11/06/2018
75 | 241903007-Sarsha Upazila H/Q- Saratala Bazar via Laxmnpur U H/Q Rd. | [13 empty] | 0 | #DIV/0!
76 | 241903008-Benapole GC-Bahadurpur YP H/Q via Ghiba Rd. | [13 empty] | 0 | #DIV/0!
77 | 241903018-Baguri R&H -Kayba Union H/Q via Mohisha Madrasha Rd. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
78 | 241904070-Saratola Bazar-Beltaghat Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 76.584 | 0 | 0 | 2489.23 |  |  |  | 1896.272 | 17% |  | 138.16 | 193.045 | -54.885 | 10.18%
GC-Hat
Monirampur
1 | Construction of Parkhajura-Hat GC | KDRIDP/Jess/GC-15/2017-18 | 0 | 0 | 1 | 18.98 | 2018-02-08 | M/S Palash Enterprise, Nowapara, Abhoynagar, Jessore | 2018-03-04 | 17.559 | 20% | 2018-09-10 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 1 | 18.98 |  |  |  | 17.559 | 20% |  | 0 | 0 | 0 | 0%
Tree Plantation
Jessore Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Bagherpara
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Abhoynagar
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Chowgacha
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Jhikargacha
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Monirampur
6 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Keshabpur
7 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Sarsa
8 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 235.323 | 44 | 1 | 13421.18 |  |  |  | 9026.933 | 36.99% |  | 1372.548 | 2399.993 | -1027.445 | 26.59%
|  |  | 235.323 | 44 | 1 | 13421.18 |  |  |  | 9026.933 | 9.519% |  | 1372.548 | 2399.993 | -1027.445 | 26.59%

## Jhikargacha
Jhikargacha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241232012 : Navaran puraton Bazar-Seordah GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241232015-Jhikargacha Rhana Hospital More-Goaldha Bazar via Padmapukur Kashipur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 241232016 : Hazirbag UZR-Matikumra UZR via Hazirbag UPC & MatiKumra Bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 241233001-Improvement of Parbazar-Chutipur bazar (Gongganandapur UP) Road From Ch. 5775 - 9925m | KDRIDP/Jess/W-49/2017-18 | 4.15 | 0 | 0 | 290.13 | 2018-03-13 | M/S Monir Traders Natun Khayertala, Jessore | 2018-04-04 | 316.09 | 15% | 2019-01-13 | 0 | 0 | 0 | 0% | 0
5 | 241233002-Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241233004 : Improvement of Lawjani bazar-Jhikargacha Katakhal bazar(Shahid Rafique Sarak) Road From Ch. 00 - 162m & 600-1750m | KDRIDP/Jess/W-47/2017-18 | 1.312 | 0 | 0 | 82.48 | 2017-10-30 | M/S Monir Traders Natun Khayertala, Jessore | 2017-11-30 | 79.39 | 65% | 2018-07-20 | 0 | 29.32 | -29.32 | 36.93% | 0
7 | 241233006 : Improvement of Seordah GC-Moheshpara Road From Ch. 3750 - 6350m | KDRIDP/Jess/W-48/2017-18 | 2.6 | 0 | 0 | 146.91 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 140.85 | 50% | 2018-03-12 | 0 | 43.26 | -43.26 | 30.71% | 0
8 | 241233008 : Bakra UP-Jhapa (Bridge) Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241233009 : Bakra bazar(Bakra UP)-Matshia bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 241233012 : Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More. Road From Ch. 6460 - 8350m. [Salvage Cost Tk. 6,982.00] | KDRIDP/Jess/W-83/2017-18 | 1.89 | 0 | 0 | 151.4 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 18/03/2018
11 | 241233013 : Improvement of Magura New Market-Magura UP office Road From Ch. 492 - 1300m [Salvage cost Tk. 2,37,171.00] | KDRIDP/Jess/W-50/2017-18 | 0.81 | 0 | 0 | 54.34 | 2017-10-30 | MD. Humayun Kabir Nobarakpur, Jhikorgacha, Jessore | 2017-11-30 | 49.06 | 100% | 2018-04-22 | 45.885 | 45.885 | 0 | 93.53% | Final
12 | 241233017 : Godkhali UP-Bodhkhana bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241233018 : Improvement of Barbakpur bazar-Simulia UP Road From Ch. 00-1150m. | KDRIDP/Jess/W-51/2017-18 | 1.15 | 0 | 0 | 75.47 | 2017-10-26 | M/S Jamuna Prokousoli Hatkhola Road, Jessore | 2017-12-12 | 75.17 | 100% | 2018-09-16 | 75.129 | 75.129 | 0 | 99.95% | Final
14 | 241233024 : Shimulia UP-Gorpara GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241233025 : Godkhali bazar-Panishara UP(Borni bazar). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241233026 : Shimulia UP-Godkhali bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241233027 : Shimulia UP-Navaran UP (at Kalagachi RHD). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241233028 : Lawjani Bazar(Jhikargacha UP)-Naranggali bazar(Sadar) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241233029 : Jhikargacha GC-Jhikargacha UP(Lawjani Bazar) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
20 | 241234009 : Fatepur-Bodhkhana bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241234013 : Misrideara UZR Jamtala-Angarpara. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241234035 : Improvement of Komarchanda-Nayra bazar Road From Ch. 00 - 925m | KDRIDP/Jess/W-06/2016-17 | 0.925 | 0 | 0 | 55.32 | 2017-07-03 | M/S Mysha Traders, 377/1, South Goran, Sabujbag, Dhaka-1219 | 2017-09-13 | 52.25 | 70% | 2018-05-31 | 0 | 29.24 | -29.24 | 55.96% | 0
23 | 241234052-Improvement of Digri bazar-Sadipu bazar Road From Ch.00-148 m | KDRIDP/Jess/W-15/2016-17 | 0.148 | 0 | 0 | 10.36 | 2017-07-27 | M/S Bakul Enterprise Pulerhat Bazar, Chanchara, Jessore | 2017-09-25 | 10.33 | 100% | 2018-03-14 | 10.33 | 10.33 | 0 | 100% | Final
24 | 241234071-Gongganandapur UP- Panditpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 241235001 : Bishahari-Atulia UZR. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241235012 : Magura UP Office-Magura UZR. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241235028 : Nabibnagar RHD-Kamarpara GPS. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 241235031 : Kawria GPS More-Towra. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 241235282-Gongadharpur Israil's house-Palla Lutfor's house. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
30 | 241234040-Nawali bazar-Kanarali bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
31 | 241232015-Jhikargacha Thana Hospital more- Goaldah Bazar via Padmapukur Kashipur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 241233001-Parbazar-Chutipur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 241233002-Periodic Maintenance of Navaran Puratan bazar- Chutipur bazar Gongganandapur UP) Road From Ch.9750-14750m | KDRIDP/Jess/M-24/2017-18 | 5 | 0 | 0 | 166.579 | 2018-10-04 | M/S Sarder International Gohata Road, Cityplaza Complex, Jessore | 0 | 174.89 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Dare 10/05/2018
34 | 241233021-Sankarpur UP-Shamta Bazar RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 241233024-Periodic Maintenance of Shimulia UP-Gorpara GC Road From Ch.00-2401m. | KDRIDP/Jess/M-25/2017-18 | 2.401 | 0 | 0 | 60.376 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 28/05/2018
Tree Plantation
36 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 20.386 | 0 | 0 | 1093.365 |  |  |  | 898.03 | 13.89% |  | 131.344 | 233.164 | -101.82 | 25.96%

## Keshabpur
Keshabpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241382005 Improvement of Chingra-Rajgonj via Trimohani UP (Keshabpur Portation) Road From Ch. 12600-13440m | KDRIDP/Jess/W-99/2017-18 | 0.8 | 0 | 0 | 68.496 | 2018-05-27 | M/S Alom Enterprise Bagda, Keshabpur, Jessore | 0 | 71.9 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 14/06/2018
2 | 241382009 Mongalkot UP-Saraskati bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 241383004 Improvement of Biddanandakati UP-Kabilpur RHD more Via Hasanpur Road From Ch. 00-2760m. [Salvage Cost Tk. 60,56,868.00] | KDRIDP/Jess/W-100/2017-18 | 2.76 | 0 | 0 | 198.925 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 04/07/2018
4 | 241383005 Keshabpur Pilot High School-Gorvanga Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 241383008 Biddanandakati UP-Jamalgong Bazar Via Parchakra Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241383009 Sagardari UP- Kabilpur GPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241383011-Improvement of Panjia UP-Hoder hat Road From Ch. 00-3200m. [Salvage Cost Tk. 47,27,475.00] | KDRIDP/Jess/W-07/2016-17 | 3.2 | 0 | 0 | 229.93 | 2017-08-16 | M/S Mohidul Islam, 13/A Rail Road, Rail Bazar, Jessore | 2017-09-27 | 224.98 | 45% | 2017-08-17 | 0 | 0 | 0 | 0% | 0
8 | 241383014-Panjia UP-Burali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241383018 Improvement of Mangolkot UP-Buruli bazar Road From Ch. 2616-4016m. [Salvage Cost Tk. 25,250.00] | KDRIDP/Jess/W-08/2016-17 | 1.4 | 0 | 0 | 87.96 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-06-14 | 87.77 | 100% | 2018-05-20 | 87.727 | 87.727 | 0 | 99.95% | Final
Improvement of Village Road by BC
10 | 241384008 Satkira Chira mill-Habspol Madrasha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 241384022 Dewli more-Dewli non Govt Primary School | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241384025 Improvement of Dashkohonia Ruhul Amin House-Burili Rishipara Road From Ch. 1000-2705m. [Salvage Cost Tk. 7,35,719.00] | KDRIDP/Jess/W-09/2016-17 | 1.705 | 0 | 0 | 102.65 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-11-06 | 102.39 | 100% | 2018-04-14 | 102.3 | 102.3 | 0 | 99.91% | Final
13 | 241384026 Satbaria Choudary Pond-Begompur more | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241384030 Protappur – Attonda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241384035 Boga-Mohadebpur road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241384037 Borenga-Pancharoi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241384038 Jhikra-baruihati (Kasta bazar-Sikerpur bazar road) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241384043 Boga FRB-Vanderkhola Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241384050 Improvement of Bosuntia (Mongolkot bazar)-Baduria via Ramkrishnapur Road From Ch. 480-1125m | KDRIDP/Jess/W-10/2016-17 | 0.645 | 0 | 0 | 42.34 | 2017-05-15 | M/S Joy Enterprise, Keshabpur Bazar, Keshabpur, Jessore | 2017-11-06 | 42.29 | 100% | 2018-04-30 | 42.24 | 42.24 | 0 | 99.88% | Final
20 | 241384051 Jahanpur Jamtala more-Vallukghar Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241385019 Improvement of Kanderpur-Gater-hat(Bongshir Battala) Road From Ch. 1000-2485m | KDRIDP/Jess/W-11/2016-17 | 1.485 | 0 | 0 | 88.92 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-12-06 | 88.74 | 100% | 2018-04-30 | 88.68 | 88.68 | 0 | 99.93% | Final
22 | 241385022 Baliadanga-Gurvanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241385540-Improvement of Dohori Village C&B - Surindronath Mondal bari Road From Ch. 00-1100m. [Salvage Cost Tk. 6,41,862.00] | KDRIDP/Jess/W-94/2017-18 | 1.1 | 0 | 0 | 72.746 | 0 | M/S Biswajit Construction, 9 Rail Road, Jessore | 0 | 76.369 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 14/06/2018
| 241385541-Improvement of Gurdaga-Dong ghat H/O Mono Boso Road From Ch. 00-1000m. [Salvage Cost Tk. 79,300.00] |  | 1 | 0 | 0 | 68.33 |  |  |  | 71.73 |  |  | 0 | 0 | 0 | 0%
Improvement of Village Road by HBB
24 | 241384046-Keshabpur UP-Shikerpur bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
25 | 241382009 Mongalkot UP-Saraskati bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241383006-Panjia Bazar UP- Monoharnagar Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241383007-Periodic Maintenance of Mongalkot-Panjia via Magurkhali Bazar Road From Ch.2300-3846m | KDRIDP/Jess/M-10/2017-18 | 1.546 | 0 | 0 | 48.335 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 50.75 | 0% | 2019-01-21 | 0 | 0 | 0 | 0% | 0
28 | 241383014-Panjia UP- Burali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 241384001-Bhallukghar- Komorpole hat - Bakultala hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 241383010 Bakaborshi Natun hat-Durbadanga UP via Gorvanga Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 241383016 Periodic Maintenance of Mongalkot UP-Hizaldanga bazar upto Subasni RHD Road From Ch.00-3750m | KDRIDP/Jess/M-22/2017-18 | 3.75 | 0 | 0 | 181.75 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 241384029 Periodic Maintenance of Raghurampur Trimohoni (Near Reg P/School) -Saraskati Bazar Road From Ch.00-1710m | KDRIDP/Jess/M-09/2017-18 | 1.71 | 0 | 0 | 49.705 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 52.19 | 0% | 2019-01-21 | 0 | 0 | 0 | 0% | 0
33 | 241384031 Periodic Maintenance of Kasta-Raghurampur Road From Ch.00-2000m | KDRIDP/Jess/M-23/2017-18 | 2 | 0 | 0 | 69.87 | 2018-05-13 | M/S Biswajit Construction, 9 Rail Road, Jessore | 0 | 73.358 | 20% | 0 | 0 | 0 | 0 | 0% | Tender will be Recceived on Dated 14/05/2018
Tree Plantation
34 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 23.101 | 0 | 0 | 1309.957 |  |  |  | 942.467 | 13.68% |  | 320.947 | 320.947 | 0 | 34.05%

## Chowgacha
Chowgacha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 241113003:( Singahjhully UP Office-Rashtampur bazar via Koyarpara Road.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241113005-Improvement of Nimtala bazar-Pasapole bazar via Pasapole UP Office Road Ch: 3120-3520m & 4020-4120m. | KDRIDP/Jess/W-106/2017-18 | 0.5 | 0 | 0 | 32.407 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
3 | 241113008-Improvement of Shingo jhuli UP-Marua bazar Road. From Ch:3000-3495 m. | KDRIDP/Jess/W-16/2017-18 | 0.495 | 0 | 0 | 28.22 | 2017-08-07 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-02 | 29.57 | 90% | 2018-08-13 | 0 | 14.83 | -14.83 | 50.15% | 0
4 | 241113012- Improvement of Jogodishpur-Arpara GC Road From Ch: 2025-3525m. | KDRIDP/Jess/W-91/2017-18 | 1.5 | 0 | 0 | 89.331 | 2018-04-18 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 0 | 93.67 | 0% | 0 | 0 | 0 | 0 | 0% | 0
5 | 241113013-Swarupda UP-Sukpukuria U.P Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241113016-Swarupda UP Office-Kharincha Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241113020- Solua GCCR-Pashapole UP Office Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 241114011-Guatoli UZR-Narayanpur UZR Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241114024-Improvement of Goribpur-Moshiuragor Road Ch: 00-875m. [Salvage cost Tk.30.524.00] | KDRIDP/Jess/W-106/2017-18 | 0.875 | 0 | 0 | 56.958 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 241114025 Improvement of Dhuliani bazar-Shajadpur Road From Ch: 00-184m & 1728-2465m. [Salvage Cost Tk. 3,49,720.00] | KDRIDP/Jess/W-70/2017-18 | 0.921 | 0 | 0 | 71.65 | 2018-05-07 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 0 | 75.225 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
11 | 241114034-Improvement of Mosiurnagor Bazar-Bariali Road Ch: 371-1925m [Salvage cost Tk.13,79,050.00] | KDRIDP/Jess/W-88/2017-18 | 1.554 | 0 | 0 | 101.38 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241114037-Dhuliani road-Uzirpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241114049-Goyra-Mashila Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241114063-Improvement of Arpara Bazer- Sarfarajpur Bazer via Kandi Road From Ch: 1120-2225m [Salvage cost Tk.6,63,400.00] | KDRIDP/Jess/W-89/2017-18 | 1.105 | 0 | 0 | 69.94 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 0 | 73.4 | 0% | 0 | 0 | 0 | 0 | 0% | 0
15 | 241114030-Improvement of Jahatabmunshir Vhagar Road. From Ch: 00-1000m | KDRIDP/Jess/W-29/2017-18 | 1 | 0 | 0 | 65.85 | 2017-09-06 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-15 | 69.13 | 0% | 2018-04-09 | 0 | 0 | 0 | 0% | 0
16 | 241115048-Karincha bazar-Madhabpur Burning Ghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241115140-Dashpakia-Nawdaga Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241115098-Improvement of Chanda Afra-Raynagor Road. From Ch: 1952-3182m. [Salvage Cost Tk.1,71,976.00 | KDRIDP/Jess/W-28/2017-18 | 1.23 | 0 | 0 | 73.49 | 2017-09-07 | M/S Jahid Hossain Kotchandpur Bus Stand Para, Jhenidah. | 2017-10-16 | 77.14 | 60% | 2018-09-06 | 0 | 48.5 | -48.5 | 62.87% | 0
19 | 241115098-Improvement of Chanda Afra-Raynagor Road From Ch: 00-520m under. [Salvage Cost Tk. 2,43,822.00] | KDRIDP/Jess/W-84/2017-18 | 0.52 | 0 | 0 | 33.23 | 2018-05-13 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore | 0 | 34.889 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
20 | 241115181-Improvement of Batikamari - Bundalitala Road [ Inventory Name: Batikamari Bhanga road- Batikamari village Road ] From Ch: 00-610m | KDRIDP/Jess/W-71/2017-18 | 0.61 | 0 | 0 | 43.865 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [2Nd Called]
21 | 241115030-Improvement of Bergobindapur- Math Road (Bergobindapur-Goalbari via Purbo Para) From Ch: 00-1000m. [Salvage Cost Tk. 3,41,285.00] | KDRIDP/Jess/W-58/2017-18 | 1 | 0 | 0 | 59.4 | 2018-03-12 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-04-18 | 62.45 | 40% | 2019-01-15 | 0 | 0 | 0 | 0% | NOA Date 27/03/2018
22 | 241115079-Improvement of DMC Madrasha - Joynarar union Road. From Ch: 00 - 1130m. [Salvage Cost Tk. 4,91,285.00] | KDRIDP/Jess/W-12/2016-17 | 1.13 | 0 | 0 | 69.69 | 2017-05-12 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-08-06 | 72.54 | 15% | 2018-04-30 | 0 | 0 | 0 | 0% | 0
23 | 241115079-Improvement of DMC Madrasha - Rainagar union Road From Ch:1130-2100 m. [Salvage Cost Tk.89,458.00] | KDRIDP/Jess/W-52/2017-18 | 0.97 | 0 | 0 | 65.46 | 2018-01-11 | M/D Jahid Hossain Kotchandpur Bus stand para, Jhenidah | 2018-02-07 | 68.73 | 60% | 2018-09-30 | 0 | 0 | 0 | 0% | 0
24 | 241115078-Improvement of Jhinaikundu-Jamira Road. From Ch: 00-1000m | KDRIDP/Jess/W-30/2017-18 | 1 | 0 | 0 | 57.77 | 2017-07-09 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2017-10-03 | 60.52 | 100% | 2018-02-09 | 60.52 | 60.52 | 0 | 100% | Final
25 | 241115078-Improvement of Jhinaikundu-Jamira Road From Ch: 1000-1535m. [Salvage Cost Tk. 66,223.00] | KDRIDP/Jess/W-74/2017-18 | 0.535 | 0 | 0 | 32.98 | 2018-05-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 0 | 34.627 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
26 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 00-1000m. [Salvage Cost Tk. 2,61,184.00] | KDRIDP/Jess/W-24/2017-18 | 1 | 0 | 0 | 58.5 | 2017-08-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-10 | 60.88 | 0% | 2018-08-20 | 0 | 0 | 0 | 0% | 0
27 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 1000-1340m. [Salvage Cost Tk. 19,597.00] | KDRIDP/Jess/W-73/2017-18 | 0.34 | 0 | 0 | 23.4 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 04/07/2018
28 | 241115199-Improvement of Fulsara Purbopara Madrasha- Abed ali house Road. From Ch:00-645 m [Salvage Cost Tk.1,61,285.00] | KDRIDP/Jess/W-17/2017-18 | 0.645 | 0 | 0 | 38.58 | 2017-08-06 | Md. Abdul Halim Kotchanpur, Jhenaidah | 2017-05-10 | 39.4 | 100% | 2018-08-25 | 39.4 | 39.4 | 0 | 100% | Final
29 | 241115207-Improvement of Fulshara Purbopara Village Road. From Ch: 00 - 680m. [Salvage Cost Tk. 8,37,415.00] | KDRIDP/Jess/W-13/2016-17 | 0.68 | 0 | 0 | 42.75 | 2017-05-15 | M/S Mim Enterprise, Gajirhat Road, Puraton Kosba, Jessore | 2017-11-06 | 42.94 | 60% | 2018-04-28 | 0 | 19.03 | -19.03 | 44.32% | 0
30 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road. From Ch: 00-455m [Salvage Cost Tk. 1,45,870.00] | KDRIDP/Jess/W-26/2017-18 | 0.455 | 0 | 0 | 27.63 | 2017-08-21 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-15 | 28.98 | 90% | 2018-08-27 | 0 | 16.22 | -16.22 | 55.97% | 0
31 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road From Ch: 455-636m. | KDRIDP/Jess/W-87/2017-18 | 0.181 | 0 | 0 | 11.24 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 0 | 11.8 | 0% | 0 | 0 | 0 | 0 | 0% | 0
32 | 241115262-Improvement of Araddah Muktijuddah Abdur Sattar Mia House -Sibnagor village via Balidapara GPS Road. From Ch: 00-1140m. [Salvage Cost Tk.1,04,350.00] | KDRIDP/Jess/W-25/2017-18 | 1.14 | 0 | 0 | 68.25 | 2018-02-19 | M/S Sun Enterprise, Chowgacha Bazar, Chowgacha, Jessore | 0 | 75.015 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Dated 12/03/2018
33 | 241115258-Improvement of Singojhuli Jhautala - Baruhati Road. From Ch: 00-1235m | KDRIDP/Jess/W-18/2017-18 | 1.235 | 0 | 0 | 71.51 | 2017-08-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-09-28 | 74.94 | 100% | 2018-05-31 | 74.64 | 74.64 | 0 | 99.6% | Final
34 | 241115131-Improvement of Dhakinsagor-Charabari via H/O Abdul Bari Road. From Ch: 00-1650m. [Salvage Cost. Tk. 62,601.00] | KDRIDP/Jess/W-22/2017-18 | 1.65 | 0 | 0 | 94.46 | 2017-08-21 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-10-03 | 99.06 | 100% | 2018-05-31 | 98.877 | 98.877 | 0 | 99.82% | Final
35 | 241115060-Improvement of Andulia-Doulatpur Road From Ch: 2327-3350m [Salvage cost Tk.9,77,690.00] | KDRIDP/Jess/W-90/2017-18 | 1.023 | 0 | 0 | 62.158 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 19/04/2018
36 | 241115153-Improvement of Patibila UP - Hayetpur via Uttor Para Road. From Ch: 00-1000m [Salvage Cost Tk.5,65,304.00] | KDRIDP/Jess/W-23/2017-18 | 1 | 0 | 0 | 59.93 | 2017-08-18 | M/S Jamuma Prokousoli hatkhola Road, jessore | 2017-10-02 | 62.8 | 0% | 2018-08-28 | 0 | 0 | 0 | 0% | 0
37 | 241115288-Improvement of Afra R&H road near H/O Mokbul via Karamot Ali Road. From Ch: 00-475m. [Salvage Cost Tk.3,08,590.00] | KDRIDP/Jess/W-20/2017-18 | 0.475 | 0 | 0 | 32.38 | 2017-10-19 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 33.54 | 0% | 2018-05-30 | 0 | 0 | 0 | 0% | 0
38 | 241115296-Improvement of Durgabor Kathi Amir Ali H/O -Tatul Bari Korban Biswas H/O Road. From Ch: 00-587m. | KDRIDP/Jess/W-21/2017-18 | 0.587 | 0 | 0 | 37.45 | 2017-10-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-11-26 | 38.89 | 0% | 2018-02-06 | 0 | 0 | 0 | 0% | 0
39 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid Road. From Ch: 00-1000m | KDRIDP/Jess/W-27/2017-18 | 1 | 0 | 0 | 62.74 | 2017-08-20 | M/S Sarkar Construction Lalbazar, Natore | 2017-10-10 | 64 | 60% | 2018-08-27 | 0 | 36.13 | -36.13 | 56.45% | 0
40 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid From Ch: 1000-1480m. [Salvage Cost Tk. 1,10,415.00] | KDRIDP/Jess/W-75/2017-18 | 0.48 | 0 | 0 | 30.22 | 2018-02-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-04-03 | 30.61 | 0% | 2018-11-19 | 0 | 0 | 0 | 0% | 0
41 | 241115292-Improvement of Souila Arpara road near H/O Toffazial-Durabakati H/O Ismail Road. From Ch:00-350 m .[Salvage Cost Tk.1,94,990.00] | KDRIDP/Jess/W-19/2017-18 | 0.35 | 0 | 0 | 21.76 | 2017-10-17 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 21.458 | 0% | 2018-05-30 | 0 | 0 | 0 | 0% | 0
42 | 241115269-Improvement of Sayedpur Shek Para Abdur Razzak Shop- Purbo Mat Pucca Road From Ch: 00-1470m. [Salvage Cost Tk. 1,89,585.00] | KDRIDP/Jess/W-72/2017-18 | 1.47 | 0 | 0 | 97.755 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 241115008-Improvement of Swruppur Hajambari-Bagdanga Road From Ch: 00-2200m. [Salvage Cost Tk. 5,95,622.00] | KDRIDP/Jess/W-60/2017-18 | 2.2 | 0 | 0 | 142.81 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 07/05/2018
44 | 241115014-Improvement of Tazbizpur-Jatrapur Road From Ch: 864-2035m | KDRIDP/Jess/W-59/2017-18 | 1.171 | 0 | 0 | 71.695 | 2018-04-25 | M/S Renu Enterprise Asrom Road Jessore | 2018-05-24 | 75.25 | 0% | 2018-02-24 | 0 | 0 | 0 | 0% | 0
45 | 241115286-Improvement of Anderkota Primary school-Panchbaria Beel Tematha BC Road From Ch:00-1075 m | KDRIDP/Jess/W-55/2017-18 | 1.075 | 0 | 0 | 58.92 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 63.028 | 0% | 2019-01-24 | 0 | 0 | 0 | 0% | 0
46 | 241115044-Improvement of Baishagari BC Road - Hazrakhana Kadamtala BC Road via Anderkota, Batikamari Road. (Batkamari- Mohespur Road.)Road. From Ch:1500-2680m | KDRIDP/Jess/W-56/2017-18 | 1.18 | 0 | 0 | 70.706 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 75.649 | 0% | 2019-01-15 | 0 | 0 | 0 | 0% | 0
47 | 241114026-Improvement of Kongsharipur-Mashila Road. From Ch: 2043-2198m & 4080-5510m | KDRIDP/Jess/W-57/2017-18 | 1.585 | 0 | 0 | 89.53 | 2018-03-12 | MD. Noor Islam. Purbo Barandipara, Jessore | 2018-04-17 | 95.72 | 40% | 2018-09-12 | 0 | 0 | 0 | 0% | NOA Date 27/03/2018
48 | 241115271- Sayedpur Altab Mondol House-H/O Thandu Mondol via Mondol Para Jame Mosque Road. | KDRIDP/Jess/W-85/2017-18 | 0.236 | 0 | 0 | 15.95 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | Tender will be Recceived on Dated 04/07/2018
Improvement of Village Road by HBB
49 | 241114038-Burinda-Dashpakia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
50 | 241112008-Periodic Maintenance of Solua GC-Arpara GC Road From Ch.5500-7325m | KDRIDP/Jess/M-11/2017-18 | 1.825 | 0 | 0 | 60.646 | 2018-04-25 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore | 0 | 63.678 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 20/05/2018
51 | 241112011-Purapara GC-Moheshpur Pucca road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
52 | 241113010-Periodic Maintenance of Debipur-Narayanpur GC Road From Ch.00-1260m. | KDRIDP/Jess/M-12/2017-18 | 1.26 | 0 | 0 | 30.358 | 2018-04-25 | M/S Sheba Traders Chowgacha Bazar, Chowgacha, Jessore | 0 | 31.87 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Dare 16/05/2018
53 | 241113011-Periodic Maintenance of Chowgacha U.P-Dhuliani Via Bergobindapur Baor Road From Ch.275-1100m. | KDRIDP/Jess/M-13/2017-18 | 0.825 | 0 | 0 | 19.82 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 20.809 | 100% | 2018-11-30 | 20.8 | 20.8 | 0 | 99.96% | Final
54 | 241113014-Periodic Maintenance of Sukpukuria U.P-Andulia bazar Road From Ch.900-3680m | KDRIDP/Jess/M-14/2017-18 | 2.78 | 0 | 0 | 47.95 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
55 | 241113005-Nimtala Bazar-Pasapole Bazar via Pasapole UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
56 | 241113017-Sukpukria UP Office -Goira Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
57 | 241113013-Swarupda UP- Sukpukuria UO Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
58 | 241114052-Chowgacha -Kabilpur Rd Mashampur more - Masila Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
59 | 241115022-Maligati -Bariali Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
60 | 241114009(Roghonatpur-Dashpakhia bazar Road) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
61 | 241114014-Periodic Maintenance of Purapara Sonali Bank-Ballave pur Road From Ch.820-4900m | KDRIDP/Jess/M-16/2017-18 | 4.08 | 0 | 0 | 109.69 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 117.36 | 100% | 2018-11-30 | 117.36 | 117.36 | 0 | 100% | Final
62 | 241114024(Goribpur-Moshiuragor Road.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
63 | 241114026(Kongsharipur-Mashila Road). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
64 | 241114028-Periodic Maintenance of Kamlapur More-Mashila Bazar Road From Ch.00-1115m | KDRIDP/Jess/M-15/2017-18 | 1.15 | 0 | 0 | 28.174 | 2018-07-05 | Md. Noor Islam, Purbo Barandipara, Jessore | 0 | 29.58 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Dare 27/05/2018
65 | 241114044Muktadah-Jagadishpur UP Road..) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
66 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 48.023 | 0 | 0 | 2538.583 |  |  |  | 2009.148 | 16.89% |  | 411.597 | 546.307 | -134.71 | 27.19%

## Jessore Sadar
Jessore Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241472009-Rupdia GC-Basundia Moor RHD via Shakarigati Road | KDRIDP/Jess/W-81/2017-18 | 2.71 | 0 | 0 | 224.256 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 17/05/2018
2 | 241472012-Razarhat GC-Hamidpur RHD Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 241472013-Jongle Bandle RHD-Basundia GC Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch: 7500-9350m. [Salvage Cost Tk. 28,17,772.00 ] | KDRIDP/Jess/W-14/2016-17 | 1.85 | 0 | 0 | 128.13 | 2017-05-29 | M/S Morol Enterprise Balia, Vakutia Bazar, Sadar, Jessore | 2017-12-07 | 128.11 | 50% | 2018-06-19 | 0 | 0 | 0 | 0% | 0
5 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch:10416-11460m under Upazila: Sadar, District: Jessore. | KDRIDP/Jess/W-82/2017-18 | 1.044 | 0 | 0 | 78.89 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore | 0 | 82.83 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
Improvement of Union Road by BC
6 | 241473003-Improvement of Lebutala UP Office-Shyamnagar via Fultola Bazar Road. From Ch:5423-7723m & 9450-10236m. [Salvage Cost. Tk.42,07,378.00] | KDRIDP/Jess/W-54/2017-18 | 3.086 | 0 | 0 | 221.42 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
7 | 241473005-Upashahor UP-Dolennagar Bazar Rd via Kashimpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241473007-Chanchra UP office-Kuadah Bazar via Sarapol Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241473010-Improvement of Chanchra Bazar-Chanchar UP via Vaturia(Jessore Khulna Hogway Beltolarmore Bormonpara Nodermore via Chanchra High School) Road. From Ch:00-1300m. [Salvage Cost. Tk.12,59,686.00] | KDRIDP/Jess/W-101/2017-18 | 1.3 | 0 | 0 | 86.959 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 241473011-Natunhat-Deara UP office via Dattopara Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 241473019-Arabpur UP Office-Faridpur Old Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241473020-Haibatpur UP-Ambottola via Kamalpur, Shahabajpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241473021-Churamonkati UP Office-Khojar Hat Rd (Kashimpur UP) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241473022-Fatehpur UP Office-Bablatola Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241473024-Labutola UP-Andolpota via Agrail, Enayetpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241473025-Lawjani Bazar-Deeara UP Office via Narangali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241473030-Ichali UP (Bangda more) - Labutala Bazar via Rajapur (RHD) . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241473031-Pulerhat - Arabpur UP (Mondalgati) Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241473001-Improvement of Chowlia Gate-Sutighata Ramnagar UP Office Road. From Ch:2660-4255m. [Salvage Cost. Tk.37,44,628.00] | KDRIDP/Jess/W-68/2017-18 | 1.595 | 0 | 0 | 107.517 | 2018-05-28 | M/S Jamuna Prokousoli, Hatkhola Road, Jessore | 0 | 112.87 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 14/06/2018
Improvement of Village Road by BC
20 | 241474002-Improvement of Haibathpur -Uttar Lolitadha Road. From Ch:1030-104m & 1180-2560m. [Salvage Cost. Tk.34,666.00] | KDRIDP/Jess/W-95/2017-18 | 1.39 | 0 | 0 | 102.107 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore | 0 | 107.207 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
21 | 241474003-New Khairtala R&H-Bahadurpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241474004-Khairrala Seed Office-Boalpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241474007-Sujalpur Muchipara-Faridpur old Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 241474009-Improvement of Gopalpur-Rampur Pry. School Road. From Ch:2000-4105m. [Salvage Cost. Tk.3,68,686.00] | KDRIDP/Jess/W-69/2017-18 | 2.105 | 0 | 0 | 130.835 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
25 | 241474015-Rudropur-Sarapole bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241474017-Rupdia Jamtala R&HD- Rustompur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241474020-Basundia bazar-Jogonnathpur Kheaghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 241474021-Deapara-Ghop RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 241474027-Muroli more R&HD-Kanitala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 241474052-Setarampur-Jhumjhumpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 241474055-Dhopakhola RHD-Durgapur Koyetpara Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 241474056-Taragonj-Ramkrisnapur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 241474063-Mondolgaty (Kholadanga)-Arabpur UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | Patan Paikpara-Chitra Bazar-Bagerpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | Monsefnagar village Biswas para Jame Mosque-Monsefnagar Secendary School rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 241475293 Enayetpur-Teerhat Road. via Kadir Para (H/O Minaz-Manikdihe-Dhaka rd) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 241475285 Narendropur Pucca Road to Narendropur High School Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 241475292 ahsania mission road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
39 | 241474005-Churmankati Rail gate-Dogachia Beel Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 241474016-Hamidpur Kamar bari-Dhitila Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
41 | 241473016-Const. of RCC Bridge on Stiantola Bazar-Ichali UP via Suro Kamergona Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 241473002-Const. of RCC Bridge on Narendrapur UP-Dailala Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
43 | 241472012-Razarhat GC-Hamidpur RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 241472014-Churamankati GC-Kayemkhola GC via Bagdanga Jhowdia Bazar Chandutia Rd | KDRIDP/Jess/M-01/2017-18 | 2.805 | 0 | 0 | 120.728 | 2018-04-25 | M/S L Rahaman Enterprise R. N. Road, Jessore | 0 | 126.76 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 20/05/2018
45 | 241472017-Monohorpur Bazar RHD - Narikel Baria GC via Raipur UP ( sadar part) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 241473002-Narendrapur UP-Daitala Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 241473005-Periodic Maintenance of Upashahor UP - Tail kup Bazar Rd. Via Kashimpur, Dighirpar Road From Ch.00-1300m | KDRIDP/Jess/M-21/2017-18 | 1.33 | 0 | 0 | 62.36 | 2018-11-05 | M/S S S Traders Kazi Para, Puraton Koshba, Jessore | 2018-05-28 | 65.469 | 85% | 2019-02-03 | 0 | 54.885 | -54.885 | 83.83% | 0
48 | 241473007-Chanchra UP Office-Kuadah Bazar via Sarapol Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 241473008-Bagerhat Bazar-Ramnagar UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
50 | 241473009-Sannashi Bottala Bazar- Ramnagar UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
51 | 241473010-Chanchara Bazar -Chanchar UP via Vaturia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
52 | 241473016-Periodic Maintenance of Satiantola Bazar- (Fulbari More) Ichali UP via Suro, Kamergona Road From Ch.00-2975m | KDRIDP/Jess/M-02/2017-18 | 2.975 | 0 | 0 | 73.158 | 2018-04-22 | M/S Dilip Enterprise, Calectorit Mosjid Market, Jessore | 0 | 76.808 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 16/05/2018
53 | 241473028-Khajura(Bagherpara) GC-Barobazar(Kaligonj) GC Road via Labutola UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
54 | 241474010-Periodic Maintenance of Basundia Bazar-Afraghat Ghat Road From Ch.00-2540m. | KDRIDP/Jess/M-04/2017-18 | 2.54 | 0 | 0 | 74.54 | 2018-04-23 | M/S Sharif Rabrul Enterprise Jail Road Ghop, Jessore | 0 | 78.266 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 20/05/2018
55 | 241474012-R&H Rd. at Bijoynagar-Bolpur Ghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
56 | 241474026-Periodic Maintenance of Pulerhat Shishu Aparad Centre-Vaturia Road From Ch.00-1400m | KDRIDP/Jess/M-03/2017-18 | 1.4 | 0 | 0 | 84.418 | 2018-04-24 | M/S Harun or Rashid Nowapara Road, Ghop, Jessore | 0 | 88.45 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 20/05/2018
57 | 241474033-Bablatola Taxi Stand-Sarothi Mill Gabtola Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
58 | 241474044-Nutunhat RHD-Bagerhat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
59 | 241475083-Beltola -Khmalpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
60 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 26.13 | 0 | 0 | 1495.318 |  |  |  | 866.77 | 2.25% |  | 0 | 54.885 | -54.885 | 6.332%

## Monirampur
Monirampur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241612008-Monirampur-Mukterpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241612018-Dighirpar-Dumurkhali Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 241613001-Improvement of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 3500-6420m | KDRIDP/Jess/W-03/2016-17 | 2.92 | 0 | 0 | 176.63 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-06-01 | 168.71 | 100% | 2018-04-26 | 168.67 | 168.67 | 0 | 99.98% | Final
4 | 241613002-Chalkidanga Bazar-Rohita UP via Kashimnagar UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241613006-mprovement of Chalkidanga Bazer-Haridashkati UP via Joypur bazar Road From Ch. 4371-5800m | KDRIDP/Jess/W-44/2017-18 | 1.429 | 0 | 0 | 92.44 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 91.41 | 100% | 2018-07-15 | 0 | 49.86 | -49.86 | 54.55% | 0
7 | 241613009-Improvement of Nehalpur UP-Hazirhat bazar via Kultia UP Road From Ch. 00-3557m | KDRIDP/Jess/W-04/2016-17 | 3.557 | 0 | 0 | 231.18 | 2017-10-22 | M/S Motinur Rahaman Nannu, 57, Chalk Bazar, Faridpur | 2017-11-16 | 250.7 | 60% | 2018-02-12 | 0 | 125.52 | -125.52 | 50.07% | 0
8 | 241613011-Improvement of Sundalpur bazar-Haridashkati UP via Salimpur Road From Ch. 9050-10920m. [Salvage Cost Tk. 1,73,331.00] | KDRIDP/Jess/W-103/2017-18 | 1.87 | 0 | 0 | 137.89 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
| 241613019-Improvement of Khanpur UP-Horidaskati UP Road From Ch. 2550-3380m. [Salvage Cost Tk. 13,90,230.00] |  | 0.83 | 0 | 0 | 61.04 | [6 empty] | 0 | 0 | 0 | #DIV/0!
9 | 241613012-Improvement of Bhojgati UP-Dhakuria UP via Horergati Road From Ch. 1000-4810m. [Salvage Cost Tk. 3,15,834.00] | KDRIDP/Jess/W-79/2017-18 | 3.81 | 0 | 0 | 270.36 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 17/05/2018
10 | 241613013-Improvement of Tangramari-Khedapara U.P.via Jalalpur Road From Ch. 00-2120m. [Salvage Cost Tk. 54,342.00] | KDRIDP/Jess/W-77/2017-18 | 2.12 | 0 | 0 | 151.21 | 2018-05-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 0 | 155.72 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 14/06/2018
11 | 241613014-Shyamkur Up-Chandipur via Lakkanpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241613016-Improvement of Muragacha-Horihornagor U.P.via Modonpur Road From Ch. 1000-2695m. [Salvage Cost Tk. 13,90,230.00] | KDRIDP/Jess/W-45/2017-18 | 1.695 | 0 | 0 | 116.18 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 111.33 | 45% | 2018-09-03 | 0 | 0 | 0 | 0% | 0
13 | 241613022-Nangro Bazar - Rashulpur via Jamtala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
14 | 241614005-Monirampur College-Debidaspur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241614019-Improvement of Komolpur-Tazpur Road From Ch. 00-2000m [Salvage Cost Tk. 21,76,122.00] | KDRIDP/Jess/W-78/2017-18 | 2 | 0 | 0 | 143.17 | 2018-05-12 | Sayed Nahid Hassan Keshabpur Bazar, Keshabpur, Jessore | 0 | 150.25 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
16 | 241614020-Chandipur-Hanuar Amtala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241614025-Improvement of Rajgonj Jamshed mill-Monohorpur Road From Ch. 1540-2106m. [Salvage Cost Tk. 51,999.00] | KDRIDP/Jess/W-41/2017-18 | 0.566 | 0 | 0 | 40.63 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 40.39 | 60% | 2018-05-28 | 0 | 22.87 | -22.87 | 56.62% | 0
18 | 241614041-Mobarokpur Ghospara-Negura Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241614048-Fakirrasta-Keshabpur via Hashadanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 241614066-Kharinci-Rohita Shaikpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241614079-Improvement of Kashimpur Battala-Rohita U.P Road From Ch. 1250-3200m. [Salvage Cost Tk. 1,59,608.00] | KDRIDP/Jess/W-80/2017-18 | 1.95 | 0 | 0 | 139.45 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 30/05/2018
22 | 241614100-Subalkati Edgah-Lawkunda Sr.Madrasha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241614113-Improvement of Hazrakati Daspara More - Hazrakati Sanapara Road From Ch. 944-1985m. [Salvage Cost Tk. 1,86,215.00] | KDRIDP/Jess/W-42/2017-18 | 1.041 | 0 | 0 | 79.4 | 2017-10-29 | M/S Hira construction Main Road, Monirampur, Jessore | 2017-11-30 | 79.5 | 40% | 2018-05-28 | 0 | 12.31 | -12.31 | 15.48% | 0
24 | 241615035-Improvement of Parala-Satgati Road From Ch. 00-925m | KDRIDP/Jess/W-05/2016-17 | 0.925 | 0 | 0 | 61.07 | 2017-05-15 | M/S Hira Construction, Main Road Monirampur, Jessore | 2017-05-29 | 60.81 | 100% | 2018-04-28 | 59.575 | 59.575 | 0 | 97.97% | Final
25 | 241615071-Boalia Bazar-Uttarpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241615110-Moshimnagor Charabattala-Vorotpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241614076-Improvement of 8 mile(RHD)-Khahimnagor U.P. Road From Ch. 00-1780m. [Salvage Cost Tk. 10,61,912.00] | KDRIDP/Jess/W-38/2017-18 | 1.67 | 0 | 0 | 131.55 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 130.25 | 100% | 2018-07-15 | 130.13 | 130.13 | 0 | 99.91% | Final
28 | 241615398-Improvement of Atghara purbopara - Amjamtola Road From Ch. 00-805m | KDRIDP/Jess/W-39/2017-18 | 0.805 | 0 | 0 | 57.11 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore | 0 | 59.948 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
29 | 241614060-Improvement of Lakhanpur Mandartala-Gouripur FWC Road From Ch. 00-470m | KDRIDP/Jess/W-40/2017-18 | 0.47 | 0 | 0 | 34.81 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 34.96 | 60% | 2018-05-28 | 0 | 19 | -19 | 54.35% | 0
30 | Routia UP Bashdebpur bazar Torafdar Bostlay-Bashdebpur Dakil Madrasha & Attimkhana-Mathpara mono molla H/O road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 241615185-Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 00-1000m. [Salvage Cost Tk. 83,892.00] | KDRIDP/Jess/W-53/2017-18 | 1 | 0 | 0 | 75.93 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore | 0 | 79.7 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 27/05/2018
32 | 241615185- Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 1000-2095m | KDRIDP/Jess/W-92/2017-18 | 1.095 | 0 | 0 | 77.93 | 2018-04-09 | M/S Sajan Enterprise Chanchara Cheakpost Jessore | 0 | 81.827 | 40% | 0 | 0 | 0 | 0 | 0% | 0
33 | 241615336-Parkhaajura-Baroypara more-Garidkhali road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
34 | 241614089-Khedapara U.P.-Kasipur Mandertala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
35 | 241613020-Const. of RCC Bridge on Dhakuria UP- Gabukhali Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 241614070-Construction of 44.0m RCC Girder Bridge on Fakir Rasta-Pazia Road at Ch.500m | KDRIDP/Jess/W-31/2017-18 | 0 | 44 | 0 | 245.86 | 2017-10-23 | Kamarjani-Brojen-Anowara-JV, Sree Angoan, faridpur | 2017-11-30 | 221.27 | 60% | 2018-02-12 | 0 | 124.82 | -124.82 | 56.41% | Pair pile & Cap casting complet
37 | 241615002-Const. of RCC Bridge onMujguni-Durgapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
38 | 241612011-Monirampur- Noapara -Kultia -Nehalpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 241612014-Periodic Maintenance of Monoharpur Bazar-Chinatola Bazar Road From Ch. 00-3900m [Salvage Cost Tk.5,14,017.00] | KDRIDP/Jess/M-18/2017-18 | 3.9 | 0 | 0 | 147.2 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 241612015-Sundali Bazar-Dhakuria-Pramebag Gate road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 241612019-Periodic Maintenance of Nehalpur-Durbadanga-Bajitpur Road From Ch. 2830-8690m. [Salvage Cost Tk.7,61,457.00] | KDRIDP/Jess/M-17/2017-18 | 5.86 | 0 | 0 | 249.06 | 2018-05-16 | M/S Bonantor Trading Corporation Benapol Road Chanchara, Jessore | 0 | 261.418 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Dare 07/06/2018
42 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 241233002 : Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 241233005 : Borni bzar(Panishara UP)-Bejiatala bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 241233006 : Seordah GC-Moheshpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 241613018-Fakir Rasta bazar-Chaluahati UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 241612016-Lawri (Madrasha) RHD -Khedapara GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 241613001-Periodic Maintenance of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 7580-8703m [Salvage Cost Tk.Tk.1,42,500.00] | KDRIDP/Jess/M-19/2017-18 | 1.123 | 0 | 0 | 26.38 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 241613010-Periodic Maintenance of Gopalpur Bazar-Kultia U.P.office Road From Ch. 00-4590m [Salvage Cost Tk.4,92,836.00] | KDRIDP/Jess/M-20/2017-18 | 4.59 | 0 | 0 | 122.29 | 2018-03-13 | M/S. Banantor Trading Corporation Benapol Road Chanchara, Jessore | 2018-04-15 | 128.4 | 10% | 2019-01-22 | 0 | 0 | 0 | 0% | 0
50 | 24164080-Khedapara-Maragacha via Gangulia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
51 | Construction of Parkhajura-Hat GC | KDRIDP/Jess/GC-15/2017-18 | 0 | 0 | 1 | 18.98 | 2018-02-08 | M/S Palash Enterprise, Nowapara, Abhoynagar, Jessore | 2018-03-04 | 17.559 | 20% | 2018-09-10 | 0 | 0 | 0 | 0% | 0
Tree Plantation
52 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 45.226 | 44 | 1 | 2887.75 |  |  |  | 2124.152 | 15.29% |  | 358.375 | 712.755 | -354.38 | 33.55%

## Sarsa
Sarsa
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241902004-Improvement of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra Road From Ch.5064-7300m, 8725-9225m & 12150-15397m. [Salvage Cost Tk.18,35,766.00] | KDRIDP/Jess/W-33/2017-18 | 5.983 | 0 | 0 | 436.357 | 43030 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 43058 | 419.76 | 50% | 2018-10-15 | 0 | 139.79 | -139.79 | 33.3% | 0
Improvement of Union Road by BC
2 | 241903001-Improvement of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.10665-13520m. [Salvage Cost Tk.21,87,707.00] | KDRIDP/Jess/W-36/2017-18 | 2.855 | 0 | 0 | 171.625 | 43030 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 43058 | 165.09 | 60% | 2018-10-15 | 0 | 104.24 | -104.24 | 63.14% | 0
3 | 241903003-Kuchia More (Ulashi UP)-Dhaldah road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 241903004-Improvement of Dehi Union H/Q-Shikerpur Bazar via Fulsar Road From Ch.4480-6190m. [Salvage Cost Tk.2,04,049.00] | KDRIDP/Jess/W-34/2017-18 | 1.71 | 0 | 0 | 103.175 | 43030 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 43058 | 99.25 | 60% | 2018-10-15 | 0 | 29.65 | -29.65 | 29.87% | 0
5 | 241903008-Improvement of Benapole G.C-Bahadurpur UP H/Q via Ghiba Road From Ch.2545-7000m | KDRIDP/Jess/W-35/2017-18 | 4.455 | 0 | 0 | 268.13 | 43030 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 43058 | 265.08 | 25% | 2018-10-15 | 0 | 0 | 0 | 0% | 0
6 | 241903011-Goga Union H /Q-Khalshi bazar via Agrabhulat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241903016-Bahadurpur Union H/Q-Sharbunghuda Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241473020 Dehi Union H/Q –Wapda Bazar upto Kashipur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241903017-Ulashi Union H/Q-Jamtala Bazar Via Benekhori road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
10 | 241904002-Ghiba Uttar para-Sharbunghuda bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 241904003-Bagarchara (GC)-Basatpur Bazar rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241904015-Chandrapur-Belta ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241904023-Ulashi Debdar Tala-Jirengacha road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241904024-Ulashi Bazar Mosjheed R&H-Kannyadah Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241904026-Kagojpukur-Dubpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241904043-Trimohini-Kulpala via Bolidadah road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241904046-Naihati-Dehi road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241904047-Saratola High School-Tebaria Mosque via Daridurgapur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241904048-Sikerpur-Salta road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 241904052-Ekjhala Bazar-Kondarpopur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241904061-Bosotpur Madrasha-Baikola road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241904115-Golapole More-Keshadanga Village Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241905198- Improvement of Sibobash Khalil's House-Shalkona Primary School road Via Sahid Shangbadic Shamsur Rahman House Road From Ch.00-1440m [Salvage Cost. Tk. 3,68,361.00] | KDRIDP/Jess/W-37/2017-18 | 1.44 | 0 | 0 | 91.38 | 43025 | M/S Ashraf Traders Voirob stand, Haspatal Ghat, Khulna | 43095 | 91.16 | 60% | 2018-11-16 | 0 | 45.98 | -45.98 | 50.44% | 0
Improvement of Village Road by HBB
23 | 241904105-Improvement of Nizampur Bazar-Bahadurpur Road From Ch.2643-4718m. [Salvage Cost Tk.45,344.00] | KDRIDP/Jess/W-32/2017-18 | 2.075 | 0 | 0 | 75.315 | 43025 | M/S Asraf Traders, Voirob Road, Haspatal Ghat, Khulna | 43095 | 75.3 | 85% | 2018-11-16 | 0 | 61.99 | -61.99 | 82.32% | 0
Maintenance
24 | 241902004-Periodic Maintenance of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra. Road From Ch.00-2225m,9225-10413m &10886-12150m | KDRIDP/Jess/M-06/2017-18 | 4.677 | 0 | 0 | 203.2 | 43157 | Abdur Razzaque Navaron Rail Bazar, Sharsha, Jessore | 43377 | 223.52 | 25% | 2019-09-01 | 0 | 0 | 0 | 0% | 0
25 | 241903001-Periodic Maintenance of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.206-2783m,5060-6785m, 8341-9471m &9665-10665m | KDRIDP/Jess/M-05/2017-18 | 6.432 | 0 | 0 | 160.54 | 43240 | Md. Oahiduzzaman Navaron Rail Bazar, Sarsha, Jessore | 0 | 168.49 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 11/06/2018
26 | 241903007-Sarsha Upazila H/Q- Saratala Bazar via Laxmnpur U H/Q Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241903008-Benapole GC-Bahadurpur YP H/Q via Ghiba Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 241903018-Baguri R&H -Kayba Union H/Q via Mohisha Madrasha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 241904070-Saratola Bazar-Beltaghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
30 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 29.627 | 0 | 0 | 1509.722 |  |  |  | 1507.65 | 11.77% |  | 0 | 381.65 | -381.65 | 25.31%

## Abhoynagar
Abhoynagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241042005-Nowapara Upazila H/Q (Sankerpasha Bazarghat)-Amtala GC via Vatpara Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241042012-Nowapara GC (Shankerpasha Ghat)-Gobra GC via Borni Bazer road From Ch. 293-28450m [Salvage Cost Tk. 56,24,401.00] | KDRIDP/Jess/W-76/2017-18 | 2.552 | 0 | 0 | 199.92 | 2018-02-19 | Md. Abdur Rouf Molla, Bhoakhali, Ratangonj, Narail | 2018-04-18 | 210 | 0% | 2018-01-09 | 0 | 0 | 0 | 0% | 0
Improvement of Union Road by BC
3 | 241043002-Improvement of Chengutia Bazar-Sreedharpur UP Office Road From Ch. 1217-3600m | KDRIDP/Jess/W-01/2016-17 | 2.383 | 0 | 0 | 144.16 | 2017-05-15 | Md. Abdur Rouf Molla , Bhoakhali, Ratangonj, Narail | 2017-07-06 | 150.3 | 100% | 2018-04-30 | 150.285 | 150.285 | 0 | 99.99% | Final
4 | 241043004-Nowapara H/Q (Peer Bari Kheya ghat)-Baghutia U.P. Office via Maddhapur Pry.School ,Bogratala Mosque & Chow matha,Vatpara Gramin Bank Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 241043006-Paira U.P.Office-Chalisha U.P.Office (Bagdah Dharmatala Eid-gah) via Kuta madrasha,Bagdah Paschimpara Baltala More Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241043007-Sundali U.P.Office-Moshihati Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241043010-Baghutia UP office-Singari Bazar via Singari Dakhil Madrasha Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | BTMC ghat -Barni Bazar via Sreedarpur UP Complex Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 241044003-Improvement of Nowapara Betar South Corner R&H-Dumurtala via Dhopadi Road From Ch. 4175-5000m | KDRIDP/Jess/W-02/2016-17 | 0.825 | 0 | 0 | 51.38 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [5th Called]
10 | 241044004-Noapara North Bengal(Bengal Textile)-Gobindapur Thrimohony via Dhopapara primary school Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 241044006-Taltala-Gramtala via Ektarpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241044010-Paira(Kota Eayler More)-Kuta Shoyailer ghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241044018-Nowly Bazar-Hanorgari Ghat via Madhur Dokan Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241044019-Rajghat R&H-Bakardanga via Gazipur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241044023-Bashuari more(UZR)-Suvarara River Ghat via Dighirpar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241044024-Ichamoti UZR-Peruli Gc Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241044026-Arpara UZR(Prembag More)-Zialtala Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241044035-Magura Gabukhali Collage-Joyanta via Dholergati school Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241044036-Chengutia Baruari Mondir-Beel Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 241044043-Nowly High school UZR-Beelkul Totarmatha via Nowly Mollik bari Jame-Mosque & Biswas Bari Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241044050-Barandi Fakirhat Bazar-Takerghat road via WAPDA Office. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241045086-Ranaghati Khayghat - Bhugilhat Mor Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241045230-Nowly Biswas para-Mosque road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 241045516-Improvement of Nowly Momin Biswas house - Mir Bari Tematha Road From Ch. 00-412m | KDRIDP/Jess/W-104/2017-18 | 0.412 | 0 | 0 | 27.728 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241045613-Improvement of Nowly Golamar Bari more-Tatultala Ghat Road From Ch. 00-500m [Salvage Cost Tk. 1,21,853.00] |  | 0.5 | 0 | 0 | 34.54 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
25 | 241045406-Improvement of Bagutia Palpara Puja mondir- Mojibor house Road From Ch. 00-634m. [Salvage Cost Tk. 50,471.00] | KDRIDP/Jess/W-105/2017-18 | 0.634 | 0 | 0 | 43.15 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241045188-Improvement of Baghutia Bridge-Baghutia Dhakinpara Mosque Road From Ch. 00-1550m. |  | 1.55 | 0 | 0 | 106.627 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
26 | 241044022 Improvement of Abhoynagar Puraton Kheya Ghat-Shibnagor UZR(N/H/O Kalachand) via Bogratala Mosque Road From Ch.584-2560 m. [salvage Cost Tk. 3,17,894.00] | KDRIDP/Jess/W-61/2017-18 | 1.976 | 0 | 0 | 130.88 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 28/02/2018 [3Rd Called]
27 | 241044062 Improvement of Horishpur Reg.Primary school-Magura G.C. via Ramsara chowmatha, shishutala Road From Ch. 2435-4130m. [salvage Cost Tk. 8,78,194.00] | KDRIDP/Jess/W-62/2017-18 | 1.695 | 0 | 0 | 117.66 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 28/02/2018 [3Rd Called]
28 | 241044069-Improvement of Gopinathpur Village-Dokhanpara Abdul Gofur khan shope-Batiul Nure Jame Mosque Road From Ch. 00-775m. [Salvage Cost Tk. 3,85,651.00] | KDRIDP/Jess/W-63/2017-18 | 0.775 | 0 | 0 | 53.47 | 2018-02-05 | B.M Rafiqul Islam, Dariyapur, Narial Sadar, Narial | 2018-03-12 | 57.49 | 0% | 2018-12-13 | 0 | 0 | 0 | 0% | 0
29 | 241044066 Improvement of Bhabadha Sluice gate-Zamira UZR. Road From Ch.00-3160m. [Salvage Cost Tk. 71,67,422.00] | KDRIDP/Jess/W-64/2017-18 | 3.16 | 0 | 0 | 208.65 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [2Nd Called]
30 | 241045137 Improvement of Dattagati WAPDA Road near the house of Ashu babu- Dattagati East para Culvert Road From Ch. 00-290m. [Salvage Cost Tk. 6,51,733.00] | KDRIDP/Jess/W-102/2017-18 | 0.29 | 0 | 0 | 19.265 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
| 241044039 Improvement of Takerghat-Kapalia bazar via Bhabadha Sluice gate, College & kalishakul Bazer Road From Ch. 3300-5300m |  | 2 | 0 | 0 | 152.43 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
Improvement of Village Road by HBB
31 | 241044060-Dhulgram Club-Siddipasha U.P.Office(Nowly Bazar) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
32 | 241042005-Nowapara Upazila H/Q- Amtala GC via Vatpara Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 241042009-Alipur RHD-Sundali GC via Rajapur more Ramsaradham, Arpara Clinic more, Harishpur RNGPS Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 241043001-Noapara HQ(BTMC Ghat)-Borni Bazar via Sreedharpur UP Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 241043007-Periodic Maintenance of Sundali U.P.Office-Moshihati Bazar Road From Ch.00-3050m | KDRIDP/Jess/M-07/2017-18 | 3.05 | 0 | 0 | 68.045 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 25/06/2018
36 | 241043009-Siddipasha UP Office(Nowly Bazer)-Phultala G.C. via Dhulgram kheya Ghat. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 241044005-Periodic Maintenance of Taltala Bazar-Dumortala road via Sirajkati,Chalishia Rishipara Chourasta More Road From Ch.00-5310m | KDRIDP/Jess/M-08/2017-18 | 5.31 | 0 | 0 | 162.81 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 241044017-Hidia Madrasha UZR- Kharoria Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 241044039-Takerhat-Kapalia Bazarvia Bhabadha Sluicegate Collage & Kalishakul Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 241044063-Rajapur More- Magura Madrasha more UZR via Sishutala Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 241044066-Bhabadha Sluicegate -Zamira UZR Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
42 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 27.112 | 0 | 0 | 1520.715 |  |  |  | 417.79 | 2.381% |  | 150.285 | 150.285 | 0 | 35.97%

## Bagherpara
Bagherpara
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241092006-Simakhali RHD-Narikelbaria GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241092011-Dhalgram GC- Maijpara UP to Kalukhali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 241092014-Improvement of Narikelbaria GC Bunagati GC (Shersha Sarak) Road. From Ch: 700-3270m. [salvage Cost Tk.20,890.00] | KDRIDP/Jess/W-96/2017-18 | 2.57 | 0 | 0 | 199.065 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 21/05/2018
4 | 241092018 Improvement of Narikelbaria GC - Monohorpur Bazar RHD at Joynagor More via Raypur UP (Bagherpara Part) Road. From Ch: 406-4144m,5400-5987m & 6372-7057m. [salvage Cost Tk.95,88,834.00] | KDRIDP/Jess/W-67/2017-18 | 5.01 | 0 | 0 | 396.55 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 241093003-Bandabila UP- Puinerhat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241093008-Improvement of Joharpur up office-Betalpara Bazar Road. From Ch: 1900-3250m. [salvage Cost Tk.5,096.00] | KDRIDP/Jess/W-97/2017-18 | 1.35 | 0 | 0 | 99.547 | 2018-05-21 | M/S Monir Traders Natun Khayertala, Jessore | 0 | 104.5 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Date 05/06/2018
| 241093010-Improvement of Raipur UP Office-Vater bazar Road. From Ch: 3611-3997m & 4689-5620m. [salvage Cost Tk.24,19,116.00] |  | 1.317 | 0 | 0 | 87.845 |  |  |  | 92.22 |  |  | 0 | 0 | 0 | 0%
7 | 241093013-Vangura RHD.-Dhalgram UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241093014-Vangura RHD.-Basundia UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241093017-Simakhali UP- Johurpur UP via Betalpara Bazar, Premchara. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 241093018-Dhalgram UP- Garerhat Bazar via Antaikhola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
11 | 241094005-Indra- Azmeherpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241094010-Improvement of Narikelbaria (Salikha Upazila) – Paschima Das Para More Road. From Ch: 500-1300m | KDRIDP/Jess/W-98/2017-18 | 0.8 | 0 | 0 | 49.66 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 21/05/2018
13 | 241094018-Satiantala bazar to RHD at Dadpur bazar via Sayed Mahmudpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241094020-Khanpur Bazer-Indra Bazer (Khanpur Freedom Fiter Gopal House-Rahaman House) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241094028-Pashima H/O Sariful- Dari Agra via Napte more | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241094034-Kadamtola- Bandabila hat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241095145-Punihar Battala- Sreerampur High School Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241095284-Improvement of Kundupara Senbari- Tapan Master house[Inventory Name ;-Narikelbaria Senbari - Narikelbaria North Para via Narikelpara kundupara Mandir] Road. From Ch: 00-710m. | KDRIDP/Jess/W-86/2017-18 | 0.71 | 0 | 0 | 63.405 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 13/03/2018
19 | 241095127 Improvement of Madhyapara Mosque RHD (jessore-Narial)-Joka [Inventory Name ;-RHD Rashid Karimpur H/O Omar Molla Khalshi] Road. From Ch: 00-1696m. [salvage Cost Tk.25,76,452.00] | KDRIDP/Jess/W-93/2017-18 | 1.696 | 0 | 0 | 108.45 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 10/04/2018
20 | 241095285-Khetrapara School -Hablapara Shawkat's House Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
21 | 241095221-Ramkrishnapur Bazar-Silumpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
22 | 241092003-Jessore Narail RHD-Dhalgram more- Narikelbaria via Dhalgram Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241092011-Periodic Maintenance of Dhalgram GC.-Maijpara Up to Kalukhali Road From Ch.00-2265m | KDRIDP/Jess/M-26/2017-18 | 2.265 | 0 | 0 | 61.248 | 2018-05-11 | M/S Biswas Construction, 134 Dhaka Road, Puraton Kashba, Jessore | 0 | 64.206 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Dare 27/05/2018
Tree Plantation
24 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 15.718 | 0 | 0 | 1065.77 |  |  |  | 260.926 | 0% |  | 0 | 0 | 0 | 0%

## Summary
JESSORE
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 8 | 5 | 22.519 | 0 | 0 | 912.6 | 139.79 | 20% | 15.32%
Union Road by BC | 26 | 20 | 60.049 | 0 | 0 | 2863.73 | 924.376 | 55.75% | 32.28%
Village Road by BC | 66 | 45 | 74.096 | 0 | 0 | 3040.202 | 955.972 | 38.15% | 31.44%
Village Road by HBB | 1 | 1 | 2.075 | 0 | 0 | 75.315 | 61.99 | 85% | 82.32%
Bridge on Upazila Road | 1 | 1 | 0 | 44 | 0 | 221.27 | 124.82 | 60% | 56.41%
Bridge on Union Road/Village Road | [9 empty] | N/A
Maintenance | 26 | 18 | 76.584 | 0 | 0 | 1896.272 | 193.045 | 17% | 10.18%
GC-Hat | 1 | 1 | 0 | 0 | 1 | 17.559 | 0.2 | 20% | 0%
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 129 | 91 | 235.323 | 44 | 1 | 9026.948 | 2400.193 | 36.99% | 26.59%