## Narail
NARAIL
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Narail Sadar
1 | 265762006-Singa Solepur-Khororia Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Improvement of Union Road by BC
Narail Sadar
1 | 265763003-Nakosi - Sarkeldanga Rd. | [13 empty] | 0 | #DIV/0!
2 | 265763005-Shahabad UP-Hobokhali U.P Rd. | [13 empty] | 0 | #DIV/0!
3 | 265763012-Improvement of Shimakhali RHD – via Kurulia Village- Chandibarpur UP Road (Ch-00-1359m & 8150m-10800m) by BC | KDRIDP/Narail/W-13/2016-17 | 4.009 | 0 | 0 | 227.69 | 2017-07-12 | AKM Akramuzzaman Bhanga, Faridpur | 2017-10-02 | 208.88 | 25% | 2018-12-31 |  | 35.39 | -35.39 | 16.94% | 1359m WBM Ongoing & other part ISG Completed
4 | 265763013-Improvement of Maizpara UP- Gorerhat Road (Narail-S part) from Ch. 2200m - 3450m | KDRIDP/Narail/W-18/2017-18 | 1.25 | 0 | 0 | 76.9 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 77.58 | 100% | 2018-11-14 | 77.534 | 77.534 | 0 | 99.94% | Final
Lohagara
5 | 265523005-Improvement of Manikgonj Bazar – Lahuria UP Road (Ch-5865m-7725m) by BC | KDRIDP/Narail/W-01/2016-17 | 1.86 | 0 | 0 | 104.97 | 2017-07-03 | M/S Shimul Enterprise, Madhukhali, Faridpur | 2017-08-22 | 98.607 | 70% | 2018-05-31 |  | 57.48 | -57.48 | 58.29% | WBM Completed
6 | 265523006-Improvement of Naldi UP-Lahuria Road Ch. 2100-7020m. Salvage Cost Tk. 142650.00 | KDRIDP/Narail/W-14/2017-18 | 4.92 | 0 | 0 | 293.31 | 2017-09-26 | M/S Lipu Enterprise, Kanaipur, Faridpur | 2017-11-13 | 274.94 | 40% | 2018-06-24 |  | 81.47 | -81.47 | 29.63% | AS Completed
Kalia
7 | 265283002-Kalabaria UP office-Beeldhuria Hat Rd. | [13 empty] | 0 | #DIV/0!
8 | 265283005-Babra R&H-Suktogram Bazer Rd.(Proposed name Babra UP Office- Suktogram Bazer) | [13 empty] | 0 | #DIV/0!
9 | 265283006-Babra UP Office via Chanchuri UP Office - Dadontala RHD Road. | [13 empty] | 0 | #DIV/0!
10 | 265283007-Khasial UP office-Patnabazar (Talbaria) | [13 empty] | 0 | #DIV/0!
11 | 265283008-Improvement of Chapail UZR – Bagudanga Bazar Road (Ch-700m-1061m) by BC | KDRIDP/Narail/W-07/2016-17 | 0.361 | 0 | 0 | 22.34 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 20.16 | 70% | 2018-05-15 |  | 11.5 | -11.5 | 57.04% | WBM Completed
Total |  |  | 12.4 | 0 | 0 | 725.21 |  |  |  | 680.167 | 61% |  | 77.534 | 263.374 | -185.84 | 38.72%
Improvement of Village Road by BC
Narail Sadar
1 | 265764022-Improvement of Mathabhanga – Nondahkol (House of Bejoy Sarker) Road (Ch-1000m-2100m) by BC | KDRIDP/Narail/W-03/2016-17 | 1.1 | 0 | 0 | 69.13 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 66.366 | 0% | 2018-05-31 |  |  | 0 | 0% | Work Canceled
2 | 265764026- Improvement of Baliadanga – Ramchandrapur Road (Ch-1206m-3045m) by BC | KDRIDP/Narail/W-04/2016-17 | 1.839 | 0 | 0 | 104.92 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 100.726 | 0% | 2018-05-31 |  |  | 0 | 0% | Work Canceled
3 | 265764049- Rukhali Bazar (up office)-Akdia char FRB Road | [13 empty] | 0 | #DIV/0!
4 | 265764057- Improvement of Chanchra RHD – Benahati Road (Ch-2456m-3494m) by BC | KDRIDP/Narail/W-05/2016-17 | 1.038 | 0 | 0 | 63.64 | 2017-09-26 | M/S Islam Traders Jessore | 2017-11-10 | 63.26 | 40% | 2018-05-15 |  | 13.18 | -13.18 | 20.83% | AS Completed
5 | 265764059- Garuchira - Alukdia UP office Road | [13 empty] | 0 | #DIV/0!
6 | 265764061-Birgram R&H-Mulia UP office Rd. | [13 empty] | 0 | #DIV/0!
7 | 265764066-Improvement of Maizpara - Dhalgram Road from Ch 00m - 161m & Ch-1440m - 2440m | KDRIDP/Narail/W-21/2017-18 | 1.161 | 0 | 0 | 82.15 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 76.987 | 100% | 2018-11-21 | 76.9 | 76.9 | 0 | 99.89% | Final
8 | 265764071-Chakoi chowmatha-Bichali FRB Rd | [13 empty] | 0 | #DIV/0!
9 | 265764073- Improvement of Doulatpur-via Hosinpur Grave Yeard – Boramara river side Road (Ch-1600m-2720m) by BC | KDRIDP/Narail/W-06/2016-17 | 1.12 | 0 | 0 | 65.44 | 2017-07-03 | M/S MA Enterprise Bhanga, Faridpur | 2017-08-16 | 63.48 | 25% | 2018-05-31 |  | 7.46 | -7.46 | 11.75% | AS Ongoing
10 | 265765006-Peroli River side Road | [13 empty] | 0 | #DIV/0!
11 | 265765009-Improvement of Malidanga Village Road from Ch 00m- 825m | KDRIDP/Narail/W-20/2017-18 | 0.825 | 0 | 0 | 54.31 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 54.28 | 40% | 2018-05-31 |  | 18.33 | -18.33 | 33.77% | AS Completed
12 | 265764002-Improvement of Jangelgram - Chandiborpur Road from Ch. 802m - 4359m | KDRIDP/Narail/W-25/2017-18 | 3.557 | 0 | 0 | 206.66 | 2018-02-28 | M/S Eden Prise, Mohishkhola, Narail | 2018-04-04 | 215.21 | 25% | 2019-04-10 |  | 41.47 | -41.47 | 19.27% | ISG Completed, AS Materials Mobilized
13 | 265765310-Improvement of Sonkorpur GPS west side - Pazarkhali Road from Ch. 00m - 630m | KDRIDP/Narail/W-26/2017-18 | 0.63 | 0 | 0 | 38.2 | 2018-01-10 | M/S kailash Construction | 2018-02-22 | 38.96 | 10% | 2018-09-02 |  |  | 0 | 0% | Materials Mobilizing
14 | 265765152-Improvement of Mathabhanga - Hogladanga Road from Ch 00m-1150m. | KDRIDP/Narail/W-22/2017-18 | 1.15 | 0 | 0 | 72.23 | 2017-10-02 | BM. Rafiqul Islam, Rupgonj Bazar, Narail | 2017-11-12 | 72.12 | 70% | 2018-11-19 |  | 44.32 | -44.32 | 61.45% | WBM Completed
15 | 265765241-Improvement of Soraspur Pucca Road - Narayanpur Shahid Freedom Fighter Shofiuddin Khan House Road from Ch. 00m -1982m | KDRIDP/Narail/W-27/2017-18 | 1.982 | 0 | 0 | 123.898 | 2018-02-04 | M/S Moni Construction | 2018-02-26 | 133.892 | 12% | 2019-03-12 |  |  | 0 | 0% | ISG Ongoing
16 | 265765322-Chorbilla Govt.Primary School-Dokkin-Kali bari khayghat road. | [13 empty] | 0 | #DIV/0!
17 | 265765113-Hobokhali VILLAGE ROAD.(Hobokhali H/O Nayeb Master-Narial Magura link road. | [13 empty] | 0 | #DIV/0!
18 | 265765086- Improvement of Moyenkhola - Charbila Road from Ch. 00m- 1450m | KDRIDP/Narail/W-19/2017-18 | 1.45 | 0 | 0 | 91.3 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 86.02 | 100% | 2018-11-21 | 85.94 | 85.94 | 0 | 99.91% | Final
19 | 265765072- Improvement of Ghorakhali sholua Road Ch. 482-1560m | KDRIDP/Narail/W-16/2017-18 | 1.078 | 0 | 0 | 62.91 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 58.97 | 20% | 2018-06-17 |  |  | 0 | 0% | ISG Completed
20 | 265765259-Hosenpur Rostum Sikder Bari-Kayem Biswas Bari road. | [13 empty] | 0 | #DIV/0!
Lohagara
21 | 265524001-Lahuria Bazar-Chimanarchar Rd. | [13 empty] | 0 | #DIV/0!
22 | 265524009 - Lohagara Bazar -Char Korfa Rd | [13 empty] | 0 | #DIV/0!
23 | 265524016-Raghunathpur-Taltala Satrahazari bazar Rd. | [13 empty] | 0 | #DIV/0!
24 | 265524005-Lohagara Bazar - Char Korfa Road | [13 empty] | 0 | #DIV/0!
25 | 265524026-Improvement of Sattrahazari Bazar – Brammondanga Bazar Road (Ch-3500m-5930m)by BC | KDRIDP/Narail/W-02/2016-17 | 2.43 | 0 | 0 | 131.8 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 123.89 | 10% | 2018-05-31 |  |  | 0 | 0% | Box-Cutting Conpleted
26 | 265524055-Radhanagar Bazar bridge - Kumardanga bazar Road | [13 empty] | 0 | #DIV/0!
27 | 265525005-Improvement of Bhadradanga - Makrail Road from Ch.1680m - 3000m | KDRIDP/Narail/W-28/2017-18 | 1.32 | 0 | 0 | 78.42 | 2018-02-04 | M/S Fakir Enterprise | 2018-02-14 | 85.47 | 45% |  |  | 31.83 | -31.83 | 37.24% | WBM Ongoing
28 | 265524062-Improvement of Dinanathpara – Gobindapur Road from Ch. 610m - 1370m. | KDRIDP/Narail/W-29/2017-18 | 0.76 | 0 | 0 | 50.12 | 2018-02-28 | M/S Rupali Construction, Kalibari Road, Barisal | 2018-04-08 | 51.629 | 0% | 2018-09-16 |  |  | 0 | 0%
29 | 265525222-Makrail Mujam Molla H/O - Mukter Shikder house Road | [13 empty] | 0 | #DIV/0!
30 | 265525508-Improvement of Mait Kumra C&B road H/O Akkas Master-H/O Lutfor Rahman via Nazrul Ahmed House Road Ch. 00-530m. Salvage Cost Tk. 617629.00 | KDRIDP/Narail/W-15/2017-18 | 0.53 | 0 | 0 | 31.25 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 28.667 | 40% | 2018-02-28 |  | 9.28 | -9.28 | 32.37% | AS Completed
31 | 265525226-Kamil Madrasha road. | [13 empty] | 0 | #DIV/0!
32 | 265524042-Improvement of Jalalshe Maddrasha - Char Bramman Danga Road from Ch. 00m - 1740m | KDRIDP/Narail/W-24/2017-18 | 1.74 | 0 | 0 | 104.77 | 2017-10-09 | M/S Fakir Enterprise, Lohagara, Narail | 2017-11-27 | 103.76 | 55% | 2018-11-30 |  | 50.38 | -50.38 | 48.55% | WBM Ongoing
Kalia
33 | 265284002-Baddyabati hat-Mirzapur Rd | [13 empty] | 0 | #DIV/0!
34 | 265284008-Raghunathpur Sumarkhola WDB Embk. | [13 empty] | 0 | #DIV/0!
35 | 265284015-Jogania-sachiadha via Kachuadanga road. | [13 empty] | 0 | #DIV/0!
36 | 265284036-Hamidpur (Silimpur)-Chalitatala Rd. | [13 empty] | 0 | #DIV/0!
37 | 265284037-Peroli Hat-Kharoria Mollabari Bazer Via Kharoria Abashan Rd. | [13 empty] | 0 | #DIV/0!
38 | 265285001-Harishpur-Hadayetpur | [13 empty] | 0 | #DIV/0!
39 | 265285012-Improvement of Kathadura – Chanderchar WDB Road (Ch-700m-1815m) by BC | KDRIDP/Narail/W-08/2016-17 | 1.115 | 0 | 0 | 60.43 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-20 | 57.11 | 100% | 2018-05-15 | 55.888 | 55.89 | -0.002 | 97.86% | Final
40 | 265285057-Improvement of Kamshia Village Road (Ch-00m-1250m) by BC | KDRIDP/Narail/W-11/2016-17 | 1.25 | 0 | 0 | 70.76 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 63.72 | 40% | 2018-05-15 |  | 19.19 | -19.19 | 30.12% | AS Completed
41 | 265285016-Improvement of Putimary – Panipara Road (Ch-700m-1116m) by BC | KDRIDP/Narail/W-09/2016-17 | 0.416 | 0 | 0 | 25.33 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 22.86 | 40% | 2018-05-15 |  | 6.8 | -6.8 | 29.75% | AS Completed
42 | 265285044-Improvement of Khashial – Uttar Khashial Road (Ch-500m-1150m) by BC | KDRIDP/Narail/W-10/2016-17 | 0.65 | 0 | 0 | 35.89 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-24 | 32.39 | 100% | 2018-05-15 | 32.35 | 32.35 | 0 | 99.88% | Final
43 | 265285072-Dumuria-Dudkuria Rd. | [13 empty] | 0 | #DIV/0!
44 | 265285137-Improvement of Patna Bridge – Kalinagar (Kalinagar UZR – Naldanga Loboner Kheyaghat) Road (Ch-1620m-3200m) by BC | KDRIDP/Narail/W-12/2016-17 | 1.58 | 0 | 0 | 89.63 | 2017-07-05 | M/S Ruma Enterprise Kalia, Narail | 2017-08-16 | 88.63 | 100% | 2018-03-24 | 87.74 | 87.742 | -0.002 | 99% | Final
45 | 265285149-Improvement of Baoisona Boroghat - Kanaypur Road (Ch-00m-1000m) by BC. | KDRIDP/Narail/W-17/2017-18 | 1 | 0 | 0 | 63.197 | 2017-10-02 | M/S Ruma Enterprise Kalia, Narail | 2017-11-22 | 57.2 | 55% | 2018-09-28 |  | 24.4 | -24.4 | 42.66% | WBM Ongoing
Total |  |  | 29.721 | 0 | 0 | 1776.385 |  |  |  | 1745.597 | 44.65% |  | 338.818 | 605.462 | -266.644 | 34.69%
Improvement of Village Road by HBB
Narail Sadar
1 | 265764045-Improvement of Burikhali RHD - Charshalikha Road by HBB from Ch 1472m - 2137m | KDRIDP/Narail/W-23/2017-18 | 0.665 | 0 | 0 | 22.417 | 2017-10-02 | M/S Eden Prise Mohiskhola Narail | 2017-10-30 | 21.3 | 100% | 2018-02-28 | 21.3 | 21.3 | 0 | 100% | Final
Lohagara
2 | 265524030-Kalagachi bazar-Manikgonj bazar Rd. | [13 empty] | 0 | #DIV/0!
Kalia
3 | 265284018-Kalabaria-Patna Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0.665 | 0 | 0 | 22.417 |  |  |  | 21.3 | 100% |  | 21.3 | 21.3 | 0 | 100%
Construction of Bridge on Upazila Road (7.30m width)
Narail Sadar
1 | 265762007- Construction of 30m RCC Girder Bridge on Gabtala R&H - Maizpara GC Road at Ch-2000m | KDRIDP/Narail/B-01/2017-18 | 0 | 30 | 0 | 199.79 |  |  |  |  | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 30 | 0 | 199.79 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Narail Sadar
1 | 265763007-Construction of 30m RCC Girder Bridge on Singasolpur - Chakoi via Rukhali Road at Ch-3405m | KDRIDP/Narail/B-02/2017-18 | 0 | 30 | 0 | 224.488 | [8 empty] | 0 | #DIV/0! | Estimate Checking
Kalia
2 | 265285137-Kalinagar UZR - Naldanga Loboner Kheya Ghat Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 30 | 0 | 224.488 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Maintenance
Narail Sadar
1 | 265763003-Nakosi-Sarakeldanga Rd. | [13 empty] | 0 | #DIV/0!
2 | 265763008-Kolora (Akdia)UP Office-Shaikhati GC Rd. | [13 empty] | 0 | #DIV/0!
3 | 265763012-Shimakhali RHD-via Kurulia village-Chandibarpur UP Rd | [13 empty] | 0 | #DIV/0!
4 | 265764052-Periodic Maintenance of Mirapara Bazar - Raghunathpur road Ch. 00m -1665m | KDRIDP/Narail/M-01/2017-18 | 1.665 | 0 | 0 | 41.11 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 43.71 | 100% | 2018-08-30 | 43.707 | 43.71 | -0.003 | 100% | Final
5 | 265764053-Periodic Maintenance of Chowgacha RHD- Hogladanga Road Ch. 5800m - 7700m | KDRIDP/Narail/M-05/2017-18 | 1.9 | 0 | 0 | 46.457 | 2018-04-08 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 48.77 | 100% | 2018-12-31 | 48.75 | 48.75 | 0 | 99.96% | Final
6 | 265764054-Durbaguri R&H Mulia UP Office Rd | [13 empty] | 0 | #DIV/0!
7 | 265764061-Birgram R&H -Mulia UP Office Rd | [13 empty] | 0 | #DIV/0!
8 | 265764064- Malidanga (GCCR)-Durgapur RHD | [13 empty] | 0 | #DIV/0!
9 | 265765163-Periodic Maintenance of Solpur - Roghunathpur road Ch. 00m -1410m | KDRIDP/Narail/M-02/2017-18 | 1.41 | 0 | 0 | 36.62 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 39.78 | 100% | 2018-08-30 | 39.77 | 39.77 | 0 | 99.97% | Final
Lohagara
10 | 265523006-Periodic Maintenance of Naldi UP- Lahuria UP Road Ch. 00m - 1973m. | KDRIDP/Narail/M-04/2017-18 | 1.973 | 0 | 0 | 58.99 | 2018-04-04 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 61.94 | 0% | 2019-01-11 |  |  | 0 | 0%
11 | 265524001-Periodic Maintenance of Lahuria Bazar - Chimanarchar road Ch. 00m - 2350m | KDRIDP/Narail/M-03/2017-18 | 2.35 | 0 | 0 | 59.53 | 2018-02-28 | BM Rafiqul Islam Rupgonj, Narail | 2018-04-11 | 65.237 | 5% | 2018-09-17 |  |  | 0 | 0% | Partly Hard Bed Preparation Completed
12 | 265524017-Rampur RHD Singa-Baka -Jikra Rd. | [13 empty] | 0 | #DIV/0!
13 | 265524035-Chachoi CD-Kalna R&H Rd. | [13 empty] | 0 | #DIV/0!
14 | 265524046-Char Daulatpur-Kheyaghat Rd. | [13 empty] | 0 | #DIV/0!
Kalia
15 | 265284015-Jogania -Sachiadha via Kachuadanga Rd. | [13 empty] | 0 | #DIV/0!
16 | 265285027-Dumuria -Dudkuria Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 9.298 | 0 | 0 | 242.707 |  |  |  | 259.437 | 61% |  | 132.227 | 132.23 | -0.003 | 50.97%
GC-Hat
Narail Sadar
1 | Construction of Gobra Growth Centre | KDRIDP/Narail/GC-16/2017-18 | 0 | 0 | 1 | 18.65 | 2018-02-04 | M/S Liton Traders, Jhenaidah | 2018-03-08 | 16.789 | 75% | 2018-06-16 |  | 10 | -10 | 59.56%
Total |  |  | 0 | 0 | 1 | 18.65 |  |  |  | 16.789 | 75% |  | 0 | 10 | -10 | 59.56%
Tree Plantation
Narail Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Lohagara
2 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Kalia
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 52.084 | 60 | 1 | 3209.647 |  |  |  | 2723.29 | 37.96% |  | 569.879 | 1032.366 | -462.487 | 37.91%
|  |  | 52.084 | 60 | 1 | 3209.647 |  |  |  | 2723.29 | 20.43% |  | 569.879 | 1032.366 | -462.487 | 37.91%

## Narail Sadar
Narail Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 265762006-Singa Solepur-Khororia Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
2 | 265763003-Nakosi - Sarkeldanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 265763005-Shahabad UP-Hobokhali U.P Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 265763012-Improvement of Shimakhali RHD – via Kurulia Village- Chandibarpur UP Road (Ch-00-1359m & 8150m-10800m) by BC | KDRIDP/Narail/W-13/2016-17 | 4.009 | 0 | 0 | 227.69 | 2017-07-12 | AKM Akramuzzaman Bhanga, Faridpur | 2017-10-02 | 208.88 | 25% | 2018-12-31 | 0 | 35.39 | -35.39 | 16.94% | 1359m WBM Ongoing & other part ISG Completed
5 | 265763013-Improvement of Maizpara UP- Gorerhat Road (Narail-S part) from Ch. 2200m - 3450m | KDRIDP/Narail/W-18/2017-18 | 1.25 | 0 | 0 | 76.9 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 77.58 | 100% | 2018-11-14 | 77.534 | 77.534 | 0 | 99.94% | Final
Improvement of Village Road by BC
6 | 265764022-Improvement of Mathabhanga – Nondahkol (House of Bejoy Sarker) Road (Ch-1000m-2100m) by BC | KDRIDP/Narail/W-03/2016-17 | 1.1 | 0 | 0 | 69.13 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 66.366 | 0% | 2018-05-31 | 0 | 0 | 0 | 0% | Work Canceled
7 | 265764026- Improvement of Baliadanga – Ramchandrapur Road (Ch-1206m-3045m) by BC | KDRIDP/Narail/W-04/2016-17 | 1.839 | 0 | 0 | 104.92 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 100.726 | 0% | 2018-05-31 | 0 | 0 | 0 | 0% | Work Canceled
8 | 265764049- Rukhali Bazar (up office)-Akdia char FRB Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 265764057- Improvement of Chanchra RHD – Benahati Road (Ch-2456m-3494m) by BC | KDRIDP/Narail/W-05/2016-17 | 1.038 | 0 | 0 | 63.64 | 2017-09-26 | M/S Islam Traders Jessore | 2017-11-10 | 63.26 | 40% | 2018-05-15 | 0 | 13.18 | -13.18 | 20.83% | AS Completed
10 | 265764059- Garuchira - Alukdia UP office Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 265764061-Birgram R&H-Mulia UP office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 265764066-Improvement of Maizpara - Dhalgram Road from Ch 00m - 161m & Ch-1440m - 2440m | KDRIDP/Narail/W-21/2017-18 | 1.161 | 0 | 0 | 82.15 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 76.987 | 100% | 2018-11-21 | 76.9 | 76.9 | 0 | 99.89% | Final
13 | 265764071-Chakoi chowmatha-Bichali FRB Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 265764073- Improvement of Doulatpur-via Hosinpur Grave Yeard – Boramara river side Road (Ch-1600m-2720m) by BC | KDRIDP/Narail/W-06/2016-17 | 1.12 | 0 | 0 | 65.44 | 2017-07-03 | M/S MA Enterprise Bhanga, Faridpur | 2017-08-16 | 63.48 | 25% | 2018-05-31 | 0 | 7.46 | -7.46 | 11.75% | AS Ongoing
15 | 265765006-Peroli River side Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 265765009-Improvement of Malidanga Village Road from Ch 00m- 825m | KDRIDP/Narail/W-20/2017-18 | 0.825 | 0 | 0 | 54.31 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 54.28 | 40% | 2018-05-31 | 0 | 18.33 | -18.33 | 33.77% | AS Completed
17 | 265764002-Improvement of Jangelgram - Chandiborpur Road from Ch. 802m - 4359m | KDRIDP/Narail/W-25/2017-18 | 3.557 | 0 | 0 | 206.66 | 2018-02-28 | M/S Eden Prise, Mohishkhola, Narail | 2018-04-04 | 215.21 | 25% | 2019-04-10 | 0 | 41.47 | -41.47 | 19.27% | ISG Completed, AS Materials Mobilized
18 | 265765310-Improvement of Sonkorpur GPS west side - Pazarkhali Road from Ch. 00m - 630m | KDRIDP/Narail/W-26/2017-18 | 0.63 | 0 | 0 | 38.2 | 2018-01-10 | M/S kailash Construction | 2018-02-22 | 38.96 | 10% | 2018-09-02 | 0 | 0 | 0 | 0% | Materials Mobilizing
19 | 265765152-Improvement of Mathabhanga - Hogladanga Road from Ch 00m-1150m. | KDRIDP/Narail/W-22/2017-18 | 1.15 | 0 | 0 | 72.23 | 2017-10-02 | BM. Rafiqul Islam, Rupgonj Bazar, Narail | 2017-11-12 | 72.12 | 70% | 2018-11-19 | 0 | 44.32 | -44.32 | 61.45% | WBM Completed
20 | 265765241-Improvement of Soraspur Pucca Road - Narayanpur Shahid Freedom Fighter Shofiuddin Khan House Road from Ch. 00m -1982m | KDRIDP/Narail/W-27/2017-18 | 1.982 | 0 | 0 | 123.898 | 2018-02-04 | M/S Moni Construction | 2018-02-26 | 133.892 | 12% | 2019-03-12 | 0 | 0 | 0 | 0% | ISG Ongoing
21 | 265765322-Chorbilla Govt.Primary School-Dokkin-Kali bari khayghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 265765113-Hobokhali VILLAGE ROAD.(Hobokhali H/O Nayeb Master-Narial Magura link road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 265765086- Improvement of Moyenkhola - Charbila Road from Ch. 00m- 1450m | KDRIDP/Narail/W-19/2017-18 | 1.45 | 0 | 0 | 91.3 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 86.02 | 100% | 2018-11-21 | 85.94 | 85.94 | 0 | 99.91% | Final
24 | 265765072- Improvement of Ghorakhali sholua Road Ch. 482-1560m | KDRIDP/Narail/W-16/2017-18 | 1.078 | 0 | 0 | 62.91 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 58.97 | 20% | 2018-06-17 | 0 | 0 | 0 | 0% | ISG Completed
25 | 265765259-Hosenpur Rostum Sikder Bari-Kayem Biswas Bari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
26 | 265764045-Improvement of Burikhali RHD - Charshalikha Road by HBB from Ch 1472m - 2137m | KDRIDP/Narail/W-23/2017-18 | 0.665 | 0 | 0 | 22.417 | 2017-10-02 | M/S Eden Prise Mohiskhola Narail | 2017-10-30 | 21.3 | 100% | 2018-02-28 | 21.3 | 21.3 | 0 | 100% | Final
Construction of Bridge on Upazila Road (7.30m width)
27 | 265762007- Construction of 30m RCC Girder Bridge on Gabtala R&H - Maizpara GC Road at Ch-2000m | KDRIDP/Narail/B-01/2017-18 | 0 | 30 | 0 | 199.79 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
28 | 265763007-Construction of 30m RCC Girder Bridge on Singasolpur - Chakoi via Rukhali Road at Ch-3405m | KDRIDP/Narail/B-02/2017-18 | 0 | 30 | 0 | 224.488 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Estimate Checking
Maintenance
29 | 265763003-Nakosi-Sarakeldanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 265763008-Kolora (Akdia)UP Office-Shaikhati GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 265763012-Shimakhali RHD-via Kurulia village-Chandibarpur UP Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 265764052-Periodic Maintenance of Mirapara Bazar - Raghunathpur road Ch. 00m -1665m | KDRIDP/Narail/M-01/2017-18 | 1.665 | 0 | 0 | 41.11 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 43.71 | 100% | 2018-08-30 | 43.707 | 43.71 | -0.003 | 100% | Final
33 | 265764053-Periodic Maintenance of Chowgacha RHD- Hogladanga Road Ch. 5800m - 7700m | KDRIDP/Narail/M-05/2017-18 | 1.9 | 0 | 0 | 46.457 | 2018-04-08 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 48.77 | 100% | 2018-12-31 | 48.75 | 48.75 | 0 | 99.96% | Final
34 | 265764054-Durbaguri R&H Mulia UP Office Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 265764061-Birgram R&H -Mulia UP Office Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 265764064- Malidanga (GCCR)-Durgapur RHD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 265765163-Periodic Maintenance of Solpur - Roghunathpur road Ch. 00m -1410m | KDRIDP/Narail/M-02/2017-18 | 1.41 | 0 | 0 | 36.62 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 39.78 | 100% | 2018-08-30 | 39.77 | 39.77 | 0 | 99.97% | Final
GC-Hat
38 | Construction of Gobra Growth Centre | KDRIDP/Narail/GC-16/2017-18 | 0 | 0 | 1 | 18.65 | 2018-02-04 | M/S Liton Traders, Jhenaidah | 2018-03-08 | 16.789 | 75% | 2018-06-16 | 0 | 10 | -10 | 59.56% | 0
Tree Plantation
39 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 27.829 | 60 | 1 | 1928.91 |  |  |  | 1487.08 | 26.72% |  | 393.901 | 564.054 | -170.153 | 37.93%

## Lohagara
Lohagara
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 265523005-Improvement of Manikgonj Bazar – Lahuria UP Road (Ch-5865m-7725m) by BC | KDRIDP/Narail/W-01/2016-17 | 1.86 | 0 | 0 | 104.97 | 2017-07-03 | M/S Shimul Enterprise, Madhukhali, Faridpur | 2017-08-22 | 98.607 | 70% | 2018-05-31 | 0 | 57.48 | -57.48 | 58.29% | WBM Completed
2 | 265523006-Improvement of Naldi UP-Lahuria Road Ch. 2100-7020m. Salvage Cost Tk. 142650.00 | KDRIDP/Narail/W-14/2017-18 | 4.92 | 0 | 0 | 293.31 | 2017-09-26 | M/S Lipu Enterprise, Kanaipur, Faridpur | 2017-11-13 | 274.94 | 40% | 2018-06-24 | 0 | 81.47 | -81.47 | 29.63% | AS Completed
Improvement of Village Road by BC
3 | 265524001-Lahuria Bazar-Chimanarchar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 265524009 - Lohagara Bazar -Char Korfa Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 265524016-Raghunathpur-Taltala Satrahazari bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 265524005-Lohagara Bazar - Char Korfa Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 265524026-Improvement of Sattrahazari Bazar – Brammondanga Bazar Road (Ch-3500m-5930m)by BC | KDRIDP/Narail/W-02/2016-17 | 2.43 | 0 | 0 | 131.8 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 123.89 | 10% | 2018-05-31 | 0 | 0 | 0 | 0% | Box-Cutting Conpleted
8 | 265524055-Radhanagar Bazar bridge - Kumardanga bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 265525005-Improvement of Bhadradanga - Makrail Road from Ch.1680m - 3000m | KDRIDP/Narail/W-28/2017-18 | 1.32 | 0 | 0 | 78.42 | 2018-02-04 | M/S Fakir Enterprise | 2018-02-14 | 85.47 | 45% | 0 | 0 | 31.83 | -31.83 | 37.24% | WBM Ongoing
10 | 265524062-Improvement of Dinanathpara – Gobindapur Road from Ch. 610m - 1370m. | KDRIDP/Narail/W-29/2017-18 | 0.76 | 0 | 0 | 50.12 | 2018-02-28 | M/S Rupali Construction, Kalibari Road, Barisal | 2018-04-08 | 51.629 | 0% | 2018-09-16 | 0 | 0 | 0 | 0% | 0
11 | 265525222-Makrail Mujam Molla H/O - Mukter Shikder house Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 265525508-Improvement of Mait Kumra C&B road H/O Akkas Master-H/O Lutfor Rahman via Nazrul Ahmed House Road Ch. 00-530m. Salvage Cost Tk. 617629.00 | KDRIDP/Narail/W-15/2017-18 | 0.53 | 0 | 0 | 31.25 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 28.667 | 40% | 2018-02-28 | 0 | 9.28 | -9.28 | 32.37% | AS Completed
13 | 265525226-Kamil Madrasha road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 265524042-Improvement of Jalalshe Maddrasha - Char Bramman Danga Road from Ch. 00m - 1740m | KDRIDP/Narail/W-24/2017-18 | 1.74 | 0 | 0 | 104.77 | 2017-10-09 | M/S Fakir Enterprise, Lohagara, Narail | 2017-11-27 | 103.76 | 55% | 2018-11-30 | 0 | 50.38 | -50.38 | 48.55% | WBM Ongoing
Improvement of Village Road by HBB
15 | 265524030-Kalagachi bazar-Manikgonj bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
16 | 265523006-Periodic Maintenance of Naldi UP- Lahuria UP Road Ch. 00m - 1973m. | KDRIDP/Narail/M-04/2017-18 | 1.973 | 0 | 0 | 58.99 | 2018-04-04 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 61.94 | 0% | 2019-01-11 | 0 | 0 | 0 | 0% | 0
17 | 265524001-Periodic Maintenance of Lahuria Bazar - Chimanarchar road Ch. 00m - 2350m | KDRIDP/Narail/M-03/2017-18 | 2.35 | 0 | 0 | 59.53 | 2018-02-28 | BM Rafiqul Islam Rupgonj, Narail | 2018-04-11 | 65.237 | 5% | 2018-09-17 | 0 | 0 | 0 | 0% | Partly Hard Bed Preparation Completed
18 | 265524017-Rampur RHD Singa-Baka -Jikra Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 265524035-Chachoi CD-Kalna R&H Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 265524046-Char Daulatpur-Kheyaghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
21 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 17.883 | 0 | 0 | 913.16 |  |  |  | 894.14 | 12.62% |  | 0 | 230.44 | -230.44 | 25.77%

## Kalia
Kalia
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 265283002-Kalabaria UP office-Beeldhuria Hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 265283005-Babra R&H-Suktogram Bazer Rd.(Proposed name Babra UP Office- Suktogram Bazer) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 265283006-Babra UP Office via Chanchuri UP Office - Dadontala RHD Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 265283007-Khasial UP office-Patnabazar (Talbaria) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 265283008-Improvement of Chapail UZR – Bagudanga Bazar Road (Ch-700m-1061m) by BC | KDRIDP/Narail/W-07/2016-17 | 0.361 | 0 | 0 | 22.34 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 20.16 | 70% | 2018-05-15 | 0 | 11.5 | -11.5 | 57.04% | WBM Completed
Improvement of Village Road by BC
6 | 265284002-Baddyabati hat-Mirzapur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 265284008-Raghunathpur Sumarkhola WDB Embk. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 265284015-Jogania-sachiadha via Kachuadanga road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 265284036-Hamidpur (Silimpur)-Chalitatala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 265284037-Peroli Hat-Kharoria Mollabari Bazer Via Kharoria Abashan Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 265285001-Harishpur-Hadayetpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 265285012-Improvement of Kathadura – Chanderchar WDB Road (Ch-700m-1815m) by BC | KDRIDP/Narail/W-08/2016-17 | 1.115 | 0 | 0 | 60.43 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-20 | 57.11 | 100% | 2018-05-15 | 55.888 | 55.89 | -0.002 | 97.86% | Final
13 | 265285057-Improvement of Kamshia Village Road (Ch-00m-1250m) by BC | KDRIDP/Narail/W-11/2016-17 | 1.25 | 0 | 0 | 70.76 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 63.72 | 40% | 2018-05-15 | 0 | 19.19 | -19.19 | 30.12% | AS Completed
14 | 265285016-Improvement of Putimary – Panipara Road (Ch-700m-1116m) by BC | KDRIDP/Narail/W-09/2016-17 | 0.416 | 0 | 0 | 25.33 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 22.86 | 40% | 2018-05-15 | 0 | 6.8 | -6.8 | 29.75% | AS Completed
15 | 265285044-Improvement of Khashial – Uttar Khashial Road (Ch-500m-1150m) by BC | KDRIDP/Narail/W-10/2016-17 | 0.65 | 0 | 0 | 35.89 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-24 | 32.39 | 100% | 2018-05-15 | 32.35 | 32.35 | 0 | 99.88% | Final
16 | 265285072-Dumuria-Dudkuria Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 265285137-Improvement of Patna Bridge – Kalinagar (Kalinagar UZR – Naldanga Loboner Kheyaghat) Road (Ch-1620m-3200m) by BC | KDRIDP/Narail/W-12/2016-17 | 1.58 | 0 | 0 | 89.63 | 2017-07-05 | M/S Ruma Enterprise Kalia, Narail | 2017-08-16 | 88.63 | 100% | 2018-03-24 | 87.74 | 87.742 | -0.002 | 99% | Final
18 | 265285149-Improvement of Baoisona Boroghat - Kanaypur Road (Ch-00m-1000m) by BC. | KDRIDP/Narail/W-17/2017-18 | 1 | 0 | 0 | 63.197 | 2017-10-02 | M/S Ruma Enterprise Kalia, Narail | 2017-11-22 | 57.2 | 55% | 2018-09-28 | 0 | 24.4 | -24.4 | 42.66% | WBM Ongoing
Improvement of Village Road by HBB
19 | 265284018-Kalabaria-Patna Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
20 | 265285137-Kalinagar UZR - Naldanga Loboner Kheya Ghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
21 | 265284015-Jogania -Sachiadha via Kachuadanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 265285027-Dumuria -Dudkuria Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
54 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 6.372 | 0 | 0 | 367.577 |  |  |  | 342.07 | 21.96% |  | 175.978 | 237.872 | -61.894 | 69.54%

## Summary
NARAIL
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Union Road by BC | 5 | 5 | 12.4 | 0 | 0 | 680.167 | 263.374 | 61% | 38.72%
Village Road by BC | 23 | 23 | 29.721 | 0 | 0 | 1745.597 | 605.462 | 44.65% | 34.69%
Village Road by HBB | 1 | 1 | 0.665 | 0 | 0 | 21.3 | 21.3 | 100% | 100%
Bridge on Upazila Road | 0 |  | 0 | 30 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 1 |  | 0 | 30 | 0 | 0 | 0 | 0% | #DIV/0!
Maintenance | 5 | 4 | 9.298 | 0 | 0 | 259.437 | 132.23 | 61% | 50.97%
GC-Hat | 1 | 1 | 0 | 0 | 1 | 16.789 | 10 | 75% | 59.56%
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 36 | 34 | 52.084 | 60 | 1 | 2723.29 | 1032.366 | 37.96% | 37.91%