## Jhenaidah
JHENAIDAH
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Shailkupa
1 | 244802001-Sailkupa-Langolbandh GC via Shaduhati Bazar | [13 empty] | 0 | #DIV/0!
2 | 244802005-Shekpara R&H (DM Collage)- Katlagari GC Rd. | [13 empty] | 0 | #DIV/0!
3 | 244802006 - Improvement of Langolbandh GC - Hatfazilpur GC Road.Ch3700m - 7200m. [Salvage Tk. 40268.00]. | KDRIDP/JHENAI/W-59/2017-18 | 3.5 | 0 | 0 | 266.31 | 2018-03-05 | MP(JV) Sailkupa, Jhenaidah | 2018-05-15 | 266.02 | 0% | 2019-04-20 |  |  | 0 | 0% | Salvage Tk. 40268.00
4 | 244802010-Panti GC-Garagonj Bazar via Kancherkole Up Office | [13 empty] | 0 | #DIV/0!
Jhenaidah Sadar
5 | 244192014- Bishoykahli R&H - Ganna GC road via Kulbaria by BC Ch.4210m 7560m & Construction of 02 Nos PVC Pipe Culvert at Ch.5035m & 5910m. Salvage Tk. 2339302.00 | KDRIDP/JHENAI/W-07/2016-17 | 3.35 | 0 | 0 | 227.947 | 2017-05-23 | M/S Molla Enterprise, Garagonj, sailkupa, jhenaidah | 2017-07-16 | 205.15 | 10% | 2018-06-28 |  |  | 0 | 0%
Kotchandpur
6 | 244422004-Sabdarpur GC- Andulbaria GC road( Kotchandpur part) | [13 empty] | 0 | #DIV/0!
7 | 244422005- Talsar GC - Sabdarpur GC via Kamarkundu Mamunsia. road By BC Ch.171m 1958m & Construction of 04 Nos 625mm x 600mm U-Type Culvert at Ch.308m700m1240m & 1432m Kotchandpur | KDRIDP/JHENAI/W-06/2016-17 | 1.787 | 0 | 0 | 100.33 | 2017-05-16 | Md.Rafiqul Islam, Sher-e-Bangla sarak, Jhenaidah | 2017-07-16 | 92.96 | 0% | 2018-04-22 |  |  | 0 | 0%
8 | 244422005- Talsar GC - Sabdarpur GC via Kamarkundu Mamunsia. road By BC Ch.2596m 6266m & Construction of 04 Nos 625mm x 600mm U-Type Culvert at Ch.3730m3995m5270m & 5790m Kotchandpur Salvage Tk. 182693.00 | KDRIDP/JHENAI/W-05/2016-17 | 3.67 | 0 | 0 | 205.46 | 2017-05-16 | M/S Molla Enterprise Garagonj, Sailkupa Jhenaidah | 2017-07-16 | 189.03 | 0% | 2018-06-28 |  |  | 0 | 0% | Salvage-182639.00
Kaligonj
9 | 244332003-Sala Bhora Bazar (RHD) -Kola GC Rd. | [13 empty] | 0 | #DIV/0!
10 | 244332014 - Gazir Bazar GC-Chaturbaria GC Via Salua Bazar Road. | [13 empty] | 0 | #DIV/0!
Moheshpur
11 | 244712006-Jadabpur GC - Purapara GC Rd (Moheshpur portion) | [13 empty] | 0 | #DIV/0!
12 | 244712009-Bhairaba GC-Jadobpur GC via Patra Bazar | [13 empty] | 0 | #DIV/0!
Total |  |  | 12.307 | 0 | 0 | 800.047 |  |  |  | 753.16 | 2.5% |  | 0 | 0 | 0 | 0%
Improvement of Union Road by BC
Shailkupa
1 | ID No – 2444803002 , Chariarbill Bazar- Ramchandrapur Bazar via Mirzapur UP Road | [13 empty] | 0 | #DIV/0!
2 | 244803004-Dudshar Up Office-Rayra Bazar via Tongbila Bazar Rd. | [13 empty] | 0 | #DIV/0!
3 | 244803005-Fulbari UP Office - Royra Bazar Rd. | [13 empty] | 0 | #DIV/0!
4 | 244803006-Kancherkole Up Office-Katlagari GC Rd. | [13 empty] | 0 | #DIV/0!
5 | 244803012 Improvement of Nittynandapur UP Office - Gangutia GC Road. Ch.00m - 1367m, Salvage Tk. 3269731.00. | KDRIDP/JHENAI/W-52/2017-18 | 1.367 | 0 | 0 | 83.78 | 2018-05-15 | M/S Molla Ent. Shailkupa Jhenaidah |  | 81.26 | 0% |  |  |  | 0 | 0% | Salvage Tk. 3269731.00 NOA Issued
6 | ID No – 2444803016, Abaipur UP Office - Bagni Bazar Road | [13 empty] | 0 | #DIV/0!
7 | 244803018- Dhalaharachandra UP Office - Shitli Bazar Road Ch. 2110 - 3786m. | KDRIDP/JHENAI/W-43/2016-17 | 1.676 | 0 | 0 | 127.89 | 2017-08-21 | Liton Traders Modon mohonpara, Jhenaidah | 2017-10-26 | 115.098 | 15% | 2018-07-27 |  |  | 0 | 0%
8 | ID No- 244803019, Shekpara Bazar - Sharutia UP office via Kancherkole UP Road | [13 empty] | 0 | #DIV/0!
Jhenaidah Sadar
9 | 244193007-Improvement of Shadhuhati up H/Q Harinakundu G.C road.Ch2200m - 2590m. | KDRIDP/JHENAI/W-57/2017-18 | 0.39 | 0 | 0 | 23.88 | 2018-03-05 | M/S Emon Enterprise Kanchannagor Jhenaidah | 2018-05-15 | 22.59 | 0% | 2019-01-20 |  |  | 0 | 0%
10 | 244193008-Improvement of Saganna UP H/Q - Holidhani Via Katlamari Bazar Baradi Major Tofique House Jamtola road. Ch 3000m - 3635m. | KDRIDP/JHENAI/W-55/2017-18 | 0.635 | 0 | 0 | 39.13 | 2018-03-05 | Md.Rafiqul Islam Ser-e-Bangla Sarak Jhenaidah | 2018-05-15 | 36.146 | 0% | 2019-01-20 |  |  | 0 | 0%
11 | 244193009-Porahati UP H/Q-Basudavepur Bazer Road. | [13 empty] | 0 | #DIV/0!
12 | 244193012-Padmaker UP office-Bakri Bazar Rd. | [13 empty] | 0 | #DIV/0!
13 | 244193014-Improvement of Surat up office - Baniabhaha Bazer road.Ch300m - 1767m. [Salvage Tk. 170175.00] | KDRIDP/JHENAI/W-58/2017-18 | 1.467 | 0 | 0 | 95.99 | 2018-03-05 | Md.Rafiqul Islam Ser-e-Bangla Sarak Jhenaidah | 2018-05-15 | 87.5 | 0% | 2019-01-20 |  |  | 0 | 0%
14 | 244193015- Improvement of Nariklbaria - Kola via East Narayanpur Road. Ch. 4500m - 5830m. | KDRIDP/JHENAI/W-50/2017-18 | 1.33 | 0 | 0 | 81.62 | 2018-01-08 | M/S Emon Enterprise Kanchannagor, Jhenaidah | 2018-02-19 | 76.29 | 30% | 2018-12-15 |  |  | 0 | 0%
15 | 244193017-Improvement of Ganna UP Office - Chaindepur Bazar road.Ch850m - 1665m. | KDRIDP/JHENAI/W-56/2017-18 | 0.815 | 0 | 0 | 51.28 | 2018-03-05 | M/S Mugdho Builders, Mawlana Bhashani Sarak, Jhenaidah | 2018-05-15 | 47.238 | 0% | 2019-01-20 |  |  | 0 | 0%
16 | 244193021-Dogashi up office-kushabaria hat Rd. | [13 empty] | 0 | #DIV/0!
17 | 244193022 Improvement of Fursandi UP Office -Tikari Bazer Road Ch.5300m - 6090m. | KDRIDP/JHENAI/W-53/2017-18 | 0.79 | 0 | 0 | 50.5 | 2018-02-05 | Md.Rafiqul Islam Ser-e Bangla Sarak Jhenaidah. | 2018-03-29 | 50.479 | 40% |  |  | 15 | -15 | 29.72%
18 | 244193031 Holidhani UP H/Q.- Chandipur bazar via Geramara by BC Ch.4780m 5900m Jhenaidah-S | KDRIDP/JHENAI/W-08/2016-17 | 1.12 | 0 | 0 | 61.908 | 2017-05-23 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-06-19 | 55.72 | 100% | 2017-12-22 | 55.718 | 55.718 | 0 | 100% | Final
Moheshpur
19 | 244713001-Natima UP office (Uzzalpur)-Bhabnagor bazar via ShamKur UP office Rd. | [13 empty] | 0 | #DIV/0!
20 | 244713003-Chulkani Bazar-Purondopur Bazar Via Fotepur UP Office & Zia Collage(ch.3700-6265m) | KDRIDP/JHENAI/W-38/2016-17 | 2.565 | 0 | 0 | 143.15 | 2017-08-03 | M/S Kazi Mahabubur Rahman, Kabi Sukanto Sarak, Jhenaidah | 2017-09-25 | 148.741 | 60% | 2018-07-01 |  | 72 | -72 | 48.41%
21 | 244713006- Nepa U.P. Office - Kushumpur bazar viia Mailbaria By BC Ch.2960m 3650m & Construction of 02 Nos 625mm x 600mm U-Type Culvert at Ch.3080m & 3320m Moheshpur | KDRIDP/JHENAI/W-01/2016-17 | 0.69 | 0 | 0 | 38.63 | 2017-05-16 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2017-06-18 | 36.27 | 100% | 2018-01-17 | 36.265 | 36.265 | 0 | 99.99% | Final
22 | 244713007-Natima U.P Office - Natima bazar By BC Ch.00m 2450m & Construction of 06 Nos 625mm x 600mm U-Type Culvert at Ch.385m439m1100m1218m1232m & 2084m Moheshpur Salvage Tk.4472713.00 | KDRIDP/JHENAI/W-02/2016-17 | 2.45 | 0 | 0 | 155.09 | 2017-05-16 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-07-16 | 139.58 | 100% | 2018-08-04 | 139.576 | 139.576 | 0 | 100% | Final
23 | 244713010-Basbaria UP Office-Vasanpota bazar via Sreepur | [13 empty] | 0 | #DIV/0!
24 | 244713011-Mandarbaria UP Office-Sreerampur bazar | [13 empty] | 0 | #DIV/0!
25 | 244713016-Mandarbaria UP Office-Jhowtala bazar (Chowgacha UZP) | [13 empty] | 0 | #DIV/0!
26 | 244713025-Bakosputa Bazar-Kazirber UP office (Samanta Bazar) Road Via Islampur | [13 empty] | 0 | #DIV/0!
27 | 244713026 - Improvement of S.B.K. UP Office Office Khalishpur GC - Roypur UP Office Jibonnagor via Khardokhalishpur Moheshpur Portion Road .Ch2500m - 4300m [Salvage Tk. 713180.00.] | KDRIDP/JHENAI/W-60/2017-18 | 1.8 | 0 | 0 | 105.72 | 2018-03-05 | M/S Shohor Enterprise Votiargati, Jhenaidah | 2018-05-15 | 97.25 | 20% | 2019-01-20 |  |  | 0 | 0% | Salvage Tk. 713180.00.
Kotchandpur
28 | 244423001-Boluhar UP Office(Railgate) - Talser GC Road via Mamunshia Rd. | [13 empty] | 0 | #DIV/0!
29 | 244423003- Kusha UP office - Gurpara Bazar (Boksipur More) | [13 empty] | 0 | #DIV/0!
30 | 244423004-Boluhar UP Office(Fishery More)-Raypur road viaLaxmikundu Rd. | [13 empty] | 0 | #DIV/0!
31 | 244423005-Elangi UP Office-Kotchandpur(Bolorampur)Via Rangiarputa Road (ch.1597-3858m) | KDRIDP/JHENAI/W-40/2016-17 | 2.261 | 0 | 0 | 128.26 | 2017-08-03 | M/S Unique Cons .(Pvt) Ltd, Arappur Jhenaidah | 2017-09-28 | 119.43 | 0% | 2018-06-28 |  |  | 0 | 0% | Salvage-308447
32 | 244423010-Kushna UP(Mohonpur)-Harindia bazar road. | [13 empty] | 0 | #DIV/0!
Kaligonj
33 | 244333006- Talshar Bazar - Baliadanga GC Road by BC Ch.3350m 4350m Kaligonj Salvage Tk. 345412.00 | KDRIDP/JHENAI/W-15/2016-17 | 1 | 0 | 0 | 58.4 | 2017-05-06 | M/S Unik Builders, Parkpara, Jhenaidah | 2017-07-31 | 57.18 | 100% | 2018-06-30 | 57.126 | 57.126 | 0 | 99.91% | Final
34 | 244333006- Improvement of Talshar Bazar - Baliadanga GC Road Ch. 1755m - 3300m Under Kaligonj Upazila Dist Jhenaidah | KDRIDP/JHENAI/W-70/2017-18 | 1.545 | 0 | 0 | 103.436 | 2018-03-29 | M/S R.M Bricks Chuadanga |  | 98.265 | [6 empty] | NOA Issued
35 | 244333010-Niamathpur Up-Chapraril Bazar Road (ch 500-1500m) | KDRIDP/JHENAI/W-34/2016-17 | 1 | 0 | 0 | 56.5 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 50.85 | 100% | 2018-06-28 | 50.816 | 50.816 | 0 | 99.93% | Final
36 | 244333010- Improvement of Niamathpur UP - Chapraril Bazar Road Ch. 1500m - 3120m Under Kaligonj Upazila Dist Jhenaidah. | KDRIDP/JHENAI/W-71/2017-18 | 1.62 | 0 | 0 | 110.656 | 2018-03-29 | Md.Nayeb Ali Joader Dudsar Sailkupa,Jhenaidah | 2018-04-29 | 105.12 | 0% | 2019-01-29
37 | 244333011 - Improvement of Sundarpur UP - Kalukhali bazar road. Ch.00 - 3440m Kaligonj Salvage Tk. 5625895.00, Jhenaidah | KDRIDP/JHENAI/W-47/2016-17 | 3.44 | 0 | 0 | 207.38 | 2017-10-26 | M/S Shohor Enterprise Bhuatiargati Jhenaidah | 2017-12-24 | 217.04 | 50% | 2018-09-26 |  | 88 | -88 | 40.55% | Salvage-5625895.00
38 | 244333012- Maliat UP - Bathulia bazar Road by BC Ch.1277m 2780m Kaligonj | KDRIDP/JHENAI/W-13/2016-17 | 1.503 | 0 | 0 | 83.11 | 2017-05-06 | Nishit Bosu, Bagajotin Sarak,Jhenaidah | 2017-07-31 | 79.99 | 100% | 2018-06-30 | 79.946 | 79.946 | 0 | 99.94% | Final
39 | 244333012-Maliat Up-Bathulia Bazar Road (ch 2780-4000m) | KDRIDP/JHENAI/W-33/2016-17 | 1.22 | 0 | 0 | 68.96 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 62.067 | 100% | 2018-06-28 | 62.028 | 62.028 | 0 | 99.94% | Final
40 | 244333021-Rakhilgachi UP - Tilla Bazar Rd. | [13 empty] | 0 | #DIV/0!
Harinakundu
41 | 244143004-Kulbaria - Joradah UP Office Rd. | [13 empty] | 0 | #DIV/0!
42 | 244143005- Thaerhuda Up Office-Joradah Kalitola Bazar Road (Ch:500-2300m & 3050-4150m) | KDRIDP/JHENAI/W-36/2016-17 | 2.9 | 0 | 0 | 157.33 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-27 | 141.606 | 0% | 2018-06-28 |  |  | 0 | 0%
Total |  |  | 33.584 | 0 | 0 | 2032.6 |  |  |  | 1925.71 | 43.57% |  | 481.475 | 656.475 | -175 | 34.09%
Improvement of Village Road by BC
Shailkupa
1 | 244804010-Hatfazilpur Bazar-Rotonpur | [13 empty] | 0 | #DIV/0!
2 | 244804012-Alamdanga bazar Shadukhali-Ramchandrapur bazar | [13 empty] | 0 | #DIV/0!
3 | 244804022- Kushabaria - Doutia Bazar Road at Ch.5000m 7000m. Salvage Tk. 518008.00 | KDRIDP/JHENAI/W-24/2016-17 | 2 | 0 | 0 | 111.206 | 2017-06-19 | Liton Traders Modon mohonpara, Jhenaidah | 2017-08-15 | 105.48 | 100% | 2018-06-28 | 105.475 | 105.475 | 0 | 100% | Final
4 | 244804041- Fulhari Bazar - Bhatai Bazar Via Putimari Bhagoban Nagar Road at Ch.00m 2330m. Salvage Tk. 678813.00 | KDRIDP/JHENAI/W-22/2016-17 | 2.3 | 0 | 0 | 139.59 | 2017-06-19 | M/S Molla Enterprise, Garagonj, Sailkupa, Jhenaidah. | 2017-08-22 | 132.51 | 15% | 2018-06-28 |  |  | 0 | 0%
5 | 244804044- Nagirat bazar-Dhalaharachandra (Pakenpara) via Shitali | [13 empty] | 0 | #DIV/0!
6 | 244804042-Panti Bazar-Garagonj Bridge Rd. | [13 empty] | 0 | #DIV/0!
7 | 244804045- B.L.K. bazar - Garagonj bazar Road at Ch.5740m 6390m. Salvage Tk. 1084234.00 | KDRIDP/JHENAI/W-23/2016-17 | 0.65 | 0 | 0 | 37.94 | 2017-06-19 | Monirul Islam Tokon Ser-e-Bangla Sarak, Jhenaidah | 2017-08-13 | 35.83 | 100% | 2018-06-30 | 35.435 | 35.435 | 0 | 98.9% | Final
8 | 244804112-Nagirat bazar-Dhalaharachandra (Pakenpara) via Shitali | [13 empty] | 0 | #DIV/0!
9 | 2444804120-Dhigal gram-PDR school Road | [13 empty] | 0 | #DIV/0!
10 | 244805050-Khondokbaria-Bakhorbar Rd. | [13 empty] | 0 | #DIV/0!
11 | 244804009-Kanchua Bazar-Baliadanga | [13 empty] | 0 | #DIV/0!
12 | 244805159-Debtola Govt. Primary School-Hafiz Pire home via Libat Ali khan road. | [13 empty] | 0 | #DIV/0!
13 | 244805140 - H/Q Khondokar Road at Muratola Road. Ch. 00 - 400.m Salvage Tk. 155676.00,Jhenaidah. | KDRIDP/JHENAI/W-44/2016-17 | 0.4 | 0 | 0 | 22.94 | 2017-08-21 | M/S Molla Enterprise, Garagonj, Sailkupa, Jhenaidah. | 2017-10-22 | 20.65 | 100% | 2018-07-27 | 20.649 | 20.649 | 0 | 100% | Final
14 | 244804160-Brammapur Modhuban High School to Baro Moukuri Govt. Primary School. | [13 empty] | 0 | #DIV/0!
15 | 244805094-Burulia cannel-Burulia Abdul Jallil( Muktizodda) H/O. | [13 empty] | 0 | #DIV/0!
16 | 244805109-Vulida Mosque-Channel road. | [13 empty] | 0 | #DIV/0!
17 | 244804100-Brahamapur High School-Siddhi Bazar via Khairul Master H/O. | [13 empty] | 0 | #DIV/0!
18 | 244805084- Dahakola - Shiddhi Pr. School Road at Ch. 717m - 3500m. | KDRIDP/JHENAI/W-21/2016-17 | 2.783 | 0 | 0 | 156.18 | 2017-06-19 | Liton Traders, Modon mohonpara, Jhenaidah | 2017-09-27 | 154.387 | 60% | 2018-06-28 |  | 74 | -74 | 47.93%
19 | 244805095-Katla Gari UP Office-Channel via Edghi road. | [13 empty] | 0 | #DIV/0!
20 | 244804029- Improvement of Rupdha - Hatfazilpur Bazar Road. Ch. 500 - 1015m & 1765 - 1980m. | KDRIDP/JHENAI/W-45/2016-17 | 0.73 | 0 | 0 | 38.34 | 2017-08-21 | Liton Traders, Modon mohonpara, Jhenaidah | 2017-10-24 | 34.5 | 60% | 2018-07-27 |  |  | 0 | 0% | Out of DPP
21 | 244805204- Improvement of Patchpakia mosque Dual Biswas to H/O Mongla Pachpakhia Battala Road. Ch. 500 - 870m. | KDRIDP/JHENAI/W-46/2016-17 | 0.37 | 0 | 0 | 16.21 | 2017-08-21 | M/S Unik Builders, Parkpara,Jhenaidah | 2017-10-24 | 14.59 | 100% | 2018-07-27 | 14.586 | 14.586 | 0 | 99.97% | Final
Harinakundu
20 | 244144011- Shakharidah Bazar to Sreefaltola Bazar Road (Ch:1600-2976m) | KDRIDP/JHENAI/W-35/2016-17 | 1.376 | 0 | 0 | 73.45 | [8 empty] | 0 | #DIV/0! | Over Laping
21 | 244144014- Pakhimara-Harispur Road (Ch:690-2450m) | KDRIDP/JHENAI/W-37/2016-17 | 1.76 | 0 | 0 | 95.98 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-27 | 86.39 | 60% | 2018-06-28 |  | 46 | -46 | 53.25%
22 | 244144004- Kalishankarpur Pry School - vayna Road by BC Ch.200m 1805m & Construction of 05 Nos 625mm x 600mm U-Type Culvert at Ch.640m841m1060m1400m & 1560m. Salvage Tk.494127.00 | KDRIDP/JHENAI/W-09/2016-17 | 1.605 | 0 | 0 | 93.54 | 2017-05-23 | Shomoy Enterprise, Arappur, Jhenaidah | 2017-06-22 | 84.65 | 35% | 2018-03-24 |  |  | 0 | 0%
23 | 244144006 purbotipur sober shop -Ramchandropur bridge more | [13 empty] | 0 | #DIV/0!
24 | 244144008 kapashitia R&H-sorabria via garabarea | [13 empty] | 0 | #DIV/0!
25 | 244144012 soratola Eidgah-joradah FRB more via beltola and joradah | [13 empty] | 0 | #DIV/0!
26 | 244144017 Kashpur ghat - Hizli | [13 empty] | 0 | #DIV/0!
27 | 244144019Vadra - bhatoi bazar | [13 empty] | 0 | #DIV/0!
28 | 244144022 Padmanagor- Roghunathpur | [13 empty] | 0 | #DIV/0!
29 | 244144024 Baithapara-per folshe | [13 empty] | 0 | #DIV/0!
30 | 244144025- Rishkhali Pucca Kabar - bhuyapara Road by BC Ch.00m 1900m Harinakundu Salvage Tk. 107769.00 | KDRIDP/JHENAI/W-10/2016-17 | 1.9 | 0 | 0 | 99.61 | 2017-05-23 | Nishit Bosu, Kanchannagor | 2017-07-06 | 89.64 | 100% | 2018-04-15 | 88.715 | 88.715 | 0 | 98.97% | Final
31 | 244144036- Kulbaria Pry school - Hoshpur Pucca Road by BC Ch.00m 202m & 822m - 1275m Harinakundu Salvage Tk. 405257.00 | KDRIDP/JHENAI/W-11/2016-17 | 0.655 | 0 | 0 | 35.33 | 2017-05-23 | Jamaluddin Sailkupa, Jhenaidah | 2017-07-16 | 31.8 | 35% | 2018-06-28 |  |  | 0 | 0%
32 | 244145010 Daribinni higschool-radhanagor CARE bridge | [13 empty] | 0 | #DIV/0!
33 | 244145018 purbotepur bazar -pultadanga School more | [13 empty] | 0 | #DIV/0!
34 | 244145126- Raghunathpur H/O Abed Ali to Echamara Main canal road by BC Ch.00m 1260m Harinakundu Salvage Tk. 919109.00 | KDRIDP/JHENAI/W-12/2016-17 | 1.26 | 0 | 0 | 67.38 | 2017-05-23 | Shomoy Enterprise, Arappur, Jhenaidah | 2017-06-19 | 60.65 | 35% | 2018-12-15 |  |  | 0 | 0%
35 | 241115014-Andulia Golam Rasul House Pucca Road to Mandia Bazar Rd. | [13 empty] | 0 | #DIV/0!
Jhenaidah Sadar
36 | 244194016-Dhakhin Ramnagor-Moharajpur Road (ch4300-5553m) | KDRIDP/JHENAI/W-26/2016-17 | 1.253 | 0 | 0 | 69.96 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-18 | 62.967 | 100% | 2018-06-28 | 62.895 | 62.895 | 0 | 99.89% | Final
37 | 244194016-Dhakhin Ramnagor-Mharajpur Road (ch 2238-3238m) | KDRIDP/JHENAI/W-42/2016-17 | 1 | 0 | 0 | 0 | 2017-07-11 | Jahirul Ltd., Meherpur | 2017-09-25 | 77.918 | 0% | 2018-06-28 |  |  | 0 | 0%
38 | 244194038-Aruakandi R&H-Kalamonkhali Bazar Rd. | [13 empty] | 0 | #DIV/0!
39 | 244194039 - Improvement of Kushabaria GC Road - Bamonail via Miakundu Road Ch.1900m - 2540m & 3920m - 4427m. [Salvage Tk.2176433.00] | KDRIDP/JHENAI/W-69/2017-18 | 1.107 | 0 | 0 | 70.96 | 2018-05-24 | M/S Ratul Ente Bhutargati Jhenaidah |  | 67.409 |  |  |  |  | 0 | 0% | NOA Issued
40 | 244194050-Madhubpur to chandipur Bazar Rd. | [13 empty] | 0 | #DIV/0!
41 | 244194061 - Improvement of Naricalbaria GC - Sonatonpur Akra Road Ch.500m - 1000m | KDRIDP/JHENAI/W-67/2017-18 | 0.5 | 0 | 0 | 33.85 | 2018-05-24 | M/S Alamin Enter. Ser-e-Bangla Sarak Jhenaidah |  | 32.156 |  |  |  |  | 0 | 0% | NOA Issued
42 | 244194076 - Improvement of - Furshhundi UP HQ - Kushabaria hat via Laxmipur Marundi Road Ch.1900m - 3070m. | KDRIDP/JHENAI/W-66/2017-18 | 1.17 | 0 | 0 | 70.97 | 2018-05-24 | M/S Shahidul Islam Arappur Bus Stand Jhenaidah |  | 67.417 |  |  |  |  | 0 | 0% | NOA Issued
43 | 244194088-Noldanga Up-Salavorta Bazar Road (ch 1000-2264m) | KDRIDP/JHENAI/W-27/2016-17 | 1.264 | 0 | 0 | 69.97 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-18 | 62.97 | 50% | 2018-06-28 |  | 27 | -27 | 42.88%
44 | 244194092-Porahati UP HQ-Joybangla bazar Rd. | [13 empty] | 0 | #DIV/0!
45 | 244195048-Pobahati Udaipur Road-Pobahati Village Rd. | [13 empty] | 0 | #DIV/0!
46 | 244195056-Baliadanga Madrasa-Kanshi Govt. pry.school. via west in village to aruadangh village road.
47 | 244195080-Putia G/H/ School-Chhayail pry.school road Rd. | [13 empty] | 0 | #DIV/0!
48 | 244195093 - Improvement of Monururia - Bamonaia Village Road Ch 0.00m - 2200m. | KDRIDP/JHENAI/W-68/2017-18 | 2.2 | 0 | 0 | 140.73 | 2018-05-24 | M/S Raine Enterprise Bharakhali Joradah Harinakundu |  | 133.696 |  |  |  |  | 0 | 0% | NOA Issued
49 | 244195106-Chutlia Arapara-Rathan Hat Rd. | [13 empty] | 0 | #DIV/0!
50 | 244195107-Karatipara Village-Kharadani Road (ch 00-1267m) | KDRIDP/JHENAI/W-28/2016-17 | 1.267 | 0 | 0 | 69.99 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-18 | 62.99 | 10% | 2018-06-28 |  |  | 0 | 0%
51 | 244195109-Goriala Non Govt. Pry. School- Gariala Rd. | [13 empty] | 0 | #DIV/0!
52 | 244195130-Ganna Roghunathpur primary school-Betai village road. Rd. | [13 empty] | 0 | #DIV/0!
Kaligonj
53 | 244334017- Jaganathpur - Majdia bazar Khajura Road by BC Ch.2590m-3540m | KDRIDP/JHENAI/W-17/2016-17 | 0.95 | 0 | 0 | 50.92 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 50.73 | 40% | 2018-06-30 |  |  | 0 | 0%
54 | 244334017-Jaganathpur-Majdia Bazar Khajura Road (ch 00-1000m) | KDRIDP/JHENAI/W-29/2016-17 | 1 | 0 | 0 | 55.586 | 2017-06-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-27 | 58.08 | 100% | 2018-06-28 | 58.02 | 58.02 | 0 | 99.9% | Final
55 | 244334021- Perkhirda -Tattipur Bazer Road by BC Ch.970m 2030m Kaligonj Salvage Tk. 164377.00 | KDRIDP/JHENAI/W-16/2016-17 | 1.06 | 0 | 0 | 59.3 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 59.06 | 60% | 2018-06-30 |  |  | 0 | 0%
56 | 244334047-Mallat-Pandhadang(RHD) Road (ch 00-1000m) | KDRIDP/JHENAI/W-30/2016-17 | 1 | 0 | 0 | 55.55 | 2017-06-18 | Nishit Bosu, Bagajotin Sarak, Jhenaidah | 2017-09-27 | 58.305 | 100% | 2018-06-28 | 58.28 | 58.28 | 0 | 99.96% | Final
57 | 244334058 - Improvement of - Perojpur Battala RHD - Kastobhanga UP Office via molladanga Road Ch.00m - 2595m. [Salvage Tk.4893668.00] | KDRIDP/JHENAI/W-65/2017-18 | 2.595 | 0 | 0 | 179.03 | 2018-05-24 | M/S SS Cons. HSS Road, Jhenaidah |  | 170.077 |  |  |  |  | 0 | 0% | NOA Issued
58 | 244334059-Fulbari Railgate (RHD) Hasanhati via Kastobhanga Bazar Rd. | [13 empty] | 0 | #DIV/0!
59 | 244334061-Basepara RHD-Vatpara Road (ch 1860-2115m & 2133-2878m) | KDRIDP/JHENAI/W-32/2016-17 | 1 | 0 | 0 | 58.39 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 52.556 | 100% | 2018-06-28 | 52.53 | 52.53 | 0 | 99.95% | Final
60 | 244334061 - Improvement of - Basepara RHD - Vatpara Road Ch.2878m - 3850m.[Salvage Tk.44943.00] | KDRIDP/JHENAI/W-64/2017-18 | 0.972 | 0 | 0 | 69.13 | 2018-05-24 | M/S Unike Builders Park Para, Jhenaidah |  | 65.677 | [6 empty] | NOA Issued
61 | 244334066 - Improvement of Talian - Narkalbaria Road Ch0.00m - 1180m. | KDRIDP/JHENAI/W-61/2017-18 | 1.18 | 0 | 0 | 71.75 | 2018-05-24 | M/S Unike Builders Park Para, Jhenaidah |  | 68.165 |  |  |  |  | 0 | 0% | NOA Issued
62 | 244334080 Improvement of Satbaria Village South Side - Parkhirdda Khal Road Ch.00m -1000m. | KDRIDP/JHENAI/W-54/2017-18 | 1 | 0 | 0 | 60.22 | 2018-02-05 | Nishit Bosu Kanchan Nagor Jhenaidah. | 2018-03-29 | 55.66 | 50% |  |  | 14.698 | -14.698 | 26.41%
63 | 244335070 - Improvement of Babehi - Mohishahati Road Ch.980m - 2050m. | KDRIDP/JHENAI/W-63/2017-18 | 1.07 | 0 | 0 | 74.28 | 2018-05-24 | Md.Obaidullah Arappur Jhenaidah |  | 70.565 |  |  |  |  | 0 | 0% | NOA Issued
64 | 244335144-Rakhalgachi more-Chotodhopadi Rd | [13 empty] | 0 | #DIV/0!
65 | 244335181-Mohishahati purbopara-Baburgacha Rd | [13 empty] | 0 | #DIV/0!
66 | 244334093- Baro Bazar Health Complex FWC - Fulbari Jhanjonia Pucca Road by BC Ch.401m 1418m Kaligonj Salvage Tk. 162024.00 | KDRIDP/JHENAI/W-19/2016-17 | 1.017 | 0 | 0 | 60.71 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 60.47 | 60% | 2018-06-30 |  |  | 0 | 0%
67 | 244335106-Barobazar Up Office - Badadihi Dakkhin para. | [13 empty] | 0 | #DIV/0!
68 | 244335181-Baro Bazar Kharoja road Moshihati Porbopara-Barobazar Kola road via Badurgacha. | [13 empty] | 0 | #DIV/0!
69 | 244335225- Khedapara - Khalkula Pacca Road bt BC Ch.00m 896m Kaligonj | KDRIDP/JHENAI/W-20/2016-17 | 0.896 | 0 | 0 | 53.44 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 53.24 | 100% | 2018-06-30 | 53.17 | 53.17 | 0 | 99.87% | Final
70 | 244335029-Jamtal (UZR-Therpur)-Rampur | [13 empty] | 0 | #DIV/0!
71 | 244335258- Tilla Bazar to Nowdapara Road | [13 empty] | 0 | #DIV/0!
72 | 244334101- Rakra Uttorpara Mosque RHD - Krishnopur UZR Road bt BC Ch.00m 1200m Kaligonj Salvage Tk. 66098.00 | KDRIDP/JHENAI/W-18/2016-17 | 1.2 | 0 | 0 | 67.15 | 2017-05-06 | Nishit Bosu, Bagajotin Sarak, Jhenaidah | 2017-07-31 | 64.63 | 100% | 2018-06-30 | 64.598 | 64.598 | 0 | 99.95% | Final
73 | 244335219-Kabilpur Nur Ali Master house side-Kabilpur Grayviered Road (ch 00-500m) | KDRIDP/JHENAI/W-31/2016-17 | 0.5 | 0 | 0 | 30.07 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 27.068 | 100% | 2018-06-28 | 27.06 | 27.06 | 0 | 99.97% | Final
74 | 244334105 - Improvement of Banuria Pal Para Baliadanga GC to Bogergasi Via Nawdapara Bridge Road Ch.650m - 1244m.[Salvage Tk. 170957.00] | KDRIDP/JHENAI/W-62/2017-18 | 0.594 | 0 | 0 | 35.978 | 2018-05-24 | M/S Saifur Rahman Hospital Para Kotchandpur Jhenaidah |  | 34.179 |  |  |  |  | 0 | 0% | NOA Issued
75 | 244335143- Improvement of Singdah to Kaligonj - Ganna R&H Beltala Road Ch. 0.00m - 910m Under Kaligonj Upazila Dist Jhenaidah. Salvage Tk. 352429.00 | KDRIDP/JHENAI/W-74/2017-18 | 0.91 | 0 | 0 | 60.065 | 2018-03-29 | Md. Lutfor Rahman Kotchandpur, Jhenaidah |  | 57.06 | 0% |  |  |  | 0 | 0%
76 | 244335044- Improvement of Vhatpara to Kola - Salavora GC Rd. Via Commiunity Clinic Road Ch. 0.00m - 500m Under Kaligonj Upazila Dist Jhenaidah. | KDRIDP/JHENAI/W-73/2017-18 | 0.5 | 0 | 0 | 32.21 | 2018-03-29 | Binay Krishno Biswas, Jhenaidah | 2018-05-15 | 30.6 | 0% | 2019-02-11 |  |  | 0 | 0%
77 | 244335147- Improvement of Basepara Paschimpara Mosque to Mathbari Road. Ch. 0.00m - 616m. Salvage Tk. 243497.00. | KDRIDP/JHENAI/W-51/2017-18 | 0.616 | 0 | 0 | 38.74 | 2018-01-08 | M/S Nishit Telecom Moulana Vasani Sarak Jhenaidah | 2018-02-19 | 34.86 | 60% | 2018-12-15 |  | 12 | -12 | 34.42%
78 | 244335203- Improvement of Doulotpur Sabur House - Bottala Kkalek House Via H/O Mizans Road Ch. 0.00m - 1067m Under Kaligonj Upazila Dist Jhenaidah. | KDRIDP/JHENAI/W-72/2017-18 | 1.067 | 0 | 0 | 78.186 | 2018-03-29 | M/S Alamgir Basar Jhenaidah | 2018-03-29 | 74.277 | 0% | 2019-02-11 |  |  | 0 | 0%
Kotchandpur
79 | 244424001-Saudi - Gorsuti road via Chaykhada, Sreerampuri | [13 empty] | 0 | #DIV/0!
80 | 244424002-Kasuna bazer-Kamarkundu Rd via Sherkhali | [13 empty] | 0 | #DIV/0!
81 | 244424004-Gurpara bazar-Katalia bazar Rd. | [13 empty] | 0 | #DIV/0!
82 | 244424039-Elangi-Chandpara Road (ch.1000-2200m) | KDRIDP/JHENAI/W-41/2016-17 | 1.2 | 0 | 0 | 68.6 | 2017-08-03 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2017-09-25 | 61.74 | 30% | 2018-06-28 |  |  | 0 | 0% | Salvage-407278.00
83 | 244424060-Laxmipur bazar RHD - Dhopabila Dashpara via bridge ghat, Dhopabila GPS. | [13 empty] | 0 | #DIV/0!
84 | 244424063-Kusna UP - Horindia bazar road via Mohonpur, Alukdia | [13 empty] | 0 | #DIV/0!
85 | 244424066-Jalalpur Bazar-Talsar via Ghaga Asshram Road. | [13 empty] | 0 | #DIV/0!
86 | 2444245068-Gobindapur Govt.primary school-Khalishpur SabderpurR&HD | [13 empty] | 0 | #DIV/0!
87 | 2444425071-Alukdia-Tarachan molla H/O to Fulbari Somaskallon Road Via Alukdia | [13 empty] | 0 | #DIV/0!
88 | Pallar pacca road-pallar Govt. Primary School road. | [13 empty] | 0 | #DIV/0!
89 | Alukdia Likat Mango Gardeen to Dublakura road. | [13 empty] | 0 | #DIV/0!
Moheshpur
90 | 244714001-Dattanagar-Purapara Road (ch.1650-4400m) | KDRIDP/JHENAI/W-39/2016-17 | 2.75 | 0 | 0 | 161.23 | 2017-08-03 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2017-09-25 | 145.11 | 60% | 2018-06-28 |  | 37 | -37 | 25.5% | Salvage-4962458.00
91 | 244714010-Padmapukur-Purapara Via Dakatia | [13 empty] | 0 | #DIV/0!
92 | 244714012-Ramchandropur-Belelmath Madrasha | [13 empty] | 0 | #DIV/0!
93 | 244714013-Nasti-Padmarajpur | [13 empty] | 0 | #DIV/0!
94 | 244714016-Improvement of Shamkur-Laraighata Road. Ch1080-2855m. | KDRIDP/JHENAI/W-48/2016-17 | 1.775 | 0 | 0 | 105.33 | 2018-02-05 | Md.Nayeb Ali Dudsar, Sailkupa Jhenaidah | 2018-04-29 | 105.326 | 20% | 2019-01-29 |  |  | 0 | 0%
95 | 244714040-Kadamtala Fotepur via Barermath | [13 empty] | 0 | #DIV/0!
96 | 244714042-Jinnanagar bazar-Baghadanga bazar road via Hudapara | [13 empty] | 0 | #DIV/0!
97 | 244715004-Khalishpur-Marupdha | [13 empty] | 0 | #DIV/0!
98 | 244715012-Gakulnaga-Karincha road | [13 empty] | 0 | #DIV/0!
99 | 244715014-Samanta-Gopalpur-Lalpur | [13 empty] | 0 | #DIV/0!
100 | 244713021 - Sayamkur UP Office to Sayamkur bazar Road Ch. 1750 - 3660m. Salvage TK. 2059801.00 | KDRIDP/JHENAI/W-49/2016-17 | 1.91 | 0 | 0 | 118.09 | 2018-02-05 | Md.Rafiqul Islam Ser-e-Bangla Sarak Jhenaidah | 2018-03-29 | 114.46 | 10% |  |  |  | 0 | 0%
101 | 244715101-Shamkur village road. | [13 empty] | 0 | #DIV/0!
102 | 244715033-Bashbaria-Mokordhajpur Road. | [13 empty] | 0 | #DIV/0!
103 | 244715034-Nowdagram-Bolivadrapur via Sayedpur Road . | [13 empty] | 0 | #DIV/0!
104 | 244715039-Manderbaria-Juka via Vatpara Road. | [13 empty] | 0 | #DIV/0!
105 | 244715022- West side of Rofiqul Islam shod H/O Noyapara Shafi H/O Mosque road By BC Ch.400m 2080m & Construction of 01 Nos 2.00m x 2.00m RCC Box Culvert at Ch.635m Moheshpur | KDRIDP/JHENAI/W-03/2016-17 | 1.68 | 0 | 0 | 97.14 | 2017-05-16 | Md.Rafiqul Islam, Sher-e-Bangla sarak, Jhenaidah | 2017-07-16 | 91.02 | 60% | 2018-03-24 |  |  | 0 | 0%
Total |  |  | 55.992 | 0 | 0 | 3255.221 |  |  |  | 3081.515 | 57.43% |  | 641.413 | 852.111 | -210.698 | 27.65%
Improvement of Village Road by HBB
Jhenaidah Sadar
1 | 244193012-Padmaker up office-Bakri Bazer Rd. | [13 empty] | 0 | #DIV/0!
Kotchandpur
2 | 244424042-Signboard bazar-Shoshanghat road. | [13 empty] | 0 | #DIV/0!
Kaligonj
3 | 244334023- Balorampur - Mostofapur Rd. at Ch.00-1868m, 1950-2340m, 2460-2950m, 3040-3390m. Salvage Tk. 125698.00 | KDRIDP/Jhenai/W-25/2016-17 | 3.098 | 0 | 0 | 101.35 | 2017-06-22 | Saynir Enterprise Moulana Vasani Sarak Jhenaidah | 2017-08-22 | 92.62 | 10% | 2018-06-28 |  |  | 0 | 0%
Total |  |  | 3.098 | 0 | 0 | 101.35 |  |  |  | 92.62 | 10% |  | 0 | 0 | 0 | 0%
Construction of Bridge on Upazila Road (7.30m width)
Shailkupa
1 | 244802006-Const. of RCC Bridge on Hatfazilpur- Nangalband Rd alfapur khal | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Kaligonj
1 | 244334019- Construction of 66.00m Long RCC girder gridge on Mongalpotra - Barfa road over Chitra River at Ch. 2050m Under Kaligonj upazila Dist Jhenaidah. | KDRIDP/Jhenai/ B-03/2017-18 | 0 | 66 | 0 | 361.52 | 2018-02-28 | M/S Shohor Enterprise Bhutiargati ,Jhenaidah | 2018-04-29 | 337 | 0% | 2019-01-28 |  |  | 0 | 0%
2 | 244335059- Construction of 66.00m Long RCC girder gridge on Alipur Chitra River road over Chitra River at Ch.750m Under Kaligonj upazila Dist Jhenaidah. | KDRIDP/Jhenai/ B-02/2017-18 | 0 | 66 | 0 | 362.42 | 2018-02-28 | UJAB-MST(JV) Jibonnagor, Chuadanga | 2018-04-29 | 347.09 | 0% | 2019-01-28 |  |  | 0 | 0%
Jhenaidah Sadar
3 | 244194027-Const. of RCC Bridge on Gabindapur RHD-Kudropara Rd Kadomtalaghat over Naboganga River | [13 empty] | 0 | #DIV/0!
4 | 244194056-Const. of RCC Bridge on Ghorshal up office-Bamonail Bazer via Tekari Bazer(St. Kushabaria bazer) Rd Sanchoi River. | [13 empty] | 0 | #DIV/0!
5 | 244193022- Construction of 54.00m Long RCC Girder Bridge on Fursandi up office - Tikari Bazar road at Ch. 5070m | KDRIDP/Jhenai/B-04/2017-18 | 0 | 54 | 0 | 268.335 | 2018-04-19 | M/S Niaz Traders Sher-e-Bangla Sarak Jhenaidah |  | 249.08 |  |  |  |  | 0 | 0% | NOA Issued
Harinakundu
6 | 244145028- Construction of 22.00m RCC bridge on Dokhalpur Bridge - Perdokhalpur Bottala road over GK9D - 14Khal at Ch.485m | KDRIDP/Jhenai/B-01/2017-18 | 0 | 22 | 0 | 191.598 | 2018-02-28 | Md. Mijanur Raahman Bhotergati, Jhenaidah | 2018-04-29 | 184.205 | 0% |  |  |  | 0 | 0%
Total |  |  | 0 | 208 | 0 | 1183.873 |  |  |  | 1117.375 | 0% |  | 0 | 0 | 0 | 0%
Maintenance
Shailkupa
1 | 24802006-Langolbandh GC -Hatfazilpur GC Rd. | [13 empty] | 0 | #DIV/0!
2 | 24802004-Dudshar UP office-Roypur Bazar Rd. | [13 empty] | 0 | #DIV/0!
3 | ID No – 244802008, Shekpara R&H - Ramchandrapur- Mohishgari - Alomdanga - Fulhari-Bhatai GC Road. | [13 empty] | 0 | #DIV/0!
4 | 244803005- Periodic Maintenance of Fulhari UP Office - Roypur Bazar Road from Ch.0.00m - 800m & 9716m 11640m. | KDRIDP/JHENAI/M-16/2017-18 | 2.724 | 0 | 0 | 72.14 | 2017-12-27 | M/S Molla Enterprise Garagonj Sailkupa Jhenaidah | 2018-02-19 | 64.93 | 10% | 2018-11-20 |  |  | 0 | 0%
5 | 244803006-Kancherkole UP- Katlagari GC Rd. | [13 empty] | 0 | #DIV/0!
6 | 244803007-Monoharpur UP Office- Khulnmbaria Bazar via Banuganj Bazar Rd. | [13 empty] | 0 | #DIV/0!
7 | 244803011-Monharpur UP Office- Shitali Bazar Rd (Ch. 00-1000m) | [13 empty] | 0 | #DIV/0!
8 | 244803018-Dhalahara Chandra UP Office- Shitala Bazar Rd. | [13 empty] | 0 | #DIV/0!
9 | 244804045-BLK Bazar-GARAgonj Bazar Rd. | [13 empty] | 0 | #DIV/0!
10 | 244803004- Periodic Maintenance of Dudshar UP Office - Royra Bazar via Tongbila Bazar Road Ch.750m - 5720m Sailkupa,Jhenaidah. | KDRIDP/JHENAI/M-17/2017-18 | 4.97 | 0 | 0 | 88.888 | 2017-12-27 | M/S Molla Enterprise Garagonj Sailkupa Jhenaidah | 2018-02-19 | 79.999 | 100% | 2018-11-20 | 79.999 | 79.999 | 0 | 100% | Final
11 | 244803019- Periodic Maintenance of Shealhpara Bazar - Sarutia UP Office Road via Kancherkole UP office Road Ch. 2176m - 3326m 5610m 8210m & 8560m 9260m Sailkupa,Jhenaidah. | KDRIDP/JHENAI/M-18/2017-18 | 4.45 | 0 | 0 | 133.08 | 2017-12-27 | M/S Molla Enterprise Garagonj Sailkupa Jhenaidah | 2018-02-19 | 119.776 | 20% | 2018-11-20 |  |  | 0 | 0%
12 | 2444804042-Panti bazar-Garagonj bridge | [13 empty] | 0 | #DIV/0!
13 | 2444804066- Lakhandia to Garagonj Road. | [13 empty] | 0 | #DIV/0!
14 | 241115008-Tola-Mondoltola road | [13 empty] | 0 | #DIV/0!
Harinakundu
15 | 244142010- Periodic Maintenance of Purahati Mandia bazar R&H more - Kalapaharia - Andulia - Taherhuda - Bhawanipur - Bharakhali Road Ch. 5500m -10025m. | KDRIDP/JHENAI/M-09/2017-18 | 4.525 | 0 | 0 | 79.69 | 2017-12-27 | Md.Jamaluddin Fulhori Sailkupa Jhenaidah | 2018-02-27 | 78.498 | 0% | 2018-11-27 |  |  | 0 | 0%
16 | 244143003-Kapashitia UP office(sakaridah bazar C&B)toRishkhali bazar | [13 empty] | 0 | #DIV/0!
17 | 244144001- Periodic Maintenance of Joradha UP office Kumar River via Bherakhali Road Ch. 0.00m -1800m. | KDRIDP/JHENAI/M-10/2017-18 | 1.8 | 0 | 0 | 33.19 | 2017-12-27 | Md.Monirul Islam Chowdhury Arappur Jhenaidah | 2018-02-18 | 33.189 | 0% | 2018-11-20 |  |  | 0 | 0%
18 | 244144011- Periodic Maintenance of Shakharidah bazar - Sreefaltola Bazar Road Ch.0.00m - 546m & 3550m 4950m. | KDRIDP/JHENAI/M-11/2017-18 | 1.946 | 0 | 0 | 36.057 | 2017-12-27 | Md.Monirul Islam Chowdhury Arappur Jhenaidah | 2018-02-18 | 36.046 | 100% | 2018-11-20 | 36.007 | 36.007 | 0 | 99.89% | Final
Jhenaidah Sadar
19 | 244192007-Bishaykhali GC-Nargar bathan BazarR&H via Defolbaria Rd. | [13 empty] | 0 | #DIV/0!
20 | 244193009-Porahati Up H/Q Basudavepur bazar Rd. | [13 empty] | 0 | #DIV/0!
21 | 244193011 - Periodic Maintenance of Naldanga UP Office - Nirsinnapur Bazar R&H road via Kuberear Ghat road. Ch. 0.00m - 800m & 2330m - 3950m under Sadar upazila Dist. Jhenaidah. | KDRIDP/JHENAI/M-19/2017-18 | 2.42 | 0 | 0 | 66.947 | 2018-03-29 | M/S Emon Enterprise Kanchannagor, Jhenaidah |  | 63.6 | 100% |  | 62.43 | 62.43 | 0 | 98.16% | Final
22 | 244193014-Surat UP office-Baniabhabu Bazar Rd. | [13 empty] | 0 | #DIV/0!
23 | 244193015- Periodic Maintenance of Narikelbaria Kola via East Narayanpur Road Ch. 2590m - 4500m Jhenaidah-S ,Jhenaidah. | KDRIDP/JHENAI/M-14/2017-18 | 1.91 | 0 | 0 | 44.18 | 2017-12-27 | M/S Mugdho Builders Moulana Vasani Sarak Jhenaidah | 2018-02-25 | 43.98 | 100% | 2018-11-27 | 43.929 | 43.929 | 0 | 99.88% | Final
24 | 244193021-Dogashi UP- Kushbaria hat Rd. | [13 empty] | 0 | #DIV/0!
25 | 244193022 - Periodic Maintenance of Fursandi UP -Tikari Bazar road. Ch. 3500m - 4365m under Sadar upazila Dist. Jhenaidah. | KDRIDP/JHENAI/M-20/2017-18 | 0.865 | 0 | 0 | 17.61 | 2018-03-29 | Western Construction Harinakundu ,Jhenaidah | 2018-05-15 | 16.734 | 0% | 2019-02-13 |  |  | 0 | 0%
26 | 244193029- Periodic Maintenance of Moharajpur UP HQ - Bhabanipur bazar Road Ch.0.00m - 2850m Jhenaidah-S,Jhenaidah. | KDRIDP/JHENAI/M-13/2017-18 | 2.85 | 0 | 0 | 50.1 | 2017-12-27 | M/S Shohor Enterprise Bhutiargati Jhenaidah | 2018-02-25 | 49.7 | 100% | 2018-11-27 | 49.7 | 49.7 | 0 | 100% | Final
27 | 244193031- Periodic Maintenance of Holidhani UP HQ.- Chandipur bazar via Geramara Road Ch. 0.00m - 2300m & 6000m-7000m Jhenaidah-S ,Jhenaidah. | KDRIDP/JHENAI/M-15/2017-18 | 3.3 | 0 | 0 | 65.73 | 2017-12-27 | M/S Shohor Enterprise Bhutiargati Jhenaidah | 2018-02-25 | 65.669 | 90% | 2018-11-27 |  | 51 | -51 | 77.66%
Moheshpur
28 | 244713001-Natima UP Office-Bhaba nagor Bazar via Shamkur UP Office | [13 empty] | 0 | #DIV/0!
29 | 244713013-Kazirber UP Office Baghadanga bazar via Hudapara Rd. | [13 empty] | 0 | #DIV/0!
30 | 244713018- Peroidic Maintenance of Azampur UP Office - Modonpur bazar via Jiterpur Road Ch.0.00m-3200m Moheshpur ,Jhenaidah. | KDRIDP/JHENAI/M-01/2017-18 | 3.2 | 0 | 0 | 56.14 | 2017-12-27 | M/S Proma Traders Arappur, Jhenaidah | 2018-02-13 | 54.96 | 40% | 2018-11-15 |  |  | 0 | 0%
31 | 244713023- Peroidic Maintenance of Mandarbaria UP Office - Mirzapur Bazar Road Ch.0.00m - 395m. | KDRIDP/JHENAI/M-04/2017-18 | 0.395 | 0 | 0 | 11.31 | 2017-12-27 | M/S Keya Bakery & Confectionary Station Road Nilphamari | 2018-02-25 | 11.29 | 0% | 2018-11-27 |  |  | 0 | 0%
32 | 244714001-Dattanagar-Purapara | [13 empty] | 0 | #DIV/0!
33 | 244714033- Peroidic Maintenance of Goyeshpur village Road Ch. 840m - 2000m. | KDRIDP/JHENAI/M-05/2017-18 | 1.16 | 0 | 0 | 21.39 | 2017-12-27 | S.M Abdus Sobur Chowgacha, Jessore | 2018-02-25 | 21.39 | 100% | 2018-11-27 | 21.35 | 21.35 | 0 | 99.81% | Final
34 | 244714042- Peroidic Maintenance of Jinnanagar bazar - Baghadanga bazar road via Hudapara Road Ch.0.00m - 500m & 4550m 4800m Moheshpur ,Jhenaidah. | KDRIDP/JHENAI/M-03/2017-18 | 0.75 | 0 | 0 | 20.97 | 2017-12-27 | Md.Rafiqul Islam Sher-e-Bangla Sarak Jhenaidah | 2018-02-25 | 20.85 | 0% | 2018-11-27 |  |  | 0 | 0%
35 | 244715001- Peroidic Maintenance of Bhalaipur Dargar More - Bedergary More Road Ch.0.00m - 2250m. | KDRIDP/JHENAI/M-06/2017-18 | 2.25 | 0 | 0 | 67.298 | 2017-12-27 | Modhubon Cons., Kotchandpur Jhenaidah | 2018-02-25 | 65.62 | 100% | 2018-11-27 | 65.616 | 65.616 | 0 | 99.99% | Final
36 | 244715012-Gokulnagar-Karincha Rd. | [13 empty] | 0 | #DIV/0!
37 | 244715020-Jinnanagor-Polianpur | [13 empty] | 0 | #DIV/0!
38 | 244715033-Bashbaria-Mokordhajpur | [13 empty] | 0 | #DIV/0!
39 | 244715029-Manderbaria-Juka via Vatpara | [13 empty] | 0 | #DIV/0!
40 | 244715053- Peroidic Maintenance of of Vhalaipur R&H bridge - Vhalaipur village Road Ch.0.00m - 1160m Moheshpur ,Jhenaidah. | KDRIDP/JHENAI/M-02/2017-18 | 1.16 | 0 | 0 | 37.559 | 2017-12-27 | Modhubon Cons., Kotchandpur Jhenaidah | 2018-02-25 | 36.695 | 100% | 2018-11-27 |  | 15 | -15 | 40.88% | Work Complete
41 | 244715090-Saighoria-Roypur road. | [13 empty] | 0 | #DIV/0!
42 | 244715134-Sundorpur Bazar-Shahabazpur road. | [13 empty] | 0 | #DIV/0!
Kotchandpur
43 | 244422006-Sabdarpur GC-Sarajgonj GC via Soadi Bhomradanga Rd. | [13 empty] | 0 | #DIV/0!
44 | 244423001- Periodic Maintenance of Boluhar U.P. - Talser G.C. Road Ch.2050m -3300m. | KDRIDP/JHENAI/M-07/2017-18 | 1.25 | 0 | 0 | 26.23 | 2017-12-27 | M/S Mugdho Builders, Moulana Vasani Sarak, Jhenaidah | 2018-02-25 | 26.228 | 100% | 2018-11-27 | 25.696 | 25.7 | -0.004 | 97.99% | Final
45 | 244423002-Dora UP-Raghunathpur Bazar via Laxmikundu Rd. | [13 empty] | 0 | #DIV/0!
46 | 244423004-Boluhar UP Office (Fishery more) -Raypur Bazar via Lakxmikundu Rd. | [13 empty] | 0 | #DIV/0!
47 | 244423005- Periodic Maintenance Earth Work of Elangi UP office - Kotchandpur via Rangiarpota Road Ch.0.00m - 1700m. | KDRIDP/JHENAI/M-08/2017-18 | 1.7 | 0 | 0 | 3.68 | 2017-12-27 | M/S Raine Enterprise Harinakundu Jhenaidah | 2018-02-25 | 3.667 | 0% | 2018-08-23 |  |  | 0 | 0%
Kaligonj
48 | 244332003-Sala Bhora Bazar (RHD) -Kola GC Rd. | [13 empty] | 0 | #DIV/0!
49 | 244333008-Jamal UP-Blorampur Bazar | [13 empty] | 0 | #DIV/0!
50 | 244332010-Sadikpur Trimohoni-Arpara Bazar R. | [13 empty] | 0 | #DIV/0!
51 | 244333011-Sundarpur UP-Kalukhali Bazar Rd | [13 empty] | 0 | #DIV/0!
52 | 244333017-Kaligonj H/Q (Balidapara RHD)-Raigram UPKastobhanga Bazar. | [13 empty] | 0 | #DIV/0!
53 | 244334059-Fulbari Railgate RHD-Hasanhati Kastobhabag Bazar Rd. | [13 empty] | 0 | #DIV/0!
54 | 244334062-Dinormore R&H - Damodarpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
55 | 244335050-Kola Pashu Hospital - Dowlotpur Rd. | [13 empty] | 0 | #DIV/0!
56 | 244335067- Periodic Maintenance of Ramchandrapur bazar - Shalikha border.Road Ch.0.00m - 1550m Kaligonj ,Jhenaidah. | KDRIDP/JHENAI/M-12/2017-18 | 1.55 | 0 | 0 | 40.52 | 2017-12-27 | Nishit Bosu Kanchannagor Jhenaidah | 2018-02-25 | 40.298 | 30% | 2018-11-27 |  |  | 0 | 0%
Total |  |  | 45.175 | 0 | 0 | 972.709 |  |  |  | 933.119 | 54.5% |  | 384.727 | 450.731 | -66.004 | 48.3%
GC-Hat
Jhenaidah Sadar
1 | Construction of Naldanga Bazar GC. | KDRIDP/Jhenai/GC-11/2017-18 | 0 | 0 | 1 | 20.55 | 2018-02-19 | Jahirul Ltd. Meherpur | 2018-04-29 | 18.49 | 0% | 2019-01-19 |  |  | 0 | 0%
2 | Construction of Pannatala Bazar GC. | KDRIDP/Jhenai/GC-12/2017-18 | 0 | 0 | 1 | 20.19 | 2018-05-15 | M/S Faiem Ent. HSS Road Jhenaidah |  | 19.176 |  |  |  |  | 0 | 0% | NOA Issued
Kaligonj
3 | Construction of Mandar Baria Bazar GC. | KDRIDP/Jhenai/GC-13/2017-18 | 0 | 0 | 1 | 17.64 | 2018-02-19 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2018-04-29 | 16.2 | 0% | 2019-01-29 |  |  | 0 | 0%
4 | Construction of Damodarpur Bazar GC. | KDRIDP/Jhenai/GC-14/2017-18 | 0 | 0 | 1 | 19.32 | 2018-02-19 | Md.Mijanur Rahman,Bhutiargati ,Jhenaidah | 2018-04-26 | 18 | 40% | 2019-01-26 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 4 | 77.7 |  |  |  | 71.866 | 13.33% |  | 0 | 0 | 0 | 0%
Tree Plantation
Shailkupa
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Harinakundu
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Jhenaidah Sadar
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Moheshpur
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kotchandpur
5 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Kaligonj
6 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 150.156 | 208 | 4 | 8423.5 |  |  |  | 7975.365 | 20.15% |  | 1507.615 | 1959.317 | -451.702 | 24.57%
|  |  | 150.156 | 208 | 4 | 8423.5 |  |  |  | 7975.365 | 16.01% |  | 1507.615 | 1959.317 | -451.702 | 24.57%

## Kaligonj
Kaligonj
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 244332003-Sala Bhora Bazar (RHD) -Kola GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 244332014 - Gazir Bazar GC-Chaturbaria GC Via Salua Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 244333006- Talshar Bazar - Baliadanga GC Road by BC Ch.3350m 4350m Kaligonj Salvage Tk. 345412.00 | KDRIDP/JHENAI/W-15/2016-17 | 1 | 0 | 0 | 58.4 | 2017-05-06 | M/S Unik Builders, Parkpara, Jhenaidah | 2017-07-31 | 57.18 | 100% | 2018-06-30 | 57.126 | 57.126 | 0 | 99.91% | Final
4 | 244333006- Improvement of Talshar Bazar - Baliadanga GC Road Ch. 1755m - 3300m Under Kaligonj Upazila Dist Jhenaidah | KDRIDP/JHENAI/W-70/2017-18 | 1.545 | 0 | 0 | 103.436 | 2018-03-29 | M/S R.M Bricks Chuadanga | 0 | 98.265 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
5 | 244333010-Niamathpur Up-Chapraril Bazar Road (ch 500-1500m) | KDRIDP/JHENAI/W-34/2016-17 | 1 | 0 | 0 | 56.5 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 50.85 | 100% | 2018-06-28 | 50.816 | 50.816 | 0 | 99.93% | Final
6 | 244333010- Improvement of Niamathpur UP - Chapraril Bazar Road Ch. 1500m - 3120m Under Kaligonj Upazila Dist Jhenaidah. | KDRIDP/JHENAI/W-71/2017-18 | 1.62 | 0 | 0 | 110.656 | 2018-03-29 | Md.Nayeb Ali Joader Dudsar Sailkupa,Jhenaidah | 2018-04-29 | 105.12 | 0% | 2019-01-29 | 0 | 0 | 0 | 0% | 0
7 | 244333011 - Improvement of Sundarpur UP - Kalukhali bazar road. Ch.00 - 3440m Kaligonj Salvage Tk. 5625895.00, Jhenaidah | KDRIDP/JHENAI/W-47/2016-17 | 3.44 | 0 | 0 | 207.38 | 2017-10-26 | M/S Shohor Enterprise Bhuatiargati Jhenaidah | 2017-12-24 | 217.04 | 50% | 2018-09-26 | 0 | 88 | -88 | 40.55% | Salvage-5625895.00
8 | 244333012- Maliat UP - Bathulia bazar Road by BC Ch.1277m 2780m Kaligonj | KDRIDP/JHENAI/W-13/2016-17 | 1.503 | 0 | 0 | 83.11 | 2017-05-06 | Nishit Bosu, Bagajotin Sarak,Jhenaidah | 2017-07-31 | 79.99 | 100% | 2018-06-30 | 79.946 | 79.946 | 0 | 99.94% | Final
9 | 244333012-Maliat Up-Bathulia Bazar Road (ch 2780-4000m) | KDRIDP/JHENAI/W-33/2016-17 | 1.22 | 0 | 0 | 68.96 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 62.067 | 100% | 2018-06-28 | 62.028 | 62.028 | 0 | 99.94% | Final
10 | 244333021-Rakhilgachi UP - Tilla Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
11 | 244334017- Jaganathpur - Majdia bazar Khajura Road by BC Ch.2590m-3540m | KDRIDP/JHENAI/W-17/2016-17 | 0.95 | 0 | 0 | 50.92 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 50.73 | 40% | 2018-06-30 | 0 | 0 | 0 | 0% | 0
12 | 244334017-Jaganathpur-Majdia Bazar Khajura Road (ch 00-1000m) | KDRIDP/JHENAI/W-29/2016-17 | 1 | 0 | 0 | 55.586 | 2017-06-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-27 | 58.08 | 100% | 2018-06-28 | 58.02 | 58.02 | 0 | 99.9% | Final
13 | 244334021- Perkhirda -Tattipur Bazer Road by BC Ch.970m 2030m Kaligonj Salvage Tk. 164377.00 | KDRIDP/JHENAI/W-16/2016-17 | 1.06 | 0 | 0 | 59.3 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 59.06 | 60% | 2018-06-30 | 0 | 0 | 0 | 0% | 0
14 | 244334047-Mallat-Pandhadang(RHD) Road (ch 00-1000m) | KDRIDP/JHENAI/W-30/2016-17 | 1 | 0 | 0 | 55.55 | 2017-06-18 | Nishit Bosu, Bagajotin Sarak, Jhenaidah | 2017-09-27 | 58.305 | 100% | 2018-06-28 | 58.28 | 58.28 | 0 | 99.96% | Final
15 | 244334058 - Improvement of - Perojpur Battala RHD - Kastobhanga UP Office via molladanga Road Ch.00m - 2595m. [Salvage Tk.4893668.00] | KDRIDP/JHENAI/W-65/2017-18 | 2.595 | 0 | 0 | 179.03 | 2018-05-24 | M/S SS Cons. HSS Road, Jhenaidah | 0 | 170.077 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
16 | 244334059-Fulbari Railgate (RHD) Hasanhati via Kastobhanga Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 244334061-Basepara RHD-Vatpara Road (ch 1860-2115m & 2133-2878m) | KDRIDP/JHENAI/W-32/2016-17 | 1 | 0 | 0 | 58.39 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 52.556 | 100% | 2018-06-28 | 52.53 | 52.53 | 0 | 99.95% | Final
18 | 244334061 - Improvement of - Basepara RHD - Vatpara Road Ch.2878m - 3850m.[Salvage Tk.44943.00] | KDRIDP/JHENAI/W-64/2017-18 | 0.972 | 0 | 0 | 69.13 | 2018-05-24 | M/S Unike Builders Park Para, Jhenaidah | 0 | 65.677 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
19 | 244334066 - Improvement of Talian - Narkalbaria Road Ch0.00m - 1180m. | KDRIDP/JHENAI/W-61/2017-18 | 1.18 | 0 | 0 | 71.75 | 2018-05-24 | M/S Unike Builders Park Para, Jhenaidah | 0 | 68.165 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
20 | 244334080 Improvement of Satbaria Village South Side - Parkhirdda Khal Road Ch.00m -1000m. | KDRIDP/JHENAI/W-54/2017-18 | 1 | 0 | 0 | 60.22 | 2018-02-05 | Nishit Bosu Kanchan Nagor Jhenaidah. | 2018-03-29 | 55.66 | 50% | 0 | 0 | 14.698 | -14.698 | 26.41% | 0
21 | 244335070 - Improvement of Babehi - Mohishahati Road Ch.980m - 2050m. | KDRIDP/JHENAI/W-63/2017-18 | 1.07 | 0 | 0 | 74.28 | 2018-05-24 | Md.Obaidullah Arappur Jhenaidah | 0 | 70.565 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
22 | 244335144-Rakhalgachi more-Chotodhopadi Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 244335181-Mohishahati purbopara-Baburgacha Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 244334093- Baro Bazar Health Complex FWC - Fulbari Jhanjonia Pucca Road by BC Ch.401m 1418m Kaligonj Salvage Tk. 162024.00 | KDRIDP/JHENAI/W-19/2016-17 | 1.017 | 0 | 0 | 60.71 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 60.47 | 60% | 2018-06-30 | 0 | 0 | 0 | 0% | 0
25 | 244335106-Barobazar Up Office - Badadihi Dakkhin para. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 244335181-Baro Bazar Kharoja road Moshihati Porbopara-Barobazar Kola road via Badurgacha. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 244335225- Khedapara - Khalkula Pacca Road bt BC Ch.00m 896m Kaligonj | KDRIDP/JHENAI/W-20/2016-17 | 0.896 | 0 | 0 | 53.44 | 2017-05-06 | Md.Nayeb Ali Joarder, Dudsar, Sailkupa Jhenaidah | 2017-07-31 | 53.24 | 100% | 2018-06-30 | 53.17 | 53.17 | 0 | 99.87% | Final
28 | 244335029-Jamtal (UZR-Therpur)-Rampur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 244335258- Tilla Bazar to Nowdapara Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 244334101- Rakra Uttorpara Mosque RHD - Krishnopur UZR Road bt BC Ch.00m 1200m Kaligonj Salvage Tk. 66098.00 | KDRIDP/JHENAI/W-18/2016-17 | 1.2 | 0 | 0 | 67.15 | 2017-05-06 | Nishit Bosu, Bagajotin Sarak, Jhenaidah | 2017-07-31 | 64.63 | 100% | 2018-06-30 | 64.598 | 64.598 | 0 | 99.95% | Final
31 | 244335219-Kabilpur Nur Ali Master house side-Kabilpur Grayviered Road (ch 00-500m) | KDRIDP/JHENAI/W-31/2016-17 | 0.5 | 0 | 0 | 30.07 | 2017-07-18 | M/S Shohor Enterprise Bhutiargati, Jhenaidah | 2017-09-20 | 27.068 | 100% | 2018-06-28 | 27.06 | 27.06 | 0 | 99.97% | Final
32 | 244334105 - Improvement of Banuria Pal Para Baliadanga GC to Bogergasi Via Nawdapara Bridge Road Ch.650m - 1244m.[Salvage Tk. 170957.00] | KDRIDP/JHENAI/W-62/2017-18 | 0.594 | 0 | 0 | 35.978 | 2018-05-24 | M/S Saifur Rahman Hospital Para Kotchandpur Jhenaidah | 0 | 34.179 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
33 | 244335143- Improvement of Singdah to Kaligonj - Ganna R&H Beltala Road Ch. 0.00m - 910m Under Kaligonj Upazila Dist Jhenaidah. Salvage Tk. 352429.00 | KDRIDP/JHENAI/W-74/2017-18 | 0.91 | 0 | 0 | 60.065 | 2018-03-29 | Md. Lutfor Rahman Kotchandpur, Jhenaidah | 0 | 57.06 | 0% | 0 | 0 | 0 | 0 | 0% | 0
34 | 244335044- Improvement of Vhatpara to Kola - Salavora GC Rd. Via Commiunity Clinic Road Ch. 0.00m - 500m Under Kaligonj Upazila Dist Jhenaidah. | KDRIDP/JHENAI/W-73/2017-18 | 0.5 | 0 | 0 | 32.21 | 2018-03-29 | Binay Krishno Biswas, Jhenaidah | 2018-05-15 | 30.6 | 0% | 2019-02-11 | 0 | 0 | 0 | 0% | 0
35 | 244335147- Improvement of Basepara Paschimpara Mosque to Mathbari Road. Ch. 0.00m - 616m. Salvage Tk. 243497.00. | KDRIDP/JHENAI/W-51/2017-18 | 0.616 | 0 | 0 | 38.74 | 2018-01-08 | M/S Nishit Telecom Moulana Vasani Sarak Jhenaidah | 2018-02-19 | 34.86 | 60% | 2018-12-15 | 0 | 12 | -12 | 34.42% | 0
36 | 244335203- Improvement of Doulotpur Sabur House - Bottala Kkalek House Via H/O Mizans Road Ch. 0.00m - 1067m Under Kaligonj Upazila Dist Jhenaidah. | KDRIDP/JHENAI/W-72/2017-18 | 1.067 | 0 | 0 | 78.186 | 2018-03-29 | M/S Alamgir Basar Jhenaidah | 2018-03-29 | 74.277 | 0% | 2019-02-11 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by HBB
37 | 244334023- Balorampur - Mostofapur Rd. at Ch.00-1868m, 1950-2340m, 2460-2950m, 3040-3390m. Salvage Tk. 125698.00 | KDRIDP/Jhenai/W-25/2016-17 | 3.098 | 0 | 0 | 101.35 | 2017-06-22 | Saynir Enterprise Moulana Vasani Sarak Jhenaidah | 2017-08-22 | 92.62 | 10% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
38 | 244334019- Construction of 66.00m Long RCC girder gridge on Mongalpotra - Barfa road over Chitra River at Ch. 2050m Under Kaligonj upazila Dist Jhenaidah. | KDRIDP/Jhenai/ B-03/2017-18 | 0 | 66 | 0 | 361.52 | 2018-02-28 | M/S Shohor Enterprise Bhutiargati ,Jhenaidah | 2018-04-29 | 337 | 0% | 2019-01-28 | 0 | 0 | 0 | 0% | 0
39 | 244335059- Construction of 66.00m Long RCC girder gridge on Alipur Chitra River road over Chitra River at Ch.750m Under Kaligonj upazila Dist Jhenaidah. | KDRIDP/Jhenai/ B-02/2017-18 | 0 | 66 | 0 | 362.42 | 2018-02-28 | UJAB-MST(JV) Jibonnagor, Chuadanga | 2018-04-29 | 347.09 | 0% | 2019-01-28 | 0 | 0 | 0 | 0% | 0
Maintenance
40 | 244332003-Sala Bhora Bazar (RHD) -Kola GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 244333008-Jamal UP-Blorampur Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 244332010-Sadikpur Trimohoni-Arpara Bazar R. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 244333011-Sundarpur UP-Kalukhali Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 244333017-Kaligonj H/Q (Balidapara RHD)-Raigram UPKastobhanga Bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 244334059-Fulbari Railgate RHD-Hasanhati Kastobhabag Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 244334062-Dinormore R&H - Damodarpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 244335050-Kola Pashu Hospital - Dowlotpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 244335067- Periodic Maintenance of Ramchandrapur bazar - Shalikha border.Road Ch.0.00m - 1550m Kaligonj ,Jhenaidah. | KDRIDP/JHENAI/M-12/2017-18 | 1.55 | 0 | 0 | 40.52 | 2017-12-27 | Nishit Bosu Kanchannagor Jhenaidah | 2018-02-25 | 40.298 | 30% | 2018-11-27 | 0 | 0 | 0 | 0% | 0
GC-Hat
49 | Construction of Mandar Baria Bazar GC. | KDRIDP/Jhenai/GC-13/2017-18 | 0 | 0 | 1 | 17.64 | 2018-02-19 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2018-04-29 | 16.2 | 0% | 2019-01-29 | 0 | 0 | 0 | 0% | 0
50 | Construction of Damodarpur Bazar GC. | KDRIDP/Jhenai/GC-14/2017-18 | 0 | 0 | 1 | 19.32 | 2018-02-19 | Md.Mijanur Rahman,Bhutiargati ,Jhenaidah | 2018-04-26 | 18 | 40% | 2019-01-26 | 0 | 0 | 0 | 0% | 0
Tree Plantation
51 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 35.103 | 132 | 2 | 2781.917 |  |  |  | 2666.979 | 27.45% |  | 563.574 | 678.272 | -114.698 | 25.43%

## Harinakundu
Harinakundu
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 244143004-Kulbaria - Joradah UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 244143005- Thaerhuda Up Office-Joradah Kalitola Bazar Road (Ch:500-2300m & 3050-4150m) | KDRIDP/JHENAI/W-36/2016-17 | 2.9 | 0 | 0 | 157.33 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-27 | 141.606 | 0% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by BC
3 | 244144011- Shakharidah Bazar to Sreefaltola Bazar Road (Ch:1600-2976m) | KDRIDP/JHENAI/W-35/2016-17 | 1.376 | 0 | 0 | 73.45 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Over Laping
4 | 244144014- Pakhimara-Harispur Road (Ch:690-2450m) | KDRIDP/JHENAI/W-37/2016-17 | 1.76 | 0 | 0 | 95.98 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-27 | 86.39 | 60% | 2018-06-28 | 0 | 46 | -46 | 53.25% | 0
5 | 244144004- Kalishankarpur Pry School - vayna Road by BC Ch.200m 1805m & Construction of 05 Nos 625mm x 600mm U-Type Culvert at Ch.640m841m1060m1400m & 1560m. Salvage Tk.494127.00 | KDRIDP/JHENAI/W-09/2016-17 | 1.605 | 0 | 0 | 93.54 | 2017-05-23 | Shomoy Enterprise, Arappur, Jhenaidah | 2017-06-22 | 84.65 | 35% | 2018-03-24 | 0 | 0 | 0 | 0% | 0
6 | 244144006 purbotipur sober shop -Ramchandropur bridge more | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 244144008 kapashitia R&H-sorabria via garabarea | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 244144012 soratola Eidgah-joradah FRB more via beltola and joradah | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 244144017 Kashpur ghat - Hizli | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 244144019Vadra - bhatoi bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 244144022 Padmanagor- Roghunathpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 244144024 Baithapara-per folshe | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 244144025- Rishkhali Pucca Kabar - bhuyapara Road by BC Ch.00m 1900m Harinakundu Salvage Tk. 107769.00 | KDRIDP/JHENAI/W-10/2016-17 | 1.9 | 0 | 0 | 99.61 | 2017-05-23 | Nishit Bosu, Kanchannagor | 2017-07-06 | 89.64 | 100% | 2018-04-15 | 88.715 | 88.715 | 0 | 98.97% | Final
14 | 244144036- Kulbaria Pry school - Hoshpur Pucca Road by BC Ch.00m 202m & 822m - 1275m Harinakundu Salvage Tk. 405257.00 | KDRIDP/JHENAI/W-11/2016-17 | 0.655 | 0 | 0 | 35.33 | 2017-05-23 | Jamaluddin Sailkupa, Jhenaidah | 2017-07-16 | 31.8 | 35% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
15 | 244145010 Daribinni higschool-radhanagor CARE bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 244145018 purbotepur bazar -pultadanga School more | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 244145126- Raghunathpur H/O Abed Ali to Echamara Main canal road by BC Ch.00m 1260m Harinakundu Salvage Tk. 919109.00 | KDRIDP/JHENAI/W-12/2016-17 | 1.26 | 0 | 0 | 67.38 | 2017-05-23 | Shomoy Enterprise, Arappur, Jhenaidah | 2017-06-19 | 60.65 | 35% | 2018-12-15 | 0 | 0 | 0 | 0% | 0
18 | 241115014-Andulia Golam Rasul House Pucca Road to Mandia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
35 | 244145028- Construction of 22.00m RCC bridge on Dokhalpur Bridge - Perdokhalpur Bottala road over GK9D - 14Khal at Ch.485m | KDRIDP/Jhenai/B-01/2017-18 | 0 | 22 | 0 | 191.598 | 2018-02-28 | Md. Mijanur Raahman Bhotergati, Jhenaidah | 2018-04-29 | 184.205 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Maintenance
19 | 244142010- Periodic Maintenance of Purahati Mandia bazar R&H more - Kalapaharia - Andulia - Taherhuda - Bhawanipur - Bharakhali Road Ch. 5500m -10025m. | KDRIDP/JHENAI/M-09/2017-18 | 4.525 | 0 | 0 | 79.69 | 2017-12-27 | Md.Jamaluddin Fulhori Sailkupa Jhenaidah | 2018-02-27 | 78.498 | 0% | 2018-11-27 | 0 | 0 | 0 | 0% | 0
20 | 244143003-Kapashitia UP office(sakaridah bazar C&B)toRishkhali bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 244144001- Periodic Maintenance of Joradha UP office Kumar River via Bherakhali Road Ch. 0.00m -1800m. | KDRIDP/JHENAI/M-10/2017-18 | 1.8 | 0 | 0 | 33.19 | 2017-12-27 | Md.Monirul Islam Chowdhury Arappur Jhenaidah | 2018-02-18 | 33.189 | 0% | 2018-11-20 | 0 | 0 | 0 | 0% | 0
22 | 244144011- Periodic Maintenance of Shakharidah bazar - Sreefaltola Bazar Road Ch.0.00m - 546m & 3550m 4950m. | KDRIDP/JHENAI/M-11/2017-18 | 1.946 | 0 | 0 | 36.057 | 2017-12-27 | Md.Monirul Islam Chowdhury Arappur Jhenaidah | 2018-02-18 | 36.046 | 100% | 2018-11-20 | 36.007 | 36.007 | 0 | 99.89% | Final
Tree Plantation
23 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 19.727 | 22 | 0 | 963.155 |  |  |  | 826.674 | 15.21% |  | 124.722 | 170.722 | -46 | 20.65%

## Jhenaidah Sadar
Jhenaidah Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 244192014- Bishoykahli R&H - Ganna GC road via Kulbaria by BC Ch.4210m 7560m & Construction of 02 Nos PVC Pipe Culvert at Ch.5035m & 5910m. Salvage Tk. 2339302.00 | KDRIDP/JHENAI/W-07/2016-17 | 3.35 | 0 | 0 | 227.947 | 2017-05-23 | M/S Molla Enterprise, Garagonj, sailkupa, jhenaidah | 2017-07-16 | 205.15 | 10% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
Improvement of Union Road by BC
2 | 244193007-Improvement of Shadhuhati up H/Q Harinakundu G.C road.Ch2200m - 2590m. | KDRIDP/JHENAI/W-57/2017-18 | 0.39 | 0 | 0 | 23.88 | 2018-03-05 | M/S Emon Enterprise Kanchannagor Jhenaidah | 2018-05-15 | 22.59 | 0% | 2019-01-20 | 0 | 0 | 0 | 0% | 0
3 | 244193008-Improvement of Saganna UP H/Q - Holidhani Via Katlamari Bazar Baradi Major Tofique House Jamtola road. Ch 3000m - 3635m. | KDRIDP/JHENAI/W-55/2017-18 | 0.635 | 0 | 0 | 39.13 | 2018-03-05 | Md.Rafiqul Islam Ser-e-Bangla Sarak Jhenaidah | 2018-05-15 | 36.146 | 0% | 2019-01-20 | 0 | 0 | 0 | 0% | 0
4 | 244193009-Porahati UP H/Q-Basudavepur Bazer Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 244193012-Padmaker UP office-Bakri Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 244193014-Improvement of Surat up office - Baniabhaha Bazer road.Ch300m - 1767m. [Salvage Tk. 170175.00] | KDRIDP/JHENAI/W-58/2017-18 | 1.467 | 0 | 0 | 95.99 | 2018-03-05 | Md.Rafiqul Islam Ser-e-Bangla Sarak Jhenaidah | 2018-05-15 | 87.5 | 0% | 2019-01-20 | 0 | 0 | 0 | 0% | 0
7 | 244193015- Improvement of Nariklbaria - Kola via East Narayanpur Road. Ch. 4500m - 5830m. | KDRIDP/JHENAI/W-50/2017-18 | 1.33 | 0 | 0 | 81.62 | 2018-01-08 | M/S Emon Enterprise Kanchannagor, Jhenaidah | 2018-02-19 | 76.29 | 30% | 2018-12-15 | 0 | 0 | 0 | 0% | 0
8 | 244193017-Improvement of Ganna UP Office - Chaindepur Bazar road.Ch850m - 1665m. | KDRIDP/JHENAI/W-56/2017-18 | 0.815 | 0 | 0 | 51.28 | 2018-03-05 | M/S Mugdho Builders, Mawlana Bhashani Sarak, Jhenaidah | 2018-05-15 | 47.238 | 0% | 2019-01-20 | 0 | 0 | 0 | 0% | 0
9 | 244193021-Dogashi up office-kushabaria hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 244193022 Improvement of Fursandi UP Office -Tikari Bazer Road Ch.5300m - 6090m. | KDRIDP/JHENAI/W-53/2017-18 | 0.79 | 0 | 0 | 50.5 | 2018-02-05 | Md.Rafiqul Islam Ser-e Bangla Sarak Jhenaidah. | 2018-03-29 | 50.479 | 40% | 0 | 0 | 15 | -15 | 29.72% | 0
11 | 244193031 Holidhani UP H/Q.- Chandipur bazar via Geramara by BC Ch.4780m 5900m Jhenaidah-S | KDRIDP/JHENAI/W-08/2016-17 | 1.12 | 0 | 0 | 61.908 | 2017-05-23 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-06-19 | 55.72 | 100% | 2017-12-22 | 55.718 | 55.718 | 0 | 100% | Final
Improvement of Village Road by BC
12 | 244194016-Dhakhin Ramnagor-Moharajpur Road (ch4300-5553m) | KDRIDP/JHENAI/W-26/2016-17 | 1.253 | 0 | 0 | 69.96 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-18 | 62.967 | 100% | 2018-06-28 | 62.895 | 62.895 | 0 | 99.89% | Final
13 | 244194016-Dhakhin Ramnagor-Mharajpur Road (ch 2238-3238m) | KDRIDP/JHENAI/W-42/2016-17 | 1 | 0 | 0 | 0 | 2017-07-11 | Jahirul Ltd., Meherpur | 2017-09-25 | 77.918 | 0% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
14 | 244194038-Aruakandi R&H-Kalamonkhali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 244194039 - Improvement of Kushabaria GC Road - Bamonail via Miakundu Road Ch.1900m - 2540m & 3920m - 4427m. [Salvage Tk.2176433.00] | KDRIDP/JHENAI/W-69/2017-18 | 1.107 | 0 | 0 | 70.96 | 2018-05-24 | M/S Ratul Ente Bhutargati Jhenaidah | 0 | 67.409 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
16 | 244194050-Madhubpur to chandipur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 244194061 - Improvement of Naricalbaria GC - Sonatonpur Akra Road Ch.500m - 1000m | KDRIDP/JHENAI/W-67/2017-18 | 0.5 | 0 | 0 | 33.85 | 2018-05-24 | M/S Alamin Enter. Ser-e-Bangla Sarak Jhenaidah | 0 | 32.156 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
18 | 244194076 - Improvement of - Furshhundi UP HQ - Kushabaria hat via Laxmipur Marundi Road Ch.1900m - 3070m. | KDRIDP/JHENAI/W-66/2017-18 | 1.17 | 0 | 0 | 70.97 | 2018-05-24 | M/S Shahidul Islam Arappur Bus Stand Jhenaidah | 0 | 67.417 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
19 | 244194088-Noldanga Up-Salavorta Bazar Road (ch 1000-2264m) | KDRIDP/JHENAI/W-27/2016-17 | 1.264 | 0 | 0 | 69.97 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-18 | 62.97 | 50% | 2018-06-28 | 0 | 27 | -27 | 42.88% | 0
20 | 244194092-Porahati UP HQ-Joybangla bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 244195048-Pobahati Udaipur Road-Pobahati Village Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 244195056-Baliadanga Madrasa-Kanshi Govt. pry.school. via west in village to aruadangh village road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0
23 | 244195080-Putia G/H/ School-Chhayail pry.school road Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 244195093 - Improvement of Monururia - Bamonaia Village Road Ch 0.00m - 2200m. | KDRIDP/JHENAI/W-68/2017-18 | 2.2 | 0 | 0 | 140.73 | 2018-05-24 | M/S Raine Enterprise Bharakhali Joradah Harinakundu | 0 | 133.696 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
25 | 244195106-Chutlia Arapara-Rathan Hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 244195107-Karatipara Village-Kharadani Road (ch 00-1267m) | KDRIDP/JHENAI/W-28/2016-17 | 1.267 | 0 | 0 | 69.99 | 2017-07-18 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-09-18 | 62.99 | 10% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
27 | 244195109-Goriala Non Govt. Pry. School- Gariala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 244195130-Ganna Roghunathpur primary school-Betai village road. Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
29 | 244193012-Padmaker up office-Bakri Bazer Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
30 | 244194027-Const. of RCC Bridge on Gabindapur RHD-Kudropara Rd Kadomtalaghat over Naboganga River | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 244194056-Const. of RCC Bridge on Ghorshal up office-Bamonail Bazer via Tekari Bazer(St. Kushabaria bazer) Rd Sanchoi River. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 244193022- Construction of 54.00m Long RCC Girder Bridge on Fursandi up office - Tikari Bazar road at Ch. 5070m | KDRIDP/Jhenai/B-04/2017-18 | 0 | 54 | 0 | 268.335 | 2018-04-19 | M/S Niaz Traders Sher-e-Bangla Sarak Jhenaidah | 0 | 249.08 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
Maintenance
33 | 244192007-Bishaykhali GC-Nargar bathan BazarR&H via Defolbaria Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 244193009-Porahati Up H/Q Basudavepur bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 244193011 - Periodic Maintenance of Naldanga UP Office - Nirsinnapur Bazar R&H road via Kuberear Ghat road. Ch. 0.00m - 800m & 2330m - 3950m under Sadar upazila Dist. Jhenaidah. | KDRIDP/JHENAI/M-19/2017-18 | 2.42 | 0 | 0 | 66.947 | 2018-03-29 | M/S Emon Enterprise Kanchannagor, Jhenaidah | 0 | 63.6 | 100% | 0 | 62.43 | 62.43 | 0 | 98.16% | Final
36 | 244193014-Surat UP office-Baniabhabu Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 244193015- Periodic Maintenance of Narikelbaria Kola via East Narayanpur Road Ch. 2590m - 4500m Jhenaidah-S ,Jhenaidah. | KDRIDP/JHENAI/M-14/2017-18 | 1.91 | 0 | 0 | 44.18 | 2017-12-27 | M/S Mugdho Builders Moulana Vasani Sarak Jhenaidah | 2018-02-25 | 43.98 | 100% | 2018-11-27 | 43.929 | 43.929 | 0 | 99.88% | Final
38 | 244193021-Dogashi UP- Kushbaria hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 244193022 - Periodic Maintenance of Fursandi UP -Tikari Bazar road. Ch. 3500m - 4365m under Sadar upazila Dist. Jhenaidah. | KDRIDP/JHENAI/M-20/2017-18 | 0.865 | 0 | 0 | 17.61 | 2018-03-29 | Western Construction Harinakundu ,Jhenaidah | 2018-05-15 | 16.734 | 0% | 2019-02-13 | 0 | 0 | 0 | 0% | 0
40 | 244193029- Periodic Maintenance of Moharajpur UP HQ - Bhabanipur bazar Road Ch.0.00m - 2850m Jhenaidah-S,Jhenaidah. | KDRIDP/JHENAI/M-13/2017-18 | 2.85 | 0 | 0 | 50.1 | 2017-12-27 | M/S Shohor Enterprise Bhutiargati Jhenaidah | 2018-02-25 | 49.7 | 100% | 2018-11-27 | 49.7 | 49.7 | 0 | 100% | Final
41 | 244193031- Periodic Maintenance of Holidhani UP HQ.- Chandipur bazar via Geramara Road Ch. 0.00m - 2300m & 6000m-7000m Jhenaidah-S ,Jhenaidah. | KDRIDP/JHENAI/M-15/2017-18 | 3.3 | 0 | 0 | 65.73 | 2017-12-27 | M/S Shohor Enterprise Bhutiargati Jhenaidah | 2018-02-25 | 65.669 | 90% | 2018-11-27 | 0 | 51 | -51 | 77.66% | 0
GC-Hat
42 | Construction of Naldanga Bazar GC. | KDRIDP/Jhenai/GC-11/2017-18 | 0 | 0 | 1 | 20.55 | 2018-02-19 | Jahirul Ltd. Meherpur | 2018-04-29 | 18.49 | 0% | 2019-01-19 | 0 | 0 | 0 | 0% | 0
43 | Construction of Pannatala Bazar GC. | KDRIDP/Jhenai/GC-12/2017-18 | 0 | 0 | 1 | 20.19 | 2018-05-15 | M/S Faiem Ent. HSS Road Jhenaidah | 0 | 19.176 | 0% | 0 | 0 | 0 | 0 | 0% | NOA Issued
Tree Plantation
44 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 31.003 | 54 | 2 | 1712.327 |  |  |  | 1675.065 | 16.59% |  | 274.672 | 367.672 | -93 | 21.95%

## Moheshpur
Moheshpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 244712006-Jadabpur GC - Purapara GC Rd (Moheshpur portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 244712009-Bhairaba GC-Jadobpur GC via Patra Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 244713001-Natima UP office (Uzzalpur)-Bhabnagor bazar via ShamKur UP office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 244713003-Chulkani Bazar-Purondopur Bazar Via Fotepur UP Office & Zia Collage(ch.3700-6265m) | KDRIDP/JHENAI/W-38/2016-17 | 2.565 | 0 | 0 | 143.15 | 2017-08-03 | M/S Kazi Mahabubur Rahman, Kabi Sukanto Sarak, Jhenaidah | 2017-09-25 | 148.741 | 60% | 2018-07-01 | 0 | 72 | -72 | 48.41% | 0
5 | 244713006- Nepa U.P. Office - Kushumpur bazar viia Mailbaria By BC Ch.2960m 3650m & Construction of 02 Nos 625mm x 600mm U-Type Culvert at Ch.3080m & 3320m Moheshpur | KDRIDP/JHENAI/W-01/2016-17 | 0.69 | 0 | 0 | 38.63 | 2017-05-16 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2017-06-18 | 36.27 | 100% | 2018-01-17 | 36.265 | 36.265 | 0 | 99.99% | Final
6 | 244713007-Natima U.P Office - Natima bazar By BC Ch.00m 2450m & Construction of 06 Nos 625mm x 600mm U-Type Culvert at Ch.385m439m1100m1218m1232m & 2084m Moheshpur Salvage Tk.4472713.00 | KDRIDP/JHENAI/W-02/2016-17 | 2.45 | 0 | 0 | 155.09 | 2017-05-16 | Md.Mijanur Rahman, Bhutiargati, Jhenaidah | 2017-07-16 | 139.58 | 100% | 2018-08-04 | 139.576 | 139.576 | 0 | 100% | Final
7 | 244713010-Basbaria UP Office-Vasanpota bazar via Sreepur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 244713011-Mandarbaria UP Office-Sreerampur bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 244713016-Mandarbaria UP Office-Jhowtala bazar (Chowgacha UZP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 244713025-Bakosputa Bazar-Kazirber UP office (Samanta Bazar) Road Via Islampur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 244713026 - Improvement of S.B.K. UP Office Office Khalishpur GC - Roypur UP Office Jibonnagor via Khardokhalishpur Moheshpur Portion Road .Ch2500m - 4300m [Salvage Tk. 713180.00.] | KDRIDP/JHENAI/W-60/2017-18 | 1.8 | 0 | 0 | 105.72 | 2018-03-05 | M/S Shohor Enterprise Votiargati, Jhenaidah | 2018-05-15 | 97.25 | 20% | 2019-01-20 | 0 | 0 | 0 | 0% | Salvage Tk. 713180.00.
Improvement of Village Road by BC
12 | 244714001-Dattanagar-Purapara Road (ch.1650-4400m) | KDRIDP/JHENAI/W-39/2016-17 | 2.75 | 0 | 0 | 161.23 | 2017-08-03 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2017-09-25 | 145.11 | 60% | 2018-06-28 | 0 | 37 | -37 | 25.5% | Salvage-4962458.00
13 | 244714010-Padmapukur-Purapara Via Dakatia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 244714012-Ramchandropur-Belelmath Madrasha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 244714013-Nasti-Padmarajpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 244714016-Improvement of Shamkur-Laraighata Road. Ch1080-2855m. | KDRIDP/JHENAI/W-48/2016-17 | 1.775 | 0 | 0 | 105.33 | 2018-02-05 | Md.Nayeb Ali Dudsar, Sailkupa Jhenaidah | 2018-04-29 | 105.326 | 20% | 2019-01-29 | 0 | 0 | 0 | 0% | 0
17 | 244714040-Kadamtala Fotepur via Barermath | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 244714042-Jinnanagar bazar-Baghadanga bazar road via Hudapara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 244715004-Khalishpur-Marupdha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 244715012-Gakulnaga-Karincha road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 244715014-Samanta-Gopalpur-Lalpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 244713021 - Sayamkur UP Office to Sayamkur bazar Road Ch. 1750 - 3660m. Salvage TK. 2059801.00 | KDRIDP/JHENAI/W-49/2016-17 | 1.91 | 0 | 0 | 118.09 | 2018-02-05 | Md.Rafiqul Islam Ser-e-Bangla Sarak Jhenaidah | 2018-03-29 | 114.46 | 10% | 0 | 0 | 0 | 0 | 0% | 0
23 | 244715101-Shamkur village road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 244715033-Bashbaria-Mokordhajpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 244715034-Nowdagram-Bolivadrapur via Sayedpur Road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 244715039-Manderbaria-Juka via Vatpara Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 244715022- West side of Rofiqul Islam shod H/O Noyapara Shafi H/O Mosque road By BC Ch.400m 2080m & Construction of 01 Nos 2.00m x 2.00m RCC Box Culvert at Ch.635m Moheshpur | KDRIDP/JHENAI/W-03/2016-17 | 1.68 | 0 | 0 | 97.14 | 2017-05-16 | Md.Rafiqul Islam, Sher-e-Bangla sarak, Jhenaidah | 2017-07-16 | 91.02 | 60% | 2018-03-24 | 0 | 0 | 0 | 0% | 0
Maintenance
28 | 244713001-Natima UP Office-Bhaba nagor Bazar via Shamkur UP Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 244713013-Kazirber UP Office Baghadanga bazar via Hudapara Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 244713018- Peroidic Maintenance of Azampur UP Office - Modonpur bazar via Jiterpur Road Ch.0.00m-3200m Moheshpur ,Jhenaidah. | KDRIDP/JHENAI/M-01/2017-18 | 3.2 | 0 | 0 | 56.14 | 2017-12-27 | M/S Proma Traders Arappur, Jhenaidah | 2018-02-13 | 54.96 | 40% | 2018-11-15 | 0 | 0 | 0 | 0% | 0
31 | 244713023- Peroidic Maintenance of Mandarbaria UP Office - Mirzapur Bazar Road Ch.0.00m - 395m. | KDRIDP/JHENAI/M-04/2017-18 | 0.395 | 0 | 0 | 11.31 | 2017-12-27 | M/S Keya Bakery & Confectionary Station Road Nilphamari | 2018-02-25 | 11.29 | 0% | 2018-11-27 | 0 | 0 | 0 | 0% | 0
32 | 244714001-Dattanagar-Purapara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 244714033- Peroidic Maintenance of Goyeshpur village Road Ch. 840m - 2000m. | KDRIDP/JHENAI/M-05/2017-18 | 1.16 | 0 | 0 | 21.39 | 2017-12-27 | S.M Abdus Sobur Chowgacha, Jessore | 2018-02-25 | 21.39 | 100% | 2018-11-27 | 21.35 | 21.35 | 0 | 99.81% | Final
34 | 244714042- Peroidic Maintenance of Jinnanagar bazar - Baghadanga bazar road via Hudapara Road Ch.0.00m - 500m & 4550m 4800m Moheshpur ,Jhenaidah. | KDRIDP/JHENAI/M-03/2017-18 | 0.75 | 0 | 0 | 20.97 | 2017-12-27 | Md.Rafiqul Islam Sher-e-Bangla Sarak Jhenaidah | 2018-02-25 | 20.85 | 0% | 2018-11-27 | 0 | 0 | 0 | 0% | 0
35 | 244715001- Peroidic Maintenance of Bhalaipur Dargar More - Bedergary More Road Ch.0.00m - 2250m. | KDRIDP/JHENAI/M-06/2017-18 | 2.25 | 0 | 0 | 67.298 | 2017-12-27 | Modhubon Cons., Kotchandpur Jhenaidah | 2018-02-25 | 65.62 | 100% | 2018-11-27 | 65.616 | 65.616 | 0 | 99.99% | Final
36 | 244715012-Gokulnagar-Karincha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 244715020-Jinnanagor-Polianpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 244715033-Bashbaria-Mokordhajpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 244715029-Manderbaria-Juka via Vatpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 244715053- Peroidic Maintenance of of Vhalaipur R&H bridge - Vhalaipur village Road Ch.0.00m - 1160m Moheshpur ,Jhenaidah. | KDRIDP/JHENAI/M-02/2017-18 | 1.16 | 0 | 0 | 37.559 | 2017-12-27 | Modhubon Cons., Kotchandpur Jhenaidah | 2018-02-25 | 36.695 | 100% | 2018-11-27 | 0 | 15 | -15 | 40.88% | Work Complete
41 | 244715090-Saighoria-Roypur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 244715134-Sundorpur Bazar-Shahabazpur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
43 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 24.535 | 0 | 0 | 1139.047 |  |  |  | 1088.562 | 17.91% |  | 262.807 | 386.807 | -124 | 35.53%

## Kotchandpur
Kotchandpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 244422004-Sabdarpur GC- Andulbaria GC road( Kotchandpur part) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 244422005- Talsar GC - Sabdarpur GC via Kamarkundu Mamunsia. road By BC Ch.171m 1958m & Construction of 04 Nos 625mm x 600mm U-Type Culvert at Ch.308m700m1240m & 1432m Kotchandpur | KDRIDP/JHENAI/W-06/2016-17 | 1.787 | 0 | 0 | 100.33 | 2017-05-16 | Md.Rafiqul Islam, Sher-e-Bangla sarak, Jhenaidah | 2017-07-16 | 92.96 | 0% | 2018-04-22 | 0 | 0 | 0 | 0% | 0
3 | 244422005- Talsar GC - Sabdarpur GC via Kamarkundu Mamunsia. road By BC Ch.2596m 6266m & Construction of 04 Nos 625mm x 600mm U-Type Culvert at Ch.3730m3995m5270m & 5790m Kotchandpur Salvage Tk. 182693.00 | KDRIDP/JHENAI/W-05/2016-17 | 3.67 | 0 | 0 | 205.46 | 2017-05-16 | M/S Molla Enterprise Garagonj, Sailkupa Jhenaidah | 2017-07-16 | 189.03 | 0% | 2018-06-28 | 0 | 0 | 0 | 0% | Salvage-182639.00
Improvement of Union Road by BC
4 | 244423001-Boluhar UP Office(Railgate) - Talser GC Road via Mamunshia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 244423003- Kusha UP office - Gurpara Bazar (Boksipur More) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 244423004-Boluhar UP Office(Fishery More)-Raypur road viaLaxmikundu Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 244423005-Elangi UP Office-Kotchandpur(Bolorampur)Via Rangiarputa Road (ch.1597-3858m) | KDRIDP/JHENAI/W-40/2016-17 | 2.261 | 0 | 0 | 128.26 | 2017-08-03 | M/S Unique Cons .(Pvt) Ltd, Arappur Jhenaidah | 2017-09-28 | 119.43 | 0% | 2018-06-28 | 0 | 0 | 0 | 0% | Salvage-308447
8 | 244423010-Kushna UP(Mohonpur)-Harindia bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 244424001-Saudi - Gorsuti road via Chaykhada, Sreerampuri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 244424002-Kasuna bazer-Kamarkundu Rd via Sherkhali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 244424004-Gurpara bazar-Katalia bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 244424039-Elangi-Chandpara Road (ch.1000-2200m) | KDRIDP/JHENAI/W-41/2016-17 | 1.2 | 0 | 0 | 68.6 | 2017-08-03 | M/S Jakaullah & Brothers, Jebonnagor, Chuadaga | 2017-09-25 | 61.74 | 30% | 2018-06-28 | 0 | 0 | 0 | 0% | Salvage-407278.00
13 | 244424060-Laxmipur bazar RHD - Dhopabila Dashpara via bridge ghat, Dhopabila GPS. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 244424063-Kusna UP - Horindia bazar road via Mohonpur, Alukdia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 244424066-Jalalpur Bazar-Talsar via Ghaga Asshram Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 2444245068-Gobindapur Govt.primary school-Khalishpur SabderpurR&HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 2444425071-Alukdia-Tarachan molla H/O to Fulbari Somaskallon Road Via Alukdia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | Pallar pacca road-pallar Govt. Primary School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | Alukdia Likat Mango Gardeen to Dublakura road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
20 | 244424042-Signboard bazar-Shoshanghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
21 | 244422006-Sabdarpur GC-Sarajgonj GC via Soadi Bhomradanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 244423001- Periodic Maintenance of Boluhar U.P. - Talser G.C. Road Ch.2050m -3300m. | KDRIDP/JHENAI/M-07/2017-18 | 1.25 | 0 | 0 | 26.23 | 2017-12-27 | M/S Mugdho Builders, Moulana Vasani Sarak, Jhenaidah | 2018-02-25 | 26.228 | 100% | 2018-11-27 | 25.696 | 25.7 | -0.004 | 97.99% | Final
23 | 244423002-Dora UP-Raghunathpur Bazar via Laxmikundu Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 244423004-Boluhar UP Office (Fishery more) -Raypur Bazar via Lakxmikundu Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 244423005- Periodic Maintenance Earth Work of Elangi UP office - Kotchandpur via Rangiarpota Road Ch.0.00m - 1700m. | KDRIDP/JHENAI/M-08/2017-18 | 1.7 | 0 | 0 | 3.68 | 2017-12-27 | M/S Raine Enterprise Harinakundu Jhenaidah | 2018-02-25 | 3.667 | 0% | 2018-08-23 | 0 | 0 | 0 | 0% | 0
Tree Plantation
26 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 11.868 | 0 | 0 | 532.56 |  |  |  | 493.055 | 5% |  | 25.696 | 25.7 | -0.004 | 5.212%

## Shailkupa
Shailkupa
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 244802001-Sailkupa-Langolbandh GC via Shaduhati Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 244802005-Shekpara R&H (DM Collage)- Katlagari GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 244802006 - Improvement of Langolbandh GC - Hatfazilpur GC Road.Ch3700m - 7200m. [Salvage Tk. 40268.00]. | KDRIDP/JHENAI/W-59/2017-18 | 3.5 | 0 | 0 | 266.31 | 2018-03-05 | MP(JV) Sailkupa, Jhenaidah | 2018-05-15 | 266.02 | 0% | 2019-04-20 | 0 | 0 | 0 | 0% | Salvage Tk. 40268.00
4 | 244802010-Panti GC-Garagonj Bazar via Kancherkole Up Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | ID No – 2444803002 , Chariarbill Bazar- Ramchandrapur Bazar via Mirzapur UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 244803004-Dudshar Up Office-Rayra Bazar via Tongbila Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 244803005-Fulbari UP Office - Royra Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 244803006-Kancherkole Up Office-Katlagari GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 244803012 Improvement of Nittynandapur UP Office - Gangutia GC Road. Ch.00m - 1367m, Salvage Tk. 3269731.00. | KDRIDP/JHENAI/W-52/2017-18 | 1.367 | 0 | 0 | 83.78 | 2018-05-15 | M/S Molla Ent. Shailkupa Jhenaidah | 0 | 81.26 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage Tk. 3269731.00 NOA Issued
10 | ID No – 2444803016, Abaipur UP Office - Bagni Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 244803018- Dhalaharachandra UP Office - Shitli Bazar Road Ch. 2110 - 3786m. | KDRIDP/JHENAI/W-43/2016-17 | 1.676 | 0 | 0 | 127.89 | 2017-08-21 | Liton Traders Modon mohonpara, Jhenaidah | 2017-10-26 | 115.098 | 15% | 2018-07-27 | 0 | 0 | 0 | 0% | 0
12 | ID No- 244803019, Shekpara Bazar - Sharutia UP office via Kancherkole UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
13 | 244804010-Hatfazilpur Bazar-Rotonpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 244804012-Alamdanga bazar Shadukhali-Ramchandrapur bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 244804022- Kushabaria - Doutia Bazar Road at Ch.5000m 7000m. Salvage Tk. 518008.00 | KDRIDP/JHENAI/W-24/2016-17 | 2 | 0 | 0 | 111.206 | 2017-06-19 | Liton Traders Modon mohonpara, Jhenaidah | 2017-08-15 | 105.48 | 100% | 2018-06-28 | 105.475 | 105.475 | 0 | 100% | Final
16 | 244804041- Fulhari Bazar - Bhatai Bazar Via Putimari Bhagoban Nagar Road at Ch.00m 2330m. Salvage Tk. 678813.00 | KDRIDP/JHENAI/W-22/2016-17 | 2.3 | 0 | 0 | 139.59 | 2017-06-19 | M/S Molla Enterprise, Garagonj, Sailkupa, Jhenaidah. | 2017-08-22 | 132.51 | 15% | 2018-06-28 | 0 | 0 | 0 | 0% | 0
17 | 244804044- Nagirat bazar-Dhalaharachandra (Pakenpara) via Shitali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 244804042-Panti Bazar-Garagonj Bridge Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 244804045- B.L.K. bazar - Garagonj bazar Road at Ch.5740m 6390m. Salvage Tk. 1084234.00 | KDRIDP/JHENAI/W-23/2016-17 | 0.65 | 0 | 0 | 37.94 | 2017-06-19 | Monirul Islam Tokon Ser-e-Bangla Sarak, Jhenaidah | 2017-08-13 | 35.83 | 100% | 2018-06-30 | 35.435 | 35.435 | 0 | 98.9% | Final
20 | 244804112-Nagirat bazar-Dhalaharachandra (Pakenpara) via Shitali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 2444804120-Dhigal gram-PDR school Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 244805050-Khondokbaria-Bakhorbar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 244804009-Kanchua Bazar-Baliadanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 244805159-Debtola Govt. Primary School-Hafiz Pire home via Libat Ali khan road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 244805140 - H/Q Khondokar Road at Muratola Road. Ch. 00 - 400.m Salvage Tk. 155676.00,Jhenaidah. | KDRIDP/JHENAI/W-44/2016-17 | 0.4 | 0 | 0 | 22.94 | 2017-08-21 | M/S Molla Enterprise, Garagonj, Sailkupa, Jhenaidah. | 2017-10-22 | 20.65 | 100% | 2018-07-27 | 20.649 | 20.649 | 0 | 100% | Final
26 | 244804160-Brammapur Modhuban High School to Baro Moukuri Govt. Primary School. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 244805094-Burulia cannel-Burulia Abdul Jallil( Muktizodda) H/O. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 244805109-Vulida Mosque-Channel road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 244804100-Brahamapur High School-Siddhi Bazar via Khairul Master H/O. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 244805084- Dahakola - Shiddhi Pr. School Road at Ch. 717m - 3500m. | KDRIDP/JHENAI/W-21/2016-17 | 2.783 | 0 | 0 | 156.18 | 2017-06-19 | Liton Traders, Modon mohonpara, Jhenaidah | 2017-09-27 | 154.387 | 60% | 2018-06-28 | 0 | 74 | -74 | 47.93% | 0
31 | 244805095-Katla Gari UP Office-Channel via Edghi road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 244804029- Improvement of Rupdha - Hatfazilpur Bazar Road. Ch. 500 - 1015m & 1765 - 1980m. | KDRIDP/JHENAI/W-45/2016-17 | 0.73 | 0 | 0 | 38.34 | 2017-08-21 | Liton Traders, Modon mohonpara, Jhenaidah | 2017-10-24 | 34.5 | 60% | 2018-07-27 | 0 | 0 | 0 | 0% | Out of DPP
33 | 244805204- Improvement of Patchpakia mosque Dual Biswas to H/O Mongla Pachpakhia Battala Road. Ch. 500 - 870m. | KDRIDP/JHENAI/W-46/2016-17 | 0.37 | 0 | 0 | 16.21 | 2017-08-21 | M/S Unik Builders, Parkpara,Jhenaidah | 2017-10-24 | 14.59 | 100% | 2018-07-27 | 14.586 | 14.586 | 0 | 99.97% | Final
Construction of Bridge on Upazila Road (7.30m width)
34 | 244802006-Const. of RCC Bridge on Hatfazilpur- Nangalband Rd alfapur khal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
36 | 24802006-Langolbandh GC -Hatfazilpur GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 24802004-Dudshar UP office-Roypur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | ID No – 244802008, Shekpara R&H - Ramchandrapur- Mohishgari - Alomdanga - Fulhari-Bhatai GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 244803005- Periodic Maintenance of Fulhari UP Office - Roypur Bazar Road from Ch.0.00m - 800m & 9716m 11640m. | KDRIDP/JHENAI/M-16/2017-18 | 2.724 | 0 | 0 | 72.14 | 2017-12-27 | M/S Molla Enterprise Garagonj Sailkupa Jhenaidah | 2018-02-19 | 64.93 | 10% | 2018-11-20 | 0 | 0 | 0 | 0% | 0
40 | 244803006-Kancherkole UP- Katlagari GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 244803007-Monoharpur UP Office- Khulnmbaria Bazar via Banuganj Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 244803011-Monharpur UP Office- Shitali Bazar Rd (Ch. 00-1000m) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 244803018-Dhalahara Chandra UP Office- Shitala Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 244804045-BLK Bazar-GARAgonj Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 244803004- Periodic Maintenance of Dudshar UP Office - Royra Bazar via Tongbila Bazar Road Ch.750m - 5720m Sailkupa,Jhenaidah. | KDRIDP/JHENAI/M-17/2017-18 | 4.97 | 0 | 0 | 88.888 | 2017-12-27 | M/S Molla Enterprise Garagonj Sailkupa Jhenaidah | 2018-02-19 | 79.999 | 100% | 2018-11-20 | 79.999 | 79.999 | 0 | 100% | Final
46 | 244803019- Periodic Maintenance of Shealhpara Bazar - Sarutia UP Office Road via Kancherkole UP office Road Ch. 2176m - 3326m 5610m 8210m & 8560m 9260m Sailkupa,Jhenaidah. | KDRIDP/JHENAI/M-18/2017-18 | 4.45 | 0 | 0 | 133.08 | 2017-12-27 | M/S Molla Enterprise Garagonj Sailkupa Jhenaidah | 2018-02-19 | 119.776 | 20% | 2018-11-20 | 0 | 0 | 0 | 0% | 0
47 | 2444804042-Panti bazar-Garagonj bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 2444804066- Lakhandia to Garagonj Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 241115008-Tola-Mondoltola road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
50 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 27.92 | 0 | 0 | 1294.494 |  |  |  | 1225.03 | 13.88% |  | 256.144 | 330.144 | -74 | 26.95%

## Summary
JHENAIDAH
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 4 | 3 | 12.307 | 0 | 0 | 753.16 | 0 | 2.5% | 0%
Union Road by BC | 22 | 22 | 33.584 | 0 | 0 | 1925.71 | 656.475 | 43.57% | 34.09%
Village Road by BC | 45 | 40 | 55.992 | 0 | 0 | 3081.515 | 852.111 | 57.43% | 27.65%
Village Road by HBB | 1 | 1 | 3.098 | 0 | 0 | 92.62 | 0 | 10% | 0%
Bridge on Upazila Road | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 4 | 4 | 0 | 208 | 0 | 1117.375 | 0 | 0% | 0%
Maintenance | 20 | 20 | 45.175 | 0 | 0 | 933.119 | 450.731 | 54.5% | 48.3%
GC-Hat | 4 | 4 | 0 | 0 | 4 | 71.866 | 0 | 13.33% | 0%
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 100 | 94 | 150.156 | 208 | 4 | 7975.365 | 1959.317 | 20.15% | 24.57%