## Chuadanga
CHUADANGA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Alamdanga
1 | 218072006-Bondabil R&H-Durlavpur-Hardi-Mirpur (Alamdanga Portion) Rd. | [13 empty] | 0 | #DIV/0!
2 | 218072014-(a) Improvement of Goldari GC-Nilmonigonj Alamdanga Portion road by BC Ch 00-2740m (b) Construction of 6 nos 625x600mm U-Type Drian Culvert at Ch 8 360 720 1510 1820 and 2578m on same road. Salvage Amount TK 510471.00 | KDRIDP/Chua/W-03/2016-17 | 2.74 | 0 | 0 | 202.05 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-11 | 202.03 | 70% | 2018-04-14 |  | 133.34 | -133.34 | 66%
Damurhuda
3 | 218312008-Improvement of Damurhuda GC-Golaidari RHD road Ch 7850-9360m. | KDRIDP/Chua/W-25/2016-17 | 1.51 | 0 | 0 | 100.92 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 90.83 | 70% | 2018-07-11 |  | 60.591 | -60.591 | 66.71%
4 | 218312006-Improvement of Memnagar RHD-Karpashdanga G.C via Buichitala Ch 16670-17800m. Salvage Amount TK. 31050.00 | KDRIDP/Chua/W-24/2016-17 | 1.13 | 0 | 0 | 80.18 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 72.16 | 70% | 2018-07-11 |  | 56.561 | -56.561 | 78.38%
Jibonnagar
5 | 218552009-a) Improvement of Uthali R&H Mollabari-Uthali GC road Ch 00-1140m (b) Construction of 1 nos U-Type Drain Culvert size 625x600mm at Ch 40.00m on same road under Jibannagar Upazila in Chuadanga District Salvage Amount TK. 1723642.00 | KDRIDP/Chua/W-18/2016-17 | 1.14 | 0 | 0 | 82.45 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 74.2 | 60% | 2018-06-19 | 74.13 | 74.13 | 0 | 99.91% | Final
Total |  |  | 6.52 | 0 | 0 | 465.6 |  |  |  | 439.22 | 67.5% |  | 74.13 | 324.622 | -250.492 | 73.91%
Improvement of Union Road by BC
Chuadanga Sadar
1 | 218233002-(a) Improvement of Dingadah Shankarchandra UP Makaldanga-Doster Hat road by BC Ch 6820-7735m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 7165m on same road. Salvage Amount TK 53178.00 | KDRIDP/Chua/W-05/2016-17 | 0.915 | 0 | 0 | 53.24 | 2017-05-22 | M/S Saiful Hasan Joarder | 2017-07-09 | 47.92 | 65% | 2018-04-11 |  | 27.344 | -27.344 | 57.06%
2 | 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 00-25m Ch 70-258m & Ch 680-1400m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 740m 775m 858m & 1173m on The same road. Salvage Amount TK.589357.00 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 1800-5100m Part-B.2 Construction of 1no Size 2.00x1.60m Box Culvert at Ch 4806m Part-B.3 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2396m & 3311m on The same road. Salvage Amount TK.1785054.00 | KDRIDP/Chua/W-39/2017-18 | 4.233 | 0 | 0 | 291.45 | [8 empty] | 0 | #DIV/0!
3 | 218233010-Titudaho UP-Sarabaria-Sujatpur Rd. | [13 empty] | 0 | #DIV/0!
Alamdanga
4 | 218073003-(a) Improvement of Baradi Up-Morebhanga Hat.road Ch -4250m -6704m & 8222-8835 (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 4310, 5355, 5755 & 8468m same road under Alamdanga Upazila in Chuadanga District. Salvage-1526030.00 | KDRIDP/Chua/W-32/2017-18 | 3.067 | 0 | 0 | 204.45 | 2018-02-28 | RAB-RC (PVT) Limited-MS Shahana Construction Md. Mejanur Rahman | 2018-04-15 | 184 | 70% | 2019-01-16 |  | 98.957 | -98.957 | 53.78%
5 | 218073007-Belgachi UP-Ghosbiala Hat Rd. | [13 empty] | 0 | #DIV/0!
6 | 218073015-(A) Improvement of Belgachi UP-Jehala UP road Ch 2100m-5260m (B) Construction of 2Nos 2.00mx2.00m RCC Box Culvert at Ch 2604 & 4425m (C) Construction of 1No 1.00mx1.00m RCC Box Culvert at Ch 3644m D Construction of 11 nos 0.600mx0.625m U-Type Drain Culvert at Ch2300m, 2410m, 2624m, 2742m, 2975m, 3530m, 3612m, 3826m, 4332m, 4666m & 5240m. Salvage Amount TK.740657.00 | KDRIDP/Chua/W-35/2017-18 | 3.16 | 0 | 0 | 230.507 | 2018-05-10 | [7 empty] | 0 | #DIV/0!
7 | 218073017-(A) Improvement of Ailhas UP-Loxmipur Hat road Ch 750m-2650m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 2468m (C) Construction of 7 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1275m, 1522m, 1633m, 1923m, 2000m, 2108m & 2635m on The same road | KDRIDP/Chua/W-36/2017-18 | 1.9 | 0 | 0 | 131.037 | 2018-05-07 | Md. Afzalul Haque | 2018-06-12 | 124.48 | 0% | 2019-03-17 |  |  | 0 | 0%
8 | 218073025-(a) Improvement of Jehala UP-Kumari UP road by BC Ch 2250-2484m 2934-3540m 3650-4675m5208-7383m 7583-7977m and 8727-9111m (b) Construction of 12 nos 625x600mm U-Type Drian Culvert at Ch 3268 3379 3418 3828 3888 3936 6025 6170 6230 6375 6705 and 8834m on same road. Salvage Amount TK 904869.00 | KDRIDP/Chua/W-04/2016-17 | 4.818 | 0 | 0 | 295.3 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 295.16 | 70% | 2018-04-07 |  | 198.052 | -198.052 | 67.1%
9 | 218073028-Part-A.1 Improvement of Alamdanga-Nagdah UP Office via Damas Kedernagar Road Ch 1573-4755m & Ch 5535-7512m Part-A.2 Construction of 2nos Size 1.00x1.00m Box Culvert at Ch 2098 & 4104m Part-A.3 Construction of 11nos Size 0.600mx0.625m U-Type Drain Culvert at Ch 1588m 1969m 2520m 2850m 4650m 5233m 5339m 5837m 5954m 6110m & 6318m on The same road. Salvage Amount TK.2328406.00. | KDRIDP/Chua/W-42/2017-18 | 5.159 | 0 | 0 | 328.115 | [8 empty] | 0 | #DIV/0!
10 | 218073021-Bhangabaria UP-Bogadi hat road. | [13 empty] | 0 | #DIV/0!
Damurhuda
11 | 218313002-Gobindahuda Hat-Karpasdanga UP Road | [13 empty] | 0 | #DIV/0!
12 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC (Ch 12257-13600m). Salvage Amount TK 24740.00 | KDRIDP/Chua/W-10/2016-17 | 1.343 | 0 | 0 | 67.49 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 60.74 | 70% | 2018-04-11 |  | 36.833 | -36.833 | 60.64%
13 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC Ch 10957-12257m. | KDRIDP/Chua/W-12/2016-17 | 1.3 | 0 | 0 | 71.36 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 64.22 | 70% | 2018-04-11 |  | 41.513 | -41.513 | 64.64%
14 | 218313004-Parkrisnopur Madna UP-Kuralgachhi UP | [13 empty] | 0 | #DIV/0!
Jibonnagar
15 | 218553001-Jibannagar-Shimanta UP-Benipur Hat road. | [13 empty] | 0 | #DIV/0!
16 | 218553004-Improvement of Shimanta UP-Goyespur-Dhopakhali Hat road Ch 5510-7960m. Salvage Amount TK. 537215.00 | KDRIDP/Chua/W-22/2016-17 | 2.45 | 0 | 0 | 134.99 | 2017-08-24 | RAB-RC (PVT) Limited | 2017-10-09 | 121.49 | 65% | 2018-07-05 |  | 74.385 | -74.385 | 61.23%
17 | 218553007-Barbhanga R&H-Sutiahat-Hashadah UP Rd. | [13 empty] | 0 | #DIV/0!
18 | 218553008-Shimanto UP- Goyespur-Dhapakhalihat Rd. | [13 empty] | 0 | #DIV/0!
19 | 218553009-Simanto UP-Korotoya-Horihornagar Rd. | [13 empty] | 0 | #DIV/0!
20 | 218553013-Raypur UP-Khalispur GC Rd. | [13 empty] | 0 | #DIV/0!
21 | 218553014-Andulbaria UP - Begumpur Hat Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 28.345 | 0 | 0 | 1807.939 |  |  |  | 898.01 | 58.57% |  | 0 | 477.084 | -477.084 | 53.13%
Improvement of Village Road by BC
Chuadanga Sadar
1 | 218234013-(a) Improvement of Shamvonagar-Shahebnagar road Ch - 910m-2410m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1390m & 2250m. Salvage-929613.00 | KDRIDP/Chua/W-16/2016-17 | 1.5 | 0 | 0 | 90.6 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 81.535 | 60% | 2018-06-19 |  | 38.067 | -38.067 | 46.69%
2 | 218234013-Improvement of Shambunagar-Shahebnagor road Ch 2410-3410m Part-B.2 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2503m & 2674m on The same road. Salvage Amount TK.785762.00 | KDRIDP/Chua/W-38/2017-18 | 1 | 0 | 0 | 64.61 | 2018-05-10 | Md. Babul Mia | 2018-06-12 | 61.38
| 218234020-Improvement of Nehalpur GCCR-Krishnopur road Ch 1000-1992m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 11105m 1362m 1583m & 1940m on The same road. |  | 0.992 | 0 | 0 | 65.33 |  |  |  | 62.06 |  |  |  |  | 0 | 0%
3 | 218234015-Bhultia R&H-Kharagoda Road | [13 empty] | 0 | #DIV/0!
4 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasar road Ch - 1500m-3000m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1824m & 2140m. | KDRIDP/Chua/W-15/2016-17 | 1.5 | 0 | 0 | 84.82 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 76.335 | 70% | 2018-06-19 |  | 44.393 | -44.393 | 58.16%
5 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasha road by BC Ch 3000-3395m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 3100m. Salvage Amount TK 262371.00 | KDRIDP/Chua/W-07/2016-17 | 0.395 | 0 | 0 | 27.87 | 2017-05-22 | M/S Shahana Construction | 2017-07-03 | 25.08 | 100% | 2018-04-06 | 25.07 | 25.074 | -0.004 | 99.98% | Final
6 | 218234040-Badargong R&H-Ashananda pur bazar Via Kotubpur Bazar Rd | [13 empty] | 0 | #DIV/0!
7 | 218234042-Chhoto Salua - Jrishnogar bazar Rd | [13 empty] | 0 | #DIV/0!
8 | 218234049-(a) Improvement of Bhultia R&H-Tiorbila road by BC Ch 1310-2332m (b) Construction of 1no U-drain Culvert 625x600mm at Ch 2140m. Salvage Amount TK 143978.00 | KDRIDP/Chua/W-08/2016-17 | 1.022 | 0 | 0 | 57.85 | 2017-05-22 | Md.Ali Reza | 2017-06-13 | 52.066 | 70% | 2018-03-17 | 52.066 | 52.066 | 0 | 100% | Final
9 | 218234049-Improvement of Bhultia R&H-Tiorbila road Ch 2332-3445m | KDRIDP/Chua/W-37/2017-18 | 1.113 | 0 | 0 | 68.6 | 2018-05-10 | M/S Padma Traders | 2018-06-12 | 65.17 | 0% | 2019-03-06
| 218235011-Improvement of Subdia R&H-Baliakandi road Ch 820-1265m Salvage Amount TK.479973.00 |  | 0.445 | 0 | 0 | 27.856 |  |  |  | 26.46 |  |  |  |  | 0 | 0%
10 | 218235021-Improvement of Dehi-Darsana road Ch 1750-2138m Part-A.2 Construction of 1no Size 0.625mx0.600m U-Type Drain Culvert at Ch 1969m on The same road. | KDRIDP/Chua/W-41/2017-18 | 0.388 | 0 | 0 | 26.23 | 2018-05-10 | Md. Babul Akter | 2018-06-12 | 24.92 |  | 2019-03-06 |  |  | 0 | 0%
| 218235028-Improvement of Makaldanga-Srikele road Ch 970-3265m Part-B.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 1222m 2274m 2453m & 3115m on The same road. Salvage Amount TK.441147.00 |  | 2.295 | 0 | 0 | 148.606 |  |  | 2018-06-12 | 141.176 |  |  |  |  | 0 | 0%
11 | 218235041-(a) Improvement of Batikadanga-Sujayetpur road by BC Ch 1368-2000m (b) Construction of 2 nos U-Drain Culvert 625x600mm at Ch 1398 & 1603m | KDRIDP/Chua/W-06/2016-17 | 0.632 | 0 | 0 | 39.27 | 2017-05-22 | M/S. R. M. Bricks | 2017-07-03 | 35.35 | 100% | 2018-04-06 | 35.347 | 35.347 | 0 | 99.99% | Final
12 | 218235057-(a) Improvement of Natun Bhanderdah-Basu Bhanderdah-Bhanderdah-Jugirhuda road Ch - 4575m-6200m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 4910m & 5225m. Salvage-414736.00 | KDRIDP/Chua/W-27/2017-18 | 1.625 | 0 | 0 | 107.36 | 2018-05-28 | M/S Nitu Traders |  | 101.99 | 0% |  |  |  | 0 | 0% | NOA ISSUED
13 | 218235139-(a) Improvement of Akondobaria Azizuler House-Gunonpara Hudar Bari road by BC Ch 00-1500m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 400 and 770m on same road. Salvage Amount TK 113311.00 | KDRIDP/Chua/W-02/2016-17 | 1.5 | 0 | 0 | 84.8 | 2017-05-15 | Md.Bokhtier Uddin | 2017-06-06 | 84.58 | 25% | 2018-04-09 |  |  | 0 | 0%
14 | 218235100-Alukdia Shead Member house-Rabbani Mondol house via Huchokpara road. | [13 empty] | 0 | #DIV/0!
15 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road by BC Ch 00-2000m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 28 730 and 1782m on same road. Salvage 3746786 | KDRIDP/Chua/W-01/2016-17 | 2 | 0 | 0 | 118.1 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 118.09 | 70% | 2018-04-07 |  | 78.211 | -78.211 | 66.23%
16 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road Ch -2000m-3215m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 2328m 2555m & 2812m same road under Chuadanga Sadar Upazila in Chuadanga District. Salvage 1881928 | KDRIDP/Chua/W-14/2016-17 | 1.22 | 0 | 0 | 76.07 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 68.459 | 70% | 2018-06-19 |  | 43.367 | -43.367 | 63.35%
Alamdanga
17 | 218074004-Improvement of Faridpur-Damos road by BC at Ch: 00-3060m. Salvage Amount TK. 544625.00. | KDRIDP/Chua/W-44/2017-18 | 3.06 | 0 | 0 | 199.799 | 2018-07-05 | [7 empty] | 0 | #DIV/0!
18 | 218074010-Ailhas - Sonatonpur Rd. | [13 empty] | 0 | #DIV/0!
19 | 218074022-Potimari Bottala - Belgech UP via Kadarnagar Rd. | [13 empty] | 0 | #DIV/0!
20 | 218075016-(a) Improvement of MochaiNagar-Shalikha Ch - 00m -1244m & 2200-3290m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 235, 273, 2225, 2311, 2700 & 2936 m. Salvage-4194651.00 | KDRIDP/Chua/W-33/2017-18 | 2.334 | 0 | 0 | 181.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 163.725 | 0% | 2019-02-03 |  |  | 0 | 0%
21 | 218075027-(A) Improvement of Shampur bridge-Alamdanga Rail gate road Ch 1140-3370m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 275m ( C) Construction of 6 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1990m, 2028m, 2182m, 2672m, 2790m & 3068m. Salvage Amount TK.515428.00. | KDRIDP/Chua/W-34/2017-18 | 2.23 | 0 | 0 | 138.98 | 2018-05-07 | R.F.M Construction | 2018-06-07 | 132.03 | 0% | 2019-03-12 |  |  | 0 | 0%
22 | 218075030-Pardurgapur-Digholdanga Rd. | [13 empty] | 0 | #DIV/0!
23 | 218075031-(a) Improvement of Kachikata Bridge-Baradi road Ch - 500m -2635m (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 547, 1048, 1342m & 2112m. Salvage-23000.00 | KDRIDP/Chua/W-30/2017-18 | 2.135 | 0 | 0 | 134.19 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 120.77 | 10% | 2019-02-03 |  |  | 0 | 0%
24 | 218075032-Madarhuda - Tamaltala - Jehala UP Rd. | [13 empty] | 0 | #DIV/0!
25 | 218075070-Improvement of Paikpara Math road by BC at Ch 1300-2000m | KDRIDP/Chua/W-45/2017-18 | 0.7 | 0 | 0 | 47.61 | 2018-07-05 | [7 empty] | 0 | #DIV/0!
| 218075186-Improvement of Par Laximpur-Kodamtola Allas Bazar road by BC at Ch 00-1174m. | KDRIDP/Chua/W-45/2017-18 | 1.174 | 0 | 0 | 77.42 | [8 empty] | 0 | #DIV/0!
26 | 218075155-Jehale UP - Munshigong Poshu hat via Gorgori Asrayon Rd. | [13 empty] | 0 | #DIV/0!
27 | 218075201-Chitlamore road - Panchkomlapur road via Aliatnagar Rd. | [13 empty] | 0 | #DIV/0!
28 | 218075213-(a) Improvement of Jehala Mohon Master house - Matpara Mosque - Gorchapra Shaid Mamber houseroad Ch - 120m -1450m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 250, 488, 810, 1061, 1130 & 1227m same road under Alamdanga Upazila in Chuadanga District. Salvage-299944.00 | KDRIDP/Chua/W-31/2017-18 | 1.33 | 0 | 0 | 88.85 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 79.968 | 40% | 2019-02-03 |  |  | 0 | 0%
Damurhuda
29 | 218314012-a) Improvement of Kushaghata R&H-Purapara road Ch 514-1120m (b) Construction of 2 nos Pipe Culvert at Ch 915 & 1100m. Salvage Amount TK. 160525.00 | KDRIDP/Chua/W-26/2016-17 | 0.606 | 0 | 0 | 33.54 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 30.18 | 100% | 2018-07-11 | 30.175 | 30.175 | 0 | 99.98% | Final
30 | 218314016-Improvement of Dugdugi Family Planing Center-Gobindapur road by BC Ch 00-1640 & 3273-3333m. Salvage Amount TK 209026.00 | KDRIDP/Chua/W-11/2016-17 | 1.7 | 0 | 0 | 93.49 | 2017-05-22 | Jahirul Limited | 2017-07-09 | 84.14 | 100% | 2018-04-11 | 84.14 | 84.14 | 0 | 100% | Final
31 | 218314017-Hawli Eidgah-Shaikpara R&H Road. | [13 empty] | 0 | #DIV/0!
32 | 218314019-Javrampur Battala Parimary School -Uktya Road. | [13 empty] | 0 | #DIV/0!
33 | 218314032-Parkisnopur-Jhajadanga Rd | [13 empty] | 0 | #DIV/0!
34 | 218314040-Pirpur Kullah-Shihnagar via Boyra Rd | [13 empty] | 0 | #DIV/0!
35 | 218314053-(a) Improvement of Chandra FRB-Kanidanga road by BC Ch 4733-6233m (b) Construction of 2 nos U-Tyup Drain Culvert at Ch 5922 & 5788m | KDRIDP/Chua/W-09/2016-17 | 1.5 | 0 | 0 | 84.25 | 2017-05-22 | Md. Shamshodwha Malick | 2017-07-09 | 75.83 | 70% | 2018-04-11 |  | 53.712 | -53.712 | 70.83%
36 | 218314054-Jhapjhapi bridge-Hogoldanga FRB Road | [13 empty] | 0 | #DIV/0!
37 | 218314006-Jhoragacha-Kalabaria Road | [13 empty] | 0 | #DIV/0!
Jibonnagar
38 | 218554001-Purandupur - Nischatapur Road | [13 empty] | 0 | #DIV/0!
39 | 218554002-Panarasoti Bhanga Bridge-Tarinibash Road | [13 empty] | 0 | #DIV/0!
40 | 218554004-Narayanpur-Gangadaspur Rd | [13 empty] | 0 | #DIV/0!
41 | 218554012-a) Improvement of Krishnopur more-Maerudah hat-Shebkhali road Ch 2420-3220m (b) Construction of 1 no RCC Box Culvert size 2.00x2.60m at Ch 2713m (c) Construction of 2 Nos U Type Drain Culvert size 625 x 600 m at Ch 2600 and 2947m. Salvage Amount TK. 597943.00 | KDRIDP/Chua/W-23/2016-17 | 0.8 | 0 | 0 | 57.51 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 51.76 | 82% | 2018-07-11 |  | 41.56 | -41.56 | 80.29%
42 | 218554014-Balihuda-Natun Chakla Road | [13 empty] | 0 | #DIV/0!
43 | 218554017-a) Improvement of Tutulia BGB camp-Rakhal Shah Mazar road Ch 1800-4150m (b) Construction of 3 nos U-Drain Culvert at Ch 2730, 3300 & 3400m. Salvage Amount TK. 560988.00 | KDRIDP/Chua/W-19/2016-17 | 2.35 | 0 | 0 | 133.02 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 119.72 | 15% | 2018-06-19 |  |  | 0 | 0%
44 | 218554023 a) Improvement of Muktarpur-Shahebkhali road via Katapol Chakla road Ch 2050-3810m (b) Construction of 1 no U-Type Drain Culvert size 625x600mm at Ch 3271m. Salvage Amount TK.106683.00 | KDRIDP/Chua/W-21/2016-17 | 1.76 | 0 | 0 | 97.48 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 87.73 | 76% | 2018-07-11 |  | 66.28 | -66.28 | 75.55%
45 | 218554031- A) Improvement of Goyespur-BGB Camp-Changkhali road Ch 4140-6542m B) Construction of 4 nos U-Type Drain Culvert at Ch 4150, 4650,5800 & 6310 m. Salvage Amount TK.142098.00 | KDRIDP/Chua/W-29/2017-18 | 2.402 | 0 | 0 | 150.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-17 | 135.83 | 0% | 2019-02-17 |  |  | 0 | 0%
46 | 218554035-Sontoshpur R&H-Rajapur UZR Road | [13 empty] | 0 | #DIV/0!
47 | 218554037-Improvement of Daulatgong GC-Benipur hat road at ch 6140-8900m. Salvage Amount TK. 280855.00 | KDRIDP/Chua/W-20/2016-17 | 2.76 | 0 | 0 | 151.79 | 2017-07-25 | M/S. JAKAULLAH & BROTHERS | 2017-08-27 | 136.608 | 100% | 2018-06-02 | 136.608 | 136.608 | 0 | 100% | Final
48 | 218554050-a) Improvement of Uthali R&H-Dhopakhali Hat road Ch 1425-3981m (b) Construction of 2 nos 1.00x1.60m Box Culvert at CH 2359 and 3085m (c) Construction of 1 No U-Drain Culvert at Ch 2001m. Salvage Amount TK. 2029785.00 | KDRIDP/Chua/W-17/2016-17 | 2.556 | 0 | 0 | 150.77 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 135.687 | 70% | 2018-09-18 |  | 66.74 | -66.74 | 49.19%
49 | 218555003-A) Improvement of Annantopur Mosque-Mondertola road Ch 00m-1150m B) Construction of 2 nos U-Type Drain Culvert size 600x625mm at Ch 3.00 & 295m. Salvage Amount TK.333332.00 | KDRIDP/Chua/W-28/2017-18 | 1.15 | 0 | 0 | 77.885 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 70.1 | 10% | 2018-08-29 |  |  | 0 | 0%
Total |  |  | 48.174 | 0 | 0 | 2987.396 |  |  |  | 2448.729 | 51.58% |  | 363.406 | 795.74 | -432.334 | 32.5%
Improvement of Village Road by HBB
Chuadanga Sadar
1 | 218235019-Akandabaria bazar-Chandpur Rd. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Alamdanga
2 | 218075047-Bokshipur-Bhodhua Rd. | [13 empty] | 0 | #DIV/0!
3 | 218075147-Boksipur Moor-Maju Bridge via Modhppur Road. | [13 empty] | 0 | #DIV/0!
Damurhuda
4 | 248314073-Chandrabass-Satiantala Road | [13 empty] | 0 | #DIV/0!
5 | 248315080-Laxmipur Hat Mosque Kana Pukorlkor via Dhakian para Graveyard Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Alamdanga
1 | 218073033-Const. of RCC Bridge on Bhangbaria UP Office -Udaypurhat via Bhshbaria Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
2 | 218073018-Const. of RCC Bridge on Gangni UP- Baradi UP Road. | [13 empty] | 0 | #DIV/0!
Damurhuda
3 | 218313009-Const. of RCC Bridge on Par Damurhdua to Karpasdanga UP Road. | [13 empty] | 0 | #DIV/0!
4 | 218314059-Const. of RCC Bridge on Kanaidanga FRB-Kunia Ferryghat Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Maintenance
Chuadanga Sadar
1 | 218234002-Hakita RH-Hatikata Mazar Rd. | [13 empty] | 0 | #DIV/0!
2 | 218234004-Periodic Maintenance of Nilmoniganj-Kulchara more road Ch. 00m-2615m | KDRIDP/Chua/M-07/2017-18 | 2.615 | 0 | 0 | 52.17 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.95 | 10% | 2018-08-29 |  |  | 0 | 0%
3 | 218234034-Jafarpur-Hanur Baradi Rd. | [13 empty] | 0 | #DIV/0!
4 | 218234036-Periodic Maintenance of Chuadanga-Makaldanga road Ch. 3800m-5250m | KDRIDP/Chua/M-08/2017-18 | 1.45 | 0 | 0 | 26.995 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 24.3 | 100% | 2018-08-29 | 24.286 | 24.29 | -0.004 | 99.96% | Final
5 | 218234037-Periodic Maintenance of Joyrampur-Chuadanga road Ch. 3730m-8000m. | KDRIDP/Chua/M-09/2017-18 | 4.27 | 0 | 0 | 73.79 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 66.41 | 100% | 2018-08-29 | 57.77 | 57.77 | 0 | 86.99% | Final
6 | 218234040-Badargong R&H -Ashana ndapur Bazar via Kotubpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
7 | 218234050-Alukdia UP-Khadimpur Rd. | [13 empty] | 0 | #DIV/0!
8 | 218234051-Periodic Maintenance of 5Mils R&H-Balshapur via Harukadi Road Ch. 00m-4190m | KDRIDP/Chua/M-10/2017-18 | 4.19 | 0 | 0 | 72.77 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 65.49 | 10% | 2018-08-29 |  |  | 0 | 0%
9 | 218234053-Periodic Maintenance of Titudah UP-Gopalnagar Road Ch. 00m-1050m | KDRIDP/Chua/M-11/2017-18 | 1.05 | 0 | 0 | 16.446 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 14.8 | 10% | 2018-08-29 |  |  | 0 | 0%
10 | 218235027-Makaldanga- Dinnathpur Rd. | [13 empty] | 0 | #DIV/0!
Alamdanga
11 | 218072012-Munshigonj- Asmankhali GC Rd. | [13 empty] | 0 | #DIV/0!
12 | 218073007-Belgachi UP-Ghosbiala hat Rd. | [13 empty] | 0 | #DIV/0!
13 | 218073010-Baradi UP-Natidangahat Rd. | [13 empty] | 0 | #DIV/0!
14 | 218073028-Alamdanga-Nagdah UP Office via Damas, Kedernagar Road. | [13 empty] | 0 | #DIV/0!
15 | 218074010-Periodic Maintenance of Nagdah Sonatonpur road Ch. 00m-1250m | KDRIDP/Chua/M-03/2017-18 | 1.25 | 0 | 0 | 20.465 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.42 | 100% | 2018-08-29 | 18.42 | 18.42 | 0 | 100% | Final
16 | 218074012-Paikpara-Srimrampur Road. | [13 empty] | 0 | #DIV/0!
17 | 218074013-Periodic Maintenance of Hakimpur-Toirbila road Ch. 00m-2550m | KDRIDP/Chua/M-04/2017-18 | 2.55 | 0 | 0 | 51.905 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.71 | 100% | 2018-08-29 | 46.699 | 46.7 | -0.001 | 99.98% | Final
18 | 218074017-Periodic Maintenance of Bademaju-Binadpur R&H road Ch. 00m-1120m. | KDRIDP/Chua/M-05/2017-18 | 1.12 | 0 | 0 | 29.776 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 26.8 | 100% | 2018-08-29 | 26.79 | 26.79 | 0 | 99.96% | Final
19 | 218074019-Periodic Maintenance of Kayradanga FRB-Gokulkhali GC road. Ch 00m-2040m | KDRIDP/Chua/M-01/2017-18 | 2.04 | 0 | 0 | 25.43 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 22.89 | 20% | 2018-08-29 |  |  | 0 | 0%
20 | 218074026-Periodic Maintenance of Gobindhopur-Kashipur via Faridpur road Ch. 00m-1700m. | KDRIDP/Chua/M-06/2017-18 | 1.7 | 0 | 0 | 38.76 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 34.89 | 0% | 2018-08-29 |  |  | 0 | 0%
21 | 218074029-Periodic Maintenance of Ruhitanpur Hat-Kulpala Ch. 00m-2720m | KDRIDP/Chua/M-02/2017-18 | 2.72 | 0 | 0 | 47.07 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 42.37 | 0% | 2018-08-29 |  |  | 0 | 0%
22 | 218075016-Mochainagar-Shalikha Rd. | [13 empty] | 0 | #DIV/0!
Damurhuda
23 | 218312014-Darsana GC- Madna-Sada bari -Pirpukullah -Karpashdanga GC Rd. | [13 empty] | 0 | #DIV/0!
24 | 218314002-Periodic Maintenance of Gopalpur Primary School-Daliarpur Road Ch. 00m-1095m. | KDRIDP/Chua/M-12/2017-18 | 1.095 | 0 | 0 | 18.23 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 16.41 | 0% | 2018-08-29 |  |  | 0 | 0%
25 | 218314015-Loknathpur R&H-Darsona Dingadah Rd. | [13 empty] | 0 | #DIV/0!
26 | 218314019-Periodic Maintenance of Joyrampur Battala School-Uktya Road Ch. 00m-1740m | KDRIDP/Chua/M-13/2017-18 | 1.74 | 0 | 0 | 31.676 | 2017-12-27 | Liton Traders | 2018-02-19 | 28.51 | 0% | 2018-08-29 |  |  | 0 | 0%
27 | 218314033-Periodic Maintenance of Modna-Hoybadpur more Road Ch. 00m-900m | KDRIDP/Chua/M-14/2017-18 | 0.9 | 0 | 0 | 14.825 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 13.34 | 100% | 2018-08-29 | 13.34 | 13.34 | 0 | 100% | Final
28 | 218314045-Damurhuda Brac more-Upazila more Rd. | [13 empty] | 0 | #DIV/0!
29 | 218314049-Periodic Maintenance of Baroboldia Bazar-Chindipur via Sarabaria Road Ch. 3380m-5125m. | KDRIDP/Chua/M-15/2017-18 | 1.745 | 0 | 0 | 28.15 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 25.34 | 100% | 2018-08-29 | 25.337 | 25.34 | -0.003 | 100% | Final
30 | 218314071-Periodic Maintenance of Talsari R&H-Horirampur Road Ch. 1120m-2690m. | KDRIDP/Chua/M-16/2017-18 | 1.57 | 0 | 0 | 20.11 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.1 | 100% | 2018-08-29 | 18.086 | 18.09 | -0.004 | 99.94% | Final
31 | 218314084-Periodic Maintenance of Buinchatala Tematha-Aramdanga via Thakurpur Road Part-A Ch. 00m-1940m & Part-B Ch. 8840-1189m | KDRIDP/Chua/M-17/2017-18 | 4.99 | 0 | 0 | 113.27 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 101.95 | 20% | 2018-08-29 |  |  | 0 | 0%
Jibonnagar
32 | 218553010-Andulbaria UP - Grisnagar Bazar Rd. | [13 empty] | 0 | #DIV/0!
33 | 218554043-Periodic Maintenance of Balihuda UZR-Raypur Bazar Road Ch. 00m-2400m | KDRIDP/Chua/M-20/2017-18 | 2.4 | 0 | 0 | 38.87 | 2017-12-28 | M/S. Khandaker Shahin Ahmed | 2018-02-19 | 34.98 | 15% | 2018-08-29 |  |  | 0 | 0%
34 | 218554047-Bokundia R&H - Minajpur hat Rd. | [13 empty] | 0 | #DIV/0!
35 | 218554054-Periodic Maintenance of Piaratala R&H-Kasipur Hat Road Ch. 00m-6420m. | KDRIDP/Chua/M-18/2017-18 | 6.42 | 0 | 0 | 92.81 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 83.53 | 70% | 2018-08-29 |  | 21.81 | -21.81 | 26.11%
36 | 218554058-Banka UP-Dattanagar Bazar Rd. | [13 empty] | 0 | #DIV/0!
37 | 218554062-Uthali UZR-Uthali GC Rd. | [13 empty] | 0 | #DIV/0!
38 | 218554068-Periodic Maintenance of Anantapur UZR-Pankahat Road Ch. 00m-3310m | KDRIDP/Chua/M-19/2017-18 | 3.31 | 0 | 0 | 58.35 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 52.52 | 25% | 2018-08-29 |  |  | 0 | 0%
Total |  |  | 49.125 | 0 | 0 | 871.868 |  |  |  | 784.71 | 49% |  | 230.728 | 252.55 | -21.822 | 32.18%
GC-Hat
Alamdanga
1 | Construction of Hardi Market Growth Center | KDRIDP/Chua/GC-22/2017-18 | 0 | 0 | 1 | 20.8 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.78 | 80% | 2018-12-24 |  | 12 | -12 | 57.75%
Jibonnagar
2 | Construction of Raypur Market Growth Center | KDRIDP/Chua/GC-23/2017-18 | 0 | 0 | 1 | 20.07 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.05 | 0% | 2018-12-28 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 2 | 40.87 |  |  |  | 40.83 | 40% |  | 0 | 12 | -12 | 29.39%
Landing/ Riverghat
Alamdanga
1 | RCC Ghatla at Kumar River | KDRIDP/Khul/ G-16/2017-18 | 0 | 0 | 1 | 30.28 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 30.267 | 10% | 2018-12-24 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 1 | 30.28 |  |  |  | 30.267 | 10% |  | 0 | 0 | 0 | 0%
Tree Plantation
Chuadanga Sadar
1 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Alamdanga
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Damurhuda
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Jibonnagar
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 132.164 | 0 | 3 | 6203.953 |  |  |  | 4641.766 | 30.74% |  | 668.264 | 1861.996 | -1193.732 | 40.11%
|  |  | 132.164 | 0 | 3 | 6203.953 |  |  |  | 4641.766 | 23.69% |  | 668.264 | 1861.996 | -1193.732 | 40.11%

## Chuadanga Sadar
Chuadanga Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 218233002-(a) Improvement of Dingadah Shankarchandra UP Makaldanga-Doster Hat road by BC Ch 6820-7735m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 7165m on same road. Salvage Amount TK 53178.00 | KDRIDP/Chua/W-05/2016-17 | 0.915 | 0 | 0 | 53.24 | 2017-05-22 | M/S Saiful Hasan Joarder | 2017-07-09 | 47.92 | 65% | 2018-04-11 | 0 | 27.344 | -27.344 | 57.06% | 0
2 | 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 00-25m Ch 70-258m & Ch 680-1400m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 740m 775m 858m & 1173m on The same road. Salvage Amount TK.589357.00 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 1800-5100m Part-B.2 Construction of 1no Size 2.00x1.60m Box Culvert at Ch 4806m Part-B.3 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2396m & 3311m on The same road. Salvage Amount TK.1785054.00 | KDRIDP/Chua/W-39/2017-18 | 4.233 | 0 | 0 | 291.45 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 218233010-Titudaho UP-Sarabaria-Sujatpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
4 | 218234013-(a) Improvement of Shamvonagar-Shahebnagar road Ch - 910m-2410m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1390m & 2250m. Salvage-929613.00 | KDRIDP/Chua/W-16/2016-17 | 1.5 | 0 | 0 | 90.6 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 81.535 | 60% | 2018-06-19 | 0 | 38.067 | -38.067 | 46.69% | 0
5 | 218234013-Improvement of Shambunagar-Shahebnagor road Ch 2410-3410m Part-B.2 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2503m & 2674m on The same road. Salvage Amount TK.785762.00 | KDRIDP/Chua/W-38/2017-18 | 1 | 0 | 0 | 64.61 | 2018-05-10 | Md. Babul Mia | 2018-06-12 | 61.38 | 0% | 0 | 0 | 0 | 0 | 0% | 0
| 218234020-Improvement of Nehalpur GCCR-Krishnopur road Ch 1000-1992m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 11105m 1362m 1583m & 1940m on The same road. |  | 0.992 | 0 | 0 | 65.33 |  |  |  | 62.06 |  |  | 0 | 0 | 0 | 0% | 0
6 | 218234015-Bhultia R&H-Kharagoda Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasar road Ch - 1500m-3000m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1824m & 2140m. | KDRIDP/Chua/W-15/2016-17 | 1.5 | 0 | 0 | 84.82 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 76.335 | 70% | 2018-06-19 | 0 | 44.393 | -44.393 | 58.16% | 0
8 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasha road by BC Ch 3000-3395m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 3100m. Salvage Amount TK 262371.00 | KDRIDP/Chua/W-07/2016-17 | 0.395 | 0 | 0 | 27.87 | 2017-05-22 | M/S Shahana Construction | 2017-07-03 | 25.08 | 100% | 2018-04-06 | 25.07 | 25.074 | -0.004 | 99.98% | Final
9 | 218234040-Badargong R&H-Ashananda pur bazar Via Kotubpur Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 218234042-Chhoto Salua - Jrishnogar bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218234049-(a) Improvement of Bhultia R&H-Tiorbila road by BC Ch 1310-2332m (b) Construction of 1no U-drain Culvert 625x600mm at Ch 2140m. Salvage Amount TK 143978.00 | KDRIDP/Chua/W-08/2016-17 | 1.022 | 0 | 0 | 57.85 | 2017-05-22 | Md.Ali Reza | 2017-06-13 | 52.066 | 70% | 2018-03-17 | 52.066 | 52.066 | 0 | 100% | Final
12 | 218234049-Improvement of Bhultia R&H-Tiorbila road Ch 2332-3445m | KDRIDP/Chua/W-37/2017-18 | 1.113 | 0 | 0 | 68.6 | 2018-05-10 | M/S Padma Traders | 2018-06-12 | 65.17 | 0% | 2019-03-06 | 0 | 0 | 0 | 0% | 0
| 218235011-Improvement of Subdia R&H-Baliakandi road Ch 820-1265m Salvage Amount TK.479973.00 |  | 0.445 | 0 | 0 | 27.856 | 0 |  |  | 26.46 |  |  | 0 | 0 | 0 | 0% | 0
13 | 218235021-Improvement of Dehi-Darsana road Ch 1750-2138m Part-A.2 Construction of 1no Size 0.625mx0.600m U-Type Drain Culvert at Ch 1969m on The same road. | KDRIDP/Chua/W-41/2017-18 | 0.388 | 0 | 0 | 26.23 | 2018-05-10 | Md. Babul Akter | 2018-06-12 | 24.92 | 0% | 2019-03-06 | 0 | 0 | 0 | 0% | 0
| 218235028-Improvement of Makaldanga-Srikele road Ch 970-3265m Part-B.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 1222m 2274m 2453m & 3115m on The same road. Salvage Amount TK.441147.00 |  | 2.295 | 0 | 0 | 148.606 |  |  |  | 141.176 |  |  | 0 | 0 | 0 | 0% | 0
14 | 218235041-(a) Improvement of Batikadanga-Sujayetpur road by BC Ch 1368-2000m (b) Construction of 2 nos U-Drain Culvert 625x600mm at Ch 1398 & 1603m | KDRIDP/Chua/W-06/2016-17 | 0.632 | 0 | 0 | 39.27 | 2017-05-22 | M/S. R. M. Bricks | 2017-07-03 | 35.35 | 100% | 2018-04-06 | 35.347 | 35.347 | 0 | 99.99% | Final
15 | 218235057-(a) Improvement of Natun Bhanderdah-Basu Bhanderdah-Bhanderdah-Jugirhuda road Ch - 4575m-6200m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 4910m & 5225m. Salvage-414736.00 | KDRIDP/Chua/W-27/2017-18 | 1.625 | 0 | 0 | 107.36 | 2018-05-28 | M/S Nitu Traders | 0 | 101.99 | 0% | 0 | 0 | 0 | 0 | 0% | NOA ISSUED
16 | 218235139-(a) Improvement of Akondobaria Azizuler House-Gunonpara Hudar Bari road by BC Ch 00-1500m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 400 and 770m on same road. Salvage Amount TK 113311.00 | KDRIDP/Chua/W-02/2016-17 | 1.5 | 0 | 0 | 84.8 | 2017-05-15 | Md.Bokhtier Uddin | 2017-06-06 | 84.58 | 25% | 2018-04-09 | 0 | 0 | 0 | 0% | 0
17 | 218235100-Alukdia Shead Member house-Rabbani Mondol house via Huchokpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road by BC Ch 00-2000m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 28 730 and 1782m on same road. Salvage 3746786 | KDRIDP/Chua/W-01/2016-17 | 2 | 0 | 0 | 118.1 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 118.09 | 70% | 2018-04-07 | 0 | 78.211 | -78.211 | 66.23% | 0
19 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road Ch -2000m-3215m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 2328m 2555m & 2812m same road under Chuadanga Sadar Upazila in Chuadanga District. Salvage 1881928 | KDRIDP/Chua/W-14/2016-17 | 1.22 | 0 | 0 | 76.07 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 68.459 | 70% | 2018-06-19 | 0 | 43.367 | -43.367 | 63.35% | 0
Improvement of Village Road by HBB
20 | 218235019-Akandabaria bazar-Chandpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
21 | 218234002-Hakita RH-Hatikata Mazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 218234004-Periodic Maintenance of Nilmoniganj-Kulchara more road Ch. 00m-2615m | KDRIDP/Chua/M-07/2017-18 | 2.615 | 0 | 0 | 52.17 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.95 | 10% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
23 | 218234034-Jafarpur-Hanur Baradi Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 218234036-Periodic Maintenance of Chuadanga-Makaldanga road Ch. 3800m-5250m | KDRIDP/Chua/M-08/2017-18 | 1.45 | 0 | 0 | 26.995 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 24.3 | 100% | 2018-08-29 | 24.286 | 24.29 | -0.004 | 99.96% | Final
25 | 218234037-Periodic Maintenance of Joyrampur-Chuadanga road Ch. 3730m-8000m. | KDRIDP/Chua/M-09/2017-18 | 4.27 | 0 | 0 | 73.79 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 66.41 | 100% | 2018-08-29 | 57.77 | 57.77 | 0 | 86.99% | Final
26 | 218234040-Badargong R&H -Ashana ndapur Bazar via Kotubpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 218234050-Alukdia UP-Khadimpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 218234051-Periodic Maintenance of 5Mils R&H-Balshapur via Harukadi Road Ch. 00m-4190m | KDRIDP/Chua/M-10/2017-18 | 4.19 | 0 | 0 | 72.77 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 65.49 | 10% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
29 | 218234053-Periodic Maintenance of Titudah UP-Gopalnagar Road Ch. 00m-1050m | KDRIDP/Chua/M-11/2017-18 | 1.05 | 0 | 0 | 16.446 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 14.8 | 10% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
30 | 218235027-Makaldanga- Dinnathpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
31 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 36.35 | 0 | 0 | 1674.833 |  |  |  | 1290.521 | 27.74% |  | 194.539 | 425.929 | -231.39 | 33%

## Alamdanga
Alamdanga
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 218072006-Bondabil R&H-Durlavpur-Hardi-Mirpur (Alamdanga Portion) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 218072014-(a) Improvement of Goldari GC-Nilmonigonj Alamdanga Portion road by BC Ch 00-2740m (b) Construction of 6 nos 625x600mm U-Type Drian Culvert at Ch 8 360 720 1510 1820 and 2578m on same road. Salvage Amount TK 510471.00 | KDRIDP/Chua/W-03/2016-17 | 2.74 | 0 | 0 | 202.05 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-11 | 202.03 | 70% | 2018-04-14 | 0 | 133.34 | -133.34 | 66% | 0
Improvement of Union Road by BC
3 | 218073003-(a) Improvement of Baradi Up-Morebhanga Hat.road Ch -4250m -6704m & 8222-8835 (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 4310, 5355, 5755 & 8468m same road under Alamdanga Upazila in Chuadanga District. Salvage-1526030.00 | KDRIDP/Chua/W-32/2017-18 | 3.067 | 0 | 0 | 204.45 | 2018-02-28 | RAB-RC (PVT) Limited-MS Shahana Construction Md. Mejanur Rahman | 2018-04-15 | 184 | 70% | 2019-01-16 | 0 | 98.957 | -98.957 | 53.78% | 0
4 | 218073007-Belgachi UP-Ghosbiala Hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 218073015-(A) Improvement of Belgachi UP-Jehala UP road Ch 2100m-5260m (B) Construction of 2Nos 2.00mx2.00m RCC Box Culvert at Ch 2604 & 4425m (C) Construction of 1No 1.00mx1.00m RCC Box Culvert at Ch 3644m D Construction of 11 nos 0.600mx0.625m U-Type Drain Culvert at Ch2300m, 2410m, 2624m, 2742m, 2975m, 3530m, 3612m, 3826m, 4332m, 4666m & 5240m. Salvage Amount TK.740657.00 | KDRIDP/Chua/W-35/2017-18 | 3.16 | 0 | 0 | 230.507 | 2018-05-10 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 218073017-(A) Improvement of Ailhas UP-Loxmipur Hat road Ch 750m-2650m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 2468m (C) Construction of 7 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1275m, 1522m, 1633m, 1923m, 2000m, 2108m & 2635m on The same road | KDRIDP/Chua/W-36/2017-18 | 1.9 | 0 | 0 | 131.037 | 2018-05-07 | Md. Afzalul Haque | 2018-06-12 | 124.48 | 0% | 2019-03-17 | 0 | 0 | 0 | 0% | 0
7 | 218073025-(a) Improvement of Jehala UP-Kumari UP road by BC Ch 2250-2484m 2934-3540m 3650-4675m5208-7383m 7583-7977m and 8727-9111m (b) Construction of 12 nos 625x600mm U-Type Drian Culvert at Ch 3268 3379 3418 3828 3888 3936 6025 6170 6230 6375 6705 and 8834m on same road. Salvage Amount TK 904869.00 | KDRIDP/Chua/W-04/2016-17 | 4.818 | 0 | 0 | 295.3 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 295.16 | 70% | 2018-04-07 | 0 | 198.052 | -198.052 | 67.1% | 0
8 | 218073028-Part-A.1 Improvement of Alamdanga-Nagdah UP Office via Damas Kedernagar Road Ch 1573-4755m & Ch 5535-7512m Part-A.2 Construction of 2nos Size 1.00x1.00m Box Culvert at Ch 2098 & 4104m Part-A.3 Construction of 11nos Size 0.600mx0.625m U-Type Drain Culvert at Ch 1588m 1969m 2520m 2850m 4650m 5233m 5339m 5837m 5954m 6110m & 6318m on The same road. Salvage Amount TK.2328406.00. | KDRIDP/Chua/W-42/2017-18 | 5.159 | 0 | 0 | 328.115 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 218073021-Bhangabaria UP-Bogadi hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
10 | 218074004-Improvement of Faridpur-Damos road by BC at Ch: 00-3060m. Salvage Amount TK. 544625.00. | KDRIDP/Chua/W-44/2017-18 | 3.06 | 0 | 0 | 199.799 | 2018-07-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218074010-Ailhas - Sonatonpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 218074022-Potimari Bottala - Belgech UP via Kadarnagar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 218075016-(a) Improvement of MochaiNagar-Shalikha Ch - 00m -1244m & 2200-3290m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 235, 273, 2225, 2311, 2700 & 2936 m. Salvage-4194651.00 | KDRIDP/Chua/W-33/2017-18 | 2.334 | 0 | 0 | 181.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 163.725 | 0% | 2019-02-03 | 0 | 0 | 0 | 0% | 0
14 | 218075027-(A) Improvement of Shampur bridge-Alamdanga Rail gate road Ch 1140-3370m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 275m ( C) Construction of 6 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1990m, 2028m, 2182m, 2672m, 2790m & 3068m. Salvage Amount TK.515428.00. | KDRIDP/Chua/W-34/2017-18 | 2.23 | 0 | 0 | 138.98 | 2018-05-07 | R.F.M Construction | 2018-06-07 | 132.03 | 0% | 2019-03-12 | 0 | 0 | 0 | 0% | 0
15 | 218075030-Pardurgapur-Digholdanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 218075031-(a) Improvement of Kachikata Bridge-Baradi road Ch - 500m -2635m (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 547, 1048, 1342m & 2112m. Salvage-23000.00 | KDRIDP/Chua/W-30/2017-18 | 2.135 | 0 | 0 | 134.19 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 120.77 | 10% | 2019-02-03 | 0 | 0 | 0 | 0% | 0
17 | 218075032-Madarhuda - Tamaltala - Jehala UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 218075070-Improvement of Paikpara Math road by BC at Ch 1300-2000m | KDRIDP/Chua/W-45/2017-18 | 0.7 | 0 | 0 | 47.61 | 2018-07-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 218075186-Improvement of Par Laximpur-Kodamtola Allas Bazar road by BC at Ch 00-1174m. |  | 1.174 | 0 | 0 | 77.42 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | 0
19 | 218075155-Jehale UP - Munshigong Poshu hat via Gorgori Asrayon Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 218075201-Chitlamore road - Panchkomlapur road via Aliatnagar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 218075213-(a) Improvement of Jehala Mohon Master house - Matpara Mosque - Gorchapra Shaid Mamber houseroad Ch - 120m -1450m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 250, 488, 810, 1061, 1130 & 1227m same road under Alamdanga Upazila in Chuadanga District. Salvage-299944.00 | KDRIDP/Chua/W-31/2017-18 | 1.33 | 0 | 0 | 88.85 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 79.968 | 40% | 2019-02-03 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by HBB
22 | 218075047-Bokshipur-Bhodhua Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 218075147-Boksipur Moor-Maju Bridge via Modhppur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
24 | 218073033-Const. of RCC Bridge on Bhangbaria UP Office -Udaypurhat via Bhshbaria Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 218073018-Const. of RCC Bridge on Gangni UP- Baradi UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
26 | 218072012-Munshigonj- Asmankhali GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 218073007-Belgachi UP-Ghosbiala hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 218073010-Baradi UP-Natidangahat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 218073028-Alamdanga-Nagdah UP Office via Damas, Kedernagar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 218074010-Periodic Maintenance of Nagdah Sonatonpur road Ch. 00m-1250m | KDRIDP/Chua/M-03/2017-18 | 1.25 | 0 | 0 | 20.465 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.42 | 100% | 2018-08-29 | 18.42 | 18.42 | 0 | 100% | Final
31 | 218074012-Paikpara-Srimrampur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 218074013-Periodic Maintenance of Hakimpur-Toirbila road Ch. 00m-2550m | KDRIDP/Chua/M-04/2017-18 | 2.55 | 0 | 0 | 51.905 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.71 | 100% | 2018-08-29 | 46.699 | 46.7 | -0.001 | 99.98% | Final
33 | 218074017-Periodic Maintenance of Bademaju-Binadpur R&H road Ch. 00m-1120m. | KDRIDP/Chua/M-05/2017-18 | 1.12 | 0 | 0 | 29.776 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 26.8 | 100% | 2018-08-29 | 26.79 | 26.79 | 0 | 99.96% | Final
34 | 218074019-Periodic Maintenance of Kayradanga FRB-Gokulkhali GC road. Ch 00m-2040m | KDRIDP/Chua/M-01/2017-18 | 2.04 | 0 | 0 | 25.43 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 22.89 | 20% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
35 | 218074026-Periodic Maintenance of Gobindhopur-Kashipur via Faridpur road Ch. 00m-1700m. | KDRIDP/Chua/M-06/2017-18 | 1.7 | 0 | 0 | 38.76 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 34.89 | 0% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
36 | 218074029-Periodic Maintenance of Ruhitanpur Hat-Kulpala Ch. 00m-2720m | KDRIDP/Chua/M-02/2017-18 | 2.72 | 0 | 0 | 47.07 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 42.37 | 0% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
37 | 218075016-Mochainagar-Shalikha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
38 | Construction of Hardi Market Growth Center | KDRIDP/Chua/GC-22/2017-18 | 0 | 0 | 1 | 20.8 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.78 | 80% | 2018-12-24 | 0 | 12 | -12 | 57.75% | 0
Landing/ Riverghat
39 | RCC Ghatla at Kumar River | KDRIDP/Khul/ G-16/2017-18 | 0 | 0 | 1 | 30.28 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 30.267 | 10% | 2018-12-24 | 0 | 0 | 0 | 0% | 0
Tree Plantation
40 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 45.187 | 0 | 2 | 2524.714 |  |  |  | 1545.29 | 16.75% |  | 91.909 | 534.259 | -442.35 | 34.57%

## Damurhuda
Damurhuda
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 218312008-Improvement of Damurhuda GC-Golaidari RHD road Ch 7850-9360m. | KDRIDP/Chua/W-25/2016-17 | 1.51 | 0 | 0 | 100.92 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 90.83 | 70% | 2018-07-11 | 0 | 60.591 | -60.591 | 66.71% | 0
2 | 218312006-Improvement of Memnagar RHD-Karpashdanga G.C via Buichitala Ch 16670-17800m. Salvage Amount TK. 31050.00 | KDRIDP/Chua/W-24/2016-17 | 1.13 | 0 | 0 | 80.18 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 72.16 | 70% | 2018-07-11 | 0 | 56.561 | -56.561 | 78.38% | 0
Improvement of Union Road by BC
3 | 218313002-Gobindahuda Hat-Karpasdanga UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC (Ch 12257-13600m). Salvage Amount TK 24740.00 | KDRIDP/Chua/W-10/2016-17 | 1.343 | 0 | 0 | 67.49 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 60.74 | 70% | 2018-04-11 | 0 | 36.833 | -36.833 | 60.64% | 0
5 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC Ch 10957-12257m. | KDRIDP/Chua/W-12/2016-17 | 1.3 | 0 | 0 | 71.36 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 64.22 | 70% | 2018-04-11 | 0 | 41.513 | -41.513 | 64.64% | 0
6 | 218313004-Parkrisnopur Madna UP-Kuralgachhi UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 218314012-a) Improvement of Kushaghata R&H-Purapara road Ch 514-1120m (b) Construction of 2 nos Pipe Culvert at Ch 915 & 1100m. Salvage Amount TK. 160525.00 | KDRIDP/Chua/W-26/2016-17 | 0.606 | 0 | 0 | 33.54 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 30.18 | 100% | 2018-07-11 | 30.175 | 30.175 | 0 | 99.98% | Final
7 | 218314016-Improvement of Dugdugi Family Planing Center-Gobindapur road by BC Ch 00-1640 & 3273-3333m. Salvage Amount TK 209026.00 | KDRIDP/Chua/W-11/2016-17 | 1.7 | 0 | 0 | 93.49 | 2017-05-22 | Jahirul Limited | 2017-07-09 | 84.14 | 100% | 2018-04-11 | 84.14 | 84.14 | 0 | 100% | Final
8 | 218314017-Hawli Eidgah-Shaikpara R&H Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 218314019-Javrampur Battala Parimary School -Uktya Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 218314032-Parkisnopur-Jhajadanga Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218314040-Pirpur Kullah-Shihnagar via Boyra Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 218314053-(a) Improvement of Chandra FRB-Kanidanga road by BC Ch 4733-6233m (b) Construction of 2 nos U-Tyup Drain Culvert at Ch 5922 & 5788m | KDRIDP/Chua/W-09/2016-17 | 1.5 | 0 | 0 | 84.25 | 2017-05-22 | Md. Shamshodwha Malick | 2017-07-09 | 75.83 | 70% | 2018-04-11 | 0 | 53.712 | -53.712 | 70.83% | 0
13 | 218314054-Jhapjhapi bridge-Hogoldanga FRB Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 218314006-Jhoragacha-Kalabaria Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
15 | 248314073-Chandrabass-Satiantala Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 248315080-Laxmipur Hat Mosque Kana Pukorlkor via Dhakian para Graveyard Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
17 | 218313009-Const. of RCC Bridge on Par Damurhdua to Karpasdanga UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 218314059-Const. of RCC Bridge on Kanaidanga FRB-Kunia Ferryghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
19 | 218312014-Darsana GC- Madna-Sada bari -Pirpukullah -Karpashdanga GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 218314002-Periodic Maintenance of Gopalpur Primary School-Daliarpur Road Ch. 00m-1095m. | KDRIDP/Chua/M-12/2017-18 | 1.095 | 0 | 0 | 18.23 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 16.41 | 0% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
21 | 218314015-Loknathpur R&H-Darsona Dingadah Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 218314019-Periodic Maintenance of Joyrampur Battala School-Uktya Road Ch. 00m-1740m | KDRIDP/Chua/M-13/2017-18 | 1.74 | 0 | 0 | 31.676 | 2017-12-27 | Liton Traders | 2018-02-19 | 28.51 | 0% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
23 | 218314033-Periodic Maintenance of Modna-Hoybadpur more Road Ch. 00m-900m | KDRIDP/Chua/M-14/2017-18 | 0.9 | 0 | 0 | 14.825 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 13.34 | 100% | 2018-08-29 | 13.34 | 13.34 | 0 | 100% | Final
24 | 218314045-Damurhuda Brac more-Upazila more Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 218314049-Periodic Maintenance of Baroboldia Bazar-Chindipur via Sarabaria Road Ch. 3380m-5125m. | KDRIDP/Chua/M-15/2017-18 | 1.745 | 0 | 0 | 28.15 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 25.34 | 100% | 2018-08-29 | 25.337 | 25.34 | -0.003 | 100% | Final
26 | 218314071-Periodic Maintenance of Talsari R&H-Horirampur Road Ch. 1120m-2690m. | KDRIDP/Chua/M-16/2017-18 | 1.57 | 0 | 0 | 20.11 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.1 | 100% | 2018-08-29 | 18.086 | 18.09 | -0.004 | 99.94% | Final
27 | 218314084-Periodic Maintenance of Buinchatala Tematha-Aramdanga via Thakurpur Road Part-A Ch. 00m-1940m & Part-B Ch. 8840-1189m | KDRIDP/Chua/M-17/2017-18 | 4.99 | 0 | 0 | 113.27 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 101.95 | 20% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
Tree Plantation
28 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 21.129 | 0 | 0 | 757.491 |  |  |  | 681.75 | 30% |  | 171.078 | 420.295 | -249.217 | 61.65%

## Jibonnagar
Jibonnagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 218552009-a) Improvement of Uthali R&H Mollabari-Uthali GC road Ch 00-1140m (b) Construction of 1 nos U-Type Drain Culvert size 625x600mm at Ch 40.00m on same road under Jibannagar Upazila in Chuadanga District Salvage Amount TK. 1723642.00 | KDRIDP/Chua/W-18/2016-17 | 1.14 | 0 | 0 | 82.45 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 74.2 | 60% | 2018-06-19 | 74.13 | 74.13 | 0 | 99.91% | Final
Improvement of Union Road by BC
2 | 218553001-Jibannagar-Shimanta UP-Benipur Hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 218553004-Improvement of Shimanta UP-Goyespur-Dhopakhali Hat road Ch 5510-7960m. Salvage Amount TK. 537215.00 | KDRIDP/Chua/W-22/2016-17 | 2.45 | 0 | 0 | 134.99 | 2017-08-24 | RAB-RC (PVT) Limited | 2017-10-09 | 121.49 | 65% | 2018-07-05 | 0 | 74.385 | -74.385 | 61.23% | 0
4 | 218553007-Barbhanga R&H-Sutiahat-Hashadah UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 218553008-Shimanto UP- Goyespur-Dhapakhalihat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 218553009-Simanto UP-Korotoya-Horihornagar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 218553013-Raypur UP-Khalispur GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 218553014-Andulbaria UP - Begumpur Hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 218554001-Purandupur - Nischatapur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 218554002-Panarasoti Bhanga Bridge-Tarinibash Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218554004-Narayanpur-Gangadaspur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 218554012-a) Improvement of Krishnopur more-Maerudah hat-Shebkhali road Ch 2420-3220m (b) Construction of 1 no RCC Box Culvert size 2.00x2.60m at Ch 2713m (c) Construction of 2 Nos U Type Drain Culvert size 625 x 600 m at Ch 2600 and 2947m. Salvage Amount TK. 597943.00 | KDRIDP/Chua/W-23/2016-17 | 0.8 | 0 | 0 | 57.51 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 51.76 | 82% | 2018-07-11 | 0 | 41.56 | -41.56 | 80.29% | 0
13 | 218554014-Balihuda-Natun Chakla Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 218554017-a) Improvement of Tutulia BGB camp-Rakhal Shah Mazar road Ch 1800-4150m (b) Construction of 3 nos U-Drain Culvert at Ch 2730, 3300 & 3400m. Salvage Amount TK. 560988.00 | KDRIDP/Chua/W-19/2016-17 | 2.35 | 0 | 0 | 133.02 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 119.72 | 15% | 2018-06-19 | 0 | 0 | 0 | 0% | 0
15 | 218554023 a) Improvement of Muktarpur-Shahebkhali road via Katapol Chakla road Ch 2050-3810m (b) Construction of 1 no U-Type Drain Culvert size 625x600mm at Ch 3271m. Salvage Amount TK.106683.00 | KDRIDP/Chua/W-21/2016-17 | 1.76 | 0 | 0 | 97.48 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 87.73 | 76% | 2018-07-11 | 0 | 66.28 | -66.28 | 75.55% | 0
16 | 218554031- A) Improvement of Goyespur-BGB Camp-Changkhali road Ch 4140-6542m B) Construction of 4 nos U-Type Drain Culvert at Ch 4150, 4650,5800 & 6310 m. Salvage Amount TK.142098.00 | KDRIDP/Chua/W-29/2017-18 | 2.402 | 0 | 0 | 150.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-17 | 135.83 | 0% | 2019-02-17 | 0 | 0 | 0 | 0% | 0
17 | 218554035-Sontoshpur R&H-Rajapur UZR Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 218554037-Improvement of Daulatgong GC-Benipur hat road at ch 6140-8900m. Salvage Amount TK. 280855.00 | KDRIDP/Chua/W-20/2016-17 | 2.76 | 0 | 0 | 151.79 | 2017-07-25 | M/S. JAKAULLAH & BROTHERS | 2017-08-27 | 136.608 | 100% | 2018-06-02 | 136.608 | 136.608 | 0 | 100% | Final
19 | 218554050-a) Improvement of Uthali R&H-Dhopakhali Hat road Ch 1425-3981m (b) Construction of 2 nos 1.00x1.60m Box Culvert at CH 2359 and 3085m (c) Construction of 1 No U-Drain Culvert at Ch 2001m. Salvage Amount TK. 2029785.00 | KDRIDP/Chua/W-17/2016-17 | 2.556 | 0 | 0 | 150.77 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 135.687 | 70% | 2018-09-18 | 0 | 66.74 | -66.74 | 49.19% | 0
20 | 218555003-A) Improvement of Annantopur Mosque-Mondertola road Ch 00m-1150m B) Construction of 2 nos U-Type Drain Culvert size 600x625mm at Ch 3.00 & 295m. Salvage Amount TK.333332.00 | KDRIDP/Chua/W-28/2017-18 | 1.15 | 0 | 0 | 77.885 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 70.1 | 10% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
Maintenance
21 | 218553010-Andulbaria UP - Grisnagar Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 218554043-Periodic Maintenance of Balihuda UZR-Raypur Bazar Road Ch. 00m-2400m | KDRIDP/Chua/M-20/2017-18 | 2.4 | 0 | 0 | 38.87 | 2017-12-28 | M/S. Khandaker Shahin Ahmed | 2018-02-19 | 34.98 | 15% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
23 | 218554047-Bokundia R&H - Minajpur hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 218554054-Periodic Maintenance of Piaratala R&H-Kasipur Hat Road Ch. 00m-6420m. | KDRIDP/Chua/M-18/2017-18 | 6.42 | 0 | 0 | 92.81 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 83.53 | 70% | 2018-08-29 | 0 | 21.81 | -21.81 | 26.11% | 0
25 | 218554058-Banka UP-Dattanagar Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 218554062-Uthali UZR-Uthali GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 218554068-Periodic Maintenance of Anantapur UZR-Pankahat Road Ch. 00m-3310m | KDRIDP/Chua/M-19/2017-18 | 3.31 | 0 | 0 | 58.35 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 52.52 | 25% | 2018-08-29 | 0 | 0 | 0 | 0% | 0
GC-Hat
28 | Construction of Raypur Market Growth Center | KDRIDP/Chua/GC-23/2017-18 | 0 | 0 | 1 | 20.07 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.05 | 0% | 2018-12-28 | 0 | 0 | 0 | 0% | 0
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 29.498 | 0 | 1 | 1246.915 |  |  |  | 1124.205 | 20.28% |  | 210.738 | 481.513 | -270.775 | 42.83%

## Summary
CHUADANGA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 4 | 4 | 6.52 | 0 | 0 | 439.22 | 324.622 | 67.5% | 73.91%
Union Road by BC | 10 | 6 | 28.345 | 0 | 0 | 898.01 | 477.084 | 58.57% | 53.13%
Village Road by BC | 28 | 24 | 48.174 | 0 | 0 | 2448.729 | 795.74 | 51.58% | 32.5%
Village Road by HBB |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Upazila Road | [9 empty] | N/A
Bridge on Union Road/Village Road |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Maintenance | 20 | 20 | 49.125 | 0 | 0 | 784.71 | 252.55 | 49% | 32.18%
GC-Hat | 2 | 2 | 0 | 0 | 2 | 40.83 | 12 | 40% | 29.39%
Landing/ Riverghat | 1 | 1 | 0 | 0 | 1 | 30.267 | 0 | 10% | 0%
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 65 | 57 | 132.164 | 0 | 3 | 4641.766 | 1861.996 | 30.74% | 40.11%