## Meherpur
MEHERPUR
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Gangni
1 | 257472008-Improvement of Bamundi GC-Hatboalia GC via Chatian Road Ch. 8898-9200m | KDRIDP/Meher/W-17/2017-18 | 0.302 | 0 | 0 | 20.42 | 2017-08-29 | Md. Shaharin Haque Malik | 2017-10-22 | 20.01 | 100% | 2017-12-17 | 20.01 | 20.01 | 0 | 100% | Final
Mujibnagar
2 | 257882008-Anandhobas GC-Jaganathpur GC via Ratanpur (Muzibnagar Part) road. | KDRIDP/Meher/W-08/2016-17 | 0.67 | 0 | 0 | 46.11 | 2017-03-08 | M/S. Jony Enterprise | 2017-10-09 | 42.376 | 100% | 2018-09-04 | 42.363 | 42.363 | 0 | 99.97% | Final
3 | 257882009-Improvement of Dariapur GC- Kaderganj R&H via KalitolaRamnagar Road Ch. 332-367m & 1215-1527m | KDRIDP/Meher/W-02/2016-17 | 0.347 | 0 | 0 | 19.18 | 2017-11-05 | M/S. Jony Enterprise | 2017-05-31 | 19.07 | 100% | 2017-06-19 | 19.07 | 19.07 | 0 | 100% | Final Bill Salvage Cost Tk. 395191.00
Meherpur Sadar
4 | 257872010-Improvement of Kathalpota RHD-Vogirothpur GC Road Ch. 2600-2900m | KDRIDP/Meher/W-32/2017-18 | 0.3 | 0 | 0 | 29.18 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 27.72 | 25% | 2019-03-31 | 25.75 | 25.747 | 0.003 | 92.88% | Final
5 | 257872011-A) Improvement of Chandpur RHD-Sholmari GC Via Hitimpara Road. Ch.00-734m & Ch. 5000-6082m under Sadar Upazila District Meherpur. B) Construction of 3nos U-Type Drain 625mmx600mm on Chandpur RHD-Sholmari GC Via Hitimpara Road. Ch. 5350m 5550m & 5750m. | KDRIDP/Meher/W-03/2016-17 | 1.816 | 0 | 0 | 123.01 | 2017-08-06 | M/S. Jony Enterprise | 2017-07-16 | 121.63 | 100% | 2017-12-21 | 120.85 | 120.85 | 0 | 99.36% | Final Bill Salvage Cost Tk. 3433427.00
Total |  |  | 3.435 | 0 | 0 | 237.9 |  |  |  | 230.806 | 85% |  | 228.043 | 228.04 | 0.003 | 98.8%
Improvement of Union Road by BC
Mujibnagar
1 | 257883003-Improvement of Mohazonpur UP (Komorpur)-Mohazonpur GC Road. (Ch. 2518-3710m) | KDRIDP/Meher/W-07/2016-17 | 1.192 | 0 | 0 | 65.13 | 2017-03-08 | M/S. Biswas Construction | 2017-10-09 | 58.62 | 100% | 2018-02-27 | 58.617 | 58.617 | 0 | 99.99% | Final
2 | 257883006-Improvement of Komorpur-Gopalpur-Pirozpur UP road (Muzibnagar part). (Ch. 1790-2365m) | KDRIDP/Meher/W-09/2016-17 | 0.575 | 0 | 0 | 32.52 | 2017-03-08 | Jahirul Limited | 2017-10-09 | 29.26 | 100% | 2017-12-03 | 29.25 | 29.25 | 0 | 99.97% | Final
3 | 257883012-Mohajanpur UP- Pirozpur UP via Jadukhali Ghat Road. | [13 empty] | 0 | #DIV/0!
Gangni
4 | 257473001-Improvement of Shaharbati UP-Manikdia Hat via Jorepukur Road Ch. 2760-3467m | KDRIDP/Meher/ W-18/2017-18 | 0.707 | 0 | 0 | 53.03 | 2017-08-29 | Md. Ehsanul Haque | 2017-10-22 | 49.91 | 100% | 2018-04-28 | 49.811 | 49.811 | 0 | 99.8% | Final
5 | 257473004-Improvement of Hijol Baria Hat-Sholotaka UP via Chengara Road Ch. 1670-2559m | KDRIDP/Meher/W-12/2017-18 | 0.889 | 0 | 0 | 58.03 | 2017-08-29 | M/S. Rumana Enterprise | 2017-08-10 | 57.37 | 100% | 2018-05-20 | 56.98 | 56.98 | 0 | 99.32% | Final
6 | 257473011-Improvement of Arrpara Hat -Raipur road via Raipur UP Road Ch. 00-950m & 3923-4200m. Salvage Cost Tk. 2307687.00 | KDRIDP/Meher/W-25/2017-18 | 1.227 | 0 | 0 | 80.079 | 2018-04-06 | M/S ASHRAF TRADERS | 2018-10-07 | 80.039 | 0% | 2019-03-31 |  |  | 0 | 0%
7 | 257473013-Improvement of Dhankhola UP - Koshba bazar via Vatpara Khorempur Road Ch. 1857-2493m & 3191m-4500m | KDRIDP/Meher/ W-16/2017-18 | 1.945 | 0 | 0 | 133.08 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 119.77 | 100% | 2018-04-28 | 119.371 | 119.371 | 0 | 99.67% | Final
8 | 257473016-Improvement of Bhobanipur FRB Hat-Kazipur UP Road Ch. 1587-2309m & 2593-4170m. Salvage Cost Tk. 1051680.00 | KDRIDP/Meher/ W-26/2017-18 | 2.299 | 0 | 0 | 144.776 | 2018-04-06 | M/S ASHRAF TRADERS | 2018-10-07 | 137.537 | 60% | 2019-03-31 |  | 31.66 | -31.66 | 23.02%
9 | 257473019-Improvement of Roypur UP Office Koroigachi -Ashmankhali GC via Elangi Hat Road Ch. 1000-2750m 4171-4945m & 5335-5353m. Salvage Cost Tk. 5690269.00 | KDRIDP/Meher/W-27/2017-18 | 2.542 | 0 | 0 | 176.218 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 184.85 | 50% | 2019-01-03 |  | 88.776 | -88.776 | 48.03%
Meherpur Sadar
10 | 257874068-Improvement of Dindatta Bridge-Aamjhupi UP via Hizuli bazar Road Ch. 1431m-2031m. Salvage Cost Tk. 1474731.00 (257873006-Dindatta Bridge-Aamjhupi UP via Hizuli bazar Road.) | KDRIDP/Meher/W-32/2017-18 | 0.6 | 0 | 0 | 38.89 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 37.896 | 25% | 2019-03-31 | 35.19 | 35.19 | 0 | 92.86% | Final
11 | 257873007-Improvement of Kuthipara- Kulbaria Hat via Kutubpur UP Office Road Ch. 1488-2100m. Salvage Cost TK. 1477447.00 | KDRIDP/Meher/ W-31/2017-18 | 0.612 | 0 | 0 | 41.948 | 2018-07-23 | Md. Nadim Iqbal | 2018-05-09 | 39.851 | 50% | 2019-03-31 | 39.8 | 39.8 | 0 | 99.87% | Final
12 | 257873007-Improvement of Kuthipara- Kulbaria Road via Kutubpur UP Office road by BC at Ch. 2100-4100m | KDRIDP/Meher/ W-33/2018-19 | 2 | 0 | 0 | 141.839 | 2018-05-12 | [9 empty] | Salvage Cost Tk. 4845623.00
13 | 257873013-Mohajonpur UP-Tengramari via Shahebpur-Islampur Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 14.588 | 0 | 0 | 965.54 |  |  |  | 795.103 | 68.5% |  | 389.019 | 509.455 | -120.436 | 64.07%
Improvement of Village Road by BC
Meherpur Sadar
1 | 257874001-Improvement of Bandar RHD -Bhabanandapur Hat Road Ch. 1540m-1655m 2037m-4250m & 4290m-4430m. Salvage Cost Tk. 239064.00. | KDRIDP/Meher/ W-31/ 2017-18 | 2.468 | 0 | 0 | 160.97 | 2018-07-23 | Md. Nadim Iqbal | 2018-05-09 | 152.922 | 50% | 2019-03-31 | 152.76 | 152.76 | 0 | 99.89% | Final
2 | 257874022-Improvement of Hasnabadh UNR-Barshibaria patapuka RHD road by BC at Ch. 00-1300m and 3574-4439m | KDRIDP/Meher/ W-34/2018-19 | 2.165 | 0 | 0 | 161.688 | 2018-05-12 | M/S. Emi Motors | 2019-01-22 | 153.604 | 60% | 2019-06-30 |  |  | 0 | 0% | Salvage Cost Tk. 3353372.00
3 | 257874024-Improvement of Teroghoria Asrayan -Vittermath Road. Ch. 00-2444m. | KDRIDP/Meher/W-22/2017-18 | 2.44 | 0 | 0 | 139.22 | 2017-11-10 | Jahirul Limited | 2017-12-11 | 125.298 | 100% | 2018-04-18 | 125.26 | 125.26 | 0 | 99.97% | Final
4 | 257874032-Improvement of Baliarpur RHD-Roghunathpur UNR Road. Ch.3347-4547m | KDRIDP/Meher/W-04/2016-17 | 1.2 | 0 | 0 | 65.67 | 2017-08-06 | M/S. Biswas Construction | 2017-07-16 | 63.307 | 100% | 2017-12-22 | 63.307 | 63.307 | 0 | 100% | Final
5 | 257874032-Improvement of Baliarpur RHD-Roghunathpur Road Ch. 2314m-3347m | KDRIDP/Meher/W-32/2017-18 | 1.033 | 0 | 0 | 67.757 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 64.369 | 50% | 2019-03-31 | 59.78 | 59.78 | 0 | 92.87% | Final
| 257874047-Improvement of Ragunathpur-Pirojpur bazar Road Ch. 574-1369m. Salvage Cost Tk. 494323.00 | KDRIDP/Meher/W-32/2017-18 | 0.795 | 0 | 0 | 48.357 |  | Md. Hafizur Rahman |  | 45.939 |  |  | 42.66 | 42.66 | 0 | 92.86% | Final
6 | 257874047-Improvement of Ragunathpur-Pirojpur bazaar Road. Ch.1369-2369m | KDRIDP/Meher/W-06/2016-17 | 1 | 0 | 0 | 54.74 | 2017-08-06 | M/S. Rumana Enterprise | 2017-07-09 | 53.37 | 100% | 2017-10-12 | 53.37 | 53.37 | 0 | 100% | Final
7 | 257874040-Improvement of Musurivaza-Jukindha Road. Ch.1450-3100m | KDRIDP/Meher/W-05/2016-17 | 1.65 | 0 | 0 | 91.08 | 2017-08-06 | M/S. Biswas Construction | 2017-07-16 | 87.51 | 100% | 2017-12-21 | 87.51 | 87.51 | 0 | 100% | Final Bill Salvage Cost Tk. 2883802.00
8 | 257874048-Improvement of Rajnagar Golamnabi RHD -Jugindha Hat road Ch. 2701-3378m | KDRIDP/Meher/W-21/2017-18 | 0.677 | 0 | 0 | 37.455 | 2017-11-10 | Jahirul Limited | 2017-12-11 | 33.71 | 100% | 17-5-18 | 33.71 | 33.71 | 0 | 100% | Final
9 | 257875120-Islamnagar-Juginda Rd. | [13 empty] | 0 | #DIV/0!
Mujibnagar
10 | 257884018-Improvement of Dariapur R&H to Dariapur BOP Road. (Ch. 200-2200m) | KDRIDP/Meher/W-10/2016-17 | 2 | 0 | 0 | 111.92 | 2017-03-08 | Jahirul Limited | 2017-10-09 | 100.724 | 100% | 2018-03-31 | 100.724 | 100.724 | 0 | 100% | Final
11 | 257884018-Improvement of Dariapur R&H to Dariapur BOP Road. (Ch. 2200-2800m) | KDRIDP/Meher/ W-29/2017-18 | 0.6 | 0 | 0 | 37.359 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 35.49 | 45% | 2019-01-03 |  | 11.99 | -11.99 | 33.78%
| 257884022-Improvement of Shibpur Ghat-Tangramari via Shibpur hat Road Ch. 485-845m. Salvage Cost Tk. 128997.00. | KDRIDP/Meher/ W-29/2017-18 | 0.36 | 0 | 0 | 21.95 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 20.85 |  |  |  | 7.042 | -7.042 | 33.77%
| 257884027-Improvement of Taranagar BC UZR road - Jagonathpur BOP Road Ch. 1200-2900m. | KDRIDP/Meher/ W-29/2017-18 | 1.7 | 0 | 0 | 107.926 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 102.53 |  |  |  | 34.643 | -34.643 | 33.79%
12 | 257884027-Improvement of Taranagar BC - Jagonathpur BOP Road Ch. 00-1200m | KDRIDP/Meher/W-01/2016-17 | 1.2 | 0 | 0 | 66.16 | 2017-11-05 | Jahirul Limited | 2017-05-24 | 59.54 | 100% | 2017-11-30 | 59.54 | 59.54 | 0 | 100% | Final Salvage Cost Tk. 216051.00
13 | 257884031-Improvement of Mujibnagar BOP to Bhebarpara Bazar via Mujibnagar Shrtisoudo Road Ch. 350-680m. Salvage Cost TK. 31844.00 | KDRIDP/Meher/W-30/2017-18 | 0.33 | 0 | 0 | 20.59 | 2018-04-06 | M/S.Khan Enterprise | 2018-12-07 | 19.56 | 45% | 2019-01-03 |  | 6.046 | -6.046 | 30.91%
| 257884033-Improvement of Gopalpur BC road H/O Mannan Master - Sonapur Road Ch. 1000-1350m. | KDRIDP/Meher/W-30/2017-18 | 0.35 | 0 | 0 | 21.276 | 2018-04-06 | M/S.Khan Enterprise | 2018-12-07 | 20.21 | 45% | 2019-01-03 |  | 6.247 | -6.247 | 30.91%
| 257885008-Improvement of Sonapur Mohir Dhakka Godown-Sutir Math Road Ch. 1615-2805m. | KDRIDP/Meher/W-30/2017-18 | 1.19 | 0 | 0 | 76.259 | 2018-04-06 | M/S.Khan Enterprise | 2018-12-07 | 72.446 | 45% | 2019-01-03 |  | 22.394 | -22.394 | 30.91%
14 | 257884033-Improvement of Gopalpur BC rd. - Sonapur Road(Gopalpur H/O Mannan Master-Sonapur). (Ch. 00-1000m) | KDRIDP/Meher/W-11/2016-17 | 1 | 0 | 0 | 54.87 | 2017-03-08 | Jahirul Limited | 2017-10-09 | 49.38 | 100% | 2018-03-31 |  | 34 | -34 | 68.85%
15 | 257885018-Anandabash FRB-Anandabash JGHS Rd. | [13 empty] | 0 | #DIV/0!
Gangni
16 | 257474010-Improvement of Garadob Kachari-Vatpara Road. Ch. 00-1000m | KDRIDP/Meher/ W-23/2017-18 | 1 | 0 | 0 | 63.28 | 2017-11-14 | Md. Abdul Hannan | 2017-12-18 | 59.4 | 100% | 2018-05-24 | 59.388 | 59.388 | 0 | 99.98% | Salvage Cost Tk. 1890447.00 Final
17 | 257474026-Choktola-Morka bazar via Kashtodah Rd. | [13 empty] | 0 | #DIV/0!
18 | 257474028-Improvement of Terail-Shindurkota via Mahabbotpur Road Ch. 3400-3827m & 4556-5149m | KDRIDP/Meher/ W-15/2017-18 | 1.02 | 0 | 0 | 56.05 | 2017-08-29 | M/S. Rumana Enterprise | 2017-10-22 | 55.15 | 100% | 2018-04-28 | 55.15 | 55.15 | 0 | 100% | Final
19 | 257474057-Improvement of Bashbaria RHD Bazar - Shaharbati Barishar Moure Club Rood Ch. 436-2186m | KDRIDP/Meher/W-13/2017-18 | 1.75 | 0 | 0 | 109.49 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 98.54 | 100% | 2018-04-28 | 98.024 | 98.024 | 0 | 99.48% | Final
20 | 257474059-Improvement of Betbaria Eidgha-Vallege Shihala Ghat Road Ch. 200-810m & 1500-2090m. Salvage Cost Tk. 154886.00 | KDRIDP/Meher/ W-24/2017-18 | 1.2 | 0 | 0 | 84.78 | 2018-02-28 | Jahirul Limited | 2018-04-16 | 76.3 | 100% | 2018-10-22 | 76.277 | 76.277 | 0 | 99.97% | Salvage Cost Tk. 154886.00 Final
21 | 257474055-Improvement of Kumaridanga-Bholadanga bazar road via Kodalkati Road Ch. 1700-2315m. Salvage cost Tk. 1172002.00 | KDRIDP/Meher/ W-28/2017-18 | 0.615 | 0 | 0 | 39.183 | 2018-04-06 | Md. Easin Ali | 2018-07-17 | 37.22 | 100% | 2019-03-31 | 37.05 | 37.05 | 0 | 99.54% | Final
| 257475138-Improvement of Juginda pucca road - Shop of hasem at Azan Road Ch. 00-840m. Salvage Cost Tk. 149443.00 | KDRIDP/Meher/ W-28/2017-18 | 0.84 | 0 | 0 | 54.787 | 2018-04-06 | Md. Easin Ali |  | 52.048 |  |  | 51.81 | 51.81 | 0 | 99.54% | Final
| 257475023-Improvement of Pakuiria-Dhepa Road Ch. 2200-2900m | KDRIDP/Meher/ W-28/2017-18 | 0.7 | 0 | 0 | 43.14 | 2018-04-06 | Md. Easin Ali |  | 40.98 |  |  | 40.79 | 40.79 | 0 | 99.54% | Final
22 | 257475149-Improvement of Garabria Bank - Gangni-Kathuli R&H Road Ch. 00-300m & 885-1590m | KDRIDP/Meher/ W-14/2017-18 | 1.005 | 0 | 0 | 57.4 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 51.66 | 100% | 2018-04-28 | 51.655 | 51.655 | 0 | 99.99% | Final
Total |  |  | 30.288 | 0 | 0 | 1853.357 |  |  |  | 1732.057 | 82.86% |  | 1248.765 | 1371.127 | -122.362 | 79.16%
Construction of Bridge on Upazila Road (7.30m width)
Gangni
1 | 257472006-Const. of RCC Bridge on Bamondi R&H -Pragpur GC via Madhugari ghat Road over Mathabhanga river. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
2 | 257472007-Const. of RCC Bridge on Upazila H/Q (Malshadah) -Kazipur GC- Malshbaria Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Maintenance
Meherpur Sadar
1 | 257873013-Periodic Maintenance of Mohajonpur UP-Tengramari via Shahebpur-Islampur road at Ch. 00-1070m | KDRIDP/Meher/ M-09/2018-19 | 1.07 | 0 | 0 | 11.134 | 2018-11-27 | M/S. Nur Islam Enterprise | 2018-12-24 | 10.577 | 100% | 2019-03-31 | 10.57 | 10.57 | 0 | 99.93% | Final
2 | 257874010-Periodic Maintenance of Bazitpur-Harirumpur Road from Ch. 000m -493m | KDRIDP/Meher/ M-01/2017-18 | 0.493 | 0 | 0 | 5.23 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 5.22 | 100% | 2018-03-28 | 5.215 | 5.215 | 0 | 99.9% | Final
3 | 257874019-Digirpara-Jowbaria Pakurtala Rd. | [13 empty] | 0 | #DIV/0!
4 | 257874022-Periodic Maintenance of Hasanabad-Barshibaria Patapuka road at Ch. 1300-2305m | KDRIDP/Meher/M-10/2018-19 | 1.005 | 0 | 0 | 11.88 | 2018-11-27 | Md. Abdul Hannan | 2019-10-01 | 11.288 | 100% | 2019-01-20 | 11.273 | 11.273 | 0 | 99.87% | Final
5 | 257874062-Sholmari GC.-Meherpur via Rudronagar-Kamdebpur Road. | [13 empty] | 0 | #DIV/0!
Mujibnagar
6 | 257882008-Anandhobas GC-Jaganathpur GC via Ratanpur Rd. | [13 empty] | 0 | #DIV/0!
7 | 257883003-Mohazonpur UP-Mohazonpur GC Rd. | [13 empty] | 0 | #DIV/0!
8 | 257884025-Periodic Maintenance of Kedergong Bazar to Bagoan R&H via Bollovepur graveyard Mission Hospital from Ch. 000m -1466m | KDRIDP/Meher/ M-05/2017-18 | 1.466 | 0 | 0 | 16.33 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 16.25 | 100% | 2018-04-05 | 16.063 | 16.063 | 0 | 98.85% | Final
9 | 257885055-Periodic Maintenance of Baguan RHD Community Clinic-Baguan Jam-E-Mosque UZR Road 000m -1192m | KDRIDP/Meher/ M-08/2017-18 | 1.192 | 0 | 0 | 22.73 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 22.61 | 100% | 2018-04-05 | 22.509 | 22.509 | 0 | 99.55% | Final
10 | 257884036-Kadamtala RHD-UP Office-Dariapur GC & T&T(RHD) Road. | [13 empty] | 0 | #DIV/0!
11 | 257884037-Periodic Maintenance of Gopalnagar RHD-Shibpur Ghat Road 00m -805m | KDRIDP/Meher/ M-06/2017-18 | 0.805 | 0 | 0 | 10.01 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 10 | 100% | 2018-04-05 | 9.928 | 9.928 | 0 | 99.28% | Final
12 | 257884039-Periodic Maintenance of Kedargonj Bazar RHD - Muzibnagar HQ Bhebarpara Bazar via Nazirakona Road Ch. 2415-5297m | KDRIDP/Meher/ M-07/2017-18 | 2.882 | 0 | 0 | 44.67 | 2017-12-21 | M/S. Jony Enterprise | 2018-05-03 | 43.61 | 100% | 2018-05-22 | 43.56 | 43.56 | 0 | 99.89% | Final
Gangni
13 | 257474001-Periodic Maintenance of Garadob Purapara RHD - Juginda Islamnagar Road from Ch. 000m -2000m | KDRIDP/Meher/ M-02/2017-18 | 2 | 0 | 0 | 26.62 | 2017-12-21 | Md. Abdul Hannan | 2017-01-22 | 24.48 | 100% | 2018-04-22 | 24.301 | 24.301 | 0 | 99.27% | Final
14 | 257474053-Maintenance of Akubpur RHD-Mohammodpur Hat Road Ch. 00-1800m | KDRIDP/Meher/ W-19/2017-18 | 1.8 | 0 | 0 | 56.84 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 51.16 | 100% | 2017-10-22 | 51.06 | 51.06 | 0 | 99.8% | Final
15 | 257475016-Maintenance of Hemayatpur-Ruyerkandi Road Ch. 00-1500m | KDRIDP/Meher/ W-20/2017-18 | 1.5 | 0 | 0 | 33.98 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 30.58 | 100% | 2018-02-02 | 30.517 | 30.517 | 0 | 99.79% | Final
16 | 257474023-Periodic Maintenance of Garadav Munshi Zamiruddin Road from Ch. 000m -370m | KDRIDP/Meher/ M-03/2017-18 | 0.37 | 0 | 0 | 9.14 | 2017-12-21 | Md. Abdul Hannan | 2017-01-22 | 8.56 | 100% | 2018-04-20 | 8.55 | 8.55 | 0 | 99.88% | Final
17 | 257475023-Periodic Maintenance of Pakuiria-Dhepa Road from Ch. 000m -1100m | KDRIDP/Meher/ M-04/2017-18 | 1.1 | 0 | 0 | 23.08 | 2017-12-21 | Md. Mofijul Islam | 2017-01-29 | 21.51 | 100% | 2018-06-04 | 21.46 | 21.46 | 0 | 99.77% | Final
18 | 257475004-Shukurkandi-Shindhurkota road. | [13 empty] | 0 | #DIV/0!
19 | 257475120-Baot R&H - Baot Graveyard via Kodalkathi BC road | [13 empty] | 0 | #DIV/0!
Total |  |  | 15.683 | 0 | 0 | 271.644 |  |  |  | 255.845 | 100% |  | 255.006 | 255.006 | 0 | 99.67%
GC-Hat
Meherpur Sadar
1 | Construction of Ashrafpur Bazar Growth Center. | KDRIDP/Meher/ GC-20/2017-18 | 0 | 0 | 1 | 20.33 | 2018-01-25 | Md. Abdul Hannan | 2018-05-03 | 18.297 | 100% | 2018-12-06 | 18.28 | 18.28 | 0 | 99.91% | Final
Gangni
2 | Construction of Bamundi Growth Center under Gangni Upazila District Meherpur. | KDRIDP/Meher/ GC-21/2017-18 | 0 | 0 | 1 | 18.23 | 2018-01-25 | Md. Mozirul Islam | 2018-05-03 | 16.408 | 100% | 2018-06-25 | 16.4 | 16.4 | 0 | 99.95% | Final
Total |  |  | 0 | 0 | 2 | 38.56 |  |  |  | 34.705 | 100% |  | 34.68 | 34.68 | 0 | 99.93%
Tree Plantation
Meherpur Sadar
1 | 257874024-Tree Plantation of Teroghoria Asrayan-Vittermath road at Ch. 00-2000m. | KDRIDP/Meher/ TP-01/ 2018-19 | 2 | 0 | 0 | 1.99 |  | LCS |  | 1.99 | 60% | 2021-06-30 |  | 0.53 | -0.53 | 26.63%
Mujibnagar
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Gangni
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 2 | 0 | 0 | 1.99 |  |  |  | 1.99 | 60% |  | 0 | 0.53 | -0.53 | 26.63%
Grand Total |  |  | 65.994 | 0 | 2 | 3368.991 |  |  |  | 3050.506 | 70.91% |  | 2155.513 | 2398.838 | -243.325 | 78.64%
|  |  | 65.994 | 0 | 2 | 3368.991 |  |  |  | 3050.506 | 63.68% |  | 2155.513 | 2398.838 | -243.325 | 78.64%

## Meherpur Sadar
Meherpur Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 257872010-Improvement of Kathalpota RHD-Vogirothpur GC Road Ch. 2600-2900m | KDRIDP/Meher/W-32/2017-18 | 0.3 | 0 | 0 | 29.18 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 27.72 | 25% | 2019-03-31 | 25.75 | 25.747 | 0.003 | 92.88% | Final
2 | 257872011-A) Improvement of Chandpur RHD-Sholmari GC Via Hitimpara Road. Ch.00-734m & Ch. 5000-6082m under Sadar Upazila District Meherpur. B) Construction of 3nos U-Type Drain 625mmx600mm on Chandpur RHD-Sholmari GC Via Hitimpara Road. Ch. 5350m 5550m & 5750m. | KDRIDP/Meher/W-03/2016-17 | 1.816 | 0 | 0 | 123.01 | 2017-08-06 | M/S. Jony Enterprise | 2017-07-16 | 121.63 | 100% | 2017-12-21 | 120.85 | 120.85 | 0 | 99.36% | Final Bill Salvage Cost Tk. 3433427.00
Improvement of Union Road by BC
3 | 257874068-Improvement of Dindatta Bridge-Aamjhupi UP via Hizuli bazar Road Ch. 1431m-2031m. Salvage Cost Tk. 1474731.00 (257873006-Dindatta Bridge-Aamjhupi UP via Hizuli bazar Road.) | KDRIDP/Meher/W-32/2017-18 | 0.6 | 0 | 0 | 38.89 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 37.896 | 25% | 2019-03-31 | 35.19 | 35.19 | 0 | 92.86% | Final
4 | 257873007-Improvement of Kuthipara- Kulbaria Hat via Kutubpur UP Office Road Ch. 1488-2100m. Salvage Cost TK. 1477447.00 | KDRIDP/Meher/ W-31/2017-18 | 0.612 | 0 | 0 | 41.948 | 2018-07-23 | Md. Nadim Iqbal | 2018-05-09 | 39.851 | 50% | 2019-03-31 | 39.8 | 39.8 | 0 | 99.87% | Final
5 | 257873007-Improvement of Kuthipara- Kulbaria Road via Kutubpur UP Office road by BC at Ch. 2100-4100m | KDRIDP/Meher/ W-33/2018-19 | 2 | 0 | 0 | 141.839 | 2018-05-12 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage Cost Tk. 4845623.00
6 | 257873013-Mohajonpur UP-Tengramari via Shahebpur-Islampur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
7 | 257874001-Improvement of Bandar RHD -Bhabanandapur Hat Road Ch. 1540m-1655m 2037m-4250m & 4290m-4430m. Salvage Cost Tk. 239064.00. | KDRIDP/Meher/ W-31/ 2017-18 | 2.468 | 0 | 0 | 160.97 | 2018-07-23 | Md. Nadim Iqbal | 2018-05-09 | 152.922 | 50% | 2019-03-31 | 152.76 | 152.76 | 0 | 99.89% | Final
8 | 257874022-Improvement of Hasnabadh UNR-Barshibaria patapuka RHD road by BC at Ch. 00-1300m and 3574-4439m | KDRIDP/Meher/ W-34/2018-19 | 2.165 | 0 | 0 | 161.688 | 2018-05-12 | M/S. Emi Motors | 2019-01-22 | 153.604 | 60% | 2019-06-30 | 0 | 0 | 0 | 0% | Salvage Cost Tk. 3353372.00
9 | 257874024-Improvement of Teroghoria Asrayan -Vittermath Road. Ch. 00-2444m. | KDRIDP/Meher/W-22/2017-18 | 2.44 | 0 | 0 | 139.22 | 2017-11-10 | Jahirul Limited | 2017-12-11 | 125.298 | 100% | 2018-04-18 | 125.26 | 125.26 | 0 | 99.97% | Final
10 | 257874032-Improvement of Baliarpur RHD-Roghunathpur UNR Road. Ch.3347-4547m | KDRIDP/Meher/W-04/2016-17 | 1.2 | 0 | 0 | 65.67 | 2017-08-06 | M/S. Biswas Construction | 2017-07-16 | 63.307 | 100% | 2017-12-22 | 63.307 | 63.307 | 0 | 100% | Final
| 257874032-Improvement of Baliarpur RHD-Roghunathpur Road Ch. 2314m-3347m | KDRIDP/Meher/W-32/2017-18 | 1.033 | 0 | 0 | 67.757 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 64.369 | 50% | 2019-03-31 | 59.78 | 59.78 | 0 | 92.87% | Final
11 | 257874047-Improvement of Ragunathpur-Pirojpur bazar Road Ch. 574-1369m. Salvage Cost Tk. 494323.00 |  | 0.795 | 0 | 0 | 48.357 |  |  |  | 45.939 |  |  | 42.66 | 42.66 | 0 | 92.86%
12 | 257874047-Improvement of Ragunathpur-Pirojpur bazaar Road. Ch.1369-2369m | KDRIDP/Meher/W-06/2016-17 | 1 | 0 | 0 | 54.74 | 2017-08-06 | M/S. Rumana Enterprise | 2017-07-09 | 53.37 | 100% | 2017-10-12 | 53.37 | 53.37 | 0 | 100% | Final
13 | 257874040-Improvement of Musurivaza-Jukindha Road. Ch.1450-3100m | KDRIDP/Meher/W-05/2016-17 | 1.65 | 0 | 0 | 91.08 | 2017-08-06 | M/S. Biswas Construction | 2017-07-16 | 87.51 | 100% | 2017-12-21 | 87.51 | 87.51 | 0 | 100% | Final Bill Salvage Cost Tk. 2883802.00
14 | 257874048-Improvement of Rajnagar Golamnabi RHD -Jugindha Hat road Ch. 2701-3378m | KDRIDP/Meher/W-21/2017-18 | 0.677 | 0 | 0 | 37.455 | 2017-11-10 | Jahirul Limited | 2017-12-11 | 33.71 | 100% | 17-5-18 | 33.71 | 33.71 | 0 | 100% | Final
14.6667 | 257875120-Islamnagar-Juginda Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
16 | 257873013-Periodic Maintenance of Mohajonpur UP-Tengramari via Shahebpur-Islampur road at Ch. 00-1070m | KDRIDP/Meher/ M-09/2018-19 | 1.07 | 0 | 0 | 11.134 | 2018-11-27 | M/S. Nur Islam Enterprise | 2018-12-24 | 10.577 | 100% | 2019-03-31 | 10.57 | 10.57 | 0 | 99.93% | Final
17 | 257874010-Periodic Maintenance of Bazitpur-Harirumpur Road from Ch. 000m -493m | KDRIDP/Meher/ M-01/2017-18 | 0.493 | 0 | 0 | 5.23 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 5.22 | 100% | 2018-03-28 | 5.215 | 5.215 | 0 | 99.9% | Final
18 | 257874019-Digirpara-Jowbaria Pakurtala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 257874022-Periodic Maintenance of Hasanabad-Barshibaria Patapuka road at Ch. 1300-2305m | KDRIDP/Meher/M-10/2018-19 | 1.005 | 0 | 0 | 11.88 | 2018-11-27 | Md. Abdul Hannan | 2019-10-01 | 11.288 | 100% | 2019-01-20 | 11.273 | 11.273 | 0 | 99.87% | Final
20 | 257874062-Sholmari GC.-Meherpur via Rudronagar-Kamdebpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
21 | Construction of Ashrafpur Bazar Growth Center. | KDRIDP/Meher/ GC-20/2017-18 | 0 | 0 | 1 | 20.33 | 2018-01-25 | Md. Abdul Hannan | 2018-05-03 | 18.297 | 100% | 2018-12-06 | 18.28 | 18.28 | 0 | 99.91% | Final
Tree Plantation
22 | 257874024-Tree Plantation of Teroghoria Asrayan-Vittermath road at Ch. 00-2000m. | KDRIDP/Meher/ TP-01/ 2018-19 | 2 | 0 | 0 | 1.99 | 0 | LCS | 0 | 1.99 | 60% | 2021-06-30 | 0 | 0.53 | -0.53 | 26.63% | 0
Total |  |  | 23.324 | 0 | 1 | 1252.368 |  |  |  | 1054.498 | 60% |  | 885.285 | 885.812 | -0.527 | 84%

## Gangni
Gangni
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 257472008-Improvement of Bamundi GC-Hatboalia GC via Chatian Road Ch. 8898-9200m | KDRIDP/Meher/W-17/2017-18 | 0.302 | 0 | 0 | 20.42 | 2017-08-29 | Md. Shaharin Haque Malik | 2017-10-22 | 20.01 | 100% | 2017-12-17 | 20.01 | 20.01 | 0 | 100% | Final
Improvement of Union Road by BC
2 | 257473001-Improvement of Shaharbati UP-Manikdia Hat via Jorepukur Road Ch. 2760-3467m | KDRIDP/Meher/ W-18/2017-18 | 0.707 | 0 | 0 | 53.03 | 2017-08-29 | Md. Ehsanul Haque | 2017-10-22 | 49.91 | 100% | 2018-04-28 | 49.811 | 49.811 | 0 | 99.8% | Final
3 | 257473004-Improvement of Hijol Baria Hat-Sholotaka UP via Chengara Road Ch. 1670-2559m | KDRIDP/Meher/W-12/2017-18 | 0.889 | 0 | 0 | 58.03 | 2017-08-29 | M/S. Rumana Enterprise | 2017-08-10 | 57.37 | 100% | 2018-05-20 | 56.98 | 56.98 | 0 | 99.32% | Final
4 | 257473011-Improvement of Arrpara Hat -Raipur road via Raipur UP Road Ch. 00-950m & 3923-4200m. Salvage Cost Tk. 2307687.00 | KDRIDP/Meher/W-25/2017-18 | 1.227 | 0 | 0 | 80.079 | 2018-04-06 | M/S ASHRAF TRADERS | 2018-10-07 | 80.039 | 0% | 2019-03-31 | 0 | 0 | 0 | 0% | 0
5 | 257473013-Improvement of Dhankhola UP - Koshba bazar via Vatpara Khorempur Road Ch. 1857-2493m & 3191m-4500m | KDRIDP/Meher/ W-16/2017-18 | 1.945 | 0 | 0 | 133.08 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 119.77 | 100% | 2018-04-28 | 119.371 | 119.371 | 0 | 99.67% | Final
6 | 257473016-Improvement of Bhobanipur FRB Hat-Kazipur UP Road Ch. 1587-2309m & 2593-4170m. Salvage Cost Tk. 1051680.00 | KDRIDP/Meher/ W-26/2017-18 | 2.299 | 0 | 0 | 144.776 | 2018-04-06 | M/S ASHRAF TRADERS | 2018-10-07 | 137.537 | 60% | 2019-03-31 | 0 | 31.66 | -31.66 | 23.02% | 0
7 | 257473019-Improvement of Roypur UP Office Koroigachi -Ashmankhali GC via Elangi Hat Road Ch. 1000-2750m 4171-4945m & 5335-5353m. Salvage Cost Tk. 5690269.00 | KDRIDP/Meher/W-27/2017-18 | 2.542 | 0 | 0 | 176.218 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 184.85 | 50% | 2019-01-03 | 0 | 88.776 | -88.776 | 48.03% | 0
Improvement of Village Road by BC
8 | 257474010-Improvement of Garadob Kachari-Vatpara Road. Ch. 00-1000m | KDRIDP/Meher/ W-23/2017-18 | 1 | 0 | 0 | 63.28 | 2017-11-14 | Md. Abdul Hannan | 2017-12-18 | 59.4 | 100% | 2018-05-24 | 59.388 | 59.388 | 0 | 99.98% | Salvage Cost Tk. 1890447.00 Final
9 | 257474026-Choktola-Morka bazar via Kashtodah Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 257474028-Improvement of Terail-Shindurkota via Mahabbotpur Road Ch. 3400-3827m & 4556-5149m | KDRIDP/Meher/ W-15/2017-18 | 1.02 | 0 | 0 | 56.05 | 2017-08-29 | M/S. Rumana Enterprise | 2017-10-22 | 55.15 | 100% | 2018-04-28 | 55.15 | 55.15 | 0 | 100% | Final
11 | 257474057-Improvement of Bashbaria RHD Bazar - Shaharbati Barishar Moure Club Rood Ch. 436-2186m | KDRIDP/Meher/W-13/2017-18 | 1.75 | 0 | 0 | 109.49 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 98.54 | 100% | 2018-04-28 | 98.024 | 98.024 | 0 | 99.48% | Final
12 | 257474059-Improvement of Betbaria Eidgha-Vallege Shihala Ghat Road Ch. 200-810m & 1500-2090m. Salvage Cost Tk. 154886.00 | KDRIDP/Meher/ W-24/2017-18 | 1.2 | 0 | 0 | 84.78 | 2018-02-28 | Jahirul Limited | 2018-04-16 | 76.3 | 100% | 2018-10-22 | 76.277 | 76.277 | 0 | 99.97% | Salvage Cost Tk. 154886.00 Final
13 | 257474055-Improvement of Kumaridanga-Bholadanga bazar road via Kodalkati Road Ch. 1700-2315m. Salvage cost Tk. 1172002.00 | KDRIDP/Meher/ W-28/2017-18 | 0.615 | 0 | 0 | 39.183 | 2018-04-06 | Md. Easin Ali | 2018-07-17 | 37.22 | 100% | 2019-03-31 | 37.05 | 37.05 | 0 | 99.54% | Final
| 257475138-Improvement of Juginda pucca road - Shop of hasem at Azan Road Ch. 00-840m. Salvage Cost Tk. 149443.00 |  | 0.84 | 0 | 0 | 54.787 |  |  |  | 52.048 |  |  | 51.81 | 51.81 | 0 | 99.54%
| 257475023-Improvement of Pakuiria-Dhepa Road Ch. 2200-2900m |  | 0.7 | 0 | 0 | 43.14 |  |  |  | 40.98 |  |  | 40.79 | 40.79 | 0 | 99.54%
14 | 257475149-Improvement of Garabria Bank - Gangni-Kathuli R&H Road Ch. 00-300m & 885-1590m | KDRIDP/Meher/ W-14/2017-18 | 1.005 | 0 | 0 | 57.4 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 51.66 | 100% | 2018-04-28 | 51.655 | 51.655 | 0 | 99.99% | Final
Construction of Bridge on Upazila Road (7.30m width)
15 | 257472006-Const. of RCC Bridge on Bamondi R&H -Pragpur GC via Madhugari ghat Road over Mathabhanga river. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 257472007-Const. of RCC Bridge on Upazila H/Q (Malshadah) -Kazipur GC- Malshbaria Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
17 | 257474001-Periodic Maintenance of Garadob Purapara RHD - Juginda Islamnagar Road from Ch. 000m -2000m | KDRIDP/Meher/ M-02/2017-18 | 2 | 0 | 0 | 26.62 | 2017-12-21 | Md. Abdul Hannan | 2017-01-22 | 24.48 | 100% | 2018-04-22 | 24.301 | 24.301 | 0 | 99.27% | Final
18 | 257474053-Maintenance of Akubpur RHD-Mohammodpur Hat Road Ch. 00-1800m | KDRIDP/Meher/ W-19/2017-18 | 1.8 | 0 | 0 | 56.84 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 51.16 | 100% | 2017-10-22 | 51.06 | 51.06 | 0 | 99.8% | Final
19 | 257475016-Maintenance of Hemayatpur-Ruyerkandi Road Ch. 00-1500m | KDRIDP/Meher/ W-20/2017-18 | 1.5 | 0 | 0 | 33.98 | 2017-08-29 | Jahirul Limited | 2017-10-22 | 30.58 | 100% | 2018-02-02 | 30.517 | 30.517 | 0 | 99.79% | Final
20 | 257474023-Periodic Maintenance of Garadav Munshi Zamiruddin Road from Ch. 000m -370m | KDRIDP/Meher/ M-03/2017-18 | 0.37 | 0 | 0 | 9.14 | 2017-12-21 | Md. Abdul Hannan | 2017-01-22 | 8.56 | 100% | 2018-04-20 | 8.55 | 8.55 | 0 | 99.88% | Final
21 | 257475023-Periodic Maintenance of Pakuiria-Dhepa Road from Ch. 000m -1100m | KDRIDP/Meher/ M-04/2017-18 | 1.1 | 0 | 0 | 23.08 | 2017-12-21 | Md. Mofijul Islam | 2017-01-29 | 21.51 | 100% | 2018-06-04 | 21.46 | 21.46 | 0 | 99.77% | Final
22 | 257475004-Shukurkandi-Shindhurkota road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 257475120-Baot R&H - Baot Graveyard via Kodalkathi BC road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
24 | Construction of Bamundi Growth Center under Gangni Upazila District Meherpur. | KDRIDP/Meher/ GC-21/2017-18 | 0 | 0 | 1 | 18.23 | 2018-01-25 | Md. Mozirul Islam | 2018-05-03 | 16.408 | 100% | 2018-06-25 | 16.4 | 16.4 | 0 | 99.95% | Final
Tree Plantation
25 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 24.811 | 0 | 1 | 1341.633 |  |  |  | 1273.482 | 68.4% |  | 868.604 | 989.04 | -120.436 | 77.66%

## Mujibnagar
Mujibnagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 257882008-Anandhobas GC-Jaganathpur GC via Ratanpur (Muzibnagar Part) road. | KDRIDP/Meher/W-08/2016-17 | 0.67 | 0 | 0 | 46.11 | 2017-03-08 | M/S. Jony Enterprise | 2017-10-09 | 42.376 | 100% | 2018-09-04 | 42.363 | 42.363 | 0 | 99.97% | Final
2 | 257882009-Improvement of Dariapur GC- Kaderganj R&H via KalitolaRamnagar Road Ch. 332-367m & 1215-1527m | KDRIDP/Meher/W-02/2016-17 | 0.347 | 0 | 0 | 19.18 | 2017-11-05 | M/S. Jony Enterprise | 2017-05-31 | 19.07 | 100% | 2017-06-19 | 19.07 | 19.07 | 0 | 100% | Final Bill Salvage Cost Tk. 395191.00
Improvement of Union Road by BC
3 | 257883003-Improvement of Mohazonpur UP (Komorpur)-Mohazonpur GC Road. (Ch. 2518-3710m) | KDRIDP/Meher/W-07/2016-17 | 1.192 | 0 | 0 | 65.13 | 2017-03-08 | M/S. Biswas Construction | 2017-10-09 | 58.62 | 100% | 2018-02-27 | 58.617 | 58.617 | 0 | 99.99% | Final
4 | 257883006-Improvement of Komorpur-Gopalpur-Pirozpur UP road (Muzibnagar part). (Ch. 1790-2365m) | KDRIDP/Meher/W-09/2016-17 | 0.575 | 0 | 0 | 32.52 | 2017-03-08 | Jahirul Limited | 2017-10-09 | 29.26 | 100% | 2017-12-03 | 29.25 | 29.25 | 0 | 99.97% | Final
5 | 257883012-Mohajanpur UP- Pirozpur UP via Jadukhali Ghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 257884018-Improvement of Dariapur R&H to Dariapur BOP Road. (Ch. 200-2200m) | KDRIDP/Meher/W-10/2016-17 | 2 | 0 | 0 | 111.92 | 2017-03-08 | Jahirul Limited | 2017-10-09 | 100.724 | 100% | 2018-03-31 | 100.724 | 100.724 | 0 | 100% | Final
7 | 257884018-Improvement of Dariapur R&H to Dariapur BOP Road. (Ch. 2200-2800m) | KDRIDP/Meher/ W-29/2017-18 | 0.6 | 0 | 0 | 37.359 | 2018-04-06 | Md. Hafizur Rahman | 2018-12-07 | 35.49 | 45% | 2019-01-03 | 0 | 11.99 | -11.99 | 33.78% | 0
| 257884022-Improvement of Shibpur Ghat-Tangramari via Shibpur hat Road Ch. 485-845m. Salvage Cost Tk. 128997.00. |  | 0.36 | 0 | 0 | 21.95 |  |  |  | 20.85 |  |  | 0 | 7.042 | -7.042 | 33.77%
| 257884027-Improvement of Taranagar BC UZR road - Jagonathpur BOP Road Ch. 1200-2900m. |  | 1.7 | 0 | 0 | 107.926 |  |  |  | 102.53 |  |  | 0 | 34.643 | -34.643 | 33.79%
8 | 257884027-Improvement of Taranagar BC - Jagonathpur BOP Road Ch. 00-1200m | KDRIDP/Meher/W-01/2016-17 | 1.2 | 0 | 0 | 66.16 | 2017-11-05 | Jahirul Limited | 2017-05-24 | 59.54 | 100% | 2017-11-30 | 59.54 | 59.54 | 0 | 100% | Final Salvage Cost Tk. 216051.00
9 | 257884031-Improvement of Mujibnagar BOP to Bhebarpara Bazar via Mujibnagar Shrtisoudo Road Ch. 350-680m. Salvage Cost TK. 31844.00 | KDRIDP/Meher/W-30/2017-18 | 0.33 | 0 | 0 | 20.59 | 2018-04-06 | M/S.Khan Enterprise | 2018-12-07 | 19.56 | 45% | 2019-01-03 | 0 | 6.046 | -6.046 | 30.91% | 0
| 257884033-Improvement of Gopalpur BC road H/O Mannan Master - Sonapur Road Ch. 1000-1350m. |  | 0.35 | 0 | 0 | 21.276 |  |  |  | 20.21 |  |  | 0 | 6.247 | -6.247 | 30.91% | 0
| 257885008-Improvement of Sonapur Mohir Dhakka Godown-Sutir Math Road Ch. 1615-2805m. |  | 1.19 | 0 | 0 | 76.259 |  |  |  | 72.446 |  |  | 0 | 22.394 | -22.394 | 30.91% | 0
10 | 257884033-Improvement of Gopalpur BC rd. - Sonapur Road(Gopalpur H/O Mannan Master-Sonapur). (Ch. 00-1000m) | KDRIDP/Meher/W-11/2016-17 | 1 | 0 | 0 | 54.87 | 2017-03-08 | Jahirul Limited | 2017-10-09 | 49.38 | 100% | 2018-03-31 | 0 | 34 | -34 | 68.85% | 0
11 | 257885018-Anandabash FRB-Anandabash JGHS Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
12 | 257882008-Anandhobas GC-Jaganathpur GC via Ratanpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 257883003-Mohazonpur UP-Mohazonpur GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 257884025-Periodic Maintenance of Kedergong Bazar to Bagoan R&H via Bollovepur graveyard Mission Hospital from Ch. 000m -1466m | KDRIDP/Meher/ M-05/2017-18 | 1.466 | 0 | 0 | 16.33 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 16.25 | 100% | 2018-04-05 | 16.063 | 16.063 | 0 | 98.85% | Final
15 | 257885055-Periodic Maintenance of Baguan RHD Community Clinic-Baguan Jam-E-Mosque UZR Road 000m -1192m | KDRIDP/Meher/ M-08/2017-18 | 1.192 | 0 | 0 | 22.73 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 22.61 | 100% | 2018-04-05 | 22.509 | 22.509 | 0 | 99.55% | Final
16 | 257884036-Kadamtala RHD-UP Office-Dariapur GC & T&T(RHD) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 257884037-Periodic Maintenance of Gopalnagar RHD-Shibpur Ghat Road 00m -805m | KDRIDP/Meher/ M-06/2017-18 | 0.805 | 0 | 0 | 10.01 | 2017-12-21 | M/S. Rumana Enterprise | 2017-01-29 | 10 | 100% | 2018-04-05 | 9.928 | 9.928 | 0 | 99.28% | Final
18 | 257884039-Periodic Maintenance of Kedargonj Bazar RHD - Muzibnagar HQ Bhebarpara Bazar via Nazirakona Road Ch. 2415-5297m | KDRIDP/Meher/ M-07/2017-18 | 2.882 | 0 | 0 | 44.67 | 2017-12-21 | M/S. Jony Enterprise | 2018-05-03 | 43.61 | 100% | 2018-05-22 | 43.56 | 43.56 | 0 | 99.89% | Final
Tree Plantation
19 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 17.859 | 0 | 0 | 774.99 |  |  |  | 722.526 | 62.63% |  | 401.624 | 523.986 | -122.362 | 72.52%

## Summary
MEHERPUR
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 4 | 4 | 3.435 | 0 | 0 | 230.806 | 228.04 | 85% | 98.8%
Union Road by BC | 10 | 9 | 14.588 | 0 | 0 | 795.103 | 509.455 | 68.5% | 64.07%
Village Road by BC | 18 | 18 | 30.288 | 0 | 0 | 1732.057 | 1371.127 | 82.86% | 79.16%
Village Road by HBB | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A
Bridge on Upazila Road | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A
Maintenance | 12 | 12 | 15.683 | 0 | 0 | 255.845 | 255.006 | 100% | 99.67%
GC-Hat | 2 | 2 | 0 | 0 | 2 | 34.705 | 34.68 | 100% | 99.93%
Landing/ Riverghat | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | 0% | N/A
Tree Plantation | 1 | 1 | 2 | 0 | 0 | 1.99 | 0.53 | 60% | 26.63%
Total | 47 | 46 | 65.994 | 0 | 2 | 3050.506 | 2398.838 | 49.64% | 78.64%