## Bagerhat
BAGERHAT
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Sharankhola
1 | 201772004-Amragachia RHD - Banglabazar GC road | [13 empty] | 0 | #DIV/0!
2 | 201772006-Development of Baniakhali GC- Dhansagar RHD Road. Ch 1000 -3805 m. Salvage TK. 1634778.00 | KDRIDP/Bager/W-08/2016-17 | 2.805 | 0 | 0 | 210.72 | 2017-06-08 | M/S Ahamed Steel Industries, Kapuria patty, Mathbaris, Barisal | 2017-07-20 | 219.13 | 100% | 2018-09-02 | 217 | 217 | 0 | 99.03% | Final
3 | 201772007-Tafalbari GC-Rasulpur GC-Rajapur GC-Pollanbari RHD Road. | [13 empty] | 0 | #DIV/0!
Morrelgonj
4 | 201602002 - Chingrakhali GC-Daibajnahati GC | [13 empty] | 0 | #DIV/0!
5 | 201602006 - Pollerhat GC-Chingrakhali UP-Zianagar RHD (Morel Part) | [13 empty] | 0 | #DIV/0!
6 | 201602007-Dhansagar RHD-Baniakhali GC Rd | [13 empty] | 0 | #DIV/0!
7 | 201602012 - Khalkula Steel bridge to Chingrakhali bazar via Kachuabunia Rahmatia School | [13 empty] | 0 | #DIV/0!
Mollahat
8 | 201562008-Harida more- Machuarkul Rd. | [13 empty] | 0 | #DIV/0!
9 | 201562009-Gawla-Kodalia Bazar Rd. | [13 empty] | 0 | #DIV/0!
10 | 201562010-Ghoradair -Kachna Road. | [13 empty] | 0 | #DIV/0!
Rampal
11 | 201732007-Improvement of Bhaga RHD-Kapasdanga-Kaigardashkati-Chalnahat GC (Rampal portion) Road by BC at Ch. 12500m-13100m | KDRIDP/Bager/W-111/2018-19 | 0.6 | 0 | 0 | 68.326 | 2019-05-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. |  | 64.91 |  |  |  |  | 0 | 0% | NOA issued on 30.06.19
12 | 201732010-Improvement of Balai Bridge-Rampal Road Ch. 0.00m-5100m. Under Rampal Upazila Bagerhat. Road ID No. 201732010 Salvage cost Tk. 3840719.00 | KDRIDP/Bager/W-72/2017-18 | 5.1 | 0 | 0 | 416.04 | 2018-03-06 | M.A. Jalil Khan, Rupsha Stand Road, Khulna. | 2018-04-25 | 456.72 | 35% | 2019-05-02 |  | 50 | -50 | 10.95% | 1st R/A
13 | 201732013-A) Development of Baliadanga Bus Stand- Vangonpar Road by BC Ch 00-5200 m. B) Construction of 2 nos U-Drain at ch 300 m& 495 m.C Construction of 04 Nos Rcc 3x3 V Box Culvert at ch 2040m3450 m4170 m & 4525 mOn Same Road. Salvage Cost TK. 2101973.00 Fixed | KDRIDP/Bager/W-01/2016-17 | 5.2 | 0 | 0 | 251.31 | 2017-05-15 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-07-03 | 262.62 | 70% | 2019-05-31 |  | 47.42 | -47.42 | 18.06% | 1st R/A
14 | 201732014-Improvement of Babur bari-Bujbunia Road by BC at Ch. 2654m-5580m. Salvage Amount Tk. 24,79,651.00 | KDRIDP/Bager/W-109/2018-19 | 2.926 | 0 | 0 | 270.25 | [8 empty] | 0 | #DIV/0! | Evaluation under process
15 | 201732015-Improvement of Tatulia Bridge - Kadirkhola road Ch1175-2904m by BC. Salvage amount Tk.1486339.00 Fixed | KDRIDP/Bager/W-44/2017-18 | 1.729 | 0 | 0 | 138.038 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 144.56 | 40% | 2019-08-03 |  | 46.15 | -46.15 | 31.92% | 1st R/A
Mongla
16 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 00-4550 m. Salvage cost TK.8984664.00 Fixed | KDRIDP/Bager/W-02/2016-17 | 4.55 | 0 | 0 | 370.91 | 2017-06-14 | MSEBA and AB (JV), 211, Khanjahan Ali, Road, Khulna. | 2017-08-02 | 388.83 | 40% | 2019-05-31 |  | 101.72 | -101.72 | 26.16%
17 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 4550-8340 m. Salvage cost TK.4928783.00 Fixed(2nd Call) | KDRIDP/Bager/W-03/2016-17 | 3.79 | 0 | 0 | 261.14 | 2017-06-14 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-08-02 | 272.72 | 40% | 2019-05-31 |  | 75.06 | -75.06 | 27.52% | 1st R/A
18 | 201582006-Improvement of Chaterhat GC-Banshtola GC-Joymonirghol (Baddamary) Road by BC at Ch. 6670m-9270m (Road ID No-201582006) Salvage Amount Tk. 22,57,877.00 | KDRIDP/Bager/W-117/2018-19 | 3.686 | 0 | 0 | 312.814 | [8 empty] | 0 | #DIV/0!
19 | 201582007-Improvement of Digiraj-Jhalmalia Dhigi road. Ch.4040m-7395m. Salvage Cost Tk. 3563628 | KDRIDP/Bager/W-77/2017-18 | 3.355 | 0 | 0 | 314.226 | 2019-05-28 | JE & IE (JV), Sk. Abdul Hai Sarok, Mongla, Bagerhat |  | 313.462 |  |  |  |  | 0 | 0% | NOA issued on 08.07.19
Fakirhat
20 | 201342013 Lokhpur GC-Dhaka Khulna RHD (Nowapara More) | [13 empty] | 0 | #DIV/0!
Total |  |  | 33.741 | 0 | 0 | 2613.774 |  |  |  | 2122.952 | 54.17% |  | 217 | 537.35 | -320.35 | 25.31%
Improvement of Union Road by BC
Bagerhat Sadar
1 | 201083011 Improvement of Baroipara UP office-Haderhat bazar via Kartickdia bazar Road by BC at Ch. 4300m-4800m & 5226m-5450m. Salvage Amount Tk. 4,27,779.00 | KDRIDP/Bager/W-108/2018-19 | 0.724 | 0 | 0 | 47.592 | 2019-05-26 | Md. Nazrul Islam Nilu, College Road, Bagerhat |  | 45.212 |  |  |  |  | 0 | 0% | NOA issued on 30.06.19
2 | 201083012 Baroipara UP office-Ujalpur bazar via Kafurpura school road. | [13 empty] | 0 | #DIV/0!
3 | 201083017 Improvement of Chulkathi bazar-Betaga UP Road Sadar Portion Ch00-1476. Salvage amount tk. 157003. fixed | KDRIDP/Bager/W-35/2017-18 | 1.476 | 0 | 0 | 87.09 | 2017-09-11 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 91.08 | 100% | 2018-07-22 | 91.064 | 91.064 | 0 | 99.98% | Final
4 | 201084086-Improvement of Bemorta UP (At Fatepur)-Bottala bazar via Bijoypur Road at Ch. 00m-1068m. Salvage Amount Tk. 23,85,276.00 (201083018) | KDRIDP/Bager/W-102/2018-19 | 1.068 | 0 | 0 | 78.887 | 2019-03-19 | M/S Alif Store, Chitalmari, Bagerhat. | 2019-04-10 | 74.94 | 35% | 2020-04-16 |  |  | 0 | 0%
5 | 201083019-Improvement of Bishnapur UP-Kandapara GC Road by BC at Ch. 00m-1600m Road ID No-201083019 Salvage Amount Tk. 464006.00 | KDRIDP/Bager/W-107/2018-19 | 1.6 | 0 | 0 | 149.308 | [8 empty] | 0 | #DIV/0!
6 | 201083022-Karapara UP office to Karapara bazar via Magnitala bazar rd.. | [13 empty] | 0 | #DIV/0!
Sharankhola
7 | 201773004-Banglabazar GC-Dhansagar UP Office Rd via Rashid Khan Bridge Road. | [13 empty] | 0 | #DIV/0!
Morrelgonj
8 | 201603002 - Improvement of Baharbunia U.P.-Madrasa Hat Road by BC from Ch. 00m-5200m under Morrelgonj Upazila Bagerhat. Salvage Amount Tk. 62,96,862.00 | KDRIDP/Bager/W-99/2018-19 | 5.2 | 0 | 0 | 439.996 | 2019-01-20 | M/S Jharna Enterprise, 13 Dharmashava cross Road, Khulna | 2019-03-24 | 417.908 | 0% | 2020-03-30 |  |  | 0 | 0% | Re-tender dt. 03.04.18
9 | 201603003 - Mazhibari RHD at Badsharhat-Nishanbaria U.P office | [13 empty] | 0 | #DIV/0!
10 | 201603004 - Improvement of Khowla UP office-CARE bazar RHD ch2686-4906m | KDRIDP/Bager/W-51/2017-18 | 2.22 | 0 | 0 | 127.62 | 2017-10-03 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2017-11-28 | 116.71 | 100% | 2018-12-04 | 113.93 | 113.93 | 0 | 97.62% | Final
11 | 201603007 - Improvement of Banagrame Bazar-Hoglapasha U.P Road by BC Ch.4840m-5800m. Salvage Cost Tk. 7,08,811.00 | KDRIDP/Bager/W-105/ 2018-19 | 0.96 | 0 | 0 | 72.463 | 2019-05-12 | M/S Sweet Enterprise, Basabati, Bagerhat | 2019-06-10 | 68.84 | 0% | 2020-06-16 |  |  | 0 | 0%
12 | 201603009 - Morrelgonj-Upazila H.Q.to Baharbunia Union H.Q. | [13 empty] | 0 | #DIV/0!
13 | 201603010 - Putikhali UP office-Sonakhali bazar | [13 empty] | 0 | #DIV/0!
14 | 201603012 - Hoglabunia UP office-Lakhaner hat via Nager Hat | [13 empty] | 0 | #DIV/0!
15 | 201603017 - Baraikhali UP office-JeoDhara UP via Kalibari bazar | [13 empty] | 0 | #DIV/0!
16 | 201603019 - Improvement of Banagram UP- Shailkhali ch2100-2343m | KDRIDP/Bager/W-52/2017-18 | 0.243 | 0 | 0 | 15.39 | 2017-10-03 | M/S Sher-e-Bangla Traders, Mathbaria, Perojpur | 2017-11-28 | 14.82 | 100% | 2019-05-30 |  |  | 0 | 0%
17 | 201603015-Improvement of Jewdhara UP office -Joybangla bazar Ekramkhali Baytun Akram Hazi Bari Mosque road. Ch: 00-2169m | KDRIDP/Bager/W-56/2017-18 | 2.169 | 0 | 0 | 159.219 | 2017-10-26 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-12-13 | 166.84 | 45% | 2019-05-30 |  | 49.52 | -49.52 | 29.68% | 2nd R/A
Fakirhat
18 | 201343005-Singati Bazar-Piljong UP-Balir Dokan-Shambagat RHD. | KDRIDP/Bager/W-25/2017-18 | 1.02 | 0 | 0 | 64.92 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 60.65 | 100% | 2018-07-18 | 60.63 | 60.63 | 0 | 99.97% | Final
19 | 201343001-Fakirhat H/Q-Naldah Maubhog UP | [13 empty] | 0 | #DIV/0!
20 | 201343006 Upazila H/Q(Livestock Office)-Satsika-Baliadanga-Rakhalgachi UP (Fakirhat Part | [13 empty] | 0 | #DIV/0!
21 | 201343011 - Mulgor UP-Nalda Moubog UP Road | [13 empty] | 0 | #DIV/0!
Mollahat
22 | 201563004-Improvement of Kodalia U.P Office- Aruadehi hat road ch.1400-3480m | KDRIDP/Bager/W-71/2017-18 | 2.08 | 0 | 0 | 151.85 | 2018-02-07 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-03-21 | 136.66 | 40% | 2019-03-27 |  | 21.1 | -21.1 | 15.44% | 1st R/A
23 | 201563006-Improvement of Gaula UP-Chanderhat-Faltita Bazar Road by BC at Ch. 6200m-7163m. Salvage Amount Tk. 2,55,499.00 | KDRIDP/Bager/W-114/2018-19 | 0.963 | 0 | 0 | 73.18 | 2019-06-09 | Sahid Enterprise (PVT) Ltd, Boyra, Khulna |  | 69.523 |  |  |  |  | 0 | 0% | NOA issued on 02.07.19
24 | 201563007-Kulia Up-Nagarkandi GC Rd. | [13 empty] | 0 | #DIV/0!
25 | 201563008 - Singgati hat-Chunkhola UP H/Q | [13 empty] | 0 | #DIV/0!
26 | 201563009-Mollarkul Bazar-Udyapur UP Road. | [13 empty] | 0 | #DIV/0!
Rampal
27 | 201733002-Gilatale G.C-Bhospatia UP Rd. | [13 empty] | 0 | #DIV/0!
28 | 201733005-Improvement of Perikhali G.C-Bhojpatia U.P office Road by BC at Ch. 6054m-9740m. Salvage Amount Tk. 70,88,741.00 | KDRIDP/Bager/W-110/2018-19 | 3.686 | 0 | 0 | 312.814 | [8 empty] | 0 | #DIV/0! | Re-tender last selling 16.07.19
29 | 201733006-Improvement of Rampa-Bashtoli UP Road Ch.1890m-3695m. Under Rampal Upazila Bagerhat. Road ID No. 201733006 Salvage cost Tk. 2,87,317.00 | KDRIDP/Bager/W-104/2017-18 | 1.805 | 0 | 0 | 122.52 | 2019-03-19 | M/S Niloy Enterprise, 19 South Tootpara 2no cross road, Khulna | 2019-05-14 | 116.4 | 25% | 2020-05-20 |  |  | 0 | 0%
30 | 201733007-Uzalkur UP-Baburhat Road | [13 empty] | 0 | #DIV/0!
31 | 201733009-Perikhali GC-Hurka UP | [13 empty] | 0 | #DIV/0!
32 | 201733010-Kaligonj bazar-Mollikarbare UP | [13 empty] | 0 | #DIV/0!
33 | 201733014-Improvement of Rampa UP-Pabantala hat Road Ch.0.00m-2380m & 4646m-5484m .Under Rampal Upozila Bagerhat. Road ID No. 201733014 Salvage cost Tk. 2551146 | KDRIDP/Bager/W-74/2017-18 | 3.218 | 0 | 0 | 210.72 | 2018-03-06 | M/S Ziaul & Brothers, Bhandaria, Pirojpur | 2018-04-24 | 231.3 | 35% | 2019-04-29 |  | 31 | -31 | 13.4% | 1st R/A
Mongla
34 | 201583002-Burirdanga hat-Sonaeiltola UP Rd. | [13 empty] | 0 | #DIV/0!
35 | 201583007-Khulna-Mongla RHD at Goni Bridge- Burirdanga UP Office via Kapalirmeat Rd. | [13 empty] | 0 | #DIV/0!
36 | 201583001-Impropment of Chandpai UP - Chila hat Road. | [13 empty] | 0 | #DIV/0!
Chitalmari
37 | 201143001 - Chitalmari-Hizla UP-Kalatola UP | [13 empty] | 0 | #DIV/0!
38 | 201143006-Chinguri hat-Kalatala UP-Banglabazar Road. | [13 empty] | 0 | #DIV/0!
39 | 201143007 - Saildah hat-Kalatala UP | [13 empty] | 0 | #DIV/0!
Kachua
40 | 201383004-Improvement of Dhopakhali UP-Madertola bazar House Road by BC at Ch.987-1881m. Salvage Amount Tk. 15,94,676.00 | KDRIDP/Bager/W-84/2017-18 | 0.894 | 0 | 0 | 64.787 | 2018-05-17 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-06-05 | 68.026 | 100% | 2019-06-10 | 68.02 | 68.02 | 0 | 99.99% | Final
| 201383009-Improvement of Kachua UP-Talwshwer bazar Road by BC at Ch.00m-1143m & 2961m-3600m. Salvage Amount Tk. 22,87,655.00 |  | 1.782 | 0 | 0 | 123.059 |  |  |  | 129.21 |  |  | 129.19 | 129.19 | 0 | 99.98%
41 | 201383005-Improvement of Fatehpur bazar-Gopalpur UP- Fultala bazar Road. Ch4794-5353 m & 6300-7100 m. Salvage Cost Tk. 1345002.00 | KDRIDP/Bager/W-48/2017-18 | 1.359 | 0 | 0 | 83.459 | 2017-12-04 | M/S Sonia Enterprise, Nagerbazar, Bagerhat | 2018-02-05 | 87.15 | 100% | 2019-02-11 | 86.61 | 86.61 | 0 | 99.38% | Final
42 | 201383008-Improvement of Badhal UP-Atharogati bazar Road by BC at Ch. 2203m-3430m. Salvage Amount Tk.19,12,208.00 | KDRIDP/Bager/W-94/2017-18 | 1.227 | 0 | 0 | 95.278 | 2018-08-02 | M/S Rahamat Traders, Amlapara, Bagerhat | 2018-09-11 | 93.849 | 100% | 2019-09-17 | 74.721 | 74.721 | 0 | 79.62% | Final
Total |  |  | 33.694 | 0 | 0 | 2480.152 |  |  |  | 1989.118 | 62.86% |  | 624.165 | 725.785 | -101.62 | 36.49%
Improvement of Village Road by BC
Bagerhat Sadar
1 | 201084001-South Khanpur-Taterhat-Ranjeetpur.(start from Ranjeetpur Asrayan) | [13 empty] | 0 | #DIV/0!
2 | 201084011-B.Sc High school-Laksmikhali BWDB-Chaksree(Kalibari) hat road. | [13 empty] | 0 | #DIV/0!
3 | 201084017-Patorpara-Karapra road(Add.CE R&H dept). | [13 empty] | 0 | #DIV/0!
4 | 201084018-Patilakhali-Nataikhali road | [13 empty] | 0 | #DIV/0!
5 | 201084019-Kandapara GC(Parnowapara)-Betkhali bazar-Taleswar bazar road. | [13 empty] | 0 | #DIV/0!
6 | 201084038-Haderhat bazar-Bakhergonj bazar via singa kheyaghat WDB road. | [13 empty] | 0 | #DIV/0!
7 | 201084040-Improvement of Monigonj- Gopalkati- Bishnapur Road from Ch. 823m-1658m. Salvage Cost Tk. 17,83,391.00 | KDRIDP/Bager/W-103/2018-19 | 0.835 | 0 | 0 | 98.57 | 2019-03-19 | M/S Monir Bricks, Keshabpur, Bagerhat | 2019-05-08 | 93.643 | 30% | 2020-05-14 |  |  | 0 | 0%
8 | 201084074-Improvement of Rakhalgachi UP-Chulkathi bazar via Ranjeetpur Road by BC at Ch. 1440m-3065m. Salvage Amount Tk. 3,32,248.00 | KDRIDP/Bager/W-101/2018-19 | 1.625 | 0 | 0 | 122.88 | 2019-03-19 | M/S Faruk Enterprise, Kachua, Bagerhat | 2019-04-11 | 116.73 | 30% | 2020-04-17 |  |  | 0 | 0%
9 | 201085010-Improvement of Doritaluk Rd-Bagmara Road by BC at Ch. 950m-1702m. Salvage Amount Tk. 16,51,331.00 | KDRIDP/Bager/W-106/2018-19 | 0.752 | 0 | 0 | 63.22 | [8 empty] | 0 | #DIV/0!
| 201084067-Improvement of Chapatola (H/O Amin)-Jattrapur govt. pri. School Road by BC at Ch. 1000m-1410m. Salvage Amount Tk. 2,70,137.00 | KDRIDP/Bager/W-106/2018-19 | 0.41 | 0 | 0 | 43.175 | [8 empty] | 0 | #DIV/0!
| 201084024-Improvement of Zindapir mazar-Khanjahan Ali mazar with link of nine gambuj mosque Road by BC at Ch. 1384m-2080m. Salvage Amount Tk. 8,28,643.00 | KDRIDP/Bager/W-106/2018-19 | 0.696 | 0 | 0 | 50.164 | [8 empty] | 0 | #DIV/0!
10 | 201085288-Chaparkul –Bakarganj bazar via khalispur road. | [13 empty] | 0 | #DIV/0!
11 | 201085039-Bara Bansh Baria road | [13 empty] | 0 | #DIV/0!
12 | 201085044-Improvement of Bansh Baria High school road Road by BC at Ch. 12m-1366m. Salvage Amount Tk.1,89,208.00 | KDRIDP/Bager/W-100/2018-19 | 1.354 | 0 | 0 | 107.18 | 2019-03-19 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2019-04-11 | 101.82 | 30% | 2020-04-17 |  |  | 0 | 0%
13 | 201084046- Improvement of Jattrapur at UZR- Komorpur via Afra Mowmachi Palon project & Murshidpur Ch00-2151m. Salvage Amount tk.-592374 fixed | KDRIDP/Bager/W-36/2017-18 | 2.151 | 0 | 0 | 127.185 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 133.33 | 100% | 2018-08-30 | 133.31 | 133.31 | 0 | 99.98% | Final
14 | 201084040-Improvement of Monigonj- Gopalkati- Bishnapur Road from Ch. 823m-1658m. Salvage Cost Tk. 1642597.00 | KDRIDP/Bager/W-78/2017-18 | 0.835 | 0 | 0 | 85.79 | [8 empty] | 0 | #DIV/0! | Request sent to HQ for cancellation.
15 | 201085013-Keshobpur Charogram-Kondola-Talswar road. | [13 empty] | 0 | #DIV/0!
16 | 201085191-Improvement of Hakimpur Pry. School-Chandromahel road Ch 995-1845m. Salvage amount tk. 246687.00 fixed | KDRIDP/Bager/W-37/2017-18 | 0.85 | 0 | 0 | 60.78 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 63.72 | 100% | 2018-08-30 | 63.664 | 63.664 | 0 | 99.91% | Final
17 | 201084069-West Saera Bazar-Sree Ghat Bazar via Sadullahpur road. | KDRIDP/Bager/W-16/2016-17 | 0.702 | 0 | 0 | 41.58 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-13 | 43.56 | 100% | 2018-08-19 | 43.553 | 43.553 | 0 | 99.98% | Final
18 | 201085234-Rangeetpur-Southpara via Morralpara Tater hat road. | [13 empty] | 0 | #DIV/0!
19 | 201085238-Development of Ranjitpur- Guchegram- Morolpara- Surjamukhi Club Road. Ch 00-821 m. Salvage Cost Tk.145827.00 | KDRIDP/Bager/W-10/2016-17 | 0.821 | 0 | 0 | 49.28 | 2017-06-14 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-07-26 | 51.69 | 100% | 2018-05-29 | 51.654 | 51.654 | 0 | 99.93% | Final
20 | 201085040- Improvement of PC Dema Pucca Road-Mallik bari Road CH00-350M. Salvage amount 176715.00 fixed | KDRIDP/Bager/W-58/2017-18 | 0.35 | 0 | 0 | 20.11 | 2017-10-26 | M/S S.S. Brothers, 18, Sarker lane, Tootpara, Khulna. | 2017-12-12 | 21.11 | 100% | 2018-06-18 | 21.106 | 21.106 | 0 | 99.98% | Final
Kachua
20 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.1278m-3278m. Salvage Amount Tk. 3144409.00 | KDRIDP/Bager/W-85/2017-18 | 2 | 0 | 0 | 190.819 | 2018-05-27 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-06-28 | 199.31 | 100% | 2019-12-04 | 167.852 | 167.852 | 0 | 84.22% | Final
21 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.5780m-7564m. Salvage Amount Tk. 297535.00 | KDRIDP/Bager/W-86/2017-18 | 1.784 | 0 | 0 | 134.255 | 2018-05-28 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-07-01 | 140.968 | 100% | 2019-12-07 | 140.96 | 140.96 | 0 | 99.99% | Final
22 | 201384001-Improvement of Shibpur-Biskhali Road at Ch. 3278m-4093m. Salvage Amount Tk.1384216.00 | KDRIDP/Bager/W-96/2018-19 | 0.815 | 0 | 0 | 89.87 | 2018-08-19 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-09-30 | 85.38 | 100% | 2019-10-06 | 71.526 | 71.526 | 0 | 83.77% | Final
23 | 201384017-Development of Bakultala- Moshni Road. Ch. 2059-3135 m. Salvage Cost. TK.-539470.00 | KDRIDP/Bager/W-20/2016-17 | 1.076 | 0 | 0 | 78.97 | 2017-08-08 | M/S Rupali Construction, Hospital Road, Barisal | 2017-09-11 | 82.5 | 50% | 2018-09-17 |  | 45.29 | -45.29 | 54.9% | 2nd R/A
24 | 201384016-Improvement of Kachua-Badamtali Road by BC at Ch.1673m-3173m. Salvage Amount Tk. 904835.00 | KDRIDP/Bager/W-88/2017-18 | 1.5 | 0 | 0 | 145.075 | 2018-05-28 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-07-01 | 152.328 | 100% | 2019-12-07 | 152.272 | 152.272 | 0 | 99.96% | Final
25 | 201384044-Improvement of Maliporton School-bishkhali Road. Ch400-1260 m Under Kachua Upazila. Bagerhat. Salvage Cost Tk. 107512.00(Fixed) | KDRIDP/Bager/W-50/2017-18 | 0.86 | 0 | 0 | 63.956 | 2017-11-21 | M/S Robel Enterprise, Madaripur | 2018-01-25 | 66.52 | 100% | 2019-01-30 | 66.511 | 66.511 | 0 | 99.99% | Final
26 | 201384045-Laraahat-Lararkul | [13 empty] | 0 | #DIV/0!
27 | 201384085-Improvement of Mosni Bazar-Bhuddobhumi Road by BC at Ch.1500m-2566m. Salvage Amount Tk. 7,80,539.00 | KDRIDP/Bager/W-87/2017-18 | 1.066 | 0 | 0 | 94.25 | 2018-05-28 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-07-01 | 98.96 | 100% | 2019-12-07 | 98.951 | 98.952 | -0.001 | 99.99% | Final
| 201384031-Improvement of Mogia-Shirokhali Road by BC at Ch. 510m-1060m. Salvage Amount Tk. 8,59,367.00 |  | 0.55 | 0 | 0 | 36.06 |  |  |  | 37.86 |  |  | 37.852 | 37.851 | 0.001 | 99.98%
28 | 201385032-Afra Battala- Afra Jame Mosque Rd. | [13 empty] | 0 | #DIV/0!
29 | 201384103-Development of Guzarpara- Baleshor River Ghat Road. Ch.558-1540 m. Salvage Cost TK. 211626.00 | KDRIDP/Bager/W-18/2016-17 | 0.982 | 0 | 0 | 68.2 | 2017-07-10 | M/S Sufia Enterprise, Badura Parerhat, Pirojpur. | 2017-08-22 | 71.4 | 100% | 2018-08-29 | 71.391 | 71.391 | 0 | 99.99% | Final
30 | 201384103-Improvement of Guzarpara-Baleshor River Ghat Road Ch.1540m-1767m. Salvage cost Tk. 135904 | KDRIDP/Bager/W-75/2017-18 | 0.227 | 0 | 0 | 15.7 | 2018-01-25 | M/S Upokar Enterprise, LGED, Pirojpur. | 2018-05-01 | 14.8 | 100% | 2019-03-31 | 14.8 | 14.8 | 0 | 100% | Final
31 | 201385014-Development of B. Andermanik S Club - Huchibaga- Andermanik H. School Road. Ch.271-2146 m. Salvage Cost TK. 900690.00 | KDRIDP/Bager/W-17/2016-17 | 1.875 | 0 | 0 | 139.996 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 146.93 | 100% | 2018-08-12 | 146.913 | 146.913 | 0 | 99.99% | Final
32 | 201384100-Improvement of Shibpur- Palpara Road. Ch 00-1359 m. Salvage Cost Tk. 491805.00 (201384078) | KDRIDP/Bager/W-46/2017-18 | 1.359 | 0 | 0 | 90.636 | 2017-12-18 | M/S Khandaker Brothers, Nalcity, Jhalokati. | 2018-01-28 | 96.38 | 100% | 2019-02-03 | 96.372 | 96.372 | 0 | 99.99% | Final
33 | 201384025-Improvement of Protappur-Bokaterkathi Road. Ch00-625 m. Salvage Cost Tk. 330365.00 | KDRIDP/Bager/W-49/2017-18 | 0.625 | 0 | 0 | 69.678 | 2017-10-04 | M/S Masud Enterprise, Kachua, Bagerhat. | 2017-11-13 | 72.73 | 100% | 2018-11-19 | 72.425 | 72.425 | 0 | 99.58% | Final
34 | 201384115-Padonagur masin shop via chato khal to signboard (201384065) | KDRIDP/Bager/W-29/2017-18 | 1.114 | 0 | 0 | 89.598 | 2017-08-22 | Md. Noor Hossain, Mission para, Jessore. | 2017-10-11 | 83.12 | 35% | 2018-07-17 |  | 12.52 | -12.52 | 15.06% | 1st R/A
35 | 201384050-Improvement of Charkati- Baruikhali Shosan Ghat Road. Ch1000-2325 m. Salvage Cost Tk. 460221.00 | KDRIDP/Bager/W-47/2017-18 | 1.325 | 0 | 0 | 83.92 | 2017-10-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2017-11-13 | 88.12 | 100% | 2018-11-19 | 88.112 | 88.112 | 0 | 99.99% | Final
36 | 201384043-Development of Uttar Gopalpur- Kachua Araian Bridge Road. Ch.00-961 m. Salvage Cost TK. 475021.00 | KDRIDP/Bager/W-19/2016-17 | 0.961 | 0 | 0 | 70 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 73.4 | 100% | 2018-08-12 | 73.282 | 73.282 | 0 | 99.84% | Final
37 | 201384043-Improvement of Uttar Gopalpur FWC-Kachua Iron Bridge Road at Ch. 961m-1940m. Salvage Amount Tk.5,56,673.00 | KDRIDP/Bager/W-93/2017-18 | 0.979 | 0 | 0 | 65.57 | 2018-08-02 | M/S Rahamat Traders, Amlapara, Bagerhat | 2018-09-11 | 64.095 | 100% | 2019-09-17 | 61.511 | 61.511 | 0 | 95.97% | Final
| 201384019-Improvement of Madertala-Jobai Road at Ch. 972m-1722m. Salvage Amount Tk. 3,05,462.00 | KDRIDP/Bager/W-93/2017-18 | 0.75 | 0 | 0 | 75.95 |  | M/S Rahamat Traders, Amlapara, Bagerhat |  | 74.24 |  |  | 71.251 | 71.251 | 0 | 95.97%
38 | 201385059-Atharogati-Sardar Bari House to Ohidkhan road. | [13 empty] | 0 | #DIV/0!
39 | fatepur fultala(paddanagar)via brigde to habibshop | [13 empty] | 0 | #DIV/0!
Sharankhola
40 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Rd | [13 empty] | 0 | #DIV/0!
41 | 201774006: Improvement of Kadamtala Ashar alo Mosjid- Varanirper upgrade GPS Road Ch4885-5885m | KDRIDP/Bager/W-26/2017-18 | 1 | 0 | 0 | 56.797 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 54.46 | 100% | 2018-07-10 | 51.601 | 51.601 | 0 | 94.75% | Final
42 | 201774007: Nalbunia-Baniakhali road | [13 empty] | 0 | #DIV/0!
43 | 201774011-Improvement of Rajapur-Dhansagar Bazar Road by BC at Ch.505m-1875m. Salvage Amount Tk. 2,04,825.00 | KDRIDP/Bager/W-91/2017-18 | 1.37 | 0 | 0 | 89.544 | 2018-07-08 | M/S Habib Enterprise, Sundorghona, Bagerhat | 2018-08-27 | 92.9 | 100% | 2019-09-02 |  | 60.76 | -60.76 | 65.4% | 2nd R/A
| 201774048-Improvement of Rajapur WAPDA-Rajapur GC (Police Fary) Bazar Road by BC at Ch.675m-1450m. Salvage Amount Tk. 4,36,293.00 |  | 0.775 | 0 | 0 | 51.07 | 2018-07-08 | M/S Habib Enterprise, Sundorghona, Bagerhat |  | 52.99 |  |  |  | 34.66 | -34.66 | 65.41%
44 | 201774014-Amtoli-Badhal Road. | [13 empty] | 0 | #DIV/0!
45 | 201774018: Improvement of Golbunia Talukderbari-Motherper Ladenmor Road Ch2900-4300m. Salvage amount -tk.548997.00( fixed) | KDRIDP/Bager/W-27/2017-18 | 1.4 | 0 | 0 | 80.36 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 75.29 | 100% | 2018-07-10 | 73.384 | 73.384 | 0 | 97.47% | Final
46 | 201774022: Jhilbunia-Lakurtala road | [13 empty] | 0 | #DIV/0!
47 | 201774023: Khada -Lakurtala Road | [13 empty] | 0 | #DIV/0!
48 | 201774024: Improvement of Banglabazar-Tafalbari-Mourashi Road by BC at Ch. 1350m-3400m. Salvage Amount Tk. 2,10,068.00 | KDRIDP/Bager/W-112/2018-19 | 2.05 | 0 | 0 | 153.259 | [8 empty] | 0 | #DIV/0!
49 | 201774025: Improvement of Khada-North Tafalbari-Mourasi Bazar Road by BC at Ch.00m-2000m. Salvage Amount Tk. 3,78,627.00 (2nd Call) | KDRIDP/Bager/W-90/2017-18 | 2 | 0 | 0 | 135.226 | 2018-07-05 | M/S Noyan Enterprise, Sharankhola, Bagerhat | 2018-08-27 | 139.28 | 35% | 2019-09-02 |  | 28 | -28 | 20.1% | 1st R/A
50 | 201774035:Improvement of Bakultala-Sonatala Road by BC at Ch. 00m-1600m. Salvage Amount Tk. 9,48,202.00 | KDRIDP/Bager/W-113/2018-19 | 1.6 | 0 | 0 | 116.159 | [8 empty] | 0 | #DIV/0!
51 | 201774040: Improvement of Khontakata-Charerper Road by BC at Ch.1640m-3280m. Salvage Amount Tk. 388301.00 | KDRIDP/Bager/W-81/2017-18 | 1.64 | 0 | 0 | 112.27 | 2018-05-29 | M/S Sohana Enterprise, Sharankhola, Bagerhat | 2018-06-28 | 117.58 | 60% | 2019-07-04 |  | 45.971 | -45.971 | 39.1% | 2nd R/A
52 | 201775078-Improvement of Rajapur Bayor-Saver Madrasa via Gojen Roy House Road by BC at Ch.00m-1500m. Salvage Amount Tk. 572444.00 | KDRIDP/Bager/W-82/2017-18 | 1.5 | 0 | 0 | 97.406 | 2018-06-11 | M/S Sohana Enterprise, Sharankhola, Bagerhat | 2018-06-28 | 102.016 | 50% | 2019-07-04 |  | 31.75 | -31.75 | 31.12% | 2nd R/A
53 | 201774047-Improvement of Taltoli bazer-Nalbunia (Bezitana) bazer Road Ch1500-2505m. Salvage amount -tk.554716.00 (fixed) | KDRIDP/Bager/W-28/2017-18 | 1.005 | 0 | 0 | 62.45 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 58.02 | 100% | 2018-07-10 | 55.247 | 55.247 | 0 | 95.22% | Final
Morrelgonj
54 | 201604011-Chingrakhali-Dharadoha Rd. | [13 empty] | 0 | #DIV/0!
55 | 201604027 - Improvement of Gabagachia-Burujbaria road. Ch 500m-2150m. Salvage Cost Tk.49606.00. | KDRIDP/Bager/W-70/2017-18 | 1.65 | 0 | 0 | 127.54 | 2018-01-25 | Md. Shariful Alam, Fakirhat, Bagerhat | 2018-03-11 | 126.778 | 10% | 2019-03-17 |  |  | 0 | 0%
56 | 201604044 - R&H road (at Saralia wooden bridge)-Kutghata bazar. | [13 empty] | 0 | #DIV/0!
57 | 201604050 - Amtala bazar-Chandipur Highschool via Taltola bazar | [13 empty] | 0 | #DIV/0!
58 | 201604065 - Improvement of Srenikhali- Bashbaria road Paschim Kalikabari- C & B road ch800-2480m. Salvage amount tk.482190.00 fixed | KDRIDP/Bager/W-54/2017-18 | 1.68 | 0 | 0 | 123.3 | 2017-10-04 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-11-28 | 128.23 | 60% | 2019-05-31 |  | 61.77 | -61.77 | 48.17% | 2nd R/A
59 | 201604069 - Chingrakhali FRB Road-Khalkula-sagorkati | [13 empty] | 0 | #DIV/0!
60 | 201604072 - Improvement of Tulatola RHD near h/o M. Talukder-Uttttarjoka RHD ch4250-5140m. Salvage Amount Tk.502421.00 fixed | KDRIDP/Bager/W-53/2017-18 | 0.89 | 0 | 0 | 51.02 | 2017-10-03 | M/S Faruk Enterprise, Kachua, Bagerhat | 2017-11-19 | 53.54 | 100% | 2018-11-25 | 53.54 | 53.54 | 0 | 100% | Final
61 | 201604074 - Development of Bashbaria R & H to Mongolerhat. CH 00-1260 m. Salvage Cost. TK. 109498.00 | KDRIDP/Bager/W-21/2016-17 | 1.26 | 0 | 0 | 100.49 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-07 | 104.567 | 100% | 2018-08-29 | 104.426 | 104.426 | 0 | 99.87% | Final
62 | 201604088 - Panchakaran UP office to Sonakhali bazar | [13 empty] | 0 | #DIV/0!
63 | 201604098 - Chairman Bazar-RHD road via H/O Master Abul Kashem | [13 empty] | 0 | #DIV/0!
64 | 201605121--Daskhali RHD-Shoilkhali Bazar | [13 empty] | 0 | #DIV/0!
65 | 201605095-Kalibari Bazar - Srizon Smriti high School via Mothbaria School Road. | [13 empty] | 0 | #DIV/0!
66 | 201605124-Improvement of Nurul Islam Dakhil Madrasa-Gulishakhali UP office via Sonamuddin Chokidar Bari by BC Road from Ch. 00m-2500m. Salvage Amount Tk. 3,56,993.00 | KDRIDP/Bager/W-98/2018-19 | 2.5 | 0 | 0 | 228.918 | 2018-11-22 | M/S Jharna Enterprise, 13 Dharmashava cross road, Khulna. | 2019-01-02 | 227.95 | 10% | 2020-01-08 |  |  | 0 | 0% | Re-tender dt. 03.04.18
67 | 201605004-Development of Kalikabari- Guabaria Road. Ch 220 - 2776 m | KDRIDP/Bager/W-09/2016-17 | 2.556 | 0 | 0 | 209.99 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-11 | 217.576 | 20% | 2019-05-31 |  | 8.75 | -8.75 | 4.022% | 1st R/A
68 | 201604140-Improvement of Badshar hat C & B- Hasan Member bari Mazibari road via Tassen Uddin Howlader bari road. Ch00m-2130m. Salvage Cost Tk.172678.00. | KDRIDP/Bager/W-69/2017-18 | 2.13 | 0 | 0 | 153.08 | 2018-01-30 | Sayed Milon, Post office road, Jhalokathi. | 2018-02-20 | 157.599 | 40% | 2019-05-09 |  | 62.25 | -62.25 | 39.5% | 2nd R/A
69 | 201605061-Improvement of Sleeper bridge Near RHD North Balvadrapur Shasapara via Tripolli RNGPS ch 00-1482m | KDRIDP/Bager/W-55/2017-18 | 1.482 | 0 | 0 | 104.457 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 108.63 | 60% | 2019-11-30 |  | 56.63 | -56.63 | 52.13% | 2nd R/A
70 | 201605124-Improvement of NUrul Islam Dhakil Madrasha Gulishakhali UP Office via Sona Muddin Chokider bari road. | [13 empty] | 0 | #DIV/0!
71 | 201604063-Morrelganj-Bisarighata | [13 empty] | 0 | #DIV/0!
72 | 201605165-W.Kachubunia Primary School Road. | [13 empty] | 0 | #DIV/0!
Fakirhat
73 | 201344004- Khulna Mollahat R&H at Talerpukur pagla deapara | [13 empty] | 0 | #DIV/0!
74 | 201344008-Improvement of Khazura R &H-Bolloppur Road. Ch1194-2650m. Salvage Cost-103999.00(fixed) | KDRIDP/Bager/W-24/2017-18 | 1.456 | 0 | 0 | 84.83 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 79.3 | 100% | 2018-07-18 | 79.3 | 79.3 | 0 | 100% | Final
75 | 201344009-Lockpur Ballata-Bollopur village rd | [13 empty] | 0 | #DIV/0!
76 | 201344013- Shibbari-Dohor Moubog Road | [13 empty] | 0 | #DIV/0!
77 | 201344014- Mollar bazar-Bangopar bazar via Tekatia road | [13 empty] | 0 | #DIV/0!
78 | 201344018 - Betaga bazar-pasur river via Chakuli Pry.school road | [13 empty] | 0 | #DIV/0!
79 | 201344024 - Singati Gilatala road upto C&B Bazer | [13 empty] | 0 | #DIV/0!
80 | 201344026 - Kanarpukur-Deapara Rd | [13 empty] | 0 | #DIV/0!
81 | 201344042 - Singati-Baliadanga road | [13 empty] | 0 | #DIV/0!
82 | 201344061- Nawapara Baloyer Dokan-Syambagat Rd | [13 empty] | 0 | #DIV/0!
83 | 201344088-Kanarpukur-Satshikha Rd | [13 empty] | 0 | #DIV/0!
Chitalmari
84 | 201144020-Kirtankhali - Kharamkhali road (via Khasherhat GC) Road. | [13 empty] | 0 | #DIV/0!
85 | 201144011 - Development of Moidah Shibpur Club- Kaligati Road. Ch 00-878. Salvage Cost TK. 404704.00 | KDRIDP/Bager/W-15/2016-17 | 0.878 | 0 | 0 | 61.46 | 2017-07-10 | M/S S.S. Traders, Tungipara, Gopalgonj | 2017-08-24 | 59.92 | 100% | 2018-08-30 | 59.87 | 59.87 | 0 | 99.92% | Final
86 | 201144023 - Chinguri kheaghat-Krishi Bank-Kalatala road | [13 empty] | 0 | #DIV/0!
87 | 201144032 - Development of Khaserhat- Asoknagar Road. Ch 2300-4595 m. Salvage Cost TK. 433415.00 | KDRIDP/Bager/W-13/2016-17 | 2.295 | 0 | 0 | 147.91 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 143.47 | 100% | 2018-08-29 | 142.57 | 142.57 | 0 | 99.37% | Final
88 | 201144033-Development of Shampara- Kudari via Panchpara Hat Road. Ch 1000-2550 m. Salvage Cost TK. 796234.00 | KDRIDP/Bager/W-12/2016-17 | 1.55 | 0 | 0 | 140.03 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 135.17 | 100% | 2018-08-29 | 126.446 | 126.446 | 0 | 93.55% | Final
89 | 201144049-Development of Barobaria at RHD Road-Ghola High School-Baroguni bazar Road. Ch 00-1700 m. Salvage Cost TK. 261420.00 | KDRIDP/Bager/W-14/2016-17 | 1.7 | 0 | 0 | 105.59 | 2017-07-10 | Md. Iqbal Hossain, Tungipara, Gopalgonj. | 2017-08-06 | 101.05 | 100% | 2018-08-29 | 100.98 | 100.98 | 0 | 99.93% | Final
90 | 201145027-Improvement of Hizla Sheikpara- Agakhal RPS Road. Ch 00 -1275m. Salvage Cost TK. 618000.00 | KDRIDP/Bager/W-64/2017-18 | 1.275 | 0 | 0 | 103.13 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-02-06 | 92.82 | 100% | 2019-02-12 | 90.1 | 90.1 | 0 | 97.07% | Final
Mongla
91 | 201584014 - Khaserdanga more-Kharkharia-Dewotala bazar | [13 empty] | 0 | #DIV/0!
92 | 201584021-Bashtala bazar-Digraj bazar Rd. | [13 empty] | 0 | #DIV/0!
93 | 201584030 - Chila hat-Monumia High School-Katakhali-Joymoni Battola | [13 empty] | 0 | #DIV/0!
94 | 201584040 - Improvement of Mongla ( Fire brigate)- Malgazi C.S- Moukhali (GCCR).. (Ch:3100.00-4250m). Salvage Cost Tk. 153808.00 | KDRIDP/Bager/W-92/2017-18 | 1.15 | 0 | 0 | 85.497 | 2018-06-24 | M/S Bhi Bhi Enterprise, Mongla, Bagerhat | 2018-08-05 | 93.334 | 50% | 2019-08-11 |  | 39.54 | -39.54 | 42.36% | 2nd R/A
| 201584044 - Improvement of Holdibunia Baliar more-Burburia via malgazi-hid office Road. Ch3300m-4500m. Salvage Cost Tk.2220602.00 |  | 1.2 | 0 | 0 | 88.178 |  | M/S Bhi Bhi Enterprise, Mongla, Bagerhat |  | 96.26 |  |  |  | 40.77 | -40.77 | 42.35%
95 | 201584045 - Development of Digraj College - Burirdanga FWC Ch. 650-2380 m. Salvage Cost. Tk. 2023367.00 | KDRIDP/Bager/W-11/2016-17 | 1.73 | 0 | 0 | 112.53 | 2017-06-13 | Sardar Jashim, Kharder, Bagerhat | 2017-08-02 | 118.01 | 70% | 2019-06-14 |  | 80.99 | -80.99 | 68.63% | 2nd R/A
96 | 201584071 - Sonailtola UP Office - Bokultola | [13 empty] | 0 | #DIV/0!
97 | 201584094 - Madurpalta Govt. Pond Road | [13 empty] | 0 | #DIV/0!
98 | 201584103 - Digraj bazar - Kitunia Bazar Road | [13 empty] | 0 | #DIV/0!
99 | 201584068-Improvement of Kumerkhali Bridge to Narkeltola Bridge to Masmara Village Road. Ch 0.00 -1895 m. Salvage Cost Tk. 4079725.00 | KDRIDP/Bager/W-66/2017-18 | 1.895 | 0 | 0 | 135.11 | 2018-01-24 | M/S Iqbal Enterprise, Mongla, Bagerhat | 2018-03-07 | 141.5 | 100% | 2019-03-13 | 140.06 | 140.06 | 0 | 98.98% | Final
Mollahat
100 | 201564022-Kahalpur RHD-Joydehihat | [13 empty] | 0 | #DIV/0!
101 | 201564090 - Improvement of Singati-Capil Bridge Road. Ch 500-920 m Under Mollahat Upazila Bagerhat. | KDRIDP/Bager/W-39/2017-18 | 0.42 | 0 | 0 | 26.66 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 23.996 | 100% | 2018-11-21 | 18.997 | 18.997 | 0 | 79.17% | Final
102 | 201564005 - Boaliahat-Kahalpur R&H Rd. | [13 empty] | 0 | #DIV/0!
103 | 201564007 - Improvement of Rajpat - Gaola UP Road. Ch 1062-2900 m. Salvage Cost. TK. 1386398.00 | KDRIDP/Bager/W-38/2017-18 | 1.838 | 0 | 0 | 111.297 | 2017-09-28 | M/S Rubel Enterprise, Rajoir, Madaripur | 2017-11-15 | 100.167 | 100% | 2018-11-21 |  | 86.7 | -86.7 | 86.56% | 3rd R/A
104 | 201564013 - Improvement of Charkuliahat-Takiarkul Road by BC at Ch. 2000m-2950m. Salvage Amount Tk. 2,99,882.00 | KDRIDP/Bager/W-115/2018-19 | 0.95 | 0 | 0 | 72.65 | [8 empty] | 0 | #DIV/0!
| 201565018 - Improvement of Kahalpur Barapukurpar-Kahalpur H/School via Omar Moulana House Road by BC at Ch. 1002m-1464m |  | 0.462 | 0 | 0 | 33.586 | [8 empty] | 0 | #DIV/0!
105 | 201564016 - Atjuri UP-Kadamtala Kheyaghat | [13 empty] | 0 | #DIV/0!
106 | 201564039 - Boalia RHD-Bhandarkhola hat(Atjuri UP) | [13 empty] | 0 | #DIV/0!
107 | 201564047 - Improvement of Garfa- Girishnagar-Kadamtala Khayaghat Road. Ch 4100-4900 m Under Mollahat Upazila Bagerhat. Salvage Cost. TK. 114374.00 | KDRIDP/Bager/W-40/2017-18 | 0.8 | 0 | 0 | 46.965 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 42.27 | 100% | 2018-11-21 | 42.26 | 42.26 | 0 | 99.98% | Final
108 | 201565009 - Improvement of Chaulturi-Kodalia Bill Road. Ch 880-2255 m | KDRIDP/Bager/W-41/2017-18 | 1.375 | 0 | 0 | 77.9 | 2017-09-27 | Shikder Zahidul Islam, Mollahat, Bagerhat. | 2017-11-15 | 70.11 | 100% | 2018-11-21 | 70.11 | 70.11 | 0 | 100% | Final
109 | 201565079 - Improvement of Shason Sobed Molla House-Jamai More Road by BC at Ch. 1000m-1280m & 1380m-1700 | KDRIDP/Bager/W-116/2018-19 | 0.6 | 0 | 0 | 43.039 | 2019-06-11 | M/S Abu Bokkar Timber Traders, Fakirhat, Bagerhat |  | 40.887 |  |  |  |  | 0 | 0% | NOA issued on 02.07.19
| 201565022 - Improvement of Kahalpur Charpara Road by BC at Ch. 1000m-1300m Salvage Amount Tk. 1,93,297.00 |  | 0.3 | 0 | 0 | 21.58 |  | M/S Abu Bokkar Timber Traders, Fakirhat, Bagerhat |  | 20.5 |  |  |  |  | 0 | 0%
110 | 201565017 - Kahalpur Alek house-Kutimia house | [13 empty] | 0 | #DIV/0!
111 | 201564096-Uddaypur Uttar kandy Pacca road-Uddaypur Uttar Kandy GPS-Uttar kandy Graveyard with link of H/O Kamal Molla road. | [13 empty] | 0 | #DIV/0!
Rampal
112 | 201734104-Banshtali UP-Solakora | [13 empty] | 0 | #DIV/0!
113 | 201734018-Improvement of Kismat Kumlai-Saguna road Ch00-2080m by BC. Salvage amount Tk.2388545.00Fixed | KDRIDP/Bager/W-45/2017-18 | 2.08 | 0 | 0 | 154.76 | 2017-11-13 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 166.37 | 50% | 2019-12-22 |  | 65.83 | -65.83 | 39.57%
114 | 201734028-Sakurhat-Saguna Rd. | [13 empty] | 0 | #DIV/0!
115 | 201734032-Telikhali-Baruipara Rd. | [13 empty] | 0 | #DIV/0!
116 | 201734038-Development of KataKhali P/S - Dakra Road By HBB. Ch 1000-1650 m. Salvage Cost. TK.454832.00(2nd call) | KDRIDP/Bager/W-05/2016-17 | 0.65 | 0 | 0 | 21.95 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 23.6 | 100% | 2018-08-20 | 23.108 | 23.108 | 0 | 97.92% | Final
117 | 201734042-Development of Dakhin Mollikerber-Dhalipara Road By HBB. Ch 1140- 2950 m Under Rampal Upazila Bagerhat. Road ID No. 201734042. Salvage Cost. TK.333359. (2nd call) | KDRIDP/Bager/W-97/2018-19 | 1.81 | 0 | 0 | 112.347 | 2018-11-19 | Abul Kalam Azad, Terokhada, Khulna | 2018-12-31 | 106.73 | 90% | 2020-01-06 |  | 91.8 | -91.8 | 86.01% | 2nd R/A
118 | 201734046-Rajnagor-Gorerdanga Road | [13 empty] | 0 | #DIV/0!
119 | 201734066-Foyla-Baburhat. | [13 empty] | 0 | #DIV/0!
120 | 201734068-Amtala bazar-Pabantala Bazar | [13 empty] | 0 | #DIV/0!
121 | 201734129-Development of Nolbunia borun BishasTran Bridge house-Babur bari bus Stand Road By BC. Ch (1915-2385m). Salvage Cost. TK.306072.00 (2nd call) | KDRIDP/Bager/W-07/2016-17 | 0.47 | 0 | 0 | 37.26 | 2017-11-13 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-01-04 | 40.15 | 100% | 2018-10-10 | 39.553 | 39.553 | 0 | 98.51% | Final
122 | 201735195-Development of Banga-Gilatola GC-Sorder Bari More-Hospital link Road Ch00-570m under Rampal Upazila District-Bagerhat Road ID No201735195 Salvage amount Tk.164834fixed | KDRIDP/Bager/W-59/2017-18 | 0.57 | 0 | 0 | 35.37 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 37.09 | 0% | 2018-11-06 |  |  | 0 | 0% | PD memo no. 663 dt. 10/03/19 Contract Cancelled due to Site problem
Total |  |  | 87.171 | 0 | 0 | 6385.382 |  |  |  | 5824.754 | 80.35% |  | 3016.82 | 3870.801 | -853.981 | 66.45%
Improvement of Village Road by HBB
Kachua
1 | 201384051-Improvement of Bisherkhola-Bottola School Road by HBB at Ch.00m-2533m. Salvage Amount Tk. 845746.00 | KDRIDP/Bager/W-89/2017-18 | 2.533 | 0 | 0 | 162.366 | 2018-05-24 | M/S Rina Enterprise, Fultola, Bagerhat | 2018-06-25 | 161.96 | 50% | 2019-12-01 |  | 47.79 | -47.79 | 29.51% | 2nd R/A
Sharankhola
2 | 201774013-Improvement of Purba Khontakata-Nalbunia Road by HBB at Ch.00m-1378m & 2818m-4090m. Salvage Amount Tk. 2312135.00 | KDRIDP/Bager/W-83/2017-18 | 2.65 | 0 | 0 | 111.809 | 2018-05-13 | M/S Chan Enterprise, Puraton Bazar, Bagerhat | 2018-06-18 | 116.84 | 20% | 2019-06-24 |  |  | 0 | 0%
Morrelgonj
3 | 201605021-Mohonpur-Banagramme Rd. | [13 empty] | 0 | #DIV/0!
4 | 201604098-Moslem khan's house - Gharami bari bridge Rd. | [13 empty] | 0 | #DIV/0!
5 | 201604140-Badshar hat C & B - Hasan Member bari (Mazibari) road via Tassen Uddin Howlader bari | [13 empty] | 0 | #DIV/0!
Fakirhat
6 | 201344006-Bahirdia-satbaria road. | [13 empty] | 0 | #DIV/0!
7 | 201344088-Bahirdia UP office to Weast Bahirdia GPS Rd. | [13 empty] | 0 | #DIV/0!
Mongla
8 | 201584030-Chila hat-Monumia High School-Katakhali-Joymoni Battola Rd. | [13 empty] | 0 | #DIV/0!
9 | 201584075- Khulna Mongla RHD Gania Bridge to Burirdanga Up Office via Kapalirmat Road. | [13 empty] | 0 | #DIV/0!
Rampal
10 | 201734046-Development of Rajnagar-Gorerdanga Road By HBB. Ch 1000-1970 m. Salvage Cost. TK.226330.00(2nd Call) | KIDRIDP/Bager/W-06/2016-17 | 0.97 | 0 | 0 | 33.34 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 35.83 | 100% | 2018-08-20 |  | 29.22 | -29.22 | 81.55% | 2nd R/A
11 | 201734033-Improvement of Modnakhali-Khayghat-East Banstali cyclone shelter road Ch500-2000m by HBB Salvage amount Tk.592188.00 Fixed | KDRIDP/Bager/W-43/2017-18 | 1.5 | 0 | 0 | 67.54 | 2017-09-27 | M/S Ziaul & Brothers, Bhandaria, Perojpur | 2017-11-14 | 67.33 | 100% | 2018-11-20 | 67.141 | 67.141 | 0 | 99.72% | Final
12 | 201734139-Srifaltala new market-Veternary hospital via sarner field. | [13 empty] | 0 | #DIV/0!
13 | 201734135-Sreefultola bridge - Jahanjhaia Hospatal Road. | [13 empty] | 0 | #DIV/0!
Chitalmari
14 | 201145133-Improvment of HBB Road at Umajuri Pachimpara road-Umajuri Bottala Hasans House Road Ch00-620m. Salvage Cost Tk.-129789.00(fixed) | KDRIDP/Bager/W-30/2017-18 | 0.62 | 0 | 0 | 26.72 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 26.72 | 100% | 2018-07-22 | 26.58 | 26.58 | 0 | 99.48% | Final
15 | 201145115-Improvement of HBB Road at Baburhat Khayaghat Chursta -Hanif Sheks house road. Ch00-510m | KDRIDP/Bager/W-33/2017-18 | 0.51 | 0 | 0 | 18.42 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-11-21 | 18.42 | 100% | 2018-08-27 | 18.42 | 18.42 | 0 | 100% | Final
16 | 201145114-Improvement of Besharkhola (Bottola)-Bottola Abdul Gazi house road via Sultan Chairman road Ch750-1590m by BC | KDRIDP/Bager/W-42/2017-18 | 0.84 | 0 | 0 | 49.346 | 2017-09-25 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-15 | 44.41 | 100% | 2018-11-21 | 44.23 | 44.23 | 0 | 99.59% | Final
17 | 201145116-Improvement of HBB Road at Bottola Khuria AKub Sheks house Katchuria Baser Gazi house road. Ch00-926m. Salvage Cost. TK. -338716.00 | KDRIDP/Bager/W-34/2017-18 | 0.926 | 0 | 0 | 34.41 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 34.39 | 100% | 2018-07-16 | 34.38 | 34.38 | 0 | 99.97% | Final
18 | 201145121-Improvement of Bottola Bazar (Mozam Mistry Bari)- Khuria Motin House Road Ch00-670 m. Salvage Cost-2,31,118.00 | KDRIDP/Bager/W-23/2017-18 | 0.67 | 0 | 0 | 39.58 | 2017-08-17 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-10-09 | 35.62 | 100% | 2018-07-15 | 34.61 | 34.61 | 0 | 97.16% | Final
19 | 201145106-Improvement of Babuana of Shantos pur Lararkul Road Lalrarkul primary School Road By HBB. Ch 00-800 m | KDRIDP/Bager/W-61/2017-18 | 0.8 | 0 | 0 | 56.88 | 2018-05-17 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-06-05 | 59.298 | 100% | 2019-06-10 | 59.083 | 59.083 | 0 | 99.64% | Final
20 | 201144024-Improvement of HBB Road at KirtonKhali Santoshpur R&H road. Ch. 2875-3235m. Salvage amount tk.1,91,274.00 (fixed) | KDRIDP/Bager/W-32/2017-18 | 0.36 | 0 | 0 | 13.94 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 13.93 | 100% | 2018-07-16 | 13.866 | 13.866 | 0 | 99.54% | Final
21 | 201144006-Improvement of Santospur Uttar LararculSantospur primary School road Road By HBB. Ch 1600-2470 m | KDRIDP/Bager/W-60/2017-18 | 0.87 | 0 | 0 | 51.31 | 2017-12-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 55.9 | 100% | 2018-11-11 | 55.77 | 55.77 | 0 | 99.77% | Final
22 | 201144059-Improvement of HBB Road at Kaligonj Bazar-Bashbaria road. Ch00-1260m. Salvage Cost Tk.-356489.00 | KDRIDP/Bager/W-31/2017-18 | 1.26 | 0 | 0 | 53.938 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 53.94 | 100% | 2018-07-22 | 52.83 | 52.83 | 0 | 97.94% | Final
23 | 201145137-Improvement of Bottola Satghor jame Mosque- Motin Sheikh wooden bridge Road By HBB. Ch 00-570 m | KDRIDP/Bager/W-62/2017-18 | 0.57 | 0 | 0 | 46.11 | 2017-12-26 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-02-05 | 48.34 | 100% | 2018-11-11 | 48.25 | 48.25 | 0 | 99.81% | Final
24 | 201145108-Improvement of Umazuri- Kachuria pry. Regd. School- Kachuuria Road by HBB. Ch 00- 2560 m | KDRIDP/Bager/W-57/2017-18 | 2.56 | 0 | 0 | 147.65 | 2017-10-16 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-16 | 147.64 | 100% | 2018-11-22 | 146.734 | 146.734 | 0 | 99.39% | Final
25 | 201144029-Kaligonj-Kachuria Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 17.639 | 0 | 0 | 913.359 |  |  |  | 920.568 | 91.33% |  | 601.894 | 678.904 | -77.01 | 73.75%
Construction of Bridge on Upazila Road (7.30m width)
Sharankhola
1 | 201772004-Construction of 42.00m Long RCC Girder Bridge at Amragachia RHD-Banglabazar GC Road at Ch 4200m | KDRIDP/Bager/B-11/2017-18 | 0 | 42 | 0 | 235.666 | 2018-05-09 | EFTE.ETCL (PVT.) LIMITED, Eastern Paradise, 35, Segun Bagicha, Suit-302, (3rd Floor) Shahbag, Dhaka | 2018-12-13 | 246.85 | 0% | 2019-12-19 |  |  | 0 | 0%
2 | 201772007-Construction of 22.00m Long RCC Girder Bridge at Tafalbari GC- Rasulpur GC- Rajapur GC- Pollanbari RHD Road at Ch 1215m | KDRIDP/Bager/B-08/2017-18 | 0 | 22 | 0 | 183.14 | 2018-05-09 | EFTE.ETCL (PVT.) LIMITED, Eastern Paradise, 35, Segun Bagicha, Suit-302, (3rd Floor) Shahbag, Dhaka | 2018-12-13 | 192.208 | 0% | 2019-12-19 |  |  | 0 | 0%
Mollahat
3 | 201552009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | [13 empty] | 0 | #DIV/0!
4 | 201562009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | [13 empty] | 0 | #DIV/0!
5 | 201562009-Construction of 30.00m Long RCC Girder Bridge at Gawla-Kodalia Bazar Road at Ch 3300m. | KDRIDP/Bager/B-12/2017-18 | 0 | 30 | 0 | 215.987 | 2018-06-13 | M/S Kamrul & Brothers, Gopalgonj | 2018-08-02 | 226.57 | 85% | 2019-08-08 |  | 181 | -181 | 79.89% | 2nd R/A
Rampal
6 | 201732010-Construction of 60.00m Long RCC Girder Bridge on Balai Bridge-Rampal Road at Ch 3940m | KDRIDP/Bager/B-01/2017-18 | 0 | 60 | 0 | 358.53 | 2018-04-10 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-05-23 | 392.51 | 35% | 2019-05-29 |  | 111.29 | -111.29 | 28.35% | 2nd R/A
7 | 201732004-Construction of 30.00m Long RCC Girder Bridge on Foyla hat-Chaksree GC Road at Ch 841m | KDRIDP/Bager/B-06/2017-18 | 0 | 30 | 0 | 192.018 | 2018-08-13 | IT & JE JV, 13 Dharmashava cross road, Khulna. | 2018-10-09 | 210.4 | 0% | 2019-10-15 |  |  | 0 | 0%
Mongla
8 | 201582007-Construction of 28.00m Long PSC Girder Bridge on Digiraj-Jhalmalia Dhigi Road at Ch 3980m | KDRIDP/Bager/B-03/2017-18 | 0 | 28 | 0 | 176 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. | 2018-07-28 | 190.38 | 75% | 2019-08-04 |  | 105.11 | -105.11 | 55.21% | 3rd R/A
9 | 201582006-Construction of 90.00m Long PSC Girder Bridge on Chaterhat GC-Banshtola GC-Joymonirghol Baddamary Road at Ch 6600m | KDRIDP/Bager/B-05/2017-18 | 0 | 90 | 0 | 569.596 | 2018-04-18 | M/S Abul Kalam Azad, Patuakhali | 2018-06-06 | 624.509 | 0% | 2019-12-31 |  |  | 0 | 0%
Bagerhat Sadar
10 | 201082012-Construction of 42.00m Long RCC Girder Bridge at Chulkath R&H- Faila GC via Ranjeetpur road Sadar Part Road at Ch 6898m. | KDRIDP/Bager/B-13/2017-18 | 0 | 42 | 0 | 232.74 | 2018-06-13 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-08-05 | 231 | 20% | 2019-08-11 |  |  | 0 | 0%
Total |  |  | 0 | 344 | 0 | 2163.677 |  |  |  | 2314.427 | 26.88% |  | 0 | 397.4 | -397.4 | 17.17%
Construction of Bridge on Union Road/Village Road (5.50m width)
Kachua
1 | 201383005-Construction of RCC Bridge on Fatehpur Bazar-Gopalpur UP -Fultala Bazar Road. | [13 empty] | 0 | #DIV/0!
2 | 201384050-Construction of RCC Box culvert 5.00mx3.50m at Ch. 1762m on Charkati-Baruikhali Shosan Ghat | KDRIDP/Bager/W-76/2017-18 | 0 | 5 | 0 | 13.07 | 2017-12-26 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 11.76 | 100% | 2018-10-11 | 11.76 | 11.76 | 0 | 100% | Final
Sharankhola
2 | 201774020-Construction of 30.00m Long RCC Girder Bridge on South Amragachia-Jibanduari Road at Ch 3500m. (201774019) | KDRIDP/Bager/B-07/2017-18 | 0 | 30 | 0 | 213.51 | 2018-05-09 | EFTE.ETCL (PVT.) LIMITED, Eastern Paradise, 35, Segun Bagicha, Suit-302, (3rd Floor) Shahbag, Dhaka | 2018-12-13 | 223.976 | 0% | 2019-12-19 |  |  | 0 | 0%
Morrelgonj
3 | 201603021-Construction of 22.00m Long RCC Girder Bridge on Putikhali U.P.-Panchakaran UP via Gazalia bazar Road at Ch 2738m. | KDRIDP/Bager/B-14/2017-18 | 0 | 22 | 0 | 195.2 | 2018-08-13 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-10-09 | 203.008 | 60% | 2019-10-15 |  | 113.07 | -113.07 | 55.7% | 2nd R/A
4 | 201605020-Construction of 13.00m Long RCC Girder Bridge on Balavadrapur (Badhal Bazar)-Mohonpur Road at Ch 4200m | KDRIDP/Bager/B-16/2018-19 | 0 | 13 | 0 | 85.77 | [8 empty] | 0 | #DIV/0! | Chainage Problem
5 | 201604098-Const. of RCC Bridge on Moslem khan's house - Gharami bari bridge Road. | [13 empty] | 0 | #DIV/0!
6 | 201603006-Construction of 54.00m Long RCC Girder Bridge on Baharbunia U.P-Shonirjore Bazer Near the House of Talukder Mustafizur Rahman Road at Ch 1191m | KDRIDP/Bager/B-09/2017-18 | 0 | 54 | 0 | 306.29 | 2018-06-04 | MKB-MSE (JV), Nalchity, Jhalakati | 2018-07-29 | 325 | 40% | 2019-08-04 |  | 105.69 | -105.69 | 32.52% | 2nd R/A
7 | 201605061-Improvement of Sleeper Bridge near RHD north Balvadrapur Shahapara via Tripolli RNGPS. | [13 empty] | 0 | #DIV/0!
Chitalmari
8 | 201143006-Construction of 17.00m Long RCC Girder Bridge on Chinguri hat-Kalatala UP-Banglabazar Road at Ch 8090m. | KDRIDP/Bager/B-10/2017-18 | 0 | 17 | 0 | 141.19 | 2018-05-09 | M/S Kamrul & Brothers, Gopalgonj | 2018-06-25 | 140.999 | 80% | 2019-07-01 |  | 107.39 | -107.39 | 76.16% | 2nd R/A
9 | 201144029-Const. of RCC Box Culvert 1vX1.00X1.00m , 2vX4.00X4.00m & 1vX4.30X3.60m at Kaligonj-Kachuria Road | KDRIDP/Bager/W-63/2017-18 | 0 | 13.3 | 0 | 48.27 | 2017-11-13 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2018-01-04 | 43.44 | 100% | 2019-01-10 | 42.25 | 42.25 | 0 | 97.26% | Final
10 | 201145121-Const. of RCC Box Culvert 2vX4.00X4.00m over canal at Bottola Bazar (Mozam Mistry Bari)-Khuria Motin House road. | KDRIDP/Bager/W-65/2017-18 | 0 | 8 | 0 | 23.61 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-01-04 | 21.25 | 100% | 2019-01-10 | 21.18 | 21.18 | 0 | 99.67% | Final
Rampal
9 | 201734069-Construction of 48.00m Long RCC Girder Bridge on Gourbamha G.C-Konyadubi Kheya Ghat Road at Ch 1850m. | KDRIDP/Bager/B-15/2018-19 | 0 | 48 | 0 | 315.599 | 2018-10-08 | M/S Mohiuddin Ahmed, Patuakhali | 2018-12-02 | 343.999 | 0% | 2019-12-08 |  |  | 0 | 0%
10 | 201734069-Gourbamha G.C-Konnadubi kheya ghat | [13 empty] | 0 | #DIV/0!
Mongla
11 | 201584044-Construction of 22.00m Long RCC Girder Bridge on Holdibunia (Baliar more)-Burburia via Malgazi-Hid office Road at Ch 2900m | KDRIDP/Bager/B-02/2017-18 | 0 | 22 | 0 | 177.85 | 2018-02-20 | M/S Mizan Enterprise, Madaripur | 2018-04-11 | 184.07 | 60% | 2019-04-17 |  | 85.99 | -85.99 | 46.72% | 2nd R/A
12 | 201584035-Construction of 25.00m Long PSC Girder Bridge on Banshtala Bridge Pakhimara Khal-Shikari Houst at Burburia Road at Ch 1510m | KDRIDP/Bager/B-04/2017-18 | 0 | 25 | 0 | 196 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. | 2018-07-28 | 212.98 | 60% | 2019-08-04 |  | 89.99 | -89.99 | 42.25% | 2nd R/A
Total |  |  | 0 | 257.3 | 0 | 1716.359 |  |  |  | 1710.482 | 60% |  | 75.19 | 577.32 | -502.13 | 33.75%
Maintenance
Bagerhat Sadar
1 | 201083011-Periodic Maintenance of Baroipara UP Office-Haderhat Bazar via Kartickdia Bazar Road at Ch. 00m-2450m. | KDRIDP/Bager/M-19/2018-19 | 2.45 | 0 | 0 | 55.496 | 2018-11-26 | Syed Ziaul Hoque, Kazdia, Rupsha, Khulna. | 2019-01-06 | 52.72 | 100% | 2019-07-12 | 52.695 | 52.695 | 0 | 99.95% | Final
2 | 201084002 Periodic Maintenance of Dashani(R&H)-Shatgambuj UZR-via Upazila HQ Road from Ch. 2780m-4540m. | KDRIDP/Bager/M-13/2017-18 | 1.76 | 0 | 0 | 33.68 | 2018-04-26 | M/S A. Samad Traders, Sharankhola, Bagerhat | 2018-05-30 | 31.996 | 65% | 2019-06-05 |  | 19.117 | -19.117 | 59.75% | 1st R/A
| 201084048-Periodic Maintenance of Nonadanga-Krishnanagar Road from Ch. 00m-780m. | KDRIDP/Bager/M-13/2017-18 | 0.78 | 0 | 0 | 11.829 |  |  |  | 11.24 |  |  |  | 6.715 | -6.715 | 59.74%
| 201084087-Periodic Maintenance of Khanpur UP-Uttor Khanpur UHC Road from Ch. 00m-1420m | KDRIDP/Bager/M-13/2017-18 | 1.42 | 0 | 0 | 29.936 |  |  |  | 28.44 |  |  |  | 16.993 | -16.993 | 59.75%
3 | 201084005 Periodic Maintenance of Mathabhanga R & H-Sukdara bus stand via Sunagar from Ch. 850m-4212m. | KDRIDP/Bager/M-12/2017-18 | 3.36 | 0 | 0 | 51.24 | 2018-04-26 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-05-23 | 48.678 | 100% | 2019-05-29 | 48.66 | 48.66 | 0 | 99.96% | Final
| 201084036 Periodic Maintenance of C & B bazar-Shaawliabag mazar Road at H/O Mayor Mr.Tayyab from Ch. 00m-1339m. | KDRIDP/Bager/M-12/2017-18 | 1.339 | 0 | 0 | 28.446 |  |  |  | 27.024 |  |  | 27.01 | 27.01 | 0 | 99.95%
| 201084045 Periodic Maintenance of Bagerhat Pallibidyut DC rd-Polghat-Monigonj ferrighat Road from Ch. 00m-1520m. | KDRIDP/Bager/M-12/2017-18 | 1.52 | 0 | 0 | 25.936 |  |  |  | 24.639 |  |  | 24.62 | 24.62 | 0 | 99.92%
4 | 201084082-Periodic Maintenance of Noapara bazar- Baitpur R&H Road at Ch. 1355m-2700m. | KDRIDP/Bager/M-18/2018-19 | 1.35 | 0 | 0 | 35.455 | 2018-11-25 | M/S Joy Enterprise, Basabati, Bagerhat | 2019-01-07 | 33.68 | 15% | 2019-07-13 |  |  | 0 | 0%
Kachua
5 | 201382008-Periodic Maintenance of Maddham Teligati-Malomgacha-Brhmankathi-Kakarbill Kachua Part from Ch. 00m-2233m | KDRIDP/Bager/M-08/2017-18 | 2.233 | 0 | 0 | 41.037 | 2018-04-03 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-04-26 | 38.98 | 100% | 2018-12-17 | 38.98 | 38.98 | 0 | 100% | Final
6 | 201383005-Periodic Maintenance of Fatehpur bazar-Gopalpur UP-Fultala bazar Road from Ch. 2584m-4794m & 7100m-8086m. | KDRIDP/Bager/M-09/2017-18 | 3.196 | 0 | 0 | 47.02 | 2018-04-04 | M/S Mou Enterprise, Kharder, Bagerhat | 2018-08-05 | 44.67 | 100% | 2018-12-30 | 44.66 | 44.66 | 0 | 99.98% | Final
7 | 201383006.Gopulpur UP-Natunhat Bazar Road | [13 empty] | 0 | #DIV/0!
8 | 201383007.Kachua UP-Natun hat bazar | [13 empty] | 0 | #DIV/0!
9 | 201383008-Periodic Maintenance of Badhal UP-Atharogati bazar Road from Ch. 00m-915m | KDRIDP/Bager/M-10/2017-18 | 0.915 | 0 | 0 | 17.339 | 2018-04-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-04-26 | 16.47 | 100% | 2018-12-17 | 16.47 | 16.47 | 0 | 100% | Final
10 | 201383010-Dhopakhali UP-Lararhat via Madhopkati Rd. | [13 empty] | 0 | #DIV/0!
11 | 201384013-Periodic Maintenance of Goalmath-Jessordi End Panbaria Road from Ch. 00m-310m | KDRIDP/Bager/M-11/2017-18 | 0.31 | 0 | 0 | 7.273 | 2018-09-18 | M/S. Sweet Enterprise, KB road, Basabati, Bagerhat. | 2018-10-08 | 6.909 | 100% | 2019-04-15 | 6.907 | 6.907 | 0 | 99.97% | Final
12 | 201384014-Kachua-Badhal FRB to Tagrakhal river Ghat (Football field) Road. | [13 empty] | 0 | #DIV/0!
13 | 201384120.Hazarkhali Bazar-Joygashi Taleshwar Road | [13 empty] | 0 | #DIV/0!
Sharankhola
14 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Road | [13 empty] | 0 | #DIV/0!
15 | 201774016-Periodic Maintenance of Baniakhali GC-Pollanbari RHD via B-Dhansagar Community Clinic Delower house Sharankhola part Road from Ch. 1500m-3500m. | KDRIDP/Bager/M-06/2017-18 | 2 | 0 | 0 | 30.03 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 29.805 | 10% | 2019-01-17 | 29.805 | 29.805 | 0 | 100% | Final
16 | 201774023: Periodic Maintenance of Khada- Lakurtala Road from Ch. 00m-1350m | KDRIDP/Bager/M-07/2017-18 | 1.35 | 0 | 0 | 20.09 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 19.918 | 100% | 2019-01-17 | 18.93 | 18.93 | 0 | 95.04% | Final
17 | 201774024: Periodic Maintenance of Banglabazar-Tafalbari-Mourashi Road from Ch. 00m-930m | KDRIDP/Bager/M-17/2018-19 | 0.93 | 0 | 0 | 21.648 | 2018-11-07 | M/S S. Zaman Enterprise, Daulatpur, Khulna | 2019-01-10 | 20.566 | 0% | 2019-07-16 |  |  | 0 | 0%
Mollahat
18 | 201552008-Harida More-Machuarkul Rd. | [13 empty] | 0 | #DIV/0!
19 | 201552009-Gawla-Kadalia Bazar Rd. | [13 empty] | 0 | #DIV/0!
20 | 201553007-Kulia UP-Nagarkandi GC R | [13 empty] | 0 | #DIV/0!
21 | 201564020 - Periodic Maintenance of Moupura-Singati Road from Ch. 00m-2500m | KDRIDP/Bager/M-03/2017-18 | 2.5 | 0 | 0 | 41.48 | 2018-02-24 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 37.33 | 100% | 2019-01-11 |  | 30 | -30 | 80.36% | 1st R/A
22 | 201564002 - Periodic Maintenance of Mollarkul hat-Mollarkul Govt. Pry. School Road from Ch. 00m-1000m | KDRIDP/Bager/M-05/2017-18 | 1 | 0 | 0 | 18.47 | 2018-02-25 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 16.62 | 100% | 2019-01-11 | 16.62 | 16.62 | 0 | 100% | Final
23 | 201563005 - Periodic Maintenance of Joydehihat-Kulia U.P Office Road from Ch. 00m-1000m | KDRIDP/Bager/M-01/2017-18 | 1 | 0 | 0 | 22.22 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20 | 100% | 2019-01-11 | 20 | 20 | 0 | 100% | Final
24 | 201564028 - Periodic Maintenance of Mollahat Hospital -Derbolia RHD Road from Ch. 00m-695m | KDRIDP/Bager/M-02/2017-18 | 0.695 | 0 | 0 | 22.75 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20.47 | 100% | 2019-01-11 | 20.41 | 20.41 | 0 | 99.71% | Final
25 | 201565017 - Periodic Maintenance of Kahalpur Alek house-Kutimia house Road from Ch. 00m-1150m | KDRIDP/Bager/M-04/2017-18 | 1.15 | 0 | 0 | 17.26 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 15.53 | 100% | 2019-01-11 | 15.529 | 15.529 | 0 | 99.99% | Final
Chitalmari
26 | 201143006-Chigurihat -Kalatola UP-BanglabazarRd. | [13 empty] | 0 | #DIV/0!
Rampal
27 | 201732015-Periodic Maintenance of Tatulia bridge-Kadirkhola Road from Ch. 00m-1185m | KDRIDP/Bager/M-20/2017-18 | 1.185 | 0 | 0 | 25.848 | 2019-01-15 | M/S M R Khan Enterprise, Khulna | 2019-02-05 | 24.56 | 65% | 2020-02-11 |  | 8 | -8 | 32.57% | 1st R/A
| 201733009-Periodic Maintenance of Perikhali GC-Hurka UP Road from Ch. 00m-1860m |  | 1.86 | 0 | 0 | 57.19 | 2019-01-15 | M/S M R Khan Enterprise, Khulna | 2019-02-05 | 54.33 | 50% | 2020-02-11 |  | 17.7 | -17.7 | 32.58%
28 | 201733005-Perikhali GC -Bhojpatia UP Office | [13 empty] | 0 | #DIV/0!
29 | 201734054-Ronsan-Mirakhali Road | [13 empty] | 0 | #DIV/0!
30 | 201734104-Banshtali UP-Solakora | [13 empty] | 0 | #DIV/0!
Mongla
31 | 201582007-Digraj-Jholmolia Dhige Rd | [13 empty] | 0 | #DIV/0!
32 | 201583002-Burirdangahat Sonailtala up Office Rd. | [13 empty] | 0 | #DIV/0!
33 | 201584060-Periodic Maintenance of Khanjahan Ali Hat-RHD Road at Gazir bridge from Ch. 00m-1000m. (201583007) | KDRIDP/Bager/M-15/2018-19 | 1 | 0 | 0 | 19.376 | 2018-11-06 | M/S Noyan Enterprise, Dhansagor, Sharankhola, Bagerhat | 2019-01-07 | 18.407 | 0% | 2019-07-13 |  |  | 0 | 0%
Fakirhat
34 | 201344001-Maintenance of Fakirhat L.S.D Godown-singgaty road. | [13 empty] | 0 | #DIV/0!
35 | 201344009 Periodic Maintenance of Lockpur Ballata-Bollopur village Road from Ch. 00m-1900m | KDRIDP/Bager/M-21/2018-19 | 1.9 | 0 | 0 | 40.567 | 2019-03-21 | M/S Utpol Das, Khulna | 2019-03-10 | 38.539 | 100% | 2019-09-17 |  | 38.463 | -38.463 | 99.8% | Final
| 201344024-Periodic Maintenance of Singati Gilatala road upto C&B Bazer Road from Ch. 800m-1030m. |  | 0.23 | 0 | 0 | 9.999 |  |  |  | 9.499 |  |  |  | 9.48 | -9.48 | 99.8%
36 | 201343014-Periodic Maintenance of Katakhali Bazar(RHD)-Baintola Bazar Road via Lokhpur UP (Fakirhat part) Road from Ch. 00m-3000m. (201344025) | KDRIDP/Bager/M-22/2018-19 | 3 | 0 | 0 | 68.739 | 2019-03-21 | M/S Alfa Enterprise, 3, TB Cross Road, Khulna. | 2019-04-17 | 65.3 | 100% | 2020-04-23 | 63.666 | 63.666 | 0 | 97.5% | Final
Morrelgonj
37 | 201603007 - Periodic Maintenance of Banagrame Bazar-Hoglapasha U.P Road from Ch. 00m-2523m | KDRIDP/Bager/M-16/2018-19 | 2.523 | 0 | 0 | 69.157 | 2018-11-05 | M/S Roni Enterprise, Bagerhat | 2019-01-09 | 65.699 | 50% | 2020-01-15 |  | 27.58 | -27.58 | 41.98% | 2nd R/A
38 | 201604059 - Sannashi Launch ghat-Chairmanbazar-(Sannashi Bazer) Pallimangal C&B road | [13 empty] | 0 | #DIV/0!
Total |  |  | 42.956 | 0 | 0 | 869.511 |  |  |  | 822.019 | 75.23% |  | 444.962 | 619.01 | -174.048 | 75.3%
GC-Hat
Sharankhola
1 | Construction of Banglabazar Growth Center | KDRIDP/Bager/GC-04/2017-18 | 0 | 0 | 1 | 19.45 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-08-02 | 20.13 | 60% | 2019-05-08 |  | 5.995 | -5.995 | 29.78%
Mollahat
2 | Construction of Nagarkandi Growth Center | KDRIDP/Bager/GC-05/2017-18 | 0 | 0 | 1 | 20.52 | 2018-02-08 | M/S Kamrul & Brothers, Gopalgonj | 2018-04-05 | 18.467 | 100% | 2019-01-11 | 18.463 | 18.463 | 0 | 99.98% | Final
Rampal
3 | Construction of Foylahat Growth Center | KDRIDP/Bager/GC-06/2017-18 | 0 | 0 | 1 | 21.55 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-03-28 | 20.889 | 100% | 2019-01-03 |  | 9.413 | -9.413 | 45.06%
Mongla
4 | Construction of Mithakhali Growth Center | KDRIDP/Bager/GC-07/2017-18 | 0 | 0 | 1 | 19.38 | 2018-02-08 | M/S Sk. Nurul Amin, Mongla, Bagerhat | 2018-03-28 | 20.29 | 100% | 2019-01-31 | 20.216 | 20.216 | 0 | 99.64% | Final
Chitalmari
5 | Construction of Saildah Growth Center | KDRIDP/Bager/GC-08/2017-18 | 0 | 0 | 1 | 20.43 | 2018-02-08 | M/S S.S. Traders, Tungipara, Gopalgonj | 2018-03-19 | 18.387 | 95% | 2018-12-26 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 5 | 101.33 |  |  |  | 98.163 | 91% |  | 38.679 | 54.087 | -15.408 | 55.1%
Landing/ Riverghat
Sharankhola
1 | Rayenda Bandaghataghat | [13 empty] | 0 | #DIV/0!
2 | Construction of Tafalbari GC Ghat | KDRIDP/Bager/G-11/2017-18 | 0 | 0 | 1 | 17.25 | 2017-12-27 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-02-19 | 16.23 | 20% | 2018-11-25 |  |  | 0 | 0% | NOA issued on 22.01.18
Mollahat
3 | Construction of Udaypur Ghat | KDRIDP/Bager/G-09/2017-18 | 0 | 0 | 1 | 24.598 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 22.14 | 0% | 2018-11-12 |  |  | 0 | 0% | Site Problem
4 | Construction of Udaypur Gholarchak Madrasa Ghat | KDRIDP/Bager/G-10/2017-18 | 0 | 0 | 1 | 12.58 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 11.32 | 100% | 2018-11-12 | 11.32 | 11.32 | 0 | 100% | Final
Morrelgonj
5 | Amtoli Bazar Khal | KDRlDP/Bager/G-01/2017-18 | 0 | 0 | 1 | 17.04 | 2017-11-29 | M/S Shikto Enterprise, Zianagar, Perojpur. | 2018-01-21 | 16.65 | 100% | 2018-10-27 | 16.596 | 16.596 | 0 | 99.68% | Final
6 | Sannasi Bazar Khal | KDRlDP/Bager/G-03/2017-18 | 0 | 0 | 1 | 25.78 | 2017-11-30 | M/S Shanta & Brothers, Basabati, Bagerhat. | 2018-02-05 | 24.98 | 40% | 2018-11-11 |  |  | 0 | 0%
7 | Bisharighata Bazar Khal | KDRlDP/Bager/G-02/2017-18 | 0 | 0 | 1 | 19.64 | 2018-01-25 | N & S brothers, College Road, Morrelgonj, Bagerhat | 2018-03-07 | 20.3 | 100% | 2018-07-13 | 20.227 | 20.227 | 0 | 99.64% | Final
Rampal
8 | Construction of Kaligonj Khaya Ghat | KDRIDP/Bager/G-12/2017-18 | 0 | 0 | 1 | 21.59 | [8 empty] | 0 | #DIV/0! | No tender dropped
9 | Construction of Dakra Khaya Ghat | KDRIDP/Bager/G-13/2017-18 | 0 | 0 | 1 | 20.33 | [8 empty] | 0 | #DIV/0! | No tender dropped
Mongla
10 | Digraj Kheyaghat | KDRIDP/Bager/G-05/20 17-18 | 0 | 0 | 1 | 17.77 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 17.53 | 0% | 2018-11-06 |  |  | 0 | 0% | Site Problem
11 | Chila Growth Center Ghat | KDRIDP/Bager/G-04/2017-18 | 0 | 0 | 1 | 20.41 | 2017-11-29 | M/S Antar Enterprise, Mongla, Bagerhat. | 2018-02-01 | 20.37 | 100% | 2018-11-27 | 20.285 | 20.285 | 0 | 99.58% | Final
Chitalmari
12 | Construction of RCC Ghatla at Khaserhat GC | KDRIDP/Bager/G-08/2017-18 | 0 | 0 | 1 | 15.28 | 2017-12-27 | M/S Muzahidul Islam, Gopalgonj | 2018-02-15 | 13.75 | 0% | 2018-10-21 |  |  | 0 | 0%
Total |  |  | 0 | 0 | 11 | 212.268 |  |  |  | 163.27 | 51.11% |  | 68.428 | 68.428 | 0 | 41.91%
Tree Plantation
Bagerhat Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kachua
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Sharankhola
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Morrelgonj
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Fakirhat
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Mollahat
6 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Chitalmari
7 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Rampal
8 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Mongla
9 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 215.201 | 601.3 | 16 | 17455.812 |  |  |  | 15965.753 | 59.29% |  | 5087.138 | 7529.085 | -2441.947 | 47.16%
|  |  | 215.201 | 601.3 | 16 | 17455.812 |  |  |  | 15965.753 | 35.32% |  | 5087.138 | 7529.085 | -2441.947 | 47.16%

## Mollahat
Mollahat
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201562008-Harida more- Machuarkul Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201562009-Gawla-Kodalia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201562010-Ghoradair -Kachna Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 201563004-Improvement of Kodalia U.P Office- Aruadehi hat road ch.1400-3480m | KDRIDP/Bager/W-71/2017-18 | 2.08 | 0 | 0 | 151.85 | 2018-02-07 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-03-21 | 136.66 | 40% | 2019-03-27 | 0 | 21.1 | -21.1 | 15.44% | 1st R/A
5 | 201563006-Improvement of Gaula UP-Chanderhat-Faltita Bazar Road by BC at Ch. 6200m-7163m. Salvage Amount Tk. 2,55,499.00 | KDRIDP/Bager/W-114/2018-19 | 0.963 | 0 | 0 | 73.18 | 2019-06-09 | Sahid Enterprise (PVT) Ltd, Boyra, Khulna | 0 | 69.523 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 02.07.19
6 | 201563007-Kulia Up-Nagarkandi GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201563008 - Singgati hat-Chunkhola UP H/Q | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201563009-Mollarkul Bazar-Udyapur UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 201564022-Kahalpur RHD-Joydehihat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201564090 - Improvement of Singati-Capil Bridge Road. Ch 500-920 m Under Mollahat Upazila Bagerhat. | KDRIDP/Bager/W-39/2017-18 | 0.42 | 0 | 0 | 26.66 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 23.996 | 100% | 2018-11-21 | 18.997 | 18.997 | 0 | 79.17% | Final
11 | 201564005 - Boaliahat-Kahalpur R&H Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201564007 - Improvement of Rajpat - Gaola UP Road. Ch 1062-2900 m. Salvage Cost. TK. 1386398.00 | KDRIDP/Bager/W-38/2017-18 | 1.838 | 0 | 0 | 111.297 | 2017-09-28 | M/S Rubel Enterprise, Rajoir, Madaripur | 2017-11-15 | 100.167 | 100% | 2018-11-21 | 0 | 86.7 | -86.7 | 86.56% | 3rd R/A
13 | 201564013 - Improvement of Charkuliahat-Takiarkul Road by BC at Ch. 2000m-2950m. Salvage Amount Tk. 2,99,882.00 | KDRIDP/Bager/W-115/2018-19 | 0.95 | 0 | 0 | 72.65 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 201565018 - Improvement of Kahalpur Barapukurpar-Kahalpur H/School via Omar Moulana House Road by BC at Ch. 1002m-1464m |  | 0.462 | 0 | 0 | 33.586 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
14 | 201564016 - Atjuri UP-Kadamtala Kheyaghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201564039 - Boalia RHD-Bhandarkhola hat(Atjuri UP) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201564047 - Improvement of Garfa- Girishnagar-Kadamtala Khayaghat Road. Ch 4100-4900 m Under Mollahat Upazila Bagerhat. Salvage Cost. TK. 114374.00 | KDRIDP/Bager/W-40/2017-18 | 0.8 | 0 | 0 | 46.965 | 2017-09-27 | M/S Molla Enterprise, Mollahat, Bagerhat | 2017-11-15 | 42.27 | 100% | 2018-11-21 | 42.26 | 42.26 | 0 | 99.98% | Final
17 | 201565009 - Improvement of Chaulturi-Kodalia Bill Road. Ch 880-2255 m | KDRIDP/Bager/W-41/2017-18 | 1.375 | 0 | 0 | 77.9 | 2017-09-27 | Shikder Zahidul Islam, Mollahat, Bagerhat. | 2017-11-15 | 70.11 | 100% | 2018-11-21 | 70.11 | 70.11 | 0 | 100% | Final
18 | 201565079 - Improvement of Shason Sobed Molla House-Jamai More Road by BC at Ch. 1000m-1280m & 1380m-1700 | KDRIDP/Bager/W-116/2018-19 | 0.6 | 0 | 0 | 43.039 | 2019-06-11 | M/S Abu Bokkar Timber Traders, Fakirhat, Bagerhat | 0 | 40.887 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 02.07.19
| 201565022 - Improvement of Kahalpur Charpara Road by BC at Ch. 1000m-1300m Salvage Amount Tk. 1,93,297.00 |  | 0.3 | 0 | 0 | 21.58 |  |  |  | 20.5 |  |  | 0 | 0 | 0 | 0%
19 | 201565017 - Kahalpur Alek house-Kutimia house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201564096-Uddaypur Uttar kandy Pacca road-Uddaypur Uttar Kandy GPS-Uttar kandy Graveyard with link of H/O Kamal Molla road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
21 | 201552009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 201562009-Const. of RCC Bridge on Gawla-Kodalia Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 201562009-Construction of 30.00m Long RCC Girder Bridge at Gawla-Kodalia Bazar Road at Ch 3300m. | KDRIDP/Bager/B-12/2017-18 | 0 | 30 | 0 | 215.987 | 2018-06-13 | M/S Kamrul & Brothers, Gopalgonj | 2018-08-02 | 226.57 | 85% | 2019-08-08 | 0 | 181 | -181 | 79.89% | 2nd R/A
Maintenance
24 | 201552008-Harida More-Machuarkul Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201552009-Gawla-Kadalia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 201553007-Kulia UP-Nagarkandi GC R | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201564020 - Periodic Maintenance of Moupura-Singati Road from Ch. 00m-2500m | KDRIDP/Bager/M-03/2017-18 | 2.5 | 0 | 0 | 41.48 | 2018-02-24 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 37.33 | 100% | 2019-01-11 | 0 | 30 | -30 | 80.36% | 1st R/A
28 | 201564002 - Periodic Maintenance of Mollarkul hat-Mollarkul Govt. Pry. School Road from Ch. 00m-1000m | KDRIDP/Bager/M-05/2017-18 | 1 | 0 | 0 | 18.47 | 2018-02-25 | Mozahar Enterprise (PVT.) Ltd. Khulna. | 2018-04-05 | 16.62 | 100% | 2019-01-11 | 16.62 | 16.62 | 0 | 100% | Final
29 | 201563005 - Periodic Maintenance of Joydehihat-Kulia U.P Office Road from Ch. 00m-1000m | KDRIDP/Bager/M-01/2017-18 | 1 | 0 | 0 | 22.22 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20 | 100% | 2019-01-11 | 20 | 20 | 0 | 100% | Final
30 | 201564028 - Periodic Maintenance of Mollahat Hospital -Derbolia RHD Road from Ch. 00m-695m | KDRIDP/Bager/M-02/2017-18 | 0.695 | 0 | 0 | 22.75 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 20.47 | 100% | 2019-01-11 | 20.41 | 20.41 | 0 | 99.71% | Final
31 | 201565017 - Periodic Maintenance of Kahalpur Alek house-Kutimia house Road from Ch. 00m-1150m | KDRIDP/Bager/M-04/2017-18 | 1.15 | 0 | 0 | 17.26 | 2018-02-25 | M/S Ziaul Traders, Khulna. | 2018-04-05 | 15.53 | 100% | 2019-01-11 | 15.529 | 15.529 | 0 | 99.99% | Final
GC-Hat
32 | Construction of Nagarkandi Growth Center | KDRIDP/Bager/GC-05/2017-18 | 0 | 0 | 1 | 20.52 | 2018-02-08 | M/S Kamrul & Brothers, Gopalgonj | 2018-04-05 | 18.467 | 100% | 2019-01-11 | 18.463 | 18.463 | 0 | 99.98% | Final
Landing/ Riverghat
33 | Construction of Udaypur Ghat | KDRIDP/Bager/G-09/2017-18 | 0 | 0 | 1 | 24.598 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 22.14 | 0% | 2018-11-12 | 0 | 0 | 0 | 0% | Site Problem
34 | Construction of Udaypur Gholarchak Madrasa Ghat | KDRIDP/Bager/G-10/2017-18 | 0 | 0 | 1 | 12.58 | 2017-12-27 | M/S Kamrul & Brothers, Gopalgonj | 2018-02-06 | 11.32 | 100% | 2018-11-12 | 11.32 | 11.32 | 0 | 100% | Final
Tree Plantation
35 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 16.133 | 30 | 3 | 1054.572 |  |  |  | 892.56 | 35% |  | 233.709 | 552.509 | -318.8 | 61.9%

## Fakirhat
Fakirhat
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201342013 Lokhpur GC-Dhaka Khulna RHD (Nowapara More) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
2 | 201343005-Singati Bazar-Piljong UP-Balir Dokan-Shambagat RHD. | KDRIDP/Bager/W-25/2017-18 | 1.02 | 0 | 0 | 64.92 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 60.65 | 100% | 2018-07-18 | 60.63 | 60.63 | 0 | 99.97% | Final
3 | 201343001-Fakirhat H/Q-Naldah Maubhog UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 201343006 Upazila H/Q(Livestock Office)-Satsika-Baliadanga-Rakhalgachi UP (Fakirhat Part | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 201343011 - Mulgor UP-Nalda Moubog UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 201344004- Khulna Mollahat R&H at Talerpukur pagla deapara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201344008-Improvement of Khazura R &H-Bolloppur Road. Ch1194-2650m. Salvage Cost-103999.00(fixed) | KDRIDP/Bager/W-24/2017-18 | 1.456 | 0 | 0 | 84.83 | 2017-08-23 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-10-12 | 79.3 | 100% | 2018-07-18 | 79.3 | 79.3 | 0 | 100% | Final
8 | 201344009-Lockpur Ballata-Bollopur village rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201344013- Shibbari-Dohor Moubog Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201344014- Mollar bazar-Bangopar bazar via Tekatia road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201344018 - Betaga bazar-pasur river via Chakuli Pry.school road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201344024 - Singati Gilatala road upto C&B Bazer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201344026 - Kanarpukur-Deapara Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201344042 - Singati-Baliadanga road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201344061- Nawapara Baloyer Dokan-Syambagat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201344088-Kanarpukur-Satshikha Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
17 | 201344006-Bahirdia-satbaria road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201344088-Bahirdia UP office to Weast Bahirdia GPS Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
19 | 201344001-Maintenance of Fakirhat L.S.D Godown-singgaty road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201344009 Periodic Maintenance of Lockpur Ballata-Bollopur village Road from Ch. 00m-1900m | KDRIDP/Bager/M-21/2018-19 | 1.9 | 0 | 0 | 40.567 | 2019-03-21 | M/S Utpol Das, Khulna | 2019-03-10 | 38.539 | 100% | 2019-09-17 | 0 | 38.463 | -38.463 | 99.8% | Final
| 201344024-Periodic Maintenance of Singati Gilatala road upto C&B Bazer Road from Ch. 800m-1030m. |  | 0.23 | 0 | 0 | 9.999 |  |  |  | 9.499 |  |  | 0 | 9.48 | -9.48 | 99.8%
21 | 201343014-Periodic Maintenance of Katakhali Bazar(RHD)-Baintola Bazar Road via Lokhpur UP (Fakirhat part) Road from Ch. 00m-3000m. (201344025) | KDRIDP/Bager/M-22/2018-19 | 3 | 0 | 0 | 68.739 | 2019-03-21 | M/S Alfa Enterprise, 3, TB Cross Road, Khulna. | 2019-04-17 | 65.3 | 100% | 2020-04-23 | 63.666 | 63.666 | 0 | 97.5% | Final
Tree Plantation
22 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 7.606 | 0 | 0 | 269.055 |  |  |  | 253.288 | 18.18% |  | 203.596 | 251.539 | -47.943 | 99.31%

## Chitalmari
Chitalmari
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 201143001 - Chitalmari-Hizla UP-Kalatola UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201143006-Chinguri hat-Kalatala UP-Banglabazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201143007 - Saildah hat-Kalatala UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
4 | 201144020-Kirtankhali - Kharamkhali road (via Khasherhat GC) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 201144011 - Development of Moidah Shibpur Club- Kaligati Road. Ch 00-878. Salvage Cost TK. 404704.00 | KDRIDP/Bager/W-15/2016-17 | 0.878 | 0 | 0 | 61.46 | 2017-07-10 | M/S S.S. Traders, Tungipara, Gopalgonj | 2017-08-24 | 59.92 | 100% | 2018-08-30 | 59.87 | 59.87 | 0 | 99.92% | Final
6 | 201144023 - Chinguri kheaghat-Krishi Bank-Kalatala road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201144032 - Development of Khaserhat- Asoknagar Road. Ch 2300-4595 m. Salvage Cost TK. 433415.00 | KDRIDP/Bager/W-13/2016-17 | 2.295 | 0 | 0 | 147.91 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 143.47 | 100% | 2018-08-29 | 142.57 | 142.57 | 0 | 99.37% | Final
8 | 201144033-Development of Shampara- Kudari via Panchpara Hat Road. Ch 1000-2550 m. Salvage Cost TK. 796234.00 | KDRIDP/Bager/W-12/2016-17 | 1.55 | 0 | 0 | 140.03 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-22 | 135.17 | 100% | 2018-08-29 | 126.446 | 126.446 | 0 | 93.55% | Final
9 | 201144049-Development of Barobaria at RHD Road-Ghola High School-Baroguni bazar Road. Ch 00-1700 m. Salvage Cost TK. 261420.00 | KDRIDP/Bager/W-14/2016-17 | 1.7 | 0 | 0 | 105.59 | 2017-07-10 | Md. Iqbal Hossain, Tungipara, Gopalgonj. | 2017-08-06 | 101.05 | 100% | 2018-08-29 | 100.98 | 100.98 | 0 | 99.93% | Final
10 | 201145027-Improvement of Hizla Sheikpara- Agakhal RPS Road. Ch 00 -1275m. Salvage Cost TK. 618000.00 | KDRIDP/Bager/W-64/2017-18 | 1.275 | 0 | 0 | 103.13 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-02-06 | 92.82 | 100% | 2019-02-12 | 90.1 | 90.1 | 0 | 97.07% | Final
Improvement of Village Road by HBB
11 | 201145133-Improvment of HBB Road at Umajuri Pachimpara road-Umajuri Bottala Hasans House Road Ch00-620m. Salvage Cost Tk.-129789.00(fixed) | KDRIDP/Bager/W-30/2017-18 | 0.62 | 0 | 0 | 26.72 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 26.72 | 100% | 2018-07-22 | 26.58 | 26.58 | 0 | 99.48% | Final
12 | 201145115-Improvement of HBB Road at Baburhat Khayaghat Chursta -Hanif Sheks house road. Ch00-510m | KDRIDP/Bager/W-33/2017-18 | 0.51 | 0 | 0 | 18.42 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-11-21 | 18.42 | 100% | 2018-08-27 | 18.42 | 18.42 | 0 | 100% | Final
13 | 201145114-Improvement of Besharkhola (Bottola)-Bottola Abdul Gazi house road via Sultan Chairman road Ch750-1590m by BC | KDRIDP/Bager/W-42/2017-18 | 0.84 | 0 | 0 | 49.346 | 2017-09-25 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-15 | 44.41 | 100% | 2018-11-21 | 44.23 | 44.23 | 0 | 99.59% | Final
14 | 201145116-Improvement of HBB Road at Bottola Khuria AKub Sheks house Katchuria Baser Gazi house road. Ch00-926m. Salvage Cost. TK. -338716.00 | KDRIDP/Bager/W-34/2017-18 | 0.926 | 0 | 0 | 34.41 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 34.39 | 100% | 2018-07-16 | 34.38 | 34.38 | 0 | 99.97% | Final
15 | 201145121-Improvement of Bottola Bazar (Mozam Mistry Bari)- Khuria Motin House Road Ch00-670 m. Salvage Cost-2,31,118.00 | KDRIDP/Bager/W-23/2017-18 | 0.67 | 0 | 0 | 39.58 | 2017-08-17 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-10-09 | 35.62 | 100% | 2018-07-15 | 34.61 | 34.61 | 0 | 97.16% | Final
16 | 201145106-Improvement of Babuana of Shantos pur Lararkul Road Lalrarkul primary School Road By HBB. Ch 00-800 m | KDRIDP/Bager/W-61/2017-18 | 0.8 | 0 | 0 | 56.88 | 2018-05-17 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-06-05 | 59.298 | 100% | 2019-06-10 | 59.083 | 59.083 | 0 | 99.64% | Final
17 | 201144024-Improvement of HBB Road at KirtonKhali Santoshpur R&H road. Ch. 2875-3235m. Salvage amount tk.1,91,274.00 (fixed) | KDRIDP/Bager/W-32/2017-18 | 0.36 | 0 | 0 | 13.94 | 2017-09-12 | M/S Munna Enterprise, Chitalmari, Bagerhat. | 2017-10-10 | 13.93 | 100% | 2018-07-16 | 13.866 | 13.866 | 0 | 99.54% | Final
18 | 201144006-Improvement of Santospur Uttar LararculSantospur primary School road Road By HBB. Ch 1600-2470 m | KDRIDP/Bager/W-60/2017-18 | 0.87 | 0 | 0 | 51.31 | 2017-12-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 55.9 | 100% | 2018-11-11 | 55.77 | 55.77 | 0 | 99.77% | Final
19 | 201144059-Improvement of HBB Road at Kaligonj Bazar-Bashbaria road. Ch00-1260m. Salvage Cost Tk.-356489.00 | KDRIDP/Bager/W-31/2017-18 | 1.26 | 0 | 0 | 53.938 | 2017-09-12 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 53.94 | 100% | 2018-07-22 | 52.83 | 52.83 | 0 | 97.94% | Final
20 | 201145137-Improvement of Bottola Satghor jame Mosque- Motin Sheikh wooden bridge Road By HBB. Ch 00-570 m | KDRIDP/Bager/W-62/2017-18 | 0.57 | 0 | 0 | 46.11 | 2017-12-26 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-02-05 | 48.34 | 100% | 2018-11-11 | 48.25 | 48.25 | 0 | 99.81% | Final
21 | 201145108-Improvement of Umazuri- Kachuria pry. Regd. School- Kachuuria Road by HBB. Ch 00- 2560 m | KDRIDP/Bager/W-57/2017-18 | 2.56 | 0 | 0 | 147.65 | 2017-10-16 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2017-11-16 | 147.64 | 100% | 2018-11-22 | 146.734 | 146.734 | 0 | 99.39% | Final
22 | 201144029-Kaligonj-Kachuria Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
23 | 201143006-Construction of 17.00m Long RCC Girder Bridge on Chinguri hat-Kalatala UP-Banglabazar Road at Ch 8090m. | KDRIDP/Bager/B-10/2017-18 | 0 | 17 | 0 | 141.19 | 2018-05-09 | M/S Kamrul & Brothers, Gopalgonj | 2018-06-25 | 140.999 | 80% | 2019-07-01 | 0 | 107.39 | -107.39 | 76.16% | 2nd R/A
24 | 201144029-Const. of RCC Box Culvert 1vX1.00X1.00m , 2vX4.00X4.00m & 1vX4.30X3.60m at Kaligonj-Kachuria Road | KDRIDP/Bager/W-63/2017-18 | 0 | 13.3 | 0 | 48.27 | 2017-11-13 | M/S Joy Enterprise, Khan tower, Shibbari more, Khulna | 2018-01-04 | 43.44 | 100% | 2019-01-10 | 42.25 | 42.25 | 0 | 97.26% | Final
25 | 201145121-Const. of RCC Box Culvert 2vX4.00X4.00m over canal at Bottola Bazar (Mozam Mistry Bari)-Khuria Motin House road. | KDRIDP/Bager/W-65/2017-18 | 0 | 8 | 0 | 23.61 | 2017-11-12 | M/S Kamrul & Brothers, Mohammadpara, Gopalgonj | 2018-01-04 | 21.25 | 100% | 2019-01-10 | 21.18 | 21.18 | 0 | 99.67% | Final
Maintenance
24 | 201143006-Chigurihat -Kalatola UP-BanglabazarRd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
25 | Construction of Saildah Growth Center | KDRIDP/Bager/GC-08/2017-18 | 0 | 0 | 1 | 20.43 | 2018-02-08 | M/S S.S. Traders, Tungipara, Gopalgonj | 2018-03-19 | 18.387 | 95% | 2018-12-26 | 0 | 0 | 0 | 0% | 0
Landing/ Riverghat
26 | Construction of RCC Ghatla at Khaserhat GC | KDRIDP/Bager/G-08/2017-18 | 0 | 0 | 1 | 15.28 | 2017-12-27 | M/S Muzahidul Islam, Gopalgonj | 2018-02-15 | 13.75 | 0% | 2018-10-21 | 0 | 0 | 0 | 0% | 0
Tree Plantation
27 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 17.684 | 38.3 | 2 | 1345.204 |  |  |  | 1308.864 | 68.1% |  | 1118.149 | 1225.539 | -107.39 | 93.63%

## Bagerhat Sadar
Bagerhat Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 201083011 Improvement of Baroipara UP office-Haderhat bazar via Kartickdia bazar Road by BC at Ch. 4300m-4800m & 5226m-5450m. Salvage Amount Tk. 4,27,779.00 | KDRIDP/Bager/W-108/2018-19 | 0.724 | 0 | 0 | 47.592 | 2019-05-26 | Md. Nazrul Islam Nilu, College Road, Bagerhat | 0 | 45.212 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 30.06.19
2 | 201083012 Baroipara UP office-Ujalpur bazar via Kafurpura school road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201083017 Improvement of Chulkathi bazar-Betaga UP Road Sadar Portion Ch00-1476. Salvage amount tk. 157003. fixed | KDRIDP/Bager/W-35/2017-18 | 1.476 | 0 | 0 | 87.09 | 2017-09-11 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-10-16 | 91.08 | 100% | 2018-07-22 | 91.064 | 91.064 | 0 | 99.98% | Final
4 | 201084086-Improvement of Bemorta UP (At Fatepur)-Bottala bazar via Bijoypur Road at Ch. 00m-1068m. Salvage Amount Tk. 23,85,276.00 (201083018) | KDRIDP/Bager/W-102/2018-19 | 1.068 | 0 | 0 | 78.887 | 2019-03-19 | M/S Alif Store, Chitalmari, Bagerhat. | 2019-04-10 | 74.94 | 35% | 2020-04-16 | 0 | 0 | 0 | 0% | 0
5 | 201083019-Improvement of Bishnapur UP-Kandapara GC Road by BC at Ch. 00m-1600m Road ID No-201083019 Salvage Amount Tk. 464006.00 | KDRIDP/Bager/W-107/2018-19 | 1.6 | 0 | 0 | 149.308 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201083022-Karapara UP office to Karapara bazar via Magnitala bazar rd.. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
7 | 201084001-South Khanpur-Taterhat-Ranjeetpur.(start from Ranjeetpur Asrayan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201084011-B.Sc High school-Laksmikhali BWDB-Chaksree(Kalibari) hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201084017-Patorpara-Karapra road(Add.CE R&H dept). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201084018-Patilakhali-Nataikhali road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201084019-Kandapara GC(Parnowapara)-Betkhali bazar-Taleswar bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201084038-Haderhat bazar-Bakhergonj bazar via singa kheyaghat WDB road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201084040-Improvement of Monigonj- Gopalkati- Bishnapur Road from Ch. 823m-1658m. Salvage Cost Tk. 17,83,391.00 | KDRIDP/Bager/W-103/2018-19 | 0.835 | 0 | 0 | 98.57 | 2019-03-19 | M/S Monir Bricks, Keshabpur, Bagerhat | 2019-05-08 | 93.643 | 30% | 2020-05-14 | 0 | 0 | 0 | 0% | 0
14 | 201084074-Improvement of Rakhalgachi UP-Chulkathi bazar via Ranjeetpur Road by BC at Ch. 1440m-3065m. Salvage Amount Tk. 3,32,248.00 | KDRIDP/Bager/W-101/2018-19 | 1.625 | 0 | 0 | 122.88 | 2019-03-19 | M/S Faruk Enterprise, Kachua, Bagerhat | 2019-04-11 | 116.73 | 30% | 2020-04-17 | 0 | 0 | 0 | 0% | 0
15 | 201085010-Improvement of Doritaluk Rd-Bagmara Road by BC at Ch. 950m-1702m. Salvage Amount Tk. 16,51,331.00 | KDRIDP/Bager/W-106/2018-19 | 0.752 | 0 | 0 | 63.22 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 201084067-Improvement of Chapatola (H/O Amin)-Jattrapur govt. pri. School Road by BC at Ch. 1000m-1410m. Salvage Amount Tk. 2,70,137.00 |  | 0.41 | 0 | 0 | 43.175 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
| 201084024-Improvement of Zindapir mazar-Khanjahan Ali mazar with link of nine gambuj mosque Road by BC at Ch. 1384m-2080m. Salvage Amount Tk. 8,28,643.00 |  | 0.696 | 0 | 0 | 50.164 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
16 | 201085288-Chaparkul –Bakarganj bazar via khalispur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 201085039-Bara Bansh Baria road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201085044-Improvement of Bansh Baria High school road Road by BC at Ch. 12m-1366m. Salvage Amount Tk.1,89,208.00 | KDRIDP/Bager/W-100/2018-19 | 1.354 | 0 | 0 | 107.18 | 2019-03-19 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2019-04-11 | 101.82 | 30% | 2020-04-17 | 0 | 0 | 0 | 0% | 0
19 | 201084046- Improvement of Jattrapur at UZR- Komorpur via Afra Mowmachi Palon project & Murshidpur Ch00-2151m. Salvage Amount tk.-592374 fixed | KDRIDP/Bager/W-36/2017-18 | 2.151 | 0 | 0 | 127.185 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 133.33 | 100% | 2018-08-30 | 133.31 | 133.31 | 0 | 99.98% | Final
20 | 201084040-Improvement of Monigonj- Gopalkati- Bishnapur Road from Ch. 823m-1658m. Salvage Cost Tk. 1642597.00 | KDRIDP/Bager/W-78/2017-18 | 0.835 | 0 | 0 | 85.79 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Request sent to HQ for cancellation.
21 | 201085013-Keshobpur Charogram-Kondola-Talswar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 201085191-Improvement of Hakimpur Pry. School-Chandromahel road Ch 995-1845m. Salvage amount tk. 246687.00 fixed | KDRIDP/Bager/W-37/2017-18 | 0.85 | 0 | 0 | 60.78 | 2017-09-11 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-10-24 | 63.72 | 100% | 2018-08-30 | 63.664 | 63.664 | 0 | 99.91% | Final
23 | 201084069-West Saera Bazar-Sree Ghat Bazar via Sadullahpur road. | KDRIDP/Bager/W-16/2016-17 | 0.702 | 0 | 0 | 41.58 | 2017-07-09 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-08-13 | 43.56 | 100% | 2018-08-19 | 43.553 | 43.553 | 0 | 99.98% | Final
24 | 201085234-Rangeetpur-Southpara via Morralpara Tater hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201085238-Development of Ranjitpur- Guchegram- Morolpara- Surjamukhi Club Road. Ch 00-821 m. Salvage Cost Tk.145827.00 | KDRIDP/Bager/W-10/2016-17 | 0.821 | 0 | 0 | 49.28 | 2017-06-14 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2017-07-26 | 51.69 | 100% | 2018-05-29 | 51.654 | 51.654 | 0 | 99.93% | Final
26 | 201085040- Improvement of PC Dema Pucca Road-Mallik bari Road CH00-350M. Salvage amount 176715.00 fixed | KDRIDP/Bager/W-58/2017-18 | 0.35 | 0 | 0 | 20.11 | 2017-10-26 | M/S S.S. Brothers, 18, Sarker lane, Tootpara, Khulna. | 2017-12-12 | 21.11 | 100% | 2018-06-18 | 21.106 | 21.106 | 0 | 99.98% | Final
Construction of Bridge on Upazila Road (7.30m width)
27 | 201082012-Construction of 42.00m Long RCC Girder Bridge at Chulkath R&H- Faila GC via Ranjeetpur road Sadar Part Road at Ch 6898m. | KDRIDP/Bager/B-13/2017-18 | 0 | 42 | 0 | 232.74 | 2018-06-13 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-08-05 | 231 | 20% | 2019-08-11 | 0 | 0 | 0 | 0% | 0
Maintenance
28 | 201083011-Periodic Maintenance of Baroipara UP Office-Haderhat Bazar via Kartickdia Bazar Road at Ch. 00m-2450m. | KDRIDP/Bager/M-19/2018-19 | 2.45 | 0 | 0 | 55.496 | 2018-11-26 | Syed Ziaul Hoque, Kazdia, Rupsha, Khulna. | 2019-01-06 | 52.72 | 100% | 2019-07-12 | 52.695 | 52.695 | 0 | 99.95% | Final
29 | 201084002 Periodic Maintenance of Dashani(R&H)-Shatgambuj UZR-via Upazila HQ Road from Ch. 2780m-4540m. | KDRIDP/Bager/M-13/2017-18 | 1.76 | 0 | 0 | 33.68 | 2018-04-26 | M/S A. Samad Traders, Sharankhola, Bagerhat | 2018-05-30 | 31.996 | 65% | 2019-06-05 | 0 | 19.117 | -19.117 | 59.75% | 1st R/A
| 201084048-Periodic Maintenance of Nonadanga-Krishnanagar Road from Ch. 00m-780m. |  | 0.78 | 0 | 0 | 11.829 |  |  |  | 11.24 |  |  | 0 | 6.715 | -6.715 | 59.74%
| 201084087-Periodic Maintenance of Khanpur UP-Uttor Khanpur UHC Road from Ch. 00m-1420m |  | 1.42 | 0 | 0 | 29.936 |  |  |  | 28.44 |  |  | 0 | 16.993 | -16.993 | 59.75%
30 | 201084005 Periodic Maintenance of Mathabhanga R & H-Sukdara bus stand via Sunagar from Ch. 850m-4212m. | KDRIDP/Bager/M-12/2017-18 | 3.36 | 0 | 0 | 51.24 | 2018-04-26 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-05-23 | 48.678 | 100% | 2019-05-29 | 48.66 | 48.66 | 0 | 99.96% | Final
| 201084036 Periodic Maintenance of C & B bazar-Shaawliabag mazar Road at H/O Mayor Mr.Tayyab from Ch. 00m-1339m. |  | 1.339 | 0 | 0 | 28.446 |  |  |  | 27.024 |  |  | 27.01 | 27.01 | 0 | 99.95%
| 201084045 Periodic Maintenance of Bagerhat Pallibidyut DC rd-Polghat-Monigonj ferrighat Road from Ch. 00m-1520m. |  | 1.52 | 0 | 0 | 25.936 |  |  |  | 24.639 |  |  | 24.62 | 24.62 | 0 | 99.92%
31 | 201084082-Periodic Maintenance of Noapara bazar- Baitpur R&H Road at Ch. 1355m-2700m. | KDRIDP/Bager/M-18/2018-19 | 1.35 | 0 | 0 | 35.455 | 2018-11-25 | M/S Joy Enterprise, Basabati, Bagerhat | 2019-01-07 | 33.68 | 15% | 2019-07-13 | 0 | 0 | 0 | 0% | 0
Tree Plantation
32 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 30.228 | 42 | 0 | 1737.549 |  |  |  | 1326.252 | 32.03% |  | 557.336 | 600.161 | -42.825 | 45.25%

## Kachua
Kachua
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 201383004-Improvement of Dhopakhali UP-Madertola bazar House Road by BC at Ch.987-1881m. Salvage Amount Tk. 15,94,676.00 | KDRIDP/Bager/W-84/2017-18 | 0.894 | 0 | 0 | 64.787 | 2018-05-17 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-06-05 | 68.026 | 100% | 2019-06-10 | 68.02 | 68.02 | 0 | 99.99% | Final
| 201383009-Improvement of Kachua UP-Talwshwer bazar Road by BC at Ch.00m-1143m & 2961m-3600m. Salvage Amount Tk. 22,87,655.00 |  | 1.782 | 0 | 0 | 123.059 |  |  |  | 129.21 |  |  | 129.19 | 129.19 | 0 | 99.98%
2 | 201383005-Improvement of Fatehpur bazar-Gopalpur UP- Fultala bazar Road. Ch4794-5353 m & 6300-7100 m. Salvage Cost Tk. 1345002.00 | KDRIDP/Bager/W-48/2017-18 | 1.359 | 0 | 0 | 83.459 | 2017-12-04 | M/S Sonia Enterprise, Nagerbazar, Bagerhat | 2018-02-05 | 87.15 | 100% | 2019-02-11 | 86.61 | 86.61 | 0 | 99.38% | Final
3 | 201383008-Improvement of Badhal UP-Atharogati bazar Road by BC at Ch. 2203m-3430m. Salvage Amount Tk.19,12,208.00 | KDRIDP/Bager/W-94/2017-18 | 1.227 | 0 | 0 | 95.278 | 2018-08-02 | M/S Rahamat Traders, Amlapara, Bagerhat | 2018-09-11 | 93.849 | 100% | 2019-09-17 | 74.721 | 74.721 | 0 | 79.62% | Final
Improvement of Village Road by BC
4 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.1278m-3278m. Salvage Amount Tk. 3144409.00 | KDRIDP/Bager/W-85/2017-18 | 2 | 0 | 0 | 190.819 | 2018-05-27 | M/S Sohel Construction, Pourashava Road, Bagerhat | 2018-06-28 | 199.31 | 100% | 2019-12-04 | 167.852 | 167.852 | 0 | 84.22% | Final
5 | 201384001-Improvement of Shibpur-Biskhali Road by BC at Ch.5780m-7564m. Salvage Amount Tk. 297535.00 | KDRIDP/Bager/W-86/2017-18 | 1.784 | 0 | 0 | 134.255 | 2018-05-28 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-07-01 | 140.968 | 100% | 2019-12-07 | 140.96 | 140.96 | 0 | 99.99% | Final
6 | 201384001-Improvement of Shibpur-Biskhali Road at Ch. 3278m-4093m. Salvage Amount Tk.1384216.00 | KDRIDP/Bager/W-96/2018-19 | 0.815 | 0 | 0 | 89.87 | 2018-08-19 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-09-30 | 85.38 | 100% | 2019-10-06 | 71.526 | 71.526 | 0 | 83.77% | Final
7 | 201384017-Development of Bakultala- Moshni Road. Ch. 2059-3135 m. Salvage Cost. TK.-539470.00 | KDRIDP/Bager/W-20/2016-17 | 1.076 | 0 | 0 | 78.97 | 2017-08-08 | M/S Rupali Construction, Hospital Road, Barisal | 2017-09-11 | 82.5 | 50% | 2018-09-17 | 0 | 45.29 | -45.29 | 54.9% | 2nd R/A
| 201384016-Improvement of Kachua-Badamtali Road by BC at Ch.1673m-3173m. Salvage Amount Tk. 904835.00 | KDRIDP/Bager/W-88/2017-18 | 1.5 | 0 | 0 | 145.075 | 2018-05-28 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-07-01 | 152.328 | 100% | 2019-12-07 | 152.272 | 152.272 | 0 | 99.96% | Final
8 | 201384044-Improvement of Maliporton School-bishkhali Road. Ch400-1260 m Under Kachua Upazila. Bagerhat. Salvage Cost Tk. 107512.00(Fixed) | KDRIDP/Bager/W-50/2017-18 | 0.86 | 0 | 0 | 63.956 | 2017-11-21 | M/S Robel Enterprise, Madaripur | 2018-01-25 | 66.52 | 100% | 2019-01-30 | 66.511 | 66.511 | 0 | 99.99% | Final
9 | 201384045-Laraahat-Lararkul | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201384085-Improvement of Mosni Bazar-Bhuddobhumi Road by BC at Ch.1500m-2566m. Salvage Amount Tk. 7,80,539.00 | KDRIDP/Bager/W-87/2017-18 | 1.066 | 0 | 0 | 94.25 | 2018-05-28 | M/S Tasfia Construction, Chitalmari, Bagerhat | 2018-07-01 | 98.96 | 100% | 2019-12-07 | 98.951 | 98.952 | -0.001 | 99.99% | Final
| 201384031-Improvement of Mogia-Shirokhali Road by BC at Ch. 510m-1060m. Salvage Amount Tk. 8,59,367.00 |  | 0.55 | 0 | 0 | 36.06 |  |  |  | 37.86 |  | 0 | 37.852 | 37.851 | 0.001 | 99.98%
11 | 201385032-Afra Battala- Afra Jame Mosque Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201384103-Development of Guzarpara- Baleshor River Ghat Road. Ch.558-1540 m. Salvage Cost TK. 211626.00 | KDRIDP/Bager/W-18/2016-17 | 0.982 | 0 | 0 | 68.2 | 2017-07-10 | M/S Sufia Enterprise, Badura Parerhat, Pirojpur. | 2017-08-22 | 71.4 | 100% | 2018-08-29 | 71.391 | 71.391 | 0 | 99.99% | Final
13 | 201384103-Improvement of Guzarpara-Baleshor River Ghat Road Ch.1540m-1767m. Salvage cost Tk. 135904 | KDRIDP/Bager/W-75/2017-18 | 0.227 | 0 | 0 | 15.7 | 2018-01-25 | M/S Upokar Enterprise, LGED, Pirojpur. | 2018-05-01 | 14.8 | 100% | 2019-03-31 | 14.8 | 14.8 | 0 | 100% | Final
14 | 201385014-Development of B. Andermanik S Club - Huchibaga- Andermanik H. School Road. Ch.271-2146 m. Salvage Cost TK. 900690.00 | KDRIDP/Bager/W-17/2016-17 | 1.875 | 0 | 0 | 139.996 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 146.93 | 100% | 2018-08-12 | 146.913 | 146.913 | 0 | 99.99% | Final
15 | 201384100-Improvement of Shibpur- Palpara Road. Ch 00-1359 m. Salvage Cost Tk. 491805.00 (201384078) | KDRIDP/Bager/W-46/2017-18 | 1.359 | 0 | 0 | 90.636 | 2017-12-18 | M/S Khandaker Brothers, Nalcity, Jhalokati. | 2018-01-28 | 96.38 | 100% | 2019-02-03 | 96.372 | 96.372 | 0 | 99.99% | Final
16 | 201384025-Improvement of Protappur-Bokaterkathi Road. Ch00-625 m. Salvage Cost Tk. 330365.00 | KDRIDP/Bager/W-49/2017-18 | 0.625 | 0 | 0 | 69.678 | 2017-10-04 | M/S Masud Enterprise, Kachua, Bagerhat. | 2017-11-13 | 72.73 | 100% | 2018-11-19 | 72.425 | 72.425 | 0 | 99.58% | Final
17 | 201384115-Padonagur masin shop via chato khal to signboard (201384065) | KDRIDP/Bager/W-29/2017-18 | 1.114 | 0 | 0 | 89.598 | 2017-08-22 | Md. Noor Hossain, Mission para, Jessore. | 2017-10-11 | 83.12 | 35% | 2018-07-17 | 0 | 12.52 | -12.52 | 15.06% | 1st R/A
18 | 201384050-Improvement of Charkati- Baruikhali Shosan Ghat Road. Ch1000-2325 m. Salvage Cost Tk. 460221.00 | KDRIDP/Bager/W-47/2017-18 | 1.325 | 0 | 0 | 83.92 | 2017-10-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2017-11-13 | 88.12 | 100% | 2018-11-19 | 88.112 | 88.112 | 0 | 99.99% | Final
19 | 201384043-Development of Uttar Gopalpur- Kachua Araian Bridge Road. Ch.00-961 m. Salvage Cost TK. 475021.00 | KDRIDP/Bager/W-19/2016-17 | 0.961 | 0 | 0 | 70 | 2017-07-10 | M/S Alif Store, Chitalmari, Bagerhat. | 2017-08-06 | 73.4 | 100% | 2018-08-12 | 73.282 | 73.282 | 0 | 99.84% | Final
20 | 201384043-Improvement of Uttar Gopalpur FWC-Kachua Iron Bridge Road at Ch. 961m-1940m. Salvage Amount Tk.5,56,673.00 | KDRIDP/Bager/W-93/2017-18 | 0.979 | 0 | 0 | 65.57 | 2018-08-02 | M/S Rahamat Traders, Amlapara, Bagerhat | 2018-09-11 | 64.095 | 100% | 2019-09-17 | 61.511 | 61.511 | 0 | 95.97% | Final
| 201384019-Improvement of Madertala-Jobai Road at Ch. 972m-1722m. Salvage Amount Tk. 3,05,462.00 |  | 0.75 | 0 | 0 | 75.95 |  |  |  | 74.24 |  |  | 71.251 | 71.251 | 0 | 95.97%
21 | 201385059-Atharogati-Sardar Bari House to Ohidkhan road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | fatepur fultala(paddanagar)via brigde to habibshop | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
23 | 201384051-Improvement of Bisherkhola-Bottola School Road by HBB at Ch.00m-2533m. Salvage Amount Tk. 845746.00 | KDRIDP/Bager/W-89/2017-18 | 2.533 | 0 | 0 | 162.366 | 2018-05-24 | M/S Rina Enterprise, Fultola, Bagerhat | 2018-06-25 | 161.96 | 50% | 2019-12-01 | 0 | 47.79 | -47.79 | 29.51% | 2nd R/A
Construction of Bridge on Union Road/Village Road (5.50m width)
24 | 201383005-Construction of RCC Bridge on Fatehpur Bazar-Gopalpur UP -Fultala Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201384050-Construction of RCC Box culvert 5.00mx3.50m at Ch. 1762m on Charkati-Baruikhali Shosan Ghat | KDRIDP/Bager/W-76/2017-18 | 0 | 5 | 0 | 13.07 | 2017-12-26 | M/S Alif Store, Chitalmari, Bagerhat. | 2018-02-05 | 11.76 | 100% | 2018-10-11 | 11.76 | 11.76 | 0 | 100% | Final
Maintenance
26 | 201382008-Periodic Maintenance of Maddham Teligati-Malomgacha-Brhmankathi-Kakarbill Kachua Part from Ch. 00m-2233m | KDRIDP/Bager/M-08/2017-18 | 2.233 | 0 | 0 | 41.037 | 2018-04-03 | M/S Masud Enterprise, Kachua, Bagerhat. | 2018-04-26 | 38.98 | 100% | 2018-12-17 | 38.98 | 38.98 | 0 | 100% | Final
27 | 201383005-Periodic Maintenance of Fatehpur bazar-Gopalpur UP-Fultala bazar Road from Ch. 2584m-4794m & 7100m-8086m. | KDRIDP/Bager/M-09/2017-18 | 3.196 | 0 | 0 | 47.02 | 2018-04-04 | M/S Mou Enterprise, Kharder, Bagerhat | 2018-08-05 | 44.67 | 100% | 2018-12-30 | 44.66 | 44.66 | 0 | 99.98% | Final
28 | 201383006.Gopulpur UP-Natunhat Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 201383007.Kachua UP-Natun hat bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 201383008-Periodic Maintenance of Badhal UP-Atharogati bazar Road from Ch. 00m-915m | KDRIDP/Bager/M-10/2017-18 | 0.915 | 0 | 0 | 17.339 | 2018-04-04 | M/S Tasfia Construction, Chitalmari, Bagerhat. | 2018-04-26 | 16.47 | 100% | 2018-12-17 | 16.47 | 16.47 | 0 | 100% | Final
31 | 201383010-Dhopakhali UP-Lararhat via Madhopkati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 201384013-Periodic Maintenance of Goalmath-Jessordi End Panbaria Road from Ch. 00m-310m | KDRIDP/Bager/M-11/2017-18 | 0.31 | 0 | 0 | 7.273 | 2018-09-18 | M/S. Sweet Enterprise, KB road, Basabati, Bagerhat. | 2018-10-08 | 6.909 | 100% | 2019-04-15 | 6.907 | 6.907 | 0 | 99.97% | Final
33 | 201384014-Kachua-Badhal FRB to Tagrakhal river Ghat (Football field) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 201384120.Hazarkhali Bazar-Joygashi Taleshwar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
35 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 34.297 | 5 | 0 | 2257.191 |  |  |  | 2308.025 | 64.86% |  | 1909.299 | 2014.899 | -105.6 | 87.3%

## Rampal
Rampal
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201732007-Improvement of Bhaga RHD-Kapasdanga-Kaigardashkati-Chalnahat GC (Rampal portion) Road by BC at Ch. 12500m-13100m | KDRIDP/Bager/W-111/2018-19 | 0.6 | 0 | 0 | 68.326 | 2019-05-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 0 | 64.91 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 30.06.19
2 | 201732010-Improvement of Balai Bridge-Rampal Road Ch. 0.00m-5100m. Under Rampal Upazila Bagerhat. Road ID No. 201732010 Salvage cost Tk. 3840719.00 | KDRIDP/Bager/W-72/2017-18 | 5.1 | 0 | 0 | 416.04 | 2018-03-06 | M.A. Jalil Khan, Rupsha Stand Road, Khulna. | 2018-04-25 | 456.72 | 35% | 2019-05-02 | 0 | 50 | -50 | 10.95% | 1st R/A
3 | 201732013-A) Development of Baliadanga Bus Stand- Vangonpar Road by BC Ch 00-5200 m. B) Construction of 2 nos U-Drain at ch 300 m& 495 m.C Construction of 04 Nos Rcc 3x3 V Box Culvert at ch 2040m3450 m4170 m & 4525 mOn Same Road. Salvage Cost TK. 2101973.00 Fixed | KDRIDP/Bager/W-01/2016-17 | 5.2 | 0 | 0 | 251.31 | 2017-05-15 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-07-03 | 262.62 | 70% | 2019-05-31 | 0 | 47.42 | -47.42 | 18.06% | 1st R/A
4 | 201732014-Improvement of Babur bari-Bujbunia Road by BC at Ch. 2654m-5580m. Salvage Amount Tk. 24,79,651.00 | KDRIDP/Bager/W-109/2018-19 | 2.926 | 0 | 0 | 270.25 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Evaluation under process
5 | 201732015-Improvement of Tatulia Bridge - Kadirkhola road Ch1175-2904m by BC. Salvage amount Tk.1486339.00 Fixed | KDRIDP/Bager/W-44/2017-18 | 1.729 | 0 | 0 | 138.038 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 144.56 | 40% | 2019-08-03 | 0 | 46.15 | -46.15 | 31.92% | 1st R/A
Improvement of Union Road by BC
6 | 201733002-Gilatale G.C-Bhospatia UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201733005-Improvement of Perikhali G.C-Bhojpatia U.P office Road by BC at Ch. 6054m-9740m. Salvage Amount Tk. 70,88,741.00 | KDRIDP/Bager/W-110/2018-19 | 3.686 | 0 | 0 | 312.814 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Re-tender last selling 16.07.19
8 | 201733006-Improvement of Rampa-Bashtoli UP Road Ch.1890m-3695m. Under Rampal Upazila Bagerhat. Road ID No. 201733006 Salvage cost Tk. 2,87,317.00 | KDRIDP/Bager/W-104/2017-18 | 1.805 | 0 | 0 | 122.52 | 2019-03-19 | M/S Niloy Enterprise, 19 South Tootpara 2no cross road, Khulna | 2019-05-14 | 116.4 | 25% | 2020-05-20 | 0 | 0 | 0 | 0% | 0
9 | 201733007-Uzalkur UP-Baburhat Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201733009-Perikhali GC-Hurka UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201733010-Kaligonj bazar-Mollikarbare UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201733014-Improvement of Rampa UP-Pabantala hat Road Ch.0.00m-2380m & 4646m-5484m .Under Rampal Upozila Bagerhat. Road ID No. 201733014 Salvage cost Tk. 2551146 | KDRIDP/Bager/W-74/2017-18 | 3.218 | 0 | 0 | 210.72 | 2018-03-06 | M/S Ziaul & Brothers, Bhandaria, Pirojpur | 2018-04-24 | 231.3 | 35% | 2019-04-29 | 0 | 31 | -31 | 13.4% | 1st R/A
Improvement of Village Road by BC
13 | 201734104-Banshtali UP-Solakora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201734018-Improvement of Kismat Kumlai-Saguna road Ch00-2080m by BC. Salvage amount Tk.2388545.00Fixed | KDRIDP/Bager/W-45/2017-18 | 2.08 | 0 | 0 | 154.76 | 2017-11-13 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 166.37 | 50% | 2019-12-22 | 0 | 65.83 | -65.83 | 39.57% | 0
15 | 201734028-Sakurhat-Saguna Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201734032-Telikhali-Baruipara Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 201734038-Development of KataKhali P/S - Dakra Road By HBB. Ch 1000-1650 m. Salvage Cost. TK.454832.00(2nd call) | KDRIDP/Bager/W-05/2016-17 | 0.65 | 0 | 0 | 21.95 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 23.6 | 100% | 2018-08-20 | 23.108 | 23.108 | 0 | 97.92% | Final
18 | 201734042-Development of Dakhin Mollikerber-Dhalipara Road By HBB. Ch 1140- 2950 m Under Rampal Upazila Bagerhat. Road ID No. 201734042. Salvage Cost. TK.333359. (2nd call) | KDRIDP/Bager/W-97/2018-19 | 1.81 | 0 | 0 | 112.347 | 2018-11-19 | Abul Kalam Azad, Terokhada, Khulna | 2018-12-31 | 106.73 | 90% | 2020-01-06 | 0 | 91.8 | -91.8 | 86.01% | 2nd R/A
19 | 201734046-Rajnagor-Gorerdanga Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 201734066-Foyla-Baburhat. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201734068-Amtala bazar-Pabantala Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 201734129-Development of Nolbunia borun BishasTran Bridge house-Babur bari bus Stand Road By BC. Ch (1915-2385m). Salvage Cost. TK.306072.00 (2nd call) | KDRIDP/Bager/W-07/2016-17 | 0.47 | 0 | 0 | 37.26 | 2017-11-13 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-01-04 | 40.15 | 100% | 2018-10-10 | 39.553 | 39.553 | 0 | 98.51% | Final
23 | 201735195-Development of Banga-Gilatola GC-Sorder Bari More-Hospital link Road Ch00-570m under Rampal Upazila District-Bagerhat Road ID No201735195 Salvage amount Tk.164834fixed | KDRIDP/Bager/W-59/2017-18 | 0.57 | 0 | 0 | 35.37 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 37.09 | 0% | 2018-11-06 | 0 | 0 | 0 | 0% | PD memo no. 663 dt. 10/03/19 Contract Cancelled due to Site problem
Improvement of Village Road by HBB
24 | 201734046-Development of Rajnagar-Gorerdanga Road By HBB. Ch 1000-1970 m. Salvage Cost. TK.226330.00(2nd Call) | KIDRIDP/Bager/W-06/2016-17 | 0.97 | 0 | 0 | 33.34 | 2017-09-27 | M/S Mijan Enterprise, Fakirhat, Bagerhat. | 2017-11-14 | 35.83 | 100% | 2018-08-20 | 0 | 29.22 | -29.22 | 81.55% | 2nd R/A
25 | 201734033-Improvement of Modnakhali-Khayghat-East Banstali cyclone shelter road Ch500-2000m by HBB Salvage amount Tk.592188.00 Fixed | KDRIDP/Bager/W-43/2017-18 | 1.5 | 0 | 0 | 67.54 | 2017-09-27 | M/S Ziaul & Brothers, Bhandaria, Perojpur | 2017-11-14 | 67.33 | 100% | 2018-11-20 | 67.141 | 67.141 | 0 | 99.72% | Final
26 | 201734139-Srifaltala new market-Veternary hospital via sarner field. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201734135-Sreefultola bridge - Jahanjhaia Hospatal Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
28 | 201732010-Construction of 60.00m Long RCC Girder Bridge on Balai Bridge-Rampal Road at Ch 3940m | KDRIDP/Bager/B-01/2017-18 | 0 | 60 | 0 | 358.53 | 2018-04-10 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-05-23 | 392.51 | 35% | 2019-05-29 | 0 | 111.29 | -111.29 | 28.35% | 2nd R/A
29 | 201732004-Construction of 30.00m Long RCC Girder Bridge on Foyla hat-Chaksree GC Road at Ch 841m | KDRIDP/Bager/B-06/2017-18 | 0 | 30 | 0 | 192.018 | 2018-08-13 | IT & JE JV, 13 Dharmashava cross road, Khulna. | 2018-10-09 | 210.4 | 0% | 2019-10-15 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
30 | 201734069-Construction of 48.00m Long RCC Girder Bridge on Gourbamha G.C-Konyadubi Kheya Ghat Road at Ch 1850m. | KDRIDP/Bager/B-15/2018-19 | 0 | 48 | 0 | 315.599 | 2018-10-08 | M/S Mohiuddin Ahmed, Patuakhali | 2018-12-02 | 343.999 | 0% | 2019-12-08 | 0 | 0 | 0 | 0% | 0
31 | 201734069-Gourbamha G.C-Konnadubi kheya ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
32 | 201732015-Periodic Maintenance of Tatulia bridge-Kadirkhola Road from Ch. 00m-1185m | KDRIDP/Bager/M-20/2017-18 | 1.185 | 0 | 0 | 25.848 | 2019-01-15 | M/S M R Khan Enterprise, Khulna | 2019-02-05 | 24.56 | 65% | 2020-02-11 | 0 | 8 | -8 | 32.57% | 1st R/A
| 201733009-Periodic Maintenance of Perikhali GC-Hurka UP Road from Ch. 00m-1860m |  | 1.86 | 0 | 0 | 57.19 |  |  |  | 54.33 |  |  | 0 | 17.7 | -17.7 | 32.58%
33 | 201733005-Perikhali GC -Bhojpatia UP Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 201734054-Ronsan-Mirakhali Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 201734104-Banshtali UP-Solakora | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
36 | Construction of Foylahat Growth Center | KDRIDP/Bager/GC-06/2017-18 | 0 | 0 | 1 | 21.55 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-03-28 | 20.889 | 100% | 2019-01-03 | 0 | 9.413 | -9.413 | 45.06% | 0
Landing/ Riverghat
37 | Construction of Kaligonj Khaya Ghat | KDRIDP/Bager/G-12/2017-18 | 0 | 0 | 1 | 21.59 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | No tender dropped
38 | Construction of Dakra Khaya Ghat | KDRIDP/Bager/G-13/2017-18 | 0 | 0 | 1 | 20.33 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | No tender dropped
Tree Plantation
39 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 35.359 | 138 | 3 | 3265.24 |  |  |  | 2800.298 | 24.23% |  | 129.802 | 637.625 | -507.823 | 22.77%

## Mongla
Mongla
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 00-4550 m. Salvage cost TK.8984664.00 Fixed | KDRIDP/Bager/W-02/2016-17 | 4.55 | 0 | 0 | 370.91 | 2017-06-14 | MSEBA and AB (JV), 211, Khanjahan Ali, Road, Khulna. | 2017-08-02 | 388.83 | 40% | 2019-05-31 | 0 | 101.72 | -101.72 | 26.16% | 0
2 | 201582005-Development of Mongla- Mithakhali- Mallikerbar Rampal Road by BC. CH 4550-8340 m. Salvage cost TK.4928783.00 Fixed(2nd Call) | KDRIDP/Bager/W-03/2016-17 | 3.79 | 0 | 0 | 261.14 | 2017-06-14 | M/S Apu & Brothers, 1/1 M.T. road, Khulna. | 2017-08-02 | 272.72 | 40% | 2019-05-31 | 0 | 75.06 | -75.06 | 27.52% | 1st R/A
3 | 201582006-Improvement of Chaterhat GC-Banshtola GC-Joymonirghol (Baddamary) Road by BC at Ch. 6670m-9270m (Road ID No-201582006) Salvage Amount Tk. 22,57,877.00 | KDRIDP/Bager/W-117/2018-19 | 3.686 | 0 | 0 | 312.814 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 201582007-Improvement of Digiraj-Jhalmalia Dhigi road. Ch.4040m-7395m. Salvage Cost Tk. 3563628 | KDRIDP/Bager/W-77/2017-18 | 3.355 | 0 | 0 | 314.226 | 2019-05-28 | JE & IE (JV), Sk. Abdul Hai Sarok, Mongla, Bagerhat | 0 | 313.462 | 0% | 0 | 0 | 0 | 0 | 0% | NOA issued on 08.07.19
Improvement of Union Road by BC
5 | 201583002-Burirdanga hat-Sonaeiltola UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201583007-Khulna-Mongla RHD at Goni Bridge- Burirdanga UP Office via Kapalirmeat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201583001-Impropment of Chandpai UP - Chila hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 201584014 - Khaserdanga more-Kharkharia-Dewotala bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 201584021-Bashtala bazar-Digraj bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201584030 - Chila hat-Monumia High School-Katakhali-Joymoni Battola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201584040 - Improvement of Mongla ( Fire brigate)- Malgazi C.S- Moukhali (GCCR).. (Ch:3100.00-4250m). Salvage Cost Tk. 153808.00 | KDRIDP/Bager/W-92/2017-18 | 1.15 | 0 | 0 | 85.497 | 2018-06-24 | M/S Bhi Bhi Enterprise, Mongla, Bagerhat | 2018-08-05 | 93.334 | 50% | 2019-08-11 | 0 | 39.54 | -39.54 | 42.36% | 2nd R/A
| 201584044 - Improvement of Holdibunia Baliar more-Burburia via malgazi-hid office Road. Ch3300m-4500m. Salvage Cost Tk.2220602.00 |  | 1.2 | 0 | 0 | 88.178 |  |  |  | 96.26 |  |  | 0 | 40.77 | -40.77 | 42.35%
12 | 201584045 - Development of Digraj College - Burirdanga FWC Ch. 650-2380 m. Salvage Cost. Tk. 2023367.00 | KDRIDP/Bager/W-11/2016-17 | 1.73 | 0 | 0 | 112.53 | 2017-06-13 | Sardar Jashim, Kharder, Bagerhat | 2017-08-02 | 118.01 | 70% | 2019-06-14 | 0 | 80.99 | -80.99 | 68.63% | 2nd R/A
13 | 201584071 - Sonailtola UP Office - Bokultola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 201584094 - Madurpalta Govt. Pond Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201584103 - Digraj bazar - Kitunia Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201584068-Improvement of Kumerkhali Bridge to Narkeltola Bridge to Masmara Village Road. Ch 0.00 -1895 m. Salvage Cost Tk. 4079725.00 | KDRIDP/Bager/W-66/2017-18 | 1.895 | 0 | 0 | 135.11 | 2018-01-24 | M/S Iqbal Enterprise, Mongla, Bagerhat | 2018-03-07 | 141.5 | 100% | 2019-03-13 | 140.06 | 140.06 | 0 | 98.98% | Final
Improvement of Village Road by HBB
17 | 201584030-Chila hat-Monumia High School-Katakhali-Joymoni Battola Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201584075- Khulna Mongla RHD Gania Bridge to Burirdanga Up Office via Kapalirmat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
19 | 201582007-Construction of 28.00m Long PSC Girder Bridge on Digiraj-Jhalmalia Dhigi Road at Ch 3980m | KDRIDP/Bager/B-03/2017-18 | 0 | 28 | 0 | 176 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. | 2018-07-28 | 190.38 | 75% | 2019-08-04 | 0 | 105.11 | -105.11 | 55.21% | 3rd R/A
20 | 201582006-Construction of 90.00m Long PSC Girder Bridge on Chaterhat GC-Banshtola GC-Joymonirghol Baddamary Road at Ch 6600m | KDRIDP/Bager/B-05/2017-18 | 0 | 90 | 0 | 569.596 | 2018-04-18 | M/S Abul Kalam Azad, Patuakhali | 2018-06-06 | 624.509 | 0% | 2019-12-31 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
21 | 201584044-Construction of 22.00m Long RCC Girder Bridge on Holdibunia (Baliar more)-Burburia via Malgazi-Hid office Road at Ch 2900m | KDRIDP/Bager/B-02/2017-18 | 0 | 22 | 0 | 177.85 | 2018-02-20 | M/S Mizan Enterprise, Madaripur | 2018-04-11 | 184.07 | 60% | 2019-04-17 | 0 | 85.99 | -85.99 | 46.72% | 2nd R/A
22 | 201584035-Construction of 25.00m Long PSC Girder Bridge on Banshtala Bridge Pakhimara Khal-Shikari Houst at Burburia Road at Ch 1510m | KDRIDP/Bager/B-04/2017-18 | 0 | 25 | 0 | 196 | 2018-06-04 | AKA & IE (JV), Sk. Abdul Hai Sarak, Mongla, Bagerhat. | 2018-07-28 | 212.98 | 60% | 2019-08-04 | 0 | 89.99 | -89.99 | 42.25% | 2nd R/A
Maintenance
23 | 201582007-Digraj-Jholmolia Dhige Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 201583002-Burirdangahat Sonailtala up Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201584060-Periodic Maintenance of Khanjahan Ali Hat-RHD Road at Gazir bridge from Ch. 00m-1000m. (201583007) | KDRIDP/Bager/M-15/2018-19 | 1 | 0 | 0 | 19.376 | 2018-11-06 | M/S Noyan Enterprise, Dhansagor, Sharankhola, Bagerhat | 2019-01-07 | 18.407 | 0% | 2019-07-13 | 0 | 0 | 0 | 0% | 0
GC-Hat
26 | Construction of Mithakhali Growth Center | KDRIDP/Bager/GC-07/2017-18 | 0 | 0 | 1 | 19.38 | 2018-02-08 | M/S Sk. Nurul Amin, Mongla, Bagerhat | 2018-03-28 | 20.29 | 100% | 2019-01-31 | 20.216 | 20.216 | 0 | 99.64% | Final
Landing/ Riverghat
27 | Digraj Kheyaghat | KDRIDP/Bager/G-05/20 17-18 | 0 | 0 | 1 | 17.77 | 2017-11-29 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-02-01 | 17.53 | 0% | 2018-11-06 | 0 | 0 | 0 | 0% | Site Problem
28 | Chila Growth Center Ghat | KDRIDP/Bager/G-04/2017-18 | 0 | 0 | 1 | 20.41 | 2017-11-29 | M/S Antar Enterprise, Mongla, Bagerhat. | 2018-02-01 | 20.37 | 100% | 2018-11-27 | 20.285 | 20.285 | 0 | 99.58% | Final
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 22.356 | 165 | 3 | 2876.787 |  |  |  | 2712.652 | 23.97% |  | 180.561 | 799.731 | -619.17 | 29.48%

## Morrelgonj
Morrelgonj
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201602002 - Chingrakhali GC-Daibajnahati GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201602006 - Pollerhat GC-Chingrakhali UP-Zianagar RHD (Morel Part) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 201602007-Dhansagar RHD-Baniakhali GC Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 201602012 - Khalkula Steel bridge to Chingrakhali bazar via Kachuabunia Rahmatia School | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 201603002 - Improvement of Baharbunia U.P.-Madrasa Hat Road by BC from Ch. 00m-5200m under Morrelgonj Upazila Bagerhat. Salvage Amount Tk. 62,96,862.00 | KDRIDP/Bager/W-99/2018-19 | 5.2 | 0 | 0 | 439.996 | 2019-01-20 | M/S Jharna Enterprise, 13 Dharmashava cross Road, Khulna | 2019-03-24 | 417.908 | 0% | 2020-03-30 | 0 | 0 | 0 | 0% | Re-tender dt. 03.04.18
6 | 201603003 - Mazhibari RHD at Badsharhat-Nishanbaria U.P office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 201603004 - Improvement of Khowla UP office-CARE bazar RHD ch2686-4906m | KDRIDP/Bager/W-51/2017-18 | 2.22 | 0 | 0 | 127.62 | 2017-10-03 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2017-11-28 | 116.71 | 100% | 2018-12-04 | 113.93 | 113.93 | 0 | 97.62% | Final
8 | 201603007 - Improvement of Banagrame Bazar-Hoglapasha U.P Road by BC Ch.4840m-5800m. Salvage Cost Tk. 7,08,811.00 | KDRIDP/Bager/W-105/ 2018-19 | 0.96 | 0 | 0 | 72.463 | 2019-05-12 | M/S Sweet Enterprise, Basabati, Bagerhat | 2019-06-10 | 68.84 | 0% | 2020-06-16 | 0 | 0 | 0 | 0% | 0
9 | 201603009 - Morrelgonj-Upazila H.Q.to Baharbunia Union H.Q. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 201603010 - Putikhali UP office-Sonakhali bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201603012 - Hoglabunia UP office-Lakhaner hat via Nager Hat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201603017 - Baraikhali UP office-JeoDhara UP via Kalibari bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201603019 - Improvement of Banagram UP- Shailkhali ch2100-2343m | KDRIDP/Bager/W-52/2017-18 | 0.243 | 0 | 0 | 15.39 | 2017-10-03 | M/S Sher-e-Bangla Traders, Mathbaria, Perojpur | 2017-11-28 | 14.82 | 100% | 2019-05-30 | 0 | 0 | 0 | 0% | 0
14 | 201603015-Improvement of Jewdhara UP office -Joybangla bazar Ekramkhali Baytun Akram Hazi Bari Mosque road. Ch: 00-2169m | KDRIDP/Bager/W-56/2017-18 | 2.169 | 0 | 0 | 159.219 | 2017-10-26 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-12-13 | 166.84 | 45% | 2019-05-30 | 0 | 49.52 | -49.52 | 29.68% | 2nd R/A
Improvement of Village Road by BC
15 | 201604011-Chingrakhali-Dharadoha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 201604027 - Improvement of Gabagachia-Burujbaria road. Ch 500m-2150m. Salvage Cost Tk.49606.00. | KDRIDP/Bager/W-70/2017-18 | 1.65 | 0 | 0 | 127.54 | 2018-01-25 | Md. Shariful Alam, Fakirhat, Bagerhat | 2018-03-11 | 126.778 | 10% | 2019-03-17 | 0 | 0 | 0 | 0% | 0
17 | 201604044 - R&H road (at Saralia wooden bridge)-Kutghata bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 201604050 - Amtala bazar-Chandipur Highschool via Taltola bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 201604065 - Improvement of Srenikhali- Bashbaria road Paschim Kalikabari- C & B road ch800-2480m. Salvage amount tk.482190.00 fixed | KDRIDP/Bager/W-54/2017-18 | 1.68 | 0 | 0 | 123.3 | 2017-10-04 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-11-28 | 128.23 | 60% | 2019-05-31 | 0 | 61.77 | -61.77 | 48.17% | 2nd R/A
20 | 201604069 - Chingrakhali FRB Road-Khalkula-sagorkati | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 201604072 - Improvement of Tulatola RHD near h/o M. Talukder-Uttttarjoka RHD ch4250-5140m. Salvage Amount Tk.502421.00 fixed | KDRIDP/Bager/W-53/2017-18 | 0.89 | 0 | 0 | 51.02 | 2017-10-03 | M/S Faruk Enterprise, Kachua, Bagerhat | 2017-11-19 | 53.54 | 100% | 2018-11-25 | 53.54 | 53.54 | 0 | 100% | Final
22 | 201604074 - Development of Bashbaria R & H to Mongolerhat. CH 00-1260 m. Salvage Cost. TK. 109498.00 | KDRIDP/Bager/W-21/2016-17 | 1.26 | 0 | 0 | 100.49 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-07 | 104.567 | 100% | 2018-08-29 | 104.426 | 104.426 | 0 | 99.87% | Final
23 | 201604088 - Panchakaran UP office to Sonakhali bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 201604098 - Chairman Bazar-RHD road via H/O Master Abul Kashem | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 201605121--Daskhali RHD-Shoilkhali Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 201605095-Kalibari Bazar - Srizon Smriti high School via Mothbaria School Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 201605124-Improvement of Nurul Islam Dakhil Madrasa-Gulishakhali UP office via Sonamuddin Chokidar Bari by BC Road from Ch. 00m-2500m. Salvage Amount Tk. 3,56,993.00 | KDRIDP/Bager/W-98/2018-19 | 2.5 | 0 | 0 | 228.918 | 2018-11-22 | M/S Jharna Enterprise, 13 Dharmashava cross road, Khulna. | 2019-01-02 | 227.95 | 10% | 2020-01-08 | 0 | 0 | 0 | 0% | Re-tender dt. 03.04.18
28 | 201605004-Development of Kalikabari- Guabaria Road. Ch 220 - 2776 m | KDRIDP/Bager/W-09/2016-17 | 2.556 | 0 | 0 | 209.99 | 2017-08-07 | M/S Polli Stors, Town kalikapur, Patuakhali | 2017-09-11 | 217.576 | 20% | 2019-05-31 | 0 | 8.75 | -8.75 | 4.022% | 1st R/A
29 | 201604140-Improvement of Badshar hat C & B- Hasan Member bari Mazibari road via Tassen Uddin Howlader bari road. Ch00m-2130m. Salvage Cost Tk.172678.00. | KDRIDP/Bager/W-69/2017-18 | 2.13 | 0 | 0 | 153.08 | 2018-01-30 | Sayed Milon, Post office road, Jhalokathi. | 2018-02-20 | 157.599 | 40% | 2019-05-09 | 0 | 62.25 | -62.25 | 39.5% | 2nd R/A
30 | 201605061-Improvement of Sleeper bridge Near RHD North Balvadrapur Shasapara via Tripolli RNGPS ch 00-1482m | KDRIDP/Bager/W-55/2017-18 | 1.482 | 0 | 0 | 104.457 | 2017-10-26 | M/S Prince & Co. Nalcity, Jhallakathi. | 2017-12-14 | 108.63 | 60% | 2019-11-30 | 0 | 56.63 | -56.63 | 52.13% | 2nd R/A
31 | 201605124-Improvement of NUrul Islam Dhakil Madrasha Gulishakhali UP Office via Sona Muddin Chokider bari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 201604063-Morrelganj-Bisarighata | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 201605165-W.Kachubunia Primary School Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
34 | 201605021-Mohonpur-Banagramme Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 201604098-Moslem khan's house - Gharami bari bridge Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 201604140-Badshar hat C & B - Hasan Member bari (Mazibari) road via Tassen Uddin Howlader bari | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
37 | 201603021-Construction of 22.00m Long RCC Girder Bridge on Putikhali U.P.-Panchakaran UP via Gazalia bazar Road at Ch 2738m. | KDRIDP/Bager/B-14/2017-18 | 0 | 22 | 0 | 195.2 | 2018-08-13 | IT & JE JV, 13 Dharmashava Cross Road, Khulna. | 2018-10-09 | 203.008 | 60% | 2019-10-15 | 0 | 113.07 | -113.07 | 55.7% | 2nd R/A
38 | 201605020-Construction of 13.00m Long RCC Girder Bridge on Balavadrapur (Badhal Bazar)-Mohonpur Road at Ch 4200m | KDRIDP/Bager/B-16/2018-19 | 0 | 13 | 0 | 85.77 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Chainage Problem
39 | 201604098-Const. of RCC Bridge on Moslem khan's house - Gharami bari bridge Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 201603006-Construction of 54.00m Long RCC Girder Bridge on Baharbunia U.P-Shonirjore Bazer Near the House of Talukder Mustafizur Rahman Road at Ch 1191m | KDRIDP/Bager/B-09/2017-18 | 0 | 54 | 0 | 306.29 | 2018-06-04 | MKB-MSE (JV), Nalchity, Jhalakati | 2018-07-29 | 325 | 40% | 2019-08-04 | 0 | 105.69 | -105.69 | 32.52% | 2nd R/A
41 | 201605061-Improvement of Sleeper Bridge near RHD north Balvadrapur Shahapara via Tripolli RNGPS. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
42 | 201603007 - Periodic Maintenance of Banagrame Bazar-Hoglapasha U.P Road from Ch. 00m-2523m | KDRIDP/Bager/M-16/2018-19 | 2.523 | 0 | 0 | 69.157 | 2018-11-05 | M/S Roni Enterprise, Bagerhat | 2019-01-09 | 65.699 | 50% | 2020-01-15 | 0 | 27.58 | -27.58 | 41.98% | 2nd R/A
43 | 201604059 - Sannashi Launch ghat-Chairmanbazar-(Sannashi Bazer) Pallimangal C&B road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Landing/ Riverghat
44 | Amtoli Bazar Khal | KDRlDP/Bager/G-01/2017-18 | 0 | 0 | 1 | 17.04 | 2017-11-29 | M/S Shikto Enterprise, Zianagar, Perojpur. | 2018-01-21 | 16.65 | 100% | 2018-10-27 | 16.596 | 16.596 | 0 | 99.68% | Final
45 | Sannasi Bazar Khal | KDRlDP/Bager/G-03/2017-18 | 0 | 0 | 1 | 25.78 | 2017-11-30 | M/S Shanta & Brothers, Basabati, Bagerhat. | 2018-02-05 | 24.98 | 40% | 2018-11-11 | 0 | 0 | 0 | 0% | 0
46 | Bisharighata Bazar Khal | KDRlDP/Bager/G-02/2017-18 | 0 | 0 | 1 | 19.64 | 2018-01-25 | N & S brothers, College Road, Morrelgonj, Bagerhat | 2018-03-07 | 20.3 | 100% | 2018-07-13 | 20.227 | 20.227 | 0 | 99.64% | Final
Tree Plantation
47 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 27.463 | 89 | 3 | 2632.36 |  |  |  | 2565.625 | 22.02% |  | 308.719 | 793.979 | -485.26 | 30.95%

## Sharankhola
Sharankhola
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 201772004-Amragachia RHD - Banglabazar GC road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 201772006-Development of Baniakhali GC- Dhansagar RHD Road. Ch 1000 -3805 m. Salvage TK. 1634778.00 | KDRIDP/Bager/W-08/2016-17 | 2.805 | 0 | 0 | 210.72 | 2017-06-08 | M/S Ahamed Steel Industries, Kapuria patty, Mathbaris, Barisal | 2017-07-20 | 219.13 | 100% | 2018-09-02 | 217 | 217 | 0 | 99.03% | Final
3 | 201772007-Tafalbari GC-Rasulpur GC-Rajapur GC-Pollanbari RHD Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 201773004-Banglabazar GC-Dhansagar UP Office Rd via Rashid Khan Bridge Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
5 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 201774006: Improvement of Kadamtala Ashar alo Mosjid- Varanirper upgrade GPS Road Ch4885-5885m | KDRIDP/Bager/W-26/2017-18 | 1 | 0 | 0 | 56.797 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 54.46 | 100% | 2018-07-10 | 51.601 | 51.601 | 0 | 94.75% | Final
7 | 201774007: Nalbunia-Baniakhali road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 201774011-Improvement of Rajapur-Dhansagar Bazar Road by BC at Ch.505m-1875m. Salvage Amount Tk. 2,04,825.00 | KDRIDP/Bager/W-91/2017-18 | 1.37 | 0 | 0 | 89.544 | 2018-07-08 | M/S Habib Enterprise, Sundorghona, Bagerhat | 2018-08-27 | 92.9 | 100% | 2019-09-02 | 0 | 60.76 | -60.76 | 65.4% | 2nd R/A
| 201774048-Improvement of Rajapur WAPDA-Rajapur GC (Police Fary) Bazar Road by BC at Ch.675m-1450m. Salvage Amount Tk. 4,36,293.00 |  | 0.775 | 0 | 0 | 51.07 | 2018-07-08 |  |  | 52.99 |  |  | 0 | 34.66 | -34.66 | 65.41%
9 | 201774018: Improvement of Golbunia Talukderbari-Motherper Ladenmor Road Ch2900-4300m. Salvage amount -tk.548997.00( fixed) | KDRIDP/Bager/W-27/2017-18 | 1.4 | 0 | 0 | 80.36 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 75.29 | 100% | 2018-07-10 | 73.384 | 73.384 | 0 | 97.47% | Final
10 | 201774022: Jhilbunia-Lakurtala road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 201774023: Khada -Lakurtala Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 201774024: Improvement of Banglabazar-Tafalbari-Mourashi Road by BC at Ch. 1350m-3400m. Salvage Amount Tk. 2,10,068.00 | KDRIDP/Bager/W-112/2018-19 | 2.05 | 0 | 0 | 153.259 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 201774025: Improvement of Khada-North Tafalbari-Mourasi Bazar Road by BC at Ch.00m-2000m. Salvage Amount Tk. 3,78,627.00 (2nd Call) | KDRIDP/Bager/W-90/2017-18 | 2 | 0 | 0 | 135.226 | 2018-07-05 | M/S Noyan Enterprise, Sharankhola, Bagerhat | 2018-08-27 | 139.28 | 35% | 2019-09-02 | 0 | 28 | -28 | 20.1% | 1st R/A
14 | 201774035:Improvement of Bakultala-Sonatala Road by BC at Ch. 00m-1600m. Salvage Amount Tk. 9,48,202.00 | KDRIDP/Bager/W-113/2018-19 | 1.6 | 0 | 0 | 116.159 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 201774040: Improvement of Khontakata-Charerper Road by BC at Ch.1640m-3280m. Salvage Amount Tk. 388301.00 | KDRIDP/Bager/W-81/2017-18 | 1.64 | 0 | 0 | 112.27 | 2018-05-29 | M/S Sohana Enterprise, Sharankhola, Bagerhat | 2018-06-28 | 117.58 | 60% | 2019-07-04 | 0 | 45.971 | -45.971 | 39.1% | 2nd R/A
16 | 201775078-Improvement of Rajapur Bayor-Saver Madrasa via Gojen Roy House Road by BC at Ch.00m-1500m. Salvage Amount Tk. 572444.00 | KDRIDP/Bager/W-82/2017-18 | 1.5 | 0 | 0 | 97.406 | 2018-06-11 | M/S Sohana Enterprise, Sharankhola, Bagerhat | 2018-06-28 | 102.016 | 50% | 2019-07-04 | 0 | 31.75 | -31.75 | 31.12% | 2nd R/A
17 | 201774047-Improvement of Taltoli bazer-Nalbunia (Bezitana) bazer Road Ch1500-2505m. Salvage amount -tk.554716.00 (fixed) | KDRIDP/Bager/W-28/2017-18 | 1.005 | 0 | 0 | 62.45 | 2017-08-23 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2017-10-04 | 58.02 | 100% | 2018-07-10 | 55.247 | 55.247 | 0 | 95.22% | Final
Improvement of Village Road by HBB
18 | 201774013-Improvement of Purba Khontakata-Nalbunia Road by HBB at Ch.00m-1378m & 2818m-4090m. Salvage Amount Tk. 2312135.00 | KDRIDP/Bager/W-83/2017-18 | 2.65 | 0 | 0 | 111.809 | 2018-05-13 | M/S Chan Enterprise, Puraton Bazar, Bagerhat | 2018-06-18 | 116.84 | 20% | 2019-06-24 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Upazila Road (7.30m width)
19 | 201772004-Construction of 42.00m Long RCC Girder Bridge at Amragachia RHD-Banglabazar GC Road at Ch 4200m | KDRIDP/Bager/B-11/2017-18 | 0 | 42 | 0 | 235.666 | 2018-05-09 | EFTE.ETCL (PVT.) LIMITED, Eastern Paradise, 35, Segun Bagicha, Suit-302, (3rd Floor) Shahbag, Dhaka | 2018-12-13 | 246.85 | 0% | 2019-12-19 | 0 | 0 | 0 | 0% | 0
20 | 201772007-Construction of 22.00m Long RCC Girder Bridge at Tafalbari GC- Rasulpur GC- Rajapur GC- Pollanbari RHD Road at Ch 1215m | KDRIDP/Bager/B-08/2017-18 | 0 | 22 | 0 | 183.14 | 2018-05-09 | EFTE.ETCL (PVT.) LIMITED, Eastern Paradise, 35, Segun Bagicha, Suit-302, (3rd Floor) Shahbag, Dhaka | 2018-12-13 | 192.208 | 0% | 2019-12-19 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
21 | 201774020-Construction of 30.00m Long RCC Girder Bridge on South Amragachia-Jibanduari Road at Ch 3500m. (201774019) | KDRIDP/Bager/B-07/2017-18 | 0 | 30 | 0 | 213.51 | 2018-05-09 | EFTE.ETCL (PVT.) LIMITED, Eastern Paradise, 35, Segun Bagicha, Suit-302, (3rd Floor) Shahbag, Dhaka | 2018-12-13 | 223.976 | 0% | 2019-12-19 | 0 | 0 | 0 | 0% | 0
Maintenance
22 | 201774005: Pallanbari (Chutu Kharhat)-Khajurbaria Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 201774016-Periodic Maintenance of Baniakhali GC-Pollanbari RHD via B-Dhansagar Community Clinic Delower house Sharankhola part Road from Ch. 1500m-3500m. | KDRIDP/Bager/M-06/2017-18 | 2 | 0 | 0 | 30.03 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 29.805 | 10% | 2019-01-17 | 29.805 | 29.805 | 0 | 100% | Final
24 | 201774023: Periodic Maintenance of Khada- Lakurtala Road from Ch. 00m-1350m | KDRIDP/Bager/M-07/2017-18 | 1.35 | 0 | 0 | 20.09 | 2018-02-24 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-04-11 | 19.918 | 100% | 2019-01-17 | 18.93 | 18.93 | 0 | 95.04% | Final
25 | 201774024: Periodic Maintenance of Banglabazar-Tafalbari-Mourashi Road from Ch. 00m-930m | KDRIDP/Bager/M-17/2018-19 | 0.93 | 0 | 0 | 21.648 | 2018-11-07 | M/S S. Zaman Enterprise, Daulatpur, Khulna | 2019-01-10 | 20.566 | 0% | 2019-07-16 | 0 | 0 | 0 | 0% | 0
GC-Hat
26 | Construction of Banglabazar Growth Center | KDRIDP/Bager/GC-04/2017-18 | 0 | 0 | 1 | 19.45 | 2018-02-08 | M/S Shovo Enterprise, Nagerbazar, Bagerhat. | 2018-08-02 | 20.13 | 60% | 2019-05-08 | 0 | 5.995 | -5.995 | 29.78% | 0
Landing/ Riverghat
27 | Rayenda Bandaghataghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | Construction of Tafalbari GC Ghat | KDRIDP/Bager/G-11/2017-18 | 0 | 0 | 1 | 17.25 | 2017-12-27 | M.A. Jalil Khan, 47/4, Rupsha stand road, Khulna. | 2018-02-19 | 16.23 | 20% | 2018-11-25 | 0 | 0 | 0 | 0% | NOA issued on 22.01.18
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 24.075 | 94 | 2 | 2017.854 |  |  |  | 1798.189 | 29.48% |  | 445.967 | 653.103 | -207.136 | 36.32%

## Summary
BAGERHAT
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 10 | 8 | 33.741 | 0 | 0 | 2122.952 | 537.35 | 54.17% | 25.31%
Union Road by BC | 17 | 15 | 33.694 | 0 | 0 | 1989.118 | 725.785 | 62.86% | 36.49%
Village Road by BC | 64 | 59 | 87.171 | 0 | 0 | 5824.754 | 3870.801 | 80.35% | 66.45%
Village Road by HBB | 15 | 15 | 17.639 | 0 | 0 | 920.568 | 678.904 | 91.33% | 73.75%
Bridge on Upazila Road | 8 | 8 | 0 | 344 | 0 | 2314.427 | 397.4 | 26.88% | 17.17%
Bridge on Union Road/Village Road | 11 | 10 | 0 | 257.3 | 0 | 1710.482 | 577.32 | 60% | 33.75%
Maintenance | 21 | 21 | 42.956 | 0 | 0 | 822.019 | 619.01 | 75.23% | 75.3%
GC-Hat | 5 | 5 | 0 | 0 | 5 | 98.163 | 54.087 | 91% | 55.1%
Landing/ Riverghat | 11 | 9 | 0 | 0 | 11 | 163.27 | 68.428 | 51.11% | 41.91%
Tree Plantation |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 162 | 150 | 215.201 | 601.3 | 16 | 15965.753 | 7529.085 | 59.29% | 47.16%