## Satkhira
SATKHIRA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Assasuni
1 | 287042010-Chiledanga RHD - Bangadah GC Paithali Bazer Rd. | [13 empty] | 0 | #DIV/0!
2 | 287042012-Mohishkur RHD - Bashtala bazar via Mohishkur GC Road (Assasuni part). | [13 empty] | 0 | #DIV/0!
3 | 287042013-Protapnagar GC-Pakhimara RHD(Assasuni part). | [13 empty] | 0 | #DIV/0!
Debhata
4 | 287252007-Improvement of Subornabad GC-Bangdah GC Road by BC (Ch. 3240-5240m) with 15nos. 625mmX600mm U-Drain at Ch. 3241m, 3275m, 3352m, 3529m, 3568m, 3678m, 3705m, 3952m, 4093m, 4291m 4539m, 4642m, 4816m, 5032m & 5058m on the Same Road. | KDRIDP/Sat/W-08/2016-17 | 2 | 0 | 0 | 165.74 | 2017-05-22 | M/S Habib Enterprise Satkhira | 2017-06-14 | 173.1 | 100% | 2018-06-20 | 172.248 | 172.248 | 0 | 99.51% | Salvage Amount Tk. 8,93,628 Final
5 | 287252008-Improvement of Bohera Bazar (RHD) - Ellarchor Bazar -Bangdah GC(Sadar) Road by BC (Ch. 6704-8000m) with 3nos. 625mmX600mm U-Drain at Ch.7050m, 7640m & 7775m and 1no. 900mmX900mm U-Drain at Ch. 7700m on the Same Road | KDRIDP/Sat/W-07/2016-17 | 1.296 | 0 | 0 | 87.3 | 2017-05-22 | M/S Joint Bricks Traders Bankal, Satkhira | 2017-07-02 | 84.78 | 100% | 2018-10-08 |  | 76.054 | -76.054 | 89.71% | 1st R/A Bill
6 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 8000-9660m | KDRIDP/Sat/W-61/2017-18 | 1.66 | 0 | 0 | 146.46 | 2018-05-30 | M/S Joint Bricks Traders, Bankal, Satkihra | 2018-07-12 | 153.787 | 100% | 2019-06-20 |  | 16 | -16 | 10.4% | 1st R/A Bill
7 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 9660m-11910m | KDRIDP/Sat/ W-85/2018-19 | 2.25 | 0 | 0 | 211.187 | 2019-04-30 | M/S Joint Bricks Traders, Bankal, Satkhira. | 2019-06-19 | 216.994 | 0% | 2020-06-25 |  |  |  |  | Salvage amount Tk. 458337.00
Kaligonj
8 | 287472004-Khanpur-Baliadanga GC-Uzirpur GC via Gobindokatihat Rd. | [13 empty] | 0 | #DIV/0!
9 | 287472005-Improvement of Raipur RHD - Noornagar GC Via Sirajpur Hat Road at Ch 600-3385m | KDRIDP/Sat/W-29/2017-18 | 2.79 | 0 | 0 | 265.359 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk. 4462226.00
10 | 287472006-Improvement of Dudly RHD - Ratanpur GC Road at Ch 00-4200m, | KDRIDP/Sat/W-28/2017-18 | 4.08 | 0 | 0 | 388.96 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk. 8575180.00
11 | 287472010-Approach of Bashtola bridge | [13 empty] | 0 | #DIV/0!
Tala
12 | 287902001-Improvement of Tala-Kalaroa UP HQ via Dalua GC-Patkelghata GC road Tala Portion road by BC (Ch. 10020-11788m) with 1no. 925mmX900mm U-Drain at Ch. 11160m on the Same Road | KDRIDP/Sat/W-09/2016-17 | 1.94 | 0 | 0 | 160 | 2017-06-08 | M/S Basu Traders Tala, Satkhira | 2017-07-11 | 158.79 | 100% | 2018-09-28 |  | 137.138 | -137.138 | 86.36% | Salvage Amount Tk. 3,08,136/-
13 | 287902004-Improvement of Jethua GC-Budhata GC via Horihornagar Bazar (Tala Portion) Road by BC at Ch. 11830m-16250m | KDRIDP/Sat/ W-94/2018-19 | 4.42 | 0 | 0 | 417.939 | 2018-12-18 | M/S Rafid Traders- M/S Bosu Traders (JV), Tala, Satkhira | 2019-02-24 | 401.259 | 25% | 2020-03-01 |  |  | 0 | 0%
14 | 287902005-Improvement of Kopilmoni GC-Jatua GC road at Ch. 5465-6429m | KDRIDP/Sat/W-57/2017-18 | 0.964 | 0 | 0 | 78.67 | 2018-04-10 | Uttam Traders, Tala, Satkhira. | 2018-05-21 | 82.434 | 100% | 2019-05-27 | 82.434 | 82.434 | 0 | 100% | Final
Shyamnagar
15 | 287862002-Improvement of Nowabenki GC - Khanpur R&H via Vetkhali GC road at (Ch. 27100-29000m & Ch. 32300-34100m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 27350m, 27800m & 33200m on the Same Road | KDRIDP/Sat/W-11/2016-17 | 3.7 | 0 | 0 | 321.22 | 2017-10-09 | mewebajv Shyamnagar, Satkhira | 2017-12-03 | 330.37 | 70% | 2019-05-31 |  | 199.21 | -199.21 | 60.3% | 3rd R/A Bill
16 | 287862005-Pakhimara R&H -Protapnagar GC Road | [13 empty] | 0 | #DIV/0!
Kalaroa
17 | 287432005-Kalaroa GC-Gaira GC via Chandanpur UP Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 25.1 | 0 | 0 | 2242.835 |  |  |  | 1601.514 | 74.38% |  | 254.682 | 683.084 | -428.402 | 42.65%
Improvement of Union Road by BC
Satkhira Sadar
1 | 287823010-Mahamudpur Bazar-Abaderhat Via Jaghanathpur road. | [13 empty] | 0 | #DIV/0!
2 | 287823020 - Improvement of Ghona Bazar - Kushkhali UPC Bhadra Ziader more road via Aruakhali GPS at ch 1665-2687m and 2687-3914m | KDRIDP/Sat/W-69/2017-18 | 2.25 | 0 | 0 | 170.68 | 2018-06-28 | M/S Uttam Traders Tala, Satkhira | 2018-08-16 | 178.84 | 45% | 2019-08-22 |  | 48.895 | -48.895 | 27.34% | 2nd R/A bill
3 | 287823020-Improvement of Ghona Bazar - Kushkhali UPC (Bhadra Ziader more) road via Aruakhali GPS road by BC at ch.00-1665m | KDRIDP/Sat/W-104a/2018-19 | 1.665 | 0 | 0 | 140.697 | 2019-04-23 | Sk Sirajul Haq Labsha, Satkhira. | 2019-06-27 | 140.613 | 0% | 2020-06-27 |  |  | 0 | 0% | Salvage amount Tk.456583.00
4 | 287823022-Agordari UP Office (Abadehat GC ) - Bharukhaki Bazar ( Bharukhali GPS) Road Via Jhitkee | [13 empty] | 0 | #DIV/0!
5 | 287823023-Bali UP office - Raipur Bazar road via Shumundanga | [13 empty] | 0 | #DIV/0!
Assasuni
6 | 287043001-Kadakati UP office - Kadakati GC via Gabtala Bazar road. | [13 empty] | 0 | #DIV/0!
7 | 287043004-Ekshora bazar-Bichotbazar(Anulia UP) Rd. | [13 empty] | 0 | #DIV/0!
8 | 287043008-Dargapur UP Office-Tentulia Bazer Rd. | [13 empty] | 0 | #DIV/0!
9 | 287043010-Paithali Bazar - Sobhnali UP office via Kamalkati kheyaghat road. | [13 empty] | 0 | #DIV/0!
10 | 287043011-Bardal UP office - Kapsanda Bazar via Baintala & Fatikkhali road. | [13 empty] | 0 | #DIV/0!
Debhata
11 | 287253002-Sakhipur UP-Nangla Bazar via Eidgah Chandipur Road | [13 empty] | 0 | #DIV/0!
12 | 287253003-Debhata UP Office-Komorpur Road(Debhata Portion) | [13 empty] | 0 | #DIV/0!
13 | 287253005-Nowapara UP -Bodarhata GC via Chandpur Atapur road. | [13 empty] | 0 | #DIV/0!
Tala
14 | 287903003-Patkelghata GC(R&H) near Pollibiddut-Khalishkhali UP Road. | [13 empty] | 0 | #DIV/0!
15 | 287903006-(a) Improvement of Tala UP Office Hospital-Jatpur GC road by BC (Ch. 1596-5096m) (b) Construction of 6nos. 625mmX600mm U-Drain at Ch. 169m, 2896m, 3396m, 3641m, 3946m & 4616m and (c) Construction of 1no. 925mmX900mm U-Drain at Ch. 2286m on the Same Road | KDRIDP/Sat/W-10/2016-17 | 3.5 | 0 | 0 | 226.07 | 2017-06-12 | Md. Iqbal Jamader, Polashpole, Satkhira | 2017-07-16 | 223.62 | 100% | 2018-05-30 | 219.69 | 219.69 | 0 | 98.24% | Salvage Amount Tk. 1,39,115.00 Final
16 | 287903013-Improvement of Khesra UP-Shalika Bazar via Dakshin Sahjadpur Bazar & KSD Girls School Road by BC at Ch. 00m-900m , 3294m-3902m & 6879m-8870m | KDRIDP/Sat/ W-95/2018-19 | 3.499 | 0 | 0 | 264.3 | 2018-12-18 | M/S Bosu Traders Tala, Satkhira | 2019-02-24 | 249.619 | 35% | 2020-03-01 |  | 68 | -68 | 27.24% | Salvage Amount Tk. 846368.00
17 | 287903007-Improvement of Magura UP Office-Madra Bazar road at Ch. 1000-2215m | KDRIDP/Sat/ W-56/2017-18 | 1.215 | 0 | 0 | 79.239 | 2018-04-10 | M/S Raka Enterprise, Tala, Satkhira. | 2018-05-21 | 79.235 | 100% | 2019-06-24 | 79.013 | 79.013 | 0 | 99.72% | Final
17 | 287903015-Improvement of Islamkati UP Office-Magura Bazar road at Ch. 1000-2215m |  | 0.982 | 0 | 0 | 64.59 |  |  |  | 64.586 |  |  | 64.405 | 64.405 | 0
18 | 287903011-Improvement of Nagarghata UP-Pulirhat road at Ch. 00-1670m | KDRIDP/Sat/ W-55/2017-18 | 1.67 | 0 | 0 | 116.069 | 2018-04-10 | M/S Uttam Traders Tala, Satkhira | 2018-11-29 | 119.888 | 10% | 2019-12-07 |  |  |  | 0% | NOA issued on 03.05.18
19 | 287903008-Improvement of Tentulia UP Office Madanpur R&H-Ghona Bazar via Dewanipara Bazar road by BC Ch.2000-4000m | KDRIDP/Sat/ W-113/2018-19 | 2 | 0 | 0 | 148.804 | 2019-06-18 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 3228643.00
20 | 287903013-Khesra UP-Dakshin Sahjadpur Bazar | [13 empty] | 0 | #DIV/0!
Kalaroa
21 | 287433002-(a) Improvement of Jalalabad UP Koila more - Batra bazar road at (Ch. 5050-6920m) by 25mm BC + 7mm SC (b) Construction of 3nos. 315mm PVC Pipe Drain at Ch. 5290m, 6770m & 6828m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 6190m, 6296m & 6504m on the Same Road. | KDRIDP/Sat/W-17/2016-17 | 1.87 | 0 | 0 | 117.52 | 2017-07-17 | M/S Sarder Bricks Kalaroa, Satkhira | 2017-09-06 | 111.406 | 100% | 2018-09-21 |  | 88 | -88 | 78.99%
22 | 287433005-Chandanpur UO-Sultanpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
23 | 287433006-(a) Improvement of Chandanpur UP - Hejaldi bazar via Sultanpur bazar road at (Ch. 3600-7270m) by 25mm BC + 7mm SC (b) Construction of 8nos. 315mm PVC Pipe Drain at Ch. 4282m, 4560m, 5014m, 5172m, 5229m, 5278m, 5784m & 6116m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 4828m, 6337m & 6518m on the Same Road. | KDRIDP/Sat/W-16/2016-17 | 3.67 | 0 | 0 | 262.63 | 2017-07-17 | Sk. Sirajul Haque Labsha, Satkhira | 2017-09-06 | 259.999 | 100% | 2018-09-12 | 259.327 | 259.327 | 0 | 99.74% | Final (Salvage Amount Tk. 9,03,849)
24 | 287433007-287433007-Improvement of Helatola UP-Kazirhat Bazar Road by BC at Ch. 882-2545m | KDRIDP/Sat/W-106/2018-19 | 1.663 | 0 | 0 | 124.766 | 2019-04-23 | [7 empty] | 0 | #DIV/0! | Salvage Amount Tk. 32814.00
| 287433017-Improvement of Brojabaksa Bazar-Kushodanga UP Road by BC at Ch. 1459-2465m. | KDRIDP/Sat/W-106/2018-19 | 1.006 | 0 | 0 | 90.597 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk. 32814.00 Tender receiving date 01.07.19
25 | 287433008-(a) Improvement of Kushadanga UP (Kalibari more)-Kalatupi nutun bazar via Raita bazar road by BC (Ch. 2952-5675m) (b) Construction of 3nos. PVC Pipe Drain Culvert at Ch. 3384m, 3917m & 5300m, (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 3185m & 3871m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 5615m on the Same Road | KDRIDP/Sat/W-02/2016-17 | 2.72 | 0 | 0 | 169.15 | 2017-05-21 | Sk. Sirajul Haque Labsha, Satkhira | 2017-07-02 | 164.55 | 100% | 2018-07-08 | 164.468 | 164.468 | 0 | 99.95% | Final
26 | 287433016-Improvement of Damdam Bazar Halatala UP Brojabakas Jamal more road by BC (Ch. 1839-2652m) with 1no. PVC Pipe Drain Culvert at Ch. 315m and 1no. 625mmX600mm U-Drain at Ch. 1843m on the Same Road | KDRIDP/Sat/W-03/2016-17 | 0.81 | 0 | 0 | 54.64 | 2017-05-22 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-07-02 | 53.55 | 100% | 2018-11-20 | 53.375 | 53.375 | 0 | 99.67% | Final
27 | 287433021-Bamonkhali Bazar-Jugakhali UP rd. | [13 empty] | 0 | #DIV/0!
Shyamnagar
28 | 287863003-Nakipur-Sirajpur hat road. | [13 empty] | 0 | #DIV/0!
29 | 287863004-Improvement of Iswaripur UP-Harinagar hat via Dhumkali Road by BC (Ch. 00-4090m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 210m, 3305m & 3950m on the Same Road | KDRIDP/Sat/W-04/2016-17 | 4.09 | 0 | 0 | 279.02 | 2017-05-25 | M/S Rabeya Traders Dhaka | 2017-06-14 | 273.53 | 65% | 2019-12-31 |  | 126.5 | -126.5 | 46.25% | Salvage Amount Tk. 38,60,858/- 2nd R/A Bill
30 | 287863013-Improvement of Iswaripur UP-Paranpur hat via Ramjannagar Road by BC (Ch. 1900-3475m) | KDRIDP/Sat/W-05/2016-17 | 1.575 | 0 | 0 | 102.54 | 2017-05-22 | M/S Rabeya Traders Dhaka | 2017-06-14 | 95.93 | 10% | 2019-12-31 |  |  | 0 | 0% | Salvage Amount Tk. 13,04,167/-
31 | 287863017-Improvement of Iswaripur UP- Gumantali hat via Golabari Ghat Road by BC at Ch. 2730-4500m. | KDRIDP/Sat/ W-83/2018-19 | 1.77 | 0 | 0 | 162.496 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1671706
32 | 28783012-Noornagar-Kultali Bazar road. | [13 empty] | 0 | #DIV/0!
Kaligonj
33 | 287473002-(a) Improvement of Dudly Bazar (Natun Hat)-Dhalbaria UP via Ratanpur GC Road at Ch 2400-2900m & (b) Construction of 3 nos. u-PVC Pipe Culvert on the Same Road. | KDRIDP/Sat/W-31/2017-18 | 0.5 | 0 | 0 | 33.16 | 2018-01-18 | M/S Sheikh Bricks Kaligonj, Satkira | 2018-03-05 | 33.05 | 100% | 2018-12-30 | 31.655 | 31.655 | 0 | 95.78% | Final
34 | 287473017-Improvement of Dakhinsripur UP Bazar-Gobindokati Bazar via Uttarsripur road at Ch. 2745-4350m | KDRIDP/Sat/W-46/2017-18 | 1.605 | 0 | 0 | 107.169 |  | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 109.26 | 100% | 2019-07-04 | 108.872 | 108.872 | 0 | 99.64% | Final
Total |  |  | 38.06 | 0 | 0 | 2714.137 |  |  |  | 2157.676 | 68.93% |  | 980.805 | 1312.2 | -331.395 | 60.82%
Improvement of Village Road by BC
Satkhira Sadar
1 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | [13 empty] | 0 | #DIV/0!
2 | 287824004-Bansdah UP Office-Kawan danga Rd. | [13 empty] | 0 | #DIV/0!
3 | 287824009-Dhohakula FRB-Dhohakula R&H (Assasuni) road. | [13 empty] | 0 | #DIV/0!
4 | 287824014-Improvement of Dhuliar- Damarpara WAPDA Embt road Ch.0.00-1000m | KDRIDP/Sat/ W-80/2018-19 | 1 | 0 | 0 | 82.37 | 2019-01-23 | M/S Biswas Enterprise, Old Satkhira, Satkhira | 2019-03-31 | 86.489 | 10% | 2020-04-06 |  |  | 0 | 0% | Salvage amount Tk. 1018994.00
| 287825133-Improvement of Brahmmorajpur Bazar to Chalerdangi RHD Assasuni road Brahmmorajpur Bazar to Baradal Pucca road via Dhulihor Chandra Pukur road at ch. 00-866m | KDRIDP/Sat/ W-80/2018-19 | 0.866 | 0 | 0 | 71.026 |  | M/S Biswas Enterprise, Old Satkhira, Satkhira |  | 74.582 |  |  |  |  | 0 | 0% | Salvage amount Tk. 1018994.00
5 | 287824023-Taltala R&H to Kaikhali Mistripara road. | [13 empty] | 0 | #DIV/0!
6 | 287824025-Improvement of Brahmmorajpur Maniktala to Machkhola Hatkhola road by BC at ch 1950-2950m | KDRIDP/Sat/W-101/2018-19 | 1 | 0 | 0 | 79.837 | 2019-04-23 | M/S Raka Enterprise Tala, Satkhira. | 2019-06-19 | 78.24 | 0% | 2020-06-25 |  |  | 0 | 0% | Salvage amount Tk. 255428.00
7 | 287824028-Improvement of Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road by BC at ch.1285-3245m | KDRIDP/Sat/W-102/2018-19 | 1.96 | 0 | 0 | 155.369 | 2019-04-08 | [7 empty] | 0 | #DIV/0! | Salvage amount Tk.1382987.00 Re-tenderer receiving date 01.07.19
8 | 287824061-Improvement of Faizullahpur more (Satkhira-Assasuni R&H) to Fingri UP Office road by BC at ch 00-490m & 2892-3362m. | KDRIDP/Sat/W-104/2018-19 | 0.96 | 0 | 0 | 81.029 | 2019-03-25 |  |  | 76.978 |  |  |  |  | 0 | 0% | Salvage amount Tk.1344528.00
9 | 287825021-Gobindakati Satrano Battola-Reui Bazar Road. | [13 empty] | 0 | #DIV/0!
10 | 287825016-Improvement of Bhabanipur more- Toloigacha BDR Camp road by BC at ch.2470-2993m | KDRIDP/Sat/W-105/2018-19 | 0.523 | 0 | 0 | 40.285 | 2019-03-25 |  |  | 38.271 |  |  |  |  | 0 | 0% | Salvage amount Tk.423046.00
11 | 287825060-Improvement of Babulia FRB-Satkhira City College Road by BC at Ch. 1390-3200m | KDRIDP/Sat/ W-79/2018-19 | 1.81 | 0 | 0 | 136.916 | 2018-10-25 | M/S Raka Enterprise, Tala, Satkhira | 2018-12-06 | 130.07 | 10% | 2019-12-12 |  |  | 0 | 0% | Salvage amount Tk. 868320.00
12 | 287825062-Chandpur-Budhata Road | [13 empty] | 0 | #DIV/0!
13 | 287825187-Improvement of Jardia Sheikh Para.GPS-Jardia SK Para-SK Mizanur Rahman house road by BC at ch 00m-1005m | KDRIDP/Sat/W-100/2018-19 | 1.005 | 0 | 0 | 78.899 | 2019-03-25 | M/S Reba Enterprise Bagerhat. |  | 81.818 |  |  |  |  | 0 | 0% | Salvage amount Tk. 280487.00 NOA issued on 26.06.19
14 | 287825158-Bankal-Bagmari road | [13 empty] | 0 | #DIV/0!
15 | 287825107-Goalpota Hatkhola to Kamardangi Sluice Gate road. | [13 empty] | 0 | #DIV/0!
16 | 287824028-Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road. | [13 empty] | 0 | #DIV/0! | Duplicate
17 | 287824054-Improvement of R&H Puraton Satkhira-Machkhola Road at Ch.1500-2970m | KDRIDP/Sat/W-112/2018-19 | 1.47 | 0 | 0 | 108.823 | 2019-04-23 | [7 empty] | 0 | #DIV/0! | Salvage amount Tk.109805.00 TER sent to HQ
Assasuni
18 | 287044018-Badartala-Mozgurkhali Rd. | [13 empty] | 0 | #DIV/0!
19 | 287044089-Agordhari-Gabtala via Kampura rd. | [13 empty] | 0 | #DIV/0!
20 | 287044094-APS Collage-Gokulnagar Road. | [13 empty] | 0 | #DIV/0!
21 | 287045059-Improvement of Agordari Dhalibari- Hazi bari Graveyard via Agordari High School road at ch.00-1330m. | KDRIDP/Sat/W-96/2018-19 | 1.33 | 0 | 0 | 120.808 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk.145777.00 Re-tender receiving date 18.07.19
22 | 287044119-Improvement of Kachua Girls high School- Agordari High School road at ch.00-1380m. | KDRIDP/Sat/W-97/2018-19 | 1.38 | 0 | 0 | 116.615 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk.727589.00 Re-tender receiving date 18.07.19
23 | 287044156-Improvement of Agordari west para Mosque- Kadakati GC road at ch.00m-1445m. | KDRIDP/Sat/W-98/2018-19 | 1.445 | 0 | 0 | 128.93 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 325005.00 Re-tender receiving date 18.07.19
24 | 287045066-Natana bazar - Hashkhali GPS via Hashkhali culvert road. | [13 empty] | 0 | #DIV/0!
25 | 287044133-Kurikahunia Makbul Dokanderer Bari - Nakna Gazibari road. | [13 empty] | 0 | #DIV/0!
26 | 287044034-Sriula R&H-Sriula Shashibari Bridge via BD Chow house. | [13 empty] | 0 | #DIV/0!
27 | 287044030-Budhata Bazar to Budhata Pr.School road. | [13 empty] | 0 | #DIV/0!
28 | 287045064-Mohishadanga High school-Ganesher Khey ghat via H-O. Kishor Babu. | [13 empty] | 0 | #DIV/0!
29 | 287044051-Mohistpur- Boyershing khal road. | [13 empty] | 0 | #DIV/0!
30 | 287045126-Badar tola Hazi Jallauddin Collage- Mozjurkhali Pr.School road. | [13 empty] | 0 | #DIV/0!
31 | 287045072-Sreeula Molla Bari Mosque road. | [13 empty] | 0 | #DIV/0!
32 | 287044228-Improvement of Godaipur-Rautara road by BC at ch.00-825m | KDRIDP/Sat/W-111/2018-19 | 0.825 | 0 | 0 | 69.94 | 2019-04-23 | M/S Ziaul Traders Khulna. | 2019-06-27 | 69.44 | 0% | 2020-06-27 |  |  | 0 | 0% | Salvage amount Tk. 2332396.00
| 287045092-Improvement of Sreeula Football Field-Sluice Gate via Jela Parishad road by BC at ch.00-500m | KDRIDP/Sat/W-111/2018-19 | 0.5 | 0 | 0 | 39.936 |  | M/S Ziaul Traders Khulna. |  | 39.651 |  |  |  |  | 0 | 0% | Salvage amount Tk. 2332396.00
| 287045057-Improvement of Sreeulia R&H-Sreeulia UP Office road by BC at ch.00-500m | KDRIDP/Sat/W-111/2018-19 | 0.5 | 0 | 0 | 37.986 |  | M/S Ziaul Traders Khulna. |  | 37.715 |  |  |  |  | 0 | 0% | Salvage amount Tk. 2332396.00
Debhata
33 | 287254001-Sekendra R&H-WDB Embankment (Ghariadanga) Rd. | [13 empty] | 0 | #DIV/0!
34 | 287254006-North Parulia R&H-Naziergheer Rd | [13 empty] | 0 | #DIV/0!
35 | 287254021-Konra Pakralala R&H-Kazimoholla Samsuddin M. House Road . | [13 empty] | 0 | #DIV/0!
36 | 287254035-Debhata Parulia UZR-Bhatshala Cyclone Shelter Road. | [13 empty] | 0 | #DIV/0!
37 | 287254037-Sushilgati FRB-Eidgah Sakhipur Road. | [13 empty] | 0 | #DIV/0!
38 | 287254045-Badartola Bazar-Rangashisha Road. | [13 empty] | 0 | #DIV/0!
39 | 287255032-Ratanshapur Babar Ali Shop-Teyor GCCR Road | [13 empty] | 0 | #DIV/0!
40 | 287255175-Improvement of Shakhipur Mosque - Khegurbaria Southpara Mosque road at Ch 00-1135m with 2nos. 625mmX600mm U-Drain at Ch.62m & 560m on the Same Road | KDRIDP/Sat/W-59/2017-18 | 1.135 | 0 | 0 | 92.117 | 2018-04-23 | Md. Shajahan Alam, Kaligonj, Satkhira. | 2018-06-06 | 96.61 | 40% | 2019-06-12 |  | 27.015 | -27.015 | 27.96% | Salvage Amount Tk. 863133.00
| 287255075-Improvement of Shakhipur Nimay house - Lakhimi Kanta house road at Ch 00-1038m with 3nos. 625mmX600mm U-Drain at Ch.450m, 615m & 892m on the Same Road. |  | 1.038 | 0 | 0 | 81.768 |  |  |  | 85.76 |  |  |  | 23.985 | -23.985 | 27.97% | Salvage Amount Tk. 1536290.00
41 | 287254033-Subornabad FRB-Darer khal Ferry ghat Via Shasadanga Madrasha). | [13 empty] | 0 | #DIV/0!
42 | 287254043-Improvement of Shakhipur Bazar - Bhatshala UNR WDB Embankment road at Ch 00-6210m | KDRIDP/Sat/W-58/2017-18 | 6.21 | 0 | 0 | 418.94 | 2018-06-25 | M/S Rafid Traders & M/S Bosu Traders JV, Tala, Satkhira | 2018-09-11 | 443.5 | 25% | 2019-09-17 |  |  | 0 | 0% | Salvage Amount Tk. 1384326.00
43 | 287255045-Chaltatola-Synnasir chack via roingashisha( WDB) Emabankmnet road. | [13 empty] | 0 | #DIV/0!
44 | 287255153-Parulia Sunial Desh House- Jhal Bagen Road | [13 empty] | 0 | #DIV/0!
45 | 2872555130-pubo kulia bridge tosadesh hachari Rd. | [13 empty] | 0 | #DIV/0!
Tala
46 | 287904004-Improvement of Manikhar-Ghorerdanga Road by 25mm BC+7mm SC (Ch. 00-1494m) with 4nos. 625mmX600mm U-Drain at Ch. 120m, 380m, 916m & 1309m on the Same Road. | KDRIDP/Sat/W-34/2017-18 | 1.494 | 0 | 0 | 105.99 | 2018-07-19 | M/S M M Brothers, Khulna. | 2018-09-09 | 109.68 | 60% | 2019-09-15 |  | 35 | -35 | 31.91% | Salvage Amount Tk. 455369.00 1st R/A Bill
47 | 287904011-Baliadha-Bolarumpur Road. | [13 empty] | 0 | #DIV/0!
48 | 287904018-Improvement of Khalishkhali-Dalua road by BC Ch.1000-2700m | KDRIDP/Sat/ W-114/2018-19 | 1.7 | 0 | 0 | 128.53 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk. 756131.00
49 | 287904057-Improvement of Sujansah Bazar R&H-Ghona Road at Ch. 1000-2140m | KDRIDP/Sat/W-70/2017-18 | 1.14 | 0 | 0 | 78.705 | 2018-06-28 | Uttam Traders Tala, Satkhira | 2018-08-14 | 77.83 | 50% | 2019-08-20 |  | 21.228 | -21.228 | 27.28% | Salvage Amount Tk. 44892.00 2nd R/A Bill
| 287905031-Improvement of Magura girls school - joynwddin house Road at Ch. 00m - 995m |  | 0.995 | 0 | 0 | 69.59 |  | Uttam Traders Tala, Satkhira |  | 68.818 |  |  |  | 18.772 | -18.772 |  | Salvage Amount Tk. 413124.00 2nd R/A Bill
50 | 287904064-Improvement of Sujanshoha Bazar Paranpur Israil house road at Ch. 00-1007m | KDRIDP/SAT/W-37/2017-18 | 1.007 | 0 | 0 | 71.786 | 2018-04-23 | M/S Roshni Enterprise, Tala, Satkhira. | 2018-06-06 | 74.765 | 100% | 2019-06-12 | 74.765 | 74.765 | 0 | 100% | Final
51 | 287904073-Improvement of Shalika College-Dalua GC road at Ch. 4500-8210m | KDRIDP/Sat/ W-54/2017-18 | 3.71 | 0 | 0 | 246.85 | 2018-04-19 | M/S Basu Traders Tala, Satkhira | 2018-06-25 | 255.3 | 50% | 2019-05-30 |  |  | 0 | 0% | Salvage Amount Tk. 186115.00
52 | 287905147-Bathuadanga Primary school - Kalagachi Road | [13 empty] | 0 | #DIV/0!
53 | 287904010-Shahpur R&H – Hazrakati Bazar | [13 empty] | 0 | #DIV/0!
54 | 287904039-Barobila(UZR)- Sarulia Bazar via Barobila GPS | [13 empty] | 0 | #DIV/0!
55 | 287904088-Improvement of Bhairabnagar R&H-AKrakhola Bazar via Nagarghata UP Office road by BC Ch.5090-6090m | KDRIDP/Sat/ W-116/2018-19 | 1 | 0 | 0 | 73.134 | [8 empty] | 0 | #DIV/0! | Salvage Amount Tk. 756131.00
56 | 287905134-Boyardanga UZR - Mokolandokati GPS via Pakshia Durgha Mondir Road | [13 empty] | 0 | #DIV/0!
57 | 287905186-Improvement of Daibari More-H/O Intaz Golder via Maspara Mosjid Road by BC (Old ID 287905185) at Ch. 00-850m | KDRIDP/Sat/W-110/2018-19 | 0.85 | 0 | 0 | 74.95 | 2019-04-08 | M/S Emran Trading Tala, Satkhira. | 2019-05-21 | 71.2 | 0% | 2020-05-27 |  |  | 0 | 0% | Salvage Amount Tk. 310228.00
58 | 287905108-Improvement of Majiara (House of Azhar Ali more) Khorerdanga Bazar Road by BC (Ch. 118-2024m) with 1no. 625mmX600mm U-Drain at Ch. 1040m on the Same Road | KDRIDP/Sat/W-06/2016-17 | 1.906 | 0 | 0 | 129.44 | 2017-05-22 | M/S Roshni Enterprise Tala, Satkhira | 2017-06-22 | 126.53 | 100% | 2018-06-28 | 126.47 | 126.47 | 0 | 99.95% | Final (Salvage Amount Tk. 22,97,337.00)
59 | 28790516-Kazidanga H/O-Dr. Aminuddin Gazi-Kharail,Bhabanipur road. | [13 empty] | 0 | #DIV/0!
Kalaroa
60 | 287434006-Improvement of Tin Bot-tala to Satpota bazar Via Nathpur Rd by BC (Ch. 1621-3622m) with 4nos. Pipe Drain Culvert at Ch. 1861m, 2090m, 2206m & 2465m and 1no. 625mmX600mm U-Drain at Ch. 2588m on the Same Road | KDRIDP/Sat/W-01/2016-17 | 2.001 | 0 | 0 | 121.34 | 2017-05-22 | Star Enterprise Munjitpur, Satkhira | 2017-07-02 | 119.46 | 0% | 2019-06-30 |  |  | 0 | 0% | Salvage Amount Tk. 2,24,703/-
61 | 287434028-Improvement of Kesmot Elishpur-Chitla Bottola road at Ch. 2062-3680m | KDRIDP/Sat/ W-49/2017-18 | 1.618 | 0 | 0 | 111.62 | 2018-04-10 | M/S Sardar Bricks Kalaroa, Satkhira | 2018-12-02 | 117.026 | 30% | 2019-12-08 |  |  | 0 | 0%
62 | 287434053-Improvement of Kalaroa-Saraskati R&H at Hamidpur More-Bamonkhali road at Ch. 1540-3115m | KDRIDP/Sat/ W-53/2017-18 | 1.575 | 0 | 0 | 111.359 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 114.69 | 30% | 2019-06-11 |  |  | 0 | 0% | Salvage Amount Tk. 75036.00
63 | 287434059-Improvement of Brojabaksah jamal More - Jhapagat Pukur road by BC at Ch. 1175-2605m | KDRIDP/Sat/W-36/2017-18 | 1.43 | 0 | 0 | 91.18 | 2018-07-26 | Md. Rafiqul Islam Kalaroa, Satkhira | 2018-10-01 | 95.71 | 65% | 2019-10-07 |  | 56 | -56 | 58.51% | 1st R/A Bill
64 | 287434057-(a) Improvement of Boyerdanga FRB - N. Kati Charabattala FRB road at (Ch. 00-1995m) by 25mm BC + 7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 746m and (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 15m & 1083m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 1302m on the Same Road | KDRIDP/Sat/W-18/2016-17 | 1.995 | 0 | 0 | 133.75 | 2017-07-17 | Star Enterprise Munjitpur, Satkhira | 2017-09-06 | 129.609 | 0% | 2019-06-30 |  |  | 0 | 0% | Salvage Amount Tk. 4,24,435/-
65 | 287434061-Improvement of Kazirhat Bazar-Bahura Komorpur road at Ch. 2480-3520m | KDRIDP/Sat/ W-51/2017-18 | 1.04 | 0 | 0 | 73.28 | 2018-04-10 | M/S Sardar Bricks Kalaroa, Satkhira | 2018-12-02 | 76.86 | 40% | 2019-12-08 |  |  | 0 | 0% | Salvage Amount Tk. 52529.00 NOA issued on 03.05.18
66 | 287434068-Improvement of Boalia Fakirpara Bazar-Bhadiali Bazar road at Ch. 499-1972m | KDRIDP/Sat/ W-40/2017-18 | 1.473 | 0 | 0 | 97.27 | 2018-06-25 | M/S Star Enterprise Munjitpur, Satkhira | 2018-10-18 | 101.409 | 65% | 2019-10-20 |  |  | 0 | 0% | Salvage Amount Tk.1012925.00
67 | 287434072-Improvement of Bamonkhali Bazar-Batra Bazar road at Ch. 3980-5250m | KDRIDP/Sat/ W-52/2017-18 | 1.27 | 0 | 0 | 81.245 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 81.2 | 65% | 2019-06-11 |  | 47 | -47 | 57.88% | Salvage Amount Tk. 21921.00 1st R/A Bill
68 | 287434085-Brikrompur FRB-Hojoldi bazar road. | [13 empty] | 0 | #DIV/0!
69 | 287435004-Improvement of Kayla-Morarikati road at Ch. 2593-4080m | KDRIDP/Sat/ W-86/2018-19 | 1.487 | 0 | 0 | 125.668 | 2018-11-26 | M/S Aman Traders Kalaroa, Satkhira | 2019-01-22 | 119.38 | 5% | 2020-01-28 |  |  | 0 | 0% | Salvage amount Tk. 78310.00
70 | 287435018-(a) Improvement of Helatala UP Tile Fectory - Kashpur P/School more road at Ch 1599m - 3114m by 25mm BC+7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 2219m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 1745m, 2076m & 2739m on the Same Road. | KDRIDP/Sat/W-35/2017-18 | 1.515 | 0 | 0 | 100.56 | 2018-04-23 | Md. Rafiqul Islam, Kalaroa, Satkhira. | 2018-06-06 | 95.536 | 65% | 2019-06-12 |  |  | 0 | 0%
71 | 287434093-Improvement of Khordo Batra Regd. Non-Govt. Primary School More to Maniknagar-Ofapur (DPP Name-Ofapur Govt. Primary School to Basantapur) Govt. Primary School Road by BC at Ch. 1978-3187m | KDRIDP/Sat/W-105a/2018-19 | 1.209 | 0 | 0 | 93 | 2019-04-08 | M/S Tasin Enterprise Kalaroa, Satkhira. | 2019-05-21 | 88.35 | 0% | 2020-05-27 |  |  | 0 | 0% | Salvage Amount Tk. 260607.00
72 | 287435085-Improvement of Panchpota - Sonabaria bazar road at (Ch. 2944-3500m) by 25mm BC + 7mm SC | KDRIDP/Sat/W-19/2016-17 | 0.556 | 0 | 0 | 34.29 | 2017-07-17 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-09-06 | 33.606 | 100% | 2018-06-12 | 33.567 | 33.567 | 0 | 99.88% | Final
73 | 287435045-Hulhulia Notun Bazar More-Hulhulia Govt.Primary School road. | [13 empty] | 0 | #DIV/0!
74 | 287434035-Improvement of South Barali A Rahman House - Sonabaria Hazrat House (Ramkesnopur hat khola more-Nurmohammad Gazi H/O) Road by BC at Ch. 442-1365m | KDRIDP/Sat/W-99/2018-19 | 0.923 | 0 | 0 | 80.156 | 2019-03-25 | M/S Shahid Enterprise, Kalaroa, Satkhira. | 2019-05-05 | 76.148 | 0% | 2020-05-11 |  |  | 0 | 0% | Salvage Amount Tk. 261683.00
75 | 287435110-Improvement of Nathpur Khanpukur more - Nathpur Gazipara via Kamarepota road at (Ch. 00-575m) by 25mm BC + 7mm SC (b) Construction of 2nos. 315mm PVC Pipe Drain at Ch. 130m & 375m on the Same Road | KDRIDP/Sat/W-20/2016-17 | 0.575 | 0 | 0 | 35 | 2017-07-17 | G M Enterprise Kalaroa, Satkhira | 2017-09-06 | 36.55 | 100% | 2018-04-30 | 36.548 | 36.548 | 0 | 99.99% | Final
Shyamnagar
76 | 287864007-Improvement of Iswaripur FWC - Beramollah Hat road at (Ch. 00-3000m) & Construction of 7.0m Long 600mmX600mm U-Drain at Ch. 368m on the Same Road | KDRIDP/Sat/W-12/2016-17 | 3 | 0 | 0 | 182.52 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 187.9 | 65% | 2019-02-06 |  | 115.267 | -115.267 | 61.34% | Salvage Amount Tk. 2,62,483/- 3rd R/A Bill Time ext. sent to PD
77 | 287864026-Ramjibonpur More-Horinagari Road | [13 empty] | 0 | #DIV/0!
78 | 287864038-ZR at Sonaremore-Fulbari-Chigrikhali road. | [13 empty] | 0 | #DIV/0!
79 | 287864040 Chandipur R&H-Sankarkati hat-Majhergonj hat road. | [13 empty] | 0 | #DIV/0!
80 | 287864062- Munshigonj Bazar-Garrage hat Bridge. | [13 empty] | 0 | #DIV/0!
81 | 287864077 Jadappur Pucca road-Kallyanpur Sluicegate-Chingrikhali road | [13 empty] | 0 | #DIV/0!
82 | 287864102- Improvement of Biramollah hat Kowsar Gazi bari road at (Ch. 1000-2200m) | KDRIDP/Sat/W-15/2016-17 | 1.2 | 0 | 0 | 73.26 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 75.4 | 100% | 2019-02-06 | 73.158 | 73.158 | 0 | 97.03% | Salvage Amount Tk. 5,06,656 Final
83 | 287864102-Improvement of Khagraghat H/O Fazlul Haque- R & H road by BC.Ch0.00m-1100m | KDRIDP/Sat/W-48/2017-18 | 1.1 | 0 | 0 | 76.22 |  | M/S Asa Construction, Shyamnagar, Satkira | 2018-04-22 | 80.03 | 100% | 2019-06-07 | 79.426 | 79.426 | 0 | 99.25% | Final
84 | 287864119- Badaghata-Anowara khatun Mohila Madrasa via Muktijoddha. | [13 empty] | 0 | #DIV/0!
85 | 287865149- Improvement of Mohendrakata - Badda house road at (Ch. 00-1650m) & Construction of 2nos. 7.0m Long 600mmX600mm U-Drain at Ch. 1100m & 1400m on the Same Road | KDRIDP/Sat/W-13/2016-17 | 1.65 | 0 | 0 | 99.52 | 2017-10-09 | Md. Abdul Hakim Situlpur, Kaligonj | 2017-11-19 | 103.965 | 100% | 2019-03-30 |  | 30.944 | -30.944 | 29.76% | 2nd R/A Bill
86 | 287864110-Improvement of Biramollah hat - Ruhit Majhi - Dakin Srifalkati road at (Ch. 1000-2718m) | KDRIDP/Sat/W-14/2016-17 | 1.718 | 0 | 0 | 104.69 | 2017-07-16 | M/S Asha Construction Ishwaripur, Shyamnagar, Satkhira | 2017-09-20 | 109.897 | 100% | 2018-07-22 | 108.872 | 108.872 | 0 | 99.07% | Salvage Amount Tk. 1,74,989.00 Final
87 | 287864148-Improvement of Padmapukur R&H-Baintala GPS road at Ch. 00-2000m | KDRIDP/Sat/W-42/2017-18. | 2 | 0 | 0 | 85.906 |  | Md. Iqbal Jamader Polashpole, Satkhira | 2018-04-24 | 85.65 | 30% | 2019-07-03 |  |  | 0 | 0%
88 | 28785149-Mohendrokata-Baidda house | [13 empty] | 0 | #DIV/0!
89 | 287864045 - Improvement of Sapkhali - Kaikhali BOP Road by BC at Ch.00m-3000m | KDRIDP/Sat/ W-84/2018-19 | 3 | 0 | 0 | 225.073 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 2271785
90 | 287864031-Improvement of Hawalbhangi-Baduria road at CH. 00-2651m | KDRIDP/Sat/ W-82/2018-19 | 2.615 | 0 | 0 | 211.467 | 2019-04-08 |  |  | 208.929 |  |  |  |  | 0 | 0% | Salvage amount Tk. 1849998
91 | 287864100-Dumuria Bazr-Parsheemari Kheyaghat road. | [13 empty] | 0 | #DIV/0!
92 | 287865048-Improvement of Jada more-Gani Mollik road at (Ch. 00-1500m) | KDRIDP/Sat/W-21/2017-18 | 1.5 | 0 | 0 | 105.17 | 2017-08-31 | Molla Engineering Workshop Shyamnagar, Satkhira | 2017-10-09 | 109.27 | 100% | 2018-11-30 |  | 99.09 | -99.09 | 90.68% | Salvage Amount Tk. 2,04,581/- Final (Part)
93 | Gorkumarpur Bazar to Diglarait Moszid. | [13 empty] | 0 | #DIV/0!
94 | 287864041-Zr. Moutala-Tajhori hat road. | [13 empty] | 0 | #DIV/0!
95 | 287864105-Improvement of Isakur LGED Pacca Road-Jahasghata Shahi Mosque Road by BC at Ch. 00-1050m | KDRIDP/Sat/W-115/2018-19 | 1.05 | 0 | 0 | 83.42 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1437362
96 | 287865036- Improvement of Bongshipur-Azad Gazi road at CH. 00-950m | KDRIDP/Sat/ W-81/2018-19 | 0.95 | 0 | 0 | 86.11 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1341082.00 Tender receiving date 18.07.19
| 287864048-Improvement of Jotindanagar hat-Manikhali R&H road at Ch. 9180-11180m |  | 2 | 0 | 0 | 167.37 | [8 empty] | 0 | #DIV/0!
Kaligonj
97 | 287474028-Kushlia G.C.C.-Uttar Sreepur WAPDA Emb.via Chanditala Road. | [13 empty] | 0 | #DIV/0!
98 | 287474053-Improvement of Kaligonj Upazila-Nazimgonj Bazar-Bosontopur BOP via Kaligonj BOP Road by BC at Ch. 1650-4000m | KDRIDP/Sat/W-107/2018-19 | 2.35 | 0 | 0 | 165.515 | [8 empty] | 0 | #DIV/0!
99 | 287475001-Gorapota R&H - Maniltala Rd. | [13 empty] | 0 | #DIV/0!
100 | 287475003-(a) Improvement of Nalta RHD Girls School - Nalta College Road at Ch 00-2100m, (b) Construction of 2 nos. u-PVC Pipe Culvert & (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1230m & 1855m on the Same Road. | KDRIDP/Sat/W-32/2017-18 | 2.1 | 0 | 0 | 125.89 | 2018-04-23 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 132.1 | 70% | 2019-05-23 |  | 82 | -82 | 62.07% | 2nd R/A Bill
101 | 287475017-Bhathudanga - Goalkhali Road. | [13 empty] | 0 | #DIV/0!
102 | 287475027-(a) Improvement of Parulgacha pry. School - Radhapada Mondol House (Nengi beel) Road at Ch 00-1080m & (b) Construction of 1nos. 625mmX600mm U-Drain at Ch. 707m on the Same Road | KDRIDP/Sat/W-33/2017-18 | 1.08 | 0 | 0 | 75.907 | 2018-04-23 | Sk. Shahinur Rahman, Kaligonj, Satkhira | 2018-05-29 | 79.28 | 60% | 2019-08-16 |  | 26.163 | -26.163 | 33% | 1st R/A Bill
103 | 287475386-Improvement of Pania Rashid Choukidar H/O-Jerongacha hat-Makhun Shop Road by BC at Ch. 00-2040m | KDRIDP/Sat/W-90/2018-19 | 2.04 | 0 | 0 | 154.14 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 2900856
104 | 287475071-Moutala Deputy Sb.H.-Kamarpara | [13 empty] | 0 | #DIV/0!
105 | 287475074-Moutala Old Bazar-Jhorukhamar | [13 empty] | 0 | #DIV/0!
106 | 287475118-Improvement of Gobindrakati-Uttar Sreepur road at Ch. 00-1550m | KDRIDP/Sat/W-45/2017-18 | 1.55 | 0 | 0 | 101.059 |  | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 106 | 65% | 2019-07-04 |  | 20 | -20 | 18.87% | 1st R/A Bill
107 | 287475246 fatapur to nilkanthapurl road. | [13 empty] | 0 | #DIV/0!
108 | 287475409-Uttar Srepur Malipara Eidgah-Dakkin Srepur Bazar via Latif Member House road. | [13 empty] | 0 | #DIV/0!
109 | 287475065-Improvement of Moutala GPS-Liakot Ali House Road by BC at Ch.00-2315m | KDRIDP/Sat/W-89/2018-19 | 2.315 | 0 | 0 | 174.05 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1912646
110 | 287474033-Moutala ZR.-ParamanDakati | [13 empty] | 0 | #DIV/0!
111 | 287475210-Improvement of Pania GPS-M. Gobindapur Emam Chowkidar H/O Via Mirpara Mosque Road by BC at Ch.00-1730m | KDRIDP/Sat/W-87/2018-19 | 1.73 | 0 | 0 | 133.937 | 2019-01-16 | M/S M M Enterprise, Kaligonj, Satkhira | 2019-03-28 | 140.567 | 20% | 2020-04-03 |  |  | 0 | 0% | Salvage amount Tk. 1210849.00
112 | 287475378-Improvement of Pania Akkas Shikari H/O-West Moutala Khanpara GPS Road by BC at Ch 00-1420m | KDRIDP/Sat/W-88/2018-19 | 1.42 | 0 | 0 | 109.24 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1663067
113 | 287475057-Improvement of Kaligonj (R&H)-Khazabaria Bridge-Ujzymari road at Ch. 00-1170m | KDRIDP/Sat/W-41/2017-18 | 1.17 | 0 | 0 | 96.49 |  | Molla Engineering Workshop Shyamnagar, Satkhira | 2018-04-15 | 99.337 | 45% | 2019-07-03 |  | 67 | -67 | 67.45% | Salvage Amount Tk. 440937.00 3rd R/A Bill
114 | 287475326-Improvement of Charjumina Khaldhar-Notun hat via Powkhali Perojpur Shoshanghat road at Ch. 00-2500m | KDRIDP/Sat/W-47/2017-18 | 2.5 | 0 | 0 | 164.547 |  | Motiur Rahman, Kaligonj, Satkhira | 2018-04-30 | 156.32 | 100% | 2019-03-07 | 151.456 | 151.456 | 0 | 96.89% | Final
115 | 287475364-Laxinathpur Jahid Kazi H/O-Moral para via Laxinathpur bholar H/O. | [13 empty] | 0 | #DIV/0!
116 | 287475387-Norohore kathi Sattar Dr. More via Motola Govt.Pr.School via Boldy para road. | [13 empty] | 0 | #DIV/0!
117 | 287475016 Wapda office to Satpur bridge road. | [13 empty] | 0 | #DIV/0!
118 | 287475115-Chatta pokur(WAPDA Khayghat)via Khartola bazarto via abdul mannan house to iman ali house road. | [13 empty] | 0 | #DIV/0!
119 | 287474003-Thakra shoner bangla Clube-Kolijoga Moktizoda Abdus Sadak H/O. rod. | [13 empty] | 0 | #DIV/0!
120 | 287475022-Improvement of Thakra Chowmoni-Tollakati School via Kulia Dargapur Road by BC at Ch.00-1850m. | KDRIDP/Sat/W-91/2018-19 | 1.85 | 0 | 0 | 143.65 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 3712368
121 | 287475317-Improvement of Sreekola Mohila Madrasha Gate-Sreekhola High School Road by BC at Ch.00-1030m | KDRIDP/Sat/W-92/2018-19 | 1.03 | 0 | 0 | 81.88 | 2019-04-23 | Md. Tahirul Huda Kaligonj, Satkhira. | 2019-06-11 | 84.336 | 0% | 2020-06-27 |  |  | 0 | 0% | Salvage amount Tk. 701389.00
122 | 287475037-Improvement of Pania School (Ramjan's House)-Abdul Moazzem's House via Janakalyan Samiti (Ramjan House-Shamsuddin Mistry House) Road at Ch. 00-800m | KDRIDP/Sat/W-93/2018-19 | 0.8 | 0 | 0 | 64.11 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1926775
123 | 287475384-Bashtola Graveyard - Barkhali Dr. Poretosh pokur via Baruni mondir road. | [13 empty] | 0 | #DIV/0!
124 | 287475393-Improvement of Hogla Ansar Sana Shop-Nenggi Secondary School Road by BC at Ch. 00-1500m | KDRIDP/Sat/W-109/2018-19 | 1.5 | 0 | 0 | 146.62 | [8 empty] | 0 | #DIV/0! | Salvage amount Tk. 1437362
| 287475058-Improvement of Dudly Village-Ex. Chairman H/O Road by BC at Ch. 00-690m | KDRIDP/Sat/W-109/2018-19 | 0.69 | 0 | 0 | 54.577 | [8 empty] | 0 | #DIV/0!
125 | 287475143-Bastola Bazar via Uzipur bazar via Chandulia Thalna road. | [13 empty] | 0 | #DIV/0!
126 | 287474009-Uksha Likat More-Osman Sk. House. | [13 empty] | 0 | #DIV/0!
127 | 287475365-Namazgar shamsul karighor H/O- Namazgar Govt. Pr.Scool, | [13 empty] | 0 | #DIV/0!
128 | 287475253-Bondokati H/Q Raish Miostry-Nilkonthapur Halima Member road. | [13 empty] | 0 | #DIV/0!
129 | 28475123-Romsh Kormokar H.(Komarpur)-Raridpur Mohammad Ali H/O | [13 empty] | 0 | #DIV/0!
130 | 287475212-Batuadanga Moksed Shop UZR-Katakhali Gulli Bill Road | [13 empty] | 0 | #DIV/0!
Total |  |  | 103.334 | 0 | 0 | 7502.625 |  |  |  | 5167.762 | 49.13% |  | 684.262 | 1353.726 | -669.464 | 26.2%
Improvement of Village Road by HBB
Satkhira Sadar
1 | 287824005-Matiadanga Khaya ghat-Khariadanga Road. | [13 empty] | 0 | #DIV/0!
2 | 287824008-Ghona-Vharukhali Sluice gate Road. | [13 empty] | 0 | #DIV/0!
3 | 287824011-Ghona BOP-Gazipur Golam Ali House Road. | [13 empty] | 0 | #DIV/0!
4 | 287824003-Dhulihar puraton Bazar Khola more to Damarpota via Kazir house & Bardal Village road | [13 empty] | 0 | #DIV/0!
5 | 287824007-Vatpara-Gharchala P/School Road | [13 empty] | 0 | #DIV/0!
6 | 287824010-Chandpur bazar-Kulpota WAPDA Embt. Road | [13 empty] | 0 | #DIV/0!
7 | 287824016-Kumorpur R&H-Kumorpur WDB EMB Road. | [13 empty] | 0 | #DIV/0!
8 | 287825041-Nehalpur WDB Emb. to Jugipota (Sukdebpur) Road. | [13 empty] | 0 | #DIV/0!
Assasuni
9 | 287044032-Naktara FRB to Baliakhali WAPDA via Radharati Rd. | [13 empty] | 0 | #DIV/0!
10 | 287044179-Tuardanga Culvert - Bamondanga bridge via Tuardanga Paschimpara Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Debhata
11 | 287254013-Gazirhat- Kalabaria via Borohula Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Upazila Road (7.30m width)
Kaligonj
1 | 287472011-Const. of RCC Bridge on Nazimging GC-Pawkhali RHD Road over Jamuna Khal | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Kaligonj
1 | 287473001- Construction of 20m Long RCC Girder Bridge on Mothoreshpur UP-Powkhali RHD road over Jamuna Khal at ch. 950m | KDRIDP/Sat/B-02/2018-19 | 0 | 20 | 0 | 128.029 | 2018-09-20 | Md. Moyenuddin (Bashi)-M/S Sattar Enterprise (JV), Tejgaon, Dahaka. | 2018-11-12 | 127.999 | 25% | 2019-11-18 |  |  | 0 | 0%
Assasuni
2 | 287043012-Construction of 32.0m Long PSC Girder Bridge on Sovnali UP-Nashukhali Bazar via Paschim Kamalkati Radha Shyamsundar Mondir Road at Ch. 5300m | KDRIDP/Sat/B-01/2018-19 | 0 | 32 | 0 | 230.94 | 2018-09-13 | Md. Moyenuddin (Bashi)-M/S Sattar Enterprise (JV), Tejgaon, Dahaka. | 2018-11-12 | 229.84 | 35% | 2019-11-18 |  | 64 | -64 | 27.85% | Pile casting on going. 1st R/A Bill
3 | 287044188-Construction of Bridge on Gazir hat-Chumuria road over Morischap khal. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Tala
4 | 247904059-Dakin Sahajadpur Launch ghat-Kathipara bazar | [13 empty] | 0 | #DIV/0!
5 | 287864101-Construction of 20m Long RCC Girder Bridge on Biramolla Hat-Kawser Gazi Bari Road at Ch. 350.00m | KDRIDP/Sat/B-03/2018-19 | 0 | 20 | 0 | 130.634 |  | M/S Jakaullah & Brothers, Chuadanga. | 2019-04-17 | 120.6 | 0% | 2020-04-23 |  |  | 0 | 0%
Total |  |  | 0 | 72 | 0 | 489.603 |  |  |  | 478.439 | 15% |  | 0 | 64 | -64 | 13.38%
Maintenance
Satkhira Sadar
1 | 287822010-Periodic Maintenance of Rasulpur R&H-Baikari UP via Pairadanga-Aruakhali via Mirgidanga road at Ch. 00-4200m | KDRIDP/Sat/ M-01/2017-18 | 4.2 | 0 | 0 | 105.51 | 2018-05-17 | Md. Ashraful Kabir Khokun, Katia, Satkhira | 2018-06-25 | 110.785 | 100% | 2019-03-30 | 110.785 | 110.785 | 0 | 100% | Final
2 | 287823010-Mahamudpur Bazar -Abaderhat via Jaghanathpur Road. | [13 empty] | 0 | #DIV/0!
3 | 287823024-Periodic Maintenance of Kulia Sreerampur Chubaria-Bhamra road at Ch. 00-1000m | KDRIDP/Sat/M-03/2017-18 | 1 | 0 | 0 | 20.34 | 2018-05-17 | S.M. Shawkat Hossain, Katia, Satkhira | 2018-06-25 | 21.35 | 100% | 2019-02-28 | 21.348 | 21.348 | 0 | 99.99% | Final
4 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | [13 empty] | 0 | #DIV/0!
5 | 287824004-Bansdah UP Office-Kawandanga Road | [13 empty] | 0 | #DIV/0!
6 | 287824006-Binerpota bridge-Rajnagore Road. | [13 empty] | 0 | #DIV/0!
7 | 287824012-Puraton Satkhira R&H hat-Gobindopur Bazar Road via jiala | [13 empty] | 0 | #DIV/0!
8 | 287824032-Periodic Maintenance of Shaighoria R&H-Akhrakhola Bazar via Satianatala & Battala More road at Ch. 00-2752m | KDRIDP/Sat/ M-02/2017-18 | 2.752 | 0 | 0 | 57.8 | 2018-05-17 | Santa Mahmud, Kamalnagor, Satkhira | 2018-06-25 | 60.11 | 100% | 2019-04-01 | 60.097 | 60.097 | 0 | 99.98%
9 | 287824032-Shaighoria R&H-Akhrakhola Bazar via Satiantala & Battala more road. | [13 empty] | 0 | #DIV/0!
10 | 287824042-Shaighoria R&H-Babulia Bazar Road | [13 empty] | 0 | #DIV/0!
11 | 287824050-Madabkati-Satani Bazar road | [13 empty] | 0 | #DIV/0!
12 | 287825145-Alipur Jangalar Bridge - Nathuar Danga Road via Kulpura Rd | [13 empty] | 0 | #DIV/0!
Assasuni
13 | 287042001-Periodic Maintenance of Assasuni GC-Manikkhali Ferry Ghat Road at Ch. 00-155m & 1178-2260m | KDRIDP/Sat/ M-07/2018-19 | 1.237 | 0 | 0 | 30.904 | 2018-11-26 | Md. Abdus Salam Gazi, Assasuni, Satkhira | 2019-01-22 | 29.36 | 100% | 2019-07-28 | 29.356 | 29.356 | 0 | 99.99% | Final
14 | 287042010-Chiledanga RHD -Bangdah GC Road via Paithali Bazar Rd. | [13 empty] | 0 | #DIV/0!
15 | 287043002-Khazra UP- Bordol GC Rd. | [13 empty] | 0 | #DIV/0!
16 | 287043008-Dargapur UP Office -Tentulia Bazar Rd. | [13 empty] | 0 | #DIV/0!
17 | 287044088-Gunaharkati Bazar-Mohajanpur Rd. | [13 empty] | 0 | #DIV/0!
18 | 287044089-Periodic Maintenance of Agordhari-Gabtola via Humkura road at ch. 00-1430m | KDRIDP/Sat/ M-08/2018-19 | 1.43 | 0 | 0 | 37.828 | 2018-11-26 | M/S Saleha Enterprise, Debhata, Satkhira | 2018-12-27 | 35.937 | 100% | 2019-07-02 | 35.937 | 35.937 | 0 | 100% | Final
Debhata
19 | 287252008-Periodic Maintenance of Bohera Bazar RHD-Ellarchor Bazar-Bangdah GC road at Ch. 00-1735m | KDRIDP/Sat/ M-04/2017-18 | 1.735 | 0 | 0 | 47.5 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 49.39 | 100% | 2019-06-20 |  |  | 0 | 0%
20 | 287254025-Periodic Maintenance of Hadipur R&H-Hadipur Masrasha via Ashkarpur Alimiya Kallyan Sangoshta road at Ch. 1145-2296m | KDRIDP/Sat/M-05/2017-18 | 1.151 | 0 | 0 | 15.6 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 16.22 | 100% | 2018-11-23 | 16.215 | 16.215 | 0 | 99.97% | Final
21 | 287254038-Periodic Maintenance of Parulia R&H-Debhata Parulia GCR via Sakhipur Dhopadanga road at Ch. 00-1045m | KDRIDP/Sat/ M-06/2017-18 | 1.045 | 0 | 0 | 20.519 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 21.33 | 100% | 2018-12-08 | 21.218 | 21.218 | 0 | 99.47% | Final
22 | 287255070-Nowapara Nawser house-Bibuti`s house Road. | [13 empty] | 0 | #DIV/0!
Tala
23 | 287902005-Periodic Maintenance of Tala GC-Kopilmoni GC via Jatua GC Road at Ch. 7550-9543m | KDRIDP/Sat/ M-09/2018-19 | 1.993 | 0 | 0 | 39.904 | 2019-01-30 | M/S Avanova Enterprise, Basabati, Bagerhat. | 2019-03-19 | 37.908 | 100% | 2019-09-25 | 37.908 | 37.908 | 0 | 100% | Final
24 | 287904048-Kanchanpur Eidgah (R & H)-Hizaldanga Bazar Road. | [13 empty] | 0 | #DIV/0!
25 | 287904115-Periodic Maintenance of Kumira R&H-Magura Bazar Road at Ch. 3460-5300m | KDRIDP/Sat/ M-10/2018-19 | 1.84 | 0 | 0 | 45.8 | 2019-01-30 | Md Rafiqul Islam, Kalaroa, Satkhira. | 2019-03-25 | 43.511 | 60% | 2019-12-30 |  | 19.73 | -19.73 | 45.34% | 1st R/A
| 287904088-Periodic Maintenance of Bhairabnagor R&H-Akrakhola Bazar via Nagorghata UP Road at Ch. 2500-4900m | KDRIDP/Sat/ M-10/2018-19 | 2.4 | 0 | 0 | 40.08 |  | Md Rafiqul Islam, Kalaroa, Satkhira. |  | 38.076 |  |  |  | 17.27 | -17.27 | 45.36%
26 | 287905096-Islamkati Primary School - Vagba House of Abdul Malek Mohalder Road. | [8 empty] | 81.587 |  |  |  |  | 0 | 0%
Kalaroa
27 | 287432003-Baguri Beltala -Chandanpur GC Rd. | [13 empty] | 0 | #DIV/0!
28 | 287432006-Kalaroa- Tala via Dhandia Bazar Rd. | [13 empty] | 0 | #DIV/0!
Shyamnagar
29 | 287862002-Nowabenki GC-Khanpur R&H via Vetkhali GC Rd. | [13 empty] | 0 | #DIV/0!
30 | 287863007-Burigoalini UP-Nildumur hat Masud more via Durgabati Road. | [13 empty] | 0 | #DIV/0!
31 | 287863009-Nakipur GC-Chandipur hat Rd | [13 empty] | 0 | #DIV/0!
32 | 287864074-Soalia Mosque-Kallanpur Sluice gate Road. | [13 empty] | 0 | #DIV/0!
33 | 287864077-Jadabpur Pacca road-Kallanpur Sluice gate Road. | [13 empty] | 0 | #DIV/0!
34 | 287864146-Nurnagar-Ramchandrapur-Habibpur Road | [13 empty] | 0 | #DIV/0!
35 | 287863002 Kasimari UP-Jhapali hat Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
36 | 287864041 ZR at Moutala-Teghori hat Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 20.783 | 0 | 0 | 461.785 |  |  |  | 545.564 | 87.27% |  | 332.864 | 369.864 | -37 | 67.79%
GC-Hat
Assasuni
1 | Construction of East Nakna Bazar Chairman Bazar GC | KDRIDP/Sat/ GC-09/2017-18 | 0 | 0 | 1 | 20.59 | 2018-04-10 | Md. Abul Hossain Kamalnagar, Satkhira | 2018-05-06 | 20.264 | 100% | 2018-11-12 | 20.264 | 20.264 | 0 | 100% | Final
Kaligonj
2 | Construction of Bhodrakhali Bazar GC | KDRIDP/Sat/ GC-10/2017-18 | 0 | 0 | 1 | 20.32 | 2018-02-28 | Md. Rafiqul Islam Kaligonj, Satkhira | 2018-04-03 | 20.2 | 100% | 2018-11-15 | 20.074 | 20.074 | 0 | 99.38% | Final
Total |  |  | 0 | 0 | 2 | 40.91 |  |  |  | 40.464 | 100% |  | 40.338 | 40.338 | 0 | 99.69%
Landing/ Riverghat
Shyamnagar
1 | Garkunerpur bazar ghat | [13 empty] | 0 | #DIV/0!
Assasuni
2 | Boundhir Khyaghat | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Kaligonj
3 | Construction of Kalikapur ghat | KDRIDP/Khul/G-15/2017-18 | 0 | 0 | 1 | 30.69 | [8 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 1 | 30.69 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Tree Plantation
Satkhira Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Assasuni
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Debhata
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kaligonj
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Tala
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kalaroa
6 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Shyamnagar
7 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 187.277 | 72 | 3 | 13482.585 |  |  |  | 9991.419 | 39.47% |  | 2292.951 | 3823.212 | -1530.261 | 38.26%
|  |  | 187.277 | 72 | 3 | 13482.585 |  |  |  | 9991.419 | 21.03% |  | 2292.951 | 3823.212 | -1530.261 | 38.26%

## Kaligonj
Kaligonj
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287472004-Khanpur-Baliadanga GC-Uzirpur GC via Gobindokatihat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 287472005-Improvement of Raipur RHD - Noornagar GC Via Sirajpur Hat Road at Ch 600-3385m | KDRIDP/Sat/W-29/2017-18 | 2.79 | 0 | 0 | 265.359 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 4462226.00
3 | 287472006-Improvement of Dudly RHD - Ratanpur GC Road at Ch 00-4200m, | KDRIDP/Sat/W-28/2017-18 | 4.08 | 0 | 0 | 388.96 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 8575180.00
4 | 287472010-Approach of Bashtola bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
5 | 287473002-(a) Improvement of Dudly Bazar (Natun Hat)-Dhalbaria UP via Ratanpur GC Road at Ch 2400-2900m & (b) Construction of 3 nos. u-PVC Pipe Culvert on the Same Road. | KDRIDP/Sat/W-31/2017-18 | 0.5 | 0 | 0 | 33.16 | 2018-01-18 | M/S Sheikh Bricks Kaligonj, Satkira | 2018-03-05 | 33.05 | 100% | 2018-12-30 | 31.655 | 31.655 | 0 | 95.78% | Final
6 | 287473017-Improvement of Dakhinsripur UP Bazar-Gobindokati Bazar via Uttarsripur road at Ch. 2745-4350m | KDRIDP/Sat/W-46/2017-18 | 1.605 | 0 | 0 | 107.169 | 0 | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 109.26 | 100% | 2019-07-04 | 108.872 | 108.872 | 0 | 99.64% | Final
Improvement of Village Road by BC
7 | 287474028-Kushlia G.C.C.-Uttar Sreepur WAPDA Emb.via Chanditala Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 287474053-Improvement of Kaligonj Upazila-Nazimgonj Bazar-Bosontopur BOP via Kaligonj BOP Road by BC at Ch. 1650-4000m | KDRIDP/Sat/W-107/2018-19 | 2.35 | 0 | 0 | 165.515 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 287475001-Gorapota R&H - Maniltala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287475003-(a) Improvement of Nalta RHD Girls School - Nalta College Road at Ch 00-2100m, (b) Construction of 2 nos. u-PVC Pipe Culvert & (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 1230m & 1855m on the Same Road. | KDRIDP/Sat/W-32/2017-18 | 2.1 | 0 | 0 | 125.89 | 2018-04-23 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 132.1 | 70% | 2019-05-23 | 0 | 82 | -82 | 62.07% | 2nd R/A Bill
11 | 287475017-Bhathudanga - Goalkhali Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287475027-(a) Improvement of Parulgacha pry. School - Radhapada Mondol House (Nengi beel) Road at Ch 00-1080m & (b) Construction of 1nos. 625mmX600mm U-Drain at Ch. 707m on the Same Road | KDRIDP/Sat/W-33/2017-18 | 1.08 | 0 | 0 | 75.907 | 2018-04-23 | Sk. Shahinur Rahman, Kaligonj, Satkhira | 2018-05-29 | 79.28 | 60% | 2019-08-16 | 0 | 26.163 | -26.163 | 33% | 1st R/A Bill
13 | 287475386-Improvement of Pania Rashid Choukidar H/O-Jerongacha hat-Makhun Shop Road by BC at Ch. 00-2040m |  | 2.04 | 0 | 0 | 154.14 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 2900856
14 | 287475071-Moutala Deputy Sb.H.-Kamarpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 287475074-Moutala Old Bazar-Jhorukhamar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 287475118-Improvement of Gobindrakati-Uttar Sreepur road at Ch. 00-1550m | KDRIDP/Sat/W-45/2017-18 | 1.55 | 0 | 0 | 101.059 | 0 | Sk. Bricks Kaligonj, Satkhira | 2018-04-15 | 106 | 65% | 2019-07-04 | 0 | 20 | -20 | 18.87% | 1st R/A Bill
17 | 287475246 fatapur to nilkanthapurl road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287475409-Uttar Srepur Malipara Eidgah-Dakkin Srepur Bazar via Latif Member House road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287475065-Improvement of Moutala GPS-Liakot Ali House Road by BC at Ch.00-2315m | KDRIDP/Sat/W-89/2018-19 | 2.315 | 0 | 0 | 174.05 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 1912646
20 | 287474033-Moutala ZR.-ParamanDakati | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287475210-Improvement of Pania GPS-M. Gobindapur Emam Chowkidar H/O Via Mirpara Mosque Road by BC at Ch.00-1730m | KDRIDP/Sat/W-87/2018-19 | 1.73 | 0 | 0 | 133.937 | 2019-01-16 | M/S M M Enterprise, Kaligonj, Satkhira | 2019-03-28 | 140.567 | 20% | 2020-04-03 | 0 | 0 | 0 | 0% | Salvage amount Tk. 1210849.00
22 | 287475378-Improvement of Pania Akkas Shikari H/O-West Moutala Khanpara GPS Road by BC at Ch 00-1420m | KDRIDP/Sat/W-88/2018-19 | 1.42 | 0 | 0 | 109.24 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
23 | 287475057-Improvement of Kaligonj (R&H)-Khazabaria Bridge-Ujzymari road at Ch. 00-1170m | KDRIDP/Sat/W-41/2017-18 | 1.17 | 0 | 0 | 96.49 | 0 | Molla Engineering Workshop Shyamnagar, Satkhira | 2018-04-15 | 99.337 | 45% | 2019-07-03 | 0 | 67 | -67 | 67.45% | Salvage Amount Tk. 440937.00 3rd R/A Bill
24 | 287475326-Improvement of Charjumina Khaldhar-Notun hat via Powkhali Perojpur Shoshanghat road at Ch. 00-2500m | KDRIDP/Sat/W-47/2017-18 | 2.5 | 0 | 0 | 164.547 | 0 | Motiur Rahman, Kaligonj, Satkhira | 2018-04-30 | 156.32 | 100% | 2019-03-07 | 151.456 | 151.456 | 0 | 96.89% | Final
25 | 287475364-Laxinathpur Jahid Kazi H/O-Moral para via Laxinathpur bholar H/O. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287475387-Norohore kathi Sattar Dr. More via Motola Govt.Pr.School via Boldy para road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287475016 Wapda office to Satpur bridge road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 287475115-Chatta pokur(WAPDA Khayghat)via Khartola bazarto via abdul mannan house to iman ali house road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287474003-Thakra shoner bangla Clube-Kolijoga Moktizoda Abdus Sadak H/O. rod. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287475022-Improvement of Thakra Chowmoni-Tollakati School via Kulia Dargapur Road by BC at Ch.00-1850m. | KDRIDP/Sat/W-91/2018-19 | 1.85 | 0 | 0 | 143.65 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 3712368
31 | 287475317-Improvement of Sreekola Mohila Madrasha Gate-Sreekhola High School Road by BC at Ch.00-1030m | KDRIDP/Sat/W-92/2018-19 | 1.03 | 0 | 0 | 81.88 |  |  |  | 84.336 |  |  | 0 | 0 | 0 | 0% | Salvage amount Tk. 701389.00
32 | 287475037-Improvement of Pania School (Ramjan's House)-Abdul Moazzem's House via Janakalyan Samiti (Ramjan House-Shamsuddin Mistry House) Road at Ch. 00-800m | KDRIDP/Sat/W-93/2018-19 | 0.8 | 0 | 0 | 64.11 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 1926775
33 | 287475384-Bashtola Graveyard - Barkhali Dr. Poretosh pokur via Baruni mondir road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 287475393-Improvement of Hogla Ansar Sana Shop-Nenggi Secondary School Road by BC at Ch. 00-1500m | KDRIDP/Sat/W-109/2018-19 | 1.5 | 0 | 0 | 146.62 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 1437362
| 287475058-Improvement of Dudly Village-Ex. Chairman H/O Road by BC at Ch. 00-690m |  | 0.69 | 0 | 0 | 54.577 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
35 | 287475143-Bastola Bazar via Uzipur bazar via Chandulia Thalna road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 287474009-Uksha Likat More-Osman Sk. House. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 287475365-Namazgar shamsul karighor H/O- Namazgar Govt. Pr.Scool, | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 287475253-Bondokati H/Q Raish Miostry-Nilkonthapur Halima Member road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 28475123-Romsh Kormokar H.(Komarpur)-Raridpur Mohammad Ali H/O | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 287475212-Batuadanga Moksed Shop UZR-Katakhali Gulli Bill Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
41 | 287472011-Const. of RCC Bridge on Nazimging GC-Pawkhali RHD Road over Jamuna Khal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
42 | 287473001- Construction of 20m Long RCC Girder Bridge on Mothoreshpur UP-Powkhali RHD road over Jamuna Khal at ch. 950m | KDRIDP/Sat/B-02/2018-19 | 0 | 20 | 0 | 128.029 | 2018-09-20 | Md. Moyenuddin (Bashi)-M/S Sattar Enterprise (JV), Tejgaon, Dahaka. | 2018-11-12 | 127.999 | 25% | 2019-11-18 | 0 | 0 | 0 | 0% | 0
GC-Hat
43 | Construction of Bhodrakhali Bazar GC | KDRIDP/Sat/ GC-10/2017-18 | 0 | 0 | 1 | 20.32 | 2018-02-28 | Md. Rafiqul Islam Kaligonj, Satkhira | 2018-04-03 | 20.2 | 100% | 2018-11-15 | 20.074 | 20.074 | 0 | 99.38% | Final
Landing/ Riverghat
44 | Construction of Kalikapur ghat | KDRIDP/Khul/G-15/2017-18 | 0 | 0 | 1 | 30.69 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
45 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 33.1 | 20 | 2 | 2765.299 |  |  |  | 1088.449 | 16.71% |  | 312.057 | 507.22 | -195.163 | 46.6%

## Kalaroa
Kalaroa
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287432005-Kalaroa GC-Gaira GC via Chandanpur UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
2 | 287433002-(a) Improvement of Jalalabad UP Koila more - Batra bazar road at (Ch. 5050-6920m) by 25mm BC + 7mm SC (b) Construction of 3nos. 315mm PVC Pipe Drain at Ch. 5290m, 6770m & 6828m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 6190m, 6296m & 6504m on the Same Road. | KDRIDP/Sat/W-17/2016-17 | 1.87 | 0 | 0 | 117.52 | 2017-07-17 | M/S Sarder Bricks Kalaroa, Satkhira | 2017-09-06 | 111.406 | 100% | 2018-09-21 | 0 | 88 | -88 | 78.99% | 0
3 | 287433005-Chandanpur UO-Sultanpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 287433006-(a) Improvement of Chandanpur UP - Hejaldi bazar via Sultanpur bazar road at (Ch. 3600-7270m) by 25mm BC + 7mm SC (b) Construction of 8nos. 315mm PVC Pipe Drain at Ch. 4282m, 4560m, 5014m, 5172m, 5229m, 5278m, 5784m & 6116m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 4828m, 6337m & 6518m on the Same Road. | KDRIDP/Sat/W-16/2016-17 | 3.67 | 0 | 0 | 262.63 | 2017-07-17 | Sk. Sirajul Haque Labsha, Satkhira | 2017-09-06 | 259.999 | 100% | 2018-09-12 | 259.327 | 259.327 | 0 | 99.74% | Final (Salvage Amount Tk. 9,03,849)
5 | 287433007-287433007-Improvement of Helatola UP-Kazirhat Bazar Road by BC at Ch. 882-2545m | KDRIDP/Sat/W-106/2018-19 | 1.663 | 0 | 0 | 124.766 | 2019-04-23 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 32814.00
| 287433017-Improvement of Brojabaksa Bazar-Kushodanga UP Road by BC at Ch. 1459-2465m. |  | 1.006 | 0 | 0 | 90.597 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
6 | 287433008-(a) Improvement of Kushadanga UP (Kalibari more)-Kalatupi nutun bazar via Raita bazar road by BC (Ch. 2952-5675m) (b) Construction of 3nos. PVC Pipe Drain Culvert at Ch. 3384m, 3917m & 5300m, (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 3185m & 3871m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 5615m on the Same Road | KDRIDP/Sat/W-02/2016-17 | 2.72 | 0 | 0 | 169.15 | 2017-05-21 | Sk. Sirajul Haque Labsha, Satkhira | 2017-07-02 | 164.55 | 100% | 2018-07-08 | 164.468 | 164.468 | 0 | 99.95% | Final
7 | 287433016-Improvement of Damdam Bazar Halatala UP Brojabakas Jamal more road by BC (Ch. 1839-2652m) with 1no. PVC Pipe Drain Culvert at Ch. 315m and 1no. 625mmX600mm U-Drain at Ch. 1843m on the Same Road | KDRIDP/Sat/W-03/2016-17 | 0.81 | 0 | 0 | 54.64 | 2017-05-22 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-07-02 | 53.55 | 100% | 2018-11-20 | 53.375 | 53.375 | 0 | 99.67% | Final
8 | 287433021-Bamonkhali Bazar-Jugakhali UP rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 287434006-Improvement of Tin Bot-tala to Satpota bazar Via Nathpur Rd by BC (Ch. 1621-3622m) with 4nos. Pipe Drain Culvert at Ch. 1861m, 2090m, 2206m & 2465m and 1no. 625mmX600mm U-Drain at Ch. 2588m on the Same Road | KDRIDP/Sat/W-01/2016-17 | 2.001 | 0 | 0 | 121.34 | 2017-05-22 | Star Enterprise Munjitpur, Satkhira | 2017-07-02 | 119.46 | 0% | 2019-06-30 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 2,24,703/-
10 | 287434028-Improvement of Kesmot Elishpur-Chitla Bottola road at Ch. 2062-3680m | KDRIDP/Sat/ W-49/2017-18 | 1.618 | 0 | 0 | 111.62 | 2018-04-10 | M/S Sardar Bricks Kalaroa, Satkhira | 2018-12-02 | 117.026 | 30% | 2019-12-08 | 0 | 0 | 0 | 0% | 0
11 | 287434053-Improvement of Kalaroa-Saraskati R&H at Hamidpur More-Bamonkhali road at Ch. 1540-3115m | KDRIDP/Sat/ W-53/2017-18 | 1.575 | 0 | 0 | 111.359 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 114.69 | 30% | 2019-06-11 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 75036.00
12 | 287434059-Improvement of Brojabaksah jamal More - Jhapagat Pukur road by BC at Ch. 1175-2605m | KDRIDP/Sat/W-36/2017-18 | 1.43 | 0 | 0 | 91.18 | 2018-07-26 | Md. Rafiqul Islam Kalaroa, Satkhira | 2018-10-01 | 95.71 | 65% | 2019-10-07 | 0 | 56 | -56 | 58.51% | 1st R/A Bill
13 | 287434057-(a) Improvement of Boyerdanga FRB - N. Kati Charabattala FRB road at (Ch. 00-1995m) by 25mm BC + 7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 746m and (c) Construction of 2nos. 625mmX600mm U-Drain at Ch. 15m & 1083m and (d) Construction of 1no. 900mmX900mm U-Drain at Ch. 1302m on the Same Road | KDRIDP/Sat/W-18/2016-17 | 1.995 | 0 | 0 | 133.75 | 2017-07-17 | Star Enterprise Munjitpur, Satkhira | 2017-09-06 | 129.609 | 0% | 2019-06-30 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 4,24,435/-
14 | 287434061-Improvement of Kazirhat Bazar-Bahura Komorpur road at Ch. 2480-3520m | KDRIDP/Sat/ W-51/2017-18 | 1.04 | 0 | 0 | 73.28 | 2018-04-10 | M/S Sardar Bricks Kalaroa, Satkhira | 2018-12-02 | 76.86 | 40% | 2019-12-08 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 52529.00 NOA issued on 03.05.18
15 | 287434068-Improvement of Boalia Fakirpara Bazar-Bhadiali Bazar road at Ch. 499-1972m | KDRIDP/Sat/ W-40/2017-18 | 1.473 | 0 | 0 | 97.27 | 2018-06-25 | M/S Star Enterprise Munjitpur, Satkhira | 2018-10-18 | 101.409 | 65% | 2019-10-20 | 0 | 0 | 0 | 0% | Salvage Amount Tk.1012925.00
16 | 287434072-Improvement of Bamonkhali Bazar-Batra Bazar road at Ch. 3980-5250m | KDRIDP/Sat/ W-52/2017-18 | 1.27 | 0 | 0 | 81.245 | 2018-04-10 | Borna Trading Internationl, Kalaroa, Satkhira | 2018-06-05 | 81.2 | 65% | 2019-06-11 | 0 | 47 | -47 | 57.88% | Salvage Amount Tk. 21921.00 1st R/A Bill
17 | 287434085-Brikrompur FRB-Hojoldi bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287435004-Improvement of Kayla-Morarikati road at Ch. 2593-4080m | KDRIDP/Sat/ W-86/2018-19 | 1.487 | 0 | 0 | 125.668 | 2018-11-26 | M/S Aman Traders Kalaroa, Satkhira | 2019-01-22 | 119.38 | 5% | 2020-01-28 | 0 | 0 | 0 | 0% | Salvage amount Tk. 78310.00
19 | 287435018-(a) Improvement of Helatala UP Tile Fectory - Kashpur P/School more road at Ch 1599m - 3114m by 25mm BC+7mm SC (b) Construction of 1no. 315mm PVC Pipe Drain at Ch. 2219m and (c) Construction of 3nos. 625mmX600mm U-Drain at Ch. 1745m, 2076m & 2739m on the Same Road. | KDRIDP/Sat/W-35/2017-18 | 1.515 | 0 | 0 | 100.56 | 2018-04-23 | Md. Rafiqul Islam, Kalaroa, Satkhira. | 2018-06-06 | 95.536 | 65% | 2019-06-12 | 0 | 0 | 0 | 0% | 0
20 | 287434093-Improvement of Khordo Batra Regd. Non-Govt. Primary School More to Maniknagar-Ofapur (DPP Name-Ofapur Govt. Primary School to Basantapur) Govt. Primary School Road by BC at Ch. 1978-3187m | KDRIDP/Sat/W-105a/2018-19 | 1.209 | 0 | 0 | 93 | 2019-04-08 | M/S Tasin Enterprise Kalaroa, Satkhira. | 2019-05-21 | 88.35 | 0% | 2020-05-27 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 260607.00
21 | 287435085-Improvement of Panchpota - Sonabaria bazar road at (Ch. 2944-3500m) by 25mm BC + 7mm SC | KDRIDP/Sat/W-19/2016-17 | 0.556 | 0 | 0 | 34.29 | 2017-07-17 | Md. Rafiqul Islam Kalaroa, Satkhira | 2017-09-06 | 33.606 | 100% | 2018-06-12 | 33.567 | 33.567 | 0 | 99.88% | Final
22 | 287435045-Hulhulia Notun Bazar More-Hulhulia Govt.Primary School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 287434035-Improvement of South Barali A Rahman House - Sonabaria Hazrat House (Ramkesnopur hat khola more-Nurmohammad Gazi H/O) Road by BC at Ch. 442-1365m | KDRIDP/Sat/W-99/2018-19 | 0.923 | 0 | 0 | 80.156 | 2019-03-25 | M/S Shahid Enterprise, Kalaroa, Satkhira. | 2019-05-05 | 76.148 | 0% | 2020-05-11 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 261683.00
24 | 287435110-Improvement of Nathpur Khanpukur more - Nathpur Gazipara via Kamarepota road at (Ch. 00-575m) by 25mm BC + 7mm SC (b) Construction of 2nos. 315mm PVC Pipe Drain at Ch. 130m & 375m on the Same Road | KDRIDP/Sat/W-20/2016-17 | 0.575 | 0 | 0 | 35 | 2017-07-17 | G M Enterprise Kalaroa, Satkhira | 2017-09-06 | 36.55 | 100% | 2018-04-30 | 36.548 | 36.548 | 0 | 99.99% | Final
Maintenance
25 | 287432003-Baguri Beltala -Chandanpur GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287432006-Kalaroa- Tala via Dhandia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
27 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 30.406 | 0 | 0 | 2109.021 |  |  |  | 1875.039 | 35.74% |  | 547.285 | 738.285 | -191 | 39.37%

## Satkhira Sadar
Satkhira Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 287823010-Mahamudpur Bazar-Abaderhat Via Jaghanathpur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 287823020 - Improvement of Ghona Bazar - Kushkhali UPC Bhadra Ziader more road via Aruakhali GPS at ch 1665-2687m and 2687-3914m | KDRIDP/Sat/W-69/2017-18 | 2.25 | 0 | 0 | 170.68 | 2018-06-28 | M/S Uttam Traders Tala, Satkhira | 2018-08-16 | 178.84 | 45% | 2019-08-22 | 0 | 48.895 | -48.895 | 27.34% | 2nd R/A bill
3 | 287823020-Improvement of Ghona Bazar - Kushkhali UPC (Bhadra Ziader more) road via Aruakhali GPS road by BC at ch.00-1665m | KDRIDP/Sat/W-104a/2018-19 | 1.665 | 0 | 0 | 140.697 | 2019-04-23 | Sk Sirajul Haq Labsha, Satkhira. | 2019-06-27 | 140.613 | 0% | 2020-06-27 | 0 | 0 | 0 | 0% | Salvage amount Tk.456583.00
4 | 287823022-Agordari UP Office (Abadehat GC ) - Bharukhaki Bazar ( Bharukhali GPS) Road Via Jhitkee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 287823023-Bali UP office - Raipur Bazar road via Shumundanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287824004-Bansdah UP Office-Kawan danga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 287824009-Dhohakula FRB-Dhohakula R&H (Assasuni) road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 287824014-Improvement of Dhuliar- Damarpara WAPDA Embt road Ch.0.00-1000m | KDRIDP/Sat/ W-80/2018-19 | 1 | 0 | 0 | 82.37 | 2019-01-23 | M/S Biswas Enterprise, Old Satkhira, Satkhira | 2019-03-31 | 86.489 | 10% | 2020-04-06 | 0 | 0 | 0 | 0% | Salvage amount Tk. 1018994.00
| 287825133-Improvement of Brahmmorajpur Bazar to Chalerdangi RHD Assasuni road Brahmmorajpur Bazar to Baradal Pucca road via Dhulihor Chandra Pukur road at ch. 00-866m |  | 0.866 | 0 | 0 | 71.026 |  |  |  | 74.582 |  |  | 0 | 0 | 0 | 0%
10 | 287824023-Taltala R&H to Kaikhali Mistripara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287824025-Improvement of Brahmmorajpur Maniktala to Machkhola Hatkhola road by BC at ch 1950-2950m | KDRIDP/Sat/W-101/2018-19 | 1 | 0 | 0 | 79.837 | 2019-04-23 | M/S Raka Enterprise Tala, Satkhira. | 2019-06-19 | 78.24 | 0% | 2020-06-25 | 0 | 0 | 0 | 0% | Salvage amount Tk. 255428.00
12 | 287824028-Improvement of Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road by BC at ch.1285-3245m | KDRIDP/Sat/W-102/2018-19 | 1.96 | 0 | 0 | 155.369 | 2019-04-08 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.1382987.00 Re-tenderer receiving date 01.07.19
13 | 287824061-Improvement of Faizullahpur more (Satkhira-Assasuni R&H) to Fingri UP Office road by BC at ch 00-490m & 2892-3362m. | KDRIDP/Sat/W-104/2018-19 | 0.96 | 0 | 0 | 81.029 | 2019-03-25 | 0 | 0 | 76.978 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage amount Tk.1344528.00
14 | 287825021-Gobindakati Satrano Battola-Reui Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 287825016-Improvement of Bhabanipur more- Toloigacha BDR Camp road by BC at ch.2470-2993m | KDRIDP/Sat/W-105/2018-19 | 0.523 | 0 | 0 | 40.285 | 2019-03-25 | 0 | 0 | 38.271 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage amount Tk.423046.00
16 | 287825060-Improvement of Babulia FRB-Satkhira City College Road by BC at Ch. 1390-3200m | KDRIDP/Sat/ W-79/2018-19 | 1.81 | 0 | 0 | 136.916 | 2018-10-25 | M/S Raka Enterprise, Tala, Satkhira | 2018-12-06 | 130.07 | 10% | 2019-12-12 | 0 | 0 | 0 | 0% | Salvage amount Tk. 868320.00
18 | 287825062-Chandpur-Budhata Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287825187-Improvement of Jardia Sheikh Para.GPS-Jardia SK Para-SK Mizanur Rahman house road by BC at ch 00m-1005m | KDRIDP/Sat/W-100/2018-19 | 1.005 | 0 | 0 | 78.899 | 2019-03-25 | M/S Reba Enterprise Bagerhat. | 0 | 81.818 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage amount Tk. 280487.00 NOA issued on 26.06.19
20 | 287825158-Bankal-Bagmari road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287825107-Goalpota Hatkhola to Kamardangi Sluice Gate road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287824028-Brahmmorajpur Bazar to Ellarchor Pucca road via Mallekpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Duplicate
23.2121 | 287824054-Improvement of R&H Puraton Satkhira-Machkhola Road at Ch.1500-2970m | KDRIDP/Sat/W-112/2018-19 | 1.47 | 0 | 0 | 108.823 | 2019-04-23 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.109805.00 TER sent to HQ
Improvement of Village Road by HBB
24 | 287824005-Matiadanga Khaya ghat-Khariadanga Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 287824008-Ghona-Vharukhali Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287824011-Ghona BOP-Gazipur Golam Ali House Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287824003-Dhulihar puraton Bazar Khola more to Damarpota via Kazir house & Bardal Village road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 287824007-Vatpara-Gharchala P/School Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287824010-Chandpur bazar-Kulpota WAPDA Embt. Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287824016-Kumorpur R&H-Kumorpur WDB EMB Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287825041-Nehalpur WDB Emb. to Jugipota (Sukdebpur) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
32 | 287822010-Periodic Maintenance of Rasulpur R&H-Baikari UP via Pairadanga-Aruakhali via Mirgidanga road at Ch. 00-4200m | KDRIDP/Sat/ M-01/2017-18 | 4.2 | 0 | 0 | 105.51 | 2018-05-17 | Md. Ashraful Kabir Khokun, Katia, Satkhira | 2018-06-25 | 110.785 | 100% | 2019-03-30 | 110.785 | 110.785 | 0 | 100% | Final
33 | 287823010-Mahamudpur Bazar -Abaderhat via Jaghanathpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 287823024-Periodic Maintenance of Kulia Sreerampur Chubaria-Bhamra road at Ch. 00-1000m | KDRIDP/Sat/M-03/2017-18 | 1 | 0 | 0 | 20.34 | 2018-05-17 | S.M. Shawkat Hossain, Katia, Satkhira | 2018-06-25 | 21.35 | 100% | 2019-02-28 | 21.348 | 21.348 | 0 | 99.99% | Final
35 | 287824001-Padma Sakra UP office-Sakra Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 287824004-Bansdah UP Office-Kawandanga Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 287824006-Binerpota bridge-Rajnagore Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 287824012-Puraton Satkhira R&H hat-Gobindopur Bazar Road via jiala | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 287824032-Periodic Maintenance of Shaighoria R&H-Akhrakhola Bazar via Satianatala & Battala More road at Ch. 00-2752m | KDRIDP/Sat/ M-02/2017-18 | 2.752 | 0 | 0 | 57.8 | 2018-05-17 | Santa Mahmud, Kamalnagor, Satkhira | 2018-06-25 | 60.11 | 100% | 2019-04-01 | 60.097 | 60.097 | 0 | 99.98% | 0
40 | 287824032-Shaighoria R&H-Akhrakhola Bazar via Satiantala & Battala more road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 287824042-Shaighoria R&H-Babulia Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 287824050-Madabkati-Satani Bazar road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 287825145-Alipur Jangalar Bridge - Nathuar Danga Road via Kulpura Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
44 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 22.461 | 0 | 0 | 1329.581 |  |  |  | 1078.146 | 8.488% |  | 192.23 | 241.125 | -48.895 | 22.36%

## Tala
Tala
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287902001-Improvement of Tala-Kalaroa UP HQ via Dalua GC-Patkelghata GC road Tala Portion road by BC (Ch. 10020-11788m) with 1no. 925mmX900mm U-Drain at Ch. 11160m on the Same Road | KDRIDP/Sat/W-09/2016-17 | 1.94 | 0 | 0 | 160 | 2017-06-08 | M/S Basu Traders Tala, Satkhira | 2017-07-11 | 158.79 | 100% | 2018-09-28 | 0 | 137.138 | -137.138 | 86.36% | Salvage Amount Tk. 3,08,136/-
2 | 287902004-Improvement of Jethua GC-Budhata GC via Horihornagar Bazar (Tala Portion) Road by BC at Ch. 11830m-16250m | KDRIDP/Sat/ W-94/2018-19 | 4.42 | 0 | 0 | 417.939 | 2018-12-18 | M/S Rafid Traders- M/S Bosu Traders (JV), Tala, Satkhira | 2019-02-24 | 401.259 | 25% | 2020-03-01 | 0 | 0 | 0 | 0% | 0
3 | 287902005-Improvement of Kopilmoni GC-Jatua GC road at Ch. 5465-6429m | KDRIDP/Sat/W-57/2017-18 | 0.964 | 0 | 0 | 78.67 | 2018-04-10 | Uttam Traders, Tala, Satkhira. | 2018-05-21 | 82.434 | 100% | 2019-05-27 | 82.434 | 82.434 | 0 | 100% | Final
Improvement of Union Road by BC
4 | 287903003-Patkelghata GC(R&H) near Pollibiddut-Khalishkhali UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 287903006-(a) Improvement of Tala UP Office Hospital-Jatpur GC road by BC (Ch. 1596-5096m) (b) Construction of 6nos. 625mmX600mm U-Drain at Ch. 169m, 2896m, 3396m, 3641m, 3946m & 4616m and (c) Construction of 1no. 925mmX900mm U-Drain at Ch. 2286m on the Same Road | KDRIDP/Sat/W-10/2016-17 | 3.5 | 0 | 0 | 226.07 | 2017-06-12 | Md. Iqbal Jamader, Polashpole, Satkhira | 2017-07-16 | 223.62 | 100% | 2018-05-30 | 219.69 | 219.69 | 0 | 98.24% | Salvage Amount Tk. 1,39,115.00 Final
6 | 287903013-Improvement of Khesra UP-Shalika Bazar via Dakshin Sahjadpur Bazar & KSD Girls School Road by BC at Ch. 00m-900m , 3294m-3902m & 6879m-8870m | KDRIDP/Sat/ W-95/2018-19 | 3.499 | 0 | 0 | 264.3 | 2018-12-18 | M/S Bosu Traders Tala, Satkhira | 2019-02-24 | 249.619 | 35% | 2020-03-01 | 0 | 68 | -68 | 27.24% | Salvage Amount Tk. 846368.00
7 | 287903007-Improvement of Magura UP Office-Madra Bazar road at Ch. 1000-2215m | KDRIDP/Sat/ W-56/2017-18 | 1.215 | 0 | 0 | 79.239 | 2018-04-10 | M/S Raka Enterprise, Tala, Satkhira. | 2018-05-21 | 79.235 | 100% | 2019-06-24 | 79.013 | 79.013 | 0 | 99.72% | Final
| 287903015-Improvement of Islamkati UP Office-Magura Bazar road at Ch. 1000-2215m |  | 0.982 | 0 | 0 | 64.59 |  |  |  | 64.586 |  |  | 64.405 | 64.405 | 0
8 | 287903011-Improvement of Nagarghata UP-Pulirhat road at Ch. 00-1670m | KDRIDP/Sat/ W-55/2017-18 | 1.67 | 0 | 0 | 116.069 | 2018-04-10 | M/S Uttam Traders Tala, Satkhira | 2018-11-29 | 119.888 | 10% | 2019-12-07 | 0 | 0 | 0 | 0% | NOA issued on 03.05.18
9 | 287903008-Improvement of Tentulia UP Office Madanpur R&H-Ghona Bazar via Dewanipara Bazar road by BC Ch.2000-4000m | KDRIDP/Sat/ W-113/2018-19 | 2 | 0 | 0 | 148.804 | 2019-06-18 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 3228643.00
10 | 287903013-Khesra UP-Dakshin Sahjadpur Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
11 | 287904004-Improvement of Manikhar-Ghorerdanga Road by 25mm BC+7mm SC (Ch. 00-1494m) with 4nos. 625mmX600mm U-Drain at Ch. 120m, 380m, 916m & 1309m on the Same Road. | KDRIDP/Sat/W-34/2017-18 | 1.494 | 0 | 0 | 105.99 | 2018-07-19 | M/S M M Brothers, Khulna. | 2018-09-09 | 109.68 | 60% | 2019-09-15 | 0 | 35 | -35 | 31.91% | Salvage Amount Tk. 455369.00 1st R/A Bill
12 | 287904011-Baliadha-Bolarumpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 287904018-Improvement of Khalishkhali-Dalua road by BC Ch.1000-2700m | KDRIDP/Sat/ W-114/2018-19 | 1.7 | 0 | 0 | 128.53 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 756131.00
14 | 287904057-Improvement of Sujansah Bazar R&H-Ghona Road at Ch. 1000-2140m | KDRIDP/Sat/W-70/2017-18 | 1.14 | 0 | 0 | 78.705 | 2018-06-28 | Uttam Traders Tala, Satkhira | 2018-08-14 | 77.83 | 50% | 2019-08-20 | 0 | 21.228 | -21.228 | 27.28% | Salvage Amount Tk. 44892.00 2nd R/A Bill
| 287905031-Improvement of Magura girls school - joynwddin house Road at Ch. 00m - 995m |  | 0.995 | 0 | 0 | 69.59 |  |  |  | 68.818 |  |  | 0 | 18.772 | -18.772 |  | Salvage Amount Tk. 413124.00 2nd R/A Bill
15 | 287904064-Improvement of Sujanshoha Bazar Paranpur Israil house road at Ch. 00-1007m | KDRIDP/SAT/W-37/2017-18 | 1.007 | 0 | 0 | 71.786 | 2018-04-23 | M/S Roshni Enterprise, Tala, Satkhira. | 2018-06-06 | 74.765 | 100% | 2019-06-12 | 74.765 | 74.765 | 0 | 100% | Final
16 | 287904073-Improvement of Shalika College-Dalua GC road at Ch. 4500-8210m | KDRIDP/Sat/ W-54/2017-18 | 3.71 | 0 | 0 | 246.85 | 2018-04-19 | M/S Basu Traders Tala, Satkhira | 2018-06-25 | 255.3 | 50% | 2019-05-30 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 186115.00
17 | 287905147-Bathuadanga Primary school - Kalagachi Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287904010-Shahpur R&H – Hazrakati Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287904039-Barobila(UZR)- Sarulia Bazar via Barobila GPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 287904088-Improvement of Bhairabnagar R&H-AKrakhola Bazar via Nagarghata UP Office road by BC Ch.5090-6090m | KDRIDP/Sat/ W-116/2018-19 | 1 | 0 | 0 | 73.134 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage Amount Tk. 756131.00
21 | 287905134-Boyardanga UZR - Mokolandokati GPS via Pakshia Durgha Mondir Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287905186-Improvement of Daibari More-H/O Intaz Golder via Maspara Mosjid Road by BC (Old ID 287905185) at Ch. 00-850m | KDRIDP/Sat/W-110/2018-19 | 0.85 | 0 | 0 | 74.95 | 2019-04-08 | M/S Emran Trading Tala, Satkhira. | 2019-05-21 | 71.2 | 0% | 2020-05-27 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 310228.00
23 | 287905108-Improvement of Majiara (House of Azhar Ali more) Khorerdanga Bazar Road by BC (Ch. 118-2024m) with 1no. 625mmX600mm U-Drain at Ch. 1040m on the Same Road | KDRIDP/Sat/W-06/2016-17 | 1.906 | 0 | 0 | 129.44 | 2017-05-22 | M/S Roshni Enterprise Tala, Satkhira | 2017-06-22 | 126.53 | 100% | 2018-06-28 | 126.47 | 126.47 | 0 | 99.95% | Final (Salvage Amount Tk. 22,97,337.00)
24 | 28790516-Kazidanga H/O-Dr. Aminuddin Gazi-Kharail,Bhabanipur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
25 | 247904059-Dakin Sahajadpur Launch ghat-Kathipara bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287864101-Construction of 20m Long RCC Girder Bridge on Biramolla Hat-Kawser Gazi Bari Road at Ch. 350.00m | KDRIDP/Sat/B-03/2018-19 | 0 | 20 | 0 | 130.634 | 0 | M/S Jakaullah & Brothers, Chuadanga. | 2019-04-17 | 120.6 | 0% | 2020-04-23 | 0 | 0 | 0 | 0% | 0
Maintenance
27 | 287902005-Periodic Maintenance of Tala GC-Kopilmoni GC via Jatua GC Road at Ch. 7550-9543m | KDRIDP/Sat/ M-09/2018-19 | 1.993 | 0 | 0 | 39.904 | 2019-01-30 | M/S Avanova Enterprise, Basabati, Bagerhat. | 2019-03-19 | 37.908 | 100% | 2019-09-25 | 37.908 | 37.908 | 0 | 100% | Final
28 | 287904048-Kanchanpur Eidgah (R & H)-Hizaldanga Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 287904115-Periodic Maintenance of Kumira R&H-Magura Bazar Road at Ch. 3460-5300m | KDRIDP/Sat/ M-10/2018-19 | 1.84 | 0 | 0 | 45.8 | 2019-01-30 | Md Rafiqul Islam, Kalaroa, Satkhira. | 2019-03-25 | 43.511 | 60% | 2019-12-30 | 0 | 19.73 | -19.73 | 45.34% | 1st R/A
| 287904088-Periodic Maintenance of Bhairabnagor R&H-Akrakhola Bazar via Nagorghata UP Road at Ch. 2500-4900m |  | 2.4 | 0 | 0 | 40.08 |  |  |  | 38.076 |  |  | 0 | 17.27 | -17.27 | 45.36%
30 | 287905096-Islamkati Primary School - Vagba House of Abdul Malek Mohalder Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.587 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Tree Plantation
31 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 40.225 | 20 | 0 | 2791.074 |  |  |  | 2485.236 | 31.94% |  | 684.685 | 1001.823 | -317.138 | 40.31%

## Shyamnagar
Shyamnagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287862002-Improvement of Nowabenki GC - Khanpur R&H via Vetkhali GC road at (Ch. 27100-29000m & Ch. 32300-34100m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 27350m, 27800m & 33200m on the Same Road | KDRIDP/Sat/W-11/2016-17 | 3.7 | 0 | 0 | 321.22 | 2017-10-09 | mewebajv Shyamnagar, Satkhira | 2017-12-03 | 330.37 | 70% | 2019-05-31 | 0 | 199.21 | -199.21 | 60.3% | 3rd R/A Bill
2 | 287862005-Pakhimara R&H -Protapnagar GC Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 287863003-Nakipur-Sirajpur hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 287863004-Improvement of Iswaripur UP-Harinagar hat via Dhumkali Road by BC (Ch. 00-4090m) with 3nos. 1mX1m Single Vent RCC Box Culvert at Ch. 210m, 3305m & 3950m on the Same Road | KDRIDP/Sat/W-04/2016-17 | 4.09 | 0 | 0 | 279.02 | 2017-05-25 | M/S Rabeya Traders Dhaka | 2017-06-14 | 273.53 | 65% | 2019-12-31 | 0 | 126.5 | -126.5 | 46.25% | Salvage Amount Tk. 38,60,858/- 2nd R/A Bill
5 | 287863013-Improvement of Iswaripur UP-Paranpur hat via Ramjannagar Road by BC (Ch. 1900-3475m) | KDRIDP/Sat/W-05/2016-17 | 1.575 | 0 | 0 | 102.54 | 2017-05-22 | M/S Rabeya Traders Dhaka | 2017-06-14 | 95.93 | 10% | 2019-12-31 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 13,04,167/-
6 | 287863017-Improvement of Iswaripur UP- Gumantali hat via Golabari Ghat Road by BC at Ch. 2730-4500m. | KDRIDP/Sat/ W-83/2018-19 | 1.77 | 0 | 0 | 162.496 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 1671706
7 | 28783012-Noornagar-Kultali Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 287864007-Improvement of Iswaripur FWC - Beramollah Hat road at (Ch. 00-3000m) & Construction of 7.0m Long 600mmX600mm U-Drain at Ch. 368m on the Same Road | KDRIDP/Sat/W-12/2016-17 | 3 | 0 | 0 | 182.52 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 187.9 | 65% | 2019-02-06 | 0 | 115.267 | -115.267 | 61.34% | Salvage Amount Tk. 2,62,483/- 3rd R/A Bill Time ext. sent to PD
9 | 287864026-Ramjibonpur More-Horinagari Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287864038-ZR at Sonaremore-Fulbari-Chigrikhali road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287864040 Chandipur R&H-Sankarkati hat-Majhergonj hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287864062- Munshigonj Bazar-Garrage hat Bridge. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 287864077 Jadappur Pucca road-Kallyanpur Sluicegate-Chingrikhali road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287864102- Improvement of Biramollah hat Kowsar Gazi bari road at (Ch. 1000-2200m) | KDRIDP/Sat/W-15/2016-17 | 1.2 | 0 | 0 | 73.26 | 2017-10-09 | Md. Rafiqul Islam Situlpur, Kaligonj | 2017-11-19 | 75.4 | 100% | 2019-02-06 | 73.158 | 73.158 | 0 | 97.03% | Salvage Amount Tk. 5,06,656 Final
15 | 287864102-Improvement of Khagraghat H/O Fazlul Haque- R & H road by BC.Ch0.00m-1100m | KDRIDP/Sat/W-48/2017-18 | 1.1 | 0 | 0 | 76.22 | 0 | M/S Asa Construction, Shyamnagar, Satkira | 2018-04-22 | 80.03 | 100% | 2019-06-07 | 79.426 | 79.426 | 0 | 99.25% | Final
16 | 287864119- Badaghata-Anowara khatun Mohila Madrasa via Muktijoddha. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287865149- Improvement of Mohendrakata - Badda house road at (Ch. 00-1650m) & Construction of 2nos. 7.0m Long 600mmX600mm U-Drain at Ch. 1100m & 1400m on the Same Road | KDRIDP/Sat/W-13/2016-17 | 1.65 | 0 | 0 | 99.52 | 2017-10-09 | Md. Abdul Hakim Situlpur, Kaligonj | 2017-11-19 | 103.965 | 100% | 2019-03-30 | 0 | 30.944 | -30.944 | 29.76% | 2nd R/A Bill
18 | 287864110-Improvement of Biramollah hat - Ruhit Majhi - Dakin Srifalkati road at (Ch. 1000-2718m) | KDRIDP/Sat/W-14/2016-17 | 1.718 | 0 | 0 | 104.69 | 2017-07-16 | M/S Asha Construction Ishwaripur, Shyamnagar, Satkhira | 2017-09-20 | 109.897 | 100% | 2018-07-22 | 108.872 | 108.872 | 0 | 99.07% | Salvage Amount Tk. 1,74,989.00 Final
19 | 287864148-Improvement of Padmapukur R&H-Baintala GPS road at Ch. 00-2000m | KDRIDP/Sat/W-42/2017-18. | 2 | 0 | 0 | 85.906 | 0 | Md. Iqbal Jamader Polashpole, Satkhira | 2018-04-24 | 85.65 | 30% | 2019-07-03 | 0 | 0 | 0 | 0% | 0
20 | 28785149-Mohendrokata-Baidda house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287864045 - Improvement of Sapkhali - Kaikhali BOP Road by BC at Ch.00m-3000m | KDRIDP/Sat/ W-84/2018-19 | 3 | 0 | 0 | 225.073 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 2271785
22 | 287864031-Improvement of Hawalbhangi-Baduria road at CH. 00-2651m | KDRIDP/Sat/ W-82/2018-19 | 2.615 | 0 | 0 | 211.467 | 2019-04-08 | 0 | 0 | 208.929 | 0% | 0 | 0 | 0 | 0 | 0% | Salvage amount Tk. 1849998
23 | 287864100-Dumuria Bazr-Parsheemari Kheyaghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 287865048-Improvement of Jada more-Gani Mollik road at (Ch. 00-1500m) | KDRIDP/Sat/W-21/2017-18 | 1.5 | 0 | 0 | 105.17 | 2017-08-31 | Molla Engineering Workshop Shyamnagar, Satkhira | 2017-10-09 | 109.27 | 100% | 2018-11-30 | 0 | 99.09 | -99.09 | 90.68% | Salvage Amount Tk. 2,04,581/- Final (Part)
25 | Gorkumarpur Bazar to Diglarait Moszid. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 287864041-Zr. Moutala-Tajhori hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 287864105-Improvement of Isakur LGED Pacca Road-Jahasghata Shahi Mosque Road by BC at Ch. 00-1050m | KDRIDP/Sat/W-115/2018-19 | 1.05 | 0 | 0 | 83.42 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 1437362
28 | 287865036- Improvement of Bongshipur-Azad Gazi road at CH. 00-950m | KDRIDP/Sat/ W-81/2018-19 | 0.95 | 0 | 0 | 86.11 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 1341082.00 Tender receiving date 18.07.19
| 287864048-Improvement of Jotindanagar hat-Manikhali R&H road at Ch. 9180-11180m |  | 2 | 0 | 0 | 167.37 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
Maintenance
29 | 287862002-Nowabenki GC-Khanpur R&H via Vetkhali GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287863007-Burigoalini UP-Nildumur hat Masud more via Durgabati Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287863009-Nakipur GC-Chandipur hat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 287864074-Soalia Mosque-Kallanpur Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 287864077-Jadabpur Pacca road-Kallanpur Sluice gate Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 287864146-Nurnagar-Ramchandrapur-Habibpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 287863002 Kasimari UP-Jhapali hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 287864041 ZR at Moutala-Teghori hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Landing/ Riverghat
37 | Garkunerpur bazar ghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
38 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 32.918 | 0 | 0 | 2366.002 |  |  |  | 1660.871 | 19.47% |  | 261.456 | 832.467 | -571.011 | 50.12%

## Debhata
Debhata
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287252007-Improvement of Subornabad GC-Bangdah GC Road by BC (Ch. 3240-5240m) with 15nos. 625mmX600mm U-Drain at Ch. 3241m, 3275m, 3352m, 3529m, 3568m, 3678m, 3705m, 3952m, 4093m, 4291m 4539m, 4642m, 4816m, 5032m & 5058m on the Same Road. | KDRIDP/Sat/W-08/2016-17 | 2 | 0 | 0 | 165.74 | 2017-05-22 | M/S Habib Enterprise Satkhira | 2017-06-14 | 173.1 | 100% | 2018-06-20 | 172.248 | 172.248 | 0 | 99.51% | Salvage Amount Tk. 8,93,628 Final
2 | 287252008-Improvement of Bohera Bazar (RHD) - Ellarchor Bazar -Bangdah GC(Sadar) Road by BC (Ch. 6704-8000m) with 3nos. 625mmX600mm U-Drain at Ch.7050m, 7640m & 7775m and 1no. 900mmX900mm U-Drain at Ch. 7700m on the Same Road | KDRIDP/Sat/W-07/2016-17 | 1.296 | 0 | 0 | 87.3 | 2017-05-22 | M/S Joint Bricks Traders Bankal, Satkhira | 2017-07-02 | 84.78 | 100% | 2018-10-08 | 0 | 76.054 | -76.054 | 89.71% | 1st R/A Bill
3 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 8000-9660m | KDRIDP/Sat/W-61/2017-18 | 1.66 | 0 | 0 | 146.46 | 2018-05-30 | M/S Joint Bricks Traders, Bankal, Satkihra | 2018-07-12 | 153.787 | 100% | 2019-06-20 | 0 | 16 | -16 | 10.4% | 1st R/A Bill
4 | 287252008- Improvement of Bohera Bazar RHD- Ellarchor Bazar- Bangdah GC road Ch. 9660m-11910m | KDRIDP/Sat/ W-85/2018-19 | 2.25 | 0 | 0 | 211.187 | 2019-04-30 | M/S Joint Bricks Traders, Bankal, Satkhira. | 2019-06-19 | 216.994 | 0% | 2020-06-25 | 0 | 0 | 0 | 0% | Salvage amount Tk. 458337.00
Improvement of Union Road by BC
5 | 287253002-Sakhipur UP-Nangla Bazar via Eidgah Chandipur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 287253003-Debhata UP Office-Komorpur Road(Debhata Portion) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287253005-Nowapara UP -Bodarhata GC via Chandpur Atapur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 287254001-Sekendra R&H-WDB Embankment (Ghariadanga) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 287254006-North Parulia R&H-Naziergheer Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287254021-Konra Pakralala R&H-Kazimoholla Samsuddin M. House Road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287254035-Debhata Parulia UZR-Bhatshala Cyclone Shelter Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287254037-Sushilgati FRB-Eidgah Sakhipur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 287254045-Badartola Bazar-Rangashisha Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 287255032-Ratanshapur Babar Ali Shop-Teyor GCCR Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 287255175-Improvement of Shakhipur Mosque - Khegurbaria Southpara Mosque road at Ch 00-1135m with 2nos. 625mmX600mm U-Drain at Ch.62m & 560m on the Same Road | KDRIDP/Sat/W-59/2017-18 | 1.135 | 0 | 0 | 92.117 | 2018-04-23 | Md. Shajahan Alam, Kaligonj, Satkhira. | 2018-06-06 | 96.61 | 40% | 2019-06-12 | 0 | 27.015 | -27.015 | 27.96% | Salvage Amount Tk. 863133.00
15 | 287255075-Improvement of Shakhipur Nimay house - Lakhimi Kanta house road at Ch 00-1038m with 3nos. 625mmX600mm U-Drain at Ch.450m, 615m & 892m on the Same Road. |  | 1.038 | 0 | 0 | 81.768 |  |  |  | 85.76 |  |  | 0 | 23.985 | -23.985 | 27.97% | Salvage Amount Tk. 1536290.00
16 | 287254033-Subornabad FRB-Darer khal Ferry ghat Via Shasadanga Madrasha). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287254043-Improvement of Shakhipur Bazar - Bhatshala UNR WDB Embankment road at Ch 00-6210m | KDRIDP/Sat/W-58/2017-18 | 6.21 | 0 | 0 | 418.94 | 2018-06-25 | M/S Rafid Traders & M/S Bosu Traders JV, Tala, Satkhira | 2018-09-11 | 443.5 | 25% | 2019-09-17 | 0 | 0 | 0 | 0% | Salvage Amount Tk. 1384326.00
18 | 287255045-Chaltatola-Synnasir chack via roingashisha( WDB) Emabankmnet road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18.784 | 287255153-Parulia Sunial Desh House- Jhal Bagen Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19.6245 | 2872555130-pubo kulia bridge tosadesh hachari Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
21 | 287254013-Gazirhat- Kalabaria via Borohula Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
22 | 287252008-Periodic Maintenance of Bohera Bazar RHD-Ellarchor Bazar-Bangdah GC road at Ch. 00-1735m | KDRIDP/Sat/ M-04/2017-18 | 1.735 | 0 | 0 | 47.5 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 49.39 | 100% | 2019-06-20 | 0 | 0 | 0 | 0% | 0
23 | 287254025-Periodic Maintenance of Hadipur R&H-Hadipur Masrasha via Ashkarpur Alimiya Kallyan Sangoshta road at Ch. 1145-2296m | KDRIDP/Sat/M-05/2017-18 | 1.151 | 0 | 0 | 15.6 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 16.22 | 100% | 2018-11-23 | 16.215 | 16.215 | 0 | 99.97% | Final
24 | 287254038-Periodic Maintenance of Parulia R&H-Debhata Parulia GCR via Sakhipur Dhopadanga road at Ch. 00-1045m | KDRIDP/Sat/ M-06/2017-18 | 1.045 | 0 | 0 | 20.519 | 2018-04-10 | Md. Taherul Huda Kaligonj, Satkhira | 2018-05-17 | 21.33 | 100% | 2018-12-08 | 21.218 | 21.218 | 0 | 99.47% | Final
25 | 287255070-Nowapara Nawser house-Bibuti`s house Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
26 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 19.52 | 0 | 0 | 1287.131 |  |  |  | 1341.471 | 25.58% |  | 209.681 | 352.735 | -143.054 | 26.29%

## Assasuni
Assasuni
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 287042010-Chiledanga RHD - Bangadah GC Paithali Bazer Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 287042012-Mohishkur RHD - Bashtala bazar via Mohishkur GC Road (Assasuni part). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 287042013-Protapnagar GC-Pakhimara RHD(Assasuni part). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 287043001-Kadakati UP office - Kadakati GC via Gabtala Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 287043004-Ekshora bazar-Bichotbazar(Anulia UP) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 287043008-Dargapur UP Office-Tentulia Bazer Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 287043010-Paithali Bazar - Sobhnali UP office via Kamalkati kheyaghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 287043011-Bardal UP office - Kapsanda Bazar via Baintala & Fatikkhali road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 287044018-Badartala-Mozgurkhali Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 287044089-Agordhari-Gabtala via Kampura rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 287044094-APS Collage-Gokulnagar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 287045059-Improvement of Agordari Dhalibari- Hazi bari Graveyard via Agordari High School road at ch.00-1330m. | KDRIDP/Sat/W-96/2018-19 | 1.33 | 0 | 0 | 120.808 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.145777.00 Re-tender receiving date 18.07.19
13 | 287044119-Improvement of Kachua Girls high School- Agordari High School road at ch.00-1380m. | KDRIDP/Sat/W-97/2018-19 | 1.38 | 0 | 0 | 116.615 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk.727589.00 Re-tender receiving date 18.07.19
14 | 287044156-Improvement of Agordari west para Mosque- Kadakati GC road at ch.00m-1445m. | KDRIDP/Sat/W-98/2018-19 | 1.445 | 0 | 0 | 128.93 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Salvage amount Tk. 325005.00 Re-tender receiving date 18.07.19
15 | 287045066-Natana bazar - Hashkhali GPS via Hashkhali culvert road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 287044133-Kurikahunia Makbul Dokanderer Bari - Nakna Gazibari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 287044034-Sriula R&H-Sriula Shashibari Bridge via BD Chow house. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 287044030-Budhata Bazar to Budhata Pr.School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 287045064-Mohishadanga High school-Ganesher Khey ghat via H-O. Kishor Babu. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 287044051-Mohistpur- Boyershing khal road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 287045126-Badar tola Hazi Jallauddin Collage- Mozjurkhali Pr.School road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 287045072-Sreeula Molla Bari Mosque road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 287044228-Improvement of Godaipur-Rautara road by BC at ch.00-825m | KDRIDP/Sat/W-111/2018-19 | 0.825 | 0 | 0 | 69.94 | 2019-04-23 | M/S Ziaul Traders Khulna. | 2019-06-27 | 69.44 | 0% | 2020-06-27 | 0 | 0 | 0 | 0% | Salvage amount Tk. 2332396.00
| 287045092-Improvement of Sreeula Football Field-Sluice Gate via Jela Parishad road by BC at ch.00-500m |  | 0.5 | 0 | 0 | 39.936 |  |  |  | 39.651 |  |  | 0 | 0 | 0 | 0%
| 287045057-Improvement of Sreeulia R&H-Sreeulia UP Office road by BC at ch.00-500m |  | 0.5 | 0 | 0 | 37.986 |  |  |  | 37.715 |  |  | 0 | 0 | 0 | 0%
Improvement of Village Road by HBB
24 | 287044032-Naktara FRB to Baliakhali WAPDA via Radharati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 287044179-Tuardanga Culvert - Bamondanga bridge via Tuardanga Paschimpara Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
26 | 287043012-Construction of 32.0m Long PSC Girder Bridge on Sovnali UP-Nashukhali Bazar via Paschim Kamalkati Radha Shyamsundar Mondir Road at Ch. 5300m | KDRIDP/Sat/B-01/2018-19 | 0 | 32 | 0 | 230.94 | 2018-09-13 | Md. Moyenuddin (Bashi)-M/S Sattar Enterprise (JV), Tejgaon, Dahaka. | 2018-11-12 | 229.84 | 35% | 2019-11-18 | 0 | 64 | -64 | 27.85% | Pile casting on going. 1st R/A Bill
27 | 287044188-Construction of Bridge on Gazir hat-Chumuria road over Morischap khal. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
28 | 287042001-Periodic Maintenance of Assasuni GC-Manikkhali Ferry Ghat Road at Ch. 00-155m & 1178-2260m | KDRIDP/Sat/ M-07/2018-19 | 1.237 | 0 | 0 | 30.904 | 2018-11-26 | Md. Abdus Salam Gazi, Assasuni, Satkhira | 2019-01-22 | 29.36 | 100% | 2019-07-28 | 29.356 | 29.356 | 0 | 99.99% | Final
29 | 287042010-Chiledanga RHD -Bangdah GC Road via Paithali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 287043002-Khazra UP- Bordol GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 287043008-Dargapur UP Office -Tentulia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 287044088-Gunaharkati Bazar-Mohajanpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 287044089-Periodic Maintenance of Agordhari-Gabtola via Humkura road at ch. 00-1430m | KDRIDP/Sat/ M-08/2018-19 | 1.43 | 0 | 0 | 37.828 | 2018-11-26 | M/S Saleha Enterprise, Debhata, Satkhira | 2018-12-27 | 35.937 | 100% | 2019-07-02 | 35.937 | 35.937 | 0 | 100% | Final
GC-Hat
34 | Construction of East Nakna Bazar Chairman Bazar GC | KDRIDP/Sat/ GC-09/2017-18 | 0 | 0 | 1 | 20.59 | 2018-04-10 | Md. Abul Hossain Kamalnagar, Satkhira | 2018-05-06 | 20.264 | 100% | 2018-11-12 | 20.264 | 20.264 | 0 | 100% | Final
Landing/ Riverghat
35 | Boundhir Khyaghat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
36 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 8.647 | 32 | 1 | 834.477 |  |  |  | 462.207 | 9.306% |  | 85.557 | 149.557 | -64 | 32.36%

## Summary
SATKHIRA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 10 | 8 | 25.1 | 0 | 0 | 1601.514 | 683.084 | 74.38% | 42.65%
Union Road by BC | 17 | 14 | 38.06 | 0 | 0 | 2157.676 | 1312.2 | 68.93% | 60.82%
Village Road by BC | 60 | 40 | 103.334 | 0 | 0 | 5167.762 | 1353.726 | 49.13% | 26.2%
Village Road by HBB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Upazila Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 3 | 3 | 0 | 72 | 0 | 478.439 | 64 | 15% | 13.38%
Maintenance | 10 | 9 | 20.783 | 0 | 0 | 545.564 | 369.864 | 87.27% | 67.79%
GC-Hat | 2 | 2 | 0 | 0 | 2 | 40.464 | 40.338 | 100% | 99.69%
Landing/ Riverghat | 1 |  | 0 | 0 | 1 | 0 | 0 | 0% | #DIV/0!
Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 103 | 76 | 187.277 | 72 | 3 | 9991.419 | 3823.212 | 39.47% | 38.26%