## Jessore
JESSORE
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Jessore Sadar
1 | 241472009-Improvement of Rupdia GC-Basundia Moor RHD via Shakarigati Road. From Ch:1100-3360m & 3970-4420m. [Salvage Cost. Tk.37,85,349.00] | KDRIDP/Jess/W-81/2017-18 | 2.71 | 0 | 0 | 263.11 | [8 empty] | 0 | #DIV/0!
2 | 241472012-Razarhat GC-Hamidpur RHD Road | [13 empty] | 0 | #DIV/0!
3 | 241472013-Jongle Bandle RHD-Basundia GC Road | [13 empty] | 0 | #DIV/0!
4 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch: 7500-9350m. [Salvage Cost Tk. 28,17,772.00 ] | KDRIDP/Jess/W-14/2016-17 | 1.85 | 0 | 0 | 128.13 | 2017-05-29 | M/S Morol Enterprise Balia, Vakutia Bazar, Sadar, Jessore | 2017-12-07 | 128.11 | 100% | 2018-06-19 | 127.802 | 127.802 | 0 | 99.76% | Final
5 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch:10416-11460m under Upazila: Sadar, District: Jessore. | KDRIDP/Jess/W-82/2017-18 | 1.044 | 0 | 0 | 78.89 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore | 2018-06-10 | 82.83 | 100% | 2019-05-07 |  | 27.2 | -27.2 | 32.84%
Bagherpara
6 | 241092006-Simakhali RHD-Narikelbaria GC Rd. | [13 empty] | 0 | #DIV/0!
7 | 241092011-Dhalgram GC- Maijpara UP to Kalukhali | [13 empty] | 0 | #DIV/0!
8 | 241092014-Improvement of Narikelbaria GC Bunagati GC (Shersha Sarak) Road. From Ch: 700-3270m. [salvage Cost Tk.20,890.00] | KDRIDP/Jess/W-96/2017-18 | 2.57 | 0 | 0 | 199.065 | 2018-08-20 | M/S Biswas Construction, Puraton Kashba, Jashore | 2018-10-18 | 208.998 | 20% | 2019-07-25 |  | 27.88 | -27.88 | 13.34%
9 | 241092018 Improvement of Narikelbaria GC - Monohorpur Bazar RHD at Joynagor More via Raypur UP (Bagherpara Part) Road. From Ch: 406-4144m,5400-5987m & 6372-7057m. [salvage Cost Tk.95,88,834.00] | KDRIDP/Jess/W-67/2017-18 | 5.01 | 0 | 0 | 396.55 | 2018-07-12 | Rafia Construction Ltd, Brammonkandi,Sreeongon,Faridpur. | 2018-09-06 | 436.16 | 50% | 2019-07-22 |  | 91.86 | -91.86 | 21.06%
Abhoynagar
10 | 241042005-Nowapara Upazila H/Q (Sankerpasha Bazarghat)-Amtala GC via Vatpara Bazar Rd. | [13 empty] | 0 | #DIV/0!
11 | 241042012-Nowapara GC (Shankerpasha Ghat)-Gobra GC via Borni Bazer road From Ch. 293-2845m [Salvage Cost Tk. 46,26,515.00] | KDRIDP/Jess/W-76/2017-18 | 2.552 | 0 | 0 | 199.92 | 2018-02-19 | Md. Abdur Rouf Molla, Bhoakhali, Ratangonj, Narail | 2018-04-18 | 177.14 | 100% | 2018-01-09 |  | 124.566 | -124.566 | 70.32%
12 | 241042012-Improvement of Nowapara GC (Shankerpasha Ghat)-Gobra GC via Borni Baze Road By BC From Ch. 8073-9098m. [salvage Cost Tk.25,44,253.00] | KDRIDP/Jess/W-126/2018-19 | 1.025 | 0 | 0 | 103.02 |  |  |  | 97.87 |  |  |  |  | 0 | 0%
Jhikargacha
13 | 241232012 : Navaran puraton Bazar-Seordah GC Road. | [13 empty] | 0 | #DIV/0!
14 | 241232015-Improvement of Jhikargacha Thana Hospital more to Goaldha Bazar via Padmapukur Kashipu Road By BC From Ch. 4650 - 6560m | KDRIDP/Jess/W-138/2018-19 | 1.91 | 0 | 0 | 209.6 | [8 empty] | 0 | #DIV/0!
15 | 241232016 : Hazirbag UZR-Matikumra UZR via Hazirbag UPC & MatiKumra Bazar. | [13 empty] | 0 | #DIV/0!
Monirampur
16 | 241612008-Monirampur-Mukterpur Road | [13 empty] | 0 | #DIV/0!
17 | 241612018-Dighirpar-Dumurkhali Bazar Road | [13 empty] | 0 | #DIV/0!
Sarsa
18 | 241902004-Improvement of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra Road From Ch.5064-7300m, 8725-9225m & 12150-15397m. [Salvage Cost Tk.18,35,766.00] | KDRIDP/Jess/W-33/2017-18 | 5.983 | 0 | 0 | 436.357 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 419.76 | 100% | 2019-05-30 |  | 295.98 | -295.98 | 70.51%
Keshabpur
19 | 241382005 Improvement of Chingra-Rajgonj via Trimohani UP (Keshabpur Portation) Road From Ch. 12600-13440m | KDRIDP/Jess/W-99/2017-18 | 0.8 | 0 | 0 | 68.496 | 2018-05-27 | M/S Alom Enterprise Bagda, Keshabpur, Jessore | 2018-08-07 | 71.9 | 100% | 2019-04-14 | 71.874 | 71.874 | 0 | 99.96% | Final
20 | 241382009 Mongalkot UP-Saraskati bazar | [13 empty] | 0 | #DIV/0!
Total |  |  | 25.454 | 0 | 0 | 2083.138 |  |  |  | 1622.768 | 81.43% |  | 199.676 | 767.162 | -567.486 | 47.27%
Improvement of Union Road by BC
Jessore Sadar
1 | 241473003-Improvement of Lebutala UP Office-Shyamnagar via Fultola Bazar Road. From Ch:5423-7723m & 9450-10236m. [Salvage Cost. Tk.55,29,697.00] | KDRIDP/Jess/W-119/2018-19 | 3.086 | 0 | 0 | 254.02 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 11/09/2018
2 | 241473005-Upashahor UP-Dolennagar Bazar Rd via Kashimpur Rd. | [13 empty] | 0 | #DIV/0!
3 | 241473007-Chanchra UP office-Kuadah Bazar via Sarapol Rd. | [13 empty] | 0 | #DIV/0!
4 | 241473010-Improvement of Chanchra Bazar-Chanchar UP via Vaturia(Jessore Khulna Hogway Beltolarmore Bormonpara Nodermore via Chanchra High School) Road. From Ch:00-1300m. [Salvage Cost. Tk.12,59,686.00] | KDRIDP/Jess/W-101/2017-18 | 1.3 | 0 | 0 | 86.959 | 2018-06-29 | Md Harun or Rashid, Nowapara Road, Ghop,Kotoali, Jessore. | 2018-09-05 | 91.297 | 100% | 2019-12-05 | 91.28 | 91.28 | 0 | 99.98% | Final
5 | 241473010-Improvement of Chanchra Bazar-Chanchar UP via Vaturia (DPP Name: Jessore-Khulna road Beltala more - Chasria High School) Road By BC From Ch:1300-3260m under Upazila: Sadar, District: Jessore. [Salvage Cost. Tk.24,10,020.00] | KDRIDP/Jess/W-127/2018-19 | 1.96 | 0 | 0 | 155.77 | 2019-04-23 | Md Harun or Rashid |  | 153.799 | 0%
6 | 241473011-Improvement of Natunhat-Deara UP office via Dattopara Road By BC From Ch:2980-4980m [Salvage Cost. Tk.21,89,721.00] | KDRIDP/Jess/W-144/2018-19 | 2 | 0 | 0 | 148.4 | [8 empty] | 0 | #DIV/0!
7 | 241473019-Arabpur UP Office-Faridpur Old Bazar Rd. | [13 empty] | 0 | #DIV/0!
8 | 241473020-Haibatpur UP-Ambottola via Kamalpur, Shahabajpur Rd. | [13 empty] | 0 | #DIV/0!
9 | 241473021-Improvement of Churamonkati UP Office-Khojar Hat Rd (Kashimpur UP) Road By BC From Ch:2000-2750m under Upazila: Sadar, District: Jessore. [Salvage Cost. Tk.18,24,040.00] | KDRIDP/Jess/W-143/2018-19 | 0.75 | 0 | 0 | 52.404 | [8 empty] | 0 | #DIV/0!
| 241473031-Improvement of Pulerhat - Arabpur UP (Mondalgati) Road By BC From Ch:2050-3052m. [Salvage Cost. Tk.7,89,600.00] |  | 1.002 | 0 | 0 | 65.594 | [8 empty] | 0 | #DIV/0!
10 | 241473022-Fatehpur UP Office-Bablatola Bazar Rd. | [13 empty] | 0 | #DIV/0!
11 | 241473024-Labutola UP-Andolpota via Agrail, Enayetpur Rd. | [13 empty] | 0 | #DIV/0!
12 | 241473025-Improvement of Lawjani Bazar-Deeara UP Office via Narangali Bazar Road By BC From Ch:1500-2575m | KDRIDP/Jess/W-145/2018-19 | 1.075 | 0 | 0 | 86.046 |  |  |  | 81.744 |  |  |  |  | 0 | 0%
13 | 241473030-Ichali UP (Bangda more) - Labutala Bazar via Rajapur (RHD) . | [13 empty] | 0 | #DIV/0!
14 | 241473001-Improvement of Chowlia Gate-Sutighata Ramnagar UP Office Road. From Ch:2660-4255m. [Salvage Cost. Tk.37,44,628.00] | KDRIDP/Jess/W-68/2017-18 | 1.595 | 0 | 0 | 107.517 | 2018-05-28 | M/S Jamuna Prokousoli, Hatkhola Road, Jessore | 2018-06-24 | 112.87 | 100% | 2019-03-30 | 112.808 | 112.808 | 0 | 99.95% | Final
Bagherpara
15 | 241093003-Bandabila UP- Puinerhat | [13 empty] | 0 | #DIV/0!
16 | 241093008-Improvement of Joharpur up office-Betalpara Bazar Road. From Ch: 1900-3250m. [salvage Cost Tk.5,096.00] | KDRIDP/Jess/W-97/2017-18 | 1.35 | 0 | 0 | 99.547 | 2018-05-21 | M/S Monir Traders Natun Khayertala, Jessore | 2018-06-24 | 104.5 | 100% | 2019-03-30 |  | 42.81 | -42.81 | 40.97%
| 241093010-Improvement of Raipur UP Office-Vater bazar Road. From Ch: 3611-3997m & 4689-5620m. [salvage Cost Tk.24,19,116.00] |  | 1.317 | 0 | 0 | 87.845 |  |  |  | 92.22 |  |  |  | 37.78 | -37.78 | 40.97%
17 | 241093013-Vangura RHD.-Dhalgram UP Rd. | [13 empty] | 0 | #DIV/0!
18 | 241093014-Improvement of Vangura RHD.-Basundia UP. Road. From Ch: 4778-6204m [salvage Cost Tk.9,02,090.00] | KDRIDP/Jess/W-132/2018-19 | 1.426 | 0 | 0 | 110.7 | [8 empty] | 0 | #DIV/0!
19 | 241093017-Simakhali UP- Johurpur UP via Betalpara Bazar, Premchara. | [13 empty] | 0 | #DIV/0!
20 | 241093018-Dhalgram UP- Garerhat Bazar via Antaikhola | [13 empty] | 0 | #DIV/0!
Abhoynagar
21 | 241043002-Improvement of Chengutia Bazar-Sreedharpur UP Office Road From Ch. 1217-3600m | KDRIDP/Jess/W-01/2016-17 | 2.383 | 0 | 0 | 144.16 | 2017-05-15 | Md. Abdur Rouf Molla , Bhoakhali, Ratangonj, Narail | 2017-07-06 | 150.3 | 100% | 2018-04-30 | 150.285 | 150.285 | 0 | 99.99% | Final
22 | 241043004-Nowapara H/Q (Peer Bari Kheya ghat)-Baghutia U.P. Office via Maddhapur Pry.School ,Bogratala Mosque & Chow matha,Vatpara Gramin Bank Road. | [13 empty] | 0 | #DIV/0!
23 | 241043006-Paira U.P.Office-Chalisha U.P.Office (Bagdah Dharmatala Eid-gah) via Kuta madrasha,Bagdah Paschimpara Baltala More Road. | [13 empty] | 0 | #DIV/0!
24 | 241043007-Sundali U.P.Office-Moshihati Bazar Road. | [13 empty] | 0 | #DIV/0!
25 | 241043010-Baghutia UP office-Singari Bazar via Singari Dakhil Madrasha Road. | [13 empty] | 0 | #DIV/0!
26 | BTMC ghat -Barni Bazar via Sreedarpur UP Complex Road. | [13 empty] | 0 | #DIV/0!
Chowgacha
27 | 241113003:( Singahjhully UP Office-Rashtampur bazar via Koyarpara Road.) | [13 empty] | 0 | #DIV/0!
28 | 241113005-Improvement of Nimtala bazar-Pasapole bazar via Pasapole UP Office Road Ch: 3120-3520m & 4020-4120 m [Salvage Cost Tk. 2,65,830.00] | KDRIDP/Jess/W-117/2018-19 | 0.5 | 0 | 0 | 37.085 | 2019-03-24 | A.M & T SARKAR CONSTRUCTION, Holding No-81, Kalitola, Chowgacha,Jashore | 2019-04-25 | 35.23 | 30% | 2019-02-12 |  |  | 0 | 0% | Tender will be Recceived on Dated 25/06/2018
29 | 241113008-Improvement of Shingo jhuli UP-Marua bazar Road. From Ch:3000-3495 m. | KDRIDP/Jess/W-16/2017-18 | 0.495 | 0 | 0 | 28.22 | 2017-08-07 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-02 | 29.57 | 100% | 2018-08-13 | 29.573 | 29.573 | 0 | 100% | Final
30 | 241113012- Improvement of Jogodishpur-Arpara GC Road From Ch: 2025-3525m. | KDRIDP/Jess/W-91/2017-18 | 1.5 | 0 | 0 | 89.331 | 2018-04-18 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-05-24 | 93.67 | 100% | 2019-02-24 | 93.645 | 93.645 | 0 | 99.97% | Final
31 | 241113013-Swarupda UP-Sukpukuria U.P Office Rd. | [13 empty] | 0 | #DIV/0!
32 | 241113016-Swarupda UP Office-Kharincha Bazar Road. | [13 empty] | 0 | #DIV/0!
33 | 241113020- Solua GCCR-Pashapole UP Office Road. | [13 empty] | 0 | #DIV/0!
Jhikargacha
34 | 241233001-Improvement of Parbazar-Chutipur bazar (Gongganandapur UP) Road From Ch. 5775 - 9925m | KDRIDP/Jess/W-49/2017-18 | 4.15 | 0 | 0 | 290.13 | 2018-03-13 | M/S Monir Traders Natun Khayertala, Jessore | 2018-04-04 | 316.09 | 80% | 2019-06-04 |  | 202.85 | -202.85 | 64.17%
35 | 241233002-Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP) Rd. | [13 empty] | 0 | #DIV/0!
36 | 241233004 : Improvement of Lawjani bazar-Jhikargacha Katakhal bazar(Shahid Rafique Sarak) Road From Ch. 00 - 162m & 600-1750m | KDRIDP/Jess/W-47/2017-18 | 1.312 | 0 | 0 | 82.48 | 2017-10-30 | M/S Monir Traders Natun Khayertala, Jessore | 2017-11-30 | 79.39 | 100% | 2018-12-31 | 78.314 | 78.314 | 0 | 98.64% | Final
37 | 241233006 : Improvement of Seordah GC-Moheshpara Road From Ch. 3750 - 6350m | KDRIDP/Jess/W-48/2017-18 | 2.6 | 0 | 0 | 146.91 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 140.85 | 100% | 2019-01-14 | 138.39 | 138.39 | 0 | 98.25% | Final
38 | 241233008 : Bakra UP-Jhapa (Bridge) Bazar | [13 empty] | 0 | #DIV/0!
39 | 241233009 : Bakra bazar(Bakra UP)-Matshia bazar. | [13 empty] | 0 | #DIV/0!
40 | 241233012 : Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More. Road From Ch. 6460 - 8350m. [Salvage Cost Tk. 6,982.00] | KDRIDP/Jess/W-83/2017-18 | 1.89 | 0 | 0 | 151.4 | 2018-06-25 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2018-08-20 | 145.02 | 30% | 2019-07-26 |  |  | 0 | 0%
41 | 241233012 : Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More. Road From Ch. 1000 - 1915m | KDRIDP/Jess/W-139/2018-19 | 0.915 | 0 | 0 | 71.56
| 241233029 : Improvement of Jhikargacha GC-Jhikargacha UP(Lawjani Bazar) Road By BC From Ch. 2770 - 3668m. [Salvage Cost Tk. 5,58,102.00] |  | 0.898 | 0 | 0 | 77 | [8 empty] | 0 | #DIV/0!
42 | 241233013 : Improvement of Magura New Market-Magura UP office Road From Ch. 492 - 1300m [Salvage cost Tk. 2,37,171.00] | KDRIDP/Jess/W-50/2017-18 | 0.81 | 0 | 0 | 54.34 | 2017-10-30 | MD. Humayun Kabir Nobarakpur, Jhikorgacha, Jessore | 2017-11-30 | 49.06 | 100% | 2018-04-22 | 45.885 | 45.885 | 0 | 93.53% | Final
43 | 241233017 : Godkhali UP-Bodhkhana bazar | [13 empty] | 0 | #DIV/0!
44 | 241233018 : Improvement of Barbakpur bazar-Simulia UP Road From Ch. 00-1150m. | KDRIDP/Jess/W-51/2017-18 | 1.15 | 0 | 0 | 75.47 | 2017-10-26 | M/S Jamuna Prokousoli Hatkhola Road, Jessore | 2017-12-12 | 75.17 | 100% | 2018-09-16 | 75.129 | 75.129 | 0 | 99.95% | Final
45 | 241233024 : Shimulia UP-Gorpara GC | [13 empty] | 0 | #DIV/0!
46 | 241233025 : Godkhali bazar-Panishara UP(Borni bazar). | [13 empty] | 0 | #DIV/0!
47 | 241233026: Improvement of Shimulia UP-Godkhali bazar Road By BCFrom Ch. 00 - 1430m. [Salvage Cost Tk. 1,51,081.00] | KDRIDP/Jess/W-128/2018-19 | 1.43 | 0 | 0 | 125.099 | 2019-04-01 | Md.Lutfor Rahman, Bagdah, Keshabpur, Jessore | 2019-05-21 | 118.844 | 0% | 2020-01-05 |  |  | 0 | 0%
48 | 241233027 : Shimulia UP-Navaran UP (at Kalagachi RHD). | [13 empty] | 0 | #DIV/0!
49 | 241233028 : Lawjani Bazar(Jhikargacha UP)-Naranggali bazar(Sadar) | [13 empty] | 0 | #DIV/0!
Monirampur
50 | 241613001-Improvement of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 3500-6420m | KDRIDP/Jess/W-03/2016-17 | 2.92 | 0 | 0 | 176.63 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-06-01 | 168.71 | 100% | 2018-04-26 | 168.67 | 168.67 | 0 | 99.98% | Final
51 | 241613001-Improvement of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road by BC From Ch. 7390-7580m& 8703-10690m [Salvage Cost Tk. 25,86,180.00] | KDRIDP/Jess/W-122/2018-19 | 2.177 | 0 | 0 | 191.05 |  | M/S SARDER INTERNATIONAL, Jessore | 2019-04-23 | 181.5 | 0% |  |  |  | 0 | 0%
52 | 241613002-Chalkidanga Bazar-Rohita UP via Kashimnagar UP Road | [13 empty] | 0 | #DIV/0!
53 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia Road | [13 empty] | 0 | #DIV/0!
54 | 241613006-mprovement of Chalkidanga Bazer-Haridashkati UP via Joypur bazar Road From Ch. 4371-5800m | KDRIDP/Jess/W-44/2017-18 | 1.429 | 0 | 0 | 92.44 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 91.41 | 100% | 2018-07-15 | 89.63 | 89.63 | 0 | 98.05% | Final
55 | 241613009-Improvement of Nehalpur UP-Hazirhat bazar via Kultia UP Road From Ch. 00-3557m | KDRIDP/Jess/W-04/2016-17 | 3.557 | 0 | 0 | 231.18 | 2017-10-22 | M/S Motinur Rahaman Nannu, 57, Chalk Bazar, Faridpur | 2017-11-16 | 250.7 | 100% | 2018-02-12 | 250.65 | 250.65 | 0 | 99.98% | Final
56 | 241613011-Improvement of Sundalpur bazar-Haridashkati UP via Salimpur Road From Ch. 9050-10920m. [Salvage Cost Tk. 1,73,331.00] | KDRIDP/Jess/W-103/2017-18 | 1.87 | 0 | 0 | 137.89 | 2018-08-26 | M/S Hira construction Main Road, Monirampur, Jessore | 2018-10-15 | 143.39 | 100% | 2019-03-09 |  | 100.27 | -100.27 | 69.93%
| 241613019-Improvement of Khanpur UP-Horidaskati UP Road From Ch. 2550-3380m. [Salvage Cost Tk. 13,90,230.00] |  | 0.83 | 0 | 0 | 61.04 |  |  |  | 63.475 |  |  |  | 44.38 | -44.38 | 69.92%
57 | 241613012-Improvement of Bhojgati UP-Dhakuria UP via Horergati Road From Ch. 1000-4810m. [Salvage Cost Tk. 3,63,209.00] | KDRIDP/Jess/W-121/2018-19 | 3.81 | 0 | 0 | 313.166 | 2019-04-15 | M/S BISWAJIT Constroction, 9 Rail Road, Jessore | 2019-06-20 | 316.577 | 0% | 2020-10-05 |  |  | 0 | 0%
58 | 241613013-Improvement of Tangramari-Khedapara U.P.via Jalalpur Road From Ch. 00-2120m. [Salvage Cost Tk. 54,342.00] | KDRIDP/Jess/W-77/2017-18 | 2.12 | 0 | 0 | 151.21 | 2018-05-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-06-24 | 155.72 | 100% | 2019-04-07 |  | 84 | -84 | 53.94%
59 | 241613014-Shyamkur Up-Chandipur via Lakkanpur Road | [13 empty] | 0 | #DIV/0!
60 | 241613016-Improvement of Muragacha-Horihornagor U.P.via Modonpur Road From Ch. 1000-2695m. [Salvage Cost Tk. 13,90,230.00] | KDRIDP/Jess/W-45/2017-18 | 1.695 | 0 | 0 | 116.18 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 111.33 | 100% | 2018-03-09 |  | 99.4 | -99.4 | 89.28%
61 | 241613022-Nangro Bazar - Rashulpur via Jamtala Rd. | [13 empty] | 0 | #DIV/0!
Keshabpur
62 | 241383004 Improvement of Biddanandakati UP-Kabilpur RHD more Via Hasanpur Road From Ch. 00-2760m. [Salvage Cost Tk. 69,65,398.00] | KDRIDP/Jess/W-120/2018-19 | 2.76 | 0 | 0 | 222.597 | 2019-07-04 | M/S FEROZ ENTERPRISE, Gurdash Babu Lane, Jessor | 2019-06-19 | 206.288 | 0% | 2019-11-12 |  |  | 0 | 0% | Tender will be Recceived on Dated 04/07/2018
63 | 241383005- Improvement of Keshabpur Pilot High School-Gorvanga Bazar Road from Ch.46 00-5600m. [Salvage Cost Tk. 4,51,606.00] | KDRIDP/Jess/W-146/2018-19 | 1 | 0 | 0 | 74.264 |  |  |  | 70.551 |  |  |  |  | 0 | 0%
64 | 241383008 Biddanandakati UP-Jamalgong Bazar Via Parchakra Bazar | [13 empty] | 0 | #DIV/0!
65 | 241383009 Sagardari UP- Kabilpur GPS | [13 empty] | 0 | #DIV/0!
66 | 241383011-Improvement of Panjia UP-Hoder hat Road From Ch. 00-3200m. [Salvage Cost Tk. 47,27,475.00] | KDRIDP/Jess/W-07/2016-17 | 3.2 | 0 | 0 | 229.93 | 2017-08-16 | M/S Mohidul Islam, 13/A Rail Road, Rail Bazar, Jessore | 2017-09-27 | 224.98 | 100% | 2018-10-20 | 224.84 | 224.84 | 0 | 99.94% | Final
67 | 241383014-Panjia UP-Burali Bazar Rd. | [13 empty] | 0 | #DIV/0!
68 | 241383018 Improvement of Mangolkot UP-Buruli bazar Road From Ch. 2616-4016m. [Salvage Cost Tk. 25,250.00] | KDRIDP/Jess/W-08/2016-17 | 1.4 | 0 | 0 | 87.96 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-06-14 | 87.77 | 100% | 2018-05-20 | 87.727 | 87.727 | 0 | 99.95% | Final
Sarsa
69 | 241903001-Improvement of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.10665-13520m. [Salvage Cost Tk.21,87,707.00] | KDRIDP/Jess/W-36/2017-18 | 2.855 | 0 | 0 | 171.625 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 165.09 | 100% | 2018-10-15 | 164.97 | 164.97 | 0 | 99.93% | Final
70 | 241903003-Kuchia More (Ulashi UP)-Dhaldah road | [13 empty] | 0 | #DIV/0!
71 | 241903004-Improvement of Dehi Union H/Q-Shikerpur Bazar via Fulsar Road From Ch.4480-6190m. [Salvage Cost Tk.2,04,049.00] | KDRIDP/Jess/W-34/2017-18 | 1.71 | 0 | 0 | 103.175 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 99.25 | 100% | 2018-10-15 | 99.234 | 99.234 | 0 | 99.98% | Final
72 | 241903008-Improvement of Benapole G.C-Bahadurpur UP H/Q via Ghiba Road From Ch.2545-7000m | KDRIDP/Jess/W-35/2017-18 | 4.455 | 0 | 0 | 268.13 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 265.08 | 100% | 2019-05-30 |  | 153.45 | -153.45 | 57.89%
73 | 241903011-Goga Union H /Q-Khalshi bazar via Agrabhulat road. | [13 empty] | 0 | #DIV/0!
74 | 241903016-Bahadurpur Union H/Q-Sharbunghuda Bazar road. | [13 empty] | 0 | #DIV/0!
75 | 241473020 Dehi Union H/Q –Wapda Bazar upto Kashipur Rd | [13 empty] | 0 | #DIV/0!
76 | 241903017-Improvement of Ulashi Union H/Q-Jamtala Bazar Via Benekhori. Road by BC From Ch.1350-2500m | KDRIDP/ Jess/W-137/ 2018-19 | 1.15 | 0 | 0 | 93.655 |  |  |  | 88.972 |  |  |  |  | 0 | 0%
Total |  |  | 75.832 | 0 | 0 | 5350.109 |  |  |  | 4560.417 | 77.24% |  | 1901.03 | 2665.97 | -764.94 | 58.46%
Improvement of Village Road by BC
Jessore Sadar
1 | 241474002-Improvement of Haibathpur -Uttar Lolitadha Road. From Ch:1030-104m & 1180-2560m. [Salvage Cost. Tk.34,666.00] | KDRIDP/Jess/W-95/2017-18 | 1.39 | 0 | 0 | 102.107 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore | 2018-10-06 | 107.207 | 100% | 2019-03-14 | 106.7 | 106.7 | 0 | 99.53% | Final
2 | 241474003-New Khairtala R&H-Bahadurpur Rd. | [13 empty] | 0 | #DIV/0!
3 | 241474004-Khairrala Seed Office-Boalpur Rd. | [13 empty] | 0 | #DIV/0!
4 | 241474007-Sujalpur Muchipara-Faridpur old Bazar Rd. | [13 empty] | 0 | #DIV/0!
5 | 241474009-Improvement of Gopalpur-Rampur Pry. School Road. From Ch:2000-4105m. [Salvage Cost. Tk.3,68,686.00] | KDRIDP/Jess/W-69/2017-18 | 2.105 | 0 | 0 | 130.835 | 2018-08-27 | M/S Gazi Enterprise, Nutum Khaertala Road, Kotoali, Jashore. | 2018-10-15 | 136.92 | 60% | 2019-07-20 |  | 11.3 | -11.3 | 8.253%
6 | 241474015-Rudropur-Sarapole bazar Rd. | [13 empty] | 0 | #DIV/0!
7 | 241474017-Rupdia Jamtala R&HD- Rustompur Rd. | [13 empty] | 0 | #DIV/0!
8 | 241474020-Basundia bazar-Jogonnathpur Kheaghat Rd. | [13 empty] | 0 | #DIV/0!
9 | 241474021-Deapara-Ghop RHD Rd. | [13 empty] | 0 | #DIV/0!
10 | 241474052-Setarampur-Jhumjhumpur Rd. | [13 empty] | 0 | #DIV/0!
11 | 241474055-Improvement of Dhopakhola RHD-Durgapur Koyetpara Road By BC From Ch:1600-3175m | KDRIDP/Jess/W-141/2018-19 | 1.575 | 0 | 0 | 112 | [8 empty] | 0 | #DIV/0!
12 | 241474056-Improvement of Taragonj-Ramkrisnapur Road By BC From Ch:1000-2385m. [Salvage Cost. Tk.14,10,691.00] | KDRIDP/Jess/W-142/2018-19 | 1.385 | 0 | 0 | 101.944 | [8 empty] | 0 | #DIV/0!
| 241474027-Improvement of Muroli more R&HD-Kanitala Road By BC From Ch:1950-2800m. [Salvage Cost. Tk.6,31,704.00] |  | 0.85 | 0 | 0 | 66.48 | [8 empty] | 0 | #DIV/0!
13 | 241474063-Mondolgaty (Kholadanga)-Arabpur UP Office Rd. | [13 empty] | 0 | #DIV/0!
14 | Patan Paikpara-Chitra Bazar-Bagerpara road. | [13 empty] | 0 | #DIV/0!
15 | Monsefnagar village Biswas para Jame Mosque-Monsefnagar Secendary School rd. | [13 empty] | 0 | #DIV/0!
16 | 241475293 Enayetpur-Teerhat Road. via Kadir Para (H/O Minaz-Manikdihe-Dhaka rd) | [13 empty] | 0 | #DIV/0!
17 | 241475285 Narendropur Pucca Road to Narendropur High School Rd | [13 empty] | 0 | #DIV/0!
18 | 241475292 ahsania mission road | [13 empty] | 0 | #DIV/0!
Bagherpara
19 | 241094005-Indra- Azmeherpur | [13 empty] | 0 | #DIV/0!
20 | 241094010-Improvement of Narikelbaria (Salikha Upazila) – Paschima Das Para More Road. From Ch: 500-1300m | KDRIDP/Jess/W-98/2017-18 | 0.8 | 0 | 0 | 49.66 | 2018-08-20 | M/S. Hridoy Construction, 147 Ghop, Noapara, Kotwali,Jashore. | 2018-10-18 | 51.646 | 50% | 2019-07-24 |  |  | 0 | 0%
21 | 241094018-Satiantala bazar to RHD at Dadpur bazar via Sayed Mahmudpur | [13 empty] | 0 | #DIV/0!
22 | 241094020-Khanpur Bazer-Indra Bazer (Khanpur Freedom Fiter Gopal House-Rahaman House) Rd. | [13 empty] | 0 | #DIV/0!
23 | 241094028-Improvement of Paschima H/O Shariful - Dari Agra Via Napte More Road from Ch: 00-800m & 3132-3963m. [salvage Cost Tk.93,148.00] | KDRIDP/Jess/W-130/2018-19 | 1.631 | 0 | 0 | 116.9 | 2019-04-02 | M/S SHARIFUL ISLAM, Arappur, Jhenaidah | 2019-05-19 | 111.055 | 0% | 2020-02-25 |  |  | 0 | 0%
24 | 241094034-Kadamtola- Bandabila hat | [13 empty] | 0 | #DIV/0!
25 | 241095145-Punihar Battala- Sreerampur High School Rd. | [13 empty] | 0 | #DIV/0!
26 | 241095284-Improvement of Kundupara Senbari- Tapan Master house[Inventory Name ;-Narikelbaria Senbari - Narikelbaria North Para via Narikelpara kundupara Mandir] Road. From Ch: 00-710m. | KDRIDP/Jess/W-86/2017-18 | 0.71 | 0 | 0 | 63.405 | 2018-08-29 | M/S.Abdul Alim & Sons, Mohiram, Bagherpara, Jashore | 2018-10-11 | 66.1 | 60% | 2019-07-17 |  | 33.32 | -33.32 | 50.41%
27 | 241095127 Improvement of Madhyapara Mosque RHD (jessore-Narial)-Joka [Inventory Name ;-RHD Rashid Karimpur H/O Omar Molla Khalshi] Road. From Ch: 00-1696m. [salvage Cost Tk.25,76,452.00] | KDRIDP/Jess/W-93/2017-18 | 1.12 | 0 | 0 | 85.779 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 10/04/2018
28 | 241095285-Khetrapara School -Hablapara Shawkat's House Road. | [13 empty] | 0 | #DIV/0!
Abhoynagar
29 | 241044003-Improvement of Nowapara Betar South Corner R&H-Dumurtala via Dhopadi Road From Ch. 4175-5000m | KDRIDP/Jess/W-02/2016-17 | 0.825 | 0 | 0 | 51.38 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [5th Called]
30 | 241044004-Noapara North Bengal(Bengal Textile)-Gobindapur Thrimohony via Dhopapara primary school Road. | [13 empty] | 0 | #DIV/0!
31 | 241044006-Taltala-Gramtala via Ektarpur Road. | [13 empty] | 0 | #DIV/0!
32 | 241044010-Paira(Kota Eayler More)-Kuta Shoyailer ghat Road. | [13 empty] | 0 | #DIV/0!
33 | 241044018-Nowly Bazar-Hanorgari Ghat via Madhur Dokan Road. | [13 empty] | 0 | #DIV/0!
34 | 241044019-Rajghat R&H-Bakardanga via Gazipur Road. | [13 empty] | 0 | #DIV/0!
35 | 241044023-Bashuari more(UZR)-Suvarara River Ghat via Dighirpar road. | [13 empty] | 0 | #DIV/0!
36 | 241044024-Ichamoti UZR-Peruli Gc Rd. | [13 empty] | 0 | #DIV/0!
37 | 241044026-Arpara UZR(Prembag More)-Zialtala Bazar Road. | [13 empty] | 0 | #DIV/0!
38 | 241044035-Magura Gabukhali Collage-Joyanta via Dholergati school Road. | [13 empty] | 0 | #DIV/0!
39 | 241044036-Chengutia Baruari Mondir-Beel Road. | [13 empty] | 0 | #DIV/0!
40 | 241044043-Nowly High school UZR-Beelkul Totarmatha via Nowly Mollik bari Jame-Mosque & Biswas Bari Road. | [13 empty] | 0 | #DIV/0!
41 | 241044050-Barandi Fakirhat Bazar-Takerghat road via WAPDA Office. | [13 empty] | 0 | #DIV/0!
42 | 241045086-Ranaghati Khayghat - Bhugilhat Mor Rd. | [13 empty] | 0 | #DIV/0!
43 | 241045230-Nowly Biswas para-Mosque road. | [13 empty] | 0 | #DIV/0!
44 | 241045516-Improvement of Nowly Momin Biswas house - Mir Bari Tematha Road From Ch. 00-412m | KDRIDP/Jess/W-109/2018-19 | 0.412 | 0 | 0 | 31.977 | 2019-01-21 | M/S SHARIFUL ISLAM, Arappur, Jhenaidah | 2019-03-11 | 30.378 | 0% | 2019-07-25 |  |  | 0 | 0%
| 241045613-Improvement of Nowly Golamar Bari more-Tatultala Ghat Road From Ch. 00-500m [Salvage Cost Tk. 1,40,131.00] |  | 0.5 | 0 | 0 | 39.95 |  |  |  | 37.953 |  |  |  |  | 0 | 0%
45 | 241045406-Improvement of Bagutia Palpara Puja mondir- Mojibor house Road From Ch. 00-634m [Salvage Cost Tk. 58,042.00] | KDRIDP/Jess/W-107/2018-19 | 0.634 | 0 | 0 | 49.738 |  | M/S Biswajit Construction, 9 Rail Road, Jessore | 2019-01-08 | 47.25 | 0% | 2019-10-15 |  |  | 0 | 0%
| 241045188-Improvement of Baghutia Bridge-Baghutia Dhakinpara Mosque Road From Ch. 00-1550m. |  | 1.55 | 0 | 0 | 122.619 |  |  |  | 116.488 |  |  |  |  | 0 | 0%
46 | 241044022 Improvement of Abhoynagar Puraton Kheya Ghat-Shibnagor UZR(N/H/O Kalachand) via Bogratala Mosque Road From Ch.584-2560 m. [salvage Cost Tk. 3,17,894.00] | KDRIDP/Jess/W-110/2018-19 | 1.976 | 0 | 0 | 153.01 | 2018-11-20 | Sonali Bricks Manufacture, Nowapara, Abhoynagar, Jessore | 2019-01-15 | 145.36 | 40% | 2019-10-21 |  |  | 0 | 0%
47 | 241044062 Improvement of Horishpur Reg.Primary school-Magura G.C. via Ramsara chowmatha, shishutala Road From Ch. 2435-4130m. [salvage Cost Tk. 8,78,194.00] | KDRIDP/Jess/W-62/2017-18 | 1.695 | 0 | 0 | 117.66 | 2018-08-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-10-15 | 122.78 | 100% | 2019-05-20 | 122.71 | 122.71 | 0 | 99.94% | Final
48 | 241044069-Improvement of Gopinathpur Village-Dokhanpara Abdul Gofur khan shope-Batiul Nure Jame Mosque Road From Ch. 00-775m. [Salvage Cost Tk. 3,85,651.00] | KDRIDP/Jess/W-63/2017-18 | 0.775 | 0 | 0 | 53.47 | 2018-02-05 | B.M Rafiqul Islam, Dariyapur, Narial Sadar, Narial | 2018-03-12 | 57.49 | 60% | 2018-12-13 |  | 15.42 | -15.42 | 26.82%
49 | 241044066- Improvement of Bhabadha Sluice gate-Zamira UZR. Road From Ch.00-3160m [Salvage Cost Tk. 82,42,535.00] | KDRIDP/Jess/W-111/2018-19 | 3.16 | 0 | 0 | 239.59 | 2018-11-18 | M/S Joy Enterprise, 16 Hazi Abul Karim Road, Jessore | 2019-01-08 | 227.615 | 0% | 2019-10-15 |  |  | 0 | 0%
50 | 241045137- Improvement of Dattagati WAPDA Road near the house of Ashu babu- Dattagati East para Culvert Road From Ch. 00-290m [Salvage Cost Tk. 7,49,493.00] | KDRIDP/Jess/W-108/2018-19 | 0.29 | 0 | 0 | 22.079 | 2018-11-18 | M/S Jony Enterprise, 16 Hazi Abul Karim Road, Jessore | 2019-01-08 | 20.975 | 15% | 2019-10-10 |  |  | 0 | 0% | Tender will be Recceived on Dated 25/06/2018
| 241044039- Improvement of Takerghat-Kapalia bazar via Bhabadha Sluice gate, College & kalishakul Bazer Road From Ch. 3300-5300m [Salvage Cost Tk. 62,45,075.00] |  | 2 | 0 | 0 | 175.127 |  |  |  | 166.371 |  |  |  |  | 0 | 0%
Chowgacha
51 | 241114011-Guatoli UZR-Narayanpur UZR Rd | [13 empty] | 0 | #DIV/0!
52 | 241114025 Improvement of Dhuliani bazar-Shajadpur Road From Ch: 00-184m & 1728-2465m. [Salvage Cost Tk. 3,49,720.00] | KDRIDP/Jess/W-70/2017-18 | 0.921 | 0 | 0 | 71.65 | 2018-05-07 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-06-24 | 75.225 | 70% | 2019-03-30 |  | 50.5 | -50.5 | 67.13%
53 | 241114034-Improvement of Mosiurnagor Bazar-Bariali Road Ch: 371-1925m [Salvage cost Tk.19,93,248.00] | KDRIDP/Jess/W-115/2018-19 | 1.554 | 0 | 0 | 118.855 | 2019-03-24 | M/S RUBIA Enterprise, Khaertola Bazar, Jessore Sadar, Jessore. | 2019-04-25 | 112.91 | 10% | 2019-02-12 |  |  | 0 | 0%
54 | 241114037-Dhuliani road-Uzirpur Rd. | [13 empty] | 0 | #DIV/0!
55 | 241114049-Goyra-Mashila Road. | [13 empty] | 0 | #DIV/0!
56 | 241114063-Improvement of Arpara Bazer- Sarfarajpur Bazer via Kandi Road From Ch: 1120-2225m [Salvage cost Tk.6,63,400.00] | KDRIDP/Jess/W-89/2017-18 | 1.105 | 0 | 0 | 69.94 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-05-22 | 73.4 | 0% | 2019-02-24 |  |  | 0 | 0%
57 | 241114030-Improvement of Jahatabmunshir Vhagar Road. From Ch: 00-1000m | KDRIDP/Jess/W-29/2017-18 | 1 | 0 | 0 | 65.85 | 2017-09-06 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-15 | 69.13 | 30% | 2018-04-09 |  |  | 0 | 0%
58 | 241115048-Improvement of Karincha bazar-Madhabpur Burning Ghat Road Ch: 00-1807m. [Salvage Cost Tk. 42,70,739.00] | KDRIDP/Jess/W-131/2018-19 | 1.807 | 0 | 0 | 135.847 | [8 empty] | 0 | #DIV/0!
59 | 241115140-Dashpakia-Nawdaga Road. | [13 empty] | 0 | #DIV/0!
60 | 241115098-Improvement of Chanda Afra-Raynagor Road. From Ch: 1952-3182m. [Salvage Cost Tk.1,71,976.00 | KDRIDP/Jess/W-28/2017-18 | 1.23 | 0 | 0 | 73.49 | 2017-09-07 | M/S Jahid Hossain Kotchandpur Bus Stand Para, Jhenidah. | 2017-10-16 | 77.14 | 100% | 2018-12-20 | 77.007 | 77.007 | 0 | 99.83% | Final
61 | 241115098-Improvement of Chanda Afra-Raynagor Road From Ch: 00-520m under. [Salvage Cost Tk. 2,43,822.00] | KDRIDP/Jess/W-84/2017-18 | 0.52 | 0 | 0 | 33.23 | 2018-05-13 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore | 2018-06-24 | 34.89 | 100% | 2019-02-02 | 34.89 | 34.89 | 0 | 100% | Final
62 | 241115181-Improvement of Batikamari - Bundalitala Road [ Inventory Name: Batikamari Bhanga road- Batikamari village Road ] From Ch: 00-610m | KDRIDP/Jess/W-71/2017-18 | 0.61 | 0 | 0 | 43.865 | 2018-08-27 | M/S Renu Enterprise, Asrom Road, Kotoali, Jashore | 2018-10-17 | 45.576 | 100% | 2019-05-20 |  | 25.97 | -25.97 | 56.98%
63 | 241115030-Improvement of Bergobindapur- Math Road (Bergobindapur-Goalbari via Purbo Para) From Ch: 00-1000m. [Salvage Cost Tk. 3,41,285.00] | KDRIDP/Jess/W-58/2017-18 | 1 | 0 | 0 | 59.4 | 2018-03-12 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-04-18 | 62.45 | 100% | 2019-01-15 |  | 53.9 | -53.9 | 86.31%
64 | 241115079-Improvement of DMC Madrasha - Joynarar union Road. From Ch: 00 - 1130m. [Salvage Cost Tk. 4,91,285.00] | KDRIDP/Jess/W-12/2016-17 | 1.13 | 0 | 0 | 69.69 | 2017-05-12 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-08-06 | 72.54 | 40% | 2018-04-30 |  |  | 0 | 0%
65 | 241115079-Improvement of DMC Madrasha - Rainagar union Road From Ch:1130-2100 m. [Salvage Cost Tk.89,458.00] | KDRIDP/Jess/W-52/2017-18 | 0.97 | 0 | 0 | 65.46 | 2018-01-11 | M/D Jahid Hossain Kotchandpur Bus stand para, Jhenidah | 2018-02-07 | 68.73 | 100% | 2018-09-30 | 68.55 | 68.55 | 0 | 99.74% | Final
66 | 241115078-Improvement of Jhinaikundu-Jamira Road. From Ch: 00-1000m | KDRIDP/Jess/W-30/2017-18 | 1 | 0 | 0 | 57.77 | 2017-07-09 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2017-10-03 | 60.52 | 100% | 2018-02-09 | 60.523 | 60.523 | 0 | 100% | Final
67 | 241115078-Improvement of Jhinaikundu-Jamira Road From Ch: 1000-1535m. [Salvage Cost Tk. 66,223.00] | KDRIDP/Jess/W-74/2017-18 | 0.535 | 0 | 0 | 32.98 | 2018-05-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-06-18 | 34.627 | 100% | 2019-03-24 | 34.215 | 34.215 | 0 | 98.81% | Final
68 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 00-1000m. [Salvage Cost Tk. 2,61,184.00] | KDRIDP/Jess/W-24/2017-18 | 1 | 0 | 0 | 58.5 | 2017-08-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-10 | 60.88 | 30% | 2018-08-20 |  |  | 0 | 0%
69 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 1000-1340m. [Salvage Cost Tk. 19,597.00] | KDRIDP/Jess/W-114/2018-19 | 0.34 | 0 | 0 | 26.968 | 2019-03-24 | M/S Sun Enterprise, Chowgacha Bazar, Chowgacha, Jessore | 2019-05-14 | 25.62 | 10% | 2019-11-21 |  |  | 0 | 0%
| 241115271- Sayedpur Altab Mondol House-H/O Thandu Mondol via Mondol Para Jame Mosque Road. |  | 0.236 | 0 | 0 | 18.488 |  |  |  | 17.564 |  |  |  |  | 0 | 0%
70 | 241115199-Improvement of Fulsara Purbopara Madrasha- Abed ali house Road. From Ch:00-645 m [Salvage Cost Tk.1,61,285.00] | KDRIDP/Jess/W-17/2017-18 | 0.645 | 0 | 0 | 38.58 | 2017-08-06 | Md. Abdul Halim Kotchanpur, Jhenaidah | 2017-05-10 | 39.4 | 100% | 2018-08-25 | 39.4 | 39.4 | 0 | 100% | Final
71 | 241115207-Improvement of Fulshara Purbopara Village Road. From Ch: 00 - 680m. [Salvage Cost Tk. 8,37,415.00] | KDRIDP/Jess/W-13/2016-17 | 0.68 | 0 | 0 | 42.75 | 2017-05-15 | M/S Mim Enterprise, Gajirhat Road, Puraton Kosba, Jessore | 2017-11-06 | 42.94 | 60% | 2018-04-28 |  | 19.03 | -19.03 | 44.32%
72 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road. From Ch: 00-455m [Salvage Cost Tk. 1,45,870.00] | KDRIDP/Jess/W-26/2017-18 | 0.455 | 0 | 0 | 27.63 | 2017-08-21 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-15 | 28.98 | 100% | 2018-08-27 | 28.97 | 28.974 | -0.004 | 99.98% | Final
73 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road From Ch: 455-636m. | KDRIDP/Jess/W-87/2017-18 | 0.181 | 0 | 0 | 11.24 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-05-22 | 11.8 | 100% |  | 11.578 | 11.578 | 0 | 98.12% | Final
74 | 241115262-Improvement of Araddah Muktijuddah Abdur Sattar Mia House -Sibnagor village via Balidapara GPS Road. From Ch: 00-1140m. [Salvage Cost Tk.1,04,350.00] | KDRIDP/Jess/W-112/2018-19 | 1.14 | 0 | 0 | 85.11 | 2018-11-19 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2019-01-03 | 80.85 | 10% | 2019-10-10 |  |  | 0 | 0%
75 | 241115258-Improvement of Singojhuli Jhautala - Baruhati Road. From Ch: 00-1235m | KDRIDP/Jess/W-18/2017-18 | 1.235 | 0 | 0 | 71.51 | 2017-08-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-09-28 | 74.94 | 100% | 2018-05-31 | 74.644 | 74.644 | 0 | 99.61% | Final
76 | 241115131-Improvement of Dhakinsagor-Charabari via H/O Abdul Bari Road. From Ch: 00-1650m. [Salvage Cost. Tk. 62,601.00] | KDRIDP/Jess/W-22/2017-18 | 1.65 | 0 | 0 | 94.46 | 2017-08-21 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-10-03 | 99.06 | 100% | 2018-05-31 | 98.877 | 98.877 | 0 | 99.82% | Final
77 | 241115060-Improvement of Andulia-Doulatpur Road From Ch: 2327-3350m. [Salvage cost Tk.11,24,654.00] | KDRIDP/Jess/W-116/2018-19 | 1.023 | 0 | 0 | 73.384 | 2019-04-16 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2019-06-13 | 73.253 | 0% | 2020-01-30 |  |  | 0 | 0%
| 241114024-Improvement of Goribpur-Moshiuragor Road From Ch: 00-875m.[Salvage cost Tk. 35.104.00] |  | 0.875 | 0 | 0 | 65.448 |  |  |  | 65.33 |  |  |  |  | 0 | 0%
78 | 241115153-Improvement of Patibila UP - Hayetpur via Uttor Para Road. From Ch: 00-1000m [Salvage Cost Tk.5,65,304.00] | KDRIDP/Jess/W-23/2017-18 | 1 | 0 | 0 | 59.93 | 2017-08-18 | M/S Jamuma Prokousoli hatkhola Road, jessore | 2017-10-02 | 62.8 | 60% | 2018-08-28 |  |  | 0 | 0%
79 | 241115288-Improvement of Afra R&H road near H/O Mokbul via Karamot Ali Road. From Ch: 00-475m. [Salvage Cost Tk.3,08,590.00] | KDRIDP/Jess/W-20/2017-18 | 0.475 | 0 | 0 | 32.38 | 2017-10-19 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 33.54 | 5% | 2018-05-30 |  |  | 0 | 0%
80 | 241115296-Improvement of Durgabor Kathi Amir Ali H/O -Tatul Bari Korban Biswas H/O Road. From Ch: 00-587m. | KDRIDP/Jess/W-21/2017-18 | 0.587 | 0 | 0 | 37.45 | 2017-10-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-11-26 | 38.89 | 40% | 2018-02-06 |  |  | 0 | 0%
81 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid Road. From Ch: 00-1000m | KDRIDP/Jess/W-27/2017-18 | 1 | 0 | 0 | 62.74 | 2017-08-20 | M/S Sarkar Construction Lalbazar, Natore | 2017-10-10 | 64 | 100% | 2018-08-27 | 63.299 | 63.299 | 0 | 98.9% | Final
82 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid From Ch: 1000-1480m. [Salvage Cost Tk. 1,10,415.00] | KDRIDP/Jess/W-75/2017-18 | 0.48 | 0 | 0 | 30.22 | 2018-02-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-04-03 | 30.61 | 60% | 2018-11-19 |  | 4.65 | -4.65 | 15.19%
83 | 241115292-Improvement of Souila Arpara road near H/O Toffazial-Durabakati H/O Ismail Road. From Ch:00-350 m .[Salvage Cost Tk.1,94,990.00] | KDRIDP/Jess/W-19/2017-18 | 0.35 | 0 | 0 | 21.76 | 2017-10-17 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 21.458 | 100% | 2018-05-30 | 21.238 | 21.238 | 0 | 98.97% | Final
84 | 241115269-Improvement of Sayedpur Shek Para Abdur Razzak Shop- Purbo Mat Pucca Road From Ch: 00-1470m. [Salvage Cost Tk. 2,18,023.00] | KDRIDP/Jess/W-113/2018-19 | 1.47 | 0 | 0 | 113.21 | 2019-05-05 | Mortaza Reza, Krishnanagar, Jhikargacha, Jessore. |  | 107.55 | 0% |  |  |  | 0 | 0%
85 | 241115008-Improvement of Swruppur Hajambari-Bagdanga Road From Ch: 00-2200m. [Salvage Cost Tk. 6,84,966.00] | KDRIDP/Jess/W-118/2018-19 | 2.2 | 0 | 0 | 163.935 | 2019-04-08 | Md.Noor Islam, Purbobarandipara, Jessore | 2019-06-13 | 163.607 | 0% | 2019-10-14 |  |  | 0 | 0%
86 | 241115014-Improvement of Tazbizpur-Jatrapur Road From Ch: 864-2035m | KDRIDP/Jess/W-59/2017-18 | 1.171 | 0 | 0 | 71.695 | 2018-04-25 | M/S Renu Enterprise Asrom Road Jessore | 2018-05-24 | 75.25 | 100% | 2019-04-18 |  | 47.9 | -47.9 | 63.65%
87 | 241115286-Improvement of Anderkota Primary school-Panchbaria Beel Tematha BC Road From Ch:00-1075 m | KDRIDP/Jess/W-55/2017-18 | 1.075 | 0 | 0 | 58.92 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 63.028 | 100% | 2019-05-30 |  | 29.167 | -29.167 | 46.28%
88 | 241115044-Improvement of Baishagari BC Road - Hazrakhana Kadamtala BC Road via Anderkota, Batikamari Road. (Batkamari- Mohespur Road.)Road. From Ch:1500-2680m | KDRIDP/Jess/W-56/2017-18 | 1.18 | 0 | 0 | 70.706 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 75.649 | 100% | 2019-05-30 |  | 43.9 | -43.9 | 58.03%
89 | 241114026-Improvement of Kongsharipur-Mashila Road. From Ch: 2043-2198m & 4080-5510m | KDRIDP/Jess/W-57/2017-18 | 1.585 | 0 | 0 | 89.53 | 2018-03-12 | MD. Noor Islam. Purbo Barandipara, Jessore | 2018-04-17 | 95.72 | 100% | 2018-09-12 | 95.72 | 95.72 | 0 | 100% | Final
Jhikargacha
90 | 241234009 : Improvement of Fatepur-Bodhkhana bazar. Road By BC From Ch. 846 - 1303m | KDRIDP/Jess/W-140/2018-19 | 0.457 | 0 | 0 | 38.418 | [8 empty] | 0 | #DIV/0!
| 241235282-Improvement of Gongadharpur Israil's house-Palla Lutfor's house. Road By BC From Ch. 00 - 1000m under. [Salvage Cost Tk. 5,58,102.00] |  | 1 | 0 | 0 | 82.803 | [8 empty] | 0 | #DIV/0!
91 | 241234013 : Misrideara UZR Jamtala-Angarpara. | [13 empty] | 0 | #DIV/0!
92 | 241234035 : Improvement of Komarchanda-Nayra bazar Road From Ch. 00 - 925m | KDRIDP/Jess/W-06/2016-17 | 0.925 | 0 | 0 | 55.32 | 2017-07-03 | M/S Mysha Traders, 377/1, South Goran, Sabujbag, Dhaka-1219 | 2017-09-13 | 52.25 | 100% | 2018-05-31 | 52.207 | 52.207 | 0 | 99.92% | Final
93 | 241234052-Improvement of Digri bazar-Sadipu bazar Road From Ch.00-148 m | KDRIDP/Jess/W-15/2016-17 | 0.148 | 0 | 0 | 10.36 | 2017-07-27 | M/S Bakul Enterprise Pulerhat Bazar, Chanchara, Jessore | 2017-09-25 | 10.33 | 100% | 2018-03-14 | 10.33 | 10.33 | 0 | 100% | Final
94 | 241234071-Gongganandapur UP- Panditpur Rd. | [13 empty] | 0 | #DIV/0!
95 | 241235001 : Bishahari-Atulia UZR. | [13 empty] | 0 | #DIV/0!
96 | 241235012 : Magura UP Office-Magura UZR. | [13 empty] | 0 | #DIV/0!
97 | 241235028: Improvement of Nabibnagar RHD-Kamarpara GPS Road By BCFrom Ch. 826 - 1656m | KDRIDP/Jess/W-129/2018-19 | 0.83 | 0 | 0 | 63.7 | 2019-04-01 | Fayaz Enterprise, Jashore | 2019-05-21 | 60.515 | 0% | 2020-02-28 |  |  | 0 | 0%
98 | 241235031 : Kawria GPS More-Towra. | [13 empty] | 0 | #DIV/0!
Monirampur
99 | 241614005-Monirampur College-Debidaspur | [13 empty] | 0 | #DIV/0!
100 | 241614019-Improvement of Komolpur-Tazpur Road From Ch. 00-2000m [Salvage Cost Tk. 21,76,122.00] | KDRIDP/Jess/W-78/2017-18 | 2 | 0 | 0 | 143.17 | 2018-05-12 | Sayed Nahid Hassan Keshabpur Bazar, Keshabpur, Jessore | 2018-06-14 | 150.25 | 100% | 2019-05-11 |  | 103.62 | -103.62 | 68.97%
101 | 241614020-Improvement of Chandipur-Hanuar Amtala Road by BC From Ch. 00-2080m | KDRIDP/Jess/W-125/2018-19 | 2.08 | 0 | 0 | 170 |  |  |  | 164.04 |  |  |  |  | 0 | 0%
102 | 241614025-Improvement of Rajgonj Jamshed mill-Monohorpur Road From Ch. 1540-2106m. [Salvage Cost Tk. 51,999.00] | KDRIDP/Jess/W-41/2017-18 | 0.566 | 0 | 0 | 40.63 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 40.39 | 100% | 2019-06-28 | 40.367 | 40.367 | 0 | 99.94% | Final
103 | 241614041-Improvement of Mobarokpur Ghospara-Negura Bazar Road From Ch: 1895-3185m | KDRIDP/Jess/W-124/2018-19 | 1.29 | 0 | 0 | 105.34 | 2019-04-01 | M/s. Alom Enterprise, Keshobpur, Jessore | 2019-05-19 | 100.07 | 10% | 2020-05-01 |  |  | 0 | 0%
104 | 241614048-Fakirrasta-Keshabpur via Hashadanga | [13 empty] | 0 | #DIV/0!
105 | 241614066-Kharinci-Rohita Shaikpara | [13 empty] | 0 | #DIV/0!
106 | 241614079-Improvement of Kashimpur Battala-Rohita U.P Road From Ch. 1250-3200m. [Salvage Cost Tk. 1,59,608.00] | KDRIDP/Jess/W-80/2017-18 | 1.95 | 0 | 0 | 139.45 | 2018-07-29 | Md Harun or Rashid, Nowapara Road, Ghop,Kotoali, Jessore. | 2018-05-09 | 146.27 | 100% | 2019-11-06 | 94.06 | 94.06 | 0 | 64.31% | Final
107 | 241614100-Subalkati Edgah-Lawkunda Sr.Madrasha | [13 empty] | 0 | #DIV/0!
108 | 241614113-Improvement of Hazrakati Daspara More - Hazrakati Sanapara Road From Ch. 944-1985m. [Salvage Cost Tk. 1,86,215.00] | KDRIDP/Jess/W-42/2017-18 | 1.041 | 0 | 0 | 79.4 | 2017-10-29 | M/S Hira construction Main Road, Monirampur, Jessore | 2017-11-30 | 79.5 | 100% | 2018-12-30 | 78.944 | 78.944 | 0 | 99.3% | Final
109 | 241615035-Improvement of Parala-Satgati Road From Ch. 00-925m | KDRIDP/Jess/W-05/2016-17 | 0.925 | 0 | 0 | 61.07 | 2017-05-15 | M/S Hira Construction, Main Road Monirampur, Jessore | 2017-05-29 | 60.81 | 100% | 2018-04-28 | 59.575 | 59.575 | 0 | 97.97% | Final
110 | 241615071-Boalia Bazar-Uttarpara | [13 empty] | 0 | #DIV/0!
111 | 241615110-Improvement of Moshimnagor Charabattala-Vorotpur Road by BC From Ch. 1400-1650m. [Salvage Cost Tk. 1,04,669.00] | KDRIDP/Jess/W-123/2018-19 | 0.25 | 0 | 0 | 18.11 | 2019-03-28 | M/S. Diganta Enterprise, Agorhati, Laware, Monirumpur, Jessore | 2019-12-05 | 17.2 | 60% | 2020-02-19 |  |  | 0 | 0%
112 | 241614076-Improvement of 8 mile(RHD)-Khahimnagor U.P. Road From Ch. 00-1780m. [Salvage Cost Tk. 10,61,912.00] | KDRIDP/Jess/W-38/2017-18 | 1.67 | 0 | 0 | 131.55 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 130.25 | 100% | 2018-07-15 | 130.127 | 130.127 | 0 | 99.91% | Final
113 | 241615398-Improvement of Atghara purbopara - Amjamtola Road From Ch. 00-805m | KDRIDP/Jess/W-39/2017-18 | 0.805 | 0 | 0 | 57.11 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore | 2018-06-18 | 59.948 | 60% | 2019-05-05 |  | 24.8 | -24.8 | 41.37%
114 | 241614060-Improvement of Lakhanpur Mandartala-Gouripur FWC Road From Ch. 00-470m | KDRIDP/Jess/W-40/2017-18 | 0.47 | 0 | 0 | 34.81 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 34.96 | 100% | 2018-06-28 | 34.64 | 34.64 | 0 | 99.08% | Final
115 | Routia UP Bashdebpur bazar Torafdar Bostlay-Bashdebpur Dakil Madrasha & Attimkhana-Mathpara mono molla H/O road. | [13 empty] | 0 | #DIV/0!
116 | 241615185-Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 00-1000m. [Salvage Cost Tk. 83,892.00] | KDRIDP/Jess/W-53/2017-18 | 1 | 0 | 0 | 75.93 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore | 2018-06-18 | 79.7 | 60% | 2019-04-24 |  | 21.7 | -21.7 | 27.23%
117 | 241615185- Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 1000-2095m | KDRIDP/Jess/W-92/2017-18 | 1.095 | 0 | 0 | 77.93 | 2018-04-09 | M/S Sajan Enterprise Chanchara Cheakpost Jessore | 2018-03-06 | 81.827 | 100% | 2019-03-03 | 80.755 | 80.755 | 0 | 98.69% | Final
118 | 241615336-Parkhaajura-Baroypara more-Garidkhali road. | [13 empty] | 0 | #DIV/0!
Keshabpur
119 | 241384008 Satkira Chira mill-Habspol Madrasha | [13 empty] | 0 | #DIV/0!
120 | 241384022- Improvement of Dewli more-Dewli non Govt Primary School Road Ch. 980-1980m [Salvage Cost Tk. 5,18,512.00] | KDRIDP/Jess/W-148/2018-19 | 1 | 0 | 0 | 79.162 |  |  |  | 75.204 |  |  |  |  | 0 | 0%
121 | 241384025 Improvement of Dashkohonia Ruhul Amin House-Burili Rishipara Road From Ch. 1000-2705m. [Salvage Cost Tk. 7,35,719.00] | KDRIDP/Jess/W-09/2016-17 | 1.705 | 0 | 0 | 102.65 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-11-06 | 102.39 | 100% | 2018-04-14 | 102.3 | 102.299 | 0.001 | 99.91% | Final
122 | 241384026- Improvement of Satbaria Choudary Pond-Begompur more Road by BC From Ch. 600-2200m & 2300-2940m. [Salvage Cost Tk. 4,61,149.00] | KDRIDP/Jess/W-147/2018-19 | 2.24 | 0 | 0 | 170.459 | [8 empty] | 0 | #DIV/0!
123 | 241384030 Protappur – Attonda | [13 empty] | 0 | #DIV/0!
124 | 241384035 Boga-Mohadebpur road | [13 empty] | 0 | #DIV/0!
125 | 241384037 Borenga-Pancharoi | [13 empty] | 0 | #DIV/0!
126 | 241384038 Jhikra-baruihati (Kasta bazar-Sikerpur bazar road) | [13 empty] | 0 | #DIV/0!
127 | 241384043 Boga FRB-Vanderkhola Bazar | [13 empty] | 0 | #DIV/0!
128 | 241384050 Improvement of Bosuntia (Mongolkot bazar)-Baduria via Ramkrishnapur Road From Ch. 480-1125m | KDRIDP/Jess/W-10/2016-17 | 0.645 | 0 | 0 | 42.34 | 2017-05-15 | M/S Joy Enterprise, Keshabpur Bazar, Keshabpur, Jessore | 2017-11-06 | 42.29 | 100% | 2018-04-30 | 42.24 | 42.24 | 0 | 99.88% | Final
129 | 241384051 Jahanpur Jamtala more-Vallukghar Bazar road. | [13 empty] | 0 | #DIV/0!
130 | 241385019 Improvement of Kanderpur-Gater-hat(Bongshir Battala) Road From Ch. 1000-2485m | KDRIDP/Jess/W-11/2016-17 | 1.485 | 0 | 0 | 88.92 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-12-06 | 88.74 | 100% | 2018-04-30 | 88.68 | 88.68 | 0 | 99.93% | Final
131 | 241385022 Baliadanga-Gurvanga | [13 empty] | 0 | #DIV/0!
132 | 241385540-Improvement of Dohori Village C&B - Surindronath Mondal bari Road From Ch. 00-1100m. [Salvage Cost Tk. 6,41,862.00] | KDRIDP/Jess/W-94/2017-18 | 1.1 | 0 | 0 | 72.746 |  | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-06-24 | 76.369 | 42.5% | 2019-02-19 |  |  | 0 | 0%
| 241385541-Improvement of Gurdaga-Dong ghat H/O Mono Boso Road From Ch. 00-1000m. [Salvage Cost Tk. 79,300.00] |  | 1 | 0 | 0 | 68.33 |  |  |  | 71.73 |  |  |  |  | 0 | 0%
Sarsa
133 | 241904003-Bagarchara (GC)-Basatpur Bazar rd. | [13 empty] | 0 | #DIV/0!
134 | 241904015-Improvement of Chandrapur-Belta Ghat Road by BC From Ch.3360-5000m [Salvage Cost. Tk. 22,10,761.00] | KDRIDP/ Jess/W-135/ 2018-19 | 1.64 | 0 | 0 | 118.657 | [8 empty] | 0 | #DIV/0!
135 | 241904023-Improvement of Ulashi Debdar Tala-Jirengacha Road by BC From Ch.1439-3300m under Sarsha Upazila District Jessore [Salvage Cost. Tk. 8,91,495.00] | KDRIDP/ Jess/W-136/ 2018-19 | 1.861 | 0 | 0 | 136.86 | [8 empty] | 0 | #DIV/0!
136 | 241904024-Ulashi Bazar Mosjheed R&H-Kannyadah Bazar road. | [13 empty] | 0 | #DIV/0!
137 | 241904026-Improvement of Kagojpukur-Dubpara Road by BC From Ch.3300-3680m | KDRIDP/Jess/W-134/2018-19 | 0.38 | 0 | 0 | 35.693 | [8 empty] | 0 | #DIV/0!
| 241904061-Improvement of Bosotpur Madrasha-Baikola Road by BC From Ch.1667-3085m |  | 1.418 | 0 | 0 | 106.683 | [8 empty] | 0 | #DIV/0!
138 | 241904043-Trimohini-Kulpala via Bolidadah road | [13 empty] | 0 | #DIV/0!
139 | 241904046-Naihati-Dehi road. | [13 empty] | 0 | #DIV/0!
140 | 241904047-Improvement of Saratola High School-Tebaria Mosque via Daridurgapur Road by BC From Ch.1000-1805m. [Salvage Cost. Tk. 28,328.00] | KDRIDP/Jess/W-133/2018-19 | 0.805 | 0 | 0 | 72.15 | [8 empty] | 0 | #DIV/0!
| 241904002-Improvement of Ghiba Uttar para-Sharbunghuda bazar Road by BC From Ch.2000-2980m |  | 0.98 | 0 | 0 | 76.52 | [8 empty] | 0 | #DIV/0!
141 | 241904048-Sikerpur-Salta road. | [13 empty] | 0 | #DIV/0!
142 | 241904052-Ekjhala Bazar-Kondarpopur road. | [13 empty] | 0 | #DIV/0!
143 | 241904115-Golapole More-Keshadanga Village Rd. | [13 empty] | 0 | #DIV/0!
144 | 241905198- Improvement of Sibobash Khalil's House-Shalkona Primary School road Via Sahid Shangbadic Shamsur Rahman House Road From Ch.00-1440m [Salvage Cost. Tk. 3,68,361.00] | KDRIDP/Jess/W-37/2017-18 | 1.44 | 0 | 0 | 91.38 | 2017-10-17 | M/S Ashraf Traders Voirob stand, Haspatal Ghat, Khulna | 2017-12-26 | 95.041 | 100% | 2018-11-16 |  | 71.15 | -71.15 | 74.86%
Total |  |  | 96.999 | 0 | 0 | 6857.932 |  |  |  | 5505.519 | 65.8% |  | 1752.546 | 2308.876 | -556.33 | 41.94%
Improvement of Village Road by HBB
Jessore Sadar
1 | 241474005-Churmankati Rail gate-Dogachia Beel Rd. | [13 empty] | 0 | #DIV/0!
2 | 241474016-Hamidpur Kamar bari-Dhitila Rd. | [13 empty] | 0 | #DIV/0!
Bagherpara
3 | 241095221-Ramkrishnapur Bazar-Silumpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
Abhoynagar
4 | 241044060-Dhulgram Club-Siddipasha U.P.Office(Nowly Bazar) Rd. | [13 empty] | 0 | #DIV/0!
Chowgacha
5 | 241114038-Burinda-Dashpakia Rd. | [13 empty] | 0 | #DIV/0!
Jhikargacha
6 | 241234040-Nawali bazar-Kanarali bazar Rd. | [13 empty] | 0 | #DIV/0!
Monirampur
7 | 241614089-Khedapara U.P.-Kasipur Mandertala Rd. | [13 empty] | 0 | #DIV/0!
Keshabpur
8 | 241384046-Keshabpur UP-Shikerpur bazar Rd. | [13 empty] | 0 | #DIV/0!
Sarsa
9 | 241904105-Improvement of Nizampur Bazar-Bahadurpur Road From Ch.2643-4718m. [Salvage Cost Tk.45,344.00] | KDRIDP/Jess/W-32/2017-18 | 2.075 | 0 | 0 | 75.315 | 2017-10-17 | M/S Asraf Traders, Voirob Road, Haspatal Ghat, Khulna | 2017-12-26 | 75.3 | 100% | 2018-11-16 | 74.58 | 74.58 | 0 | 99.04% | Final
Total |  |  | 2.075 | 0 | 0 | 75.315 |  |  |  | 75.3 | 100% |  | 74.58 | 74.58 | 0 | 99.04%
Construction of Bridge on Union Road/Village Road (5.50m width)
Jessore Sadar
1 | 241473016-Construction of 22.00m Long RCC Girder Bridge on Satiantola Bazar-(Fulbari More) Ichali UP via Suro,Kamergona Road at Ch.2900m | KDRIDP/Jess/B-01/2018-19 | 0 | 22 | 0 | 214.928 | [8 empty] | 0 | #DIV/0!
2 | 241473002-Construction of 72.00m Long RCC Girder Bridge on Narendrapur UP-Dailala Bazar (over Dakua River) Road at Ch.100m | KDRIDP/Jess/B-02/2018-19 | 0 | 72 | 0 | 585.605 | 2019-03-28 | Kamarjani-Anowara JV, 15 no Shreeangan Market, Goalchamot, Faridpur | 2019-05-15 | 570.36 | 0% | 2020-03-14 |  |  | 0 | 0%
Monirampur
3 | 241613020-Const. of RCC Bridge on Dhakuria UP- Gabukhali Bazar Road | [13 empty] | 0 | #DIV/0!
4 | 241614070-Construction of 44.0m RCC Girder Bridge on Fakir Rasta-Pazia Road at Ch.500m | KDRIDP/Jess/W-31/2017-18 | 0 | 44 | 0 | 245.86 | 2017-10-23 | Kamarjani-Brojen-Anowara-JV, Sree Angoan, faridpur | 2017-11-30 | 221.27 | 100% | 2019-02-10 |  | 197.74 | -197.74 | 89.37%
5 | 241615002-Const. of RCC Bridge onMujguni-Durgapur | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 138 | 0 | 1046.393 |  |  |  | 791.63 | 50% |  | 0 | 197.74 | -197.74 | 24.98%
Maintenance
Jessore Sadar
1 | 241472012-Razarhat GC-Hamidpur RHD Rd. | [13 empty] | 0 | #DIV/0!
2 | 241472014-Churamankati GC-Kayemkhola GC via Bagdanga Jhowdia Bazar Chandutia Rd | KDRIDP/Jess/M-01/2017-18 | 2.805 | 0 | 0 | 120.728 | 2018-04-25 | M/S L Rahaman Enterprise R. N. Road, Jessore | 2018-10-06 | 126.76 | 50% | 2019-03-16 |  | 20.82 | -20.82 | 16.42%
3 | 241472017-Monohorpur Bazar RHD - Narikel Baria GC via Raipur UP ( sadar part) Road. | [13 empty] | 0 | #DIV/0!
4 | 241473002-Narendrapur UP-Daitala Bazar Rd. | [13 empty] | 0 | #DIV/0!
5 | 241473005-Periodic Maintenance of Upashahor UP - Tail kup Bazar Rd. Via Kashimpur, Dighirpar Road From Ch.00-1300m | KDRIDP/Jess/M-21/2017-18 | 1.33 | 0 | 0 | 62.36 | 2018-05-11 | M/S S S Traders Kazi Para, Puraton Koshba, Jessore | 2018-05-28 | 65.469 | 100% | 2019-02-03 | 65.469 | 65.469 | 0 | 100% | Final
6 | 241473007-Chanchra UP Office-Kuadah Bazar via Sarapol Rd. | [13 empty] | 0 | #DIV/0!
7 | 241473008-Bagerhat Bazar-Ramnagar UP Office Rd. | [13 empty] | 0 | #DIV/0!
8 | 241473009-Sannashi Bottala Bazar- Ramnagar UP Office Rd. | [13 empty] | 0 | #DIV/0!
9 | 241473010-Chanchara Bazar -Chanchar UP via Vaturia Rd. | [13 empty] | 0 | #DIV/0!
10 | 241473016-Periodic Maintenance of Satiantola Bazar- (Fulbari More) Ichali UP via Suro, Kamergona Road From Ch.00-2975m | KDRIDP/Jess/M-02/2017-18 | 2.975 | 0 | 0 | 73.158 | 2018-04-22 | M/S Dilip Enterprise, Calectorit Mosjid Market, Jessore | 2018-05-30 | 76.808 | 100% | 2019-02-20 | 76.79 | 76.79 | 0 | 99.98% | Final
11 | 241473028-Khajura(Bagherpara) GC-Barobazar(Kaligonj) GC Road via Labutola UP Rd. | [13 empty] | 0 | #DIV/0!
12 | 241474010-Periodic Maintenance of Basundia Bazar-Afraghat Ghat Road From Ch.00-2540m. | KDRIDP/Jess/M-04/2017-18 | 2.54 | 0 | 0 | 74.54 | 2018-04-23 | M/S Sharif Rabrul Enterprise Jail Road Ghop, Jessore | 2018-10-06 | 78.266 | 100% | 2019-01-30 | 78.26 | 78.26 | 0 | 99.99% | Final
13 | 241474012-R&H Rd. at Bijoynagar-Bolpur Ghat Rd. | [13 empty] | 0 | #DIV/0!
14 | 241474026-Periodic Maintenance of Pulerhat Shishu Aparad Centre-Vaturia Road From Ch.00-1400m | KDRIDP/Jess/M-03/2017-18 | 1.4 | 0 | 0 | 84.418 | 2018-04-24 | M/S Harun or Rashid Nowapara Road, Ghop, Jessore | 2018-03-06 | 88.45 | 100% | 2019-04-17 | 81.46 | 81.46 | 0 | 92.1% | Final
15 | 241474033-Bablatola Taxi Stand-Sarothi Mill Gabtola Rd. | [13 empty] | 0 | #DIV/0!
16 | 241474044-Nutunhat RHD-Bagerhat Rd. | [13 empty] | 0 | #DIV/0!
17 | 241475083-Beltola -Khmalpur Rd. | [13 empty] | 0 | #DIV/0!
Bagherpara
18 | 241092003-Jessore Narail RHD-Dhalgram more- Narikelbaria via Dhalgram Bazar Rd. | [13 empty] | 0 | #DIV/0!
19 | 241092011-Periodic Maintenance of Dhalgram GC.-Maijpara Up to Kalukhali Road From Ch.00-2265m | KDRIDP/Jess/M-26/2017-18 | 2.265 | 0 | 0 | 61.248 | 2018-05-11 | M/S Biswas Construction, 134 Dhaka Road, Puraton Kashba, Jessore | 2018-05-28 | 64.206 | 100% | 2019-02-03 | 64.153 | 64.153 | 0 | 99.92% | Final
Abhoynagar
20 | 241042005-Nowapara Upazila H/Q- Amtala GC via Vatpara Bazar Rd. | [13 empty] | 0 | #DIV/0!
21 | 241042009-Alipur RHD-Sundali GC via Rajapur more Ramsaradham, Arpara Clinic more, Harishpur RNGPS Rd. | [13 empty] | 0 | #DIV/0!
22 | 241043001-Noapara HQ(BTMC Ghat)-Borni Bazar via Sreedharpur UP Office | [13 empty] | 0 | #DIV/0!
23 | 241043007-Periodic Maintenance of Sundali U.P.Office-Moshihati Bazar Road From Ch.00-3050m | KDRIDP/Jess/M-07/2017-18 | 3.05 | 0 | 0 | 68.045 | [8 empty] | 0 | #DIV/0! | Tender will be Recceived on Dated 31/07/2018
24 | 241043009-Periodic Maintenance of Siddipasha UP Office (Nowly Bazer)-Phultala G.C. via Dhulgram kheya Ghat Road From Ch.00-2280m | KDRIDP/Jess/M-32/2018-19 | 2.28 | 0 | 0 | 76.566 | 2019-04-10 | M/S.Palash Enterprise, 1488, Buinkara, Nowapara, Abhaynagar, Jessore | 2019-05-19 | 72.738 | 0% | 2019-12-22 |  |  | 0 | 0%
25 | 241044005-Periodic Maintenance of Taltala Bazar-Dumortala road via Sirajkati,Chalishia Rishipara Chourasta More Road From Ch.00-5310m | KDRIDP/Jess/M-08/2017-18 | 5.31 | 0 | 0 | 162.81 | [8 empty] | 0 | #DIV/0!
26 | 241044017-Hidia Madrasha UZR- Kharoria Bazar Rd. | [13 empty] | 0 | #DIV/0!
27 | 241044039-Takerhat-Kapalia Bazarvia Bhabadha Sluicegate Collage & Kalishakul Bazar Rd. | [13 empty] | 0 | #DIV/0!
28 | 241044063-Rajapur More- Magura Madrasha more UZR via Sishutala Rd | [13 empty] | 0 | #DIV/0!
29 | 241044066-Bhabadha Sluicegate -Zamira UZR Rd. | [13 empty] | 0 | #DIV/0!
Chowgacha
30 | 241112008-Periodic Maintenance of Solua GC-Arpara GC Road From Ch.5500-7325m | KDRIDP/Jess/M-11/2017-18 | 1.825 | 0 | 0 | 60.646 | 2018-04-25 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore | 2018-06-24 | 63.678 | 100% | 2019-01-11 | 63.545 | 63.545 | 0 | 99.79% | Final
31 | 241112011-Purapara GC-Moheshpur Pucca road | [13 empty] | 0 | #DIV/0!
32 | 241113010-Periodic Maintenance of Debipur-Narayanpur GC Road From Ch.00-1260m. | KDRIDP/Jess/M-12/2017-18 | 1.26 | 0 | 0 | 30.358 | 2018-04-25 | M/S Sheba Traders Chowgacha Bazar, Chowgacha, Jessore | 2018-03-06 | 31.87 | 100% | 2019-03-03 |  |  | 0 | 0%
33 | 241113011-Periodic Maintenance of Chowgacha U.P-Dhuliani Via Bergobindapur Baor Road From Ch.275-1100m. | KDRIDP/Jess/M-13/2017-18 | 0.825 | 0 | 0 | 19.82 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 20.809 | 100% | 2018-11-30 | 20.8 | 20.799 | 0.001 | 99.95% | Final
34 | 241113014-Periodic Maintenance of Sukpukuria U.P-Andulia bazar Road From Ch.900-3680m | KDRIDP/Jess/M-14/2017-18 | 2.78 | 0 | 0 | 47.95 | 2018-09-27 | Md. Noor Islam, Purbo Barandipara, Jessore | 2018-10-16 | 50.232 | 100% | 2019-08-03 | 50.232 | 50.23 | 0.002 | 100% | Final
35 | 241113005-Nimtala Bazar-Pasapole Bazar via Pasapole UP Office Rd. | [13 empty] | 0 | #DIV/0!
36 | 241113017-Sukpukria UP Office -Goira Bazar Rd. | [13 empty] | 0 | #DIV/0!
37 | 241113013-Swarupda UP- Sukpukuria UO Office Rd. | [13 empty] | 0 | #DIV/0!
38 | 241114052-Chowgacha -Kabilpur Rd Mashampur more - Masila Bazar Rd | [13 empty] | 0 | #DIV/0!
39 | 241115022-Maligati -Bariali Rd. | [13 empty] | 0 | #DIV/0!
40 | 241114009(Roghonatpur-Dashpakhia bazar Road) | [13 empty] | 0 | #DIV/0!
41 | 241114014-Periodic Maintenance of Purapara Sonali Bank-Ballave pur Road From Ch.820-4900m | KDRIDP/Jess/M-16/2017-18 | 4.08 | 0 | 0 | 109.69 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 117.36 | 100% | 2018-11-30 | 117.361 | 117.361 | 0 | 100% | Final
42 | 241114024-Periodic Maintenance of Goribpur-Moshiuragor (Muktinagar ) via Jogonathpur Road From Ch.2375-3795m | KDRIDP/Jess/M-30/2018-19 | 1.42 | 0 | 0 | 63.47 | 2019-04-16 | Nishit Bosu, Kanchan nagar, Jhenaidah | 2019-05-30 | 60.3 | 0% | 2020-01-30 |  |  | 0 | 0%
43 | 241114026(Kongsharipur-Mashila Road). | [13 empty] | 0 | #DIV/0!
44 | 241114028-Periodic Maintenance of Kamlapur More-Mashila Bazar Road From Ch.00-1115m | KDRIDP/Jess/M-15/2017-18 | 1.15 | 0 | 0 | 28.174 | 2018-07-05 | Md. Noor Islam, Purbo Barandipara, Jessore | 2018-10-06 | 29.58 | 100% | 2019-01-30 |  | 22.95 | -22.95 | 77.59%
45 | 241114044Muktadah-Jagadishpur UP Road..) | [13 empty] | 0 | #DIV/0!
Jhikargacha
46 | 241232015-Jhikargacha Thana Hospital more- Goaldah Bazar via Padmapukur Kashipur Rd. | [13 empty] | 0 | #DIV/0!
47 | 241233001-Parbazar-Chutipur Bazar Rd. | [13 empty] | 0 | #DIV/0!
48 | 241233002-Periodic Maintenance of Navaran Puratan bazar- Chutipur bazar Gongganandapur UP) Road From Ch.9750-14750m | KDRIDP/Jess/M-24/2017-18 | 5 | 0 | 0 | 166.579 | 2018-10-04 | M/S Sarder International Gohata Road, Cityplaza Complex, Jessore | 2018-05-30 | 174.89 | 70% | 2018-10-19 |  | 56.68 | -56.68 | 32.41%
49 | 241233021-Sankarpur UP-Shamta Bazar RHD Rd. | [13 empty] | 0 | #DIV/0!
50 | 241233024-Periodic Maintenance of Shimulia UP-Gorpara GC Road From Ch.00-2401m. | KDRIDP/Jess/M-27/2018-19 | 2.401 | 0 | 0 | 82.317 | 2018-10-21 | M/S Mysha Traders, Jail Road, Jessore | 2019-03-01 | 78.2 | 65% | 2019-01-06 |  | 24.1 | -24.1 | 30.82%
Monirampur
51 | 241612011-Periodic Maintenance of Monirampur - Nowapara - Kultia -Nehalpur Road From Ch. 12410-12920m | KDRIDP/Jess/M-28/2018-19 | 0.51 | 0 | 0 | 25.869 | 2019-03-24 | M/S HIRA CONSTRACTION, Main road,Monirampur, Jessore | 2019-05-14 | 24.576 | 0% | 2019-11-17 |  |  | 0 | 0%
52 | 241612014-Periodic Maintenance of Monoharpur Bazar-Chinatola Bazar Road From Ch. 00-3900m [Salvage Cost Tk.5,14,017.00] | KDRIDP/Jess/M-18/2017-18 | 3.9 | 0 | 0 | 147.2 | 2018-08-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-10-15 | 161.07 | 100% | 2019-05-20 |  | 121.85 | -121.85 | 75.65%
53 | 241612015-Periodic Maintenance of Sundali Bazar-Dhakuria-Pramebag Gate Road From Ch. 5500-11920m. [Salvage Cost Tk.9,49,699.00] | KDRIDP/Jess/M-29/2018-19 | 6.42 | 0 | 0 | 292.7 |  |  |  | 261.123 |  |  |  |  | 0 | 0%
54 | 241612019-Periodic Maintenance of Nehalpur-Durbadanga-Bajitpur Road From Ch. 2830-8690m. [Salvage Cost Tk.7,61,457.00] | KDRIDP/Jess/M-17/2017-18 | 5.86 | 0 | 0 | 249.06 | 2018-05-16 | M/S Bonantor Trading Corporation Benapol Road Chanchara, Jessore | 2018-06-24 | 261.418 | 100% | 2019-03-30 |  | 202.06 | -202.06 | 77.29%
55 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia | [13 empty] | 0 | #DIV/0!
56 | 241233002 : Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP). | [13 empty] | 0 | #DIV/0!
57 | 241233005 : Borni bzar(Panishara UP)-Bejiatala bazar. | [13 empty] | 0 | #DIV/0!
58 | 241233006 : Seordah GC-Moheshpara | [13 empty] | 0 | #DIV/0!
59 | 241613018-Fakir Rasta bazar-Chaluahati UP | [13 empty] | 0 | #DIV/0!
60 | 241612016-Lawri (Madrasha) RHD -Khedapara GC Rd. | [13 empty] | 0 | #DIV/0!
61 | 241613001-Periodic Maintenance of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 7580-8703m [Salvage Cost Tk.Tk.1,42,500.00] | KDRIDP/Jess/M-19/2017-18 | 1.123 | 0 | 0 | 26.38 | 2018-08-26 | M/S Ara Enterprise, Main Road, Monirampur | 2018-10-18 | 27.268 | 100% | 2019-02-21 |  | 22.62 | -22.62 | 82.95%
62 | 241613010-Periodic Maintenance of Gopalpur Bazar-Kultia U.P.office Road From Ch. 00-4590m [Salvage Cost Tk.4,92,836.00] | KDRIDP/Jess/M-20/2017-18 | 4.59 | 0 | 0 | 122.29 | 2018-03-13 | M/S. Banantor Trading Corporation Benapol Road Chanchara, Jessore | 2018-04-15 | 128.4 | 100% | 2019-01-22 | 128.4 | 128.4 | 0 | 100% | Final
63 | 24164080-Khedapara-Maragacha via Gangulia Rd. | [13 empty] | 0 | #DIV/0!
Keshabpur
64 | 241382009 Mongalkot UP-Saraskati bazar | [13 empty] | 0 | #DIV/0!
65 | 241383006-Panjia Bazar UP- Monoharnagar Bazar Rd. | [13 empty] | 0 | #DIV/0!
66 | 241383007-Periodic Maintenance of Mongalkot-Panjia via Magurkhali Bazar Road From Ch.2300-3846m | KDRIDP/Jess/M-10/2017-18 | 1.546 | 0 | 0 | 48.335 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 50.75 | 100% | 2019-01-21 |  | 44.31 | -44.31 | 87.31%
67 | 241383014-Periodic Maintenance of Panjia UP-Burali Bazar Road From Ch.00-500m | KDRIDP/Jess/M-31/2018-19 | 0.5 | 0 | 0 | 9.935 | 2019-04-15 | Ms. Asraf Ali, Keshobpur Bazar, Keshobpur, Jessore | 2019-05-16 | 9.439 | 0% | 2019-11-23 |  |  | 0 | 0%
68 | 241384001-Bhallukghar- Komorpole hat - Bakultala hat Rd. | [13 empty] | 0 | #DIV/0!
69 | 241383010 Bakaborshi Natun hat-Durbadanga UP via Gorvanga Bazar | [13 empty] | 0 | #DIV/0!
70 | 241383016 Periodic Maintenance of Mongalkot UP-Hizaldanga bazar upto Subasni RHD Road From Ch.00-3750m | KDRIDP/Jess/M-22/2017-18 | 3.75 | 0 | 0 | 181.75 | 2018-06-24 | M/S Feroz Enterprise Gurudas Babu Lane. Jessore | 2018-09-08 | 181.739 | 90% | 2019-05-15 |  | 107.6 | -107.6 | 59.21%
71 | 241384029 Periodic Maintenance of Raghurampur Trimohoni (Near Reg P/School) -Saraskati Bazar Road From Ch.00-1710m | KDRIDP/Jess/M-09/2017-18 | 1.71 | 0 | 0 | 49.705 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 52.19 | 100% | 2019-01-21 |  | 52.175 | -52.175 | 99.97%
72 | 241384031 Periodic Maintenance of Kasta-Raghurampur Road From Ch.00-2000m | KDRIDP/Jess/M-23/2017-18 | 2 | 0 | 0 | 69.87 | 2018-05-13 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-03-06 | 73.358 | 100% | 2018-10-29 | 72.17 | 72.17 | 0 | 98.38% | Final
Sarsa
73 | 241902004-Periodic Maintenance of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra. Road From Ch.00-2225m,9225-10413m &10886-12150m | KDRIDP/Jess/M-06/2017-18 | 4.677 | 0 | 0 | 203.2 | 2018-02-26 | Abdur Razzaque Navaron Rail Bazar, Sharsha, Jessore | 2018-10-04 | 223.52 | 100% | 2019-09-01 | 223.44 | 223.44 | 0 | 99.96% | Final
74 | 241903001-Periodic Maintenance of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.206-2783m,5060-6785m, 8341-9471m &9665-10665m | KDRIDP/Jess/M-05/2017-18 | 6.432 | 0 | 0 | 160.54 | 2018-05-20 | Md. Oahiduzzaman Navaron Rail Bazar, Sarsha, Jessore | 2018-06-25 | 168.49 | 100% | 2019-05-23 | 168.43 | 168.43 | 0 | 99.96% | Final
75 | 241903007-Sarsha Upazila H/Q- Saratala Bazar via Laxmnpur U H/Q Rd. | [13 empty] | 0 | #DIV/0!
76 | 241903008-Benapole GC-Bahadurpur YP H/Q via Ghiba Rd. | [13 empty] | 0 | #DIV/0!
77 | 241903018-Baguri R&H -Kayba Union H/Q via Mohisha Madrasha Rd. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
78 | 241904070-Saratola Bazar-Beltaghat Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 87.714 | 0 | 0 | 2979.711 |  |  |  | 2822.957 | 78.45% |  | 1210.51 | 1885.672 | -675.162 | 66.8%
GC-Hat
Monirampur
1 | Construction of Parkhajura-Hat GC | KDRIDP/Jess/GC-15/2017-18 | 0 | 0 | 1 | 18.98 | 2018-02-08 | M/S Palash Enterprise, Nowapara, Abhoynagar, Jessore | 2018-03-04 | 17.559 | 90% | 2019-06-30 |  | 9 | -9 | 51.26%
Total |  |  | 0 | 0 | 1 | 18.98 |  |  |  | 17.559 | 90% |  | 0 | 9 | -9 | 51.26%
Tree Plantation
Jessore Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Bagherpara
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Abhoynagar
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Chowgacha
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Jhikargacha
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Monirampur
6 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Keshabpur
7 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Sarsa
8 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 288.074 | 138 | 1 | 18411.578 |  |  |  | 15396.15 | 67.86% |  | 5138.342 | 7909 | -2770.658 | 51.37%
|  |  | 288.074 | 138 | 1 | 18411.578 |  |  |  | 15396.15 | 26.47% |  | 5138.342 | 7909 | -2770.658 | 51.37%

## Jhikargacha
Jhikargacha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241232012 : Navaran puraton Bazar-Seordah GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241232015-Improvement of Jhikargacha Thana Hospital more to Goaldha Bazar via Padmapukur Kashipu Road By BC From Ch. 4650 - 6560m | KDRIDP/Jess/W-138/2018-19 | 1.91 | 0 | 0 | 209.6 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 241232016 : Hazirbag UZR-Matikumra UZR via Hazirbag UPC & MatiKumra Bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
4 | 241233001-Improvement of Parbazar-Chutipur bazar (Gongganandapur UP) Road From Ch. 5775 - 9925m | KDRIDP/Jess/W-49/2017-18 | 4.15 | 0 | 0 | 290.13 | 2018-03-13 | M/S Monir Traders Natun Khayertala, Jessore | 2018-04-04 | 316.09 | 80% | 2019-06-04 | 0 | 202.85 | -202.85 | 64.17% | 0
5 | 241233002-Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241233004 : Improvement of Lawjani bazar-Jhikargacha Katakhal bazar(Shahid Rafique Sarak) Road From Ch. 00 - 162m & 600-1750m | KDRIDP/Jess/W-47/2017-18 | 1.312 | 0 | 0 | 82.48 | 2017-10-30 | M/S Monir Traders Natun Khayertala, Jessore | 2017-11-30 | 79.39 | 100% | 2018-12-31 | 78.314 | 78.314 | 0 | 98.64% | Final
7 | 241233006 : Improvement of Seordah GC-Moheshpara Road From Ch. 3750 - 6350m | KDRIDP/Jess/W-48/2017-18 | 2.6 | 0 | 0 | 146.91 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 140.85 | 100% | 2019-01-14 | 138.39 | 138.39 | 0 | 98.25% | Final
8 | 241233008 : Bakra UP-Jhapa (Bridge) Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241233009 : Bakra bazar(Bakra UP)-Matshia bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 241233012 : Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More. Road From Ch. 6460 - 8350m. [Salvage Cost Tk. 6,982.00] | KDRIDP/Jess/W-83/2017-18 | 1.89 | 0 | 0 | 151.4 | 2018-06-25 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2018-08-20 | 145.02 | 30% | 2019-07-26 | 0 | 0 | 0 | 0% | 0
11 | 241233012 : Improvement of Jagodanandakati bazar Bridge-Bakra UP bazar Gondhor More. Road From Ch. 1000 - 1915m | KDRIDP/Jess/W-139/2018-19 | 0.915 | 0 | 0 | 71.56 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0% | 0
| 241233029 : Improvement of Jhikargacha GC-Jhikargacha UP(Lawjani Bazar) Road By BC From Ch. 2770 - 3668m. [Salvage Cost Tk. 5,58,102.00] |  | 0.898 | 0 | 0 | 77 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
12 | 241233013 : Improvement of Magura New Market-Magura UP office Road From Ch. 492 - 1300m [Salvage cost Tk. 2,37,171.00] | KDRIDP/Jess/W-50/2017-18 | 0.81 | 0 | 0 | 54.34 | 2017-10-30 | MD. Humayun Kabir Nobarakpur, Jhikorgacha, Jessore | 2017-11-30 | 49.06 | 100% | 2018-04-22 | 45.885 | 45.885 | 0 | 93.53% | Final
13 | 241233017 : Godkhali UP-Bodhkhana bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241233018 : Improvement of Barbakpur bazar-Simulia UP Road From Ch. 00-1150m. | KDRIDP/Jess/W-51/2017-18 | 1.15 | 0 | 0 | 75.47 | 2017-10-26 | M/S Jamuna Prokousoli Hatkhola Road, Jessore | 2017-12-12 | 75.17 | 100% | 2018-09-16 | 75.129 | 75.129 | 0 | 99.95% | Final
15 | 241233024 : Shimulia UP-Gorpara GC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241233025 : Godkhali bazar-Panishara UP(Borni bazar). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241233026: Improvement of Shimulia UP-Godkhali bazar Road By BCFrom Ch. 00 - 1430m. [Salvage Cost Tk. 1,51,081.00] | KDRIDP/Jess/W-128/2018-19 | 1.43 | 0 | 0 | 125.099 | 2019-04-01 | Md.Lutfor Rahman, Bagdah, Keshabpur, Jessore | 2019-05-21 | 118.844 | 0% | 2020-01-05 | 0 | 0 | 0 | 0% | 0
18 | 241233027 : Shimulia UP-Navaran UP (at Kalagachi RHD). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241233028 : Lawjani Bazar(Jhikargacha UP)-Naranggali bazar(Sadar) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
20 | 241234009 : Improvement of Fatepur-Bodhkhana bazar. Road By BC From Ch. 846 - 1303m | KDRIDP/Jess/W-140/2018-19 | 0.457 | 0 | 0 | 38.418 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241235282-Improvement of Gongadharpur Israil's house-Palla Lutfor's house. Road By BC From Ch. 00 - 1000m under. [Salvage Cost Tk. 5,58,102.00] |  | 1 | 0 | 0 | 82.803 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
21 | 241234013 : Misrideara UZR Jamtala-Angarpara. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241234035 : Improvement of Komarchanda-Nayra bazar Road From Ch. 00 - 925m | KDRIDP/Jess/W-06/2016-17 | 0.925 | 0 | 0 | 55.32 | 2017-07-03 | M/S Mysha Traders, 377/1, South Goran, Sabujbag, Dhaka-1219 | 2017-09-13 | 52.25 | 100% | 2018-05-31 | 52.207 | 52.207 | 0 | 99.92% | Final
23 | 241234052-Improvement of Digri bazar-Sadipu bazar Road From Ch.00-148 m | KDRIDP/Jess/W-15/2016-17 | 0.148 | 0 | 0 | 10.36 | 2017-07-27 | M/S Bakul Enterprise Pulerhat Bazar, Chanchara, Jessore | 2017-09-25 | 10.33 | 100% | 2018-03-14 | 10.33 | 10.33 | 0 | 100% | Final
24 | 241234071-Gongganandapur UP- Panditpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 241235001 : Bishahari-Atulia UZR. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241235012 : Magura UP Office-Magura UZR. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241235028: Improvement of Nabibnagar RHD-Kamarpara GPS Road By BCFrom Ch. 826 - 1656m | KDRIDP/Jess/W-129/2018-19 | 0.83 | 0 | 0 | 63.7 | 2019-04-01 | Fayaz Enterprise, Jashore | 2019-05-21 | 60.515 | 0% | 2020-02-28 | 0 | 0 | 0 | 0% | 0
28 | 241235031 : Kawria GPS More-Towra. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
29 | 241234040-Nawali bazar-Kanarali bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
30 | 241232015-Jhikargacha Thana Hospital more- Goaldah Bazar via Padmapukur Kashipur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 241233001-Parbazar-Chutipur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 241233002-Periodic Maintenance of Navaran Puratan bazar- Chutipur bazar Gongganandapur UP) Road From Ch.9750-14750m | KDRIDP/Jess/M-24/2017-18 | 5 | 0 | 0 | 166.579 | 2018-10-04 | M/S Sarder International Gohata Road, Cityplaza Complex, Jessore | 2018-05-30 | 174.89 | 70% | 2018-10-19 | 0 | 56.68 | -56.68 | 32.41% | 0
33 | 241233021-Sankarpur UP-Shamta Bazar RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 241233024-Periodic Maintenance of Shimulia UP-Gorpara GC Road From Ch.00-2401m. | KDRIDP/Jess/M-27/2018-19 | 2.401 | 0 | 0 | 82.317 | 2018-10-21 | M/S Mysha Traders, Jail Road, Jessore | 2019-03-01 | 78.2 | 65% | 2019-01-06 | 0 | 24.1 | -24.1 | 30.82% | 0
Tree Plantation
35 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 27.826 | 0 | 0 | 1783.486 |  |  |  | 1300.609 | 24.14% |  | 400.255 | 683.885 | -283.63 | 52.58%

## Keshabpur
Keshabpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241382005 Improvement of Chingra-Rajgonj via Trimohani UP (Keshabpur Portation) Road From Ch. 12600-13440m | KDRIDP/Jess/W-99/2017-18 | 0.8 | 0 | 0 | 68.496 | 2018-05-27 | M/S Alom Enterprise Bagda, Keshabpur, Jessore | 2018-08-07 | 71.9 | 100% | 2019-04-14 | 71.874 | 71.874 | 0 | 99.96% | Final
2 | 241382009 Mongalkot UP-Saraskati bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 241383004 Improvement of Biddanandakati UP-Kabilpur RHD more Via Hasanpur Road From Ch. 00-2760m. [Salvage Cost Tk. 69,65,398.00] | KDRIDP/Jess/W-120/2018-19 | 2.76 | 0 | 0 | 222.597 | 2019-07-04 | M/S FEROZ ENTERPRISE, Gurdash Babu Lane, Jessor | 2019-06-19 | 206.288 | 0% | 2019-11-12 | 0 | 0 | 0 | 0% | Tender will be Recceived on Dated 04/07/2018
4 | 241383005- Improvement of Keshabpur Pilot High School-Gorvanga Bazar Road from Ch.46 00-5600m. [Salvage Cost Tk. 4,51,606.00] | KDRIDP/Jess/W-146/2018-19 | 1 | 0 | 0 | 74.264 | 0 | 0 | 0 | 70.551 | 0% | 0 | 0 | 0 | 0 | 0% | 0
5 | 241383008 Biddanandakati UP-Jamalgong Bazar Via Parchakra Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241383009 Sagardari UP- Kabilpur GPS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241383011-Improvement of Panjia UP-Hoder hat Road From Ch. 00-3200m. [Salvage Cost Tk. 47,27,475.00] | KDRIDP/Jess/W-07/2016-17 | 3.2 | 0 | 0 | 229.93 | 2017-08-16 | M/S Mohidul Islam, 13/A Rail Road, Rail Bazar, Jessore | 2017-09-27 | 224.98 | 100% | 2018-10-20 | 224.84 | 224.84 | 0 | 99.94% | Final
8 | 241383014-Panjia UP-Burali Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241383018 Improvement of Mangolkot UP-Buruli bazar Road From Ch. 2616-4016m. [Salvage Cost Tk. 25,250.00] | KDRIDP/Jess/W-08/2016-17 | 1.4 | 0 | 0 | 87.96 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-06-14 | 87.77 | 100% | 2018-05-20 | 87.727 | 87.727 | 0 | 99.95% | Final
Improvement of Village Road by BC
10 | 241384008 Satkira Chira mill-Habspol Madrasha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 241384022- Improvement of Dewli more-Dewli non Govt Primary School Road Ch. 980-1980m [Salvage Cost Tk. 5,18,512.00] | KDRIDP/Jess/W-148/2018-19 | 1 | 0 | 0 | 79.162 | 0 | 0 | 0 | 75.204 | 0% | 0 | 0 | 0 | 0 | 0% | 0
12 | 241384025 Improvement of Dashkohonia Ruhul Amin House-Burili Rishipara Road From Ch. 1000-2705m. [Salvage Cost Tk. 7,35,719.00] | KDRIDP/Jess/W-09/2016-17 | 1.705 | 0 | 0 | 102.65 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-11-06 | 102.39 | 100% | 2018-04-14 | 102.3 | 102.299 | 0.001 | 99.91% | Final
13 | 241384026- Improvement of Satbaria Choudary Pond-Begompur more Road by BC From Ch. 600-2200m & 2300-2940m. [Salvage Cost Tk. 4,61,149.00] | KDRIDP/Jess/W-147/2018-19 | 2.24 | 0 | 0 | 170.459 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241384030 Protappur – Attonda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241384035 Boga-Mohadebpur road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241384037 Borenga-Pancharoi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241384038 Jhikra-baruihati (Kasta bazar-Sikerpur bazar road) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241384043 Boga FRB-Vanderkhola Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241384050 Improvement of Bosuntia (Mongolkot bazar)-Baduria via Ramkrishnapur Road From Ch. 480-1125m | KDRIDP/Jess/W-10/2016-17 | 0.645 | 0 | 0 | 42.34 | 2017-05-15 | M/S Joy Enterprise, Keshabpur Bazar, Keshabpur, Jessore | 2017-11-06 | 42.29 | 100% | 2018-04-30 | 42.24 | 42.24 | 0 | 99.88% | Final
20 | 241384051 Jahanpur Jamtala more-Vallukghar Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241385019 Improvement of Kanderpur-Gater-hat(Bongshir Battala) Road From Ch. 1000-2485m | KDRIDP/Jess/W-11/2016-17 | 1.485 | 0 | 0 | 88.92 | 2017-05-15 | M/S Biswas Construction, Dhaka Road, Puraton Kashba, Jessore | 2017-12-06 | 88.74 | 100% | 2018-04-30 | 88.68 | 88.68 | 0 | 99.93% | Final
22 | 241385022 Baliadanga-Gurvanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241385540-Improvement of Dohori Village C&B - Surindronath Mondal bari Road From Ch. 00-1100m. [Salvage Cost Tk. 6,41,862.00] | KDRIDP/Jess/W-94/2017-18 | 1.1 | 0 | 0 | 72.746 | 0 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-06-24 | 76.369 | 42.5% | 2019-02-19 | 0 | 0 | 0 | 0% | 0
| 241385541-Improvement of Gurdaga-Dong ghat H/O Mono Boso Road From Ch. 00-1000m. [Salvage Cost Tk. 79,300.00] |  | 1 | 0 | 0 | 68.33 |  |  |  | 71.73 |  |  | 0 | 0 | 0 | 0%
Improvement of Village Road by HBB
24 | 241384046-Keshabpur UP-Shikerpur bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
25 | 241382009 Mongalkot UP-Saraskati bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241383006-Panjia Bazar UP- Monoharnagar Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241383007-Periodic Maintenance of Mongalkot-Panjia via Magurkhali Bazar Road From Ch.2300-3846m | KDRIDP/Jess/M-10/2017-18 | 1.546 | 0 | 0 | 48.335 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 50.75 | 100% | 2019-01-21 | 0 | 44.31 | -44.31 | 87.31% | 0
28 | 241383014-Periodic Maintenance of Panjia UP-Burali Bazar Road From Ch.00-500m | KDRIDP/Jess/M-31/2018-19 | 0.5 | 0 | 0 | 9.935 | 2019-04-15 | Ms. Asraf Ali, Keshobpur Bazar, Keshobpur, Jessore | 2019-05-16 | 9.439 | 0% | 2019-11-23 | 0 | 0 | 0 | 0% | 0
29 | 241384001-Bhallukghar- Komorpole hat - Bakultala hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 241383010 Bakaborshi Natun hat-Durbadanga UP via Gorvanga Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 241383016 Periodic Maintenance of Mongalkot UP-Hizaldanga bazar upto Subasni RHD Road From Ch.00-3750m | KDRIDP/Jess/M-22/2017-18 | 3.75 | 0 | 0 | 181.75 | 2018-06-24 | M/S Feroz Enterprise Gurudas Babu Lane. Jessore | 2018-09-08 | 181.739 | 90% | 2019-05-15 | 0 | 107.6 | -107.6 | 59.21% | 0
32 | 241384029 Periodic Maintenance of Raghurampur Trimohoni (Near Reg P/School) -Saraskati Bazar Road From Ch.00-1710m | KDRIDP/Jess/M-09/2017-18 | 1.71 | 0 | 0 | 49.705 | 2018-05-22 | M/S Joy Enterprise Keshabpur Bazar, Jessore | 2018-05-24 | 52.19 | 100% | 2019-01-21 | 0 | 52.175 | -52.175 | 99.97% | 0
33 | 241384031 Periodic Maintenance of Kasta-Raghurampur Road From Ch.00-2000m | KDRIDP/Jess/M-23/2017-18 | 2 | 0 | 0 | 69.87 | 2018-05-13 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-03-06 | 73.358 | 100% | 2018-10-29 | 72.17 | 72.17 | 0 | 98.38% | Final
Tree Plantation
34 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 27.841 | 0 | 0 | 1667.449 |  |  |  | 1485.688 | 30.37% |  | 689.831 | 893.915 | -204.084 | 60.17%

## Chowgacha
Chowgacha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 241113003:( Singahjhully UP Office-Rashtampur bazar via Koyarpara Road.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241113005-Improvement of Nimtala bazar-Pasapole bazar via Pasapole UP Office Road Ch: 3120-3520m & 4020-4120 m [Salvage Cost Tk. 2,65,830.00] | KDRIDP/Jess/W-117/2018-19 | 0.5 | 0 | 0 | 37.085 | 2019-03-24 | A.M & T SARKAR CONSTRUCTION, Holding No-81, Kalitola, Chowgacha,Jashore | 2019-04-25 | 35.23 | 30% | 2019-02-12 | 0 | 0 | 0 | 0% | Tender will be Recceived on Dated 25/06/2018
3 | 241113008-Improvement of Shingo jhuli UP-Marua bazar Road. From Ch:3000-3495 m. | KDRIDP/Jess/W-16/2017-18 | 0.495 | 0 | 0 | 28.22 | 2017-08-07 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-02 | 29.57 | 100% | 2018-08-13 | 29.573 | 29.573 | 0 | 100% | Final
4 | 241113012- Improvement of Jogodishpur-Arpara GC Road From Ch: 2025-3525m. | KDRIDP/Jess/W-91/2017-18 | 1.5 | 0 | 0 | 89.331 | 2018-04-18 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-05-24 | 93.67 | 100% | 2019-02-24 | 93.645 | 93.645 | 0 | 99.97% | Final
5 | 241113013-Swarupda UP-Sukpukuria U.P Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241113016-Swarupda UP Office-Kharincha Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241113020- Solua GCCR-Pashapole UP Office Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
8 | 241114011-Guatoli UZR-Narayanpur UZR Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241114025 Improvement of Dhuliani bazar-Shajadpur Road From Ch: 00-184m & 1728-2465m. [Salvage Cost Tk. 3,49,720.00] | KDRIDP/Jess/W-70/2017-18 | 0.921 | 0 | 0 | 71.65 | 2018-05-07 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-06-24 | 75.225 | 70% | 2019-03-30 | 0 | 50.5 | -50.5 | 67.13% | 0
10 | 241114034-Improvement of Mosiurnagor Bazar-Bariali Road Ch: 371-1925m [Salvage cost Tk.19,93,248.00] | KDRIDP/Jess/W-115/2018-19 | 1.554 | 0 | 0 | 118.855 | 2019-03-24 | M/S RUBIA Enterprise, Khaertola Bazar, Jessore Sadar, Jessore. | 2019-04-25 | 112.91 | 10% | 2019-02-12 | 0 | 0 | 0 | 0% | 0
11 | 241114037-Dhuliani road-Uzirpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241114049-Goyra-Mashila Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241114063-Improvement of Arpara Bazer- Sarfarajpur Bazer via Kandi Road From Ch: 1120-2225m [Salvage cost Tk.6,63,400.00] | KDRIDP/Jess/W-89/2017-18 | 1.105 | 0 | 0 | 69.94 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-05-22 | 73.4 | 0% | 2019-02-24 | 0 | 0 | 0 | 0% | 0
14 | 241114030-Improvement of Jahatabmunshir Vhagar Road. From Ch: 00-1000m | KDRIDP/Jess/W-29/2017-18 | 1 | 0 | 0 | 65.85 | 2017-09-06 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-15 | 69.13 | 30% | 2018-04-09 | 0 | 0 | 0 | 0% | 0
15 | 241115048-Improvement of Karincha bazar-Madhabpur Burning Ghat Road Ch: 00-1807m. [Salvage Cost Tk. 42,70,739.00] | KDRIDP/Jess/W-131/2018-19 | 1.807 | 0 | 0 | 135.847 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241115140-Dashpakia-Nawdaga Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241115098-Improvement of Chanda Afra-Raynagor Road. From Ch: 1952-3182m. [Salvage Cost Tk.1,71,976.00 | KDRIDP/Jess/W-28/2017-18 | 1.23 | 0 | 0 | 73.49 | 2017-09-07 | M/S Jahid Hossain Kotchandpur Bus Stand Para, Jhenidah. | 2017-10-16 | 77.14 | 100% | 2018-12-20 | 77.007 | 77.007 | 0 | 99.83% | Final
18 | 241115098-Improvement of Chanda Afra-Raynagor Road From Ch: 00-520m under. [Salvage Cost Tk. 2,43,822.00] | KDRIDP/Jess/W-84/2017-18 | 0.52 | 0 | 0 | 33.23 | 2018-05-13 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore | 2018-06-24 | 34.89 | 100% | 2019-02-02 | 34.89 | 34.89 | 0 | 100% | Final
19 | 241115181-Improvement of Batikamari - Bundalitala Road [ Inventory Name: Batikamari Bhanga road- Batikamari village Road ] From Ch: 00-610m | KDRIDP/Jess/W-71/2017-18 | 0.61 | 0 | 0 | 43.865 | 2018-08-27 | M/S Renu Enterprise, Asrom Road, Kotoali, Jashore | 2018-10-17 | 45.576 | 100% | 2019-05-20 | 0 | 25.97 | -25.97 | 56.98% | 0
20 | 241115030-Improvement of Bergobindapur- Math Road (Bergobindapur-Goalbari via Purbo Para) From Ch: 00-1000m. [Salvage Cost Tk. 3,41,285.00] | KDRIDP/Jess/W-58/2017-18 | 1 | 0 | 0 | 59.4 | 2018-03-12 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2018-04-18 | 62.45 | 100% | 2019-01-15 | 0 | 53.9 | -53.9 | 86.31% | 0
21 | 241115079-Improvement of DMC Madrasha - Joynarar union Road. From Ch: 00 - 1130m. [Salvage Cost Tk. 4,91,285.00] | KDRIDP/Jess/W-12/2016-17 | 1.13 | 0 | 0 | 69.69 | 2017-05-12 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-08-06 | 72.54 | 40% | 2018-04-30 | 0 | 0 | 0 | 0% | 0
22 | 241115079-Improvement of DMC Madrasha - Rainagar union Road From Ch:1130-2100 m. [Salvage Cost Tk.89,458.00] | KDRIDP/Jess/W-52/2017-18 | 0.97 | 0 | 0 | 65.46 | 2018-01-11 | M/D Jahid Hossain Kotchandpur Bus stand para, Jhenidah | 2018-02-07 | 68.73 | 100% | 2018-09-30 | 68.55 | 68.55 | 0 | 99.74% | Final
23 | 241115078-Improvement of Jhinaikundu-Jamira Road. From Ch: 00-1000m | KDRIDP/Jess/W-30/2017-18 | 1 | 0 | 0 | 57.77 | 2017-07-09 | M/S Sheba Traders, Chowgacha Bazar, Chowgacha, Jessore | 2017-10-03 | 60.52 | 100% | 2018-02-09 | 60.523 | 60.523 | 0 | 100% | Final
24 | 241115078-Improvement of Jhinaikundu-Jamira Road From Ch: 1000-1535m. [Salvage Cost Tk. 66,223.00] | KDRIDP/Jess/W-74/2017-18 | 0.535 | 0 | 0 | 32.98 | 2018-05-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-06-18 | 34.627 | 100% | 2019-03-24 | 34.215 | 34.215 | 0 | 98.81% | Final
25 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 00-1000m. [Salvage Cost Tk. 2,61,184.00] | KDRIDP/Jess/W-24/2017-18 | 1 | 0 | 0 | 58.5 | 2017-08-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-10-10 | 60.88 | 30% | 2018-08-20 | 0 | 0 | 0 | 0% | 0
26 | 241115198-Improvement of Afra BC road -Sibnagor road via Sibnagor Prymary school Road. From Ch: 1000-1340m. [Salvage Cost Tk. 19,597.00] | KDRIDP/Jess/W-114/2018-19 | 0.34 | 0 | 0 | 26.968 | 2019-03-24 | M/S Sun Enterprise, Chowgacha Bazar, Chowgacha, Jessore | 2019-05-14 | 25.62 | 10% | 2019-11-21 | 0 | 0 | 0 | 0% | 0
| 241115271- Sayedpur Altab Mondol House-H/O Thandu Mondol via Mondol Para Jame Mosque Road. |  | 0.236 | 0 | 0 | 18.488 |  |  |  | 17.564 |  |  | 0 | 0 | 0 | 0%
27 | 241115199-Improvement of Fulsara Purbopara Madrasha- Abed ali house Road. From Ch:00-645 m [Salvage Cost Tk.1,61,285.00] | KDRIDP/Jess/W-17/2017-18 | 0.645 | 0 | 0 | 38.58 | 2017-08-06 | Md. Abdul Halim Kotchanpur, Jhenaidah | 2017-05-10 | 39.4 | 100% | 2018-08-25 | 39.4 | 39.4 | 0 | 100% | Final
28 | 241115207-Improvement of Fulshara Purbopara Village Road. From Ch: 00 - 680m. [Salvage Cost Tk. 8,37,415.00] | KDRIDP/Jess/W-13/2016-17 | 0.68 | 0 | 0 | 42.75 | 2017-05-15 | M/S Mim Enterprise, Gajirhat Road, Puraton Kosba, Jessore | 2017-11-06 | 42.94 | 60% | 2018-04-28 | 0 | 19.03 | -19.03 | 44.32% | 0
29 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road. From Ch: 00-455m [Salvage Cost Tk. 1,45,870.00] | KDRIDP/Jess/W-26/2017-18 | 0.455 | 0 | 0 | 27.63 | 2017-08-21 | M/S SK. Enterprise, Chowgacha, Jessore | 2017-10-15 | 28.98 | 100% | 2018-08-27 | 28.97 | 28.974 | -0.004 | 99.98% | Final
30 | 241115270-Improvement of Araddah Muktijhodda Siddque Master House- Raton Mistri House via Jame Mosque Road From Ch: 455-636m. | KDRIDP/Jess/W-87/2017-18 | 0.181 | 0 | 0 | 11.24 | 2018-04-18 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-05-22 | 11.8 | 100% | 0 | 11.578 | 11.578 | 0 | 98.12% | Final
31 | 241115262-Improvement of Araddah Muktijuddah Abdur Sattar Mia House -Sibnagor village via Balidapara GPS Road. From Ch: 00-1140m. [Salvage Cost Tk.1,04,350.00] | KDRIDP/Jess/W-112/2018-19 | 1.14 | 0 | 0 | 85.11 | 2018-11-19 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2019-01-03 | 80.85 | 10% | 2019-10-10 | 0 | 0 | 0 | 0% | 0
32 | 241115258-Improvement of Singojhuli Jhautala - Baruhati Road. From Ch: 00-1235m | KDRIDP/Jess/W-18/2017-18 | 1.235 | 0 | 0 | 71.51 | 2017-08-07 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-09-28 | 74.94 | 100% | 2018-05-31 | 74.644 | 74.644 | 0 | 99.61% | Final
33 | 241115131-Improvement of Dhakinsagor-Charabari via H/O Abdul Bari Road. From Ch: 00-1650m. [Salvage Cost. Tk. 62,601.00] | KDRIDP/Jess/W-22/2017-18 | 1.65 | 0 | 0 | 94.46 | 2017-08-21 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2017-10-03 | 99.06 | 100% | 2018-05-31 | 98.877 | 98.877 | 0 | 99.82% | Final
34 | 241115060-Improvement of Andulia-Doulatpur Road From Ch: 2327-3350m. [Salvage cost Tk.11,24,654.00] | KDRIDP/Jess/W-116/2018-19 | 1.023 | 0 | 0 | 73.384 | 2019-04-16 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2019-06-13 | 73.253 | 0% | 2020-01-30 | 0 | 0 | 0 | 0% | 0
| 241114024-Improvement of Goribpur-Moshiuragor Road From Ch: 00-875m.[Salvage cost Tk. 35.104.00] |  | 0.875 | 0 | 0 | 65.448 |  |  |  | 65.33 |  |  | 0 | 0 | 0 | 0%
35 | 241115153-Improvement of Patibila UP - Hayetpur via Uttor Para Road. From Ch: 00-1000m [Salvage Cost Tk.5,65,304.00] | KDRIDP/Jess/W-23/2017-18 | 1 | 0 | 0 | 59.93 | 2017-08-18 | M/S Jamuma Prokousoli hatkhola Road, jessore | 2017-10-02 | 62.8 | 60% | 2018-08-28 | 0 | 0 | 0 | 0% | 0
36 | 241115288-Improvement of Afra R&H road near H/O Mokbul via Karamot Ali Road. From Ch: 00-475m. [Salvage Cost Tk.3,08,590.00] | KDRIDP/Jess/W-20/2017-18 | 0.475 | 0 | 0 | 32.38 | 2017-10-19 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 33.54 | 5% | 2018-05-30 | 0 | 0 | 0 | 0% | 0
37 | 241115296-Improvement of Durgabor Kathi Amir Ali H/O -Tatul Bari Korban Biswas H/O Road. From Ch: 00-587m. | KDRIDP/Jess/W-21/2017-18 | 0.587 | 0 | 0 | 37.45 | 2017-10-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2017-11-26 | 38.89 | 40% | 2018-02-06 | 0 | 0 | 0 | 0% | 0
38 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid Road. From Ch: 00-1000m | KDRIDP/Jess/W-27/2017-18 | 1 | 0 | 0 | 62.74 | 2017-08-20 | M/S Sarkar Construction Lalbazar, Natore | 2017-10-10 | 64 | 100% | 2018-08-27 | 63.299 | 63.299 | 0 | 98.9% | Final
39 | 241115294-Improvement of Bolida Bari Purbo Para Tipu House- Pacchim Para Mosjid From Ch: 1000-1480m. [Salvage Cost Tk. 1,10,415.00] | KDRIDP/Jess/W-75/2017-18 | 0.48 | 0 | 0 | 30.22 | 2018-02-20 | M/S Mehedi Masud Chowdhuri, Solua bazar, Chowgacha, Jessore | 2018-04-03 | 30.61 | 60% | 2018-11-19 | 0 | 4.65 | -4.65 | 15.19% | 0
40 | 241115292-Improvement of Souila Arpara road near H/O Toffazial-Durabakati H/O Ismail Road. From Ch:00-350 m .[Salvage Cost Tk.1,94,990.00] | KDRIDP/Jess/W-19/2017-18 | 0.35 | 0 | 0 | 21.76 | 2017-10-17 | M/S Sadar Intarnational, Gohata Road, City Plaza Complex, Jessore | 2017-11-23 | 21.458 | 100% | 2018-05-30 | 21.238 | 21.238 | 0 | 98.97% | Final
41 | 241115269-Improvement of Sayedpur Shek Para Abdur Razzak Shop- Purbo Mat Pucca Road From Ch: 00-1470m. [Salvage Cost Tk. 2,18,023.00] | KDRIDP/Jess/W-113/2018-19 | 1.47 | 0 | 0 | 113.21 | 2019-05-05 | Mortaza Reza, Krishnanagar, Jhikargacha, Jessore. | 0 | 107.55 | 0% | 0 | 0 | 0 | 0 | 0% | 0
42 | 241115008-Improvement of Swruppur Hajambari-Bagdanga Road From Ch: 00-2200m. [Salvage Cost Tk. 6,84,966.00] | KDRIDP/Jess/W-118/2018-19 | 2.2 | 0 | 0 | 163.935 | 2019-04-08 | Md.Noor Islam, Purbobarandipara, Jessore | 2019-06-13 | 163.607 | 0% | 2019-10-14 | 0 | 0 | 0 | 0% | 0
43 | 241115014-Improvement of Tazbizpur-Jatrapur Road From Ch: 864-2035m | KDRIDP/Jess/W-59/2017-18 | 1.171 | 0 | 0 | 71.695 | 2018-04-25 | M/S Renu Enterprise Asrom Road Jessore | 2018-05-24 | 75.25 | 100% | 2019-04-18 | 0 | 47.9 | -47.9 | 63.65% | 0
44 | 241115286-Improvement of Anderkota Primary school-Panchbaria Beel Tematha BC Road From Ch:00-1075 m | KDRIDP/Jess/W-55/2017-18 | 1.075 | 0 | 0 | 58.92 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 63.028 | 100% | 2019-05-30 | 0 | 29.167 | -29.167 | 46.28% | 0
45 | 241115044-Improvement of Baishagari BC Road - Hazrakhana Kadamtala BC Road via Anderkota, Batikamari Road. (Batkamari- Mohespur Road.)Road. From Ch:1500-2680m | KDRIDP/Jess/W-56/2017-18 | 1.18 | 0 | 0 | 70.706 | 2018-03-12 | M/S SK. Enterprise, Chowgacha, Jessore | 2018-04-17 | 75.649 | 100% | 2019-05-30 | 0 | 43.9 | -43.9 | 58.03% | 0
46 | 241114026-Improvement of Kongsharipur-Mashila Road. From Ch: 2043-2198m & 4080-5510m | KDRIDP/Jess/W-57/2017-18 | 1.585 | 0 | 0 | 89.53 | 2018-03-12 | MD. Noor Islam. Purbo Barandipara, Jessore | 2018-04-17 | 95.72 | 100% | 2018-09-12 | 95.72 | 95.72 | 0 | 100% | Final
Improvement of Village Road by HBB
47 | 241114038-Burinda-Dashpakia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
48 | 241112008-Periodic Maintenance of Solua GC-Arpara GC Road From Ch.5500-7325m | KDRIDP/Jess/M-11/2017-18 | 1.825 | 0 | 0 | 60.646 | 2018-04-25 | M/S Chowdhury Construction Salua Bazar Chowgacha, Jessore | 2018-06-24 | 63.678 | 100% | 2019-01-11 | 63.545 | 63.545 | 0 | 99.79% | Final
49 | 241112011-Purapara GC-Moheshpur Pucca road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
50 | 241113010-Periodic Maintenance of Debipur-Narayanpur GC Road From Ch.00-1260m. | KDRIDP/Jess/M-12/2017-18 | 1.26 | 0 | 0 | 30.358 | 2018-04-25 | M/S Sheba Traders Chowgacha Bazar, Chowgacha, Jessore | 2018-03-06 | 31.87 | 100% | 2019-03-03 | 0 | 0 | 0 | 0% | 0
51 | 241113011-Periodic Maintenance of Chowgacha U.P-Dhuliani Via Bergobindapur Baor Road From Ch.275-1100m. | KDRIDP/Jess/M-13/2017-18 | 0.825 | 0 | 0 | 19.82 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 20.809 | 100% | 2018-11-30 | 20.8 | 20.799 | 0.001 | 99.95% | Final
52 | 241113014-Periodic Maintenance of Sukpukuria U.P-Andulia bazar Road From Ch.900-3680m | KDRIDP/Jess/M-14/2017-18 | 2.78 | 0 | 0 | 47.95 | 2018-09-27 | Md. Noor Islam, Purbo Barandipara, Jessore | 2018-10-16 | 50.232 | 100% | 2019-08-03 | 50.232 | 50.23 | 0.002 | 100% | Final
53 | 241113005-Nimtala Bazar-Pasapole Bazar via Pasapole UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
54 | 241113017-Sukpukria UP Office -Goira Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
55 | 241113013-Swarupda UP- Sukpukuria UO Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
56 | 241114052-Chowgacha -Kabilpur Rd Mashampur more - Masila Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
57 | 241115022-Maligati -Bariali Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
58 | 241114009(Roghonatpur-Dashpakhia bazar Road) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
59 | 241114014-Periodic Maintenance of Purapara Sonali Bank-Ballave pur Road From Ch.820-4900m | KDRIDP/Jess/M-16/2017-18 | 4.08 | 0 | 0 | 109.69 | 2018-05-03 | Nishit Bosu, Kanchan Nagar, Jhenaidah | 2018-02-04 | 117.36 | 100% | 2018-11-30 | 117.361 | 117.361 | 0 | 100% | Final
60 | 241114024-Periodic Maintenance of Goribpur-Moshiuragor (Muktinagar ) via Jogonathpur Road From Ch.2375-3795m | KDRIDP/Jess/M-30/2018-19 | 1.42 | 0 | 0 | 63.47 | 2019-04-16 | Nishit Bosu, Kanchan nagar, Jhenaidah | 2019-05-30 | 60.3 | 0% | 2020-01-30 | 0 | 0 | 0 | 0% | 0
61 | 241114026(Kongsharipur-Mashila Road). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
62 | 241114028-Periodic Maintenance of Kamlapur More-Mashila Bazar Road From Ch.00-1115m | KDRIDP/Jess/M-15/2017-18 | 1.15 | 0 | 0 | 28.174 | 2018-07-05 | Md. Noor Islam, Purbo Barandipara, Jessore | 2018-10-06 | 29.58 | 100% | 2019-01-30 | 0 | 22.95 | -22.95 | 77.59% | 0
63 | 241114044Muktadah-Jagadishpur UP Road..) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
64 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 51.25 | 0 | 0 | 2839.315 |  |  |  | 2772.156 | 47.73% |  | 1084.067 | 1382.035 | -297.968 | 49.85%

## Jessore Sadar
Jessore Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241472009-Improvement of Rupdia GC-Basundia Moor RHD via Shakarigati Road. From Ch:1100-3360m & 3970-4420m. [Salvage Cost. Tk.37,85,349.00] | KDRIDP/Jess/W-81/2017-18 | 2.71 | 0 | 0 | 263.11 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241472012-Razarhat GC-Hamidpur RHD Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 241472013-Jongle Bandle RHD-Basundia GC Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch: 7500-9350m. [Salvage Cost Tk. 28,17,772.00 ] | KDRIDP/Jess/W-14/2016-17 | 1.85 | 0 | 0 | 128.13 | 2017-05-29 | M/S Morol Enterprise Balia, Vakutia Bazar, Sadar, Jessore | 2017-12-07 | 128.11 | 100% | 2018-06-19 | 127.802 | 127.802 | 0 | 99.76% | Final
5 | 241472014-Improvement of Churamankati GC-Kayemkhola GC via Bagdanga, Jhowdia Bazar, Chandutia Road. From Ch:10416-11460m under Upazila: Sadar, District: Jessore. | KDRIDP/Jess/W-82/2017-18 | 1.044 | 0 | 0 | 78.89 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore | 2018-06-10 | 82.83 | 100% | 2019-05-07 | 0 | 27.2 | -27.2 | 32.84% | 0
Improvement of Union Road by BC
6 | 241473003-Improvement of Lebutala UP Office-Shyamnagar via Fultola Bazar Road. From Ch:5423-7723m & 9450-10236m. [Salvage Cost. Tk.55,29,697.00] | KDRIDP/Jess/W-119/2018-19 | 3.086 | 0 | 0 | 254.02 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 11/09/2018
7 | 241473005-Upashahor UP-Dolennagar Bazar Rd via Kashimpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241473007-Chanchra UP office-Kuadah Bazar via Sarapol Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241473010-Improvement of Chanchra Bazar-Chanchar UP via Vaturia(Jessore Khulna Hogway Beltolarmore Bormonpara Nodermore via Chanchra High School) Road. From Ch:00-1300m. [Salvage Cost. Tk.12,59,686.00] | KDRIDP/Jess/W-101/2017-18 | 1.3 | 0 | 0 | 86.959 | 2018-06-29 | Md Harun or Rashid, Nowapara Road, Ghop,Kotoali, Jessore. | 2018-09-05 | 91.297 | 100% | 2019-12-05 | 91.28 | 91.28 | 0 | 99.98% | Final
10 | 241473010-Improvement of Chanchra Bazar-Chanchar UP via Vaturia (DPP Name: Jessore-Khulna road Beltala more - Chasria High School) Road By BC From Ch:1300-3260m under Upazila: Sadar, District: Jessore. [Salvage Cost. Tk.24,10,020.00] | KDRIDP/Jess/W-127/2018-19 | 1.96 | 0 | 0 | 155.77 | 2019-04-23 | Md Harun or Rashid | 0 | 153.799 | 0% | 0 | 0 | 0 | 0 | 0% | 0
11 | 241473011-Improvement of Natunhat-Deara UP office via Dattopara Road By BC From Ch:2980-4980m [Salvage Cost. Tk.21,89,721.00] | KDRIDP/Jess/W-144/2018-19 | 2 | 0 | 0 | 148.4 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241473019-Arabpur UP Office-Faridpur Old Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241473020-Haibatpur UP-Ambottola via Kamalpur, Shahabajpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241473021-Improvement of Churamonkati UP Office-Khojar Hat Rd (Kashimpur UP) Road By BC From Ch:2000-2750m under Upazila: Sadar, District: Jessore. [Salvage Cost. Tk.18,24,040.00] | KDRIDP/Jess/W-143/2018-19 | 0.75 | 0 | 0 | 52.404 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241473031-Improvement of Pulerhat - Arabpur UP (Mondalgati) Road By BC From Ch:2050-3052m. [Salvage Cost. Tk.7,89,600.00] |  | 1.002 | 0 | 0 | 65.594 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
15 | 241473022-Fatehpur UP Office-Bablatola Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241473024-Labutola UP-Andolpota via Agrail, Enayetpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241473025-Improvement of Lawjani Bazar-Deeara UP Office via Narangali Bazar Road By BC From Ch:1500-2575m | KDRIDP/Jess/W-145/2018-19 | 1.075 | 0 | 0 | 86.046 | 0 | 0 | 0 | 81.744 | 0% | 0 | 0 | 0 | 0 | 0% | 0
18 | 241473030-Ichali UP (Bangda more) - Labutala Bazar via Rajapur (RHD) . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241473001-Improvement of Chowlia Gate-Sutighata Ramnagar UP Office Road. From Ch:2660-4255m. [Salvage Cost. Tk.37,44,628.00] | KDRIDP/Jess/W-68/2017-18 | 1.595 | 0 | 0 | 107.517 | 2018-05-28 | M/S Jamuna Prokousoli, Hatkhola Road, Jessore | 2018-06-24 | 112.87 | 100% | 2019-03-30 | 112.808 | 112.808 | 0 | 99.95% | Final
Improvement of Village Road by BC
20 | 241474002-Improvement of Haibathpur -Uttar Lolitadha Road. From Ch:1030-104m & 1180-2560m. [Salvage Cost. Tk.34,666.00] | KDRIDP/Jess/W-95/2017-18 | 1.39 | 0 | 0 | 102.107 | 2018-05-12 | M/S L Rahaman Enterprise, R N Road, Jessore | 2018-10-06 | 107.207 | 100% | 2019-03-14 | 106.7 | 106.7 | 0 | 99.53% | Final
21 | 241474003-New Khairtala R&H-Bahadurpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241474004-Khairrala Seed Office-Boalpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241474007-Sujalpur Muchipara-Faridpur old Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 241474009-Improvement of Gopalpur-Rampur Pry. School Road. From Ch:2000-4105m. [Salvage Cost. Tk.3,68,686.00] | KDRIDP/Jess/W-69/2017-18 | 2.105 | 0 | 0 | 130.835 | 2018-08-27 | M/S Gazi Enterprise, Nutum Khaertala Road, Kotoali, Jashore. | 2018-10-15 | 136.92 | 60% | 2019-07-20 | 0 | 11.3 | -11.3 | 8.253% | 0
25 | 241474015-Rudropur-Sarapole bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241474017-Rupdia Jamtala R&HD- Rustompur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241474020-Basundia bazar-Jogonnathpur Kheaghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 241474021-Deapara-Ghop RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 241474052-Setarampur-Jhumjhumpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 241474055-Improvement of Dhopakhola RHD-Durgapur Koyetpara Road By BC From Ch:1600-3175m | KDRIDP/Jess/W-141/2018-19 | 1.575 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 241474056-Improvement of Taragonj-Ramkrisnapur Road By BC From Ch:1000-2385m. [Salvage Cost. Tk.14,10,691.00] | KDRIDP/Jess/W-142/2018-19 | 1.385 | 0 | 0 | 101.944 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241474027-Improvement of Muroli more R&HD-Kanitala Road By BC From Ch:1950-2800m. [Salvage Cost. Tk.6,31,704.00] |  | 0.85 | 0 | 0 | 66.48 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
32 | 241474063-Mondolgaty (Kholadanga)-Arabpur UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | Patan Paikpara-Chitra Bazar-Bagerpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | Monsefnagar village Biswas para Jame Mosque-Monsefnagar Secendary School rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 241475293 Enayetpur-Teerhat Road. via Kadir Para (H/O Minaz-Manikdihe-Dhaka rd) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 241475285 Narendropur Pucca Road to Narendropur High School Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 241475292 ahsania mission road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
38 | 241474005-Churmankati Rail gate-Dogachia Beel Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 241474016-Hamidpur Kamar bari-Dhitila Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
40 | 241473016-Construction of 22.00m Long RCC Girder Bridge on Satiantola Bazar-(Fulbari More) Ichali UP via Suro,Kamergona Road at Ch.2900m | KDRIDP/Jess/B-01/2018-19 | 0 | 22 | 0 | 214.928 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 241473002-Construction of 72.00m Long RCC Girder Bridge on Narendrapur UP-Dailala Bazar (over Dakua River) Road at Ch.100m | KDRIDP/Jess/B-02/2018-19 | 0 | 72 | 0 | 585.605 | 2019-03-28 | Kamarjani-Anowara JV, 15 no Shreeangan Market, Goalchamot, Faridpur | 2019-05-15 | 570.36 | 0% | 2020-03-14 | 0 | 0 | 0 | 0% | 0
Maintenance
42 | 241472012-Razarhat GC-Hamidpur RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 241472014-Churamankati GC-Kayemkhola GC via Bagdanga Jhowdia Bazar Chandutia Rd | KDRIDP/Jess/M-01/2017-18 | 2.805 | 0 | 0 | 120.728 | 2018-04-25 | M/S L Rahaman Enterprise R. N. Road, Jessore | 2018-10-06 | 126.76 | 50% | 2019-03-16 | 0 | 20.82 | -20.82 | 16.42% | 0
44 | 241472017-Monohorpur Bazar RHD - Narikel Baria GC via Raipur UP ( sadar part) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 241473002-Narendrapur UP-Daitala Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 241473005-Periodic Maintenance of Upashahor UP - Tail kup Bazar Rd. Via Kashimpur, Dighirpar Road From Ch.00-1300m | KDRIDP/Jess/M-21/2017-18 | 1.33 | 0 | 0 | 62.36 | 2018-05-11 | M/S S S Traders Kazi Para, Puraton Koshba, Jessore | 2018-05-28 | 65.469 | 100% | 2019-02-03 | 65.469 | 65.469 | 0 | 100% | Final
47 | 241473007-Chanchra UP Office-Kuadah Bazar via Sarapol Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 241473008-Bagerhat Bazar-Ramnagar UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 241473009-Sannashi Bottala Bazar- Ramnagar UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
50 | 241473010-Chanchara Bazar -Chanchar UP via Vaturia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
51 | 241473016-Periodic Maintenance of Satiantola Bazar- (Fulbari More) Ichali UP via Suro, Kamergona Road From Ch.00-2975m | KDRIDP/Jess/M-02/2017-18 | 2.975 | 0 | 0 | 73.158 | 2018-04-22 | M/S Dilip Enterprise, Calectorit Mosjid Market, Jessore | 2018-05-30 | 76.808 | 100% | 2019-02-20 | 76.79 | 76.79 | 0 | 99.98% | Final
52 | 241473028-Khajura(Bagherpara) GC-Barobazar(Kaligonj) GC Road via Labutola UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
53 | 241474010-Periodic Maintenance of Basundia Bazar-Afraghat Ghat Road From Ch.00-2540m. | KDRIDP/Jess/M-04/2017-18 | 2.54 | 0 | 0 | 74.54 | 2018-04-23 | M/S Sharif Rabrul Enterprise Jail Road Ghop, Jessore | 2018-10-06 | 78.266 | 100% | 2019-01-30 | 78.26 | 78.26 | 0 | 99.99% | Final
54 | 241474012-R&H Rd. at Bijoynagar-Bolpur Ghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
55 | 241474026-Periodic Maintenance of Pulerhat Shishu Aparad Centre-Vaturia Road From Ch.00-1400m | KDRIDP/Jess/M-03/2017-18 | 1.4 | 0 | 0 | 84.418 | 2018-04-24 | M/S Harun or Rashid Nowapara Road, Ghop, Jessore | 2018-03-06 | 88.45 | 100% | 2019-04-17 | 81.46 | 81.46 | 0 | 92.1% | Final
56 | 241474033-Bablatola Taxi Stand-Sarothi Mill Gabtola Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
57 | 241474044-Nutunhat RHD-Bagerhat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
58 | 241475083-Beltola -Khmalpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
59 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 36.727 | 94 | 0 | 3155.943 |  |  |  | 1900.89 | 17.12% |  | 740.569 | 799.889 | -59.32 | 42.08%

## Monirampur
Monirampur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241612008-Monirampur-Mukterpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241612018-Dighirpar-Dumurkhali Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 241613001-Improvement of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 3500-6420m | KDRIDP/Jess/W-03/2016-17 | 2.92 | 0 | 0 | 176.63 | 2017-05-12 | M/S Biswajit Constroction, 9 Rail Road, Jessore | 2017-06-01 | 168.71 | 100% | 2018-04-26 | 168.67 | 168.67 | 0 | 99.98% | Final
4 | 241613001-Improvement of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road by BC From Ch. 7390-7580m& 8703-10690m [Salvage Cost Tk. 25,86,180.00] | KDRIDP/Jess/W-122/2018-19 | 2.177 | 0 | 0 | 191.05 | 0 | M/S SARDER INTERNATIONAL, Jessore | 2019-04-23 | 181.5 | 0% | 0 | 0 | 0 | 0 | 0% | 0
5 | 241613002-Chalkidanga Bazar-Rohita UP via Kashimnagar UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241613006-mprovement of Chalkidanga Bazer-Haridashkati UP via Joypur bazar Road From Ch. 4371-5800m | KDRIDP/Jess/W-44/2017-18 | 1.429 | 0 | 0 | 92.44 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 91.41 | 100% | 2018-07-15 | 89.63 | 89.63 | 0 | 98.05% | Final
8 | 241613009-Improvement of Nehalpur UP-Hazirhat bazar via Kultia UP Road From Ch. 00-3557m | KDRIDP/Jess/W-04/2016-17 | 3.557 | 0 | 0 | 231.18 | 2017-10-22 | M/S Motinur Rahaman Nannu, 57, Chalk Bazar, Faridpur | 2017-11-16 | 250.7 | 100% | 2018-02-12 | 250.65 | 250.65 | 0 | 99.98% | Final
9 | 241613011-Improvement of Sundalpur bazar-Haridashkati UP via Salimpur Road From Ch. 9050-10920m. [Salvage Cost Tk. 1,73,331.00] | KDRIDP/Jess/W-103/2017-18 | 1.87 | 0 | 0 | 137.89 | 2018-08-26 | M/S Hira construction Main Road, Monirampur, Jessore | 2018-10-15 | 143.39 | 100% | 2019-03-09 | 0 | 100.27 | -100.27 | 69.93% | 0
| 241613019-Improvement of Khanpur UP-Horidaskati UP Road From Ch. 2550-3380m. [Salvage Cost Tk. 13,90,230.00] |  | 0.83 | 0 | 0 | 61.04 |  |  |  | 63.475 |  |  | 0 | 44.38 | -44.38 | 69.92%
10 | 241613012-Improvement of Bhojgati UP-Dhakuria UP via Horergati Road From Ch. 1000-4810m. [Salvage Cost Tk. 3,63,209.00] | KDRIDP/Jess/W-121/2018-19 | 3.81 | 0 | 0 | 313.166 | 2019-04-15 | M/S BISWAJIT Constroction, 9 Rail Road, Jessore | 2019-06-20 | 316.577 | 0% | 2020-10-05 | 0 | 0 | 0 | 0% | 0
11 | 241613013-Improvement of Tangramari-Khedapara U.P.via Jalalpur Road From Ch. 00-2120m. [Salvage Cost Tk. 54,342.00] | KDRIDP/Jess/W-77/2017-18 | 2.12 | 0 | 0 | 151.21 | 2018-05-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-06-24 | 155.72 | 100% | 2019-04-07 | 0 | 84 | -84 | 53.94% | 0
12 | 241613014-Shyamkur Up-Chandipur via Lakkanpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241613016-Improvement of Muragacha-Horihornagor U.P.via Modonpur Road From Ch. 1000-2695m. [Salvage Cost Tk. 13,90,230.00] | KDRIDP/Jess/W-45/2017-18 | 1.695 | 0 | 0 | 116.18 | 2017-10-30 | M/S Alif Enterprise, Chapatala, Mirzapur, Jhikorgacha, Jessore | 2017-11-30 | 111.33 | 100% | 2018-03-09 | 0 | 99.4 | -99.4 | 89.28% | 0
14 | 241613022-Nangro Bazar - Rashulpur via Jamtala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
15 | 241614005-Monirampur College-Debidaspur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241614019-Improvement of Komolpur-Tazpur Road From Ch. 00-2000m [Salvage Cost Tk. 21,76,122.00] | KDRIDP/Jess/W-78/2017-18 | 2 | 0 | 0 | 143.17 | 2018-05-12 | Sayed Nahid Hassan Keshabpur Bazar, Keshabpur, Jessore | 2018-06-14 | 150.25 | 100% | 2019-05-11 | 0 | 103.62 | -103.62 | 68.97% | 0
17 | 241614020-Improvement of Chandipur-Hanuar Amtala Road by BC From Ch. 00-2080m | KDRIDP/Jess/W-125/2018-19 | 2.08 | 0 | 0 | 170 | 0 | 0 | 0 | 164.04 | 0% | 0 | 0 | 0 | 0 | 0% | 0
18 | 241614025-Improvement of Rajgonj Jamshed mill-Monohorpur Road From Ch. 1540-2106m. [Salvage Cost Tk. 51,999.00] | KDRIDP/Jess/W-41/2017-18 | 0.566 | 0 | 0 | 40.63 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 40.39 | 100% | 2019-06-28 | 40.367 | 40.367 | 0 | 99.94% | Final
19 | 241614041-Improvement of Mobarokpur Ghospara-Negura Bazar Road From Ch: 1895-3185m | KDRIDP/Jess/W-124/2018-19 | 1.29 | 0 | 0 | 105.34 | 2019-04-01 | M/s. Alom Enterprise, Keshobpur, Jessore | 2019-05-19 | 100.07 | 10% | 2020-05-01 | 0 | 0 | 0 | 0% | 0
20 | 241614048-Fakirrasta-Keshabpur via Hashadanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241614066-Kharinci-Rohita Shaikpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241614079-Improvement of Kashimpur Battala-Rohita U.P Road From Ch. 1250-3200m. [Salvage Cost Tk. 1,59,608.00] | KDRIDP/Jess/W-80/2017-18 | 1.95 | 0 | 0 | 139.45 | 2018-07-29 | Md Harun or Rashid, Nowapara Road, Ghop,Kotoali, Jessore. | 2018-05-09 | 146.27 | 100% | 2019-11-06 | 94.06 | 94.06 | 0 | 64.31% | Final
23 | 241614100-Subalkati Edgah-Lawkunda Sr.Madrasha | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 241614113-Improvement of Hazrakati Daspara More - Hazrakati Sanapara Road From Ch. 944-1985m. [Salvage Cost Tk. 1,86,215.00] | KDRIDP/Jess/W-42/2017-18 | 1.041 | 0 | 0 | 79.4 | 2017-10-29 | M/S Hira construction Main Road, Monirampur, Jessore | 2017-11-30 | 79.5 | 100% | 2018-12-30 | 78.944 | 78.944 | 0 | 99.3% | Final
25 | 241615035-Improvement of Parala-Satgati Road From Ch. 00-925m | KDRIDP/Jess/W-05/2016-17 | 0.925 | 0 | 0 | 61.07 | 2017-05-15 | M/S Hira Construction, Main Road Monirampur, Jessore | 2017-05-29 | 60.81 | 100% | 2018-04-28 | 59.575 | 59.575 | 0 | 97.97% | Final
26 | 241615071-Boalia Bazar-Uttarpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241615110-Improvement of Moshimnagor Charabattala-Vorotpur Road by BC From Ch. 1400-1650m. [Salvage Cost Tk. 1,04,669.00] | KDRIDP/Jess/W-123/2018-19 | 0.25 | 0 | 0 | 18.11 | 2019-03-28 | M/S. Diganta Enterprise, Agorhati, Laware, Monirumpur, Jessore | 2019-12-05 | 17.2 | 60% | 2020-02-19 | 0 | 0 | 0 | 0% | 0
28 | 241614076-Improvement of 8 mile(RHD)-Khahimnagor U.P. Road From Ch. 00-1780m. [Salvage Cost Tk. 10,61,912.00] | KDRIDP/Jess/W-38/2017-18 | 1.67 | 0 | 0 | 131.55 | 2017-10-30 | M/S L Rahaman Enterprise, R. N Road Jessore | 2017-11-26 | 130.25 | 100% | 2018-07-15 | 130.127 | 130.127 | 0 | 99.91% | Final
29 | 241615398-Improvement of Atghara purbopara - Amjamtola Road From Ch. 00-805m | KDRIDP/Jess/W-39/2017-18 | 0.805 | 0 | 0 | 57.11 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore | 2018-06-18 | 59.948 | 60% | 2019-05-05 | 0 | 24.8 | -24.8 | 41.37% | 0
30 | 241614060-Improvement of Lakhanpur Mandartala-Gouripur FWC Road From Ch. 00-470m | KDRIDP/Jess/W-40/2017-18 | 0.47 | 0 | 0 | 34.81 | 2017-10-25 | M/S Billal Hossain, Rail Road, Ashrom More, Jessore | 2017-12-21 | 34.96 | 100% | 2018-06-28 | 34.64 | 34.64 | 0 | 99.08% | Final
31 | Routia UP Bashdebpur bazar Torafdar Bostlay-Bashdebpur Dakil Madrasha & Attimkhana-Mathpara mono molla H/O road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 241615185-Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 00-1000m. [Salvage Cost Tk. 83,892.00] | KDRIDP/Jess/W-53/2017-18 | 1 | 0 | 0 | 75.93 | 2017-05-07 | Abdul Islam Atghora, Monirampur, Jessore | 2018-06-18 | 79.7 | 60% | 2019-04-24 | 0 | 21.7 | -21.7 | 27.23% | 0
33 | 241615185- Improvement of Basudevpur N/H/O Iman Ali-Saraskati via Basudevpur Madrasha Road From Ch. 1000-2095m | KDRIDP/Jess/W-92/2017-18 | 1.095 | 0 | 0 | 77.93 | 2018-04-09 | M/S Sajan Enterprise Chanchara Cheakpost Jessore | 2018-03-06 | 81.827 | 100% | 2019-03-03 | 80.755 | 80.755 | 0 | 98.69% | Final
34 | 241615336-Parkhaajura-Baroypara more-Garidkhali road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
35 | 241614089-Khedapara U.P.-Kasipur Mandertala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
36 | 241613020-Const. of RCC Bridge on Dhakuria UP- Gabukhali Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 241614070-Construction of 44.0m RCC Girder Bridge on Fakir Rasta-Pazia Road at Ch.500m | KDRIDP/Jess/W-31/2017-18 | 0 | 44 | 0 | 245.86 | 2017-10-23 | Kamarjani-Brojen-Anowara-JV, Sree Angoan, faridpur | 2017-11-30 | 221.27 | 100% | 2019-02-10 | 0 | 197.74 | -197.74 | 89.37% | 0
38 | 241615002-Const. of RCC Bridge onMujguni-Durgapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
39 | 241612011-Periodic Maintenance of Monirampur - Nowapara - Kultia -Nehalpur Road From Ch. 12410-12920m | KDRIDP/Jess/M-28/2018-19 | 0.51 | 0 | 0 | 25.869 | 2019-03-24 | M/S HIRA CONSTRACTION, Main road,Monirampur, Jessore | 2019-05-14 | 24.576 | 0% | 2019-11-17 | 0 | 0 | 0 | 0% | 0
40 | 241612014-Periodic Maintenance of Monoharpur Bazar-Chinatola Bazar Road From Ch. 00-3900m [Salvage Cost Tk.5,14,017.00] | KDRIDP/Jess/M-18/2017-18 | 3.9 | 0 | 0 | 147.2 | 2018-08-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-10-15 | 161.07 | 100% | 2019-05-20 | 0 | 121.85 | -121.85 | 75.65% | 0
41 | 241612015-Periodic Maintenance of Sundali Bazar-Dhakuria-Pramebag Gate Road From Ch. 5500-11920m. [Salvage Cost Tk.9,49,699.00] | KDRIDP/Jess/M-29/2018-19 | 6.42 | 0 | 0 | 292.7 | 0 | 0 | 0 | 261.123 | 0% | 0 | 0 | 0 | 0 | 0% | 0
42 | 241612019-Periodic Maintenance of Nehalpur-Durbadanga-Bajitpur Road From Ch. 2830-8690m. [Salvage Cost Tk.7,61,457.00] | KDRIDP/Jess/M-17/2017-18 | 5.86 | 0 | 0 | 249.06 | 2018-05-16 | M/S Bonantor Trading Corporation Benapol Road Chanchara, Jessore | 2018-06-24 | 261.418 | 100% | 2019-03-30 | 0 | 202.06 | -202.06 | 77.29% | 0
43 | 241613003-Ramnagar Bazar(Shyamkur)-Chaluahati UP via Pardia | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 241233002 : Navaran Puratan bazar-Chutipur bazar(Gongganandapur UP). | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 241233005 : Borni bzar(Panishara UP)-Bejiatala bazar. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 241233006 : Seordah GC-Moheshpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 241613018-Fakir Rasta bazar-Chaluahati UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 241612016-Lawri (Madrasha) RHD -Khedapara GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 241613001-Periodic Maintenance of Bhojgati UP-Basudevpur Bazar via Kashimnagar UP Road From Ch. 7580-8703m [Salvage Cost Tk.Tk.1,42,500.00] | KDRIDP/Jess/M-19/2017-18 | 1.123 | 0 | 0 | 26.38 | 2018-08-26 | M/S Ara Enterprise, Main Road, Monirampur | 2018-10-18 | 27.268 | 100% | 2019-02-21 | 0 | 22.62 | -22.62 | 82.95% | 0
50 | 241613010-Periodic Maintenance of Gopalpur Bazar-Kultia U.P.office Road From Ch. 00-4590m [Salvage Cost Tk.4,92,836.00] | KDRIDP/Jess/M-20/2017-18 | 4.59 | 0 | 0 | 122.29 | 2018-03-13 | M/S. Banantor Trading Corporation Benapol Road Chanchara, Jessore | 2018-04-15 | 128.4 | 100% | 2019-01-22 | 128.4 | 128.4 | 0 | 100% | Final
51 | 24164080-Khedapara-Maragacha via Gangulia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
52 | Construction of Parkhajura-Hat GC | KDRIDP/Jess/GC-15/2017-18 | 0 | 0 | 1 | 18.98 | 2018-02-08 | M/S Palash Enterprise, Nowapara, Abhoynagar, Jessore | 2018-03-04 | 17.559 | 90% | 2019-06-30 | 0 | 9 | -9 | 51.26% | 0
Tree Plantation
53 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 57.953 | 44 | 1 | 3733.625 |  |  |  | 3730.711 | 41.13% |  | 1155.818 | 2187.258 | -1031.44 | 58.63%

## Sarsa
Sarsa
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241902004-Improvement of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra Road From Ch.5064-7300m, 8725-9225m & 12150-15397m. [Salvage Cost Tk.18,35,766.00] | KDRIDP/Jess/W-33/2017-18 | 5.983 | 0 | 0 | 436.357 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 419.76 | 100% | 2019-05-30 | 0 | 295.98 | -295.98 | 70.51% | 0
Improvement of Union Road by BC
2 | 241903001-Improvement of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.10665-13520m. [Salvage Cost Tk.21,87,707.00] | KDRIDP/Jess/W-36/2017-18 | 2.855 | 0 | 0 | 171.625 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 165.09 | 100% | 2018-10-15 | 164.97 | 164.97 | 0 | 99.93% | Final
3 | 241903003-Kuchia More (Ulashi UP)-Dhaldah road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 241903004-Improvement of Dehi Union H/Q-Shikerpur Bazar via Fulsar Road From Ch.4480-6190m. [Salvage Cost Tk.2,04,049.00] | KDRIDP/Jess/W-34/2017-18 | 1.71 | 0 | 0 | 103.175 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 99.25 | 100% | 2018-10-15 | 99.234 | 99.234 | 0 | 99.98% | Final
5 | 241903008-Improvement of Benapole G.C-Bahadurpur UP H/Q via Ghiba Road From Ch.2545-7000m | KDRIDP/Jess/W-35/2017-18 | 4.455 | 0 | 0 | 268.13 | 2017-10-22 | Abdur Razzaque Navaran Rail Bazar, Sharsha, Jessore | 2017-11-19 | 265.08 | 100% | 2019-05-30 | 0 | 153.45 | -153.45 | 57.89% | 0
6 | 241903011-Goga Union H /Q-Khalshi bazar via Agrabhulat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241903016-Bahadurpur Union H/Q-Sharbunghuda Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241473020 Dehi Union H/Q –Wapda Bazar upto Kashipur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241903017-Improvement of Ulashi Union H/Q-Jamtala Bazar Via Benekhori. Road by BC From Ch.1350-2500m | KDRIDP/ Jess/W-137/ 2018-19 | 1.15 | 0 | 0 | 93.655 | 0 | 0 | 0 | 88.972 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by BC
10 | 241904003-Bagarchara (GC)-Basatpur Bazar rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 241904015-Improvement of Chandrapur-Belta Ghat Road by BC From Ch.3360-5000m [Salvage Cost. Tk. 22,10,761.00] | KDRIDP/ Jess/W-135/ 2018-19 | 1.64 | 0 | 0 | 118.657 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241904023-Improvement of Ulashi Debdar Tala-Jirengacha Road by BC From Ch.1439-3300m under Sarsha Upazila District Jessore [Salvage Cost. Tk. 8,91,495.00] | KDRIDP/ Jess/W-136/ 2018-19 | 1.861 | 0 | 0 | 136.86 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241904024-Ulashi Bazar Mosjheed R&H-Kannyadah Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241904026-Improvement of Kagojpukur-Dubpara Road by BC From Ch.3300-3680m | KDRIDP/Jess/W-134/2018-19 | 0.38 | 0 | 0 | 35.693 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241904061-Improvement of Bosotpur Madrasha-Baikola Road by BC From Ch.1667-3085m |  | 1.418 | 0 | 0 | 106.683 |  |  |  | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0!
15 | 241904043-Trimohini-Kulpala via Bolidadah road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241904046-Naihati-Dehi road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241904047-Improvement of Saratola High School-Tebaria Mosque via Daridurgapur Road by BC From Ch.1000-1805m. [Salvage Cost. Tk. 28,328.00] | KDRIDP/Jess/W-133/2018-19 | 0.805 | 0 | 0 | 72.15 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 241904002-Improvement of Ghiba Uttar para-Sharbunghuda bazar Road by BC From Ch.2000-2980m |  | 0.98 | 0 | 0 | 76.52 |  |  |  | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0!
18 | 241904048-Sikerpur-Salta road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241904052-Ekjhala Bazar-Kondarpopur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 241904115-Golapole More-Keshadanga Village Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241905198- Improvement of Sibobash Khalil's House-Shalkona Primary School road Via Sahid Shangbadic Shamsur Rahman House Road From Ch.00-1440m [Salvage Cost. Tk. 3,68,361.00] | KDRIDP/Jess/W-37/2017-18 | 1.44 | 0 | 0 | 91.38 | 2017-10-17 | M/S Ashraf Traders Voirob stand, Haspatal Ghat, Khulna | 2017-12-26 | 95.041 | 100% | 2018-11-16 | 0 | 71.15 | -71.15 | 74.86% | 0
Improvement of Village Road by HBB
22 | 241904105-Improvement of Nizampur Bazar-Bahadurpur Road From Ch.2643-4718m. [Salvage Cost Tk.45,344.00] | KDRIDP/Jess/W-32/2017-18 | 2.075 | 0 | 0 | 75.315 | 2017-10-17 | M/S Asraf Traders, Voirob Road, Haspatal Ghat, Khulna | 2017-12-26 | 75.3 | 100% | 2018-11-16 | 74.58 | 74.58 | 0 | 99.04% | Final
Maintenance
23 | 241902004-Periodic Maintenance of Baganchra GC (Moynar Battala) -Benapole GC via Sati More, Balunda, Brittianchra. Road From Ch.00-2225m,9225-10413m &10886-12150m | KDRIDP/Jess/M-06/2017-18 | 4.677 | 0 | 0 | 203.2 | 2018-02-26 | Abdur Razzaque Navaron Rail Bazar, Sharsha, Jessore | 2018-10-04 | 223.52 | 100% | 2019-09-01 | 223.44 | 223.44 | 0 | 99.96% | Final
24 | 241903001-Periodic Maintenance of Sharsha Upazila H/Q-Bahadurpur Bazar via Bahadurpur UP H/Q. Road From Ch.206-2783m,5060-6785m, 8341-9471m &9665-10665m | KDRIDP/Jess/M-05/2017-18 | 6.432 | 0 | 0 | 160.54 | 2018-05-20 | Md. Oahiduzzaman Navaron Rail Bazar, Sarsha, Jessore | 2018-06-25 | 168.49 | 100% | 2019-05-23 | 168.43 | 168.43 | 0 | 99.96% | Final
25 | 241903007-Sarsha Upazila H/Q- Saratala Bazar via Laxmnpur U H/Q Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 241903008-Benapole GC-Bahadurpur YP H/Q via Ghiba Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 241903018-Baguri R&H -Kayba Union H/Q via Mohisha Madrasha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 241904070-Saratola Bazar-Beltaghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 37.861 | 0 | 0 | 2149.94 |  |  |  | 1600.503 | 25.81% |  | 730.654 | 1251.234 | -520.58 | 78.18%

## Abhoynagar
Abhoynagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241042005-Nowapara Upazila H/Q (Sankerpasha Bazarghat)-Amtala GC via Vatpara Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241042012-Nowapara GC (Shankerpasha Ghat)-Gobra GC via Borni Bazer road From Ch. 293-2845m [Salvage Cost Tk. 46,26,515.00] | KDRIDP/Jess/W-76/2017-18 | 2.552 | 0 | 0 | 199.92 | 2018-02-19 | Md. Abdur Rouf Molla, Bhoakhali, Ratangonj, Narail | 2018-04-18 | 177.14 | 100% | 2018-01-09 | 0 | 124.566 | -124.566 | 70.32% | 0
3 | 241042012-Improvement of Nowapara GC (Shankerpasha Ghat)-Gobra GC via Borni Baze Road By BC From Ch. 8073-9098m. [salvage Cost Tk.25,44,253.00] | KDRIDP/Jess/W-126/2018-19 | 1.025 | 0 | 0 | 103.02 | 0 | 0 | 0 | 97.87 | 0% | 0 | 0 | 0 | 0 | 0% | 0
Improvement of Union Road by BC
4 | 241043002-Improvement of Chengutia Bazar-Sreedharpur UP Office Road From Ch. 1217-3600m | KDRIDP/Jess/W-01/2016-17 | 2.383 | 0 | 0 | 144.16 | 2017-05-15 | Md. Abdur Rouf Molla , Bhoakhali, Ratangonj, Narail | 2017-07-06 | 150.3 | 100% | 2018-04-30 | 150.285 | 150.285 | 0 | 99.99% | Final
5 | 241043004-Nowapara H/Q (Peer Bari Kheya ghat)-Baghutia U.P. Office via Maddhapur Pry.School ,Bogratala Mosque & Chow matha,Vatpara Gramin Bank Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241043006-Paira U.P.Office-Chalisha U.P.Office (Bagdah Dharmatala Eid-gah) via Kuta madrasha,Bagdah Paschimpara Baltala More Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 241043007-Sundali U.P.Office-Moshihati Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241043010-Baghutia UP office-Singari Bazar via Singari Dakhil Madrasha Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | BTMC ghat -Barni Bazar via Sreedarpur UP Complex Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
10 | 241044003-Improvement of Nowapara Betar South Corner R&H-Dumurtala via Dhopadi Road From Ch. 4175-5000m | KDRIDP/Jess/W-02/2016-17 | 0.825 | 0 | 0 | 51.38 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 05/03/2018 [5th Called]
11 | 241044004-Noapara North Bengal(Bengal Textile)-Gobindapur Thrimohony via Dhopapara primary school Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241044006-Taltala-Gramtala via Ektarpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 241044010-Paira(Kota Eayler More)-Kuta Shoyailer ghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241044018-Nowly Bazar-Hanorgari Ghat via Madhur Dokan Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241044019-Rajghat R&H-Bakardanga via Gazipur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 241044023-Bashuari more(UZR)-Suvarara River Ghat via Dighirpar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241044024-Ichamoti UZR-Peruli Gc Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241044026-Arpara UZR(Prembag More)-Zialtala Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 241044035-Magura Gabukhali Collage-Joyanta via Dholergati school Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 241044036-Chengutia Baruari Mondir-Beel Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 241044043-Nowly High school UZR-Beelkul Totarmatha via Nowly Mollik bari Jame-Mosque & Biswas Bari Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 241044050-Barandi Fakirhat Bazar-Takerghat road via WAPDA Office. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241045086-Ranaghati Khayghat - Bhugilhat Mor Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 241045230-Nowly Biswas para-Mosque road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 241045516-Improvement of Nowly Momin Biswas house - Mir Bari Tematha Road From Ch. 00-412m | KDRIDP/Jess/W-109/2018-19 | 0.412 | 0 | 0 | 31.977 | 2019-01-21 | M/S SHARIFUL ISLAM, Arappur, Jhenaidah | 2019-03-11 | 30.378 | 0% | 2019-07-25 | 0 | 0 | 0 | 0% | 0
| 241045613-Improvement of Nowly Golamar Bari more-Tatultala Ghat Road From Ch. 00-500m [Salvage Cost Tk. 1,40,131.00] |  | 0.5 | 0 | 0 | 39.95 |  |  |  | 37.953 |  |  | 0 | 0 | 0 | 0% | 0
26 | 241045406-Improvement of Bagutia Palpara Puja mondir- Mojibor house Road From Ch. 00-634m [Salvage Cost Tk. 58,042.00] | KDRIDP/Jess/W-107/2018-19 | 0.634 | 0 | 0 | 49.738 | 0 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2019-01-08 | 47.25 | 0% | 2019-10-15 | 0 | 0 | 0 | 0% | 0
| 241045188-Improvement of Baghutia Bridge-Baghutia Dhakinpara Mosque Road From Ch. 00-1550m. |  | 1.55 | 0 | 0 | 122.619 |  |  |  | 116.488 |  |  | 0 | 0 | 0 | 0% | 0
27 | 241044022 Improvement of Abhoynagar Puraton Kheya Ghat-Shibnagor UZR(N/H/O Kalachand) via Bogratala Mosque Road From Ch.584-2560 m. [salvage Cost Tk. 3,17,894.00] | KDRIDP/Jess/W-110/2018-19 | 1.976 | 0 | 0 | 153.01 | 2018-11-20 | Sonali Bricks Manufacture, Nowapara, Abhoynagar, Jessore | 2019-01-15 | 145.36 | 40% | 2019-10-21 | 0 | 0 | 0 | 0% | 0
28 | 241044062 Improvement of Horishpur Reg.Primary school-Magura G.C. via Ramsara chowmatha, shishutala Road From Ch. 2435-4130m. [salvage Cost Tk. 8,78,194.00] | KDRIDP/Jess/W-62/2017-18 | 1.695 | 0 | 0 | 117.66 | 2018-08-27 | M/S Biswajit Construction, 9 Rail Road, Jessore | 2018-10-15 | 122.78 | 100% | 2019-05-20 | 122.71 | 122.71 | 0 | 99.94% | Final
29 | 241044069-Improvement of Gopinathpur Village-Dokhanpara Abdul Gofur khan shope-Batiul Nure Jame Mosque Road From Ch. 00-775m. [Salvage Cost Tk. 3,85,651.00] | KDRIDP/Jess/W-63/2017-18 | 0.775 | 0 | 0 | 53.47 | 2018-02-05 | B.M Rafiqul Islam, Dariyapur, Narial Sadar, Narial | 2018-03-12 | 57.49 | 60% | 2018-12-13 | 0 | 15.42 | -15.42 | 26.82% | 0
30 | 241044066- Improvement of Bhabadha Sluice gate-Zamira UZR. Road From Ch.00-3160m [Salvage Cost Tk. 82,42,535.00] | KDRIDP/Jess/W-111/2018-19 | 3.16 | 0 | 0 | 239.59 | 2018-11-18 | M/S Joy Enterprise, 16 Hazi Abul Karim Road, Jessore | 2019-01-08 | 227.615 | 0% | 2019-10-15 | 0 | 0 | 0 | 0% | 0
31 | 241045137- Improvement of Dattagati WAPDA Road near the house of Ashu babu- Dattagati East para Culvert Road From Ch. 00-290m [Salvage Cost Tk. 7,49,493.00] | KDRIDP/Jess/W-108/2018-19 | 0.29 | 0 | 0 | 22.079 | 2018-11-18 | M/S Jony Enterprise, 16 Hazi Abul Karim Road, Jessore | 2019-01-08 | 20.975 | 15% | 2019-10-10 | 0 | 0 | 0 | 0% | Tender will be Recceived on Dated 25/06/2018
| 241044039- Improvement of Takerghat-Kapalia bazar via Bhabadha Sluice gate, College & kalishakul Bazer Road From Ch. 3300-5300m [Salvage Cost Tk. 62,45,075.00] |  | 2 | 0 | 0 | 175.127 |  |  |  | 166.371 |  |  | 0 | 0 | 0 | 0%
Improvement of Village Road by HBB
32 | 241044060-Dhulgram Club-Siddipasha U.P.Office(Nowly Bazar) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
33 | 241042005-Nowapara Upazila H/Q- Amtala GC via Vatpara Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 241042009-Alipur RHD-Sundali GC via Rajapur more Ramsaradham, Arpara Clinic more, Harishpur RNGPS Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 241043001-Noapara HQ(BTMC Ghat)-Borni Bazar via Sreedharpur UP Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 241043007-Periodic Maintenance of Sundali U.P.Office-Moshihati Bazar Road From Ch.00-3050m | KDRIDP/Jess/M-07/2017-18 | 3.05 | 0 | 0 | 68.045 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 31/07/2018
37 | 241043009-Periodic Maintenance of Siddipasha UP Office (Nowly Bazer)-Phultala G.C. via Dhulgram kheya Ghat Road From Ch.00-2280m | KDRIDP/Jess/M-32/2018-19 | 2.28 | 0 | 0 | 76.566 | 2019-04-10 | M/S.Palash Enterprise, 1488, Buinkara, Nowapara, Abhaynagar, Jessore | 2019-05-19 | 72.738 | 0% | 2019-12-22 | 0 | 0 | 0 | 0% | 0
38 | 241044005-Periodic Maintenance of Taltala Bazar-Dumortala road via Sirajkati,Chalishia Rishipara Chourasta More Road From Ch.00-5310m | KDRIDP/Jess/M-08/2017-18 | 5.31 | 0 | 0 | 162.81 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 241044017-Hidia Madrasha UZR- Kharoria Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 241044039-Takerhat-Kapalia Bazarvia Bhabadha Sluicegate Collage & Kalishakul Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 241044063-Rajapur More- Magura Madrasha more UZR via Sishutala Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 241044066-Bhabadha Sluicegate -Zamira UZR Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
43 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 30.417 | 0 | 0 | 1811.121 |  |  |  | 1470.708 | 9.651% |  | 272.995 | 412.981 | -139.986 | 28.08%

## Bagherpara
Bagherpara
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 241092006-Simakhali RHD-Narikelbaria GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 241092011-Dhalgram GC- Maijpara UP to Kalukhali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 241092014-Improvement of Narikelbaria GC Bunagati GC (Shersha Sarak) Road. From Ch: 700-3270m. [salvage Cost Tk.20,890.00] | KDRIDP/Jess/W-96/2017-18 | 2.57 | 0 | 0 | 199.065 | 2018-08-20 | M/S Biswas Construction, Puraton Kashba, Jashore | 2018-10-18 | 208.998 | 20% | 2019-07-25 | 0 | 27.88 | -27.88 | 13.34% | 0
4 | 241092018 Improvement of Narikelbaria GC - Monohorpur Bazar RHD at Joynagor More via Raypur UP (Bagherpara Part) Road. From Ch: 406-4144m,5400-5987m & 6372-7057m. [salvage Cost Tk.95,88,834.00] | KDRIDP/Jess/W-67/2017-18 | 5.01 | 0 | 0 | 396.55 | 2018-07-12 | Rafia Construction Ltd, Brammonkandi,Sreeongon,Faridpur. | 2018-09-06 | 436.16 | 50% | 2019-07-22 | 0 | 91.86 | -91.86 | 21.06% | 0
Improvement of Union Road by BC
5 | 241093003-Bandabila UP- Puinerhat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 241093008-Improvement of Joharpur up office-Betalpara Bazar Road. From Ch: 1900-3250m. [salvage Cost Tk.5,096.00] | KDRIDP/Jess/W-97/2017-18 | 1.35 | 0 | 0 | 99.547 | 2018-05-21 | M/S Monir Traders Natun Khayertala, Jessore | 2018-06-24 | 104.5 | 100% | 2019-03-30 | 0 | 42.81 | -42.81 | 40.97% | 0
| 241093010-Improvement of Raipur UP Office-Vater bazar Road. From Ch: 3611-3997m & 4689-5620m. [salvage Cost Tk.24,19,116.00] |  | 1.317 | 0 | 0 | 87.845 |  |  |  | 92.22 |  |  | 0 | 37.78 | -37.78 | 40.97%
7 | 241093013-Vangura RHD.-Dhalgram UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 241093014-Improvement of Vangura RHD.-Basundia UP. Road. From Ch: 4778-6204m [salvage Cost Tk.9,02,090.00] | KDRIDP/Jess/W-132/2018-19 | 1.426 | 0 | 0 | 110.7 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 241093017-Simakhali UP- Johurpur UP via Betalpara Bazar, Premchara. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 241093018-Dhalgram UP- Garerhat Bazar via Antaikhola | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
11 | 241094005-Indra- Azmeherpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 241094010-Improvement of Narikelbaria (Salikha Upazila) – Paschima Das Para More Road. From Ch: 500-1300m | KDRIDP/Jess/W-98/2017-18 | 0.8 | 0 | 0 | 49.66 | 2018-08-20 | M/S. Hridoy Construction, 147 Ghop, Noapara, Kotwali,Jashore. | 2018-10-18 | 51.646 | 50% | 2019-07-24 | 0 | 0 | 0 | 0% | 0
13 | 241094018-Satiantala bazar to RHD at Dadpur bazar via Sayed Mahmudpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 241094020-Khanpur Bazer-Indra Bazer (Khanpur Freedom Fiter Gopal House-Rahaman House) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 241094028-Improvement of Paschima H/O Shariful - Dari Agra Via Napte More Road from Ch: 00-800m & 3132-3963m. [salvage Cost Tk.93,148.00] | KDRIDP/Jess/W-130/2018-19 | 1.631 | 0 | 0 | 116.9 | 2019-04-02 | M/S SHARIFUL ISLAM, Arappur, Jhenaidah | 2019-05-19 | 111.055 | 0% | 2020-02-25 | 0 | 0 | 0 | 0% | 0
16 | 241094034-Kadamtola- Bandabila hat | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 241095145-Punihar Battala- Sreerampur High School Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 241095284-Improvement of Kundupara Senbari- Tapan Master house[Inventory Name ;-Narikelbaria Senbari - Narikelbaria North Para via Narikelpara kundupara Mandir] Road. From Ch: 00-710m. | KDRIDP/Jess/W-86/2017-18 | 0.71 | 0 | 0 | 63.405 | 2018-08-29 | M/S.Abdul Alim & Sons, Mohiram, Bagherpara, Jashore | 2018-10-11 | 66.1 | 60% | 2019-07-17 | 0 | 33.32 | -33.32 | 50.41% | 0
19 | 241095127 Improvement of Madhyapara Mosque RHD (jessore-Narial)-Joka [Inventory Name ;-RHD Rashid Karimpur H/O Omar Molla Khalshi] Road. From Ch: 00-1696m. [salvage Cost Tk.25,76,452.00] | KDRIDP/Jess/W-93/2017-18 | 1.12 | 0 | 0 | 85.779 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Tender will be Recceived on Dated 10/04/2018
20 | 241095285-Khetrapara School -Hablapara Shawkat's House Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
21 | 241095221-Ramkrishnapur Bazar-Silumpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
22 | 241092003-Jessore Narail RHD-Dhalgram more- Narikelbaria via Dhalgram Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 241092011-Periodic Maintenance of Dhalgram GC.-Maijpara Up to Kalukhali Road From Ch.00-2265m | KDRIDP/Jess/M-26/2017-18 | 2.265 | 0 | 0 | 61.248 | 2018-05-11 | M/S Biswas Construction, 134 Dhaka Road, Puraton Kashba, Jessore | 2018-05-28 | 64.206 | 100% | 2019-02-03 | 64.153 | 64.153 | 0 | 99.92% | Final
Tree Plantation
24 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 18.199 | 0 | 0 | 1270.699 |  |  |  | 1134.885 | 15.83% |  | 64.153 | 297.803 | -233.65 | 26.24%

## Summary
JESSORE
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 10 | 8 | 25.454 | 0 | 0 | 1622.768 | 767.162 | 81.43% | 47.27%
Union Road by BC | 37 | 31 | 75.832 | 0 | 0 | 4560.417 | 2665.97 | 77.24% | 58.46%
Village Road by BC | 79 | 64 | 96.999 | 0 | 0 | 5505.519 | 2308.876 | 65.8% | 41.94%
Village Road by HBB | 1 | 1 | 2.075 | 0 | 0 | 75.315 | 74.58 | 100% | 99.04%
Bridge on Upazila Road | 1 | 1 | 0 | 138 | 0 | 791.63 | 197.74 | 50% | 24.98%
Bridge on Union Road/Village Road | 2 | 1
Maintenance | 31 | 28 | 87.714 | 0 | 0 | 2822.957 | 1885.672 | 78.45% | 66.8%
GC-Hat | 1 | 1 | 0 | 0 | 1 | 17.559 | 9 | 90% | 51.26%
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 162 | 135 | 288.074 | 138 | 1 | 15396.165 | 7909 | 67.86% | 51.37%