## Narail
NARAIL
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Narail Sadar
1 | 265762006-Singa Solepur-Khororia Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Improvement of Union Road by BC
Narail Sadar
1 | 265763003-Nakosi - Sarkeldanga Rd. | [13 empty] | 0 | #DIV/0!
2 | 265763005-Shahabad UP-Hobokhali U.P Rd. | [13 empty] | 0 | #DIV/0!
3 | 265763012-Improvement of Shimakhali RHD – via Kurulia Village- Chandibarpur UP Road (Ch-00-1359m & 8150m-10800m) by BC | KDRIDP/Narail/W-13/2016-17 | 4.009 | 0 | 0 | 227.69 | 2017-07-12 | AKM Akramuzzaman Bhanga, Faridpur | 2017-10-02 | 52.616 | 25% | 2018-12-31 | 35.39 | 35.39 | 0 | 67.26% | Contract Cancelled (Partial Payment Done)
4 | 265763013-Improvement of Maizpara UP- Gorerhat Road (Narail-S part) from Ch. 2200m - 3450m | KDRIDP/Narail/W-18/2017-18 | 1.25 | 0 | 0 | 76.9 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 77.58 | 100% | 2018-11-14 | 77.534 | 77.534 | 0 | 99.94% | Final
Lohagara
5 | 265523005-Improvement of Manikgonj Bazar – Lahuria UP Road (Ch-5865m-7725m) by BC | KDRIDP/Narail/W-01/2016-17 | 1.86 | 0 | 0 | 104.97 | 2017-07-03 | M/S Shimul Enterprise, Madhukhali, Faridpur | 2017-08-22 | 98.607 | 100% | 2019-02-21 | 96.03 | 96.03 | 0 | 97.39% | Final
6 | 265523006-Improvement of Naldi UP-Lahuria Road Ch. 2100-7020m. Salvage Cost Tk. 142650.00 | KDRIDP/Narail/W-14/2017-18 | 4.92 | 0 | 0 | 293.31 | 2017-09-26 | M/S Lipu Enterprise, Kanaipur, Faridpur | 2017-11-13 | 274.94 | 50% | 2019-05-24 |  | 94.27 | -94.27 | 34.29% | WBM Ongoing
Kalia
7 | 265283002-Kalabaria UP office-Beeldhuria Hat Rd. | [13 empty] | 0 | #DIV/0!
8 | 265283005-Babra R&H-Suktogram Bazer Rd.(Proposed name Babra UP Office- Suktogram Bazer) | [13 empty] | 0 | #DIV/0!
9 | 265283006- Improvement of Babra UP Office via Chanchuri UP Office - Dadontala RHD Road by BC from Ch 00m - 5100m. | KDRIDP/Narail/W-30/2017-18 | 5.1 | 0 | 0 | 392.64 | 2019-04-29 | M/S Jakaullah & Brothers, Chuadanga |  | 392.423 | 0% |  |  |  | 0 | 0% | NOA under Process
10 | 265283007-Khasial UP office-Patnabazar (Talbaria) | [13 empty] | 0 | #DIV/0!
11 | 265283008-Improvement of Chapail UZR – Bagudanga Bazar Road (Ch-700m-1061m) by BC | KDRIDP/Narail/W-07/2016-17 | 0.361 | 0 | 0 | 22.34 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 20.16 | 100% | 2018-05-15 |  | 18.5 | -18.5 | 91.77% | Work Completed
Total |  |  | 17.5 | 0 | 0 | 1117.85 |  |  |  | 916.326 | 62.5% |  | 208.954 | 321.724 | -112.77 | 35.11%
Improvement of Village Road by BC
Narail Sadar
1 | 265764022-Improvement of Mathabhanga – Nondahkol (House of Bejoy Sarker) Road (Ch-1000m-2100m) by BC | KDRIDP/Narail/W-31/2018-19 | 1.1 | 0 | 0 | 90.789 | 2018-10-28 | Md. Abdur Rouf Molla, Narail | 2019-01-22 | 90.51 | 100% | 2019-06-20 |  | 86.76 | -86.76 | 95.86% | Work Completed
| 265764026- Improvement of Baliadanga – Ramchandrapur Road (Ch-1206m-3045m) by BC | KDRIDP/Narail/W-31/2018-19 | 1.839 | 0 | 0 | 134.807 |  | Md. Abdur Rouf Molla, Narail |  | 134.39 |  |  |  | 128.84 | -128.84 | 95.87% | Work Completed
3 | 265764049- Rukhali Bazar (up office)-Akdia char FRB Road | [13 empty] | 0 | #DIV/0!
4 | 265764057- Improvement of Chanchra RHD – Benahati Road (Ch-2456m-3494m) by BC | KDRIDP/Narail/W-05/2016-17 | 1.038 | 0 | 0 | 63.64 | 2017-09-26 | M/S Islam Traders Jessore | 2017-11-10 | 63.26 | 100% | 2018-05-15 |  | 55.86 | -55.86 | 88.3% | Work Completed
5 | 265764059- Garuchira - Alukdia UP office Road | [13 empty] | 0 | #DIV/0!
6 | 265764061-Birgram R&H-Mulia UP office Rd. | [13 empty] | 0 | #DIV/0!
7 | 265764066-Improvement of Maizpara - Dhalgram Road from Ch 00m - 161m & Ch-1440m - 2440m | KDRIDP/Narail/W-21/2017-18 | 1.161 | 0 | 0 | 82.15 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 76.987 | 100% | 2018-11-21 | 76.9 | 76.9 | 0 | 99.89% | Final
8 | 265764071-Chakoi chowmatha-Bichali FRB Rd | [13 empty] | 0 | #DIV/0!
9 | 265764073- Improvement of Doulatpur-via Hosinpur Grave Yeard – Boramara river side Road (Ch-1600m-2720m) by BC | KDRIDP/Narail/W-06/2016-17 | 1.12 | 0 | 0 | 65.44 | 2017-07-03 | M/S MA Enterprise Bhanga, Faridpur | 2017-08-16 | 63.48 | 50% | 2018-05-31 |  | 7.46 | -7.46 | 11.75% | WBM Ongoing
10 | 265765006-Peroli River side Road | [13 empty] | 0 | #DIV/0!
11 | 265765009-Improvement of Malidanga Village Road from Ch 00m- 825m | KDRIDP/Narail/W-20/2017-18 | 0.825 | 0 | 0 | 54.31 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 54.28 | 100% | 2018-05-31 |  | 18.33 | -18.33 | 33.77% | Work Completed
12 | 265764002-Improvement of Jangelgram - Chandiborpur Road from Ch. 802m - 4359m | KDRIDP/Narail/W-25/2017-18 | 3.557 | 0 | 0 | 206.66 | 2018-02-28 | M/S Eden Prise, Mohishkhola, Narail | 2018-04-04 | 215.21 | 70% | 2019-04-10 |  | 108.784 | -108.784 | 50.55% | WBM Completed
13 | 265765310-Improvement of Sonkorpur GPS west side - Pazarkhali Road from Ch. 00m - 630m | KDRIDP/Narail/W-26/2017-18 | 0.63 | 0 | 0 | 38.2 | 2018-01-10 | M/S kailash Construction | 2018-02-22 | 38.96 | 70% | 2018-09-02 |  | 26.988 | -26.988 | 69.27% | WBM Completed
14 | 265765152-Improvement of Mathabhanga - Hogladanga Road from Ch 00m-1150m. | KDRIDP/Narail/W-22/2017-18 | 1.15 | 0 | 0 | 72.23 | 2017-10-02 | BM. Rafiqul Islam, Rupgonj Bazar, Narail | 2017-11-12 | 72.12 | 100% | 2018-10-16 | 72.117 | 72.117 | 0 | 100% | Final
15 | 265765241-Improvement of Soraspur Pucca Road - Narayanpur Shahid Freedom Fighter Shofiuddin Khan House Road from Ch. 00m -1982m | KDRIDP/Narail/W-27/2017-18 | 1.982 | 0 | 0 | 123.898 | 2018-02-04 | M/S Moni Construction | 2018-02-26 | 133.892 | 100% | 2019-03-12 |  | 118.89 | -118.89 | 88.8% | Work Completed
16 | 265765322-Chorbilla Govt.Primary School-Dokkin-Kali bari khayghat road. | [13 empty] | 0 | #DIV/0!
17 | 265765113-Hobokhali VILLAGE ROAD.(Hobokhali H/O Nayeb Master-Narial Magura link road. | [13 empty] | 0 | #DIV/0!
18 | 265765086- Improvement of Moyenkhola - Charbila Road from Ch. 00m- 1450m | KDRIDP/Narail/W-19/2017-18 | 1.45 | 0 | 0 | 91.3 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 86.02 | 100% | 2018-11-21 | 85.94 | 85.94 | 0 | 99.91% | Final
19 | 265765072- Improvement of Ghorakhali sholua Road Ch. 482-1560m | KDRIDP/Narail/W-16/2017-18 | 1.078 | 0 | 0 | 62.91 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 58.97 | 31% | 2018-06-17 |  |  | 0 | 0% | Contract Cancelled
20 | 265765259-Hosenpur Rostum Sikder Bari-Kayem Biswas Bari road. | [13 empty] | 0 | #DIV/0!
Lohagara
21 | 265524001-Lahuria Bazar-Chimanarchar Rd. | [13 empty] | 0 | #DIV/0!
22 | 265524009 - Lohagara Bazar -Char Korfa Rd | [13 empty] | 0 | #DIV/0!
23 | 265524016-Raghunathpur-Taltala Satrahazari bazar Rd. | [13 empty] | 0 | #DIV/0!
24 | 265524005-Lohagara Bazar - Char Korfa Road | [13 empty] | 0 | #DIV/0!
25 | 265524026-Improvement of Sattrahazari Bazar – Brammondanga Bazar Road (Ch-3500m-5930m)by BC | KDRIDP/Narail/W-02/2016-17 | 2.43 | 0 | 0 | 131.8 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 123.89 | 0% | 2018-05-31 |  |  | 0 | 0% | Contract Cancelled
26 | 265524055-Radhanagar Bazar bridge - Kumardanga bazar Road | [13 empty] | 0 | #DIV/0!
27 | 265525005-Improvement of Bhadradanga - Makrail Road from Ch.1680m - 3000m | KDRIDP/Narail/W-28/2017-18 | 1.32 | 0 | 0 | 78.42 | 2018-02-04 | M/S Fakir Enterprise | 2018-02-14 | 85.47 | 100% | 2018-11-30 |  | 76.54 | -76.54 | 89.55% | Work Completed
28 | 265524062-Improvement of Dinanathpara – Gobindapur Road from Ch. 610m - 1370m. | KDRIDP/Narail/W-29/2017-18 | 0.76 | 0 | 0 | 50.12 | 2018-02-28 | M/S Rupali Construction, Kalibari Road, Barisal | 2018-04-08 | 51.629 | 15% | 2018-09-16 |  |  | 0 | 0% | ISG Ongoing
29 | 265525222-Makrail Mujam Molla H/O - Mukter Shikder house Road | [13 empty] | 0 | #DIV/0!
30 | 265525508-Improvement of Mait Kumra C&B road H/O Akkas Master-H/O Lutfor Rahman via Nazrul Ahmed House Road Ch. 00-530m. Salvage Cost Tk. 617629.00 | KDRIDP/Narail/W-15/2017-18 | 0.53 | 0 | 0 | 31.25 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 28.667 | 37% | 2018-02-28 |  | 9.28 | -9.28 | 32.37% | Contract Cancelled
31 | 265525226-Kamil Madrasha road. | [13 empty] | 0 | #DIV/0!
32 | 265524042-Improvement of Jalalshe Maddrasha - Char Bramman Danga Road from Ch. 00m - 1740m | KDRIDP/Narail/W-24/2017-18 | 1.74 | 0 | 0 | 104.77 | 2017-10-09 | M/S Fakir Enterprise, Lohagara, Narail | 2017-11-27 | 103.76 | 100% | 2018-11-30 | 101.908 | 101.908 | 0 | 98.22% | Final
Kalia
33 | 265284002-Baddyabati hat-Mirzapur Rd | [13 empty] | 0 | #DIV/0!
34 | 265284008-Raghunathpur Sumarkhola WDB Embk. | [13 empty] | 0 | #DIV/0!
35 | 265284015-Jogania-sachiadha via Kachuadanga road. | [13 empty] | 0 | #DIV/0!
36 | 265284036-Hamidpur (Silimpur)-Chalitatala Rd. | [13 empty] | 0 | #DIV/0!
37 | 265284037-Peroli Hat-Kharoria Mollabari Bazer Via Kharoria Abashan Rd. | [13 empty] | 0 | #DIV/0!
38 | 265285001-Harishpur-Hadayetpur | [13 empty] | 0 | #DIV/0!
39 | 265285012-Improvement of Kathadura – Chanderchar WDB Road (Ch-700m-1815m) by BC | KDRIDP/Narail/W-08/2016-17 | 1.115 | 0 | 0 | 60.43 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-20 | 57.11 | 100% | 2018-05-15 | 55.888 | 55.89 | -0.002 | 97.86% | Final
40 | 265285057-Improvement of Kamshia Village Road (Ch-00m-1250m) by BC | KDRIDP/Narail/W-11/2016-17 | 1.25 | 0 | 0 | 70.76 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 63.72 | 70% | 2018-05-15 |  | 37.385 | -37.385 | 58.67% | WBM Completed
41 | 265285016-Improvement of Putimary – Panipara Road (Ch-700m-1116m) by BC | KDRIDP/Narail/W-09/2016-17 | 0.416 | 0 | 0 | 25.33 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 22.86 | 100% | 2018-05-15 | 22.848 | 22.848 | 0 | 99.95% | Final
42 | 265285044-Improvement of Khashial – Uttar Khashial Road (Ch-500m-1150m) by BC | KDRIDP/Narail/W-10/2016-17 | 0.65 | 0 | 0 | 35.89 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-24 | 32.39 | 100% | 2018-05-15 | 32.35 | 32.35 | 0 | 99.88% | Final
43 | 265285072-Dumuria-Dudkuria Rd. | [13 empty] | 0 | #DIV/0!
44 | 265285137-Improvement of Patna Bridge – Kalinagar (Kalinagar UZR – Naldanga Loboner Kheyaghat) Road (Ch-1620m-3200m) by BC | KDRIDP/Narail/W-12/2016-17 | 1.58 | 0 | 0 | 89.63 | 2017-07-05 | M/S Ruma Enterprise Kalia, Narail | 2017-08-16 | 88.63 | 100% | 2018-03-24 | 87.74 | 87.742 | -0.002 | 99% | Final
45 | 265285149-Improvement of Baoisona Boroghat - Kanaypur Road (Ch-00m-1000m) by BC. | KDRIDP/Narail/W-17/2017-18 | 1 | 0 | 0 | 63.197 | 2017-10-02 | M/S Ruma Enterprise Kalia, Narail | 2017-11-22 | 57.2 | 100% | 2018-09-28 | 57.01 | 57.01 | 0 | 99.67% | Final
Total |  |  | 29.721 | 0 | 0 | 1827.931 |  |  |  | 1803.405 | 79.23% |  | 592.701 | 1267.822 | -675.121 | 70.3%
Improvement of Village Road by HBB
Narail Sadar
1 | 265764045-Improvement of Burikhali RHD - Charshalikha Road by HBB from Ch 1472m - 2137m | KDRIDP/Narail/W-23/2017-18 | 0.665 | 0 | 0 | 22.417 | 2017-10-02 | M/S Eden Prise Mohiskhola Narail | 2017-10-30 | 21.3 | 100% | 2018-02-28 | 21.3 | 21.3 | 0 | 100% | Final
Lohagara
2 | 265524030-Kalagachi bazar-Manikgonj bazar Rd. | [13 empty] | 0 | #DIV/0!
Kalia
3 | 265284018-Kalabaria-Patna Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0.665 | 0 | 0 | 22.417 |  |  |  | 21.3 | 100% |  | 21.3 | 21.3 | 0 | 100%
Construction of Bridge on Upazila Road (7.30m width)
Narail Sadar
1 | 265762007- Construction of 30m RCC Girder Bridge on Gabtala R&H - Maizpara GC Road at Ch-2000m | KDRIDP/Narail/B-01/2017-18 | 0 | 30 | 0 | 199.79 | 2018-07-09 | SDMSjandbjv Haque para, Chuadanga | 2018-08-30 | 188.98 | 35% | 2019-09-07 |  | 48.95 | -48.95 | 25.9% | Pile Work Completed
Total |  |  | 0 | 30 | 0 | 199.79 |  |  |  | 188.98 | 35% |  | 0 | 48.95 | -48.95 | 25.9%
Construction of Bridge on Union Road/Village Road (5.50m width)
Narail Sadar
1 | 265763007-Construction of 30m RCC Girder Bridge on Singasolpur - Chakoi via Rukhali Road at Ch-3405m | KDRIDP/Narail/B-02/2017-18 | 0 | 30 | 0 | 224.488 | 2018-07-09 | SDMSjandbjv Haque para, Chuadanga | 2018-08-30 | 224.2 | 45% | 2019-09-07 |  | 85.438 | -85.438 | 38.11% | Abut. & Pier Base Casting Completed
Kalia
2 | 265285137-Construction of 32m PSC Girder Bridge on Kalinagar UZR - Naldanga Loboner Kheyaghat Road at Ch-4500m. | KDRIDP/Narail/B-03/2018-19 | 0 | 32 | 0 | 237.44 | 2018-12-12 | M/S Islam Traders, Jashore | 2019-03-19 | 225.237 | 35% | 2020-03-21 |  |  | 0 | 0% | Pile Work Completed
Total |  |  | 0 | 62 | 0 | 461.928 |  |  |  | 449.437 | 40% |  | 0 | 85.438 | -85.438 | 19.01%
Maintenance
Narail Sadar
1 | 265763003-Nakosi-Sarakeldanga Rd. | [13 empty] | 0 | #DIV/0!
2 | 265763008-Kolora (Akdia)UP Office-Shaikhati GC Rd. | [13 empty] | 0 | #DIV/0!
3 | 265763012-Shimakhali RHD-via Kurulia village-Chandibarpur UP Rd | [13 empty] | 0 | #DIV/0!
4 | 265764052-Periodic Maintenance of Mirapara Bazar - Raghunathpur road Ch. 00m -1665m | KDRIDP/Narail/M-01/2017-18 | 1.665 | 0 | 0 | 41.11 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 43.71 | 100% | 2018-08-30 | 43.707 | 43.71 | -0.003 | 100% | Final
5 | 265764053-Periodic Maintenance of Chowgacha RHD- Hogladanga Road Ch. 5800m - 7700m | KDRIDP/Narail/M-05/2017-18 | 1.9 | 0 | 0 | 46.457 | 2018-04-08 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 48.77 | 100% | 2018-12-31 | 48.75 | 48.75 | 0 | 99.96% | Final
6 | 265764054-Durbaguri R&H Mulia UP Office Rd | [13 empty] | 0 | #DIV/0!
7 | 265764061-Birgram R&H -Mulia UP Office Rd | [13 empty] | 0 | #DIV/0!
8 | 265764064- Malidanga (GCCR)-Durgapur RHD | [13 empty] | 0 | #DIV/0!
9 | 265765163-Periodic Maintenance of Solpur - Roghunathpur road Ch. 00m -1410m | KDRIDP/Narail/M-02/2017-18 | 1.41 | 0 | 0 | 36.62 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 39.78 | 100% | 2018-08-30 | 39.77 | 39.77 | 0 | 99.97% | Final
Lohagara
10 | 265523006-Periodic Maintenance of Naldi UP- Lahuria UP Road Ch. 00m - 1973m. | KDRIDP/Narail/M-04/2017-18 | 1.973 | 0 | 0 | 58.99 | 2018-04-04 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 61.94 | 100% | 2019-01-11 | 61.91 | 61.91 | 0 | 99.95% | Final
11 | 265524001-Periodic Maintenance of Lahuria Bazar - Chimanarchar road Ch. 00m - 2350m | KDRIDP/Narail/M-03/2017-18 | 2.35 | 0 | 0 | 59.53 | 2018-02-28 | BM Rafiqul Islam Rupgonj, Narail | 2018-04-11 | 65.237 | 100% | 2019-01-25 | 64.5 | 64.5 | 0 | 98.87% | Final
12 | 265524017-Rampur RHD Singa-Baka -Jikra Rd. | [13 empty] | 0 | #DIV/0!
13 | 265524035-Chachoi CD-Kalna R&H Rd. | [13 empty] | 0 | #DIV/0!
14 | 265524046-Char Daulatpur-Kheyaghat Rd. | [13 empty] | 0 | #DIV/0!
Kalia
15 | 265284015-Periodic Maintenance of Jogania Sachiadha via Kachuadanga Road from Ch. 00m -2000m | KDRIDP/Narail/M-06/2018-19 | 2 | 0 | 0 | 41.44 | 2018-12-12 | Md. Obydul Islam, Terokhada, Khulna | 2019-02-27 | 39.368 | 100% | 2019-07-28 |  | 29.057 | -29.057 | 73.81% | Work Completed
| 265285072-Periodic Maintenance of Dumuria Dudkuria(Dumuria Nalamara Pry School to Jogania - Bordia ) Road from Ch. 00m -2400m. |  | 2.4 | 0 | 0 | 49.01 |  | Md. Obydul Islam, Terokhada, Khulna |  | 46.56 |  |  |  | 34.36 | -34.36 | 73.8% | Work Completed
Total |  |  | 13.698 | 0 | 0 | 333.157 |  |  |  | 345.365 | 100% |  | 258.637 | 322.057 | -63.42 | 93.25%
GC-Hat
Narail Sadar
1 | Construction of Gobra Growth Centre | KDRIDP/Narail/GC-16/2017-18 | 0 | 0 | 1 | 18.65 | 2018-02-04 | M/S Liton Traders, Jhenaidah | 2018-03-08 | 16.789 | 100% | 2018-06-16 | 16.21 | 16.21 | 0 | 96.55% | Final
Total |  |  | 0 | 0 | 1 | 18.65 |  |  |  | 16.789 | 100% |  | 16.21 | 16.21 | 0 | 96.55%
Tree Plantation
Narail Sadar
1 | Tree Plantation of Moyenkhola Charbila Road from Ch-00m-1450m | KDRIDP/Narail/TP-01/2018-19 | 1.45 | 0 | 0 | 1.089 |  |  | 2018-10-20 | 1.089 | 50% | 2019-06-25 |  | 0.48 | -0.48 | 44.08% | Work Ongoing
Lohagara
2 | Tree Plantation of Manikgonj Bazar -Lahuria UP Road from Ch-4000m-5000m | KDRIDP/Narail/TP-02/2018-19 | 1 | 0 | 0 | 1 |  |  | 2018-10-20 | 1 | 50% | 2019-06-25 |  | 0.392 | -0.392 | 39.2% | Work Ongoing
Kalia
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 2.45 | 0 | 0 | 2.089 |  |  |  | 2.089 | 50% |  | 0 | 0.872 | -0.872 | 41.74%
Grand Total |  |  | 64.034 | 92 | 1 | 3983.812 |  |  |  | 3743.691 | 62.97% |  | 1097.802 | 2084.373 | -986.571 | 55.68%
|  |  | 64.034 | 92 | 1 | 3983.812 |  |  |  | 3743.691 | 37.25% |  | 1097.802 | 2084.373 | -986.571 | 55.68%

## Narail Sadar
Narail Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 265762006-Singa Solepur-Khororia Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
2 | 265763003-Nakosi - Sarkeldanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 265763005-Shahabad UP-Hobokhali U.P Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 265763012-Improvement of Shimakhali RHD – via Kurulia Village- Chandibarpur UP Road (Ch-00-1359m & 8150m-10800m) by BC | KDRIDP/Narail/W-13/2016-17 | 4.009 | 0 | 0 | 227.69 | 2017-07-12 | AKM Akramuzzaman Bhanga, Faridpur | 2017-10-02 | 52.616 | 25% | 2018-12-31 | 35.39 | 35.39 | 0 | 67.26% | Contract Cancelled (Partial Payment Done)
5 | 265763013-Improvement of Maizpara UP- Gorerhat Road (Narail-S part) from Ch. 2200m - 3450m | KDRIDP/Narail/W-18/2017-18 | 1.25 | 0 | 0 | 76.9 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 77.58 | 100% | 2018-11-14 | 77.534 | 77.534 | 0 | 99.94% | Final
Improvement of Village Road by BC
6 | 265764022-Improvement of Mathabhanga – Nondahkol (House of Bejoy Sarker) Road (Ch-1000m-2100m) by BC | KDRIDP/Narail/W-31/2018-19 | 1.1 | 0 | 0 | 90.789 | 2018-10-28 | Md. Abdur Rouf Molla, Narail | 2019-01-22 | 90.51 | 100% | 2019-06-20 | 0 | 86.76 | -86.76 | 95.86% | Work Completed
| 265764026- Improvement of Baliadanga – Ramchandrapur Road (Ch-1206m-3045m) by BC |  | 1.839 | 0 | 0 | 134.807 |  |  |  | 134.39 |  |  | 0 | 128.84 | -128.84 | 95.87%
7 | 265764049- Rukhali Bazar (up office)-Akdia char FRB Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 265764057- Improvement of Chanchra RHD – Benahati Road (Ch-2456m-3494m) by BC | KDRIDP/Narail/W-05/2016-17 | 1.038 | 0 | 0 | 63.64 | 2017-09-26 | M/S Islam Traders Jessore | 2017-11-10 | 63.26 | 100% | 2018-05-15 | 0 | 55.86 | -55.86 | 88.3% | Work Completed
9 | 265764059- Garuchira - Alukdia UP office Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 265764061-Birgram R&H-Mulia UP office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 265764066-Improvement of Maizpara - Dhalgram Road from Ch 00m - 161m & Ch-1440m - 2440m | KDRIDP/Narail/W-21/2017-18 | 1.161 | 0 | 0 | 82.15 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 76.987 | 100% | 2018-11-21 | 76.9 | 76.9 | 0 | 99.89% | Final
12 | 265764071-Chakoi chowmatha-Bichali FRB Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 265764073- Improvement of Doulatpur-via Hosinpur Grave Yeard – Boramara river side Road (Ch-1600m-2720m) by BC | KDRIDP/Narail/W-06/2016-17 | 1.12 | 0 | 0 | 65.44 | 2017-07-03 | M/S MA Enterprise Bhanga, Faridpur | 2017-08-16 | 63.48 | 50% | 2018-05-31 | 0 | 7.46 | -7.46 | 11.75% | WBM Ongoing
14 | 265765006-Peroli River side Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 265765009-Improvement of Malidanga Village Road from Ch 00m- 825m | KDRIDP/Narail/W-20/2017-18 | 0.825 | 0 | 0 | 54.31 | 2017-10-02 | M/S Moni Construction Vawakhali, Narail | 2017-11-06 | 54.28 | 100% | 2018-05-31 | 0 | 18.33 | -18.33 | 33.77% | Work Completed
16 | 265764002-Improvement of Jangelgram - Chandiborpur Road from Ch. 802m - 4359m | KDRIDP/Narail/W-25/2017-18 | 3.557 | 0 | 0 | 206.66 | 2018-02-28 | M/S Eden Prise, Mohishkhola, Narail | 2018-04-04 | 215.21 | 70% | 2019-04-10 | 0 | 108.784 | -108.784 | 50.55% | WBM Completed
17 | 265765310-Improvement of Sonkorpur GPS west side - Pazarkhali Road from Ch. 00m - 630m | KDRIDP/Narail/W-26/2017-18 | 0.63 | 0 | 0 | 38.2 | 2018-01-10 | M/S kailash Construction | 2018-02-22 | 38.96 | 70% | 2018-09-02 | 0 | 26.988 | -26.988 | 69.27% | WBM Completed
18 | 265765152-Improvement of Mathabhanga - Hogladanga Road from Ch 00m-1150m. | KDRIDP/Narail/W-22/2017-18 | 1.15 | 0 | 0 | 72.23 | 2017-10-02 | BM. Rafiqul Islam, Rupgonj Bazar, Narail | 2017-11-12 | 72.12 | 100% | 2018-10-16 | 72.117 | 72.117 | 0 | 100% | Final
19 | 265765241-Improvement of Soraspur Pucca Road - Narayanpur Shahid Freedom Fighter Shofiuddin Khan House Road from Ch. 00m -1982m | KDRIDP/Narail/W-27/2017-18 | 1.982 | 0 | 0 | 123.898 | 2018-02-04 | M/S Moni Construction | 2018-02-26 | 133.892 | 100% | 2019-03-12 | 0 | 118.89 | -118.89 | 88.8% | Work Completed
20 | 265765322-Chorbilla Govt.Primary School-Dokkin-Kali bari khayghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 265765113-Hobokhali VILLAGE ROAD.(Hobokhali H/O Nayeb Master-Narial Magura link road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 265765086- Improvement of Moyenkhola - Charbila Road from Ch. 00m- 1450m | KDRIDP/Narail/W-19/2017-18 | 1.45 | 0 | 0 | 91.3 | 2017-10-02 | Nishit Basu, Jhenaidah | 2017-11-14 | 86.02 | 100% | 2018-11-21 | 85.94 | 85.94 | 0 | 99.91% | Final
23 | 265765072- Improvement of Ghorakhali sholua Road Ch. 482-1560m | KDRIDP/Narail/W-16/2017-18 | 1.078 | 0 | 0 | 62.91 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 58.97 | 31% | 2018-06-17 | 0 | 0 | 0 | 0% | Contract Cancelled
24 | 265765259-Hosenpur Rostum Sikder Bari-Kayem Biswas Bari road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
25 | 265764045-Improvement of Burikhali RHD - Charshalikha Road by HBB from Ch 1472m - 2137m | KDRIDP/Narail/W-23/2017-18 | 0.665 | 0 | 0 | 22.417 | 2017-10-02 | M/S Eden Prise Mohiskhola Narail | 2017-10-30 | 21.3 | 100% | 2018-02-28 | 21.3 | 21.3 | 0 | 100% | Final
Construction of Bridge on Upazila Road (7.30m width)
26 | 265762007- Construction of 30m RCC Girder Bridge on Gabtala R&H - Maizpara GC Road at Ch-2000m | KDRIDP/Narail/B-01/2017-18 | 0 | 30 | 0 | 199.79 | 2018-07-09 | SDMSjandbjv Haque para, Chuadanga | 2018-08-30 | 188.98 | 35% | 2019-09-07 | 0 | 48.95 | -48.95 | 25.9% | Pile Work Completed
Construction of Bridge on Union Road/Village Road (5.50m width)
27 | 265763007-Construction of 30m RCC Girder Bridge on Singasolpur - Chakoi via Rukhali Road at Ch-3405m | KDRIDP/Narail/B-02/2017-18 | 0 | 30 | 0 | 224.488 | 2018-07-09 | SDMSjandbjv Haque para, Chuadanga | 2018-08-30 | 224.2 | 45% | 2019-09-07 | 0 | 85.438 | -85.438 | 38.11% | Abut. & Pier Base Casting Completed
Maintenance
28 | 265763003-Nakosi-Sarakeldanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 265763008-Kolora (Akdia)UP Office-Shaikhati GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 265763012-Shimakhali RHD-via Kurulia village-Chandibarpur UP Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 265764052-Periodic Maintenance of Mirapara Bazar - Raghunathpur road Ch. 00m -1665m | KDRIDP/Narail/M-01/2017-18 | 1.665 | 0 | 0 | 41.11 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 43.71 | 100% | 2018-08-30 | 43.707 | 43.71 | -0.003 | 100% | Final
32 | 265764053-Periodic Maintenance of Chowgacha RHD- Hogladanga Road Ch. 5800m - 7700m | KDRIDP/Narail/M-05/2017-18 | 1.9 | 0 | 0 | 46.457 | 2018-04-08 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 48.77 | 100% | 2018-12-31 | 48.75 | 48.75 | 0 | 99.96% | Final
33 | 265764054-Durbaguri R&H Mulia UP Office Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 265764061-Birgram R&H -Mulia UP Office Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 265764064- Malidanga (GCCR)-Durgapur RHD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 265765163-Periodic Maintenance of Solpur - Roghunathpur road Ch. 00m -1410m | KDRIDP/Narail/M-02/2017-18 | 1.41 | 0 | 0 | 36.62 | 2018-02-28 | SM Alamgir Kabir Auria, Narail | 2018-03-23 | 39.78 | 100% | 2018-08-30 | 39.77 | 39.77 | 0 | 99.97% | Final
GC-Hat
37 | Construction of Gobra Growth Centre | KDRIDP/Narail/GC-16/2017-18 | 0 | 0 | 1 | 18.65 | 2018-02-04 | M/S Liton Traders, Jhenaidah | 2018-03-08 | 16.789 | 100% | 2018-06-16 | 16.21 | 16.21 | 0 | 96.55% | Final
Tree Plantation
38 | Tree Plantation of Moyenkhola Charbila Road from Ch-00m-1450m | KDRIDP/Narail/TP-01/2018-19 | 1.45 | 0 | 0 | 1.089 | 0 | 0 | 2018-10-20 | 1.089 | 50% | 2019-06-25 | 0 | 0.48 | -0.48 | 44.08% | Work Ongoing
Total |  |  | 29.279 | 60 | 1 | 1981.545 |  |  |  | 1802.893 | 44.11% |  | 517.618 | 1204.401 | -686.783 | 66.8%

## Lohagara
Lohagara
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 265523005-Improvement of Manikgonj Bazar – Lahuria UP Road (Ch-5865m-7725m) by BC | KDRIDP/Narail/W-01/2016-17 | 1.86 | 0 | 0 | 104.97 | 2017-07-03 | M/S Shimul Enterprise, Madhukhali, Faridpur | 2017-08-22 | 98.607 | 100% | 2019-02-21 | 96.03 | 96.03 | 0 | 97.39% | Final
2 | 265523006-Improvement of Naldi UP-Lahuria Road Ch. 2100-7020m. Salvage Cost Tk. 142650.00 | KDRIDP/Narail/W-14/2017-18 | 4.92 | 0 | 0 | 293.31 | 2017-09-26 | M/S Lipu Enterprise, Kanaipur, Faridpur | 2017-11-13 | 274.94 | 50% | 2019-05-24 | 0 | 94.27 | -94.27 | 34.29% | WBM Ongoing
Improvement of Village Road by BC
3 | 265524001-Lahuria Bazar-Chimanarchar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 265524009 - Lohagara Bazar -Char Korfa Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 265524016-Raghunathpur-Taltala Satrahazari bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 265524005-Lohagara Bazar - Char Korfa Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 265524026-Improvement of Sattrahazari Bazar – Brammondanga Bazar Road (Ch-3500m-5930m)by BC | KDRIDP/Narail/W-02/2016-17 | 2.43 | 0 | 0 | 131.8 | 2017-07-03 | AKM Akramuzzaman Bhanga, Faridpur | 2017-08-16 | 123.89 | 0% | 2018-05-31 | 0 | 0 | 0 | 0% | Contract Cancelled
8 | 265524055-Radhanagar Bazar bridge - Kumardanga bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 265525005-Improvement of Bhadradanga - Makrail Road from Ch.1680m - 3000m | KDRIDP/Narail/W-28/2017-18 | 1.32 | 0 | 0 | 78.42 | 2018-02-04 | M/S Fakir Enterprise | 2018-02-14 | 85.47 | 100% | 2018-11-30 | 0 | 76.54 | -76.54 | 89.55% | Work Completed
10 | 265524062-Improvement of Dinanathpara – Gobindapur Road from Ch. 610m - 1370m. | KDRIDP/Narail/W-29/2017-18 | 0.76 | 0 | 0 | 50.12 | 2018-02-28 | M/S Rupali Construction, Kalibari Road, Barisal | 2018-04-08 | 51.629 | 15% | 2018-09-16 | 0 | 0 | 0 | 0% | ISG Ongoing
11 | 265525222-Makrail Mujam Molla H/O - Mukter Shikder house Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 265525508-Improvement of Mait Kumra C&B road H/O Akkas Master-H/O Lutfor Rahman via Nazrul Ahmed House Road Ch. 00-530m. Salvage Cost Tk. 617629.00 | KDRIDP/Narail/W-15/2017-18 | 0.53 | 0 | 0 | 31.25 | 2017-08-16 | AKM Akramuzzaman Bhanga, Faridpur | 2017-09-20 | 28.667 | 37% | 2018-02-28 | 0 | 9.28 | -9.28 | 32.37% | Contract Cancelled
13 | 265525226-Kamil Madrasha road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 265524042-Improvement of Jalalshe Maddrasha - Char Bramman Danga Road from Ch. 00m - 1740m | KDRIDP/Narail/W-24/2017-18 | 1.74 | 0 | 0 | 104.77 | 2017-10-09 | M/S Fakir Enterprise, Lohagara, Narail | 2017-11-27 | 103.76 | 100% | 2018-11-30 | 101.908 | 101.908 | 0 | 98.22% | Final
Improvement of Village Road by HBB
15 | 265524030-Kalagachi bazar-Manikgonj bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
16 | 265523006-Periodic Maintenance of Naldi UP- Lahuria UP Road Ch. 00m - 1973m. | KDRIDP/Narail/M-04/2017-18 | 1.973 | 0 | 0 | 58.99 | 2018-04-04 | M/S Moni Construction Vawakhali, Narail | 2018-05-06 | 61.94 | 100% | 2019-01-11 | 61.91 | 61.91 | 0 | 99.95% | Final
17 | 265524001-Periodic Maintenance of Lahuria Bazar - Chimanarchar road Ch. 00m - 2350m | KDRIDP/Narail/M-03/2017-18 | 2.35 | 0 | 0 | 59.53 | 2018-02-28 | BM Rafiqul Islam Rupgonj, Narail | 2018-04-11 | 65.237 | 100% | 2019-01-25 | 64.5 | 64.5 | 0 | 98.87% | Final
18 | 265524017-Rampur RHD Singa-Baka -Jikra Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 265524035-Chachoi CD-Kalna R&H Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 265524046-Char Daulatpur-Kheyaghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
21 | Tree Plantation of Manikgonj Bazar -Lahuria UP Road from Ch-4000m-5000m | KDRIDP/Narail/TP-02/2018-19 | 1 | 0 | 0 | 1 | 0 | 0 | 2018-10-20 | 1 | 50% | 2019-06-25 | 0 | 0.392 | -0.392 | 39.2% | Work Ongoing
Total |  |  | 18.883 | 0 | 0 | 914.16 |  |  |  | 895.14 | 31.05% |  | 324.348 | 504.83 | -180.482 | 56.4%

## Kalia
Kalia
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 265283002-Kalabaria UP office-Beeldhuria Hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 265283005-Babra R&H-Suktogram Bazer Rd.(Proposed name Babra UP Office- Suktogram Bazer) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 265283006- Improvement of Babra UP Office via Chanchuri UP Office - Dadontala RHD Road by BC from Ch 00m - 5100m. | KDRIDP/Narail/W-30/2017-18 | 5.1 | 0 | 0 | 392.64 | 2019-04-29 | M/S Jakaullah & Brothers, Chuadanga | 0 | 392.423 | 0% | 0 | 0 | 0 | 0 | 0% | NOA under Process
4 | 265283007-Khasial UP office-Patnabazar (Talbaria) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 265283008-Improvement of Chapail UZR – Bagudanga Bazar Road (Ch-700m-1061m) by BC | KDRIDP/Narail/W-07/2016-17 | 0.361 | 0 | 0 | 22.34 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 20.16 | 100% | 2018-05-15 | 0 | 18.5 | -18.5 | 91.77% | Work Completed
Improvement of Village Road by BC
6 | 265284002-Baddyabati hat-Mirzapur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 265284008-Raghunathpur Sumarkhola WDB Embk. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 265284015-Jogania-sachiadha via Kachuadanga road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 265284036-Hamidpur (Silimpur)-Chalitatala Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 265284037-Peroli Hat-Kharoria Mollabari Bazer Via Kharoria Abashan Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 265285001-Harishpur-Hadayetpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 265285012-Improvement of Kathadura – Chanderchar WDB Road (Ch-700m-1815m) by BC | KDRIDP/Narail/W-08/2016-17 | 1.115 | 0 | 0 | 60.43 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-20 | 57.11 | 100% | 2018-05-15 | 55.888 | 55.89 | -0.002 | 97.86% | Final
13 | 265285057-Improvement of Kamshia Village Road (Ch-00m-1250m) by BC | KDRIDP/Narail/W-11/2016-17 | 1.25 | 0 | 0 | 70.76 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 63.72 | 70% | 2018-05-15 | 0 | 37.385 | -37.385 | 58.67% | WBM Completed
14 | 265285016-Improvement of Putimary – Panipara Road (Ch-700m-1116m) by BC | KDRIDP/Narail/W-09/2016-17 | 0.416 | 0 | 0 | 25.33 | 2017-07-05 | SM Nurul Islam, Sonakur, Gopalgonj | 2017-08-22 | 22.86 | 100% | 2018-05-15 | 22.848 | 22.848 | 0 | 99.95% | Final
15 | 265285044-Improvement of Khashial – Uttar Khashial Road (Ch-500m-1150m) by BC | KDRIDP/Narail/W-10/2016-17 | 0.65 | 0 | 0 | 35.89 | 2017-07-05 | M/S Jakyullah & Brothers, Jibonnagar Chuadanga | 2017-08-24 | 32.39 | 100% | 2018-05-15 | 32.35 | 32.35 | 0 | 99.88% | Final
16 | 265285072-Dumuria-Dudkuria Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 265285137-Improvement of Patna Bridge – Kalinagar (Kalinagar UZR – Naldanga Loboner Kheyaghat) Road (Ch-1620m-3200m) by BC | KDRIDP/Narail/W-12/2016-17 | 1.58 | 0 | 0 | 89.63 | 2017-07-05 | M/S Ruma Enterprise Kalia, Narail | 2017-08-16 | 88.63 | 100% | 2018-03-24 | 87.74 | 87.742 | -0.002 | 99% | Final
18 | 265285149-Improvement of Baoisona Boroghat - Kanaypur Road (Ch-00m-1000m) by BC. | KDRIDP/Narail/W-17/2017-18 | 1 | 0 | 0 | 63.197 | 2017-10-02 | M/S Ruma Enterprise Kalia, Narail | 2017-11-22 | 57.2 | 100% | 2018-09-28 | 57.01 | 57.01 | 0 | 99.67% | Final
Improvement of Village Road by HBB
19 | 265284018-Kalabaria-Patna Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
20 | 265285137-Construction of 32m PSC Girder Bridge on Kalinagar UZR - Naldanga Loboner Kheyaghat Road at Ch-4500m. | KDRIDP/Narail/B-03/2018-19 | 0 | 32 | 0 | 237.44 | 2018-12-12 | M/S Islam Traders, Jashore | 2019-03-19 | 225.237 | 35% | 2020-03-21 | 0 | 0 | 0 | 0% | Pile Work Completed
Maintenance
21 | 265284015-Periodic Maintenance of Jogania Sachiadha via Kachuadanga Road from Ch. 00m -2000m | KDRIDP/Narail/M-06/2018-19 | 2 | 0 | 0 | 41.44 | 2018-12-12 | Md. Obydul Islam, Terokhada, Khulna | 2019-02-27 | 39.368 | 100% | 2019-07-28 | 0 | 29.057 | -29.057 | 73.81% | Work Completed
| 265285072-Periodic Maintenance of Dumuria Dudkuria(Dumuria Nalamara Pry School to Jogania - Bordia ) Road from Ch. 00m -2400m. |  | 2.4 | 0 | 0 | 49.01 |  |  |  | 46.56 |  |  | 0 | 34.36 | -34.36 | 73.8%
Tree Plantation
22 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 15.872 | 32 | 0 | 1088.107 |  |  |  | 1045.658 | 36.59% |  | 255.836 | 375.142 | -119.306 | 35.88%

## Summary
NARAIL
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Union Road by BC | 6 | 6 | 17.5 | 0 | 0 | 916.326 | 321.724 | 62.5% | 35.11%
Village Road by BC | 22 | 22 | 29.721 | 0 | 0 | 1803.405 | 1267.822 | 79.23% | 70.3%
Village Road by HBB | 1 | 1 | 0.665 | 0 | 0 | 21.3 | 21.3 | 100% | 100%
Bridge on Upazila Road | 1 | 1 | 0 | 30 | 0 | 188.98 | 48.95 | 35% | 25.9%
Bridge on Union Road/Village Road | 2 | 2 | 0 | 62 | 0 | 449.437 | 85.438 | 40% | 19.01%
Maintenance | 6 | 6 | 13.698 | 0 | 0 | 345.365 | 322.057 | 100% | 93.25%
GC-Hat | 1 | 1 | 0 | 0 | 1 | 16.789 | 16.21 | 100% | 96.55%
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation | 1 | 1 | 2.45 | 0 | 0 | 2.089 | 0.872 | 50% | 41.74%
Total | 40 | 40 | 64.034 | 92 | 1 | 3743.691 | 2084.373 | 62.97% | 55.68%