## Magura
MAGURA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Magura Sadar
1 | 255572005-Improvement of Kadamtala R&H - Hat Gopalpur via Hazipur- Sreerampur road from ch. 11670.00m to 13731.00m | KDRIDP/Magura/W-39/2017-18 | 2.061 | 0 | 0 | 164.21 | 2017-12-19 | M/S : Khandoker Enterprise, Khamarpara, Sreepur, Magura. | 2018-01-21 | 148.35 | 100% | 2017-07-29 | 147.166 | 147.166 | 0 | 99.2% | Final
2 | 255572013-Improvement of Jagla R&H - Beroil Polita GC via Borosoloighat School- Batikabari-Amuria Bazar-Blugram road from ch. 11890.00m to 12800.00m | KDRIDP/Magura/ W-06/2016-17 | 0.91 | 0 | 0 | 57.899 | 2018-05-08 | Md. Zaman Ent: Mollapara, Magura | 2017-05-30 | 57.49 | 100% | 2017-11-05 | 57.49 | 57.49 | 0 | 100% | Final
Mohammadpur
3 | 255662008-Improvement of Nohata GC- Gangarampur RHD via Panighata road by BC from ch. 2140.00m to 5425.00m | KDRIDP/Magura/W-09/2016-17 | 3.285 | 0 | 0 | 220.5 | 2017-05-31 | Mir Abu Syed, Mirpara, Magura. | 2017-07-04 | 220.47 | 100% | 2018-02-08 |  | 220.11 | -220.11 | 99.84% | Final
4 | 255662009 Mohommadpur upazila HQ- Ruijani RHD . | [13 empty] | 0 | #DIV/0!
Salikha
5 | 255852006: Improvement of Bunagati- Gangarampur via Pulum Bazar road from ch. 7756.00m to 9136.00m | KDRIDP/Magura/W-02/2016-17 | 1.38 | 0 | 0 | 89.3 | 2017-05-31 | Subash Enterprise, Shampur, Faridpur | 2017-07-06 | 89.27 | 100% | 2018-01-12 | 85.5 | 85.5 | 0 | 95.78% | Final
Total |  |  | 7.636 | 0 | 0 | 531.909 |  |  |  | 515.58 | 100% |  | 290.156 | 510.266 | -220.11 | 98.97%
Improvement of Union Road by BC
Magura Sadar
1 | 255573001-Improvement of Sattrujitpur UP-Amuria bazar via Baharbag bazar road from ch. 6770.00m to 8350.00m | KDRIDP/Magura/W-24/2017-18 | 1.58 | 0 | 0 | 97.12 | 2017-11-02 | Mohon Motsha Aroth, Pernanduali, Magura. | 2017-12-10 | 96.74 | 100% | 2018-06-17 | 96.72 | 96.72 | 0 | 99.98% | Final
2 | 255573002-Improvement of Moghi U.P Office-Jagdal U.P office via Jagla Chara Bottola road by BC (Ch.2146-5310m) | KDRIDP/Magura/W-60/2018-19 | 3.164 | 0 | 0 | 228.427 | [8 empty] | 0 | #DIV/0!
3 | 255573006-Raghobdair UP(Bolloh bazar)-Danpara bazar Rd | [13 empty] | 0 | #DIV/0!
4 | 255573007-Improvement of Raghobdair UP Ballo Bazar-Bangha Tematha Bazar via Baliadanga bazar road from ch. 1650.00m to 4275.00m | KDRIDP/Magura/W-28/2017-18 | 2.625 | 0 | 0 | 154.93 | 2017-11-02 | M/S : Asif Construction, Abalpur, Magura. | 2017-11-26 | 144.48 | 100% | 2018-10-14 | 144.48 | 144.48 | 0 | 100% | Final
5 | 255573008-Improvement of Jagdal Bazar-Satrujitpur UP office road by BC (Ch.2370-3550m) | KDRIDP/Magura/W-61/2018-19 | 1.18 | 0 | 0 | 88.58 | 2019-05-06 | M/S Jakaullah & brothers,Chuadanga | 2019-06-26 | 88.57 | 0% | 2020-06-29 |  |  | 0 | 0%
| 255573001-Improvement of Sattrujitpur UP-Amuria bazar via Baharbag bazar road (Ch.8350-9000m) |  | 0.65 | 0 | 0 | 45.587 |  |  |  | 45.58 | [5 empty] | 0%
| 255573016-Improvement of Gopalgram U.P Office-Kullia Bazar (Ch.6963-7613m) |  | 0.65 | 0 | 0 | 47.595 |  |  |  | 47.59 |  |  |  |  | 0 | 0%
6 | 255573011-Moghi U.P Office- Raghobdair Bazar via Andalbaria road. | [13 empty] | 0 | #DIV/0!
7 | 255573013-Improvement of Niznanduali bazar-Atharokhada Up office Kamar bari R&H road by BC from ch. 8921.00m to 9489.00m | KDRIDP/Magura/ W-10/2016-17 | 0.568 | 0 | 0 | 31.66 | 2017-05-31 | Md. Ziaul Haque, Ghoramara, Magura | 2017-07-13 | 31.606 | 100% | 2018-01-12 |  | 26.7 | -26.7 | 84.48%
8 | 255573015-Chowlia UP office (Malikgram)- Jogdol UP office (Jogdol Kalitola) Road. | KDRIDP/Magura/W-42/2017-18 | 1.895 | 0 | 0 | 109.26 | 2018-02-26 | M/S : P.K. Traders. Kukna, Magura. | 2018-04-01 | 107.106 | 100% | 2019-02-25 | 106.716 | 106.716 | 0 | 99.64% | Final
9 | 255573003-Improvement of Bharbag Bazar-Baroil Polita UP road from ch. 00.00m to 2260.00m | KDRIDP/Magura/W-25/2017-18 | 2.26 | 0 | 0 | 136.85 | 2017-11-02 | M/S : P.K. Traders, Kukna, Magura. | 2017-11-29 | 124.95 | 100% | 2018-11-15 | 124.58 | 124.58 | 0 | 99.7% | Final
10 | 255573003-Improvement of Baharbag bazar-Beroil Polita UP road from ch. 2260.00m to 3760.00m | KDRIDP/Magura/W-40/2017-18 | 1.5 | 0 | 0 | 97.15 | 2018-01-29 | Modhubon Construction, Dudsara, Kotchandpur, Jhenaidah. | 2018-03-06 | 97.1 | 100% | 2018-08-09 |  | 58.93 | -58.93 | 60.69%
11 | 255573003-Dharbag bazar-Barol Polta UP Road, | [13 empty] | 0 | #DIV/0! | Duplicate
Salikha
12 | 255853001-Improvement of Poragachi-Horispur road from ch. 1390.00m to 4985.00m | KDRIDP/Magura/W-04/2016-17 | 3.6 | 0 | 0 | 190.036 | 2017-08-21 | Mir Abu Syed, Mirpara, Magura. | 2017-10-02 | 190 | 70% | 2018-04-07 |  | 100 | -100 | 52.63%
13 | 255853001-Improvement of Poragachi-Horispur road from ch. 6535.00m to 7600.00m | KDRIDP/Magura/ W-03/2016-17 | 1.065 | 0 | 0 | 55.519 | 2017-05-08 | Md. Rana Amir Osman Vina, Magura. | 2017-05-30 | 54.41 | 100% | 2017-10-31 | 54.394 | 54.39 | 0.004 | 99.96% | Final
14 | 255853009-Improvement of Talkhori - Dighalgram road from ch. 1700.00m to 2745.00m | KDRIDP/Magura/W-31/2017-18 | 1.045 | 0 | 0 | 65.41 | 2017-11-02 | Nishit Bashu, Kanchannagar, Jhenaidah. | 2018-12-03 | 65.36 | 100% | 2018-06-29 | 65.36 | 65.36 | 0 | 100% | Final
15 | 255853010-Improvement of Sarsuna-Gorcrhat via Horiarkhal road at (ch: 00m to 2722m) | KDRIDP/Magura/W-62/2018-19 | 2.722 | 0 | 0 | 197.989 | 2019-08-05 | [7 empty] | 0 | #DIV/0!
16 | 255853011-Improvement of Singra-Naghosa via Gurpagla road from ch. 1400.00m to 3900.00m | KDRIDP/Magura/W-35/2017-18 | 2.5 | 0 | 0 | 152.67 | 2017-11-02 | Md. Ziaul Haque, Ghoramara, Magura. | 2018-12-03 | 152.66 | 100% | 2018-06-08 | 152.5 | 152.5 | 0 | 99.9% | Final
Mohammadpur
17 | 255663003-Digha Up office-Dhuljuri Bazar Rd. | [13 empty] | 0 | #DIV/0!
18 | 255663004 Palashbaria up to Fulbaria Bazar | [13 empty] | 0 | #DIV/0!
19 | 255663005-Palasbaria UP to Kalisankarpur Hat via Jhama Bazar Rd. | [13 empty] | 0 | #DIV/0!
20 | 255663007-Improvement of Balidia UP office Kalamdhori Bazar via Sreepur road from ch. 00.00m to 3325.00m | KDRIDP/Magura/W-19/2017-18 | 3.325 | 0 | 0 | 186.85 | 2017-10-25 | Rasel Enterprise, Police Linepara, Magura. | 2017-11-26 | 186.61 | 100% | 2018-09-29 | 185.406 | 185.406 | 0 | 99.35% | Final
21 | 255663010 Mohammadpur UZ H/Q-Horekrisnapur road | [13 empty] | 0 | #DIV/0!
22 | 255663011-Improvement of Mohammadpur Hospital-Dhoail Bazar via Horekrishnapur hat road from ch. 1962.00m to 3210.00m | KDRIDP/Magura/W-21/2017-18 | 1.248 | 0 | 0 | 76.55 | 2017-10-25 | M/S : Amirun Enterprise, Rupsha, Khulna | 2018-12-03 | 69.76 | 70% | 2018-06-08 |  | 18 | -18 | 25.8%
23 | 255663014 Bethuli Bazar (Kalukhandi More) to Babukahli UP via Dumurshia Bazar Rd. | [13 empty] | 0 | #DIV/0!
24 | 255663016 Improvement of Aownara Bazar - Babukhali UP via Hatbaria Bazar road from ch. 00.00m to 1445.00m | KDRIDP/Magura/ W-12/2016-17 | 1.445 | 0 | 0 | 74.12 | 2017-10-18 | M/S : Asif Construction, Abalpur, Magura. | 2017-11-07 | 77.77 | 100% | 2018-05-14 | 76.85 | 76.85 | 0 | 98.82% | Final
25 | 255663018-Palasbaria UP office-Nohata GC via Chakulia Rd. | [13 empty] | 0 | #DIV/0!
26 | 255663027-Palasbaria UP to Gazir more bazar upto Joshobontopur RHD. | [13 empty] | 0 | #DIV/0!
Sreepur
27 | 255953005-Improvement of Bakera Hat-Kadirpara Up office at Radhanagar GC road by BC From ch. 4339.00m to 6700m | KDRIDP/Magura/ W-07/2016-17 | 2.361 | 0 | 0 | 131.21 | 2017-07-24 | M/S : Rohan Construction, Mollapara, magura. | 2017-08-21 | 131.065 | 100% | 2018-04-15 | 131.05 | 131.05 | 0 | 99.99% | Final
28 | 255953007-Improvement of Kadirpara UP office at Radhanagar GC to Nokal bazar via Gashira road from ch. 00.00m to 1500.00m | KDRIDP/Magura/W-38/2017-18 | 1.5 | 0 | 0 | 89.43 | 2017-11-02 | M/S : Rohima Traders, Mollapara, Magura. | 2018-12-03 | 85.81 | 100% | 2018-06-08 | 85.81 | 85.81 | 0 | 100% | Final
29 | 255953008-Improvement of Tikerbila Hat- Amalshar UP office at chato Udash road from ch. 1150.00m to 3200.00m | KDRIDP/Magura/W-37/2017-18 | 2.05 | 0 | 0 | 119.21 | 2017-11-02 | M/S : Hamza Tradrs, Khamarpara, Sreepur, Magura. | 2017-11-26 | 117.84 | 100% | 2018-06-17 | 117.84 | 117.84 | 0 | 100% | Final
30 | 255953009-Improvement of Sabdalpur Hat- Sabdalpur UP office at Kajoli bazar road from ch. 1040.00m to 2765.00m & 2950m to 4055m | KDRIDP/Magura/W-36/2017-18 | 2.83 | 0 | 0 | 172.69 | 2017-11-02 | M/S : Rohima Traders, Mollapara, Magura. | 2017-12-03 | 155.51 | 100% | 2018-06-08 | 150.28 | 150.28 | 0 | 96.64% | Final
31 | 255953010-Dariapur UP Office (Chowgachi) to Tikerbila Bazar via Rajapur Bazar road at ch. 2800-3535m. & 4818-5023m | KDRIDP/Magura/ W-17/2016-17 | 0.94 | 0 | 0 | 49.95 | 2017-09-21 | M/S :Unic Traders, Mirpur, Kushtia. | 2017-07-25 | 49.94 | 100% | 2018-11-04 | 49.94 | 49.94 | 0 | 100% | Final
32 | 255953010-Improvement of Dariapur UP office Chowgachi to Tikerbila bazar via Rajapur bazar road by BC from ch.5023.00m to 5284.00m | KDRIDP/Magura/W-50/2017-18 | 0.261 | 0 | 0 | 17.62 | 2018-08-01 | M/S Razia Enterprise Alukdia Bazar, Magura. | 2018-08-29 | 16.74 | 50% | 2019-03-05 | 16.73 | 16.73 | 0 | 99.94% | Final
33 | 255953011-Improvement of Nakol UP- Durannagar hat via Kamlapur Pry.school road (Ch. 3750-4200m) | KDRIDP/Magura/W-53/2018-19 | 0.45 | 0 | 0 | 31.629 | 2019-03-28 | M/S Sarma Enterprise, Mollapara, Magura. | 2019-04-21 | 30.048 | 50% | 2019-06-27 |  |  | 0 | 0%
34 | 255953015-Improvement of Nakol UP-WAPDA bazar road from ch. 1405.00m to 3700.00m | KDRIDP/Magura/ W-01/2016-17 | 2.295 | 0 | 0 | 119.27 | 2017-05-08 | Md. Ziaul Haque, Ghoramara, Magura | 2017-05-30 | 119.24 | 100% | 2017-12-05 | 119.23 | 119.23 | 0 | 99.99% | Final
35 | 255953016-Ganga Nanla bazar-Sabdalpur UP via Barishat Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 45.709 | 0 | 0 | 2767.312 |  |  |  | 2286.485 | 88.18% |  | 1677.886 | 1881.512 | -203.626 | 82.29%
Improvement of Village Road by BC
Magura Sadar
1 | 255574002-Naldha Gangnalia Rd. | [13 empty] | 0 | #DIV/0!
2 | 255574015-Ghoranas-Kukila Rd. | [13 empty] | 0 | #DIV/0!
3 | 255574018-Ramnagar Hat-Krishnapur via Thakurbari Rd. | [13 empty] | 0 | #DIV/0!
4 | 255574020-Improvement of Vitashair RHD-Dhalahara bazar road by BC from ch. 6710.00m to 8180.00m & 8221.00m to 9320.00m | KDRIDP/Magura/W-08/2016-17 | 2.569 | 0 | 0 | 138.22 | 2017-05-31 | M/S : Aroma Enterprise, Ator Ali Road, Magura. | 2017-07-13 | 138.19 | 100% | 2018-02-18 | 138.09 | 138.09 | 0 | 99.93% | Final
5 | 255574021-Improvement of Bhabanhati Dhal (R&H)-Raghobdair Bazar via Bhabanhati Bazar road at ch:4755.00m-7782.00m | KDRIDP/Magura/W-47/2017-18 | 3.027 | 0 | 0 | 189.19 | 2018-05-07 | M/S Rohan Const. Mollapara, Magura | 2018-05-27 | 189.2 | 70% | 2019-06-30 |  | 128.337 | -128.337 | 67.83%
6 | 255574022-Shalpara RHD-Sounpur H/O Zafar Mouri Rd. | [13 empty] | 0 | #DIV/0!
7 | 255574024-Barosala School - Asba via Barosala ghat Rd. | [13 empty] | 0 | #DIV/0!
8 | 255574025-Jagdal Dakhinpara FRB-Baharbag bazar Rd. | [13 empty] | 0 | #DIV/0!
9 | 255574033-Ichakhada R&H-Defulia bazar Rd. | [13 empty] | 0 | #DIV/0!
10 | 255574035-Improvement of Laskarpur Aksi more FRB-Katakhali GC road from ch. 500.00m to 1332.00m | KDRIDP/Magura/W-27/2017-18 | 0.832 | 0 | 0 | 50.21 | 2017-11-02 | M/S : Bali Construction, Tati Para, Magura. | 2017-11-29 | 50.2 | 100% | 2018-10-07 | 48.37 | 48.37 | 0 | 96.35% | Final
11 | 255574045-Improvement of Batkebari bazar-Jagla bazar road from ch. 07.00m to 638.00m | KDRIDP/Magura/W-30/2017-18 | 0.631 | 0 | 0 | 37.29 | 2017-11-02 | M/S : Abu Ishaq & Sons, Abu Ishaq road, Magura. | 2017-11-26 | 37.87 | 100% | 2018-05-04 | 37.87 | 37.87 | 0 | 100% | Final
12 | 255574078-Improvement of Beroil Polita R&H Baharbag bazar road from ch. 3623.00m to 4200.00m | KDRIDP/Magura/W-29/2017-18 | 0.577 | 0 | 0 | 34.35 | 2017-11-02 | Sumon Enterprise, Pernanduali, Magura. | 2017-11-26 | 34.29 | 100% | 2018-11-11 | 34.28 | 34.28 | 0 | 99.97% | Final
13 | 255574098-Improvement of Kechuadubi Pri. School- Bhabonhati bazar road from ch. 1000.00m to 1672.00m | KDRIDP/Magura/W-26/2017-18 | 0.672 | 0 | 0 | 40.14 | 2017-11-02 | M/S : Hayet Enterprise, Vaina, Magura. | 2017-11-28 | 40.1 | 100% | 2018-05-06 | 40.1 | 40.1 | 0 | 100% | Final
14 | 255574090-Improvement of Sreerampur-Sreepur Tremohone via Purba para Mosque road by BC from ch. 0.00m to 980.00m | KDRIDP/Magura/ W-11/2016-17 | 0.98 | 0 | 0 | 65.18 | 2017-05-31 | Md. Ali Ahmed Ahad, Vaina, Magura. | 2017-07-04 | 65.17 | 100% | 2017-12-10 | 64.54 | 64.54 | 0 | 99.03% | Final
15 | 255574041-Hazipur UP Office Ful Bari Boalia via Mostofapur road. | [13 empty] | 0 | #DIV/0!
16 | 255575012-Angardah-Kapiladanga | [13 empty] | 0 | #DIV/0!
17 | 255574008-Improvement of Mirzapur-Nrihati road from ch. 2300.00m to 2598.00m | KDRIDP/Magura/W-41/2017-18 | 0.298 | 0 | 0 | 18.86 | 2018-05-07 | Pavel Enterprise Adarsopara, Magura | 2018-05-22 | 19.61 | 100% | 2018-09-22 | 19.61 | 19.61 | 0 | 100% | Final
18 | 255575020-Katakhali UZ road-beel Aksi (Badsha Mia)(Norshinghati pacca road-beel Aksi Magura road.) | [13 empty] | 0 | #DIV/0!
19 | 255575018-Beel Aksi Purbopara-Aksi UZ Road. | [13 empty] | 0 | #DIV/0!
20 | 255575193-Improvement of Kapashhati Ball Fiedl to Kuknapara road at ch. 00-1617m | KDRIDP/Magura/W-43/2017-18 | 1.617 | 0 | 0 | 99.78 | 2018-02-26 | M/S : Rohima Trader, Mollapara, Magura. | 2018-03-29 | 91.76 | 100% | 2018-10-02 | 91.76 | 91.76 | 0 | 100% | Final
21 | 255574032-Improvement of Benga Tamatha to Maghail via Beroil Porbopara Bazar road at ch. 663-1663m. | KDRIDP/Magura/W-46/2017-18 | 1 | 0 | 0 | 60.53 | 2018-04-24 | Asif Construction, Eitkhola, Abalpur, Magura | 2018-05-21 | 57.506 | 100% | 2018-10-17 | 57.506 | 57.506 | 0 | 100% | Final
Salikha
22 | 255854001- Improvement of sandra Chowrastta- Singra Simakhali UZR At Goalkhali via kuskhali Salta beel- sandra road road from ch. 00.00m to 1410.00m | KDRIDP/Magura/W-33/2017-18 | 1.41 | 0 | 0 | 114.78 | 2018-01-29 | M/S : Kabirul Islam Siddiqui, Rotkhola, Goalchamot, Faridpur. | 2018-02-22 | 120.517 | 100% | 2018-08-27 | 120.44 | 120.44 | 0 | 99.94% | Final
23 | 255854004- Improvement of Hatbaria- Baulia Bazar road (Ch.1225-2950m) | KDRIDP/Magura/W-58/2018-19 | 1.725 | 0 | 0 | 121.34 | 2019-04-17 | M/S Kazi Mahabubur Rahman Jhenaidha. | 2019-05-29 | 121.085 | 0% | 2019-06-08 |  |  | 0 | 0%
| 255854013-Improvement of Talkhari UP office Dhaneswargati Bazar via Gobindopur road (Ch. 1330-2062m) |  | 0.732 | 0 | 0 | 53.268 |  |  |  | 53.156
24 | 255854010- Improvement of Satakhali R&H-Sandra FRB road (Ch.1500-2830m) | KDRIDP/Magura/W-56/2018-19 | 1.33 | 0 | 0 | 96.99 |  |  |  | 93.6 |  |  |  |  | 0 | 0%
| 255854019- Improvement of Krishnapur Primary School (R&H)-Sreehatta R&H via Gopalgram road (Ch. 1370-2262m) |  | 0.892 | 0 | 0 | 63.39 |  |  |  | 61.175 |  |  |  |  | 0 | 0%
25 | 255854020- Improvement of Bhulbaria R&H-Thaipara via Nurpur road (Ch.1500-3450m) | KDRIDP/Magura/W-57/2018-19 | 1.95 | 0 | 0 | 145.345 | 2019-04-17 | M/S Kazi Mahabubur Rahman Jhenaidha. | 2019-05-29 | 145.04 | 30% | 2019-06-08 |  |  | 0 | 0%
26 | 255855001- Improvement of Kholabaria -Harispur road from ch. 1000.00m to 3653.00m | KDRIDP/Magura/W-34/2017-18 | 2.653 | 0 | 0 | 162.4 | 2017-11-02 | Mir Abu Syed, Mirpara, Magura. | 2017-12-11 | 153.38 | 100% | 2018-06-17 |  | 100.437 | -100.437 | 65.48% | Final
27 | 255855003-Improvement of Rampur-Hatbaria road at (ch. 2743m to 3140m) | KDRIDP/Magura/W-64/2018-19 | 0.397 | 0 | 0 | 30.955 | 2019-07-17 | [7 empty] | 0 | #DIV/0!
| 255854002-Improvement of Satokhali Nutun Bazar- Katoli road at (ch. 2350m to 2519m + 3018m to 3330m) |  | 0.481 | 0 | 0 | 35.482 | [8 empty] | 0 | #DIV/0!
29 | 255855005- Raizadapur-Hazrahati Road | [13 empty] | 0 | #DIV/0!
30 | 255855007-Improvement of Gongarampur - Gabtola road at (ch: 365m to 1400m | KDRIDP/Magura/W-63/2018-19 | 1.035 | 0 | 0 | 78.52 | 2019-07-17 | [7 empty] | 0 | #DIV/0!
31 | 255855021- Improvement of Kumarkota - Junary road from ch. 2375.00m to 4175.00m | KDRIDP/Magura/W-32/2017-18 | 1.8 | 0 | 0 | 108.98 | 2017-11-02 | Mir Abu Syed, Mirpara, Magura. | 2017-12-11 | 108.96 | 70% | 2018-06-17 |  | 50 | -50 | 45.89%
32 | 255854013-Improvement of Talkhari UP Office- Dhaneswargati bazar via Gobindopur road from ch. 2062.00m to 3330.00m | KDRIDP/Magura/ W-05/2016-17 | 1.268 | 0 | 0 | 70.78 |  | M/S Lipi Jewellers Chuadanga | 2017-06-21 | 70.66 | 100% | 2017-12-17 | 70.6 | 70.6 | 0 | 99.92% | Final
Mohammadpur
33 | 255664015-Improvement of Mousha-Kanutia via Nikorhata road from ch. 700.00m to 4150.00m | KDRIDP/Magura/W-20/2017-18 | 3.45 | 0 | 0 | 195.75 | 2017-10-25 | Rasel Enterprise, Police Linepara, Magura. | 2017-11-26 | 195.55 | 100% | 2018-12-15 | 195.316 | 195.316 | 0 | 99.88% | Final
34 | 255664017 Omedpur RHD to Gopinathpur bazar | [13 empty] | 0 | #DIV/0!
35 | 255664020 Joyrampur to Mobarekpur Rd. | [13 empty] | 0 | #DIV/0!
36 | 255664050-Panighata Sikderpara-Joyrampur Rd. | [13 empty] | 0 | #DIV/0!
37 | 25664056-Palasbaria Alemer more - Khalishakhali Hat Via Bethuri | [13 empty] | 0 | #DIV/0!
38 | 255665211-Panighata Shikderpara Madrasha- Hasan Sk H/O- Delowar Sk. road. | [13 empty] | 0 | #DIV/0!
39 | 255664043-Bangram-Mondalgati Rd. | [13 empty] | 0 | #DIV/0!
40 | 255664096-Improvement of Joshobontopur H/S Bongram Pucca road via Shadan Pal house road from ch. 750.00m to 2100.00m | KDRIDP/Magura/W-22/2017-18 | 1.35 | 0 | 0 | 83.55 | 2017-10-25 | M/S : Asif Construction, Abalpur, Magura. | 2017-11-22 | 79.13 | 100% | 2018-04-29 | 78.06 | 78.06 | 0 | 98.65% | Final
41 | 255664104dariakha brigde more ti batiaghaga house | [13 empty] | 0 | #DIV/0!
42 | 255664078 Improvement of Digha to foloshia road from ch. 00.00m to 586.00m | KDRIDP/Magura/W-23/2017-18 | 0.586 | 0 | 0 | 37.48 | 2017-10-25 | Md. Firoz Elahi, Satdoha Para, Magura. | 2017-11-27 | 37.27 | 100% | 2018-05-10 | 37.198 | 37.198 | 0 | 99.81% | Final
43 | 255664016-Jashpur R&H to Mousha Rd. | [13 empty] | 0 | #DIV/0!
44 | 255664065-Improvement of Dumurshia Hat to Chalmia road by BC at ch.00m-1000m | KDRIDP/Magura/W-52/2018-19 | 1 | 0 | 0 | 78.394 | 2018-10-24 | M/S Tuli Enterprise Kanutia Bazar, Mohammadpur, Magura | 2018-11-25 | 74.47 | 100% | 2019-04-30 |  | 30 | -30 | 40.28%
45 | 255664067-Improvement of Kumrul-palla road (Ch.2245-3450m) | KDRIDP/Magura/W-59/2018-19 | 1.205 | 0 | 0 | 82.616 | 2019-03-28 | R.K Traders,Vaina, Magura | 2019-05-05 | 78.485 | 0% | 2019-08-09 |  |  | 0 | 0%
Sreepur
46 | 255954004-Improvement of Chongacha-Noinshah ghat road (Ch.1000-1500m) |  | 0.5 | 0 | 0 | 38.718 | 2019-04-17 | Unique Construction Jhenaidha. | 2019-06-10 | 38.624 | 2.5% | 2020-06-17 |  |  | 0 | 0%
| 255954009-Improvement of Sabdalpur bazar Durgapur road (Ch.200-1320m) |  | 1.12 | 0 | 0 | 81.035 |  |  |  | 80.838 |  |  |  |  | 0 | 0%
47 | 255954005-Baroipara boat Tola-Sreekhol bazar road. | [13 empty] | 0 | #DIV/0!
48 | 255954016-Sreepur-Kurundi via Chilgari bazar road. | [13 empty] | 0 | #DIV/0!
49 | 255954018-Improvement of Kachua-Razapur hat road by BC from ch.1680.00m to2495.00m | KDRIDP/Magura/W-51/2017-18 | 0.815 | 0 | 0 | 59.195 | 2018-08-01 | Rasel Enterprise, Policepara, Magura. | 2018-08-26 | 56.235 | 100% | 2019-02-28 | 51.27 | 51.27 | 0 | 91.17% | Final
| 255954042-Improvement of Dariapur Kalibari Shanbandha ghat via Dariapur Natunpara road by BC from ch.2950.00m to 3160.00m | KDRIDP/Magura/W-51/2017-18 | 0.21 | 0 | 0 | 12.354 |  | Rasel Enterprise, Policepara, Magura. |  | 11.736 |  |  | 10.7 | 10.7 | 0 | 91.17%
| 255955029-Improvement of Sonatundi-Amtoil bazar road by BC from ch.2750.00m to 3232.00m | KDRIDP/Magura/W-51/2017-18 | 0.482 | 0 | 0 | 30.375 |  | Rasel Enterprise, Policepara, Magura. |  | 28.856 |  |  | 26.307 | 26.307 | 0 | 91.17%
50 | 255954019-Hogoldanga-Razapur hat road. | [13 empty] | 0 | #DIV/0!
51 | 255954027-Improvement of Dariapur Kalibari-Moheshpur via Malainagar road by BC from ch. 2200.00m to 4400.00m | KDRIDP/Magura/W-50/2017-18 | 2.2 | 0 | 0 | 133.756 | 2018-08-01 | M/S Razia Enterprise Alukdia Bazar, Magura. | 2018-08-29 | 127.068 | 50% | 2019-03-05 | 127.03 | 127.03 | 0 | 99.97% | Final
52 | 255954029-Improvement of Joka bridge Nobagram bridge via Mashalia road (Ch.2350-4300m) | KDRIDP/Magura/W-54/2018-19 | 1.95 | 0 | 0 | 139.99 | 2019-04-17 | M/S Asif Construction, Abalpur, Magura. | 2019-06-10 | 138.414 | 20% | 2019-05-03 |  |  | 0 | 0%
53 | 255954037-Modhupur bazar-Gobindapur road. | [13 empty] | 0 | #DIV/0!
54 | 255954052-Nakol UP office-Wapda Bazar road. | [13 empty] | 0 | #DIV/0!
55 | 255954053-Sarongodia GPS-Sarongodia Purbopara Eidgha road. | [13 empty] | 0 | #DIV/0!
56 | 255955033-Kamarpara-Barobell road. | [13 empty] | 0 | #DIV/0!
57 | 255954066-Majhail pucca rd.-Madartola Road. | [13 empty] | 0 | #DIV/0!
58 | 255954014-Gashiara Purbopara Mosque-Kamlapur Primary School Road. | [13 empty] | 0 | #DIV/0!
59 | 255954080-Nakol Bazar- Boralidah West para Mosque road near house of Dulal Master to Sreepur- Ramnagar R&H at WAPDA Pamp House road at ch. 00-1454m | KDRIDP/Magura/ W-18/2017-18 | 1.454 | 0 | 0 | 95.28 | 2017-10-18 | M/S : Bali Construction, Tatipara, Magura | 2017-11-08 | 89.41 | 100% | 2018-05-15 | 89.19 | 89.19 | 0 | 99.75% | Final
60 | 255955212-Improvement of Boralidah Purbapara infront the H/O Bader Master to Towards H/O Bakkar Shek road from ch. 00.00m to 446.00m | KDRIDP/Magura/ W-16/2016-17 | 0.446 | 0 | 0 | 24.41 | 2017-07-24 | Mir Abu Syed, Mirpara, Magura. | 2017-08-16 | 24.39 | 100% | 2018-01-17 | 24.38 | 24.38 | 0 | 99.96% | Final
61 | 255955201-Improvement of Boralidah Asraf Mollas house-Ghasiara village via Boralida road from ch. 00.00m to 360.00m | KDRIDP/Magura/ W-14/2016-17 | 0.36 | 0 | 0 | 19.24 | 2017-07-24 | Mir Abu Syed, Mirpara, Magura. | 2017-08-16 | 19.23 | 100% | 2018-01-17 | 19.21 | 19.21 | 0 | 99.9% | Final
62 | 255955205-Improvement of Boralidah Purpapara Jame Mosque-Nakol Kali Bottola road from ch. 00.00m to 826.00m. Salvage Materials 34320.00 | KDRIDP/Magura/ W-15/2016-17 | 0.826 | 0 | 0 | 43.79 | 2017-07-24 | Mir Abu Syed, Mirpara, Magura. | 2017-08-16 | 43.777 | 100% | 2018-01-17 | 43.77 | 43.77 | 0 | 99.98% | Final
63 | 255955148-Baroipara Pucca road-Baroipara Primary School. | [13 empty] | 0 | #DIV/0!
64 | 255955006-WAPDA-Endurbaria Road. | [13 empty] | 0 | #DIV/0!
65 | 255955207-Improvement of Baralidoha Modhyapara-Salek Molla H/O Goalbari Rofik More road by BC from ch. 00.00m to 1380.00m. Salvage Materials 387799.00 | KDRIDP/Magura/W-48/2017-18 | 1.38 | 0 | 0 | 78.799 | 2018-06-07 | M/S Asif Construction Abalpur, Magura | 2018-07-09 | 74.86 | 100% | 2019-02-24 |  | 52.92 | -52.92 | 70.69%
| 255954041-Improvement of Badonpur Bridge-Amlasar hat via Beelnathur road by BC from ch. 692.00m to 1300.00m. Salvage Materials 467984.00 |  | 0.608 | 0 | 0 | 35.728 |  |  |  | 33.94 |  |  |  | 24 | -24 | 70.71%
66 | 255954031-Improvement of Kachua Upazila road to Tarauzail (Sreepur-Shalipur Upazila road-Kachua Kabil Molla House- Tarauzail School) Road. | KDRIDP/Magura/W-49/2017-18 | 0.82 | 0 | 0 | 51.01 | 2017-07-10 | M/S Hamza Traders, Khamarpara | 2018-08-08 | 50.99 | 100% | 2019-01-23 | 50.976 | 50.976 | 0 | 99.97% | Final
67 | 255954049- Improvement of Goaldha to Malainagar road at ch. 00-2130m. | KDRIDP/Magura/W-44/2017-18 | 2.13 | 0 | 0 | 127.18 | 2018-02-26 | M/S : Khandoker Enterprise, Sreepur, Magura. | 2018-03-29 | 116.62 | 100% | 2018-10-03 | 112.91 | 112.91 | 0 | 96.82% | Final
68 | 255955292- Improvement of Chowgachi Purbapara Shibab more to Shariful Islam Ex. Chairman house road at ch. 00-1250m. | KDRIDP/Magura/W-45/2017-18 | 1.25 | 0 | 0 | 86.29 | 2018-02-26 | M/S : Hamza Traders, Sreepur, magura. | 2018-03-25 | 81.25 | 100% | 2018-10-02 | 81.25 | 81.25 | 0 | 100% | Final
Total |  |  | 52.018 | 0 | 0 | 3350.92 |  |  |  | 3132.612 | 83.11% |  | 1670.733 | 2056.427 | -385.694 | 65.65%
Improvement of Village Road by HBB
Magura Sadar
1 | 255574027-Pajhakhola R & H-Gobindapur Bazar via Dhalhara Paschimpara road. | [13 empty] | 0 | #DIV/0!
Mohammadpur
2 | 255665102-Khajarbaganpara-Bhabdia puratonpara road. | [13 empty] | 0 | #DIV/0!
Sreepur
3 | 255955029-Sonatundi-Amtoli bazar Road. | [13 empty] | 0 | #DIV/0!
4 | 255955194-Sachilapur Harizmolla house-Durgapur Akmal house Road. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
5 | 255955195-Kagoli - Hogladanga Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Upazila Road (7.30m width)
Salikha
1 | 255572005-Construction of 24.00m long RCC Girder Bridge on Kadamtala R&H-Hat Gopalpur via Hazipur-Sreerampur road at Ch : 4200.00 m | KDRIDP/Magura/B-02/2018-19 | 0 | 24 | 0 | 185.37 |  |  |  |  | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 24 | 0 | 185.37 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Salikha
1 | 255855109-Const. of RCC Bridge on Asbab-Baraichara Rd over Fatki River. | [13 empty] | 0 | #DIV/0!
2 | 255853002-Const. of RCC Bridge on Boulia-Sorsuna Road over Chitra River. | [13 empty] | 0 | #DIV/0!
Magura Sadar
3 | 255573004-Construction of 28.00m long PSC girder bridge on Isakhada-Hazipur UP road over Nabaganga river road at ch: 200.00m | KDRIDP/Magura/B-01/2018-19 | 0 | 28 | 0 | 210.215 | 2018-11-28 | Islam Traders, Jessore | 2019-01-06 | 207.459 | 30% | 2020-01-13 |  | 40 | -40 | 19.28%
Total |  |  | 0 | 28 | 0 | 210.215 |  |  |  | 207.459 | 30% |  | 0 | 40 | -40 | 19.28%
Maintenance
Magura Sadar
1 | 255572013-Periodic Maintenace of Jagla R&H to Beroil Polia GC via Borosoloi Ghat, School, Batikabari, Amria Bazar & Blugrame bazar road at ch. 00-3900m. & 8120-10370m. & 12800-14992m, & 17640-17895m. | KDRIDP/Magura/M-16/2017-18 | 8.597 | 0 | 0 | 266.8 | 2018-04-12 | Siddique Kabir(JV) Goalchmat, Faridpur | 2018-05-22 | 288.147 | 60% | 2018-11-27 |  | 82 | -82 | 28.46%
2 | 255573006-Periodic Maintenace of Raghobdair UP Office to (Ballo Bazar) to Dhanpara Bazar via Defulia Bazar road at ch. 3870-4900m. | KDRIDP/Magura/M-15/2017-18 | 1.03 | 0 | 0 | 25.859 | 2018-03-28 | M/S Anggosree Enterprise | 2018-05-03 | 24.566 | 10% | 2018-09-06 |  |  | 0 | 0%
3 | 255573007-Maintenance of Raghobdair UP Office (Ballo Bazar)-Bangha Tematha Bazar via Baliadanga Bazar road at (ch. 00.00m to 1000.00m) | KDRIDP/Magura/ M-19/2018-19 | 1 | 0 | 0 | 26.95 | 2018-11-12 | M/S R.K Traders Bisha road, Magura | 2018-12-10 | 25.6 | 75% | 2019-05-02 |  | 19.089 | -19.089 | 74.57%
| 255573016-Maintenance of Gopalgram UP Office-Kullia Bazar via Bahargag road at (ch. 8880.00m to 10000.00m) | KDRIDP/Magura/ M-19/2018-19 | 1.12 | 0 | 0 | 27.315 |  | M/S R.K Traders Bisha road, Magura |  | 25.949 |  |  |  | 19.347 | -19.347 | 74.56%
| 255573011-Maintenance of Moghi UP Office-Raghobdair Bazar via Andalbaria road at (ch. 00.00m to 1200.00m) | KDRIDP/Magura/ M-19/2018-19 | 1.2 | 0 | 0 | 34.68 |  | M/S R.K Traders Bisha road, Magura |  | 32.946 |  |  |  | 24.56 | -24.56 | 74.55%
4 | 255573012-Jagdol UP Office -Uttor Dharmashina (Asba Bazar) Road. | [13 empty] | 0 | #DIV/0!
5 | 255573015-Periodic Maintenace of Chowlia UP Office (Malikgram)-Jogdol UP office (Jogdol Kalitola) road at ch. 400.00m-2097m. | KDRIDP/Magura/M-14/2017-18 | 1.697 | 0 | 0 | 40.589 | 2018-07-10 | M/S Kuddus Enterprise, Jhenaidah. | 2018-08-19 | 42.21 | 0% | 2018-12-24 |  |  | 0 | 0%
6 | 255573018-Hazipur UP Office -Gangnalia Bazar via Boraichara Rd. | [13 empty] | 0 | #DIV/0!
8 | 255574010-Baharbag-Sayed Rupati Rd. | [13 empty] | 0 | #DIV/0!
9 | 255574015-Ghoranas-Kukila Rd. | [13 empty] | 0 | #DIV/0!
10 | 255574020-Vitashair R&H-Dhalahara bazar via Nischitonpur Rd. | [13 empty] | 0 | #DIV/0!
11 | 255574021-Bhabanhati Fhal (R&H)- Taghobdair Bazar via Bhabanhati Bazar Rd. | [13 empty] | 0 | #DIV/0!
12 | 255574024-Barosala School - Asba via Barosala ghat Rd. | [13 empty] | 0 | #DIV/0!
13 | 255574033-Ichakhada R&H-Defulia bazar Rd. | [13 empty] | 0 | #DIV/0!
14 | 255574036-Niznanduali Eidgha-Tangakhali bazar Rd. | [13 empty] | 0 | #DIV/0!
15 | 255574078-Beroil Polita R&H-Baharbag bazar Rd. | [13 empty] | 0 | #DIV/0!
16 | 255575109-Bashkhota - Jakarartach Rd. | [13 empty] | 0 | #DIV/0!
Salikha
17 | 255853009-Periodic Maintenance of Talkhori-Dighalgram road from ch. 00.00m to 1160.00m | KDRIDP/Magura/M-02/2017-18 | 1.16 | 0 | 0 | 30.11 | 2018-02-26 | Nishit Bashu, Kanchannagar, Jhenaidah. | 2018-04-03 | 32.82 | 100% | 2018-08-08 | 34.755 | 32.754 | 2.001 | 99.8% | Final
18 | 255853012-Talkhori -Naghosha via Sonadanga Rd. | [13 empty] | 0 | #DIV/0!
19 | 255854019-Periodic Maintenance of Krishnapur Pry. School R&H-Sreehatta UZR via Gopalgram road from ch. 00.00m to 1370.00m | KDRIDP/Magura/M-01/2017-18 | 1.37 | 0 | 0 | 27.07 | 2018-08-01 | M/S Khnondoker Enterprise, Khamarpara, Magura. | 2018-08-28 | 28.427 | 100% | 2018-10-28 | 27.918 | 27.918 | 0 | 98.21% | Final
Mohammadpur
20 | 255664007 Periodic Maintenance of Palasbaria hat-Fulbaria road from ch. 1000.00m to 2850.00m | KDRIDP/Magura/M-17/2017-18 | 1.85 | 0 | 0 | 49.126 | 2018-08-01 | M/S Amina Enterprise, Abalpur, Magura. | 2018-09-10 | 46.67 | 100% | 2019-02-12 |  | 28.828 | -28.828 | 61.77%
| 255663003-Periodic Maintenance of Digha UP Office-Dhuljuri Bazar road from ch. 00.00m to 1580.00m |  | 1.58 | 0 | 0 | 28.55 |  | M/S Amina Enterprise, Abalpur, Magura. |  | 27.123 |  |  |  | 16.75 | -16.75 | 61.76%
| 255664003 Periodic Maintenance of Nohata-Shaldha road from ch. 1700.00m to 2390.00m |  | 0.69 | 0 | 0 | 7.538 |  | M/S Amina Enterprise, Abalpur, Magura. |  | 7.16 |  |  |  | 4.422 | -4.422 | 61.76%
21 | 255663004-Polashbaria UP- Fulbaria Bazar Rd. | [13 empty] | 0 | #DIV/0!
22 | 255663006-Balidia UP Office -Rarikhalihat via Gopinathpurhat Rd. | [13 empty] | 0 | #DIV/0!
23 | 255663007-Balidia UP Office -Kalamdhari Bazar via Sreepur Rd. | [13 empty] | 0 | #DIV/0!
24 | 255663015-Binodpur UP- Madhabpurhat via Thakurerhat & Chuargatihat Rd. | [13 empty] | 0 | #DIV/0!
25 | 255663017-Mohammadpur H/Q-Balidia UP Office Rd. | [13 empty] | 0 | #DIV/0!
26 | 255663018-Polashbaria UP Office- Nohata GC via Chakulia Rd. | [13 empty] | 0 | #DIV/0!
27 | 255664017 Omedpur RHD to Gopinathpur bazar | [13 empty] | 0 | #DIV/0!
28 | 255664015 Mousha-Kanutia via Nikorhata Rd. | [13 empty] | 0 | #DIV/0!
29 | 255664023 Periodic Maintenance of Binodpur - Narayanpur road from ch.0.00m to 1300.00m | KDRIDP/Magura/M-18/2017-18 | 1.3 | 0 | 0 | 22.7 | 2017-07-10 | M/S Emon Enter Prise, Jhenaidah | 2018-08-13 | 23.835 | 100% | 2019-01-23 |  |  | 0 | 0%
| 255663011-Periodic Maintenance of Mohammadpur Hospital-Dhaoil Bazar via Horekrishnopur hat road from ch. 3660.00m to 4760.00m. |  | 1.1 | 0 | 0 | 13.46 |  | M/S Emon Enter Prise, Jhenaidah |  | 14.13 |  |  |  |  | 0 | 0%
| 255664060-Periodic Maintenance of Laxmipur to Balorampur road from ch. 0.00m to 475.00m |  | 0.475 | 0 | 0 | 8.77 |  | M/S Emon Enter Prise, Jhenaidah |  | 9.21 |  |  |  |  | 0 | 0%
30 | 255664027 Periodic Maintenance of Khajura-Sirgram road from ch. 2000.00m to 3960.00m | KDRIDP/Magura/M-06/2017-18 | 1.96 | 0 | 0 | 36.64 | 2018-02-26 | M/S : Emon Enterprise, Jhenaidah. | 2018-03-21 | 40.12 | 100% | 2018-07-26 | 39 | 39 | 0 | 97.21% | Final
31 | 255664033 Sirishdia R&H-Khalia Rd. | [13 empty] | 0 | #DIV/0!
32 | 255664019Billapara-Moifulkanda Rd. | [13 empty] | 0 | #DIV/0!
Sreepur
34 | 255953004-Periodic Maintenance of Sreekhol UP office Khamarpara-Khalia hat via Tupipara & Dosatina road from ch. 2456.00m to 3800.00m & 7000.00m to 9545.00m | KDRIDP/Magura/M-03/2017-18 | 3.889 | 0 | 0 | 84.5 | 2018-01-29 | M/S Khandoker Enterprise, Sreepur, Magura. | 2018-02-25 | 88.517 | 100% | 2018-06-30 | 88.52 | 88.52 | 0 | 100% | Final
35 | 255953010-Dariapur UP Office (Chawgachi) to Takerbila Bazar via Rajapur Bazar Rd. | [13 empty] | 0 | #DIV/0!
36 | 255954004-Periodic Maintenance of Chongacha-Noinshah Ghat road from ch. 00.00m to 1000.00m | KDRIDP/Magura/M-04/2017-18 | 1 | 0 | 0 | 25.08 | 2017-12-13 | M/S : Bismillah Traders, Chandpur, Magura. | 2018-01-24 | 25.08 | 100% | 2018-05-26 | 25.014 | 25.014 | 0 | 99.74% | Final
37 | 255954052-Nakol UP Office -WAPDA Bazar Rd | [13 empty] | 0 | #DIV/0!
38 | 255954061-Periodic Maintenance of Kamlapur Dharimath road from ch. 00.00m to 250.00m | KDRIDP/Magura/M-05/2017-18 | 0.25 | 0 | 0 | 4.377 | 2018-05-07 | M/S Anti Enter Prise Magura Pourashava |  | 4.59 | 100% | 2018-10-18 | 4.594 | 4.594 | 0 | 100.1% | Final
Total |  |  | 31.268 | 0 | 0 | 760.114 |  |  |  | 787.1 | 78.75% |  | 219.801 | 412.796 | -192.995 | 52.45%
GC-Hat
Magura Sadar
1 | Raghobdair Bazar | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Tree Plantation
Magura Sadar
1 | 255573007-Tree Plantation of Raghobdair UP (Ballo Bazar)-Bangha Tematha Bazar via Baliadanga Bazar road at ch: 1000-3000m. | KDRIDP/Magura/TP-02/2018-19 | 2 | 0 | 0 | 1.99 |  |  |  | 1.99 | 100% |  |  | 0.447 | -0.447 | 22.46%
Salikha
2 | Tree Plantation of Sigra-Naghosa via Gurpagla road at ch: 2000-3500m under Salikha Upazila, Dist. Magura | KDRIDP/Magura/TP-01/2018-19 | 1.5 | 0 | 0 | 1.127 |  |  |  | 1.127 | 100% |  |  | 0.943 | -0.943 | 83.67%
Mohammadpur
3 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Sreepur
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 3.5 | 0 | 0 | 3.117 |  |  |  | 3.117 | 66.67% |  | 0 | 1.39 | -1.39 | 44.59%
Grand Total |  |  | 140.131 | 52 | 0 | 7808.957 |  |  |  | 6932.353 | 49.63% |  | 3858.576 | 4902.391 | -1043.815 | 70.72%
|  |  | 140.131 | 52 | 0 | 7808.957 |  |  |  | 6932.353 | 40.76% |  | 3858.576 | 4902.391 | -1043.815 | 70.72%

## Magura Sadar
Magura Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 255572005-Improvement of Kadamtala R&H - Hat Gopalpur via Hazipur- Sreerampur road from ch. 11670.00m to 13731.00m | KDRIDP/Magura/W-39/2017-18 | 2.061 | 0 | 0 | 164.21 | 2017-12-19 | M/S : Khandoker Enterprise, Khamarpara, Sreepur, Magura. | 2018-01-21 | 148.35 | 100% | 2017-07-29 | 147.166 | 147.166 | 0 | 99.2% | Final
2 | 255572013-Improvement of Jagla R&H - Beroil Polita GC via Borosoloighat School- Batikabari-Amuria Bazar-Blugram road from ch. 11890.00m to 12800.00m | KDRIDP/Magura/ W-06/2016-17 | 0.91 | 0 | 0 | 57.899 | 2018-05-08 | Md. Zaman Ent: Mollapara, Magura | 2017-05-30 | 57.49 | 100% | 2017-11-05 | 57.49 | 57.49 | 0 | 100% | Final
Improvement of Union Road by BC
3 | 255573001-Improvement of Sattrujitpur UP-Amuria bazar via Baharbag bazar road from ch. 6770.00m to 8350.00m | KDRIDP/Magura/W-24/2017-18 | 1.58 | 0 | 0 | 97.12 | 2017-11-02 | Mohon Motsha Aroth, Pernanduali, Magura. | 2017-12-10 | 96.74 | 100% | 2018-06-17 | 96.72 | 96.72 | 0 | 99.98% | Final
4 | 255573002-Improvement of Moghi U.P Office-Jagdal U.P office via Jagla Chara Bottola road by BC (Ch.2146-5310m) | KDRIDP/Magura/W-60/2018-19 | 3.164 | 0 | 0 | 228.427 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 255573006-Raghobdair UP(Bolloh bazar)-Danpara bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 255573007-Improvement of Raghobdair UP Ballo Bazar-Bangha Tematha Bazar via Baliadanga bazar road from ch. 1650.00m to 4275.00m | KDRIDP/Magura/W-28/2017-18 | 2.625 | 0 | 0 | 154.93 | 2017-11-02 | M/S : Asif Construction, Abalpur, Magura. | 2017-11-26 | 144.48 | 100% | 2018-10-14 | 144.48 | 144.48 | 0 | 100% | Final
7 | 255573008-Improvement of Jagdal Bazar-Satrujitpur UP office road by BC (Ch.2370-3550m) | KDRIDP/Magura/W-61/2018-19 | 1.18 | 0 | 0 | 88.58 | 2019-05-06 | M/S Jakaullah & brothers,Chuadanga | 2019-06-26 | 88.57 | 0% | 2020-06-29 | 0 | 0 | 0 | 0% | 0
| 255573001-Improvement of Sattrujitpur UP-Amuria bazar via Baharbag bazar road (Ch.8350-9000m) |  | 0.65 | 0 | 0 | 45.587 |  |  |  | 45.58 |  |  | 0 | 0 | 0 | 0%
| 255573016-Improvement of Gopalgram U.P Office-Kullia Bazar (Ch.6963-7613m) |  | 0.65 | 0 | 0 | 47.595 |  |  |  | 47.59 |  |  | 0 | 0 | 0 | 0%
8 | 255573011-Moghi U.P Office- Raghobdair Bazar via Andalbaria road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 255573013-Improvement of Niznanduali bazar-Atharokhada Up office Kamar bari R&H road by BC from ch. 8921.00m to 9489.00m | KDRIDP/Magura/ W-10/2016-17 | 0.568 | 0 | 0 | 31.66 | 2017-05-31 | Md. Ziaul Haque, Ghoramara, Magura | 2017-07-13 | 31.606 | 100% | 2018-01-12 | 0 | 26.7 | -26.7 | 84.48% | 0
10 | 255573015-Chowlia UP office (Malikgram)- Jogdol UP office (Jogdol Kalitola) Road. | KDRIDP/Magura/W-42/2017-18 | 1.895 | 0 | 0 | 109.26 | 2018-02-26 | M/S : P.K. Traders. Kukna, Magura. | 2018-04-01 | 107.106 | 100% | 2019-02-25 | 106.716 | 106.716 | 0 | 99.64% | Final
11 | 255573003-Improvement of Bharbag Bazar-Baroil Polita UP road from ch. 00.00m to 2260.00m | KDRIDP/Magura/W-25/2017-18 | 2.26 | 0 | 0 | 136.85 | 2017-11-02 | M/S : P.K. Traders, Kukna, Magura. | 2017-11-29 | 124.95 | 100% | 2018-11-15 | 124.58 | 124.58 | 0 | 99.7% | Final
12 | 255573003-Improvement of Baharbag bazar-Beroil Polita UP road from ch. 2260.00m to 3760.00m | KDRIDP/Magura/W-40/2017-18 | 1.5 | 0 | 0 | 97.15 | 2018-01-29 | Modhubon Construction, Dudsara, Kotchandpur, Jhenaidah. | 2018-03-06 | 97.1 | 100% | 2018-08-09 | 0 | 58.93 | -58.93 | 60.69% | 0
13 | 255573003-Dharbag bazar-Barol Polta UP Road, | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | Duplicate
Improvement of Village Road by BC
14 | 255574002-Naldha Gangnalia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 255574015-Ghoranas-Kukila Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 255574018-Ramnagar Hat-Krishnapur via Thakurbari Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 255574020-Improvement of Vitashair RHD-Dhalahara bazar road by BC from ch. 6710.00m to 8180.00m & 8221.00m to 9320.00m | KDRIDP/Magura/W-08/2016-17 | 2.569 | 0 | 0 | 138.22 | 2017-05-31 | M/S : Aroma Enterprise, Ator Ali Road, Magura. | 2017-07-13 | 138.19 | 100% | 2018-02-18 | 138.09 | 138.09 | 0 | 99.93% | Final
18 | 255574021-Improvement of Bhabanhati Dhal (R&H)-Raghobdair Bazar via Bhabanhati Bazar road at ch:4755.00m-7782.00m | KDRIDP/Magura/W-47/2017-18 | 3.027 | 0 | 0 | 189.19 | 2018-05-07 | M/S Rohan Const. Mollapara, Magura | 2018-05-27 | 189.2 | 70% | 2019-06-30 | 0 | 128.337 | -128.337 | 67.83% | 0
19 | 255574022-Shalpara RHD-Sounpur H/O Zafar Mouri Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 255574024-Barosala School - Asba via Barosala ghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 255574025-Jagdal Dakhinpara FRB-Baharbag bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 255574033-Ichakhada R&H-Defulia bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 255574035-Improvement of Laskarpur Aksi more FRB-Katakhali GC road from ch. 500.00m to 1332.00m | KDRIDP/Magura/W-27/2017-18 | 0.832 | 0 | 0 | 50.21 | 2017-11-02 | M/S : Bali Construction, Tati Para, Magura. | 2017-11-29 | 50.2 | 100% | 2018-10-07 | 48.37 | 48.37 | 0 | 96.35% | Final
24 | 255574045-Improvement of Batkebari bazar-Jagla bazar road from ch. 07.00m to 638.00m | KDRIDP/Magura/W-30/2017-18 | 0.631 | 0 | 0 | 37.29 | 2017-11-02 | M/S : Abu Ishaq & Sons, Abu Ishaq road, Magura. | 2017-11-26 | 37.87 | 100% | 2018-05-04 | 37.87 | 37.87 | 0 | 100% | Final
25 | 255574078-Improvement of Beroil Polita R&H Baharbag bazar road from ch. 3623.00m to 4200.00m | KDRIDP/Magura/W-29/2017-18 | 0.577 | 0 | 0 | 34.35 | 2017-11-02 | Sumon Enterprise, Pernanduali, Magura. | 2017-11-26 | 34.29 | 100% | 2018-11-11 | 34.28 | 34.28 | 0 | 99.97% | Final
26 | 255574098-Improvement of Kechuadubi Pri. School- Bhabonhati bazar road from ch. 1000.00m to 1672.00m | KDRIDP/Magura/W-26/2017-18 | 0.672 | 0 | 0 | 40.14 | 2017-11-02 | M/S : Hayet Enterprise, Vaina, Magura. | 2017-11-28 | 40.1 | 100% | 2018-05-06 | 40.1 | 40.1 | 0 | 100% | Final
27 | 255574090-Improvement of Sreerampur-Sreepur Tremohone via Purba para Mosque road by BC from ch. 0.00m to 980.00m | KDRIDP/Magura/ W-11/2016-17 | 0.98 | 0 | 0 | 65.18 | 2017-05-31 | Md. Ali Ahmed Ahad, Vaina, Magura. | 2017-07-04 | 65.17 | 100% | 2017-12-10 | 64.54 | 64.54 | 0 | 99.03% | Final
28 | 255574041-Hazipur UP Office Ful Bari Boalia via Mostofapur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 255575012-Angardah-Kapiladanga | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 255574008-Improvement of Mirzapur-Nrihati road from ch. 2300.00m to 2598.00m | KDRIDP/Magura/W-41/2017-18 | 0.298 | 0 | 0 | 18.86 | 2018-05-07 | Pavel Enterprise Adarsopara, Magura | 2018-05-22 | 19.61 | 100% | 2018-09-22 | 19.61 | 19.61 | 0 | 100% | Final
31 | 255575020-Katakhali UZ road-beel Aksi (Badsha Mia)(Norshinghati pacca road-beel Aksi Magura road.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 255575018-Beel Aksi Purbopara-Aksi UZ Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 255575193-Improvement of Kapashhati Ball Fiedl to Kuknapara road at ch. 00-1617m | KDRIDP/Magura/W-43/2017-18 | 1.617 | 0 | 0 | 99.78 | 2018-02-26 | M/S : Rohima Trader, Mollapara, Magura. | 2018-03-29 | 91.76 | 100% | 2018-10-02 | 91.76 | 91.76 | 0 | 100% | Final
34 | 255574032-Improvement of Benga Tamatha to Maghail via Beroil Porbopara Bazar road at ch. 663-1663m. | KDRIDP/Magura/W-46/2017-18 | 1 | 0 | 0 | 60.53 | 2018-04-24 | Asif Construction, Eitkhola, Abalpur, Magura | 2018-05-21 | 57.506 | 100% | 2018-10-17 | 57.506 | 57.506 | 0 | 100% | Final
Improvement of Village Road by HBB
35 | 255574027-Pajhakhola R & H-Gobindapur Bazar via Dhalhara Paschimpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
36 | 255573004-Construction of 28.00m long PSC girder bridge on Isakhada-Hazipur UP road over Nabaganga river road at ch: 200.00m | KDRIDP/Magura/B-01/2018-19 | 0 | 28 | 0 | 210.215 | 2018-11-28 | Islam Traders, Jessore | 2019-01-06 | 207.459 | 30% | 2020-01-13 | 0 | 40 | -40 | 19.28% | 0
Maintenance
37 | 255572013-Periodic Maintenace of Jagla R&H to Beroil Polia GC via Borosoloi Ghat, School, Batikabari, Amria Bazar & Blugrame bazar road at ch. 00-3900m. & 8120-10370m. & 12800-14992m, & 17640-17895m. | KDRIDP/Magura/M-16/2017-18 | 8.597 | 0 | 0 | 266.8 | 2018-04-12 | Siddique Kabir(JV) Goalchmat, Faridpur | 2018-05-22 | 288.147 | 60% | 2018-11-27 | 0 | 82 | -82 | 28.46% | 0
38 | 255573006-Periodic Maintenace of Raghobdair UP Office to (Ballo Bazar) to Dhanpara Bazar via Defulia Bazar road at ch. 3870-4900m. | KDRIDP/Magura/M-15/2017-18 | 1.03 | 0 | 0 | 25.859 | 2018-03-28 | M/S Anggosree Enterprise | 2018-05-03 | 24.566 | 10% | 2018-09-06 | 0 | 0 | 0 | 0% | 0
39 | 255573007-Maintenance of Raghobdair UP Office (Ballo Bazar)-Bangha Tematha Bazar via Baliadanga Bazar road at (ch. 00.00m to 1000.00m) | KDRIDP/Magura/ M-19/2018-19 | 1 | 0 | 0 | 26.95 | 2018-11-12 | M/S R.K Traders Bisha road, Magura | 2018-12-10 | 25.6 | 75% | 2019-05-02 | 0 | 19.089 | -19.089 | 74.57% | 0
| 255573016-Maintenance of Gopalgram UP Office-Kullia Bazar via Bahargag road at (ch. 8880.00m to 10000.00m) |  | 1.12 | 0 | 0 | 27.315 |  |  |  | 25.949 |  |  | 0 | 19.347 | -19.347 | 74.56%
| 255573011-Maintenance of Moghi UP Office-Raghobdair Bazar via Andalbaria road at (ch. 00.00m to 1200.00m) |  | 1.2 | 0 | 0 | 34.68 |  |  |  | 32.946 |  |  | 0 | 24.56 | -24.56 | 74.55%
40 | 255573012-Jagdol UP Office -Uttor Dharmashina (Asba Bazar) Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 255573015-Periodic Maintenace of Chowlia UP Office (Malikgram)-Jogdol UP office (Jogdol Kalitola) road at ch. 400.00m-2097m. | KDRIDP/Magura/M-14/2017-18 | 1.697 | 0 | 0 | 40.589 | 2018-07-10 | M/S Kuddus Enterprise, Jhenaidah. | 2018-08-19 | 42.21 | 0% | 2018-12-24 | 0 | 0 | 0 | 0% | 0
42 | 255573018-Hazipur UP Office -Gangnalia Bazar via Boraichara Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 255574010-Baharbag-Sayed Rupati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 255574015-Ghoranas-Kukila Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 255574020-Vitashair R&H-Dhalahara bazar via Nischitonpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 255574021-Bhabanhati Fhal (R&H)- Taghobdair Bazar via Bhabanhati Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 255574024-Barosala School - Asba via Barosala ghat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
49 | 255574033-Ichakhada R&H-Defulia bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
50 | 255574036-Niznanduali Eidgha-Tangakhali bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
51 | 255574078-Beroil Polita R&H-Baharbag bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
52 | 255575109-Bashkhota - Jakarartach Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
53 | Raghobdair Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
54 | 255573007-Tree Plantation of Raghobdair UP (Ballo Bazar)-Bangha Tematha Bazar via Baliadanga Bazar road at ch: 1000-3000m. | KDRIDP/Magura/TP-02/2018-19 | 2 | 0 | 0 | 1.99 | 0 | 0 | 0 | 1.99 | 100% | 0 | 0 | 0.447 | -0.447 | 22.46% | 0
Total |  |  | 47.89 | 28 | 0 | 2627.416 |  |  |  | 2362.325 | 38.58% |  | 1209.278 | 1608.688 | -399.41 | 68.1%

## Mohammadpur
Mohammadpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 255662008-Improvement of Nohata GC- Gangarampur RHD via Panighata road by BC from ch. 2140.00m to 5425.00m | KDRIDP/Magura/W-09/2016-17 | 3.285 | 0 | 0 | 220.5 | 2017-05-31 | Mir Abu Syed, Mirpara, Magura. | 2017-07-04 | 220.47 | 100% | 2018-02-08 | 0 | 220.11 | -220.11 | 99.84% | Final
2 | 255662009 Mohommadpur upazila HQ- Ruijani RHD . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 255663003-Digha Up office-Dhuljuri Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 255663004 Palashbaria up to Fulbaria Bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 255663005-Palasbaria UP to Kalisankarpur Hat via Jhama Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 255663007-Improvement of Balidia UP office Kalamdhori Bazar via Sreepur road from ch. 00.00m to 3325.00m | KDRIDP/Magura/W-19/2017-18 | 3.325 | 0 | 0 | 186.85 | 2017-10-25 | Rasel Enterprise, Police Linepara, Magura. | 2017-11-26 | 186.61 | 100% | 2018-09-29 | 185.406 | 185.406 | 0 | 99.35% | Final
7 | 255663010 Mohammadpur UZ H/Q-Horekrisnapur road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 255663011-Improvement of Mohammadpur Hospital-Dhoail Bazar via Horekrishnapur hat road from ch. 1962.00m to 3210.00m | KDRIDP/Magura/W-21/2017-18 | 1.248 | 0 | 0 | 76.55 | 2017-10-25 | M/S : Amirun Enterprise, Rupsha, Khulna | 2018-12-03 | 69.76 | 70% | 2018-06-08 | 0 | 18 | -18 | 25.8% | 0
9 | 255663014 Bethuli Bazar (Kalukhandi More) to Babukahli UP via Dumurshia Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 255663016 Improvement of Aownara Bazar - Babukhali UP via Hatbaria Bazar road from ch. 00.00m to 1445.00m | KDRIDP/Magura/ W-12/2016-17 | 1.445 | 0 | 0 | 74.12 | 2017-10-18 | M/S : Asif Construction, Abalpur, Magura. | 2017-11-07 | 77.77 | 100% | 2018-05-14 | 76.85 | 76.85 | 0 | 98.82% | Final
11 | 255663018-Palasbaria UP office-Nohata GC via Chakulia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 255663027-Palasbaria UP to Gazir more bazar upto Joshobontopur RHD. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
13 | 255664015-Improvement of Mousha-Kanutia via Nikorhata road from ch. 700.00m to 4150.00m | KDRIDP/Magura/W-20/2017-18 | 3.45 | 0 | 0 | 195.75 | 2017-10-25 | Rasel Enterprise, Police Linepara, Magura. | 2017-11-26 | 195.55 | 100% | 2018-12-15 | 195.316 | 195.316 | 0 | 99.88% | Final
14 | 255664017 Omedpur RHD to Gopinathpur bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 255664020 Joyrampur to Mobarekpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 255664050-Panighata Sikderpara-Joyrampur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 25664056-Palasbaria Alemer more - Khalishakhali Hat Via Bethuri | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 255665211-Panighata Shikderpara Madrasha- Hasan Sk H/O- Delowar Sk. road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 255664043-Bangram-Mondalgati Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 255664096-Improvement of Joshobontopur H/S Bongram Pucca road via Shadan Pal house road from ch. 750.00m to 2100.00m | KDRIDP/Magura/W-22/2017-18 | 1.35 | 0 | 0 | 83.55 | 2017-10-25 | M/S : Asif Construction, Abalpur, Magura. | 2017-11-22 | 79.13 | 100% | 2018-04-29 | 78.06 | 78.06 | 0 | 98.65% | Final
21 | 255664104dariakha brigde more ti batiaghaga house | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 255664078 Improvement of Digha to foloshia road from ch. 00.00m to 586.00m | KDRIDP/Magura/W-23/2017-18 | 0.586 | 0 | 0 | 37.48 | 2017-10-25 | Md. Firoz Elahi, Satdoha Para, Magura. | 2017-11-27 | 37.27 | 100% | 2018-05-10 | 37.198 | 37.198 | 0 | 99.81% | Final
23 | 255664016-Jashpur R&H to Mousha Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 255664065-Improvement of Dumurshia Hat to Chalmia road by BC at ch.00m-1000m | KDRIDP/Magura/W-52/2018-19 | 1 | 0 | 0 | 78.394 | 2018-10-24 | M/S Tuli Enterprise Kanutia Bazar, Mohammadpur, Magura | 2018-11-25 | 74.47 | 100% | 2019-04-30 | 0 | 30 | -30 | 40.28% | 0
25 | 255664067-Improvement of Kumrul-palla road (Ch.2245-3450m) | KDRIDP/Magura/W-59/2018-19 | 1.205 | 0 | 0 | 82.616 | 2019-03-28 | R.K Traders,Vaina, Magura | 2019-05-05 | 78.485 | 0% | 2019-08-09 | 0 | 0 | 0 | 0% | 0
Improvement of Village Road by HBB
26 | 255665102-Khajarbaganpara-Bhabdia puratonpara road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
27 | 255664007 Periodic Maintenance of Palasbaria hat-Fulbaria road from ch. 1000.00m to 2850.00m | KDRIDP/Magura/M-17/2017-18 | 1.85 | 0 | 0 | 49.126 | 2018-08-01 | M/S Amina Enterprise, Abalpur, Magura. | 2018-09-10 | 46.67 | 100% | 2019-02-12 | 0 | 28.828 | -28.828 | 61.77% | 0
28 | 255663003-Periodic Maintenance of Digha UP Office-Dhuljuri Bazar road from ch. 00.00m to 1580.00m |  | 1.58 | 0 | 0 | 28.55 |  |  |  | 27.123 | 0% |  | 0 | 16.75 | -16.75 | 61.76%
29 | 255664003 Periodic Maintenance of Nohata-Shaldha road from ch. 1700.00m to 2390.00m |  | 0.69 | 0 | 0 | 7.538 |  |  |  | 7.16 | 0% |  | 0 | 4.422 | -4.422 | 61.76%
30 | 255663004-Polashbaria UP- Fulbaria Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 255663006-Balidia UP Office -Rarikhalihat via Gopinathpurhat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
32 | 255663007-Balidia UP Office -Kalamdhari Bazar via Sreepur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 255663015-Binodpur UP- Madhabpurhat via Thakurerhat & Chuargatihat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 255663017-Mohammadpur H/Q-Balidia UP Office Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 255663018-Polashbaria UP Office- Nohata GC via Chakulia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 255664017 Omedpur RHD to Gopinathpur bazar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 255664015 Mousha-Kanutia via Nikorhata Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 255664023 Periodic Maintenance of Binodpur - Narayanpur road from ch.0.00m to 1300.00m | KDRIDP/Magura/M-18/2017-18 | 1.3 | 0 | 0 | 22.7 | 2017-07-10 | M/S Emon Enter Prise, Jhenaidah | 2018-08-13 | 23.835 | 100% | 2019-01-23 | 0 | 0 | 0 | 0% | 0
| 255663011-Periodic Maintenance of Mohammadpur Hospital-Dhaoil Bazar via Horekrishnopur hat road from ch. 3660.00m to 4760.00m. |  | 1.1 | 0 | 0 | 13.46 |  |  |  | 14.13 |  |  | 0 | 0 | 0 | 0%
| 255664060-Periodic Maintenance of Laxmipur to Balorampur road from ch. 0.00m to 475.00m |  | 0.475 | 0 | 0 | 8.77 |  |  |  | 9.21 |  |  | 0 | 0 | 0 | 0%
39 | 255664027 Periodic Maintenance of Khajura-Sirgram road from ch. 2000.00m to 3960.00m | KDRIDP/Magura/M-06/2017-18 | 1.96 | 0 | 0 | 36.64 | 2018-02-26 | M/S : Emon Enterprise, Jhenaidah. | 2018-03-21 | 40.12 | 100% | 2018-07-26 | 39 | 39 | 0 | 97.21% | Final
40 | 255664033 Sirishdia R&H-Khalia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 255664019Billapara-Moifulkanda Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
43 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 25.849 | 0 | 0 | 1202.594 |  |  |  | 1187.763 | 25.48% |  | 611.83 | 929.94 | -318.11 | 78.29%

## Salikha
Salikha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 255852006: Improvement of Bunagati- Gangarampur via Pulum Bazar road from ch. 7756.00m to 9136.00m | KDRIDP/Magura/W-02/2016-17 | 1.38 | 0 | 0 | 89.3 | 2017-05-31 | Subash Enterprise, Shampur, Faridpur | 2017-07-06 | 89.27 | 100% | 2018-01-12 | 85.5 | 85.5 | 0 | 95.78% | Final
Improvement of Union Road by BC
2 | 255853001-Improvement of Poragachi-Horispur road from ch. 1390.00m to 4985.00m | KDRIDP/Magura/W-04/2016-17 | 3.6 | 0 | 0 | 190.036 | 2017-08-21 | Mir Abu Syed, Mirpara, Magura. | 2017-10-02 | 190 | 70% | 2018-04-07 | 0 | 100 | -100 | 52.63% | 0
3 | 255853001-Improvement of Poragachi-Horispur road from ch. 6535.00m to 7600.00m | KDRIDP/Magura/ W-03/2016-17 | 1.065 | 0 | 0 | 55.519 | 2017-05-08 | Md. Rana Amir Osman Vina, Magura. | 2017-05-30 | 54.41 | 100% | 2017-10-31 | 54.394 | 54.39 | 0.004 | 99.96% | Final
4 | 255853009-Improvement of Talkhori - Dighalgram road from ch. 1700.00m to 2745.00m | KDRIDP/Magura/W-31/2017-18 | 1.045 | 0 | 0 | 65.41 | 2017-11-02 | Nishit Bashu, Kanchannagar, Jhenaidah. | 2018-12-03 | 65.36 | 100% | 2018-06-29 | 65.36 | 65.36 | 0 | 100% | Final
5 | 255853010-Improvement of Sarsuna-Gorcrhat via Horiarkhal road at (ch: 00m to 2722m) | KDRIDP/Magura/W-62/2018-19 | 2.722 | 0 | 0 | 197.989 | 2019-08-05 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 255853011-Improvement of Singra-Naghosa via Gurpagla road from ch. 1400.00m to 3900.00m | KDRIDP/Magura/W-35/2017-18 | 2.5 | 0 | 0 | 152.67 | 2017-11-02 | Md. Ziaul Haque, Ghoramara, Magura. | 2018-12-03 | 152.66 | 100% | 2018-06-08 | 152.5 | 152.5 | 0 | 99.9% | Final
Improvement of Village Road by BC
7 | 255854001- Improvement of sandra Chowrastta- Singra Simakhali UZR At Goalkhali via kuskhali Salta beel- sandra road road from ch. 00.00m to 1410.00m | KDRIDP/Magura/W-33/2017-18 | 1.41 | 0 | 0 | 114.78 | 2018-01-29 | M/S : Kabirul Islam Siddiqui, Rotkhola, Goalchamot, Faridpur. | 2018-02-22 | 120.517 | 100% | 2018-08-27 | 120.44 | 120.44 | 0 | 99.94% | Final
8 | 255854004- Improvement of Hatbaria- Baulia Bazar road (Ch.1225-2950m) | KDRIDP/Magura/W-58/2018-19 | 1.725 | 0 | 0 | 121.34 | 2019-04-17 | M/S Kazi Mahabubur Rahman Jhenaidha. | 2019-05-29 | 121.085 | 0% | 2019-06-08 | 0 | 0 | 0 | 0% | 0
| 255854013-Improvement of Talkhari UP office Dhaneswargati Bazar via Gobindopur road (Ch. 1330-2062m) |  | 0.732 | 0 | 0 | 53.268 | 0 |  |  | 53.156 |  |  | 0 | 0 | 0 | 0%
9 | 255854010- Improvement of Satakhali R&H-Sandra FRB road (Ch.1500-2830m) | KDRIDP/Magura/W-56/2018-19 | 1.33 | 0 | 0 | 96.99 | 0 | 0 | 0 | 93.6 | 0% | 0 | 0 | 0 | 0 | 0% | 0
| 255854019- Improvement of Krishnapur Primary School (R&H)-Sreehatta R&H via Gopalgram road (Ch. 1370-2262m) |  | 0.892 | 0 | 0 | 63.39 |  |  |  | 61.175 |  |  | 0 | 0 | 0 | 0%
10 | 255854020- Improvement of Bhulbaria R&H-Thaipara via Nurpur road (Ch.1500-3450m) | KDRIDP/Magura/W-57/2018-19 | 1.95 | 0 | 0 | 145.345 | 2019-04-17 | M/S Kazi Mahabubur Rahman Jhenaidha. | 2019-05-29 | 145.04 | 30% | 2019-06-08 | 0 | 0 | 0 | 0% | 0
11 | 255855001- Improvement of Kholabaria -Harispur road from ch. 1000.00m to 3653.00m | KDRIDP/Magura/W-34/2017-18 | 2.653 | 0 | 0 | 162.4 | 2017-11-02 | Mir Abu Syed, Mirpara, Magura. | 2017-12-11 | 153.38 | 100% | 2018-06-17 | 0 | 100.437 | -100.437 | 65.48% | Final
12 | 255855003-Improvement of Rampur-Hatbaria road at (ch. 2743m to 3140m) | KDRIDP/Magura/W-64/2018-19 | 0.397 | 0 | 0 | 30.955 | 2019-07-17 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 255854002-Improvement of Satokhali Nutun Bazar- Katoli road at (ch. 2350m to 2519m + 3018m to 3330m) |  | 0.481 | 0 | 0 | 35.482 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
13 | 255855005- Raizadapur-Hazrahati Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 255855007-Improvement of Gongarampur - Gabtola road at (ch: 365m to 1400m | KDRIDP/Magura/W-63/2018-19 | 1.035 | 0 | 0 | 78.52 | 2019-07-17 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 255855021- Improvement of Kumarkota - Junary road from ch. 2375.00m to 4175.00m | KDRIDP/Magura/W-32/2017-18 | 1.8 | 0 | 0 | 108.98 | 2017-11-02 | Mir Abu Syed, Mirpara, Magura. | 2017-12-11 | 108.96 | 70% | 2018-06-17 | 0 | 50 | -50 | 45.89% | 0
16 | 255854013-Improvement of Talkhari UP Office- Dhaneswargati bazar via Gobindopur road from ch. 2062.00m to 3330.00m | KDRIDP/Magura/ W-05/2016-17 | 1.268 | 0 | 0 | 70.78 | 0 | M/S Lipi Jewellers Chuadanga | 2017-06-21 | 70.66 | 100% | 2017-12-17 | 70.6 | 70.6 | 0 | 99.92% | Final
Construction of Bridge on Upazila Road (7.30m width)
17 | 255572005-Construction of 24.00m long RCC Girder Bridge on Kadamtala R&H-Hat Gopalpur via Hazipur-Sreerampur road at Ch : 4200.00 m | KDRIDP/Magura/B-02/2018-19 | 0 | 24 | 0 | 185.37 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
18 | 255855109-Const. of RCC Bridge on Asbab-Baraichara Rd over Fatki River. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 255853002-Const. of RCC Bridge on Boulia-Sorsuna Road over Chitra River. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
20 | 255853009-Periodic Maintenance of Talkhori-Dighalgram road from ch. 00.00m to 1160.00m | KDRIDP/Magura/M-02/2017-18 | 1.16 | 0 | 0 | 30.11 | 2018-02-26 | Nishit Bashu, Kanchannagar, Jhenaidah. | 2018-04-03 | 32.82 | 100% | 2018-08-08 | 34.755 | 32.754 | 2.001 | 99.8% | Final
21 | 255853012-Talkhori -Naghosha via Sonadanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 255854019-Periodic Maintenance of Krishnapur Pry. School R&H-Sreehatta UZR via Gopalgram road from ch. 00.00m to 1370.00m | KDRIDP/Magura/M-01/2017-18 | 1.37 | 0 | 0 | 27.07 | 2018-08-01 | M/S Khnondoker Enterprise, Khamarpara, Magura. | 2018-08-28 | 28.427 | 100% | 2018-10-28 | 27.918 | 27.918 | 0 | 98.21% | Final
Tree Plantation
23 | Tree Plantation of Sigra-Naghosa via Gurpagla road at ch: 2000-3500m under Salikha Upazila, Dist. Magura | KDRIDP/Magura/TP-01/2018-19 | 1.5 | 0 | 0 | 1.127 | 0 | 0 | 0 | 1.127 | 100% | 0 | 0 | 0.943 | -0.943 | 83.67% | 0
Total |  |  | 32.015 | 24 | 0 | 2076.831 |  |  |  | 1541.647 | 50.87% |  | 611.467 | 860.842 | -249.375 | 55.84%

## Sreepur
Sreepur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 255953005-Improvement of Bakera Hat-Kadirpara Up office at Radhanagar GC road by BC From ch. 4339.00m to 6700m | KDRIDP/Magura/ W-07/2016-17 | 2.361 | 0 | 0 | 131.21 | 2017-07-24 | M/S : Rohan Construction, Mollapara, magura. | 2017-08-21 | 131.065 | 100% | 2018-04-15 | 131.05 | 131.05 | 0 | 99.99% | Final
2 | 255953007-Improvement of Kadirpara UP office at Radhanagar GC to Nokal bazar via Gashira road from ch. 00.00m to 1500.00m | KDRIDP/Magura/W-38/2017-18 | 1.5 | 0 | 0 | 89.43 | 2017-11-02 | M/S : Rohima Traders, Mollapara, Magura. | 2018-12-03 | 85.81 | 100% | 2018-06-08 | 85.81 | 85.81 | 0 | 100% | Final
3 | 255953008-Improvement of Tikerbila Hat- Amalshar UP office at chato Udash road from ch. 1150.00m to 3200.00m | KDRIDP/Magura/W-37/2017-18 | 2.05 | 0 | 0 | 119.21 | 2017-11-02 | M/S : Hamza Tradrs, Khamarpara, Sreepur, Magura. | 2017-11-26 | 117.84 | 100% | 2018-06-17 | 117.84 | 117.84 | 0 | 100% | Final
4 | 255953009-Improvement of Sabdalpur Hat- Sabdalpur UP office at Kajoli bazar road from ch. 1040.00m to 2765.00m & 2950m to 4055m | KDRIDP/Magura/W-36/2017-18 | 2.83 | 0 | 0 | 172.69 | 2017-11-02 | M/S : Rohima Traders, Mollapara, Magura. | 2017-12-03 | 155.51 | 100% | 2018-06-08 | 150.28 | 150.28 | 0 | 96.64% | Final
5 | 255953010-Dariapur UP Office (Chowgachi) to Tikerbila Bazar via Rajapur Bazar road at ch. 2800-3535m. & 4818-5023m | KDRIDP/Magura/ W-17/2016-17 | 0.94 | 0 | 0 | 49.95 | 2017-09-21 | M/S :Unic Traders, Mirpur, Kushtia. | 2017-07-25 | 49.94 | 100% | 2018-11-04 | 49.94 | 49.94 | 0 | 100% | Final
6 | 255953010-Improvement of Dariapur UP office Chowgachi to Tikerbila bazar via Rajapur bazar road by BC from ch.5023.00m to 5284.00m | KDRIDP/Magura/W-50/2017-18 | 0.261 | 0 | 0 | 17.62 | 2018-08-01 | M/S Razia Enterprise Alukdia Bazar, Magura. | 2018-08-29 | 16.74 | 50% | 2019-03-05 | 16.73 | 16.73 | 0 | 99.94% | Final
7 | 255953011-Improvement of Nakol UP- Durannagar hat via Kamlapur Pry.school road (Ch. 3750-4200m) | KDRIDP/Magura/W-53/2018-19 | 0.45 | 0 | 0 | 31.629 | 2019-03-28 | M/S Sarma Enterprise, Mollapara, Magura. | 2019-04-21 | 30.048 | 50% | 2019-06-27 | 0 | 0 | 0 | 0% | 0
8 | 255953015-Improvement of Nakol UP-WAPDA bazar road from ch. 1405.00m to 3700.00m | KDRIDP/Magura/ W-01/2016-17 | 2.295 | 0 | 0 | 119.27 | 2017-05-08 | Md. Ziaul Haque, Ghoramara, Magura | 2017-05-30 | 119.24 | 100% | 2017-12-05 | 119.23 | 119.23 | 0 | 99.99% | Final
9 | 255953016-Ganga Nanla bazar-Sabdalpur UP via Barishat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
10 | 255954004-Improvement of Chongacha-Noinshah ghat road (Ch.1000-1500m) | 0 | 0.5 | 0 | 0 | 38.718 | 2019-04-17 | Unique Construction Jhenaidha. | 2019-06-10 | 38.624 | 2.5% | 2020-06-17 | 0 | 0 | 0 | 0% | 0
| 255954009-Improvement of Sabdalpur bazar Durgapur road (Ch.200-1320m) |  | 1.12 | 0 | 0 | 81.035 |  |  |  | 80.838 |  |  | 0 | 0 | 0 | 0%
11 | 255954005-Baroipara boat Tola-Sreekhol bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 255954016-Sreepur-Kurundi via Chilgari bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 255954018-Improvement of Kachua-Razapur hat road by BC from ch.1680.00m to2495.00m | KDRIDP/Magura/W-51/2017-18 | 0.815 | 0 | 0 | 59.195 | 2018-08-01 | Rasel Enterprise, Policepara, Magura. | 2018-08-26 | 56.235 | 100% | 2019-02-28 | 51.27 | 51.27 | 0 | 91.17% | Final
| 255954042-Improvement of Dariapur Kalibari Shanbandha ghat via Dariapur Natunpara road by BC from ch.2950.00m to 3160.00m |  | 0.21 | 0 | 0 | 12.354 |  |  |  | 11.736 |  |  | 10.7 | 10.7 | 0 | 91.17% | 0
| 255955029-Improvement of Sonatundi-Amtoil bazar road by BC from ch.2750.00m to 3232.00m |  | 0.482 | 0 | 0 | 30.375 |  |  |  | 28.856 |  |  | 26.307 | 26.307 | 0 | 91.17% | 0
14 | 255954019-Hogoldanga-Razapur hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 255954027-Improvement of Dariapur Kalibari-Moheshpur via Malainagar road by BC from ch. 2200.00m to 4400.00m | KDRIDP/Magura/W-50/2017-18 | 2.2 | 0 | 0 | 133.756 | 2018-08-01 | M/S Razia Enterprise Alukdia Bazar, Magura. | 2018-08-29 | 127.068 | 50% | 2019-03-05 | 127.03 | 127.03 | 0 | 99.97% | Final
16 | 255954029-Improvement of Joka bridge Nobagram bridge via Mashalia road (Ch.2350-4300m) | KDRIDP/Magura/W-54/2018-19 | 1.95 | 0 | 0 | 139.99 | 2019-04-17 | M/S Asif Construction, Abalpur, Magura. | 2019-06-10 | 138.414 | 20% | 2019-05-03 | 0 | 0 | 0 | 0% | 0
17 | 255954037-Modhupur bazar-Gobindapur road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 255954052-Nakol UP office-Wapda Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 255954053-Sarongodia GPS-Sarongodia Purbopara Eidgha road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 255955033-Kamarpara-Barobell road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 255954066-Majhail pucca rd.-Madartola Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 255954014-Gashiara Purbopara Mosque-Kamlapur Primary School Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 255954080-Nakol Bazar- Boralidah West para Mosque road near house of Dulal Master to Sreepur- Ramnagar R&H at WAPDA Pamp House road at ch. 00-1454m | KDRIDP/Magura/ W-18/2017-18 | 1.454 | 0 | 0 | 95.28 | 2017-10-18 | M/S : Bali Construction, Tatipara, Magura | 2017-11-08 | 89.41 | 100% | 2018-05-15 | 89.19 | 89.19 | 0 | 99.75% | Final
24 | 255955212-Improvement of Boralidah Purbapara infront the H/O Bader Master to Towards H/O Bakkar Shek road from ch. 00.00m to 446.00m | KDRIDP/Magura/ W-16/2016-17 | 0.446 | 0 | 0 | 24.41 | 2017-07-24 | Mir Abu Syed, Mirpara, Magura. | 2017-08-16 | 24.39 | 100% | 2018-01-17 | 24.38 | 24.38 | 0 | 99.96% | Final
25 | 255955201-Improvement of Boralidah Asraf Mollas house-Ghasiara village via Boralida road from ch. 00.00m to 360.00m | KDRIDP/Magura/ W-14/2016-17 | 0.36 | 0 | 0 | 19.24 | 2017-07-24 | Mir Abu Syed, Mirpara, Magura. | 2017-08-16 | 19.23 | 100% | 2018-01-17 | 19.21 | 19.21 | 0 | 99.9% | Final
26 | 255955205-Improvement of Boralidah Purpapara Jame Mosque-Nakol Kali Bottola road from ch. 00.00m to 826.00m. Salvage Materials 34320.00 | KDRIDP/Magura/ W-15/2016-17 | 0.826 | 0 | 0 | 43.79 | 2017-07-24 | Mir Abu Syed, Mirpara, Magura. | 2017-08-16 | 43.777 | 100% | 2018-01-17 | 43.77 | 43.77 | 0 | 99.98% | Final
27 | 255955148-Baroipara Pucca road-Baroipara Primary School. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 255955006-WAPDA-Endurbaria Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 255955207-Improvement of Baralidoha Modhyapara-Salek Molla H/O Goalbari Rofik More road by BC from ch. 00.00m to 1380.00m. Salvage Materials 387799.00 | KDRIDP/Magura/W-48/2017-18 | 1.38 | 0 | 0 | 78.799 | 2018-06-07 | M/S Asif Construction Abalpur, Magura | 2018-07-09 | 74.86 | 100% | 2019-02-24 | 0 | 52.92 | -52.92 | 70.69% | 0
29 | 255954041-Improvement of Badonpur Bridge-Amlasar hat via Beelnathur road by BC from ch. 692.00m to 1300.00m. Salvage Materials 467984.00 |  | 0.608 | 0 | 0 | 35.728 |  |  |  | 33.94 |  | 0 | 0 | 24 | -24 | 70.71% | 0
30 | 255954031-Improvement of Kachua Upazila road to Tarauzail (Sreepur-Shalipur Upazila road-Kachua Kabil Molla House- Tarauzail School) Road. | KDRIDP/Magura/W-49/2017-18 | 0.82 | 0 | 0 | 51.01 | 2017-07-10 | M/S Hamza Traders, Khamarpara | 2018-08-08 | 50.99 | 100% | 2019-01-23 | 50.976 | 50.976 | 0 | 99.97% | Final
31 | 255954049- Improvement of Goaldha to Malainagar road at ch. 00-2130m. | KDRIDP/Magura/W-44/2017-18 | 2.13 | 0 | 0 | 127.18 | 2018-02-26 | M/S : Khandoker Enterprise, Sreepur, Magura. | 2018-03-29 | 116.62 | 100% | 2018-10-03 | 112.91 | 112.91 | 0 | 96.82% | Final
32 | 255955292- Improvement of Chowgachi Purbapara Shibab more to Shariful Islam Ex. Chairman house road at ch. 00-1250m. | KDRIDP/Magura/W-45/2017-18 | 1.25 | 0 | 0 | 86.29 | 2018-02-26 | M/S : Hamza Traders, Sreepur, magura. | 2018-03-25 | 81.25 | 100% | 2018-10-02 | 81.25 | 81.25 | 0 | 100% | Final
Improvement of Village Road by HBB
33 | 255955029-Sonatundi-Amtoli bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 255955194-Sachilapur Harizmolla house-Durgapur Akmal house Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 255955195-Kagoli - Hogladanga Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
36 | 255953004-Periodic Maintenance of Sreekhol UP office Khamarpara-Khalia hat via Tupipara & Dosatina road from ch. 2456.00m to 3800.00m & 7000.00m to 9545.00m | KDRIDP/Magura/M-03/2017-18 | 3.889 | 0 | 0 | 84.5 | 2018-01-29 | M/S Khandoker Enterprise, Sreepur, Magura. | 2018-02-25 | 88.517 | 100% | 2018-06-30 | 88.52 | 88.52 | 0 | 100% | Final
37 | 255953010-Dariapur UP Office (Chawgachi) to Takerbila Bazar via Rajapur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 255954004-Periodic Maintenance of Chongacha-Noinshah Ghat road from ch. 00.00m to 1000.00m | KDRIDP/Magura/M-04/2017-18 | 1 | 0 | 0 | 25.08 | 2017-12-13 | M/S : Bismillah Traders, Chandpur, Magura. | 2018-01-24 | 25.08 | 100% | 2018-05-26 | 25.014 | 25.014 | 0 | 99.74% | Final
39 | 255954052-Nakol UP Office -WAPDA Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 255954061-Periodic Maintenance of Kamlapur Dharimath road from ch. 00.00m to 250.00m | KDRIDP/Magura/M-05/2017-18 | 0.25 | 0 | 0 | 4.377 | 2018-05-07 | M/S Anti Enter Prise Magura Pourashava | 0 | 4.59 | 100% | 2018-10-18 | 4.594 | 4.594 | 0 | 100.1% | Final
Tree Plantation
41 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 34.377 | 0 | 0 | 1902.116 |  |  |  | 1840.618 | 48.11% |  | 1426.001 | 1502.921 | -76.92 | 81.65%

## Summary
MAGURA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 4 | 4 | 7.636 | 0 | 0 | 515.58 | 510.266 | 100% | 98.97%
Union Road by BC | 24 | 22 | 45.709 | 0 | 0 | 2286.485 | 1881.512 | 88.18% | 82.29%
Village Road by BC | 34 | 32 | 52.018 | 0 | 0 | 3132.612 | 2056.427 | 83.11% | 65.65%
Village Road by HBB |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Upazila Road | 1 |  | 0 | 24 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Union Road/Village Road | 1 | 1 | 0 | 28 | 0 | 207.459 | 40 | 30% | 19.28%
Maintenance | 12 | 12 | 31.268 | 0 | 0 | 787.1 | 412.796 | 78.75% | 52.45%
GC-Hat |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation | 2 | 2 | 3.5 | 0 | 0 | 3.117 | 1.39 | 66.67% | 44.59%
Total | 78 | 73 | 140.131 | 52 | 0 | 6932.353 | 4902.391 | 49.63% | 70.72%