## Kushtia
KUSHTIA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Mirpur
1 | 250942005-Improvement of Mirpur-Alamdanga GC via Halsha Road ch18730-20350m Salvage Cost Tk. 211042.00 | KDRIDP/KUSH/W-08/2016-17 | 1.62 | 0 | 0 | 124.4 | 2017-07-24 | M/S Sumsudoula mollek | 2017-09-13 | 130.16 | 100% | 2018-05-27 |  | 85 | -85 | 65.3% | work completed
Bheramara
2 | 250152007-Improvement of Pakshi R&H Fary Ghat via Moulahabaspur Golapnagar Bazar road-R&H (Dakabari) Dhorompur road ch: 5842-6083m & 7479-8944m Salvage Cost Tk. 418922.00 | KDRIDP/KUSH/W-11/2016-17 | 1.706 | 0 | 0 | 115.97 | 2017-07-24 | M/s Meherul Alam | 2017-09-14 | 109.688 | 100% | 2018-08-29 | 64.608 | 64.608 | 0 | 58.9% | Final
Khoksha
3 | 250632007-Improvement of Khoksha GC-Kushtia Rajbari RHD Vai Bosoa road.(Ch:4900-5950) Salvage Coast(Tk 571774.00). | KDRIDP/KUSH/W-33/2017-18 | 1.05 | 0 | 0 | 71.056 | 2017-10-02 | M/s Rupali Trders | 2017-11-27 | 69.46 | 100% | 2018-05-24 | 68.707 | 62.99 | 5.717 | 90.69% | Work completed
4 | 250632004-Khoksha-Ektarpur GC-Bonogram-Katlagaria. | [13 empty] | 0 | #DIV/0!
Kushtia Sadar
5 | 250792012-Bhadalia GC-Swargopur-Ballabpur R&H | [13 empty] | 0 | #DIV/0!
6 | 250792008-Improvement of Bashgrame GC Durbachara Razzaque more-Shibpur-Horinarayanpur Road. Ch:4100-5900m | KDRIDP/KUSH/W-15/2016-17 | 2.35 | 0 | 0 | 107.56 | 2017-07-31 | Md Ataur Rahman | 2017-09-14 | 106.476 | 100% | 2018-08-22 | 106.476 | 106.476 | 0 | 100% | Final
Daulatpur
7 | 250392012-Improvement of Kalayanpur Bazar-Daulatpur GC Road ch00-2440m Salvage Cost Tk. 4396874.00 | KDRIDP/KUSH/W-24/2017-18 | 2.44 | 0 | 0 | 180.88 | 2017-08-21 | Shamim Enterprise | 2017-09-14 | 175.46 | 100% | 2018-03-05 | 172.548 | 128.58 | 43.968 | 73.28% | work completed
8 | 250392012-Improvement of Kalayanpur Bazar-Daulatpur GC Road ch2440 -4528mSalvage Cost Tk. 2904017.00 | KDRIDP/KUSH/W-47/2017-18 | 2.09 | 0 | 0 | 120.76 | 2018-12-07 | Sadikuzzaman Khan Sumon | 2018-02-19 | 125.61 | 100% | 2018-06-24 | 125.55 | 96.511 | 29.039 | 76.83% | work completed
Total |  |  | 11.256 | 0 | 0 | 720.626 |  |  |  | 716.854 | 100% |  | 537.889 | 544.165 | -6.276 | 75.91%
Improvement of Union Road by BC
Kushtia Sadar
1 | 250793006-Improvement of Monohordia- Radhanagar-Chhaighoria-Bhabanipur Bazar Road. Ch5900-6000m Salvage cost Tk 49560.00 | KDRIDP/KUSH/W-18/2016-17 | 0.1 | 0 | 0 | 6.27 | 2017-07-31 | M/s Ahasan Habib | 2017-09-13 | 6.146 | 100% | 2018-01-28 |  | 5.28 | -5.28 | 85.91% | Final
2 | 250793017-Improvement of Shidurghat and Mazilahat Road. Ch 6500-8087m | KDRIDP/KUSH/W-19/2016-17 | 1.587 | 0 | 0 | 107.35 | 2017-07-31 | M/s Khan construction | 2017-09-14 | 103.96 | 100% | 2018-05-28 |  | 96.04 | -96.04 | 92.38% | work Completed
3 | 250793008-Improvement of Alampur UP - Alampur Hat - - Gajnabipur- Ujangram GC Road. (Ch.3250m-5415m). | KDRIDP/KUSH/W-57/2017-18 | 2.165 | 0 | 0 | 120.29 | 2017-12-24 | Md. Alamgir Zahan | 2018-02-12 | 119.205 | 60% | 2018-08-16 |  | 54.42 | -54.42 | 45.65% | WBM completed (28 days letter given on 16.04.18)
Daulatpur
4 | 250393004-Improvement of Refayetpur UP-Horingacha-Gazipur Hat road ch1250-2550m Salvage Cost Tk. 2356957.00 | KDRIDP/KUSH/W-25/2017-18 | 1.3 | 0 | 0 | 82.18 | 2017-08-21 | Shamim Enterprise | 2017-09-14 | 79.7 | 100% | 2018-01-28 | 79.7 | 79.7 | 0 | 100% | Final
5 | 250393004-Improvement of Refayetpur UP-Horingacha-Gazipur Hat road ch2550-3920m Salvage Cost Tk. 2706004.00 | KDRIDP/KUSH/W-48/2017-18 | 1.37 | 0 | 0 | 90.72 | 2018-02-15 | sadikuzzaman khan sumon | 2018-04-12 | 94.348 | 100% | 2018-10-14 |  | 67.29 | -67.29 | 71.32% | work completed
6 | 250393009-Taragunia GC-Kaipal H/O Nazimuddin-Basepur-Daulatpur UP Road. | [13 empty] | 0 | #DIV/0!
7 | 250393015-Refaetpur UP-Horingachi Malithapara-Paikpara-Naudapara Road. | [13 empty] | 0 | #DIV/0!
8 | 250393017-Boragangdia GC-Aria Shajimore-Parhsitly-Digholkandi Road. | [13 empty] | 0 | #DIV/0!
9 | 250393018-(a) Improvement of Dangmorka Bazar-Primary School-Adabaria UP Office-Tekalahat Road ch2000-3000m (b) Improvement of Dangmorka Bazar-Primary School-Adabaria UP Office-Tekalahat Road ch4058-4890m Salvage Cost Tk. 1189755.00 | KDRIDP/KUSH/W-26/2017-18 | 1.832 | 0 | 0 | 106.795 | 2017-08-21 | Md Abdur razzak | 2017-09-13 | 111.01 | 100% | 2018-09-09 | 110.91 | 110.91 | 0 | 99.91% | Final
Kumarkhali
10 | 250713001-Improvement of Bagulat UP Offich-Bharora Bazar Road.(Ch:5393-6392m) | KDRIDP/KUSH/W-32/2017-18 | 0.999 | 0 | 0 | 64.349 | 2017-09-12 | M/s Asif Enterprise | 2017-10-18 | 57.91 | 100% | 2018-07-05 |  | 47.384 | -47.384 | 81.82% | work completed
11 | 250713008-Improvement of Panti UP Offich-Kushlibasha Hat Via Ramdia, Monoharpur Road.(Ch:5190-6120m) | KDRIDP/KUSH/W-31/2017-18 | 0.93 | 0 | 0 | 59.18 | 2017-09-12 | M/s Rahman Enterprise | 2017-10-09 | 61.99 | 100% | 2018-04-12 |  |  | 0 | 0% | palasiding completed
12 | 250713009-Improvement of chandpur up office-kushlibasha hat via mohan nagar road.(Ch: 2600-3940m) | KDRIDP/KUSH/W-80/2017-18 | 1.34 | 0 | 0 | 77.29 | 2018-04-10 | Pampus Agro & Logistics Ltd | 2018-05-29 | 77.29 | 0% | 2019-02-27 |  |  | 0 | 0% | Not yet started & Cancellation letter sent.
13 | 250713010- Improvement of Zaduboyra UP Office - Lalon bazar via Zaduboyra hat road by BC. at Ch:1380-2510m . | KDRIDP/KUSH/W-91/2018-19 | 1.13 | 0 | 0 | 80.956 |  |  |  | 76.908 |  |  |  |  | 0 | 0%
14 | 250713013-Nandolalpur UP-Charikol Station bazar Rd. | [13 empty] | 0 | #DIV/0!
Khoksha
15 | 250633005-Khoksa (Moragacha) UP-Somospur via Rajinathpur Road. | [13 empty] | 0 | #DIV/0!
16 | 250633013- Improvement of Jpntihazra UP-Amlabaria via Dangipara road by BC. at Ch:3680-4490m .(Salvage Cost: 5,17,004) | KDRIDP/KUSH/W-90/2018-19 | 0.81 | 0 | 0 | 57.87 |  |  |  | 54.98 |  |  |  |  | 0 | 0%
17 | 250633014-Shomospur GC-Gopogram GC via Nichantabaria, Sathpakhia bazar road. | [13 empty] | 0 | #DIV/0!
Bheramara
18 | 250153003-Mokarimpur UP HQ-Dharampur Hat via SomitirHat Road. | [13 empty] | 0 | #DIV/0!
Mirpur
19 | 250943003-Improvement of Bahalbaria UP-Boria Bazar via Dhubail Bazar road ch: 2106-6420m & 9213-10270m Salvage Cost Tk. 3180964.00 | KDRIDP/KUSH/W-09/2016-17 | 5.371 | 0 | 0 | 320.11 | 2017-07-24 | Sayket Enterprise | 2017-09-20 | 335.145 | 100% | 2018-09-09 |  | 315.121 | -315.121 | 94.03% | Work completed
20 | 250943006-Baruipara UP-Jogti GC Road. | [13 empty] | 0 | #DIV/0!
21 | 250943010-Improvement of Kushabari-Chatian Up Via Burapara Miltoan Road. (Ch:1915-2960m) | KDRIDP/KUSH/W-49/2017-18 | 1.045 | 0 | 0 | 58.27 | 2017-10-10 | M/S Abu Hanif D sons | 2017-11-08 | 57.69 | 100% | 2018-05-13 |  | 26.13 | -26.13 | 45.29% | work completed
22 | 250943014-Improvement of Sorupdah (Poradah GC) -Mirpur Upazila HQ via Chatian Up Road ch11221-12260m Salvage Cost Tk. 955598.00 | KDRIDP/KUSH/W-10/2016-17 | 1.039 | 0 | 0 | 65.22 | 2017-07-24 | M/S Ekramul Haque | 2017-09-14 | 68.33 | 100% | 2018-03-29 | 67.977 | 67.98 | -0.003 | 99.49% | Final
Total |  |  | 21.018 | 0 | 0 | 1296.85 |  |  |  | 1304.612 | 88.33% |  | 258.587 | 870.255 | -611.668 | 66.71%
Improvement of Village Road by BC
Kushtia Sadar
1 | 250794011-Improvement of Nowpara - sargapur Road( ch:0.00m-1000m) | KDRIDP/KUSH/W-72/2017-18 | 1 | 0 | 0 | 63.265 | 2018-04-10 | Pampus Agro & Logistics Ltd | 2018-05-24 | 63.26 | 0% | 2019-02-27 |  |  | 0 | 0% | Cancelation letter given on 13.02.19 & memo no: 523
2 | 250794024-Improvement of Barkhada-Charulia Anwar Yousuf Road. Ch 6500-8087m | KDRIDP/KUSH/W-17/2016-17 | 1.587 | 0 | 0 | 68.71 | 2017-08-17 | Md Abdul Khaleque | 2017-09-13 | 64.888 | 100% | 2018-06-10 |  | 59.156 | -59.156 | 91.17% | work completed
3 | 250794053-Improvement of Astanagar-Jhawdia hat. Road Ch.1250-1405m. | KDRIDP/Kush/W-82/2017-18 | 0.155 | 0 | 0 | 9.41 | 2018-05-31 | Nice Home Constriction & Supplyer | 2018-07-24 | 9.69 | 60% | 2019-01-26 |  | 1.9 | -1.9 | 19.61% | sand filling Running
| 250794057-Improvement of Bhadalia- alampur Road( ch:0.00m-1280m). |  | 1.28 | 0 | 0 | 80.645 |  |  |  | 83.06 |  |  |  | 16.29 | -16.29 | 19.61% | sand filling Running
| 250794043-Improvement of gossami - durgapur bazar- gandi grangpara - natnaghat Road ( ch:500m-1010m) |  | 0.51 | 0 | 0 | 33.687 |  |  |  | 34.698 |  |  |  | 6.808 | -6.808 | 19.62% | sand filling Running
4 | 250794029-Improvement of sargapur - koboor hat Road (ch:0.00m-2340m). | KDRIDP/KUSH/W-70/2017-18 | 2.34 | 0 | 0 | 160.11 | 2018-04-10 | Pampus Agro & Logistics Ltd | 2018-05-29 | 160.11 | 35% | 2019-02-27 |  |  | 0 | 0% | ISG CompletedCancelation letter given on 13.02.19 & memo no: 524
5 | 250794031-Patikabari-Alamdanga via shakpara | [13 empty] | 0 | #DIV/0!
6 | 250794032-Improvement of Arpara Karimpur Road. (Ch.1240m-3060m) | KDRIDP/KUSH/W-55/2017-18 | 1.82 | 0 | 0 | 121.18 | 2017-12-24 | M/S. Rowshan Traders | 2018-02-08 | 120.75 | 20% | 2018-08-12 |  |  | 0 | 0% | palisading running 28 days Notice on 29.07.18, Memo :2248
7 | 250794038-Kamlapur Bazar-Ishakhali Road | [13 empty] | 0 | #DIV/0!
8 | 250794039-Improvement of R&H - Aqlampur- Chapaigachi- Dahokhola Road. (Ch.2290m-4750m) | KDRIDP/KUSH/W-54/2017-18 | 2.46 | 0 | 0 | 140.22 | 2017-12-24 | Md. Alamgir Zahan | 2018-02-12 | 138.89 | 20% | 2018-08-16 |  |  | 0 | 0% | (28 days letter given on 16.04.18)
9 | 250794040-Harinarayanpur-Purba Abdulpur Road | [13 empty] | 0 | #DIV/0!
10 | 250794062-Improvement of sonaidanga korimpur Road (ch:991m-2325m) | KDRIDP/KUSH/W-69/2017-18 | 1.334 | 0 | 0 | 117.61 | 2018-04-09 | Md. Abu Hena Mostofa Kamal | 2018-12-06 | 122.2 | 100% | 2019-02-27 |  | 80 | -80 | 65.47% | work Completed
11 | 250794064-Improvement of Asannagar Kasem mour-sankordia- natnaghat Road (ch:4000m-4897m) | KDRIDP/KUSH/W-68/2017-18 | 0.897 | 0 | 0 | 62.87 | 2018-05-07 | Shohag Enterprise | 2018-07-11 | 65.92 | 100% | 2019-01-12 |  | 50 | -50 | 75.85% | work Completed
12 | 250794077-Improvement of Jowdia Barrack more-Shai Mosque Darbar Sharif via Jowdia College ball field Road. Ch.00-358m Salvage Cost Tk 203031.00 | KDRIDP/Kush/W-07/2016-17 | 0.358 | 0 | 0 | 20.1 | 2017-07-18 | M/s Bijoy construction | 2017-08-27 | 18.7 | 100% |  | 18.7 | 18.7 | 0 | 100% | Final
13 | 250794079-Improvement of Jugia H&H water board Traning center-Sabgi Farm Road (ch:1918m-2543m). | KDRIDP/KUSH/W-76/2017-18 | 0.625 | 0 | 0 | 47.856 | 2018-04-10 | Md. Aminul Islam | 2018-05-24 | 45.46 | 100% | 2019-02-27 |  | 40.723 | -40.723 | 89.58%
14 | 250794026-Improvement of Astanagar Bazruk bakhoy Rd Ch.00-2160m Salvage Cost Tk 127976.00 | KDRIDP/Kush/W-06/2016-17 | 2.16 | 0 | 0 | 118.54 | 2017-05-25 | Md Akkas Ali Kushtia | 2017-06-22 | 117.05 | 100% | 2018-02-20 | 114.116 | 114.116 | 0 | 97.49% | Final
15 | 250795100-Improvement of bhatai senerchatal-farid member s house Road (ch:500m-1145m) | KDRIDP/KUSH/W-74/2017-18 | 0.645 | 0 | 0 | 41.11 | 2018-04-09 | Pampus Agro & logistics Ltd | 2018-06-14 | 43.16 | 0% | 2019-01-27 |  |  | 0 | 0% | Canceled
16 | 250795284-Improvement of Namdar Ali Biswass -H/O Akbor Ali Biswass H/O Hossain Mpndol Bora Khal Road (ch:0.00m-574m). | KDRIDP/KUSH/W-78/2017-18 | 0.574 | 0 | 0 | 37.778 | 2018-05-07 | M/S Ekramul Haque | 2018-07-01 | 39.629 | 60% | 2019-01-28 |  | 21.145 | -21.145 | 53.36% | BC Preparation
17 | 250794076-Improvement of Aisha Abed Berbaradi foundation Upokendro- Pamanagor Road. Ch.00-1700m Salvage Cost Tk 2233626.00 | KDRIDP/KUSH/W-21/2016-17 | 1.7 | 0 | 0 | 95.79 | 2017-07-31 | M/s Rowshon Traders | 2017-09-14 | 100.43 | 100% | 2018-03-29 |  | 94.62 | -94.62 | 94.21% | Work Completed
18 | 250795514- Improvement of Kumargara Kalimondir road-Kumargara towards road Ch:00-357m. (Salvage Cost: 1,63,289) | KDRIDP/Kush/W-89/2018-19 | 0.357 | 0 | 0 | 27.14 | [8 empty] | 0 | #DIV/0!
| 250794081- Improvement of Majhila Eidgah maidan-Majhila bazar-Majhila dakkhinpara Mosque road via Majhila mohila shomiti- Majhila Health center & Girls School road Ch:1336-2500m . |  | 1.164 | 0 | 0 | 84.757 | [8 empty] | 0 | #DIV/0!
19 | 250795181-Improvement of Takimara H/o Shek Joshimuddin - Takimara Graveyard Road. (Ch.0.00m-340m) | KDRIDP/KUSH/W-56/2017-18 | 0.34 | 0 | 0 | 22.67 | 2017-12-24 | Md. Alamgir Zahan | 2018-02-12 | 22.12 | 100% | 2018-06-17 | 22.12 | 22.12 | 0 | 100% | Work completed
20 | 250795305-Improvement of Horora Nocimon More-Community Clinic via Ducter Rahamot Road. Ch00-610m. | KDRIDP/KUSH/W-20/2016-17 | 0.61 | 0 | 0 | 34.97 | 2017-07-31 | M/s SR construction | 2017-09-14 | 34 | 100% | 2018-03-29 |  | 33.04 | -33.04 | 97.18% | work Completed
21 | 250795257-Improvement of koburhat H/O Babulm chairman-Shorgopur Road (ch:0.00m-335m). | KDRIDP/KUSH/W-75/2017-18 | 0.335 | 0 | 0 | 21.38 | 2018-05-31 | M/S Chunnu Enterprise (Md Saiful Islam) | 2018-07-17 | 20.31 | 45% | 2018-11-19 |  |  | 0 | 0% | WBM ON Going
22 | 250795604-Ziarikey Nagar Mohommadpur More-Nagar-Mohommadpur Graveyard road. | [13 empty] | 0 | #DIV/0!
23 | 250795228-Improvement of Hamida shiddque Collage & School-Bhadhalia para primary School via Boria Graveyard road (ch:1290m-2000m). | KDRIDP/KUSH/W-77/2017-18 | 0.71 | 0 | 0 | 45.759 | 2018-04-09 | Nice Home Constriction & Supplyer | 2018-06-14 | 47.13 | 100% | 2019-02-27 |  | 39.69 | -39.69 | 84.21% | work Completed
24 | 250795605-Improvement of Lahini Basgram road-H/O Ator Ali Mia-Peirpur Jame Mosque via H/O Shofiuddin Road. Ch 00-300m Salvage Cost Tk 190155.00 | KDRIDP/KUSH/W-16/2016-17 | 0.3 | 0 | 0 | 19.14 | 2017-07-31 | M/s SR construction | 2017-09-14 | 18.805 | 100% | 2018-09-03 | 18.168 | 18.168 | 0 | 96.61% | Final
25 | 250795117-Improvement of Belgoria medha para pacca road-Colloni para pacca Road. Ch00-2350m Salvage cost Tk 542962.00 | KDRIDP/KUSH/W-14/2016-17 | 2.35 | 0 | 0 | 134.68 | 2017-07-31 | M/s Turnna Trade system | 2017-09-12 | 139.745 | 100% | 2018-03-29 | 139.55 | 139.55 | 0 | 99.86% | Final
26 | 250795008-Jogia R&H-Mubarok Bandth | [13 empty] | 0 | #DIV/0!
Daulatpur
27 | 250394002-Bialgathua-Mohishkundi Road. | [13 empty] | 0 | #DIV/0!
28 | 250394017-Lalnagar-Laximpur Road. | [13 empty] | 0 | #DIV/0!
29 | 250394019-Improvement of Horingachi-Laximikhola Road ch837-1673m | KDRIDP/KUSH/W-27/2017-18 | 0.836 | 0 | 0 | 45.86 | 2017-08-21 | Md Shohel Choduary | 2017-09-13 | 48.115 | 100% | 2018-09-05 | 48.115 | 48.115 | 0 | 100% | Final
30 | 250394021-Improvement of Laximikhola- Horingachi road (ch.1000-2190m) | KDRIDP/KUSH/W-60/2017-18 | 1.19 | 0 | 0 | 73.768 | 2018-02-15 | sadikuzzaman khan sumon | 2018-04-12 | 76.715 | 100% | 2018-10-14 |  | 55 | -55 | 71.69% | work completed
31 | 250394030-Khalishakuandi-Moubaria Road. | [13 empty] | 0 | #DIV/0!
32 | 250394048-Jogonathpur-Pearpur Road. | [13 empty] | 0 | #DIV/0!
33 | 250394068-Improvement of shoshidarpur-Hoshenabad road (ch.980-2434m) | KDRIDP/KUSH/W-61/2017-18 | 1.454 | 0 | 0 | 86.69 | 2018-02-15 | Hisna Engineers (Md.Mohidul Islam Ripon) | 2018-07-17 | 97.176 | 100% | 2019-01-18 |  | 85 | -85 | 87.47% | work completed
34 | 250394074-Lalnagar bazar-Pakkula-Sadarpur GC Road. | [13 empty] | 0 | #DIV/0!
35 | 250394079-Sangrampur-Lalnagar bazar Rd | [13 empty] | 0 | #DIV/0!
36 | 250394082-Mothurapur Bazar-Gobargara-Darerpara-Daulatpur UP Road. | [13 empty] | 0 | #DIV/0!
37 | 250394084-Mainkdiar-Moslempur-Hogolbaria UP | [13 empty] | 0 | #DIV/0!
38 | 250394086 Chatarpara hat-Angdia-Sadarpur Road . | [13 empty] | 0 | #DIV/0!
39 | 250394065-Improvement of Bagoan-Poalbaria-Chilmari Road ch1100-1550m | KDRIDP/KUSH/W-28/2017-18 | 0.45 | 0 | 0 | 26.46 | 2017-08-21 | J.S Construction | 2017-09-04 | 27.72 | 100% | 2018-06-14 | 27.708 | 27.708 | 0 | 99.96% | Final
40 | 250394162-Improvement of H/O Fajlu Molla UZR at Dharmodah-Matpara ch00-1000m | KDRIDP/KUSH/W-29/2017-18 | 1 | 0 | 0 | 54.86 | 2017-08-21 | Md Shem Choduary | 2017-09-24 | 57.58 | 60% | 2018-09-10 |  |  | 0 | 0% | WBM Completed (ch;oo-500 m)
Bheramara
41 | 250154001-Improvement of Dharampur near Mango Garden-Maulahabaspur R.R. Bridge road. (Ch.2514-3455m) | KDRIDP/KUSH/W-45/2017-18 | 0.941 | 0 | 0 | 63.71 | 2017-12-07 | M/S Meherul Alam | 2018-02-18 | 60.88 | 100% | 2018-08-22 |  | 50.477 | -50.477 | 82.91% | Work completed
42 | 250154003-Improvement of Parankhali-Dalua Hat Road ch1000-2500m Salvage Cost Tk 2665728.00 | KDRIDP/KUSH/W-12/2016-17 | 1.5 | 0 | 0 | 83.29 | 2017-07-24 | National Enginearing | 2017-08-30 | 81.49 | 100% | 2018-03-29 | 80.407 | 79.23 | 1.177 | 97.23% | Final
43 | 250154005-Improvement of Thakur Daulatpur-Arkandi Rly Gate road ch00-1360m Road ID No-250154005 Salvage Cost Tk. 1638217.00 | KDRIDP/KUSH/W-13/2016-17 | 1.36 | 0 | 0 | 75.22 | 2017-07-24 | Md Nazmul Islam | 2017-09-14 | 72.13 | 100% | 2018-08-28 | 71.568 | 71.568 | 0 | 99.22% | Final
44 | 250154028-R&H 12 mile Cold Store -Baradi Hat Road. | [13 empty] | 0 | #DIV/0!
45 | 250154053-Jagssar Hat-Nalua Hat Road. | [13 empty] | 0 | #DIV/0!
46 | 250154090-Improvement of -Junidha Haripur-Gachia Daulatpur Battola More Vai Baktepur RD. (Ch:-1200-2123m) | KDRIDP/KUSH/W-42/2017-18 | 0.923 | 0 | 0 | 52.43 | 2018-12-07 | National Engineering | 2018-02-08 | 50.04 | 60% | 2018-08-22 |  | 27.043 | -27.043 | 54.04% | Sand filing completed
47 | 250154093-Improvement of Kazihata R&H -Mohishadora R&H -Via Amdha Rd. (1000-3030m) | KDRIDP/KUSH/W-43/2017-18 | 2.03 | 0 | 0 | 116.22 | 2017-12-07 | Md. Shamshodwha Mallick | 2018-02-13 | 110.006 | 40% | 2018-08-17 |  |  | 0 | 0% | Materials mobilized
48 | 250154068-Improvement of Pagli bitir House to Gopinathpur Gorostan road. (Ch:500-2000 m) | KDRIDP/KUSH/W-46/2017-18 | 1.5 | 0 | 0 | 92.038 | 2017-12-07 | M/s. Meherul Alam | 2018-02-18 | 88.62 | 100% | 2018-08-22 |  | 85 | -85 | 95.92% | Work completed
49 | 250154074-G.K Canle Bulbul Kabir’s house near of Chandripur Khalil house road | [13 empty] | 0 | #DIV/0!
50 | 250155228-Improvement of Uttar Bhabanipur Samsul `S Murri Mill-Abdul`S House road. (Ch: 00-705m) | KDRIDP/KUSH/W-44/2017-18 | 0.705 | 0 | 0 | 40.698 | 2017-12-07 | Abu Hena Mostofa Kamal | 2018-01-03 | 40.19 | 100% | 2018-06-09 | 40.189 | 40.189 | 0 | 100% | Final
Mirpur
51 | 250944018-Improvement of chuniapara -khewpur bazar Road (ch:1500m-3600m) | KDRIDP/KUSH/W-64/2017-18 | 2.1 | 0 | 0 | 144.94 | 2018-04-09 | Bashundhara Enterprise | 2018-05-20 | 137.696 | 100% | 2019-03-29 |  | 39 | -39 | 28.32% | work completed
52 | 250944034-Majihat bazar-Beshinagor rd. | [13 empty] | 0 | #DIV/0!
53 | 250944041-Improvement of Aburia-Ahsan Nagar Road. (Ch:0.00-1500m). | KDRIDP/KUSH/W-58/2017-18 | 1.5 | 0 | 0 | 84.47 | 2018-02-15 | MD.SARWAR HOSSAIN | 2018-04-17 | 88.485 | 60% | 2018-10-19 |  | 20 | -20 | 22.6%
54 | 250944056-Improvement of Chatian Uttorpara Hat - Atigram Golabari Hat Via Atigram FWC Road. (Ch:3600-4685m). | KDRIDP/KUSH/W-59/2017-18 | 1.085 | 0 | 0 | 78.5 | 2017-12-24 | Bashundhara Enterprise | 2018-02-18 | 76.808 | 100% | 2018-06-30 | 76.731 | 76.731 | 0 | 99.9% | Final
55 | 250944057- Improvement of Paharpur bazar(WDB bridge) -Amla bazar road Ch:(00-1350m)+(1700-2400m) | KDRIDP/KUSH/W-87/2018-19 | 2.05 | 0 | 0 | 146.583 | [8 empty] | 0 | #DIV/0!
56 | 250945023- Improvement of Gobindopur-Tatibandh road Ch:(00-1435m) (Salvage cost:27,20,817) | KDRIDP/KUSH/W-88/2018-19 | 1.435 | 0 | 0 | 121.91 | [8 empty] | 0 | #DIV/0!
57 | 250945099-Improvement of Sorupdah Madrasha-Gobindapur Hazrakhali Road. (Ch:850-1720m). | KDRIDP/KUSH/W-50/2017-18 | 0.87 | 0 | 0 | 47.68 | 2018-02-15 | Afsar Trading | 2018-07-09 | 50.04 | 60% | 2019-01-27 |  | 27.613 | -27.613 | 55.18%
58 | 250945184-Karir hat JHS-Bakek Mondol house road. | [13 empty] | 0 | #DIV/0!
59 | 250945235-Baliashisa mathpara- Dangarpara GPS road. | [13 empty] | 0 | #DIV/0!
60 | 250945239-Improvement of Ahammadpur-Amod Ali house -Bedonbil Bridge Road. (Ch:1300-2290m) | KDRIDP/KUSH/W-51/2017-18 | 0.99 | 0 | 0 | 66.7 | 2018-12-07 | M/S. Rowshan Traders | 2018-02-08 | 68.536 | 60% | 2018-08-12 |  | 16.084 | -16.084 | 23.47% | WBM completed.(28 days Notice on 14.08.18, Memo :2507 )
61 | 250945261-Improvement of Ramnagar bridge-Basbaria Road. (Ch:1300-2290m) | KDRIDP/KUSH/W-52/2017-18 | 0.935 | 0 | 0 | 56.29 | 2018-12-07 | M/S. Rowshan Traders | 2018-02-08 | 56.238 | 0% | 2018-08-12 |  |  | 0 | 0% | Contract cacelled, 28 days Notice on 14.08.18, Memo :2506
62 | 250945369-Improvement of chuniapara -khewpur Road( ch:0.00m-1838m) | KDRIDP/KUSH/W-67/2017-18 | 1.838 | 0 | 0 | 89.65 | 2018-04-09 | Bashundhara Enterprise | 2018-05-20 | 85.168 | 100% | 2019-03-29 |  | 24 | -24 | 28.18% | work completed
63 | 250945103-Nowab Sirajdaula college-(Syphone bridge)-Kewpur Charpara road | [13 empty] | 0 | #DIV/0!
64 | 250945381-Balidapara Mosque-Balidapara atiar H/O Road. | [13 empty] | 0 | #DIV/0!
65 | 250945382-Balidapara Anez Mondol H/O-Baruipara Noor Hosain H/O. road, | [13 empty] | 0 | #DIV/0!
66 | 250945375-Moshan Poraadaha road Babul H/O Kewpur Billpara road. | KDRIDP/KUSH/W-66/2017-18 | 0.405 | 0 | 0 | 25.798 | 2018-04-09 | Bashundhara Enterprise | 2018-05-20 | 24.508 | 100% | 2019-01-28 |  | 7 | -7 | 28.56% | Not yet Started
67 | 250945376-Improvement of Baruipara Ufan Member H/O-Fakirabad Mahatab H/O Road. (Ch:00-945m). | KDRIDP/KUSH/W-53/2017-18 | 0.945 | 0 | 0 | 55.49 | 2017-12-20 | Md. Aminul Islam | 2018-02-12 | 54.85 | 100% | 2018-08-16 | 54.85 | 54.85 | 0 | 100% | Final
68 | 250945376-Improvement of Baruipara Ufan Member H/O-Fokirabad Mahatab H/O Road. (Ch:1432m-1619 m) | KDRIDP/KUSH/W-62/2017-18 | 0.187 | 0 | 0 | 22.11 | 2018-02-01 | m/s asif traders | 2018-03-27 | 21.96 | 100% | 2018-08-29 |  | 21.862 | -21.862 | 99.55% | Work completed
69 | 250945370-Improvement of balidapara Hinif H/O- balidapara salam H/O road. (Ch:0.00m-1515m). | KDRIDP/KUSH/W-65/2017-18 | 1.515 | 0 | 0 | 97.517 | 2018-04-09 | Nice Home Construction & Supplyer | 2018-05-27 | 92.64 | 10% | 2019-02-27 |  |  | 0 | 0% | Materials mobilization on going
Kumarkhali
70 | 250714001- Improvement of Zaduboyra hat-Sandiara via Bhalbaria road by BC. At Ch:(00-700m)+(1750-2720m). (Salvage Cost: 1,30,792) | KDRIDP/KUSH/W-92/2018-19 | 1.67 | 0 | 0 | 136.925 | [8 empty] | 0 | #DIV/0!
71 | 250714005-Improvement of Sandiara Canal-Enayetpur Via Krisnapur Hat Rd. (Ch:00-700m & 2840-3930m) | KDRIDP/KUSH/W-30/2017-18 | 1.79 | 0 | 0 | 103.93 | 2017-09-12 | M/s Asif Enterprise | 2017-10-18 | 93.54 | 100% | 2018-07-05 |  | 76.625 | -76.625 | 81.92% | work completed
72 | 250714016-Kanchanpur- Niamotbari School Rd. | [13 empty] | 0 | #DIV/0!
73 | 250715006-Improvement of Valuka Canal- Nagarkoya Road.(Ch:00-1070 m) | KDRIDP/KUSH/W-38/2017-18 | 1.07 | 0 | 0 | 64.51 | 2017-09-26 | M/s Gorai pipe Industry | 2017-10-31 | 63.87 | 100% | 2018-03-24 | 63.61 | 63.61 | 0 | 99.59% | Final
74 | 250714026-Improvement of Baraichara-Ramdia Road. Ch.1200-1920m. | KDRIDP/Kush/W-01/2016-17 | 0.72 | 0 | 0 | 41.36 | 2017-05-25 | Md Shahidur Rahman Mintu Kalisonkorpur Kushtia | 2017-06-22 | 38.88 | 100% | 2018-03-28 | 38.258 | 38.26 | -0.002 | 98.41% | Final
75 | 250714028-Improvement of Baraichara-Naturia bazar Road.(Ch:00-1000 m) Salvage Coast Tk 66824.00 | KDRIDP/KUSH/W-39/2017-18 | 1 | 0 | 0 | 55.92 | 2017-09-26 | Md Liakot Ali | 2017-11-20 | 58.68 | 100% | 2018-10-30 |  | 56 | -56 | 95.43% | Work Completed
76 | 250714030-Improvement of Chapra-Madhupur road at ch00-1970m & 2035-3300m. | KDRIDP/KUSH/W-63/2017-18 | 3.235 | 0 | 0 | 203.07 | 2018-02-08 | M/S Sabit Enterprise | 2018-07-24 | 217.6 | 15% | 2019-01-25 |  |  | 0 | 0% | Sand filling on going.
77 | 250714035- Improvement of Kamlapur-Dhekipara road by BC. At Ch:(1000-2085m). (Salvage Cost: 53,657) | KDRIDP/KUSH/W-93/2018-19 | 1.085 | 0 | 0 | 87.41 | [8 empty] | 0 | #DIV/0!
| 250714086- Improvement of Khordo Valuka-Nagarokoya graveyard road by BC. At Ch:(00-1060m). (Salvage Cost: 1,44,806) |  | 1.06 | 0 | 0 | 86.62 | [8 empty] | 0 | #DIV/0!
78 | 250714041- Improvement of Durgapur pacca road to puraton Charikpl (Durgapur Khokn house-Prodon Charikol) road Ch:(1200-1585m). (Salvage Cost: 8,40,596) | KDRIDP/KUSH/W-94/2018-19 | 0.385 | 0 | 0 | 31.017 | [8 empty] | 0 | #DIV/0!
| 250714108- Improvement of Jotmora- Maudpur bazar road by BC. At Ch:(900-2278m) . (Salvage Cost: 1,30,792) |  | 1.302 | 0 | 0 | 104.268 | [8 empty] | 0 | #DIV/0!
79 | 250714048-Improvement of Tarapur to Maliat via Baniakandi Rd ch: 1450-2590m. | KDRIDP/KUSH/W-22/2016-17 | 1.14 | 0 | 0 | 62.83 | 2017-09-25 | Md Abul Kashem Sorower Pabari | 2017-11-05 | 65.88 | 60% | 2018-05-09 |  | 20 | -20 | 30.36% | WBM completed & BC under process.
80 | 250714071-Sadipur-Ghoespur Road. | [13 empty] | 0 | #DIV/0!
81 | 250714084-Improvement of Khal bazar-Shalghor Madhua Rd Ch.00-1000m | KDRIDP/Kush/W-03/2016-17 | 1 | 0 | 0 | 54.82 | 2017-05-25 | Md Liakot Ali Kumarkhali Kushtia | 2017-07-04 | 52.08 | 100% | 2018-02-19 |  | 45.952 | -45.952 | 88.23% | BC preparetion
82 | 250714103-Improvement of Gobrab GPS -Khacakkhol Paka road ch00-1000m. | KDRIDP/KUSH/W-23/2017-18 | 1 | 0 | 0 | 60.5 | 2017-09-25 | Md Sumsu dhuda mollik | 2017-11-05 | 63.15 | 60% | 2018-05-17 |  | 15 | -15 | 23.75% | WBM Completed, BC under process. (28 days notice on 14.08.18 , memo: 2503
83 | 250714104-Bashgram bazar-Kushlibasha hat road. | [13 empty] | 0 | #DIV/0!
84 | 250714105-Improvement of Modupur Bazar-Nathuria Bazar road.(Ch:1225-1910m) | KDRIDP/KUSH/W-40/2017-18 | 0.685 | 0 | 0 | 38.68 | 2017-09-26 | M/s Millenium enterprise | 2017-11-12 | 40.54 | 100% | 2018-11-06 |  | 31.88 | -31.88 | 78.64% | work Completed
85 | 250714115-Khairchara RHD-Agrikundu via Pathorbaria Road. | [13 empty] | 0 | #DIV/0!
86 | 250714175-Improvement of Birikya UZR-Sazipara Bridge Vai Beltala road. (Ch:00-290 m) &1245-3245m Salvage Coast (Tk 27821.00) | KDRIDP/KUSH/W-41/2017-18 | 2.29 | 0 | 0 | 139.97 | 2017-09-26 | Md Ataur Rahman Ata | 2017-11-05 | 139.67 | 100% | 2018-05-09 | 139.66 | 139.66 | 0 | 99.99% | Final
87 | 250714177-Koburhat Jr. High School- Biswasbari Graveyard Road. | [13 empty] | 0 | #DIV/0!
88 | 250715100-Improvement of Chandpur bazar-Madhupur bazar road (ch -800m-2150m ) | KDRIDP/KUSH/W-79/2017-18 | 1.35 | 0 | 0 | 80 | 2018-04-26 | M/S Millenium Enterprise | 2018-06-14 | 82.406 | 10% | 2019-02-27 |  |  | 0 | 0% | lay out given & materials mobilization on going.
89 | 250715063-Improvement of Dhalnagar Mollapara-Dhalnagar Mirpara Graveyard via Mr.Somen house Road. Ch.00-1000m Salvage Cost Tk 219180.00 | KDRIDP/Kush/W-02/2016-17 | 1 | 0 | 0 | 54.88 | 2017-05-25 | Md Liakot Ali Kumarkhali Kushtia | 2017-07-04 | 52.13 | 100% | 2018-05-18 |  | 43.64 | -43.64 | 83.71% | Work completed
90 | 250715132- Nandolalpur UP Office to H/O Engr. Kamal Uddin Road. | [13 empty] | 0 | #DIV/0!
91 | 250715137- Improvement of Ethmampur Shah jalal mor-Ethmampur graveyard Road Ch. 00-1000m. | KDRIDP/Kush/W-04/2016-17 | 1 | 0 | 0 | 60.83 | 2017-05-25 | M/s Uttom Kumar Kundu Pangsha Rajbari | 2017-07-05 | 57.69 | 100% | 2018-06-11 | 48.9 | 48.9 | 0 | 84.76% | Work completed
92 | 250715063-250715063 Dhalnagar mollhapara- Dhalnagar Mirpara Graveyard via Mir Borhan Ali house road | [13 empty] | 0 | #DIV/0!
Khoksha
93 | 250634001-Khoksa (Moragacha) UP-Dudrajpur | [13 empty] | 0 | #DIV/0!
94 | 250634011-Improvement of Gonesshpur Bazar-Panti GC road Khoksha protion . (Ch:1060-1700m) Salvage Cost (Tk :1089453.00) | KDRIDP/KUSH/W-37/2017-18 | 0.64 | 0 | 0 | 41.175 | 2017-09-26 | M/s Rowshon Traders | 2017-11-22 | 43.13 | 100% | 2018-05-03 | 43.1 | 43.1 | 0 | 99.93% | Final
95 | 250634012-Uazila HQ-Mirzapur RHD Road. | [13 empty] | 0 | #DIV/0!
96 | 250634014- Improvement ofRaipur Charabotgac-Hizlabot bazar Sreepur Primary School via Devinagar Primary School road. (Ch:00-1390m) | KDRIDP/KUSH/W-81/2017-18 | 1.39 | 0 | 0 | 85.329 | 2018-05-31 | Md. Rashedul Harun Sajol | 2018-07-24 | 89.595 | 60% | 2019-02-25 |  | 33.1 | -33.1 | 36.94% | WBM Completed
| 250634035- Improvement of Osmanpur Kheyaghgat-Raypur bottalla mor via Raypur graveyard road (ch:1000m-2275m). |  | 1.275 | 0 | 0 | 80.999 |  |  |  | 85.049 |  |  |  | 31.426 | -31.426 | 36.95% | WBM Completed
97 | 250634015-Ramanathpur GK canal-Goneshpur Bazar Road. | [13 empty] | 0 | #DIV/0!
98 | 250634022-Shimulia RHD-Tatipara Care Bridge | [13 empty] | 0 | #DIV/0!
99 | 250634023-Biljani Eidgah-Biljani Bazar Rd. | [13 empty] | 0 | #DIV/0!
100 | 250635014- Improvement of Raypur chara Bot gach-Osmanpur GPS GK Canel road ch-1390-1750m. | KDRIDP/KUSH/W-83/2018-19 | 0.36 | 0 | 0 | 26.04 | 2018-10-25 | Md. Mujibul Haque Khan Chowdhuri | 2018-12-10 | 24.738 | 60% | 2019-06-13 |  |  | 0 | 0% | WBM Completed
| 250635037-Improvement of ajol care bridge - mohisgari beel road at 977-1550m |  | 0.573 | 0 | 0 | 40.695 |  | Md. Mujibul Haque Khan Chowdhuri |  | 38.66 |  |  |  |  | 0 | 0% | WBM Completed
| 250634019 Improvement of Osmanpur up office bari badh via raipur mosque road by bc at ch 00.0m-570.0m |  | 0.57 | 0 | 0 | 40.45 |  | Md. Mujibul Haque Khan Chowdhuri |  | 38.428 |  |  |  |  | 0 | 0% | WBM Completed
101 | 250635019-Improvement of Komlapur-Narayanpur road.(Ch:710-1600m) Salvage Coast(Tk 571774.00) | KDRIDP/KUSH/W-35/2017-18 | 0.89 | 0 | 0 | 49.127 | 2017-09-26 | M/s Hashib Enterprise Rajbari | 2017-11-05 | 51.44 | 100% | 2018-05-09 |  | 50.4 | -50.4 | 97.98% | Work Completed
102 | 250635039-Improvement of Iswardi-Beharia Shiekpara road.(Ch:1860-2750m) Salvage Coast(Tk 571774.00) | KDRIDP/KUSH/W-34/2017-18 | 0.89 | 0 | 0 | 49.66 | 2017-09-26 | M/s Hashib Enterprise Rajbari | 2017-11-05 | 52 | 100% | 2018-05-09 |  | 52 | -52 | 100% | Work Completed
103 | 250634007-Improvement of Mashilia Bazar to Boraichar road. (Ch:00-1160m) Salvage Coast(Tk :14105060.00). | KDRIDP/KUSH/W-36/2017-18 | 1.16 | 0 | 0 | 75.019 | 2017-09-26 | Md Rohim Khan | 2017-11-05 | 78.55 | 100% | 2018-04-26 | 78.48 | 78.48 | 0 | 99.91% | Final
104 | 250635059-Fulbaria RHD - Pangsha Boundary via Laxandia Road. | [13 empty] | 0 | #DIV/0!
105 | 250635076-Sreepur H/O Liakot - Military Botgas Via Sreepur RNG Primary School. | [13 empty] | 0 | #DIV/0!
Total |  |  | 85.885 | 0 | 0 | 5414.293 |  |  |  | 4605.302 | 78.31% |  | 1124.23 | 2480.529 | -1356.299 | 53.86%
Improvement of Village Road by HBB
Kushtia Sadar
1 | 250794020-Bisnudia-Abdalpur Rd. | [13 empty] | 0 | #DIV/0!
Daulatpur
2 | 250394002-Bialgathua-Mohishkundi Road. | [13 empty] | 0 | #DIV/0!
Mirpur
3 | 250945206-Kachubaria Kazi Arif Sarok- Chuwduar Via Kachubaria Grave Yerd Road. | [13 empty] | 0 | #DIV/0!
4 | 250945237- Improvement of Belgachi Club via Sabed Member house road Ch:00-2130m. | KDRIDP/KUSH/W-85/2018-19 | 2.13 | 0 | 0 | 96.9 |  |  |  | 92.06 |  |  |  |  | 0 | 0%
5 | 250945248-Jogoti Sugar Mill Grave Yerd- BTC gate via Kalabaria Purbapara Jame Mosque Road. | [13 empty] | 0 | #DIV/0!
6 | 250945250- Improvement of Kalabaria Eidgah-Dosttopara via GK khal road Ch:00-915m.(Salvage cost:3,18,439) | KDRIDP/KUSH/W-86/2018-19 | 0.915 | 0 | 0 | 40.423 |  |  |  | 38.402 |  |  |  |  | 0 | 0%
| 250945252- Improvement of Poradah Chitalia Moinagari gate-Sodirazpur road Ch:500-1827m. |  | 1.327 | 0 | 0 | 56.29 |  |  |  | 53.476 |  |  |  |  | 0 | 0%
Kumarkhali
7 | 250714016-Gottia-Baradi-Fultala Rd | [13 empty] | 0 | #DIV/0!
8 | 250714069- Improvement of Kamarkandi- Kashaba road at ch-00-1300m | KDRIDP/KUSH/W-84/2018-19 | 1.3 | 0 | 0 | 56.61 | 2019-01-16 | Md. Jinnath Ali Jinnah (pabna) | 2019-03-06 | 56.069 | 66% | 2019-09-07 |  | 12.685 | -12.685 | 22.62%
| 250714070-Improvement of Gospur -gobindopur via sadipur road ch: 00-2100m |  | 2.1 | 0 | 0 | 78.76 |  |  |  | 78.008 |  |  |  | 17.645 | -17.645 | 22.62%
| 250714071- Improvement of Gospur- Sadipur road ch-3300-5202m |  | 1.902 | 0 | 0 | 87.81 |  |  |  | 86.97 |  |  |  | 19.67 | -19.67 | 22.62%
Total |  |  | 9.674 | 0 | 0 | 416.793 |  |  |  | 404.985 | 66% |  | 0 | 50 | -50 | 12.35%
Construction of Bridge on Upazila Road (7.30m width)
Kushtia Sadar
1 | 250792008-Const. of RCC Bridge on Bashgrame GC- Shibpur-Horinarayanpur Road. | [13 empty] | 0 | #DIV/0!
2 | 250792004- Construction of 12.00m Long RCC Girder Bridge on Kushtia (Lahini)- Bashgram GC Road at Ch: 6750m. | [13 empty] | 0 | #DIV/0!
3 | 250792004-Kushtia (Lahini)-Bashgram G.C Road | KDRIDP/KUSH/B-01/2017-18 | 0 | 12 | 0 | 119.717 | 2019-01-15 | M/S. Islam Traders | 2019-03-06 | 113.11 | 0% | 2020-01-20 |  |  | 0 | 0% | 28 days notice on 13.05.19, Memo : 1334
4 | 250792005- Bittipara Hat R&H-Jamjami G.C via Jhowdia Hat Road | [13 empty] | 0 | #DIV/0!
5 | 250792005- Construction of 45.00m Long RCC Girder Bridge on Kushtia Bittipara Hat R&H- Jamjami GC via Jhowdia Hat Road at Ch:1400m. | KDRIDP/KUSH/B-06/2018-19 | 0 | 45 | 0 | 454.02 | 2018-11-12 | [7 empty] | 0 | #DIV/0! | 90 m Bridge required
Kumarkhali
6 | 250712005 Construction of 25.00m PSC Girder Bridge on Kumarkhali GC- Gopogram GC Road at Ch:1100m. | KDRIDP/KUSH/B-03/2017-18 | 0 | 25 | 0 | 204.687 | 2018-11-27 | [7 empty] | 0 | #DIV/0!
7 | 250712004 Construction of 96.00m Long PSC Bridge on Lahini Bottola R&H - Kaser kole Gc Via Panti Bashgram GC at Ch:1200m | KDRIDP/KUSH/B-07/2018-19 | 0 | 96 | 0 | 675.686 | 2019-04-15 | Rafia Cons.Ltd. | 2019-06-03 | 669.376 | 0% | 2020-06-04 |  |  | 0 | 0%
Total |  |  | 0 | 178 | 0 | 1454.11 |  |  |  | 782.486 | 0% |  | 0 | 0 | 0 | 0%
Construction of Bridge on Union Road/Village Road (5.50m width)
Kushtia Sadar
1 | 250795321-Const. of RCC Bridge on Machpara Primary School-Shidurghat road. | [13 empty] | 0 | #DIV/0!
Kumarkhali
3 | 250714067-Construction of 66.00m RCC Girder Bridge on Purbasha Club-Beltola Bazar Road (Dakua River ) at Ch:1125m | KDRIDP/KUSH/B-02/2017-18 | 0 | 66 | 0 | 393.2 |  |  |  | 407.345 | 0% |  |  |  | 0 | 0%
4 | 250714104 Construction of 60.00m Long RCC Girder Bridge on Kumarkhali Bashgram bazar-Kushlibasha hat Road at Ch:1000m. | KDRIDP/KUSH/B-04/2018-19 | 0 | 60 | 0 | 354.02 | [8 empty] | 0 | #DIV/0!
Bheramara
5 | 250154052-Construction of 22.00m Long RCC Girder Bridge on Ghikri parankhali-Golapnagar Bazar Road at Ch: 985m. | KDRIDP/KUSH/B-05/2018-19 | 0 | 22 | 0 | 208.09 | [8 empty] | 0 | #DIV/0!
Total |  |  | 0 | 148 | 0 | 955.31 |  |  |  | 407.345 | 0% |  | 0 | 0 | 0 | 0%
Maintenance
Mirpur
1 | 250942004- Mirpur GC-Bheramara Gc road. | [13 empty] | 0 | #DIV/0!
2 | 250943008- Periodic Maintennance of Nowdangodindopur R&H -Bahalbaria UP via Talbaria UP Road .(Ch:1168m-3000m) | KDRIDP/KUSH/M-14/2017-18 | 1.832 | 0 | 0 | 33.706 | 2018-02-26 | ESHANUL HAQUE | 2018-04-26 | 36.74 | 100% | 2018-09-28 | 36.575 | 36.575 | 0 | 99.55% | Final
3 | 250943011- Periodic Maintennance of Mirpur BDR camp-Kuchuadha bazer Road. (Ch:0.00m-3375m) | KDRIDP/KUSH/M-15/2017-18 | 4.348 | 0 | 0 | 67.49 | 2018-02-01 | Md. Esanul haque | 2018-03-20 | 70.53 | 100% | 2018-09-21 | 70.53 | 70.53 | 0 | 100% | Final
4 | 250943012-Periodic Maintennance of Nowpara bazer- Mirzanagor bazer Road .(Ch:1100m-3782m). | KDRIDP/KUSH/M-16/2017-18 | 2.682 | 0 | 0 | 47.18 | 2018-02-26 | ESHANUL HAQUE | 2018-04-26 | 51.43 | 100% | 2018-09-24 |  | 50.733 | -50.733 | 98.64% | Work completed
5 | 250943013-Periodic Maintennance of Ambaria-Sree Rampur bazer UP- Road .(Ch:4400m-5800m) | KDRIDP/KUSH/M-17/2017-18 | 1.4 | 0 | 0 | 42.808 | 2018-02-08 | M/S SR CONSTRUCTION | 2018-03-28 | 43.665 | 100% | 2018-09-29 |  | 8 | -8 | 18.32% | BC preparetion on going, .(28 days Notice on 14.08.18, Memo :2501)
6 | 250943014-Periodic Maintennance of Sorupdah(PoradahGC)-Mirpur UP H/Q via Chatian UP - Road .(Ch:0.00m-3800m &5050m-5900m). | KDRIDP/KUSH/M-18/2017-18 | 4.65 | 0 | 0 | 82.03 | 2018-02-01 | MD.ESANUL HOQUE | 2018-03-20 | 89.496 | 100% | 2018-09-21 |  | 88.34 | -88.34 | 98.71% | Work completed
7 | 250944004- Khadimpur Bazar-Nowda R&H road. | [13 empty] | 0 | #DIV/0!
8 | 250944014- Hazrahati Bazar-Jogoti Main Cannel road. | [13 empty] | 0 | #DIV/0!
9 | 250944038-Bamungari-Ambaria Rd. | [13 empty] | 0 | #DIV/0!
10 | 250944050- Mirpur-Bahalbaria Bazar road. | [13 empty] | 0 | #DIV/0!
11 | 250944060-Poradha-Katdhachar RHD Rd. | [13 empty] | 0 | #DIV/0!
12 | 25094200- Mirpur Upazila H/Q- Poradah Gc road. | [13 empty] | 0 | #DIV/0!
Kumarkhali
13 | 250713006-Periodic Maintennance of Bagulat UP-Enayatpur bazer via Chowrongi bazer Road .(Ch:8000m-10830m) | KDRIDP/KUSH/M-19/2017-18 | 2.83 | 0 | 0 | 87.198 | 2018-02-01 | MD.ATAUR RAHAMAN ATA | 2018-03-28 | 86.55 | 100% | 2018-07-31 |  | 20.508 | -20.508 | 23.69% | completed
14 | 250713014-Periodic Maintenance of kaya Gc-Kalua Bazar via kaya up office road at ch (00-2890)m | KDRIDP/KUSH/M-24/2018-19 | 2.89 | 0 | 0 | 80.65 | 2018-12-10 | R.R Trading (Khan Mohammod Wahid Rony) | 2019-02-08 | 76.618 | 40% | 2019-07-13 |  | 15 | -15 | 19.58% | WBM completed & BC under process
15 | 250713015-Shilaidah UP- Kushtia Upazila H/Q Rd via Kalua Rd. | [13 empty] | 0 | #DIV/0!
16 | 250714014-Periodic Maintennance of Sultanpur- Fultola Picca Road .(Ch:1000m-3010m) | KDRIDP/KUSH/M-20/2017-18 | 2.01 | 0 | 0 | 66.71 | 2017-12-28 | M/S Don Enterprise | 2018-02-08 | 64.91 | 100% | 2018-08-12 |  | 44.5 | -44.5 | 68.56% | WBM completed
17 | 250714019-G/ bari Kanchonpur- Mirpur-Boalia Rd. | [13 empty] | 0 | #DIV/0!
18 | 250714022-Periodic Maintenance of Ramchandrapur- Gobra- Islami University road at ch:0.00m-2210m. | KDRIDP/KUSH/M-21/2018-19 | 2.21 | 0 | 0 | 102 | 2018-10-08 | Md. Ataur Rahman Ata | 2018-11-29 | 96.9 | 100% | 2019-06-02 |  | 92.676 | -92.676 | 95.64% | completed.
19 | 250714031-Diurgapur-Modhupur Bazar via Varora Rd. | [13 empty] | 0 | #DIV/0!
20 | 250714033-Kumlapur- Dudkumar -Khal Bazar Rd. | [13 empty] | 0 | #DIV/0!
21 | 250714067-Purbasha Jobashanga - Beltala bazar Rd. | [13 empty] | 0 | #DIV/0!
22 | 250714083-Boroichara more-Nowdapara via Sheikh para road. | [13 empty] | 0 | #DIV/0!
23 | 250714116-Madhupur Bazar-Chowrangi Bazar Road | [13 empty] | 0 | #DIV/0!
24 | 250715061-Abdul Jabbar More- Dhalnagar road | [13 empty] | 0 | #DIV/0!
25 | 250715056-Jungali Jamee mosque to Ayuddin Shop Via Dahnagor Gk khal | [13 empty] | 0 | #DIV/0!
Daulatpur
26 | 250394012-Periodic Maintennance of Sadipur -Mandalpara Road .(Ch:0.00m-1050m) | KDRIDP/KUSH/M-10/2017-18 | 1.05 | 0 | 0 | 22.247 | 2018-02-01 | M/S Monjil traders | 2018-03-28 | 23.2 | 0% | 2018-07-31 |  |  | 0 | 0% | Canceled & Now Pakage Name will change for Retender
27 | 250394020-Periodic Maintennance of Sherpur Pearpur- UP Road at (Ch:0.00m-4133m) | KDRIDP/KUSH/M-23/2018-19 | 4.133 | 0 | 0 | 98.99 | 2018-11-29 | Md. Alomgir Kabir Titu | 2019-01-13 | 94.04 | 20% | 2019-07-17 |  |  | 0 | 0% | Earth work. (to send 28 days letter ).
28 | 250394043-Periodic Maintennance of Mashaura-Bagoan Road. (Ch:0.00m-590m and 928m-2375m) | KDRIDP/KUSH/M-13/2017-18 | 2.037 | 0 | 0 | 47.985 | 2018-02-01 | mir mamun hossain | 2018-03-20 | 51.258 | 100% | 2019-02-08 | 51.255 | 51.255 | 0 | 99.99% | Final
29 | 250394055-Periodic Maintennance of Bagoan -Madapur Road. (Ch:0.00m-1987m) | KDRIDP/KUSH/M-12/2017-18 | 1.987 | 0 | 0 | 38.335 | 2018-02-01 | mir mamun hossain | 2018-03-20 | 42.15 | 100% | 2019-02-08 | 42.122 | 42.122 | 0 | 99.93% | Final
30 | 250394067-Periodic Maintennance of Garura College Mor- UP complex -Adabaria Road. (Ch:0.00m-2730m) | KDRIDP/KUSH/M-22/2017-18 | 2.73 | 0 | 0 | 57.942 | 2018-02-01 | M/S. Tamanna Trade International (Md. Saidur Rahman) | 2019-01-17 | 55.04 | 40% | 2019-07-21 |  |  | 0 | 0% | Hard bed preraration. (to send 28 days letter ).
31 | 250395005-Balirdiar-Koldiar Road. | [13 empty] | 0 | #DIV/0!
32 | 250392010-Mothurapur GC-Hoshenabad Vocational-Farakpur-Chakdiar-Toltolipara-Gachirdiar-Juniadaha GC Road . | [13 empty] | 0 | #DIV/0!
33 | 250392010-Mothurapur GC-Hoshenabad Vocational-Farakpur-Chakdiar-Toltolipara-Gachirdiar-Juniadaha GC Road . | [13 empty] | 0 | #DIV/0!
Bheramara
34 | 250152007-Pakshi R&H Fary Ghat via moulahabashpur Golapnagar bazar road-R&H(Dakerbari) Dhorompur rd. | [13 empty] | 0 | #DIV/0!
35 | 250154001-Periodic Maintennance of Dharampur Mangro Garden-Maulahabashpur R.R Bridge Road .(Ch:0.00m-1000m). | KDRIDP/KUSH/M-04/2017-18 | 1 | 0 | 0 | 17.63 | 2017-12-28 | M/S Meherul Alam | 2018-02-26 | 17.01 | 100% | 2018-07-01 | 16.98 | 16.98 | 0 | 99.82% | Final
36 | 250154028-Periodic Maintennance of R&H 12mile Cold Store -Baradi Hat Road .(Ch:1478-2765m) | KDRIDP/KUSH/M-01/2017-18 | 1.287 | 0 | 0 | 28.33 | 2017-12-28 | M/S Meherul Alam | 2018-02-26 | 26.84 | 100% | 2018-07-01 | 26.8 | 26.8 | 0 | 99.85% | Final
37 | 250154053-Jagssar Hat-Nalua Hat Rd | [13 empty] | 0 | #DIV/0!
38 | 250154090-Periodic Maintennance of Junidah Haripur -Gachia Doulatpur Batttola Via Bektepur Road .(Ch:0.00m-702m) | KDRIDP/KUSH/M-06/2017-18 | 0.702 | 0 | 0 | 13.26 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 13.225 | 100% | 2018-07-31 | 13.222 | 13.222 | 0 | 99.98% | Final
39 | 250154060-Khamirdiar-Ramkrishnapur via Mokarimpur Up road. | [13 empty] | 0 | #DIV/0!
40 | 250154004- Periodic Maintennance of Jagassar-Jagassar Mosque Road .(Ch:0.00m-528m) | KDRIDP/KUSH/M-05/2017-18 | 0.528 | 0 | 0 | 10.096 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 10.057 | 100% | 2018-07-31 | 10.056 | 10.056 | 0 | 99.99% | Final
41 | 250154024-Saruper ghope Pry. School- Nobogonga Graveyard rd. | [13 empty] | 0 | #DIV/0!
42 | 250154037- Kazihata RHD -Satbaria (Dharompur Millpara) Rd. | [13 empty] | 0 | #DIV/0!
43 | Bir Muktizodda Morhoom Osman Ali Srite (Chandipr (H/O Lozen more - 12 mile R&H)Road.250154072 | [13 empty] | 0 | #DIV/0!
44 | Kazihata R&H to Mohishadora R&H via Amdha Road.250154093 | [13 empty] | 0 | #DIV/0!
45 | 250154012-Periodic Maintennance of Golopnagor Bazer -WAPDA Embankment Road .(Ch:0.00m-1665m) | KDRIDP/KUSH/M-03/2017-18 | 1.665 | 0 | 0 | 20.36 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 20.27 | 100% | 2018-08-30 | 20.22 | 20.22 | 0 | 99.75% | Final
46 | Bahadurpur Hat-WAPDA Embankment.250154013 | [13 empty] | 0 | #DIV/0!
47 | Kuchiamora Bazer-Malipara Embankment.250154016 | [13 empty] | 0 | #DIV/0!
48 | 250154034-Periodic Maintennance of Fayzullahpur (UZR-Junidah) via Horipur Road .(Ch:0.00m-773m) | KDRIDP/KUSH/M-02/2017-18 | 0.773 | 0 | 0 | 14.75 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 14.71 | 100% | 2018-07-31 | 14.63 | 14.63 | 0 | 99.46% | Final
Khoksha
49 | 250635019-Periodic Maintennance of Komlapur- Narayanpur Road. (Ch:0.00m-710m) | KDRIDP/KUSH/M-08/2017-18 | 0.71 | 0 | 0 | 12.69 | 2018-02-26 | M/s Hashib Enterprise Rajbari | 2018-04-17 | 13.9 | 0% | 2018-08-20 |  |  | 0 | 0% | work Completed under municipality
50 | 250635023-Periodic Maintennance of East Bonogram-Bohorampur Road . (Ch:0.00m-1540m) | KDRIDP/KUSH/M-09/2017-18 | 1.54 | 0 | 0 | 15.69 | 2018-02-26 | M/s Hashib Enterprise Rajbari | 2018-04-17 | 17.185 | 100% | 2018-08-20 | 17.15 | 17.15 | 0 | 99.8% | Final
51 | 250635028-Khoksa Dangbangla-Patildangi road | [13 empty] | 0 | #DIV/0!
Kushtia Sadar
52 | 250795008-Jogia R&H-Mubarok Bandth Road. | [13 empty] | 0 | #DIV/0!
53 | 250794052-Periodic Maintennance of Ujangram belly Bridge to Alinogor Sidurghat Jhowdia Road. (Ch: 6850-7850 m) | KDRIDP/KUSH/M-07/2017-18 | 1 | 0 | 0 | 14.39 | 2018-02-01 | ATAUR RAHAMAN ATA | 2018-04-26 | 15.75 | 100% | 2018-08-29 | 15.75 | 15.75 | 0 | 100% | Final
54 | 250794001-Shaldha-H.Horipur bazar Road. | [13 empty] | 0 | #DIV/0!
55 | 250794063-Kanchonpur-Kamlapur Rd | [13 empty] | 0 | #DIV/0!
56 | 250794002-Hatos Horripur-Saldah Rd | [13 empty] | 0 | #DIV/0!
57 | 250794036-Police line R&H-Paschim Majumpur(Hazi A.Rahaman Road) | [13 empty] | 0 | #DIV/0!
58 | 250794065-Abdulpur bazar-Jhoudia Road | [13 empty] | 0 | #DIV/0!
59 | 250795030-Baliapara-Baraiapara Bridge Rd | [13 empty] | 0 | #DIV/0!
Total |  |  | 45.994 | 0 | 0 | 1022.467 |  |  |  | 1031.474 | 82.61% |  | 335.29 | 655.047 | -319.757 | 63.51%
GC-Hat
Kushtia Sadar
1 | Contuction of Bhadalia Growth Center | KDRIDP/KUSH/GC-17/2017-18 | 0 | 0 | 1 | 20.04 | 2018-02-08 | M/S JAKAULLAH & BROTHERS | 2018-04-10 | 18.038 | 100% | 2018-08-13 |  | 15.8 | -15.8 | 87.59% | Work completed
Kumarkhali
2 | Constuction Of Enayetpur Growth Center | KDRIDP/KUSH/GC-18/ 17-18 | 0 | 0 | 1 | 18.85 | 2018-02-08 | M/S JAKAULLAH & BROTHERS | 2018-04-10 | 16.96 | 100% | 2018-08-13 |  | 15.49 | -15.49 | 91.33% | Completed
3 | Constuction Of Chowrangi Bazar Growth Center | KDRIDP/KUSH/GC-19/ 17-18 | 0 | 0 | 1 | 18.85 | 2018-02-08 | M/S JAKAULLAH & BROTHERS | 2018-04-10 | 16.96 | 100% | 2018-08-13 |  | 12.64 | -12.64 | 74.53% | shed completed
Total |  |  | 0 | 0 | 3 | 57.74 |  |  |  | 51.958 | 100% |  | 0 | 43.93 | -43.93
Tree Plantation
Kushtia Sadar
1 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Daulatpur
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Bheramara
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Mirpur
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Kumarkhali
5 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Khoksha
6 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 173.827 | 326 | 3 | 11338.189 |  |  |  | 9305.016 | 57.25% |  | 2255.996 | 4643.926 | -2387.93 | 49.91%
|  |  | 173.827 | 326 | 3 | 11338.189 |  |  |  | 9305.016 | 39.26% |  | 2255.996 | 4643.926 | -2387.93 | 49.91%

## Khoksha
Khoksha
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 250632007-Improvement of Khoksha GC-Kushtia Rajbari RHD Vai Bosoa road.(Ch:4900-5950) Salvage Coast(Tk 571774.00). | KDRIDP/KUSH/W-33/2017-18 | 1.05 | 0 | 0 | 71.056 | 2017-10-02 | M/s Rupali Trders | 2017-11-27 | 69.46 | 100% | 2018-05-24 | 68.707 | 62.99 | 5.717 | 90.69% | Work completed
2 | 250632004-Khoksha-Ektarpur GC-Bonogram-Katlagaria. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Union Road by BC
3 | 250633005-Khoksa (Moragacha) UP-Somospur via Rajinathpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 250633013- Improvement of Jpntihazra UP-Amlabaria via Dangipara road by BC. at Ch:3680-4490m .(Salvage Cost: 5,17,004) | KDRIDP/KUSH/W-90/2018-19 | 0.81 | 0 | 0 | 57.87 | 0 | 0 | 0 | 54.98 | 0% | 0 | 0 | 0 | 0 | 0% | 0
5 | 250633014-Shomospur GC-Gopogram GC via Nichantabaria, Sathpakhia bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 250634001-Khoksa (Moragacha) UP-Dudrajpur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 250634011-Improvement of Gonesshpur Bazar-Panti GC road Khoksha protion . (Ch:1060-1700m) Salvage Cost (Tk :1089453.00) | KDRIDP/KUSH/W-37/2017-18 | 0.64 | 0 | 0 | 41.175 | 2017-09-26 | M/s Rowshon Traders | 2017-11-22 | 43.13 | 100% | 2018-05-03 | 43.1 | 43.1 | 0 | 99.93% | Final
8 | 250634012-Uazila HQ-Mirzapur RHD Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 250634014- Improvement ofRaipur Charabotgac-Hizlabot bazar Sreepur Primary School via Devinagar Primary School road. (Ch:00-1390m) | KDRIDP/KUSH/W-81/2017-18 | 1.39 | 0 | 0 | 85.329 | 2018-05-31 | Md. Rashedul Harun Sajol | 2018-07-24 | 89.595 | 60% | 2019-02-25 | 0 | 33.1 | -33.1 | 36.94% | WBM Completed
| 250634035- Improvement of Osmanpur Kheyaghgat-Raypur bottalla mor via Raypur graveyard road (ch:1000m-2275m). |  | 1.275 | 0 | 0 | 80.999 |  |  |  | 85.049 |  |  | 0 | 31.426 | -31.426 | 36.95%
10 | 250634015-Ramanathpur GK canal-Goneshpur Bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 250634022-Shimulia RHD-Tatipara Care Bridge | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 250634023-Biljani Eidgah-Biljani Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 250635014- Improvement of Raypur chara Bot gach-Osmanpur GPS GK Canel road ch-1390-1750m. | KDRIDP/KUSH/W-83/2018-19 | 0.36 | 0 | 0 | 26.04 | 2018-10-25 | Md. Mujibul Haque Khan Chowdhuri | 2018-12-10 | 24.738 | 60% | 2019-06-13 | 0 | 0 | 0 | 0% | WBM Completed
| 250635037-Improvement of ajol care bridge - mohisgari beel road at 977-1550m |  | 0.573 | 0 | 0 | 40.695 |  |  |  | 38.66 |  |  | 0 | 0 | 0 | 0%
| 250634019 Improvement of Osmanpur up office bari badh via raipur mosque road by bc at ch 00.0m-570.0m |  | 0.57 | 0 | 0 | 40.45 |  |  |  | 38.428 |  |  | 0 | 0 | 0 | 0%
14 | 250635019-Improvement of Komlapur-Narayanpur road.(Ch:710-1600m) Salvage Coast(Tk 571774.00) | KDRIDP/KUSH/W-35/2017-18 | 0.89 | 0 | 0 | 49.127 | 2017-09-26 | M/s Hashib Enterprise Rajbari | 2017-11-05 | 51.44 | 100% | 2018-05-09 | 0 | 50.4 | -50.4 | 97.98% | Work Completed
15 | 250635039-Improvement of Iswardi-Beharia Shiekpara road.(Ch:1860-2750m) Salvage Coast(Tk 571774.00) | KDRIDP/KUSH/W-34/2017-18 | 0.89 | 0 | 0 | 49.66 | 2017-09-26 | M/s Hashib Enterprise Rajbari | 2017-11-05 | 52 | 100% | 2018-05-09 | 0 | 52 | -52 | 100% | Work Completed
16 | 250634007-Improvement of Mashilia Bazar to Boraichar road. (Ch:00-1160m) Salvage Coast(Tk :14105060.00). | KDRIDP/KUSH/W-36/2017-18 | 1.16 | 0 | 0 | 75.019 | 2017-09-26 | Md Rohim Khan | 2017-11-05 | 78.55 | 100% | 2018-04-26 | 78.48 | 78.48 | 0 | 99.91% | Final
17 | 250635059-Fulbaria RHD - Pangsha Boundary via Laxandia Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 250635076-Sreepur H/O Liakot - Military Botgas Via Sreepur RNG Primary School. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
19 | 250635019-Periodic Maintennance of Komlapur- Narayanpur Road. (Ch:0.00m-710m) | KDRIDP/KUSH/M-08/2017-18 | 0.71 | 0 | 0 | 12.69 | 2018-02-26 | M/s Hashib Enterprise Rajbari | 2018-04-17 | 13.9 | 0% | 2018-08-20 | 0 | 0 | 0 | 0% | work Completed under municipality
20 | 250635023-Periodic Maintennance of East Bonogram-Bohorampur Road . (Ch:0.00m-1540m) | KDRIDP/KUSH/M-09/2017-18 | 1.54 | 0 | 0 | 15.69 | 2018-02-26 | M/s Hashib Enterprise Rajbari | 2018-04-17 | 17.185 | 100% | 2018-08-20 | 17.15 | 17.15 | 0 | 99.8% | Final
21 | 250635028-Khoksa Dangbangla-Patildangi road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
22 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 11.858 | 0 | 0 | 645.8 |  |  |  | 657.115 | 32.73% |  | 207.437 | 368.646 | -161.209 | #DIV/0!

## Kumarkhali
Kumarkhali
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 250713001-Improvement of Bagulat UP Offich-Bharora Bazar Road.(Ch:5393-6392m) | KDRIDP/KUSH/W-32/2017-18 | 0.999 | 0 | 0 | 64.349 | 2017-09-12 | M/s Asif Enterprise | 2017-10-18 | 57.91 | 100% | 2018-07-05 | 0 | 47.384 | -47.384 | 81.82% | work completed
2 | 250713008-Improvement of Panti UP Offich-Kushlibasha Hat Via Ramdia, Monoharpur Road.(Ch:5190-6120m) | KDRIDP/KUSH/W-31/2017-18 | 0.93 | 0 | 0 | 59.18 | 2017-09-12 | M/s Rahman Enterprise | 2017-10-09 | 61.99 | 100% | 2018-04-12 | 0 | 0 | 0 | 0% | palasiding completed
3 | 250713009-Improvement of chandpur up office-kushlibasha hat via mohan nagar road.(Ch: 2600-3940m) | KDRIDP/KUSH/W-80/2017-18 | 1.34 | 0 | 0 | 77.29 | 2018-04-10 | Pampus Agro & Logistics Ltd | 2018-05-29 | 77.29 | 0% | 2019-02-27 | 0 | 0 | 0 | 0% | Not yet started & Cancellation letter sent.
4 | 250713010- Improvement of Zaduboyra UP Office - Lalon bazar via Zaduboyra hat road by BC. at Ch:1380-2510m . | KDRIDP/KUSH/W-91/2018-19 | 1.13 | 0 | 0 | 80.956 | 0 | 0 | 0 | 76.908 | 0% | 0 | 0 | 0 | 0 | 0% | 0
5 | 250713013-Nandolalpur UP-Charikol Station bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 250714001- Improvement of Zaduboyra hat-Sandiara via Bhalbaria road by BC. At Ch:(00-700m)+(1750-2720m). (Salvage Cost: 1,30,792) | KDRIDP/KUSH/W-92/2018-19 | 1.67 | 0 | 0 | 136.925 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 250714005-Improvement of Sandiara Canal-Enayetpur Via Krisnapur Hat Rd. (Ch:00-700m & 2840-3930m) | KDRIDP/KUSH/W-30/2017-18 | 1.79 | 0 | 0 | 103.93 | 2017-09-12 | M/s Asif Enterprise | 2017-10-18 | 93.54 | 100% | 2018-07-05 | 0 | 76.625 | -76.625 | 81.92% | work completed
8 | 250714016-Kanchanpur- Niamotbari School Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 250715006-Improvement of Valuka Canal- Nagarkoya Road.(Ch:00-1070 m) | KDRIDP/KUSH/W-38/2017-18 | 1.07 | 0 | 0 | 64.51 | 2017-09-26 | M/s Gorai pipe Industry | 2017-10-31 | 63.87 | 100% | 2018-03-24 | 63.61 | 63.61 | 0 | 99.59% | Final
10 | 250714026-Improvement of Baraichara-Ramdia Road. Ch.1200-1920m. | KDRIDP/Kush/W-01/2016-17 | 0.72 | 0 | 0 | 41.36 | 2017-05-25 | Md Shahidur Rahman Mintu Kalisonkorpur Kushtia | 2017-06-22 | 38.88 | 100% | 2018-03-28 | 38.258 | 38.26 | -0.002 | 98.41% | Final
11 | 250714028-Improvement of Baraichara-Naturia bazar Road.(Ch:00-1000 m) Salvage Coast Tk 66824.00 | KDRIDP/KUSH/W-39/2017-18 | 1 | 0 | 0 | 55.92 | 2017-09-26 | Md Liakot Ali | 2017-11-20 | 58.68 | 100% | 2018-10-30 | 0 | 56 | -56 | 95.43% | Work Completed
12 | 250714030-Improvement of Chapra-Madhupur road at ch00-1970m & 2035-3300m. | KDRIDP/KUSH/W-63/2017-18 | 3.235 | 0 | 0 | 203.07 | 2018-02-08 | M/S Sabit Enterprise | 2018-07-24 | 217.6 | 15% | 2019-01-25 | 0 | 0 | 0 | 0% | Sand filling on going.
13 | 250714035- Improvement of Kamlapur-Dhekipara road by BC. At Ch:(1000-2085m). (Salvage Cost: 53,657) | KDRIDP/KUSH/W-93/2018-19 | 1.085 | 0 | 0 | 87.41 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 250714086- Improvement of Khordo Valuka-Nagarokoya graveyard road by BC. At Ch:(00-1060m). (Salvage Cost: 1,44,806) |  | 1.06 | 0 | 0 | 86.62 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
14 | 250714041- Improvement of Durgapur pacca road to puraton Charikpl (Durgapur Khokn house-Prodon Charikol) road Ch:(1200-1585m). (Salvage Cost: 8,40,596) | KDRIDP/KUSH/W-94/2018-19 | 0.385 | 0 | 0 | 31.017 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 250714108- Improvement of Jotmora- Maudpur bazar road by BC. At Ch:(900-2278m) . (Salvage Cost: 1,30,792) |  | 1.302 | 0 | 0 | 104.268 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
15 | 250714048-Improvement of Tarapur to Maliat via Baniakandi Rd ch: 1450-2590m. | KDRIDP/KUSH/W-22/2016-17 | 1.14 | 0 | 0 | 62.83 | 2017-09-25 | Md Abul Kashem Sorower Pabari | 2017-11-05 | 65.88 | 60% | 2018-05-09 | 0 | 20 | -20 | 30.36% | WBM completed & BC under process.
16 | 250714071-Sadipur-Ghoespur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 250714084-Improvement of Khal bazar-Shalghor Madhua Rd Ch.00-1000m | KDRIDP/Kush/W-03/2016-17 | 1 | 0 | 0 | 54.82 | 2017-05-25 | Md Liakot Ali Kumarkhali Kushtia | 2017-07-04 | 52.08 | 100% | 2018-02-19 | 0 | 45.952 | -45.952 | 88.23% | BC preparetion
18 | 250714103-Improvement of Gobrab GPS -Khacakkhol Paka road ch00-1000m. | KDRIDP/KUSH/W-23/2017-18 | 1 | 0 | 0 | 60.5 | 2017-09-25 | Md Sumsu dhuda mollik | 2017-11-05 | 63.15 | 60% | 2018-05-17 | 0 | 15 | -15 | 23.75% | WBM Completed, BC under process. (28 days notice on 14.08.18 , memo: 2503
19 | 250714104-Bashgram bazar-Kushlibasha hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 250714105-Improvement of Modupur Bazar-Nathuria Bazar road.(Ch:1225-1910m) | KDRIDP/KUSH/W-40/2017-18 | 0.685 | 0 | 0 | 38.68 | 2017-09-26 | M/s Millenium enterprise | 2017-11-12 | 40.54 | 100% | 2018-11-06 | 0 | 31.88 | -31.88 | 78.64% | work Completed
22 | 250714115-Khairchara RHD-Agrikundu via Pathorbaria Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | 250714175-Improvement of Birikya UZR-Sazipara Bridge Vai Beltala road. (Ch:00-290 m) &1245-3245m Salvage Coast (Tk 27821.00) | KDRIDP/KUSH/W-41/2017-18 | 2.29 | 0 | 0 | 139.97 | 2017-09-26 | Md Ataur Rahman Ata | 2017-11-05 | 139.67 | 100% | 2018-05-09 | 139.66 | 139.66 | 0 | 99.99% | Final
24 | 250714177-Koburhat Jr. High School- Biswasbari Graveyard Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 250715100-Improvement of Chandpur bazar-Madhupur bazar road (ch -800m-2150m ) | KDRIDP/KUSH/W-79/2017-18 | 1.35 | 0 | 0 | 80 | 2018-04-26 | M/S Millenium Enterprise | 2018-06-14 | 82.406 | 10% | 2019-02-27 | 0 | 0 | 0 | 0% | lay out given & materials mobilization on going.
26 | 250715063-Improvement of Dhalnagar Mollapara-Dhalnagar Mirpara Graveyard via Mr.Somen house Road. Ch.00-1000m Salvage Cost Tk 219180.00 | KDRIDP/Kush/W-02/2016-17 | 1 | 0 | 0 | 54.88 | 2017-05-25 | Md Liakot Ali Kumarkhali Kushtia | 2017-07-04 | 52.13 | 100% | 2018-05-18 | 0 | 43.64 | -43.64 | 83.71% | Work completed
27 | 250715132- Nandolalpur UP Office to H/O Engr. Kamal Uddin Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 250715137- Improvement of Ethmampur Shah jalal mor-Ethmampur graveyard Road Ch. 00-1000m. | KDRIDP/Kush/W-04/2016-17 | 1 | 0 | 0 | 60.83 | 2017-05-25 | M/s Uttom Kumar Kundu Pangsha Rajbari | 2017-07-05 | 57.69 | 100% | 2018-06-11 | 48.9 | 48.9 | 0 | 84.76% | Work completed
29 | 250715063-250715063 Dhalnagar mollhapara- Dhalnagar Mirpara Graveyard via Mir Borhan Ali house road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
30 | 250714016-Gottia-Baradi-Fultala Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
31 | 250714069- Improvement of Kamarkandi- Kashaba road at ch-00-1300m | KDRIDP/KUSH/W-84/2018-19 | 1.3 | 0 | 0 | 56.61 | 2019-01-16 | Md. Jinnath Ali Jinnah (pabna) | 2019-03-06 | 56.069 | 66% | 2019-09-07 | 0 | 12.685 | -12.685 | 22.62% | 0
| 250714070-Improvement of Gospur -gobindopur via sadipur road ch: 00-2100m |  | 2.1 | 0 | 0 | 78.76 |  |  |  | 78.008 |  |  | 0 | 17.645 | -17.645 | 22.62%
| 250714071- Improvement of Gospur- Sadipur road ch-3300-5202m |  | 1.902 | 0 | 0 | 87.81 |  |  |  | 86.97 |  |  | 0 | 19.67 | -19.67 | 22.62%
Construction of Bridge on Upazila Road (7.30m width)
32 | 250712005 Construction of 25.00m PSC Girder Bridge on Kumarkhali GC- Gopogram GC Road at Ch:1100m. | KDRIDP/KUSH/B-03/2017-18 | 0 | 25 | 0 | 204.687 | 2018-11-27 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
33 | 250712004 Construction of 96.00m Long PSC Bridge on Lahini Bottola R&H - Kaser kole Gc Via Panti Bashgram GC at Ch:1200m | KDRIDP/KUSH/B-07/2018-19 | 0 | 96 | 0 | 675.686 | 2019-04-15 | Rafia Cons.Ltd. | 2019-06-03 | 669.376 | 0% | 2020-06-04 | 0 | 0 | 0 | 0% | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
34 | 250714067-Construction of 66.00m RCC Girder Bridge on Purbasha Club-Beltola Bazar Road (Dakua River ) at Ch:1125m | KDRIDP/KUSH/B-02/2017-18 | 0 | 66 | 0 | 393.2 | 0 | 0 | 0 | 407.345 | 0% | 0 | 0 | 0 | 0 | 0% | 0
35 | 250714104 Construction of 60.00m Long RCC Girder Bridge on Kumarkhali Bashgram bazar-Kushlibasha hat Road at Ch:1000m. | KDRIDP/KUSH/B-04/2018-19 | 0 | 60 | 0 | 354.02 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
36 | 250713006-Periodic Maintennance of Bagulat UP-Enayatpur bazer via Chowrongi bazer Road .(Ch:8000m-10830m) | KDRIDP/KUSH/M-19/2017-18 | 2.83 | 0 | 0 | 87.198 | 2018-02-01 | MD.ATAUR RAHAMAN ATA | 2018-03-28 | 86.55 | 100% | 2018-07-31 | 0 | 20.508 | -20.508 | 23.69% | completed
37 | 250713014-Periodic Maintenance of kaya Gc-Kalua Bazar via kaya up office road at ch (00-2890)m | KDRIDP/KUSH/M-24/2018-19 | 2.89 | 0 | 0 | 80.65 | 2018-12-10 | R.R Trading (Khan Mohammod Wahid Rony) | 2019-02-08 | 76.618 | 40% | 2019-07-13 | 0 | 15 | -15 | 19.58% | WBM completed & BC under process
38 | 250713015-Shilaidah UP- Kushtia Upazila H/Q Rd via Kalua Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 250714014-Periodic Maintennance of Sultanpur- Fultola Picca Road .(Ch:1000m-3010m) | KDRIDP/KUSH/M-20/2017-18 | 2.01 | 0 | 0 | 66.71 | 2017-12-28 | M/S Don Enterprise | 2018-02-08 | 64.91 | 100% | 2018-08-12 | 0 | 44.5 | -44.5 | 68.56% | WBM completed
40 | 250714019-G/ bari Kanchonpur- Mirpur-Boalia Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
41 | 250714022-Periodic Maintenance of Ramchandrapur- Gobra- Islami University road at ch:0.00m-2210m. | KDRIDP/KUSH/M-21/2018-19 | 2.21 | 0 | 0 | 102 | 2018-10-08 | Md. Ataur Rahman Ata | 2018-11-29 | 96.9 | 100% | 2019-06-02 | 0 | 92.676 | -92.676 | 95.64% | completed.
42 | 250714031-Diurgapur-Modhupur Bazar via Varora Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 250714033-Kumlapur- Dudkumar -Khal Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 250714067-Purbasha Jobashanga - Beltala bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 250714083-Boroichara more-Nowdapara via Sheikh para road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 250714116-Madhupur Bazar-Chowrangi Bazar Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
47 | 250715061-Abdul Jabbar More- Dhalnagar road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
48 | 250715056-Jungali Jamee mosque to Ayuddin Shop Via Dahnagor Gk khal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
49 | Constuction Of Enayetpur Growth Center | KDRIDP/KUSH/GC-18/ 17-18 | 0 | 0 | 1 | 18.85 | 2018-02-08 | M/S JAKAULLAH & BROTHERS | 2018-04-10 | 16.96 | 100% | 2018-08-13 | 0 | 15.49 | -15.49 | 91.33% | Completed
50 | Constuction Of Chowrangi Bazar Growth Center | KDRIDP/KUSH/GC-19/ 17-18 | 0 | 0 | 1 | 18.85 | 2018-02-08 | M/S JAKAULLAH & BROTHERS | 2018-04-10 | 16.96 | 100% | 2018-08-13 | 0 | 12.64 | -12.64 | 74.53% | shed completed
Tree Plantation
51 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 42.423 | 247 | 2 | 3974.346 |  |  |  | 2956.88 | 37.02% |  | 290.428 | 877.725 | -587.297 | 29.68%

## Kushtia Sadar
Kushtia Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 250792012-Bhadalia GC-Swargopur-Ballabpur R&H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 250792008-Improvement of Bashgrame GC Durbachara Razzaque more-Shibpur-Horinarayanpur Road. Ch:4100-5900m | KDRIDP/KUSH/W-15/2016-17 | 2.35 | 0 | 0 | 107.56 | 2017-07-31 | Md Ataur Rahman | 2017-09-14 | 106.476 | 100% | 2018-08-22 | 106.476 | 106.476 | 0 | 100% | Final
Improvement of Union Road by BC
3 | 250793006-Improvement of Monohordia- Radhanagar-Chhaighoria-Bhabanipur Bazar Road. Ch5900-6000m Salvage cost Tk 49560.00 | KDRIDP/KUSH/W-18/2016-17 | 0.1 | 0 | 0 | 6.27 | 2017-07-31 | M/s Ahasan Habib | 2017-09-13 | 6.146 | 100% | 2018-01-28 | 0 | 5.28 | -5.28 | 85.91% | Final
4 | 250793017-Improvement of Shidurghat and Mazilahat Road. Ch 6500-8087m | KDRIDP/KUSH/W-19/2016-17 | 1.587 | 0 | 0 | 107.35 | 2017-07-31 | M/s Khan construction | 2017-09-14 | 103.96 | 100% | 2018-05-28 | 0 | 96.04 | -96.04 | 92.38% | work Completed
5 | 250793008-Improvement of Alampur UP - Alampur Hat - - Gajnabipur- Ujangram GC Road. (Ch.3250m-5415m). | KDRIDP/KUSH/W-57/2017-18 | 2.165 | 0 | 0 | 120.29 | 2017-12-24 | Md. Alamgir Zahan | 2018-02-12 | 119.205 | 60% | 2018-08-16 | 0 | 54.42 | -54.42 | 45.65% | WBM completed (28 days letter given on 16.04.18)
Improvement of Village Road by BC
6 | 250794011-Improvement of Nowpara - sargapur Road( ch:0.00m-1000m) | KDRIDP/KUSH/W-72/2017-18 | 1 | 0 | 0 | 63.265 | 2018-04-10 | Pampus Agro & Logistics Ltd | 2018-05-24 | 63.26 | 0% | 2019-02-27 | 0 | 0 | 0 | 0% | Cancelation letter given on 13.02.19 & memo no: 523
7 | 250794024-Improvement of Barkhada-Charulia Anwar Yousuf Road. Ch 6500-8087m | KDRIDP/KUSH/W-17/2016-17 | 1.587 | 0 | 0 | 68.71 | 2017-08-17 | Md Abdul Khaleque | 2017-09-13 | 64.888 | 100% | 2018-06-10 | 0 | 59.156 | -59.156 | 91.17% | work completed
8 | 250794053-Improvement of Astanagar-Jhawdia hat. Road Ch.1250-1405m. | KDRIDP/Kush/W-82/2017-18 | 0.155 | 0 | 0 | 9.41 | 2018-05-31 | Nice Home Constriction & Supplyer | 2018-07-24 | 9.69 | 60% | 2019-01-26 | 0 | 1.9 | -1.9 | 19.61% | sand filling Running
| 250794057-Improvement of Bhadalia- alampur Road( ch:0.00m-1280m). |  | 1.28 | 0 | 0 | 80.645 |  |  |  | 83.06 |  |  | 0 | 16.29 | -16.29 | 19.61%
| 250794043-Improvement of gossami - durgapur bazar- gandi grangpara - natnaghat Road ( ch:500m-1010m) |  | 0.51 | 0 | 0 | 33.687 |  |  |  | 34.698 |  |  | 0 | 6.808 | -6.808 | 19.62%
9 | 250794029-Improvement of sargapur - koboor hat Road (ch:0.00m-2340m). | KDRIDP/KUSH/W-70/2017-18 | 2.34 | 0 | 0 | 160.11 | 2018-04-10 | Pampus Agro & Logistics Ltd | 2018-05-29 | 160.11 | 35% | 2019-02-27 | 0 | 0 | 0 | 0% | ISG CompletedCancelation letter given on 13.02.19 & memo no: 524
10 | 250794031-Patikabari-Alamdanga via shakpara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 250794032-Improvement of Arpara Karimpur Road. (Ch.1240m-3060m) | KDRIDP/KUSH/W-55/2017-18 | 1.82 | 0 | 0 | 121.18 | 2017-12-24 | M/S. Rowshan Traders | 2018-02-08 | 120.75 | 20% | 2018-08-12 | 0 | 0 | 0 | 0% | palisading running 28 days Notice on 29.07.18, Memo :2248
12 | 250794038-Kamlapur Bazar-Ishakhali Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 250794039-Improvement of R&H - Aqlampur- Chapaigachi- Dahokhola Road. (Ch.2290m-4750m) | KDRIDP/KUSH/W-54/2017-18 | 2.46 | 0 | 0 | 140.22 | 2017-12-24 | Md. Alamgir Zahan | 2018-02-12 | 138.89 | 20% | 2018-08-16 | 0 | 0 | 0 | 0% | (28 days letter given on 16.04.18)
14 | 250794040-Harinarayanpur-Purba Abdulpur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 250794062-Improvement of sonaidanga korimpur Road (ch:991m-2325m) | KDRIDP/KUSH/W-69/2017-18 | 1.334 | 0 | 0 | 117.61 | 2018-04-09 | Md. Abu Hena Mostofa Kamal | 2018-12-06 | 122.2 | 100% | 2019-02-27 | 0 | 80 | -80 | 65.47% | work Completed
16 | 250794064-Improvement of Asannagar Kasem mour-sankordia- natnaghat Road (ch:4000m-4897m) | KDRIDP/KUSH/W-68/2017-18 | 0.897 | 0 | 0 | 62.87 | 2018-05-07 | Shohag Enterprise | 2018-07-11 | 65.92 | 100% | 2019-01-12 | 0 | 50 | -50 | 75.85% | work Completed
17 | 250794077-Improvement of Jowdia Barrack more-Shai Mosque Darbar Sharif via Jowdia College ball field Road. Ch.00-358m Salvage Cost Tk 203031.00 | KDRIDP/Kush/W-07/2016-17 | 0.358 | 0 | 0 | 20.1 | 2017-07-18 | M/s Bijoy construction | 2017-08-27 | 18.7 | 100% | 0 | 18.7 | 18.7 | 0 | 100% | Final
18 | 250794079-Improvement of Jugia H&H water board Traning center-Sabgi Farm Road (ch:1918m-2543m). | KDRIDP/KUSH/W-76/2017-18 | 0.625 | 0 | 0 | 47.856 | 2018-04-10 | Md. Aminul Islam | 2018-05-24 | 45.46 | 100% | 2019-02-27 | 0 | 40.723 | -40.723 | 89.58% | 0
19 | 250794026-Improvement of Astanagar Bazruk bakhoy Rd Ch.00-2160m Salvage Cost Tk 127976.00 | KDRIDP/Kush/W-06/2016-17 | 2.16 | 0 | 0 | 118.54 | 2017-05-25 | Md Akkas Ali Kushtia | 2017-06-22 | 117.05 | 100% | 2018-02-20 | 114.116 | 114.116 | 0 | 97.49% | Final
20 | 250795100-Improvement of bhatai senerchatal-farid member s house Road (ch:500m-1145m) | KDRIDP/KUSH/W-74/2017-18 | 0.645 | 0 | 0 | 41.11 | 2018-04-09 | Pampus Agro & logistics Ltd | 2018-06-14 | 43.16 | 0% | 2019-01-27 | 0 | 0 | 0 | 0% | Canceled
21 | 250795284-Improvement of Namdar Ali Biswass -H/O Akbor Ali Biswass H/O Hossain Mpndol Bora Khal Road (ch:0.00m-574m). | KDRIDP/KUSH/W-78/2017-18 | 0.574 | 0 | 0 | 37.778 | 2018-05-07 | M/S Ekramul Haque | 2018-07-01 | 39.629 | 60% | 2019-01-28 | 0 | 21.145 | -21.145 | 53.36% | BC Preparation
22 | 250794076-Improvement of Aisha Abed Berbaradi foundation Upokendro- Pamanagor Road. Ch.00-1700m Salvage Cost Tk 2233626.00 | KDRIDP/KUSH/W-21/2016-17 | 1.7 | 0 | 0 | 95.79 | 2017-07-31 | M/s Rowshon Traders | 2017-09-14 | 100.43 | 100% | 2018-03-29 | 0 | 94.62 | -94.62 | 94.21% | Work Completed
23 | 250795514- Improvement of Kumargara Kalimondir road-Kumargara towards road Ch:00-357m. (Salvage Cost: 1,63,289) | KDRIDP/Kush/W-89/2018-19 | 0.357 | 0 | 0 | 27.14 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 250794081- Improvement of Majhila Eidgah maidan-Majhila bazar-Majhila dakkhinpara Mosque road via Majhila mohila shomiti- Majhila Health center & Girls School road Ch:1336-2500m . |  | 1.164 | 0 | 0 | 84.757 |  |  |  | 0 |  |  | 0 | 0 | 0 | #DIV/0!
24 | 250795181-Improvement of Takimara H/o Shek Joshimuddin - Takimara Graveyard Road. (Ch.0.00m-340m) | KDRIDP/KUSH/W-56/2017-18 | 0.34 | 0 | 0 | 22.67 | 2017-12-24 | Md. Alamgir Zahan | 2018-02-12 | 22.12 | 100% | 2018-06-17 | 22.12 | 22.12 | 0 | 100% | Work completed
25 | 250795305-Improvement of Horora Nocimon More-Community Clinic via Ducter Rahamot Road. Ch00-610m. | KDRIDP/KUSH/W-20/2016-17 | 0.61 | 0 | 0 | 34.97 | 2017-07-31 | M/s SR construction | 2017-09-14 | 34 | 100% | 2018-03-29 | 0 | 33.04 | -33.04 | 97.18% | work Completed
26 | 250795257-Improvement of koburhat H/O Babulm chairman-Shorgopur Road (ch:0.00m-335m). | KDRIDP/KUSH/W-75/2017-18 | 0.335 | 0 | 0 | 21.38 | 2018-05-31 | M/S Chunnu Enterprise (Md Saiful Islam) | 2018-07-17 | 20.31 | 45% | 2018-11-19 | 0 | 0 | 0 | 0% | WBM ON Going
27 | 250795604-Ziarikey Nagar Mohommadpur More-Nagar-Mohommadpur Graveyard road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 250795228-Improvement of Hamida shiddque Collage & School-Bhadhalia para primary School via Boria Graveyard road (ch:1290m-2000m). | KDRIDP/KUSH/W-77/2017-18 | 0.71 | 0 | 0 | 45.759 | 2018-04-09 | Nice Home Constriction & Supplyer | 2018-06-14 | 47.13 | 100% | 2019-02-27 | 0 | 39.69 | -39.69 | 84.21% | work Completed
29 | 250795605-Improvement of Lahini Basgram road-H/O Ator Ali Mia-Peirpur Jame Mosque via H/O Shofiuddin Road. Ch 00-300m Salvage Cost Tk 190155.00 | KDRIDP/KUSH/W-16/2016-17 | 0.3 | 0 | 0 | 19.14 | 2017-07-31 | M/s SR construction | 2017-09-14 | 18.805 | 100% | 2018-09-03 | 18.168 | 18.168 | 0 | 96.61% | Final
30 | 250795117-Improvement of Belgoria medha para pacca road-Colloni para pacca Road. Ch00-2350m Salvage cost Tk 542962.00 | KDRIDP/KUSH/W-14/2016-17 | 2.35 | 0 | 0 | 134.68 | 2017-07-31 | M/s Turnna Trade system | 2017-09-12 | 139.745 | 100% | 2018-03-29 | 139.55 | 139.55 | 0 | 99.86% | Final
31 | 250795008-Jogia R&H-Mubarok Bandth | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
32 | 250794020-Bisnudia-Abdalpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Upazila Road (7.30m width)
33 | 250792008-Const. of RCC Bridge on Bashgrame GC- Shibpur-Horinarayanpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
34 | 250792004- Construction of 12.00m Long RCC Girder Bridge on Kushtia (Lahini)- Bashgram GC Road at Ch: 6750m. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
35 | 250792004-Kushtia (Lahini)-Bashgram G.C Road | KDRIDP/KUSH/B-01/2017-18 | 0 | 12 | 0 | 119.717 | 2019-01-15 | M/S. Islam Traders | 2019-03-06 | 113.11 | 0% | 2020-01-20 | 0 | 0 | 0 | 0% | 28 days notice on 13.05.19, Memo : 1334
36 | 250792005- Bittipara Hat R&H-Jamjami G.C via Jhowdia Hat Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 250792005- Construction of 45.00m Long RCC Girder Bridge on Kushtia Bittipara Hat R&H- Jamjami GC via Jhowdia Hat Road at Ch:1400m. | KDRIDP/KUSH/B-06/2018-19 | 0 | 45 | 0 | 454.02 | 2018-11-12 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 90 m Bridge required
Construction of Bridge on Union Road/Village Road (5.50m width)
38 | 250795321-Const. of RCC Bridge on Machpara Primary School-Shidurghat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
39 | 250795008-Jogia R&H-Mubarok Bandth Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 250794052-Periodic Maintennance of Ujangram belly Bridge to Alinogor Sidurghat Jhowdia Road. (Ch: 6850-7850 m) | KDRIDP/KUSH/M-07/2017-18 | 1 | 0 | 0 | 14.39 | 2018-02-01 | ATAUR RAHAMAN ATA | 2018-04-26 | 15.75 | 100% | 2018-08-29 | 15.75 | 15.75 | 0 | 100% | Final
41 | 250794001-Shaldha-H.Horipur bazar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
42 | 250794063-Kanchonpur-Kamlapur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
43 | 250794002-Hatos Horripur-Saldah Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
44 | 250794036-Police line R&H-Paschim Majumpur(Hazi A.Rahaman Road) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
45 | 250794065-Abdulpur bazar-Jhoudia Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
46 | 250795030-Baliapara-Baraiapara Bridge Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
GC-Hat
47 | Contuction of Bhadalia Growth Center | KDRIDP/KUSH/GC-17/2017-18 | 0 | 0 | 1 | 20.04 | 2018-02-08 | M/S JAKAULLAH & BROTHERS | 2018-04-10 | 18.038 | 100% | 2018-08-13 | 0 | 15.8 | -15.8 | 87.59% | Work completed
Tree Plantation
48 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 32.813 | 57 | 1 | 2559.014 |  |  |  | 1992.69 | 41.67% |  | 434.88 | 1049.792 | -614.912 | 52.68%

## Daulatpur
Daulatpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 250392012-Improvement of Kalayanpur Bazar-Daulatpur GC Road ch00-2440m Salvage Cost Tk. 4396874.00 | KDRIDP/KUSH/W-24/2017-18 | 2.44 | 0 | 0 | 180.88 | 2017-08-21 | Shamim Enterprise | 2017-09-14 | 175.46 | 100% | 2018-03-05 | 172.548 | 128.58 | 43.968 | 73.28% | work completed
1 | 250392012-Improvement of Kalayanpur Bazar-Daulatpur GC Road ch2440 -4528mSalvage Cost Tk. 2904017.00 | KDRIDP/KUSH/W-47/2017-18 | 2.09 | 0 | 0 | 120.76 | 2018-12-07 | Sadikuzzaman Khan Sumon | 2018-02-19 | 125.61 | 100% | 2018-06-24 | 125.55 | 96.511 | 29.039 | 76.83% | work completed
Improvement of Union Road by BC
2 | 250393004-Improvement of Refayetpur UP-Horingacha-Gazipur Hat road ch1250-2550m Salvage Cost Tk. 2356957.00 | KDRIDP/KUSH/W-25/2017-18 | 1.3 | 0 | 0 | 82.18 | 2017-08-21 | Shamim Enterprise | 2017-09-14 | 79.7 | 100% | 2018-01-28 | 79.7 | 79.7 | 0 | 100% | Final
3 | 250393004-Improvement of Refayetpur UP-Horingacha-Gazipur Hat road ch2550-3920m Salvage Cost Tk. 2706004.00 | KDRIDP/KUSH/W-48/2017-18 | 1.37 | 0 | 0 | 90.72 | 2018-02-15 | sadikuzzaman khan sumon | 2018-04-12 | 94.348 | 100% | 2018-10-14 | 0 | 67.29 | -67.29 | 71.32% | work completed
4 | 250393009-Taragunia GC-Kaipal H/O Nazimuddin-Basepur-Daulatpur UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 250393015-Refaetpur UP-Horingachi Malithapara-Paikpara-Naudapara Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 250393017-Boragangdia GC-Aria Shajimore-Parhsitly-Digholkandi Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 250393018-(a) Improvement of Dangmorka Bazar-Primary School-Adabaria UP Office-Tekalahat Road ch2000-3000m (b) Improvement of Dangmorka Bazar-Primary School-Adabaria UP Office-Tekalahat Road ch4058-4890m Salvage Cost Tk. 1189755.00 | KDRIDP/KUSH/W-26/2017-18 | 1.832 | 0 | 0 | 106.795 | 2017-08-21 | Md Abdur razzak | 2017-09-13 | 111.01 | 100% | 2018-09-09 | 110.91 | 110.91 | 0 | 99.91% | Final
Improvement of Village Road by BC
7 | 250394002-Bialgathua-Mohishkundi Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 250394017-Lalnagar-Laximpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 250394019-Improvement of Horingachi-Laximikhola Road ch837-1673m | KDRIDP/KUSH/W-27/2017-18 | 0.836 | 0 | 0 | 45.86 | 2017-08-21 | Md Shohel Choduary | 2017-09-13 | 48.115 | 100% | 2018-09-05 | 48.115 | 48.115 | 0 | 100% | Final
10 | 250394021-Improvement of Laximikhola- Horingachi road (ch.1000-2190m) | KDRIDP/KUSH/W-60/2017-18 | 1.19 | 0 | 0 | 73.768 | 2018-02-15 | sadikuzzaman khan sumon | 2018-04-12 | 76.715 | 100% | 2018-10-14 | 0 | 55 | -55 | 71.69% | work completed
11 | 250394030-Khalishakuandi-Moubaria Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 250394048-Jogonathpur-Pearpur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 250394068-Improvement of shoshidarpur-Hoshenabad road (ch.980-2434m) | KDRIDP/KUSH/W-61/2017-18 | 1.454 | 0 | 0 | 86.69 | 2018-02-15 | Hisna Engineers (Md.Mohidul Islam Ripon) | 2018-07-17 | 97.176 | 100% | 2019-01-18 | 0 | 85 | -85 | 87.47% | work completed
14 | 250394074-Lalnagar bazar-Pakkula-Sadarpur GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 250394079-Sangrampur-Lalnagar bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 250394082-Mothurapur Bazar-Gobargara-Darerpara-Daulatpur UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 250394084-Mainkdiar-Moslempur-Hogolbaria UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 250394086 Chatarpara hat-Angdia-Sadarpur Road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 250394065-Improvement of Bagoan-Poalbaria-Chilmari Road ch1100-1550m | KDRIDP/KUSH/W-28/2017-18 | 0.45 | 0 | 0 | 26.46 | 2017-08-21 | J.S Construction | 2017-09-04 | 27.72 | 100% | 2018-06-14 | 27.708 | 27.708 | 0 | 99.96% | Final
20 | 250394162-Improvement of H/O Fajlu Molla UZR at Dharmodah-Matpara ch00-1000m | KDRIDP/KUSH/W-29/2017-18 | 1 | 0 | 0 | 54.86 | 2017-08-21 | Md Shem Choduary | 2017-09-24 | 57.58 | 60% | 2018-09-10 | 0 | 0 | 0 | 0% | WBM Completed (ch;oo-500 m)
Improvement of Village Road by HBB
21 | 250394002-Bialgathua-Mohishkundi Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
22 | 250394012-Periodic Maintennance of Sadipur -Mandalpara Road .(Ch:0.00m-1050m) | KDRIDP/KUSH/M-10/2017-18 | 1.05 | 0 | 0 | 22.247 | 2018-02-01 | M/S Monjil traders | 2018-03-28 | 23.2 | 0% | 2018-07-31 | 0 | 0 | 0 | 0% | Canceled & Now Pakage Name will change for Retender
23 | 250394020-Periodic Maintennance of Sherpur Pearpur- UP Road at (Ch:0.00m-4133m) | KDRIDP/KUSH/M-23/2018-19 | 4.133 | 0 | 0 | 98.99 | 2018-11-29 | Md. Alomgir Kabir Titu | 2019-01-13 | 94.04 | 20% | 2019-07-17 | 0 | 0 | 0 | 0% | Earth work. (to send 28 days letter ).
24 | 250394043-Periodic Maintennance of Mashaura-Bagoan Road. (Ch:0.00m-590m and 928m-2375m) | KDRIDP/KUSH/M-13/2017-18 | 2.037 | 0 | 0 | 47.985 | 2018-02-01 | mir mamun hossain | 2018-03-20 | 51.258 | 100% | 2019-02-08 | 51.255 | 51.255 | 0 | 99.99% | Final
25 | 250394055-Periodic Maintennance of Bagoan -Madapur Road. (Ch:0.00m-1987m) | KDRIDP/KUSH/M-12/2017-18 | 1.987 | 0 | 0 | 38.335 | 2018-02-01 | mir mamun hossain | 2018-03-20 | 42.15 | 100% | 2019-02-08 | 42.122 | 42.122 | 0 | 99.93% | Final
26 | 250394067-Periodic Maintennance of Garura College Mor- UP complex -Adabaria Road. (Ch:0.00m-2730m) | KDRIDP/KUSH/M-22/2017-18 | 2.73 | 0 | 0 | 57.942 | 2018-02-01 | M/S. Tamanna Trade International (Md. Saidur Rahman) | 2019-01-17 | 55.04 | 40% | 2019-07-21 | 0 | 0 | 0 | 0% | Hard bed preraration. (to send 28 days letter ).
27 | 250395005-Balirdiar-Koldiar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 250392010-Mothurapur GC-Hoshenabad Vocational-Farakpur-Chakdiar-Toltolipara-Gachirdiar-Juniadaha GC Road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 250392010-Mothurapur GC-Hoshenabad Vocational-Farakpur-Chakdiar-Toltolipara-Gachirdiar-Juniadaha GC Road . | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
30 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 25.899 | 0 | 0 | 1134.472 |  |  |  | 1159.122 | 38.12% |  | 657.908 | 792.191 | -134.283 | 68.34%

## Bheramara
Bheramara
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 250152007-Improvement of Pakshi R&H Fary Ghat via Moulahabaspur Golapnagar Bazar road-R&H (Dakabari) Dhorompur road ch: 5842-6083m & 7479-8944m Salvage Cost Tk. 418922.00 | KDRIDP/KUSH/W-11/2016-17 | 1.706 | 0 | 0 | 115.97 | 2017-07-24 | M/s Meherul Alam | 2017-09-14 | 109.688 | 100% | 2018-08-29 | 64.608 | 64.608 | 0 | 58.9% | Final
Improvement of Union Road by BC
2 | 250153003-Mokarimpur UP HQ-Dharampur Hat via SomitirHat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
3 | 250154001-Improvement of Dharampur near Mango Garden-Maulahabaspur R.R. Bridge road. (Ch.2514-3455m) | KDRIDP/KUSH/W-45/2017-18 | 0.941 | 0 | 0 | 63.71 | 2017-12-07 | M/S Meherul Alam | 2018-02-18 | 60.88 | 100% | 2018-08-22 | 0 | 50.477 | -50.477 | 82.91% | Work completed
4 | 250154003-Improvement of Parankhali-Dalua Hat Road ch1000-2500m Salvage Cost Tk 2665728.00 | KDRIDP/KUSH/W-12/2016-17 | 1.5 | 0 | 0 | 83.29 | 2017-07-24 | National Enginearing | 2017-08-30 | 81.49 | 100% | 2018-03-29 | 80.407 | 79.23 | 1.177 | 97.23% | Final
5 | 250154005-Improvement of Thakur Daulatpur-Arkandi Rly Gate road ch00-1360m Road ID No-250154005 Salvage Cost Tk. 1638217.00 | KDRIDP/KUSH/W-13/2016-17 | 1.36 | 0 | 0 | 75.22 | 2017-07-24 | Md Nazmul Islam | 2017-09-14 | 72.13 | 100% | 2018-08-28 | 71.568 | 71.568 | 0 | 99.22% | Final
6 | 250154028-R&H 12 mile Cold Store -Baradi Hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 250154053-Jagssar Hat-Nalua Hat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 250154090-Improvement of -Junidha Haripur-Gachia Daulatpur Battola More Vai Baktepur RD. (Ch:-1200-2123m) | KDRIDP/KUSH/W-42/2017-18 | 0.923 | 0 | 0 | 52.43 | 2018-12-07 | National Engineering | 2018-02-08 | 50.04 | 60% | 2018-08-22 | 0 | 27.043 | -27.043 | 54.04% | Sand filing completed
9 | 250154093-Improvement of Kazihata R&H -Mohishadora R&H -Via Amdha Rd. (1000-3030m) | KDRIDP/KUSH/W-43/2017-18 | 2.03 | 0 | 0 | 116.22 | 2017-12-07 | Md. Shamshodwha Mallick | 2018-02-13 | 110.006 | 40% | 2018-08-17 | 0 | 0 | 0 | 0% | Materials mobilized
10 | 250154068-Improvement of Pagli bitir House to Gopinathpur Gorostan road. (Ch:500-2000 m) | KDRIDP/KUSH/W-46/2017-18 | 1.5 | 0 | 0 | 92.038 | 2017-12-07 | M/s. Meherul Alam | 2018-02-18 | 88.62 | 100% | 2018-08-22 | 0 | 85 | -85 | 95.92% | Work completed
11 | 250154074-G.K Canle Bulbul Kabir’s house near of Chandripur Khalil house road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 250155228-Improvement of Uttar Bhabanipur Samsul `S Murri Mill-Abdul`S House road. (Ch: 00-705m) | KDRIDP/KUSH/W-44/2017-18 | 0.705 | 0 | 0 | 40.698 | 2017-12-07 | Abu Hena Mostofa Kamal | 2018-01-03 | 40.19 | 100% | 2018-06-09 | 40.189 | 40.189 | 0 | 100% | Final
Construction of Bridge on Union Road/Village Road (5.50m width)
13 | 250154052-Construction of 22.00m Long RCC Girder Bridge on Ghikri parankhali-Golapnagar Bazar Road at Ch: 985m. | KDRIDP/KUSH/B-05/2018-19 | 0 | 22 | 0 | 208.09 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
14 | 250152007-Pakshi R&H Fary Ghat via moulahabashpur Golapnagar bazar road-R&H(Dakerbari) Dhorompur rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 250154001-Periodic Maintennance of Dharampur Mangro Garden-Maulahabashpur R.R Bridge Road .(Ch:0.00m-1000m). | KDRIDP/KUSH/M-04/2017-18 | 1 | 0 | 0 | 17.63 | 2017-12-28 | M/S Meherul Alam | 2018-02-26 | 17.01 | 100% | 2018-07-01 | 16.98 | 16.98 | 0 | 99.82% | Final
16 | 250154028-Periodic Maintennance of R&H 12mile Cold Store -Baradi Hat Road .(Ch:1478-2765m) | KDRIDP/KUSH/M-01/2017-18 | 1.287 | 0 | 0 | 28.33 | 2017-12-28 | M/S Meherul Alam | 2018-02-26 | 26.84 | 100% | 2018-07-01 | 26.8 | 26.8 | 0 | 99.85% | Final
17 | 250154053-Jagssar Hat-Nalua Hat Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
18 | 250154090-Periodic Maintennance of Junidah Haripur -Gachia Doulatpur Batttola Via Bektepur Road .(Ch:0.00m-702m) | KDRIDP/KUSH/M-06/2017-18 | 0.702 | 0 | 0 | 13.26 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 13.225 | 100% | 2018-07-31 | 13.222 | 13.222 | 0 | 99.98% | Final
19 | 250154060-Khamirdiar-Ramkrishnapur via Mokarimpur Up road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 250154004- Periodic Maintennance of Jagassar-Jagassar Mosque Road .(Ch:0.00m-528m) | KDRIDP/KUSH/M-05/2017-18 | 0.528 | 0 | 0 | 10.096 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 10.057 | 100% | 2018-07-31 | 10.056 | 10.056 | 0 | 99.99% | Final
21 | 250154024-Saruper ghope Pry. School- Nobogonga Graveyard rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 250154037- Kazihata RHD -Satbaria (Dharompur Millpara) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
23 | Bir Muktizodda Morhoom Osman Ali Srite (Chandipr (H/O Lozen more - 12 mile R&H)Road.250154072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | Kazihata R&H to Mohishadora R&H via Amdha Road.250154093 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 250154012-Periodic Maintennance of Golopnagor Bazer -WAPDA Embankment Road .(Ch:0.00m-1665m) | KDRIDP/KUSH/M-03/2017-18 | 1.665 | 0 | 0 | 20.36 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 20.27 | 100% | 2018-08-30 | 20.22 | 20.22 | 0 | 99.75% | Final
26 | Bahadurpur Hat-WAPDA Embankment.250154013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | Kuchiamora Bazer-Malipara Embankment.250154016 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 250154034-Periodic Maintennance of Fayzullahpur (UZR-Junidah) via Horipur Road .(Ch:0.00m-773m) | KDRIDP/KUSH/M-02/2017-18 | 0.773 | 0 | 0 | 14.75 | 2018-02-01 | M/S MEHARUL ALOM | 2018-03-28 | 14.71 | 100% | 2018-07-31 | 14.63 | 14.63 | 0 | 99.46% | Final
Tree Plantation
29 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 16.62 | 22 | 0 | 952.092 |  |  |  | 715.156 | 44.83% |  | 358.68 | 520.023 | -161.343 | 72.71%

## Mirpur
Mirpur
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 250942005-Improvement of Mirpur-Alamdanga GC via Halsha Road ch18730-20350m Salvage Cost Tk. 211042.00 | KDRIDP/KUSH/W-08/2016-17 | 1.62 | 0 | 0 | 124.4 | 2017-07-24 | M/S Sumsudoula mollek | 2017-09-13 | 130.16 | 100% | 2018-05-27 | 0 | 85 | -85 | 65.3% | work completed
Improvement of Union Road by BC
2 | 250943003-Improvement of Bahalbaria UP-Boria Bazar via Dhubail Bazar road ch: 2106-6420m & 9213-10270m Salvage Cost Tk. 3180964.00 | KDRIDP/KUSH/W-09/2016-17 | 5.371 | 0 | 0 | 320.11 | 2017-07-24 | Sayket Enterprise | 2017-09-20 | 335.145 | 100% | 2018-09-09 | 0 | 315.121 | -315.121 | 94.03% | Work completed
3 | 250943006-Baruipara UP-Jogti GC Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 250943010-Improvement of Kushabari-Chatian Up Via Burapara Miltoan Road. (Ch:1915-2960m) | KDRIDP/KUSH/W-49/2017-18 | 1.045 | 0 | 0 | 58.27 | 2017-10-10 | M/S Abu Hanif D sons | 2017-11-08 | 57.69 | 100% | 2018-05-13 | 0 | 26.13 | -26.13 | 45.29% | work completed
5 | 250943014-Improvement of Sorupdah (Poradah GC) -Mirpur Upazila HQ via Chatian Up Road ch11221-12260m Salvage Cost Tk. 955598.00 | KDRIDP/KUSH/W-10/2016-17 | 1.039 | 0 | 0 | 65.22 | 2017-07-24 | M/S Ekramul Haque | 2017-09-14 | 68.33 | 100% | 2018-03-29 | 67.977 | 67.98 | -0.003 | 99.49% | Final
Improvement of Village Road by BC
6 | 250944018-Improvement of chuniapara -khewpur bazar Road (ch:1500m-3600m) | KDRIDP/KUSH/W-64/2017-18 | 2.1 | 0 | 0 | 144.94 | 2018-04-09 | Bashundhara Enterprise | 2018-05-20 | 137.696 | 100% | 2019-03-29 | 0 | 39 | -39 | 28.32% | work completed
7 | 250944034-Majihat bazar-Beshinagor rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
8 | 250944041-Improvement of Aburia-Ahsan Nagar Road. (Ch:0.00-1500m). | KDRIDP/KUSH/W-58/2017-18 | 1.5 | 0 | 0 | 84.47 | 2018-02-15 | MD.SARWAR HOSSAIN | 2018-04-17 | 88.485 | 60% | 2018-10-19 | 0 | 20 | -20 | 22.6% | 0
9 | 250944056-Improvement of Chatian Uttorpara Hat - Atigram Golabari Hat Via Atigram FWC Road. (Ch:3600-4685m). | KDRIDP/KUSH/W-59/2017-18 | 1.085 | 0 | 0 | 78.5 | 2017-12-24 | Bashundhara Enterprise | 2018-02-18 | 76.808 | 100% | 2018-06-30 | 76.731 | 76.731 | 0 | 99.9% | Final
10 | 250944057- Improvement of Paharpur bazar(WDB bridge) -Amla bazar road Ch:(00-1350m)+(1700-2400m) | KDRIDP/KUSH/W-87/2018-19 | 2.05 | 0 | 0 | 146.583 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 250945023- Improvement of Gobindopur-Tatibandh road Ch:(00-1435m) (Salvage cost:27,20,817) | KDRIDP/KUSH/W-88/2018-19 | 1.435 | 0 | 0 | 121.91 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 250945099-Improvement of Sorupdah Madrasha-Gobindapur Hazrakhali Road. (Ch:850-1720m). | KDRIDP/KUSH/W-50/2017-18 | 0.87 | 0 | 0 | 47.68 | 2018-02-15 | Afsar Trading | 2018-07-09 | 50.04 | 60% | 2019-01-27 | 0 | 27.613 | -27.613 | 55.18% | 0
13 | 250945184-Karir hat JHS-Bakek Mondol house road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 250945235-Baliashisa mathpara- Dangarpara GPS road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 250945239-Improvement of Ahammadpur-Amod Ali house -Bedonbil Bridge Road. (Ch:1300-2290m) | KDRIDP/KUSH/W-51/2017-18 | 0.99 | 0 | 0 | 66.7 | 2018-12-07 | M/S. Rowshan Traders | 2018-02-08 | 68.536 | 60% | 2018-08-12 | 0 | 16.084 | -16.084 | 23.47% | WBM completed.(28 days Notice on 14.08.18, Memo :2507 )
16 | 250945261-Improvement of Ramnagar bridge-Basbaria Road. (Ch:1300-2290m) | KDRIDP/KUSH/W-52/2017-18 | 0.935 | 0 | 0 | 56.29 | 2018-12-07 | M/S. Rowshan Traders | 2018-02-08 | 56.238 | 0% | 2018-08-12 | 0 | 0 | 0 | 0% | Contract cacelled, 28 days Notice on 14.08.18, Memo :2506
17 | 250945369-Improvement of chuniapara -khewpur Road( ch:0.00m-1838m) | KDRIDP/KUSH/W-67/2017-18 | 1.838 | 0 | 0 | 89.65 | 2018-04-09 | Bashundhara Enterprise | 2018-05-20 | 85.168 | 100% | 2019-03-29 | 0 | 24 | -24 | 28.18% | work completed
18 | 250945103-Nowab Sirajdaula college-(Syphone bridge)-Kewpur Charpara road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 250945381-Balidapara Mosque-Balidapara atiar H/O Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
20 | 250945382-Balidapara Anez Mondol H/O-Baruipara Noor Hosain H/O. road, | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
21 | 250945375-Moshan Poraadaha road Babul H/O Kewpur Billpara road. | KDRIDP/KUSH/W-66/2017-18 | 0.405 | 0 | 0 | 25.798 | 2018-04-09 | Bashundhara Enterprise | 2018-05-20 | 24.508 | 100% | 2019-01-28 | 0 | 7 | -7 | 28.56% | Not yet Started
22 | 250945376-Improvement of Baruipara Ufan Member H/O-Fakirabad Mahatab H/O Road. (Ch:00-945m). | KDRIDP/KUSH/W-53/2017-18 | 0.945 | 0 | 0 | 55.49 | 2017-12-20 | Md. Aminul Islam | 2018-02-12 | 54.85 | 100% | 2018-08-16 | 54.85 | 54.85 | 0 | 100% | Final
23 | 250945376-Improvement of Baruipara Ufan Member H/O-Fokirabad Mahatab H/O Road. (Ch:1432m-1619 m) | KDRIDP/KUSH/W-62/2017-18 | 0.187 | 0 | 0 | 22.11 | 2018-02-01 | m/s asif traders | 2018-03-27 | 21.96 | 100% | 2018-08-29 | 0 | 21.862 | -21.862 | 99.55% | Work completed
24 | 250945370-Improvement of balidapara Hinif H/O- balidapara salam H/O road. (Ch:0.00m-1515m). | KDRIDP/KUSH/W-65/2017-18 | 1.515 | 0 | 0 | 97.517 | 2018-04-09 | Nice Home Construction & Supplyer | 2018-05-27 | 92.64 | 10% | 2019-02-27 | 0 | 0 | 0 | 0% | Materials mobilization on going
Improvement of Village Road by HBB
25 | 250945206-Kachubaria Kazi Arif Sarok- Chuwduar Via Kachubaria Grave Yerd Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 250945237- Improvement of Belgachi Club via Sabed Member house road Ch:00-2130m. | KDRIDP/KUSH/W-85/2018-19 | 2.13 | 0 | 0 | 96.9 | 0 | 0 | 0 | 92.06 | 0% | 0 | 0 | 0 | 0 | 0% | 0
27 | 250945248-Jogoti Sugar Mill Grave Yerd- BTC gate via Kalabaria Purbapara Jame Mosque Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 250945250- Improvement of Kalabaria Eidgah-Dosttopara via GK khal road Ch:00-915m.(Salvage cost:3,18,439) | KDRIDP/KUSH/W-86/2018-19 | 0.915 | 0 | 0 | 40.423 | 0 | 0 | 0 | 38.402 | 0% | 0 | 0 | 0 | 0 | 0% | 0
| 250945252- Improvement of Poradah Chitalia Moinagari gate-Sodirazpur road Ch:500-1827m. |  | 1.327 | 0 | 0 | 56.29 |  |  |  | 53.476 |  |  | 0 | 0 | 0 | 0%
Maintenance
29 | 250942004- Mirpur GC-Bheramara Gc road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
30 | 250943008- Periodic Maintennance of Nowdangodindopur R&H -Bahalbaria UP via Talbaria UP Road .(Ch:1168m-3000m) | KDRIDP/KUSH/M-14/2017-18 | 1.832 | 0 | 0 | 33.706 | 2018-02-26 | ESHANUL HAQUE | 2018-04-26 | 36.74 | 100% | 2018-09-28 | 36.575 | 36.575 | 0 | 99.55% | Final
31 | 250943011- Periodic Maintennance of Mirpur BDR camp-Kuchuadha bazer Road. (Ch:0.00m-3375m) | KDRIDP/KUSH/M-15/2017-18 | 4.348 | 0 | 0 | 67.49 | 2018-02-01 | Md. Esanul haque | 2018-03-20 | 70.53 | 100% | 2018-09-21 | 70.53 | 70.53 | 0 | 100% | Final
32 | 250943012-Periodic Maintennance of Nowpara bazer- Mirzanagor bazer Road .(Ch:1100m-3782m). | KDRIDP/KUSH/M-16/2017-18 | 2.682 | 0 | 0 | 47.18 | 2018-02-26 | ESHANUL HAQUE | 2018-04-26 | 51.43 | 100% | 2018-09-24 | 0 | 50.733 | -50.733 | 98.64% | Work completed
33 | 250943013-Periodic Maintennance of Ambaria-Sree Rampur bazer UP- Road .(Ch:4400m-5800m) | KDRIDP/KUSH/M-17/2017-18 | 1.4 | 0 | 0 | 42.808 | 2018-02-08 | M/S SR CONSTRUCTION | 2018-03-28 | 43.665 | 100% | 2018-09-29 | 0 | 8 | -8 | 18.32% | BC preparetion on going, .(28 days Notice on 14.08.18, Memo :2501)
34 | 250943014-Periodic Maintennance of Sorupdah(PoradahGC)-Mirpur UP H/Q via Chatian UP - Road .(Ch:0.00m-3800m &5050m-5900m). | KDRIDP/KUSH/M-18/2017-18 | 4.65 | 0 | 0 | 82.03 | 2018-02-01 | MD.ESANUL HOQUE | 2018-03-20 | 89.496 | 100% | 2018-09-21 | 0 | 88.34 | -88.34 | 98.71% | Work completed
35 | 250944004- Khadimpur Bazar-Nowda R&H road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
36 | 250944014- Hazrahati Bazar-Jogoti Main Cannel road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
37 | 250944038-Bamungari-Ambaria Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
38 | 250944050- Mirpur-Bahalbaria Bazar road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
39 | 250944060-Poradha-Katdhachar RHD Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
40 | 25094200- Mirpur Upazila H/Q- Poradah Gc road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
41 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 44.214 | 0 | 0 | 2072.465 |  |  |  | 1824.053 | 41.22% |  | 306.663 | 1035.549 | -728.886 | 56.77%

## Summary
KUSHTIA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 6 | 6 | 11.256 | 0 | 0 | 716.854 | 544.165 | 100% | 75.91%
Union Road by BC | 14 | 14 | 21.018 | 0 | 0 | 1304.612 | 870.255 | 88.33% | 66.71%
Village Road by BC | 67 | 58 | 85.885 | 0 | 0 | 4605.302 | 2480.529 | 78.31% | 53.86%
Village Road by HBB | 3 | 3 | 9.674 | 0 | 0 | 404.985 | 50 | 66% | 12.35%
Bridge on Upazila Road | 4 | 2 | 0 | 178 | 0 | 782.486 | 0 | 0% | 0%
Bridge on Union Road/Village Road | 2 | 1 | 0 | 148 | 0 | 407.345 | 0 | 0% | 0%
Maintenance | 23 | 23 | 45.994 | 0 | 0 | 1031.474 | 655.047 | 82.61% | 63.51%
GC-Hat | 3 | 3 | 0 | 0 | 3 | 51.958 | 43.93 | 100% | 0%
Landing/ Riverghat | [9 empty] | N/A
Tree Plantation |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 122 | 110 | 173.827 | 326 | 3 | 9305.016 | 4643.926 | 57.25% | 49.91%