## Chuadanga
CHUADANGA
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
Alamdanga
1 | 218072006-Bondabil R&H-Durlavpur-Hardi-Mirpur (Alamdanga Portion) Rd. | [13 empty] | 0 | #DIV/0!
2 | 218072014-(a) Improvement of Goldari GC-Nilmonigonj Alamdanga Portion road by BC Ch 00-2740m (b) Construction of 6 nos 625x600mm U-Type Drian Culvert at Ch 8 360 720 1510 1820 and 2578m on same road. Salvage Amount TK 510471.00 | KDRIDP/Chua/W-03/2016-17 | 2.74 | 0 | 0 | 202.05 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-11 | 202.03 | 100% | 2018-11-30 | 201.903 | 201.903 | 0 | 99.94% | Final
Damurhuda
3 | 218312008-Improvement of Damurhuda GC-Golaidari RHD road Ch 7850-9360m. | KDRIDP/Chua/W-25/2016-17 | 1.51 | 0 | 0 | 100.92 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 90.83 | 100% | 2018-07-11 | 90.823 | 90.823 | 0 | 99.99% | Final
4 | 218312006-Improvement of Memnagar RHD-Karpashdanga G.C via Buichitala Ch 16670-17800m. Salvage Amount TK. 31050.00 | KDRIDP/Chua/W-24/2016-17 | 1.13 | 0 | 0 | 80.18 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 72.164 | 100% | 2018-07-11 | 72.162 | 72.162 | 0 | 100% | Final
Jibonnagar
5 | 218552009-a) Improvement of Uthali R&H Mollabari-Uthali GC road Ch 00-1140m (b) Construction of 1 nos U-Type Drain Culvert size 625x600mm at Ch 40.00m on same road under Jibannagar Upazila in Chuadanga District Salvage Amount TK. 1723642.00 | KDRIDP/Chua/W-18/2016-17 | 1.14 | 0 | 0 | 82.45 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 74.2 | 100% | 2018-06-19 | 74.13 | 74.13 | 0 | 99.91% | Final
Total |  |  | 6.52 | 0 | 0 | 465.6 |  |  |  | 439.224 | 100% |  | 439.018 | 439.018 | 0 | 99.95%
Improvement of Union Road by BC
Chuadanga Sadar
1 | 218233002-(a) Improvement of Dingadah Shankarchandra UP Makaldanga-Doster Hat road by BC Ch 6820-7735m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 7165m on same road. Salvage Amount TK 53178.00 | KDRIDP/Chua/W-05/2016-17 | 0.915 | 0 | 0 | 53.24 | 2017-05-22 | M/S Saiful Hasan Joarder | 2017-07-09 | 47.92 | 100% | 2018-04-11 | 47.82 | 47.82 | 0 | 99.79% | Final
2 | 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 00-25m Ch 70-258m & Ch 680-1400m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 740m 775m 858m & 1173m on The same road. Salvage Amount TK.589357.00 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 1800-5100m Part-B.2 Construction of 1no Size 2.00x1.60m Box Culvert at Ch 4806m Part-B.3 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2396m & 3311m on The same road. Salvage Amount TK.1785054.00 | KDRIDP/Chua/W-39/2017-18 | 4.233 | 0 | 0 | 291.45 | 2018-05-28 | Jahirul Limited | 2018-07-30 | 256.41 | 70% | 2019-08-02 |  | 142.258 | -142.258 | 55.48%
3 | 218233010-Titudaho UP-Sarabaria-Sujatpur Rd. | [13 empty] | 0 | #DIV/0!
Alamdanga
4 | 218073003-(a) Improvement of Baradi Up-Morebhanga Hat.road Ch -4250m -6704m & 8222-8835 (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 4310, 5355, 5755 & 8468m same road under Alamdanga Upazila in Chuadanga District. Salvage-1526030.00 | KDRIDP/Chua/W-32/2017-18 | 3.067 | 0 | 0 | 204.45 | 2018-02-28 | RAB-RC (PVT) Limited-MS Shahana Construction Md. Mejanur Rahman | 2018-04-15 | 184 | 100% | 2019-01-16 | 183.98 | 183.98 | 0 | 99.99% | Final
5 | 218073007-Belgachi UP-Ghosbiala Hat Rd. | [13 empty] | 0 | #DIV/0!
6 | 218073015-(A) Improvement of Belgachi UP-Jehala UP road Ch 2100m-5260m (B) Construction of 2Nos 2.00mx2.00m RCC Box Culvert at Ch 2604 & 4425m (C) Construction of 1No 1.00mx1.00m RCC Box Culvert at Ch 3644m D Construction of 11 nos 0.600mx0.625m U-Type Drain Culvert at Ch2300m, 2410m, 2624m, 2742m, 2975m, 3530m, 3612m, 3826m, 4332m, 4666m & 5240m. Salvage Amount TK.740657.00 | KDRIDP/Chua/W-35/2017-18 | 3.16 | 0 | 0 | 230.507 | 2018-05-10 | Md. Shamshodwha Mallick | 2018-07-23 | 194.994 | 60% | 2019-11-30 |  | 106.877 | -106.877 | 54.81%
7 | 218073017-(A) Improvement of Ailhas UP-Loxmipur Hat road Ch 750m-2650m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 2468m (C) Construction of 7 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1275m, 1522m, 1633m, 1923m, 2000m, 2108m & 2635m on The same road | KDRIDP/Chua/W-36/2017-18 | 1.9 | 0 | 0 | 131.037 | 2018-05-07 | Md. Afzalul Haque | 2018-06-12 | 124.48 | 100% | 2019-05-28 | 124.467 | 124.467 | 0 | 99.99% | Final
8 | 218073025-(a) Improvement of Jehala UP-Kumari UP road by BC Ch 2250-2484m 2934-3540m 3650-4675m5208-7383m 7583-7977m and 8727-9111m (b) Construction of 12 nos 625x600mm U-Type Drian Culvert at Ch 3268 3379 3418 3828 3888 3936 6025 6170 6230 6375 6705 and 8834m on same road. Salvage Amount TK 904869.00 | KDRIDP/Chua/W-04/2016-17 | 4.818 | 0 | 0 | 295.3 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 295.16 | 100% | 2018-04-07 | 295.136 | 295.136 | 0 | 99.99% | Final
9 | 218073028-Part-A.1 Improvement of Alamdanga-Nagdah UP Office via Damas Kedernagar Road Ch 1573-4755m & Ch 5535-7512m Part-A.2 Construction of 2nos Size 1.00x1.00m Box Culvert at Ch 2098 & 4104m Part-A.3 Construction of 11nos Size 0.600mx0.625m U-Type Drain Culvert at Ch 1588m 1969m 2520m 2850m 4650m 5233m 5339m 5837m 5954m 6110m & 6318m on The same road. Salvage Amount TK.2328406.00. | KDRIDP/Chua/W-42/2017-18 | 5.159 | 0 | 0 | 328.115 | 2018-05-28 | M/S MM & SD JV | 2018-07-23 | 280.909 | 25% | 2019-07-26 |  | 56.591 | -56.591 | 20.15%
10 | 218073021-Bhangabaria UP-Bogadi hat road. | [13 empty] | 0 | #DIV/0!
Damurhuda
11 | 218313002-Gobindahuda Hat-Karpasdanga UP Road | [13 empty] | 0 | #DIV/0!
12 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC (Ch 12257-13600m). Salvage Amount TK 24740.00 | KDRIDP/Chua/W-10/2016-17 | 1.343 | 0 | 0 | 67.49 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 67.56 | 100% | 2018-09-23 | 67.317 | 67.317 | 0 | 99.64% | Final
13 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC Ch 10957-12257m. | KDRIDP/Chua/W-12/2016-17 | 1.3 | 0 | 0 | 71.36 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 64.22 | 100% | 2018-09-20 | 64.22 | 64.22 | 0 | 100% | Final
14 | 218313004-Parkrisnopur Madna UP-Kuralgachhi UP | [13 empty] | 0 | #DIV/0!
Jibonnagar
15 | 218553001-Jibannagar-Shimanta UP-Benipur Hat road. | [13 empty] | 0 | #DIV/0!
16 | 218553004-Improvement of Shimanta UP-Goyespur-Dhopakhali Hat road Ch 5510-7960m. Salvage Amount TK. 537215.00 | KDRIDP/Chua/W-22/2016-17 | 2.45 | 0 | 0 | 134.99 | 2017-08-24 | RAB-RC (PVT) Limited | 2017-10-09 | 121.49 | 100% | 2018-07-05 | 121.49 | 121.49 | 0 | 100% | Final
17 | 218553007-Barbhanga R&H-Sutiahat-Hashadah UP Rd. | [13 empty] | 0 | #DIV/0!
18 | 218553008-Shimanto UP- Goyespur-Dhapakhalihat Rd. | [13 empty] | 0 | #DIV/0!
19 | 218553009-Simanto UP-Korotoya-Horihornagar Rd. | [13 empty] | 0 | #DIV/0!
20 | 218553013-Raypur UP-Khalispur GC Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 28.345 | 0 | 0 | 1807.939 |  |  |  | 1637.143 | 85.5% |  | 904.43 | 1210.156 | -305.726 | 73.92%
Improvement of Village Road by BC
Chuadanga Sadar
1 | 218234013-(a) Improvement of Shamvonagar-Shahebnagar road Ch - 910m-2410m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1390m & 2250m. Salvage-929613.00 | KDRIDP/Chua/W-16/2016-17 | 1.5 | 0 | 0 | 90.6 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 81.536 | 100% | 2018-06-19 |  | 81.536 | -81.536 | 100%
2 | 218234013-Improvement of Shambunagar-Shahebnagor road Ch 2410-3410m Part-B.2 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2503m & 2674m on The same road. Salvage Amount TK.785762.00 | KDRIDP/Chua/W-38/2017-18 | 1 | 0 | 0 | 64.61 | 2018-05-10 | Md. Babul Mia | 2018-06-12 | 61.38 | 100% | 2019-03-06 |  | 61.37 | -61.37 | 99.98% | Final
| 218234020-Improvement of Nehalpur GCCR-Krishnopur road Ch 1000-1992m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 11105m 1362m 1583m & 1940m on The same road. |  | 0.992 | 0 | 0 | 65.33 |  |  |  | 62.06 |  |  |  | 62.06 | -62.06 | 100%
3 | 218234015-Bhultia R&H-Kharagoda Road | [13 empty] | 0 | #DIV/0!
4 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasar road Ch - 1500m-3000m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1824m & 2140m. | KDRIDP/Chua/W-15/2016-17 | 1.5 | 0 | 0 | 84.82 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 76.335 | 100% | 2018-12-31 | 76.305 | 76.305 | 0 | 99.96% | Final
5 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasha road by BC Ch 3000-3395m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 3100m. Salvage Amount TK 262371.00 | KDRIDP/Chua/W-07/2016-17 | 0.395 | 0 | 0 | 27.87 | 2017-05-22 | M/S Shahana Construction | 2017-07-03 | 25.08 | 100% | 2018-04-06 | 25.07 | 25.074 | -0.004 | 99.98% | Final
6 | 218234040-Badargong R&H-Ashananda pur bazar Via Kotubpur Bazar Rd | [13 empty] | 0 | #DIV/0!
7 | 218234042-Chhoto Salua - Jrishnogar bazar Rd | [13 empty] | 0 | #DIV/0!
8 | 218234049-(a) Improvement of Bhultia R&H-Tiorbila road by BC Ch 1310-2332m (b) Construction of 1no U-drain Culvert 625x600mm at Ch 2140m. Salvage Amount TK 143978.00 | KDRIDP/Chua/W-08/2016-17 | 1.022 | 0 | 0 | 57.85 | 2017-05-22 | Md.Ali Reza | 2017-06-13 | 52.066 | 70% | 2018-03-17 | 52.066 | 52.066 | 0 | 100% | Final
9 | 218234049-Improvement of Bhultia R&H-Tiorbila road Ch 2332-3445m | KDRIDP/Chua/W-37/2017-18 | 1.113 | 0 | 0 | 68.6 | 2018-05-10 | M/S Padma Traders | 2018-06-12 | 65.17 | 100% | 2019-05-28 | 65.17 | 65.17 | 0 | 100% | Final
| 218235011-Improvement of Subdia R&H-Baliakandi road Ch 820-1265m Salvage Amount TK.479973.00 |  | 0.445 | 0 | 0 | 27.856 |  |  |  | 26.46 |  |  | 26.46 | 26.46 | 0 | 100% | Final
10 | 218235021-Improvement of Dehi-Darsana road Ch 1750-2138m Part-A.2 Construction of 1no Size 0.625mx0.600m U-Type Drain Culvert at Ch 1969m on The same road. | KDRIDP/Chua/W-41/2017-18 | 0.388 | 0 | 0 | 26.23 | 2018-05-10 | Md. Babul Akter | 2018-06-12 | 24.92 | 50% | 2019-05-28 |  | 9.791 | -9.791 | 39.29% | Final
| 218235028-Improvement of Makaldanga-Srikele road Ch 970-3265m Part-B.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 1222m 2274m 2453m & 3115m on The same road. Salvage Amount TK.441147.00 |  | 2.295 | 0 | 0 | 148.606 |  |  | 2018-06-12 | 141.176 |  |  |  | 55.482 | -55.482 | 39.3%
11 | 218235041-(a) Improvement of Batikadanga-Sujayetpur road by BC Ch 1368-2000m (b) Construction of 2 nos U-Drain Culvert 625x600mm at Ch 1398 & 1603m | KDRIDP/Chua/W-06/2016-17 | 0.632 | 0 | 0 | 39.27 | 2017-05-22 | M/S. R. M. Bricks | 2017-07-03 | 35.35 | 100% | 2018-04-06 | 35.347 | 35.347 | 0 | 99.99% | Final
12 | 218235041-Improvement of Batikadanga-Sajayetpur road at Ch.-2000m-2858m | KDRIDP/Chua/W-40/2017-18 | 0.858 | 0 | 0 | 57.25 | 2018-09-14 | Md.Anwar Hossain | 2018-11-18 | 54.388 | 75% | 2020-01-20 |  | 36.672 | -36.672 | 67.43%
| 218235100-Improvement of Alukdia Shead Member house-Rabbani Mondol house via Huchokpara road Ch.-00m - 1780m | KDRIDP/Chua/W-40/2017-18 | 1.78 | 0 | 0 | 117.273 |  | Md.Anwar Hossain |  | 111.407 |  |  |  | 75.134 | -75.134 | 67.44%
13 | 218235057-(a) Improvement of Natun Bhanderdah-Basu Bhanderdah-Bhanderdah-Jugirhuda road Ch - 4575m-6200m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 4910m & 5225m. Salvage-414736.00 | KDRIDP/Chua/W-27/2017-18 | 1.625 | 0 | 0 | 107.36 | 2018-05-28 | M/S Nitu Traders | 2018-07-04 | 101.99 | 100% | 2019-04-08 | 101.892 | 101.892 | 0 | 99.9% | Final
14 | 218235139-(a) Improvement of Akondobaria Azizuler House-Gunonpara Hudar Bari road by BC Ch 00-1500m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 400 and 770m on same road. Salvage Amount TK 113311.00 | KDRIDP/Chua/W-02/2016-17 | 1.5 | 0 | 0 | 84.8 | 2017-05-15 | Md.Bokhtier Uddin | 2017-06-06 | 84.58 | 100% | 2018-11-06 | 84.561 | 84.561 | 0 | 99.98% | Final
15 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road by BC Ch 00-2000m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 28 730 and 1782m on same road. Salvage 3746786 | KDRIDP/Chua/W-01/2016-17 | 2 | 0 | 0 | 118.1 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 118.09 | 100% | 2018-04-07 | 118.06 | 118.06 | 0 | 99.97% | Final
16 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road Ch -2000m-3215m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 2328m 2555m & 2812m same road under Chuadanga Sadar Upazila in Chuadanga District. Salvage 1881928 | KDRIDP/Chua/W-14/2016-17 | 1.22 | 0 | 0 | 76.07 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 68.459 | 100% | 2018-06-19 | 68.426 | 68.426 | 0 | 99.95% | Final
Alamdanga
17 | 218074004-Improvement of Faridpur-Damos road by BC at Ch: 00-3060m. Salvage Amount TK. 544625.00. | KDRIDP/Chua/W-44/2017-18 | 3.06 | 0 | 0 | 199.799 | 2018-07-05 | Md. Sirazul Islam | 2018-08-02 | 189.809 | 100% | 2019-07-07 | 189.655 | 189.655 | 0 | 99.92% | Final
18 | 218074010-Ailhas - Sonatonpur Rd. | [13 empty] | 0 | #DIV/0!
19 | 218074022-Potimari Bottala - Belgech UP via Kadarnagar Rd. | [13 empty] | 0 | #DIV/0!
20 | 218075016-(a) Improvement of MochaiNagar-Shalikha Ch - 00m -1244m & 2200-3290m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 235, 273, 2225, 2311, 2700 & 2936 m. Salvage-4194651.00 | KDRIDP/Chua/W-33/2017-18 | 2.334 | 0 | 0 | 181.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 163.725 | 60% | 2019-04-04 |  | 94.077 | -94.077 | 57.46%
21 | 218075027-(A) Improvement of Shampur bridge-Alamdanga Rail gate road Ch 1140-3370m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 275m ( C) Construction of 6 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1990m, 2028m, 2182m, 2672m, 2790m & 3068m. Salvage Amount TK.515428.00. | KDRIDP/Chua/W-34/2017-18 | 2.23 | 0 | 0 | 138.98 | 2018-05-07 | R.F.M Construction | 2018-06-07 | 132.03 | 40% | 2019-05-17 |  | 24.418 | -24.418 | 18.49%
22 | 218075030-Pardurgapur-Digholdanga Rd. | [13 empty] | 0 | #DIV/0!
23 | 218075031-(a) Improvement of Kachikata Bridge-Baradi road Ch - 500m -2635m (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 547, 1048, 1342m & 2112m. Salvage-23000.00 | KDRIDP/Chua/W-30/2017-18 | 2.135 | 0 | 0 | 134.19 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 120.77 | 100% | 2019-03-27 | 120.54 | 120.54 | 0 | 99.81% | Final
24 | 218075070-Improvement of Paikpara Math road by BC at Ch 1300-2000m | KDRIDP/Chua/W-45/2017-18 | 0.7 | 0 | 0 | 47.61 | 2018-07-05 | M/S Hashina and Sons | 2018-08-13 | 45.23 | 15% | 2019-08-18 |  |  | 0 | 0%
| 218075186-Improvement of Par Laximpur-Kodamtola Allas Bazar road by BC at Ch 00-1174m. | KDRIDP/Chua/W-45/2017-18 | 1.174 | 0 | 0 | 77.42 |  | M/S Hashina and Sons |  | 73.55 |  |  |  |  | 0 | 0%
25 | 218075155-(Part-A1) Improvement of Jehala UP-Munshigonj Poshu Hat via Gorgori Asrayon road by BC at Ch 1210m-2449m & 3145m-4290m (Part-A2) Construction of 4nos (Size 0.600mx0.625m) U-Type Drain Culvert at Ch 1300m, 1418m, 1792m, & 3555m on The same road. (Salvage Amount :TK.27,25,611.00) | KDRIDP/Chua/W-46/2018-19 | 2.384 | 0 | 0 | 179.527 | 2018-11-20 | Liton Traders | 2019-01-21 | 179.47 | 0% | 2020-01-27 |  |  | 0 | 0%
| 218075032-(Part-B-1) Improvement of Madarhuda-Tamaltala-Jehala UP road by BC at Ch 00m-1374m (Part-B2) Construction of 5nos (Size 0.600mx0.625m) U-Type Drain Culvert at Ch 41m, 506m, 618m, 954m, & 1119m on The same road. (Salvage Amount: TK. 4,86,687.00) | KDRIDP/Chua/W-46/2018-19 | 1.374 | 0 | 0 | 94.61 |  | Liton Traders |  | 94.58 |  |  |  |  | 0 | 0%
26 | 218075201-(Part-A) Improvement of Chitlamore road-Panchkomlapur road via Aliatnagar road At (Ch 1185-1930m) (Part-B) Construction of 3nos Size 0.600mx0.625m U-Type Drain Culvert at Ch 1745m, 1870m & 1920m on same road. | KDRIDP/Chua/W-43/2017-18 | 0.745 | 0 | 0 | 49.208 | 2018-05-28 | Md. Mozaharul Haque Mollick | 2018-07-08 | 46.748 | 100% | 2019-04-12 | 46.748 | 46.748 | 0 | 100% | Final
27 | 218075213-(a) Improvement of Jehala Mohon Master house - Matpara Mosque - Gorchapra Shaid Mamber houseroad Ch - 120m -1450m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 250, 488, 810, 1061, 1130 & 1227m same road under Alamdanga Upazila in Chuadanga District. Salvage-299944.00 | KDRIDP/Chua/W-31/2017-18 | 1.33 | 0 | 0 | 88.85 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 79.968 | 100% | 2019-03-27 | 79.968 | 79.968 | 0 | 100% | Final
Damurhuda
28 | 218314012-a) Improvement of Kushaghata R&H-Purapara road Ch 514-1120m (b) Construction of 2 nos Pipe Culvert at Ch 915 & 1100m. Salvage Amount TK. 160525.00 | KDRIDP/Chua/W-26/2016-17 | 0.606 | 0 | 0 | 33.54 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 30.18 | 100% | 2018-07-11 | 30.175 | 30.175 | 0 | 99.98% | Final
29 | 218314016-Improvement of Dugdugi Family Planing Center-Gobindapur road by BC Ch 00-1640 & 3273-3333m. Salvage Amount TK 209026.00 | KDRIDP/Chua/W-11/2016-17 | 1.7 | 0 | 0 | 93.49 | 2017-05-22 | Jahirul Limited | 2017-07-09 | 84.14 | 100% | 2018-04-11 | 84.14 | 84.14 | 0 | 100% | Final
30 | 218314017-Hawli Eidgah-Shaikpara R&H Road. | [13 empty] | 0 | #DIV/0!
31 | 218314019-Javrampur Battala Parimary School -Uktya Road. | [13 empty] | 0 | #DIV/0!
32 | 218314032-Parkisnopur-Jhajadanga Rd | [13 empty] | 0 | #DIV/0!
33 | 218314040-Improvement of Pirpur Kullah-Shihnagar via Boyra road by BC at Ch 3700m-6170m. Part-A2 Construction of 7nos U-Type Drain Culvert at Ch 4230m 4443m 4640m 4777m 4937m 5057m & 5520m on The same road. Salvage Amount TK.783608.00 | KDRIDP/Chua/W-47/2018-19 | 2.47 | 0 | 0 | 187.41 | 2018-11-20 | M/s Madani Enterprise | 2019-01-24 | 187.38 | 70% | 2020-01-30 |  | 104.752 | -104.752 | 55.9%
| 218314006-Improvement of Jhoragacha-Kalabaria road by BC at Ch 00m-1950m Part-B2 Construction of 6nos U-Type Drain Culvert at Ch 948m 1077m 1107m 1200m 1549m & 1906m on The same road. Salvage Amount TK.932751.00 | KDRIDP/Chua/W-47/2018-19 | 1.95 | 0 | 0 | 147.169 |  | M/s Madani Enterprise |  | 147.147 |  |  |  | 82.272 | -82.272 | 55.91%
34 | 218314053-(a) Improvement of Chandra FRB-Kanidanga road by BC Ch 4733-6233m (b) Construction of 2 nos U-Tyup Drain Culvert at Ch 5922 & 5788m | KDRIDP/Chua/W-09/2016-17 | 1.5 | 0 | 0 | 84.25 | 2017-05-22 | Md. Shamshodwha Malick | 2017-07-09 | 75.83 | 100% | 2018-11-30 | 75.816 | 75.816 | 0 | 99.98% | Final
35 | 218314054-Jhapjhapi bridge-Hogoldanga FRB Road | [13 empty] | 0 | #DIV/0!
Jibonnagar
36 | 218554001-Purandupur - Nischatapur Road | [13 empty] | 0 | #DIV/0!
37 | 218554002-Panarasoti Bhanga Bridge-Tarinibash Road | [13 empty] | 0 | #DIV/0!
38 | 218554004-Narayanpur-Gangadaspur Rd | [13 empty] | 0 | #DIV/0!
39 | 218554012-a) Improvement of Krishnopur more-Maerudah hat-Shebkhali road Ch 2420-3220m (b) Construction of 1 no RCC Box Culvert size 2.00x2.60m at Ch 2713m (c) Construction of 2 Nos U Type Drain Culvert size 625 x 600 m at Ch 2600 and 2947m. Salvage Amount TK. 597943.00 | KDRIDP/Chua/W-23/2016-17 | 0.8 | 0 | 0 | 57.51 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 51.76 | 100% | 2018-08-31 | 51.65 | 51.65 | 0 | 99.79% | Final
40 | 218554014-Balihuda-Natun Chakla Road | [13 empty] | 0 | #DIV/0!
41 | 218554017-a) Improvement of Tutulia BGB camp-Rakhal Shah Mazar road Ch 1800-4150m (b) Construction of 3 nos U-Drain Culvert at Ch 2730, 3300 & 3400m. Salvage Amount TK. 560988.00 | KDRIDP/Chua/W-19/2016-17 | 2.35 | 0 | 0 | 133.02 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 119.72 | 100% | 2018-11-28 | 119.718 | 119.718 | 0 | 100% | Final
42 | 218554023 a) Improvement of Muktarpur-Shahebkhali road via Katapol Chakla road Ch 2050-3810m (b) Construction of 1 no U-Type Drain Culvert size 625x600mm at Ch 3271m. Salvage Amount TK.106683.00 | KDRIDP/Chua/W-21/2016-17 | 1.76 | 0 | 0 | 97.48 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 87.73 | 100% | 2018-07-11 | 87.72 | 87.72 | 0 | 99.99% | Final
43 | 218554023 Part-A Improvement of Muktarpur-Shahebkhali road via Katapol Chakla road by BC at Ch 00-1400m Part-B Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 52, 984, 1155 & 1370m | KDRIDP/Chua/W-48/2018-19 | 1.4 | 0 | 0 | 105.83 | 2019-03-04 | Md. Alauddin | 2019-04-09 | 100.538 | 0% | 2020-01-09 |  |  | 0 | 0%
44 | 218554031- A) Improvement of Goyespur-BGB Camp-Changkhali road Ch 4140-6542m B) Construction of 4 nos U-Type Drain Culvert at Ch 4150, 4650,5800 & 6310 m. Salvage Amount TK.142098.00 | KDRIDP/Chua/W-29/2017-18 | 2.402 | 0 | 0 | 150.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-17 | 135.83 | 60% | 2019-04-12 |  | 73.153 | -73.153 | 53.86%
45 | 218554035-Sontoshpur R&H-Rajapur UZR Road | [13 empty] | 0 | #DIV/0!
46 | 218554037-Improvement of Daulatgong GC-Benipur hat road at ch 6140-8900m. Salvage Amount TK. 280855.00 | KDRIDP/Chua/W-20/2016-17 | 2.76 | 0 | 0 | 151.79 | 2017-07-25 | M/S. JAKAULLAH & BROTHERS | 2017-08-27 | 136.608 | 100% | 2018-06-02 | 136.608 | 136.608 | 0 | 100% | Final
47 | 218554050-a) Improvement of Uthali R&H-Dhopakhali Hat road Ch 1425-3981m (b) Construction of 2 nos 1.00x1.60m Box Culvert at CH 2359 and 3085m (c) Construction of 1 No U-Drain Culvert at Ch 2001m. Salvage Amount TK. 2029785.00 | KDRIDP/Chua/W-17/2016-17 | 2.556 | 0 | 0 | 150.77 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 135.687 | 100% | 2018-09-18 | 135.687 | 135.687 | 0 | 100% | Final
48 | 218554050- Improvement of Uthali R&H Dhopakhali Hat road by BC at Ch 3981-4606m | KDRIDP/Chua/W-49/2018-19 | 0.625 | 0 | 0 | 44.478 | 2019-03-04 | M/S Shekh Traders | 2019-04-01 | 42.25 | 70% | 2020-01-01 |  | 24.34 | -24.34 | 57.61%
| 218554078- Improvement of Andulbaria UP-Begumpur Hat road by BC at Ch 00-750m | KDRIDP/Chua/W-49/2018-19 ( Road ID NO 218554050) & (Road ID NO 218554078) | 0.75 | 0 | 0 | 55.18 |  | M/S Shekh Traders |  | 52.42 |  |  |  | 30.2 | -30.2 | 57.61%
49 | 218555003-A) Improvement of Annantopur Mosque-Mondertola road Ch 00m-1150m B) Construction of 2 nos U-Type Drain Culvert size 600x625mm at Ch 3.00 & 295m. Salvage Amount TK.333332.00 | KDRIDP/Chua/W-28/2017-18 | 1.15 | 0 | 0 | 77.885 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 70.1 | 100% | 2018-10-07 |  | 58.116 | -58.116 | 82.9%
Total |  |  | 62.51 | 0 | 0 | 4025.331 |  |  |  | 3773.647 | 82.65% |  | 1811.782 | 2685.159 | -873.377 | 71.16%
Improvement of Village Road by HBB
Chuadanga Sadar
1 | 218235019-Akandabaria bazar-Chandpur Rd. | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Alamdanga
2 | 218075047-Bokshipur-Bhodhua Rd. | [13 empty] | 0 | #DIV/0!
3 | 218075147-Boksipur Moor-Maju Bridge via Modhppur Road. | [13 empty] | 0 | #DIV/0!
Damurhuda
4 | 248314073-Chandrabass-Satiantala Road | [13 empty] | 0 | #DIV/0!
5 | 248315080-Laxmipur Hat Mosque Kana Pukorlkor via Dhakian para Graveyard Rd. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Construction of Bridge on Union Road/Village Road (5.50m width)
Alamdanga
1 | 218073033-Construction of 84.00m long PC girder bridge on bhangbaria UP office to udaypurhat via bhshbaria road at ch 400.00m | KDRIDP/CHUA/B-02/2018-19 | 0 | 84 | 0 | 437.705 | 2018-11-27 | Md. Shamshodwha Mallick | 2019-02-12 | 359.595 | 5% | 2020-07-27 |  |  | 0 | 0%
2 | 218073018-Construction of 75.00m long PC girder bridge on gangni UP to baradi UP road at ch 4300.00m | KDRIDP/CHUA/B-01/2018-19 | 0 | 75 | 0 | 395.27 | 2018-11-27 | Md. Shamshodwha Mallick | 2019-02-12 | 351.358 | 0% | 2020-07-27 |  |  | 0 | 0%
Damurhuda
3 | 218313009-Const. of RCC Bridge on Par Damurhdua to Karpasdanga UP Road. | [13 empty] | 0 | #DIV/0!
4 | 218314059-Const. of RCC Bridge on Kanaidanga FRB-Kunia Ferryghat Road. | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 159 | 0 | 832.975 |  |  |  | 710.953 | 2.5% |  | 0 | 0 | 0 | 0%
Maintenance
Chuadanga Sadar
1 | 218234002-Hakita RH-Hatikata Mazar Rd. | [13 empty] | 0 | #DIV/0!
2 | 218234004-Periodic Maintenance of Nilmoniganj-Kulchara more road Ch. 00m-2615m | KDRIDP/Chua/M-07/2017-18 | 2.615 | 0 | 0 | 52.17 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.95 | 100% | 2018-08-29 | 46.95 | 46.95 | 0 | 100% | Final
3 | 218234034-Periodic Maintenance of Jafarpur-Hanurbaradi Road at Ch 00-2400m. | KDRIDP/Chua/M-23/2018-19 | 2.4 | 0 | 0 | 67.267 | 2018-11-08 | M/S. Kaba Enterprise | 2018-12-23 | 63.9 | 50% | 2019-09-27 |  | 28.476 | -28.476 | 44.56%
| 218234037-Periodic Maintenance of Joyrampur-Chuadanga Road at Ch 00-1850m. | KDRIDP/Chua/M-23/2018-19 | 1.85 | 0 | 0 | 33.477 |  | M/S. Kaba Enterprise |  | 31.8 |  |  |  | 14.175 | -14.175 | 44.58%
| 218234050-Periodic Maintenance of Alukdia U.P-Khadimpur Road at Ch 00-2200m | KDRIDP/Chua/M-23/2018-19 | 2.2 | 0 | 0 | 49.525 |  | M/S. Kaba Enterprise |  | 47.049 |  |  |  | 20.97 | -20.97 | 44.57%
4 | 218234036-Periodic Maintenance of Chuadanga-Makaldanga road Ch. 3800m-5250m | KDRIDP/Chua/M-08/2017-18 | 1.45 | 0 | 0 | 26.995 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 24.3 | 100% | 2018-08-29 | 24.286 | 24.29 | -0.004 | 99.96% | Final
5 | 218234037-Periodic Maintenance of Joyrampur-Chuadanga road Ch. 3730m-8000m. | KDRIDP/Chua/M-09/2017-18 | 4.27 | 0 | 0 | 73.79 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 66.41 | 100% | 2018-08-29 | 57.77 | 57.77 | 0 | 86.99% | Final
6 | 218234040-Badargong R&H -Ashana ndapur Bazar via Kotubpur Bazar Rd. | [13 empty] | 0 | #DIV/0!
7 | 218234051-Periodic Maintenance of 5Mils R&H-Balshapur via Harukadi Road Ch. 00m-4190m | KDRIDP/Chua/M-10/2017-18 | 4.19 | 0 | 0 | 72.77 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 65.49 | 100% | 2018-08-29 | 65.487 | 65.487 | 0 | 100% | Final
8 | 218234053-Periodic Maintenance of Titudah UP-Gopalnagar Road Ch. 00m-1050m | KDRIDP/Chua/M-11/2017-18 | 1.05 | 0 | 0 | 16.446 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 14.8 | 100% | 2018-08-29 | 14.799 | 14.799 | 0 | 99.99% | Final
9 | 218235027-Makaldanga- Dinnathpur Rd. | [13 empty] | 0 | #DIV/0!
Alamdanga
10 | 218072012-Periodic Maintenance of Munshigonj-Asmankhali GC road at ch-3730-8756 m | KDRIDP/CHUA/M-26/2018-19 | 5.026 | 0 | 0 | 112.106 | 2018-11-29 | M/S Sirishti International | 2019-01-15 | 106.5 | 0% | 2019-07-20 |  |  | 0 | 0%
11 | 218073007-Belgachi UP-Ghosbiala hat Rd. | [13 empty] | 0 | #DIV/0!
12 | 218073010-Baradi UP-Natidangahat Rd. | [13 empty] | 0 | #DIV/0!
13 | 218073028-Alamdanga-Nagdah UP Office via Damas, Kedernagar Road. | [13 empty] | 0 | #DIV/0!
14 | 218074010-Periodic Maintenance of Nagdah Sonatonpur road Ch. 00m-1250m | KDRIDP/Chua/M-03/2017-18 | 1.25 | 0 | 0 | 20.465 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.42 | 100% | 2018-08-29 | 18.42 | 18.42 | 0 | 100% | Final
15 | 218074012-Periodic Maintenance of Paikpara-Sreerampur Road at Ch 00-1500m | KDRIDP/Chua/M-25/2018-19 | 1.5 | 0 | 0 | 34.648 | 2018-11-08 | Md. Rawshan Alam | 2019-01-08 | 32.916 | 100% | 2019-07-17 |  | 32.9 | -32.9 | 99.95% | Final
| 218075016-Periodic Maintenance of MochaiNagar-Shalikha Road at Ch 1244-1971m | KDRIDP/Chua/M-25/2018-19 | 0.727 | 0 | 0 | 28.194 |  | Md. Rawshan Alam |  | 26.784 |  |  |  | 26.77 | -26.77 | 99.95% | Final
16 | 218074013-Periodic Maintenance of Hakimpur-Toirbila road Ch. 00m-2550m | KDRIDP/Chua/M-04/2017-18 | 2.55 | 0 | 0 | 51.905 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.71 | 100% | 2018-08-29 | 46.699 | 46.7 | -0.001 | 99.98% | Final
17 | 218074017-Periodic Maintenance of Bademaju-Binadpur R&H road Ch. 00m-1120m. | KDRIDP/Chua/M-05/2017-18 | 1.12 | 0 | 0 | 29.776 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 26.8 | 100% | 2018-08-29 | 26.793 | 26.793 | 0 | 99.97% | Final
18 | 218074019-Periodic Maintenance of Kayradanga FRB-Gokulkhali GC road. Ch 00m-2040m | KDRIDP/Chua/M-01/2017-18 | 2.04 | 0 | 0 | 25.43 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 22.89 | 100% | 2018-08-29 | 22.87 | 22.87 | 0 | 99.91% | Final
19 | 218074026-Periodic Maintenance of Gobindhopur-Kashipur via Faridpur road Ch. 00m-1700m. | KDRIDP/Chua/M-06/2017-18 | 1.7 | 0 | 0 | 38.76 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 34.89 | 100% | 2018-10-05 | 34.879 | 34.879 | 0 | 99.97% | Final
20 | 218074029-Periodic Maintenance of Ruhitanpur Hat-Kulpala Ch. 00m-2720m | KDRIDP/Chua/M-02/2017-18 | 2.72 | 0 | 0 | 47.07 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 42.37 | 100% | 2018-08-29 | 42.358 | 42.358 | 0 | 99.97% | Final
Damurhuda
21 | 218312014-Darsana GC- Madna-Sada bari -Pirpukullah -Karpashdanga GC Rd. | [13 empty] | 0 | #DIV/0!
22 | 218314002-Periodic Maintenance of Gopalpur Primary School-Daliarpur Road Ch. 00m-1095m. | KDRIDP/Chua/M-12/2017-18 | 1.095 | 0 | 0 | 18.23 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 16.41 | 100% | 2018-08-29 | 16.41 | 16.41 | 0 | 100% | Final
23 | 218314002-Periodic Maintenance of Gopalpur Prymary School-Daliarpur Road at Ch 1095-2023m | KDRIDP/Chua/M-21/2018-19 | 0.928 | 0 | 0 | 17.387 | 2018-11-08 | Md.Anwar Hossain | 2019-01-08 | 16.518 | 100% | 2019-07-13 | 16.48 | 16.48 | 0 | 99.77% | Final
| 218314019-Periodic Maintenance of Jayrampur Battala School-Uktya Road at Ch 1740-4345m | KDRIDP/Chua/M-21/2018-19 | 2.605 | 0 | 0 | 78.269 |  | Md.Anwar Hossain |  | 74.356 |  |  | 74.15 | 74.15 | 0 | 99.72% | Final
24 | 218314015-Loknathpur R&H-Darsona Dingadah Rd. | [13 empty] | 0 | #DIV/0!
25 | 218314019-Periodic Maintenance of Joyrampur Battala School-Uktya Road Ch. 00m-1740m | KDRIDP/Chua/M-13/2017-18 | 1.74 | 0 | 0 | 31.676 | 2017-12-27 | Liton Traders | 2018-02-19 | 28.51 | 100% | 2018-08-29 | 28.51 | 28.51 | 0 | 100% | Final
26 | 218314033-Periodic Maintenance of Modna-Hoybadpur more Road Ch. 00m-900m | KDRIDP/Chua/M-14/2017-18 | 0.9 | 0 | 0 | 14.825 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 13.34 | 100% | 2018-08-29 | 13.34 | 13.34 | 0 | 100% | Final
27 | 218314045-Damurhuda Brac more-Upazila more Rd. | [13 empty] | 0 | #DIV/0!
28 | 218314049-Periodic Maintenance of Baroboldia Bazar-Chindipur via Sarabaria Road Ch. 3380m-5125m. | KDRIDP/Chua/M-15/2017-18 | 1.745 | 0 | 0 | 28.15 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 25.34 | 100% | 2018-08-29 | 25.337 | 25.34 | -0.003 | 100% | Final
29 | 218314071-Periodic Maintenance of Talsari R&H-Horirampur Road Ch. 1120m-2690m. | KDRIDP/Chua/M-16/2017-18 | 1.57 | 0 | 0 | 20.11 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.1 | 100% | 2018-08-29 | 18.086 | 18.09 | -0.004 | 99.94% | Final
30 | 218314084-Periodic Maintenance of Buinchatala Tematha-Aramdanga via Thakurpur Road Part-A Ch. 00m-1940m & Part-B Ch. 8840-1189m | KDRIDP/Chua/M-17/2017-18 | 4.99 | 0 | 0 | 113.27 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 101.95 | 100% | 2018-08-29 | 101.934 | 101.934 | 0 | 99.98% | Final
Jibonnagar
31 | 218553010-Andulbaria UP - Grisnagar Bazar Rd. | [13 empty] | 0 | #DIV/0!
32 | 218554043-Periodic Maintenance of Balihuda UZR-Raypur Bazar Road Ch. 00m-2400m | KDRIDP/Chua/M-20/2017-18 | 2.4 | 0 | 0 | 38.87 | 2017-12-28 | M/S. Khandaker Shahin Ahmed | 2018-02-20 | 34.98 | 100% | 2018-09-04 | 34.951 | 34.951 | 0 | 99.92% | Final
33 | 218554047-Bokundia R&H - Minajpur hat Rd. | [13 empty] | 0 | #DIV/0!
34 | 218554054-Periodic Maintenance of Piaratala R&H-Kasipur Hat Road Ch. 00m-6420m. | KDRIDP/Chua/M-18/2017-18 | 6.42 | 0 | 0 | 92.81 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 83.53 | 100% | 2018-08-29 | 83.498 | 83.498 | 0 | 99.96% | Final
35 | 218554058-Periodic Maintenance of Hasadah UP-Dattanagar (Banka UP- Dattanagar) Bazar. Road at Ch 2000-5700m | KDRIDP/Chua/M-24/2018-19 | 3.7 | 0 | 0 | 137.047 | 2018-11-08 | M/S Shopno Construction | 2019-01-01 | 130.195 | 100% | 2019-07-06 |  | 128.7 | -128.7 | 98.85%
36 | 218554062-Periodic Maintenance of Uthali UZR-Uthali GC road at Ch 00-780m | KDRIDP/Chua/M-22/2018-19 | 0.78 | 0 | 0 | 17.878 | 2018-11-08 | RELATION ARCHITECT HOME | 2019-01-08 | 16.984 | 100% | 2019-07-13 | 16.981 | 16.981 | 0 | 99.98% | Final
37 | 218554068-Periodic Maintenance of Anantapur UZR-Pankahat Road Ch. 00m-3310m | KDRIDP/Chua/M-19/2017-18 | 3.31 | 0 | 0 | 58.35 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 52.52 | 100% | 2018-08-29 | 52.463 | 52.463 | 0 | 99.89% | Final
Total |  |  | 70.841 | 0 | 0 | 1447.666 |  |  |  | 1331.712 | 94.23% |  | 883.451 | 1135.454 | -252.003 | 85.26%
GC-Hat
Alamdanga
1 | Construction of Hardi Market Growth Center | KDRIDP/Chua/GC-22/2017-18 | 0 | 0 | 1 | 20.8 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.78 | 100% | 2018-12-24 |  | 13.916 | -13.916 | 66.97%
Jibonnagar
2 | Construction of Raypur Market Growth Center | KDRIDP/Chua/GC-23/2017-18 | 0 | 0 | 1 | 20.07 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.05 | 100% | 2018-12-28 | 19.997 | 19.997 | 0 | 99.74% | Final
Total |  |  | 0 | 0 | 2 | 40.87 |  |  |  | 40.83 | 100% |  | 19.997 | 33.913 | -13.916 | 83.06%
Landing/ Riverghat
Alamdanga
1 | RCC Ghatla at Kumar River | KDRIDP/Khul/ G-16/2017-18 | 0 | 0 | 1 | 30.28 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 30.267 | 100% | 2018-12-24 | 30.205 | 30.205 | 0 | 99.8% | Final
Total |  |  | 0 | 0 | 1 | 30.28 |  |  |  | 30.267 | 100% |  | 30.205 | 30.205 | 0 | 99.8%
Tree Plantation
Chuadanga Sadar
1 | Tree Plantation | [9 empty] | 0% |  |  |  | 0 | #DIV/0!
Alamdanga
2 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Damurhuda
3 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Jibonnagar
4 | Tree Plantation | [13 empty] | 0 | #DIV/0!
Total |  |  | 0 | 0 | 0 | 0 |  |  |  | 0 | 0% |  | 0 | 0 | 0 | #DIV/0!
Grand Total |  |  | 168.216 | 159 | 3 | 8650.661 |  |  |  | 7963.776 | 62.76% |  | 4088.883 | 5533.905 | -1445.022 | 69.49%
|  |  | 168.216 | 159 | 3 | 8650.661 |  |  |  | 7963.776 | 53.49% |  | 4088.883 | 5533.905 | -1445.022 | 69.49%

## Chuadanga Sadar
Chuadanga Sadar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Union Road by BC
1 | 218233002-(a) Improvement of Dingadah Shankarchandra UP Makaldanga-Doster Hat road by BC Ch 6820-7735m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 7165m on same road. Salvage Amount TK 53178.00 | KDRIDP/Chua/W-05/2016-17 | 0.915 | 0 | 0 | 53.24 | 2017-05-22 | M/S Saiful Hasan Joarder | 2017-07-09 | 47.92 | 100% | 2018-04-11 | 47.82 | 47.82 | 0 | 99.79% | Final
2 | 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 00-25m Ch 70-258m & Ch 680-1400m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 740m 775m 858m & 1173m on The same road. Salvage Amount TK.589357.00 218233007-Improvement of Grisnagar Bazar-Begumpur UP road Ch 1800-5100m Part-B.2 Construction of 1no Size 2.00x1.60m Box Culvert at Ch 4806m Part-B.3 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2396m & 3311m on The same road. Salvage Amount TK.1785054.00 | KDRIDP/Chua/W-39/2017-18 | 4.233 | 0 | 0 | 291.45 | 2018-05-28 | Jahirul Limited | 2018-07-30 | 256.41 | 70% | 2019-08-02 | 0 | 142.258 | -142.258 | 55.48% | 0
3 | 218233010-Titudaho UP-Sarabaria-Sujatpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
4 | 218234013-(a) Improvement of Shamvonagar-Shahebnagar road Ch - 910m-2410m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1390m & 2250m. Salvage-929613.00 | KDRIDP/Chua/W-16/2016-17 | 1.5 | 0 | 0 | 90.6 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 81.536 | 100% | 2018-06-19 | 0 | 81.536 | -81.536 | 100% | 0
5 | 218234013-Improvement of Shambunagar-Shahebnagor road Ch 2410-3410m Part-B.2 Construction of 2nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 2503m & 2674m on The same road. Salvage Amount TK.785762.00 | KDRIDP/Chua/W-38/2017-18 | 1 | 0 | 0 | 64.61 | 2018-05-10 | Md. Babul Mia | 2018-06-12 | 61.38 | 100% | 2019-03-06 | 0 | 61.37 | -61.37 | 99.98% | Final
| 218234020-Improvement of Nehalpur GCCR-Krishnopur road Ch 1000-1992m Part-A.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 11105m 1362m 1583m & 1940m on The same road. |  | 0.992 | 0 | 0 | 65.33 |  |  |  | 62.06 |  |  | 0 | 62.06 | -62.06 | 100%
6 | 218234015-Bhultia R&H-Kharagoda Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasar road Ch - 1500m-3000m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 1824m & 2140m. | KDRIDP/Chua/W-15/2016-17 | 1.5 | 0 | 0 | 84.82 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 76.335 | 100% | 2018-12-31 | 76.305 | 76.305 | 0 | 99.96% | Final
8 | 218234039-(a) Improvement of Sankarchandra-Boldia Madrasha road by BC Ch 3000-3395m (b) Construction of 1 no U-Drain Culvert 625x600mm at Ch 3100m. Salvage Amount TK 262371.00 | KDRIDP/Chua/W-07/2016-17 | 0.395 | 0 | 0 | 27.87 | 2017-05-22 | M/S Shahana Construction | 2017-07-03 | 25.08 | 100% | 2018-04-06 | 25.07 | 25.074 | -0.004 | 99.98% | Final
9 | 218234040-Badargong R&H-Ashananda pur bazar Via Kotubpur Bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 218234042-Chhoto Salua - Jrishnogar bazar Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218234049-(a) Improvement of Bhultia R&H-Tiorbila road by BC Ch 1310-2332m (b) Construction of 1no U-drain Culvert 625x600mm at Ch 2140m. Salvage Amount TK 143978.00 | KDRIDP/Chua/W-08/2016-17 | 1.022 | 0 | 0 | 57.85 | 2017-05-22 | Md.Ali Reza | 2017-06-13 | 52.066 | 70% | 2018-03-17 | 52.066 | 52.066 | 0 | 100% | Final
12 | 218234049-Improvement of Bhultia R&H-Tiorbila road Ch 2332-3445m | KDRIDP/Chua/W-37/2017-18 | 1.113 | 0 | 0 | 68.6 | 2018-05-10 | M/S Padma Traders | 2018-06-12 | 65.17 | 100% | 2019-05-28 | 65.17 | 65.17 | 0 | 100% | Final
| 218235011-Improvement of Subdia R&H-Baliakandi road Ch 820-1265m Salvage Amount TK.479973.00 |  | 0.445 | 0 | 0 | 27.856 | 0 |  |  | 26.46 |  |  | 26.46 | 26.46 | 0 | 100%
13 | 218235021-Improvement of Dehi-Darsana road Ch 1750-2138m Part-A.2 Construction of 1no Size 0.625mx0.600m U-Type Drain Culvert at Ch 1969m on The same road. | KDRIDP/Chua/W-41/2017-18 | 0.388 | 0 | 0 | 26.23 | 2018-05-10 | Md. Babul Akter | 2018-06-12 | 24.92 | 50% | 2019-05-28 | 0 | 9.791 | -9.791 | 39.29% | Final
| 218235028-Improvement of Makaldanga-Srikele road Ch 970-3265m Part-B.2 Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 1222m 2274m 2453m & 3115m on The same road. Salvage Amount TK.441147.00 |  | 2.295 | 0 | 0 | 148.606 |  |  |  | 141.176 |  |  | 0 | 55.482 | -55.482 | 39.3%
14 | 218235041-(a) Improvement of Batikadanga-Sujayetpur road by BC Ch 1368-2000m (b) Construction of 2 nos U-Drain Culvert 625x600mm at Ch 1398 & 1603m | KDRIDP/Chua/W-06/2016-17 | 0.632 | 0 | 0 | 39.27 | 2017-05-22 | M/S. R. M. Bricks | 2017-07-03 | 35.35 | 100% | 2018-04-06 | 35.347 | 35.347 | 0 | 99.99% | Final
15 | 218235041-Improvement of Batikadanga-Sajayetpur road at Ch.-2000m-2858m | KDRIDP/Chua/W-40/2017-18 | 0.858 | 0 | 0 | 57.25 | 2018-09-14 | Md.Anwar Hossain | 2018-11-18 | 54.388 | 75% | 2020-01-20 | 0 | 36.672 | -36.672 | 67.43% | 0
| 218235100-Improvement of Alukdia Shead Member house-Rabbani Mondol house via Huchokpara road Ch.-00m - 1780m |  | 1.78 | 0 | 0 | 117.273 |  |  |  | 111.407 |  |  | 0 | 75.134 | -75.134 | 67.44%
16 | 218235057-(a) Improvement of Natun Bhanderdah-Basu Bhanderdah-Bhanderdah-Jugirhuda road Ch - 4575m-6200m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 4910m & 5225m. Salvage-414736.00 | KDRIDP/Chua/W-27/2017-18 | 1.625 | 0 | 0 | 107.36 | 2018-05-28 | M/S Nitu Traders | 2018-07-04 | 101.99 | 100% | 2019-04-08 | 101.892 | 101.892 | 0 | 99.9% | Final
17 | 218235139-(a) Improvement of Akondobaria Azizuler House-Gunonpara Hudar Bari road by BC Ch 00-1500m (b) Construction of 2 nos 625x600mm U-Type Drian Culvert at Ch 400 and 770m on same road. Salvage Amount TK 113311.00 | KDRIDP/Chua/W-02/2016-17 | 1.5 | 0 | 0 | 84.8 | 2017-05-15 | Md.Bokhtier Uddin | 2017-06-06 | 84.58 | 100% | 2018-11-06 | 84.561 | 84.561 | 0 | 99.98% | Final
18 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road by BC Ch 00-2000m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 28 730 and 1782m on same road. Salvage 3746786 | KDRIDP/Chua/W-01/2016-17 | 2 | 0 | 0 | 118.1 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 118.09 | 100% | 2018-04-07 | 118.06 | 118.06 | 0 | 99.97% | Final
19 | 218234021-(a) Improvement of Jalsuka-Chhaygharia School road Ch -2000m-3215m (b) Construction of 3 nos 625x600mm U-Type Drian Culvert at Ch 2328m 2555m & 2812m same road under Chuadanga Sadar Upazila in Chuadanga District. Salvage 1881928 | KDRIDP/Chua/W-14/2016-17 | 1.22 | 0 | 0 | 76.07 | 2017-07-25 | Mohammed Eunus & Brothers (Pvt) LTD | 2017-09-13 | 68.459 | 100% | 2018-06-19 | 68.426 | 68.426 | 0 | 99.95% | Final
Improvement of Village Road by HBB
20 | 218235019-Akandabaria bazar-Chandpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
21 | 218234002-Hakita RH-Hatikata Mazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 218234004-Periodic Maintenance of Nilmoniganj-Kulchara more road Ch. 00m-2615m | KDRIDP/Chua/M-07/2017-18 | 2.615 | 0 | 0 | 52.17 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.95 | 100% | 2018-08-29 | 46.95 | 46.95 | 0 | 100% | Final
23 | 218234034-Periodic Maintenance of Jafarpur-Hanurbaradi Road at Ch 00-2400m. | KDRIDP/Chua/M-23/2018-19 | 2.4 | 0 | 0 | 67.267 | 2018-11-08 | M/S. Kaba Enterprise | 2018-12-23 | 63.9 | 50% | 2019-09-27 | 0 | 28.476 | -28.476 | 44.56% | 0
| 218234037-Periodic Maintenance of Joyrampur-Chuadanga Road at Ch 00-1850m. |  | 1.85 | 0 | 0 | 33.477 |  |  |  | 31.8 |  |  | 0 | 14.175 | -14.175 | 44.58%
| 218234050-Periodic Maintenance of Alukdia U.P-Khadimpur Road at Ch 00-2200m |  | 2.2 | 0 | 0 | 49.525 |  |  |  | 47.049 |  |  | 0 | 20.97 | -20.97 | 44.57%
24 | 218234036-Periodic Maintenance of Chuadanga-Makaldanga road Ch. 3800m-5250m | KDRIDP/Chua/M-08/2017-18 | 1.45 | 0 | 0 | 26.995 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 24.3 | 100% | 2018-08-29 | 24.286 | 24.29 | -0.004 | 99.96% | Final
25 | 218234037-Periodic Maintenance of Joyrampur-Chuadanga road Ch. 3730m-8000m. | KDRIDP/Chua/M-09/2017-18 | 4.27 | 0 | 0 | 73.79 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 66.41 | 100% | 2018-08-29 | 57.77 | 57.77 | 0 | 86.99% | Final
26 | 218234040-Badargong R&H -Ashana ndapur Bazar via Kotubpur Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 218234051-Periodic Maintenance of 5Mils R&H-Balshapur via Harukadi Road Ch. 00m-4190m | KDRIDP/Chua/M-10/2017-18 | 4.19 | 0 | 0 | 72.77 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 65.49 | 100% | 2018-08-29 | 65.487 | 65.487 | 0 | 100% | Final
28 | 218234053-Periodic Maintenance of Titudah UP-Gopalnagar Road Ch. 00m-1050m | KDRIDP/Chua/M-11/2017-18 | 1.05 | 0 | 0 | 16.446 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 14.8 | 100% | 2018-08-29 | 14.799 | 14.799 | 0 | 99.99% | Final
29 | 218235027-Makaldanga- Dinnathpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Tree Plantation
30 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 45.438 | 0 | 0 | 1999.625 |  |  |  | 1855.476 | 63.83% |  | 910.469 | 1498.401 | -587.932 | 80.76%

## Alamdanga
Alamdanga
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 218072006-Bondabil R&H-Durlavpur-Hardi-Mirpur (Alamdanga Portion) Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
2 | 218072014-(a) Improvement of Goldari GC-Nilmonigonj Alamdanga Portion road by BC Ch 00-2740m (b) Construction of 6 nos 625x600mm U-Type Drian Culvert at Ch 8 360 720 1510 1820 and 2578m on same road. Salvage Amount TK 510471.00 | KDRIDP/Chua/W-03/2016-17 | 2.74 | 0 | 0 | 202.05 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-11 | 202.03 | 100% | 2018-11-30 | 201.903 | 201.903 | 0 | 99.94% | Final
Improvement of Union Road by BC
3 | 218073003-(a) Improvement of Baradi Up-Morebhanga Hat.road Ch -4250m -6704m & 8222-8835 (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 4310, 5355, 5755 & 8468m same road under Alamdanga Upazila in Chuadanga District. Salvage-1526030.00 | KDRIDP/Chua/W-32/2017-18 | 3.067 | 0 | 0 | 204.45 | 2018-02-28 | RAB-RC (PVT) Limited-MS Shahana Construction Md. Mejanur Rahman | 2018-04-15 | 184 | 100% | 2019-01-16 | 183.98 | 183.98 | 0 | 99.99% | Final
4 | 218073007-Belgachi UP-Ghosbiala Hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 218073015-(A) Improvement of Belgachi UP-Jehala UP road Ch 2100m-5260m (B) Construction of 2Nos 2.00mx2.00m RCC Box Culvert at Ch 2604 & 4425m (C) Construction of 1No 1.00mx1.00m RCC Box Culvert at Ch 3644m D Construction of 11 nos 0.600mx0.625m U-Type Drain Culvert at Ch2300m, 2410m, 2624m, 2742m, 2975m, 3530m, 3612m, 3826m, 4332m, 4666m & 5240m. Salvage Amount TK.740657.00 | KDRIDP/Chua/W-35/2017-18 | 3.16 | 0 | 0 | 230.507 | 2018-05-10 | Md. Shamshodwha Mallick | 2018-07-23 | 194.994 | 60% | 2019-11-30 | 0 | 106.877 | -106.877 | 54.81% | 0
6 | 218073017-(A) Improvement of Ailhas UP-Loxmipur Hat road Ch 750m-2650m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 2468m (C) Construction of 7 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1275m, 1522m, 1633m, 1923m, 2000m, 2108m & 2635m on The same road | KDRIDP/Chua/W-36/2017-18 | 1.9 | 0 | 0 | 131.037 | 2018-05-07 | Md. Afzalul Haque | 2018-06-12 | 124.48 | 100% | 2019-05-28 | 124.467 | 124.467 | 0 | 99.99% | Final
7 | 218073025-(a) Improvement of Jehala UP-Kumari UP road by BC Ch 2250-2484m 2934-3540m 3650-4675m5208-7383m 7583-7977m and 8727-9111m (b) Construction of 12 nos 625x600mm U-Type Drian Culvert at Ch 3268 3379 3418 3828 3888 3936 6025 6170 6230 6375 6705 and 8834m on same road. Salvage Amount TK 904869.00 | KDRIDP/Chua/W-04/2016-17 | 4.818 | 0 | 0 | 295.3 | 2017-05-15 | M/S Saiful Hasan Joarder | 2017-06-04 | 295.16 | 100% | 2018-04-07 | 295.136 | 295.136 | 0 | 99.99% | Final
8 | 218073028-Part-A.1 Improvement of Alamdanga-Nagdah UP Office via Damas Kedernagar Road Ch 1573-4755m & Ch 5535-7512m Part-A.2 Construction of 2nos Size 1.00x1.00m Box Culvert at Ch 2098 & 4104m Part-A.3 Construction of 11nos Size 0.600mx0.625m U-Type Drain Culvert at Ch 1588m 1969m 2520m 2850m 4650m 5233m 5339m 5837m 5954m 6110m & 6318m on The same road. Salvage Amount TK.2328406.00. | KDRIDP/Chua/W-42/2017-18 | 5.159 | 0 | 0 | 328.115 | 2018-05-28 | M/S MM & SD JV | 2018-07-23 | 280.909 | 25% | 2019-07-26 | 0 | 56.591 | -56.591 | 20.15% | 0
9 | 218073021-Bhangabaria UP-Bogadi hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
10 | 218074004-Improvement of Faridpur-Damos road by BC at Ch: 00-3060m. Salvage Amount TK. 544625.00. | KDRIDP/Chua/W-44/2017-18 | 3.06 | 0 | 0 | 199.799 | 2018-07-05 | Md. Sirazul Islam | 2018-08-02 | 189.809 | 100% | 2019-07-07 | 189.655 | 189.655 | 0 | 99.92% | Final
11 | 218074010-Ailhas - Sonatonpur Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 218074022-Potimari Bottala - Belgech UP via Kadarnagar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
13 | 218075016-(a) Improvement of MochaiNagar-Shalikha Ch - 00m -1244m & 2200-3290m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 235, 273, 2225, 2311, 2700 & 2936 m. Salvage-4194651.00 | KDRIDP/Chua/W-33/2017-18 | 2.334 | 0 | 0 | 181.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 163.725 | 60% | 2019-04-04 | 0 | 94.077 | -94.077 | 57.46% | 0
14 | 218075027-(A) Improvement of Shampur bridge-Alamdanga Rail gate road Ch 1140-3370m ( B) Construction of 1No 2.00mx2.00m RCC Box Culvert at Ch 275m ( C) Construction of 6 nos 0.600mx0.625m U-Type Drain Culvert at Ch 1990m, 2028m, 2182m, 2672m, 2790m & 3068m. Salvage Amount TK.515428.00. | KDRIDP/Chua/W-34/2017-18 | 2.23 | 0 | 0 | 138.98 | 2018-05-07 | R.F.M Construction | 2018-06-07 | 132.03 | 40% | 2019-05-17 | 0 | 24.418 | -24.418 | 18.49% | 0
15 | 218075030-Pardurgapur-Digholdanga Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
16 | 218075031-(a) Improvement of Kachikata Bridge-Baradi road Ch - 500m -2635m (b) Construction of 4 nos 600x625mm U-Type Drian Culvert at Ch 547, 1048, 1342m & 2112m. Salvage-23000.00 | KDRIDP/Chua/W-30/2017-18 | 2.135 | 0 | 0 | 134.19 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 120.77 | 100% | 2019-03-27 | 120.54 | 120.54 | 0 | 99.81% | Final
17 | 218075070-Improvement of Paikpara Math road by BC at Ch 1300-2000m | KDRIDP/Chua/W-45/2017-18 | 0.7 | 0 | 0 | 47.61 | 2018-07-05 | M/S Hashina and Sons | 2018-08-13 | 45.23 | 15% | 2019-08-18 | 0 | 0 | 0 | 0% | 0
| 218075186-Improvement of Par Laximpur-Kodamtola Allas Bazar road by BC at Ch 00-1174m. |  | 1.174 | 0 | 0 | 77.42 |  |  |  | 73.55 |  |  | 0 | 0 | 0 | 0% | 0
18 | 218075155-(Part-A1) Improvement of Jehala UP-Munshigonj Poshu Hat via Gorgori Asrayon road by BC at Ch 1210m-2449m & 3145m-4290m (Part-A2) Construction of 4nos (Size 0.600mx0.625m) U-Type Drain Culvert at Ch 1300m, 1418m, 1792m, & 3555m on The same road. (Salvage Amount :TK.27,25,611.00) | KDRIDP/Chua/W-46/2018-19 | 2.384 | 0 | 0 | 179.527 | 2018-11-20 | Liton Traders | 2019-01-21 | 179.47 | 0% | 2020-01-27 | 0 | 0 | 0 | 0% | 0
| 218075032-(Part-B-1) Improvement of Madarhuda-Tamaltala-Jehala UP road by BC at Ch 00m-1374m (Part-B2) Construction of 5nos (Size 0.600mx0.625m) U-Type Drain Culvert at Ch 41m, 506m, 618m, 954m, & 1119m on The same road. (Salvage Amount: TK. 4,86,687.00) |  | 1.374 | 0 | 0 | 94.61 |  |  |  | 94.58 |  |  | 0 | 0 | 0 | 0%
19 | 218075201-(Part-A) Improvement of Chitlamore road-Panchkomlapur road via Aliatnagar road At (Ch 1185-1930m) (Part-B) Construction of 3nos Size 0.600mx0.625m U-Type Drain Culvert at Ch 1745m, 1870m & 1920m on same road. | KDRIDP/Chua/W-43/2017-18 | 0.745 | 0 | 0 | 49.208 | 2018-05-28 | Md. Mozaharul Haque Mollick | 2018-07-08 | 46.748 | 100% | 2019-04-12 | 46.748 | 46.748 | 0 | 100% | Final
20 | 218075213-(a) Improvement of Jehala Mohon Master house - Matpara Mosque - Gorchapra Shaid Mamber houseroad Ch - 120m -1450m (b) Construction of 6 nos 600x625mm U-Type Drian Culvert at Ch 250, 488, 810, 1061, 1130 & 1227m same road under Alamdanga Upazila in Chuadanga District. Salvage-299944.00 | KDRIDP/Chua/W-31/2017-18 | 1.33 | 0 | 0 | 88.85 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-03 | 79.968 | 100% | 2019-03-27 | 79.968 | 79.968 | 0 | 100% | Final
Improvement of Village Road by HBB
21 | 218075047-Bokshipur-Bhodhua Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 218075147-Boksipur Moor-Maju Bridge via Modhppur Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
23 | 218073033-Construction of 84.00m long PC girder bridge on bhangbaria UP office to udaypurhat via bhshbaria road at ch 400.00m | KDRIDP/CHUA/B-02/2018-19 | 0 | 84 | 0 | 437.705 | 2018-11-27 | Md. Shamshodwha Mallick | 2019-02-12 | 359.595 | 5% | 2020-07-27 | 0 | 0 | 0 | 0% | 0
24 | 218073018-Construction of 75.00m long PC girder bridge on gangni UP to baradi UP road at ch 4300.00m | KDRIDP/CHUA/B-01/2018-19 | 0 | 75 | 0 | 395.27 | 2018-11-27 | Md. Shamshodwha Mallick | 2019-02-12 | 351.358 | 0% | 2020-07-27 | 0 | 0 | 0 | 0% | 0
Maintenance
25 | 218072012-Periodic Maintenance of Munshigonj-Asmankhali GC road at ch-3730-8756 m | KDRIDP/CHUA/M-26/2018-19 | 5.026 | 0 | 0 | 112.106 | 2018-11-29 | M/S Sirishti International | 2019-01-15 | 106.5 | 0% | 2019-07-20 | 0 | 0 | 0 | 0% | 0
26 | 218073007-Belgachi UP-Ghosbiala hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
27 | 218073010-Baradi UP-Natidangahat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
28 | 218073028-Alamdanga-Nagdah UP Office via Damas, Kedernagar Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
29 | 218074010-Periodic Maintenance of Nagdah Sonatonpur road Ch. 00m-1250m | KDRIDP/Chua/M-03/2017-18 | 1.25 | 0 | 0 | 20.465 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.42 | 100% | 2018-08-29 | 18.42 | 18.42 | 0 | 100% | Final
30 | 218074012-Periodic Maintenance of Paikpara-Sreerampur Road at Ch 00-1500m | KDRIDP/Chua/M-25/2018-19 | 1.5 | 0 | 0 | 34.648 | 2018-11-08 | Md. Rawshan Alam | 2019-01-08 | 32.916 | 100% | 2019-07-17 | 0 | 32.9 | -32.9 | 99.95% | Final
| 218075016-Periodic Maintenance of MochaiNagar-Shalikha Road at Ch 1244-1971m |  | 0.727 | 0 | 0 | 28.194 |  |  |  | 26.784 |  |  | 0 | 26.77 | -26.77 | 99.95%
31 | 218074013-Periodic Maintenance of Hakimpur-Toirbila road Ch. 00m-2550m | KDRIDP/Chua/M-04/2017-18 | 2.55 | 0 | 0 | 51.905 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 46.71 | 100% | 2018-08-29 | 46.699 | 46.7 | -0.001 | 99.98% | Final
32 | 218074017-Periodic Maintenance of Bademaju-Binadpur R&H road Ch. 00m-1120m. | KDRIDP/Chua/M-05/2017-18 | 1.12 | 0 | 0 | 29.776 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 26.8 | 100% | 2018-08-29 | 26.793 | 26.793 | 0 | 99.97% | Final
33 | 218074019-Periodic Maintenance of Kayradanga FRB-Gokulkhali GC road. Ch 00m-2040m | KDRIDP/Chua/M-01/2017-18 | 2.04 | 0 | 0 | 25.43 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 22.89 | 100% | 2018-08-29 | 22.87 | 22.87 | 0 | 99.91% | Final
34 | 218074026-Periodic Maintenance of Gobindhopur-Kashipur via Faridpur road Ch. 00m-1700m. | KDRIDP/Chua/M-06/2017-18 | 1.7 | 0 | 0 | 38.76 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 34.89 | 100% | 2018-10-05 | 34.879 | 34.879 | 0 | 99.97% | Final
35 | 218074029-Periodic Maintenance of Ruhitanpur Hat-Kulpala Ch. 00m-2720m | KDRIDP/Chua/M-02/2017-18 | 2.72 | 0 | 0 | 47.07 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 42.37 | 100% | 2018-08-29 | 42.358 | 42.358 | 0 | 99.97% | Final
GC-Hat
36 | Construction of Hardi Market Growth Center | KDRIDP/Chua/GC-22/2017-18 | 0 | 0 | 1 | 20.8 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.78 | 100% | 2018-12-24 | 0 | 13.916 | -13.916 | 66.97% | 0
Landing/ Riverghat
37 | RCC Ghatla at Kumar River | KDRIDP/Khul/ G-16/2017-18 | 0 | 0 | 1 | 30.28 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 30.267 | 100% | 2018-12-24 | 30.205 | 30.205 | 0 | 99.8% | Final
Tree Plantation
38 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 56.943 | 159 | 2 | 3855.982 |  |  |  | 3527.733 | 50.13% |  | 1464.621 | 1820.171 | -355.55 | 51.6%

## Damurhuda
Damurhuda
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 218312008-Improvement of Damurhuda GC-Golaidari RHD road Ch 7850-9360m. | KDRIDP/Chua/W-25/2016-17 | 1.51 | 0 | 0 | 100.92 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 90.83 | 100% | 2018-07-11 | 90.823 | 90.823 | 0 | 99.99% | Final
2 | 218312006-Improvement of Memnagar RHD-Karpashdanga G.C via Buichitala Ch 16670-17800m. Salvage Amount TK. 31050.00 | KDRIDP/Chua/W-24/2016-17 | 1.13 | 0 | 0 | 80.18 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 72.164 | 100% | 2018-07-11 | 72.162 | 72.162 | 0 | 100% | Final
Improvement of Union Road by BC
3 | 218313002-Gobindahuda Hat-Karpasdanga UP Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
4 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC (Ch 12257-13600m). Salvage Amount TK 24740.00 | KDRIDP/Chua/W-10/2016-17 | 1.343 | 0 | 0 | 67.49 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 67.56 | 100% | 2018-09-23 | 67.317 | 67.317 | 0 | 99.64% | Final
5 | 218313003-Improvement of Juranpur UP-Laxmipur Hat road by BC Ch 10957-12257m. | KDRIDP/Chua/W-12/2016-17 | 1.3 | 0 | 0 | 71.36 | 2017-05-22 | Toma Construction & Co. Limited | 2017-07-09 | 64.22 | 100% | 2018-09-20 | 64.22 | 64.22 | 0 | 100% | Final
6 | 218313004-Parkrisnopur Madna UP-Kuralgachhi UP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
6 | 218314012-a) Improvement of Kushaghata R&H-Purapara road Ch 514-1120m (b) Construction of 2 nos Pipe Culvert at Ch 915 & 1100m. Salvage Amount TK. 160525.00 | KDRIDP/Chua/W-26/2016-17 | 0.606 | 0 | 0 | 33.54 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 30.18 | 100% | 2018-07-11 | 30.175 | 30.175 | 0 | 99.98% | Final
7 | 218314016-Improvement of Dugdugi Family Planing Center-Gobindapur road by BC Ch 00-1640 & 3273-3333m. Salvage Amount TK 209026.00 | KDRIDP/Chua/W-11/2016-17 | 1.7 | 0 | 0 | 93.49 | 2017-05-22 | Jahirul Limited | 2017-07-09 | 84.14 | 100% | 2018-04-11 | 84.14 | 84.14 | 0 | 100% | Final
8 | 218314017-Hawli Eidgah-Shaikpara R&H Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
9 | 218314019-Javrampur Battala Parimary School -Uktya Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 218314032-Parkisnopur-Jhajadanga Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218314040-Improvement of Pirpur Kullah-Shihnagar via Boyra road by BC at Ch 3700m-6170m. Part-A2 Construction of 7nos U-Type Drain Culvert at Ch 4230m 4443m 4640m 4777m 4937m 5057m & 5520m on The same road. Salvage Amount TK.783608.00 | KDRIDP/Chua/W-47/2018-19 | 2.47 | 0 | 0 | 187.41 | 2018-11-20 | M/s Madani Enterprise | 2019-01-24 | 187.38 | 70% | 2020-01-30 | 0 | 104.752 | -104.752 | 55.9% | 0
| 218314006-Improvement of Jhoragacha-Kalabaria road by BC at Ch 00m-1950m Part-B2 Construction of 6nos U-Type Drain Culvert at Ch 948m 1077m 1107m 1200m 1549m & 1906m on The same road. Salvage Amount TK.932751.00 | KDRIDP/Chua/W-47/2018-19 | 1.95 | 0 | 0 | 147.169 | 0 | M/s Madani Enterprise | 0 | 147.147 | 0% | 0 | 0 | 82.272 | -82.272 | 55.91% | 0
12 | 218314053-(a) Improvement of Chandra FRB-Kanidanga road by BC Ch 4733-6233m (b) Construction of 2 nos U-Tyup Drain Culvert at Ch 5922 & 5788m | KDRIDP/Chua/W-09/2016-17 | 1.5 | 0 | 0 | 84.25 | 2017-05-22 | Md. Shamshodwha Malick | 2017-07-09 | 75.83 | 100% | 2018-11-30 | 75.816 | 75.816 | 0 | 99.98% | Final
13 | 218314054-Jhapjhapi bridge-Hogoldanga FRB Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by HBB
14 | 248314073-Chandrabass-Satiantala Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
15 | 248315080-Laxmipur Hat Mosque Kana Pukorlkor via Dhakian para Graveyard Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Construction of Bridge on Union Road/Village Road (5.50m width)
16 | 218313009-Const. of RCC Bridge on Par Damurhdua to Karpasdanga UP Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
17 | 218314059-Const. of RCC Bridge on Kanaidanga FRB-Kunia Ferryghat Road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Maintenance
18 | 218312014-Darsana GC- Madna-Sada bari -Pirpukullah -Karpashdanga GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 218314002-Periodic Maintenance of Gopalpur Primary School-Daliarpur Road Ch. 00m-1095m. | KDRIDP/Chua/M-12/2017-18 | 1.095 | 0 | 0 | 18.23 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 16.41 | 100% | 2018-08-29 | 16.41 | 16.41 | 0 | 100% | Final
20 | 218314002-Periodic Maintenance of Gopalpur Prymary School-Daliarpur Road at Ch 1095-2023m | KDRIDP/Chua/M-21/2018-19 | 0.928 | 0 | 0 | 17.387 | 2018-11-08 | Md.Anwar Hossain | 2019-01-08 | 16.518 | 100% | 2019-07-13 | 16.48 | 16.48 | 0 | 99.77% | Final
| 218314019-Periodic Maintenance of Jayrampur Battala School-Uktya Road at Ch 1740-4345m |  | 2.605 | 0 | 0 | 78.269 |  |  |  | 74.356 |  |  | 74.15 | 74.15 | 0 | 99.72%
21 | 218314015-Loknathpur R&H-Darsona Dingadah Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
22 | 218314019-Periodic Maintenance of Joyrampur Battala School-Uktya Road Ch. 00m-1740m | KDRIDP/Chua/M-13/2017-18 | 1.74 | 0 | 0 | 31.676 | 2017-12-27 | Liton Traders | 2018-02-19 | 28.51 | 100% | 2018-08-29 | 28.51 | 28.51 | 0 | 100% | Final
23 | 218314033-Periodic Maintenance of Modna-Hoybadpur more Road Ch. 00m-900m | KDRIDP/Chua/M-14/2017-18 | 0.9 | 0 | 0 | 14.825 | 2017-12-27 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 13.34 | 100% | 2018-08-29 | 13.34 | 13.34 | 0 | 100% | Final
24 | 218314045-Damurhuda Brac more-Upazila more Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
25 | 218314049-Periodic Maintenance of Baroboldia Bazar-Chindipur via Sarabaria Road Ch. 3380m-5125m. | KDRIDP/Chua/M-15/2017-18 | 1.745 | 0 | 0 | 28.15 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 25.34 | 100% | 2018-08-29 | 25.337 | 25.34 | -0.003 | 100% | Final
26 | 218314071-Periodic Maintenance of Talsari R&H-Horirampur Road Ch. 1120m-2690m. | KDRIDP/Chua/M-16/2017-18 | 1.57 | 0 | 0 | 20.11 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 18.1 | 100% | 2018-08-29 | 18.086 | 18.09 | -0.004 | 99.94% | Final
27 | 218314084-Periodic Maintenance of Buinchatala Tematha-Aramdanga via Thakurpur Road Part-A Ch. 00m-1940m & Part-B Ch. 8840-1189m | KDRIDP/Chua/M-17/2017-18 | 4.99 | 0 | 0 | 113.27 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 101.95 | 100% | 2018-08-29 | 101.934 | 101.934 | 0 | 99.98% | Final
Tree Plantation
28 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 29.082 | 0 | 0 | 1187.726 |  |  |  | 1113.975 | 49% |  | 778.9 | 965.931 | -187.031 | 86.71%

## Jibonnagar
Jibonnagar
SL | Road ID & Scheme | Package No. | Estimated Amount |  |  |  | Tender Receiving Date | Name of Contractor | Date of Contract | Contract Amount (Tk. In Lakh) | Physical Progress (%) | Planned/Actual Date of Completion | Payment Status |  |  | Financial Progress (%) | Remarks
|  |  | Length |  |  | Amount (Tk. in Lakh) | [6 empty] | Final Bill (Tk in Lakh) | Payment Made (Tk in Lakh) | Remaining Payment (Tk. in Lakh)
|  |  | km | m | Nos
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Improvement of Upazila Road by BC
1 | 218552009-a) Improvement of Uthali R&H Mollabari-Uthali GC road Ch 00-1140m (b) Construction of 1 nos U-Type Drain Culvert size 625x600mm at Ch 40.00m on same road under Jibannagar Upazila in Chuadanga District Salvage Amount TK. 1723642.00 | KDRIDP/Chua/W-18/2016-17 | 1.14 | 0 | 0 | 82.45 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 74.2 | 100% | 2018-06-19 | 74.13 | 74.13 | 0 | 99.91% | Final
Improvement of Union Road by BC
2 | 218553001-Jibannagar-Shimanta UP-Benipur Hat road. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
3 | 218553004-Improvement of Shimanta UP-Goyespur-Dhopakhali Hat road Ch 5510-7960m. Salvage Amount TK. 537215.00 | KDRIDP/Chua/W-22/2016-17 | 2.45 | 0 | 0 | 134.99 | 2017-08-24 | RAB-RC (PVT) Limited | 2017-10-09 | 121.49 | 100% | 2018-07-05 | 121.49 | 121.49 | 0 | 100% | Final
4 | 218553007-Barbhanga R&H-Sutiahat-Hashadah UP Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
5 | 218553008-Shimanto UP- Goyespur-Dhapakhalihat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
6 | 218553009-Simanto UP-Korotoya-Horihornagar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
7 | 218553013-Raypur UP-Khalispur GC Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Improvement of Village Road by BC
9 | 218554001-Purandupur - Nischatapur Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
10 | 218554002-Panarasoti Bhanga Bridge-Tarinibash Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
11 | 218554004-Narayanpur-Gangadaspur Rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
12 | 218554012-a) Improvement of Krishnopur more-Maerudah hat-Shebkhali road Ch 2420-3220m (b) Construction of 1 no RCC Box Culvert size 2.00x2.60m at Ch 2713m (c) Construction of 2 Nos U Type Drain Culvert size 625 x 600 m at Ch 2600 and 2947m. Salvage Amount TK. 597943.00 | KDRIDP/Chua/W-23/2016-17 | 0.8 | 0 | 0 | 57.51 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 51.76 | 100% | 2018-08-31 | 51.65 | 51.65 | 0 | 99.79% | Final
13 | 218554014-Balihuda-Natun Chakla Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
14 | 218554017-a) Improvement of Tutulia BGB camp-Rakhal Shah Mazar road Ch 1800-4150m (b) Construction of 3 nos U-Drain Culvert at Ch 2730, 3300 & 3400m. Salvage Amount TK. 560988.00 | KDRIDP/Chua/W-19/2016-17 | 2.35 | 0 | 0 | 133.02 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 119.72 | 100% | 2018-11-28 | 119.718 | 119.718 | 0 | 100% | Final
15 | 218554023 a) Improvement of Muktarpur-Shahebkhali road via Katapol Chakla road Ch 2050-3810m (b) Construction of 1 no U-Type Drain Culvert size 625x600mm at Ch 3271m. Salvage Amount TK.106683.00 | KDRIDP/Chua/W-21/2016-17 | 1.76 | 0 | 0 | 97.48 | 2017-08-24 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2017-10-15 | 87.73 | 100% | 2018-07-11 | 87.72 | 87.72 | 0 | 99.99% | Final
16 | 218554023 Part-A Improvement of Muktarpur-Shahebkhali road via Katapol Chakla road by BC at Ch 00-1400m Part-B Construction of 4nos Size 0.625mx0.600m U-Type Drain Culvert at Ch 52, 984, 1155 & 1370m | KDRIDP/Chua/W-48/2018-19 | 1.4 | 0 | 0 | 105.83 | 2019-03-04 | Md. Alauddin | 2019-04-09 | 100.538 | 0% | 2020-01-09 | 0 | 0 | 0 | 0% | 0
17 | 218554031- A) Improvement of Goyespur-BGB Camp-Changkhali road Ch 4140-6542m B) Construction of 4 nos U-Type Drain Culvert at Ch 4150, 4650,5800 & 6310 m. Salvage Amount TK.142098.00 | KDRIDP/Chua/W-29/2017-18 | 2.402 | 0 | 0 | 150.92 | 2018-02-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-05-17 | 135.83 | 60% | 2019-04-12 | 0 | 73.153 | -73.153 | 53.86% | 0
18 | 218554035-Sontoshpur R&H-Rajapur UZR Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
19 | 218554037-Improvement of Daulatgong GC-Benipur hat road at ch 6140-8900m. Salvage Amount TK. 280855.00 | KDRIDP/Chua/W-20/2016-17 | 2.76 | 0 | 0 | 151.79 | 2017-07-25 | M/S. JAKAULLAH & BROTHERS | 2017-08-27 | 136.608 | 100% | 2018-06-02 | 136.608 | 136.608 | 0 | 100% | Final
20 | 218554050-a) Improvement of Uthali R&H-Dhopakhali Hat road Ch 1425-3981m (b) Construction of 2 nos 1.00x1.60m Box Culvert at CH 2359 and 3085m (c) Construction of 1 No U-Drain Culvert at Ch 2001m. Salvage Amount TK. 2029785.00 | KDRIDP/Chua/W-17/2016-17 | 2.556 | 0 | 0 | 150.77 | 2017-07-25 | Jahirul Limited | 2017-09-12 | 135.687 | 100% | 2018-09-18 | 135.687 | 135.687 | 0 | 100% | Final
21 | 218554050- Improvement of Uthali R&H Dhopakhali Hat road by BC at Ch 3981-4606m | KDRIDP/Chua/W-49/2018-19 | 0.625 | 0 | 0 | 44.478 | 2019-03-04 | M/S Shekh Traders | 2019-04-01 | 42.25 | 70% | 2020-01-01 | 0 | 24.34 | -24.34 | 57.61% | 0
| 218554078- Improvement of Andulbaria UP-Begumpur Hat road by BC at Ch 00-750m |  | 0.75 | 0 | 0 | 55.18 |  |  |  | 52.42 |  |  | 0 | 30.2 | -30.2 | 57.61%
22 | 218555003-A) Improvement of Annantopur Mosque-Mondertola road Ch 00m-1150m B) Construction of 2 nos U-Type Drain Culvert size 600x625mm at Ch 3.00 & 295m. Salvage Amount TK.333332.00 | KDRIDP/Chua/W-28/2017-18 | 1.15 | 0 | 0 | 77.885 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 70.1 | 100% | 2018-10-07 | 0 | 58.116 | -58.116 | 82.9% | 0
Maintenance
23 | 218553010-Andulbaria UP - Grisnagar Bazar Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
24 | 218554043-Periodic Maintenance of Balihuda UZR-Raypur Bazar Road Ch. 00m-2400m | KDRIDP/Chua/M-20/2017-18 | 2.4 | 0 | 0 | 38.87 | 2017-12-28 | M/S. Khandaker Shahin Ahmed | 2018-02-20 | 34.98 | 100% | 2018-09-04 | 34.951 | 34.951 | 0 | 99.92% | Final
25 | 218554047-Bokundia R&H - Minajpur hat Rd. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
26 | 218554054-Periodic Maintenance of Piaratala R&H-Kasipur Hat Road Ch. 00m-6420m. | KDRIDP/Chua/M-18/2017-18 | 6.42 | 0 | 0 | 92.81 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 83.53 | 100% | 2018-08-29 | 83.498 | 83.498 | 0 | 99.96% | Final
27 | 218554058-Periodic Maintenance of Hasadah UP-Dattanagar (Banka UP- Dattanagar) Bazar. Road at Ch 2000-5700m | KDRIDP/Chua/M-24/2018-19 | 3.7 | 0 | 0 | 137.047 | 2018-11-08 | M/S Shopno Construction | 2019-01-01 | 130.195 | 100% | 2019-07-06 | 0 | 128.7 | -128.7 | 98.85% | 0
28 | 218554062-Periodic Maintenance of Uthali UZR-Uthali GC road at Ch 00-780m | KDRIDP/Chua/M-22/2018-19 | 0.78 | 0 | 0 | 17.878 | 2018-11-08 | RELATION ARCHITECT HOME | 2019-01-08 | 16.984 | 100% | 2019-07-13 | 16.981 | 16.981 | 0 | 99.98% | Final
29 | 218554068-Periodic Maintenance of Anantapur UZR-Pankahat Road Ch. 00m-3310m | KDRIDP/Chua/M-19/2017-18 | 3.31 | 0 | 0 | 58.35 | 2017-12-28 | MOZAHAR ENTERPRISE (PVT.) LTD. | 2018-02-19 | 52.52 | 100% | 2018-08-29 | 52.463 | 52.463 | 0 | 99.89% | Final
GC-Hat
30 | Construction of Raypur Market Growth Center | KDRIDP/Chua/GC-23/2017-18 | 0 | 0 | 1 | 20.07 | 2018-02-19 | M/S Jakaullah & Brothers | 2018-03-20 | 20.05 | 100% | 2018-12-28 | 19.997 | 19.997 | 0 | 99.74% | Final
Tree Plantation
31 | Tree Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | #DIV/0! | 0
Total |  |  | 36.753 | 0 | 1 | 1607.328 |  |  |  | 1466.592 | 51% |  | 934.893 | 1249.402 | -314.509 | 85.19%

## Summary
CHUADANGA
Component | No. of Packages Approved | No. of Packages Contract | Length |  |  | Contract Amount (Tk. in Lakh) | Fund Spent (Tk. in Lakh) | Average Physical Progress (%) | Financial Progress (%) | Remarks
|  |  | km | m | Nos
Upazila Road by BC | 4 | 4 | 6.52 | 0 | 0 | 439.224 | 439.018 | 100% | 99.95%
Union Road by BC | 10 | 10 | 28.345 | 0 | 0 | 1637.143 | 1210.156 | 85.5% | 73.92%
Village Road by BC | 34 | 33 | 62.51 | 0 | 0 | 3773.647 | 2685.159 | 82.65% | 71.16%
Village Road by HBB |  |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Bridge on Upazila Road | [9 empty] | N/A
Bridge on Union Road/Village Road | 2 | 2 | 0 | 159 | 0 | 710.953 | 0 | 2.5% | 0%
Maintenance | 25 | 25 | 70.841 | 0 | 0 | 1331.712 | 1135.454 | 94.23% | 85.26%
GC-Hat | 2 | 2 | 0 | 0 | 2 | 40.83 | 33.913 | 100% | 83.06%
Landing/ Riverghat | 1 | 1 | 0 | 0 | 1 | 30.267 | 30.205 | 100% | 99.8%
Tree Plantation | 0 |  | 0 | 0 | 0 | 0 | 0 | 0% | #DIV/0!
Total | 78 | 77 | 168.216 | 159 | 3 | 7963.776 | 5533.905 | 62.76% | 69.49%