## DPP Bandarban scheme list
Proposed Roads & Structures
Name of The Project : Rural Infrastructure Development Project: Chittagong Hill Tracts- 2nd Phase
District : Bandarban
Sl No | Upazila | Name of the Road and proposed chainage | ID No | Nature of works | Total Road length |  |  | Already completed length |  |  | Unit Cost |  |  | Proposed Length |  |  | Estimated Cost (Tk.in Lakh) | Remaining length to be developed |  |  | Remarks
[5 empty] | Road (Km) | Bridge (m) | Culverts (m) | Road (Km) | Bridge (m) | Culverts (m) | Road (Km) | Bridge (m) | Culverts (m) | Road (Km) | Bridge (m) | Culverts (m) |  | Road (Km) | Bridge (m) | Culverts (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road.(Ch.2950-7060m) | 403143002 | BC | 10.12 | 111.6 | 51.81 | 2.95 | 71.6 | 51.81 | 105 | 6.5 | 4.5 | 4.11 | 0 | 0 | 431.55 | 3.06 | 40 | 0
2 |  | Holudia-Vaggakul-Tankbati Road.(Ch.00-3350m) | 403143005 | BC | 27.15 | 108 | 207.85 | 6.15 | 90 | 194.35 | 105 | 6.5 | 4.5 | 3.35 | 48 | 0 | 663.75 | 17.65 | -30 | 13.5
Sadar Sub-Total (UNR) | [13 empty] | 7.46 | 48 | 0 | 1095.3 | 20.71 | 10 | 13.5
3 | Lama | Lama muk-Selertua road Ch.00-3300m | 403513007 | HBB | 8.72 | 140 | 28.8 | 0 | 13 | 0 | 84 | 6.5 | 4.5 | 3.3 | 0 | 22.85 | 380.025 | 5.42 | 127 | 5.95
4 |  | Shelertua-Rupashi Para Road Ch.00-1650m | 403513010 | HBB | 5.1 | 126.1 | 28.5 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 1.65 | 30 | 21.7 | 431.25 | 3.45 | 96.1 | 6.8
Lama Sub-Total (UNR) | [13 empty] | 4.95 | 30 | 44.55 | 811.275 | 8.87 | 223.1 | 12.75
5 | Ruma | Thana HQ (Ruma Mukh)-Gallanga UP office Road(Ch.00-1230m) | 403913003 | BC | 22 | 604.4 | 197 | 0 | 12.4 | 21.8 | 105 | 6.5 | 4.5 | 1.23 | 152 | 40 | 1297.15 | 20.77 | 440 | 135.2 | Not a Single Bridge
Ruma Sub-Total (UNR) | [13 empty] | 1.23 | 152 | 40 | 1297.15 | 20.77 | 440 | 135.2
6 | Thanchi | Thanchi-Balipara road.(Ch.1000-6200m) | 403952001 | BC | 12.17 | 450 | 12.5 | 1 | 31.95 | 6.5 | 135 | 6.5 | 4.5 | 5.2 | 76 | 0 | 1196 | 5.97 | 342.05 | 6
Thanchi Sub-Total (UZR) | [13 empty] | 5.2 | 76 | 0 | 1196 | 5.97 | 342.05 | 6
7 | Alikadam | Alikadam Bazar- Naikhongchari Border via Rombow road. (Ch.00-2880m) | 403042002 | BC | 2.88 | 94 | 15 | 0 | 14 | 5 | 135 | 6.5 | 4.5 | 2.88 | 80 | 10 | 953.8 | 0 | 0 | 0
Alikadam Sub-Total (UZR) | [13 empty] | 2.88 | 80 | 10 | 953.8 | 0 | 0 | 0
8 | Alikadam | Alikadam-Dochori Road (ch.00-2000m) | 403043004 | BC | 14 | 56 | 41 | 9.5 | 56 | 41 | 105 | 6.5 | 4.5 | 2 | 0 | 0 | 210 | 2.5 | 0 | 0
9 |  | Sonaichori R&H-Varirmukh Road.(Ch.821-1571m) | 403043005 | BC | 3 | 0 | 9 | 0.821 | 0 | 9 | 105 | 6.5 | 4.5 | 0.75 | 0 | 1 | 83.25 | 1.429 | 0 | -1
10 |  | Chikkan para (cioni para) road (Ch.1441-2191m) | 403043006 | BC | 3 | 24 | 9 | 1.44 | 24 | 4 | 105 | 6.5 | 4.5 | 0.75 | 0 | 1 | 83.25 | 0.81 | 0 | 4
11 |  | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 00-2600m) | 403043007 | BC | 2.6 | 70 | 11 | 0 | 0 | 9 | 105 | 6.5 | 4.5 | 2.6 | 70 | 2 | 737 | 0 | 0 | 0
Alikadam Sub-Total (UNR) | [13 empty] | 6.1 | 70 | 4 | 1113.5 | 4.739 | 0 | 3
12 | Rowangchari | Taracha up - Meufapara(Ruma Road - Tarasa UP Office Road) road.(Ch.4200-6500m) | 403893007 | HBB | 8.5 | 119 | 66.85 | 4.2 | 74 | 22.7 | 84 | 6.5 | 4.5 | 2.3 | 0 | 27 | 314.7 | 2 | 45 | 17.15
13 |  | Kalaghata to Taracha UP office road(Ch.00-3000m) | 403893004 | BC | 8.25 | 237 | 57.05 | 5 | 12 | 47.15 | 105 | 6.5 | 4.5 | 3 | 50 | 0 | 640 | 0.25 | 175 | 9.9
Rowangchari Sub-Total (UNR) | [13 empty] | 5.3 | 50 | 27 | 954.7 | 2.25 | 220 | 27.05
14 | Naikhonchari | Naikhongchari - Lemouchari road.(Ch.00-4000m) | 403733001 | BC | 10.4 | 0 | 24 | 0 | 0 | 9 | 105 | 6.5 | 4.5 | 4 | 0 | 0 | 420 | 6.4 | 0 | 15
15 |  | Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road.(Ch.00-3000m) | 403733002 | BC | 19 | 54 | 28 | 9 | 54 | 28 | 105 | 6.5 | 4.5 | 3 | 30 | 0 | 510 | 7 | -30 | 0
16 |  | North Ghumdum - Tumbru Bazar road.(Ch.1000-4000m) | 403733003 | BC | 7.78 | 77.5 | 36.4 | 1 | 14.5 | 16.4 | 105 | 6.5 | 4.5 | 3 | 20 | 0 | 445 | 3.78 | 43 | 20
17 |  | Dochori - Ali Kadam road.(Ch.00-3000m) | 403733004 | BC | 32 | 517 | 35.3 | 9 | 134 | 16.3 | 105 | 6.5 | 4.5 | 3 | 0 | 0 | 315 | 20 | 383 | 19
18 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.1600-9060m | 403733008 | HBB | 9 | 237 | 30.9 | 1.65 | 12 | 30.9 | 84 | 6.5 | 4.5 | 7.2414 | 220 | 0 | 2038.2776 | 0.1086 | 5 | 0 | At Ch.1650m Required-105m Bridge
Naikhongchari Sub-Total (UNR) | [13 empty] | 20.2414 | 270 | 0 | 3728.2776
|  | Total UZR | [11 empty] | 8.08 | 156 | 10 | 2149.8
|  | Total UNR | [11 empty] | 45.2814 | 620 | 115.55 | 9000.2026
Grand Total (UZR+UNR) | [13 empty] | 53.3614 | 776 | 125.55 | 11150.0026
[18 empty] | Road | Bridge | Culvet
[13 empty] | Road UZR cost |  |  |  |  | 1090.8 | 1014 | 45
3232.95
[13 empty] | Road UNR cost |  |  |  |  | 1217.2776 | 4030 | 519.975
[18 empty] | 5541.0276 | 5044 | 564.975 | 11150.0026

## DPP Khagrachari scheme list
Proposed Roads & Structure
Name of the Porject: Rural Intrastructure Development Project: Chittagong Hill Tracts-2nd Phase
District: Khagrachari
Sl. No. | Upazila | Name of the Road and Proposed Chainage | ID No | Nature of Works | Total Road Length |  |  | Already Completed Length |  |  | Unit Cost |  |  | Proposed Length |  |  | Estimated Cost (Tk. in Lakh) | Remaining Length to be development
[5 empty] | Road (km) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) |  | Road (km) | Bridge (m) | Culvert (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Bhaibonchara GC-Gumti GC via Chota Bari Para Road (Sadar Part) (Ch: 00-7000m). | 446492001 | BC | 7 | 150 | 0 | 0 | 150 | 0 | 135 | 6.5 | 4.5 | 7 | 0 | 0 | 945 | 0 | 0 | 0
2 | Sadar | Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road (Sadar Part) (Ch: 00-2940m). | 446492002 | BC | 16 | 31.1 | 0 | 0 | 11.1 | 0 | 135 | 6.5 | 4.5 | 2.94 | 20 | 0 | 526.9 | 13.06 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 9.94 | 20 | 0 | 1471.9
3 | Sadar | Golabari Union H/Q (Upper Perachara)-Pora Bazar via Bhuachari & Cristian Para Road (Ch: 4100-7040m). | 446493001 | BC | 11 | 102.36 | 0 | 4.1 | 102.36 | 0 | 105 | 6.5 | 4.5 | 2.9 | 0 | 0 | 304.5 | 4 | 0 | 0
4 | Sadar | Bichitola Bazar-Khagrachari Sadar HQ (Battali) Road (Ch: 1130-3130m). | 446493002 | BC | 8 | 88.7 | 0 | 1.13 | 78.7 | 0 | 105 | 6.5 | 4.5 | 2 | 10 | 0 | 275 | 4.87 | 0 | 0
|  | Sub: Total (UNR) | [11 empty] | 4.9 | 10 | 0 | 579.5
5 | Matiranga | BGumti GC-Bhibonchara GC Road. (Matiranga Part) (Ch: 00-2500m). | 446702002 | BC | 8.19 | 45 | 0 | 0 | 0 | 0 | 135 | 6.5 | 4.5 | 2.5 | 45 | 0 | 630 | 5.69 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 2.5 | 45 | 0 | 630
6 | Matiranga | Belchari Union H/Q-Ajuddah Bazar Road (Ch: 6480-7980m). | 446703004 | BC | 15 | 77.7 | 0 | 6.48 | 0 | 0 | 105 | 6.5 | 4.5 | 1.5 | 40 | 0 | 417.5 | 7.02 | 37.7 | 0
7 | Matiranga | Gumti UP Office-Bhibonchara GC via Tailafang & Gakulmani BDR Camp Road (Ch: 00-1500m). | 446703010 | BC | 8.57 | 10 | 0 | 0 | 0 | 0 | 105 | 6.5 | 4.5 | 1.5 | 0 | 0 | 157.5 | 7.07 | 10 | 0
8 | Matiranga | Gumti Bazar-Ramsharia Bazar Road (Ch: 4280-7280m). | 446703006 | BC | 7.28 | 0 | 0 | 4.28 | 0 | 0 | 105 | 6.5 | 4.5 | 3 | 0 | 0 | 315 | 0 | 0 | 0
|  | Sub: Total (UNR) | [11 empty] | 6 | 40 | 0 | 890
9 | Panchari | Panchari-Langadu Road. [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) (Ch: 3291-7292m). | 446772001 | BC | 15 | 138 | 54.07 | 3.29 | 102.07 | 39.7 | 135 | 6.5 | 4.5 | 4 | 0 | 15 | 607.5 | 7.71 | 35.93 | -0.63
10 | Panchari | Panchari GC-Bhaibonchara GC via Shantipur Road (Panchari Part) (Ch: 11058-12280m). | 446772003 | BC | 12.28 | 202 | 151.7 | 11.058 | 152 | 149.7 | 135 | 6.5 | 4.5 | 1.17 | 50 | 2 | 491.95 | 0.052 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 5.17 | 50 | 17 | 1099.45
11 | Panchari | Logong Union H/Q-Tanakkya Para Bazar Road (Panchari Part) (Ch.8500-12500m). | 446773001 | BC | 19 | 96 | 11 | 8.5 | 54 | 11 | 105 | 6.5 | 4.5 | 5 | 20 | 0 | 655 | 5.5 | 22 | 0
|  | Sub: Total (UNR) | [11 empty] | 5 | 20 | 0 | 655
12 | Mohalchari | Mahalchari GC-Maischari GC Road (Ch: 4118-6347m). | 446652001 | BC | 10.98 | 110.9 | 51.25 | 8.754 | 80.9 | 54.25 | 135 | 6.5 | 4.5 | 2.228 | 30 | 10 | 540.78 | -0.002 | 0 | -13
13 | Mohalchari | Maischari GC (Juramyachari)-Longadu GC Road (Mahalchari Part) (Ch: 2525-2950m & Ch: 3029-4817m). | 446652002 | BC | 15.5 | 139.5 | 20.6 | 2.604 | 100.5 | 20.6 | 135 | 6.5 | 4.5 | 2.2142 | 39 | 8 | 588.417 | 10.6818 | 0 | -8
14 | Mohalchari | Mahalchari GC (Singinala)-Khagrachari Sadar Upazila H/Q Road (Mahalchari Part) (Ch: 574-5574m). | 446652005 | BC | 12.85 | 52.52 | 23.3 | 1.284 | 42.52 | 23.3 | 135 | 6.5 | 4.5 | 5 | 10 | 20 | 830 | 6.566 | 0 | -20
|  | Sub: Total (UZR) | [11 empty] | 9.4422 | 79 | 38 | 1959.197
15 | Mohalchari | Sindukchari Union H/Q-Tinduck Chari Bazar Road (Ch: 1520-3520m). | 446653002 | BC | 10.86 | 0 | 0 | 1.52 | 0 | 0 | 105 | 6.5 | 4.5 | 2 | 0 | 0 | 210 | 7.34 | 0 | 0
|  | Sub: Total (UNR) | [11 empty] | 2 | 0 | 0 | 210
16 | Dighinala | Panchari-Langadu road. [Dighinala GC-Panchari GC Via Nunchari Road] (Dighinala Part) (Ch: 2320-4320m). | 446432001 | BC | 22.12 | 207.3 | 72.1 | 2.318 | 37.3 | 37.5 | 135 | 6.5 | 4.5 | 2 | 40 | 0 | 530 | 17.802 | 130 | 34.6
17 | Dighinala | Choto Merung Bazar R&H - Baghaichari Upazila HQ Road (Ch: 2600-4600m). | 446432003 | BC | 6.2 | 76.7 | 13.9 | 2.595 | 19.7 | 1.2 | 135 | 6.5 | 4.5 | 2 | 0 | 10 | 315 | 1.605 | 57 | 2.7
|  | Sub: Total (UZR) | [11 empty] | 4 | 40 | 10 | 845
18 | Dighinala | Babuchara Union HQ-Naraichari Bazar via Dhanpata Manorath Talukdar Para Road (Ch: 2685-4185m). | 446433003 | BC | 26.85 | 332.35 | 58.04 | 10.85 | 82.55 | 36.07 | 105 | 6.5 | 4.5 | 1.5 | 7 | 0 | 203 | 14.5 | 242.8 | 21.97
|  | Sub: Total (UNR) | [11 empty] | 1.5 | 7 | 0 | 203
19 | Ramghar | Sonaipul GC-Hayako GC via Khagrabill Road (Ramghar Part) (Ch: 13650-15000m). | 446802001 | BC | 15 | 22 | 22.7 | 13.65 | 22 | 22.7 | 135 | 6.5 | 4.5 | 1.35 | 0 | 0 | 182.25 | 0 | 0 | 0
20 | Ramghar | Khagrabill GC-Manikchari GC via Batnatali Bazar Road (Ramghar Part) (Ch: 2000-4650m). | 446802002 | BC | 7.8 | 13 | 21.05 | 2 | 13 | 21.05 | 135 | 6.5 | 4.5 | 2.65 | 0 | 0 | 357.75 | 3.15 | 0 | 0
|  | Sub: Total (UZR) | [11 empty] | 4 | 0 | 0 | 540
21 | Ramghar | Patachara Union H/Q-Guimara GC Road via Parshuramghat (Ramgarh Part) (Ch: 2000-4500m). | 446803002 | HBB | 6.25 | 0 | 17.82 | 2 | 0 | 17.82 | 84 | 6.5 | 4.5 | 2.5 | 0 | 7 | 241.5 | 1.75 | 0 | -7
|  | Sub: Total (UNR) | [11 empty] | 2.5 | 0 | 7 | 241.5
22 | Manikchari | Manikchari Union H/Q (Mohamuni)-Hatimura Bazar Road via Gaidhan (Ch: 520-3020m) | 446673002 | HBB | 20.54 | 12.5 | 41.4 | 0.52 | 12.5 | 27.4 | 84 | 6.5 | 4.5 | 2.5 | 0 | 5 | 232.5 | 17.52 | 0 | 9
23 | Manikchari | Jogyachola Bazar-Batnatali Union H/Q Road via Chadurkhil Bazar (Ch: 1220-1600m & 3150-6150m). | 446673004 | HBB | 12.05 | 118.5 | 36.6 | 9.05 | 36.5 | 23.5 | 84 | 6.5 | 4.5 | 3 | 50 | 13.1 | 635.95 | 0 | 32 | 0
|  | Sub: Total (UNR) | [11 empty] | 5.5 | 50 | 18.1 | 868.45
|  | Total (UZR) | [11 empty] | 35.0522 | 234 | 65 | 6545.547
|  | Total (UNR) | [11 empty] | 27.4 | 127 | 25.1 | 3647.45
|  | Grand Total (UZR+UNR) | [11 empty] | 62.4522 | 361 | 90.1 | 10192.997
[17 empty] | Road | Bridge | Culvet
[12 empty] | Road UZR cost |  |  |  |  | 4732.047 | 1521 | 292.5
2037
[12 empty] | Road UNR cost |  |  |  |  | 672 | 825.5 | 112.95
[17 empty] | 7441.047 | 2346.5 | 405.45 | 10192.997

## DPP Rangamati Scheme list
Proposed Roads & Structures
Name of the Project: RIDP-CHT-II
District: Rangamati
SL No | Upazila | Name of the Road and proposed Chainage | ID No | Nature of Works | Total Road Length |  |  | Already Completed Length |  |  | Unit cost |  |  | Proposed Length |  |  | Estimated Cost (Tk. In lakh) | Remaining Length to be developed |  |  | Remarks
[5 empty] | Road (m) | Bridge (m) | Culvert (m) | Road (km) | Bridge (m) | Culvert (m) | Road (m) | Bridge (m) | Culvert (m) | Road (m) | Bridge (m) | Culvert (m) |  | Road (m) | Bridge (m) | Culvert (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | Barkal | Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km | 484212001 | BC | 30.43 | 640 | 16 | 1.8 | 15 | 2 | 135 | 6.5 | 4.5 | 1.5 | 120 | 3 | 996 | 27.13 | 505 | 11 | 2 Bridge Less then 100m
Sub total(UZR) |  |  |  |  | 30.43 | 640 | 16 | 1.8 | 15 | 2 | 135 | 6.5 | 4.5 | 1.5 | 120 | 3 | 996 | 27.13 | 505 | 11
2 | Sadar | Kutukchari-Ghilachari via Battali road (Ch: 2.65-4+150km)=1.5km | 484872004 | BC | 8 | 47 | 5 | 2.65 | 47 | 2 | 135 | 6.5 | 4.5 | 1.5 | 0 | 3 | 216 | 3.85 | 0 | 0
Sub total(UZR) |  |  |  |  | 8 | 47 | 5 | 2.65 | 47 | 2 | 135 | 6.5 | 4.5 | 1.5 | 0 | 3 | 216 | 3.85 | 0 | 0
3 | Langadu | Mainimukh -Forest office to Durchari Bazar road (Ch.3+500km - 8+500km)=5.00km | 484582004 | BC | 17.85 | 300 | 90 | 1.5 | 63 | 0 | 135 | 6.5 | 4.5 | 5 | 90 | 15 | 1327.5 | 11.35 | 147 | 75 | Bridge 3 Nos Less then 100.00m
Sub-Total (UZR) |  |  |  |  | 17.85 | 300 | 90 | 1.5 | 63 | 0 | 135 | 6.5 | 4.5 | 5 | 90 | 15 | 1327.5 | 11.35 | 147 | 75
4 | Baghaichari | Marishya bazar-Durchari bazar road (Ch: 9.00 to 10.50km)=1.5km & Bridge at Ch: 10.20km | 484072003 | BC | 10.5 | 198 | 100 | 9 | 100 | 90 | 135 | 6.5 | 4.5 | 1.5 | 120 | 5 | 1005 | 0 | 78 | 5 | Durchari Bridge 120.00m
5 | Baghaichari | Durchari bazar-Karallyachari bazar Road up to Supari Pata Chara (Ch.00-3.00km)=3.00km | 484072005 | BC | 25 | 200 | 95 | 0 | 0 | 5 | 135 | 6.5 | 4.5 | 3 | 55 | 5 | 785 | 22 | 145 | 85 | Bridge 4 Nos Less then 100.00m
Sub-Total (UZR) |  |  |  |  | 35.5 | 398 | 195 | 9 | 100 | 95 | 270 | 13 | 9 | 4.5 | 175 | 10 | 1790 | 22 | 223 | 90
6 | Belaichari | Belaichari -Farua bazar road (Ch.12+000 to 16+000km)=4.00km | 484292001 | BC | 44 | 1200 | 60 | 12 | 418 | 10 | 135 | 6.5 | 4.5 | 4 | 0 | 40 | 720 | 28 | 368 | 175
Sub-Total (UZR) |  |  |  |  | 44 | 1200 | 60 | 12 | 418 | 10 | 135 | 6.5 | 4.5 | 4 | 0 | 40 | 720 | 28 | 368 | 3050
7 | Jurachari | Jurachari H/Q-Shilchari G.C. road (Ch.1+000 to 6+500km)=5.00km & Bridge at Ch: 5+750km | 484472002 | BC | 13.43 | 204 | 60 | 1 | 15 | 8 | 135 | 6.5 | 4.5 | 5.5 | 120 | 10 | 1567.5 | 6.93 | 84 | 42 | Samira Bridge 120.00m Long
8 | Jurachari | 20.00m Long Bridge on Jurachari H/Q-Eraichari Ghat road at Ch: 1+690km | 484472001 | RCC | 4.15 | 200 | 10 | 4.15 | 180 | 10 | 135 | 6.5 | 4.5 | 0 | 20 | 0 | 130 | 0 | 20 | 0 | Bridge
Sub-Total (UZR) |  |  |  |  | 17.58 | 404 | 70 | 5.15 | 195 | 18 | 270 | 13 | 9 | 5.5 | 140 | 10 | 1697.5 | 6.93 | 104 | 42
9 | Kawkhali | Ghilachari - Panchari Road (Ch.3600 to 6600km)=3.00km | 484252003 | BC | 9.14 | 100 | 45 | 3.6 | 12 | 10 | 135 | 6.5 | 4.5 | 3 | 80 | 10 | 970 | 2.54 | 20 | 25 | 2Bridge
10 | Kawkhali | 20.00m Long Bridge on Kawkhali H/Q Sugarmill road (Ch.0+690km) | 484252001 | BC | 12 | 160 | 49 | 12 | 100 | 29 | 135 | 6.5 | 4.5 | 0 | 20 | 0 | 130 | 0 | 140 | 20 | Bridge
Sub-Total (UZR) |  |  |  |  | 21.14 | 260 | 94 | 15.6 | 112 | 39 | 270 | 13 | 9 | 3 | 100 | 10 | 1100 | 2.54 | 160 | 45
11 | Rajosthali | Rajasthali H/Q-Khansama para road (To words Bagmara GC) (Ch.2.650 to 4.650km)=2.00km | 484782001 | BC | 10.57 | 120 | 80 | 2.65 | 40 | 10 | 135 | 6.5 | 4.5 | 2 | 0 | 15 | 337.5 | 5.92 | 120 | 55
Sub-Total (UZR) |  |  |  |  | 10.57 | 120 | 80 | 2.65 | 40 | 10 | 135 | 6.5 | 4.5 | 2 | 0 | 15 | 337.5 | 5.92 | 120 | 55
12 | Kaptai | Baraghonia Market-Debotachari bazar viaTanchangapara road (Ch: 3+800-5+300km)=1.5km | 484363003 | BC | 8 | 60 | 6 | 3.8 | 60 | 6 | 105 | 6.5 | 4.5 | 1.5 | 0 | 3 | 171 | 2.7 | 0 | 0
Sub total(UNR) |  |  |  |  | 8 | 60 | 6 | 3.8 | 60 | 6 | 105 | 6.5 | 4.5 | 1.5 | 0 | 3 | 171 | 2.7 | 0 | 0
13 | Langadu | Kalapakuzza Union(Mahilla)-Mainimukh growth center road (Ch.0+000 to 4+000km)=4.00km & Bridge at Ch: 1+600km | 484583002 | HBB | 6.6 | 240 | 90 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 4 | 190 | 30 | 1706 | 2.6 | 50 | 60 | 2 Bridge. Hossain Pur Bridge 120.00m another is 70.00m
14 | Langadu | Bagachattar - C.O's Tila Road (Ch.0+000 to 2+000km)=2.00km | 484583005 | HBB | 5 | 500 | 150 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 0 | 10 | 213 | 3 | 500 | 140
Sub-Total (UNR) |  |  |  |  | 11.6 | 740 | 240 | 0 | 0 | 0 | 168 | 13 | 9 | 6 | 190 | 40 | 1919 | 5.6 | 550 | 200
15 | Baghaichari | Thana H/Q-Doser road(Ch: 1640 to 3640m)=2.00km | 484073004 | HBB | 15 | 100 | 60 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 30 | 10 | 408 | 13 | 70 | 803
Sub-Total (UNR) |  |  |  |  | 15 | 100 | 60 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 30 | 10 | 408 | 13 | 70 | 803
16 | Jurachari | Juraichari G.C.-Chalka para Via Lulang Chari road.(Ch: 00-2444m=2.44km) & (Ch: 3944-4944m=1.00km) =3.44km | 484473003 | HBB | 21.23 | 100 | 69 | 1.49 | 30 | 39 | 84 | 6.5 | 4.5 | 3.4405 | 50 | 15 | 681.4995 | 16.2995 | 50 | 15
Sub-Total (UNR) |  |  |  |  | 21.23 | 100 | 69 | 1.49 | 30 | 39 | 84 | 6.5 | 4.5 | 3.4405 | 50 | 15 | 681.4995 | 16.2995 | 50 | 15
17 | Naniarchar | R & H road - Karatchari via Golachari road (Ch.0+000 to 2+000km)=2.00km | 484753006 | HBB | 7.5 | 60 | 20 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 20 | 10 | 343 | 5.5 | 40 | 10
18 | Naniarchar | R&H road-West Dewan Para Ghat (Ch: 0+00-2km)=2.00km | 484753004 | HBB | 7.75 | 90 | 20 | 0 | 0 | 0 | 84 | 6.5 | 4.5 | 2 | 0 | 10 | 213 | 5.75 | 90 | 10
Sub-Total (UNR) |  |  |  |  | 15.25 | 150 | 40 | 0 | 0 | 0 | 168 | 13 | 9 | 4 | 20 | 20 | 556 | 11.25 | 130 | 20
Total (UZR) | [13 empty] | 27 | 625 | 106 | 8184.5
Total (UNR) | [13 empty] | 16.9405 | 290 | 88 | 3735.4995
Grand Total[(UZR)+(UNR)] | [13 empty] | 43.9405 | 915 | 194 | 11919.9995
[17 empty] | Road | Bridge | Culvet
[12 empty] | Road UZR cost |  |  |  |  | 3645 | 4062.5 | 477
157.5
[12 empty] | Road UNR cost |  |  |  |  | 1296.9995 | 1885 | 396
[17 empty] | 5099.4995 | 5947.5 | 873 | 11919.9995

## Rangamati (Maint)
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2015-2016
Reporting Month:August' 2020
[14 empty] | Reporting Date |  |  |  |  | 2026-07-28
District Name: Rangamati
Sl. No. | Upazila | Name of Scheme with Chainage | Package No. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvet Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Barkal | Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km |  | BC
Sub total Barkal:
2 | Sadar | Kutukchari-Ghilachari via Battali road (Ch: 2.65-4+150km)=1.5km |  | BC
Sub total Sadar:
Maintenance Work
1 | Sadar | Periodic Maintenance of Jhagrabil (R&H) - Kaptai (R&H) via Baradam Road . Ch. 2500-1550m) Effectiove length 2500m, ID No. 484252001 | RANG/SADAR/UZR/W23 | Maint | 2016-06-27 | 2.5 | 0 |  | Road 9: 10312574; Culvert 10: 0; Brigde 11: 0; Brigde 12: 10312574; Brigde 13: 0; Brigde 21: APP Approved (H/Q) | 1
Sub-Total Sadar : |  |  | 1 |  |  | 2.5 | 0 |  | 10312574 | 0 | 0 | 10312574 | 0 |  |  | 0 | 0 | 0% | 0%
1 | Kawkhali | Periodic Maintenance of Kawkhali HQ- Sugarmil Road ch. 10000-11000m, ID No. 484252001 | RANG/KAWK/UZR/W04 | Maint | 19-11-2015 | 1 | 0 |  | 12915546 | 0 | 0 | 12915546 | 0 | 2016-01-26 | 2017-02-24 | 11941512.7 | 2720000 | 40% |  | M/S SS Traders | WBM Gi KvR Pj‡Q¦ | 1
Sub-Total Kawkhali : |  |  | 1 |  |  | 1 | 0 |  | 12915546 | 0 | 0 | 12915546 | 0 |  |  | 11941512.7 | 2720000 | 40% | 0%
1 | Kaptai | Periodic Maintenance of Raikhali Barakolapara-Bangalhalia R&H ctg. Border via Bongnal road. At ch. 00-1000m, ID No. 484362003 | RANG/KAPTAI/UZR/W20 | Maint | 2016-05-03 | 1 | 0 |  | 3332804 | 0 | 0 | 3332804 | 18350 |  |  | 3000696.545 |  | 0% |  | M/S Marma Enterprise, Ruma, Bandarban | NOA Issued | 1
Sub-Total Kaptai : |  |  | 1 |  |  | 1 | 0 |  | 3332804 | 0 | 0 | 3332804 | 18350 |  |  | 3000696.545 | 0 | 0% | 0%
|  | Total Maintenance : | 3 |  |  | 4.5 | 0 |  | 26560924 | 0 | 0 | 26560924 | 18350 |  |  | 14942209.245 | 2720000 | 8.889% | 0%
[9 empty] | Brigde 13: Total Contract Package :; Brigde 16: 3 | 3

## Bandarban
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace | [24 empty] | 64
Financial Year 2019-2020
Reporting Month:August' 2020
[14 empty] | Reporting Date: |  |  |  |  | 2026-07-28
District Name: Bandarban
Sl. No. | Upazila | Name of Scheme with Chainage & ID No. | Package Nos. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvert Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Holudia-Vaggakul-Tankbati Road.(Ch.00-2000m), ID No.403143005 | BAN/SADR/UNR/W07 | BC | 21-01-06 | 2 | 0 |  | 22971805 | 0 | 0 | 22971805 | 7217924.56 | 15/05/16 | 29/3/17 | 17134949 | 17043710 | 100% | 100% | M/S Arpmilton (JV), Bandarban | Final |  | 1 | 1
2 |  | Holudia-Vaggakul-Tankbati Road.(Ch.2000-3350m), ID No.403143005 | BAN/SADR/UNR/W08 | BC | 21-01-06 | 1.35 | 0 |  | 10735081.37 | 0 | 0 | 10735081.37 | 4040354 | 15/05/16 | 18/5/17 | 8271466.22 | 8271463 | 100% | 100% | M/S Milton Traders, Bandarban | Final |  | 1 | 1
3 |  | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road. (Ch.2950-5500m), ID No.403143002 | BAN/SADR/UNR/W11 | BC | 28-02-06 | 2.55 | 0 |  | 19912233 | 0 | 0 | 19912233 | 5752819 | 2016-09-06 | 15-06-17 Ex. 24/5/18 | 16433913.837 | 16155396 | 100% | 100% | S. Ananta Bikash Tripura, Milonpur, Khagrachari | Final |  | 1 | 1
4 |  | Construction of 12.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 780.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W19 | Bridge | 2016-09-06 |  |  | 12 |  |  | 6070959 | 6070959 |  | 2017-08-01 | 15/12/17 | 4794835 | 4794834 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
5 |  | Construction of 18.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 1430.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W20 | Bridge | 2016-09-06 |  |  | 18 |  |  | 6785192 | 6785192 |  | 2017-08-01 | 2017-11-12 | 5278818.477 | 5232131 | 100% | 100% | M/S Milton Traders, Rowangchari | Final |  | 1 | 1
6 |  | Construction of 18.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 3015.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W21 | Bridge | 2016-09-06 |  |  | 18 |  |  | 7181549 | 7181549 |  | 2017-08-01 | 2017-11-12 | 5558074.95 | 5492013 | 100% | 100% | M/S Milton Traders, Rowangchari | Final |  | 1 | 1
7 |  | (1) Construction of 22.00m long RCC Girder Bridge on Holudia-Vaggakul - Tankbati Road; at Ch.2310m. (ii) Construction of RCC Box Culvert Size; 1.50m X 1.50m; at Ch.1190m. ID No.403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W64 | Bridge | 2018-01-18 |  | 1.5 | 22 |  | 875356 | 8277663 | 9153019 |  | 2018-10-07 | 2019-09-07 | 9297095 | 9297095 | 90% | 68% | Mr.UT Mong,Maddayum Para Bandarban |  |  | 1 | 1
8 |  | Rehabilitation of Udalbunia-Jhanka Road start from Udalbunia – Rajvilla Road. (Ch.5+500-7+995km), ID No.403143002 | BAN/SADAR/UNR/W66 | BC | 2018-04-15 | 2.495 | 8 | 0 | 17917669 | 2992267 |  | 20909936 | 6113037 | 18/10/18 | 17/7/19 | 19864439.2 | 6657211 | 50% | 34% | Ms. Lumbini Enterprise, Rangamati |  |  | 1 | 1
Sadar Sub-Total : |  |  | 8 |  |  | 8.395 | 9.5 | 70 | 71536788.37 | 3867623 | 28315363 | 103719774.37 | 23124134.56 | 214843 | 129817 | 86633591.684 | 72943853 |  |  | 7 |  |  | 8
1 | Thanchi | Thanchi-Balipara road. (Ch.00-1000m), ID No.403952001 | BAN/THAN/UZR/W02 | BC | 25-10-15 | 1 | 0 |  | 15630432 | 5528250 | 0 | 21158682 | 0 | 15/2/16 | 21-02-17 Ex. 30-12-17 2nd Ex. 30-06-19 | 18394807.34 | 18081651 | 100% | 100% | M/S Milton Traders, Rowangchari | Final |  | 1 | 1
2 |  | Thanchi-Balipara road. (Ch.1000-2000m), ID No.403952001 | BAN/THAN/UZR/W13 | BC | 28-02-15 | 1 | 0 |  | 10976788 | 0 | 0 | 10976788 | 0 | 22/6/16 | 28-06-17 Ex. 30-06-18 | 9739608.14 | 9528459 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
3 |  | Construction of 20.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 2467.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W24 | Bridge | 2017-02-01 |  |  | 20 |  |  | 9870616 | 9870616 |  | 2017-02-08 | 30-06-19 | 9869497.947 | 6447805 | 90% | 65% | M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. |  |  | 1 | 1
4 |  | Construction of 20.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 3623.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W25 | Bridge | 2017-02-01 |  |  | 20 |  |  | 12644983 | 12644983 |  | 2017-02-08 | 30-06-19 | 12644266.304 | 10796949 | 70% | 66% | M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. |  |  | 1 | 1
5 |  | Construction of 45.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 1958.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W26 | Bridge | 2017-02-01 |  |  | 45 |  |  | 16636441 | 16636441 |  | 2017-02-08 | 17/2/19 | 14972796.9 | 11473203 | 70% | 62% | M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. |  |  | 1 | 1
6 |  | Rehabilitation of Thanchi-Balipara road. (Ch.2+000-3+000m); ID No: 403952001 | BAN/THANCHI/ UZR/W43 | BC | 2017-06-11 | 1 | 0 | 0 | 17736535 |  |  | 17736535 |  | 16/11/17 | 25/5/19 | 19318960.257 | 18545515 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban |  |  | 1 | 1
Thanchi Sub-Total : |  |  | 6 |  |  | 3 | 0 | 85 | 44343755 | 5528250 | 39152040 | 89024045 | 0 |  |  | 84939936.888 | 74873582 | 51% | 27% | 6 |  |  | 6
1 | Alikadam | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 00-1000m), ID No.403043007 | BAN/ALI/ UNR/W03 | BC | 15-11-15 | 1 | 0 | 0 | 8267241 | 1297011 | 0 | 9564252 | 1613216 | 16/3/16 | 2017-02-04 | 8121080.587 | 8117349 | 100% | 99.95% | M/S Milton Traders, Rowangchari | Final |  | 1 | 1
2 |  | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 1000-2600m), ID No.403043007 | BAN/ALI/ UNR/W10 | BC | 14-02-16 | 1.6 | 0 | 0 | 13307610 | 1987879 | 0 | 15295489 | 349138 | 25/5/16 | 2017-04-04 | 13597665.717 | 13364051 | 100% | 100% | M/S Emmu Construction, Rowangchari, Bandarban | Final |  | 1 | 1
3 |  | Improvement of Alikadam-Dochori Road (ch.00-2020m), ID No.403043004 | BAN/ALI/ UNR/W14 | BC | 21-03-2016 | 2 | 0 | 0 | 13037259 | 0 | 0 | 13037259 | 4614359 | 25/7/16 | 31-07-17 EX. 7/3/18 | 10729459.801 | 10724954 | 100% | 99.96% | M/S Prasanna kant Amu, Hospital raod, Bandarban | Final |  | 1 | 1
4 |  | Construction of 81.00m long PSC Gider Bridge on Alikadam Bazar- Naikhongchari Border via Rombow road. Ch.1193m) ID No: 403042002 | BAN/ ALI / BRIDGE/W22 | Bridge | 2016-10-23 |  | 0 | 81 | 44255971 | 0 | 0 | 44255971 |  | 28/03/2018 | 2020-03-01 | 39676954 | 37409025 | 80% | 71% | M/S Noor Syndicate, Pachalish,Chittagong |  |  | 1 | 1
5 |  | Improvement of Alikadam Bazar- Naikhongchari Border via Rombow road. (Ch.00-2880m) ID No. 403042002 | BAN/ALIKADAM/UZR/W39 | BC | 2017-06-08 | 2.88 | 0 | 0 | 24720436 |  |  | 24720436 | 2507186 | 17/12/17 | 23/3/19 | 22248392 | 22190607 | 95% | 90% | Mr.UT Mong,Maddayum Para Bandarban |  |  | 1 | 1
6 |  | Improvement of Sonaichori R&H-Varirmukh Road.(Ch.821-1571m) ID No. 403043005 | BAN/ALIKADAM/ UNR/W40 | BC | 2017-06-08 | 0.75 | 1.6 | 0 | 6323746 | 476351 |  | 6800097 | 482496 | 17/12/17 | 23/12/18 | 6120087.3 | 6067866 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
7 |  | Improvement of Chikkan para (cioni para) road (Ch.1441-2191m) ID No. 403043006 | BAN/ALIKADAM/ UNR/W41 | BC | 2017-06-08 | 0.75 | 3.5 |  | 4771148 | 1621901 |  | 6393049 | 269554 | 2017-05-11 | 18/2/18 | 5753744.1 | 5703742 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
8 |  | Construction of 75.00m Long PSC Girder Bridge on Fasiakhali - Alikadam main (R&H) road- Alis Suronga road ch.2600m) | BAN/ALIKADAM/ BRIDGE/W52 | BRIDGE | 2017-11-02 | 0 | 0 | 75 | 0 | 0 | 33236542 | 33236542 |  | 2018-06-09 | 2020-08-02 | 36160592.555 | 12568220 | 35% | 30% | M/S PK-AC (JV), Bandarban, Sadar, Bandarban |  |  | 1 | 1
9 |  | Improvement of Chikkan para (cioni para) road (Ch.2191-3191m) ID No. 403043006 | BAN/ALIKADAM/ UNR/W69 | BC | 31-07-18 | 1 | 0 | 0 | 11479617 | 0 | 0 | 11479617 |  | 2019-06-03 | 30/03/2020 | 11026798.13 | 5740617 | 65% | 56% | M/S M.M Traders, Rowangchari, Bandarban |  |  | 1
Alikadam Sub-Total : |  |  | 9 |  |  | 9.98 | 5.1 | 156 | 126163028 | 5383142 | 33236542 | 164782712 | 9835949 |  |  | 153434774.19 | 121886431 |  |  | 8 |  |  | 9
1 | Rowangchari | Development of Kalaghata to Taracha UP office road at Ch.00-1000m, ID No.403893004 | BAN/ROW/UNR/W01 | BC | 25/10/2015 | 1 | 4.5 | 0 | 7665778 | 2161700 | 0 | 9827478 | 1119803 | 2016-02-16 | 15-02-17 Ex.25-04-18 | 8044900.029 | 8041132 | 100% | 99.95% | M/S Milton Traders, Rowangchari | WBM ‡kl n‡q‡Q¦ |  | 1 | 1
1 |  | Development of Kalaghata to Taracha UP office road at Ch.00-1000m, ID No.403893004 | BAN/ROW/UNR/W01 | BC | 25/10/2015 | 1 | 4.5 | 0 | 7665778 | 2161700 | 0 | 9827478 | 1119803 | 16/2/16 | 22/4/18 | 8044900.029 | 8041132 | 100% | 99.95% | M/S Milton Traders, Rowangchari | Final |  | 1 | 1
2 |  | Development of Kalaghata to Taracha UP office road at Ch.1000-3000m, ID No. 403893004 | BAN/ROW/UNR/W15 | BC | 21-03-2016 | 2 | 6.4 | 0 | 22470615 | 1725180 | 0 | 24195795 | 4769663 | 2016-07-06 | 04-06-17 Ex.25-06-18 | 17941025 | 17939822 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
3 |  | Construction of 60.0m long RCC Girder Bridge on Kalaghata to Taracha UP office road at Ch.2885m, ID No: 403893004 | BAN/ROW/BRIDGE/W31 | Bridge | 2017-04-20 |  |  | 60 |  |  | 26134485 | 26134485 |  | 2017-10-08 | 16/11/18 | 23521036.5 | 22849228 | 100% | 100% | S. Ananta Bikash Tripura, Milonpur, Khagrachari | Final |  | 1 | 1
4 |  | Development of Taracha UP - Meufapara(Ruma Road - Tarasa UP Office Road) road.(Ch.4200-6500m) ID No: 403893007(Development of Ruma RHD Road – Meufpara via tarasa UP office).(Ch.4500-6690m) ID No: 403893007 | BAN/ROWAN/ UNR/W49 | HBB | 2017-10-11 | 2.19 |  | 0 | 17374646 | 28533995 |  | 45908641 |  | 14/05/18 | 2019-12-06 | 45868926.31 | 39277713 | 0% |  | M/S Marma Enterprise, Bandarban |  |  | 1 | 1
5 |  | Development of Kalaghata to Taracha UP office road at Ch.3000-5220m, ID No.403893004 | BAN/ROW/UNR/W68 | BC | 2018-07-31 | 2.22 |  |  | 35799278 |  |  | 35799278 | 3908540 | 13/1/19 | 2019-12-09 | 31616286.48 | 29477728 |  |  | acpkjv, Bandarban |  |  | 1
6 |  | Construction of 99.10m long PSC Girder Bridge on Kalaghata to Taracha UP office road at Ch.5.250 km, ID No: 403893004 | BAN/ROW/BRIDGE/W71 | Bridge | 2018-09-09 |  |  | 99 | Brigde 11: 60452545; Brigde 12: 60452545; Brigde 14: 14/3/19; Brigde 15: 13/3/20; Brigde 16: 63466163; Brigde 17: 29257147; Brigde 20: acpkjv, Bandarban |  | 1
Rowangchari Sub-Total : |  |  | 6 |  |  | 8.41 | 15.4 | 159 | 83310317 | 32420875 | 86587030 | 202318222 | 9798006 |  |  | 190458337.319 | 146842770 | 43% | 33.32% | 4 |  |  | 6
1 | Naikhonchari | Naikhongchari - Lemouchari road.(Ch.00-1000m) ID No.403733001 | BAN/NAIK/UNR/W04 | BC | 2015-02-12 | 1 | 9 | 0 | 9088672 | 2982164 | 0 | 12070836 | 2401589 | 2016-07-03 | 06-03-18 Ex. 30-03-18 | 9658461.68 | 9658461 | 100% | 100% | M/S Milton Traders, Rowangchari | Final |  | 1 | 1
2 |  | Naikhongchari - Lemouchari road.(Ch.1000-2500m), ID No.403733001 | BAN/NAIK/UNR/W05 | BC | 28-12-15 | 1.5 | 0 | 0 | 12914033 | 0 | 0 | 12914033 | 3535057 | 2016-10-03 | 01-01-18 Ex. 30-03-18 | 10509159.843 | 10506162 | 100% | 99.97% | M/S Emmu Construction , Bandarban | Final |  | 1 | 1
3 |  | Naikhongchari - Lemouchari road.(Ch.2500-4000m), ID No.403733001 | BAN/NAIK/UNR/W06 | BC | 28-12-15 | 1.5 | 0 | 0 | 13616480 | 0 | 0 | 13616480 | 3520106 | 2016-10-03 | 15-03-18 Ex. 30-03-18 | 11062329.59 | 11030308 | 100% | 99.71% | M/S Emmu Construction , Bandarban | Final |  | 1 | 1
4 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.2600-4100m, ID No.403733008 | BAN/NAIK/UNR/W09 | HBB | 28-01-16 | 1.46 | 0 | 0 | 11512651 | 0 | 0 | 11512651 | 0 | 30/6/16 | 07-07-17 Ex. 30-06-18 | 9275721.942 | 9264900 | 100% | 100% | S. Ananta Bikash Tripura, Milonpur, Khagrachari | Final |  | 1 | 1 | 42
5 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.4100-5100m, ID No.403733008 | BAN/NAIK/UNR/W18 | HBB | 2016-04-27 | 1 | 4.5 | 0 | 8369888 | 1416240 | 0 | 9786128 | 0 | 2017-06-07 | 25/9/18 | 9264612.157 | 4884597 | 100% | 53% | Mr. U.T Mong Madhyampara, Bandarban |  |  | 1 | 1
6 |  | Construction of 85.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.1600m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W32 | Bridge | 2017-04-20 |  |  | 85 |  |  | 30356111 | 30356111 |  | 28/9/17 | 31/10/19 | 30038330.44 | 24532112 | 75% | 55% | Mr. U.T Mong Madhyampara, Bandarban | Biplop |  | 1 | 1
7 |  | Construction of 36.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.3780m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W33 | Bridge | 2017-04-20 |  |  | 36 |  |  | 18179251 | 18179251 |  | 29/9/17 | 2019-05-01 | 18149186 | 13632402 | 75% | 56% | M/S MA Zaher,Adarsha Sadar Comilla. | Jico |  | 1 | 1
8 |  | Construction of 85.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.4970m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W34 | Bridge | 2016-04-24 |  |  | 85 |  |  | 28151740 | 28151740 |  | 2018-01-03 | 30/06/2020 | 30202061.066 | 14902289 | 60% | 33% | R R Construction, Comilla |  |  | 1 | 1
9 |  | Construction of 33.0m long RCC Girder Bridge on North Ghumdum - Tumbru Bazar road.Ch.2600m ID No: 403733003 | BAN/ NAIKHONG/ BRIDGE/W35 | Bridge | 2016-04-24 |  |  | 33 |  |  | 18085536 | 18085536 |  | 27/9/17 | 2019-03-03 | 16998825.6 | 16675126 | 100% | 74% | Mr. U.T Mong Madhyampara, Bandarban | Biplop |  | 1 | 1
10 |  | Construction of 33.0m long RCC Girder Bridge on Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road. Ch.3000m ID No: 403733002 | BAN/ NAIKHONG / BRIDGE/W36 | Bridge | 2016-04-24 |  |  | 33 |  |  | 18151717 | 18151717 |  | 27/9/17 | 16/12/18 | 18381798.26 | 18381506 | 100% | 83% | M/S MA Zaher,Adarsha Sadar Comilla. | Jico |  | 1 | 1
11 |  | Improvement of Dochori - Ali Kadam road .(Ch.00-3000m); ID No: 403733004 | BAN/ NAIKHONG/ UNR/W37 | BC | 2017-04-25 | 3 | 0 | 0 | 24633854 |  |  | 24633854 | 6029586 | 2018-06-05 | 2019-10-08 | 26751499.81 | 26747405 | 100% | 96% | M/s Kashem Construction, katalgong, Chittagong. | Re-Cast |  | 1 | 1
12 |  | Improvement of Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road .(Ch.00-3180m); ID No: 403733002 | BAN/ NAIKHONG/ UNR/W38 | BC | 2017-04-25 | 3.15 | 0 | 0 | 24755606 |  |  | 24755606 | 7396387 | 17/9/17 | 20/6/18 | 24718369.24 | 24718318 | 100% | 100% | M/S Abser Construction, Memberpara, Bandarban | Final |  | 1 | 1
13 |  | Construction of 33.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road). (Dochari UP office (Lemochari)-Powamohuri Bazar via Kalurghat, Painchari Bazar BGB camp & Dochari BGB Camp, Murong para BGB Camp Road) Ch.9800m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W42 | Bridge | 2017-06-08 | 0 | 0 | 33 |  |  | 14373533 | 14373533 |  | 16/11/17 | 15/11/18 | 14096979.657 |  | 0% | 0% | M/S Abser Construction, Bhandarban |  |  | 1 | 1
14 |  | Development of Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch. 00-1600m. (Effective Length 1588m) ID No: 403733008 | BAN/NAIKHONG/ UNR/W46 | BC | 2017-10-11 | 1.588 | 0 | 0 | 18725613 | 0 | 0 | 18725613 | 3483699 | 20/3/18 | 26/3/19 | 16853051.646 | 13360154 | 95% | 64% | Mayadhan Chakma, Gagra, Rangamati |  |  | 1 | 1
15 |  | Development of North Ghumdum - Tumbru Bazar road.(Ch.1000-2800m); ID No: 403733008 (Development of Uttot Ghumdum – Tumbru Bazar GC Road..(Ch.1000-2800m);(Effective Length 1790m) ID No: 403733003 | BAN/NAIKHONG/ UNR/W48 | BC | 2017-10-11 | 1.79 | 8m | 0 | 23377732 | 3900834 |  | 27278566 | 728061 | 25/4/18 | 28/4/19 | 29726858.99 | 29687707 | 100% | 100% | M/S Millon Traders, Rowangchari, Bandarban | Final |  | 1 | 1
16 |  | Development of North Ghumdum - Tumbru Bazar road. Ch.2800-4000m. (Effective Length 1159m) ; ID No: 403733003 | BAN/NAIKHONG/ UNR/W53 | HBB | 2017-11-01 | 1.159 |  |  | 14232926 |  |  | 14232926 |  | 25/4/18 | 2019-01-05 | 15014772.318 | 15010161 | 100% | 100% | M/S Millon Traders, Rowangchari, Bandarban | Final |  | 1 | 1
17 |  | Development of Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.1600-2600m. (Effective Length 815m) ;ID No: 403733008 | BAN/NAIKHONG/ UNR/W47 | HBB | 2017-11-01 | 0.815 |  |  | 8472368 |  |  | 8472368 |  | 2018-02-04 | 2019-08-04 | 7811523.296 | 7809574 | 100% | 91% | Mr. U.T Mong Madhyampara, Bandarban |  |  | 1 | 1
18 |  | Naikhongchari - Lemouchari road.(Ch.4000-6800m), ID No.403733001(Development of Naikhyongchari UZ HQ – Alikadam UZ HQ via Dochari UP Road. Ch.4000-6800m). ID No: 403732007 | BAN/NAIKHONG/ UZR /W54 | BC | 2017-11-07 | 2.8 | 0 | 0 | 32661929 | 0 | 0 | 32661929 | 5800914.11 | 21/5/18 | 27/8/19 | 35518279.849 | 35503699 | 100% | 100% | M/S Millon Traders, Rowangchari, Bandarban | Final |  | 1 | 1 | 9658461.68
19 |  | Development of Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.5100-7400m. ; ID No: 403733008 | BAN/NAIKHONG/ UNR/W55 | HBB | 2017-11-07 | 2.3 | 4 | 0 | 15209160 | 1955417 |  | 17164577 |  | 14/5/18 | 2019-10-08 | 17148784.246 | 3526353 | 35% | 21% | M/S Al-Noor Enterprise, Coxs'bazar |  |  | 1 | 1 | 10509159.843
20 |  | Improvement of Dochori - Ali Kadam road .(Ch.3000-8250m); ID No: 403733004 | BAN/NAIKHONG/ UNR/W66 | BC | 2018-07-31 | 5.157 | 10 |  | 58189892 | 5461913 |  | 63651805 | 9897910 | 29/1/19 | 27/8/20 | 68100576.46 | 62725683 | 60% | 31% | Mr. U.T Mong Madhyampara, Bandarban |  |  | 1
21 |  | Improvement of Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road.(Ch.3180-7213m); ID No: 403733002 | BAN/NAIKHONG/UNR/W67 | BC | 2018-07-31 | 4 | 2 |  | 39919106 | 684765 |  | 40603871 | 8018271 | 22/1/19 | 22/9/19 | 39919623.994 | 39917127 | 98% | 95% | M/S Milton Traders, Rowangchari |  |  | 1
22 |  | i) Improvement of Road from Naikhyongchari UZH/Q – Tumbru G.C Road by 25mm Thick Bituminous Carpating With 7mm Seal Coat at ch. 32675-33825.00 m ID No. 403732006 ii) Improvement of Road from Bodderchar Bazar – Patabhaari Moricha G.C Road by 25mm Thick Bituminous Carpating With 7mm Seal Coat at ch. 0.0-1500.00 m ID No. 403734062 | BAN/NAIK/UNR/W72 | BC | 2018-08-10 | 2.65 | 8 |  | 19594124 | 2675802 |  | 22269926 |  | 2019-11-04 | 2020-06-02 | 21251595 | 21250968 | 95% | 63% | M/S Emmu Construction, Rowangchari, Bandarban |  |  | 1
23 |  | Rehabilitation of Road from Baishari Bazar GC-Edgor Bazar Road By 25mm Dense Carpeting from Ch. 0.0m-8200m (Effective Length: 8131m) ID No. 403732003 | BAN/NAIK/UZR/W74 | BC | 22/11/18 | 8.131 | 2 |  | 73679753 | 1747212 |  | 75426965 |  | 19/03/19 | 18/3/20 | 83051059.45 | 79628921 | 55% | 46% | QC & U.T Mong (JV) |  |  | 1
24 |  | Improvement of Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) from Ch. 7400m-10650m (Effective Length: 3250m) ID No. 403733008 | BAN/NAIK/UNR/W75 | HBB | 27/01/19 | 3.25 |  |  | 33605255 | 2356723 |  | 35961978 |  |  |  | 37536439.393 | 12186769 | 0% | 0% | S. Ananta Bikash Tripura, Milonpur, Sadar, Khagrachari. |  |  | 1
Naikhongchari Sub-Total : |  |  | 24 |  |  | 46.25 | 39.5 | 305 | 315679910 | 16401333 | 127297888 | 593038000 | 50811580.11 |  |  | 601039899.927 | 505540702 | 42% | 18.86% | 19 |  |  | 24 |  | 402833151.305
1 | Ruma | Construction of 66.0m long RCC Girder Bridge on Thana HQ (Ruma Mukh)-Gallanga UP office Road. Ch.850m ID No.403913003 | BAN/RUMA/BRIDGE/W27 | Bridge | 2017-02-24 |  |  | 66 |  |  | 24564086 | 24564086 |  | 29/8/17 | 20/07/19 | 25271683 | 22490730 | 40% |  | M/S Abser Construction, Bandarban |  |  | 1 | 1 | 9275721.942
2 |  | Construction of 68.0m long PSC & RCC Girder Bridge on Thana HQ (Ruma Mukh)-Gallanga UP office Road. Ch.1120m ID No.403913003 | BAN/RUMA/BRIDGE/W28 | Bridge | 2017-03-14 |  |  | 68 |  |  | 36527218 | 36527218 |  | 29/8/17 | 2019-03-04 | 39841279 | 12781609 | 0% |  | Mohammed Eunus & Brothers (Pvt) Ltd, Chittagong. |  |  | 1 | 1 | 9264612.157
Ruma Sub-Total : |  |  | 2 |  |  |  |  | 134 | 0 | 0 | 61091304 | 61091304 | 0 |  |  | 65112962 | 35272339 |  |  | 2 |  |  | 2 |  | 27320499.9
1 | Lama | Imrovement of Lama muk-Selertua road Ch.00-3300m ID No.403513008 (Old 3007) | BAN/LAMA/UNR/W16 | HBB | 2016-04-10 | 3.3 | 9 | 0 | 17474100.89 | 3072269.11 | 0 | 20546370 | 0 | 28/8/16 | 17/11/17 | 16031768.31 | 15557556 | 100% | 100% | S. Ananta Bikash Tripura, Milonpur, Khagrachari | Final |  | 1 | 1 | 16361325.9
2 |  | Improvement of Shelertua-Rupashi Para Road Ch.00-1650m, ID No.403513011 (Old 3010) | BAN/LAMA/UNR/W17 | HBB | 2016-04-10 | 1.65 | 4.5 | 0 | 12367431.26 | 1524775.74 | 0 | 13892207 | 0 | 31/8/16 | 16-07-17 Ex. 30-04-18 | 11075616.627 | 10679906 | 100% | 100% | M/S Abser Construction, Bandarban | Final |  | 1 | 1 | 30202061.066
3 |  | Construction of 33.0m long RCC Girder Bridge on Shelertua-Rupashi Para Road at ch. 930m ID No: 403513010 | BAN/ LAMA/ BRIDGE/W29 | Bridge | 2017-04-11 |  |  | 33 |  |  | 19899758 | 19899758 |  | 2017-10-08 | 25/11/18 | 17909782.2 | 11143429 | 70% | 58% | Mr U T Mong, Madhyampara, Bandarban |  |  | 1 | 1 | 16996825.6
4 |  | Improvement of Polokhal Tetulia Moor-Quantum Cosmo College via Bodhechora public School Road. by HBB at (Ch.0+000 to 2+480km) ID No: 403515105 | BAN/LAMA/ V.Road/W44 | HBB | 2017-06-22 | 2.48 |  |  | 15801353 | 1945321 |  | 17746674 |  | 16/11/17 | 2019-05-02 | 15956067 | 15940333 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1 | 16835000
5 |  | Improvement of Bodhe Chora Bamboorian Mor - Quantum Shabujan Pry School via Ground Olympian & Chompajhiri Para Mor Road by HBB at (Ch.0+000 to 2+500km) ID No: 403515106 | BAN/LAMA/ V.Road/W45 | HBB | 2017-06-22 | 2.5 |  |  | 15427188 |  |  | 15427188 |  | 14/2/18 | 20/2/19 | 13881851 | 13869297 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final | 1 | 1 | 1 | 26751792.12
6 |  | Construction of 60m long RCC Girder Bridge on Polokhal Tetulia Moor-Quantum Cosmo College via Bodhechora public Schooll Road. At ch.30m ID No: 403515105 | /BAN/LAMA/BRIDGE/W50 | Bridge | 2017-10-15 | 0 | 0 | 60 | 0 | 0 | 25586804 | 25586804 |  | 14/2/18 | 20/5/19 | 25986267.04 | 19283251 | 80% | 73% | Mr.UT Mong,Maddayum Para Bandarban |  | 1 | 1 | 1 | 24718928.206
7 |  | Improvement of Daluchari Bazar lulying Bazar Road Ch.9+560 to 13+570km ID No: 403513012 | BAN/LAMA/UNR/W51 | HBB | 2017-11-01 | 4.01 | 2 |  | 39971996 | 734434 |  | 40706430 |  | 16/4/18 | 2019-11-06 | 40652480.98 | 40464319 | 100% | 88% | m/s marma enterprise, Nayankhan, Bandarban Sadar, Bandarban |  |  | 1 | 1 | 14096979.657
8 |  | Rehabilation of Dulahajra – Hargasa (Shapergara) Road Ch.0+000 to 11+470km. Effective length=2685.00 m; ID No: 403514011 | BAN/LAMA/V.ROAD/W65 | HBB | 2018-01-28 | 2.685 | 7 | 0 | 21846713 | 2394990 |  | 24241703 |  | 2018-05-07 | 19/5/19 | 21817532.7 | 21751166 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1 | 16853051.646
9 |  | Construction of 184.00.0m long PC with RCC Girder Bridge on Shelertua-Rupashi Para Road at ch. 170m; ID No: 403513010 | BAN/LAMA /BRIDGE /W70 | Bridge | 2018-09-10 | 0 | 0 | 184 |  |  | 106489953 | 106489953 |  | 2019-04-04 | 30/9/20 | 113654364.985 | 32214578 | 25% | 7% | Toma Construction & Co. Limited-M/S MA Zaher (JV) |  |  | 1
10 |  | Improvement of Dulahazara – Sangu Rajpara Road. Ch. 3240m – 11280m ID No. 403514019 | BAN/LAMA/VILL/W73 | HBB | 19/11/2018 | 8.04 | 3 |  | 98509896 | 1372756 |  | 99882652 |  | 15/4/19 | 14/4/20 | 97276530.763 | 68723427 | 40% | 36% | QC & Mr. U.T Mong (JV), Bandarban |  |  | 1
|  | Lama Sub-Total : | 10 |  |  | 24.665 | 25.5 | 277 | 221398678.15 | 11044545.85 | 151976515 | 384419739 | 0 |  |  | 374242261.605 | 249627262 |  |  | 8 |  |  | 10 |  | 29726858.99
Maintenance Work | [24 empty] | 15014772.318
Maintenance Work | [24 empty] | 7811523.296
1 | Sadar | Periodic Maintenance of Balaghata-Bagman Bazar Road start from B-ban Chandraghona. (Ch.5000-8000m) ID No: 403143003 | BAN/SADAR/ UNR/W23 | BC | 2016-11-27 | 3 |  |  | 10384827 |  |  | 10384827 |  | 2017-07-05 | 2018-03-15 | 9345905.17 | 9343730 | 100% | 100% | M/S marma enterprise, Mayd ampara, Bandarban | Final |  | 1 | 1
2 |  | Periodic Maintenance of Khanshama-Bagmara road start B-Ban Rowangchari Road.(Ch.2500-7313m) ID No: 403142002 | BAN/SADAR/UZR/W30 | HBB | 2017-04-11 | 4.813 |  |  | 10963617 |  |  | 10963617 |  | 2017-03-08 | 2018-08-09 | 9831735 | 9770105 | 100% | 100% | M/S Selim & Brothers, Baitus Sharaf Mosque Road, Arambag, Khagrachari. | Final |  | 1 | 1 | 17148784.246
Sadar Sub-Total : |  |  | 2 |  |  | 7.813 |  |  | Road 9: 21348444; Brigde 12: 21348444; Brigde 16: 19177640.17; Brigde 17: 19113835; Brigde 18: 85; Brigde 20: 2 |  | 2 |  | 168957690.479
1 | Lama | Maintenance of Lama-Suwalac Road. Ch.2000-5500m. ID No: 403512001 | BAN/LAMA/ UZR /W56 | BC | 2017-11-29 | 3.5 |  |  | 5462629 | 1765981 |  | 7228610 |  | 2018-03-05 | 2019-09-02 | 7730214.801 | 7705548 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final |  | 1 | 1
2 |  | Maintenance of Lama-Suwalac Road. Ch.5500-9100m. ID No: 403512001 | BAN/LAMA/ UZR /W57 | BC | 2017-11-29 | 3.6 |  |  | 4456305 |  |  | 4456305 |  | 2018-03-05 | 2019-09-02 | 4892074.45 | 4886971 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final |  | 1 | 1
3 |  | Maintenance of Daluchari Bazar-Lulying Bazar Road. Ch.2500-5490m ID No: 403513012 | BAN/LAMA/ UNR /W58 | BC | 2017-11-29 | 2.99 |  |  | 11268699 |  |  | 11268699 |  | 16/5/18 | 22/2/19 | 10141829.1 | 10067818 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final |  | 1 | 1
4 |  | Maintenance of Daluchari Bazar-Lulying Bazar Road. Ch.5490-9560m ID No: 403513012 | BAN/LAMA/ UNR /W59 | HBB | 2017-11-29 | 4.07 |  |  | 6933871 |  |  | 6933871 |  | 16/5/18 | 22/2/19 | 6240483.9 | 6231683 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final |  | 1 | 1
|  | Lama Sub-Total : | 4 |  |  | 14.16 |  |  | 28121504 | 1765981 | 0 | 29887485 | 0 |  |  | 29004602.251 | 28892020 | 66 |  | 4 |  |  | 4
1 | Alikadam | Maintenance of Amtali Road-Asuti Tripura para Dochari Road. Ch.00-1200m ID No: 403043009 | BAN/ALIKADAM/ UNR /W60 | BC | 2017-11-29 | 0.575 |  |  | 1185346 |  |  | 1185346 |  | 2018-01-08 | 2018-11-11 | 1184110.456 | 1184110 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final |  | 1 | 1
|  | Alikadam Sub-Total : | 1 |  |  | 0.575 | 0 | 0 | Road 9: 1185346; Culvert 10: 0; Brigde 11: 0; Brigde 12: 1185346; Brigde 16: 1184110.456; Brigde 17: 1184110; Brigde 20: 1 |  | 1
1 | Rowangchari | Maintenance of Khansama-Bagmara-Antapara-Kanaijupara Road. Ch.00-2000m ID No: 403892001 | BAN/ROWANG/ UZR /W61 | BC | 2017-11-29 | 2 |  |  | 4625529 |  |  | 4625529 |  | 2018-01-07 | 2019-04-04 | 4883714.33 | 4828840 | 100% | 100% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
2 |  | Maintenance of Rowangchari- Bagmara G.C via Liragong Road at Ch.5700-7760m ID No: 403892004 (Maintenance of Rowangchari- Liragong Road. at Ch.5700-7760m ID No: 403893002) | BAN/ROWANG/ UZR /W62 | BC | 2017-11-29 | 2.06 |  |  | 17887887 | 2142219 |  | 20030106 | 4159262 | 14/8/18 | 13/8/19 | 21832927.056 | 21821003 | 100% | 99% | Mr.UT Mong,Maddayum Para Bandarban | Final |  | 1 | 1
3 |  | Maintenance of Rowangchari-Gharow Road. Ch.1025-3025m ID No: 403893003 | BAN/ROWANG/ UNR /W63 | BC | 2017-11-29 | 2 |  |  | 15859574 | 551674 |  | 16411248 | 4683413 | 13/8/18 | 2019-12-08 | 17867633.649 | 8886944 | 65% | 50% | Mr. Prasanna Kanti Amu, Bandarban |  |  | 1 | 1
|  | Rowangchari Sub-Total | 3 |  |  | 6.06 | 0 | 0 | Road 9: 38372990; Culvert 10: 2693893; Brigde 11: 0; Brigde 12: 41066883; Brigde 13: 8842675; Brigde 16: 44584275.035; Brigde 17: 35536787 |  | 3
|  | Total Maintenance : | 10 |  |  | 28.608 | 0 | 0 | 89028284 | 4459874 | 0 | 93488158 | 8842675 |  |  | 93950627.912 | 84726752 |  |  | 7 |  |  | 10
Total Development : |  |  | 65 |  |  | 76.035 | 69.5 | 909 | 641033798.37 | 63601223 | 375680167 | 1598393796.37 | 93569669.67 |  |  | 1555861763.613 | 1206986939 |  |  | 54 |  |  | 65 | 66
Grand Total Bandarban Dist: |  |  | 75 |  |  | 104.643 | 69.5 | 909 | 730062082.37 | 68061097 | 375680167 | 1691881954.37 | 102412344.67 |  |  | 1649812391.525 | 1291713691 |  | 0% | 61 |  |  | 75
139

## Khagrachari
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2019-2020
Reporting Month:August' 2020
[14 empty] | Reporting Date: |  |  |  |  | 2026-07-28
District Name: Khagrachari
Sl. No. | Upazila | Name of Scheme with Chainage | Package No. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvert Length (m) | BridgeLength (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
District Name: Khagrachari
Sl. No. | Upazila | Name of Scheme with Chainage & ID No. | Package Nos. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvert Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road (Sadar Part) (Ch: 00-1000m). ID No. 446492002 | KHAGRA/SADAR/ UZR/W02 | BC | 24-11-2015 | 1 | 1 |  | 9088496 | 391918 | 0 | 9480414 | 2316695 | 21/3/16 | 24/12/16 | 9491186.151 | 9490342 | 100% | 99.99% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
2 |  | Bhaibonchara GC-Dighinala GC (Thana Bazar) via Laxmimura Road (Sadar Part) (Ch: 1000-2940m). ID No. 446492002 | KHAGRA/SADAR/ UZR/W07 | BC | 14-12-2015 | 1.94 | 0 |  | 18863110 | 0 | 0 | 18863110 | 4478411 | 2016-07-12 | 2017-07-12 | 20517807.885 | 20517554 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
3 |  | Bhaibonchara Gc-Gumti GC via Chota Bari Para Road (Sadar part) Ch.365-2365m), ID No. 446492001 | KHAGRA/SADAR/ UZR/W10 | BC | 2016-02-02 | 2 | 0 |  | 17474370 | 0 | 0 | 17474370 | 4581302 | 25/9/16 | 25/9/19 | 18080635.673 | 18077250 | 100% | 99.98% | M/S U.T Mong, Madham Para, Bandarban Sadar Bandarban, Khagrachari | Final |  | 1
4 |  | Improvement of Bhaibonchara GC-Gumti GC via Chota Bari Para Road (Sadar Part) (Ch: 2365-4365m). ID No. 446492001 | KHAGRA/SADAR/ UZR/W16 | BC | 2016-05-17 | 2 | 0 | 0 | 20840975 | 0 | 0 | 20840975 | 1862399 | 24/12/16 | 30/04/19 | 20194705.541 | 19241628 | 100% | 100% | S. Ananta Bikash Tripura | Final |  | 1
5 |  | Improvement of Golabari Union H/Q (Upper Perachara)-Pora Bazar via Bhuachari & Cristian Para Road (Ch: 4100-7040m) ID No. 446493001 | KHAGRA/SADAR/ UNR/W17 | BC | 2016-05-17 | 2.94 | 0 | 0 | 23066513 | 0 | 0 | 23066513 | 3314098 | 2016-12-12 | 23/3/18 | 22767645.025 | 22679469 | 100% | 99.61% | S. Ananta Bikash Tripura | Final |  | 1
6 |  | Improvement of Bichitola Bazar-Khagrachari Sadar HQ (Battali) Road (Ch: 1330-3330m). ID No. 446493002 | KHAGRA/SADAR/ UNR/W36 | BC | 2017-04-20 | 2 |  |  | 13365654 |  |  | 13365654 | 4689377 | 18/9/17 | 30/06/19 | 13365654 | 13288527 | 100% | 100% | M/S Shamsul Alam Mohila College Road, Sadar, Khagrachari. | Final |  | 1
7 |  | Improvement of Bhaibonchara GC-Gumti GC via Chota Bari Para Road (Sadar Part) (Ch: 4365-7450m). ID No. 446492001 | WD/RIDPCHT-2/ KHAGRA/ SADAR / UZR/W53 | BC | 2018-01-18 | 3.085 |  |  | 32635128 |  |  | 32635128 |  | 2018-07-05 | 30-06-2020 | 30871158.21 | 2163808 | 50% | 8% | M/S U.T Mong, Madham Para, Bandarban Sadar Bandarban, Khagrachari |  |  | 1
Sub: Total Sadar: |  |  | 7 |  |  | 14.965 | 1 | 0 | 135334246 | 391918 | 0 | 135726164 | 21242282 |  |  | 135288792.485 | 105458578 | 71% | 71.37%
1 | Matiranga | BGumti GC-Bhibonchara GC Road. (Matiranga Part) (Ch: 152-1152m). ID No. 446702002 | KHAGRA/MATIRA/ UZR/W03 | BC | 24-11-2015 | 1 | 0 |  | 10664086 | 0 | 0 | 10664086 | 435071 | 21/3/16 | 27/3/17 | 10663988.58 | 10598423 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
2 |  | BGumti GC-Bhibonchara GC Road. (Matiranga Part) (Ch: 1152-2500m). ID No.446702002 | KHAGRA/MATIRA/ UZR/W08 | BC | 14-12-2015 | 1.348 | 2 |  | 11518995 | 516601 | 0 | 12035596 | 0 | 14/5/17 | 15/12/18 | 13012033.562 | 12987651 | 100% | 100% | S. Ananta Bikash Tripura | Final |  | 1
3 |  | Construction of 64.06m Bridge on BGumti GC-Bhibonchara GC Road Ch: 40m. ID No. 446702002 | KHAGRA/MATIRA/ BRIDGE/W21 | Bridge | 2016-10-23 |  |  | 64.06 |  |  | 23200165 | 23200165 |  | 16/5/17 | 31-05-2020 | 25831818.79 | 19936436 | 90% | 70% | S. Ananta Bikash Tripura |  |  | 1
4 |  | Gumti Bazar-Ramsharia Bazar Road (Ch: 00-2000m). ID No. 446703006 | KHAGRA/MATIRA/ UNR/W11 | BC | 2016-02-02 | 2 |  | 0 | 14288340 | 0 | 0 | 14288340 | 4601189 | 25/9/16 | 2017-01-07 | 14816826.446 | 14689152 | 100% | 100% | M/S U.T Mong, Madham Para, Bandarban Sadar Bandarban, Khagrachari | Final |  | 1
5 |  | Improvement of Gumti UP Office-Bhibonchara GC via Tailafang & Gakulmani BDR Camp Road (Ch: 2000-3300m). ID No. 446703010 | KHAGRA/MATIRA/ UNR/W18 | BC | 2016-05-17 | 1.3 | 0 | 0 | 9796179 | 0 | 0 | 9796179 | 0 | 2016-12-12 | 2017-12-12 | 9766691.094 | 9763864 | 100% | 99.97% | S. Ananta Bikash Tripura | Final |  | 1
6 |  | Gumti Bazar-Ramsharia Bazar Road (Ch: 2000.00-3000.00m). ID No. 446703006 | KHAGRA/MATIRA/UNR/W09 | BC | 2017-04-02 | 1 |  |  | 6819865 |  |  | 6819865 | 2297009 | 2018-05-02 | 2018-11-12 | 7491831.155 | 7483279 | 100% | 100% | M/S Priti Enterprise, Rangamati | Final |  | 1
7 |  | Belchari Union H/Q-Ajuddah Bazar Road (Ch: 6480-7900m). ID No. 446703004 | KHAGRA/MATIRA/UNR/W33 | BC | 2017-04-02 | 1.5 |  |  | 11610518 |  |  | 11610518 |  | 2018-11-03 | 18/3/19 | 10875431.848 | 10828860 | 100% | 100% | M/S Selim & Brothers, Arambag, Sadar, Khagrachari | Final |  | 1
8 |  | Development of Police Inqury Center to Muktal Hossain House Road (Ch: 00-1500m). ID No. 446704051; | KHAGRA/MATIRA/Vill/W43 | BC | 2017-10-04 | 1.5 |  |  | 9774433 |  |  | 9774433 | 1821036 | 22/2/18 | 31/1/19 | 10746989.49 | 10746989 | 100% | 100% | M/S Mong ConstructionAparparachar, Sadar, Khagrachari | Final |  | 1
|  | Sub: Total Matiranga | 8 |  |  | 9.648 | 2 | 64.06 | 74472416 | 516601 | 23200165 | 98189182 | 9154305 |  |  | 103205610.965 | 97034654 | 87.78%
1 | Panchari | Panchari-Langadu Road. [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) Ch: 4659-5659m. ID No. 446772001 | KHAGRA/PANCHARI/ UZR/W04 | BC | 24-11-2015 | 1 | 0 |  |  | 12415329 | 0 | 12415329 | 0 | 221/3/16 | 30/6/19 | 12093961 | 11520997 | 100% | 100% | M/S Mallik Enterprise, South Mithakhalim Mathbaira, Pirojpur | WBM ch©šÍ Complete |  | 1
2 |  | Panchari-Langadu Road. [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) Ch: 1537-2537m. ID No. 446772001 | KHAGRA/PANCHARI/ UZR/W24 | BC | 2016-12-06 | 1 |  |  | 14592880 |  | 394518 | 14987398 | 1957961.6 | 30/4/17 | 30/6/19 | 14670003.33 | 12302927 | 90% | 70% | M/S Mallik Enterprise, South Mithakhalim Mathbaira, Pirojpur |  |  | 1
3 |  | Panchari GC-Bhaibonchara GC via Shantipur Road (Panchari Part) (Ch: 11058-12280m). ID No. 446772003 | KHAGRA/PANCHARI/ UZR/W15 | BC | 2016-03-06 | 1.222 | 0 |  | 15807908 | 0 | 0 | 15807908 | 0 | 25/9/16 | 2017-01-10 | 17222769.448 | 16808662 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
4 |  | Panchari-Langadu Road. [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) Ch: 2537-4659m. ID No. 446772001 | KHAGRA/PANCHARI/ UZR/W29 | BC | 2017-03-12 | 2.122 | 6 |  | 25483818 | 3480816 |  | 28964634 | 4648657 | 19/7/18 | 25/1/20 | 28740336.87 | 1265893 | 40% | 6% | M/S Molik Enterprise, Mathbaria, Perojpur |  |  | 1
5 |  | Construction of 48.06m Bridge on Panchari GC-Bhaibonchara GC via Shantipur Road (Panchari Part) (Ch: 10625m). ID No. 446772003 | KHAGRA/PANCHARI/ BRIDGE/W38 | Bridge | 2007-06-13 |  |  | 48 |  |  | 29759790 | 29759790 |  | 19/11/17 | 13/2/19 | 32418929.719 | 32351912 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari |  |  | 1
6 |  | Development of Logong Union H/Q-Tanakkya Para Bazar Road (Panchari Part) (Ch.00-5000m).ID No. 446773001; | KHAGRA/PANCHA/UNR/W39 | BC | 2017-10-04 | 5 |  |  | 78735318 |  |  | 78735318 | 10882082 | 23/5/18 | 29/05/20 | 86438773.05 | 86261227 | 100% | 100% | SABT – RIPEN - JV, Milonpur, Sadar, Khagrachari |  |  | 1
7 |  | Construction of 75m long PC Girder Bridge onPanchari-Langadu Road. [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) Ch: 5150m. ID No. 446772001 | KHAGRA/PANCHARI/BRIDGE/W61 | Bridge | 2019-03-02 |  |  | 75 |  |  | 47635419 | 47635419 |  | 13/5/19 | 20/05/20 | 49776829.675 | 6163468 | 20% | 0% | M/S Selim & Brothers, Arambaagh, Khagrachari |  |  | 1
Sub: Total Panchari: |  |  | 7 |  |  | 10.344 | 6 | 48 | 134619924 | 15896145 | 77789727 | 228305796 | 17488700.6 |  |  | 241361603.092 | 166675086 | 78.57%
1 | Mohalchari | Mahalchari GC-Maischari GC Road (Ch: 4118-6347m). ID No. 446652001 | KHAGRA/MAHAL/ UZR/W12 | HBB | 2016-02-02 | 2.229 | 0 |  | 11187477 | 0 | 0 | 11187477 | 0 | 2017-03-08 | 30/12/18 | 11909331.98 | 11889341 | 100% | 100% | Mr. Suvangkar Chakma, Jail Road, Rangamati | Final |  | 1
2 |  | Mahalchari GC (Singinala)-Khagrachari Sadar Upazila H/Q Road (Mahalchari Part) (Ch: 3500-5200m). ID No. 446652005 | KHAGRA/MAHAL/ UZR/W13 | HBB | 2016-02-02 | 1.7 | 0 |  | 8332352 |  | 0 | 8332352 | 0 | 20/9/16 | 28/6/17 | 8472303 | 8465308 | 100% | 100% | Mr. Suvangkar Chakma, Jail Road, Rangamati | Final |  | 1
3 |  | Construction of 60.00m RCC Girder Bridge on Mahalchari GC-Maischari GC Road Ch: 4218m.. .ID No. 446652001 | KHAGRA/MAHAL/ BRIDGE/W25 | BRIDGE | 2017-03-02 |  |  | 60 |  |  | 29796891 | 29796891 |  | 2018-04-02 | 30/06/2020 | 32595000 | 21574671 | 90% | 56% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari |  | APP | 1
4 |  | (i) Construction of 2 X 4.00X 4.00m RCC Box Culvert on Mahalchari GC-Maischari GC Road Ch: 4130-m.. .ID No. 446652001 (PART A) (ii) Construction of 2 X 4.00X 4.00m RCC Box Culvert on Maischari GC (Juramyachari)-Longadu GC Road. (Mahalchari Part) Ch. 4750m ID No. 446652002 (PART B) | KHAGRA/MAHAL/ UZR/W26 | Culvert | 2017-03-02 |  |  | 16 |  |  | 8276178 | 8276178 |  | 15/11/17 | 15/11/18 | 8054903.261 | 7860212 | 100% | 100% | M/S Prama Enterprise | Final |  | 1
5 |  | Improvement of Maischari GC (Juramyachari)-Longadu GC Road (Mahalchari Part) (Ch: 2530-4735m).= EL=2000m .ID No. 446652002 | KHAGRA/MAHAL/UZR/W27 | BC | 2017-03-12 | 2 | 3 |  | 23507789 | 1649713 |  | 25157502 | 174802 | 18/09/2017 | 24/12/2018 | 28238157.59 | 28212656 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
6 |  | Construction of 1X3.0mX 3.0m RCC box culvert Mahalchari GC-Maischari GC Road at Ch: 3051m). ID No. 446652001 c¨v‡KR bs WD/RIDPCHT-2/ | KHAGRA/MAHAL/UZR/W28 | Culvert | 2017-03-12 |  | 3 |  | 1708470 |  |  | 1708470 | 24116 | 30/08/2017 | 2018-05-06 | 1630160.112 | 1629012 | 100% | 100% | S. Ananta Bikash Tripura | Final |  | 1
7 |  | Improvement of Mahalchari GC (Singinala)- Khagrachari Sadar Upazilla H/Q road (Mahalchari Part) (Ch: 5200-6226m). ID No. 446652005 | WD/RIDPCHT-2/ KHAGRA/ MAHAL / UZR/W54 | HBB | 2018-01-18 | 1.026 | 8 |  | 13021345 | 3078285 |  | 16099630 |  | 30/6/18 | 2019-07-09 | 15938197.18 | 15751239 | 100% | 100% | S. Ananta Bikash Tripura |  |  | 1
8 |  | Construction of 1x3.00x3.00m RCC Box Culvert on Mahalchari GC to Maischari GC at ch.5920m ID No. 446652001 | WD/RIDPCHT-2/ KHAGRA/ MAHAL / UZR/W55 | Culvert | 2018-01-18 |  | 3 |  |  | 1789577 |  | 1789577 |  | 26/4/18 | 2019-03-05 | 1620000 |  | 10% | 0% | M/S Prama Enterprise |  |  | 1
9 |  | Construction of 96.00m long PSC Girder Bridge on Mahalchari GC (Chengikhal)- Longadu GC Road.(Mahalchari Part) Ch: 00m. ID No. 446652003 | KHAGRA/MAHAL/BRIDGE/W62 | Bridge | 20/3/19 |  |  | 96 |  |  | 85243906 | 88164485.2 |  | 23/06/19 | 30/6/20 | 96090438.28 | 2920579 | 0% | 0% | M/S Selim & Brothers, Arambag, Sadar, Khagrachari |  |  | 1 | 93169859.08
|  | Sub: Total Mohalchari: | 9 |  |  | 6.955 | 17 | 172 | 57757433 | 6517575 | 123316975 | 190512562.2 | 198918 |  |  | 204548491.403 | 98303018 | 87.5% | 22.22%
1 | Dighinala | Panchari-Langadu road. [Dighinala GC-Panchari GC Via Nunchari Road] (Dighinala Part) Ch: 2320-3320m. ID No. 446432001 | KHAGRA/DHIGI/ UZR/W01 | BC | 23-11-2015 | 1 | 0 |  | 8722152 | 0 | 0 | 8722152 | 2433536 | 21/3/16 | 24/12/16 | 8734563.128 | 8734295 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
2 |  | Panchari-Langadu road. [Dighinala GC-Panchari GC Via Nunchari Road] (Dighinala Part) Ch: 3320-4320m. ID No. 446432001 | KHAGRA/DHIGI/ UZR/W06 | BC | 14-12-2015 | 1 | 0 |  | 8318200 | 0 | 0 | 8318200 | 2203886 | 2016-07-12 | 17/4/17 | 9033531.57 | 9031727 | 100% | 99.98% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
3 |  | Choto Merung Bazar R&H - Baghaichari Upazila HQ Road (Ch:00-2800m). ID No. 446432003 | KHAGRA/DHIGI/ UZR/W14 | HBB | 2016-02-02 | 2.8 | 10 |  | 21238666 | 5344959 | 0 | 26583625 | 0 | 25/9/16 | 30/12/18 | 28938887.453 | 24464937 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
4 |  | Construction of 60m long RCC Bridge Over Mainee River on Choto Merung Bazar R&H - Baghaichari Upazila HQ Road; Ch:00m – 60m; ID No. 446432003 | KHAGRA/DHIGI/ BRIDGE/W59 | Bridge | 23/01/2019 |  |  | 60 |  |  | 37126917 | 37126917 |  | 30/5/19 | 2020-11-06 | 39209641.479 | 9037564 | 20% | 0% | M/S Selim & Brothers, Arambagh,Sadar, Khagrachari. |  |  | 1
|  | Sub: Total Dighinala: | 4 |  |  | 4.8 | 10 | 0 | 38279018 | 5344959 | 37126917 | 80750894 | 4637422 |  |  | 85916623.63 | 51268523 | 80% | 74.99%
1 | Ramghar | Sonaipul GC-Hayako GC via Khagrabill Road (Ramghar Part) (Ch: 13650-15000m), ID No. 446802001 | KHAGRA/RAMGHA/ UZR/W05 | BC | 23-11-2016 | 1.35 | 0 |  | 15633309 | 0 | 0 | 15633309 | 310424 | 21/3/16 | 27/3/17 | 16786426 | 16770755 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
2 |  | Improvement of Khagrabill GC-Manikchari GC via Batnatali Bazar Road (Ramghar Part) (Ch: 2000-4250m). ID No: 446802002 | KHAGRA/RAMGHA/ UZR/W34 | BC | 2017-05-31 | 2.25 |  |  | 22045102 |  |  | 22045102 |  | 2017-11-12 | 18/11/18 | 23923342.676 | 23898049 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
3 |  | Development of Patachara RHD Guimara GC via Parshuramghat road (Ramgarh Part) (Ch: 4000-4950m; ID No: 446802005 (Improvement of Patachara Union H/Q-Guimara GC Road via Parshuramghat (Ramgarh Part) (Ch: 4000-4950m). ID No: 446803002) | KHAGRA/RAMGHA/ UZR/W37 | HBB | 2017-05-31 | 0.95 |  |  | 7129317 |  |  | 7129317 |  | 16/11/17 | 2018-12-03 | 7100000.011 | 7092595 | 100% | 100% | M/S Mong Construction | Final |  | 1
|  | Sub: Total Ramghar: | 3 |  |  | 4.55 | 0 |  | 44807728 | 0 | 0 | 44807728 | 310424 |  |  | 47809768.687 | 47761399 | 100% | 100%
1 | Manikchari | Improvement of Jogyachola Bazar-Batnatali Union H/Q Road via Chadurkhil Bazar (Ch: 1220-1565m & 3275-5315m). ID No. 446673004 | KHAGRA/MANIK/ UNR/W19 | HBB | 2015-05-17 | 2.385 | 0 |  | 8028762 | 0 | 0 | 8028762 | 0 | 2016-12-12 | 2017-12-12 | 7738874.379 | 7738172 | 100% | 100% | S. Ananta Bikash Tripura | Final |  | 1
2 |  | Improvement of Manikchari Union H/Q (Mohamuni)-Hatimura Bazar Road via Gaidhan (Ch: 520-3020m) .ID No. 446673002 | KHAGRA/ MANIK / UNR/W20 | HBB | 2015-05-17 | 2.47 | 0 |  | 10673064 | 0 | 0 | 10673064 | 0 | 2016-12-12 | 2017-12-12 | 10246126.787 | 10237692 | 100% | 100% | S. Ananta Bikash Tripura | Final |  | 1
3 |  | Construction of 48.00m long RCC Girder Bridge on Jogyachola Bazar-Batnatali Union H/Q Road via Chadurkhil Bazar Ch: 1250m ID No. 446673004 | KHAGRA/MANIK/ BRIDGE/W32 | BRIDGE | 2017-03-20 |  |  | 48 |  |  | 21322381 | 21322381 |  | 2017-10-09 | 2019-10-04 | 20968483.547 | 20729597 | 100% | 100% | S. Ananta Bikash Tripura |  |  | 1
4 |  | Construction of 33.00m long RCC Girder Bridge on Jogyachola Bazar-Batnatali Union H/Q Road. Over Manikchari Khal at Ch: 3275m. .ID No. 446673004 | KHAGRA/MANIK/ BRIDGE/W35 | BRIDGE | 2017-04-19 |  |  | 33 |  |  | 15595624 | 15595624 |  | 19/11/17 | 18/1/18 | 17031116.043 | 16994103 | 100% | 100% | S. Ananta Bikash Tripura | Final | APP Apprpved Date: 25-04-17 | 1
5 |  | Improvement of Manikchari Union H/Q (Mohamuni)-Hatimura Bazar Road via Gaidhan (Ch: 3020-4020m); ID No. 446673002 | KHAGRA/MANIK/ UNR/W56 | HBB | 2018-03-07 | 1 | 12.5 |  | 8937609 | 4773371 |  | 13710980 |  | 2018-03-06 | 30/11/19 | 13691936.508 | 12748667 | 90% | 70% | S. Ananta Bikash Tripura, Milonpur, Sadar, Khagrachari. |  |  | 1
|  | Sub: Total Manikchari: | 5 |  |  | 5.855 | 12.5 | 81 | 27639435 | 4773371 | 36918005 | 69330811 | 0 |  |  | 69676537.264 | 68448231 | 90% | 40%
1 | Gumara/ Mohalchari | Development of Sindukchari Union H/Q-Tinduck Chari Bazar Road (Ch: 2210-4210m). ID No. 446633002; | KHAGRA/GUMARA/UNR/W40 | HBB | 2017-10-04 | 2 |  |  | 12041000 |  |  | 12041000 |  | 2018-04-03 | 20/3/19 | 13233059.3 | 4911323 | 80% | 37% | Subal Bindu Chackma Court Road, Sadar Khagrachari |  |  | 1
2 | Gumara/ Ramghar | Development of Patachara Union H/Q-Guimara GC Road via Parshuramghat (Gumara Part) . (Ch: 1330-2880m). ID No. 446632003; (Patachara Union H/Q-Guimara GC Road via Parshuramghat (Ramgarh Part) (Ch: 4950-6500m). ID No. 446803002) | KHAGRA/GUMARA/UNR/W41 | HBB | 2017-10-04 | 1.55 |  |  | 6445238 |  |  | 6445238 |  | 2018-05-02 | 2019-12-11 | 6779818.214 | 6779393 | 100% | 100% | M/S Priti Enterprise, Rangamati | Final |  | 1
|  | Sub: Total Gumara: | 2 |  |  | 5.855 |  |  | Road 9: 27639435; Brigde 12: 18486238; Brigde 13: 0; Brigde 16: 20012877.514; Brigde 17: 11690716; Brigde 18: 90%
100
1 | Panchari | Periodic Maintenance of Panchari-Langadu Road [Panchari GC (College Gate)-Dighinala GC via Gonggaram Para Road] (Panchari Part) (Ch: 00-1537m). ID No: 446772001 | KHAGRA/PANCHA/ UZR/W22 | BC | 2016-12-04 | 1.537 | 3 |  | 4433073 | 966949 |  | 5400022 | 99958 | 23/4/17 | 27/8/18 | 4881070.96 | 4586394 | 100% | 100% | S. Ananta Bikash Tripura | Final |  | 1
2 |  | Periodic Maintenance of 2 X 4.00m X 4.00m RCC box culvert on Logong Union H/Q-Tanakkya Para Bazar Road (Panchari Part) Structure (Ch: 1710m) & Road Ch.00-400m) ID No: 446773001 | KHAGRA/PANCHA/ UNR/W23 | Culvert | 2016-12-04 |  | 8 |  | 49000482 | 723547 |  | 5624029 | 320342 | 23/4/17 | 27/8/18 | 5286020.566 | 5285831 | 100% | 100% | Jatnashar Tripura, Madupur, Sadar, Khagrachari |  | 1 | 1
|  | Sub: Total Panchari: | 2 |  |  | 1.537 | 11 | 0 | 53433555 | 1690496 | 0 | 11024051 | 420300 |  |  | 10167091.526 | 9872225 | 100% | 50%
1 | Ramghar | Periodic Maintenance of Nakapa GC-Batnatali Union H/Q Road via Taichakma & Kumari Belchari (Ramghar Part) (Ch: 00-1570m). ID No: 446803001 | KHAGRA/RAMGHAR/ UNR/W30 | BC | 2017-03-15 | 1.57 |  |  | 13062419 |  |  | 13283001 | 3595096 | 2018-07-02 | 15/11/18 | 13940510.229 | 13436664 | 100% | 100% | Mr. Sbal Bindu Chakma, Laxmichari, khagrachari | Final |  | 1
|  | Sub: Total Ramghar: | 1 |  |  | 1.57 | 0 | 0 | 13062419 | 0 | 0 | 13283001 | 3595096 |  |  | 13940510.229 | 13436664 | 100% | 150%
1 | Mohalchari | Rehabilitation of 2x4.0x4.0m RCC Box Culvert at Ch. 393.00m and 1x3.0x3.0m RCC Box Culvert at Ch. 479.00m on Mahalchari GC (Chengikhal)-Langadu GC Road. ID No: 446652003 | KHAGRA/MAHAL/ UZR /W45 | Culvert | 2017-12-10 |  | 11 | 0 | 0 | 7202667 | 0 | 7202667 |  | 28/3/18 | 2018-10-11 | 6647263.323 | 6626278 | 100% | 100% | S. Ananta Bikash Tripura, Milonpur, Sadar, Khagrachari. |  |  | 1
2 |  | Maintenance of Mahalchari GC(Singinala) - Khagrachari Sadar Upazilla H/Q Road at Ch.12140-12850m. ID No: 446652005 | KHAGRA/MAHAL/ UZR /W46 | BC | 2017-12-10 | 0.71 | 0 | 0 | 2166914 |  | 0 | 2166914 |  | 18/3/18 | 25/9/19 | 2160415.39 | 2160101 | 100% | 100% | M/S Mong Construction, Apar Perachara, Sadar, Khagrachari | Final |  | 1
3 |  | Periodic Maintenance Mohalchari GC (Chengikhal)-Longadu GC Road (Ch: 00-2924m);, ID No. 446652003 | KHAGRA/MAHAL/ UZR /W58 | HBB | 2018-04-09 | 0.721 | 5.2 |  | 245844 | 2627836 |  | 2873680 |  | 19/7/18 | 25/7/19 | 2729996 | 2171787 | 85% | 79% | Subal Bindu Chackma Court Road, Sadar Khagrachari. |  |  | 1
|  | Sub: Total Mohalchari: | 3 |  |  | 1.431 | 16.2 | 0 | 2412758 | 9830503 | 0 | 12243261 | 0 |  |  | 11537674.713 | 10958166 | 95%
1 | Dighinala | Maintenance of Dighinala GC-Bhaibonchara GC Road from Ch.1000-2380m ID No: 446432002 | KHAGRA/DIGHI/ UZR /W47 | BC | 2017-12-10 | 1.38 |  |  | 2732773 |  |  | 2732773 |  | 24/5/18 | 2019-01-06 | 2732116.41 | 2696568 | 100% | 100% | M/S Rip Enterprise, Narankhaiya, Sadar, Khagrachari | Final |  | 1
2 |  | Maintenance of Merung Union HQ-Maidha Boalkhali Bazar via Battali Bazar Road from Ch.00-1800m ID No: 446433001 | KHAGRA/DIGHI/ UNR /W48 | BC | 2017-12-10 | 1.8 |  |  | 3215385 |  |  | 3215385 |  | 28/3/18 | 2018-04-10 | 3210298.31 | 3206395 | 100% | 100% | Mr. Banga Mitra Chakma, Komalchari, Sadar, Khagrachari | Final |  | 1
|  | Sub: Total Dighinala: | 2 |  |  | 3.18 | 0 | 0 | 5948158 | 0 | 0 | 5948158 | 0 |  |  | 5942414.72 | 5902963 | 100% | 100%
1 | Manikchari | Maintenance of Manikchari Union H/Q(Babrabill)-Chadurkhill Bazar Road from Ch.7685-9350m ID No: 446673005 | KHAGRA/MANIK/ UNR /W49 | BC | 2017-12-10 | 1.665 |  |  | 14063565 |  |  | 14063565 | 3951523 | 2018-04-12 | 19/4/19 | 15396113.13 | 15349055 | 100% | 100% | Mr. Kabi Ranjan Tripura & Subal Bindu Chakma (JV), Khagrapur, Sadar, Khagrachari | Final |  | 1
|  | Sub: Total Manikchari: | 1 |  |  | 1.665 | 0 | 0 | 14063565 | 0 | 0 | 14063565 | 3951523 |  |  | 15396113.13 | 15349055 | 100%
1 | Sadar | Maintenance of Golobari union H/Q(Upper perachara)-pora Bazar via Bhuachari & Cristianpara Road from Ch.1100-3455m ID No:446493001 | KHAGRA/SADAR/ UNR /W50 | BC | 2017-12-10 | 2.355 | 0 | 0 | 3841694 |  |  | 3841694 |  | 28/3/18 | 2018-10-04 | 3800000.14 | 3797945 | 100% | 100% | Subal Bindu Chackma Court Road, Sadar Khagrachari | Final |  | 1
|  | Sub: Total Sadar: | 1 |  |  | 2.355 | 0 | 0 | 3841694 | 0 | 0 | 3841694 | 0 |  |  | 3800000.14 | 3797945 | 100%
1 | Matiranga | Maintenance of Bornal UP Office (R&H)-Ramsira Bazar via Bhutto para & Choto ramsira para Road from Ch.00-550m ID No: 446703009 | KHAGRA/MATIRA/ UNR /W51 | BC | 2017-12-10 | 0.55 |  |  | 1410675 |  |  | 1410675 |  | 15/3/18 | 22/9/18 | 1410000.09 | 1404966 | 100% | 100% | Subal Bindu Chackma Court Road, Sadar Khagrachari | Final |  | 1
|  | Sub: Total Matiranga: | 1 |  |  | 0.55 | 0 | 0 | 1410675 | 0 | 0 | 1410675 | 0 |  |  | 1410000.09 | 1404966 | 100%
1 | Laxmichari | Maintenance of Laxichari GC (Upazilla HQ –Kawkhali Upazilla HQ Road via Barmachari UP H/Q & Barmachari Muk Bazar road at Ch.00-1670m ID No: 446612002 (Laxmichari Upazila H/Q-Barmachari union H/Q Road at ch. 1500-3170m ID No: 446613001) | KHAGRA/LAXMI/ UZR /W52 | BC | 2017-12-10 | 1.67 |  |  | 4592156 |  |  | 4592156 |  | 2018-07-05 | 20/12/18 | 4840222.49 | 4810042 | 100% | 100% | Mr . Hridoy Kumar Chakma, Laxmichari, Khagrachari |  |  | 1
|  | Sub: Total Laxmichari: | 1 |  |  | 1.67 | 0 | 0 | Road 9: 4592156; Culvert 10: 0; Brigde 11: 0; Brigde 12: 4592156; Brigde 13: 0; Brigde 16: 4840222.49; Brigde 17: 4810042
|  | Total Maintenance : | 12 |  |  | 13.958 | 27.2 | 0 | Road 9: 98764980; Culvert 10: 11520999; Brigde 11: 0; Brigde 12: 66406561; Brigde 13: 7966919; Brigde 16: 67034027.038; Brigde 17: 65532026
Total Development : |  |  | 45 |  |  | 62.972 | 48.5 | 365.06 | 540549635 | 33440569 | 298351789 | 866109375.2 | 53032051.6 |  |  | 907820305.04 | 646640205 |  | 44.08%
Grand Total Khagrachari Dist: |  |  | 57 |  |  | 76.93 | 75.7 | 365.06 | 639314615 | 44961568 | 298351789 | 932515936.2 | 60998970.6 |  |  | 974854332.078 | 712172231 |  | 44.08%
57
540549635

## Rangamathi
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2019-2020
Reporting Month:August' 2020
[14 empty] | Reporting Date |  |  |  |  | 2026-07-28
District Name: Rangamati
Sl. No. | Upazila | Name of Scheme with Chainage | Package No. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvet Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Barkal | Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km |  | BC
Sub total Barkal:
2 | Sadar | Kutukchari-Ghilachari via Battali road (Ch: 2.65-4+150km)=1.5km |  | BC
Sub total Sadar:
1 | Langadu | (Part-A) Mainimukh -Forest office to Durchari Bazar road Ch.2500 - 3500m (Part-B) Mainimukh -Forest office to Durchari Bazar road Ch.3500-4611m, ID No. 484582004 | RANG/LANGU/UZR/W08 | HBB | 30-11-2015 | 2.11 | 0 |  | 17242083 | 0 | 0 | 17242083 | 0 | 23/2/16 | 30/11/17 | 17872264.401 | 17725413 | 100% | 100% | M/S Salim & Brothers | Final | 1
2 |  | Development of Kalapakuzza Union (Mahilla)-Mainimukh growth center road Ch. 755-1750m, ID No. 484583002 | RANG/LANGU/UNR/W09 | HBB | 30-11-2015 | 0.995 | 0 |  | 13026073 | 0 | 0 | 13026073 | 0 | 22/2/16 | 01-03-17 Ex: 30-11-18 | 13495464.82 | 12007931 | 95% | 88.98% | M/S Shaleha Enterprise | Re-cast | 1
3 |  | Development of Mainimukh -Forest office to Durchari Bazar road Ch.4610 - 6631m, ID No. 484582004 | RANG/LANGU/UZR/W11 | HBB | 2016-02-09 | 2.021 | 0 |  | 24129837 | 0 | 0 | 24129837 | 0 | 22/8/16 | 2018-01-10 | 26106896.65 | 26103380 | 100% | 99.99% | Nishith Baran Talukder, Art Council, Rangamati | Final | 1
4 |  | Development of Mainimukh -Forest office to Durchari Bazar road Ch.6631-8454m, ID No. 484582004 | RANG/LANGU/UZR/W12 | HBB | 2016-02-09 | 1.823 | 0 |  | 18754628 | 0 | 0 | 18754628 | 0 | 30/8/16 | 19/11/17 | 20365125.668 | 10238706 | 80% | 50% | M/S Milton Traders, Rowangchari, Bandarban | Cancel | 1
5 |  | Development of Kalapakuzza Union (Mahilla)-Mainimukh growth center road Ch. 00-755 & Ch.3294-4415m, ID No. 484583002 | RANG/LANGU/UNR/W13 | HBB | 2016-02-09 | 1.876 | 0 |  | 18620265 | 0 | 0 | 18620265 | 0 | 18/5/16 | 25/5/18 | 20329478.25 | 20238614 | 100% | 99.55% | M/S Shaleha Enterprise | Final | 1
6 |  | Development of Bagachattar- CO's Tila road ch.840-1230m. ID No. 484583005 | RANG/LANGU/UNR/W18 | HBB | 2016-04-13 | 0.39 | 0 |  | 6717452 | 0 | 0 | 6717452 | 0 | 2016-07-18 | 31/5/18 | 6674591 | 3987555 | 85% | 59.74% | M/S Mita Tripura, Rangamati | Re-cast | 1
7 |  | Development of Bagachattar- CO's Tila road ch.1230-1815m. ID No. 484583005 | RANG/LANGU/UNR/W19 | HBB | 2016-04-13 | 0.585 | 0 |  | 5296375 | 0 | 0 | 5296375 | 0 | 18/7/16 | 31/5/18 | 5286868.65 | 5235216 | 100% | 100% | M/S Mita Tripura, Rangamati | Final | 1
8 |  | Construction of 140.00m long RCC Girder Bridge on Kalapakuzza Union(Mahilla) -Mainimukh growth center Road at ch. 3520m. ID No: 484583002 | RANG/LANGU/ BRIDGE/W39 | Bridge | 2017-03-08 |  |  | 140 |  |  | 56980157 | 56980157 |  | 13/9/17 | 30/06/2020 | 59249812.836 | 18336159 | 40% | 31% | Mr U.T Mong, Bandarban sadar,Bandarban, Khagrachari |  | 1
9 |  | Construction of 90.00m long RCC Girder Bridge on Maini Mukh Forest office to Durchari Bazar road ch.8454m ID No: 484582004 | RANG/LANGU/ BRIDGE/W40 | Bridge | 2017-03-08 |  |  | 90 |  |  | 31923740 | 31923740 |  | 13/9/17 | 19/3/19 | 34725373.221 | 34675250 | 100% | 100% | M/S Rip Enterprise | Final | 1
10 |  | Construction of 105.00m long PC Girder Bridge on Kalapakuzza Union(Mahilla) -Mainimukh growth center Road at ch.2045m. ID No: 484583002 | RANG/LANGU/ BRIDGE/W42 | Bridge | 2017-09-13 | 0 | 0 | 105 | 0 | 0 | 70891011 | 70891011 |  | 2018-09-08 | 16/2/19 | 75909536.284 | 15000000 | 32% | 20% | M/S Nipa Enterprise, & S. Ananta Bikash Tripura (JV) |  | 1
11 |  | Development of Kalapakuzza Union (Mahilla)-Mainimukh growth center road Ch. 1750-3294m, ID No. 484583002 | RANG/LANGU/UNR/W51 | HBB | 2017-12-06 | 1.284 | 0 | 0 | 10154398 | 0 | 0 | 10154398 |  | 2018-10-04 | 17/4/19 | 10115659.473 | 8018581 | 90% | 80% | M/S U. M Traders, Majerbasti, Rangamati, Sadar, Rangamati |  | 1
12 |  | Development of Bagachattar- CO's Tila road ch.1815 to 2840 m; Effective Length-1020m. ID No. 484583005 | RANG/LANGU/UNR/W57 | HBB | 2018-01-14 | 1.02 | 4 |  | 8863751 | 2367895 |  | 11231646 |  | 17/7/18 | 30-12-19 | 10891038.522 | 6723500 | 75% | 62% | M/S Shalaha Enterprise |  | 1
13 |  | Construction of 84.00m long RCC Girder Bridge Noksobil Canal on Mainimukh -Forest office to Durchari Bazar road Ch.9+054 km, ID No. 484582004 | RANG/LANGU/BRIDGE//W60 | Bridge | 2018-02-10 |  |  | 84 |  |  | 42269940 | 42269940 |  | 18/03/19 | 26/03/20 | 42055135.256 | 6315323 | 20% | 12% | S. Ananta Bikash Tripura, Khagrachari, |  | 1
14 |  | Development of Attrakchara UPC Islamabad R& H Road at the Shop of Jalil PC-Sonai Market via the H/O Barek Chowkider Road (Ch:00-900m), ID No. 484585011 | RANG/LANGU/VILL/W61 | BC | 2018-06-11 | 0.9 |  |  | 5367330 |  |  | 5367330 | 193648 | 20/01/19 | 27/02/20 | 5098963.5 | 3186164 | 90% | 62% | Suvrangkar Chakma, Jail Road, Rangamati Sadar, Rangamati |  | 1
Sub-Total Langadu : |  |  | 14 |  |  | 13.004 | 4 | 419 | 128172192 | 2367895 | 202064848 | 332604935 | 193648 |  |  | 348176208.531 | 187791792 | 47.14% | 42.73%
1 | Baghaichari | Development of Marishya bazar-Durchari bazar road Ch: 9000 to 10950km, ID No. 484072003 | RANG/BAGHAI/UZR/W05 | BC | 30-11-2015 | 1.72 | 0 |  | 16645589 | 0 | 0 | 16645589 | 150098 | 2016-11-02 | 30/6/18 | 15088307.238 | 13073959 | 100% | 100% | Nishith Baran Talukder, Art Council, Rangamati |  | 1
2 |  | Development of Durchari bazar-Karallyachari bazar Road up to Supari Pata Chara Ch.00-1740km, ID No. 484072005 | RANG/BAGHAI/UZR/W06 | BC | 30-11-2015 | 1.74 | 1.6 |  | 18352680 | 759246 | 0 | 19111926 | 0 | 2016-02-11 | 30/6/18 | 18185874.099 | 9031564 | 70% | 50% | Suvanankar Chakma |  | 1
3 |  | Thana H/Q-Doser road Ch: 1640 to 2730m, ID No. 484073004 | RANG/BAGHAI/UNR/W07 | HBB | 30-11-2015 | 1.09 | 0 |  | 8909430 | 0 | 0 | 8909430 | 68813 | 2016-11-02 | 28/2/18 | 7347911.39 | 7309546 | 100% | 100% | Mayadhan Chakma | Final | 1
4 |  | Development of Thana H/Q-Doser road Ch.2730-3640m, ID No. 484073004 | RANG/BAGHAI/UNR/W14 | HBB | 2006-02-22 | 0.91 | 0 |  | 8744391 | 0 | 0 | 8744391 | 0 | 28/2/18 | 14/5/19 | 8658783.269 | 8640722 | 100% | 100% | M/S Byagio Enterprise | Final | 1
5 |  | Construction of 54.06m Long RCC Girder Bridge on Durchari bazar-Karallyachari bazar Road up to Supari Pata Chara Ch.3940m, ID No. 484072005 | RANG/BAGHAI/BRIDGE/W34 | Bridge | 2016-12-20 |  |  | 54.06 |  |  | 20526162 | 20526162 |  | 25/5/17 | 31-05-2018 Ex 13-08-18Ex 10/1/19 | 20443616.32 | 19865771 | 100% | 100% | M/S Nipa Enterprise | Final | 1
6 |  | Development of Durchari bazar-Karallyachari bazar Road up to Supari Pata Chara Ch.1740-3000m, ID No. 484072005 | RANG/BAGHAI/UZR/W15 | BC | 2006-02-22 | 1.26 | 0 |  | 15709028 | 0 | 0 | 15709028 | 0 | 18/5/16 | 25-05-18Ex 30/03/2020 | 15782252.69 | 9717829 | 70% | 62% | M/S Shaleha Enterprise |  | 1
7 |  | Construction of 105.00m long PC Girder Bridge on Marishya bazar-Durchari bazar road at ch.10170m ID No: 484072003 | RANG/BAGHAI/ BRIDGE/W44 | Bridge | 2017-09-13 | 0 | 0 | 105 | 0 | 0 | 57882971 | 57882971 |  | 2018-10-04 | 30/05/2020 | 63477377 | 19578789 | 45% | 31% | M/S Nipa Enterprise – MNS (JV) R. F Classic Point (1st Floor), 8 Katalgonj Road(Beside Oil kha Mosque), Chawkbazar, Chittagong |  | 1
Sub-Total Bagaichari : |  |  | 7 |  |  | 6.72 | 1.6 | 159.06 | 68361118 | 759246 | 78409133 | 147529497 | 218911 |  |  | 148984122.006 | 87218180 | 73.57% | 58.86%
1 | Belaichari | Belaichari -Farua bazar road (Ch.12+000 to 16+000km)=4.00km |  | BC |  |  |  | 318.12 | Brigde 11: 156818266
Sub-Total Belaichari:
1 | Jurachari | Jurachari H/Q-Shilchari G.C. road Ch.2000 to 3500m, ID No. 484472002 | RANG/JURAI/ UZR/W01 | HBB | 17-11-2015 | 1.5 | 0 |  | 12153610 |  | 0 | 12153610 | 0 | 2016-03-07 | 25-04-2018 Ex- 15/06/19 | 13906533.004 | 10555180 | 90% | 76% | M/S Rip Enterprise |  | 1
2 |  | Jurachari H/Q-Shilchari G.C. road Ch.3500-5030m, ID No. 484472002 | RANG/JURAI/ UZR/W10 | HBB | 2016-01-30 | 1.53 | 0 |  | 14995914 |  | 0 | 14995914 | 0 | 2016-03-07 | 29-03-18 | 17197370.78 | 17183512 | 100% | 100% | M/S Rip Enterprise | Final | 1
3 |  | 20.00m Long Bridge on Jurachari H/Q-Eraichari Ghat road at Ch: 1+690km |  | HBB
4 |  | Juraichari G.C.-Chalka para Via Lulang Chari road.(Ch: 00-2444m=2.44km) & (Ch: 3944-4944m=1.00km) =3.44km |  | HBB
3 |  | Development of Juraichari G.C.-Chalka para Via Lulang Chari road.(Ch: 00-650m=650m) ID No: 484473003 | WD/RIDPCHT-2/ RANG/ JURAI / UNR/W28 | HBB | 2016-09-25 | 0.65 | 16 |  | 6581400 | 6974417 |  | 13555817 |  | 2016-11-12 | 02-03-18 Ex:31-12-2019 | 12398912 | 9880546 | 100% | 100% | M/S Dewan Enterprise |  | 1
4 |  | Development of Juraichari G.C.-Chalka para Via Lulang Chari road.(Ch: 650-1890m=1240m) ID No: 484473003 | WD/RIDPCHT-2/ RANG/ JURAI / UNR/W29 | (HBB) | 2016-09-25 | 1.24 | 1 |  | 10996651 | 883200 |  | 11879851 |  | 2017-01-04 | 01-11-18 Ex:30-11-18 | 11116241.958 | 10559413 | 100% | 100% | M/S SS Traders | Final | 1
5 |  | Construction of 16m long RCC Girder Bridge on Juraichari G.C.-Chalka para Via Lulang Chari road. At ch. 4420m | RANG/JURAI/ BRIDGE/W19 | Bridge | 2016-06-06 |  |  | 16 | 0 |  | 8722479 | 8722479 | 0 | 13/10/16 | 3/1/18 Ex 14/5/18 | 8622572.275 | 8294061 | 100% | 100% | M/S Shaleha Enterprise | Final | 1
6 |  | Construction of 18m long RCC Girder Bridge on Juraichari G.C.-Chalka para Via Lulang Chari road. At ch. 4800m | RANG/JURAI/ BRIDGE/W20 | Bridge | 2016-06-06 |  |  | 18 | 0 |  | 10655074 | 10655074 | 0 | 2017-01-03 | 3/1/18 Ex 13-08-18 | 10605127.39 | 10598198 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final | 1
7 |  | Construction of 20m long RCC Girder Bridge on Juraichari G.C.-Chalka para Via Lulang Chari road. At ch. 4280m | RANG/JURAI/ BRIDGE/W21 | Bridge | 2016-06-06 |  |  | 20 | 0 |  | 11530397 | 11530397 | 0 | 15/9/16 | 3/1/18 Ex 14-08-18 | 11483357.76 | 11480331 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final | 1
8 |  | Construction of 22m Long RCC Girder Bridge on Jurachari H/Q-Eraichari Ghat road at Ch: 1700m | RANG/JURAI/ BRIDGE/W22 | Bridge | 2016-06-06 |  |  | 22 | 0 |  | 9478019 | 9478019 |  | 21/9/16 | 21/09/2017 Ext Time. 30.08.18 | 8850404.631 | 8847931 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final | 1
9 |  | Construction of 210.00m long PC Girder Bridge on Jurachari H/Q-Shilchari G.C. road at ch.5970m ID No: 484472002 | RANG/JURAI/ BRIDGE/W43 | Bridge | 2017-09-13 | 0 | 0 | 210 | 0 | 0 | 139352139 | 139352139 |  | 2018-01-04 | 2019-03-10 | 151198404.503 | 30220244 | 35% | 20% | Quashem Construction & Nahin Enterprise (JV), Millennium Tower (4th Floor) 1558, Agrabad Access Road, Chittagong. |  | 1
10 |  | Development of Jurachari H/Q-Shilchari G.C. road (Ch.5030m to 7700m), Effective Length =2260.00m; ID No: 484472002 | RANG/JURAI/ UZR/W46 | HBB | 2017-10-15 | 2.26 | 0 | 0 | 29463807 |  |  | 29463807 |  | 2018-07-03 | 13/3/19 | 28569953.136 | 9222174 | 40% | 32% | M/S RIP ENTERPRISE, Narankhya, Khagrachari, Sadar, Khagrachari |  | 1
11 |  | Development of Jurachari H/Q-Shilchari G.C. road (Ch.7700 m to 9200m), Effective Length =1440.00m; ID No: 484472002 | RANG/JURAI/ UZR/W47 | HBB | 2017-10-15 | 1.44 | 60 | 0 | 19294759 | 23696624 |  | 42991383 |  | 2018-01-11 | 2019-08-11 | 45799061 | 8618940 | 30% | 19% | M/S RIP ENTERPRISE, Narankhya, Khagrachari, Sadar, Khagrachari |  | 1
Sub-Total Jurachari: |  |  | 11 |  |  | 8.62 | 77 | 286 | 93486141 | 31554241 | 179738108 | 304778490 | 0 |  |  | 319747938.437 | 135460530 | 63.09% | 43.27%
1 | Kawkhali | Ghilachari - Panchari Road Ch.3600 to 4620m, ID No. 484252003 | RANG/KAWK/UZR/W02 | BC | 17-11-2015 | 1.01 | 0 | 0 | 13671875 | 0 | 0 | 13671875 | 598008 | 26-01-2016 | 15-02-2017 | 13453417.723 | 13382906 | 100% | 100% | Mayadhan Chakma | Final | 1
2 |  | Construction of 20m long RCC Girder Bridge on Kawkhali H/Q to Sugarmil road at ch. 700m ID No: 484252001 | RANG/KAWKHALI/ BRIDGE/W24 | BC | 2016-06-28 | 0 | 0 | 20 | 0 | 0 | 15351733 | 15351733 | 0 | 22/9/16 | 2017-11-12 | 13301328.343 | 12987825 | 100% | 100% | Mr U.T Mong, Bandarban sadar,Bandarban, Khagrachari | Final | 1
3 |  | Construction of 50.06m long RCC Girder Bridge on Ghilachari - Panchari Road road at ch. 6510m. ID No: 484252003 | RANG/KAWKHALI/ BRIDGE/W33 | Bridge | 2016-11-17 |  |  | 50.06 |  |  | 20875921 | 20875921 |  | 14/6/17 | 28/04/2020 | 22332483.084 | 12022496 | 75% | 54% | Mr U.T Mong, Bandarban sadar,Bandarban, Khagrachari |  | 1
4 |  | Construction of 42.06m long RCC Bridge on Ghilachari - Panchari Road road at ch. 7519m. ID No: 484252003 | RANG/KAWKHALI/ BRIDGE/W27 | Bridge | 2016-09-24 |  |  | 42.06 |  |  | 13189155 | 13189155 |  | 24/4/17 | 30/4/19 | 12930714.66 | 12813845 | 100% | 100% | Mr U.T Mong, Bandarban sadar,Bandarban, Khagrachari | Final | 1
5 |  | Development of Ghilachari - Panchari Road (Ch.4620.00m to 6600.00m); Effective Length =1912.00m; ID No: 484252003 | RANG/KAWK/ UZR/W50 | BC | 2017-10-15 | 1.912 |  |  | 25714325 | 721616 |  | 26435941 |  | 26/2/18 | 31/12/19 | 28185547.86 | 21129129 | 85% | 78% | Mr U. T. Mong, Madyam Para, 4 no. Ward, Bandarban Pourosava, Bandarban |  | 1
6 |  | Construction of 20m long RCC Girder Bridge on Kawkhali H/Q-Sugarmill road at ch. 2430m. ID No: 484252001 | RANG/KAWKH/ BRIDGE/W41 | Bridge | 2018-01-18 |  |  | 20 |  |  | 7996275 | 7996275 |  | 31.07.18 | 25.06.19 | 8388537.97 | 9187049 | 100% | 100% | M/S RIP ENTERPRISE, Narankhya, Khagrachari, Sadar, Khagrachari |  | 1
Sub-Total Kawkhali : |  |  | 6 |  |  | 2.922 | 0 | 132.12 | 39386200 | 721616 | 57413084 | 97520900 | 598008 |  |  | 98592029.64 | 81523250 | 52% | 33.33%
1 | Rajosthali | Development of Rajasthali H/Q-Khansama para road (To words Bagmara GC) Ch.2400 to 3060m, ID No. 484782001 | RANG/RAJOS/ UZR/W16 | BC | 2016-04-13 | 0.66 | 0 |  | 15160488 | 0 | 0 | 15160488 | 893501 | 26/6/16 | 30-05-18 | 14493143 | 13944164 | 100% | 100% | Mr. UT Mong, Madham para, Sadar, Bandarban | Final | 1
2 |  | Development of Rajasthali H/Q-Khansama para road (To words Bagmara GC) Ch.3060 to3710m, ID No. 484782001 | RANG/RAJOS/ UZR/W17 | BC | 2016-04-13 | 0.65 | 0 |  | 16561873 | 0 | 0 | 16561873 | 0 | 21/7/16 | 28/5/18 | 15629644 | 15512420 | 100% | 100% | Mr. UT Mong, Madham para, Sadar, Bandarban | Final | 1
3 |  | Development of Rajasthali H/Q-Khansama para road (To words Bagmara GC) Ch.3710 to 6710m, Effective Length-3000m. ID No. 484782001 | RANG/RAJOS/ UZR/W58 | HBB | 2018-01-14 | 3 |  |  | 29950697 |  |  | 29950697 |  | 2018-09-08 | 30-11-19 | 31021590.103 | 25962822 | 90% | 84% | M/S RIP ENTERPRISE, Narankhya, Khagrachari, Sadar, Khagrachari |  | 1
Sub-Total Rajosthali: |  |  | 3 |  |  | 4.31 | 0 | 0 | 61673058 | 0 | 0 | 61673058 | 893501 |  |  | 61144377.103 | 55419406 | 66.67% | 66.67%
1 | Kaptai | Baraghonia Market-Debotachari bazar viaTanchangapara road (Ch: 3+800-5+300km)=1.5km |  | BC |  | 5.844 |  |  | Brigde 12: 195041800; Brigde 16: 61144377.103
Sub total Kaptai:
1 | Barkal | Development of Barkal Upazila HQ (BGB Mosque) to – Barkal College via Barkal Simanta Vocational Institute road by HBB Pavment; (Ch.422-1500m) ID No: 484214022 (Barkal H/Q-TO Choto Horina Road (Ch: 1+888-3.388km)=1.5km; ID No: 484212001) | / RANG/BARKAL/V.Road//W45 | HBB | 2017-09-14 | 1.078 | 0 | 0 | 9223110 | 0 | 0 | 9223110 |  | 2018-04-01 | 2019-08-04 | 9674650.889 | 8944769 | 100% | 100% | M/S U. M Traders, Majerbasti, Rangamati, Sadar, Rangamati | Final | 1
|  | Sub-Total Barkal: | 1 |  |  | 1.078 | 0 | 0 | Road 9: 9223110; Culvert 10: 0; Brigde 11: 0; Brigde 12: 9223110; Brigde 16: 9674650.889; Brigde 17: 8944769; Brigde 18: 85%
1 | Naniarchar | Development of R & H road - Karatchari via Golachari road (Ch1000-1610m, ID No. 484752003 | RANG/NANIA/UZR/W32 | HBB | 2016-10-27 | 0.61 |  |  | 13211979 |  |  | 13211979 |  | 24/4/17 | 30-04-2018 Ex 13-07-18 | 11890781.1 | 10709124 | 100% | 100% | S. Ananta Bikash Tripura, Khagrachari, Sadar, Khagrachari | Final | 1
2 |  | Development of R & H road - Karatchari via Golachari road (Ch00-1000m, ID No.484752003 | RANG/NANIA/UZR/W03 | HBB | 17-11-2015 | 1 | 3.2 |  | 10669664 | 962236 | 0 | 11631900 | 0 | 18/2/16 | 2016-11-08 | 12748826.158 | 12600580 | 100% | 100% | M/S Dewan Enterprise | Final | 1
3 |  | Development of R&H road-West Dewan Para Ghat (Ch: 00-1000m)=1000m; ID No. 484753004 | RANG/NANIA/UZR/W37 | BC | 2015-02-14 | 1 |  |  | 11546529 |  |  | 11546529 |  | 28/6/17 | 4/7/18 Ex 31/2/19 | 11543060.108 | 11523934 | 100% | 99.83% | Mayadhan Chakma | Final | 1
4 |  | Development of R&H road-West Dewan Para Ghat (Ch: 1000-2000m)=1000m; ID No. 484753004 | RANG/NANIA/UZR/W38 | BC | 2015-02-14 | 1 |  |  | 12595191 |  |  | 12595191 |  | 19/6/17 | 25/6/18 Ex 30/12/18 | 12498368.18 | 12449557 | 100% | 99.61% | M/S Sarkar Enterprise | Final | 1
2 |  | R&H road-West Dewan Para Ghat (Ch: 0+00-2km)=2.00km |  | HBB |  | 2.156
Sub-Total Naniarchar: |  |  | 4 |  |  | 3.61 | 3.2 | 0 | 48023363 | 962236 | 0 | 48985599 |  |  |  | 48681035.546 | 47283195 | 100% | 99.61%
1 | Belaichari | Development of Belaichari -Farua bazar road (Ch.12000m to 13300m); Effective Length =1300.00m; ID No: 484292001 | RANG/BELAI/ UZR/W48 | HBB | 2017-10-15 | 1.3 | 0 | 0 | 29307099 | 0 | 0 | 29307099 |  | 2018-08-03 | 17/3/19 | 30618500 | 30433430 | 100% | 100% | Mr U. T. Mong, Madyam Para, 4 no. Ward, Bandarban Pourosava, Bandarban | Final | 1
|  | Sub-Total Belaichari: | 1 |  |  | 1.3 | 0 | 0 | Road 9: 29307099; Culvert 10: 0; Brigde 11: 0; Brigde 12: 29307099; Brigde 16: 30618500; Brigde 17: 30433430; Brigde 18: 30%
1 | Sadar | Improvement of Kharikhong to Zamchup via Kuramara Road; Ch. 1200.00-3040.00m; Effective Length=1795.00m ID No: 484875022 | RANG/SADAR/VILL./W63 | HBB | 17/10/2019 | 1.84 | 18 |  | Road 9: 20482414; Culvert 10: 16139355; Brigde 12: 36621769; Brigde 16: 38239080.84; Brigde 20: Mr U. T. Mong, Madyam Para, 4 no. Ward, Bandarban Pourosava, Bandarban | 1
|  | Sub-Total Sadar: | 1 |  |  | 1.84 | 18 | 0 | Road 9: 20482414; Culvert 10: 16139355; Brigde 11: 0; Brigde 12: 36621769; Brigde 13: 0; Brigde 16: 38239080.84; Brigde 17: 0
Maintenance Work
1 | Sadar | Periodic Maintenance of Jhagrabil (R&H) - Kaptai (R&H) via Baradam Road . Ch. 2500-15550m) Effectiove length 2500m, ID No. 484252002 | RANG/SADAR/UZR/W23 | BC | 2016-06-27 | 2.5 | 0 |  | 10312574 | 0 | 0 | 10312574 | 0 | 16/11/16 | 22/11/17 | 8354632.767 | 8311163 | 100% | 100% | Mayadhan Chakma | Final | 1
Sub-Total Sadar : |  |  | 1 |  |  | 2.5 | 0 |  | 10312574 | 0 | 0 | 10312574 | 0 |  |  | 8354632.767 | 8311163 | 100% | 100%
1 | Kawkhali | Periodic Maintenance of Kawkhali HQ- Sugarmil Road ch. 10000-11000m, ID No. 484252001 | RANG/KAWK/UZR/W04 | BC | 19-11-2015 | 1 | 0 |  | 12915546 | 0 | 0 | 12915546 | 0 | 17/2/16 | 31/12/17 | 11941512.7 | 11761568 | 100% | 100% | M/S SS Traders | Final | 1
2 |  | Periodic Maintenance of Kawkhali HQ- Gagra bazar road. Ch. 00-5000m, ID No. 484252002 | RANG/KAWK/UZR/W56 | BC | 2018-01-21 | 5 |  |  | 7154479 |  |  | 7154479 |  | 2018-09-08 | 16/8/19 | 7836667.173 | 7830603 | 100% | 100% | Mr U. T. Mong, Madyam Para, 4 no. Ward, Bandarban Pourosava, Bandarban | Final | 1
3 |  | Periodic Maintenance of Goiatal-Sonaichari road. Ch. 00-500m, & Ch. 1500-3000m, ID No. . 484253002 | RANG/KAWK/UNR/W52 | BC | 2018-01-21 | 3 |  |  | 9318125 | 770270 |  | 10088395 |  | 2018-01-04 | 31/12/19 | 9089555.5 | 8981239 | 100% | 100% | S. Ananta Bikash Tripura, Milonpur Khagrachari |  | 1
Sub-Total Kawkhali : |  |  | 3 |  |  | 9 | 0 |  | 29388150 | 770270 | 0 | 30158420 | 0 |  |  | 28867735.373 | 28573410 | 60% | 100%
1 | Jurachari | Periodic Maintenance of Jurachari H/Q-Eraichari Ghat road at Ch: 163 – Ch: 3577km ID No: 484472001 WD/RIDPCHT-2/RANG/JURAI/ UZR/W30 | WD/RIDPCHT-2/ RANG/ JURAI / UNR/W30 | RCC | 2016-10-16 | 0.42 |  |  | 3939035 |  |  | 3939035 |  | 25/5/17 | 31/5/18 | 3545131.5 | 3516721 | 100% | 100% | M/S Milton Traders, Roangchari,Bandarban | Final | 1
Sub-Total Jurachari: |  |  | 1 |  |  | 0.42 |  |  | Road 9: 3939035; Brigde 12: 3939035; Brigde 16: 3545131.5; Brigde 17: 3516721; Brigde 18: 99%
1 | Kaptai | Periodic Maintenance of Raikhali Barakolapara-Bangalhalia R&H ctg. Border via Bongnal road. At ch. 00-1000m, ID No. 484362003 | RANG/KAPTAI/UZR/W20 | BC | 2016-05-03 | 1 | 0 |  | 3332804 | 0 | 0 | 3332804 | 18350 | 24/7/17 | 30/7/17 | 3000696.545 | 2842060 | 100% | 100% | M/S Marma Enterprise, Ruma, Bandarban | Final | 1
2 |  | Rehabilitation of Baraghonia Market-Debotachari bazar via Tanchangapara road. Ch. 1300-4100m, ID No. 484363003 | RANG/KAPTAI/UNR/W53 | BC | 2018-01-21 | 2.8 |  |  | 23093410 | 1015000 |  | 24108410 | 2175546 | 2018-09-08 | 25/6/19 | 25066460.1 | 1935544 | 35% | 9% | M/S RIP ENTERPRISE, Narankhya, Khagrachari, Sadar, Khagrachari |  | 1
Sub-Total Kaptai : |  |  | 2 |  |  | 3.8 | 0 |  | 26426214 | 1015000 | 0 | 27441214 | 2193896 |  |  | 28067156.645 | 4777604 | 100% | 100%
1 | Rajosthali | Periodic Maintenance of Bangalhalia-Raikhali Barakhola para via Dongnala road.Ch. 00-2000m, ID No. 484783004 | RANG/RAJOS/UNR/W54 | BC | 2018-01-21 | 2 |  |  | 2298916 |  |  | 2298916 |  | 19/4/18 | 25/4/19 | 2069026.2 | 2019010 | 100% | 100% | Nishith Baran Talukder, Tobolchari, Rangamati | Final | 1
2 |  | Periodic Maintenance of Rajosthali H/Q-Khansama para road Ch. 00-2000m, ID No. 484782001 | RANG/RAJOS/UZR/W55 | BC | 2018-01-21 | 2 |  |  | 3063062 |  |  | 3063062 |  | 19/4/18 | 25/4/19 | 2756755.8 | 2716489 | 100% | 100% | Mr. U T Mong, Maddampara, Bandarban | Final | 1
|  | Sub-Total Rajosthali : | 2 |  |  | 4 | 0 |  | 5361978 | 0 | 0 | 5361978 | 0 |  |  | 4825782 | 4735499 | 37% | 100%
1 | Langadu | Periodic Maintenance of Longadu-Mainimukh road. BC & HBB road (Ch.530-1420m) ID No: 484582001 | RANG/LANGU/ UZR/W31 | BC | 2016-10-27 | 0.89 | 0 |  | 5768753 | 0 | 0 | 7664667 | 1895914 | 2017-02-08 | 14-02-2018 Ex: 27-04-18 | 7167949.017 | 7165766 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final | 1
2 |  | Periodic Maintenance of Longadu-Mainimukh road. BC & HBB road (Ch.1420-2575m) (Part B) ID No: 484582001 | RANG/LANGU/ UZR/W35 | BC | 2017-02-07 | 0.6 |  |  | 6744287 |  |  | 6744287 | 1350834 | 21/5/17 | 27/5/18 | 6069858.3 | 6049272 | 100% | 100% | M/S Milton Traders, Rowangchari, Bandarban | Final | 1
3 |  | Periodic Maintenance of Longadu-Mainimukh road. BC & HBB road (Ch2575-3085m) (Part C) ID No: 484582001 | RANG/LANGU/ UZR/W36 | BC | 2017-02-07 | 0.51 |  |  | 5649054 |  |  | 5649054 | 1323000 | 15/5/17 | 21/5/18 | 5084148.6 | 5052373 | 100% | 100% | Jatnashar Tripura, Madhupur, khagrachari | Final | 1
Sub-Total Langadu : |  |  | 3 |  |  | 8 | 0 |  | 18162094 | 0 | 0 | 20058008 | 4569748 |  |  | 18321955.917 | 18267411 | 83% | 100%
1 | Baghaichari | Rehabilitation of Marishya Bazar-Durchari Bazar Road from Ch 00-2025m; & Thana Link Road Ch. 00-62m .; Effective length-2087m ID No. 484072003 | RANG/BAGHAI/ UZR/W59 | BC | 2018-04-26 | 2.087 | 0 | 0 | 23003916 | 0 | 0 | 23003916 | 5917763 | 24/10/18 | 30/06/2020 | 20363872 | 4585007 | 35% | 25% | Mr.UT Mong,Maddayum Para Bandarban. |  | 1
2 |  | Rehabilitation of Marishya Bazar-Durchari Bazar Road from Ch 2025-4500m; Effective Length-2475m ID No. 484072003 | RANG/BAGHAI/ UZR/W60 | BC | 2018-04-26 | 2.475 | 0 | 0 | 21177994 | 0 | 0 | 21177994 | 5205592 | 24/10/18 | 30/06/2020 | 23118820 |  | 20% | 0% | Mr.UT Mong,Maddayum Para Bandarban. |  | 1
3 |  | Maintenance of Upazila Sadar to Talukder para via Muslim block bazar road, Ch.3+190 km -4+660km; ID No. 484074054 | RANG/BAGHAI/VILL/W62 | BC | 20/06/19 | 1.47 | 2.6 |  | Road 9: 14329403; Culvert 10: 1029606; Brigde 12: 17148416; Brigde 16: 16680247; Brigde 20: S. Ananta Bikash Tripura, Milonpur Khagrachari | 1
|  | Sub-Total Baghaichari : | 3 |  |  | 4.562 | 0 | 0 | 44181910 | 0 | 0 | 61330326 | 11123355 | 0 | 0 | 60162939 | 4585007
|  | Total Maintenance : | 15 |  |  | 32.282 | 95 | 95 | 137771955 | 1785365 | 95 | 158601555 | 17886999 |  |  | 152145333.202 | 72766815 | 81% | 20%
Total Development : |  |  | 48 |  |  | 43.404 | 103.8 | 996.18 | 498114695 | 52504589 | 517625173 | 1068244457 | 1904068 |  |  | 1103857942.992 | 634074552 | 67.08% | 57.41%
Grand Total Rangamati Dist: |  |  | 63 |  |  | 75.686 | 198.8 | 1091.18 | 635886650 | 54289954 | 517625268 | 1226846012 | 19791067 |  |  | 1256003276.194 | 706841367 | 74.04% | 38.71%
10
63

## Total
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2019-2020
Reporting Month:August' 2020
[15 empty] | Reporting date: |  |  | 2026-07-28
|  |  | As per approved DPP | [7 empty] | Approved Estimated Cost | [5 empty] | Total Contract |  | Total Fund spent till date (Tk) | Total Physical Progress (%) | Total Financial Progress (%) | Remarks
Sl. No. | District | Nature of Work | Total Scheme Nos | DPP Length |  |  | Estimated Cost (Tk) |  |  |  | Total Package No. | Approved Length |  |  | Total Approved Cost (Tk) | Salvage Cost (Tk) | Package No. | Contract Amount (Taka)
|  |  |  | Road (km) | Culvert (m) | Bridge (m) | Road | Culvert | Bridge | Total |  | Road (km) | Culvert (m) | Bridge (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Bandarban | Dev/Rehab/Bridge | 18 | 53.36 | 125.55 | 776 | 554102760 | 56497500 | 504400000 | 1115000260 | 65 | 76.035 | 69.5 | 909 | 1598393796.37 | 93569669.67 | 0 | 1555861763.613 | 1206986939 | 0% | 0%
|  | Maint. | 9 | 29.18 | 0 | 0 | 105000000 | 0 | 0 | 105000000 | 2 | 28.608 | 0 | 0 | 93488158 |  |  | 93950627.912 | 84726752
2 | Khagrachari | Dev/Rehab/Bridge | 23 | 62.45 | 90.1 | 361 | 744104700 | 40545000 | 234650000 | 1019299700 | 45 | 62.972 | 48.5 | 365.06 | 866109375.2 | 53032051.6 | 0 | 907820305.04 | 646640205 | 0% | 44.08%
|  | Maint. | 16 | 29.25 | 0 | 0 | 75000000 | 0 | 0 | 75000000 | 12 | 13.958 | 27.2 | 0 | 66406561 | 7966919 |  | 67034027.038 | 65532026
3 | Rangamati | Dev/Rehab/Bridge | 18 | 43.94 | 194 | 915 | 509949948 | 87300000 | 594750000 | 1191999948 | 48 | 43.404 | 103.8 | 996.18 | 1068244457 | 1904068 | 0 | 1103857942.992 | 634074552 | 74.04% | 38.71%
|  | Maint. | 16 | 29.18 | 0 | 0 | 105000000 | 0 | 0 | 105000000 | 15 | 32.282 | 0 | 0 | 158601555 | 17886999 |  | 152145333.202 | 72766815
Total 03 Districts |  |  | 100 | 247.36 | 409.65 | 2052 | 2093157408 | 184342500 | 1333800000 | 3611299908 | 187 | 257.259 | 249 | 2270.24 | 3851243902.57 | 174359707.27 | 0 | 3880669999.797 | 2710727289 | 24.68% | 27.6%

## Summry
cjøx AeKvVv‡gv Dbœqb cÖKít cve©Z¨ PÆMÖvg- 2q ch©vq cÖK‡íi 01-09-2020 ZvwiL ch©šÍ †gvU Aby‡gvw`Z iv¯Ívi Z_¨vw`
µt bs | ‡Rjv | wWwcwcf~³ Dc‡Rjv iv¯Ívi ˆ`N©¨ (wKtwgt) | Aby‡gvw`Z Dc‡Rjv iv¯Ívi ˆ`N©¨ (wKtwgt) | wWwcwcf~³ BDwbqb iv¯Ívi ˆ`N©¨ (wKtwgt) | Aby‡gvw`Z BDwbqb iv¯Ívi ˆ`N©¨ (wKtwgt) | wWwcwcf~³ Dc‡Rjv Ges BDwbqb iv¯Ívi †gvU ˆ`N©¨ (wKtwgt) | ‡gvU Aby‡gvw`Z ˆ`N©¨ (wKtwgt) | †gvU Aby‡gvw`Z g~j¨ (jÿ UvKvq) | c¨v‡KR msL¨v (wU) | Tender Approved msL¨v (wU) | Aby‡gvw`Z Pzw³g~j¨ (jÿ UvKvq)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1¦ | ev›`ievb | 8.08 | 2 | 45.28 | 26.53 | 53.36 | 104.643 | 16918.8195 | 75 | 75 | 16498.1239
2¦ | LvMovQwo | 35.05 | 23.52 | 27.4 | 11.125 | 62.45 | 76.93 | 9325.1594 | 57 | 57 | 9748.5433
3¦ | iv½vgvwU | 27 | 18.324 | 16.94 | 9.415 | 43.94 | 75.686 | 12268.4601 | 63 | 63 | 12560.0328
me©‡gvU= |  | 70.13 | 43.844 | 89.62 | 47.07 | 159.75 | 257.259 | 38512.439 | 195 | 195 | 38806.7

## Sheet2 (hidden)
Monthly Progress Report Under
Rural Infrastructure Development Project:Chitagoan Hill Tracts-2nd Phace
Financial Year 2015-2016
Reporting Month: July' 2017
[14 empty] | Reporting Date: |  |  |  |  | 2026-07-28
District Name: Bandarban
Sl. No. | Upazila | Name of Scheme with Chainage & ID No. | Package Nos. | Nature of Work | Approving date (H/Q) | Approved Length |  |  | Approved Estimated Cost (Taka) |  |  | Total Approved Estimated Cost (Taka) | Salvage Cost (Tk) | Date of Contract | Date of Completion | Contract Amount (Taka) | Fund spent till date (Tk) | Physical Progress to date (%) | Financial Progress to date (%) | Name of Contructor & Address | Remarks
[6 empty] | Road Length (Km) | Culvert Length (m) | Bridge Length (m) | Road | Culvert | Brigde
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | Sadar | Holudia-Vaggakul-Tankbati Road.(Ch.00-2000m), ID No.403143005 | BAN/SADR/UNR/W07 | BC | 21-01-06 | 2 | 0 |  | 22971805 | 0 | 0 | 22971805 | 7217924.56 | 2016-04-17 | 2017-05-14 | 17134949 | 15239564 | 100% | 88.94% | M/S Arpmilton (JV), Bandarban | Variation | 1
2 |  | Holudia-Vaggakul-Tankbati Road.(Ch.2000-3350m), ID No.403143005 | BAN/SADR/UNR/W08 | BC | 21-01-06 | 1.35 | 0 |  | 10735081.37 | 0 | 0 | 10735081.37 | 4040354 | 2016-04-17 | 2017-05-14 | 8271466.22 | 8271473 | 100% | 100% | M/S Milton Traders, Bandarban | Variation | 1
3 |  | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road. (Ch.2950-5500m), ID No.403143002 | BAN/SADR/UNR/W11 | BC | 28-02-06 | 2.55 | 0 |  | 19912233 | 0 | 0 | 19912233 | 5752819 | 2016-06-09 | 2017-07-16 | 16433913.837 | 7943105 | 70% | 0% | S. Ananta Bikash Tripura, Milonpur, Khagrachari |  | 1
4 |  | Udalbunia-Jhanka Road start from Udalbunia - Rajvilla Road.(Ch.5500-7060m), ID No.403143002 | BAN/SADR/UNR/W12 | BC | 28-02-06 | 1.56 | 0 |  | 10029323 | 0 | 0 | 10029323 | 3479495 | 2016-06-30 | 2017-07-07 | 8499091.269 | 0 | 5% | 0% | M/S Emu Construction Chairman Market, Bandarban |  | 1
5 |  | Construction of 12.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 780.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W19 | Bridge | 2016-09-06 |  |  | 12 |  |  | 6070959 | 6070959 |  | 2017-01-08 | 2017-12-17 | 4798913.42 | 2975800 | 75% | 0 | Mr.UT Mong,Maddayum Para Bandarban |  | 1
6 |  | Construction of 18.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 1430.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W20 | Bridge | 2016-09-06 |  |  | 18 |  |  | 6785192 | 6785192 |  | 2017-01-08 | 2017-12-17 | 5278818.477 | 2658000 | 65% | 0 | M/S Milton Traders, Rowangchari |  | 1
7 |  | Construction of 18.0m long RCC Girder Bridge on Holudia – Vaggakul – Tonkabati via Chimbuk R & H road at ch. 3015.0m ID No: 403143005 | WD/RIDPCHT-2/BAN/ SADAR/ BRIDGE/W21 | Bridge | 2016-09-06 |  |  | 18 |  |  | 7181549 | 7181549 |  | 2017-01-08 | 2017-12-17 | 5558074.95 | 3269916 | 65% | 0 | M/S Milton Traders, Rowangchari |  | 1
Sadar Sub-Total : |  |  | 7 |  |  | 7.46 | 0 | 48 | 63648442.37 | 0 | 20037700 | 83686142.37 | 20490592.56 |  |  | 65975227.173 | 40357858 | 68.75% | 26.99%
1 | Thanchi | Thanchi-Balipara road. (Ch.00-1000m), ID No.403952001 | BAN/THAN/UZR/W02 | BC | 25-10-15 | 1 | 0 |  | 15630432 | 5528250 | 0 | 21158682 | 0 | 2016-02-15 | 2017-02-22 | 18436599.688 | 9885059 | 70% | 53.62% | M/S Milton Traders, Rowangchari | Box cutting Ges protection Gi KvR Pj‡Q | 1
2 |  | Thanchi-Balipara road. (Ch.1000-2000m), ID No.403952001 | BAN/THAN/UZR/W13 | BC | 28-02-15 | 1 | 0 |  | 10976788 | 0 | 0 | 10976788 | 0 | 2016-06-30 | 2017-07-07 | 9739608.14 | 4078464 | 70% | 41.88% | Mr.UT Mong,Maddayum Para Bandarban |  | 1
3 |  | Construction of 20.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 2467.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W24 | Bridge | 2017-02-01 |  |  | 20 | Brigde 11: 9870616; Brigde 12: 9870616; Brigde 16: 9869497.947; Brigde 20: M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. | 1
4 |  | Construction of 20.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 3623.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W25 | Bridge | 2017-02-01 |  |  | 20 | Brigde 11: 12644983; Brigde 12: 12644983; Brigde 16: 12644266.304; Brigde 20: M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. | 1
5 |  | Construction of 45.0m long RCC Girder Bridge on Thanchi-Balipara road at ch. 1958.0m ID No: 403952001 | BAN/ THANCHI/ BRIDGE/W26 | Bridge | 2017-02-01 |  |  | 45 | Brigde 11: 16636441; Brigde 12: 16636441; Brigde 16: 14972796.9; Brigde 20: M/S M M Traders, M R Pharmacy, Bandarban Bazar, Bandarban. | 1
6 |  | Rehabilitation of Thanchi-Balipara road. (Ch.2+000-3+000m); ID No: 403952001 | WD/RIDPCHT-2/ BAN/ THANCHI/ UZR/W43 | BC | 2017-06-11 | 1 | 0 | 0 | Road 9: 17736535; Brigde 12: 17736535; Brigde 21: APP Apprpved Date: 05-07-17
Thanchi Sub-Total : |  |  | 6 |  |  | 3 | 0 | 85 | 44343755 | 5528250 | 39152040 | 89024045 | 0 |  |  | 65662768.979 | 13963523 | 11.67% | 8.936%
1 | Alikadam | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 00-1000m), ID No.403043007 | BAN/ALI/ UNR/W03 | BC | 15-11-15 | 1 | 0 | 0 | 8267241 | 1297011 | 0 | 9564252 | 1613216 | 2016-03-16 | 2017-03-17 | 8121080.587 | 8117349 | 100% | 99.95% | M/S Milton Traders, Rowangchari | 750m sub-base n‡q‡Q Ges WBM , 2 nos culvert Gi KvR Pj‡Q | 1
2 |  | Fasiakhali - Alikadam main (R&H) road- Alis Suronga road (ch. 1000-2600m), ID No.403043007 | BAN/ALI/ UNR/W10 | BC | 14-02-16 | 1.6 | 0 | 0 | 13307610 | 1987879 | 0 | 15295489 | 349138 | 2016-05-25 | 2017-06-02 | 13597665.717 | 13364051 | 100% | 98.28% | M/S Emmu Construction, Rowangchari, Bandarban |  | 1
3 |  | Improvement of Alikadam-Dochori Road (ch.00-2020m), ID No.403043004 | BAN/ALI/ UNR/W14 | BC | 21-03-2016 | 2.02 | 0 | 0 | 13037259 | 0 | 0 | 13037259 | 4614359 | 2016-07-25 | 2017-08-01 | 10729459.801 | 0 | 25% | 0% | M/S Prasanna kant Amu, Hospital raod, Bandarban |  | 1
4 |  | Construction of 81.00m long PSC Gider Bridge on Alikadam Bazar- Naikhongchari Border via Rombow road. Ch.1193m) ID No: 403042002 | BAN/ ALI / BRIDGE/W22 | Bridge | 2016-10-23 |  | 0 | 81 | 44255971 | 0 | 0 | 44255971 |  | 2017-03-29 | 2018-06-03 | 39677176.309 | 0 | 5% |  | M/S Noor Syndicate, Pachalish,Chittagong |  | 1
5 |  | Improvement of Alikadam Bazar- Naikhongchari Border via Rombow road. (Ch.00-2880m) ID No. 403042002 | WD/RIDPCHT-2/BAN/ALIKADAM/UZR/W39 | BC | 2017-06-08 | 2.88 | 0 | 0 | Road 9: 24720436; Brigde 12: 24720436; Brigde 13: 2507186; Brigde 21: APP Apprpved Date: 12-07-17
6 |  | Improvement of Sonaichori R&H-Varirmukh Road.(Ch.821-1571m) ID No. 403043005 | WD/RIDPCHT-2/BAN/ALIKADAM/ UNR/W40 | BC | 2017-06-08 | 0.75 | 1.6 | 0 | Road 9: 6323746; Culvert 10: 476351; Brigde 12: 6800097; Brigde 13: 482496; Brigde 21: APP Apprpved Date: 12-07-17
7 |  | Improvement of Chikkan para (cioni para) road (Ch.1441-2191m) ID No. 403043006 | WD/RIDPCHT-2/BAN/ALIKADAM/ UNR/W41 | BC | 2017-06-08 | 0.75 | 3.5 |  | Road 9: 4771148; Culvert 10: 1621901; Brigde 12: 6393049; Brigde 13: 269554; Brigde 21: APP Apprpved Date: 12-07-17
Alikadam Sub-Total : |  |  | 7 |  |  | 9 | 5.1 | 81 | 114683411 | 5383142 | 0 | 120066553 | 9835949 |  |  | 72125382.414 | 21481400 | 29.29% | 28.32%
1 | Rowangchari | Development of Kalaghata to Taracha UP office road at Ch.00-1000m, ID No.403893004 | BAN/ROW/UNR/W01 | BC | 25/10/2015 | 1 | 4.5 | 0 | 7665778 | 2161700 | 0 | 9827478 | 1119803 | 2016-02-16 | 2017-02-15 | 8044900.029 | 5335885 | 75% | 66.33% | M/S Milton Traders, Rowangchari | WBM ‡kl n‡q‡Q¦ | 1
2 |  | Development of Kalaghata to Taracha UP office road at Ch.1000-3000m, ID No. 403893004 | BAN/ROW/UNR/W15 | BC | 21-03-2016 | 2 | 6.4 | 0 | 22470615 | 1725180 | 0 | 24195795 | 4769663 | 2016-06-07 | 2017-07-23 | 19457598.284 | 12950245 | 75% | 66.56% | Mr.UT Mong,Maddayum Para Bandarban |  | 1
3 |  | Construction of 60.0m long RCC Girder Bridge on Kalaghata to Taracha UP office road at Ch.2885m, ID No: 403893004 | BAN/ROW/BRIDGE/W31 | Bridge | 2017-04-20 |  |  | 60 | Brigde 11: 26134485; Brigde 12: 26134485; Brigde 16: 23521036.5; Brigde 20: S. Ananta Bikash Tripura, Milonpur, Khagrachari | 1
Rowangchari Sub-Total : |  |  | 3 |  |  | 3 | 10.9 | 60 | 30136393 | 3886880 | 26134485 | 60157758 | 5889466 |  |  | 51023534.813 | 18286130 | 50% | 44.29%
1 | Naikhonchari | Naikhongchari - Lemouchari road.(Ch.00-1000m), ID No.403733001 | BAN/NAIK/UNR/W04 | BC | 2015-02-12 | 1 | 9 | 0 | 9088672 | 2982164 | 0 | 12070836 | 2401589 | 2016-03-07 | 2017-03-06 | 9658461.68 | 7382035 | 95% | 76.43% | M/S Milton Traders, Rowangchari | Variation | 1
2 |  | Naikhongchari - Lemouchari road.(Ch.1000-2500m), ID No.403733001 | BAN/NAIK/UNR/W05 | BC | 28-12-15 | 1.5 | 0 | 0 | 12914033 | 0 | 0 | 12914033 | 3535057 | 2016-03-10 | 2017-03-09 | 10509159.843 | 8818029 | 95% | 83.91% | M/S Emmu Construction , Bandarban |  | 1
3 |  | Naikhongchari - Lemouchari road.(Ch.2500-4000m), ID No.403733001 | BAN/NAIK/UNR/W06 | BC | 28-12-15 | 1.5 | 0 | 0 | 13616480 | 0 | 0 | 13616480 | 3520106 | 2016-03-10 | 2017-03-09 | 11062329.59 | 8280876 | 90% | 74.86% | M/S Emmu Construction , Bandarban |  | 1
4 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.2600-4100m, ID No.403733008 | BAN/NAIK/UNR/W09 | HBB | 28-01-16 | 1.5 | 0 | 0 | 11512651 | 0 | 0 | 11512651 | 0 | 2016-06-30 | 2017-07-07 | 9275721.942 | 0 | 10% | 0% | S. Ananta Bikash Tripura, Milonpur, Khagrachari |  | 1
5 |  | Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.4100-5100m, ID No.403733008 | BAN/NAIK/UNR/W18 | HBB | 2016-04-27 | 1 | 4.5 | 0 | 8369888 | 1416240 | 0 | 9786128 | 0 |  |  | 9264612.157 | 0 | 0% |  | Mr. U.T Mong Madhyampara, Bandarban |  | 1
6 |  | Construction of 85.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.1600m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W32 | Bridge | 2017-04-20 |  |  | 85 | Brigde 11: 30356111; Brigde 12: 30356111; Brigde 16: 27320499.9; Brigde 20: Mr. U.T Mong Madhyampara, Bandarban | 1
7 |  | Construction of 36.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.3780m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W33 | Bridge | 2017-04-20 |  |  | 36 | Brigde 11: 18179251; Brigde 12: 18179251; Brigde 21: Tender Receive Date: 30-05-17
8 |  | Construction of 85.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road) Ch.4970m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W34 | Bridge | 2016-04-24 |  |  | 85 | Brigde 11: 28151740; Brigde 12: 28151740; Brigde 21: APP Apprpved Date: 11-05-17
9 |  | Construction of 33.0m long RCC Girder Bridge on North Ghumdum - Tumbru Bazar road.Ch.2600m ID No: 403733003 | BAN/ NAIKHONG / BRIDGE/W35 | Bridge | 2016-04-24 |  |  | 33 | Brigde 11: 18085536; Brigde 12: 18085536; Brigde 21: APP Apprpved Date: 11-05-17
10 |  | Construction of 33.0m long RCC Girder Bridge on Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road. Ch.3000m ID No: 403733002 | BAN/ NAIKHONG / BRIDGE/W36 | Bridge | 2016-04-24 |  |  | 33 | Brigde 11: 18151717; Brigde 12: 18151717; Brigde 21: APP Apprpved Date: 11-05-17
11 |  | Improvement of Dochori - Ali Kadam road .(Ch.00-3000m); ID No: 403733004 | BAN/ NAIKHONG/ UNR/W37 | BC | 2017-04-25 | 3 | 0 | 0 | Road 9: 24633854; Brigde 12: 24633854; Brigde 21: Tender Receive Date: 20-06-17
12 |  | Improvement of Baishari Bazar - Dochari Bazar via Longgudhu mukh Bakkhali road .(Ch.00-3180m); ID No: 403733002 | BAN/ NAIKHONG/ UNR/W38 | BC | 2017-04-25 | 3.18 | 0 | 0 | Road 9: 24755606; Brigde 12: 24755606; Brigde 21: Tender Receive Date: 20-06-17
13 |  | Construction of 33.0m long RCC Girder Bridge on Lemuchari BDR Camp-Bahirmath-Kalurghat Road.(Lemuchari BGB Camp-Mathongpara Road via Kalurghat-Painchari Murongpara road). (Dochari UP office (Lemochari)-Powamohuri Bazar via Kalurghat, Painchari Bazar BGB camp & Dochari BGB Camp, Murong para BGB Camp Road) Ch.9800m ID No: 403733008 | BAN/ NAIKHONG / BRIDGE/W42 | Bridge | 2017-06-08 | 0 | 0 | 33 | Brigde 11: 14373533; Brigde 12: 14373533; Brigde 21: APP Apprpved Date: 12-07-17
Naikhongchari Sub-Total : |  |  | 13 |  |  | 12.68 | 13.5 | 305 | 104891184 | 4398404 | 127297888 | 236587476 | 9456752 |  |  | 77090785.112 | 24480940 | 22.31% | 18.09%
1 | Ruma | Construction of 66.0m long RCC Girder Bridge on Thana HQ (Ruma Mukh)-Gallanga UP office Road. Ch.850m ID No.403913003 | BAN/RUMA/BRIDGE/W27 | Bridge | 2017-02-24 |  |  | 66 | Brigde 11: 24564086; Brigde 12: 24564086; Brigde 16: 25327853.157; Brigde 20: M/S Abser Construction, Bandarban | 1
2 |  | Construction of 68.0m long PSC & RCC Girder Bridge on Thana HQ (Ruma Mukh)-Gallanga UP office Road. Ch.850m ID No.403913003 | BAN/RUMA/BRIDGE/W28 | Bridge | 2017-03-14 |  |  | 68 | Brigde 11: 36527218; Brigde 12: 36527218; Brigde 16: 39841279.01; Brigde 20: Mohammed Eunus & Brothers (Pvt) Ltd, Chittagong. | 1
Ruma Sub-Total : |  |  | 2 |  |  |  |  | 134 | Road 9: 0; Culvert 10: 0; Brigde 11: 61091304; Brigde 12: 61091304; Brigde 13: 0; Brigde 16: 65169132.167
1 | Lama | Imrovement of Lama muk-Selertua road Ch.00-3300m ID No.403513008 (Old 3007) | BAN/LAMA/UNR/W16 | HBB | 2016-04-10 | 3.3 | 9 | 0 | 17474100.89 | 3072269.11 | 0 | 20546370 | 0 | 2016-08-28 | 2017-09-05 | 16031768.31 | 8786311 | 80% | 54.81% | S. Ananta Bikash Tripura, Milonpur, Khagrachari |  | 1
2 |  | Improvement of Shelertua-Rupashi Para Road Ch.00-1650m, ID No.403513011 (Old 3010) | BAN/LAMA/UNR/W17 | HBB | 2016-04-10 | 1.65 | 4.5 | 0 | 12367431.26 | 1524775.74 | 0 | 13892207 | 0 | 2016-06-30 | 2017-07-07 | 11075616.627 | 3355670 | 45% | 30.3% | M/S Abser Construction, Bandarban |  | 1
3 |  | Construction of 33.0m long RCC Girder Bridge on Shelertua-Rupashi Para Road at ch. 930m ID No: 403513010 | BAN/ LAMA/ BRIDGE/W29 | Bridge | 2017-04-11 |  |  | 33 | Brigde 11: 19899758; Brigde 12: 19899758; Brigde 16: 17909782.2; Brigde 20: Mr U T Mong, Madhyampara, Bandarban | 1
4 |  | Improvement of Polokhal Tetulia Moor-Quantum Cosmo College via Bodhechora public School Road. by HBB at (Ch.0+000 to 2+480km) ID No: 403515105 | BAN/LAMA/ V.Road/W44 | HBB | 2017-06-22 | 2.48 |  |  | Road 9: 15801353; Culvert 10: 1945321; Brigde 12: 17746674
5 |  | Improvement of Bodhe Chora Bamboorian Mor - Quantum Shabujan Pry School via Ground Olympian & Chompajhiri Para Mor Road by HBB at (Ch.0+000 to 2+500km) ID No: 403515106 | BAN/LAMA/ V.Road/W45 | HBB | 2017-06-22 | 2.5 |  |  | Road 9: 10827188; Brigde 12: 10827188
Lama Sub-Total : |  |  | 5 |  |  | 9.93 | 13.5 | 33 | 56470073.15 | 6542365.85 | 19899758 | 82912197 | 0 |  |  | 45017167.137 | 12141981 | 25% | 17.02%
Maintenance Work
1 | Sadar | Periodic Maintenance of Balaghata-Bagman Bazar Road start from B-ban Chandraghona. (Ch.5000-8000m) ID No: 403143003 | BAN/SADAR/ UNR/W23 | BC | 2016-11-27 | 3 |  |  | 10384827 |  |  | 10384827 |  | 2017-05-07 | 2018-03-15 | 9346344.3 | 6000000 | 75% |  | M/S marma enterprise, Mayd ampara, Bandarban |  | 1
2 |  | Khanshama-Bagmara road start B-Ban Rowangchari Road.(Ch.2500-7313m) ID No: 403142002 | BAN/SADAR/UZR/W30 | HBB | 2017-04-11 | 4.813 |  |  | Road 9: 10963617; Brigde 12: 10963617; Brigde 16: 9867255.3; Brigde 20: M/S Selim & Brothers, Baitus Sharaf Mosque Road, Arambag, Khagrachari. | 1
|  |  | 2 |  |  | 7.813 |  |  | Road 9: 21348444; Brigde 12: 21348444; Brigde 16: 19213599.6; Brigde 17: 6000000
|  | Total Maintenance : | 2 |  |  | 7.813 | 0 |  | 21348444 | 0 | 0 | 21348444 | 0 |  |  | 19213599.6 | 6000000 | 0% | 0%
Total Development : |  |  | 43 |  |  | 45.07 | 43 | 746 | 414173258.52 | 25739041.85 | 293613175 | 733525475.37 | 45672759.56 |  |  | 442063997.795 | 130711832 | 34.5% | 21.11%
Grand Total Bandarban Dist: |  |  | 45 |  |  | 52.883 | 43 | 746 | 435521702.52 | 25739041.85 | 293613175 | 754873919.37 | 45672759.56 |  |  | 461277597.395 | 136711832 | 34.5% | 21.11%
32
[13 empty] | Total Contract Package : |  |  | 32