## Summary AWPB
PART-II
Annual Work Plan & Budget (AWPB) Summary (2020-2021)
Project Code : 224243100
Project Titel: Promoting Resilience of Vulnerable through Access to Infrastructure, Improved Skills and Information (PROVATi³)
Financial Year: 2020-2021
(BDT in lac; AWPB prepared on base cost)
| Objective and Expected Results | Indicator | RIMS CORE Indicators | Implementation Target | [7 empty] | Budget
|  |  |  | Approved DPP (total) | Revised (total) | Planned (annual) | Unit cost | Achieved (cumulative) | % | Achieved (annual) | % | Approved DPP (total) | Revised (total) | Planned (annual) | Budget category | Spent (cumulative) | % | Spent (annual 2019-20) | % | Comments
| Development Objective: Enhanced resilience of population of selected flood-prone Upazilas | Percentage increase in income of extreme poor households (disaggregated by sex of HH head) | RIMS Core Indicator (outreach) 1.a Corresponding number of households reached
Com.1 | Climate Resilient Rural Infrastructure & Community Shelters | Percentage of infrastructure that are fully functional and maintained one year after rehabilitiation/up-grading
S.Com 1.1 | OUTPUT 1.1 Climate change Flood / Preparedness Research for Building Climate Resilient Infrastructure | Number of design standards incorporating climate change/resilient aspects |  | 3 |  | 1.5 | Nos | 1.5 | 50 | 1.5 | 50 | 206.95 |  | 105 | II, III, IV & V (IFAD Grant) | 100.5 | 48.56 | 100.5 | 48.56
S.Com 1.2 | OUTOUT 1.2 Climte Resilient Rural Communication Infrastructure Built | 1) Kilometers of village and Union road upgraded/paved; 2) Kilometers of road rehabiliated | RIMS Core Indicator 2.1.5 Number of kilometres of roads constructed, rehabilitated or upgraded. | 381 |  | 94.16 | Km | 21.63 | 5.67 | 7.26 | 1.9 | 39435.76 |  | 8455.77 | I(IFAD Loan) | 3962.64 | 10.05 | 3241.21 | 8.22
S.Com 1.3 | OUTPUT 1.3 Climate Resilent Rural Market Developed | Number of rural markets built in project area | RIMS Core Indicator 2.1.6 Number of market, processing or storage facilities constructed or rehabilitated | 135 |  | 39 | Nos | 0 | 0 | 0 | 0 | 12331.4 |  | 2689.71 | I(IFAD Loan) | 452.38 | 3.67 | 425.07 | 3.45
S.Com 1.4 | OUTPUT 1.4 Climate Resilent Community Shelter cum School | Number of school-cum flood shelters newly built in charlands |  | 20 (15) |  | 0 | Nos | 0 | 0 | 0 | 0 | 2996 |  | 4.57 | I(IFAD Loan) | 18.6 | 0.62 | 18.6 | 0.62
S.Com 1.5 | OUTPUT 1.5 Training on Climate/Flood proof Resilient Infrastructure Design and Construction | Number of engineers trained on climate resilient infrastructure |  | 6 |  | 2 |  | 0 | 0 | 0 | 0 | 60 |  | 35 | III(IFAD Loan) | 0 | 0 | 0 | 0
Total Budget for Component 1: | [11 empty] | 55030.11 |  | 11290.05 |  | 4534.12 | 8.24 | 3785.38 | 6.88
Com. 2 | Resilent Communities Through Employment and Early Flood Warning | Percetage of beneficiaries report increased empowerment and resilience (scored 2)
S.Com 2.1 | OUTPUT 2.1 Capacity building of LCS members and Livelihoods Developed | Number of LCS households trained in IGA and business management(by sex) | 1) RIMS Core Indicator 2.1.2 Number of persons trained in income-generating activities or business management. 2) RIMS Core Indicator 1.1.8 Number of person/households provided with trageted support to improve their nutrition | 15000 |  | 2000 | LS | 0 | 0 | 0 | 0 | 1912 |  | 330.5 | III(IFAD Loan) | 0 | 0 | 0 | 0
S.Com 2.2 | OUTPUT 2.2 Vocatioanl training for Off-farm Employment | Number of VT youths employed (disaggregated by sex) 1 year after completing training |  | 30000 |  | 5000 | Persons | 0 | 0 | 0 | 0 | 3621 |  | 1023.69 | III(IFAD Loan) | 0 | 0 | 0 | 0
S.Com 2.3 | OUTPUT 2.3 Development of Accurate Local Flood Warning and Dissemination System | Number of vulnerable unions in project area received and used flood early warning information | RIMS Core Indicator 3.1.2 Number of persons provided with climate information services | 29 |  | LS | LS | 0 | 0 | 0 | 0 | 1894.6 |  | 204.38 | III(IFAD Loan) | 0 | 0 | 0 | 0
S.Com 2.4 | OUTPUT 2.4 Parcical Policy Actions | Number of policy-relevant reviews completed | RIMS Core Indicator, Pollicy 1 - Number of policy-relevant knowledge products completed | 7 |  | 1 | Nos | 0 | 0 | 0 | 0 | 848.64 |  | 120.56 | III.IV (IFAD Loan, Grant) | 90 | 10.61 | 90 | 10.61
Total Budget for Component 2: | [11 empty] | 8276.24 |  | 1679.13 |  | 90 | 1.09 | 90 | 1.09
Com. 3 | Project Management | Project is in place
S.Com 3.1 | OUTPUT 3.1 Project Management and Technical Support | All units including PMU and at Field level fully functional |  | LS |  | LS | LS |  |  |  |  | 4895.75 |  | 762.05 | V(IFAD Loan) | 594.53 | 12.14 | 335.44 | 6.85
Total Budget for Component 3: | [11 empty] | 4895.75 |  | 762.05 |  | 594.53 | 12.14 | 335.44 | 6.85
[8 empty] | Total Budget |  |  |  | 68202.1 |  | 13731.23 |  | 5218.65 | 7.65 | 4210.82 | 6.17

## Detailed AWPB Com-1
Detailed Annual Work Plan & Budget (AWPB), Component-1: Climate Resilient Rural Infrastructure & Community Shelters
Project Code : 224243100
Project Titel: Promoting Resilience of Vulnerable through Access to Infrastructure, Improved Skills and Information (PROVATi³)
Financial Year: 2020-2021
| (BDT in lac; AWPB prepared on base cost) | [32 empty] | BDT in Lakh Taka
| Particulars of Cost | Project Indicators | RIMS Indicator | Responsible Unit/ Agency | Unit | Tompro Code | Economic code | Physical Implementation targets of 2020-2021 | [7 empty] | Budget | [6 empty] | Expenditure | [9 empty] | Remarks |  |  |  |  | Remarks
[8 empty] | DPP (Total) | To be Revised (Total) | Planned (Annual) for 2020-2021 | Procurement Method | Achieved (Cumulative) Upto June/20 | % | Achieved (Annual) in 2019-2020 | % | DPP (Total) | To be Revised (Total) | Planned (Annual) for 2020-2021 | Budget Category | Plan for 2020-21 |  |  | Spent (Cumulative) upto June 2020 |  |  |  |  | Spent (Annual)-2019-20 | [5 empty] | Spent (Annual)-2018-19
[20 empty] | IFAD Loan | IFAD Grant | GOB | IFAD Laon | IFAD Grant | GOB | Total | % | IFAD | IFAD Grant | GOB | Total | % |  | IFAD | GOB | Total | %
| (A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) | (J) | (K) | (L) | (M) | (N) | (O) | (P) | (Q) | (R) | (S) | (T) | (U) | (V) | (W) | (X) | (Y) | (Z) | (AA) | (AB) | (AC) | (AD) | (AE) | (AF) | (AG) | (W) |  |  |  | (X)
C1 | (A): Componenet -1: Climate Resilient Rural Infrastructure & Community Shelters
SC 1.1 | (A): Sub Comp 1.1 : Climate change flood/ preparedness research for building climate resilient infrastructure; (B): Infrastructure design standards updated based on climate change assessment researches; (G): 4829 (i)
A. Programme/Acitvity
| 1.1.1 Research Works & Dissemination |  |  | BUET | No |  | 4829(i) | 3 |  | 1.5 |  | 1.5 | 50 | 1.5 | 50 | 30.53 |  | 15.53 | III & V (IFAD Grant) | 0 | 15.53 | 0 | 0 | 15 | 0 | 15 | 49.132 | 0 | 15 | 0 | 15 | 49.132
| Sub Total: A (BUET expenses for research work and dessmination) | [14 empty] | 30.5287 |  | 15.53 |  | 0 | 15.53 | 0 | 0 | 15 | 0 | 15 | 49.134 | 0 | 15 | 0 | 15 | 49.134
B. Acquisition of Asset ( vehicle/equipment/material)
| Different Equipment for Research Work |  |  | BUET | No/Sets |  | 4829(v) | LS |  |  |  |  | 51.64 |  | 51.64 | 11.52 |  | 5.57 | II (IFAD Grant) | 0 | 5.57 | 0 | 0 | 5.95 | 0 | 5.95 | 51.6493 | 0 | 5.95 | 0 | 5.95 | 51.6493
| Sub-Total: B | [14 empty] | 11.5227 |  | 5.57 |  | 0 | 5.57 | 0 | 0 | 5.95 | 0 | 5.95 | 51.6371 | 0 | 5.95 | 0 | 5.95 | 51.6371
C. Recurrent Cost ( service/maintenance/ travelling/stationary/printing etc.)
| Consultancy by BUET Staff for Research Work |  |  | BUET | MM |  | 4829(iv) | 85 |  |  |  | 41 | 48 | 41 | 48 | 158.43 |  | 80.43 | IV(IFAD Grant) | 0 | 80.43 | 0 | 0 | 76.55 | 0 | 76.55 | 48.3179 | 0 | 76.55 | 0 | 76.55 | 48.3179
| Field Visit |  |  | BUET | LS |  | 4829(ii) | LS |  |  |  | LS |  | LS |  | 4.53 |  | 2.53 | V(IFAD Grant) | 0 | 2.53 | 0 | 0 | 2 | 0 | 2 | 44.1501 | 0 | 2 | 0 | 2 | 44.1501
| Travelling, Stationary, Printing etc. |  |  | BUET | LS |  | 4829(iii) | LS |  |  |  | LS |  | LS |  | 1.94 |  | 0.94 | V(IFAD Grant) | 0 | 0.94 | 0 | 0 | 1 | 0 | 1 | 51.5464 | 0 | 1 | 0 | 1 | 51.5464
| (A): Sub-Total:C; (P): 164.9; (R): 83.9; IFAD Loan (T): 0; IFAD Grant (U): 83.9; GOB (V): 0; IFAD Laon (W): 0; IFAD Grant (X): 79.55; GOB (Y): 0; Total (Z): 79.55; % (AA): 48.2414; IFAD (AB): 0; IFAD Grant (AC): 79.55; GOB (AD): 0; Total (AE): 79.55; % (AF): 48.2414; IFAD (W): 0 | 0 | 0
| (A): Total of Sub Component (1.1); (J): 1.5; (P): 206.9515; (R): 105; IFAD Loan (T): 0; IFAD Grant (U): 105; GOB (V): 0; IFAD Laon (W): 0; IFAD Grant (X): 100.5; GOB (Y): 0; Total (Z): 100.5; % (AA): 48.5621; IFAD (AB): 0; IFAD Grant (AC): 100.5; GOB (AD): 0; Total (AE): 100.5; % (AF): 48.5621; IFAD (W): 0 | 0 | 0
SC 1.2 | (A): Sub Comp 1.2 : Climate Resilient Rural Communication Infrastructure Built; (B): Climate resilient rural communication infrastructure constructed
A. Programme/Acitvity
| 1.2.1Union Road BC |  |  | PMU, PIU | Km | C1201 | 7031 (i) | 61 |  | 20.41 |  | 5.66 | 9.279% | 1 | 1.639% | 5602 |  | 1867.32 | I (IFAD Loan) | 1655.38 | 0 | 211.94 | 808.82 | 0 | 117.72 | 926.54 | 16.5395 | 727.82 | 0 | 95.72 | 823.54 | 14.7008 |  | 66.087 | 0 | 66.087
| 1.2.2 Village Road BC |  |  | PMU, PIU | Km | C1202 | 7031 (ii) | 235 |  | 44.42 |  | 14.58 | 6.204% | 6.26 | 2.664% | 20309 |  | 3838.4 | I (IFAD Loan) | 3402.74 | 0 | 435.66 | 2319.96 | 0 | 560.29 | 2880.25 | 14.1821 | 2000.4 | 0 | 394.98 | 2395.38 | 11.7947 |  | 300 | 0 | 300
| 1.2.3 Village Road HBB/RCC |  |  | PMU, PIU | Km | C1203 | 7031 (iii) | 25 |  | 4.57 |  | 1.39 | 5.56% | 0 | 0% | 1449 |  | 265.02 | I (IFAD Loan) | 234.94 | 0 | 30.08 | 7.29 | 0 | 0 | 7.29 | 0.50311 | 7.29 | 0 | 0 | 7.29 | 0.50311 |  |  |  | 0
| 1.2.4 Construction of Culvert and Cross-Drainage Structures |  |  | PMU, PIU | m | C1204 | 7031 (iv) | 1688 |  | 255.79 |  | 14.18 | 0.84% | 9.3 | 0.5509% | 8813 |  | 1335.2 | I (IFAD Loan) | 1183.65 | 0 | 151.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.2.5 Rehabilitation of Roads |  |  | PMU,PIU | Km | C1205 | 7031(v) | 60 |  | 24.76 |  | 0 | 0% | 0 | 0% | 1696.5 |  | 700 | I (IFAD Loan) | 620.55 | 0 | 79.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.2.6 LCS Capacity Building Training on Road Maintentance |  |  | PMU,PIU | Nos | C1206 | 4840 | 822 |  | 200 |  | 0 | 0% | 0 | 0% | 99.36 |  | 48.35 | III (IFAD Loan) | 42.31 | 0 | 6.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.2.7 Rural Road Maintenance (Material & Wages of LCS) |  |  | PMU,PIU | Km | C1207 | 4941 | 411 |  | 90 |  | 0 | 0% | 0 | 0% | 969.96 |  | 208.25 | III (IFAD Loan) | 182.22 | 0 | 26.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total: A; (P): 38938.82; (R): 8262.54; IFAD Loan (T): 7321.79; IFAD Grant (U): 0; GOB (V): 940.75; IFAD Laon (W): 3136.07; IFAD Grant (X): 0; GOB (Y): 678.01; Total (Z): 3814.08; % (AA): 9.7951; IFAD (AB): 2735.51; IFAD Grant (AC): 0; GOB (AD): 490.7; Total (AE): 3226.21; % (AF): 8.2853; IFAD (W): 366.087 | 0 | 366.087 | 0 | 0
| (A): B. Acquisition of Asset ( vehicle/equipment/material) |  | 0
| Vechiles for PMU+PIU (4WD pickups) |  |  | PMU | Nos. | C1208 | 6807 (iii) | 4 |  | 2 |  | 2 | 50% | 2 | 50% | 208 |  | 116 | II (IFAD Loan) | 101.5 | 0 | 14.5 | 82.6 | 0 | 8 | 90.6 | 43.5577 | 0 | 0 | 8 | 8 | 3.8462 |  |  |  | 0
| Motorbikes |  |  | PMU, PIU | Nos. | C1209 | 6807 (iv) | 36 |  | NA |  | 36 | 100% | 36 | 100% | 81 |  | 0 | II (IFAD Loan) | 0 | 0 | 0 | 48.94 | 0 | 7 | 55.94 | 69.0617 | 0 | 0 | 7 | 7 | 8.642 |  |  |  | 0
| Engneering Material |  |  | PMU, PIU | LS | C1210 | 6814 | LS |  | LS |  | 0 | 0% | 0 | 0% | 132.94 |  | 67.23 | II (IFAD Loan) | 58.83 | 0 | 8.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total: B; (P): 421.94; (R): 183.23; IFAD Loan (T): 160.33; IFAD Grant (U): 0; GOB (V): 22.9; IFAD Laon (W): 131.54; IFAD Grant (X): 0; GOB (Y): 15; Total (Z): 146.54; % (AA): 34.7301; IFAD (AB): 0; IFAD Grant (AC): 0; GOB (AD): 15; Total (AE): 15; % (AF): 3.555; IFAD (W): 0 | 0 | 0 | 0 | 0
| (A): C. Recurrent Cost ( service/maintenance/ travelling/stationary/printing etc.) |  | 0
| PMU + PIU Motorcycle and Service Vehicle |  |  | PMU,PIU | VY |  | 4901 | 144/76 |  | LS | [5 empty] | 75 |  | 10 | II (IFAD Loan) | 8.75 | 0 | 1.25 | 2.016 | 0 | 0 | 2.016 | 2.688 | 0 | 0 | 0 | 0 | 0 |  | 2.016 |  | 2.016
| (A): Sub-Total : C; (P): 75; (R): 10; IFAD Loan (T): 8.75; IFAD Grant (U): 0; GOB (V): 1.25; IFAD Laon (W): 2.016; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 2.016; % (AA): 2.688; IFAD (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0; IFAD (W): 2.016 | 0 | 2.016
| (A): Total of Sub-component (1.2); (P): 39435.76; (R): 8455.77; IFAD Loan (T): 7490.87; IFAD Grant (U): 0; GOB (V): 964.9; IFAD Laon (W): 3269.626; IFAD Grant (X): 0; GOB (Y): 693.01; Total (Z): 3962.636; % (AA): 10.0483; IFAD (AB): 2735.51; IFAD Grant (AC): 0; GOB (AD): 505.7; Total (AE): 3241.21; % (AF): 8.219; IFAD (W): 368.103 | 0 | 368.103
SC 1.3 | (A): Climate resilient rural market development; (B): Climate resilient rural market built |  | 0
| (A): A. Programme/Acitvity |  | 0
| 1.3.1 Resettlement of Shops |  |  | PMU,PIU | Nos | C1301 | 6941 | 135 |  | NA | [5 empty] | 25 |  | 0 | GOB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.3.2 Large Markets |  |  | PMU, PIU | Nos. | C1302 | 7031 | 20 |  | 9 |  | 0 | 0% | 0 | 0% | 1254 |  | 590.81 | I (IFAD Loan) | 496.28 | 0 | 94.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 185 | 185
| 1.3.3 Medium Market |  |  | PMU, PIU | Nos. | C1303 | 7031 | 100 |  | 20 |  | 0 | 0% | 0 | 0% | 4177 |  | 835.4 | I (IFAD Loan) | 735.15 | 0 | 100.25 | 18 | 0 | 0 | 18 | 0.43093 | 18 | 0 | 0 | 18 | 0.43093 |  |  |  | 0
| 1.3.4 Small Market |  |  | PMU, PIU | Nos. | C1304 | 7031 | 15 |  | 5 |  | 0 | 0% | 0 | 0% | 391.7 |  | 140.55 | I (IFAD Loan) | 106.82 | 0 | 33.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.3.5 Women Sections in Market |  |  | PMU,PIU | Nos. | C1305 | 7031 | 35 |  | 5 |  | 0 | 0% | 0 | 0% | 548.45 |  | 78.35 | I (IFAD Loan) | 68.95 | 0 | 9.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.3.6 LCS training on market development ( including tools and insurance) |  |  | PIU | Batch | C1306 | 4840 (ii) | 310 |  | 67 |  | 3 | 0.9677% | 3 | 0.9677% | 327.25 |  | 98 | III (IFAD Loan) | 85.75 | 0 | 12.25 | 1.17 | 0 | 0 | 1.17 | 0.35752 | 1.17 | 0 | 0 | 1.17 | 0.35752 |  |  |  | 0
| 1.3.7 Upazila MM workshop |  |  | PMU,PIU | Nos of WS | C1307 | 4840 | 25 |  | 13 |  | 0 | 0% | 0 | 0% | 12.5 |  | 7.5 | III (IFAD Loan) | 6.56 | 0 | 0.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.3.8 Market users/stakeholders |  |  | PMU,PIU | Nos. of WS | C1308 | 4840 | 200 |  | 50 |  | 3 | 1.5% | 3 | 1.5% | 100 |  | 24.27 | III (IFAD Loan) | 21.24 | 0 | 3.03 | 2.09 | 0 | 0 | 2.09 | 2.09 | 2.09 | 0 | 0 | 2.09 | 2.09 |  |  |  | 0
| 1.3.9 Women market users Training |  |  | PMU,PIU | Nos. of WS | C1309 | 4840 | 17 |  | 4 |  | 0 | 0% | 0 | 0% | 2.5 |  | 1.06 | III (IFAD Loan) | 0.93 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.3.10 MMC & trader associations training |  |  | PMU,PIU | Nos. of WS | C1310 | 4840 | 200 |  | 28 |  | 0 | 0% | 0 | 0% | 100 |  | 24.27 | III (IFAD Loan) | 21.24 | 0 | 3.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total: A; (P): 6938.4; (R): 1800.21; IFAD Loan (T): 1542.92; IFAD Grant (U): 0; GOB (V): 257.29; IFAD Laon (W): 21.26; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 21.26; % (AA): 0.30641; IFAD (AB): 21.26; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 21.26; % (AF): 0.30641; IFAD (W): 0 | 185 | 185 | 0 | 0
| (A): B. Acquisition of Asset ( vehicle/equipment/material) |  | 0
| Nil | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total: B | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): C. Recurrent Cost ( service/maintenance /travelling/stationary/printing etc.) |  | 0
| Car Rental/Procurement |  |  | PMU | Months | C1313 | 4893 (iii) | 132 | [7 empty] | 230 |  | 44.5 | V (IFAD Loan) | 38.94 | 0 | 5.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| PMU (TA) Team (Consultancy service) |  |  | PMU | P/M | C1311 | 4874 (i) | 3000 |  | 500 | [5 empty] | 2873 |  | 559 | IV (IFAD Loan) | 489.12 | 0 | 69.88 | 372.49 | 0 | 15.66 | 388.15 | 13.5103 | 372.49 | 0 | 15.66 | 388.15 | 13.5103 |  |  |  | 0
| Direct Cost TA Team and Others (Consultancy service) |  |  | PMU | L:S | C1312 | 4874 (ii) | LS |  | LS | [5 empty] | 600 |  | 60 | IV (IFAD Loan) | 52.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Physical Service |  |  | PMU | P/M | C1314 | 4893 (ii) | 3600 |  | 600 | [5 empty] | 1690 |  | 226 | IV (IFAD Loan) | 197.75 | 0 | 28.25 | 20.431 | 0 | 22.536 | 42.967 | 2.5424 | 0 | 0 | 15.662 | 15.662 | 0.92675 |  | 20.431 | 6.874 | 27.305
| (A): Sub-Total : C; (P): 5393; (R): 889.5; IFAD Loan (T): 778.31; IFAD Grant (U): 0; GOB (V): 111.19; IFAD Laon (W): 392.921; IFAD Grant (X): 0; GOB (Y): 38.196; Total (Z): 431.117; % (AA): 7.994; IFAD (AB): 372.49; IFAD Grant (AC): 0; GOB (AD): 31.322; Total (AE): 403.812; % (AF): 7.4877; IFAD (W): 20.431 | 6.874 | 27.305 | 0 | 0
| (A): Total of Sub-Component (1.3); (P): 12331.4; (R): 2689.71; IFAD Loan (T): 2321.23; IFAD Grant (U): 0; GOB (V): 368.48; IFAD Laon (W): 414.181; IFAD Grant (X): 0; GOB (Y): 38.196; Total (Z): 452.377; % (AA): 3.6685; IFAD (AB): 393.75; IFAD Grant (AC): 0; GOB (AD): 31.322; Total (AE): 425.072; % (AF): 3.4471; IFAD (W): 20.431 | 191.874 | 212.305 | 0 | 0
SC1.4 | (A): Climate Resilient Community Shelter cum School; (B): Multi-purpose school-cum-flood shelters built in selected char lands |  | 0
| (A): A. Programme/Acitvity |  | 0
| 1.4.1 Flood Shelter Survey & Estimate |  |  | PMU, PIU | Nos | C1401 | 4886(i) | 15 |  | 6 |  | 0 | 0 | 0 | 0 | 6 |  | 4.57 | III (IFAD Loan) | 4 | 0 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 1.4.2 Buildings, Flood Shelter |  |  | PMU,PIU | Nos. | C1402 | 7016 | 20 (15) |  |  |  | 0 | 0% | 0 | 0% | 2990 |  | 0 | I (IFAD Loan) | 0 | 0 | 0 | 18.6 | 0 | 0 | 18.6 | 0.62207 | 18.6 | 0 | 0 | 18.6 | 0.62207 |  |  |  | 0
| (A): Sub-Total : A; (P): 2996; (R): 4.57; IFAD Loan (T): 4; IFAD Grant (U): 0; GOB (V): 0.57; IFAD Laon (W): 18.6; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 18.6; % (AA): 0.62083; IFAD (AB): 18.6; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 18.6; % (AF): 0.62083; IFAD (W): 0 | 0 | 0 | 0 | 0
| (A): B. Acquisition of Asset ( vehicle/equipment/material) |  | 0
| (A): Nil; (L): 0; (M): 0%; (N): 0; (O): 0%; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Laon (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| Sub-Total:B | [10 empty] | 0 | 0% | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): C. Recurrent Cost ( service/maintenance/travelling/ stationary/printing etc.) |  | 0
| Nil | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total : C | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Total of Sub-Component (1.4); (P): 2996; (R): 4.57; IFAD Loan (T): 4; IFAD Grant (U): 0; GOB (V): 0.57; IFAD Laon (W): 18.6; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 18.6; % (AA): 0.62083; IFAD (AB): 18.6; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 18.6; % (AF): 0.62083; IFAD (W): 0 | 0 | 0
SC1.5 | (A): Training on climate/flood-prof resilient infrastructure design and construction; (B): Training on climate resilient infrastructure design and implementation conducted |  | 0
| (A): A. Programme/Activity |  | 0
| 1.5.1 Training Staff Engineer | PMU, BUET, External Experts |  | PMU | Batch | C1501 | 4840(iv) | 6 |  | 2 | [5 empty] | 60 |  | 35 | III (IFAD Loan) | 30.62 | 0 | 4.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total: A; (R): 35; IFAD Loan (T): 30.62; IFAD Grant (U): 0; GOB (V): 4.38; IFAD Laon (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0; IFAD (W): 0 | 0 | 0
| (A): B. Acquisition of Asset ( vehicle/equipment/material); IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Laon (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| Nil | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total:B | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): C. Recurrent Cost ( service/maintenance/ travelling/stationary/ printing etc.) |  | 0
| Nil | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total : C | [6 empty] | 0 |  | 0 |  | 0 | 0% | 0 | 0% | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Total of Sub-component 1.5; (P): 60; (R): 35; IFAD Loan (T): 30.62; IFAD Grant (U): 0; GOB (V): 4.38; IFAD Laon (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
Total Budget of Component 1: | (P): 55030.1115; (R): 11290.05; IFAD Loan (T): 9846.72; IFAD Grant (U): 105; GOB (V): 1338.33; IFAD Laon (W): 3702.407; IFAD Grant (X): 100.5; GOB (Y): 731.206; Total (Z): 4534.113; % (AA): 8.2393; IFAD (AB): 3147.86; IFAD Grant (AC): 100.5; GOB (AD): 537.022; Total (AE): 3785.382; % (AF): 6.8787; IFAD (W): 388.534 | 191.874 | 580.408 | 0 | 0
| IFAD (W): 388.534 | 191.874 | 580.408

## Detailed AWPB Com-2
Detailed Annual Work Plan & Budget (AWPB), Component-2: Resilient Communities through Employment and Early Flood Warning
Project Code : 224243100
Project Titel: Promoting Resilience of Vulnerable through Access to Infrastructure, Improved Skills and Information (PROVATi³)
Financial Year: 2020-21
| (BDT in lac; AWPB prepared on base cost) | [32 empty] | BDT in Lakh Taka
| Objecitves/Expected Results | Project Indicators | RIMS Indicator | Responsible Unit/ Staff | Unit | TOMPRO Code | Economic code | Physical Implementation targets of 2020-2021 and achievement of 2019-2020 | [7 empty] | Budget | [6 empty] | Expenditure | [9 empty] | Remarks |  |  |  |  | Remarks
[8 empty] | DPP (Total) | To be Revised (Total) | Planned (Annual) for 2020-2021 | Procurement Method | Achieved (Cumulative) Upto June/20 | % | Achieved (Annual) in 2019-2020 | % | DPP (Total) | To be Revised (Total) | Planned (Annual) for 2020-2021 | Budget Category | Plan for 2020-21 |  |  | Spent (Cumulative) upto June 2020 |  |  |  |  | Spent (Annual)-2019-20 | [5 empty] | Spent (Annual)-2018-19
[20 empty] | IFAD Loan | IFAD Grant | GOB | IFAD Loan | IFAD Grant | GOB | Total | % | IFAD Loan | IFAD Grant | GOB | Total | % |  | IFAD | GOB | Total | %
| (A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) | (J) | (K) | (L) | (M) | (N) | (O) | (P) | (Q) | (R) | (S) | (T) | (U) | (V) | (W) | (X) | (Y) | (Z) | (AA) | (AB) | (AC) | (AD) | (AE) | (AF) | (AG) | (W) |  |  |  | (X)
C2 | (A): Resilient Communities through Employment and Early Flood Warning
SC2.1 | (A): Sub-Com 2.1 : Capacity building of LCS members and livlihood developed; (B): LCS members are trained and made progress socio-economicaly
A. Programme / Activity
| 2.1.1 Introduction of GALS Pilot model for LCS |  |  | PMU, NGO,PIU | person | C2101 | 4840 (v) | 7000 |  | LS |  | 0 | 0 | 0 | 0 | 672 |  |  | III (IFAD Loan) |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.1.2 Replication of model for LCS |  |  | PMU, NGO,PIU | person | C2102 | 4840(v) | 8000 |  | LS |  | 0 | 0 | 0 | 0 | 512 |  |  | III (IFAD Loan) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.1.3 Workshop (TOT) |  |  | PMU, NGO, Consultant | Nos. |  | 4840 (v) | 16 | 6 | LS |  | 0 | 0 | 0 | 0 | 64 |  |  | III (IFAD Loan) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.1.5 Regional Exchange Visit |  |  | PMU | Nos. |  | 4840 (v) | 1 |  | LS |  | 0 | 0 | 0 | 0 | 40 |  |  | III (IFAD Loan) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.1.6 Knowledge Exchange Visit |  |  | PMU | Nos. |  | 4840 (v) | 1 |  | LS |  | 0 | 0 | 0 | 0 | 16 |  |  | III (IFAD Loan) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.1.7 Support to Market planning and Development |  |  | PMU,PIU | LS |  | 4840 (v) | LS |  | LS |  | 0 | 0 | 0 | 0 | 336 |  |  | III (IFAD Loan) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.1.8 Documentation & Publication |  |  | PMU | Nos. | C2103 | 4840(v) | 4 |  | LS |  | 0 | 0 | 0 | 0 | 16 |  |  | III (IFAD Loan) |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total:A; (J): LS; (P): 1656; (R): 310.66; IFAD Loan (T): 271.83; IFAD Grant (U): 0; GOB (V): 38.83; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0; IFAD (W): 0 | 0 | 0 | 0 | 0
| (A): B. Acquisition of Asset ( vehicle/ equipment / materials etc) |  | 0
| (A): Nil; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| Sub-Total:B | [10 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| (A): C. Recurrent Cost ( service/maintenace/repairing/printing) |  | 0
| International consultancy on GALS (TOT) |  |  | PMU | P/M | C2104 | 4840(v) | 16 | 3 | LS |  | 0 | 0 | 0 | 0 | 256 |  | 19.84 | IV (IFAD Loan) | 17 | 0 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-total:C; (L): 0; (M): 0; (N): 0; (O): 0; (P): 256; IFAD Loan (T): 17; IFAD Grant (U): 0; GOB (V): 2.84; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Total of Sub.Comp (2.1); (J): 335; (P): 1912; (R): 330.5; IFAD Loan (T): 288.83; IFAD Grant (U): 0; GOB (V): 41.67; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0; IFAD (W): 0 | 0 | 0 | 0 | 0
SC2.2 | (A): Total of Sub-Comp 2.2: Vocational training for off-farm employment; (B): Employment for youths in project area expanded through vocational skill development |  | 0
| (A): A. Programme/Activity |  | 0
| 2.2.1 Study deemand for skills |  |  | PMU | LS | C2201 |  | 1.5 |  | 1 |  | 0 | 0 | 0 | 0 | 15 |  | 15 | III (IFAD Loan) | 13.12 | 0 | 1.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.2.2 Workshop |  |  | PMU | Workshop | C2202 |  | 4 |  | 1 |  | 0 | 0 | 0 | 0 | 6 |  | 6 | III (IFAD Loan) | 5.25 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.2.3 Vocational training (Youth) |  |  | PMU, NGO | Persons | C2203 | 4840(vi) | 30000 |  | 5000 |  | 0 | 0 | 0 | 0 | 3600 |  | 1002.69 | III (IFAD Loan) | 877.35 | 0 | 125.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total:A | [10 empty] | 0 | 0 | 0 | 0 | 3621 |  | 1023.69 |  | 895.72 | 0 | 127.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| (A): B. Acquisition of Asset ( vehicle/ equipment / materials etc) |  | 0
| (A): Nil; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Sub-Total:B; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): C. Recurrent Cost ( service/maintenace/repair/ documentation; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0 |  | 0
| (A): Nil; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Sub-Total:C; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| Total of Sub-Component (2.2) | [10 empty] | 0 | 0 | 0 | 0 | 3621 |  | 1023.69 |  | 895.72 | 0 | 127.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
SC2.3 | (A): Sub Comp: Development of accurate local flood warning and dissemination system; (B): Local improved flood Forecasting and early warning system establised |  | 0
| (A): A. Programme/Activity |  | 0
| 2.3.1 Enhanching Local Knowledge on EWS ( Research) |  |  | DDM | LS | C2301 | 4829(vi) | 2 | 0 | LS |  | 0 | 0 | 0 | 0 | 67.3 |  | 10 | III (IFAD Loan) | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.3.2 Data Collection ( Research) |  |  | DDM | LS | C2302 | 4829(vii) | 19 | 0 | LS |  | 0 | 0 | 0 | 0 | 258.76 |  | 25 | III (IFAD Loan) | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.3.3 Tools Development (Research) |  |  | DDM | LS | C2303 | 4829(viii) | 19 | 0 | LS |  | 0 | 0 | 0 | 0 | 84 |  |  | III (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.3.4 Communication and Dessemination of Flood Warning Signal (Research) |  |  | DDM |  | C2304 | 4829(ix) | 2 | 0 | LS |  | 0 | 0 | 0 | 0 | 161.41 |  |  | III (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.3.5 Training EWS Professional |  |  | DDM | LS | C2306 | 4840(vii) | 1 | 0 | LS |  | 0 | 0 | 0 | 0 | 84.97 |  | 33 | III (IFAD Loan) | 28.87 | 0 | 4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.3.6 Training Volenteers on EWS |  |  | DDM | Nos | C2307 | 4840(viii) | 19 | 0 | LS |  | 0 | 0 | 0 | 0 | 78.2 |  | 5 | III (IFAD Loan) | 4.37 | 0 | 0.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.3.7 Workshops |  |  | DDM | Nos | C2308 | 4842(ii) | 19 | 0 | LS |  | 0 | 0 | 0 | 0 | 61.5 |  | 5.2 | III (IFAD Loan) | 4.55 | 0 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total:A | [6 empty] | 29 | 0 |  |  | 0 | 0 | 0 | 0 | 796.14 |  | 78.2 |  | 72.79 | 0 | 5.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| (A): B. Acquisition of Asset (vehicle/equipment /materials etc); (L): 0; (M): 0; (N): 0; (O): 0 |  | 0
| Motor Vehicle |  |  | DDM | Nos | C2335 | 6807(v) | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 52 |  | 60 | II (IFAD Loan) | 52.5 | 0 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | Mismatch with DPP
| Airconditioers |  |  | DDM | Nos | C2312 | 6813(ii) | 2 | 0 | 2 |  | 0 | 0 | 0 | 0 | 5 |  |  | II (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Computer and Instrument |  |  | DDM | Nos. | C2321 | 6815(vii) | 29 | 0 | 15 |  | 0 | 0 | 0 | 0 | 69.08 |  | 37.1 | II (IFAD Loan) | 32.46 | 0 | 4.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total:B; (L): 0; (M): 0; (N): 0; (O): 0; (P): 126.08; (R): 97.1; IFAD Loan (T): 84.96; IFAD Grant (U): 0; GOB (V): 12.14; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): C. Recurrent Cost ( service/maintenace/repairing/printing) |  | 0
| Local Consultancy of DDM |  |  | DDM | P/M | C2338 | 4874(iii) | 702 | 0 | 176 |  | 0 | 0 | 0 | 0 | 833.7 |  | 10 | IV (IFAD Loan) | 8.75 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | Need to review by PD
| Allowances ( daily and concvence) |  |  | DDM | Nos | C2339 |  | 2 | 0 | 2 |  | 0 | 0 | 0 | 0 | 15.84 |  | 2.7 | IV (IFAD Loan) | 2.36 | 0 | 0.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Supply and Services |  |  | DDM | LS |  | 4804(ii), 4813(ii), 4815(ii), 4816(ii), 4818(ii), 4824(ii), 4827(ii), 4828(ii), 4921(ii) | LS |  | LS |  | 0 | 0 | 0 | 0 | 103.04 |  | 13.11 | II (IFAD Loan) | 11.47 | 0 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.13 | 0 | 0.13
| Maintenance of Motor Cycle, Service Vehicles |  |  | DDM | LS |  | 4901(ii) | 66 |  | LS |  | 0 | 0 | 0 | 0 | 19.8 |  | 3.27 | II (IFAD Loan) | 2.86 | 0 | 0.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total:C | [9 empty] | 0 | 0 | 0 | 0 | 0 | 972.38 |  | 29.08 |  | 25.44 | 0 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Total of Sub-Comp (2.3); (P): 1894.6; (R): 204.38; IFAD Loan (T): 183.19; IFAD Grant (U): 0; GOB (V): 21.19; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
SC 2.4 | (A): Practical Policy Actions; (B): Institutional regulatory review conducted and integrated in policies |  | 0
| (A): A. Programme/Activity |  | 0
| 2.4.01 Internal policy initiative | PMU |  | PMU | Nos | C2401 | 4886(ii) | 6 | 0 |  |  | 0 | 0 | 0 | 0 | 192 |  | 25 | III (IFAD Loan) | 21.87 | 0 | 3.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.4.02 WFP mapping of poverty and nutritional status and Forecast work | WFP |  | WFP | No | C2402 | 4886(iii) | 1 | 0 | 1 |  | 0 | 0 | 0 | 0 | 143.5 |  | 35.56 | III (IFAD Loan) | 0 | 31.11 | 4.45 | 0 | 90 | 0 | 90 | 62.7178 | 0 | 90 | 0 | 90 | 62.7178 |  | 0 | 0 | 0
| 2.4.03 Contribution to LGED Climate Unit | PMU.LGED |  | PMU | LS | C2403 | 4874(v) | LS | 0 | LS |  | 0 | 0 | 0 | 0 | 144.14 |  | 20 | IV (IFAD Loan) | 17.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.4.04 LGED PMU Support |  |  | PMU | LS | C2404 | 4874(vi) | LS | 0 | LS |  | 0 | 0 | 0 | 0 | 124.97 |  | 10 | IV (IFAD Loan) | 8.75 | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 2.4.05 Support to CPS (KM & FM & Annual KM Events ) | ERD |  | ERD | LS | C2405 | 4874(iv) | LS | 0 | LS |  | 0 | 0 | 0 | 0 | 244.03 |  | 30 | IV (IFAD Loan) | 26.25 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Sub-Total: A | [10 empty] | 0 | 0 | 0 | 0 | 848.64 |  | 120.56 |  | 74.37 | 31.11 | 15.08 | 0 | 90 | 0 | 90 | 10.6052 | 0 | 90 | 0 | 90 | 10.6052 |  | 0 | 0 | 0 | 0 | 0
B. Acquisition of Asset ( vehicle/ equipment / materials etc)
| (A): Nil; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Sub-Total:B; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): C. Recurrent Cost ( service/maintenace/repairing/printing); (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Nil; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Sub-Total:C; (L): 0; (M): 0; (N): 0; (O): 0; (P): 0; (R): 0; IFAD Loan (T): 0; IFAD Grant (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Grant (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Grant (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): Total of Sub-Component: (2.4); (L): 0; (M): 0; (N): 0; (O): 0; (P): 848.64 |  | 0
Total Budget of Component 2: | (P): 8276.24; (R): 1679.13; IFAD Loan (T): 1442.11; IFAD Grant (U): 31.11; GOB (V): 205.91; IFAD Loan (W): 0; IFAD Grant (X): 90; GOB (Y): 0; Total (Z): 90; % (AA): 1.0875; IFAD Loan (AB): 0; IFAD Grant (AC): 90; GOB (AD): 0; Total (AE): 90; % (AF): 1.0875; IFAD (W): 0 | 0 | 0 | 0 | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (P): 55030.1215; IFAD Loan (T): 10231.2463; IFAD Grant (U): 172.01; GOB (V): 1559.9913; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (P): 63306.3615; IFAD Loan (T): 11673.3563; IFAD Grant (U): 203.12; GOB (V): 1765.9013; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; Total (AE): 0 |  | 0
| (P): 4870.75; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; Total (AE): 0 |  | 0
| (P): 68177.1115; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; Total (AE): 0 |  | 0
| (P): 7576.5; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; Total (AE): 0 |  | 0
| (P): 75753.6115; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (T): 431.04; GOB (V): 306.01; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (T): 10600.633; IFAD Grant (U): 107; GOB (V): 1317.2917; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (T): 12473.783; IFAD Grant (U): 138.11; GOB (V): 1829.2117; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (T): 12611.893; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (T): 12000; GOB (V): 1782.86; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (T): -611.8929; GOB (V): -46.3517; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (Q): #REF!; (S): #REF!; IFAD Loan (T): #REF!; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (Q): #REF!; IFAD Loan (T): 306.58; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (Q): #REF!; (S): #REF!; IFAD Loan (T): #REF!; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (Q): 13782.86; IFAD Loan (T): 1782.86; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| (Q): #REF!; IFAD Loan (T): #REF!; IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
| IFAD Loan (W): 0; GOB (Y): 0; Total (Z): 0; % (AA): #DIV/0!; Total (AE): 0 |  | 0
8290.63
14.39

## Detailed AWBCom-3 & Total
Detailed Annual Work Plan & Budget (AWPB), Component-3: Project Management and Coordination
Project Code : 224243100
Project Titel: Promoting Resilience of Vulnerable through Access to Infrastructure, Improved Skills and Information (PROVATi³)
Financial Year: 2020-2021
| (BDT in lac; AWPB prepared on base cost) | [29 empty] | BDT in Lakh Taka |  |  | BDT in Lakh Taka
| Objecitves/Expected Results | Project Indicators | RIMS Indicator | Responsible Unit/ Staff | Unit | TOMPRO Code | Economic code | Physical Implementation targets of 2020-2021 and achievement of 2019-2020 | [7 empty] | Budget | [6 empty] | Expenditure | [9 empty] | Remarks |  |  |  |  | Remarks
[8 empty] | DPP (Total) | To be Revised (Total) | Planned (Annual) for 2020-21 | Procurement Method | Achieved (Cumulative) Upto June/20 | % | Achieved (Annual) in 2019-2020 | % | DPP (Total) | To be Revised (Total) | Planned (Annual) for 2020-21 | Budget Category | Plan for 2020-21 |  |  | Spent (Cumulative) upto June 2020 |  |  |  |  | Spent (Annual)-2019-20 | [5 empty] | Spent (Annual)-2018-19
[20 empty] | IFAD Loan | IFAD Garnt | GOB | IFAD Loan | IFAD Garnt | GOB | Total | % | IFAD Loan | IFAD Garnt | GOB | Total | % |  | IFAD | GOB | Total | %
| (A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) | (J) | (K) | (L) | (M) | (N) | (O) | (P) | (Q) | (R) | (S) | (T) | (U) | (V) | (W) | (X) | (Y) | (Z) | (AA) | (AB) | (AC) | (AD) | (AE) | (AF) | (AG) | (W) |  |  |  | (X)
| Project management and Technical Support | Project Implementation Strengthened with Effective Collaboration and Partnership
A. Programme/activity
| 3.1.1 TOMPRO Software setup & operation |  |  | PMU | LS | C3101 | 6817 | 2 |  | 1 |  | 1 |  | 1 |  | 47 |  | 20.75 | III (IFAD Loan) | 18.16 | 0 | 2.59 | 24.31 | 0 | 0 | 24.31 | 51.7234 | 24.31 | 0 | 0 | 24.31 | 51.7234
| 3.1.2 Inception/Start-up workshop |  |  |  | LS | C3102 | 4840(ix) | 1 |  |  |  | 1 |  | 1 |  | 5 |  | 0 | III (IFAD Loan) | 0 | 0 | 0 | 15.45 | 0 | 0 | 15.45 | 309 | 5 | 0 | 0 | 5 | 100 |  |  |  | 0
| (A): 3.1.3 Orientation Training to staff; (E): LS; (F): C3103; (G): 4840(ix); (H): 1; (L): 3; (N): 3; (P): 15; (S): III (IFAD Loan); IFAD Loan (W): 9.82; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 9.82; % (AA): 65.4667; IFAD Loan (AB): 9.82; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 9.82; % (AF): 65.4667 |  | 0
| 3.1.4 Training on LCS Management |  |  |  | LS | C3104 | 4840(ix) | 1 |  | 2 |  | 1 |  | 1 |  | 20 |  |  | III (IFAD Loan) |  |  |  | 8 | 0 | 0 | 8 | 40 | 1.68 | 0 | 0 | 1.68 | 8.4 |  | 49.309 |  | 49.309
| 3.1.5 Project Monthly Review meetings |  |  |  | LS | C3105 | 4840(ix) | 72 |  | 12 | [5 empty] | 72 |  | 46.5 | III (IFAD Loan) | 40.69 |  | 5.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 3.1.6 PMU Workshop & Loan Negotiation/ Visit to IFAD H/Q. |  |  | PMU | Nos | C3106 | 4842(i) | 12 | [7 empty] | 50 |  | 0 | III (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 3.1.7 Overseas Training PMU |  |  | PMU | Batch | C3107 | 4840(x) | 4 |  | 1 | [5 empty] | 312.88 |  | 65 | III (IFAD Loan) | 56.87 | 0 | 8.13 | 58.77 | 0 | 0 | 58.77 | 18.7836 | 9.46 | 0 | 0 | 9.46 | 3.0235 |  |  |  | 0
| 3.1.8 Baseline survey RIMS+ |  |  |  | LS | C3108 | 4886(v) | 1 |  | 1 | [5 empty] | 90 |  | 100 | III (IFAD Loan) | 90.87 | 0 | 9.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 3.1.9 Mid-term survey RIMS + |  |  |  | LS | C3109 | 4886(v) | 1 | [7 empty] | 38 |  | 0 | III (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): 3.1.10 Endline survey RIMS +; (E): LS; (F): C3110; (G): 4886(v); (H): 1; (P): 46; (S): III (IFAD Loan); IFAD Loan (T): 0; IFAD Garnt (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): 3.1.11 Annual Outcome surveys; (E): LS; (F): C3111; (G): 4886(v); (H): 6; (P): 60; (S): III (IFAD Loan); IFAD Loan (T): 0; IFAD Garnt (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): 3.1.12 Impact assessment survey; (E): LS; (F): C3113; (G): 4886(v); (H): 2; (P): 160; (S): III (IFAD Loan); IFAD Loan (T): 0; IFAD Garnt (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| (A): 3.1.13 Knowledgement Products; (E): LS; (F): C3114; (G): 4886(v); (H): 6; (P): 120; (S): III (IFAD Loan); IFAD Loan (T): 0; IFAD Garnt (U): 0; GOB (V): 0; IFAD Loan (W): 0; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0 |  | Need to review
| (A): Sub-Total; A; (P): 1035.88; (R): 232.25; IFAD Loan (T): 206.59; IFAD Garnt (U): 0; GOB (V): 25.66; IFAD Loan (W): 116.35; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 116.35; % (AA): 11.232; IFAD Loan (AB): 50.27; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 50.27; % (AF): 4.8529; IFAD (W): 49.309 | 0 | 49.309 | 0 | 0
| (A): B. Acqusition of Assets ( vehicle/equipment/ material) |  | 0
| (A): Acquisition/Purchase of Landed; (B): 49.5; (G): 6900; (P): 25; (R): 6.48; (S): GoB; IFAD Loan (T): 0; IFAD Garnt (U): 0; GOB (V): 6.48; IFAD Loan (W): 0; IFAD Garnt (X): 0; GOB (Y): 0; Total (Z): 0; % (AA): 0; IFAD Loan (AB): 0; IFAD Garnt (AC): 0; GOB (AD): 0; Total (AE): 0; % (AF): 0 |  | 0
| Vehicles for PD |  |  | PMU | Nos. | C3115 | 6807 (i) | 1 |  |  |  | 1 |  | 1 |  | 82 |  |  | II (IFAD Loan) | 0 | 0 | 0 | 58.26 | 0 | 9.83 | 68.09 | 83.0366 | 14.08 | 0 | 9.83 | 23.91 | 29.1585 |  | 206.182 |  | 206.182 |  | No breckdown
| Vehicles for DPD, PMU |  |  | PMU | Nos. | C3116 | 6807 (ii) | 1 | [7 empty] | 52 |  |  | II (IFAD Loan) | 0 | 0 | 0 | 8.46 | 0 | 0 | 8.46 | 16.2692 | 8.46 | 0 | 0 | 8.46 | 16.2692 |  |  |  | 0
| Desktop Computers with printer |  |  | PMU | Nos | C3117 | 6815 (i) | 33 |  | 20 |  | 10 |  | 7 |  | 33 |  |  | II (IFAD Loan) | 0 | 0 | 0 | 7.444 | 0 | 5.837 | 13.281 | 40.2455 | 2.86 | 0 | 0.87 | 3.73 | 11.303 |  | 4.584 | 4.967 | 9.551
| Laptop Computers |  |  | PMU | Nos | C3118 | 6815 (ii) | 7 |  |  |  | 7 |  | 7 |  | 7 |  | 4.95 | II (IFAD Loan) | 4.33 | 0 | 0.62 | 4.33 | 0 | 1.32 | 5.65 | 80.7143 | 4.33 | 0 | 1.32 | 5.65 | 80.7143 |  |  |  | 0
| Digital Camera |  |  | PMU | Nos | C3119 | 6812 | 10 |  | 5 | [5 empty] | 5 |  | 2.85 | II (IFAD Loan) | 2.49 | 0 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Air Conditioner Equipment,PMU |  |  | PMU | Nos | C3120 | 6813 (i) | 13 |  |  |  | 7 |  | 5 |  | 20 |  | 4.6 | II (IFAD Loan) | 4.02 | 0 | 0.58 | 6.213 | 0 | 0 | 6.213 | 31.065 | 4.24 | 0 | 0 | 4.24 | 21.2 |  | 1.973 |  | 1.973
| Photocopier |  |  | PMU | Nos | C3121 | 6815 (iv) | 6 |  | 3 |  | 2 |  | 2 |  | 22 |  | 12 | II (IFAD Loan) | 10.5 | 0 | 1.5 | 4.97 | 0 | 0 | 4.97 | 22.5909 | 4.97 | 0 | 0 | 4.97 | 22.5909 |  |  |  | 0
| Scanner |  |  | PMU | Nos | C3122 | 6815 (iii) | 9 | [7 empty] | 3 |  |  | II (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Projector (Multimedia) |  |  | PMU | Nos | C3123 | 6815 (v) | 5 |  | 4 | [5 empty] | 5 |  | 4 | II (IFAD Loan) | 3.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Internet (Installation with Wifi) |  |  | PMU | LS | C3124 | 6815 (vi) | LS |  | LS | [5 empty] | 5 |  | 1 | II (IFAD Loan) | 0.87 | 0 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Office Arrangement/Equipment |  |  | PMU | Nos | C3125 | 6819 | LS |  | LS | [5 empty] | 20 |  | 3 | II (IFAD Loan) | 2.62 | 0 | 0.38 | 6.227 | 0 | 0.63 | 6.857 | 34.285 | 4.22 | 0 | 0.63 | 4.85 | 24.25 |  | 2.007 |  | 2.007
| Furniture |  |  | PMU, PIUs | Nos | C3126 | 6821 | LS |  | LS | [5 empty] | 50 |  | 3.58 | II (IFAD Loan) | 3.13 | 0 | 0.45 | 22.151 | 0 | 3.33 | 25.481 | 50.962 | 11.24 | 0 | 0 | 11.24 | 22.48 |  | 10.911 | 3.33 | 14.241
| Telephone Arrangement |  |  | PMU | Nos | C3127 | 6822 | 270 | [7 empty] | 8 |  | 0 | II (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Tree Plantation |  |  | PMU | Nos | C3128 | 5845 | LS | [7 empty] | 20 |  | 0 | II (IFAD Loan) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Others |  |  | PMU | Nos | C3129 | 6851 | LS |  | LS | [5 empty] | 10 |  | 0.5 | II (IFAD Loan) | 0.44 | 0 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| (A): Sub-Total:B; (P): 367; (R): 42.96; IFAD Loan (T): 31.9; IFAD Garnt (U): 0; GOB (V): 11.06; IFAD Loan (W): 118.055; IFAD Garnt (X): 0; GOB (Y): 20.947; Total (Z): 139.002; % (AA): 37.8752; IFAD Loan (AB): 54.4; IFAD Garnt (AC): 0; GOB (AD): 12.65; Total (AE): 67.05; % (AF): 18.2698; IFAD (W): 225.657 | 8.297 | 233.954
| (A): C. Recurrent ( Service/Maintenance/ Repairing/printing) |  | 0
| PMU+PIU Motor Vehicles |  |  | PMU & PIU | VY | C3130 | 4901 | 32 |  | 11 | [5 empty] | 27 |  | 10 | II (IFAD Loan) | 8.75 | 0 | 1.25 | 3.6 | 0 | 0 | 3.6 | 13.3333 | 3.6 | 0 | 0 | 3.6 | 13.3333 |  |  |  | 0
| Furniture |  |  | PMU & PIU | Nos. | C3131 | 4906 | LS |  | LS | [5 empty] | 10 |  | 2.3 | II (IFAD Loan) | 2.01 | 0 | 0.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Computer , Office Equipment |  |  | PMU & PIU | LS | C3132 | 4911 | 153 |  | LS | [5 empty] | 49.5 |  | 8.02 | II (IFAD Loan) | 7.02 | 0 | 1 | 0.42 | 0 | 0 | 0.42 | 0.84848 | 0.42 | 0 | 0 | 0.42 | 0.84848 |  | 0 | 0 | 0
| Machinaries and Equipment |  |  | PMU & PIU | Nos. | C3133 | 4916 | LS |  | LS | [5 empty] | 20 |  | 7.5 | II (IFAD Loan) | 6.56 | 0 | 0.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Office Complex |  |  | PMU & PIU | Nos. | C3134 | 4921(i) | LS |  | LS | [5 empty] | 45 |  | 9 | II (IFAD Loan) | 7.87 | 0 | 1.13 | 9.2 | 0 | 0 | 9.2 | 20.4444 | 9.2 | 0 | 0 | 9.2 | 20.4444 |  |  |  | 0
| Engineering Instruments |  |  | PMU & PIU | Nos. | C3135 | 4932 | 31 | [7 empty] | 11 |  | 7.5 | II (IFAD Loan) | 5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Other reparing |  |  | PMU & PIU | Nos. | C3136 | 4991 | LS |  | LS | [5 empty] | 10 |  | 2 | II (IFAD Loan) | 1.75 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| Pay of Officers & Staff and Allowances |  |  | PMU & PIU | Nos. | C3137 | 4501,4601 & 4701-4795 | 21 | [7 empty] | 1218.65 |  | 127.99 | GOB | 0 | 0 | 127.99 | 0 | 0 | 101.91 | 101.91 | 8.3625 | 0 | 0 | 66.07 | 66.07 | 5.4216 |  | 0 | 35.84 | 35.84
| Office administration supply & services |  |  | PMU & PIU | LS | C3138 | 4801,4802, 4804, 4806, 4813, 4815, 4816, 4817, 4818, 4819, 4821, 4822, 4823, 4824, 4827, 4828, 4831, 4832, 4833, 4836, 4845, 4846, 4851, 4854, 4875, 4881, 4882,4883, 4885, 4888, 4889, 4893(i), 4899 | LS |  | LS | [5 empty] | 2101.72 |  | 312.53 | V (IFAD Loan) | 273.46 | 0 | 39.07 | 100.07 | 0 | 123.98 | 224.05 | 10.6603 | 60.87 | 0 | 77.96 | 138.83 | 6.6055 |  | 39.2 | 46.02 | 85.22
| (A): Sub-Total:C; (P): 3492.87; (R): 486.84; IFAD Loan (T): 312.42; IFAD Garnt (U): 0; GOB (V): 174.42; IFAD Loan (W): 113.29; IFAD Garnt (X): 0; GOB (Y): 225.89; Total (Z): 339.18; % (AA): 9.7106; IFAD Loan (AB): 74.09; IFAD Garnt (AC): 0; GOB (AD): 144.03; Total (AE): 218.12; % (AF): 6.2447; IFAD (W): 39.2 | 81.86 | 121.06 | 0 | 0
Total Budget of Component 3 | (P): 4895.75; (R): 762.05; IFAD Loan (T): 550.91; IFAD Garnt (U): 0; GOB (V): 211.14; IFAD Loan (W): 347.695; IFAD Garnt (X): 0; GOB (Y): 246.837; Total (Z): 594.532; % (AA): 12.1438; IFAD Loan (AB): 178.76; IFAD Garnt (AC): 0; GOB (AD): 156.68; Total (AE): 335.44; % (AF): 6.8517; IFAD (W): 314.166 | 90.157 | 404.323 | 0 | 0
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
| Total (Z): 0.12144; % (AA): #DIV/0!; % (AF): #DIV/0!; IFAD (W): 574.0923 | 204.627 | 778.7193
| IFAD Loan (T): #REF!; GOB (V): #REF!; % (AA): #DIV/0!; % (AF): #DIV/0!; IFAD (W): 888.2583 | 294.784 | 1183.0423
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[20 empty] | 431.4 | 0 | 306.01 |  |  |  |  | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
[27 empty] | #DIV/0! |  |  |  |  | #DIV/0!
Grand Total | (P): 68202.1015; (R): 13731.23; IFAD Loan (T): 11839.74; IFAD Garnt (U): 136.11; GOB (V): 1755.38; IFAD Loan (W): 4050.102; IFAD Garnt (X): 190.5; GOB (Y): 978.043; Total (Z): 5218.645; % (AA): 7.6517; IFAD Loan (AB): 3326.62; IFAD Garnt (AC): 190.5; GOB (AD): 693.702; Total (AE): 4210.822; % (AF): 6.174; IFAD (W): 702.7 | 282.031 | 984.731

## Financial Performance (June)
2. Financial Performance
2.A. Financial Performance by Financier (USD in '000) as up to June 2020
Financer | Approval | Disbursement | % of Disbursement
IFAD Loan | 63250 | 8119.12 | 12.84%
IFAD Grant | 1250 | 250 | 20%
Government | 27900 | 1157.43 | 4.148%
Total | 92400 | 9526.55 | 10.31%
2.B. Financial Performance by components (in USD '000) as up to June 2020
Component |  | IFAD Loan |  |  | IFAD Grant |  |  | GOB |  |  | Total
|  | Approval | Actual | % | Approval | Actual | % | Approval | Actual | % | Approval | Actual | %
1 | Climate Resilient Infrastructure and Community Shelters | 52240 | 4197.8 | 8.036% | 254 | 118.93 | 46.82% | 22376 | 855.25 | 3.822% | 74870 | 5171.99 | 6.908%
2 | Resilient Communities Through Employment and Early Flood Warning | 7975 | 0 | 0% | 996 | 106.51 | 10.69% | 3454 |  | 0% | 12425 | 106.51 | 0.8572%
3 | Project Management | 3035 | 495.64 | 16.33% |  | - | - | 2070 | 302.18 | 14.6% | 5105 | 797.82 | 15.63%
4 | Initial Advance |  | 4000 |  |  | 250 | [5 empty] | 4250
Total |  | 63250 | 8693.44 | 13.74% | 1250 | 475.44 | 38.04% | 27900 | 1157.43 | 4.148% | 92400 | 10326.32 | 11.18%
2.C. Yearly Financial Ferformance by Components (in USD'000) as up to June 2020
Component |  | Project Total |  | Year Total |  |  | Cumulative
|  | Approval | % of Total | Approval | Actual | % | Approval | Actual | %
1 | Climate Resilient Infrastructure and Community Shelters | 52240 | 82.59% | 12386.2 | 3815.25 | 30.8% | 12484.8 | 4566.63 | 36.5%
2 | Resilient Communities Through Employment and Early Flood Warning | 7975 | 12.61% | 1048.9 | 90 | 8.5% | 1049.75 | 90 | 8.62%
3 | Project Management | 3035 | 4.8% | 1048.9 | 287.38 | 27.3% | 1097.35 | 541.7 | 49.36%
Total |  | 63250 | 100% | 14484 | 4192.63 | 28.9% | 14631.9 | 5198.33 | 35.5%
2.D. IFAD Loan Disbursements (USD 000) as at June'2020 by categories
Category | Category description | Orginal Allocation | Revised Allocation | Disbursement | WA pending | Balance | Per cent disbursed
I | Works | 39990 | 0 | 3339.85 | 363.85 | 36650.15 | 8.352%
II | Equipment & Materials | 860 | 0 | 297.95 | 38.69 | 262.05 | 34.65%
III | Training and Workshop | 7410 | 0 | 67.72 | 0 | 7342.28 | 0.9139%
IV | Cunsultancies | 4650 | 0 | 304.08 | 147.91 | 4345.92 | 6.539%
V | Recurrent Cost | 4020 | 0 | 109.53 | 28.95 | 3910.47 | 2.725%
| Unallocated | 6320 | 0 | 0 | 0 | 6320 | 0%
| Initial Deposit/Advance Account | 0 | 0 | 4000 | 0 | -4000 | 0%
Total |  | 63250 | 0 | 8119.13 | 579.4 | 54830.87 | 12.84%
2.E. IFAD Grant Disbursements (USD 000) as at June'2020 by categories
Category | Category description | Orginal Allocation | Revised Allocation | Disbursement | WA pending | Balance | Per cent disbursed
I | Works | 0 | 0 |  | 500 | 1000 | 20%
II | Equipment & Materials | 10 | 0
III | Training and Workshop | 320 | 0
IV | Cunsultancies | 610 | 0
V | Recurrent Cost | 180 | 0
| Unallocated | 130 | 0 | 0 | 0 | 0 | 0%
| Initial Deposit/Advance Account | 0 | 0 | 250 | 0 | 0 | 0%
Total |  | 1250 | 0 | 250 | 500 | 1000 | 20%
2. Financial Performance by Financier (USD in '000) as up to September 2020
Financial Performance by Financier (USD in '000) as up to September 2020
Financer | Approval | Disbursement | % of Disbursement
IFAD Loan | 63250 | 8119.12 | 12.84%
IFAD Grant | 1250 | 250 | 20%
Government | 27900 | 1157.43 | 4.148%
Total | 92400 | 9526.55 | 10.31%
Financial Performance by components (in USD '000) as up to September 2020
Component |  | IFAD Loan |  |  | IFAD Grant |  |  | GOB |  |  | Total
|  | Approval | Actual | % | Approval | Actual | % | Approval | Actual | % | Approval | Actual | %
1 | Climate Resilient Infrastructure and Community Shelters | 52240 | 4197.8 | 8.036% | 254 | 118.93 | 46.82% | 22376 | 855.25 | 3.822% | 74870 | 5171.99 | 6.908%
2 | Resilient Communities Through Employment and Early Flood Warning | 7975 | 0 | 0% | 996 | 106.51 | 10.69% | 3454 |  | 0% | 12425 | 106.51 | 0.8572%
3 | Project Management | 3035 | 495.64 | 16.33% |  | - | - | 2070 | 302.18 | 14.6% | 5105 | 797.82 | 15.63%
4 | Initial Advance |  | 4000 |  |  | 250
Total |  | 63250 | 8693.44 | 13.74% | 1250 | 475.44 | 38.04% | 27900 | 1157.43 | 4.148% | 92400 | 6076.32 | 6.576%
IFAD Loan Disbursements (USD 000) as at September'2020 by categories
Category | Category description | Orginal Allocation | Revised Allocation | Disbursement | WA pending | Balance | Per cent disbursed
I | Works | 39990 | 0 | 3339.85 | 1293.33 | 36650.15 | 8.352%
II | Equipment & Materials | 860 | 0 | 297.95 | 39.84 | 262.05 | 34.65%
III | Training and Workshop | 7410 | 0 | 67.72 | 2.51 | 7342.28 | 0.9139%
IV | Cunsultancies | 4650 | 0 | 304.08 | 230.2 | 4345.92 | 6.539%
V | Recurrent Cost | 4020 | 0 | 109.53 | 38.87 | 3910.47 | 2.725%
| Unallocated | 6320 | 0 | 0 | 0 | 6320 | 0%
| Initial Deposit/Advance Account | 0 | 0 | 4000 | 0 | -4000 | 0%
Total |  | 63250 | 0 | 8119.13 | 1604.75 | 54830.87 | 12.84%
Table 2C: IFAD Grant Disbursements (USD 000) as at September'2020 by categories
Category | Category description | Orginal Allocation | Revised Allocation | Disbursement | WA pending | Balance | Per cent disbursed
I | Works | 0 | 0 | 250 | 500 | 1000 | 20%
II | Equipment & Materials | 10 | 0
III | Training and Workshop | 320 | 0
IV | Cunsultancies | 610 | 0
V | Recurrent Cost | 180 | 0
| Unallocated | 130 | 0 | 0 | 0 | 130 | 0%
| Initial Deposit/Advance Account | 0 | 0 | 250 | 0 | 250 | 0%
Total |  | 1250 | 0 | 250 | 500 | 1000 | 20%
(Yearly Financial Ferformance by Components (in USD'000) as up to June 2020
Component |  | Project Total |  | Year Total |  |  | Cumulative
|  | Approval | % of Total | Approval | Actual | % | Approval | Actual | %
1 | Climate Resilient Infrastructure and Community Shelters | 52240 | 82.59% | 14572.56 | 4432.15 | 30.41% | 14688.17 | 5171.99 | 35.21%
2 | Resilient Communities Through Employment and Early Flood Warning | 7975 | 12.61% | 1234.82 | 106.51 | 8.63% | 1235.65 | 106.51 | 8.62%
3 | Project Management | 3035 | 4.8% | 1234.82 | 347.47 | 28.14% | 1291.24 | 797.82 | 61.79%
Total |  | 63250 | 100% | 17042.2 | 4886.13 | 28.67% | 17215.06 | 6076.32 | 35.3%

## Procurement
C. Project {Procurement Status Since Inception and Planning for the FY 2020 – 2021}
C.1. Fiscal Year 2018 - 2019
Description | Number |  |  |  | Amount (BDT in Lac)
| Project Procurement Plan | Procurement in Progress | Procurement done | % | Estimated Cost | Procurement in Progress | Contracted Amount | Completed | %
Goods | 14 | 0 | 14 | 100 | 317.0842 | 0 | 292.2908 |  | 92
Works | 45 | 0 | 24 | 53 | 7080.2061 | 0 | 4487.8673 |  | 63
Services | 4 | 0 | 3 | 75 | 173.742 | 0 | 137.52 |  | 79
Total | 63 | 0 | 27 | 43 | 7571.0323 | 0 | 4625.3873 |  | 61
C.2. Fiscal Year 2019 - 2020
Description | Number |  |  |  | Amount (BDT in Lac)
| Project Procurement Plan | Procurement in Progress | Procurement done | % | Estimated Cost | Procurement in Progress | Contracted Amount | Completed | %
Goods | 33 | 0 | 3 | 9 | 724.5659 | 0 | 168.0097 |  | 23
Works | 80 | 0 | 32 | 40 | 9577.4294 | 0 | 4576.1504 |  | 48
Services | 53 | 0 | 46 | 87 | 7349.9743 | 0 | 3244.7421 |  | 44
Total | 166 | 0 | 81 | 49 | 17651.9696 | 0 | 7988.9022 |  | 45
C.3. Fiscal Year 2020 - 2021
Description | Number |  |  |  | Amount (BDT in Lac)
| Project Procurement Plan | Procurement in Progress | Procurement done | % | Estimated Cost | Procurement in Progress | Contracted Amount | Completed | %
Goods | 32 |  |  | - | 567.8395
Works | 139 |  |  | - | 11661.0453
Services | 13 |  |  | - | 5318.0315
Total | 184 |  |  | - | 17546.9162