## Moulvibazar
Rural Access Road Improvement Project Under Sylhet Division (RARIP)
Monthly Progress Report (Physical & Financial)
District: Moulvibazar. | [18 empty] | Month February-2021
Sl No. | Upazila | Package No. | Name of Scheme with Chainage & ID No | Quantity |  | Estimated Cost (Tk) |  |  | Cost of Salvage Material (Tk) | Tender Receiving Date | Name of Contractor | Date of NOA Issued | Date of Contract/Revised Contract | Contract /Variation Amount (Tk) | Work Commencement Date | Phy. Prog. (%) | Date of Comple-tion as per contract | Payment Amount for |  |  | Fin. Prog. (%) | Remarks
|  |  |  | Road (km) | Struct. (m) | Road | Struct. | Total | [9 empty] | Road (Tk) | Bridge/ Culvert (Tk) | Remaining Payment (Tk)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Village Road
1 | Sreemangal | LGED/RARIP/MOU/VR/19-20/W-30 | (a)Saitola-Paikpara Rd (Ch. 3400-4455m) under Sreemangal Upazila, ID no: 658744115, District: Moulvibazar | 1.055 | 4.4 | 9344764 |  | 20959964 |  | 22.09.20 | M/S MB-JRIT(JV) TB Gate,Mohakhali,Dhaka. | 27.12.20 | 21.01.21 | 21730291 | 27.01.21 | 0% | 27.01.22 | 0 |  | 21730291 | 0%
|  |  | (b) Improvement of Dasherbazar -Fakirbazar road to Chandgram GC road via Talukdarpara – Tuka road (Ch.1500-2877m) under Sreemangal Upazila, ID no: 658834022, District: Moulvibazar. | 1.377 | 3 | 11615200 | [9 empty] | 0%
2 | Sadar | LGED/RARIP/MOU/VR/18-19/W-67 | Improvement of R&H(Raysree)-Kamarkapon Road (Ch. 00-1365m) Salvage Cost. 149385/= under Sadar Upazila, ID no: 658744003, District: Moulvibazar. | 1.365 |  | 11126984 |  | 11126984 | 149385 | 24.10.18 | M/S Zafor Ahmed Gilman Dakkhin Bazar, Kulaura, Moulvibazar. 01711-065800 | 29.12.19 | 24.12.18 | 10743506 | 30.12.18 | 100% | 29.12.19 | 10685785 |  | 57721 | 99.46% | Final Bill Paid
3 | Sadar | LGED/RARIP/MOU/VR/18-19/W-68 | (a) Improvement of Monu Barage Taltola (Kulaura) road (Ch. 00-1730m) under Sadar Upazila, ID no: 658744128, District: Moulvibazar | 2.73 |  | 18778190 |  | 18778190 |  | 24.10.18 | M/S Zafor Ahmed Gilman Dakkhin Bazar, Kulaura, Moulvibazar. 01711-065800 | 7.1.19 | 22.01.19 | 18766039.35 | 28.1.19 | 100% | 28.01.20 | 17824663 |  | 941376.35 | 94.98%
| Barlekha |  | (b) Improvement of Dasherbazar -Fakirbazar road to Chandgram GC road via Talukdarpara – Tuka road (Ch. 2000 -3000m) under Baralekha Upazila, ID no: 6658144058, District: Moulvibazar. | [12 empty] | 100%
4 | Rajnagar | LGED/RARIP/MOU/VR/18-19/W-69 | Improvement of Chowdhury bazar RHD-Busbal Udna Rd. (Ch. 1000-2000m) under Rajnagor Upazila, ID no:658804020, District: Moulvibazar. | 1 |  | 7322506 |  | 7322506 | 2816940 | 24.10.18 | B. M Trade Center Motojhil C/A, Dhaka 01710-908083 | 29.11.18 | 26.12.18 | 7315007 | 01.01.19 | 100% | 01.01.20/14.03.20 | 4787000 |  | 2528007 | 65.44%
5 | Sreemangal | LGED/RARIP/MOU/VR/18-19/W-70 | Dackchara TE-Hailhaor road via Nowagaon village (Ch. 00-1650m) under Sreemongol Upazila, ID no: 658834077, District: Moulvibazar. | 1.65 |  | 11691953 |  | 11691953 |  | 24.10.18 | PD-JVCA (M/S Priti Enterprise & M/S Debangshu Sen) Sreemangal, Moulvibazar. 01711-467691 | 29.11.18 | 26.12.18 | 11661112.45 | 01.01.19 | 100% | 01.01.20 | 11653612 |  | 7500.45 | 99.94% | Final Bill Paid
6 | Kulaura | LGED/RARIP/MOU/VR/18-19/W-72 | (a) Improvement of Amjuhub-Tilashijura-Bobanipur Road (Ch. 00-1901m) under Kulaura Upazila ID No. 658654119 District: Moulvibazar Salvage Cost 19055/- | 3.601 | 3 | 27572817 |  | 27572817 | 19055 | 19.12.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 24.2.19 | 20.3.19 | 27572348.65 | 26.3.19 | 50% | 26.3.20 | 10409055 |  | 17163293.65 | 37.75% | Sub-base complete
|  |  | (b) Improvement of Chowdhury bazar-Kality Road (Ch. 2000-2480 & 3292-4512m) under Kulaura Upazila ID No. 658654096 District: Moulvibazar. | [12 empty] | 100% | [5 empty] | WBM Complete
7 | Kulaura | LGED/RARIP/MOU/VR/18-19/W-73 | Improvement of R&H Polokuna-Hingazia Road (Ch. 1467-2877m) under Kulaura Upazila ID No. 658654036 District: Moulvibazar. | 1.41 | 0 | 10338308 |  | 10338308 |  | 19.12.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. | 27.1.19 | 14.2.19 | 10337830.36 | 20.02.19 | 70% | 20.02.20 | 7120612 |  | 3217218.36 | 68.88% | WBM Complete
8 | Kamalgonj | LGED/RARIP/MOU/VR/18-19/W-74 | (a) Improvement of Shamshernagar -Daffolchara BDR Camp. Road via Chatlapur Road (Ch. 1000-2000m) under Kulaura Upazila ID No. 658564015 District: Moulvibazar | 2 | 0 | 14770724 |  | 14770724 |  | 19.12.18 | M/S Suhag Enterprise Joypasa,Kulaura,Moulvibazar01712-763155 | 24.2.19 | 20.03.19 | 14770076.6 | 27.03.19 | 100% | 27.03.20 | 9730831 |  | 5039245.6 | 65.88% | WBM Complete
|  |  | (b) Improvement of Choycut-Kalenga Road (Ch. 2600-3600m) under Kulaura Upazila ID No. 658564032 District: Moulvibazar. | [12 empty] | 100% | [5 empty] | WBM Complete
9 | Barlekha | LGED/RARIP/MOU/VR/18-19/W-75 | (a) Improvement of Shahbazpur UP office-Btotrashree GPS via Uzanipara Reg. Primary School - Rail Station road (Ch. 1700 -2700m) under Baralekha Upazila, ID no: 6658144091, District: Moulvibazar | 1.61 |  | 10506182 |  | 10506182 |  | 24.10.18 | M/S Sharif Enterprise, Barlekha Moulvibazar. 01715-525005 | 29.11.18 | 27.12.18 | 10448418 | 02.01.19 | 100% | 29.11.19 | 10250155 |  | 198263 | 98.1% | Final Bill Paid
| Juri |  | (b) Improvement of Bhugtera - Biswanathpur Road (Ch. 3190-3800m) under Juri Upazila, ID no: 658844031, District: Moulvibazar | [12 empty] | 100%
10 | Barlekha | LGED/RARIP/MOU/VR/18-19/W-76 | RHD-Bichrabond Road (Ch. 00 -1000m) under Baralekha Upazila, ID no: 658144028, Salvage Cost. 117208/= District: Moulvibazar. | 1 |  | 8232437 |  | 8232437 | 117208 | 24.10.18 | M/S Sharif Enterprise, Barlekha Moulvibazar. 01715-525005 | 29.11.18 | 27.12.18 | 8200935 | 02.01.19 | 100% | 13.11.19 | 5988041 |  |  | 73.02%
11 | Juri | LGED/RARIP/MOU/VR/18-19/W-77 | Improvement of Bashirpur-Bazarchali Road (Ch. 00-1000m) under Juri Upazila, ID no: 658844008,District: Moulvibazar | 1 |  | 9082040 |  | 9082040 |  | 24.10.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 29.11.18 | 26.12.18 | 9076242.67 | 01.01.19 | 100% | 01.01.20 | 9066090 |  | 10152.67 | 99.89%
12 | Juri | LGED/RARIP/MOU/VR/18-19/W-78 | (a) Improvement of Ratna Bazar-Somai Bazar via Jalalpur (Jalalpur- Ratna ) Road (Ch. 1310 -2310m) under Juri Upazila, ID no: 658844010, District: Moulvibazar | 1.45 |  | 11096426 |  | 11096426 |  | 11.2.19 | M/S Mir Brothers-Lajowness International (JV),Tejgaon, Dhaka | 2019-09-22 | 17.10.19 | 11459812 | 23.10.19 | 25% | 22.10.20 | 0 |  | 11459812 | 0%
|  |  | (b) Paschim Shilua-Borodohor road (Ch. 1250 -1700m) under Juri Upazila, ID no: 658845089 (New ID 658845106), District: Moulvibazar | [12 empty] | 0%
13 | Kamalgonj | LGED/RARIP/MOU/VR/18-19/W-79 | Vice-principal Abdus Shahid (Hospital) Road (Ch. 1850-2460 & 3810-4200m) under Kulaura Upazila ID No. 658564029 District: Moulvibazar Salvage Cost- 44608/- | 1 | 0 | 7182757 |  | 7182757 | 44608 | 19.12.18 | M/S Suhag Enterprise Joypasa,Kulaura, Moulvibazar. 01712-763155 | 27.01.19 | 2019-02-03 | 7182656.32 | 09.02.19 | 100% | 9.2.20 | 7181268 |  | 1388.32 | 99.98% | Final Bill Paid
14 | Rajnagar | LGED/RARIP/MOU/VR/18-19/W-91 | (a) Improvement of Madhurbazar-Raktha-Amirpur road (Ch. 00 -550m) under Rajnagar Upazila, ID no: 658804051, District: Moulvibazar | 1.25 |  | 9167348 |  | 9167348 | 187891 | 24.10.18 | Shueb Ahmed Barlekha, Moulvibazar. 01910-821429 | 12.11.18 | 26.12.18 | 9122759 | 01.01.19 | 100% | 25.11.19 | 5951586 |  | 3171173 | 65.24%
| Barlekha |  | (b) Barlekha Degree College- Mohammednagar via Gangerjal & Balichara road (Ch. 1500 -2200m) under Barlekha Upazila, ID no: 6658144093, District: Moulvibazar | [5 empty] | 28212 | [6 empty] | 100%
15 | Rajnagar | LGED/RARIP/MOU/VR/18-19/W-111 | Panchanandapur-Paulpur Rd (Ch. 1000-2000m) under Rajnagor Upazila, ID no:658804044, District: Moulvibazar | 1 |  | 7342509 |  | 7342509 |  | 24.10.18 | B. M Trade Center Motojhil C/A, Dhaka . 01710-908083 | 29.11.18 | 26.12.18 | 7332073 | 01.01.19 | 25% | 01.01.20 | 0 |  | 7332073 | 0% | ISG Ongoing
15 |  |  | Sub-Total | 24.498 | 10.4 | 185171145 | 0 | 185171145 | 3363299 |  |  |  | 43499 | 185719107.4 | 0 | 16.7 | 0 | 110648698 | 0 | 72857515.4
Rehabilitation
16 | Sreemangal | LGED/RARIP/MOU/RHB/18-19/W-131 | (a) Rehabilitation of Beltuli-Madhya Road (Ch. 00-1695m) under Sreemangal Upazila ID No. 658834073 District: Moulvibazar | 6.081 | 0 | 12509918 |  | 12509918 |  | 19.12.18 | PD-JVCA (M/S Priti Enterprise & M/S Debangshu Sen) Sreemangal, Moulvibazar. 01711-467691 | 24.2.19 | 22.03.19 | 13398261.67 | 27.03.19 | 100% | 23.11.19 | 13398250 |  |  | 100% | Final Bill Paid
|  |  | (b) Rehabilitation of Hajipurbazar-Hail haor Road (Ch. 00-2151m) under Sreemangal Upazila ID No. 658835055 District: Moulvibazar | [12 empty] | 100%
|  |  | (C) Rehabilitation of Satgaon UP (Lachna) to Mirzapur UP Via Makricharra Bazar Road (Ch. 00-2235m) under Sreemangal Upazila ID No. 658833004 District: Moulvibazar. | [12 empty] | 100%
17 | Kulaura | LGED/RARIP/MOU/RHB/18-19/W-132 | (a) Rehabilitation of Tillagaon UP office -Fatikully Road (Ch. 00-1700 & 3260-3560m) under Kulaura Upazila, ID no:658653017, District: Moulvibazar | 5.4 |  | 11145183 |  | 11145183 |  | 25.10.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 29.11.18 | 24.12.18 | 11140205 | 30.12.18 | 100% | 31.12.19 | 11009480 |  |  | 98.83% | Final Bill Paid
|  |  | (b) Rehabilitation ofChowdhuribazar-Milarmar Ghat Road (Ch. 00-2100m) under Kulaura Upazila, ID no:658654022 District: Moulvibazar | [12 empty] | 100%
|  |  | (c) Rehabilitation of Brahman bazar-Fenchugonj Road to Baramchal-Mohalal Road (Ch. 00-1300m) under Kulaura Upazila, ID no: 658654030, District: Moulvibazar. | [12 empty] | 100%
18 | Barlekha | LGED/RARIP/MOU/RHB/18-19/W-133 | a) Rehabilitation of Kalibari Bazar - Nijbahadurpur UP Office Road (Ch. 3000-5000m) under Baralekha Upazila, ID no: 658143003, District: Moulvibazar | 4.96 |  | 9159076 |  | 9159076 |  | 25.10.18 | Khandakar Lutfur Rahman, & Khaled Ahmed (JV) Kulaura, Moulvibazar. 01715-095078 | 29.11.18 | 26.12.18 | 9254915.32 | 01.01.19 | 100% | 01.01.20 | 9180613 |  | 74302.32 | 99.2% | Final Bill Paid
|  |  | (b) Rehabilitation of Chandgram RHD-Purba Maizgram Road (Ch. 00-2000m) under Baralekha Upazila, ID no: 658144005, District: Moulvibazar | [12 empty] | 100%
| Kulaura |  | (c) Rehabilitation of Pekurbazar-Koula rashi salehpur Road (Ch. 00-960m) under Kulaura Upazila, ID no:658654057 District: Moulvibazar. | [12 empty] | 100%
19 | Kamalgonj | LGED/RARIP/MOU/RHB/18-19/W-134 | (a) Patrokhola-Dholai BOP Road (Ch. 1600-3600m) under Kamalgonj Upazila, ID no: 658564041, District: Moulvibazar | 3 |  | 5281392 |  | 5281392 |  | 13.11.18 | B. M Trade Center Motojhil C/A, Dhaka . 01710-908083 | 26.12.18 | 22.01.19 | 5289024 | 28.01.19 | 100% | 28.01.20 | 5152269 |  | 136755 | 97.41% | Final Bill Paid
| Rajnagar |  | (b) Highway Gayaspur-Indesswar T.E. Road (Ch. 00-1000m) under Rajnagor Upazila, ID no:658804013, District: Moulvibazar. | [12 empty] | 100%
20 | Rajnagar | LGED/RARIP/MOU/RHB/17-18/W-135 | a) Rehabilitation of Assain Highway-Bagajura Road (Ch. 00-500m) under Rajnagor Upazila, ID no:658804032, District: Moulvibazar | 2.5 |  | 6221514 |  | 6221514 |  | 25.10.18 | M/S Zafor Ahmed Gilman Dakkhin Bazar, Kulaura, Moulvibazar. 01711-065800 | 29.11.18 | 24.12.18 | 6066815 | 30.12.18 | 100% | 29.12.19 | 5919991 |  | 146824 | 97.58% | Final Bill Paid
| Sadar |  | (b) Rehabilitation of R&H (Mukambazar)-Premnagori Tea Garden Road (Ch. 80-2080m) under Sadar Upazila, ID no:658744115, District: Moulvibazar. | [12 empty] | 100%
21 | Sadar | LGED/RARIP/MOU/RHB/17-18/W-140 | Kazir Bazar-Manumukh Road (Ch. 00-2900m) under Sadar Upazila, ID no:658744061, District: Moulvibazar. | 2.9 |  | 10458481 |  | 10458481 |  | 25.10.18 | Tufaiel Ahmed Baharmordan Moulvibazar. | 29.11.18 | 26.12.18 | 9904825 | 01.01.19 | 100% | 01.01.20 | 9902738 |  |  | 99.98% | Final Bill Paid
22 | Juri | LGED/RARIP/MOU/RHB/18-19/W-146 | a) Rehabilitation of Fultala - Konagaon Road (Ch. 00-1040m) under Juri Upazila, ID no: 658844047, District: Moulvibazar. . | 6 |  | 8847160 |  | 8847160 |  | 13.11.18 | M/S Mollah Enterprise, 257/A, Bara Mogbazar, Dhaka.01711-473844 | 26.12.18 | 09.01.19 | 8836671 | 15.01.19 | 100% | 14.01.20 | 1748766 |  | 7087905 | 19.79%
|  |  | (b) Rehabilitation of Ratna Bazar-Shomai Bazar Via Jalalpur Road (Ch. 00-1310m) under Juri Upazila, ID no: 658844010, District: Moulvibazar. | [12 empty] | 100%
|  |  | (c) Rehabilitation of Shamai-Baraitali Road (Ch. 00-1650m) under Juri Upazila, ID no:65884030 District: Moulvibazar | [12 empty] | 40%
| Barlekha |  | (d) Rehabilitation of Satpur-Kazirbond Road (Ch. 810-2810m) under Baralekha Upazila, ID no:658144013 District: Moulvibazar. | [12 empty] | 0%
23 | Sadar | LGED/RARIP/MOU/RHB/19-20/W-150 | R&H (Mukambazar)-Premnagori Tea Garden Rd. (Ch. 2080-3780m)under Sadar Upazila, ID no:658744115, District: Moulvibazar. | 1.7 | 0 | 6399572 | 0 | 6399572 |  | 22.09.20 | M/S MB-JRIT(JV) TB Gate,Mohakhali,Dhaka. | 24.11.20 | 23.12.20 | 6329134 | 29.12.20 | 25% | 28.12.21 | 0 |  | 6329134 | 0%
8 |  |  | Sub-Total | 32.541 | 0 | 70022296 | 0 | 70022296 | 0 |  |  |  |  | 70219850.99 |  |  |  | 56312107 | 0 | 13774920.32
Union Road
24 | Barlekha | LGED/RARIP/MOU/UNR/18-19/W-06 | (a) Improvement of Talimpur UP Office-Edghabazar RHD via Kanchanpur Road (Ch. 1000-3000m) under Barlekha Upazila ID No. 658143011 District: Moulvibazar | 5.437 |  | 38670104 |  | 38670104 |  | 11.02.19 | M/S Mir Brothers-Lajowness International (JV),Tejgaon, Dhaka | 2019-05-12 | 2019-06-09 | 40479352.49 |  | 45% | 14.6.20 | 7001476 |  | 33477876.49 | 17.3% | Sub-base complete
| Kulaura |  | (b) Improvement of Purshai-Dewgoan-Rangichara Road (Ch. 3513-4950m) under Kulaura Upazila ID No. 658653025 District: Moulvibazar | [12 empty] | 65% | [5 empty] | WBM Complete
|  |  | (C) Improvement of Nawabgonj Batera via Berkuri [Nawabgonj UP office (Rasolgonj Bazar)- Batera via Berkuri] Road (Ch. 1500-3500m) under Kulaura Upazila ID No. 658653010 District: Moulvibazar Salvage Cost- 268537/- | [12 empty] | 10%
25 | Sadar | LGED/RARIP/MOU/UNR/18-19/W-07 | (a) Improvement of R&H -Sarkarbazar-Monumuk Bazar Road (Ch. 5000-5300m) under Sadar Upazila ID No. 658743007 District: Moulvibazar | 3.942 | 8.25 | 30049179 |  | 30049179 |  | 11.2.19 | ME & GU (JV)Motijhil, Dhaka | 12.5.16 | 9.6.19 | 29897420.85 |  | 25% | 14.6.20 | 8697615 |  | 21199805.85 | 29.09%
|  |  | (b) Improvement of Chadnighat-Balikandi-Palpur Road (Ch. 4500-4800 & 4850-6550m) under Sadar Upazila ID No. 658743006 District: Moulvibazar | [12 empty] | 50% | [5 empty] | WBM ongoing
| Kamalgonj |  | (C) Improvement of Adampur-Adkanibazar Road via Kawargola Bazar Road (Ch. 3000-4180 & 4210-4672m) under Kamalgonj Upazila ID No. 658563003 District: Moulvibazar. | [12 empty] | 55% | [5 empty] | WBM ongoing
2 |  |  | Sub-Total | 9.379 | 8.25 | 68719283 | 0 | 68719283 | 0 |  |  |  |  | 70376773.34 |  |  |  | 15699091 | 0 | 54677682.34
Bridge
26 | Kamalgonj | LGED/RARIP/MOU/BDG(UNR)/19-20/W-16 | Construction of 25m long PC Girder Bridge on Adampur-Adkanibazar Road via Kawargola Bazar at Ch.2750m |  | 25 |  | 20276039 | 20276039 |  | 12.11.19 | M/S Eli Enterprise Sadar Road,Bhola. | 29.11.20 | 29.12.20 | 20219821 | 04.01.21 | 0% | 04.01.22 |  | 0 | 20219821 | 0%
26 | Rajnagar | LGED/RARIP/MOU/BDG(VR)/19-20/W-71 | Construction of 46m long RCCC Girder Bridge on Holdigul-Kalabazar road to Bokshipur road at CH.250 |  | 46 |  | 34266286 | 34266286 |  | 12.11.19 | Dhrob-Mosarf(JV) Modhasheri Sherpur, Sherpur | 9.02.20 | 2.3.20 | 35970219 | 9.3.20 | 30% | 8.3.21 |  | 0 | 35970219 | 0%
28 | Barlekha | LGED/RARIP/MOU/BDG(VR)/19-20/W-117 | Construction of 20m long RCCC Girder Bridge onon Atuaborail-Kumarshail Road at Ch.3500m |  | 20 |  | 15755070 | 15755070 |  | 12.11.19 | Dhrob-Mosarf(JV) Modhasheri Sherpur, Sherpur | 9.2.20 | 2.3.20 | 16544966 | 9.3.20 | 70% | 8.3.21 |  | 5260000 | 11284966 | 31.79%
3 |  |  | Sub-Total | 0 | 91 | 0 | 70297395 | 70297395 | 0 |  |  |  |  | 72735006 |  |  |  | 0 | 5260000 | 67475006
Market
29 | Barlekha | LGED/RARIP/MOU/MAR/19-20/W-159 | a)Improvement of Dakshinbagh Bazar under Barlekha Upazila. District: Moulvibazar. |  |  |  |  | 4345622 | [13 empty] | Evaluation Under Process
|  |  | b)Improvement of Mammodtokti Bazar under Barlekha Upazila. District: Moulvibazar. |  |  |  |  | 4675017
| Kulaura |  | c)Improvement of Nabiganj Bazar under Kulaura Upazila. District: Moulvibazar. |  |  |  |  | 4724036
30 | Kulaura | LGED/RARIP/MOU/MAR/18-19/W-160 | a) Improvement of Rasulgonj Bazar under Kuraura Upazila, District: Moulvibazar |  |  |  |  | 7822237 |  | 8.12.19 | Md.Khaled Ahmed,Kulaura,Moulvibazar | 9.3.20 | 22.3.20 | 8199694 | 28.3.20 | 90% | 27.3.21 | 0 | 0 | 8199694 | 0%
|  |  | b) Improvement of Pirer Bazar (Hajipur UP) under Kuraura Upazila, District: Moulvibazar | [12 empty] | 95%
31 | Sadar | LGED/RARIP/MOU/MAR/18-19/W-161 | a) Improvement of Sarkar Bazar under Sadar Upazila, District: Moulvibazar |  |  |  |  | 5385547 |  | 8.12.19 | Tufaiel Ahmed Baharmordan Moulvibazar. | 9.3.20 | 11.6.20 | 5625937 | 17.6.20 | 5% | 12.5.21 | 0 | 0 | 5625937 | 0%
|  |  | b) Improvement of Dighirpar Bazar under Sadar Upazila, District: Moulvibazar | [12 empty] | 50%
32 | Sreemangal | LGED/RARIP/MOU/MAR/18-19/W-162 | a) Improvement of Mirzapur Bazar under Sreemangal Upazila, District: Moulvibazar |  |  |  |  | 4161316 |  | 8.12.19 | Tufaiel Ahmed Baharmordan Moulvibazar. | 9.3.20 | 11.6.20 | 4357986 | 17.6.20 | 70% | 12.05.21 | 1894530 | 0 | 2463456 | 43.47%
4 |  |  | Sub-Total | 0 | 0 | 0 | 0 | 31113775 | 0 |  |  |  |  | 18183617 |  |  |  | 1894530 | 0 | 16289087
32 |  |  | Grand Total = | 66.418 | 109.65 | 323912724 | 70297395 | 425323894 | 3363299 |  |  |  |  | 417234354.73 |  |  |  | 184554426 | 5260000 | 225074211.06
|  | Accountant |  | Sub-Asstt-Engineer | [5 empty] | Asstt-Engineer | [5 empty] | Senior Asstt-Engineer |  |  |  | Executive Engineer
|  | LGED, Moulvibazar. |  | LGED, Moulvibazar. | [5 empty] | LGED, Moulvibazar. | [5 empty] | LGED, Moulvibazar. |  |  |  | LGED, Moulvibazar.