## Sunamganj
Rural Access Road Improvement Project Under Sylhet Division (RARIP)
Monthly Progress Report (Physical & Financial)
District: Sunamgonj | [16 empty] | Month February-2021
SL. No. | Upazila | Package No | Name of Scheme with Chainage & road ID No | Quantity |  | Estimated Cost (TK) |  |  | Cost of Salvage Material (TK) | Tender Recei. Date | Name of Contractor | Date of NOA Issued | Date of Contrat/Received Contract | Contract /Variation Amount (tk) | Work Commen. Date. | Phy Prog (%) | Date of Comple. as per Contract | Payment made (TK) |  |  | Fin. Prog (%) | Remarks
|  |  |  | Road (km) | Struct (m) | Road | Struct | Total
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Village Road
1 | South Sunamgonj | LGED/RARIP/SUN/VR/18-19/W-31 | a)Damadurtupi -Ghuradumbur road (Ch1650-2740m)Road ID NO- 690934007 | 1.09 |  | 12907726 |  | 12907726 | [13 empty] | 2nd call Re -Tender under process
|  |  | a)Jagannathpur road -Sichni south road [RHD (sicni-RHD (Minabazer)-pagla UZR Road] (ch 1000-2000) road ID No 690934020 | 1
2 | Chatak | LGED/RARIP/SUN/VR/18-19/W-32 | Moula (UZR)-Chowmuhoni bazer road via Rajapur road (Ch 1700-2700.Road ID No 690234022 | 1 | 1.125 | 9228215 | 136823 | 9365038 |  | 5.11.18 | M/S Nurul Islam 01713-812992 | 4.12.18 | 01.01.19 | 8509132.67 | 14.1.19 | 35% | 31.12.19 | 2567000 |  | 5942132.67 | 30%
3 | Chatak | LGED/RARIP/SUN/VR/18-19/W-33 | Jugal Nagar-Tuker Bazar road (Ch.00-1000m). Road ID NN0- 690235094 | 1 |  | 7207945 |  | 7207945 | 109771 | 21.1.19 | M/S Lucky Enter Prise | 13.03.19 | 10.4.19 | 7908016 | 24.4.19 | 95% | 23.4.20 | 6634000 |  | 1274016 | 51%
4 | Jagannathpur | LGED/RARIP/SUN/VR/18-19/W-34 | Mojidpur (Pagla-Jagannathpur R&H)-Aralia road (Ch.00-1000m). Road ID No- 690474027 | 1 |  | 6585722 |  | 6585722 |  | 12.06.19 | Marina Construction Associates LTD 01711385957 01912043920 | 28.11.19 | 23.12.19 | 7532568 | 07.1.20 | 60% | 31.12.20
5 | Jagannathpur | LGED/RARIP/SUN/VR/18-19/W-35 | a) Rowail-Hilalpur road (Ch.2000-2670m). Road ID No-690474001 | 0.67 |  | 20045154 |  | 20045154 |  | 5.11.18 | JV of Belal Enterprise 01712-442893 | 14.1.19 | 07.02.19 | 19907548 | 20.2.20 | 60% | 20.02.20 | 6735000 |  | 13172548 | 32%
| Sadar |  | b) Sunamgonj-Chatak road to Alampur via Shahapur-Monoharpur Road (Ch.5750-6250m). Road ID No-690894067 | 0.5 | [11 empty] | 100%
| Sadar |  | C) Katair-Joynagar road to Kalaia Village road (Ch.00-1000m). Road ID No-690895034 | 1 | [11 empty] | 5%
6 | Jamalgonj | LGED/RARIP/SUN/VR/18-19/W-36 | Amanipur-Nidhipur road (Ch.00-1000m). Road ID No- 690504004 | 1 |  | 8840492 |  | 8840492 |  | 5.11.18 | Md. Atiqur Rahman. 01712-521355 | 4.12.18 | 01.01.19 | 8810455 | 14.1.19 | 100% | 31.12.19 | 8785996 |  |  | 100% | Final
7 | Jamalgonj | LGED/RARIP/SUN/VR/18-19/W-37 | a) Harinakandi-Ahcanpru road (Ch.00-1000m). Road ID No-690506035 | 1 |  | 15559515 |  | 15559515 |  | 5.11.18 | Aminul Islam Saim 01712-570420 | 14.1.19 | 07.02.19 | 15554733 | 21.2.19 | 100% | 20.02.20 | 8800000 |  | 6754733 | 56%
| Tahirpur |  | b) Baradol Uttar Up Office-Rajai road (Ch.1500-2250m & 2850-3100m). Road ID No-690924007 | 1 | [11 empty] | 30%
8 | Derai | LGED/RARIP/SUN/VR/18-19/W-38 | a) Negergaon Ferrighat-Nasni bazar road (Negergaon Ferryghat-Nachni bazar via Milon Bazar road) (Ch.5654-7100m). Road ID No-690294018 | 1.446 | 1.8 | 12495586 | 525313 | 27331572 | [13 empty] | TER sent to HQ 13.01.21
|  |  | b) Ditpur-Hossainpur via Pukidohar Kamribiz road (Ch.1000-2500m). Road ID No-690294018 | 1.5 |  | 14310673
9 | Derai | LGED/RARIP/SUN/VR/18-19/W-39 | Boalia Bazar-Tengrakhali road (Ch.1000-1950m). Road ID No-690294008 | 0.95 |  | 8868403 |  | 8868403 |  | 12.12.18 | Aminul Islam Saim 01712-570420 | 18.10.19 | 12.11.19 | 9754839 | 1.12.19 | 30% | 30.11.20 | 2565000 |  | 7189839 | 0.26295
10 | Biswamberpur | LGED/RARIP/SUN/VR/18-19/W-40 | a) Dhanpur-Bachurbari-Mothurkandi road(Dhanpur-Mothourkandi Bazar via Mujib bazar road) (Ch.1000-2000m. Road ID No-690184002 | 1 |  | 17388451 |  | 17388451 |  | 5.11.18 | M/S Aminul Haque & Co 01711-026722 | 14.1.19 | 07.02.19 | 17367912 | 21.2.19 | 95% | 20.02.20 | 8712000 |  | 8655912 | 50%
|  |  | b) RHD Post Office-Mollikpur Kasmer Jungle Road (Ch.00-1000m). Road ID No-690184054 | 1 | [11 empty] | 45%
11 | Dowarabazar | LGED/RARIP/SUN/VR/18-19/W-41 | a) Haripadnagar Village Road (Ch.500-1500m). Road ID No-690335077 | 1 |  | 21735398 |  | 21735398 |  | 5.11.18 | M/S Aminul Haque & Co. 01711-026722 | 14.1.19 | 07.02.19 | 20352498 | 21.2.19 | 0% | 20.02.20 | 8326003 |  | 12026495 | 40%
|  |  | b) Manargaon-Putipushi Road (Ch.1000-2000m).Road ID No-690334061 | 1 | [11 empty] | 50%
|  |  | C) Dowarabazar-Banglabazar Road to Ustingergaon road (Ch.00-500m). Road ID No-690335074 | 0.5 | [11 empty] | 100%
12 | Dowarabazar | LGED/RARIP/SUN/VR/18-19/W-42 | Norshingpur bazar-Notun Sirajpur Road (Ch.500-1500m). Road ID No-690335034 | 1 |  | 8778036 |  | 8778036 |  | 5.11.18 | M/S Nurul Islam 01713-812992 | 4.12.18 | 01.01.19 | 8995559 | 14.1.19 | 95% | 31.12.19 | 8100000 |  | 895559 | 90.04%
13 | Biswamberpur | LGED/RARIP/SUN/VR/18-19/W-43 | Mollikpur-DB College Road (Ch.00-1095m). Road ID No-690184041 | 1.095 | 2.74 | 11092489 | 231918 | 11324407 |  | 5.11.18 | M/S Akber Ali 01716-122058 | 4.12.18 | 01.01.19 | 11308919 | 14.1.19 | 95% | 31.12.19 | 10354000 |  | 954919 | 91.56%
14 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-44 | Dharmapash-Union Parishad-Kandapara via Radhanagor Rd (Ch.2200-3200m). Road ID No-690324002 | 1 |  | 10025005 |  | 10025005 |  | 5.11.18 | M/S Anwara Enterprise 01712-393624 | 4.12.18 | 01.01.19 | 10004558 | 14.1.19 | 60% | 31.12.19 | 5729000 |  | 4275558 | 57%
15 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-45 | a) Gastola Bazar-Siram Bazar (Barhatta) via Thanura Pasham road (Ch.1000-2000m). Road ID No-690324015 | 1 |  | 18902298 |  | 18902298 |  | 01.04.19 | Atiqur-Anwara (JV) 01712-393624 | 28.11.19 | 24.12.19 | 20767198 | 14.1.20 | 60% | 31.12.20
|  |  | b) Dharmapasha FRB-Singpur Road (Ch.00-1000m). Road ID No-690325025 (New 690324026). | 1 | [11 empty] | 5%
16 | Sulla | LGED/RARIP/SUN/VR/18-19/W-46 | Kashipur to Chakua road (Ch.00-1000m). Road ID No-690864002 | 1 | 2.25 | 11497300 | 359685 | 11856985 | [13 empty] | TER sent to HQ 13.01.21
17 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-98 | a) Razapur-Gazaria ghat road (Ch.00-1000m). Road ID No-690324003 | 1 |  | 16532830 |  | 16532830 |  | 12.06.20 | Atiqur-Anwara-(JV) | 3.03.20 | 25.03.20 | 19738138 | 07.04.20 | 20% | 06.04.20
|  |  | b) Paykurati Union Parishad-Jamalpur Rd (Ch.2350-3340). Road ID No-690324010 New-690323019 | 0.99
18 | South Sunamgonj | LGED/RARIP/SUN/VR/18-19/W-99 | Asampur Fery Ghat-Ashampur GPS road [RHD (Pagla)-Asampur Fery Ghat Road] (Ch.00-1500m). Road ID No-690934069 New 690934101 | 1.5 |  | 11624937 |  | 11624937 |  | 5.11.18 | M/S Sojib Construction 01714-698665/01712-442893 | 4.12.18 | 01.01.19 | 11609991 | 14.1.19 | 70% | 31.12.19 | 4975000 |  | 6634991 | 42%
19 | Dowarabazar | LGED/RARIP /SUN/VR/18-19/W-100 | Improvement of Chatak -Sunamganj Road -Beri School road (Ch.1500-2000),Road ID No: 690335059 | 0.5 |  | 4850377 |  | 4850377 | [13 empty] | Tender Received Date on 25.02.21
20 | Chatak | LGED/RARIP/SUN/VR/18-19/W-101 | Rukka Bazar-Rukka Madrasha road (Ch.1500-2500m). Road ID No-690235080 | 1 | 1.125 | 9240035 | 94962 | 9334997 |  | 5.11.18 | M/S Nurul Islam. 01713-812992 | 4.12.18 | 01.01.19 | 9306766 | 14.1.19 | 100% | 31.12.19 | 6779000 |  | 2527766 | 72.84%
21 | Chatak | LGED/RARIP/SUN/VR/18-19/W-102 | Noagaon-Senpur (Monir Gati) road (Ch.00-145m & Ch.485-1340m). Road ID No-690235036 | 1 | 1.125 | 7985261 | 101568 | 8086829 |  | 5.11.18 | M/S Lucky Enter Prise | 4.12.18 | 01.01.19 | 8073056 | 14.1.19 | 100% | 31.12.19 | 7600000 |  | 473056 | 94%
22 | Jagannathpur | LGED/RARIP/SUN/VR/18-19/W-103 | Shibganj-Arunday Girls High School roa-to -Dustapur road (Ch.00-1000m). Road ID No-690475084 | 1 |  | 6913112 |  | 6913112 | 69646 | 12.06.19 | Marina Construction Associates LTD 01711385957 01912043920 | 28.11.19 | 23.12.19 | 7768732 | 07.01.20 | 0% | 31.12.20
23 | Jamalgonj | LGED/RARIP/SUN/VR/18-19/W-104 | Gucchagram-Badarpur road (Ch.2500-3500m). Road ID No-690505007 | 1 |  | 8840492 |  | 8840492 |  | 5.11.18 | M/S Sojib Construction 01714-698665 | 4.12.18 | 01.01.19 | 8828355 | 14.1.19 | 100% | 31.12.19 | 7932000 |  | 896355 | 89.85%
24 | Dowarabazar | LGED/RARIP/SUN/VR/18-19/W-105 | Banglabazar-Haquenagar-Dhakin Chowdhuripara road (Ch.100-1100m). Road ID No-690335054 | 1 |  | 8777036 |  | 8777036 |  | 5.11.18 | M/S Aminul Haque & Co. 01711-026722 | 4.12.18 | 01.01.19 | 8224559 | 14.1.19 | 100% | 31.12.19 | 6400000 |  | 1824559 | 77.82%
25 | Dharmapash | LGED/RARIP/SUN/VR/18-19/W-106 | Paykurati-Barikandi Via Chakiacapur road (Ch.00-1000m). Road ID No-690324007 | 1 |  | 9172088 |  | 9172088 |  | 5.11.18 | M/S Baset Prokousholi, 01916-855289 | 4.12.18 | 01.01.19 | 9164721 | 14.1.19 | 100% | 31.12.19 | 9138081 |  |  | 100% | Final
25 | Sub- Total |  |  | 34.741 | 10.165 | 299404576 | 1450269 | 300854845 | 179417 |  |  |  |  | 249488253.67 |  |  |  | 120132080 | 0 | 73498438.67
Union Road
26 | Sadar | LGED/RARIP/SUN/UNR/18-19/W-03 | Haluar Ghat-Ibrahimpur (Surma UPC)-via Moinpur Road (Ch.1200-2351m). Road ID No-690893016 | 1.151 | 4.5 | 28028145 | 1376020 | 29404165 |  | 29.10.18 | M/S Milonkanti Dey 01712-020736 | 4.12.18 | 07.02.19 | 27633182 | 14.1.19 | 100% | 20.02.20 | 22381000 | 1151000 | 4101182 | 85%
| Dowarabazar |  | Banglabazar-Haquenagarbazar-Boglabazar road (Ch.6960-8960). Road ID No-690333006 | 2 | [11 empty] | 100%
27 | Derai | LGED/RARIP/SUN/UNRS/18-19/W-04 | Bangla Bazar-Alipur-Lepsia (Khaliajuri) road (Ch.5490-7690m). Road ID No-690293003 | 2.2 | 1.875 | 25387509 | 575853 | 51469258 | [13 empty] | Tender document sent to HQ 30.12.20
|  |  | Badolpur RHD-Shyamarchar via Gochia, Rajanagar, Chanarchar Bazar road (Ch.7525-9275 & 10925-11675m). Road ID No-690293008 New-690292007 | 2.5 | 1.25 | 25121994 | 383902
28 | Jagannathpur | LGED/RARIP/SUN/UNR/18-19/W-05 | Shibganj-Raniganj road (Ch.1000-3250m). Road ID No-690473015 | 2.25 |  | 32836774 |  | 32836774 | 776209 | 12.06.19 | MCAL&G I(JV) | 25.03.20 | 19.04.20 | 37664887 | 01.05.20 |  | 30.4.21
|  |  | Enayetganj-Harinakandi via Gopalgonj road (Ch.5000-7500m). Road ID No-690473007, Salvage-776209/- | 2.5 | [11 empty] | 45%
29 | jamalganj | LGED/RARIP/SUN/UNRS/19-20/W-13 | Improvement of jamalganj hat-Fenarbakh UP office -Laksmipur bazer road (ch.00-1100m & 4840-5740m) ,ID NO 690503004 | 2 |  | 23136735 |  | 76233318 | [13 empty] | Evaluation under process to HQ
|  |  | Improvement of Makorkhola-shantoshpur road (ch.00-4500m) ,ID NO 690504017 | 4.5 |  | 53096583
30 | Sulla | LGED/RARIP/SUN/UNRS/19-20/W-13(a) | Improvement of Sulla bazer-Durlabpur road (ch.1650-2500m) ,ID NO 690864005 | 0.9 |  | 10267961 |  | 57982212 | [13 empty] | Evaluation under process to HQ
| Sulla |  | Improvement of Saskhai bazer-protabpur bazer road (ch.3000-5000m) ,ID NO 690863004 | 2 | 1.5
| Derai |  | Improvement of Mirzapur-Rafinagar-Hasnabad road (ch.3080-5250m) ,ID NO 690294001 | 2.17 | 1.25
31 | Biswamberpur | LGED/RARIP/SUN/UNR/18-19/W-14 | a) Dhakin Badaghat UP Office Basantapur Bazar Katakhali Bazar road (Ch.2000-4000m). Road ID No-690183004 | 2 | 10.25 | 26947599 | 2448378 | 29395977 |  | 29.10.18 | JV of Belal Enterprise 01712-442893 | 14.1.19 | 07.02.19 | 29338743 | 21.2.19 | 60% | 20.02.20 | 16224625 |  | 13114118 | 55%
| Chatak |  | b) Burarigaon-Alampur-Khaergaon Rd (Ch.2200-3200m). Road ID No-690233002 | 1 | [11 empty] | 85%
32 | Jamalgonj | LGED/RARIP/SUN/UNRS/18-19/W-15 | a) Sachna Bazar UP Office (Fazilpur) Ramnagar-Bazar Road (Ch.4150-5150m). Road ID No-690503001 | 1 |  | 9413064 |  | 29940520 | [13 empty] | TER sent to HQ 13.01.21
| Dharmapash |  | c) Dharmapash-Badshagonj via Mohishakanda Bazar road (Ch.5400-7500m). Road ID No-690323001 | 2.1 | 1.25 | 20317855 | 209601
33 | South Sunamgonj | LGED/RARIP/SUN/UNRS/19-20/W-19 | Improvement of pagla-Birgaon road (ch.7000-8170m) ,ID NO 690933002 | 1.17 |  | 29003193 |  | 147037921 | [13 empty] | Evaluation under process to HQ
| Chatak |  | Improvement of charmahalla Up office -Chadpur road (ch.3620-5540m) ,ID NO 690233014 | 1.92 |  | 27365581
| South Sunamgonj |  | Improvement of Dungria goruabazer -Haskuri Dhalmasia village road (ch.500-4200m) ,ID NO 690934102 | 3.7 |  | 44126129
| South Sunamgonj |  | Improvement of Minabazer -paglabazer RHD via Islampur-Piprakandi road (ch.1780-5700m) ,ID NO 6909340369 | 3.92 |  | 46542718
34 | Dowarabazar | LGED/RARIP/SUN/UNRS/19-20/W-19(a) | Improvement of Mathgaon -Doulatpur school road (ch.00-2370m) ,ID NO 690334046 | 2.37 |  | 22553884 |  | 22553884 |  | 1.10.20 | M/s Milon kanti & M/s Farida Enterprise (JV )01712020736 | 27.12.20 | 13.01.21 | 22525542 | 13.01.21 | 10% | 12.01.22
9 |  |  | Sub- Total | 43.351 | 21.875 | 424145724 | 4993754 | 476854029 | 776209 |  |  |  |  | 117162354 |  |  |  | 38605625 | 1151000 | 17215300
Rehabilitation
35 | Sadar | LGED/RARIP/SUN/RHB/18-19/W-125 | a) Haluar Ghat-Ibrahimpur (Surma UPC) via Moinpur road (Ch.00-1200m). Road ID No-690893016 | 1.2 |  | 25241965 |  | 25241965 |  | 8.11.18 | M/S Akber Ali 01716-122058 | 31.1.19 | 27.02.19 | 23498522 | 14.3.19 | 100% | 13.03.20 | 22216789 |  | 1281733 | 94%
|  |  | Buristhal-Abdullahpur road via Sreenathpur GPS (Mollapara UP) (Ch.00-2400m). Road ID No-690895095 | 2.4 | [11 empty] | 95%
|  |  | Ampara-Khayergaon Bazar Pucca Road-Natun Godigaon road via Jharjaria (Ch.00-1700m). Road ID No-690893011 | 1.7 | [11 empty] | 95%
36 | Derai | LGED/RARIP/SUN/RHB/18-19/W-126 | a) Rajanagar-Bangla Bazar road (Ch.00-2000m & 8930-9330m). Road ID No-690293004 | 2.4 |  | 8739411 |  | 8739411 |  | 8.11.18 | M/S Belal Enterprise | 12.5.19 | 03.06.19 | 9533352 | 17.06.19 | 90% | 16.6.20 | 7061000 |  | 2472352 | 74%
|  |  | b) Tuk Derai to Kochua via Tajpur road (Ch.550-1550m). Road ID No-690294040 | 1 | [11 empty] | 95%
37 | Derai | LGED/RARIP/SUN/RHB/18-19/W-127 | Akilsha bazar Nagargaon Ferryghat via Kulange road (Ch.550-2419m). Road ID No-690294019 | 1.9 |  | 10798389 |  | 10798389 |  | 8.11.18 | M/S Padma Construction & Supply Firm, Dilkhuha, Dhaka. 01713-022514 | 4.12.18 | 01.01.19 | 10572051 | 14.1.19 | 5% | 31.12.19
38 | Biswamberpur | LGED/RARIP/SUN/RHB/18-19/W-128 | a) Karenter bazar-Dhanpur UP Office road (Ch.00-1204m). Road ID No-690183003 | 1.204 |  | 10351707 |  | 10351707 |  | 8.11.18 | M/S Aminul Haque & Co. Ukilpara, Sunamganj 01711-026722 | 4.12.18 | 01.01.19 | 10345428 | 14.1.19 | 30% | 31.12.19 | 5040670 |  | 5304758 | 48%
| Biswamberpur |  | b) Chhaterkona-Anandabazar road (Ch.00-750m). Road ID No-690934012 | 0.75 | [11 empty] | 15%
| Dowarabazar |  | C) Baliura bazar Chowmuni road (Ch.00-700m). Road ID No-690334058 | 0.7 | [11 empty] | 100%
39 | Chatak | LGED/RARIP/SUN/RHB/18-19/W-129 | a) Kalaruka-Tajpur road (Ch.50-80, 1500-1575 & 2200-3100m). Road ID No-690233004 | 0.975 |  | 5210159 |  | 5210159 | [13 empty] | Estimate sent to HQ for Approval on 19.10.20
|  |  | b) Jalalpur (RHD)-Hasnabad bazar (RHD) road via Kamranji Village road (Ch.930-1533 & 1866-2266m). Road ID No-690233015 | 1
40 | Tahirpur | LGED/RARIP/SUN/RHB/18-19/W-130 | a) Badaghat GC-Bordal Uttar UP Office road (Ch.00-2650m). Road ID No-690923009 | 2.65 |  | 10766544 |  | 10766544 |  | 8.11.18 | M/S Amal kanti Chowdhury, Hassannagar, Sunamganj 01716-562760 | 4.12.18 | 01.01.19 | 10433467 | 14.1.19 | 100% | 31.12.19 | 9918166 |  |  | 100% | Final
|  |  | b) Laorergar-Sharifganj Bazar Road (Ch.1700-2500m). Road ID No-690924061 | 0.8 | [11 empty] | 100%
41 | Derai | LGED/RARIP/SUN/RHB/18-19/W-141 | Patharia-Banglabazar road (Ch.4550-5760m & 6200-7000m). Road ID No-690293001 | 2.1 |  | 8502453 |  | 8502453 |  | 8.11.18 | M/S Padma Construction & Supply Firm, Dilkhuha, Dhaka. 01713-022514 | 4.12.18 | 01.01.19 | 8355111 | 14.1.19 | 0% | 31.12.19
42 | Derai | LGED/RARIP/SUN/RHB/18-19/W-148 | a) Derai Bazar to Karimpur (Derai Bazar-Karimpur Via Tuk Derai) road (Ch.207-930m). Road ID No-690294031 | 0.723 |  | 7646780 |  | 7646780 |  |  | M/S Belal Enter prise | 12.5.19 | 03.06.19 | 8139754.75 | 17.6.19 | 100% | 16.06.20 | 7639606 |  | 500148.75 | 93.86%
| South Sunamgonj |  | b) Pagla-Birgaon Road (Ch.8350-9200m). Road ID No-690933002 | 0.85 | [11 empty] | 100%
43 | Sulla | LGED/RARIP/SUN/RHB/19-20/W-149 | Improvement of Sulla H/Q -Adittopur bazer road (ch.00-1400m) ,ID NO 690863001 | 3 |  | 35305543 |  | 36748189 | [13 empty] | proposal sent to HQ for Re tender
| Jagannathpur |  | Improvement of Polykona -Goprapur road (ch.00-1000m) ,ID NO 690474008 | 1 |  | 1442646
9 |  |  | Sub- Total | 26.352 |  | 124005597 |  | 124005597 | 0 |  |  |  |  | 80877685.75 |  |  |  | 51876231 | 0 | 9558991.75
Market
44 | Dharmapasha | LGED/RARIP/SUN /MAR/19-20/W-155 | Improvement of joysree bazer under Dharmapasha |  |  |  |  | 6521204 | [13 empty] | TER sent to HQ 13.01.21
45 | Jagannathpur | LGED/RARIP/SUN/MAR/18-19/W-157 | Improvement of Goprapur Bazer under Jagannthpur Upazila |  |  |  |  | 8784192 | [13 empty] | TER sent to HQ 13.01.21
Improvement of kolkoli Bazer under Jagannthpur Upazila
46 | Jamalganj | LGED/RARIP/SUN/MAR/18-19/W-158 | Improvement of Ramnagar Bazer under Jamalganj Upazila |  |  |  |  | 2286642 |  | 12.11.19 | M/S Babul purkayasto01716072590 | 30.4.20 | 20.5.20 | 2508149 | 07.06.20 | 15% | 06.06.20
47 | Jagannathpur | LGED/RARIP/ SUN/MAR/19-20/W-170 | a) Improvement of Gobindaganj Bazar under Chattak Upazila. District: Sunamganj. |  |  | 7270930 |  | 13490326 |  | 01.04.21 | [11 empty] | Tender Received Date on 01.04.21
| Derai |  | b) Improvement of Shashkai Bazar under Sulla Upazila. District: Sunamganj. |  |  | 6219396
48 | Jagannathpur | LGED/RARIP/ SUN/MAR/19-20/W-171 | a)Improvement of chikarkandi Bazer under Dakshin Sunamganj Upazila |  |  | 3547453 |  | 8544871 | [13 empty] | Tender Received Date on 17.02.21
| Derai |  | b)Improvement of Shyamerchor (Milon bazer)Under Derai Upazila |  |  | 4997418
5 |  |  | Sub- Total | 0 | 0 | 8544871 | 0 | 26136909 | 0 |  |  |  |  | 2508149 |  |  |  | 0 | 0 | 0
48 |  |  |  | 104.444 | 32.04 | 856100768 | 6444023 | 927851380 | 955626 |  |  |  |  | 450036442.42 |  |  |  | 210613936 | 1151000 | 100272730.42
Ter Sent to HQ=08,Re-Tender =02,Contract Agreement=29,Total Scheme=39 | [17 empty] | 211764936
| Accountant LGED, Sunamgonj. |  | Sub-Assistant Engineer LGED, Sunamgonj. |  |  |  | Assistant Engineer LGED, Sunamgonj. |  |  |  |  | Senior Assistant Engineer LGED, Sunamgonj. |  |  |  |  | Executive Engineer LGED, Sunamgonj.