## January-2021
Local Government Engineering Department
Rural Access Road Improvement Project in Sylhet Division(RARIP).
Monthly Progress Report (Physical & Financial)
District : Sylhet | [18 empty] | Month : February,2021
Sl. No. | Upazila | Package No. | Name of Scheme with Chainage & ID No. | Quantity |  | Estimate Cost (Tk.) |  |  | Cost of Salvage Material (Tk.) | Tender Receiving Date | Name of Contractor | Date of NOA issued | Date of Contract/ Revised Contract. | Contract/ Variation Amount (Tk.) | Work Commencement Date | Physical progress (%) | Date of Completion as per contract | Validity date of Bank Guarantee | Payment Amount for |  |  | Financial Progress (%) | Remarks
|  |  |  | Road (Km) | Struct. (m) | Road (Tk.) | Struct. (Tk.) | Total | [10 empty] | Road (Tk.) | Bridge/ Culvert (Tk.) | Remaining Payment (Tk.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Improvement Union Road
1 | Biswanath | LGED/RARIP/SYL/UNR/18-19/W-01 | a) RHD Rampasha-Rajagonj-Uttar Biswanath-Lamakazi UP road Doshghar UP-Lohori-Mashukhali bazer road (RHD Rampasha-Rajagonj-Uttar Biswanath-Lamakazi UP road) (Ch. 2600-4600m) under Biswanath Upazila, ID no: 691203002, District: Sylhet | 2 |  | 14042406 |  | 14042406 |  | 29.05.19 | B.M Trade Center 80/A, Siddheswari Circular Road, Malibhag, Dhaka. | 03.11.19 | 28.11.19 | 49215770.28 | 04.12.19 | 10% | 03.12.20 | 27.02.21 | 4026375 |  | 45189395.28 | 8.181%
| Zakigonj |  | b) Beroshree UP Office-Shahbag Bus Stand Bazar (RHD) via Barkatpur-Raghurashi Bazar Road (Ch. 1988-3988m) under Zakiginj Upazila, ID no: 691943007, District: Sylhet | 2 |  | 16022816 |  | 16022816 | [7 empty] | 55%
| Golapgonj |  | c) Raquar bazar-Shantirbazar-Supatake Rd. (Ch. 700-2700m) under Golapgonj Upazila, ID no: 691383012, District: Sylhet | 2 |  | 19155540 |  | 19155540 | 1864932 | [6 empty] | 25%
Package Total = |  |  |  | 6 |  | 49220762 |  | 49220762 | 1864932 |  |  |  |  | 49215770.28 |  |  |  |  | 4026375 |  | 45189395.28
2 | Gowainghat | LGED/RARIP/SYL/UNR/18-19/W-10 | a) Purba Jaflong UP office – Nabamkhanda bazar road (Ch. 00-150 & 2309-3692m) under Gowainghat Upazila, ID no: 691413008, District: Sylhet | 1.488 | 4.75 | 13373276.45 | 1579900.8 | 14953177.25 | [5 empty] | 0 |  |  |  |  | 0 |  | 0 | #DIV/0! | Re-Bid under Process
|  |  | b) Pirijpur – Paschim Jaflong UP office-Sonarhat (Pirajpur – Paschim Jaflong UP office-Sonarhat-Monortal Bazar) road (Ch. 10815-11472 & 12725-13389m) under Gowainghat Upazila, ID no: 691413002, District: Sylhet | 1.321 |  | 10238183 |  | 10238183
| Jointiapur |  | c) Khorilbazar – Lalakhal – Thubang – Charikata UP HQ Road (Ch. 4460-7460m) under Jointiapur Upazila, ID no: 691533001, District: Sylhet | 3 |  | 21387856 |  | 21387856
|  |  | d) Darbostbazar (GC) – Ramproshad – Charikata UP HQ Road (Ch. 7500-9320m) under Jointiapur Upazila, ID no: 691533006, District: Sylhet | 1.82 |  | 14243113 |  | 14243113
Package Total = |  |  |  | 7.629 | 4.75 | 59242428.45 | 1579900.8 | 60822329.25 | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0
Sub Total = |  |  |  | 13.629 | 4.75 | 108463190.45 | 1579900.8 | 110043091.25 | 1864932 |  |  |  |  | 49215770.28 |  |  |  |  | 4026375 |  | 45189395.28
Improvement Village Road
3 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-20 | a) Kalagul Road (Ch. 2000-2720m) under Sylhet Sadar Upazila, ID no: 691624063, District: Sylhet. | 0.72 | 1.5 | 4992604 | 503124 | 5495728 |  | 05.09.19 | Xcellent Trade Corporation House No.54/A, Road No. 132. Gulshan-1, Dhaka. | 14.11.19 | 10.12.19 | 12210587.52 | 16.12.19 | 5% | 15.12.20 | 30.06.21
|  |  | b) Dhanpur Ferryghat-Mirpur-Muktirbazar Road (Ch. 1500-1900m) under Sylhet Sadar Upazila, ID no: 691624121,District: Sylhet. | 0.4 |  | 2815219 |  | 2815219 | [7 empty] | 0%
|  |  | c) Mohaldik-Murargaon road (Dhapnatila) (Ch. 2000-2406m) under Sylhet Sadar Upazila, ID no: 691625072, District: Sylhet. | 0.406 |  | 2796461 |  | 2796461 | [7 empty] | 0%
Package Total = |  |  |  | 1.526 | 1.5 | 10604284 | 503124 | 11107408 | [5 empty] | 12210587.52
4 | Osmaninagar | LGED/RARIP/SYL/VR /18-19/W-21 | Osmanpur UP - Madrashabazar- Nazirbazar - Dakhin Khagdior - Goinaghat road (Ch. 00-800m) under Osmaninogar Upazila, ID no: 691085180, District: Sylhet. | 0.8 | 2 | 5456471 | 686119 | 6142590 |  | 20.03.19 | M/S. Suhel Enterprise Osmaninagar,Sylhet. | 09.07.19 | 05.08.19 | 6449568.96 | 14.08.19 | 25% | 13.08.20 | 30.06.21
Package Total = |  |  |  | 0.8 | 2 | 5456471 | 686119 | 6142590 | [5 empty] | 6449568.96
5 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-22 | a) Anantapur prymary school-Hajrat Miskinsha Mukambadauni road (Ch. 00-470m) under Sylhet Sadar Upazila, ID no: 691624113, District: Sylhet. | 0.47 |  | 2955070 |  | 2955070 |  | 29.05.19 | Seaba Prokoushali Songhosta 50, Naya Paltan,Dhaka. | 14.10.19 | 7.11.19 | 8537124.25 | 14.11.19 | 0% | 13.11.20 | 06.11.21
| Biswanath |  | b) RHD Rashidpur- Shirajpur-RHD Shahjirgow Road (Ch. 2200-2925m) under Biswanath Upazila, ID no: 691204007,District: Sylhet. | 0.725 |  | 5175571 |  | 5175571 | 286482 | [6 empty] | 0%
Package Total = |  |  |  | 1.195 |  | 8130641 |  | 8130641 | 286482 |  |  |  |  | 8537124.25
6 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-47 | Kandigaon - Badhaghat Road (Ch. 00-480m)under Sylhet Sadar Upazila, ID no: 691624079, District: Sylhet | 0.48 |  | 4443966 |  | 4443966 | [14 empty] | Re-Bid under Process
|  |  | Borkapon-Kalirgaon Road (Ch. 1000-2000m) under Sadar Upazila, ID no: 691624085, District: Sylhet | 1 |  | 6971961 |  | 6971961
Package Total = |  |  |  | 1.48 |  | 11415927 |  | 11415927 | 0 |  |  |  |  | 0
7 | Companigonj | LGED/RARIP/SYL/VR /18-19/W-48 | P. K. High School-Haidari bazar Road (Ch. 1500-2542m) under Companigonj Upazila, ID no: 691274015, District: Sylhet. | 1.042 |  | 7711035 |  | 7711035 |  | 29.05.19 | LK-SC(JV) 128/A, Khojarkhola, Sylhet. | 16.10.19 | 12.11.19 | 8706384 | 18.11.19 | 70% | 17.11.20 | 05.05.21
Package Total = |  |  |  | 1.042 |  | 7711035 |  | 7711035 | [5 empty] | 8706384
8 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-49 | Dararbazar road -Semarbazar road (Monthol) (Ch. 00-940m) under Sadar Upazila, ID no: 691624134, District: Sylhet | 0.94 |  | 6461860 |  | 6461860 |  | 29.05.2019 | ITC-CB JV, House-4/1/A, Flat No.4/A, Level-3, Road-02, Gulshan-1, Dhaka. | 29.09.20 | 27.10.20 | 11701314.79 | 04.11.20 | 0% | 03.11.21 | 24.01.22
|  |  | Chowdhurypara Road No.02 Road (Ch. 00-725m) under Sadar Upazila, ID no: 691625257, District: Sylhet | 0.725 | 3.4 | 5038033 | 171800 | 5209833 | [7 empty] | 0%
Package Total = |  |  |  | 1.665 | 3.4 | 11499893 | 171800 | 11671693 | 0 |  |  |  |  | 11701314.79
9 | Biswananth | LGED/RARIP/SYL/VR /18-19/W-51 | South Dewkalash Govt. Pry.School tokahirghat bazar (Ch. 1000-2000m) under Biswanath Upazila, ID no: 691204064, District: Sylhet | 1 |  | 6816658 |  | 6816658 |  | 22.10.2018 | M/s. Alam Traders Shibpur, Norshingdi. | 05.12.18 | 01.01.19 | 11011045.84 | 07.01.20 | 100% | 20.03.20 | 30.06.21 | 4500000 |  | 6511045.84 | 40.87%
|  |  | Kaligonj bazar-Mirachar-CHalia road (Ch. 1000-1620m) under Biswanath Upazila, ID no: 691205059, District: Sylhet | 0.62 |  | 4289484 |  | 4289484 | [7 empty] | 5%
Package Total = |  |  |  | 1.62 |  | 11106142 |  | 11106142 | 0 |  |  |  |  | 11011045.84 |  |  |  |  | 4500000 |  | 6511045.84
10 | Osmaninagar | LGED/RARIP/SYL/VR /18-19/W-52 | Idgha Bazar - Kayrabad Road (Ch. 00-1000m) under Osmaninagor Upazila, ID no:691084037, District: Sylhet | 1 |  | 6811439 |  | 6811439 | [14 empty] | Re-Bid under Process
Package Total = |  |  |  | 1 |  | 6811439 |  | 6811439 | 0 |  |  |  |  | 0
11 | Balagonj | LGED/RARIP/SYL/VR /18-19/W-53 | a) Balagonj-Fenchugonj road-Nuton Sunampur Road (Ch. 500-950m) under Balagonj Upazila, ID no:691085242 (New ID 691084111), District: Sylhet | 0.45 |  | 3740842 |  | 3740842 | [14 empty] | Re-Bid under Process
|  |  | b) Taltalabazar - Jamalpur - Anwerpur - Khondokar Bazar Road (Ch. 1500-2500m) under Balagonj Upazila, ID no:691084035, District: Sylhet | 1 |  | 7166337 |  | 7166337
Package Total = |  |  |  | 1.45 |  | 10907179 |  | 10907179 | [5 empty] | 0
12 | Dakshin Surma | LGED/RARIP/SYL/VR /18-19/W-54 | Hazigonj bazar-Chisrakandi -Chandpur road (Ch. 1500-2500m) under Dakshin Surma Upazila, ID no: 691954021, District: Sylhet | 1 |  | 7152616 |  | 7152616 | 808062 | 13.06.19 | ITC-CB (JV), House-53,Road-1, Block-A, Niketon,Gulshan-1, Dhaka. | 14.10.19 | 7.11.19 | 11545953.41 | 13.11.20 | 5% | 13.11.20 | 19.01.21
|  |  | RHD ( Kadamtoli ) Shiberchok road (Ch. 00-500m) under Dakshin Surma Upazila, ID no: 691955045,District: Sylhet | 0.5 | 0.625 | 3529713 | 138627 | 3668340 | [7 empty] | 5%
Package Total = |  |  |  | 1.5 | 0.625 | 10682329 | 138627 | 10820956 | 808062 |  |  |  |  | 11545953.41
13 | Fenchugonj | LGED/RARIP/SYL/VR /18-19/W-55 | a) Bealibazar Paglachara-Dharan Mirzapur Road (Ch. 1000-2100m) under Fenchugonj Upazila, ID no: 691354001, District: Sylhet | 1.1 |  | 9337117 |  | 9337117 |  | 13.06.19 | ITC-CB JV, House-4/1/A, Flat No.4/A, Level-3, Road-02, Gulshan-1, Dhaka. | 29.09.20 | 27.10.20 | 22502947.14 | 04.11.20 | 0% | 03.11.21 | 24.01.22
|  |  | b) Sottrish GPS - Bagmara Purbara Kathaltali (Concrete Road) (Ch. 00-1000m) under Fenchugonj Upazila, ID no: 691355064, District: Sylhet | 1 |  | 11711909 |  | 11711909
Package Total = |  |  |  | 2.1 |  | 21049026 |  | 21049026 | [5 empty] | 22502947.14
14 | Osmaninagar | LGED/RARIP/SYL/VR /18-19/W-56 | Omarpur bazar-Mandaruka Road (Ch. 1230-2230m) under Osmaninagar(Ex Balagonj) Upazila, ID no: 691084007, District: Sylhet | 1 |  | 6955247 |  | 6955247 |  | 20.03.19 | Seaba Prokoushali Songhosta 50, Naya Paltan,Dhaka. | 24.04.19 | 21.05.19 | 7302327.5 | 28.05.19 | 15% | 08.08.20 | 19.11.21
Package Total = |  |  |  | 1 |  | 6955247 |  | 6955247 | 0 |  |  |  |  | 7302327.5 |  |  |  |  | 0 |  | 0
15 | Jointiapur | LGED/RARIP/SYL/VR /18-19/W-57 | Paton Village Road (Ch. 00-1470m) under Jointapur Upazila, ID no: 691535013, District: Sylhet | 1.47 |  | 11276341 |  | 11276341 |  | 20.03.19 | M/s.Molla Enterprise 297/1, Bara Moghbazar, Dhaka. | 01.08.19 | 28.08.19 |  | 03.09.19 | 0% | 02.09.20 | [5 empty] | Work Order Cencel & Received with Petition
Package Total = |  |  |  | 1.47 |  | 11276341 |  | 11276341 | 0 |  |  |  |  | 0
16 | Gowainghat | LGED/RARIP/SYL/VR /18-19/W-58 | Jolurmuk - Ramnagor - Ratergul road (Ch. 1750-2705m) under Gowainghat Upazila, ID no: 691415005, District: Sylhet | 0.955 |  | 9068305 |  | 9068305 | [14 empty] | Re-Bid under Process
Package Total = |  |  |  | 0.955 |  | 9068305 |  | 9068305 | 0 |  |  |  |  | 0
17 | Gowainghat | LGED/RARIP/SYL/VR /18-19/W-59 | a) Kandigram Chirurpar Bund Road (Ch. 600-1600m) under Gowainghat Upazila, ID no: 691415055 (New ID 691415052), District: Sylhet | 1 |  | 7815077 |  | 7815077 |  | 13.06.19 | ITC-CB JV, House-4/1/A, Flat No.4/A, Level-3, Road-02, Gulshan-1, Dhaka. | 29.09.20 | 27.10.20 | 12004281.32 | 04.11.20 | 0% | 03.11.21 | 24.01.22
|  |  | b) Tamabil RHD Lafnaut-Alirgaon UP office road (Noyamati) Latu Paschim road (Ch. 955-1395m) under Gowainghat Upazila, ID no: 691414026 (New ID 691414025), District: Sylhet. | 0.44 |  | 3326746 |  | 3326746
Package Total = |  |  |  | 1.44 |  | 11141823 |  | 11141823 | 0 |  |  |  |  | 12004281.32
18 | Companigonj | LGED/RARIP/SYL/VR /18-19/W-60 | Upazila Health Complex - Thana H/Q-Toker Bazar Road (Ch. 350-950m) under Companigonj Upazila, ID no: 691274018, District: Sylhet | 0.6 |  | 7952216 |  | 7952216 |  | 13.06.19 | M/S Zilani Traders 80/4, Siddheswari Circular Road, Ramna, Dhaka | 25.06.20 | 16.07.20 | 24248089.95 | 22.07.20 | 5% | 21.07.21 | 29.09.21
|  |  | RHD-Companigonj-Buridohar Hazi Hason Ali School (Ch. 1290-1790m) under Companigonj Upazila, ID no: 691274031, District: Sylhet | 0.5 |  | 6628120 |  | 6628120 | [7 empty] | 0%
| Kanaighat |  | Dowarimati - Majargram Road (Ch. 500-1500m) under Kanighat Upazila, ID no: 691594010, District: Sylhet | 1 |  | 8102875 |  | 8102875 | [7 empty] | 10%
Package Total = |  |  |  | 2.1 |  | 22683211 |  | 22683211 | 0 |  |  |  |  | 24248089.95
19 | Kanaighat | LGED/RARIP/SYL/VR /18-19/W-61 | a) Patromati Mosque to Thakurmati Road (Ch. 2010-3010m) under Kanighat Upazila, ID no: 691595015 (New ID 691594183), District: Sylhet | 1 |  | 7695648 |  | 7695648 |  | 28.02.19 | B.M Trade Center 80/A, Siddheswari Circular Road, Malibhag, Dhaka. | 01.08.19 | 28.08.19 | 16302404.35 | 03.09.19 | 45% | 02.09.20 | 25.08.20 | 2100000 |  | 14202404.35
|  |  | b) Boroband pry.school to Kathaltoli Road (Ch. 00-1000m) under Kanighat Upazila, ID no: 691594123, District: Sylhet | 1 | 3 | 6916721 | 927804 | 7844525 | [7 empty] | 0%
Package Total = |  |  |  | 2 | 3 | 14612369 | 927804 | 15540173 | 0 |  |  |  |  | 16302404.35 |  |  |  |  | 2100000 |  | 14202404.35
20 | Zakigonj | LGED/RARIP/SYL/VR /18-19/W-62 | Ratangonj-Pallisree Via Eaulasar Daudpur Road ( Ch.1100-2100m)under Zakiganj Upazila, ID No. 691944079, District: Sylhet. | 1 | 12 | 8243872.39 | 807027.6 | 9050899.99 | [14 empty] | Evaluationunder Process
|  |  | Zakiganj GC-Atgram RHD Road-(Abdur Rahman House) Nandirsree-Mongolpur-Manikpur UP-KajalShar UP Road (Ratangonj Bazar-Kaligonj bazar Road) ( Ch.815-2720m) under Zakiganj Upazila, ID No. 691944043, District: Sylhet. | 1.905 | 14.5 | 15965432 | 4989747 | 20955179
Package Total = |  |  |  | 2.905 | 26.5 | 24209304.39 | 5796774.6 | 30006078.99
21 | Dakshin Surma | LGED/RARIP/SYL/VR /18-19/W-63 | a) Karimpur Road ( Via Geameem Tower) (Surjamukhi GPS-Karimpur-Malakandi) Road (Ch. 00-1000m) under Dakshin Surma Upazila, ID no: 691955003, District: Sylhet. | 1 |  | 7231641 |  | 7231641 | [14 empty] | Evaluationunder Process
| Beanibazar |  | b) Punjipari-Kharabara-Pailgram Road (Ch. 836-1836m) under Beanibazar Upazila, ID no: 691174002, District: Sylhet. | 1 |  | 6975292 |  | 6975292
Package Total = |  |  |  | 2 |  | 14206933 |  | 14206933 | 0 |  |  |  |  | 0
22 | Beanibazar | LGED/RARIP/SYL/VR /18-19/W-64 | RHD-Bagbari-Gorua Road (Ch. 3800-4800m) under Beanibazar Upazila, ID no: 691174031, District: Sylhet | 1 |  | 7800639 |  | 7800639 |  | 13.06.19 | The Khan Enterprise Charaboi Beanibazar,Sylhet. | 14.10.19 | 7.11.19 | 8190441.52 | 14.11.19 | 70% | 13.11.20 | 10.02.21 | 4300000 |  | 3890441.52 | 52.5%
Package Total = |  |  |  | 1 |  | 7800639 |  | 7800639 | [5 empty] | 8190441.52 |  |  |  |  | 4300000 |  | 3890441.52
23 | Golapgonj | LGED/RARIP/SYL/VR /18-19/W-65 | Paschimbag-Murakiar-Paschimbag Mohila Madrasha Rd (Ch. 1000-1828m) under Golapgonj Upazila, ID no: 691384057, District: Sylhet | 0.828 | 1.625 | 7024677 | 756576 | 7781253 |  | 28.02.19 | Md.Mahmudul Hussain Tufa, Shahjalal Upashahar, Sylhet. | 24.04.19 | 20.05.19 | 8151956.24 | 27.05.19 | 80% | 26.05.20 | 18.08.21 | 4711473 |  | 3440483.24 | 57.8%
Package Total = |  |  |  | 0.828 | 1.625 | 7024677 | 756576 | 7781253 | [5 empty] | 8151956.24 |  |  |  |  | 4711473 |  | 3440483.24
24 | Golapgonj | LGED/RARIP/SYL/VR /18-19/W-66 | Bagha Uttar gram Rd (Parganabazar Purbagoan-Chowghurybazar Rd) (Ch. 500-1500m) under Golapgonj Upazila, ID no: 691385012, District: Sylhet | 1 | 0.625 | 6828442 | 409730 | 7238172 | [14 empty] | Re-Bid under Process
| Gowainghat |  | Atlihai –Naindahaor road (Ch. 3880-4480m) under Gowainghat Upazila, ID no: 691414001, District: Sylhet | 0.6 |  | 4453145 |  | 4453145
Package Total = |  |  |  | 1.6 | 0.625 | 11281587 | 409730 | 11691317
25 | Gowainghat | LGED/RARIP/SYL/VR /18-19/W-107 | Salutikar Bazar-Angerzur Madrasha Road (Ch. 1000-2006m) under Gowainghat Upazila, ID no: 691414010, District: Sylhet | 1.006 |  | 7099736 |  | 7099736 |  | 22.10.18 | M/s. Faruk Enterprise Kapaura, Jaflong, Gowainghat, Sylhet. | 24.01.19 | 18.02.19 | 7098081.78 | 25.02.19 | 100% | 24.02.20 | 12.02.20 | 7092456 |  |  | 100% | Final
Package Total = |  |  |  | 1.006 |  | 7099736 |  | 7099736 | [5 empty] | 7098081.78 |  |  |  |  | 7092456 |  | 0
26 | Golapgonj | LGED/RARIP/SYL/VR /18-19/W-108 | Ponair chak Village Rd (Ch. 1500-2500m) under Golapgonj Upazila, ID no: 691175015, District: Sylhet | 1 |  | 9656300 |  | 9656300 |  | 03.01.19 | M/s. Puspa Construction Raynagar, Sunarpara, Sylhet. | 18.02.19 | 14.03.19 | 10122156.8 | 21.03.19 | 100% | 20.03.20 | 13.06.20 | 8078245 |  | 2043911.8 | 79.81%
Package Total = |  |  |  | 1 |  | 9656300 |  | 9656300 | [5 empty] | 10122156.8 |  |  |  |  | 8078245 |  | 2043911.8
27 | Beanibazar | LGED/RARIP/SYL/VR /18-19/W-110 | RHD (Abdullahpur)-Gounggadia-I.L.o Road (Ch. 00-1000m) under Beanibazar Upazila, ID no: 691174025, District: Sylhet | 1 |  | 9522703 |  | 9522703 | 91662 | 28.02.19 | Md.Mahmudul Hussain Tufa, Shahjalal Upashahar, Sylhet. | 24.04.19 | 20.05.19 | 9954410.82 | 27.05.19 | 15% | 26.05.20 | 18.08.21
Package Total = |  |  |  | 1 |  | 9522703 |  | 9522703 | 91662 |  |  |  |  | 9954410.82
Sub Total = |  |  |  | 35.682 | 39.275 | 281913541.39 | 9390554.6 | 291304095.99 | 1186206 |  |  |  |  | 196039076.19 |  |  |  |  | 30782174 |  | 30088286.75
Maintenance
28 | Sylhet Sadar | LGED/RARIP/SYL/RHB/18-19/W-118 | a) Baluchor (Noyabazar)-Vateranary College Road Road (Ch. 60-640m) under Sadar Upazila, ID no: 6916224092, District: Sylhet | 0.58 |  | 5940290 |  | 5940290 |  | 29.10.18 | M/s.Zafor Ahmed Gilman Kulaura, Moulvibazar. | 05.12.18 | 01.01.19 | 11695916.22 | 08.01.19 | 100% | 07.01.20 | 30.01.20 | 10230556 |  | 1465360.22 | 87.47%
|  |  | b) Masukgonjbazar-Medinimohol Primary School-Sujatpur Road (Ch. 00-1510m) under Sadar Upazila, ID no: 691624088, District: Sylhet. | 1.51 |  | 2536887 |  | 2536887 | [7 empty] | 100%
|  |  | c) RHD-FIVDB-Zakaria city Road (Ch. 2200-2900m) under Sadar Upazila, ID no: 691624016, District: Sylhet. | 0.7 |  | 580977 |  | 580977 | [7 empty] | 100%
|  |  | d) Pirergoan-GC-Motoghat Road (Ch. 00-1775m) under Sadar Upazila, ID no:691624140, District: Sylhet | 1.775 |  | 2638567 |  | 2638567 | [7 empty] | 100%
Package Total = |  |  |  | 4.565 |  | 11696721 |  | 11696721 | 0 |  |  |  |  | 11695916.22 |  |  |  |  | 10230556 |  | 1465360.22
29 | Biswanath | LGED/RARIP/SYL/RHB/18-19/W-119 | a) Monsibazar-Ponaullah bazar Road (Ch. 00-2000m) under Biswanath Upazila, ID no: 691204005, District: Sylhet | 2 |  | 3171010 |  | 3171010 |  | 28.02.19 | M/S Md.Toyabur Rahman, North Bagbari Point, Sylhet. | 24.04.19 | 12.05.19 | 10245345.39 | 19.05.19 | 100% | 18.05.20 | 04.08.20 | 8081946 |  | 2163399.39 | 78.88%
| Osmaninagar |  | b) Terrohati-Sekandarpur-Omarpur Bazar Road (Ch. 00-2000m) under Osmainagor Upazila, ID no: 691084003, District: Sylhet | 2 |  | 5672319 |  | 5672319 | [7 empty] | 100%
| Balagonj |  | c) Illashpur (Tajpur-Balagonj Rd)-Goalabazar GC-Balagonj GC Road (Ch. 00-466m) under Balagonj Upazila, ID no: 691084083, District: Sylhet | 0.466 |  | 920983 |  | 920983 | [7 empty] | 100%
Package Total = |  |  |  | 4.466 |  | 9764312 |  | 9764312 | 0 |  |  |  |  | 10245345.39 |  |  |  |  | 8081946 |  | 2163399.39
30 | Dakshin Surma | LGED/RARIP/SYL/RHB/18-19/W-120 | a) Kamalgonj-Sadarkhola-Mollargaon road via post office Road (Ch. 00-1500m) under Dakkhin Surma Upazila, ID no:691954040, District: Sylhet | 1.5 |  | 4154692 |  | 4154692 |  | 03.01.19 | M/s. Sibabrata Bhowmik Puran Lane, Sylhet. | 18.02.19 | 14.03.19 | 12150078.97 | 21.03.19 | 100% | 20.03.20 | 09.04.20 | 9082458 |  | 3067620.97 | 74.75% |  | 9652638
|  |  | b) Syedpur-Betuarmukh Road (Ch. 00-2000m) under Dakkhin Surma Upazila, ID no:691954025, District: Sylhet | 2 |  | 6716290 |  | 6716290 | [7 empty] | 100%
Package Total = |  |  |  | 3.5 |  | 10870982 |  | 10870982 | 0 |  |  |  |  | 12150078.97 |  |  |  |  | 9082458 |  | 3067620.97
31 | Fenchugonj | LGED/RARIP/SYL /RHB/ 18-19/W-121 | a) Bangha Bondu GPS-Gazipur Mosque Road (Ch. 00-575m) under Fenchugonj Upazila, ID no:691355012, District: Sylhet | 0.575 |  | 1126771 |  | 1126771 | [14 empty] | Re-Bid under Process
|  |  | b) Shah Syed Ali mazar-Shahmal Thagor mazar road (Ch. 2000-3000m) under Fenchugonj Upazila, ID no: 691354009, District: Sylhet | 1 |  | 2099067 |  | 2099067
| Osmaninagar |  | c) Burunga Bazar-Paschim Tilapara-Anwarpur Road (Ch. 00-1300m) under Osmaninagar Upazila, ID no:691964009, District: Sylhet | 1.3 |  | 2730183 |  | 2730183
| Biswanath |  | d) Pirer Bazar-Boruni Road (Ch. 74-1870m) under Biswanath Upazila, ID no:691204010, District: Sylhet | 1.796 |  | 3163575 |  | 3163575
Package Total = |  |  |  | 4.671 |  | 9119596 |  | 9119596 | 0 |  |  |  |  | 0
32 | Kanaighat | LGED/RARIP/SYL/RHB/18-19/W-122 | a) Laksmi-prashad purba UP-Kotalpur (RHD)-Soroker Bazar Road (Ch. 445-2270m) under Kanaighat Upazila, ID no:691593013, District: Sylhet | 1.825 |  | 3806447 |  | 3806447 |  | 15.11.18 | M/s.Progoti Traders, Kumarpara,Sylhet. | 13.12.18 | 03.01.2019 | 10509171.5 | 10.01.19 | 100% | 09.01.20 | 25.03.20 | 10504157 |  | 5014.5 | 99.95% | Final
|  |  | b) Digirpar Paschim UP (Satbak UP) -Bhovanigonj Bazar-Banglabazar Road (Ch. 00-1450m) under Kanaighat Upazila, ID no:691593007, District: Sylhet | 1.45 |  | 2805954 |  | 2805954 | [7 empty] | 100%
|  |  | c) Dowarimati-Kulurmati Road (Ch. 00-1800m) under Kanaighat Upazila, ID no:691593008 (New ID: 691594008), District: Sylhet | 1.8 |  | 3898325 |  | 3898325 | [7 empty] | 100%
Package Total = |  |  |  | 5.075 |  | 10510726 |  | 10510726 | 0 |  |  |  |  | 10509171.5 |  |  |  |  | 10504157 |  | 5014.5
33 | Beanibazar | LGED/RARIP/SYL/RHB/18-19/W-123 | a) RHD Sheola-Balinga-Charaboi Bazar Road (Ch. 2000-4000m) under Beanibazar Upazila, ID no:691174027, District: Sylhet | 2 |  | 4520839 |  | 4520839 |  | 28.02.19 | Jim Corporation 80/A, Siddheswari Circular Road, Malibhag, Dhaka. | 01.08.19 | 28.08.19 | 11955340.11 | 03.09.19 | 100% | 02.09.20 | Pay Order | 8400000 |  | 3555340.11 | 70.26%
|  |  | b) Nobang-Roybasi-Dudboxi Road (Ch. 2000-4000m) under Beanibazar Upazila, ID no:691174013, District: Sylhet | 2 |  | 4107729 |  | 4107729 | [7 empty] | 100%
|  |  | c) RHD Alinagar (Nobib Ali College)-Surma Dyke Road (Ch. 00-1500m) under Beanibazar Upazila, ID no: 691175005 (New ID 691175248), District: Sylhet | 1.5 |  | 2763415 |  | 2763415 | [7 empty] | 22%
Package Total = |  |  |  | 5.5 |  | 11391983 |  | 11391983 | 0 |  |  |  |  | 11955340.11 |  |  |  |  | 8400000 |  | 3555340.11
34 | Golapgonj | LGED/RARIP/SYL/RHB/18-19/W-124 | a) Chowghari Bazar-Surma Dyke-Pattiura Road (Ch. 00-2000m) under Golapgonj Upazila, ID no: 691384015, District: Sylhet | 2 |  | 2010577 |  | 2010577 |  | 13.06.19 | M/S Zilani Traders 80/4, Siddheswari Circular Road, Ramna, Dhaka | 6.11.19 | 02.12.2019 | 11745496.42 | 08.12.19 | 0% | 07.12.20 | 22.02.21 | 6718545 |  | 5026951.42 | 57.2%
|  |  | b) Gias uddin Chowdhuri Road (Ch. 00-1570m) under Golapgonj Upazila, ID no:691384010, District: Sylhet | 1.57 |  | 3687388 |  | 3687388 | [7 empty] | 100%
| Dakshin Surma |  | c) RHD (Khalermukbazar)-Daudpur UP road (Ch. 00-2000m) under Dakkhin Surma Upazila, ID no: 691953009, District: Sylhet | 2 |  | 5280466 |  | 5280466 | [7 empty] | 100%
Package Total = |  |  |  | 5.57 |  | 10978431 |  | 10978431 | 0 |  |  |  |  | 11745496.42 |  |  |  |  | 6718545 |  | 5026951.42
35 | Zakigonj | LGED/RARIP/SYL/RHB/18-19/W-144 | a) Eidgabazar-Loharmohal Road (Ch. 00-1400m) under Zakigonj Upazila, ID no:691944024, District: Sylhet | 1.4 |  | 3782771 |  | 3782771 |  | 15.11.18 | M/s.Progoti Traders, Kumarpara,Sylhet. | 13.12.18 | 03.01.2019 | 11653820.36 | 10.01.19 | 100% | 09.01.20 | 25.03.20 | 10965062 |  | 688758.36 | 94.09% | Final
|  |  | b) Pirnagar-Mazergupat [Zakiganj HQ (Zero Point)-Pirnagar Mazergupat-Kushiara Dyke] Road (Ch. 00-1600m) under Zakigonj Upazila, ID no:691944023, District: Sylhet | 1.6 |  | 3630936 |  | 3630936 | [7 empty] | 100%
|  |  | c) R & H to Sharifabad Madrasa Road (Ch. 00-1750m) under Zakigonj Upazila, ID no:691944019, District: Sylhet | 1.75 |  | 4240314 |  | 4240314 | [7 empty] | 100%
Package Total = |  |  |  | 4.75 |  | 11654021 |  | 11654021 | 0 |  |  |  |  | 11653820.36 |  |  |  |  | 10965062 |  | 688758.36
36 | Jointiapur | LGED/RARIP/SYL/RHB/18-19/W-145 | a) Kamrangi Village - Lalakhal bazar Road (Ch. 00-2170m) under Jointapur Upazila, ID no:691534038, District: Sylhet | 2.17 |  | 5327794 |  | 5327794 |  | 13.06.19 | ITC-CB(JV) House-53, Road-1 Block-A, Niketon Gulshan-1, Dhaka. | 31.10.19 | 26.11.19 | 15707866.99 | 02.12.19 | 0% | 01.12.20 | 19.01.21
| Gowainghat |  | c) R&H(Tamabil)-Lafnaut-Alirgow U.P. Office Road (Ch. 3765-6150m) under Gowainghat Upazila, ID no:691413004, District: Sylhet | 2.385 |  | 9286623 |  | 9286623
Package Total = |  |  |  | 4.555 | 0 | 14614417 | 0 | 14614417 | 0 |  |  |  |  | 15707866.99
37 | Zakigonj | LGED/RARIP/SYL/RHB/19-20/W-152 | Shagoli Bazar-Kunargram Ferighat Road ( Ch.00-1500m) under Zakiganj Upazila, ID No.691944032, District: Sylhet. | 1.5 |  | 4272848 |  | 4272848 | [14 empty] | Bid under Process
Package Total = |  |  |  | 1.5
Sub-Total = |  |  |  | 44.152 | 0 | 100601189 | 0 | 100601189 | 0 | 0 | 0 | 0 | 0 | 95663035.96 | 0 | 0 | 0 |  | 63982724 | 0 | 15972444.97 | 0 | 0
Bridge
38 | Balagonj | LGED/RARIP/SYL/BDG(UNR)/19-20/W-17(a) | Construction of 60m long RCC Girder Bridge on Pashim Gowripur UP-Office–Donaram bazar Road (Balaganj Part) at Ch. 1875m under Balaganj Upazila, District: Sylhet ID no: 691083017 | 0 | 60 | 74151597 |  | 74151597 | 191157 | [13 empty] | Re-Bid
Package Total = |  |  |  | 0 | 60 | 74151597 |  | 74151597 | 191157
39 | Gowainghat | LGED/RARIP/SYL/BDG(UNR)/19-20/W-18 | Construction of 40m long RCC Girder Bridge on Purba Jaflong UP Office–Nabam khanda bazar road at Ch. 2534m under Gowainghat Upazila, District: Sylhet ID no: 691413008 | 0 | 40 | 45785266 |  | 45785266 | [14 empty] | Re-Bid
Package Total = |  |  |  | 0 | 40 | 45785266 |  | 45785266
Sub-Total = |  |  |  | 0 | 100 | 119936863 | 0 | 119936863 | 191157
Market
40 | Gowainghat | LGED/RARIP/SYL/MAR/19-20/W-164 | Improvement of Monortol Bazar under Gowainghat Upazila, District: Sylhet. | 0 | 0 |  |  | 5515792 | [14 empty] | Bid under Process
Package Total = |  |  |  | 0 | 0 |  |  | 5515792
41 | Companigonj | LGED/RARIP/SYL/MAR/19-20/W-165 | a)Improvement of Jaliarpar Bazar under companiganj Upazila, District: Sylhet.& b) Improvement of Islamganj Bazar under companigonj Upazila, District: Sylhet. | 0 | 0 | 0 |  | 8991214 | [14 empty] | Bid Evaluation Sent to H/Q on 05.01.21
Package Total = |  |  |  | 0 | 0 | 0 | 0 | 8991214
42 | Beanibazar & Golapgonj | LGED/RARIP/SYL/MAR/19-20/W-166 | a) Improvement of Achirgonj (Beanibazar Part) Bazar under Beanibazar Upazila, District: Sylhet. & b) Improvement of Achirgonj (Golapgonj Part) Bazar under Golapgonj Upazila, District: Sylhet. | 0 | 0 |  |  | 7680525 | [14 empty] | Bid Evaluation under Process.
Package Total = |  |  |  | 0 | 0 |  |  | 7680525
43 | Biswanath & Dakshin Surma | LGED/RARIP/SYL/MAR/19-20/W-167 | a) Improvement of Kaliganj Bazar under Biswanath Upazila, District: Sylhet. & b) Improvement of Khalermukh Bazar under Dakshin Surma Upazila, District: Sylhet. | 0 | 0 |  |  | 9173257 | [14 empty] | Bid under Process
Package Total = |  |  |  | 0 | 0 |  |  | 9173257
44 | Zakiganj & Kanaighat | LGED/RARIP/SYL/MAR/19-20/W-168 | a) Improvement of Babur Bazar under Zakiganj Upazila, District: Sylhet. & b) Improvement of Bhabaniganj Bazar under Kanaighat Upazila, District: Sylhet. | 0 | 0 |  |  | 8388490 | [14 empty] | No Bider Found
Package Total = |  |  |  | 0 | 0 |  |  | 8388490
Sub- Total = |  |  |  | 0 | 0 |  |  | 39749278 | [5 empty] | 0 |  |  |  |  | 0 |  | 0 |  |  | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total = | Package Total =
Grand Total = |  |  |  | 93.463 | 144.025 | 610914783.84 | 10970455.4 | 661634517.24 | 3242295 |  |  |  |  | 340917882.43 |  |  |  |  | 98791273 |  | 91250127
Fund Received |  | 2018-19 | 31180172
|  | 2019-20 | 58347636
|  | 2020-21 | 18000000
107527808
|  | (Md.Siddiqur Rahman) |  |  |  | (Imtiaz Hossain) | [5 empty] | (A.K.M.Shahidul Islam) | [6 empty] | (Md. Enamul Kabir)
|  | Accountant |  |  |  | Assistant Engineer | [5 empty] | Senior Assistant Engineer | [6 empty] | Executive Engineer
|  | LGED, Sylhet. |  |  |  | LGED, Sylhet. | [5 empty] | LGED, Sylhet. | [6 empty] | LGED, Sylhet.

## Sheet2
Rural Access Road Improvement Project Under Sylhet Division (RARIP)
Monthly Progress Report (Physical & Financial)
District : Sylhet | [11 empty] | Reporting Month : January,2021
Sl. No. | Upazila | Package No. | Name of Scheme with Chainage & ID No. | Quantity |  | Name of Contractor | Date of NOA issued | Date of Contract/ Revised Contract. | Contract/ Variation Amount (Tk.) | Physical progress (%) | Date of Completion as per contract | Payment Amount for |  |  | Financial Progress (%) | Remarks
|  |  |  | Road (Km) | Struct. (m) | [6 empty] | Road (Tk.) | Bridge/ Culvert (Tk.) | Remaining Payment (Tk.)
1 | 2 | 3 | 4 | 5 | 6 | 12 | 13 | 14 | 15 | 17 | 18 | 20 | 21 | 22 | 23 | 24
Improvement Union Road
1 | Biswanath | LGED/RARIP/SYL/UNR/18-19/W-01 | a) RHD Rampasha-Rajagonj-Uttar Biswanath-Lamakazi UP road Doshghar UP-Lohori-Mashukhali bazer road (RHD Rampasha-Rajagonj-Uttar Biswanath-Lamakazi UP road) (Ch. 2600-4600m) under Biswanath Upazila, ID no: 691203002, District: Sylhet | 2 |  | B.M Trade Center 80/A, Siddheswari Circular Road, Malibhag, Dhaka. | 03.11.19 | 28.11.19 | 49215770.28 | 10% | 03.12.20 | 10290000 |  | 38925770.28 | 20.91%
| Zakigonj |  | b) Beroshree UP Office-Shahbag Bus Stand Bazar (RHD) via Barkatpur-Raghurashi Bazar Road (Ch. 1988-3988m) under Zakiginj Upazila, ID no: 691943007, District: Sylhet | 2 | [5 empty] | 55%
| Golapgonj |  | c) Raquar bazar-Shantirbazar-Supatake Rd. (Ch. 700-2700m) under Golapgonj Upazila, ID no: 691383012, District: Sylhet | 2 | [5 empty] | 25%
Package Total = |  |  |  | 6 |  |  |  |  | 49215770.28 |  |  | 10290000 |  | 38925770.28
2 | Gowainghat | LGED/RARIP/SYL/UNR/18-19/W-10 | a) Purba Jaflong UP office – Nabamkhanda bazar road (Ch. 00-150 & 2309-3692m) under Gowainghat Upazila, ID no: 691413008, District: Sylhet | 1.488 | 4.75 |  |  |  | 0 |  |  | 0 |  | 0 | #DIV/0! | Re-Bid Under Process
|  |  | b) Pirijpur – Paschim Jaflong UP office-Sonarhat (Pirajpur – Paschim Jaflong UP office-Sonarhat-Monortal Bazar) road (Ch. 10815-11472 & 12725-13389m) under Gowainghat Upazila, ID no: 691413002, District: Sylhet | 1.321
| Jointiapur |  | c) Khorilbazar – Lalakhal – Thubang – Charikata UP HQ Road (Ch. 4460-7460m) under Jointiapur Upazila, ID no: 691533001, District: Sylhet | 3
|  |  | d) Darbostbazar (GC) – Ramproshad – Charikata UP HQ Road (Ch. 7500-9320m) under Jointiapur Upazila, ID no: 691533006, District: Sylhet | 1.82
Package Total = |  |  |  | 7.629 | 4.75 |  |  |  | 0 |  |  | 0 |  | 0
Sub Total = |  |  |  | 13.629 | 4.75 |  |  |  | 49215770.28 |  |  | 10290000 |  | 38925770.28
Improvement Village Road
3 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-20 | a) Kalagul Road (Ch. 2000-2720m) under Sylhet Sadar Upazila, ID no: 691624063, District: Sylhet. | 0.72 | 1.5 | Xcellent Trade Corporation House No.54/A, Road No. 132. Gulshan-1, Dhaka. | 14.11.19 | 10.12.19 | 12210587.52 | 10% | 15.12.20
|  |  | b) Dhanpur Ferryghat-Mirpur-Muktirbazar Road (Ch. 1500-1900m) under Sylhet Sadar Upazila, ID no: 691624121,District: Sylhet. | 0.4
|  |  | c) Mohaldik-Murargaon road (Dhapnatila) (Ch. 2000-2406m) under Sylhet Sadar Upazila, ID no: 691625072, District: Sylhet. | 0.406
Package Total = |  |  |  | 1.526 | 1.5 |  |  |  | 12210587.52
4 | Osmaninagar | LGED/RARIP/SYL/VR /18-19/W-21 | Osmanpur UP - Madrashabazar- Nazirbazar - Dakhin Khagdior - Goinaghat road (Ch. 00-800m) under Osmaninogar Upazila, ID no: 691085180, District: Sylhet. | 0.8 | 2 | M/S. Suhel Enterprise Osmaninagar,Sylhet. | 09.07.19 | 05.08.19 | 6449568.96 | 20% | 13.08.20
Package Total = |  |  |  | 0.8 | 2 |  |  |  | 6449568.96
5 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-22 | a) Anantapur prymary school-Hajrat Miskinsha Mukambadauni road (Ch. 00-470m) under Sylhet Sadar Upazila, ID no: 691624113, District: Sylhet. | 0.47 |  | Seaba Prokoushali Songhosta 50, Naya Paltan,Dhaka. | 14.10.19 | 7.11.19 | 8537124.25 | 0% | 13.11.20
| Biswanath |  | b) RHD Rashidpur- Shirajpur-RHD Shahjirgow Road (Ch. 2200-2925m) under Biswanath Upazila, ID no: 691204007,District: Sylhet. | 0.725
Package Total = |  |  |  | 1.195 |  |  |  |  | 8537124.25
3 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-47 | Kandigaon - Badhaghat Road (Ch. 00-480m)under Sylhet Sadar Upazila, ID no: 691624079, District: Sylhet | 0.48 |  | 4443966 |  |  | 4443966 | [6 empty] | Re-Bid under Process
|  |  | Borkapon-Kalirgaon Road (Ch. 1000-2000m) under Sadar Upazila, ID no: 691624085, District: Sylhet | 1 |  | 6971961 |  |  | 6971961
Package Total = |  |  |  | 1.48 |  | 11415927 |  |  | 11415927 |  |  |  |  | 0
8 | Sylhet Sadar | LGED/RARIP/SYL/VR /18-19/W-49 | Dararbazar road -Semarbazar road (Monthol) (Ch. 00-940m) under Sadar Upazila, ID no: 691624134, District: Sylhet | 0.94 |  | ITC-CB JV, House-4/1/A, Flat No.4/A, Level-3, Road-02, Gulshan-1, Dhaka. | 29.09.20 | 27.10.20 | 11701314.79 | 0% | 03.11.21
|  |  | Chowdhurypara Road No.02 Road (Ch. 00-725m) under Sadar Upazila, ID no: 691625257, District: Sylhet | 0.725 | 3.4 |  |  |  |  | 0%
Package Total = |  |  |  | 1.665 | 3.4 |  |  |  | 11701314.79
9 | Biswananth | LGED/RARIP/SYL/VR /18-19/W-51 | South Dewkalash Govt. Pry.School tokahirghat bazar (Ch. 1000-2000m) under Biswanath Upazila, ID no: 691204064, District: Sylhet | 1 |  | M/s. Alam Traders Shibpur, Norshingdi. | 05.12.18 | 01.01.19 | 11011045.84 | 100% | 20.03.20 | 4500000 |  | 6511045.84 | 40.87%
|  |  | Kaligonj bazar-Mirachar-CHalia road (Ch. 1000-1620m) under Biswanath Upazila, ID no: 691205059, District: Sylhet | 0.62 | [5 empty] | 5%
Package Total = |  |  |  | 1.62 |  |  |  |  | 11011045.84 |  |  | 4500000 |  | 6511045.84
6 | Osmaninagar | LGED/RARIP/SYL/VR /18-19/W-52 | Idgha Bazar - Kayrabad Road (Ch. 00-1000m) under Osmaninagor Upazila, ID no:691084037, District: Sylhet | 1 |  | 6811439 |  |  | 6811440 | [6 empty] | Re-Bid under Process
Package Total = |  |  |  | 1 |  | 6811439 |  |  | 6811440 |  |  |  |  | 0
12 | Dakshin Surma | LGED/RARIP/SYL/VR /18-19/W-54 | Hazigonj bazar-Chisrakandi -Chandpur road (Ch. 1500-2500m) under Dakshin Surma Upazila, ID no: 691954021, District: Sylhet | 1 |  | ITC-CB (JV), House-53,Road-1, Block-A, Niketon,Gulshan-1, Dhaka. | 14.10.19 | 7.11.19 | 11545953.41 | 5% | 13.11.20
|  |  | RHD ( Kadamtoli ) Shiberchok road (Ch. 00-500m) under Dakshin Surma Upazila, ID no: 691955045,District: Sylhet | 0.5 | 0.625 |  |  |  |  | 5%
Package Total = |  |  |  | 1.5 | 0.625 |  |  |  | 11545953.41
13 | Fenchugonj | LGED/RARIP/SYL/VR /18-19/W-55 | a) Bealibazar Paglachara-Dharan Mirzapur Road (Ch. 1000-2100m) under Fenchugonj Upazila, ID no: 691354001, District: Sylhet | 1.1 |  | ITC-CB JV, House-4/1/A, Flat No.4/A, Level-3, Road-02, Gulshan-1, Dhaka. | 29.09.20 | 27.10.20 | 22502947.14 | 0% | 03.11.21
|  |  | b) Sottrish GPS - Bagmara Purbara Kathaltali (Concrete Road) (Ch. 00-1000m) under Fenchugonj Upazila, ID no: 691355064, District: Sylhet | 1
Package Total = |  |  |  | 2.1 |  |  |  |  | 22502947.14
14 | Osmaninagar | LGED/RARIP/SYL/VR /18-19/W-56 | Omarpur bazar-Mandaruka Road (Ch. 1230-2230m) under Osmaninagar(Ex Balagonj) Upazila, ID no: 691084007, District: Sylhet | 1 |  | Seaba Prokoushali Songhosta 50, Naya Paltan,Dhaka. | 24.04.19 | 21.05.19 | 7302327.5 | 15% | 08.08.20
Package Total = |  |  |  | 1 |  |  |  |  | 7302327.5 |  |  | 0 |  | 0
15 | Jointiapur | LGED/RARIP/SYL/VR /18-19/W-57 | Paton Village Road (Ch. 00-1470m) under Jointapur Upazila, ID no: 691535013, District: Sylhet | 1.47 |  | M/s.Molla Enterprise 297/1, Bara Moghbazar, Dhaka. | 01.08.19 | 28.08.19 |  | 0% | 02.09.20 |  |  |  |  | Work Order Cencel & Received with Petition
Package Total = |  |  |  | 1.47 |  |  |  |  | 0
9 | Gowainghat | LGED/RARIP/SYL/VR /18-19/W-58 | Jolurmuk - Ramnagor - Ratergul road (Ch. 1750-2705m) under Gowainghat Upazila, ID no: 691415005, District: Sylhet | 0.955 |  | 9068305 |  |  | 9068306 | [6 empty] | Re-Bid under Process
Package Total = |  |  |  | 0.955 |  | 9068305 |  |  | 9068306 |  |  |  |  | 0
17 | Gowainghat | LGED/RARIP/SYL/VR /18-19/W-59 | a) Kandigram Chirurpar Bund Road (Ch. 600-1600m) under Gowainghat Upazila, ID no: 691415055 (New ID 691415052), District: Sylhet | 1 |  | ITC-CB JV, House-4/1/A, Flat No.4/A, Level-3, Road-02, Gulshan-1, Dhaka. | 29.09.20 | 27.10.20 | 12004281.32 | 0% | 03.11.21
|  |  | b) Tamabil RHD Lafnaut-Alirgaon UP office road (Noyamati) Latu Paschim road (Ch. 955-1395m) under Gowainghat Upazila, ID no: 691414026 (New ID 691414025), District: Sylhet. | 0.44
Package Total = |  |  |  | 1.44 |  |  |  |  | 12004281.32
18 | Companigonj | LGED/RARIP/SYL/VR /18-19/W-60 | Upazila Health Complex - Thana H/Q-Toker Bazar Road (Ch. 350-950m) under Companigonj Upazila, ID no: 691274018, District: Sylhet | 0.6 |  | M/S Zilani Traders 80/4, Siddheswari Circular Road, Ramna, Dhaka | 25.06.20 | 16.07.20 | 24248089.95 | 0% | 21.07.21
|  |  | RHD-Companigonj-Buridohar Hazi Hason Ali School (Ch. 1290-1790m) under Companigonj Upazila, ID no: 691274031, District: Sylhet | 0.5 | [5 empty] | 0%
| Kanaighat |  | Dowarimati - Majargram Road (Ch. 500-1500m) under Kanighat Upazila, ID no: 691594010, District: Sylhet | 1 | [5 empty] | 10%
Package Total = |  |  |  | 2.1 |  |  |  |  | 24248089.95
19 | Kanaighat | LGED/RARIP/SYL/VR /18-19/W-61 | a) Patromati Mosque to Thakurmati Road (Ch. 2010-3010m) under Kanighat Upazila, ID no: 691595015 (New ID 691594183), District: Sylhet | 1 |  | B.M Trade Center 80/A, Siddheswari Circular Road, Malibhag, Dhaka. | 01.08.19 | 28.08.19 | 16302404.35 | 45% | 02.09.20 | 2100000 |  | 14202404.35
|  |  | b) Boroband pry.school to Kathaltoli Road (Ch. 00-1000m) under Kanighat Upazila, ID no: 691594123, District: Sylhet | 1 | 3 |  |  |  |  | 0%
Package Total = |  |  |  | 2 | 3 |  |  |  | 16302404.35 |  |  | 2100000 |  | 14202404.35
27 | Beanibazar | LGED/RARIP/SYL/VR /18-19/W-110 | RHD (Abdullahpur)-Gounggadia-I.L.o Road (Ch. 00-1000m) under Beanibazar Upazila, ID no: 691174025, District: Sylhet | 1 |  | Md.Mahmudul Hussain Tufa, Shahjalal Upashahar, Sylhet. | 24.04.19 | 20.05.19 | 9954410.82 | 15% | 26.05.20
Package Total = |  |  |  | 1 |  |  |  |  | 9954410.82
Maintenance
33 | Beanibazar | LGED/RARIP/SYL/RHB/18-19/W-123 | a) RHD Sheola-Balinga-Charaboi Bazar Road (Ch. 2000-4000m) under Beanibazar Upazila, ID no:691174027, District: Sylhet | 2 |  | Jim Corporation 80/A, Siddheswari Circular Road, Malibhag, Dhaka. | 01.08.19 | 28.08.19 | 11955340.11 | 100% | 02.09.20 | 8400000 |  | 3555340.11 | 70.26%
|  |  | b) Nobang-Roybasi-Dudboxi Road (Ch. 2000-4000m) under Beanibazar Upazila, ID no:691174013, District: Sylhet | 2 | [5 empty] | 100%
|  |  | c) RHD Alinagar (Nobib Ali College)-Surma Dyke Road (Ch. 00-1500m) under Beanibazar Upazila, ID no: 691175005 (New ID 691175248), District: Sylhet | 1.5 | [5 empty] | 20%
Package Total = |  |  |  | 5.5 |  |  |  |  | 11955340.11 |  |  | 8400000 |  | 3555340.11
34 | Golapgonj | LGED/RARIP/SYL/RHB/18-19/W-124 | a) Chowghari Bazar-Surma Dyke-Pattiura Road (Ch. 00-2000m) under Golapgonj Upazila, ID no: 691384015, District: Sylhet | 2 |  | M/S Zilani Traders 80/4, Siddheswari Circular Road, Ramna, Dhaka | 6.11.19 | 02.12.2019 | 11745496.42 | 0% | 07.12.20 | 6718545 |  | 5026951.42 | 57.2%
|  |  | b) Gias uddin Chowdhuri Road (Ch. 00-1570m) under Golapgonj Upazila, ID no:691384010, District: Sylhet | 1.57 | [5 empty] | 100%
| Dakshin Surma |  | c) RHD (Khalermukbazar)-Daudpur UP road (Ch. 00-2000m) under Dakkhin Surma Upazila, ID no: 691953009, District: Sylhet | 2 | [5 empty] | 100%
Package Total = |  |  |  | 5.57 |  |  |  |  | 11745496.42 |  |  | 6718545 |  | 5026951.42
36 | Jointiapur | LGED/RARIP/SYL/RHB/18-19/W-145 | a) Kamrangi Village - Lalakhal bazar Road (Ch. 00-2170m) under Jointapur Upazila, ID no:691534038, District: Sylhet | 2.17 |  | ITC-CB(JV) House-53, Road-1 Block-A, Niketon Gulshan-1, Dhaka. | 31.10.19 | 26.11.19 | 15707866.99 | 0% | 01.12.20
| Gowainghat |  | c) R&H(Tamabil)-Lafnaut-Alirgow U.P. Office Road (Ch. 3765-6150m) under Gowainghat Upazila, ID no:691413004, District: Sylhet | 2.385
Package Total = |  |  |  | 4.555 | 0 |  |  |  | 15707866.99
37 | Zakigonj | LGED/RARIP/SYL/RHB/19-20/W-152 | Shagoli Bazar-Kunargram Ferighat Road ( Ch.00-1500m) under Zakiganj Upazila, ID No.691944032, District: Sylhet. | 1.5 | [11 empty] | Bid under Process
Package Total = |  |  |  | 1.5