## Summary
Promoting Resilience of Vulnerable Through Access to Infrastructure, Improved Skills and Information (PROVATi³) Local Government Engineering Department
ANNUAL PROCURMENT PLAN FOR 2022-2023
Works |  |  |  | Goods |  |  |  | Service
Type | Procurement Method | No of Packages | Estimated Amount | Type | Procurement Method | No | Estimated Amount | Type | Procurement Method | Nos | Estimated Amount
Market Development | DPM/LCS | 107 | 225609000 | Vehicles | DPM | 1 | 10000000 | Individual Consultant | ICS | 4 | 16600800
Road Maintenance by LCS | DPM/LCS | 33 | 247500000 | Equipment | RFQ | 6 | 3000000 | Consulting Firms | QCBS/SSS | 4 | 124350426.14
Rehabilitation of Road | OTM | 7 | 19600000 | Stationary | OTM | 1 | 7000000 | Training | SSS | 20 | 122962000
Road Improvement | OTM | 16 | 112000000
Flood shelter | OTM | 7 | 178664828
|  | 170 | 783373828 |  |  | 8 | 20000000 |  |  |  | 263913226.14
Total Estimated Cost | [10 empty] | 1067287054.14

## Total Procurement Budget
Promoting Resilience of Vulnerable Through Access to Infrastructure, Improved Skills and Information (PROVATi³) Local Government Engineering Department
Procurement Budget for 2022-23 of PROVATi³, LGED
No | Item of Procurement | APP 2022-23 | Carried Over Procurement Budget | Total Procurement Budget | Remarks
1 | Goods | 20000000 | 1600000 | 21600000
2 | Works | 783373828 | 970000000 | 1753373828
3 | Service | 263913226.14 | 177000000 | 440913226.14
| Total Budget | 1067287054.14 | 1148600000 | 2215887054.14

## Works
Promoting Resilience of Vulnerable Through Access to Infrastructure, Improved Skills and Information (PROVATi³) Project Local Government Engineering Department
ANNUAL PROCURMENT PLAN FOR 2022-2023
(W O R K S)
Sl No | Package No | Description | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Fund | Estimated Cost | Time Code for Process | Advirtise PreQual Docs | Invite/ Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | NOA | Signing of Contract | Total Time to Contract Signature [days] | Total Time Completion of Contract
1 | PRO/NIL/LM/2022-23/ W-349 (LCS-1) | Development of Large Market Through LCS Group(Bhabonchur Bazar, Dimla, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 07/7/22 | 07/7/22 | N/A | 08/9/22 | 60 | 30/10/23
Actual
2 | PRO/NIL/LM/2022-23/ W-350 (LCS-2) | Development of Large Market Through LCS Group(Bhabonchur Bazar, Dimla, Nilphamari) | nos | 2 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 07/7/22 | 07/7/22 | N/A | 08/9/22 | 60 | 30/10/23
Actual
3 | PRO/NIL/LM/2022-23/ W-351 (LCS-3) | Development of Large Market Through LCS Group(Bhabonchur Bazar, Dimla, Nilphamari) | nos | 3 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 07/7/22 | 07/7/22 | N/A | 08/9/22 | 60 | 30/10/23
Actual
4 | PRO/NIL/LM/2022-23/ W-352 (LCS-1) | Development of Large Market Through LCS Group (Tunirhat, Dimla, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/8/22 | 04/8/22 | N/A | 06/10/22 | 60 | 30/12/23
Actual
5 | PRO/NIL/LM/2022-23/ W-353 (LCS-3) | Development of Large Market Through LCS Group (Tunirhat, Dimla, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/8/22 | 04/8/22 | N/A | 06/10/22 | 60 | 30/12/23
Actual
6 | PRO/NIL/LM/2022-23/ W-354 (LCS-3) | Development of Large Market Through LCS Group (Tunirhat, Dimla, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/8/22 | 04/8/22 | N/A | 06/10/22 | 60 | 30/12/23
[7 empty] | TOTAL TK: | 12540000
7 | PRO/JAMAL/LM/2022-23/ W-355 (LCS-1) | Development of Large Market Through LCS Group (Bakshiganj, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 01/9/22 | 01/9/22 | N/A | 02/11/22 | 60 | 30/11/23
Actual
8 | PRO/JAMAL/LM/2022-23/ W-356 (LCS-2) | Development of Large Market Through LCS Group (Bakshiganj, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 01/9/22 | 01/9/22 | N/A | 02/11/22 | 60 | 30/11/23
Actual
9 | PRO/JAMAL/LM/2022-23/ W-357 (LCS-3) | Development of Large Market Through LCS Group (Bakshiganj, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 01/9/22 | 01/9/22 | N/A | 02/11/22 | 60 | 30/11/23
Actual
10 | PRO/JAMAL/LM/2022-23/ W-358 (LCS-1) | Development of Large Market Through LCS Group (Mahmudpur Bajar, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/12/22 | 04/12/22 | N/A | 02/02/23 | 60 | 02/02/24
Actual
11 | PRO/JAMAL/LM/2022-23/ W-359 (LCS-2) | Development of Large Market Through LCS Group (Mahmudpur Bajar, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/12/22 | 04/12/22 | N/A | 02/02/23 | 60 | 02/02/24
Actual
12 | PRO/JAMAL/LM/2022-23/ W-360 (LCS-3) | Development of Large Market Through LCS Group (Mahmudpur Bajar, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/12/22 | 04/12/22 | N/A | 02/02/23 | 60 | 02/02/24
Actual
13 | PRO/JAMAL/LM/2022-23/ W-361 (LCS-1) | Development of Large Market Through LCS Group (Bakshiganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 15/7/22 | 15/7/22 | N/A | 15/9/22 | 60 | 15/9/23
Actual
14 | PRO/JAMAL/LM/2022-23/ W-362 (LCS-2) | Development of Large Market Through LCS Group (Bakshiganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 15/7/22 | 15/7/22 | N/A | 15/9/22 | 60 | 15/9/23
Actual
15 | PRO/JAMAL/LM/2022-23/ W-363 (LCS-3) | Development of Large Market Through LCS Group (Bakshiganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 15/7/22 | 15/7/22 | N/A | 15/9/22 | 60 | 15/9/23
Actual
16 | PRO/JAMAL/LM/2022-23/ W-364 (LCS-1) | Development of Large Market Through LCS Group (Islampur, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 30/7/22 | 30/7/22 | N/A | 29/9/22 | 60 | 29/9/23
Actual
17 | PRO/JAMAL/LM/2022-23/ W-365 (LCS-2) | Development of Large Market Through LCS Group (Islampur, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 30/7/22 | 30/7/22 | N/A | 29/9/22 | 60 | 28/9/23
Actual
18 | PRO/JAMAL/LM/2022-23/ W-366 (LCS-3) | Development of Large Market Through LCS Group (Islampur, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 30/7/22 | 30/7/22 | N/A | 29/9/22 | 60 | 28/9/23
Actual
19 | PRO/JAMAL/LM/2022-23/ W-367 (LCS-1) | Development of Large Market Through LCS Group(Khorma Bajar, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 05/8/22 | 05/8/22 | N/A | 05/10/22 | 60 | 05/10/23
Actual
20 | PRO/JAMAL/LM/2022-23/ W-368 (LCS-2) | Development of Large Market Through LCS Group(Khorma Bajar, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 05/8/22 | 05/8/22 | N/A | 02/10/22 | 60 | 02/10/23
Actual
21 | PRO/JAMAL/LM/2022-23/ W-369 (LCS-3) | Development of Large Market Through LCS Group(Khorma Bajar, Dewanganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 05/8/22 | 05/8/22 | N/A | 02/10/22 | 60 | 02/10/23
[7 empty] | TOTAL TK: | 31350000
22 | PRO/KURI/LM/2022-23/ W-370 (LCS-1) | Development of Large Market Through LCS Group (Thana hat, Chilmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 01/2/23 | 01/2/23 | N/A | 01/3/23 | 60 | 02/3/24
Actual
23 | PRO/KURI/LM/2022-23/ W-371 (LCS-2) | Development of Large Market Through LCS Group (Thana hat, Chilmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 01/2/23 | 01/2/23 | N/A | 02/10/22 | 60 | 02/10/23
Actual
24 | PRO/KURI/LM/2022-23/ W-372 (LCS-3) | Development of Large Market Through LCS Group (Thana hat, Chilmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 01/2/23 | 01/2/23 | N/A | 02/10/22 | 60 | 02/10/23
Actual
25 | PRO/KURI/LM/2022-23/ W-373 (LCS-1) | Development of Large Market Through LCS Group (Panchgachi Hat, Kurigram Sadar, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 15/8/22 | 15/8/22 | N/A | 15/10/22 | 60 | 15/10/23
Actual
26 | PRO/KURI/LM/2022-23/ W-374 (LCS-2) | Development of Large Market Through LCS Group (Panchgachi Hat, Kurigram Sadar, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 15/8/22 | 15/8/22 | N/A | 15/10/22 | 60 | 15/10/23
Actual
27 | PRO/KURI/LM/2022-23/ W-375 (LCS-3) | Development of Large Market Through LCS Group (Panchgachi Hat, Kurigram Sadar, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 15/8/22 | 15/8/22 | N/A | 15/10/22 | 60 | 15/10/23
Actual
28 | PRO/KURI/LM/2022-23/ W-376 (LCS-1) | Development of Large Market Through LCS Group (Bhurungimari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 30/8/22 | 30/8/22 | N/A | 30/10/22 | 60 | 30/10/23
Actual
29 | PRO/KURI/LM/2022-23/ W-377 (LCS-2) | Development of Large Market Through LCS Group (Bhurungimari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 30/8/22 | 30/8/22 | N/A | 30/10/22 | 60 | 30/10/23
Actual
30 | PRO/KURI/LM/2022-23/ W-378 (LCS-3) | Development of Large Market Through LCS Group (Bhurungimari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 30/8/22 | 30/8/22 | N/A | 30/10/22 | 60 | 30/10/23
Actual
31 | PRO/KURI/LM/2022-23/ W-379 (LCS-1) | Development of Large Market Through LCS Group Kurigram Sadar, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/9/22 | 04/9/22 | N/A | 06/11/22 | 60 | 07/11/23
Actual
32 | PRO/KURI/LM/2022-23/ W-380 (LCS-2) | Development of Large Market Through LCS Group Kurigram Sadar, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/9/22 | 04/9/22 | N/A | 06/11/22 | 60 | 07/11/23
Actual
33 | PRO/KURI/LM/2022-23/ W-381 (LCS-3) | Development of Large Market Through LCS Group Kurigram Sadar, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2090000 | Plan | N/A | N/A | N/A | 04/9/22 | 04/9/22 | N/A | 06/11/22 | 60 | 07/11/23
[7 empty] | TOTAL TK: | 25080000 | Actual
34 | PRO/RANG/MM/2022-23/ W-382 (LCS-1) | Development of Medium Market through LCS Group (Gangchara, Rangpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 07/7/22 | N/A | N/A | 08/9/22 | 60 | 30/10/23
Actual
35 | PRO/RANG/MM/2022-23/ W-383 (LCS-2) | Development of Medium Market through LCS Group (Gangchara, Rangpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 07/7/22 | N/A | N/A | 08/9/22 | 60 | 30/10/23
Actual
36 | PRO/RANG/MM/2022-23/ W-384 (LCS-1) | Development of Medium Market through LCS Group (Kawnia, Rangpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/8/22 | N/A | N/A | 06/10/22 | 60 | 30/12/23
Actual
37 | PRO/RANG/MM/2022-23/ W-385 (LCS-2) | Development of Medium Market through LCS Group (Kawnia, Rangpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/8/22 | N/A | N/A | 06/10/22 | 60 | 30/12/23
Actual
38 | PRO/RANG/MM/2022-23/ W-386 (LCS-1) | Development of Medium Market through LCS Group (Abuliar Hat,Gangchara, Rangpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 01/9/22 | N/A | N/A | 02/11/22 | 60 | 30/11/23
Actual
39 | PRO/RANG/MM/2022-23/ W-387 (LCS-2) | Development of Medium Market through LCS Group (Abuliar Hat,Gangchara, Rangpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 01/9/22 | N/A | N/A | 02/11/22 | 60 | 30/11/23
[7 empty] | TOTAL TK: | 12531000 | Actual
40 | PRO/NIL/MM/2022-23/ W-388 (LCS-1) | Development of Medium Market through LCS Group (Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/12/22 | N/A | N/A | 02/02/23 | 60 | 02/02/24
Actual
41 | PRO/NIL/MM/2022-23/ W-389 (LCS-2) | Development of Medium Market through LCS Group (Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/12/22 | N/A | N/A | 02/02/23 | 60 | 02/02/24
Actual
42 | PRO/NIL/MM/2022-23/ W-390 (LCS-1) | Development of Medium Market through LCS Group (Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/7/22 | N/A | N/A | 15/9/22 | 60 | 15/9/23
Actual
43 | PRO/NIL/MM/2022-23/ W-391 (LCS-2) | Development of Medium Market through LCS Group (Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/7/22 | N/A | N/A | 15/9/22 | 60 | 15/9/23
Actual
44 | PRO/NIL/MM/2022-23/ W-392 (LCS-1) | Development of Medium Market through LCS Group(Golmunda Bazar, Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/7/22 | N/A | N/A | 29/9/22 | 60 | 29/9/23
Actual
45 | PRO/NIL/MM/2022-23/ W-393 (LCS-2) | Development of Medium Market through LCS Group(Golmunda Bazar, Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/7/22 | N/A | N/A | 29/9/22 | 60 | 29/9/23
Actual
46 | PRO/NIL/MM/2022-23/ W-394 (LCS-1) | Development of Medium Market through LCS Group(Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 01/8/22 | N/A | N/A | 02/10/22 | 60 | 02/10/23
Actual
47 | PRO/NIL/MM/2022-23/ W-395 (LCS-2) | Development of Medium Market through LCS Group(Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 01/8/22 | N/A | N/A | 02/10/22 | 60 | 02/10/23
Actual
48 | PRO/NIL/MM/2022-23/ W-396 (LCS-1) | Development of Medium Market through LCS Group(Balagram Bazar, Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/8/22 | N/A | N/A | 15/10/22 | 60 | 15/10/23
Actual
49 | PRO/NIL/MM/2022-23/ W-397 (LCS-2) | Development of Medium Market through LCS Group(Balagram Bazar, Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/8/22 | N/A | N/A | 15/10/22 | 60 | 15/10/23
Actual
50 | PRO/NIL/MM/2022-23/ W-398 (LCS-1) | Development of Medium Market through LCS Group(Pathan Para Hat, Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/8/22 | N/A | N/A | 30/10/22 | 60 | 30/10/23
Actual
51 | PRO/NIL/MM/2022-23/ W-399 (LCS-1) | Development of Medium Market through LCS Group(Pathan Para Hat, Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/8/22 | N/A | N/A | 30/10/22 | 60 | 30/10/23
Actual
52 | PRO/NIL/MM/2022-23/ W-400 (LCS-2) | Development of Medium Market through LCS Group(Dakligonj Hat,Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/8/22 | N/A | N/A | 30/10/22 | 60 | 30/10/23
Actual
53 | PRO/NIL/MM/2022-23/ W-401 (LCS-2) | Development of Medium Market through LCS Group(Dakligonj Hat,Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/8/22 | N/A | N/A | 30/10/22 | 60 | 30/10/23
Actual
54 | PRO/NIL/MM/2022-23/ W-403 (LCS-1) | Development of Medium Market through LCS Group(Shibur Hat,Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/9/22 | N/A | N/A | 06/11/22 | 60 | 07/11/23
Actual
55 | PRO/NIL/MM/2022-23/ W-404 (LCS-2) | Development of Medium Market through LCS Group(Shibur Hat,Jaldhaka, Nilphamari) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/9/22 | N/A | N/A | 06/11/22 | 60 | 07/11/23
[7 empty] | TOTAL TK: | 33416000 | Actual
56 | PRO/LAL/MM/2022-23/ W-405 (LCS-1) | Development of Medium Market through LCS Group(Sharkarar Hat, Patgram, Lalmonirhat) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 08/10/22 | N/A | N/A | 09/12/23 | 60 | 09/12/24
Actual
57 | PRO/LAL/MM/2022-23/ W-406 (LCS-2) | Development of Medium Market through LCS Group(Sharkarar Hat, Patgram, Lalmonirhat) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 08/10/22 | N/A | N/A | 09/12/23 | 60 | 09/12/24
Actual
58 | PRO/LAL/MM/2022-23/ W-407 (LCS-1) | Development of Medium Market through LCS Group (Hatibandha, Lalmonirhat) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 10/11/22 | N/A | N/A | 12/01/23 | 60 | 12/02/24
Actual
59 | PRO/LAL/MM/2022-23/ W-408 (LCS-2) | Development of Medium Market through LCS Group (Hatibandha, Lalmonirhat) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 10/11/22 | N/A | N/A | 12/01/23 | 60 | 12/02/24
Actual
60 | PRO/LAL/MM/2022-23/ W-409 (LCS-1) | Development of Medium Market through LCS Group (Loliter Hat, Patgram, Lalmonirhat) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/12/22 | N/A | N/A | 06/2/23 | 60 | 06/2/24
[7 empty] | IFAD+GOB |  | Actual
61 | PRO/LAL/MM/2022-23/ W-410 (LCS-2) | Development of Medium Market through LCS Group (Loliter Hat, Patgram, Lalmonirhat) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/12/22 | N/A | N/A | 06/2/23 | 60 | 06/2/24
[8 empty] | 0 | Actual
[7 empty] | TOTAL TK: | 12531000
62 | PRO/KURI/MM/2022-23/ W-411 (LCS-1) | Development of Medium Market through LCS Group (Fulbari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 02/2/23 | N/A | N/A | 02/4/23 | 60 | 03/04/24
[7 empty] | IFAD+GOB |  | Actual
63 | PRO/KURI/MM/2022-23/ W-412 (LCS-2) | Development of Medium Market through LCS Group (Fulbari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 02/2/23 | N/A | N/A | 02/4/23 | 60 | 03/04/24
[7 empty] | IFAD+GOB |  | Actual
64 | PRO/KURI/MM/2022-23/ W-413 (LCS-1) | Development of Medium Market through LCS Group (Nageswari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/2/23 | N/A | N/A | 16/4/23 | 60 | 16/4/24
[7 empty] | IFAD+GOB |  | Actual
65 | PRO/KURI/MM/2022-23/ W-414 (LCS-2) | Development of Medium Market through LCS Group (Nageswari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/2/23 | N/A | N/A | 16/4/23 | 60 | 16/4/24
[7 empty] | IFAD+GOB |  | Actual
66 | PRO/KURI/MM/2022-23/ W-415 (LCS-1) | Development of Medium Market through LCS Group (Rawmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 28/2/23 | N/A | N/A | 27/4/23 | 60 | 28/4/24
[7 empty] | IFAD+GOB |  | Actual
67 | PRO/KURI/MM/2022-23/ W-416 (LCS-2) | Development of Medium Market through LCS Group (Rawmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 28/2/23 | N/A | N/A | 27/4/23 | 60 | 28/4/24
[7 empty] | IFAD+GOB |  | Actual
68 | PRO/KURI/MM/2022-23/ W-417 (LCS-1) | Development of Medium Market through LCS Group (Ulipur, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/3/23 | N/A | N/A | 04/5/23 | 60 | 06/5/24
[7 empty] | IFAD+GOB |  | Actual
69 | PRO/KURI/MM/2022-23/ W-416 (LCS-2) | Development of Medium Market through LCS Group (Ulipur, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/3/23 | N/A | N/A | 04/5/23 | 60 | 06/5/24
[7 empty] | IFAD+GOB |  | Actual
70 | PRO/KURI/MM/2022-23/ W-417 (LCS-1) | Development of Medium Market through LCS Group (Rajmallirhat, Rajarhat, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 09/4/23 | N/A | N/A | 08/4/23 | 60 | 08/4/24
Actual
71 | PRO/KURI/MM/2022-23/ W-418 (LC-2) | Development of Medium Market through LCS Group (Rajmallirhat, Rajarhat, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 09/4/23 | N/A | N/A | 08/4/23 | 60 | 08/4/24
Actual
72 | PRO/KURI/MM/2022-23/ W-419 (LCS-1) | Development of Medium Market through LCS Group(Maniganj Bazar, Nageshwari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 10/5/23 | N/A | N/A | 06/5/23 | 60 | 07/5/24
Actual
73 | PRO/KURI/MM/2022-23/ W-420 (LCS-2) | Development of Medium Market through LCS Group(Maniganj Bazar, Nageshwari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 10/5/23 | N/A | N/A | 06/5/23 | 60 | 07/5/24
Actual
74 | PRO/KURI/MM/2022-23/ W-421 (LCS-1) | Development of Medium Market through LCS Group(Baraikandi Hat, Rawmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 07/7/22 | N/A | N/A | 08/9/22 | 60 | 30/10/23
Actual
75 | PRO/KURI/MM/2022-23/ W-422 (LCS-2) | Development of Medium Market through LCS Group(Baraikandi Hat, Rawmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 07/7/22 | N/A | N/A | 08/9/22 | 60 | 30/10/23
Actual
76 | PRO/KURI/MM/2022-23/ W-423 (LCS-1) | Development of Medium Market through LCS Group (Char Rajibpur, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 01/8/22 | N/A | N/A | 02/10/22 | 60 | 02/10/23
Actual
77 | PRO/KURI/MM/2022-23/ W-424 (LCS-2) | Development of Medium Market through LCS Group (Char Rajibpur, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 01/8/22 | N/A | N/A | 02/10/22 | 60 | 02/10/23
Actual
78 | PRO/KURI/MM/2022-23/ W-425 (LCS-1) | Development of Medium Market through LCS Group (Bhurungumari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/8/22 | N/A | N/A | 15/10/22 | 60 | 15/10/23
Actual
79 | PRO/KURI/MM/2022-23/ W-426 (LCS-2) | Development of Medium Market through LCS Group (Bhurungumari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/8/22 | N/A | N/A | 15/10/22 | 60 | 15/10/23
Actual
80 | PRO/KURI/MM/2022-23/ W-427 (LCS-1) | Development of Medium Market through LCS Group (Chilmari, Rawmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/7/22 | N/A | N/A | 29/9/22 | 60 | 29/9/23
Actual
81 | PRO/KURI/MM/2022-23/ W-428 (LCS-2) | Development of Medium Market through LCS Group (Chilmari, Rawmari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/7/22 | N/A | N/A | 29/9/22 | 60 | 29/9/23
Actual
[7 empty] | TOTAL TK: | 41770000
82 | PRO/GAI/MM/2022-23/ W-429 (LCS-1) | Development of Medium Market through LCS Group(Belka Bazar, Sundarganj, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/8/22 | N/A | N/A | 30/10/22 | 60 | 30/10/23
Actual
83 | PRO/GAI/MM/2022-23/ W-430 (LCS-2) | Development of Medium Market through LCS Group(Belka Bazar, Sundarganj, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 30/8/22 | N/A | N/A | 30/10/22 | 60 | 30/10/23
Actual
84 | PRO/GAI/MM/2022-23/ W-431 (LCS-1) | Development of Medium Market through LCS Group (Fulchari, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/9/22 | N/A | N/A | 06/11/22 | 60 | 07/11/23
Actual
85 | PRO/GAI/MM/2022-23/ W-432 (LCS-2) | Development of Medium Market through LCS Group (Fulchari, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 04/9/22 | N/A | N/A | 06/11/22 | 60 | 07/11/23
Actual
86 | PRO/GAI/MM/2022-23/ W-433 (LCS-1) | Development of Medium Market through LCS Group (Sadullahpur, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 08/10/22 | N/A | N/A | 09/12/23 | 60 | 09/12/24
Actual
87 | PRO/GAI/MM/2022-23/ W-434 (LCS-2) | Development of Medium Market through LCS Group (Sadullahpur, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 08/10/22 | N/A | N/A | 09/12/23 | 60 | 09/12/24
Actual
88 | PRO/GAI/MM/2022-23/ W-435 (LCS-1) | Development of Medium Market through LCS Group (Gaibandha Sadar, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 10/11/22 | N/A | N/A | 12/01/23 | 60 | 12/02/24
Actual
89 | PRO/GAI/MM/2022-23/ W-436 (LCS-2) | Development of Medium Market through LCS Group (Gaibandha Sadar, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 10/11/22 | N/A | N/A | 12/01/23 | 60 | 12/02/24
Actual
90 | PRO/GAI/MM/2022-23/ W-437 (LCS-1) | Development of Medium Market through LCS Group (Saghata, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/12/22 | N/A | N/A | 06/2/23 | 60 | 06/2/24
Actual
91 | PRO/GAI/MM/2022-23/ W-438 (LCS-2) | Development of Medium Market through LCS Group (Saghata, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/12/22 | N/A | N/A | 06/2/23 | 60 | 06/2/24
Actual
92 | PRO/GAI/MM/2022-23/ W-439 (LCS-1) | Development of Medium Market through LCS Group (Domer Hat, Sundarganj, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 02/1/23 | N/A | N/A | 05/3/23 | 60 | 06/3/24
Actual
93 | PRO/GAI/MM/2022-23/ W-440 (LCS-2) | Development of Medium Market through LCS Group (Domer Hat, Sundarganj, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 02/1/23 | N/A | N/A | 05/3/23 | 60 | 06/3/24
Actual
94 | PRO/GAI/MM/2022-23/ W-441 (LCS-1) | Development of Medium Market through LCS Group (Moyej Mear Hat,Sundargonj, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 23/12/22 | N/A | N/A | 29/12/22 | 60 | 28/12/23
Actual
95 | PRO/GAI/MM/2022-23/ W-442 (LCS-2) | Development of Medium Market through LCS Group(Moyej Mear Hat,Sundargonj, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 23/12/22 | N/A | N/A | 29/12/22 | 60 | 28/12/23
Actual
96 | PRO/GAI/MM/2022-23/ W-443 (LCS-1) | Development of Medium Market through LCS Group (Gaibandha Sadar, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 02/2/23 | N/A | N/A | 02/4/23 | 60 | 03/04/24
Actual
97 | PRO/GAI/MM/2022-23/ W-444 (LCS-2) | Development of Medium Market through LCS Group (Gaibandha Sadar, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 02/2/23 | N/A | N/A | 02/4/23 | 60 | 03/04/24
Actual
98 | PRO/GAI/MM/2022-23/ W-445 (LCS-1) | Development of Medium Market through LCS Group (Fulchori, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/2/23 | N/A | N/A | 16/4/23 | 60 | 16/4/24
Actual
99 | PRO/GAI/MM/2022-23/ W-446 (LCS-2) | Development of Medium Market through LCS Group (Fulchori, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 15/2/23 | N/A | N/A | 16/4/23 | 60 | 16/4/24
Actual
100 | PRO/GAI/MM/2022-23/ W-447 (LCS-1) | Development of Medium Market through LCS Group (Sadullahpur, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 28/2/23 | N/A | N/A | 27/4/23 | 60 | 28/4/24
Actual
101 | PRO/GAI/MM/2022-23/ W-448 (LCS-2) | Development of Medium Market through LCS Group (Sadullahpur, Gaibandha) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 28/2/23 | N/A | N/A | 27/4/23 | 60 | 28/4/24
Actual
[7 empty] | TOTAL TK: | 41770000
102 | PRO/JAMAL/MM/2022-23/W-449 (LCS-1) | Development of Medium Market through LCS Group(Gazipur Bazar, Melandaha, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/3/23 | N/A | N/A | 04/5/23 | 60 | 06/5/24
[7 empty] | IFAD+GOB |  | Actual
103 | PRO/JAMAL/MM/2022-23/W-450 (LCS-2) | Development of Medium Market through LCS Group(Gazipur Bazar, Melandaha, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2088500 | Plan | N/A | N/A | N/A | 05/3/23 | N/A | N/A | 04/5/23 | 60 | 06/5/24
[7 empty] | IFAD+GOB |  | Actual
104 | PRO/JAMAL/SM/2022-23/ W-451 | Development of Small Village Market through LCS group(Mandapara Bazar, Islampur, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2611000 | Plan | N/A | N/A | N/A | 09/4/23 | N/A | N/A | 08/4/23 | 60 | 08/4/24
|  | Development of Small Village Market through LCS group (Shirajabad Bazar, Islampur, Jamalpur) |  |  |  |  | IFAD+GOB |  | Actual
105 | PRO/JAMAL/SM/2022-23/ W-452 | Development of Small Village Market through LCS group(Sirazabad Bazar, Islampur, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2611000 | Plan | N/A | N/A | N/A | 10/5/23 | N/A | N/A | 06/5/23 | 60 | 07/5/24
|  | Development of Small Village Market through LCS group (Shirajabad Bazar, Islampur, Jamalpur) |  |  |  |  | IFAD+GOB |  | Actual
106 | PRO/JAMAL/SM/2022-23/ W-453 | Development of Small Village Market through LCS group(Merurchar, Baksiganj, Jamalpur) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2611000 | Plan | N/A | N/A | N/A | 10/5/23 | N/A | N/A | 06/5/23 | 60 | 07/5/24
|  | Development of Small Village Market through LCS group (Shirajabad Bazar, Islampur, Jamalpur) |  |  |  |  | IFAD+GOB |  | Actual
[7 empty] | TOTAL TK: | 12010000
107 | PRO/KURI/SM/2022-23/ W-454 | Development of Small Village Market through LCS group (Chander Hat, Nageswari, Kurigram) | nos | 1 | DPM/LCS | HOPE | IFAD+GOB | 2611000 | Plan | N/A | N/A | N/A | 07/7/22 | N/A | N/A | 08/9/22 | 60 | 30/10/23
|  | Development of Small Village Market through LCS group (Shokherhat, Sundorganj, Gaibandha) |  |  |  |  | IFAD+GOB |  | Actual
108 | PRO/KURI/RMP/2022-23/ W-455 | Uttar Kasipur Sen para-Kashem Bazar via Ghogur hat, Fulbari, Kurigram; Road ID: 149185050 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 8/8/22 | 25/8/22 | 31/8/22 | 07/8/22 | 10/9/22 | 77 | 10/9/23
Actual
109 | PRO/KURI/RMP/2022-23/ W-456 | H/O Shajamal- Bokultolabazar via Abder Tale house; Road ID: 149185060 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 21/8/22 | 21/9/22 | 25/9/22 | 29/9/22 | 27/10/22 | 77 | 28/10/23
Actual
110 | PRO/KURI/RMP/2022-23/ W-457 | R&H-Trimohini Shingjhar Rd(St.From Club more); Bhurungamari, Kurigram; Road ID: 149064003 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 21/9/22 | 22/10/22 | 25/10/22 | 31/10/22 | 30/11/22 | 77 | 30/11/23
Actual
111 | PRO/KURI/RMP/2022-23/ W-458 | Ramkhana UP office to Sealkanda bazar, Nageswari, Kurigram; Road ID: 149613039 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 20/10/22 | 06/11/22 | 13/11/22 | 20/11/22 | 20/12/22 | 77 | 20/12/23
Actual
112 | PRO/KURI/RMP/2022-23/ W-459 | Mondir Mouja at H/O Nousher Ali - Khamar GPS, Rajarhat, Kurigram: Road.149775079 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 20/11/22 | 15/12/22 | 22/12/22 | 26/12/22 | 25/1/23 | 77 | 25/1/24
Actual
113 | PRO/KURI/RMP/2022-23/ W-460 | WAPDA Embt. At Chaturvuj Mouja-Makli Mouja at Brammonpara, Rajarhat; Kurigram Road ID: 149775066 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 22/1/23 | 28/2/23 | 05/3/23 | 12/3/23 | 10/4/23 | 77 | 15/4/24
Actual
114 | PRO/KURI/RMP/2022-23/ W-461 | Ramrampur Mosque-hatiar mela WAPDA embk via Fakiepara, Ulipur, Kurigram; Road ID: 149944098 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 26/2/23 | 15/3/23 | 20/3/23 | 23/3/23 | 20/4/23 | 77 | 20/4/24
Actual
115 | PRO/KURI/RMP/2022-23/ W-462 | Kutigram Madrasa pacca Rd-Kachkol CARE bridge via Eblus Chairman house, Chilmari, Kurigram; Road ID: 149095036 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 13/3/23 | 04/4/23 | 09/4/23 | 13/4/23 | 04/5/23 | 77 | 04/5/24
Actual
116 | PRO/KURI/RMP/2022-23/ W-463 | Boalmari modho mosque - hangtapara via Danguapara, Rawmari, Kurigram, Road ID: 149794017 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 04/4/23 | 27/4/23 | 30/4/23 | 01/5/23 | 31/5/23 | 77 | 31/5/24
Actual
[7 empty] | TOTAL TK: | 70111000
117 | PRO/LAL/RMP/2022-23/ W-464 | Applax Badh to Dimla Border road, Hatibandha, Lalmonirhat. Road ID: 152335061 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 16/4/23 | 11/5/23 | 14/5/23 | 18/5/23 | 15/6/23 | 77 | 15/6/24
Actual
118 | PRO/LAL/RMP/2022-23/ W-465 | Singimari Nebru House - Uttor Baraipara Masque, Hatibandha, Lalmonirhat. Road ID:152334090 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 20/4/23 | 16/5/23 | 20/5/23 | 25/5/23 | 22/6/23 | 77 | 22/6/24
Actual
119 | PRO/LAL/RMP/2022-23/ W-466 | Patgram Zila road at kabarstanhat to Lalitarhat Kuchlibari UP, Patgram, Lalmonirhat. Road ID: 152703019 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 01/5/23 | 21/5/23 | 25/5/23 | 31/5/23 | 01/6/23 | 77 | 01/6/24
Actual
120 | PRO/LAL/RMP/2022-23/ W-467 | Nayerhat Mosque to Zero point of Dahagram UP.Patgram, Lalmonirhat. Road ID: 152705059 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 08/5/23 | 30/5/23 | 08/6/23 | 15/6/23 | 15/7/23 | 77 | 16/7/24
Actual
[7 empty] | TOTAL TK: | 30000000
121 | PRO/JAMAL/RMP/2022-23/ W-468 | Chakpara FRB to Sarkerpara FRB via Amkhowa Bazar. Dewanganj, Jamalpur, Road ID: 339154032 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 17/5/23 | 05/6/23 | 08/6/23 | 11/06/23 | 08/7/23 | 77 | 08/7/24
Actual
122 | PRO/JAMAL/RMP/2022-23/ W-469 | Nobbachar Bazar- Taguria h/o Khalek via Hidagari road, Madargonj, Jamalpur. Road ID: 339585035 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 25/5/23 | 25/6/23 | 29/6/23 | 05/7/23 | 05/8/23 | 77 | 05/8/24
Actual
123 | PRO/JAMAL/RMP/2022-23/ W-470 | Gabergram Bazar Embank- Bafatuddin Talukder high school road, Madargonj, Jamalpur. Road ID: 339585030 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 13/3/23 | 04/4/23 | 09/4/23 | 13/4/23 | 04/5/23 | 77 | 04/5/24
Actual
124 | PRO/JAMAL/RMP/2022-23/ W-471 | Battajure Nuton Bazar-Battajore Paschimpara via Shamisaya school road, Bakshigonj, Jamalpur, Road ID: 339075096 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 04/4/23 | 27/4/23 | 30/4/23 | 01/5/23 | 31/5/23 | 77 | 31/5/24
Actual
125 | PRO/JAMAL/RMP/2022-23/ W-472 | Merurchar UP Office - Jabbergonj GC via Chinarchar Gudaraghat road, Bakshigonj, Jamalpur, Road ID: 339073012 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 8/8/22 | 25/8/22 | 31/8/22 | 07/8/22 | 10/9/22 | 77 | 10/9/23
Actual
126 | PRO/JAMAL/RMP/2022-23/ W-473 | Gazirpara-Kamalerbatti road.Bakshigonj, Jamalpur: Road ID:339074011 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 21/8/22 | 21/9/22 | 25/9/22 | 29/9/22 | 27/10/22 | 77 | 28/10/23
Actual
127 | PRO/JAMAL/RMP/2022-23/ W-474 | Nalsia (Khashimara) - Utter Khashimara GPS Road. Melandaa, Jamalpur, Road ID: 339615107 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 21/9/22 | 22/10/22 | 25/10/22 | 31/10/22 | 30/11/22 | 77 | 30/11/23
Actual
128 | PRO/JAMAL/RMP/2022-23/ W-475 | Kangalkursha RHD to Tarakandi bazar UZR Road.Melandaa, Jamalpur, Road ID: 339615037 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 20/10/22 | 06/11/22 | 13/11/22 | 20/11/22 | 20/12/22 | 77 | 20/12/23
Actual
129 | PRO/JAMAL/RMP/2022-23/ W-476 | Khashimara bazar-Purarchar(Shahin Bazar) Road, Melandaa, Jamalpur, Road ID: 339614030 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 20/11/22 | 15/12/22 | 22/12/22 | 26/12/22 | 25/1/23 | 77 | 25/1/24
Actual
130 | PRO/JAMAL/RMP/2022-23/ W-477 | Napiterchar High School -Chandanpur village via Dasani River Ferry Ghat road. Islampur, Jamalpur; Road ID: 339294035 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 22/1/23 | 28/2/23 | 05/3/23 | 12/3/23 | 10/4/23 | 77 | 15/4/24
Actual
131 | PRO/JAMAL/RMP/2022-23/ W-478 | Duttapara R&H to Napiterchar Bazar via Adorsha Gramm road, Islampur, Jamalpur; Road ID: 339294067 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 26/2/23 | 15/3/23 | 20/3/23 | 23/3/23 | 20/4/23 | 77 | 20/4/24
Actual
132 | PRO/JAMAL/RMP/2022-23/ W-479 | Malmara Bazar-Napiterchar Bazar road, Islampur, Jamalpur; Road ID: 339294087 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 13/3/23 | 04/4/23 | 09/4/23 | 13/4/23 | 04/5/23 | 77 | 04/5/24
Actual
[7 empty] | TOTAL TK: | 90000000
133 | PRO/RANG/RMP/2022-23/ W-480 | Jummarpar R&H - Mirbag Gramen Bank More Bazar. Kaunia, Rangpur; Road ID: 185424058 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 04/4/23 | 27/4/23 | 30/4/23 | 01/5/23 | 31/5/23 | 77 | 31/5/24
Actual
[7 empty] | TOTAL TK: | 7500000
134 | PRO/GAI/RMP/2022-23/ W-481 | Pullbandhi Bazar-Ramchandrapur UP office via Boali UP office & Gonirjan Bridge, Gaibandha Sadar, Gaibandha, Road ID: 132243029 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 16/4/23 | 11/5/23 | 14/5/23 | 18/5/23 | 15/6/23 | 77 | 15/6/24
Actual
135 | PRO/GAI/RMP/2022-23/ W-482 | Bhangamore bazar-school bazar- Padumshahor UP, Saghata, Gaibandha, Road ID: 132883015 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 20/4/23 | 16/5/23 | 20/5/23 | 25/5/23 | 22/6/23 | 77 | 22/6/24
Actual
136 | PRO/GAI/RMP/2022-23/ W-483 | Betgari Kachua UZR near Patakhowa more - Sudhuir Master's house road, Gangachara, Rangpur, Road ID: 185275134 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 01/5/23 | 21/5/23 | 25/5/23 | 31/5/23 | 01/6/23 | 77 | 01/6/24
Actual
137 | PRO/GAI/RMP/2022-23/ W-484 | Pullbandhi Bazar-Ramchandrapur UP office via Boali UP office & Gonirjan Bridge, Gaibandha Sadar, Gaibandha, Road ID: 132243029 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 08/5/23 | 30/5/23 | 08/6/23 | 15/6/23 | 15/7/23 | 77 | 16/7/24
Actual
138 | PRO/GAI/RMP/2022-23/ W-485 | Bhangamore bazar-school bazar- Padumshahor UP, Saghata, Gaibanda, Road ID: 132883015 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 17/5/23 | 05/6/23 | 08/6/23 | 11/06/23 | 08/7/23 | 77 | 08/7/24
Actual
139 | PRO/GAI/RMP/2022-23/ W-486 | Dholvanga-Mohipur Bazar, Sadullahpur, Gaibandha; Road ID: 132823015 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 25/5/23 | 25/6/23 | 29/6/23 | 05/7/23 | 05/8/23 | 77 | 05/8/24
Actual
[7 empty] | TOTAL TK: | 45000000
140 | PRO/NIL/RMP/2022-23/ W-487 | Gabroll RNGPS-Tin Babul house via Rath bazer.Jaldhaka, Nilphamari; Road ID: 173365087 | km | 1 | DPM/LCS | HOPE | IFAD+GOB | 7500000 | Plan | N/A | N/A | 13/3/23 | 04/4/23 | 09/4/23 | 13/4/23 | 04/5/23 | 77 | 04/5/24
140 | PRO/NIL/REHAB/2022-23/ W-488 | Naotara U.P Office-Motirbazar, Dimla, Nilfamari; Rd ID: 173123014 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 8/8/22 | 25/8/22 | 31/8/22 | 07/8/22 | 10/9/22 | 77 | 10/9/23
Actual
141 | PRO/NIL/REHAB/2022-23/ W-489 | Tepakharibari U.P. Office-Barnirghat B.O.P. Cam Rd, Dimla, Nilfamari, ID: 173124091 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 21/8/22 | 21/9/22 | 25/9/22 | 29/9/22 | 27/10/22 | 77 | 28/10/23
Actual
[7 empty] | TOTAL TK: | 13100000
142 | PRO/LAL/REHAB/2022-23/ W-490 | Wapda Pacca Road to Thangjhara Dimla Boarder Rd, Hatibandha, Lalmonirhat; ID: 152334015 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 21/9/22 | 22/10/22 | 25/10/22 | 31/10/22 | 30/11/22 | 77 | 30/11/23
Actual
143 | PRO/LAL/REHAB/2022-23/ W-491 | Kamererhat-Sreerampur UP via Dr. hamidul islam house, Patgram, Lalmonirhat; Rd ID: 152703007 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 20/10/22 | 06/11/22 | 13/11/22 | 20/11/22 | 20/12/22 | 77 | 20/12/23
Actual
[7 empty] | TOTAL TK: | 5600000
144 | PRO/KURI/REHAB/2022-23/ W-492 | Burirhat-Gharialdanga UP office, Rajarhar, Kurigram;Rd ID: 149773010 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 20/11/22 | 15/12/22 | 22/12/22 | 26/12/22 | 25/1/23 | 77 | 25/1/24
Actual
145 | PRO/KURI/REHAB/2022-23/ W-493 | Chandamari-Shyom Narayan at Biddyananda rd. Rd, Nageswari, Kurigram; ID: 149774012 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 22/1/23 | 28/2/23 | 05/3/23 | 12/3/23 | 10/4/23 | 77 | 15/4/24
Actual
146 | PRO/KURI/REHAB/2022-23/ W-494 | Mollahat-Panchim side of Mogholbacha UP simana, Ulipur, Kurigram; Rd ID: 149944076 | km | 1 | OTM | HOPE | IFAD+GOB | 2800000 | Plan | N/A | N/A | 26/2/23 | 15/3/23 | 20/3/23 | 23/3/23 | 20/4/23 | 77 | 20/4/24
Actual
[7 empty] | TOTAL TK: | 8400000
147 | PRO/JAMAL/DEWAN/VR/2022-23/ W-495 | Chikajani Up- Charmaguri hat road, Dewanganj, Jamalpur, Road ID: 339153005 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 8/8/22 | 25/8/22 | 31/8/22 | 07/8/22 | 10/9/22 | 77 | 10/9/23
Actual
148 | PRO/JAMAL/DEWAN/VR/2022-23/W-496 | Kharma Naya Bazar RHD-Tilokpur Mollapara, Dewanganj, Jamalpur | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 21/8/22 | 21/9/22 | 25/9/22 | 29/9/22 | 27/10/22 | 77 | 28/10/23
Actual
[7 empty] | TOTAL TK: | 14000000
149 | PRO/GAI/FUL/VR/2022-23/ W-497 | Fulchari UP H/Q-Kalurpara kheya ghat via Parul govt. P/S,Fulchori, Gaibandha; Road ID: 132213011 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 21/9/22 | 22/10/22 | 25/10/22 | 31/10/22 | 30/11/22 | 77 | 30/11/23
Actual
[7 empty] | TOTAL TK: | 7000000
150 | PRO/KURI/KURI-S/VR/ 2022-23/ W-498 | Kawnia Ghat-Kaggipara G.P. School, Kurigram Sadar, Kurigram; Road ID: 149525029 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 20/10/22 | 06/11/22 | 13/11/22 | 20/11/22 | 20/12/22 | 77 | 20/12/23
Actual
151 | PRO/KURI/NAG/VR/2022-23/W-499 | Baparitary-Horibolarkuti via H/O Nur Islam Master, Nageswari, Kurigram; Road ID: 149615081 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 20/11/22 | 15/12/22 | 22/12/22 | 26/12/22 | 25/1/23 | 77 | 25/1/24
Actual
152 | PRO/KURI/ULI/VR/2022-23/W-500 | Mollahat-Panchim side of Mogholbacha UP simana, Ulipur, Kurigram; Road ID: 149944076 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 22/1/23 | 28/2/23 | 05/3/23 | 12/3/23 | 10/4/23 | 77 | 15/4/24
Actual
[7 empty] | TOTAL TK: | 21000000
153 | PRO/JAMAL/IS/VR/2022-23/W-501 | Char Shisua GPS-Changania RNGPS via Degahir road; Islampur, Jamalpur; Road ID: 339295033 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 26/2/23 | 15/3/23 | 20/3/23 | 23/3/23 | 20/4/23 | 77 | 20/4/24
Actual
[7 empty] | TOTAL TK: | 7000000
154 | PRO/GAI/GAI-S/VR/2022-23/W-502 | Salam bazar- Balata bazar via Mouja malibari Eidgah, Gaibandha Sadar,Gaibandha; Road ID: 132245158 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 13/3/23 | 04/4/23 | 09/4/23 | 13/4/23 | 04/5/23 | 77 | 04/5/24
Actual
155 | PRO/GAI/SAG/VR/2022-23/ W-503 | Dighal Kandi- Digholkandi H/O Sonaullah Mirja, Saghata, Gaibandha; Road ID: 132885022 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 04/4/23 | 27/4/23 | 30/4/23 | 01/5/23 | 31/5/23 | 77 | 31/5/24
Actual
156 | PRO/GAI/FUL/VR/2022-23/ W-504 | Fulchari Kheyaghat-Tengrakandi Road, Fulchori, Gaibadha; Road ID: 132214036 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 16/4/23 | 11/5/23 | 14/5/23 | 18/5/23 | 15/6/23 | 77 | 15/6/24
Actual
157 | PRO/GAI/FUL/VR/2022-23/ W-505 | Purba Fulchari Notun Hat - Kheya ghat via Adarsa gram, Fulchori, Gaibandha, Road ID: 132214050 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 20/4/23 | 16/5/23 | 20/5/23 | 25/5/23 | 22/6/23 | 77 | 22/6/24
Actual
158 | PRO/GAI/FUL/VR/2022-23/ W-506 | Pachim Khatiamary H/O Jalal Member-Gucha gram, Fulchori, Gaibandha, Road ID: 132215025 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 01/5/23 | 21/5/23 | 25/5/23 | 31/5/23 | 01/6/23 | 77 | 01/6/24
Actual
159 | PRO/GAI/FUL/VR/2022-23/ W-507 | Uttar khatiamari H/O Moksed- (H/O Jafor) Dhakin khatiamary, Fulchori, Gaibandha, Road ID: 132215037 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 08/5/23 | 30/5/23 | 08/6/23 | 15/6/23 | 15/7/23 | 77 | 16/7/24
Actual
160 | PRO/GAI/SUN/VR/2022-23/ W-508 | Kashem Bazar- Hazari hat, Sundarganj, Gaibandha | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 17/5/23 | 05/6/23 | 08/6/23 | 11/06/23 | 08/7/23 | 77 | 08/7/24
Actual
161 | PRO/GAI/SUN/VR/2022-23/W-509 | Kapashia UP Office to Kashim Bazar- WAPDA Embankment; Sundarganj, Gaibandha; Road ID: 132915058 | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 25/5/23 | 25/6/23 | 29/6/23 | 05/7/23 | 05/8/23 | 77 | 05/8/24
Actual
162 | PRO/GAI/SUN/VR/2022-23/W-510 | Koshim Bazar-Vati Kapasia Nuton Asraon Bazar, Sundarganj, Gaibandha | km | 1 | OTM | HOPE | IFAD+GOB | 7000000 | Plan | N/A | N/A | 13/3/23 | 04/4/23 | 09/4/23 | 13/4/23 | 04/5/23 | 77 | 04/5/24
Actual
[7 empty] | TOTAL TK: | 63000000
163 | PRO/RANG/FS/2022-23/ W-511 | Construction of Three stored school cum flood shelter at Ajam Kha Govt. Primary School, Rangpur | nos | 1 | OTM | HOPE | IFAD+GOB | 25523543 | Plan | N/A | 20/7/22 | 8/8/22 | 25/8/22 | 31/8/22 | 07/8/22 | 10/9/22 | 77 | 10/9/23
Actual
[7 empty] | TOTAL TK: | 25523543
164 | PRO/NIL/FS/2022-23/ W-512 | Construction of Three stored school cum flood shelter at Char Holdibari Govt. Primary School, Nilphamari | nos | 1 | OTM | HOPE | IFAD+GOB | 25523545 | Plan | N/A | 15/7/22 | 21/8/22 | 21/9/22 | 25/9/22 | 29/9/22 | 27/10/22 | 77 | 28/10/23
Actual
165 | PRO/NIL/FS/2022-23/ W-513 | Construction of Three stored school cum flood shelter at Shoulmari Charvorot Govt. Primary School, Nilphamari | nos | 1 | OTM | HOPE | IFAD+GOB | 25523546 | Plan | N/A | 15/8/22 | 21/9/22 | 22/10/22 | 25/10/22 | 31/10/22 | 30/11/22 | 77 | 30/11/23
Actual
166 | PRO/NIL/FS/2022-23/ W-514 | Construction of Three stored school cum flood shelter at Tapkharibari 1 Govt. Primary School, Nilphamari | nos | 1 | OTM | HOPE | IFAD+GOB | 25523547 | Plan | N/A | 30/9/22 | 20/10/22 | 06/11/22 | 13/11/22 | 20/11/22 | 20/12/22 | 77 | 20/12/23
Actual
167 | PRO/NIL/FS/2022-23/ W-515 | Construction of Three stored school cum flood shelter at Jotindra Naraya Govt. Primary School, Nilphamari | nos | 1 | OTM | HOPE | IFAD+GOB | 25523548 | Plan | N/A | 15/10/22 | 20/11/22 | 15/12/22 | 22/12/22 | 26/12/22 | 25/1/23 | 77 | 25/1/24
Actual
[7 empty] | TOTAL TK: | 102094186
168 | PRO/GAI/FS/2022-23/W-516 | Construction of Three stored school cum flood shelter at Sayedpur Govt. Primary School, Gaibandha | nos | 1 | OTM | HOPE | IFAD+GOB | 25523549 | Plan | N/A | 01/1/23 | 22/1/23 | 28/2/23 | 05/3/23 | 12/3/23 | 10/4/23 | 77 | 15/4/24
Actual
169 | PRO/GAI/FS/2022-23/ W-517 | Construction of Three stored school cum flood shelter at Chinirpol Govt. Primary School, Gaibandha | nos | 1 | OTM | HOPE | IFAD+GOB | 25523550 | Plan | N/A | 05/2/23 | 26/2/23 | 15/3/23 | 20/3/23 | 23/3/23 | 20/4/23 | 77 | 20/4/24
Actual
[7 empty] | TOTAL TK: | 51047099
Total Estimated Cost | [7 empty] | 783373828

## District Distribution of Works
Promoting Resilience of Vulnerable Through Access to Infrastructure, Improved Skills and Information (PROVATi³) Local Government Engineering Department
Sl | Procurement Particulars | Districts Wise Procurement | [11 empty] | Total Estimated Cost of Markets (District wise) | Remarks
|  | Nilfamari |  | Kurigram |  | Jamalpur |  | Lalmonirhat |  | Gaibandha |  | Rangpur
1 | Market | Nos of Package | Estimated Cost | Nos of Package | Estimated Cost | Nos of Package | Estimated Cost | Nos of Package | Estimated Cost | Nos of Package | Estimated Cost | Nos of Package | Estimated Cost
(i) | Large | 6 | 12540000 | 12 | 25080000 | 15 | 31350000 | 0 |  | 0 |  |  |  | 225609000
(ii) | Medium | 16 | 33416000 | 20 | 41770000 | 2 | 4177000 | 6 | 12531000 | 20 | 41770000 | 6 | 12531000
(iii) | Small | 0 |  | 1 | 2611000 | 3 | 7833000 | 0 |  | 0
Total |  | 22 | 45956000 | 33 | 69461000 | 20 | 43360000 | 6 | 12531000 | 20 | 41770000 | 6 | 12531000
2 | Road Maintenance [LCS] | 1 | 7500000 | 9 | 67500000 | 12 | 90000000 | 4 | 30000000 | 4 | 30000000 | 1 | 7500000 | 232500000
3 | Road Improvement (VR) |  |  | 3 | 21000000 | 3 | 21000000 |  |  | 9 | 63000000 | 1 | 7000000 | 112000000
4 | Road Rehablitation | 2 | 5600000 | 3 | 8400000 |  |  | 2 | 5600000 |  |  |  |  | 19600000
5 | Flood Shelter | 4 | 102094186 | [6 empty] | 2 | 51047099 | 8 | 25523543 | 178664828
Grand Total of Districtwise Works Procurement |  | 29 | 161150186 | 48 | 166361000 | 35 | 154360000 | 12 | 48131000 | 35 | 185817099 | 16 | 52554543
Total Estimated Cost of Works Procurement for PROVATI³ Project | [13 empty] | 768373828

## Goods
Promoting Resilience of Vulnerable Through Access to Infrastructure, Improved Skills and Information (PROVATi³) Project Local Government Engineering Department
ANNUAL PROCURMENT PLAN FOR 2022-2023
(G O O D S)
Sl No | Contract Package No | 0 | Unit | Quantity | Procurement Method | Contract Approving Autority | Source of Fund | Estimated Cost [in Lakh] | Time Code for Process | Invite/Advirtise Qualification | Tender Opening | Tender Evaluation | Notification of Award | Signing of Contract | Total Time to Contract Signature [days] | Time for Completion of Contract
1 | PRO/PMU/VH/2022-23/G-91 | Service Motor Vehicles for PMUs | nos | 2 | DPM | HOPE | IFAD+GOB | 10000000 | Planned Dates | N/A | N/A | 18/12/22 | 01/1/23 | 01/2/23 | 60 | 01/3/23
Actual Dates
2 | PRO/PMU/EQ/2022-23/G-92 | Air Conditoners | nos | 2 | RFQ | HOPE | IFAD+GOB | 500000 | Planned Dates | 03/1/22 | 13/11/22 | 17/11/22 | 20/11/22 | 20/11/22 | 30 | 3011/22
Actual Dates
3 | PRO/PMU/EQ/2022-23/G-93 | Photocopiers and Scanner | nos | 6 | RFQ | HOPE | IFAD+GOB | 500000 | Planned Dates | 01/1/22 | 10/11/22 | 15/11/22 | 17/11/22 | 17/11/22 | 20 | 28/11/22
Actual Dates
4 | PRO/PMU/EQ/2022-23/G-94 | Multimedia Projector | nos | 2 | RFQ | HOPE | IFAD+GOB | 500000 | Planned Dates | 01/1/22 | 10/02/23 | 15/02/23 | 17/02/23 | 17/02/23 | 20 | 01/03/23
Actual Dates
5 | PRO/PMU/EQ/2022-23/G-95 | Procurement of Tab/tablet Device for Outcome or other Impact Study for PROVATi³ | set | 30 | RFQ | HOPE | IFAD+GOB | 1000000 | Planned Dates | 05/1/22 | 15/11/22 | 17/11/22 | 20/11/22 | 20/11/22 | 20 | 3011/22
Actual Dates
6 | PRO/PMU/STATIONARY/2022-23/G-96 | Office Stationary for PMU | nos | 80 | OTM | HOPE | IFAD+GOB | 7000000 | Planned Dates | 07/12/22 | 22/12/22 | 30/12/22 | 01/1/23 | 01/1/23 | 45 | 15/2/23
Actual Dates
7 | PRO/PMU/EQ/2022-23/G-97 | Office Arrangement for Equipment | nos | 2 | RFQ | HOPE | IFAD+GOB | 500000 | Planned Dates | 03/1/22 | 13/11/22 | 17/11/22 | 20/11/22 | 20/11/22 | 20 | 30/11/22
Actual Dates
Total Estimated Cost | [7 empty] | 20000000

## Service
Promoting Resilience of Vulnerable Through Access to Infrastructure, Improved Skills and Information (PROVATi³) Project Local Government Engineering Department
ANNUAL PROCURMENT PLAN FOR 2022-2023
(S E R V I C E )
Sl No | Package No/Course Code | Description/ Course Title | Unit | Quantity | Procurement Method | Contract Approving Authority | Source of Fund | Estimated Cost | Time Code for Process | Advirtise EOI | Issue RFP | Proposal Opening | Proposal Evaluation | Opening Financial Proposal | Negotiation | Approval | Signing of Contract | Total Time of Contract Signature [days] | Time for Completion of Contract
1 | PRO/PMU/CON/2022-23/SE-12 | TA Personnel for PMU (Financial Management Specialist) [R] | PM | 1 | ICS | HOPE | IFAD+GOB | 6000000 | Plan | 13/11/22 | N/A | 28/11/22 | 2022-08-12 | 15/12/22 | N/A | N/A | 2023-01-01 | 45 | 31/12/25
Actual
2 | PRO/PMU/SIC/2021-22/SE-25 | TA Personnel for PMU (DTL cum Design Engineer) | PM | 1 | ICS | HOPE | IFAD+GOB | 6000000 | Plan | 1/9/22 | N/A | 15/9/22 | 22/9/22 | 29/9/22 | N/A | N/A | 02/10/22 | 45 | 31/10/24
Actual
3 | PRO/PMU/SIC/2021-22/SE-21 | TA Personnel for PMU (Market & Road Supervision Engineer) | PM | 1 | ICS | HOPE | IFAD+GOB | 3000000 | Plan | 1/9/22 | N/A | 15/9/22 | 22/9/22 | 29/9/22 | N/A | N/A | 02/10/22 | 45 | 31/10/24
Actual
4 | PRO/PMU/CON/2022-23/SE-11 | TA Personnel for PIU Monitoring and Livelihood Officers 01 nos | PM | 1 | ICS | HOPE | IFAD+GOB | 1600800 | Plan | 1/11/22 | N/A | 15/11/22 | 17/11/22 | 30/11/22 | N/A | N/A | 10/12/22 | 45 | 30/11/24
Actual
5 | PRO/PMU/Rang/VT/2022-23/SE-26 | Engagement of NGO/Consulting Firm for Implementing vocational skills training and job placement for 1500 person of Rangpur Region (Selected 11 nos. Upazilas of Rangpur, Lalmonirhat, Gaibandha & Nilphamari | nos | 1 | QCBS | HOPE | IFAD+GOB | 44497159.09 | Plan | 15/08/22 | 02/09/22 | 06/10/22 | 20/10/22 | 23/10/22 | 26/10/22 | 30/10/22 | 01/11/22 | 80 | 31/10/23
Actual
6 | PRO/PMU/Kuri/VT/2022-23/SE-27 | Engagement of NGO/MFI/Service Provider Firm for Implementing vocational skills training and job placement for 1400 person of Kurigram Region (Selected 09 nos. Upazilas of Kurigram | nos | 1 | QCBS | HOPE | IFAD+GOB | 41530681.82 | Plan | 15/09/22 | 02/10/22 | 03/11/22 | 15/11/22 | 17/11/22 | 21/11/22 | 23/11/22 | 27/11/22 | 80 | 31/12/23
Actual
7 | PRO/PMU/Jamal/VT/2022-23/SE-28 | Engagement of NGO/Consulting Firm for Implementing vocational skills training and job placement for 1275 person of Jamalpur Region (Selected 05 nos. Upazilas of Jamalpur | nos | 1 | QCBS | HOPE | IFAD+GOB | 37822585.23 | Plan | 15/10/22 | 01/11/22 | 01/12/22 | 22/12/22 | 26/12/22 | 28/12/22 | 29/12/22 | 01/01/23 | 80 | 31/01/24
Actual
8 | PRO/PMU/OS/2022-23/SE-29 | Outcome Survey/Impact Study of PROVATi³ Project | event | 1 | SSS | HOPE | IFAD+GOB | 500000 | Plan | N/A | 15/07/22 | N/A | N/A | N/A | 30/07/22 | 30/07/22 | 01/08/22 | 15 | 15/11/23
Actual
9 | PRO/PMU/SE/TR/2022-23/SE-30 | Training for Staff Engineers | PM | 90 | N/A | HOPE | IFAD+GOB | 2934000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 31/01/23
Actual
10 | PRO/PMU/FND/TR/2022-23/SE-31 | Foundation Course | PM | 40 | N/A | HOPE | IFAD+GOB | 5950000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/10/22
Actual
11 | PRO/PMU/GALS/TR/2022-23/SE-32 | Training Model of LCS (Vision Excersise) | PM | 6000 | N/A | HOPE | IFAD+GOB | 18000000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
12 | PRO/PMU/GALS/TR/2022-23/SE-33 | Training Model of LCS (IGA) | PM | 3300 | N/A | HOPE | IFAD+GOB | 9900000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
13 | PRO/PMU/GALS/TR/2022-23/SE-34 | Training Model of LCS (Financial Management & Followup) | PM | 3000 | N/A | HOPE | IFAD+GOB | 9000000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
14 | PRO/PMU/GALS/TR/2022-23/SE-35 | Training on Household Vision & Action Plan | PM | 600 | N/A | HOPE | IFAD+GOB | 1800000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
15 | PRO/PMU/GALS/TR/2022-23/SE-36 | Training on Business Plan of LCS | PM | 300 | N/A | HOPE | IFAD+GOB | 900000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
16 | PRO/PMU/GALS/TR/2022-23/SE-37 | Training on Financial Inclusion and Followup | PM | 600 | N/A | HOPE | IFAD+GOB | 900000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
17 | PRO/PMU/GALS/TR/2022-23/SE-38 | Knowledge Exchange Visit | PM | 60 | N/A | HOPE | IFAD+GOB | 400000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 31/12/22
Actual
18 | PRO/PMU/RM/TR/2022-23/SE-39 | Road maintainance by LCS | PM | 250 | N/A | HOPE | IFAD+GOB | 473000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
19 | PRO/PMU/LCS/TR/2022-23/SE-40 | Market Development by LCS (Large Market) | PM | 150 | N/A | HOPE | IFAD+GOB | 210000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
20 | PRO/PMU/LCS/TR/2022-23/SE-41 | Market Development by LCS (Medium Market) | PM | 500 | N/A | HOPE | IFAD+GOB | 700000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
21 | PRO/PMU/LCS/TR/2022-23/SE-42 | Market Development by LCS (Small Market) | PM | 100 | N/A | HOPE | IFAD+GOB | 1400000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/6/23
Actual
22 | PRO/PMU/NLS/TR/2022-23/SE-43 | Training on flood early warning for national level stakeholders (DDM, BWDB, FFWC, DAE etc) | PM | 20 | N/A | HOPE | IFAD+GOB | 100000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/06/23
Actual
23 | PRO/PMU/EWS/TR/2022-23/SE-44 | Training on early warning systems to District, Upazila and union DMC Members | PM | 225 | N/A | HOPE | IFAD+GOB | 600000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/03/23
Actual
24 | PRO/PMU/EWN/TR/2022-23/SE-45 | Training on flood early warning for national level stakeholders (DDM, BWDB, FFWC, DAE etc) | PM | 20 | N/A | HOPE | IFAD+GOB | 95000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/06/23
Actual
25 | PRO/PMU/ToT/TR/2022-23/SE-46 | ToT on IGA | PM | 25 | N/A | HOPE | IFAD+GOB | 500000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/8/23
Actual
26 | PRO/PMU/VT/TR/2022-23/SE-47 | Vocational Training | PM | 4000 | N/A | HOPE | IFAD+GOB | 49000000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/06/23
Actual
27 | PRO/PMU/PPD/TR/2022-23/SE-48 | Trainining on Planning for Pheriphery Demarcation | PM | 90 | N/A | HOPE | IFAD+GOB | 100000 | Plan | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 30/06/23
Actual
28 | PRO/PMU/OR/TR/2022-23/SE-49 | Overseas Training for PMU | nos | 2 | SSS | HOPE | IFAD+GOB | 20000000 | Plan | N/A | [8 empty] | 26/06/23
[9 empty] | Actual | N/A
Total Estimated Cost | [7 empty] | 263913226.14