**PROCUREMENT PLAN**

**Basic Data**65F

|  |  |
| --- | --- |
| **Project Name**: Coastal Towns Climate Resilience Project | |
| **Project Number:** 55201-001 | **Approval Number: 55201-001** |
| **Country:** Bangladesh  **Loan Number:** -4237/4238BAN  **Grant:** 0858 BAN | **Executing Agency**: Local Government Engineering Department (LGED) |
| **Project Procurement Risk Classification:**  High  **Project Procurement Risk:** Medium | **Implementing Agency**: Project *Pourashavas* |
| **Project Financing Amount:** US$ 310 million  **ADB Financing:** US$ 250 million  **Cofinancing (ADB Administered):** Nil  **Non-ADB Financing (Government Source):** US$ 60 million | **Project Closing Date:** 30 June 2029 |
| **Date of First Procurement Plan:** 1 Nov 2021 | **Date of this Procurement Plan**: 30 May 2023 |
| **Procurement Plan Duration (in months):** 18 | **Related to COVID-19 response efforts**: No |
| **Advance Contracting:** Yes | **e-GP:** Yes |

1. **Methods, Thresholds, Review and 18-Month Procurement Plan**
2. **Procurement and Consulting Methods and Thresholds**

Except as the Asian Development Bank (ADB) may otherwise agree, the following process thresholds shall apply to procurement of goods and works.

|  |  |
| --- | --- |
| **Procurement of Goods and Works** | |
| **Method** | **Comments** |
| Open Competitive Bidding (OCB) for Goods | OCB (International), Prior review. OCB (National), Prior review |
| Request for Quotation for Goods | Prior/Post Review |
| Open Competitive Bidding (OCB) for Works | OCB (International), Prior Review. OCB (National): Prior/Post Review |
| Direct Contracting (added) | Prior/Post Review |
| **Consulting Services** | |
| **Method** | **Comments** |
| Quality- and Cost-Based Selection (QCBS) for Consulting Firm | Open Competitive Bidding (QCBS 80:20)  S-01, S-02, S-03, S-04, and S-06 |
| Single Source Selection (SSS) | S-05 |

1. **Goods and Works Contracts Estimated to at Cost $1 Million or More.**

The following table lists goods and works contracts for which the procurement activity is either ongoing or expected to commence within the next 18 months.

| **Works / Goods** | **Package**  **Number** | **General Description** | **Estima-ted Value (USD million)**66F**[[1]](#footnote-1)** | | **Procurement Method** | **Review**  (Prior/Prior) | **Bidding Proce-dure** | **Adver-tise-ment Date**  (quarter/year) | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Bakergang *Pourashava*** | | |  | |  |  |  |  |  |
| W-01 | e-GP/ CTCRP/BAKR/RD-01 | Construction and Improvement of Roads under Bakerganj *Pourashava,* District- Barishal | 1.67 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-02 | e-GP/ CTCRP/BAKR/RD-02 | Construction and Improvement Roads under Bakerganj *Pourashava,* District- Barishal | 1.73 | | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-03 | e-GP/ CTCRP/BAKR/RD-03 | Construction and Improvement of Roads under Bakerganj *Pourashava,* District- Barishal | 1.54 | | OCB | Post | 1S-1E | Q2/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-04 | e-GP/ CTCRP/BAKR/DR-01 | Construction and Improvement of Drains under Bakerganj Paurashava, District- Barisal | 1.74 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-05 | e-GP/CTCRP/BAKR/OS-01 | Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc.) | 1.04 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: e-GP |
| **Mehendiganj Pourashava** | | |  | |  |  |  |  |  |
| W-06 | e-GP/CTCRP/MEHN/RD-01 | Construction and Improvement of Roads under Mehendiganj Pourashava, District- Barisal. | 2.28 | | OCB | Prior | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-07 | e-GP/CTCRP/MEHN/RD-02 | Construction and Improvement of Roads under Mehendiganj Pourashava, District- Barisal. | 2.10 | | OCB | Post | 1S-1E | Q4/2023  Changed to Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-08 | e-GP/CTCRP/MEHN/DR-01 | Construction and Improvement of Drains under Mehendiganj Pourashava, District- Barisal. | 1.79 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-09 | e-GP/CTCRP/MEHN/DR-02 | Construction and Improvement of Drains under Mehendiganj Pourashava, District- Barisal. | 1.70 | | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: e-GP |
| **Banaripara Pourashava** | | |  | |  |  |  |  |  |
| W-10 | e-GP/CTCRP/BANR/RD-01 | Construction and Improvement of Roads under Banaripara Paurashava, District- Barisal | 2.12 | | OCB | Prior | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-11 | e-GP/CTCRP/BANR/RD-02 | Construction and Improvement of Roads under Banaripara Paurashava, District- Barisal | 2.04 | | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-12 | e-GP/CTCRP/BANR/DR-01 | Construction and Improvement of Drains under Banaripara Paurashava, District- Barisal | 1.03 | | OCB | Prior | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-13 | e-GP/CTCRP/BANR/BR-01 | Construction of Bridge under Banaripara Paurashava, District- Barisal. | 1.12 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Muladi Pourashava** | | |  | |  |  |  |  |  |
| W-14 | e-GP/CTCRP/MULA/RD-01 | Construction and Improvement of Roads under Muladi Paurashava, District- Barisal | 2.01 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-15 | e-GP/CTCRP/MULA/RD-02 | Construction and Improvement of Roads under Muladi Paurashava, District- Barisal | 1.42 | | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-16 | e-GP/CTCRP/MULA/DR-01 | Construction and Improvement of Drains under Muladi Paurashava, District- Barisal. | 1.86 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Gouranadi Pourashava** | | |  | |  |  |  |  |  |
| W-17 | e-GP/CTCRP/GOUR/RD-01 | Construction and Improvement of Roads under Gouranadi Paurashava, District- Barisal | 1.99 | | OCB | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-18 | e-GP/CTCRP/GOUR/DR-01 | Construction and Improvement of Drains under Gouranadi Paurashava, District- Barisal. | 1.80 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-19 | e-GP/CTCRP/GOUR/DR-02 | Construction and Improvement of Drains under Gouranadi Paurashava, District- Barisal. | 1.82 | | OCB | Post | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-20 | e-GP/CTCRP/GOUR/DR-03 | Construction and Improvement of Drains under Gouranadi Paurashava, District- Barisal. | 1.90 | | OCB | Post | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Bagerhat Paurashava** | | |  | |  |  |  |  |  |
| W-21 | e-GP/CTCRP/BAGR/RD-01 | Construction and Improvement of Roads under Bagerhat Pourashava, District- Bagerhat | 1.74 | | OCB | Prior | 1S-1E | Q3/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-22 | e-GP/CTCRP/BAGR/RD-02 | Construction and Improvement of Roads under Bagerhat Pourashava, District- Bagerhat | 1.11 | | OCB | Post | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-23 | e-GP/CTCRP/BAGR/DR-01 | Construction of RCC Drains under Bagerhat Pourashava, District- Bagerhat | 2.07 | | OCB | Prior | 1S-1E | Q2/2023  Changed to  Q2/2024 | Advertising: National  No. Of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-24 | e-GP/CTCRP/BAGR/SWM-01 | Improvement of Solid Waste Management Facilities under Bagerhat Paurashava, District- Bagerhat. | 2.91 | | OCB | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-25 | e-GP/CTCRP/BAGR/BT-01 | Construction of Bus Terminal under Bagerhat Paurashava, District- Bagerhat. | 2.22 | | OCB | Prior | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Morrelgonj Paurashava** | | |  | |  |  |  |  |  |
| W-26 | e-GP/ CTCRP/MORL/RD-01 | Construction and Improvement of Roads under Morrelganj Paurashava, District- Bagerhat | 1.53 | | OCB | Prior | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-27 | e-GP/ CTCRP/MORL/RD-02 | Construction and Improvement of Roads under Morrelganj Paurashava, District- Bagerhat | 1.75 | | OCB | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-28 | e-GP/ CTCRP/MORL/RD-03 | Construction and Improvement of Roads under Morrelganj Paurashava, District- Bagerhat | 1.73 | | OCB | Post | 1S-1E | Q4/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-29 | e-GP/ CTCRP/MORL/RD-04 | Construction and Improvement of Roads under Morrelganj Paurashava, District- Bagerhat | 1.08 | | OCB | Post | 1S-1E | Q4/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-30 | e-GP/CTCRP/MORL/BT-01 | Construction of Bus Terminal Morrelganj Paurashava, District- Bagerhat. | 1.16 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Charfassion Pourashava** | | |  | |  |  |  |  |  |
| W-31 | e-GP/ CTCRP/CHAR/RD-01 | Construction and Improvement of Roads under Charfassion Paurashava, District- Bhola. | 1.12 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-32 | e-GP/ CTCRP/CHAR/RD-02 | Construction and Improvement of Roads under Charfassion Paurashava, District- Bhola. | 1.52 | | OCB | Post | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-33 | e-GP/ CTCRP/CHAR/ RD-03 | Construction and Improvement of Roads under Charfassion Paurashava, District- Bhola. | 1.61 | | OCB | Post | 1S-1E | Q3/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-34 | e-GP/ CTCRP/CHAR/ DR-01 | Construction and Improvement of Drains under Charfassion Paurashava, District- Bhola. | 1.98 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-35 | e-GP/ CTCRP/CHAR/ DR-02 | Construction and Improvement of Drains under Charfassion Paurashava, District- Bhola. | 1.23 | | OCB | Post | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Lalmohan Pourashava** | | |  | |  |  |  |  |  |
| W-36 | e-GP/CTCRP/LALM/RD-01 | Construction and Improvement of Roads under Lalmohan Paurashava, District- Bhola. | 1.17 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-37 | e-GP/CTCRP/LALM/RD-02 | Construction and Improvement of Roads under Lalmohan Pourashava, District- Bhola. | 1.18 | | OCB | Post | 1S-1E | Q3/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-38 | e-GP/CTCRP/LALM/DR-01 | Construction and Improvement of Drains under Lalmohan Paurashava, District- Bhola. | 1.49 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-39 | e-GP/CTCRP/LALM/DR-02 | Construction and Improvement of Drains under Lalmohan Paurashava, District- Bhola. | 1.11 | | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Borhanuddin Paurashava** | | |  | |  |  |  |  |  |
| W-40 | e-GP/CTCRP/BORH/RD-01 | Construction and Improvement of Roads under Borhanuddin Pourashava, District- Bhola | 1.71 | | OCB | Prior | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-41 | e-GP/CTCRP/BORH/DR-01 | Construction and Improvement of Drains under Borhanuddin Paurashava, District- Bhola. | 1.98 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-42 | e-GP/CTCRP/BORH/DR-02 | Construction and Improvement of Drains under Borhanuddin Paurashava, District- Bhola. | 1.19 | | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Patharghata Pourashava** | | |  | |  |  |  |  |  |
| W-43 | e-GP/ CTCRP/PATH/RD-01 | Construction and Improvement of Roads under Patharghata Pourashava, District- Barguna. | 2.26 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-44 | e-GP/ CTCRP/PATH/RD-02 | Construction and Improvement of Roads under Patharghata Pourashava, District- Barguna. | 1.94 | | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-45 | e-GP/ CTCRP/PATH/DR-01 | Construction and Improvement of RCC Drains under Patharghata Paurashava, District- Barguna. | 2.12 | | OCB | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Betagi Pourashava** | | |  | |  |  |  |  |  |
| W-46 | e-GP/CTCRP/BETA/RD-01 | Construction and Improvement of Roads under Betagi Pourashava, District- Barguna. | 2.00 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-47 | e-GP/CTCRP/BETA/DR-01 | Construction and Improvement of Drains under Betagi Paurashava, District- Barguna. | 1.52 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-48 | e-GP/CTCRP/BETA/BR-01 | Construction of Bridge under Betagi Paurashava, District- Barguna. | 1.22 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Jhalokathi Pourashava** | | |  | |  |  |  |  |  |
| W-49 | e-GP/CTCRP/JHAL/RD-01 | Construction and Improvement of Roads under Jhalokathi Pourashava, District- Jhalokathi . | 1.63 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-50 | e-GP/CTCRP/JHAL/RD-02 | Construction and Improvement of Roads under Jhalokathi Pourashava, District- Jhalokathi . | 1.85 | | OCB | Post | 1S-1E | Q2/2023  Changed to  Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-51 | e-GP/CTCRP/JHAL/RD-03 | Construction and Improvement of Roads under Jhalokathi Pourashava, District- Jhalokathi. | 1.65 | | OCB | Post | 1S-1E | Q3/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-52 | e-GP/CTCRP/JHAL/DR-01 | Construction and Improvement RCC Drains under Jhalokathi Pourashava, District- Jhalokathi. | 1.73 | | OCB | Prior | 1S-1E | Q2/2024  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-53 | e-GP/CTCRP/JHAL/SWM-01 | Improvement of Solid Waste Management Facilities under Jhalokathi Pourashava, District- Jhalokathi | 2.33 | | OCB | Prior | 1S-1E | Q1/2025 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-54 | e-GP/CTCRP/JHAL/BT-01 | Construction of Bus Terminal under Jhalokathi Pourashava, District- Jhalokathi | 2.33 | | OCB | Prior | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Nalchity Pourashava** | | |  | |  |  |  |  |  |
| W-55 | e-GP/ CTCRP/NALC/RD-01 | Construction and Improvement of Roads under Nalchity Pourashava, District- Jhalokathi. | 1.32 | | OCB | Prior | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-56 | e-GP/ CTCRP/NALC/RD-02 | Construction and Improvement of Roads under Nalchity Pourashava, District- Jhalokathi. | 1.40 | | OCB | Post | 1S-1E | Q4/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-57 | e-GP/ CTCRP/NALC/RD-03 | Construction and Improvement of Roads under Nalchity Pourashava, District- Jhalokathi. | 1.58 | | OCB | Post | 1S-1E | Q4/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-58 | e-GP/ CTCRP/NALC/DR-01 | Construction and Improvement of Drains under Nalchity Pourashava, District- Jhalokathi. | 1.38 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-59 | e-GP/ CTCRP/NALC/DR-02 | Construction and Improvement of Drains under Nalchity Pourashava, District- Jhalokathi. | 1.09 | | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-60 | e-GP/ CTCRP/NALC/BR-01 | Construction of Bridge under Nalchity Pourashava, District- Jhalokathi | 1.01 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Paikgacha Pourashava** | | |  | |  |  |  |  |  |
| W-61 | e-GP/ CTCRP/PAIK/RD-01 | Construction and Improvement of Roads under Paikgacha Pourashava, District- Khulna | 1.57 | | OCB | Prior | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-62 | e-GP/ CTCRP/PAIK/DR-01 | Construction and Improvement of Drains under Paikgacha Pourashava, District- Khulna | 1.72 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-63 | e-GP/ CTCRP/PAIK/DR-02 | Construction and Improvement of Drains under Paikgacha Pourashava, District- Khulna | 1.78 | | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Chalna Pourashava** | | |  | |  |  |  |  |  |
| W-64 | e-GP/CTCRP/CHAL/RD-01 | Construction and Improvement of Roads under Chalna Pourashava, District- Khulna | 2.14 | | OCB | Prior | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-65 | e-GP/CTCRP/CHAL/RD-02 | Construction and Improvement of Roads under Chalna Pourashava, District- Khulna | 1.07 | | OCB | Post | 1S-1E | Q3/2023  CHANGED TO Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Patuakhali Pourashava** | | |  | |  |  |  |  |  |
| W-66 | e-GP/ CTCRP/PATU/RD-01 | Construction and Improvement of Roads under Patuakhali Pourashava, District- Patuakhali. | 1.26 | | OCB | Prior | 1S-1E | Q2/2023  Changed to  Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-67 | e-GP/ CTCRP/PATU/RD-02 | Construction and Improvement of Roads under Patuakhali Paurashava, District- Patuakhali. | 1.91 | | OCB | Post | 1S-1E | Q2/2023  Changed to  Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-68 | e-GP/ CTCRP/PATU/RD-03 | Construction and Improvement of Roads under Patuakhali Paurashava, District- Patuakhali. | 1.82 | | OCB | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-69 | e-GP/CTCRP/PATU/DR-01 | Construction of RCC Drains under Patuakhali Pourashava, District- Patuakhali. | 1.85 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-70 | e-GP/CTCRP/PATU/DR-02 | Construction of RCC Drains under Patuakhali Pourashava, District- Patuakhali. | 1.91 | | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-71 | e-GP/CTCRP/PATU/DR-03 | Construction of Drains under Patuakhali Pourashava, District- Patuakhali. | 1.78 | | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-72 | e-GP/CTCRP/PATU/SWM-01 | Improvement of Solid Waste Management Facilities under Patuakhali Pourashava, District- Patuakhali. | 2.91 | | OCB | Prior | 1S-1E | Q2/2024  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-73 | e-GP/CTCRP/PATU/BT-02 | Construction of Bus Terminal under Patuakhali Pourashava, District- Patuakhali. | 2.72 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Kuakata Pourashava** | | |  | |  |  |  |  |  |
| W-74 | e-GP/CTCRP/KUAK/RD-01 | Construction and Improvement of Roads under Kuakata Pourashava, District- Patuakhali. | 1.41 | | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-75 | e-GP/CTCRP/KUAK/RD-02 | Construction and Improvement of Roads under Kuakata Pourashava, District- Patuakhali. | 1.18 | | OCB | Post | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-76 | e-GP/CTCRP/KUAK/DR-01 | Construction and Improvement of Drains under Kuakata Pourashava, District- Patuakhali. | 1.48 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-77 | e-GP/CTCRP/KUAK/SWM-01 | Improvement of Solid Waste Management Facilities under Kuakata Pourashava, District- Patuakhali. | 1.74 | | OCB | Prior | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Swarupkathi Pourashava** | | |  | |  |  |  |  |  |
| W-78 | e-GP/CTCRP/SWAR/RD-01 | Construction and Improvement of Roads under Swarupkathi Pourashava, District- Pirojpur. | 1.86 | | OCB | Prior | 1S-1E | Q3/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-79 | e-GP/CTCRP/SWAR/RD-02 | Construction and Improvement of Roads under Swarupkathi Pourashava, District- Pirojpur. | 2.26 | | OCB | Post | 1S-1E | Q3/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-80 | e-GP/CTCRP/SWAR/DR-01 | Construction and Improvement of Drains under Swarupkathi Pourashava, District- Pirojpur. | 2.20 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Jajira Pourashava** | | |  | |  |  |  |  |  |
| W-81 | e-GP/CTCRP/JAJI/RD-01 | Construction and Improvement of Roads under Jajira Pourashava, District- Shariatpur | 2.08 | | OCB | Prior | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-82 | e-GP/CTCRP/JAJI/RD-02 | Construction and Improvement of Roads under Jajira Pourashava, District- Shariatpur | 2.11 | | OCB | Post | 1S-1E | Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-83 | e-GP/CTCRP/JAJI/DR-01 | Construction and Improvement of Drains under Jajira Pourashava, District- Shariatpur. | 2.10 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Bhederganj Pourashava** | | |  | |  |  |  |  |  |
| W-84 | e-GP/ CTCRP/BHED/RD-01 | Construction/Improvement of Roads under Bhederganj Pourashava, District- Shariatpur. | 1.22 | | OCB | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-85 | e-GP/ CTCRP/BHED/RD-02 | Construction and Improvement of Roads under Bhederganj Pourashava, District- Shariatpur. | 1.24 | | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-86 | e-GP/ CTCRP/BHED/DR-01 | Construction and Improvement of Drains under Bhederganj Pourashava, District- Shariatpur. | 1.46 | | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-87 | e-GP/ CTCRP/BHED/BR-01 | Construction of RCC Bridges under Bhederganj Pourashava, District- Shariatpur. | 1.32 | | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Kolaroa Pourashava** | | |  | |  |  |  |  |  |
| W-88 | e-GP/CTCRP/KOLA/RD-01 | Construction and Improvement of Roads under Kolaroa Pourashava, District- Shatkhira. | 2.29 | | OCB | Prior | 1S-1E | Q3/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-89 | e-GP/CTCRP/KOLA/RD-02 | Construction and Improvement of Roads under Kolaroa Pourashava, District- Shatkhira. | 1.80 | | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-90 | e-GP/CTCRP/KOLA/DR-01 | Construction and Improvement of Drains under Kolaroa Pourashava, District- Shatkhira. | 1.60 | | OCB | Prior | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-91 | e-GP/CTCRP/KOLA/DR-02 | Construction/ Improvement of Drains under Kolaroa Pourashava, District- Shatkhira. | 1.76 | | OCB | Post | 1S-1E | Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Goods** | | |  |  | |  |  |  |  |
| G-11 | LGED/ CTCRP/GD-11 | Procurement/Development of Early warning system in Pourashava | 1.28 | OCB | | Prior | 1S-1E | Q2/2025  IN PRS INDICATETD Q4 2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 22 Set |
| G-12 | LGED/ CTCRP/GD-12 | Procurement of Livelihood Supporting's Equipment/tools. | 1.34 | OCB | | Prior | 1S-1E | Q2/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 11 Set |
| G-13 | LGED/ CTCRP/GD-13 | Procurement of Livelihood Supporting's Equipment/tools. | 1.34 | OCB | | Prior | 1S-1E | Q2/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 11 Set |
| Outsourcing | | |  |  | |  |  |  |  |
| Outsourcing | LGED/ CTCRP/Outsourcing-01 | Outsourcing | 1.45 | OCB | | Post | 1S-SE | Q2/2023 | Non-Consulting Services: Yes  Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document:  High-Risk Contract: No  e-GP: No  Covid-19 Response? No  Comments: 8820 Person Month |

1. **Consulting Services Contracts Estimated to Cost $100,000 or More**

The following table lists consulting services contracts for which the recruitment activity is either ongoing or expected to commence within the next 18 months.

| **Package**  **Number** | **General Description** | **Estima-ted Value**  **(USD million)**67F**[[2]](#footnote-2)** | **Recruitment Method** | **Review**  (Prior/Prior) | **Type of Pro-posal** | **Advertisement Date** (quarter/year) | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S-01 | Detail Design Consultants (DDC) including Waste Management Plan | 3.36 | QCBS | Prior | FTP | Q3/2022 | Non-Consulting Services: No  Advance Contracting: Yes  Type: Firm  Assignment: National  Quality-Cost ratio: 80:20  Person-months: 912  Covid-19 Response? No |
| S-02 | Project Management and Supervision Consultants (PMSC) | 6.58 | QCBS | Prior | FTP | Q3/2022 | Non-Consulting Services: No  Advance Contracting: Yes  Type: Firm  Assignment: International  Quality-Cost ratio: 80:20  Person-months: 1632  Covid-19 Response? No |
| S-03 | Institutional Capacity and Community Development Consultants (ICCDC) | 2.97 | QCBS | Prior | FTP | Q3/2022 | Non-Consulting Services: No  Advance Contracting: Yes  Type: Firm  Assignment: National  Quality-Cost ratio: 80:20  Person-months: 1044  Covid-19 Response? No |
| S-04 | Project Internal Auditing Consultants (PIAC) | 0.35 | QCBS | Prior | STP  CHANGED TO BTP | Q4/2023 | Non-Consulting Services: No  Advance Contracting: No  Type: Firm  Assignment: National  Quality-Cost ratio: 80:20  Person-months: 120  Covid-19 Response? No |
| S-05 | Consultancy Services for Development of the Integrated Drainage Plan (IDP) | 0.58 | SSS | Prior | BTP | Q2/2023 | Non-Consulting Services: No  Advance Contracting: No  Type: Firm  Assignment: National  Quality-Cost ratio: 80:20  Person-months: 86  Covid-19 Response? No |
| S-06 | Appointment of NGO for Livelihood training, Graduation program & E-PW3D. (NGO-1 & 2) | 1.32 | QCBS | Prior | STP | Q3/2023  Changed to  Q4/2023 | Non-Consulting Services: No  Advance Contracting: No  Type: Firm  Assignment: National  Quality-Cost ratio: 80:20  Person-months: 370  Covid-19 Response? No |

1. **Goods and Works Contracts Estimated to Cost Less than $1 Million and Consulting Services Contracts Less than $100,000 (Smaller Value Contracts)**

The following table lists smaller value goods, works, and consulting services contracts for which the activity is either ongoing or expected to commence within the next 18 months.

| **Works/ Goods** | **Package**  **Number** | **General Description** | **Estima-ted Value (USD million)**68F**[[3]](#footnote-3)** | **Procurement Method** | **Review**  (Prior/  Prior) | **Bidding Proce-dure** | **Adver-tisement Date**  (quarter/year) | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Bakergang *Pourashava*** | | |  |  |  |  |  |  |
| W-92 | e-GP/CTCRP/BAKR/BR-01 | Construction of Bridge and Box Culverts under Bakerganj Paurashava, District- Barisal | 0.55 | OCB | Prior | 1S-1E | Q4/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-93 | e-GP/CTCRP/BAKR/CS-01 | Construction of Cyclone Shelter under Bakerganj Pourashava, District- Barisal | 0.54 | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-94 | e-GP/CTCRP/BAKR/MM-01 | Construction of 01 no Multipurpose Market under Bakerganj Paurashava, District- Barisal | 0.67 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-95 | e-GP/CTCRP/BAKR/SI-01 | Slum Improvement under Bakerganj Paurashava, District- Barisal | 0.09 | Direct Contracting | Priort | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Mehendiganj Paurashava** | | |  |  |  |  |  |  |
| W-96 | e-GP/CTCRP/MEHN/CS-01 | Construction of Cyclone Shelter at Uttar Shabajpur Govt. Primary School. | 0.55 | OCB | Post | 1S-1E | Q2/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-97 | e-GP/CTCRP/MEHN/BR-01 | Construction of Bridge under Mehendiganj Pourashava, District- Barisal. | 0.47 | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-98 | e-GP/CTCRP/MEHN/MM-01 | Construction of Multipurpose Super market at Stimar ghat Canal side near the Stimar Ghat Bazar. Ward No 09. (Mouza-Chunarchar, BS Plot No-644) | 0.59 | OCB | Prior | 1S-1E | Q1/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-99 | e-GP/CTCRP/MEHN/SI-01 | Slum Improvement under Mehendiganj Pourashava, District- Barisal. | 0.10 | OCB | Prior | 1S-1E | Q4/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Banaripara Paurashava** | | |  |  |  |  |  |  |
| W-100 | e-GP/CTCRP/BANR/CS-01 | Construction of Cyclone Shelter under Banaripara *Pourashava,* District- Barisal | 0.59 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-101 | e-GP/CTCRP/BANR/MM-01 | Construction of 01 no Multipurpose Market under Banaripara Paurashava, District- Barisal | 0.79 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-102 | e-GP/CTCRP/BANR/SI-01 | Slum Improvement under Banaripara Paurashava, District- Barisal | 0.09 | Direct Contracting | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Muladi Paurashava** | | |  |  |  |  |  |  |
| W-103 | e-GP/CTCRP/MULA/BR-01 | Construction of Bridge under Muladi Paurashava, District- Barisal. | 0.84 | OCB | Prior | 1S-1E | Q1/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-104 | e-GP/CTCRP/MULA/CS-01 | Construction of Cyclone Shelter under Muladi *Pourashava,* District- Barisal | 0.57 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-105 | e-GP/CTCRP/MULA/MM-01 | Construction of 01 nos Multipurpose Market under Muladi Paurashava, District- Barisal. | 0.64 | OCB | Post | 1S-1E | Q1/2024  Changed to  Q@/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-106 | e-GP/CTCRP/MULA/SI-01 | Slum Improvement under Muladi Paurashava, District- Barisal. | 0.09 | Direct Contracting | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Gouranadi Paurashava** | | |  |  |  |  |  |  |
| W-107 | e-GP/CTCRP/GOUR/RD-02 | Construction and Improvement of Roads under Gouranadi Paurashava, District- Barisal. | 0.65 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-108 | e-GP/CTCRP/GOUR/BR-01 | Construction of RCC Box Culverts under Gouranadi Paurashava, District- Barisal. | 0.93 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-109 | e-GP/CTCRP/GOUR/CS-01 | Construction of Cyclone Shelter under Gouranadi Paurashava, District- Barisal. | 0.59 | OCB | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-110 | e-GP/CTCRP/GOUR/MM-01 | Construction of 01 no Multipurpose Market under Gouranadi Paurashava, District- Barisal. | 0.64 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-111 | e-GP/CTCRP/GOUR/SI-01 | Slum Improvement under Gouranadi Paurashava, District- Barisal. | 0.09 | Direct Contracting | Prior | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Bagerhat Paurashava** | | |  |  |  |  |  |  |
| W-112 | e-GP/CTCRP/BAGR/BR-01 | Construction of Box Culverts under Bagerhat Paurashava, District- Bagerhat. | 0.23 | OCB | Post | 1S-1E | Q1/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-113 | e-GP/CTCRP/BAGR/GS-01 | Development of Green Space under Bagerhat Paurashava, District- Bagerhat. | 0.87 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-114 | e-GP/CTCRP/BAGR/NBS-01 | Nature Based Solution under Bagerhat Paurashava, District- Bagerhat. | 0.88 | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-115 | e-GP/CTCRP/BAGR/MM-01 | Construction of 01 no Multipurpose Market under Bagerhat Paurashava, District- Bagerhat. | 0.69 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-116 | e-GP/CTCRP/BAGR/SI-01 | Slum Improvement under Bagerhat Paurashava, District- Bagerhat. | 0.10 | OCB | Post | 1S-1E | Q3/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Morrelganj Paurashava** | | |  |  |  |  |  |  |
| W-117 | e-GP/ CTCRP/MORL/DR-01 | Construction and Improvement of Drains under Morelganj Paurashava, District- Bagerhat | 0.88 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-118 | e-GP/ CTCRP/MORL/BR-01 | Construction of Bridge under morelganj Paurashava, District- Bagerhat. | 0.35 | OCB | Post | 1S-1E | Q1/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-119 | e-GP/ CTCRP/MORL/NBS-01 | Nature Based Solution under morelganj Paurashava, District- Bagerhat. | 0.88 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: e-GP |
| W-120 | e-GP/ CTCRP/MORL/MM-01 | Construction of 01 no Multipurpose Market under morelganj Paurashava, District- Bagerhat. | 0.61 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-121 | e-GP/ CTCRP/MORL/SI-01 | Slum Improvement under morelganj Paurashava, District- Bagerhat. | 0.10 | Direct Contracting | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: e-GP |
| **Charfassion *Pourashava*** | | |  |  |  |  |  |  |
| W-122 | e-GP/CTCRP/CHAR/BR-01 | Construction of Bridges and Box Culverts under Charfassion *Pourashava,* District- Bhola. | 0.78 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-123 | e-GP/CTCRP/CHAR/CS-01 | Construction of Cyclone Shelter under Charfassion *Pourashava,* District- Bhola. | 0.54 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: e-GP |
| W-124 | e-GP/CTCRP/CHAR/MM-01 | Construction of 01 no Multipurpose Market under Charfassion Paurashava, District- Bhola. | 0.70 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-125 | e-GP/CTCRP/CHAR/SI-01 | Slum Improvement under Charfassion Paurashava, District- Bhola. | 0.09 | Direct Contracting | Prior | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Lalmohan *Pourashava*** | | |  |  |  |  |  |  |
| W-126 | e-GP/ CTCRP/LALM/RD-03 | Construction and Improvement of Roads under Lalmohan P*ourashava,* District- Bhola. | 0.96 | OCB | Post | 1S-1E | Q3/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-127 | e-GP/CTCRP/LALM/BR-01 | Construction of Bridge under Lalmohan Paurashava, District- Bhola. | 0.93 | OCB | Prior | 1S-1E | Q1/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-128 | e-GP/CTCRP/LALM/CS-01 | Construction of Cyclone Shelter under Lalmohan *Pourashava,* District- Bhola. | 0.54 | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-129 | e-GP/CTCRP/LALM/CS-02 | Construction of Cyclone Shelter under Lalmohan *Pourashava,* District- Bhola. | 0.58 | OCB | Post | 1S-1E | Q2/2023  Changed to  Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-130 | e-GP/CTCRP/LALM/MM-01 | Construction of 01 No. Multipurpose Market under Lalmohan *Pourashava,* District- Bhola. | 0.59 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: e-GP |
| W-131 | e-GP/CTCRP/LALM/SI-01 | Slum Improvment under Lalmohan Paurashava, District- Bhola. | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Borhanuddin Paurashava** | | |  |  |  |  |  |  |
| W-132 | e-GP/CTCRP/BORH/RD-02 | Construction and Improvement of Roads under Borhanuddin *Pourashava,* District- Bhola | 0.64 | OCB | Post | 1S-1E | Q3/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-133 | e-GP/CTCRP/BORH/RD-03 | Construction and Improvement of Roada under Borhanuddin *Pourashava,* District- Bhola | 0.71 | OCB | Post | 1S-1E | Q3/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-134 | e-GP/CTCRP/BORH/CS-01 | Construction of Cyclone Shelter under Borhanuddin Paurashava, District- Bhola. | 0.55 | OCB | Prior | 1S-1E | Q4/2024  Changed to  Q3/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-135 | e-GP/CTCRP/BORH/CS-02 | Construction of Cyclone Shelter under Borhanuddin Paurashava, District- Bhola. | 0.54 | OCB | Post | 1S-1E | Q4/2024  Changed to  Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-136 | e-GP/CTCRP/BORH/BR-01 | Construction of Bridges under Borhanuddin Paurashava, District- Bhola. | 0.70 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-137 | e-GP/CTCRP/BORH/MM-01 | Construction of 01 no Multipurpose Market under Borhanuddin Paurashava, District- Bhola. | 0.57 | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-138 | e-GP/CTCRP/BORH/SI-01 | Slum Improvment under Borhanuddin Paurashava, District- Bhola. | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 1 No |
| **Patharghata Paurashava** | | |  |  |  |  |  |  |
| W-139 | e-GP/ CTCRP/PATH/BR-01 | Construction of Box Culverts under Patharghata Paurashava, District- Barguna. | 0.50 | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-140 | e-GP/ CTCRP/PATH/CS-01 | Construction of Cyclone Shelter under Patharghata Pourashava, District- Barguna | 0.59 | OCB | Prior | 1S-1E | Q3/2023  Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-141 | e-GP/ CTCRP/PATH/CS-02 | Construction of Cyclone Shelter under Patharghata Pourashava, District- Barguna | 0.59 | OCB | Post | 1S-1E | Q4/2023  Changed to  Q4/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-142 | e-GP/ CTCRP/PATH/MM-01 | Construction of 01 no Multipurpose Market under Patharghata Paurashava, District- Barguna. | 0.70 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-143 | e-GP/ CTCRP/PATH/SI-01 | Slum Improvment under Patharghata Paurashava, District- Barguna. | 0.09 | Direct Contracting | Post  (indicated PRIOR in PRS as this is DC) | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Betagi Paurashava** | | |  |  |  |  |  |  |
| W-144 | e-GP/CTCRP/BETA/DR-02 | Construction and Improvement of Drains under Betagi Paurashava, District- Barguna. | 0.99 | OCB | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-145 | e-GP/CTCRP/BETA/CS-01 | Construction of Cyclone Shelter under Betagi Paurashava, District- Barguna. | 0.59 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-146 | e-GP/CTCRP/BETA/MM-01 | Construction of 01 no Multipurpose Market under Betagi Paurashava, District- Barguna. | 0.69 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-147 | e-GP/CTCRP/BETA/SI-01 | Slum Improvement under Betagi Paurashava, District- Barguna. | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Jhalokathi Paurashava** | | |  |  |  |  |  |  |
| W-148 | e-GP/CTCRP/JHAL/BR-01 | Construction RCC Culverts under Jhalokathi Pourashava, District- Jhalokathi | 0.25 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-149 | e-GP/CTCRP/JHAL/CS-01 | Construction of Cyclone Shelter under Jhalokathi *Pourashava,* District- Jhalokathi | 0.55 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-150 | e-GP/CTCRP/JHAL/SI-01 | Slum Improvement under Jhalokathi Pourashava, District- Jhalokathi | 0.10 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-151 | e-GP/CTCRP/JHAL/MM-01 | Construction of 01 no Multipurpose Market under Jhalokathi Pourashava, District- Jhalokathi | 0.79 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Nalchity Paurashava** | | |  |  |  |  |  |  |
| W-152 | e-GP/CTCRP/NALC/CS-01 | Construction of Cyclone Shelter under Nalchity *Pourashava,* District- Jhalokathi. | 0.55 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts:1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 1 No |
| W-153 | e-GP/CTCRP/NALC/MM-01 | Construction of 01 no Multipurpose Market under Nalchity Pourashava, District- Jhalokathi | 0.59 | OCB | Prior | 1S-1E | Q4/2023  Changed to  Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 1 No |
| W-154 | e-GP/CTCRP/NALC/SI-01 | Slum Improvement under Nalchity Pourashava, District- Jhalokathi | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts:1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Paickgacha Paurashava** | | |  |  |  |  |  |  |
| W-155 | e-GP/CTCRP/PAIK/RD-02 | Construction and Improvement of Roads under Paikgacha *Pourashava,* District- Khulna | 0.95 | OCB | Post | 1S-1E | Q3/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-156 | e-GP/CTCRP/PAIK/BR-01 | Construction of Bridge and RCC Culverts under Paikgacha Pourashava, District- Khulna. | 0.93 | OCB | Prior | 1S-1E | Q1/2024  Changed to  Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-157 | e-GP/CTCRP/PAIK/CS-01 | Construction of Cyclone Shelter under Paikgacha Pourashava, District- Khulna. | 0.57 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-158 | e-GP/CTCRP/PAIK/MM-01 | Construction of 01 nos Multipurpose Market under Paikgacha Pourashava, District- Khulna. | 0.69 | OCB | Post | 1S-1E | Q1/2024  Changed to  Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-159 | e-GP/CTCRP/PAIK/SI-01 | Slum Improvement under Paikgacha Pourashava, District- Khulna. | 0.04 | Direct Contracting | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Chalna Paurashava** | | |  |  |  |  |  |  |
| W-160 | e-GP/CTCRP/CHAL/DR-01 | Construction and Improvement of Drains under Chalna Pourashava, District- Khulna. | 0.79 | OCB | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-161 | e-GP/CTCRP/CHAL/BR-01 | Construction of Bridge under Chalna Pourashava, District- Khulna. | 0.23 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-162 | e-GP/CTCRP/CHAL/CS-01 | Construction of Cyclone shelter in Abul Hossain Girls High School at Ward No 04 under Chalna *Pourashava,* District- Khulna | 0.56 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-163 | e-GP/CTCRP/CHAL/MM-01 | Construction of 01 no Multipurpose Market under Chalna Pourashava, District- Khulna. | 0.56 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-164 | e-GP/CTCRP/CHAL/NBS-01 | Nature Based Solution under Chalna Pourashava, District- Khulna. | 0.88 | OCB | Prior | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-165 | e-GP/CTCRP/CHAL/SI-01 | Slum Improvement under Chalna Pourashava, District- Khulna. | 0.09 | Direct Contracting | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Patuakhali Paurashava** | | |  |  |  |  |  |  |
| W-166 | e-GP/ CTCRP/PATU/BR-01 | Construction of Bridges under Patuakhali Pourashava, District- Patuakhali. | 0.41 | OCB | Post | 1S-1E | Q4/2023  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-167 | e-GP/ CTCRP/PATU/SI-01 | Slum improvement under Patuakhali Pourashava, District- Patuakhali. | 0.10 | Direct Contracting | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Kuakata Paurashava** | | |  |  |  |  |  |  |
| W-168 | e-GP/CTCRP/KUAK/CS-01 | Construction of Cyclone Shelter under Kuakata Pourashava, District- Patuakhali. | 0.59 | OCB | Prior | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-169 | e-GP/CTCRP/KUAK/CS-02 | Construction of Cyclone Shelter under Kuakata Pourashava, District- Patuakhali. | 0.57 | OCB | Post | 1S-1E | Q3/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-170 | e-GP/CTCRP/KUAK/BR-01 | Construction of Bridges under Kuakata Pourashava, District- Patuakhali. | 0.93 | OCB | Post | 1S-1E | Q3/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-171 | e-GP/CTCRP/KUAK/MM-01 | Construction of 01 No. Multipurpose Market under Kuakata Pourashava, District- Patuakhali. | 0.79 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-172 | e-GP/CTCRP/KUAK/GS-01 | Development of Green Space under Kuakata Pourashava, District- Patuakhali. | 0.87 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-173 | e-GP/CTCRP/KUAK/SI-01 | Slum Improvement under Kuakata Pourashava, District- Patuakhali. | 0.09 | Direct Contracting | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Swarupkathi Paurashava** | | |  |  |  |  |  |  |
| W-174 | e-GP/CTCRP/SWAR/BR-01 | Construction of RCC Bridges under Swarupkathi Pourashava, District- Pirojpur. | 0.69 | OCB | Prior | 1S-1E | Q1/2024  Changed to  Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-175 | e-GP/CTCRP/SWAR/CS-01 | Construction of Cyclone Shelter under Swarupkathi *Pourashava,* District-Pirijpur | 0.58 | OCB | Post | 1S-1E | Q2/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 1 No |
| W-176 | e-GP/CTCRP/SWAR/SI-01 | Slum Improvement under Swarupkathi Pourashava, District- Pirojpur. | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-177 | e-GP/CTCRP/SWAR/MM-01 | Construction of 01 no Multipurpose Market under Swarupkathi Pourashava, District- Pirojpur. | 0.59 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Janjira Paurashava** | | |  |  |  |  |  |  |
| W-178 | e-GP/CTCRP/JANJ/BR-01 | Construction of Bridge under Jajira Pourashava, District- Shariatpur. | 0.48 | OCB | Prior | 1S-1E | Q4/2023  Changed to  Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: 60 M |
| W-179 | e-GP/CTCRP/JANJ/BR-02 | Construction of Bridge under Jajira Pourashava, District- Shariatpur. | 0.53 | OCB | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-180 | e-GP/CTCRP/JANJ/MM-01 | Construction of 01 no Multipurpose Market under Jajira Pourashava, District- Shariatpur. | 0.51 | OCB | Post | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-181 | e-GP/CTCRP/JANJ/SI-01 | Slum Improvement under Jajira Pourashava, District- Shariatpur. | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Bhederganj Paurashava** | | |  |  |  |  |  |  |
| W-182 | e-GP/ CTCRP/BHED/MM-01 | Construction of 01 nos Multipurpose Market under Bhederganj Pourashava, District- Shariatpur. | 0.72 | OCB | Prior | 1S-1E | Q2/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-183 | e-GP/ CTCRP/BHED/SI-01 | Slum Improvement under Bhederganj Pourashava, District- Shariatpur. | 0.09 | Direct Contracting | Post | 1S-1E | Q4/2023 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Kolaroa Paurashava** | | |  |  |  |  |  |  |
| W-184 | e-GP/ CTCRP/BHED/MM-01 | Construction of Bridge and RCC Culverts under Kolaroa Pourashava, District- Shatkhira. | 0.65 | OCB | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-185 | e-GP/CTCRP/KOLA/CS-01 | Construction of Cyclone Shelter under Kolaroa Pourashava, District- Shatkhira. | 0.59 | OCB | Post | 1S-1E | Q2/2023  Changed to  Q4/2023 | Advertising: National  No. of Contracts: one/multiple  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-186 | e-GP/CTCRP/KOLA/MM-01 | Construction of 01 no Multipurpose Market under Kolaroa Pourashava, District- Shatkhira. | 0.67 | OCB | Prior | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts:1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| W-187 | e-GP/CTCRP/KOLA/SI-01 | Slum Improvement under Kolaroa Pourashava, District- Shatkhira. | 0.09 | Direct Contracting | Post | 1S-1E | Q1/2024 | Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PW3D  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| **Goods** | | |  |  |  |  |  |  |
| G-1 | LGED/ CTCRP/GD-1 | Procurement of cross-country vehicles: 4WD vehicles (2500+/- c.c., dual AC, etc.) – 3 No. | 0.35 | Direct Contracting | Prior | 1S-1E | Q2/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments:. |
| G-2 | LGED/CTCRP/GD-2 | Procurement of four-stroke motorcycle | 0.07 | RFQ | Prior | NA | Q2/2023  Changed to  Q4/2023 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-3 | LGED/ CTCRP/GD-3 | Procurement of office equipment (Laptop & Desktop Computer with accessories printers, scanner, video camera, Digital Still Camera & photocopier, Drone camera, multimedia projector, cc camera) – 153 No. | 0.24 | RFQ  Changed to  OCB | Prior | 1S-1E | Q2/2023 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-4 | LGED/CTCRP/GD-4 | Procurement of Air Cooler (AC) for PMU office | 0.03 | RFQ | Prior | NA | Q2/2023  Changed to  Q4/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-5 | LGED/CTCRP/GD-5 | Procurement of survey equipment (Total station Robotic) | 0.36 | OCB | Prior | 1S-1E | Q3/2023 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-6 | LGED/CTCRP/GD-6 | Procurement of Laboratory Equipment . | 0.45 | OCB | Prior | NA | Q4/2023 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-7 | LGED/CTCRP/GD-7 | Procurement of office furniture. | 0.09 | RFQ | ~~Prior/~~Post | 1S-1E | Q3/2023  Changed to  Q1/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-8 | LGED/CTCRP/GD-8 | Procurement of Solid Waste and Sanitary Equipment.(L-1: Garbage Dump Track,L-02: Truck mounted Suction machine L-03: TrI-CYCLE with bins) | 0.80 | OCB | Prior | 1S-1E | Q3/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-9 | LGED/CTCRP/GD-9 | Procurement of Equipment for Remote monitoring System Established under CTCRP. | 0.58 | OCB | Prior | NA | Q4/2023 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |
| G-10 | LGED/CTCRP/GD-10 | Procurement of office furniture. | 0.09 | RFQ | ~~Prior~~/Post | NA | Q1/2024 | Non-Consulting Services: No  Advertising: National  No. of Contracts: 1  Prequalification of Bidders: No  Domestic Preference: No  Advance Contracting: No  Bidding Document: e-PG3  High-Risk Contract: No  e-GP: Yes  Covid-19 Response? No  Comments: |

Works packages related to Roads, Drainage, and Cyclone Shelters with estimate less than $ 1.0 million shall be post review except first packages and packages estimated $ 1.0 million or more which shall be subject to Prior review.

1. **List of Indicative Packages (Contracts) Required Under the Project**

The following table lists goods, works, and consulting services contracts for which procurement activity is expected to commence beyond the procurement plan duration and over the life of the project (i.e., those expected beyond the current procurement plan duration).

**Goods and Works**

| **Works/ Goods** | **Package**  **Number** | | **General Description** | | | **Estimated Value (USD million)**69F**[[4]](#footnote-4)** | **Procurement**  **Method** | | | **Review** | **Bidding Procedure** | | **Tentative Advertisement/ Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Mehendiganj Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-189 | e-GP/CTCRP/MEHN/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 0.94 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Banaripara *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-190 | e-GP/CTCRP/BANR/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 0.82 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Muladi Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-191 | e-GP/CTCRP/MULA/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 1.18 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Gouranadi *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-192 | e-GP/CTCRP/GOUR/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 0.13 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Bagerhat *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-193 | e-GP/CTCRP/BAGR/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 0.58 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Morrelganj** **Porashava** | | |  | | |  |  | | |  |  | |  |
| W-194 | e-GP/CTCRP/MORR/OS-01 | | Construction of Municipal Facilites (Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 0.45 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Charfassion Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-195 | e-GP/CTCRP/CHAR/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 2.87 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Lalmohan *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-196 | e-GP/CTCRP/LALM/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 0.93 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Borhanuddin *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-197 | e-GP/CTCRP/BORH/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 0.90 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Pathargatha Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-198 | e-GP/ CTCRP/PATH/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 0.78 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Betagi *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-199 | e-GP/CTCRP/BETA/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 1.52 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Jhalokathi Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-200 | e-GP/CTCRP/JHAL/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 1.16 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Nalchity Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-201 | e-GP/ CTCRP/NALC/OS-03 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 1.52 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Paikgacha Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-202 | e-GP/ CTCRP/PAIK/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 1.28 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Chalna Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-203 | e-GP/CTCRP/CHAL/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 1.34 | OCB | | | Prior | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Patuakhali Pourashava** | | |  | | |  |  | | |  |  | |  |
| W-204 | e-GP/ CTCRP/PATU/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 0.58 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Kuakata *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-205 | e-GP/CTCRP/KUAK/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 0.86 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Swarupkathi *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-206 | e-GP/CTCRP/SWAR/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 1.30 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Janjira *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-207 | e-GP/CTCRP/JAJI/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc | | | 1.68 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Bhederganj *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-188 | e-GP/ CTCRP/BHED/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/Wash Block/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 1.61 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Kolaroa *Pourashava*** | | |  | | |  |  | | |  |  | |  |
| W-208 | e-GP/CTCRP/KOLA/OS-01 | | Other Structures: Water Body Restoration, Boat Landing Station, Public Toilet/WashBlock/Community Toilet/ Income generating infrastructure/ Community Development/Park/Public Space/ Bus Bay/ Cattle Market/ Poltun etc. | | | 1.07 | OCB | | | Post | 1S-1E | | Q4/2024  No. of Contracts: Multiple |
| **Consulting Services** | | | | | | | | | | | | | |
| **Package**  **Number** | | **General**  **Description** | | **Estimated Value (in US$)** | **Selection Method** | | | **Review** | **Type of Proposal** | | | **Comments** | |
|  | |  | |  |  | | |  |  | | |  | |
|  | |  | |  |  | | |  |  | | |  | |
|  | |  | |  |  | | |  |  | | |  | |

1. Revised the estimated value based on the updated inputs received from LGED on 10 Feb 2022; and date of Currency rate (1 USD = 84.82 BDT) applied is 02 August 2021 as per the Approved Concept Note [↑](#footnote-ref-1)
2. Revised the estimated value based on the updated inputs received from LGED on 10 Feb 2022; and date of Currency rate (1 USD = 84.82 BDT) applied is 02 August 2021 as per the Approved Concept Note [↑](#footnote-ref-2)
3. Revised the estimated value based on the updated inputs received from LGED on 10 Feb 2022; and date of Currency rate (1 USD = 84.82 BDT) applied is 02 August 2021 as per the Approved Concept Note [↑](#footnote-ref-3)
4. Revised the estimated value based on the updated inputs received from LGED on 10 Feb 2022; and date of Currency rate (1 USD = 84.82 BDT) applied is 02 August 2021 as per the Approved Concept Note [↑](#footnote-ref-4)