## ALL
Status of contract amount (Highest to lower ) & Hector
Participatory Small Scale Water Resources Sector Project
Sl. No. | SP No | Name of Subproject | Name of District | Name of Upazila | Component of Works | Name of Contractor | Date of Agreement | Completion Date | Estimated Cost (Tk). | Contract Amount (Tk) | Amuont Paid (Tk). | Physical Progress (%) |  | Financial Progress (%) | PCSS NO | Earth work (Tk). | LCS No. | LCS Contract (Tk) | Total Contract (Construction+LCS) | Benifited Area (Hector) | Date of Agreement | Date of Completion | Physical Progress (%) | Financial Progress (%) | Amuont Paid (Tk). | PCSS NO | Fund: ADB/ IFAD-1 /FAD-2 | Remarks | Per Hector Amount
[12 empty] | To be | Achievment
1 | 43045 | Pok Khali-Naikoudia | Cox's Bazar | Sadar | - Rubber Dam - O&M Shed | WEL-UI (JV), Enderson Road, Cox's Bazar. | 16.09.2013 | 15.09.2015 | 80206459 | 87841874 | 76720478 |  | 95 | 87 | 0022 |  |  |  | 87841874 | 663 | [6 empty] | IFAD-1 | Completed. Minor protective work needed | 132491.5143
2 | 41007 | Harwalchari | Chittagonj | Fatikchari | - Rubber Dam (ch. 1+895 Km) = 30m - Connecting bridge & Pumphouse - O&M Shed (12m X 6m) | M/S Abul Bashar Ruddura, Anwara, Chittagong | 07.05.2012 | 06.05.2014 | 59759859 | 79103874 | 73605410 |  | 100 | 100 | 0042 |  | 0 |  | 79103874 | 650 | [6 empty] | ADB | Revised 6.44% more.(Final) | 121698.2677
3 | 41008 | Goshinga-Sitalakha | Gazipur | Sreepur | -Irrigation pipeline both RCC & PVC with accessories -Electric Poll - O&M Shed | M/S Jerin Enterprise Koltapara, RDA, Bogra | 15.12.14 | 15.12.2014 | 80191982 | 71115798 | 68087000 |  | 98 | 84 | 006 |  | 0 |  | 71115798 | 600 | [6 empty] | IFAD-1 | 1.Header tank completed,2. Burried PipeCompleted,3. Flow control structure -80%, 4.WMCA office work- 90%. | 118526.33
4 | 46214 | Hangar Khal | Chittagonj | Lohagara | Rubber Dam (28.0m X 3.5m) with pumphouse & 2 outlet lined canal (2V-) = 900m WMCA Office (12m X 6m) 2 canal dyke | M/S Abul Bashar Rudura Anwara, Chittagong | 27.01.2016 | 23.01.2017 | 62507630 | 60382756 | 26500000 |  | 72 | 43 | 0273 | 1227866 | 2 | 1227866 | 61610622 | 1000 | 04.12.2015 | 30.04.2016 | 100 | 100 | 1227687 |  | ADB | Structure Work ongoing. LCS work Completed | 61610.622
5 | 43051 | Monirjheel-Sonaichari Khal | Cox's Bazar | Ramu | - Rubber Dam with connecting bridge,pump house and office roorm - O&M Shed | S.A.Engineering KBI (JV)Banani, Dhaka | 28.11.2013 | 27.05.2015 | 44322329 | 56624771 | 53366253 |  | 100 | 100 | 0141 |  |  |  | 56624771 | 637 | [6 empty] | ADB | Completed | 88892.8901
6 | 46262 | Boalia Chhara | Cox'sbazar | Chokoria | Rubber Dam = 1 Pucca drain = 1.20 km WMCA Office = 1 | Khandoker Buseness International 2nd Floor, 4 Shagun Bagicha, Dhaka | 26.03.2016 | 30.09.2017 | 57655519 | 52174675.36 | 20000000 |  | 65 | 38 | 0275 | 0 | 0 | 0 | 52174675.36 | 540 | [6 empty] | ADB | Base casting done. | 96619.7692
7 | 46222 | Chambi Khal | Chittagonj | Lohagara | Rubber Dam (20.0m X 4.5m) = 1 WMCA Office (12m X 6m) with pumphouse= 1 | M/S Abul Bashar Rudura Anwara, Chittagong | 27.01.2016 | 23.01.2017 | 53269156 | 51100204 | 23209401 |  | 47 | 23 | 0274 | 0 |  |  | 51100204 | 790 | [6 empty] | ADB | Abutment's wall completed. Bridge not yet done. | 64683.8025
8 | 45151 | Harinmara Dusri Khal | Cox's Bazar | Ukhia | Rubber Dam with Bridge = 1 O&M Shed = 1 | M/S Abul Bashar Rudura Anwara, Chittagong | 26.08.2015 | 11.03.2017 | 50567265 | 46847632 | 27264000 |  | 75 | 58 | 0248 |  |  |  | 46847632 | 627 | [6 empty] | ADB | O&M Shed 0%. Will be completed by February 2017. | 74717.1164
9 | 43047 | Paschim Degulia | Cox's Bazar | Ukhia | - Rubber Dam - O&M Shed | M/S Abul Bashar Rudura Anwara, Chittagonj. | 07.11.2013 | 06.05.2015 | 45281744 | 43401437 | 43961658 |  | 100 | 82 | 0024 |  |  |  | 43401437 | 881 | [6 empty] | IFAD-2 | Completed | 49263.8331
10 | 45203 | Sonai Chhara | Chittagonj | Mirersarai | Khal = 4.00 km Earthen dam (85m) spillway (3-V 3.0m X 2.0m) Reservoir outlet (1-V 1.5m X 1.5m) 5 Check structures (1-V 1.2m X 1.2m), (1-V 1.2m X 1.2m), (3-V 1.5m X 1.5m), (2-V 1.2m X 1.5m), (5-V 1.5m X 1.5m) WM CA Office | HBC-RA (JV) Haque Market Bibirhat, Fatikchari Chittagong | 08.12.2015 | 06.01.2017 | 37950588 | 40937711 | 15735500 |  | 44 | 38 |  | 1558106 | 6 | 1558106 | 42495817 | 706 | 11.10.2015 | 30.04.2016 | 100 | 100 | 1526721 |  | IFAD-1 | WRS Portion completed. 4 check structure completed except gate filling. WMCA Office 75% done. | 60192.3754
11 | 45153 | Bamer Chara | Chittagong | Banshkhali | - Earthen dam (30m) - Outlet structure WRS (1V-1.5m X 1.5m) - 2 spillways (north & south) 3V-2.0m X 2.85m) each - 1 WRS (5V- 1.5m X 1.8m) each - Repairing of 2 WRS (3-V 3.20m X 2.00m) & (8-V 1.5m X 1.8m) - Irrigation canal = 500m - WM CA Office (12m X 6m) | M/S Abul Bashar Rudura Anwara, Chittagong | 29.09.2015 | 31.10.2016 | 41123530 | 40830025 | 3303734 |  | 30 | 10 | 0279 |  |  |  | 40830025 | 680 | [6 empty] | ADB | Base casting done & wall casting underway. 5-vent check structure done. Line canal work started. | 60044.1544
12 | 41006 | Bhalabari Durgapur | Lalmonirhat | Adtimari | * Rubber Dam (30m) with Bridge, O&M Shed | JV of Alhaj Abdul Hakim & Alamgir Hossain Ranto, Aditmari, Lalmonirhat | 07.02.2012 | 06.02.2014 | 40893371.72 | 40475104 | 35925949 |  | 100 | 100 | 0027 |  | 0 |  | 40475104 | 893 | [6 empty] | ADB | Completed | 45324.8645
13 | 43046 | Thimchari-Purbakul | Cox's Bazar | Ukhia | - Rubber Dam - O&M Shed | S.S. Engineering & Construction Ltd. Purana Palton, Dhaka-1000 | 31.07.2013 | 30.01.2015 | 39409215 | 40382722.5 | 35284827 |  | 100 | 90 | 0123 |  |  |  | 40382722.5 | 784 | [6 empty] | ADB | Completed. Minor work needed | 51508.5746
14 | 44087 | Mahadanga Panna Beel | C-Nawabganj | Sadar | Header Tank = 2 RCC pipe =3100m UPVC pipe = 1000m Pond = 1 O&M Shed = 1 | Md. Sayhid Hasa (JV) D-184, Pathanpara, Rajshahi | 14.08.2014 | 13.01.2016 | 46513737 | 39347887 | 20740000 |  | 75 | 52 | 179 |  |  |  | 39347887 | 385 | [6 empty] | ADB | Header Tank not done. O&M shed not done. Revised drawing for structure done | 102202.3039
15 | 46269 | Rampur | Noakhali | Companigonj | 4 Khal = 20.29 km Regulator = 2 Culvert = 3 WMCA Office = 1 | SA-BSO-SE-JV | 29052016 | 27.02.2017 | 28776572 | 32704688 | 8500000 |  | 40 | 26 |  | 8038912 | 16 | 8038912 | 40743600 | 995 | 01.03.2016 | 30.04.2016 | 40 | 10 | 803885 |  | ADB | WRS on Saira Khal base casting done. Joynal Khal WRS completed. WMCA Office completed. | 40948.3417
16 | 44141 | Kashimpur Bundh | Panchagram | Sadar | * 7-vent WRS * 8-vent WRS * 2.55 km Khal * O&M Shed | M. Ehteshamul Haque & Md. Ashraful Alam Patowati (JV), Dhakkamara, Panchagarm. | 24.05.2015 | 02.03.2017 | 30135027 | 31743141 | 16721408 |  | 88 | 53 | 0235 | 1221466 |  | 1221466 | 32964607 | 780 | 15.01.2015 | 30.04.2016 | 100 | 66 | 800000 |  | ADB | 8-vent completed. Gate fitted. 7-vent to be done. O&M Shed not started. Post measurement done. | 42262.3167
17 | 41005 | Kanakdia FMD | Patuakhali | Bauphal | * 4 WRS (1V-1.5m X 1.8m 1 no. & 2V-1.5m X 1.8m 3 nos.) * 2 pipe sluices (1V-900mm Dia) * Rehabilitation of box culvert * 3 Khal 6.75 km * 1 Embankment 9.79 km * WMCA Office (12.0m X 6.0m) | Mohiuddin Ahmad, Azad Bhaban Muslimpara, Patuakhali | 16.07.12 | 01.04.2014 | 24974502 | 29536526 | 11500000 |  | 100 | 78 | 0003 | 15876739 | 27 | 15876739 | 45413265 | 730 | 28.02.2015 | 30.04.2015 | 100 | 50 | 7887761 | 0070 | IFAD-1 | Completed | 62209.9521
18 | 46218 | Char Fakira | Noakhali | Companiganj | WRS = 2 nos. 4 Khal = 16.96 km O&M Shed = 1 | M/S Al-Amin Traders E.M Traders & M/S Shushita Enterprise (JV) Narayanganj | 10.05.2016 | 27.02.2017 | 25460587 | 29028450 | 10550000 |  | 50 | 36 |  | 17987680 | 39 | 17987680 | 47016130 | 972 | 19.01.2016 | 30.04.2016 | 40 | 9 | 1550000 |  | IFAD-1 | WMCA Office 50%. Jailar khal WRS completed. Chaprashi Khal WRS ongoing. | 48370.5041
19 | 44109 | Jinaighary Khal | Joypurhat | Panchbibi | 1-vent Box culvert 4-vent WRS (1.5m X 1.8m) 6.25km Khal O&M Shed. | Ram Babu & Kalicharan Agarwala (JV), Old Hospital Road, Joypurhat. | 15.10.2014 | 14.10.2015 | 25077993 | 28614373 | 26934260 |  | 100 | 90 |  | 3244131 | 9 | 3244131 | 31858504 | 500 | 07.04.2014 | 31.05.2014 | 100 | 96 | 3100788 | 172 | ADB | Completeed. Revised estimated submitted to PMO. To clear revised estmate | 63717.008
20 | 46223 | Musapur | Noakhali | Companiganj | WRS = 3 7 Khal = 15.47 km | Al-Amin Traders E. M Traders & M/S Shushita Enterprise (JV), Narayangonj | 07.06.2016 | 27.02.2017 | 24018146 | 27369121.25 | 9000000 |  | 40 | 33 |  | 13682754 | 28 | 13682754 | 41051875.25 | 456 | 11.01.2016 | 30.04.2016 | 95 | 42 | 5680106 |  | IFAD-1 | Work on 3 WRS are ongoing. | 90026.0422
21 | 44118 | Tilai Khal | Dinajpur | Fulbari | * 5-vent WRS + 4 fixed weir * 8.80 km Khal * O&M Shed | Md. Nurul Islam Uttar Balubari, Sadar, Dinajpur. | 11.10.14 | 09.08.2015 | 28178741 | 25725600 | 22194000 |  | 95 | 86 | 0283 | 4402750 | 10 | 4402750 | 30128350 | 650 | 20.11.2014 | 30.04.2015 | 90 | 68 | 2996777 | 188 | ADB | Gate not fitted. CC block not good. O&M Shed done. | 46351.3077
22 | 46278 | Gorakhonathpur CAD | Chapai Nawabganj | Sadar | Road crossing = 1 Pumping platform = 3 RCC line canal = 4.34 km WMCA Office = 1 | M/S Dulha Enterprise (JV) Agaipur, Battola Hat, Chapai Nawabganj | 19.05.2016 | 27.02.2017 | 24524885 | 25358282.23 | 9930000 |  | 60 | 40 |  |  |  |  | 25358282.23 | 420 | [6 empty] | ADB | Main 3000m line canal done. Stair not done Platform=3 completed. O&M shed work ongoing | 60376.8625
23 | 45146 | Chotosingia-Goalkari | Thakurganj | Baliadangi | 4-V WRS 1 Weir 7.50 km Khal 1 O&M Shed | Md. Jamal Hossain NC Road, Thakurgaon | 14.09.2015 | 13.03.2017 | 22895523 | 25164837 | 20793958 |  | 100 | 100 | 0269 | 7984418 | 14 | 7984418 | 33149255 | 462 | 01.01.2015 | 30.04.2015 | 100 | 84 | 6681928 |  | ADB | Completed Earth work done. Post measurement done. Minor finishing work remaining. | 71751.6342
24 | 44140 | Purbajoydebpur-Kanchdaha | Dinajpur | Nowabganj | * 6-vent WRS (Modification) * 4-vent WRS * 3-vent WRS * 1-vent WRS * 1-vent Pipe * 2-vent Pipe * 5.2 km embankment * 2.875 km Khal * 1 O&M Shed | M. Ehteshamul Haque Jail road Dinajpur. | 16.03.2015 | 15.03.2016 | 22938294 | 25121675 | 22989000 |  | 95 | 91 | 0059 | 8372391 | 18 | 8372391 | 33494066 | 962 | 20.11.2014 | 30.04.2014 | 80 | 59 | 5077513 | 40 | IFAD-2 | O&M Shed done except finishing. Gate filling by December 2016. Will be completed by December 2016. | 34817.1164
25 | 44095 | Kalapania Khal | Chittagong | Fatikchari | WRS (8-V 1.50m X 2.00m) at ch. 3+400Km Khal = 0.900Km WMCA Office | HBC-EB (JV) Haque Matket, Bibirhat, Fatikchari, Chittagong, | 27.05.2014 | 26.11.2015 | 20934840 | 25109967 | 20606621 |  | 98 | 98 | 196 | 1506547 | 4 | 1506547 | 26616514 | 440 | 16.03.2014 | 30.04.2015 | 100 | 100 | 1456000 | 166 | ADB | Completed | 60492.0773
26 | 46233 | Char Hazari | Noakhali | Companiganj | 8 Khal = 17.20 Km WRS = 3 Pumping platform = 3 WMCA Office = 1 | Western Engineering (Pvt.) Ltd. TCB Bhaban 7th Floor, Kawranbazar, Dhaka | 07.03.2016 | 05.02.2017 | 22719049 | 24764953 |  |  | 40 |  |  | 23129633 | 48 | 23129633 | 47894586 | 456 | 11.01.2016 | 30.04.2016 | 90 | 43 | 9920984 |  | ADB | Dismentling of 1-Vent old pipe sluice gong on. Work ongoing. | 105031.9868
27 | 44124 | Sonaichari | Cox'sbazar | Chakoria | - 2 nos. WRS (5V-1.5m X 1.8m) each. - O&M Shed | KBI-M/S Asad Enterprise (AE), JV, Cox,sbazar | 05.03.2015 | 04.03.2016 | 26438700 | 24287709 | 12956195 |  | 75 | 53 | 0236 | 2862107 | 7 | 2862107 | 27149816 | 510 | 09.11.2014 | 30.04.2015 | 74 | 52 | 1500000 | 207 | ADB | work ongoing | 53234.9333
28 | 45213 | Fanaghata Rajullhpur | Noakhali | Begumganj | 3 Khal = 14.15 km WRS = 3 WMCA Office = 1 | M/S Mostafa & Sons Sonapur, Sadar Nokhali | 22.03.2016 | 28.03.2017 | 22078645 | 24219268 |  |  | 0 |  |  | 12240955 | 23 | 12240955 | 36460223 | 700 | 24.11.2015 | 30.04.2016 | 70 | 46 | 5567014 |  | IFAD-1 | LCS work ongoing | 52086.0329
29 | 44122 | Kahani Beel | Thakurgaon | Pirgonj | * 9-vent WRS * 10.40 km Khal * 1 O&M Shed | Ram Babu, Gudri Bazar, Thakurgaon | 17.09.2014 | 16.03.2016 | 25130609 | 22997002 | 11530000 |  | 90 | 50 | 226 | 6648648 | 15 | 6648648 | 29645650 | 1000 | 14.08.2014 | 30.04.2015 | 100 | 59 | 3927724 |  | ADB | Structure work Runing | 29645.65
30 | 46228 | Abupur | Feni | Sadar | Embankment = 1.30 km 3 Khal = 4.5 km WRS (4-V 1.50m X 1.80m) Box Culvert (2-V 4.00m X 4.50m) WMCA Office | M/S Saleh Ahmed, 194/1 Haque Plaza S S K Road, Feni | 20.01.2016 | 19.01.2017 | 20769718 | 22317913 | 19772000 |  | 100 | 89 | 0100 | 7897713 | 16 | 7897713 | 30215626 | 502 | 28.10.2015 | 30.04.2016 | 95 | 47 | 3726513 |  | IFAD-1 | Completed WRS completed. O&M Shed completed. Embankment work not yet completed. Will be completed by December 2016. | 60190.49
31 | 45179 | Karam Ali Chhara | Chittagong | Lohagara | WRS (4-V 1.50m X 2.0m) WMCA Office | KBI-A&C JV Chowdhury Market (2nd Floor), Dulhazra, Chakaria, Cox,sbazar | 29.09.2015 | 31.10.2016 | 25031214 | 22290531 | 11000000 |  | 74 | 60 |  | 36816 | 1 | 36816 | 22327347 | 450 | 08.10.2015 | 30.04.2016 | 30 |  |  |  | IFAD-2 | 1st lift wing wall done. Will be completed by February 2017. | 49616.3267
32 | 46244 | Tulsi-Trimohony-Bhaduria | Dinajpur | Nawabganj | 3 Khal (14.455+2.76+1.772) = 18.985 Km WRS (4-V 1.50m X 2.00m) & 3-V 1.50m X 2.00m) = 2 2 Irrigation pucca drain = 245m WMCA Office = 1 | Md. Nurul Islam North Balubari, Dinajpur. | 19.12.2016 | 18.01.2017 | 24050386 | 20373544 |  |  | 20 |  |  | 17583912 | 38 | 17583912 | 37957456 | 994 | 02.12.2015 | 30.04.2016 | 100 | 43 | 7586000 |  | ADB | Post work measurement will be taken after RLS done. Structure work ongoing | 38186.5755
33 | 45188 | Subidpur | Chandpur | Faridganj | 2 Khal = 3.2 km Pucca drain = 3790m | SB-NTS. JV Chandpur Sadar, Chandpur | 17.09.2015 | 21.02.2017 | 22646646 | 20154457 | 8595565 |  | 75 | 43 |  | 1799568 | 4 | 1799568 | 21954025 | 680 | 22.03.2015 | 30.04.2015 | 100 | 78 | 1413367 |  | IFAD-1 | Quality problem. Field visit done & report not satisfactory. RLS not as per design. (O&M Shed land not yet registered) | 32285.3309
34 | 44142 | Borka Khal | Panchagram | Sadar | * 8-vent WRS * 6.50 km Khal * O&M Shed | M/S Sheik Trader’s Panchagarm bazaar, Panchagarm. | 24.05.2015 | 02.03.2017 | 18946096 | 20096796 | 11140756 |  | 100 | 55 | 0082 | 3481050 | 9 | 3481050 | 23577846 | 980 | 26.01.2015 | 30.04.2015 | 100 | 80 | 2726352 | 62 | IFAD-1 | Completed. Post work measurement done. WRS completed. | 24059.0265
35 | 44093 | Paschim Joar | Chittagonj | Mirersarai | RCC Pucca Drain O&M Shed (12m X 6m) | M/S Rahim Uddin Chagoinaya, Feni. | 01.06.2014 | 31.12.2015 | 16481394 | 19665853 | 15500000 |  | 95 | 95 | 195 |  |  |  | 19665853 | 250 | [6 empty] | ADB | Completed | 78663.412
36 | 43060 | Ponahura FMD & WC | Patuakhali | Bauphal | 1 WRS (2V-1.2m X 1.5m) 3 Outlets (1V-.06m dia 1 no. (2V-.09m dia 2 nos.) 1 Inlet (1V-.09m dia) FC structure (1V-.09m dia) 2 Khal Embankment (4.46 km) WMCA Office (12.0m X 6.0m) | Abul Kalam Azad Azad Bhaban Muslimpara, Patuakhali | 04.08.2013 | 03.02.2015 | 15871674 | 19360395 | 19129912 | 100 | 100 | 100 | 0033 | 7338190 | 14 | 7338190 | 26698585 | 370 | 27.02.2013 | 30.04.2013 | 100 | 100 | 7282102 | 0051 | IFAD-1 | Completed & Handed over | 72158.3378
37 | 45210 | Char Parbati | Noakhali | Companiganj | Regulator (3V- 1.5m X 1.8m) = 1 (2-V 1.5m X 1.8m) = 1 WMCA Office = 1 | The New Trader Link & A H M (JV) Bhuiyan Plaza, Hajiganj, Chandpur | 08.03.2016 | 14.03.2017 | 17609434 | 19191432 | 12479146 |  | 73 | 65 |  | 8739891 | 19 | 8739891 | 27931323 | 860 | 26.01.2015 | 30.04.2016 | 80 | 53 | 4599870 |  | ADB | Base casting & 1st lift done for both WRS. O&M Shed not started. | 32478.2826
38 | 45207 | Dublai Bhadrabati | Bogra | Sherpur | WRS 4-vent (1.5m X 1.8m) = 1 Box culvert 4-vent (4m X 4m) = 1 WMCA Office = 1, Khal = 14.30 km | M/S S. Enterprise Sultangonjpara, Bogra | 16.03.2016 | 22.03.2017 | 17389526 | 18889405 | 2958420 |  | 35 | 16 |  | 15520185 | 28 | 15520185 | 34409590 | 508 | 24.12.2015 | 30.04.2016 | 90 | 62 | 9654714 |  | IFAD-1 | work is on going | 67735.4134
39 | 44133 | Gohelapur Shafiqpur | Naogaon | Raninagar | * 2 Box culvert * 2 nos. WRS * 9.50 km khal * O&M Shed | S & S JV, Santahar, Bogra | 30.08.2015 | 29.08.2016 | 15739691 | 18561110 | 9449642 |  | 70 | 51 | 0090 | 13265065 | 27 | 13265065 | 31826175 | 892 | 26.11.2014 | 30.04.2015 | 100 | 68.33 | 8993651 | 51 | IFAD-1 | work is going on | 35679.5684
40 | 46215 | Char Kakra | Noakhali | Companiganj | WRS =1 5 Khal = 13.97 km Link road = 1.2 Km WMCA Office = 1 | The New Trade Link AHM (JV) | 30.05.16 | 27.02.17 | 16788456 | 18460536 |  |  | 35 |  |  | 3308266 | 11 | 3308266 | 21768802 | 995 | 19.01.2016 | 30.04.2016 |  | 10 | 329661 |  | ADB | work is ongoing | 21878.193
41 | 46225 | Sendra-Belchow | Chandpur | Hajipur | 4 Khal = 6.16 km 1 Pucca line Canal = 3.5 km WMCA Office = 1 | M/S Ahsan Habib (Arun) Hazigonj Maddabazar, Chandpur | 22.03.2016 | 27.02.2017 | 18242833 | 18223990 |  |  | 60 |  |  | 3069414 | 8 | 3069414 | 21293404 | 505 | 15.01.2016 | 30.04.2016 | 80 | 23 | 700000 |  | ADB | Pucca drain 1700m done. RLS not done. WMCA work ongoing | 42165.1564
42 | 44074 | Swarupdaha Dhunar Khal | Jessore | Chowgacha | * 5V Regulator (modified bridge) * 2V Regulator (modified bridge) * 2 Khal 1.2 km * O&M Shed | M/S Kumkum Enterprise, Nowapara, Ghop, Jessore | 12.11.2013 | 11.05.2014 | 16885289 | 18181992 | 16660650 |  | 100 | 100 | 0145 | 900061 | 2 | 900061 | 19082053 | 841 | 07.11.2013 | 30.04.2014 | 100 | 100 | 810347 | 0177 | ADB | Completed | 22689.7182
43 | 44082 | Volda Beel | Manikgonj | Singair | Khal, Embankment, Regulator-1 Pipe sluice-1 Modification-1 WMCA-1 | Nabila & Nirman (JV) 137/12, A/B-4, Priagan R/A, Mirpur Dhaka. | 17.11.2014 | 16.11.2015 | 15869860 | 18114956 | 5372295 |  | 80 | 50 | 0231 | 9149833 | 21 | 9149833 | 27264789 | 529 | 23.02.2014 | 30.04.2014 | 100 | 94 | 9080200 | 164 | ADB | O&M Shed completed. WRS work ongoing. Will be completed by December 2016. | 51540.2439 | ,
44 | 46260 | Badar Mokam Khal | Feni | Sonagazi | WRS = 1 (4V-1.5m X 1.8m) Khal = 11.00 km Check structure = 2-vent WMCA Office = 1 | SA-SE (JV) Masterpara, Feni | 09.03.2017 | 27.02.2017 | 16679076 | 18030670 | 2315000 |  | 35 | 13 |  | 19269363 | 40 | 19269363 | 37300033 | 825 | 23.11.2016 | 30.04.2016 | 95 | 69 | 13291088 |  | ADB | Structure work is ongoing | 45212.1612
45 | 45156 | Orain Gulicho Naogaon | Comilla | Chandina | 2 WRS (3V-1.5m X 1.8m) (1V-1.5m X 1.5m) 3 Khals = 13.425 km WMCA Office | M/S M. M. Enterprise Chandina, Comilla | 06.07.2015 | 05.07.2016 | 16805994 | 17600620 | 9400000 |  | 85 | 53 | 0261 | 8030554 | 17 | 8030554 | 25631174 | 1000 | 30.03.2015 | 30.04.2015 | 60 | 48 | 3895888 |  | ADB | 3vent Regulator Top slab, 1 vent Regulator top slab & Protective work, Column casting & Brick work complete and WMCA Land Problem | 25631.174
46 | 44129 | Treemohani | Dinajpur | Nawabganj | * 6-vent WRS modification * 2-vent WRS * 2-vent WRS (to be dropped) * 8.80 km Khal * 1 O&M Shed | Md. Nurul Islam Uttar Balubari, Sadar, Dinajpur. | 06.01.2015 | 05.07.2016 | 15952145 | 17503781 | 8440000 |  | 85 | 48 | 0079 | 6662797 | 17 | 6662797 | 24166578 | 820 | 15.10.2014 | 30.04.2015 | 100 | 70 | 4663679 | 69 | IFAD-1 | Rubber seal be replaced. One WRS not done. May be dropped. Hoisting device of both 6V & 2V truss of shed be rectified . | 29471.4366
47 | 43032 | Chalk Temukh Islamgati | Nogaon | Atari | * 3-vent WRS * 6.80 km khal * O&M Shed | M/S Podder Construction 227, Lalbazar, Nator. | 21.07.2013 | 20.01.2015 | 16912095 | 16908441 | 13082181 |  | 100 | 77 | 0025 | 6747334 | 12 | 6747334 | 23655775 | 740 | 19.11.2012 | 30.04.2013 | 100 | 100 | 6277622 | 0013 | IFAD-1 |  | 31967.2635
48 | 44128 | Garur Khal | Laxmipur | Sadar | - Khal = 3.85 km with RL 4 nos. '- 2-V WRS (1.5m X 1.8m) - O&M Shed - Pucca Drain = 2.05 km | Mohammed Eunus & Brothers (PVT) LTD. Panchlaish, Chittagong | 26.11.2014 | 25.11.2015 | 15496314 | 16761968 | 12132359 |  | 75 | 72 |  | 5874283 | 12 | 5874283 | 22636251 | 690 | 19.11.2014 | 30.04.2015 | 85 | 65 | 3825885 | 188 | ADB | LCS work completed. Blocks are not good. To replace. Will be completed by December 2016. | 32806.1609
49 | 46266 | Nalshisha Khal | Dinajpur | Nawabganj | * 6V WRS (1.5m X 2.0m) * 10.40 km Khal * 1 O&M Shed. | M/S SR Group (JV) North Balubari, Dinajpur | 04.03.2016 | 27.02.17 | 15544376 | 16518652 |  |  | 40 |  |  | 12575940 | 26 | 12575940 | 29094592 | 650 | 20.12.2015 | 30.04.2016 | 100 | 65 | 8087506 |  | IFAD-1 | Post work measurement be taken. RLS done. WRS not started. O&M also not started. | 44760.9108
50 | 43061 | Bhagalpur Montola | Sirajgonj | Ullapara | * 4.6 km Khal 3 nos. 3-vent gated structures * 13.50 km embankment * O&M Shed | Sirajul Islam Datta bari Road, Sirajgonj | 02.07.2013 | 01.07.2014 | 14224238 | 16491491 | 15617930 |  | 100 | 100 | 0021 | 26709292 | 58 | 26709292 | 43200783 | 714 | 22.08.2013 | 30.04.2014 | 100 | 100 | 25569759 | 0022 | IFAD-2 | Completed & Handed over | 60505.2983
51 | 46261 | Sreerampur | Chapai Nawabganj | Sadar | RCC irrigation canal = 4145m Cross drain wit pipe = 2 Pumping platform with stair = 1 WMCA Office = 1 | Sanitary Museam Raipara, Rajshahi | 08.05.2016 | 14.05.2017 | 19772381 | 16375981.53 |  |  | 10 | [5 empty] | 16375981.53 | 320 | [6 empty] | ADB | Only 300m canal done. Platform completed. O&M Shed not started | 51174.9423
52 | 44132 | Dakkin Char Ababil | Laxmipur | Raipur | * 4 Khal = 12.45 km. Km with RL 14 nos. * Irrigation Pucca drain = 2 km * 4 Box culverts (1V-3.0m X 3.0m, 1V-3.0m X 3.5m, 2V-3.0m X 3.0m & 1V-2.5m X 3.0m) * WMCA Office | M/S. Keya Enterprise 193 2nd colony, Mirpur-1, Dhaka | 05.03.2015 | 11.03.2016 | 14779314 | 16159031 | 8000000 |  | 70 | 49 | 0063 | 10207036 | 22 | 10207036 | 26366067 | 940 | 20.11.2014 | 30.04.2015 | 25 | 10 | 974596 | 48 | IFAD-2 | Lined canal done. Out of 4 only 1 culvert to be executed but not yet started. O&M Shed started but construction delayed. . | 28049.0074
53 | 45208 | Tulsiganga Khal | Dinajpur | Birampur | * 3V WRS (1.5m X 1.8m) * 2V WRS * 9.10 km Khal * 1 O&M Shed. | M/S Rafiqul Islam North Balubari, Dinajpur | 14.12.2015 | 22.12.2016 | 17921610 | 15969266 | 8949000 |  | 80 | 56 |  | 4277965 | 12 | 4277965 | 20247231 | 600 | 08.12.2015 | 30.04.2016 | 70 | 45 | 1925130 |  | ADB | Structural work completed. Gate & block not fitted. O&M Shed not started. | 33745.385
54 | 44089 | Sindurpur Sekanderpur | Feni | Daganbhuya | 2 Khal = 1.86 km Embankment = 2.51 km 2 Regulator = (ch. 0+103 & 0+935 km WMCA Office | Techbay International 46 Arambagh, Motijheel, Dhaka. | 10.03.2014 | 09.09.2015 | 13214151 | 15730637 | 11606870 |  | 95 | 74 | 191 | 2988083 | 8 | 2988083 | 18718720 | 680 | 26.11.2013 | 30.04.2014 | 85 | 81 | 2430500 | 170 | ADB | Floor casting of O&M Shed still pending. Variation with ADB. Modification of design for embankment done. Approving of regulator approach sent to PD for administration approval. | 27527.5294
55 | 46229 | Patanish Noupara Khal | Chandpur | Hajigonj | 2 Khal = 4 Km RCC Irrigation Canal = 3.65 km WMCA Office = 1 | M/S Rohidas Banik Makimabadh Hazigonj Chandpur | 14.03.2016 | 27.02.2017 | 16136430 | 15636104 | 1898723 |  | 65 | 12 |  | 3006386 | 7 | 3006386 | 18642490 | 506 | 07.01.2016 | 30.04.2016 | 0 |  |  |  | ADB | 1500m Pucca drain completed. LCS work not started. WMCA Office Tin fixing ongoing. | 36842.8656
56 | 41001 | Nimai Khari Khal | Dinajpur | Sadar | Culvert-1 7V WRS (1.5 X 1.8m) O&M Shed-1 Khal = 8.372 km | M. Ehteshamul Haque, Jail Road, Dinajpur | 27.07.2011 | 26.07.2012 | 12956917 | 15489363 | 15000000 |  | 100 | 100 | 0006 | 3514708 | 12 | 3514708 | 19004071 | 850 | 26.04.11 | 30.04.2012 | 100 | 100 | 3512000 | 0014 | ADB | Copleted and handed over | 22357.7306
57 | 45176 | Dewra CAD | Comilla | Muradnagar | Khal = 7.62 km Repair existing regulator = 1 Box culvert (3.5m X 3.5m) = 1 WMCA Office | M/S Ha-Mim and Brithers South Sartha, Adarsha, Sadar Comilla | 08.09.2015 | 14.09.2016 | 14748606 | 15468364 | 10000000 |  | 75 | 65 |  | 712648 | 3 | 712648 | 16181012 | 200 | 25.03.2015 | 30.04.2015 | 90 | 48 | 346047 | 50 | IFAD-2 | Brick Line 400m running. Culvert not done. RL section not done. Not needed. WMCA land not available. Will be completed by December 2016. | 80905.06
58 | 45202 | Ramanadi-Kutubpur | Laxmipur | Sadar | 5 Irrigation Line canals = 3.25 km 5 road crossing WMCA office = 1 | Mohammad Eunus & Brothers Pvt. Ltd | 05.06.15 | 31.01.2017 | 13572815 | 15374768 | 1256462 |  | 60 | 8 |  |  |  |  | 15374768 | 228 | [6 empty] | ADB | 1700m lining canal completed. WMCA Office completed. | 67433.193
59 | 44094 | Chiri Khal | Joypurhat | Akkelpur | * 4-vent WRS * 2-Vent Box culvert * 7.80 km Khal * 1 O&M Shed | Ram Babu Gudri Bazar, Thakurgaon | 19.03.2014 | 18.09.2015 | 12633000 | 15359900 | 15313660 |  | 100 | 100 | 43 | 6152234 | 14 | 6152234 | 21512134 | 450 | 22.12.2013 | 30.04.2014 | 100 | 98 | 6036602 | 30 | IFAD-1 | Completed | 47804.7422
60 | 44102 | Bisha Udoypur | Naogaon | Atrai | * 3-vent WRS * 2.60 km khal * O&M Shed | M/S. Mamun, Kazipara Naogaon | 30.04.2014 | 29.04.2015 | 13194614 | 15340689 | 13790789 |  | 95 | 90 | 201 | 1073491 | 5 | 1073491 | 16414180 | 500 | 12.10.2014 | 30.04.2015 | 92 | 30 | 570937 | 182 | ADB | WRS wheel guard need relocation. RLS pending. Furniture pending. Revised drawing under way | 32828.36
61 | 44119 | Bangla Bazar-Gopalpur | Noakhali | Begumganj | * 3-vent Regulator = 1 * Khal = ……….. * O&M Shed = 1 | M/S Md. Mahamudur Rhaman Master Para, Maijdeebazar, Noakhai | 02.04.2015 | 01.04.2016 | 13012782 | 15335999 | 1457675 |  | 100 | 97 | 0084 | 5002926 | 13 | 5002926 | 20338925 | 690 | 01.02.2014 | 30.04.2015 | 80 | 50 | 2500000 | 62 | IFAD-1 | Structure completed. Protection of bridge approach done. Variation needed. | 29476.7029
62 | 44121 | Kalitala-Kashmahal | Chapai-Nawabganj | Sadar | Header Tank = 2 Aquiduct = 2 RCC pipe =850m UPVC pipe = 850m Distribution pipe …, Pond = 2 O&M Shed = 1 | M/S Sanitary Museum Biswas Super Market More, Rajshahi | 15.09.2014 | 21.03.2016 | 19566445 | 15269345 | 13123000 |  | 94 | 86 | 187 |  |  |  | 15269345 | 388 | [6 empty] | ADB | Header Tank Completed. O&M shed ongoing | 39353.982
63 | 44130 | Purandar Vushan Chander BariSarbesar Ghat | Gaibandha | Gobindaganj | * WRS (4V-1.5 X 1.8m) * Box culvert (4V-3.5 X 3.5m) * 4.10 km khal * WMCA Office | Md. Abdul Latiff Hakkani (JV) Bridge Road, Gaibandha | 24.11.2014 | 23.11.2015 | 13793343 | 14965258 | 12821216 |  | 100 | 85 | 0066 | 3896323 | 8 | 3896323 | 18861581 | 500 | 10.11.2014 | 30.04.2015 | 100 | 100 | 3836049 | 40 | IFAD-2 | Completed Minor finishing work needed | 37723.162
64 | 45162 | Pukurdia-Naldugi | Laxmipur | Sadar | Regulator = 1 (2V-1.5m X 1.8m) Pucca Irrigation Canal = 1.35 Km 1 Khal = 6.825 Km with RL 8 nos. WMCA Office = 1 | M/S Keya Enterprise 193, 2nd Colony, Mirpur Dhaka-1216. | 17.09.2015 | 23.09.2016 | 13832487 | 14921666 | 1058276 |  | 25 | 7 |  | 5741186 | 12 | 5741186 | 20662852 | 640 | 18.02.2016 | 30.04.2016 | 65 | 43 | 2453379 |  | ADB | WRS work is has started after settlement with the people of Noakhali Sadar. Revise design done . Work ongoing. | 32285.7062
65 | 43028 | Sapdanga Khal WC & DR | Pabna | Atghoria | * 3-vent WRS * 2-vent WRS * 4.10 km khal * 1 O&M Shed | Md. Zinnat Ali Zinnah Patikiabair, Pabna | 22.08.2013 | 20.06.2015 | 14847180 | 14863189 | 12980627 |  | 100 | 87.33 | 0020 | 1402802 | 3 | 1402802 | 16265991 | 650 | 06.02.2013 | 30.04.2013 | 100 | 100 | 1344000 | 0033 | IFAD-2 | Complete | 25024.6015
66 | 44134 | Harabati Khal | Joypurhat | Khetlal | 4-vent WRS Box culvert 4.70 km Khal O&M Shed. | Rambabu & Kalicharan Agarwala (JV), Old Hospital Road, Joypurhat | 25.11.2014 | 24.11.2015 | 13336456 | 14828475 | 8223613 |  | 80 | 55.45 | 0058 | 8022197 | 17 | 8022197 | 22850672 | 550 | 18.11.2014 | 30.04.2015 | 100 | 97 | 7769923 | 42 | IFAD-2 | WRS completed. Box culvert & O&M stared will be completed by January 2017 | 41546.6764
67 | 43072 | Pathuria Kalibari | Bagethat | Morelgonj | * 2 Regulators * 2 Closers * 2 Khals 3.76 km * Embankment 7.5 km * O&M Shed | M/S Shahid Enterprise Musgunni, Khulna. | 10.11.2014 | 09.11.2015 | 12943509 | 14705932.8 | 12758578 |  | 85 | 84 | 0202 | 13998671 | 31 | 13998671 | 28704603.8 | 375 | 12.11.2013 | 30.04.2014 | 100 | 100 | 13694496 | 0149 | ADB | Completed Revised estimate done & O&M Shed work ongoing | 76545.6101
68 | 42014 | Udura Khal | Chandpur | Kachua | - Irrigation Canal using FC Sheets = 3.65 km - One culvert - O&M Shed - Khal | M/S. A.G.A NT (JV), Dowlatpur, Kachua, Chandpur | 01.08.2013 | 31.07.2013 | 12740586 | 14572034 | 13804989 |  | 100 | 100 | 0039 | 7039472 | 14 | 7039472 | 21611506 | 997 | 15.10.2012 | 30.04.2013 | 100 | 100 | 6815600 | 0014 | IFAD-1 | Completed To be handed over by 15 October 2016. | 21676.5356
69 | 45191 | Ghoraband Khal | Dinajpur | Birganj | * 3V Regulator (1.5m X 1.8m) * Box culvert (2-vent) * Drainage outlet * 1.015 km Embankment 0.41 km Khal * 1 O&M Shed. | AH-NS (JVC) Nimtola, Dinajpur. | 09.08.2015 | 08.08.2016 | 13448036 | 14451372 | 8611000 |  | 95 | 60 |  | 772651 | 3 | 772651 | 15224023 | 400 | 18.01.2016 | 30.04.2016 |  |  |  |  | IFAD-2 | Regulator comleted except gate. Embankment not touched. O&M Shed done except tin fixing. Will be completed by February 2017. | 38060.0575
70 | 46271 | Jhanior Parbhabanipur | Bogra | Sherpur | O&M Shed = 1 RCC U drain = 120m WRS 3-vent (1.5m X 2.0m) | M/S Nahid Enterprise | 10.04.2016 | 14.04.2017 | 13389240 | 14423573.08 | 6183263 |  | 60 | 43 |  | 5563387 | 13 | 5563387 | 19986960.08 | 306 | 26.01.2016 | 30.04.2016 | 95 | 57 | 3144925 |  | IFAD-1 | work is going on | 65316.863
71 | 44098 | Sikta Madai | Joypurhat | Kalai | * 3-vent Box culvert * 3-vent WRS (1.5mX1.8m) * 1 O&M Shed, * 6.50 km Khals | Md. Jannat Ali Zinnah, Patkibari, Hemayetpur, Pabna | 23.04.2014 | 22.10.2015 | 12546514 | 14408915 | 9885685 |  | 85 | 69 | 50 | 3420475 | 7 | 3420475 | 17829390 | 415 | 22.12.2013 | 30.04.2014 | 100 | 95 | 3236999 | 31 | IFAD-1 | Box culvert done. WRS done CC block/Flag not done and O&M shed start | 42962.3855
72 | 44113 | Jhirai Bridge-Jangalpara Khal | Gaibandha | Gobindaganj | * WRS (4V-1.5m X 2.0m) * 6.68 km Khal * WMCA Office (12.0m X 6.0m) | M/S Aminul Momin (JV) Gobindaganj, Gaibandha | 24.11.2014 | 23.11.2015 | 13369015 | 14403817 | 7742824 |  | 100 | 54 | 0087 | 6126037 | 12 | 6126037 | 20529854 | 440 | 08.04.2014 | 30.04.2014 | 100 | 100 | 5975616 | 73 | IFAD-1 | Completed Minor rectification needed. Will be completed by December, 2016. | 46658.7591
73 | 45196 | Dighdaria | Natore | Gurudaspuri | Embankment = 3.75 km 2 Regulators [(2V-1.50m X 1.80m), (1V-1.50m X 1.80m)] 1 Box culvert (2V-2.00m X 2.50m) WMCA Office including rain water harvesting, electrification, office furniture | Mir. Habibul Alam & M/S Tazul Islam (JV), Uttar Boragacha, Natore | 14.02.2016 | 19.02.2017 | 13648458 | 14327796 | 0 |  | 15 |  |  | 10339610 | 21 | 10339610 | 24667406 | 360 | 03.11.2015 | 30.04.2016 | 80 | 48 | 5000000 |  | IFAD-1 | Lay out done by WMCA & Base casting complete of Regulator -1V | 68520.5722
74 | 42017 | Nabinpur-Dholar Beel | Meherpur | Gangni | * 3V Regulator * 2 Culvert * 5 pipe culverts * O&M Shed | Md. Noor Hossain, Puraton Kashba,Jessore | 02.01.2013 | 01.01.2014 | 12177803 | 13796661 | 9599340 |  | 100 | 73 | 0109 | 3362200 | 11 | 3362200 | 17158861 | 932 | 10.11.2012 | 30.04.2013 | 100 | 100 | 3700000 | 0057 | ADB | Completed | 18410.7951
75 | 43073 | Tumchar-Kalirchar | Laxmipur | Sadar | - 1 Khal = 1.8 km '- 2-V WRS (1.5m X 1.5m) - O&M Shed - Irrigation Drain = 1.6 km | M/S Keya Enterprise 193-2nd Colony, Mirpur, Dhaka-1216. | 18.05.2014 | 24.11.2015 | 13233315 | 13795548 | 947716 |  | 50 | 6 | 0056 | 2109439 | 5 | 2109439 | 15904987 | 423 | 12.12.2013 | 30.04.2014 | 100 | 66 | 1400000 | 0037 | IFAD-1 | WRS Dropped. Contractor did unspecified lining of canal work which has been rejected. Revised planning submitted to XEN to settle with contractor & WMCA. O&M Shed completed but furniture not given. O&M Shed floor cracked and need rectification. | 37600.4421
76 | 44139 | Bhadrabati-Tilkatala | Bogra | Sherpur | * 5-vent WRS (1.5m X 1.8m), * 6 km khal, * 1 O&M shed. | M/S. M. Enterprise Sultangonjpara, Bogra | 02.02.2015 | 01.02.2016 | 12595518 | 13780885 | 5743036 |  | 55 | 42 | 0079 | 9470264 | 20 | 9470264 | 23251149 | 600 | 11.11.2014 | 30.04.2015 | 95 | 57 | 5376840 | 53 | IFAD-1 | work on going | 38751.915
77 | 46256 | Adhaipur-Bailanthapur Khal | Naogaon | Badalgachhi | 2 Khal = 1.45 km Regulator = 1 (3V-1.5m X 1.8m) Culvert = 1 (1V-2.0m X 3.0m) WMCA Office = 1 | M/S Mamun, Kazipara, Naogaon | 19.0516 | 24.05.17 | 12516587 | 13689960 |  |  | 20 |  |  | 1053823 | 4 | 1053823 | 14743783 | 410 | 26.01.2016 | 30.04.2017 | 0 |  |  |  | ADB | LCS work can't be done due to social conflict and land problem. Structure work on going | 35960.4463
78 | 45209 | Gopinathpur Beel | Manikgonj | Harirampur | 2 Khal = 5.00 km Regulator (2V- 1.5m X 1.8m) WMCA Office = 1 | AC-KSA (JV) West Alipur, Faridpur | 06.03.16 | 05.03.17 | 14219081 | 13499996 | 7784000 |  | 77 | 58 |  | 10201632 | 21 | 10201632 | 23701628 | 795 | 04.01.2016 | 30.04.2016 | 100 | 65 | 6653200 |  | IFAD-1 | work is ongoing | 29813.3686
79 | 46230 | Uthli-Jayantihazara Mashalia | Kushtia | Khoksha | 5 Khal 7.39 Km 2 WRS (1V-1.5m X 2.0m)), 2V-1.5m X 1.8m) 2 Box culvert (1V-4.0m X 3.7m) & (1V-3.0m X 3.0m) WMCA Office (12m X 6m) WMCA Office | F.E & M.M. (JV), Jagoti Rail gate Jagoti, Kushtia | 26.01.2016 | 28.02.2017 | 12864498 | 13447929 | 9714930 |  | 90 | 72 |  | 3412126 | 10 | 3412126 | 16860055 | 950 | 29.01.2016 | 30.04.2016 | 100 | 59 | 2003891 |  | ADB | Gate fitting pending. Electrification not done. | 17747.4263
80 | 44097 | Dudhal | Barisal | Bakerganj | 3 Khal embankment = 6.025 km (2V 1.2X1.8) Regulator, 2 pipe sluices. O&M Shed | Md. Mahafuj Khan, Nalchity, Bandar, Jhalakathi. | 20.05.2014 | 19.05.2015 | 11652481 | 13392979 | 10655262 |  | 90 | 80 | 192 | 9175785 | 13 | 9175785 | 22568764 | 415 | 22.12.2013 | 30.04.2014 | 100 | 100 | 8594000 | 156 | ADB | Completed Block placing, finishing work of O&M Shed pending. | 54382.5639
81 | 44137 | Nimaichara-Wapda Khal | Sirajgonj | Tarash | * O&M Shed * 25m bridge * 9.10 km khal | Serajul Islam Dattabari Road, Sirajgonj | 30.08.2015 | 09.10.2016 | 11303129 | 13123165 | 10557013 |  | 85 | 80 | 0071 | 8311808 | 20 | 8311808 | 21434973 | 790 | 11.11.2014 | 30.04.2015 | 100 | 100 | 8043701 | 42 | IFAD-2 | work is on going, O&M shed work is cancelled | 27132.8772
82 | 45158 | Raikhong Khal | Cox'sbazar | Teknaf | 2-vent WRS = 1 O&M Shed = 1 Khal = ? | KBI-A&C Joint Venture Dulahazara, Chakaria, Cox'sbazar | 16.04.2015 | 19.09.2016 | 12155893 | 13069475 | 5549130 |  | 60 | 40 | 0085 |  |  |  | 13069475 | 200 | [6 empty] | IFAD-1 | Work ongoing | 65347.375
83 | 45159 | Paner Chhara Purbakul | Cox'sbazar | Ramu | * 4-v WRS O&M Shed | KBI-A&C Joint Venture 2nd Floor Chowdury Market Dulahazara, Chakaria, Cox'sbazar | 16.04.2015 | 15.09.2016 | 12116178 | 13044043.44 | 10300000 |  | 90 | 78 | 0061 | 210588 | 1 | 210588 | 13254631.44 | 200 | 19.02.2015 | 30.04.2015 | 100 | 100 | 210372 |  | IFAD-2 | Completed Minor work remaining. | 66273.1572
84 | 46242 | Montala-Chaliapara | Chandpur | Faridganj | 3 Khal = 5.520 Km Box culvert (1V- 3.50m X 3.50m) = 1 9 Pucca drain = 1.600 Km WMCA Office = 1 | Appolo Engineering & Construction Ltd. Jabber Tower, 42 Gulshan Avenue, Dhaka-1212 | 23.03.2016 | 27.02.2017 | 12516444 | 12500048 |  |  | 0 |  |  | 5182628 | 13 | 5182628 | 17682676 | 460 | 06.01.2016 | 30.04.2016 | 90 | 45 | 2400000 |  | ADB | Final notice give for canceel. Post work measurment not done . | 38440.6
85 | 45178 | Kulpagli Chara | Chittagong | Lohagara | Khal = 0.50 Km Irrigation Line Canal no. 1 &2 = 0.660 Km = 660m angle Check Structure (1V-600m dia pipe WMCA Office = 1 (12.0m X 6.0m) | KBI-A&C JV Chowdhury Market (2nd Floor), Dulhazra, Chakaria, Cox,sbazar | 29.09.2015 | 31.10.2016 | 12071052 | 12483256 | 5800000 |  | 78 | 46 |  | 2465676 | 6 | 2465676 | 14948932 | 730 | 08.10.2015 | 30.04.2016 |  |  |  |  | IFAD-1 | Work ongoing. Will be completed by February 2017. | 20477.989
86 | 46263 | Khetrapara | Satkhira | Kalaroa | Embankment 2.5 Km Khal 1.3 Km 1 foot WRS 1 Bridge WMCA Office | M/A A. H Trading | 17.05.2016 | 15.022 | 12460493 | 12450082 |  |  | 5 |  |  | 5992606 | 12 | 5992606 | 18442688 | 536 | 17.01.2016 | 30.04.2016 | 70 | 53 | 3150690 |  | ADB | work is ongoing | 34408
87 | 43065 | Bhangakha-Nyamatpur | Laxmipur | Sadar | - 4 Khal = 8.325 km with RL 8 nos. '- Check Gates, Turnouts & Precast RCC Pipe '- 3 Foot Bridges - Pucca Drain = 3 km? - O&M Shed (12.00m X 6.0m) | M/S Keya Enterprise 193-2nd Colony, Mirpur, Dhaka-1216. | 01.09.2014 | 31.02.2016 | 11224265 | 12308166.95 | 11925180 |  | 95 | 96 | 0198 | 2649671 | 7 | 2649671 | 14957837.95 | 665 | 26.11.2014 | 30.04.2015 | 80 | 57.5 | 1523400 | 0200 | ADB | Completed. 5 RLS pending. Khal excavation completed. O&M Shed floor need reapair. | 22492.9894
88 | 45147 | Barkarai Derpar Kaduti | Comilla | Chandina | WRS (4V-1.5m X 2.0m ) Khal = 17.95 Km WMCA Office (12.0m X 6.0m) | M/S Akter Enterprise Burichong Comilla | 16.07.2015 | 21.07.2016 | 11606302 | 12154225 | 5300000 |  | 62 | 43 | 0238 | 8111721 | 18 | 8111721 | 20265946 | 1000 | 25.03.2015 | 30.04.2015 | 8 | 10 | 811173 |  | ADB | Base casting complete ,Side wall , Column & Brick wall complete and LCS work stoped due to over rain filled | 20265.946
89 | 46251 | Mundail Khal | Meherpur | Gangni | 2 Khal 1 Regulator 2 Culvert WMCA Office | Md. Golam Rasul Hotel Bazar, Meherpur | 01.05.2016 | 30.04.2017 | 12068702 | 11912403.79 |  |  | 15 |  |  | 4310957 | 10 | 4310957 | 16223360.79 | 800 | 03.11.2015 | 30.04.2016 | 95 | 42 | 1799521 |  | ADB | Earth work & structure work ongoing | 20279.201
90 | 45186 | Chasri Beel | Munshiganj | Tongibari | 1 Khal & RL, 2 WRS, WMCA Office, rain harvesting, electrification and furniture | M/S Golam Sarwor Rajpara, Rajshahi. | 26.04.2015 | 08.09.2016 | 11294008 | 11828029.52 | 9000000 |  | 90 | 76 |  | 512529 | 1 | 512529 | 12340558.52 | 380 | 07.04.2015 | 30.04.2016 | 100 | 100 | 512236 | 76 | IFAD-1 | Completed Gate filling pending. | 32475.154
91 | 44100 | Dighuli Kathali | Laxmipur | Sadar | - 4 Khal = 9.462 km '- 3-V Regulator (1.5m X 1.80m) - O&M Shed | M/S. Josna International 12/B, 6/106, Mirpur, Dhaka-1216. | 13.10.2014 | 27.06.16 | 10796008 | 11686950 | 6081164 |  | 75 | 52 | 203 | 11525348 | 22 | 11525348 | 23212298 | 705 | 14.03.2015 | 30.05.2015 | 75 | 39 | 4435056 |  | ADB | WRS deck slab due. O&M framework due. Khal work slow. 810m of Paschim Dighuli Khal LCS # 21 & 600m Purba Kata Khal LCS # 22 could not be done. Earth filling due. Revised drawing & estimate of O&M Shed. Floor not done for earth filling. | 32925.2454
92 | 45190 | Nababpur Kaliarchar | Comilla | Chandina | WRS (3-V 1.50m X 2.5m) 2 Khal = 5.02 Km WMCA Office (12.0m X 6.0m) | M/S M.M. Enterprise Chindina Kazibari, Chindina, Comilla. | 01.10.2015 | 30.09.2016 | 10846539 | 11623349 | 3111348 |  | 58 | 27 | 0091 | 3717650 | 9 | 3717650 | 15340999 | 860 | 02.04.2015 | 30.04.2016 | 52 | 46 | 1728677 |  | IFAD-1 | Base casting, Column, & Brick work complete and LCS work stoped due to over rain filled up water | 17838.3709
93 | 43035 | Goal Kandi-Daturbari | Gaibandha | Gobindagonj | * Modification of RCC bridge into WRS (4V-1.5 X 1.8m) * 5.00 km khal * 1 WMCA Office (12.0m X 6.0m) | M/S. Ritu Enteprise Sonatola Bogra | 28.04.2014 | 27.10.2015 | 10542672 | 11567193 | 7704948 |  | 100 | 66 | 0058 | 8061414 | 18 | 8061414 | 19628607 | 500 | 10.01.2013 | 30.04.2013 | 100 | 100 | 4931021 | 0018 | IFAD-1 | Completed & Hannded over | 39257.214
94 | 41002 | Purba Sarail Madai Khal | Joypurhat | Kalai | 2 WRS Khal excavation | Ram Babu, Gudhuri Bazar, Thakurgaon | 18.08.2011 | 20.02.2013 | 9973530 | 11416804 | 11416000 |  | 100 | 100 | 0008 | 3989771 | 10 | 3989771 | 15406575 | 732 | 29.11.11 | 30.04.12 | 100 | 100 | 3946136 | 0018 | ADB | 1 | 21047.2336
95 | 45206 | Mithakhali | Pirijpur | Mathbaria | Regulator 1 Pucca Drain 2 Box culver 1 WMCA Office | M/S Ahmed Steel Industries. | 13.04.16 | 25.04.17 | 11269480 | 11251671 | 4249660 |  | 60 | 38 |  | 11105076 | 25 | 11105076 | 22356747 | 550 | 15.11.2015 | 30.04.2016 | 100 | 98 | 10928431 |  | ADB | Earth work completed. Structure work ongoing | 40648.6309
96 | 44112 | Harirmpur Beel | Meherpur | Sadar | 2 Khal, Rehabilitation of Box culvert for WRS Embakment (HBB road) | Md. Golam Rasul, Hotel Bazar, Meherpur | 03.09.2014 | 02.09.2015 | 10082300 | 10868329 | 7729911 |  | 100 | 71 | 217 | 2819648 | 8 | 2819648 | 13687977 | 396 | 07.04.2014 | 30.04.2014 | 100 | 100 | 3395000 | 170 | ADB | Earth work Completed. Structure minor work pending | 34565.5985
97 | 43057 | Adabaria | Patuakhali | Bauphal | 1 WRS (1V 1.5m X 1.8m) 2 Outlet (dia 0.90m) Embankment 4.6 km 1 Khal 2.3 km WMCA Office (12.0m X 6.0m) | Mohiddin Ahmed Muslimpara, Patuakhali | 03.09.2013 | 02.09.2014 | 9328556 | 10732471 | 10050871 | 100 | 100 | 100 | 0028 | 3950385 | 9 | 3950385 | 14682856 | 270 | 19.03.2013 | 30.04.2013 | 100 | 100 | 3918138 | 0013 | IFAD-2 | Completed & Handed over | 54380.9481
98 | 42027 | Nuruddin Khal | Pabna | Sujanagar | * 2.58 km Khal * 2-vent WRS * 1-vent Box Culvert * 1 O&M Shed | M/S Tushar Enterprise Radhanagar Eidga Road, Pabna | 18.02.2013 | 18.02.2014 | 10682406 | 10652297 | 8940642 |  | 100 | 83.93 | 0083 | 2304577 | 5 | 2304577 | 12956874 | 235 | 15.10.2012 | 30.04.2013 | 100 | 100 | 1800000 | 0015 | IFAD-1 | O&M shed droped & Regulator incoplete | 55135.634
99 | 45194 | Bhigram-Sirota | Joypurhat | Panchbibi | WRS 3-vent = 1 Drainage excavation = 450m WMCA Office = 1 Khal 6.40 km | Ram Babu & Kalicharan Agarwala (JV) Old Hospital Road Joypurhat | 26.01.2016 | 03.02.2017 | 9417682 | 10585118 | 8634121 |  | 85 | 81 |  | 5014911 | 12 | 5014911 | 15600029 | 600 | 03.11.2015 | 30.04.2016 | 100 | 93 | 4668749 |  | IFAD-2 | WRS Completed. Drainage outlet not required. WMCA office work one going | 26000.0483
100 | 45192 | Sanka Moni Beel | Dinajpur | Birganj | * 2V WRS (1.5m X 1.8m) * Box culvert * 4.10 km Khal (dropped) * 1 O&M Shed. | Md. Nurul Islam North Balubari, Dinajpur. | 14.09.2015 | 23.03.2017 | 10097281 | 10546085 | 4050000 |  | 80 | 38 |  | 2506772 | 6 | 2506772 | 13052857 | 460 | 27.01.2015 | 30.04.2016 |  |  |  |  | ADB | Khal under case may be dropped. WRS gate not fitted. Box culvert not started. O&M Shed not started as land not yet managed. | 28375.7761
101 | 41010 | Swarna Khali Khal | Dhaka | Dhamrai | -2-V Regulator - O&M Shed - Re-excavation of Khal and Re-sectioning of embankment | M/S. Josef Enterprise Pathantola, Dhamrai, Dhaka | 21.11.2012 | 27.08.2013 | 8256626.12 | 10437714 | 8570000 |  | 100 | 100 | 0078 | 1689258 | 7 | 1689258 | 12126972 | 370 | 09.01.12 | 30.04.2012 | 100 | 100 | 1347000 | 0028 | ADB | Revised 0.05% less | 32775.6
102 | 44099 | Nona River | Dinajpur | Birol | * 3-vent WRS (1.5 X 2.00m) * 9.40 km khal * 1 O&M Shed | Sahed Hassain Chowdhury, North Balubari, Dinajpur | 15.06.2014 | 13.06.2015 | 8983488 | 10304054 | 6034000 |  | 80 | 58 |  | 6460456 | 13 | 6460456 | 16764510 | 436 | 29.01.2014 | 30.04.2014 | 75 | 44 | 2901105 | 32 | IFAD-2 | Gate of WRS not fitted. Work is ongoing. RLS not done. Land for shed not received. Shed may be dropped. | 38450.711
103 | 44107 | Amail Indail | Bogra | Adamdighi | * 2-vent WRS(1.5mX1.8m) * 6 km Khal * 1 O&M Shed | M/S Mamun Kazipara, Neogaon | 17.07.2014 | 16.07.2015 | 9342728 | 10261218.61 | 10177274 |  | 100 | 100 | 64 | 6351897 | 19 | 6351896 | 16613114.61 | 545 | 19.03.2014 | 30.04.2014 | 100 | 82 | 5177459 | 41 | IFAD-1 | Structure work Completed & hand over. LCS work final bill under process | 30482.7791
104 | 43063 | Katurakandi Khal | Jessore | Bagherpara | * 2V Regulator * 1 Khal 1.0 km * O&M Shed | Md. Noor Hossain Puratan,Kashba, Mission Para, Jessore | 26.06.2013 | 03.01.2015 | 9425666 | 10238926 | 9264813 |  | 100 | 100 | 0024 | 349302 | 1 | 349302 | 10588228 | 750 | 05.05.2013 | 30.04.2014 | 100 | 100 | 349100 | 0045 | IFAD-1 | Completed & Handed Over | 14117.6373
105 | 44108 | Tiloch Iramati | Bogra | Adamdighi | * 1-vent box culvert (2.5m X 2.5m) * 1-vent box culvert (2.5m X 2.5m) * 1-vent box culvert (3.00m X 3.00m) * WRS (1.5mX1.5m) = * 1.2 km Khal (main) * Branch khal 0.70 km * 1 O&M Shed | Md. Sohel Santahar, Adamdighi, Bogra | 21.07.2014 | 20.07.2015 | 8854170 | 10052576.54 | 9427551 |  | 100 | 94 | 0056 | 1621546 | 6 | 1621546 | 11674122.54 | 240 | 19.03.2014 | 30.04.2014 | 60 | 40 | 643235 | 36 | IFAD-2 | Structure work Completed & hand over. LCS work final bill under process | 48642.1772
106 | 43039 | Ghoghodima-Khatbatala | Chapai-N.Gonj | Sadar | * 1758m lined canal * 2 Aquiduct * 1 Siphon * 1 O&M Shed | Mark International Chapai Nawabgonj. | 04.06.2013 | 03.05.2014 | 9633129 | 10046439 | 10041210 |  | 100 | 100 | 0027 |  |  |  | 10046439 | 105 | [6 empty] | IFAD-1 | Completed & Hannded over | 95680.3714
107 | 42021 | Fasiakhali Irrigation | Cox's Bazar | Chokoria | - Irrigation Canal using FC Sheets inclding pamping platform = 2.9 km - Aqueduct (6.6m) - Pipe culvert (5m length) - Khal - Sump (pit) - O&M Shed | M/S Unnayan International Anderson Road, Cox'sbazar | 20.12.2012 | 19.12.2013 | 10513430 | 10027665.51 | 10013248 |  | 100 | 100 | 0133 |  |  |  | 10027665.51 | 358 | [6 empty] | ADB | Completed Some minor work at WMCA Office is pending. | 28010.2389
108 | 45189 | Nali-Badurtali | Pirojpur | Mathbaria | 8 Khals = 18.27 km WMCA Office = 1 Box culvert = 2 Irrigation canal = 2 | ASI-TBK (JV), Kapuriapatti, Mathbaria, Pirojpur | 13.04.16 | 25.04.17 | 10009857 | 9975156 | 4503000 |  | 70 | 45 |  | 16311792 | 35 | 16311792 | 26286948 | 920 | 15.11.2015 | 30.04.2016 | 100 | 98 | 16074959 |  | IFAD-2 | Earth work completed. Structure work ongoing | 28572.7696
109 | 45149 | Kishoree Beel | Thakurgaon | Haripur | * Regulator (2V-1.50m X 1.80m) * 1.95 km Khal * 1 WMCA Office | Md Jamal Hossain N, C Road Thakurgaon | 10.01.2016 | 16.01.2017 | 8954191 | 9898572 | 3548726 |  | 90 | 36 |  | 2217416 | 5 | 2217416 | 12115988 | 260 | 23.02.2015 | 30.04.2015 | 100 | 60 | 1323539 |  | IFAD-2 | Structure work running | 46599.9538
110 | 41011 | Noapara-Hazirdhara | Rajshahi | Puthia | * 2-vent WRS (1.5 X 1.8m) * 2-vent Box Culvert (4 X 4m) * 1 O&M Shed * Protection works of UP Office | I) M/S Mark International Namosankar Bati Chapainawabgonj II) Md. Imran Sunny, Mohisbathan, Rajshahi | 19.04.2012 | 04.02.2014 | 9398899 | 9848847 | 9219008 |  | 100 | 100 | 0044 | 1229666 | 3 | 1229666 | 11078513 | 682 | 08.01.12 | 30.04.2012 | 100 | 100 | 623000 | 0028 | ADB | Completed & Handed over | 16244.154
111 | 44105 | Kumira Beel | Narsingdhi | Raipur | Khal 3.200 Km = 3 LCS RL = 1 LCS Embankment = 1.430 Km= 2 LCS WRS (2V-1.5m X 1.5m ) = 1 O&M Shed = 1 | M/S Belabo Traders 36/1, Laxmipur, Bhairab, Kishoreganj. | 11.06.2014 | 30.05.2016 | 8359946 | 9606830 | 4354522 |  | 97 | 45 | 199 | 2555519 | 6 | 2555519 | 12162349 | 320 | 06.04.2014 | 30.06.2014 | 50 | 37 | 963854 | 170 | ADB |  | 38007.3406
112 | 43071 | Bokrabari | Rangpur | Mithapukur | * 2-vent WRS * 1 O&M Shed | MD. Harun or Rashid GMEK & Ameco Enterprise (JV) Radhaballave, Rangpur. | 25.02.2014 | 24.02.2015 | 7941031 | 9578053 | 8308410 |  | 100 | 88 |  | 8308410 | 10 | 5140447 | 14718500 | 353 | 14.11.2013 | 30.04.2014 | 100 | 70 | 3706641 | 0026 | IFAD-2 | LCS work completed. Post work measurment taken jointly by UE office, Xen office, SE office Representative persons. | 41695.4674
113 | 45169 | Betmore-Rajpara | Pirojpur | Mathbaria | 2 culvert, 2 drain 9 Khal, 15 km, 1 no. O&M Shed | FTR (JV) Kapuriatti, Mathbaria, Pirojpur | 07.12.2015 | 08.02.2016 | 9652476 | 9528365 | 5170712 |  | 60 | 54 |  | 13294000 | 31 | 13294000 | 22822365 | 930 | 09.02.2015 | 30.04.2015 | 100 | 97.75 | 1299567 | 62 | IFAD-1 | LCS work completed.Structure work ongoing | 24540.1774
114 | 46270 | Sirajpur | Noakhali | Companigonj | 3 Khal = 9.53 km WRS = 1 WMCA Office = 1 | M/S Don Corporation | 18.05.2016 | 27.02.2017 | 8666508 | 9516421 |  |  | 60 |  |  | 7056144 | 13 | 7056144 | 16572565 | 800 | 01.03.2016 | 30.04.2016 | 10 | 10 | 705607 |  | ADB | work is ongoing | 20715.7062
115 | 42013 | South-Gohat | Chandpur | Kachua | - Irrigation Canal using FC Sheets - O&M Shed - Khal = 9.60 km | AH-SE (JV) | 01.08.2013 | 31.07.2014 | 8196053 | 9396338 | 9093088 |  | 100 | 92 |  | 6024185 | 12 | 6024185 | 15420523 | 936 | 15.10.2012 | 30.04.2013 | 100 | 100 | 5613314 |  | IFAD-1 | Completed & Handed over | 16474.9177
116 | 44123 | Kamarpur-Adamdighi | Bogra | Adamdighi | * Box culvert 2-vent (4.5m X 4.5m) = 1 * 5-V WRS (Repair) (1.2m X 1.8m) = 1 * 6 km Khal | S & R-JV Santahar, Bogra | 13.11.2014 | 12.11.2015 | 7733252 | 9282603 | 5438411 |  | 95 | 62 | 71 | 6380436 | 13 | 6380436 | 15663039 | 620 | 16.11.2014 | 30.04.2015 | 95 | 55 | 3491189 | 53 | IFAD-1 | Block setting is one going | 25262.9661
117 | 45198 | Sukti Beel | Rajshahi | Mohanpur | Regulator (2-V 1.5m X 1.8m) WMCA Office (12.0m X 6.0m) Khal Re-excavation = 5.07 km | Md. Emran Sunny (JV) Mohisbathan, Rajshahi | 10.01.2016 | 27.02.2017 | 11674020 | 9089348 |  |  | 10 |  | 0280 | 5589524 | 15 | 5589524 | 14678872 | 350 | 20.10.2015 | 30.04.2016 | 90 | 39 | 2154000 |  | ADB | Regulator work on going, WMCA office Grade Beam & Column casting complete. LCS work stoped due rain filled | 41939.6343
118 | 46247 | Firoj Khal | Chandpur | Hajiganj | 3 Khal = 8.700 Km 5 RCC Irrigation Canal = 2.11 KM WMCA Office = 1 | M/S Ahsan Habib (Arun) Hazigonj Maddabazar, Chandpur | 22.03.2016 | 27.02.2017 | 9122766 | 9081892 |  |  | 60 |  |  | 8077499 | 23 | 8077499 | 17159391 | 708 | 02.02.2016 | 30.04.2016 | 50 | 20 | 1562390 |  | ADB | Work ongoing. | 24236.428
119 | 46264 | CharBhuta Hatem Ali | Laxmipur | Sadar | 2 Khal = 9.11 km with RL 7 nos. 11 RCC Canals = 1.95 Km WMCA Office = 1 (12.0m X 6.0m) | Mohammad Eunus & Brothers | 26.05.2016 | 31.01.2017 | 8935940 | 9067546 |  |  | 20 |  |  | 12739978 | 27 | 12739978 | 21807524 | 995 | 25.12.2016 | 27.02.2017 |  |  |  |  | ADB | WMCA office work is ongoing | 21917.1095
120 | 44110 | Bokradgara | Thakurgaon | Pirganj | * 3-vent WRS * 2.80 km Khal (rev.) * 1 O&M Shed | Ram Babu, Gudri Bazar, Thakurgaon | 17.09.2014 | 16.09.2015 | 9959142 | 8862743.46 | 5700897 |  | 90 | 64 | 57 | 1713125 | 5 | 1713125 | 10575868.46 | 662 | 04.04.2014 | 30.04.2015 | 100 | 65 | 1049547 |  | IFAD-1 | Structure work running | 15975.6321
121 | 42020 | Ulushikhal | Sirajgonj | Tarash | * 2-vent WRS * 1 O&M Shed | Serajul Islam Dattabari Road, Sirajgonj | 29.11.2012 | 28.11.2013 | 7406112 | 8802256 | 8800000 |  | 100 | 100 | 0012 | 7660358 | 15 | 7660358 | 16462614 | 650 | 15.11.2012 | 30.04.2013 | 100 | 100 | 7365000 | 0074 | IFAD-2 | Complete & Hand over | 25327.0985
122 | 43041 | Sonbunia Subproject | Barguna | Sadar | ….. Khal & O&M Shed | M/S . FH Enterprise & Shadin Enterprise, Sadar road, Barguna. | 13.03.2013 | 13.03.2013 | 8626859 | 8626859 | 7628000 |  | 100 | 100 | 0023 | 4241402 | 7 | 4241402 | 12868261 | 208 | 01.11.2012 | 30.04.2013 | 100 | 100 | 4061000 | 0016 | IFAD-2 | Completed & Hannded over | 61866.6394
123 | 41003 | Baika-Barahapania | Manikgonj | Horirumpur | - 1-V Regulator - 1-V Pipe Sluice - O&M Shed - Khal/Embankment | M/S Shohag Construction Seota, Manikganj | 01.03.12 | 26.11.12 | 11241319 | 8561633 | 8561633 |  | 100 | 100 | 0040 | 895697 | 7 | 3106392 | 11668025 | 590 | 16.02.12 | 30.04.2012 | 100 | 100 | 3106392 | 0034 | ADB | Completed | 19776.3136
124 | 46250 | Anulia Beel-Barnai rever | Rajshahi | Durgapur | Khal = 1 no. 3.70 km Box culvert = (2V-2.5m X 7.0m), (2V-4.0m X 4.0m) 6 nos. Drainage outlet = (450mm dia) WMCA Office | M/S Hossain Enterprise (JV) Ramchandrapur, Ghoramara, Durgapur, Rajshahi | 03.04.2016 | 27.02.2017 | 11140059 | 8234340 | 1140000 |  | 35 | 14 |  | 1857798 | 5 | 1857798 | 10092138 | 450 | 19.11.2015 | 30.04.2016 | 60 | 16 | 281202 |  | ADB | Box Culvert (4 mX4 m) cannot be done because Diversion Road Problem and others culvert work on going. O&M shed Grade beam & column casting Coplete. | 22426.9733
125 | 46265 | Khal Ghat Basundia | Jessore | Sadar | Regulator = 1 WMCA Office = 1 | Noor Hossain Missinpara, Puratan Kasba, Jessore | 25.04.2016 | 09.05.2017 | 7275754 | 8232588 | 1339350 |  | 50 | 17 |  | 0 | 0 | 0 | 8232588 | 130 | [6 empty] | ADB | O&M shed and regulator work ongoing | 63327.6
126 | 46257 | Hazipur | Satkhira | Sadar | 1 Khal = 1 Km Foot bridge 1 2-vent regulator 1 WMCA Office | SK. EHAM & FT (JV) South Borgachi, Nator | 04.04.2016 | 17.04.2017 | 9575740 | 8217224 |  |  | 20 |  |  | 1383234 | 4 | 1383234 | 9600458 | 439 | 25.11.2016 | 30.04.2016 | 70 | 68 | 946002 |  | ADB | work is ongoing | 21868.9248
127 | 43055 | Dholdholia | Gaibandha | Shagata | * Regulator (2V-1.5 X 1.8m) * 4.20 km embankment * WMCA Office | JV of Md. Khudimul Islam Jewel & Md. Abdul Hakim Mondol V-aid Road, Gaibandha | 13.03.2014 | 12.03.2015 | 7243188 | 7889072 | 6815413 |  | 100 | 80 | 0047 | 8038430 | 14 | 8038430 | 15927502 | 748 | 10.01.13 | 30.04.2013 | 100 | 100 | 7272808 | 0015 | IFAD-2 | Completed & Handed Over | 21293.4519
128 | 45171 | Mohonganj | Barisal | Babuganj | 4 Khal = 8.4 km 2 Bculvert (1V-3.0m X 3.0m, 2V-2.5m X 2.5m) O&M Shed | M/S Rupali Construction Hospital Road, Barisal | 05.11.2015 | 17.11.2016 | 9840675 | 7873797 | 1000000 |  | 35 | 12.7 |  | 8148256 | 19 | 8148256 | 16022053 | 680 | 31.01.2016 | 31.04.2016 | 100 | 79 | 6417000 |  | ADB | 1 culvert done. | 23561.8426
129 | 45168 | Chalitabunia Ghatichara | Pirojpur | Mathbaria | Khal = 10.335 km Drain = 300m O&M Shed = 1 Culvert = 2 | M/S Efti Enterprise Prop. Md. Metazul Islam Bhandaria, Pirojpur | 04.01.2016 | 12.01.2017 | 7833358 | 7765986 | 4359491 |  | 70 | 56 |  | 9972146 | 23 | 9972146 | 17738132 | 850 | 01.02.2015 | 30.04.2015 | 100 | 97.6 | 9731108 |  | ADB | LCS work completed. Pucca drain work ongoing | 20868.3906
130 | 45160 | Chaita-Bajita | Patuakhali | Mirzaganj | O&M Shed 10 Khal 18.70 Km 2 Regulator (1V-1.5m X 1.5m) 3 Box Culvert (1V-3.5m X 3.5m, 1V-3.0m X 2.7m, 1V-3.0m X 2.5m) | Md. Reza Uddin Town Kalakapur Patuakhali | 22.7.2015 | 21.07.2016 | 16959431 | 7764586 | 2757093 | 100 | 80 | 32 |  | 9377206 | 23 | 9377206 | 17141792 | 715 | 15.01.2015 | 30.04.2015 | 100 | 100 | 9248690 |  | ADB | Earth work completed & structure work ongoing. (1 WRS & 1 Box culver is being canceled) | 23974.5343
131 | 44088 | Rauha-Kumargara | Manikgonj | Daulatpur | 1 Khal = 0.700 km Embankment 4.07 km Regulator ch. 0+496 km WMCA Office | M/S. Md. Khandaker Shahin Ahamed Road no-1, Goalchamot, Faridpur. | 01.02.2015 | 31.01.2016 | 6532296 | 7749999 | 5327566 |  | 80 | 60 | 0081 | 6149059 | 15 | 6149059 | 13899058 | 280 | 05.02.2014 | 30.04.2014 | 65 | 81 | 2430500 | 37 | IFAD-1 | Work ongoiong. Embankment damaged by flood. | 49639.4929
132 | 44078 | Dhonkundi Beel | Bogra | Sheerpur | * 2-vent WRS(1.5mX1.8m) * 1-vent Boxculvert 775m Khal * 1 O&M Shed | Md. Fazlul Haque Usha Complex Majhira, Bogra. | 22.01.2014 | 21.01.2015 | 8229340 | 7680934 | 7651377 |  | 100 | 100 | 0173 | 410869 | 1 | 410869 | 8091803 | 509 | 18.12.2013 | 30.04.2014 | 100 | 66 | 271662 | 0158 | ADB | Structure work Completed & hand over. LCS work final bill under process | 15897.4519
133 | 42015 | Sunduri Khal | Chandpur | Kachua | - Line Canal = 3.50 km - 1 Khal = - O&M Shed (not done) | Md. Anwar Hossain 989, East Monipur, Mirpur, Dhaka | 28.01.2015 | 27.07.2016 | 9956939 | 7500404 | 7415204 |  | 100 | 100 | 0065 | 8828800 | 15 | 8828800 | 16329204 | 983 | 30.12.2012 | 30.04.2013 | 100 | 64 | 5691920 | 0012 | IFAD-2 | Completed. Line canal done. O&M Shed dropped. Khal as per work done. Bill of LCS be fund soon. | 16611.6012
134 | 44116 | Nakai Beel | Gaibandha | Palashbari | * WRS (2V-1.5m X 2.0m) * 2.50 km Khal * WMCA Office | AC & SR (JV), Thanapara, Gaibandha | 24.09.2014 | 23.09.2015 | 6603711 | 7491686 |  |  | 15 |  | 0240 | 830587 | 3 | 830587 | 8322273 | 280 | 23.04.2014 | 30.04.2014 | 100 | 100 | 829928 | 172 | ADB | Land acquisition proposal with DC, Gaibandha. Public agreed with land acquition. Sheet pile driven. Base casting by 7 January 2017. | 29722.4036
135 | 43059 | Kedarpur-Gobindapur | Comilla | Chandina | - O&M Shed = 1 no. (12m X 6m) '- 5.8 km Khal + 2.20 Km D/S Khal '- WRS = 2-vent (1.5m X 1.8m)= 1 no. | M/S M.M. Enterprise Chandina, Comilla | 22.02.2015 | 28.02.2016 | 6719917 | 7334559 | 7259649 |  | 100 | 100 | 0232 | 10626032 | 23 | 10626032 | 17960591 | 630 | 07.03.2013 | 30.04.2013 | 73 | 60 | 6252585 | 0075 | ADB | LCS No 1 to 16 earth work complete and LCS No 18 to 23 works stoped due to over rain filled up water. | 28508.8746
136 | 45182 | Nilkuthi-Bhangarmore | Gaibandha | Saghata | Regulator (1V-1.5m X 1.5m) Pipe culvert (1V-1200m) 2 box culverts (1V-1200m) each WMCA Office (12.0m X 6.0m) | S.M. Rashed Hossain Alamnagar. Rangpur | 03.01.2016 | 02.01.2017 | 8006494 | 7144211 | 900000 |  | 30 | 14 |  | 6745672 | 16 | 6745672 | 13889883 | 334 | 12.12.2015 | 30.12.2016 | 90 | 65 | 4155765 |  | IFAD-1 | 1st lift casting of regulator work done | 41586.476
137 | 45184 | Oran Bridge-Bundishi Khal | Gaibandha | Gobindagonj | 1 Khal = 2.10 Km WRS (2V-1.5m X 1.8m) = 1 WMCA Office | M/S Shihab Construction (JV) Gobindaganj, Gaibandha. | 31.12.2015 | 30.12.2016 | 6601118 | 6922739 | 4105046 |  | 100 | 60 |  | 2367979 | 5 | 2367979 | 9290718 | 630 | 10.11.2015 | 30.04.2016 | 100 | 70 | 1630673 |  | IFAD-1 | Structure work on going | 14747.1714
138 | 41009 | Kusta Thakurkandi FMD | Manikgonj | Geore | - 1-V Regulator - O&M Shed - Khal (0.880 km) & embankment | JV M/S M. Zaman Enterprise & M/S Shohage Construction | 16.02.2012 | 25.11.2012 | 6270143 | 6575460 | 5980349 |  | 100 | 100 | 0043 | 2566974 | 8 | 2566974 | 9142434 | 340 | 28.02.12 | 30.04.2012 | 100 | 100 | 2550000 | 0034 | ADB | Completed Minor O&M work pending. | 26889.5118
139 | 43056 | Latifpur-Etbarpur Khal | Comilla | Chandina | - 3 nos. 1-Vent Box culvert (3.0m X 3.0m) - 5.300 km Khal '- WMCA Office (12m X 6m) | M/S. M.M. Enterprise Kazibari, Chandina, Comilla. | 27.03.2014 | 26.03.2015 | 5654469 | 6470971 | 6378022 |  | 100 | 100 | 0178 | 7462305 | 16 | 7462304 | 13933275 | 666 | 20.02.2013 | 30.04.2013 | 100 | 82 | 6173541 | 0118 | ADB | Final | 20920.8333
140 | 43054 | Mofizan Khal | Gaibandha | Shagata | * Modification of RCC culvert into WRS (4V-1.5 X 1.8m) * 2-vent WRS 3.50 km embankment * 1 WMCA Office (12.0m X 6.0m) | M/S. Saiky Builders Food Office Road, Nilphamari | 11.09.2014 | 10.09.2015 | 6188332 | 6280777 | 4423886 |  | 100 | 75 |  | 3289672 | 18 | 2585475 | 8866252 | 200 | 02.09.2013 | 30.04.2014 | 100 | 100 | 2585475 | 0148 | ADB | Completed Minor finishing work needed. Block work not done. Contract amount redueced due to ommision of embankment. | 44331.26
141 | 42018 | Kata Khal | Meherpur | Mujibnagar | * 1V Regulator * 1 Foot bridge * Khal 0.7 km * O&M Shed | Mr. Anchal Bahttacharya, Hotel Bazar, Meherpur | 02.01.2013 | 01.01.2014 | 5137855 | 5969576 | 5976848 |  | 100 | 96 | 0083 | 491000 | 1 | 491000 | 6460576 | 221 | 06.01.2013 | 30.04.2013 | 100 | 100 | 470000 | 0071 | ADB | Completed | 29233.3756
142 | 46232 | Krishnapur-Baromashi | Naogaon | Sadar | 2 Khal = 9.98 Km WRS = 1 Culvert = 1 WMCA Office = 1 | M/S Jewel Enterprise & Khan Traders JV | 19.07.16 | 27.02.17 | 5163237 | 5625683.62 |  |  | 10 |  |  | 11180061 | 20 | 11180061 | 16805744.62 | 671 | 28.01.2016 | 30.04.2016 | 80 | 42 | 4748930 |  | ADB | work is going on | 25045.8191
143 | 41004 | Chak Govindapur-Aldadpur | Gaibandha | Sadullapur | Work in progress * Modification of Existing Box Culvert * Construction of Box Culvert (1V-4.0m X 3.9m) * 2-vent WRS (1.5 X 1.8m) * 2.20 km khal * WMCA Office | M/S Nuha Traders Mohuri Para, Gaibandha | 04.04.12 | 03.09.12 | 5169620 | 5563742 | 5492373 |  | 100 | 100 | 0036 | 718823 | 2 | 718823 | 6282565 | 470 | 15.12.11 | 30.04.2012 | 100 | 100 | 443000 | 0117 | ADB | Copleted and handed over | 13367.1596
144 | 45145 | Naimuri-Alidaha | Sirajgonj | Ullapara | * 2 Sluice Gates (1V-1.2m X 1.2m) * Palisading Work * 8.00 km Embankment * 2 nos. 1-vent culvert * O&M Shed | Serajul Islam Dattabari Road, Sirajgonj | 24.03.2015 | 22.03.2016 | 5085662 | 5477628.87 | 4317731 |  | 100 | 79 | 0281 | 11616200 | 22 | 11616200 | 17093828.87 | 380 | 07.12.2014 | 30.04.2015 | 100 | 100 | 11498289 | 189 | ADB | Completed | 44983.7602
145 | 43064 | Dier Khal | Bagethat | Sadar | Box culvert 1 6 Khal 9.55 km & O&M Shed | M/S Shahid Enterprise Musgunni, High Way, Road Khulna. | 15.06.2014 | 14.06.2015 | 4689368 | 5296645 | 4400000 |  | 100 | 86.4 | 0053 | 5187325 | 13 | 5187325 | 10483970 | 665 | 27.02.2014 | 30.04.2014 | 100 | 63.39 | 3443971 | 0034 | IFAD-2 | Completed | 15765.3684
146 | 45193 | Madier Beel | Meherpur | Gangni | 3 Khal re-excavation = 3.70 Km Road earthfill = 0.650 KM Box culvert = 1 (1-V 4.50m X 5.50m) WMCA Office = 1 | M/S Unic Traders Mirpur Kushtia | 03.04.2016 | 02.04.2017 | 5248857 | 5245462 | 1522171 |  | 70 | 29 |  | 9284645 | 19 | 9284645 | 14530107 | 860 | 17.08.2015 | 30.04.3016 | 98 | 71 | 6545814 |  | IFAD-1 | Earth work completed and structure work ongoing | 16895.4733
147 | 45177 | Dakshin Trish CAD | Comilla | Muradnagar | Khal = 1.13 Km 3 Brick Lined Canal = 2.30 Km Not required Box Culvert (1V-2.0m X 2.0m). May be dropped. WMCA Office = 1 (12.0m X 6.0m) | M/S Pioneer Construction Badurtala, Comilla | 08.09.2016 | 14.09.2017 | 4918083 | 5171439 | 2449000 |  | 82 | 47 |  | 291275 | 1 | 291275 | 5462714 | 63 | 25.03.2015 | 30.04.2015 | 90 | 46 | 134093 |  | ADB | 640m irrigation canal , cross check structure & WMCA office Brick work complete | 86709.746
148 | 45173 | Charadi | Barisal | Bakerganj | 1 Khal = 4.40 km Embankment = ? 2 WRS 1 WMCA Office | M/S Talukder Enterprise & M/S Meem & Co. (JV), Uzirpur, Barisal. | 16.11.2015 | 22.11.2016 | 6400529 | 5075276 | 3100000 |  | 75 | 61 |  | 10825971 | 21 | 10825971 | 15901247 | 650 | 10.02.2015 | 30.04.2015 | 95 | 52 | 5622000 |  | ADB | Work ongoing. 1 box culvert not done. O&M Shed 85% done. | 24463.4569
149 | 45174 | Paschim VogailBaira Eidgha | Bogra | Kahaloo | 3 Khal = 7.70 km 1 Embankment = .5.3 km 1 O&M Shed 2 Box culvert 2 Drain - 600m | M/S. Sanitary Museum Laxmipur, Rajshahi | 29.11.2015 | 28.12.2016 | 6658560 | 5028302 | 2066146 |  | 90 | 41 |  | 2143826 | 5 | 2143826 | 7172128 | 200 | 21.12.2015 | 30.04.2016 | 98 | 64 | 1374862 |  | ADB | O&M shed 50%. Regulator deckslab done. Reference line section not done. | 35860.64
150 | 45172 | Birgaon Tilokia | B.baria | Nabinagar | B ox Culvert = 2 2 Khal = 10.675 km Pucca drain= 2 (600m) O&M Shed = 1 | M/S Pinto Construction Simrakandi, Brahmanbaria | 18.08.2015 | 23.082 | 5667511.96 | 4975494.29 | 692000 |  | 20 | 13.91 |  | 9267577 | 21 | 9267577 | 14243071.29 | 397 | 15.02.2015 | 30.04.2015 | 90 | 55 | 5096207 |  | IFAD-2 | Work ongoing. 1 box culvert not done. O&M Shed 85% done. | 35876.7539
151 | 45165 | Darial | Barisal | Bakerganj | Culvert 2 nos. 5 Khal = 13.556 km O&M Shed = 1 | Md. Mahfuz Khan Nalcity Bondor, Jhalokathi | 05.11.2015 | 17.11.2016 | 6068806 | 4846221 | [5 empty] | 7197729 | 17 | 7197729 | 12043950 | 620 | 31.01.2015 | 30.04.2016 | 35 | 21 | 1386000 |  | ADB | Contractor did not start even after issuing final notice which is also over. May be dropped if not responded. | 19425.7258
152 | 45205 | Napitkhali Burirchar | Barguna | Sadar | 8 Khal 10.20 Km 2 Box Culvert WMCA Office | M/S Mom Traders Barguna Sadar, Barguna | 30.01.2016 | 30.12.2016 | 4839567 | 4838253 | 4838253 |  | 100 | 100 |  | 7053708 | 16 | 7053708 | 11891961 | 550 | 25.10.2015 | 30.04.2016 | 100 | 70 | 4720000 |  | IFAD-1 | Completed | 21621.7473
153 | 44092 | Faridpur-Badorerjan | Rangpur | Mithapukur | 1-vent WRS 350m Khal Embankment 2 | M/S. RH-KZ (JV), Sultanpur, Mithapukur, Rangpur. | 02.02.2014 | 01.02.2015 | 4376508 | 4828899 | 4300000 |  | 100 | 90 | 186 | 3599200 | 7 | 3599200 | 8428099 | 310 | 10.11.2013 | 30.04.2014 | 100 | 10 | 359920 | 150 | ADB | Completed Worked done as per design. | 27187.4161
154 | 45201 | Fakirkhali Khal | Chudanga | Damurhuda | 1 Khal 2 WRS O&M Shed | M/S AB & SD JV Haque Para Chuadanga | 10.11.2015 | 09.11.2016 | 4882873 | 4177597 | 1000000 |  | 75 |  |  | 154650 | 2 | 154650 | 4332247 | 860 | 04.11.2015 | 30.04.2016 | 90 | 33 | 50000 |  | ADB | Document with ADB | 5037.4965
155 | 45212 | Nauda Durgapur-Maddamath | Chuadanga | Alamdanga | 1 Khal 1 WRS modification WMCA Office | M/S AB & SD (JV) Haque para, Chuadanga | 27.01.2016 | 26.01.2017 | 5007056 | 4099172 |  |  | 10 |  |  | 324715 | 2 | 324715 | 4423887 | 195 | 21.12.3015 | 30.04.2016 | 95 | 30 | 100000 |  | ADB | Document with ADB | 22686.6
156 | 44101 | Bondukkhali Khal | Meherpur | Sadar | 1 Khal = 1.025 km 1 Regulator 1 Box culvert Embankment (HBB Road) = 0.5 km WMCA Office | Md. Golam Rasul, Hotel Bazar, Meherpur | 15.05.2014 | 14.05.2015 | 3848384 | 4036420 | 2182269 |  | 100 | 54 | 211 | 702951 | 2 | 702951 | 4739371 | 268 | 18.12.2013 | 30.04.2014 | 100 | 100 | 336846 | 163 | ADB | Minor work pending | 17684.2201
157 | 46267 | Kamranga Monihar | Chandpur | Sadar | 1 Khal = 1.10 km 2 Lined Canal = 0.70 km WMCA Office = 1 | M/S National Traders System Ltd. Sholagar B.T. Road Chandpur | 23.03.2016 | 27.02.2017 | 3997001 | 3981954.58 | 1818632 |  | 70 | 46 |  | 1313690 | 3 | 1313690 | 5295644.58 | 138 | 14.01.2016 | 30.04.2016 | 70 | 10 | 66519 |  | ADB | work is ongoing | 38374.2361
158 | 45180 | Tengrakhali-Char Tengrakhali | Bagerhat | Kachua | 2 Khal 8.50 Km 2 Box Culvert O&M Shed | M/S. Alif Store Chitalmari, Bagerhat | 14.06.2015 | 13.06.2016 | 3601846 | 3936427 | 3886103 |  | 100 | 100 | 0086 | 7476361 | 19 | 7476361 | 11412788 | 280 | 18.03.2015 | 30.04.2015 | 100 | 100 | 7369332 | 70 | IFAD-1 | Completed | 40759.9571
159 | 45170 | Lalua-Golbunia | Patuakhali | Kalapara | 2 box culvert 2 pucca drain O&M Shed Khal = 12.99 km | M/S Gazi Enterprise Majhkahali, Patuakhali | 22.07.2015 | 21.07.2016 | 4472344 | 3859385 | 2637761 | 100 | 90 | 68 | 0069 | 3240102 | 8 | 3240102 | 7099487 | 690 | 03.02.2015 | 30.04.2015 | 100 | 46 | 1503559 | 51 | IFAD-2 | Earth work completed & structure work ongoing. | 10289.1116
160 | 44086 | Sannashipara | Thakurgaon | Sadar | * 1-vent WRS (1.5 X 1.8)m * 0.270 km. Khal * 1 O&M Shed | Ram Babu, Gudri Bazar, Thakurgaon | 17.09.2014 | 16.09.2015 | 4214055 | 3825985 | 2673109 |  | 85 | 70 | 75 | 109826 | 1 | 109826 | 3935811 | 153 | 09.03.2014 | 30.04.2014 | 100 | 86 | 96655 | 40 | IFAD-1 | Structure work is running | 25724.2549
161 | 45199 | Beel Aksi | Magura | Sadar | 2 Khal 1.20 Km 1 Pipe Sluice O&M Shed | M/S Bhawal Construction 40, Shehora Chamra Godown, Mymensingh. | 27.12.2015 | 01.01.2017 | 3802804 | 3800195 | 1514929 |  | 77 | 40 |  | 725374 | 3 | 725374 | 4525569 | 332 | 30.11.2015 | 30.04.2016 | 70 | 20 | 151590 |  | IFAD-1 | Work ongoing. | 13631.2319
162 | 45187 | Majumder Khal-Daser Khal | Patuakhali | Galachipa | 4 Khals re-excavation = 8.025 Km 2 Box culvert (1-V 3.5m X 3.0m) & 2-V 2.5m X 2.7m) WMCA Office = 1 | M/S Soma Enterprise, Old Bus Terminal, Patuakhali | 22.07.2015 | 02.03.2017 | 4602933 | 3794132 | 2410353 |  | 80 | 64 |  | 5467109 | 15 | 5467109 | 9261241 | 340 | 26.08.2015 | 30.04.2016 | 100 | 69 | 3781570 |  | IFAD-2 | Earth work completed & structure work ongoing. | 27238.9441
163 | 45195 | Jailkhana Khal | Barguna | Sadar | 3 Khal 8.40 Km 2 Box Culvert O&M Shed | M/S Afser & Co Sadar Road, Barguna | 28.01.2016 | 30.12.2016 | 4469524 | 3697764 | 2100000 |  | 90 | 65 |  | 10821162 | 23 | 10805691 | 14503455 | 500 | 08.11.2015 | 30.04.2016 | 100 | 70 | 7300000 |  | IFAD-1 | O&M Shed completed. 1 culvert completed and other ongoing. | 29006.91
164 | 44081 | Thakurmallik | Barisal | Bakerganj | 6 Khal, 1.7 km Pucca drain 5 field channel & 1 O&M Shed | M/S. Saifuddin Traders Nesarabad, Pirojpur. | 23.04.2014 | 22.04.2015 | 3115584 | 3487135 | 3205975 |  | 100 | 94 | 176 | 12772854 | 29 | 12772854 | 16259989 | 920 | 27.10.2013 | 30.04.2014 | 100 | 100 | 12265000 | 140 | ADB | Completed & Handed Over WMCA good | 17673.9011
165 | 44143 | Hetalia-Ballabhpur | Patuakhali | Sadar | 5 Khals 2 Bculvert (1V-3.0m X 3.5m, 1V-2.5m X 2.5m) O&M Shed | M/S Gazi Enterprise Majhkahali, Patuakhali | 22.07.2015 | 21.07.2016 | 4078449 | 3442267 | 2543364 | 100 | 100 | 74 | 0254 | 12089169 | 28 | 12089169 | 15531436 | 467 | 15.01.2015 | 30.04.2015 | 100 | 100 | 11879539 |  | ADB | Completed | 33257.8929
166 | 46243 | Solok Jughihati | Barisal | Uzirpur | 7 Khal 16.37 Km WMCA Office Drain = 300m Box culvert = 1 | M/S Shikdar | 06.06.2016 | 23.02.2017 | 3234714 | 3235014 |  |  | 40 |  |  | 12907780 | 26 | 12907780 | 16142794 | 900 | 29.02.2016 | 30.04.2016 | 45 | 21 | 2716000 |  | IFAD-1 | Work started. | 17936.4378
167 | 45204 | Monosatali | Barguna | Sadar | 5 Khal 1.10 Km 1 Box Culvert O&M Shed | M/S Akhondo Traders Sadar, Barguna | 26.01.2016 | 25.12.2016 | 2955983 | 3107454 | 2200000 |  | 90 | 75 |  | 4932383 | 12 | 4932383 | 8039837 | 205 | 26.11.2015 | 30.04.2016 | 100 | 55 | 2300000 |  | ADB | Culvert completed. O&M Shed may be done. | 39218.7171
168 | 44135 | Debdun Bauisena Khal | Narail | Kalia | 1 Khal 2 Km 1 Culvert O&M Shed | M/S. Showrove Traders Chandmari Road, Gopalgonj. | 31.12.2014 | 30.12.2015 | 2818829 | 2956222 |  |  | 100 |  | 0233 | 2198998 | 7 | 2198998 | 5155220 | 253 | 01.12.2014 | 30.04.2015 | 100 |  |  | 205 | ADB |  | 20376.3636
169 | 46227 | Nandahar Khal | Joypurhat | Akkelpur | * Repair of Existing BWDB Box Culvert (3V-1.5m X 1.8m) * Repair of Existing BWDB Regulator (6V-1.2m X 1.2m) * 2 khals = 10.45 km * WMCA Office = 1 | Ram Babu Garipara, Thakurgaon | 03.02.2016 | 16.02.2017 | 2682930 | 2825021 | 1738588 |  | 85 | 61.54 |  | 14634008 | 26 | 14634008 | 17459029 | 970 | 14.12.2015 | 30.04.2016 | 100 | 58 | 8548454 |  | IFAD-1 | Box culvert modifie . Regulator not yet fully repaired. O&M shed floor & furniture not done | 17998.999
170 | 44114 | Isobpur-Dakkin Beel Chaipara | Rajshahi | Durgapur | * 2.50 km Khal * O&M Shed * 50 m protection wall | Holly Hope Enterprise, 5/2 Upashahr, Sopura, Rajshahi. | 25.08.2014 | 24.08.2015 | 2671214 | 2279420 | 818798 |  | 50 | 36 | 55 | 1863801 | 5 | 1863800 | 4143220 | 418 | 03.03.2014 | 30.04.2014 | 0 |  |  |  | IFAD-2 | LCS work stop because Court case on goingWMCA office work on going | 9912.0096
171 | 43058 | Sabupara | Patuakhali | Bauphal | 6 Khal 6.55km O&M Shed | M/S. Jaman Enterprise, Bauphal, Patuakhali. | 27.08.2013 | 26.08.2014 | 1391428 | 1730165 | 1698280 | 100 | 100 | 100 | 0147 | 6456661 | 14 | 6456661 | 8186826 | 540 | 19.03.2013 | 30.04.2013 | 100 | 100 | 6318798 | 0101 | ADB | Completed & Handed over | 15160.7889
172 | 43037 | Badrabati (North) | Sirajgonj | Taras | 13.0 km Khal & O&M Shed | M/S . Liton Enterprise, Soyadhengore, Sirajgonj. | 12.03.2013 | 11.03.2014 | 1374990 | 1649328 | 1643913 |  | 100 | 100 | 0029 | 13993773 | 28 | 13993773 | 15643101 | 850 | 26.11.2012 | 30.04.2013 | 100 | 100 | 13159000 | 0017 | IFAD-2 | Completed & Hannded over | 18403.6482
173 | 43036 | Badrabati (South) | Sirajgonj | Taras | 14.30 km Khal & O&M Shed | M/S . Liton Enterprise, Soyadhengore, Sirajgonj. | 12.03.2013 | 11.03.2014 | 1374990 | 1612948 | 1612566 |  | 100 | 100 | 0034 | 27279789 | 52 | 27279789 | 28892737 | 700 | 26.11.2012 | 30.04.2013 | 100 | 100 | 25420000 | 0009 | IFAD-1 | Completed & Hannded over | 41275.3386
174 | 44103 | Gotkhali Chalitabunia | Barguna | Amtali | 4 Khal = 14.775 km WMCA Office | Md. Aktaruzzaman Khan Badol Amtali, Barguna. | 23.07.2014 | 22.04.2015 | 1573114 | 1569195 | 1513000 | 100 | 100 | 100 | 65 | 10655696 | 24 | 10655696 | 12224891 | 840 | 27.02.2014 | 30.04.2014 | 100 | 100 | 10606000 | 40 | IFAD-1 | Completed & Handed over | 14553.4417
175 | 43049 | Kapila-Krisnapur | Barisal | Bakergonj | 6 Khal 12.00 km (completed) 1 O&M Shed | M/S Khondokar Brothers, Nalcity, Jalokathi | 02.04.2013 | 01.04.2014 | 1391428 | 1563247 | 1562804 |  | 100 | 100 | 0046 | 14595150 | 25 | 14595150 | 16158397 | 845 | 30.12.2012 | 30.04.2013 | 100 | 100 | 13317000 |  | IFAD-1 | Completed & Handed Over WMCA satisfactory | 19122.3633
176 | 46254 | Karaibaria Khal | Barguna | Taltoly | 4 Khal 7.72 Km WMCA Office | M/S Joynob Enterprise Madrasha Road, Barguna | 13.04.2016 | 13.10.2016 | 1426214 | 1523431 | 300000 |  | 80 | 20 |  | 3758486 | 11 | 3758486 | 5281917 | 545 | 14.01.2016 | 30.04.2016 | 100 | 27 | 1006000 |  | ADB | O&M Shed work ongoing. | 9691.5908
177 | 42025 | Kujil-Sodakhali-Ractodoha | Noagaon | Raninagar & Atrai | * Khal 6.78 Km * O&M Shed | M/S. Chowdhury Trading, Bakterpu, Naogaon. | 27.06.2013 | 27.06.2014 | 1374982 | 1517034.34 | 651501 |  | 100 | 47.05 | 0168 | 8196803 | 14 | 8196803 | 9713837.34 | 682 | 02.12.2012 | 30.04.2013 | 100 | 100 | 8099936 | 0070 | ADB | Hand over | 14243.1633
178 | 44111 | Kashipur | Barisal | Sadar | 4 Khal 11.5 km, 1 O&M Shed | M/S Lutful Kabir Dilbag, Bagura, Alikandhi, Barisal | 31.03.2015 | 30.03.2016 | 1383157 | 1516742 | 1150000 |  | 100 | 75.82 | 0262 | 15872646 | 35 | 15872646 | 17389388 | 909 | 23.11.2014 | 30.04.2015 | 100 | 100 | 15406000 | 200 | ADB | Completed | 19130.2398
179 | 46246 | Ramna | Barguna | Bamna | 6 Khal 14.17 Km WMCA Office | Md. Nazrul Islam Bamna, Barguna | 13.04.2016 | 13.10.2016 | 1413018 | 1511346 | 1413000 |  | 100 | 100 |  | 7626351 | 20 | 7626351 | 9137697 | 990 | 03.01.3016 | 30.04.2016 | 100 | 40 | 1400000 |  | IFAD-1 | Completed as per work done | 9229.997
180 | 44075 | Losnabad Phalaghar | Barisal | Bakerganj | 6 Khal, 14.3 km 1 O&M Shed | M/S. H.M. Harun Runshi, Bakergonj, Barisal | 05.05.2014 | 04.05.2015 | 1374984 | 1509447 | 1508315 |  | 100 | 100 | 0078 | 10850502 | 26 | 10850502 | 12359949 | 900 | 20.11.2013 | 30.04.2014 | 100 | 100 | 10194000 | 0028 | IFAD-1 | Completed & Handed Over WMCA good | 13733.2767
181 | 44125 | Chakar | Barisal | Banaripara | 8 Khal, 16.5 km, O&M Shed = 1 No. | M.S. Raju Enterprise Banaripara, Barisal. | 31.08.2015 | 30.08.2016 | 1363828 | 1493370 | 1414830 |  | 100 | 94.74 | 0061 | 14238613 | 32 | 14238613 | 15731983 | 815 | 02.12.2014 | 30.04.2015 | 100 | 68 | 10221000 | 45 | IFAD-2 | Completed | 19303.0466
182 | 44084 | Silty Khal | Jhenaidah | Harinakunda | * 3 Khals * O&M Shed | M/S. Munshi Traders Kanchonpur, Jhenaidah | 25.09.2014 | 24.09.2015 | 1362774 | 1492908 | 1300000 |  | 100 | 91 |  | 4870627 | 11 | 4870627 | 6363535 | 800 | 17.11.2013 | 30.03.2014 | 100 | 100 | 4634000 | 27 | IFAD-2 |  | 7954.4187
183 | 46238 | Lakshmipur-Ranipur-Khantakata | Barguna | Betagi | 9 Khal 12.03 Km WMCA Office | M/S Kamal Enter[prise Betagi, Barguna | 26.01.2016 | 25.12.2016 | 1409172 | 1483510 | 925000 |  | 100 | 55 |  | 7923453 | 19 | 7923453 | 9406963 | 310 | 15.11.2015 | 30.04.2016 | 100 | 60 | 5100000 |  | IFAD-1 | Completed | 30345.0419
184 | 46216 | Baishtabok | Barguna | Sadar | 6 Khal 12.00 Km WMCA Office | M/S Leon Construction Amtalapar, Barguna | 13.04.2016 | 13.10.2016 | 1413019 | 1483434 | 0 |  | 80 | 0 |  | 5338026 | 13 | 5338026 | 6821460 | 600 | 20.10.2015 | 30.04.2016 | 100 | 67 | 3600000 |  | IFAD-1 | Post work done. O&M Shed yet to complete. | 11369.1
185 | 46245 | Koruna | Barguna | Betagi | 6 Khal 18.08 Km WMCA Office | M/S M.N. Mollik & Company, 87 Purana Paltan, Dhaka | 13.04.2016 | 31.12.2016 | 1413018 | 1482612 |  |  | 80 |  |  | 14513309 | 31 | 14513309 | 15995921 | 990 | 31.12.2015 | 30.04.2016 | 100 | 40 | 5100000 |  | ADB | Work ongoing. | 16157.496
186 | 46274 | Rabipur | Barisal | Babugonj | 4 Khal 4.74 Km 1 Embankment 1.19 Km WMCA Office | M/S Nahid Enterprise, B.M. College Road, Barisal | 30.05.2016 | 24.02.2017 | 1410301 | 1480874.94 |  |  | 75 |  |  | 6724983 | 16 | 6724983 | 8205857.94 | 740 | 03.02.2016 | 30.04.2016 | 90 | 67 | 6447000 |  | IFAD-2 | O&M Shed started. Work ongoing. Post work needed. | 11088.9972
187 | 46217 | Tum Char-Charshahebrampur | Barisal | Muladi | 5 Khals 6.80 Km WMCA Office =1 | M/S Nahid Enterprise, Ishakati Road, Kasipur, Barisal | 18.05.2016 | 24.02.2017 | 1409172 | 1479084 |  |  | 70 |  |  | 5535205 | 14 | 5535205 | 7014289 | 280 | 14.12.2015 | 30.04.2016 | 100 | 100 | 5478000 |  | IFAD-1 | Final bill submitted for earthwork. | 25051.0321
188 | 43050 | Madhya-Purba Rajapur | Patuakhali | Bauphal | 2 Khal 6.5 km O&M Shed (12.0m X 6.0m) | M/S. Sikder Enterprise, Pro. Shakila Zaman, Bauphal, Patuakhali. | 04.08.2013 | 03.08.2014 | 1391428 | 1469637 | 1429547 | 100 | 100 | 100 | 0169 | 9631802 | 19 | 9631802 | 11101439 | 302 | 27.02.2013 | 30.04.2013 | 100 | 70 | 6691215 | 0087 | ADB | completed | 36759.7318
189 | 46268 | Nali Maitha | Barguna | Sadar | 7 Khal 12.94 Km WMCA Office | M/S Samin Construction Islam Polkakhali, Barguna | 13.04.2016 | 13.10.2016 | 1376608 | 1463241 | 600000 |  | 100 | 40 |  | 10281534 | 20 | 10281534 | 11744775 | 550 | 20.01.2016 | 30.04.2016 | 100 | 46 | 7100000 |  | ADB | O&M Shed work ongoing. | 21354.1364
190 | 44136 | Paschim Chayam Takta | Barisal | Mehendiganj | 5 Khal, 8 km, O&M Shed = 1 No. | M/S Shafi Enterprise Fazlul Haque Avenue, Barisal | 15.04.2015 | 14.04.2016 | 1327114 | 1452940.47 | 500000 |  | 100 | 34.413 |  | 7374167 | 18 | 7374167 | 8827107.47 | 337 | 08.12.2014 | 30.04.2015 | 100 | 100 | 7301000 | 61 | IFAD-1 | Completed | 26193.1972
191 | 43066 | Bhelumia | Bhola | Sadar | 7 Khal 17.00 Km O&M Shed | M/S Charsamaya Enterprise Sadar road, Bhola. | 27.10.2015 | 27.07.2016 | 1374429 | 1443362 | 1441200 |  | 100 | 100 |  | 12980080 | 26 | 12980080 | 14423442 | 421 | 10.12.2013 | 30.04.2014 | 100 | 90 | 11639258 | 0029 | IFAD-1 | completed | 34259.9572
192 | 46255 | Dewantala Sluice Gate | Gaibandha | Gabindagonj | 1 Khal = 6.10 km WMCA Office (12.0m X 6.0m) | M/S Khandakar Enterprise Gobindaganj, Gaibandha | 14.03.2016 | 21.03.2017 | 1376044 | 1440899 |  |  | 85 |  |  | 6217349 | 14 | 6217349 | 7658248 | 680 | 15.12.2015 | 30.04.2016 | 100 | 100 | 6180035 |  | IFAD-2 | O&M Shed brick work started. | 11262.1294
193 | 46275 | Saidkati | Barisal | Banaripara | 7 Khal = 14.72 km WMCA Office = 1 | M/S Meem & Co. Uzirpur, Barisal | 19.05.2016 | 25.02.2017 | 1372777 | 1440375.95 |  |  | 70 |  |  | 9640729 | 20 | 9640729 | 11081104.95 | 649 | 28.01.2016 | 30.04.2016 | 80 | 67 | 6447000 |  | ADB |  | 17074.1216
194 | 46272 | Karapur | Barisal | Sadar | 9 Khal 13.39 Km WMCA Office | M/S Jahangir Hossain, West Jhalokhati | 19.05.2016 | 24.02.2017 | 1372777 | 1440180.89 | 400000 |  | 80 | 27 |  | 12251983 | 25 | 12251983 | 13692163.89 | 491 | 26.01.2016 | 30.06.2016 | 40 | 25 | 3029000 |  | ADB | O&M Shed not started. Work ongoing. | 27886.2808
195 | 46273 | Niamotullah-Dakshin Bhulerdia | Barisal | Babugonj | 6 Khal 12.88 Km WMCA Office | M/S A. K Traders, Fazlul Haque Avenue, Barisal | 12.05.2017 | 18.02.2018 | 1372776 | 1438746.19 |  |  | 50 |  |  | 8017700 | 18 | 8017700 | 9456446.19 | 650 | 30.01.2016 | 30.04.2016 | 85 | 62 | 4983000 |  | IFAD-1 | Work ongoing. Post work needed. | 14548.3788
196 | 43033 | Santoshpara-Chatra | Nogaon | Niamatpur | * 11.17 km khal * O&M Shed | M/S Ethen Enterprise JR Super Market Noagoan. | 14.07.2013 | 14.07.2014 | 1373904 | 1434775 | 1148000 |  | 100 | 100 | 0032 | 14523581 | 23 | 14523581 | 15958356 | 900 | 26.11.2012 | 30.04.2013 | 100 | 79 | 11484603 | 0011 | IFAD-1 | Completed & Hannded over | 17731.5067
197 | 44120 | Jabbar Ali Sharif Shimon | Barguna | Amtali | 5 Khal = 8.00 km O&M Shed = 1 no. | M/S Sharif Sharna Enterprise Amtoli Barguna | 02.08.2015 | 10.05.2016 | 1375728 | 1432972 | 163000 |  | 70 | 12 |  | 7023647 | 17 | 7023647 | 8456619 | 526 | 03.11.2014 | 30.04.2015 | 80 | 25 | 2300000 |  | IFAD-2 | 2 Khal completed and 2 Khal partly done in hap hazard manner. May be declared for completed for LCS work. Will be completed by December 2016. | 16077.2224
198 | 43031 | Belgaour-Julupara | Noagaon | Niamatpur | Post work taken * 8.20 km khal * O&M Shed | M/S Ethen Enterprise JR Super Market Noagoan. | 14.07.2013 | 14.07.2014 | 1366184 | 1432583 | 1146000 |  | 100 | 100 | 0155 | 13673215 | 22 | 13673215 | 15105798 | 1000 | 22.11.2012 | 30.04.2013 | 100 | 100 | 12902967 | 0066 | ADB | Hand over | 15105.798
199 | 46276 | Purba Chila | Barguna | Amtali | 9 Khal = 9.00 km WMCA Office = 1 | Md. Shahidul Islam, Amtali, Barguna | 13.04.2016 | 13.10.2016 | 1376608 | 1431086.72 | 1050000 |  | 100 | 73 |  | 6776935 | 14 | 6776935 | 8208021.72 | 450 | 15.02.2016 | 30.04.2016 | 100 | 25 | 1300000 |  | ADB | Completed | 18240.0483
200 | 45157 | Satail Beel | Natore | Baraigram | 4.90 km khal WMCA Office =1 | M/S MN Trades Bolaripara, Natore | 28.03.2016 | 05.01.2017 | 1280414 | 1426932 | 0 |  | 30 |  |  | 4262527 | 10 | 4262527 | 5689459 | 290 | 08.02.2015 | 30.04.2015 | 90 | 70 | 2987778 |  | ADB | Final Measurment Complete | 19618.8241
201 | 46236 | Dumjury | Pirojpur | Kawkhali | 9 Khal 6.80 Km WMCA Office | M/S Efte Enterprise | 08.05.16 | 27.02.17 | 1409172 | 1407251 | 1406489 |  | 100 | 99 |  | 4696499 | 11 | 4696499 | 6103750 | 180 | 16.02.2016 | 30.04.2016 | 60 | 29 | 1213100 |  | ADB | O&M shed work completed. Lcs work ongoing. | 33909.7222
202 | 46248 | Sikdermaollik-Hizalbaria | Pirojpur | Sadar | 7 Khal 14.97 Km WMCA Office | M/S Efte Enterprise | 08.05.2016 | 27.02.2017 | 1409172 | 1406903 | 344000 |  | 70 | 24 |  | 15091910 | 25 | 15091910 | 16498813 | 995 | 07.04.2016 | 30.04.2017 | 0 | 0 | 0 |  | ADB | O&M shed work ongoing. | 16581.7216
203 | 46237 | Parerhat | Pirojpur | Zianagar | 9 Khal 14.90 Km WMCA Office | M/S Efte Enterprise | 08.05.16 | 27.02.17 | 1409172 | 1405505 | 940000 |  | 90 | 67 |  | 11288320 | 26 | 11288320 | 12693825 | 690 | 31.01.2016 | 30.04.2016 | 90 | 47 | 5274500 |  | IFAD-1 | O&M shed work ongoing | 18396.8478
204 | 46224 | Kalardoania | Pirojpur | Nazirpur | 10 Khal 11.85 Km WMCA Office | M/S Nisha Construction, Nesarabad, Pirojpur | 08.05.16 | 27.02.17 | 1409172 | 1402778 |  |  | 70 |  |  | 7410197 | 19 | 7410197 | 8812975 | 485 | 11.01.2016 | 30.04.2016 | 100 | 59 | 4383371 |  | IFAD-1 | Post work joint measurment completed. O&M shed work ongoing | 18171.0825
205 | 42024 | Nishanbaria-Gazimahmud | Barguna | Sadar | 7.2 km Khal & O&M Shed | M/S. Shoel Traders, Amtola Road, Barguna | 30.10.2012 | 30.10.2013 | 1400227 | 1400214 | 1396000 |  | 100 | 100 | 0107 | 11096783 | 75 | 11096783 | 12496997 | 750 | 23.08.2012 | 30.04.2013 | 100 | 100 | 11084000 | 0052 | ADB | Completed & Handed Over | 16662.6627
206 | 42016 | Gabua Fultala | Barguna | Betagi | 5 Khal 12.82 km& O&M Shed | M/S. Kamal Enterprise Betagi, Barguna | 06.11.2012 | 06.11.2013 | 1400227 | 1399227 | 1397000 |  | 100 | 100 |  | 16730210 | 35 | 16730210 | 18129437 | 750 | 04.09.2012 | 30.04.2013 | 100 | 100 | 16453000 | 007 | ADB | Completed & Handed Over | 24172.5827
207 | 43043 | Dchergati | Barisal | Babugonj | 6 Khal 12.13 km (completed) 1 O&M Shed | M/S Lutful Kabir Bagura Alekanda Road, Barisal | 01.04.2013 | 31.03.2014 | 1391428 | 1399057 | 1367463 |  | 100 | 98 | 0042 | 11949967 | 20 | 11949967 | 13349024 | 700 | 18.10.12 | 30.04.2013 | 100 | 100 | 11900000 | 0008 | IFAD-1 | Completed & Handed Over WMCA satisfactory | 19070.0343
208 | 42023 | Jalabaria DR-1 | Pirojpur | Nesarabad | 8 Khal 14.13 km & O&M Shed | M/S.New Five Star Bricks, Pro. Alhaj Sultan Ahmed, Jhatkhati, Pirojpur. | 04.02.2014 | 03.02.2015 | 1399429 | 1398701 | 1331986 |  | 100 | 95 | 0060 | 10498075 | 75 | 10498075 | 11896776 | 700 | 11.12.2012 | 30.04.2013 | 100 | 100 | 9988071 | 14 | IFAD-2 | Complete & Hand over | 16995.3943
209 | 42022 | Sapleza DR-1 | Pirojpur | Mathbaria | 11 Khal 22.5 km & O&M Shed | M/S.Efte Enterprise Pro. Md. Merazul Islam Bhandria, Pirojpur. | 04.02.2014 | 03.02.2015 | 1399429 | 1398697 | 1389832 |  | 100 | 100 | 0072 | 10280488 | 26 | 10280488 | 11679185 | 896 | 13.11.2012 | 30.04.2013 | 100 | 100 | 10032000 | 007 | IFAD-1 | Complete & Hand over | 13034.8047
210 | 43038 | Silaur-Dogangy SP | B. Baria | Sadar | - 2 Khal & 1 Branch Khal = 4.50 km WMCA Office | M/S. Hasanl Enterprise T.A. Road B. Baria. | 29.05.2013 | 29.05.2014 | 1398475 | 1397395.86 | 1264802 |  | 100 | 100 |  | 5950922 | 11 | 5950922 | 7348317.86 | 623 | 19.12.2012 | 30.04.2013 | 100 | 100 | 5950576 | 0068 | ADB | Completed & Hannded over | 11795.0527
211 | 42026 | Ratan Danra (Sadokhali to Jhanjhania) | Noagaon | Raninagar & Atrai | * 5.1 km khal * O&M Shed | Md. Rafiqul Islam Chalkbed, Noagaon | 13.06.2013 | 13.06.2014 | 1374982 | 1396966 | 1096554 |  | 100 | 72.44 | 0151 | 6418909 | 12 | 6418911 | 7815877 | 511 | 02.12.2012 | 30.04.2013 | 100 | 100 | 4700000 | 0064 | ADB | Hand over | 15295.2583
212 | 43030 | Aylapatakata DR-1 | Barguna | Sadar | ….. Khal & O&M Shed | M/s. Israt Enterprise, Amtali, Barguna. | 04.11.2012 | 04.11.2013 | 1400227 | 1396227 | 1357000 |  | 100 | 100 | 0110 | 7785516 | 19 | 7785516 | 9181743 | 720 | 08.11.2012 | 30.04.2013 | 100 | 100 | 7749000 | 0065 | ADB | Completed & Handed Over | 12752.4208
213 | 43029 | Burichar-Nur Ali Charakgachia | Barguna | Sadar | ….. Khal & O&M Shed | M/S. Mithun Traders, High School road, Barguna | 30.10.2012 | 30.10.2013 | 1391428 | 1390578 | 1385000 |  | 100 | 100 | 0111 | 6328986 | 14 | 6328986 | 7719564 | 500 | 16.09.2012 | 30.04.2013 | 100 | 100 | 6301000 | 0054 | ADB | Completed & Handed Over | 15439.128
214 | 43044 | Garabania | Barguna | Amtoly | 3 Khal & 3 Branch Khal = 8.5 km O&M Shed (12.0m X 6.0m) | M/S . Fatema Enterprise, Amtali, Barguna. | 18.03.2013 | 18.03.2014 | 1391428 | 1390035 | 1361000 |  | 100 | 100 |  | 4697748 | 12 | 4697748 | 6087783 | 300 | 04.11.12 | 30.04.2013 | 100 | 100 | 4674000 | 0005 | IFAD-2 | Completed & Handed Over | 20292.61
215 | 43034 | Potka Khali DR & Irri. | Barguna | Sadar | ….. Khal & O&M Shed | M/S. Hasanl Enterprise College Branch road, Barguna | 30.10.2012 | 30.10.2013 | 1391428 | 1387528 | 1313000 |  | 100 | 100 | 0108 | 6014216 | 13 | 6014216 | 7401744 | 597 | 10.09.12 | 30.04.2013 | 100 | 100 | 6003000 | 0055 | ADB | Completed & Hannded over | 12398.2312
216 | 46234 | Shambari-Kalihari Khal | B-Baria | Kashba | 4 Khal = 10.00 Km WMCA Office = 1 | M/S Rinkey Enterprise | 01.06.16 | 01.06.17 | 1283317 | 1381812 |  |  | 0 |  |  | 5182628 | 13 | 5182628 | 6564440 | 500 | 06.01.2016 | 30.04.2016 | 35 | 18 | 1499723 |  | ADB | O&M Shed not started. Earthwork Running. | 13128.88
217 | 45155 | Baro Raghunathpur | Barisal | Bakerganj | 5 Khal = 7.67 km WMCA Office | M/S E.A Enterprise | 12.05.2016 | 18.02.2017 | 1307593 | 1381100 | 400000 |  | 75 | 29 |  | 6190634 | 16 | 6190634 | 7571734 | 402 | 20.01.2016 | 30.04.2016 | 100 | 90 | 5630000 |  | IFAD-2 | To complete by December, 2016 | 18835.1592
218 | 46219 | Muladi | Barisal | Muladi | 7 Khal 10.8 Km WMCA Office | M/S S R Builders, College Road, Barisal | 19.05.2016 | 24.02.2017 | 1312273 | 1376249 | 500000 |  | 100 | 36 |  | 9101121 | 20 | 9101121 | 10477370 | 520 | 17.01.2016 | 30.04.2016 | 100 | 64 | 5787000 |  | IFAD-1 | Completed | 20148.7885
219 | 46221 | Uzirpur | Barisal | Uzirpur | 6 Khal 14.00 Km | M/S Hemany Enterprise, West Bagura Road, Munshi Grage, Barisal | 19.05.2017 | 24.02.2018 | 1382528 | 1376057 |  |  | 0 |  |  | 9507760 | 22 | 9507760 | 10883817 | 700 | 14.02.2016 | 30.04.2016 | 50 | 39 | 3694000 |  | IFAD-1 | Construction work delayed for land problem | 15548.31
220 | 44077 | Saorakathi | Jhalokathi | Sadar | 6 Khal 11.5 km& O&M Shed | M/S.Khandaker Business Jholokathi | 07.05.2014 | 06.02.2015 | 1375922 | 1375000 | 1374789 |  | 100 | 100 | 0070 | 10744580 | 21 | 10744580 | 12119580 | 750 | 17.12.2013 | 30.04.2014 | 100 | 100 | 10641666 | 30 | IFAD-2 | Completed & Handed Over | 16159.44
221 | 44083 | Amua Patikhalghata | Jhalokati | Katalia | 6 Khal 13.30 km & O&M Shed | M/S Siraj Enterprise, Jholokathi | 25.09.2014 | 24.09.2015 | 1374984 | 1374427 | 1369786 |  | 100 | 100 | 0237 | 11328431 | 27 | 11328431 | 12702858 | 920 | 17.04.2014 | 30.04.2015 | 100 | 100 | 11178221 | 188 | ADB | Completed | 13807.4543
222 | 43068 | Pascim Char Madras | Bhola | Charfession | 6 Khal 22.00 Km O&M Shed | M/S Haider Builders Chalk bazar, Bhola | 02.03.2014 | 01.12.2014 | 1374429 | 1374252 | 1366826 |  | 100 | 100 | 0092 | 18394637 | 35 | 18394637 | 19768889 | 890 | 19.12.2013 | 30.04.2014 | 100 | 80 | 14320335 | 0035 | IFAD-1 | completed | 22212.2348
223 | 44085 | Aarabunia | Jhalokati | Katalia | 5 Khal 4.5 km & O&M Shed | M/S Rayhan Construction, Nalchity Jholokathi | 03.12.2013 | 02.12.2014 | 1374984 | 1374243 |  |  |  |  | 0245 | 12834722 | 29 | 12834722 | 14208965 | 760 | 28.01.2014 | 30.04.2014 | 100 | 100 | 12516574 |  | ADB | LCS work completed and WMCA office work problem | 18696.0066
224 | 43070 | Panchagram | Jhalokathi | Nalchiti | 6 Khal = 14.7 km O&M Shed = 1 | M/S Islam Brothers Jhalokathi | 21.09.2015 | 20.09.2016 | 1375922 | 1374196 |  |  | 100 |  |  | 13715643 | 28 | 13715643 | 15089839 | 820 | 25.11.2015 | 30.04.2016 | 100 | 100 | 134307711 |  | ADB | completed | 18402.2427
225 | 43067 | Purba Char Madras | Bhola | Charfession | 6 Khal 13.00 Km O&M Shed | M/S. Haider Builders Chack Bazar, Bhola | 11.11.2015 | 20.09.2016 | 1374429 | 1374101 | 1370854 |  | 100 | 100 |  | 13791552 | 27 | 13791552 | 15165653 | 769 | 05.01.2015 | 30.04.2015 | 70 | 60 | 8199211 |  | ADB | Structure work completed & LCS work not completed because design khal length problem | 19721.2653
226 | 44127 | Haripasha-Pironda | Jhalokati | Sadar | 5 Khal 11.00 Km O&M Shed | M/S. Islam Brother Jholokathi | 21.12.2014 | 20.12.2015 | 1374429 | 1373977 | 1370930 |  | 100 | 100 |  | 12540385 | 30 | 12540385 | 13914362 | 862 | 19.11.2014 | 30.04.2015 | 100 | 100 | 12394790 | 46 | IFAD-2 | Completed | 16141.9513
227 | 43042 | Atrai-Burigang Subproject | Noagaon | Atrai | * 6.73 km khal * O&M Shed | Md. Golam Rabbani (Dulal), Hat Noagaon, Naogoan Soyadhengore, Sirajgonj. | 13.06.2013 | 13.06.2014 | 1373904 | 1373814 | 1419619 |  | 100 | 100 | 0035 | 7581290 | 12 | 7581290 | 8955104 | 1000 | 19.11.2012 | 30.04.2013 | 100 | 100 | 8800000 | 0006 | IFAD-2 | Revised 3.37% more | 8955.104
228 | 44106 | Sachilapur | Jhalokathi | Sadar | 6 Khal 12 km & O&M Shed | M/S Ishana Construction, Sadar, Jholokathi | 17.09.2014 | 16.09.2015 | 1374429 | 1373552 | 1371169 |  | 100 | 100 | 0244 | 8450206 | 21 | 8450206 | 9823758 | 480 | 16.03.2014 | 30.04.2015 | 100 | 100 | 8154199 | 182 | ADB | Completed & Handed over | 20466.1625
229 | 44104 | Sarengal | Jhalokathi | Sadar | 6 Khal 14.20 km & O&M Shed | M/S Saidul Haque, Jholokathi | 18.09.2014 | 17.09.2015 | 1374429 | 1373372 | 800000 |  | 100 | 58 | 0064 | 9643668 | 26 | 9643668 | 11017040 | 440 | 24.03.2014 | 30.04.2015 | 100 | 100 | 9530567 | 39 | IFAD-2 | Completed & Handed over | 25038.7273
230 | 44138 | Ramanathpur | Jhalokati | Sadar | 5 Khal 11.20 Km O&M Shed | M/S Islam Brothers Jhalokathi | 21.09.2015 | 20.09.2016 | 1374429 | 1373341 |  |  | 90 |  |  | 10602678 | 21 | 10602678 | 11976019 | 800 | 18.12.2014 | 30.04.2015 | 100 | 100 | 10094682 | 205 | ADB | Minor work pending | 14970.0238
231 | 44117 | Deulkathi-Binnapara | Jhalokathi | Sadar | O&M Shed, 11 Km = 5 Khals | M/S. Islam Brother Jholokathi | 21.12.2104 | 20.12.2015 | 1374429 | 1373298.4 | 1007218 |  | 100 | 75 | 0098 | 10984094 | 23 | 10984094 | 12357392.4 | 884 | 24.11.2014 | 30.04.2015 | 100 | 100 | 10769857 |  | IFAD-1 | Completed | 13978.9507
232 | 43069 | Char Samaia | Bhola | Sadar | 3 Khal 10.50 Km | Md. Abul Kashem, Ukilpara, Bhola | 20.07.2016 | 27.02.2017 | 1374429 | 1373089 | [5 empty] | 6680237 | 14 | 6680237 | 8053326 | 267 | 22.04.2015 | 30.04.2016 | 10 | 10 | 667300 |  | IFAD-2 | O&M shed work droped . LCS work slow progress | 30162.2697
233 | 45211 | Uttampur Drainage | Barisal | Bakerganj | 6 Khal 9.20 Km WMCA Office | M/S Rupali Construction Hospital Road, Barisal | 16.05.2016 | 22.02.2017 | 1309963 | 1372903 |  |  | 10 |  |  | 7186134 | 16 | 7186134 | 8559037 | 550 | 04.01.2016 | 30.04.2016 | 100 | 66 | 4705000 |  | IFAD-1 | O&M Shed not done. Post work measurement needed. | 15561.8855
234 | 45154 | Harina Chengagashia | Comilla | Chindina | 7 Khal = 15.924 Km O&M Shed = 1 (12m X 6m) | M/S Hadayet Enterprise Chandina, Comilla | 21.09.2015 | 20.09.2016 | 1311347 | 1371558.84 |  |  | 100 |  |  | 8907352 | 21 | 8907352 | 10278910.84 | 1000 | 31.03.2015 | 30.04.2016 | 23 | 20 | 1904830 | 68 | IFAD-1 | Document with ADB (WMCA office work complete) LCS work stop due to over rain filled up water | 10278.9108
235 | 43040 | Singkhali | Barguna | Amtoly | ….. Khal & O&M Shed | Md. Alauddin Mridha, Amtali, Barguna. | 18.03.2013 | 24.02.2014 | 1365949 | 1366948 | 1364000 |  | 100 | 100 |  | 9918107 | 21 | 9918107 | 11285055 | 570 | 05.11.12 | 30.04.2013 | 100 | 100 | 9894000 | 0010 | IFAD-1 | Completed & Hannded over | 19798.3421
236 | 45164 | Nandigram-Muragacha | Kustia | Kumarkhali | 7 Khal = 8.975 Km Box culvert = 3 (2V- 3.5m X 4.0m), (1V-2.0m X 2.0m) & (1V-3.0m X 3.0m) WMCA Office = 1 | M/S Abdus Sattar Kumarkhali, Kushtia | 14.04.2016 | 14.04.2017 | 1283711 | 1350450 |  |  | 100 |  |  | 3925843 | 14 | 3925843 | 5276293 | 882 | 29.03.2015 | 30.04.2016 | 95 | 46 | 1795253 |  | IFAD-2 | work completed | 5982.1916
237 | 43048 | Deshantorkathi-Goaribonia | Barguna | Betagi | 6 Khal & 2 Branch Khal = 13.995 km WMCA Office | M/S . Kohinoor Construction, Goriabunia, Betagi, Barguna. | 13.06.2013. | 13.06.2014 | 1365048 | 1340034 | 1269000 |  | 100 | 100 |  | 10681557 | 25 | 10681557 | 12021591 | 625 | 27.01.2013 | 30.04.2013 | 100 | 95 | 10502000 |  | ADB | Completed & Handed Over | 19234.5456
238 | 44131 | Guarekha | Perojpur | Nesarabad | 7 Khal 11.10 km. 1 O&M Shed | M/S New Five Star Bricks. Pro. Md. Sultan Ahmed, Jhatakari, Pirojpur. | 30.12.2015 | 06.01.2016 | 1374429 | 1321659 | 515000 |  | 90 | 37 |  | 9266583 | 22 | 9266583 | 10588242 | 1070 | 04.12.2014 | 30.04.2015 | 100 | 66.16 | 6130958 |  | IFAD-1 | Joint measurment Remaining. O&M shed on going | 9895.5533
239 | 44076 | Paschim Gopalpur | Jhalokati | Nalchithi | 9 Khal 13.6 km & O&M Shed | M/S Islam Brothers Jhalokathi | 21.09.2015 | 20.09.2016 | 1319038 | 1317789 | 800000 |  | 100 | 60 |  | 11232784 | 24 | 11232784 | 12550573 | 883 | 19.10.2015 | 30.04.2016 | 100 | 95 | 11169101 |  | IFAD-1 | completed | 14213.5595
240 | 44080 | Challiskhania | Jhalokathi | Rajapur | 9 Khal 11.62 km & O&M Shed | M/S M.M. Enterprise, Barisal | 24.09.2014 | 23.06.2015 | 1319038 | 1317572 | 1233215 |  | 100 | 100 | 0258 | 10607426 | 25 | 10607426 | 11924998 | 869 | 25.03.2014 | 30.04.2015 | 100 | 100 | 10293162 | 190 | ADB | Completed & Handed Over | 13722.6674
241 | 43062 | Gouripur | Pirojpur | Bhandaria | 8 Khal 16 km 1 O&M Shed | M/S Jiaul & Brothers Prop. Khandakar Jiaul Hossain, Bhandaria, Pirojpur. | 31.08.15 | 21.09.15 | 1314303 | 1314220 | 500000 |  | 100 | 38 | 0251 | 9574907 | 23 | 9574907 | 10889127 | 791 | 06.08.2014 | 30.04.2015 | 100 | 66.3 | 6347987 |  | ADB | work completed. Joint post work measurment completed | 13766.2794
242 | 45200 | Kamaldeni Amishapara Khal | Noakhali | Sonaimuri | 1 Khal = 5.10 km WMNCA office = 1 | M/S Rehana Construction | 25.04.2016 | 01.05.2017 | 1312846 | 1312615 |  |  | 95 |  |  | 3720351 | 9 | 3720351 | 5032966 | 322 | 28.01.2016 | 30.04.2016 | 0 |  |  |  | ADB | LCS work not started | 15630.3292
243 | 45166 | Burinadi-Jugidhara | B.baria | Nabinagar | 1 Khal = 4.65 WMCA Office 1 | M/S Rinky Enterprise Badugun Sadar B. Baria | 9.11.2015 | 30.11.2016 | 1311347 | 1308359 | 0 |  | 45 |  |  | 5433452 | 12 | 5433452 | 6741811 | 426 | 09.11.2015 | 30.04.2016 | 60 | 27 | 1459000 |  | IFAD-1 | work is ongoing | 15825.8474
244 | 45197 | Harintana Gholer Khal | Khulna | Dacope | 3 Khal 13.457 Km WMCA Office | M/S Milton Enterprise Dacopr Khulna | 14.02.2016 | 24.02.2017 | 1303884 | 1300053 | 826908 |  | 80 | 63 |  | 11192097 | 24 | 11192097 | 12492150 | 810 | 14.01.2016 | 30.04.2016 | 100 | 59 | 6636101 |  | IFAD-2 | Completed | 15422.4074
245 | 45181 | Sarsina-Alonkerkathi | Pirojpur | Neserabad | Only WMCA Office 7 Khal = 12.75 km | M/S Mahafuzur Rahman | 06.05.16 | 27.02.17 | 1311610 | 1293791 | 0 |  | 100 | 0 |  | 7268432 | 19 | 7268432 | 8562223 | 698 | 09.03.2015 | 30.04.2015 | 100 | 68 | 4962700 | 52 | IFAD-2 | Joint post work measurement completed. O&M shed work completed | 12266.7951
246 | 45185 | Aramkathi-Kamarkathi | Pirojpur | Nesarabad | WMCA Office =1 Khal = 14.49 km | M/S Rezon Enterprise | 06.05.16 | 27.02.17 | 1305048 | 1285780 | 318000 |  | 70 | 25 |  | 5235808 | 15 | 5235808 | 6521588 | 480 | 09.03.2015 | 30.04.2015 | 100 | 65 | 3393100 | 52 | IFAD-2 | Joint post work measurement completed. O&M shed work ongoing | 13586.6417
247 | 46240 | Amtoli-Ruhita-Patkakhali | Barguna | Bamna | Khal = 17.00 km WMCA Office = 1 | M/S Business Centre High School Road Barguna | 27.01.2016 | 31.12.2016 | 1413018 | 1235533 | 1413000 |  | 100 | 100 |  | 14301739 | 32 | 14301739 | 15537272 | 847 | 04.01.2016 | 30.04.2016 | 100 | 50 | 7300000 |  | ADB | Completed | 18343.8867
248 | 45148 | Bottola | Jhalokati | Nalcity | 7 Khal = 12.00 km WMCA Office = 1 | M/S Islam Brothers Jhalokathi | 21.09.2015 | 20.09.2016 | 1231264 | 1229376 | 919348 |  | 100 | 75 |  | 12094806 | 26 | 12094806 | 13324182 | 922 | 25.11.2015 | 30.04.2016 | 100 | 100 | 11924499 |  | IFAD-1 | Minor work pending | 14451.3905
249 | 46249 | Noldoani Khal | Patuakhali | Dumki | 4 Khal 7.97 Km WMCA Office | M/S Palli Stores, Town Kalikapur, Patuakhali | 15.05.2016 | 28.02.2017 | 1413019 | 1228941 |  |  | 35 |  |  | 7206805 | 17 | 7206805 | 8435746 | 230 | 14.01.2016 | 30.04.2016 | 100 | 66 | 4837681 |  | IFAD-1 | Earth work completed & structure work ongoing | 36677.1565
250 | 46258 | Itbaria | Patuakhali | Sadar | 6 Khal 12.10 Km WMCA Office | Mohiuddin Ahmad | 26.05.2016 | 27.02.2017 | 1413019 | 1184840 |  |  | 0 |  |  | 13557274 | 28 | 13557274 | 14742114 | 560 | 12.01.2016 | 30.04.2016 | 100 | 50 | 6907050 |  | IFAD-1 | Earth work completed & structure work ongoing | 26325.2036
251 | 46253 | Arua-Kamini Khal | Barguna | Amtoly | 8 Khal 4.99 Km WMCA Office | Md. Shahidul Islam Munsefpara, Patuakhali | 13.04.2016 | 13.10.2016 | 1426214 | 1182905 |  |  | 80 |  |  | 2830494 | 10 | 2830494 | 4013399 | 225 | 12.01.2016 | 30.04.2016 | 100 | 25 | 772000 |  | IFAD-1 | O&M Shed pending. Post work done. | 17837.3289
252 | 46252 | Kukua-Nimtar Khal | Barguna | Amtoly | 7 Khal 11.22 Km WMCA Office | Md. Shikder Enterprise Patuakhali | 13.04.2016 | 13.10.2016 | 1426214 | 1181659 |  |  | 60 |  |  | 7652239 | 19 | 7652239 | 8833898 | 409 | 12.01.2016 | 30.04.2016 | 100 | 3500000 | 1900000 |  | IFAD-2 | 1 Khal pending. May be treated as final for LCS work. | 21598.7726
253 | 45144 | Perimial Khal-Baroaulia Beel | Brahamanbaria | Nabinagar | 2 Khal = 5.4 Km 1 O&M Shed | M/S. Fahim Enterprise Kazipara, Brahmanbaria. | 01.04.2015 | 30.01.2016 | 1384919 | 1169633.6 | 1169244 |  | 100 | 100 | 0239 | 3031962 | 7 | 3031962 | 4201595.6 | 376 | 21.12.2014 | 30.04.2015 | 95 | 69 | 2105356 |  | ADB | Completed | 11174.4564
254 | 45152 | Biddanandapur | Barisal | Mehendiganj | 5 Khal, 9 km, O&M Shed = 1 No. | M/S, Hasan Enterprise, Latif School Road, Patuakhali. | 26.05.2015 | 25.05.2016 | 1310867 | 1091706 | 1076367 |  | 100 | 98.59 |  | 6313401 | 13 | 6313401 | 7405107 | 383 | 21.12.2014 | 30.04.2015 | 100 | 100 | 6144000 | 60 | IFAD-1 | Completed & Handed Over | 19334.483
255 | 45150 | Chandpasha | Barisal | Babuganj | 9 Khal = 9.91 km O&M Shed | Md. Sirajul Islam Hanif Doarika, Rakudia, Babugonj, Barisal. | 20.08.2015 | 20.06.2016 | 1290689 | 1059094 | 900000 |  | 100 | 100 |  | 9353327 | 22 | 9353327 | 10412421 | 616 | 24.02.2015 | 30.04.2015 | 100 | 100 | 9070000 | 66 | IFAD-1 | Completed | 16903.2808
256 | 45161 | Kalatola Kailashgonj | Khulna | Dakope | WMCA Office = 1 4 Khal = 7.35 Km | No Structure |  |  | 3661593 | [6 empty] | 8030010 | 17 | 8030010 | 8030010 | 394 | 14.02.2016 | 30.04.2017 | 100 | 59 | 4714937 | 68 | IFAD-1 | Completed Only LCS | 20380.736
257 | 45163 | Chayani Khal | Dhaka | Dhamrai | Regulator = 1 1 Khal = 1.40 Km WMCA Office = 1 |  |  |  | 7632216 | [6 empty] | 1862946 | 4 | 1862946 | 1862946 | 500 |  |  | 30 | 30 | 555000 |  | IFAD-1 |  | 3725.892
258 | 45175 | Amlagari-Tulshiganga | Joypurhat | Khatlal | Pond as fish santuary = 1 no. (135m) Regulator 1-vent (1.5m X 1.8m) = 1 Irrigation canal -1 (L-100m) Irrigation canal-2 (L-100m) Khal = 1.30 km O&M Shed = 1 |  |  |  | 4758537 | [6 empty] | 9028983 | 20 | 9028983 | 9028983 | 600 | 24.10.15 | 30.04.16 | 100 | 59 | 5354362 |  | IFAD-1 |  | 15048.305
259 | 45183 | Bhanderkota-Laxmikhola | Khulna | Botiaghata | 7 Khal 9.587 Km 4 Box Culvert WMCA Office |  |  |  | 6977845 | [6 empty] | 7877105 | 15 | 7877105 | 7877105 | 620 | 10.02.0216 | 30.04.2016 | 70 | 37 | 2950554 |  | ADB | OnlyLCS work | 12705.0081
260 | 46235 | Ashian | Jhalokathi | Sadar | 6 Khal = 11.50 km O&M Shed 1 | No Structure | [9 empty] | 8416514 | 18 | 8416514 | 8416514 | 697 | 20.04.2016 | 31.12.2016 | 0 |  |  |  | IFAD-1 | Dec 2016. | 12075.3429
261 | 46239 | Kirtipasa | Jhalokathi | Sadar | 6 Khal = 11.90 km WMCA Office 1 | No Structure | [9 empty] | 5379458 | 17 | 5379458 | 5379458 | 536 | 31.01.2016 | 30.04.2016 | 0 |  |  |  | ADB | From IFAD-1 | 10036.3022
262 | 46279 | Komorbhog-Raipur-Ajail | Kushtia | Khoksha | 6 Khal = 10.69 km Culvert = 2 WMCA Office = 1 | No Structure | [9 empty] | 3657283 | 9 | 3637000 | 3637000 | 480 | 4.12.2016 | 27.02.2017 |  |  |  |  | ADB | LCS list with agreement work done | 7577.0833
263 | 46280 | Diakul | Jhalokathi | Sadar | 7 Khal = 11.36 km WMCA Office 1 | No structure | [9 empty] | 8082308 | 16 | 8082308 | 8082308 | 450 | 24.02.2016 | 30.04.2016 | 100 | 100 | 7952970 |  | ADB | Completed | 17960.6844
264 | 46281 | Kodomtola | Jholokathi | Rajapur | 4 Khal = 8.00 km WMCA Office 1 | No Stucture | [9 empty] | 5487401 | 11 | 5487401 | 5487401 | 580 | [6 empty] | ADB |  | 9461.0362
265 | 46288 | Dhopadah Khal | Narai | Lohagara |  | No Stucture | [9 empty] | 3821541 | 7 | 3821541 | 3821541 | 592 | [8 empty] | 6455.3057
Total | [9 empty] | 2819641537.13 | 1637433737 | 800 | 20084 | 14524.313 | 3239 | 1788881588 | 4023 | 1787184368 | 4606825905.13 | 158577 | 0 | 0 | 20738 | 3516193.03 | 1329436675 | 5776 | 0 | 1

## Sheet3
87841874
79103874
71115798
60382756
56624771
52174675.36
51100204
46847632
43401437
40937711
40830025
40475104
40382722.5
39347887
32704688
31743141
29536526
29028450
28614373
27369121.25
25725600
25358282.23
25164837
25121675
25109967
24764953
24287709
24219268
22997002
22317913
22290531
20373544
20154457
20096796
19665853
19360395
19191432
18889405
18561110
18460536
18223990
18181992
18114956
18030670
17600620
17503781
16908441
16761968
16518652
16491491
16375981.53
16159031
15969266
15730637
15636104
15489363
15468364
15374768
15359900
15340689
15335999
15269345
14965258
14921666
14863189
14828475
14705932.8
14572034
14451372
14423573.08
14408915
14403817
14327796
13796661
13795548
13780885
13689960
13499996
13447929
13392979
13123165
13069475
13044043.44
12500048
12483256
12450082
12308166.95
12154225
11912403.79
11828029.52
11686950
11623349
11567193
11416804
11251671
10868329
10732471
10652297
10585118
10546085
10437714
10304054
10261218.61
10238926
10052576.54
10046439
10027665.51
9975156
9898572
9848847
9606830
9578053
9528365
9516421
9396338
9282603
9089348
9081892
9067546
8862743.46
8802256
8626859
8561633
8234340
8232588
8217224
7889072
7873797
7765986
7764586
7749999
7680934
7500404
7491686
7334559
7144211
6922739
6575460
6470971
6280777
5969576
5625683.62
5563742
5477628.87
5296645
5245462
5171439
5075276
5028302
4975494.29
4846221
4838253
4828899
4177597
4099172
4036420
3981954.58
3936427
3859385
3825985
3800195
3794132
3697764
3487135
3442267
3235014
3107454
2956222
2825021
2279420
1730165
1649328
1612948
1569195
1563247
1523431
1517034.34
1516742
1511346
1509447
1493370
1492908
1483510
1483434
1482612
1480874.94
1479084
1469637
1463241
1452940.47
1443362
1440899
1440375.95
1440180.89
1438746.19
1434775
1432972
1432583
1431086.72
1426932
1407251
1406903
1405505
1402778
1400214
1399227
1399057
1398701
1398697
1397395.86
1396966
1396227
1390578
1390035
1387528
1381812
1381100
1376249
1376057
1375000
1374427
1374252
1374243
1374196
1374101
1373977
1373814
1373552
1373372
1373341
1373298.4
1373089
1372903
1371558.84
1366948
1350450
1340034
1321659
1317789
1317572
1314220
1312615
1308359
1300053
1293791
1285780
1235533
1229376
1228941
1184840
1182905
1181659
1169633.6
1091706
1059094
2819641537.13
5639283074.26