## Urban
cÖKí msµvšÍ gvwmK AMÖMwZi cÖwZ‡e`b
Ryb/2018Bs¦
cÖK‡íi bvg t wmwU Mfvib¨vÝ cÖ‡R± (CGP) (cÖKí †KvW- 5118)
cÖv°wjZ e¨q (j¶ UvKvq) |  | t | g~j t | 294300 |  |  | ms‡kvwaZ t -
ev¯ÍevqbKvjt |  | t | g~j t | Ryjv&B/2014 n‡Z Ryb/2020 ch©šÍ |  |  | ms‡kvwaZ t -
cÖKí ïiæ †_‡K cÖvß nvjbvMv` †gvU eivÏ |  | t | †gvU t | 89144 | { wRIwe t | 14218 | cÖK‡íi mvnvh¨ t | 74926 | (AviwcGt | 62734 |  | wWwcG t | 12192 |  | )}
eZ©gvb A_© eQ‡i ms‡kvwaZ eivÏ |  | t | †gvU t | 40932 | { wRIwe t | 7756 | cÖK‡íi mvnvh¨ t | 33176 | (AviwcGt | 29334 |  | wWwcG t | 3842 |  | )}
eZ©gvb A_© eQ‡i Aegyw³ |  | t | †gvU t | 40932 | { wRIwe t | 7756 | cÖK‡íi mvnvh¨ t | 33176 | (AviwcGt | 29334 |  | wWwcG t | 3842 |  | )}
eZ©gvb A_© eQ‡i e¨q |  | t | †gvU t | 40927.51 | { wRIwe t | 7751.51 | cÖK‡íi mvnvh¨ t | 33176 | (AviwcGt | 29334 |  | wWwcG t | 3842 |  | )}
µgcywÄZ nvjbvMv` ‡fŠZ AMÖMwZ |  | t |  | 33%
µgcywÄZ nvjbvMv` e¨q |  | t |  | 89136.8274
µwgK bs | wWwcwc Abymv‡i As‡Mi bvg (cwigvb/msL¨v) | wWwcwc Abymv‡i eivÏ (j¶ UvKvq) | eZ©gvb A_© eQ‡i GwWwc Abyhvqx ms‡kvwaZ j¶¨gvÎv |  |  | PjwZ gv‡mi AMÖMwZ |  |  |  |  | PjwZ A_© eQ‡ii µgcywÄZ AMÖMwZ |  | PjwZ gvm ch©šÍ µgcywÄZ Pyw³g~j¨ |  | gšÍe¨ | c~‡e©i gvm ch©šÍ LiP
|  |  | ‡fŠZ | Avw_©K |  | †fŠZ |  | Avw_©K
[11 empty] | ‡fŠZ | Avw_©K
1 | 2 | 3 | 4 | 5 |  | 6 |  | 7 |  |  | 8 | 9 | 10 |  | 11
(K) ivR¯^ eivÏ
1 | Kg©KZ©v‡`i †eZb | 748.85 |  | 48 | 12 |  |  | 3.97 |  |  |  | 47.44 |  |  |  | 43.47 | 3.97
2 | Kg©Pvix‡`i †eZb | 250.48 |  | 13.22 | 3.305 |  |  | 0.33 |  |  |  | 13.22 |  |  |  | 12.89
3 | fvZvw` | 1238.13 |  | 51.09 | 12.7725 |  |  | 3.08 |  |  |  | 48.01 |  |  |  | 44.93
4 | mieivn I †mev | 38218.07 |  | 4425.69 | 1106.4225 |  |  | 569.379 |  |  |  | 4424.909 |  |  |  | 3855.53
5 | ‡givgZ msiÿY I cybe©vmb | 424 |  | 33 | 8.25 |  |  | 25.05 |  |  |  | 32.94 |  |  |  | 7.89
6 | ‡_vK eivÏ | 40 |  | 1e-65 |  |  |  | 0 |  |  |  | 0
| †gvU (K) ivR¯^ = | 40919.53 |  | 4571 | 1142.75 |  |  | 601.809 |  |  |  | 4566.519 |  | 0 |  | 3964.71
(L) g~jab eivÏ
| m¤ú` msMÖn/µq | 6064.74 |  | 1455 | 363.75 |  |  | 1455 |  |  |  | 1455
| Dc-‡gvU m¤ú` msMÖn/µq = | 6064.74 |  | 1455 | 363.75 |  |  | 1455 |  |  |  | 1455 |  | 0 |  | 0
| f‚wg AwaMÖnY/µq | 1374.01 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| Dc-‡gvU f‚wg AwaMÖnY/µq = | 1374.01 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
wbg©vY I c~Z©
| 7006 Awdm feb t (¯‹zj Kvg mvB‡K¬vb †mëvi) | 11445.4749 |  | 3635.21 | 1817.605 |  |  | 235.21 |  |  | 100% | 3635.21 |  | 4969 |  | 3400
| 7006 Awdm feb t (KwgDwbwU wi‡mvvm© †m›Uvi) | 1027.931 |  | 1e-32 | 5e-33 |  |  | 0 |  |  | 0% | 0 |  |  |  | 0
| 7021 moK I gnvmoK | 82666.467 |  | 13726.79 | 3431.6975 |  |  | 2126.791 |  |  | 100% | 13726.791 |  | 50625 |  | 11600 |  | 67500
| 7026 ‡mZz | 26046.7039 |  | 6186.93 | 1546.7325 |  |  | 636.93 |  |  | 100% | 6186.93 |  | 16875 |  | 5550
| 7041 cvwb wb®‹vkb AeKvVv‡gv | 51886.0335 |  | 9924.96 | 2481.24 |  |  | 1824.96 |  |  | 100% | 9924.96 |  | 37960 |  | 8100
| 7046 ¯^v¯’¨ cwiPhv© I cvwb mieivn | 11774.3017 |  | 1e-30 | 2.5e-31 |  |  | 0 |  |  | 0% | 0 |  | 515.8 |  | 0
| 7047 bjK‚c ¯’vcb | 1653.6313 |  | 1e-37 | 2.5e-38 |  |  | 0 |  |  | 0% | 0 |  |  |  | 0
| 7056 ˆe`y¨wZK ¯’vcbv | 9735.1955 |  | 657.11 | 164.2775 |  |  | 107.11 |  |  | 100% | 657.11 |  | 4782 |  | 550
| 7081 Ab¨vb¨ | 1675.9777 |  | 325 | 81.25 |  |  | 81.25 |  |  | 100% | 325 |  |  |  | 243.75
| Dc-‡gvU wbg©vY I c~Z© = | 197911.7165 |  | 34456 | 9522.8025 |  |  | 5012.251 |  |  |  | 34456.001 |  | 115726.8 |  | 29443.75
FY I AwMÖg
| 7351 Ab¨vb¨ FY | 500 |  | 250 | 125 |  |  | 25 |  |  |  | 100 |  |  |  | 75
| Dc-‡gvU FY I AwMÖg = | 500 |  | 100 | 125 |  |  | 25 |  |  |  | 100 |  | 0 |  | 75
wmwW f¨vU
| 7901 Avg`vbx ïé I f¨vU | 1520 |  | 350 | 87.5 |  |  | 304.68 |  |  |  | 350 |  | 0 |  | 45.32
| 7981 wewea g~jab e¨q | 100 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| Dc-‡gvU g~jab LvZ I wmwW f¨vU = | 1620 |  | 350 | 87.5 |  |  | 304.68 |  |  |  | 350 |  |  |  | 45.32
| ‡gvU (L) g~jab A½ = | 207470.4665 |  | 36361 | 10099.0525 |  |  | 6796.931 |  |  |  | 36361.001 |  | 115726.8 |  | 29564.07
| (M) 7981 wewea g~jab e¨q : cÖvBm Kw›U‡RÝx | 24590 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| (N) 7981 wewea g~jab e¨q : wdwRK¨vj Kw›U‡RÝx | 21320 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| Dc-‡gvU (M) + (N) = | 45910 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| me©‡gvU (K + L + M + N ) = | 294299.9965 |  | 40932 | 11241.8025 |  |  | 7398.74 |  |  |  | 40927.52 |  | 115726.8 |  | 33528.78
| ‡gvU (%) = | [6 empty] | 17.99% |  |  | 100% | 99.99% |  |  |  |  | 7398.74
wPwýZ mgm¨v t- Team Leader mn wKQz wKQz ¸iæZ¡c~Y© c‡` we‡`kx civgk©KMY RyjvB 2016 gvm †_‡K Abycw¯’Z wQ‡jb¦ d‡j Design I Resettlement Action Plan ˆZix wejw¤^Z n‡”Q weavq mvwe©Kfv‡e cÖK‡íi AMÖMwZI wejw¤^Z n‡”Q¦
(†gvt kvn&Rvnvb †gvj¬v)
cÖKí cwiPvjK
wbim‡bi mycvwik t- | [11 empty] | wmwU Mfvib¨vÝ cÖ‡R± (wmwRwc)
Note on Y34: Eaar Uddin: don't delet sae-2 mohichhunul. 26-06-2018

## PR(P-1)
cÖKí ev¯Íevqb cÖwZ‡e`b
cªwZ‡e`b Kvj : Ryb/2018Bs¦
01 | cÖK‡íi bvg | t |  | ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦
02 | Aby‡gv`b ch©vq | t | K) | 15-07-2014 Bs Zvwi‡L AbywôZ ECNEC mfv (¯§viK bs 20.00.0000.411.14.041.14-614 ZvwiL t 26-10-2014Bs) KZ…©K Aby‡gvw`Z nq¦ ¯’vbxq miKvi wefv‡Mi 05-11-2014Bs Zvwi‡Li ¯§viK bs 46.093.014.01.00.044.2013-1267 †gvZv‡eK Ò wmwU Mfvi‡bÝ cÖ‡R±Ó kxl©K cÖKí wWwcwci cÖkvmwbK Aby‡gv`b cÖ`vb Kiv nq¦
|  |  | L) | FY Pyw³i Kvh©KvwiZvi ZvwiL t 16/06/2014 Bs ¦
|  |  | M) | Dc‡`óv dvg© wb‡qv‡Mi ZvwiL t weMZ 12/07/2015Bs Zvwi‡L wRAvBAvB As‡ki Pzw³ m¤úv`b Kiv n‡q‡Q I MZ 06/08/2015 ZvwiL n‡Z KvR Avi¤¢ n‡q‡Q Ges MZ 01/09/2015 n‡Z weGgB As‡ki KvR ïiæ n‡q‡Q¦
03 | ms¯’v I gš¿bvj‡qi bvg | t |  | ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
|  |  |  | gš¿Yvjq | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿bvjq, ¯’vbxq miKvi wefvM¦
04 | cÖK‡íi D‡Ïk¨ | t | K) | cÖKíf‚³ 5wU wmwU K‡c©v‡ik‡bi cvewjK mvwf©m Dbœqb;
|  |  | L) | BbK¬zwmf wmwU Mfvib¨vÝ m¤ú‡K© cÖwkÿ‡Yi gva¨‡g †mevi gvb e„w×;
|  |  | M) | wmwU K‡c©v‡ikb mg~‡ni cÖkvmwbK `ÿZv e„w×; Ges
|  |  | N) | bMi AeKvVv‡gv AviI kw³kvjxKiY¦
05 | ev¯Íevqb Kvj | [7 empty] | g~j
|  | t | K) KvR Avi‡¤¢i ZvwiL | [5 empty] | RyjvB/2014 Bs
|  | t | L) cÖKí mgvwßi ZvwiL | [5 empty] | Ryb/2020 Bs
06 | cÖv°wjZ e¨q (j¶ UvKvq) | t |  | ‡gvU |  |  | x |  | 294300 | j¶ UvKv
|  |  |  | UvKv |  |  |  |  | 54531 | j¶ UvKv
|  |  |  | cÖKí mvnvh¨ |  |  |  |  | 239769 | j¶ UvKv
|  |  |  | cÖKí mvnv‡h¨i UvKvsk |  |  |  |  | 227262 | j¶ UvKv
07 | cÖKí mvnv‡h¨i Drm | t |  | RvBKv
[9 empty] | 119 | -1
cÖKí ev¯Íevqb cÖwZ‡e`b
cªwZ‡e`b Kvj : A‡±vei - 2008 Bs
01 | cÖK‡íi bvg | t |  | e„nËi h‡kvi ‡Rjv AeKvVv‡gv Db&œqb cÖÖKí
02 | Aby‡gv`b ch©vq | t | K) | 11-11-1998 Bs Zvwi‡L ECNEC KZ…©K PCP Ges 24-04-1999 Bs Zvwi‡L DPEC KZ…©K PP Aby‡gvw`Z¦ 20-05-2007Bs Zvwi‡L 1g ms‡kvwaZ wWwcwc Aby‡gvw`Z (15-05-2007Bs Zvwi‡L ¯’vbxq miKvi cj­x Dbœqb I mgevq gš¿Yvj‡qi `vwq‡Z¡ wb‡qvwRZ gvbbxq Dc‡`óv 1g ms‡kvwaZ wWwcwc Aby‡gv`b K‡i‡Qb)¦ 2007 mv‡ji eb¨v DËi c~Ye©vm‡bi Rb¨ cÖK‡íi †gqv` Ryb/2009 ch©šÍ e„w×mn we‡kl ms‡kvwaZ wWwcwc MZ 07-09-08Bs Zvwi‡L cwiKíbv Kwgk‡b AbywôZ wcBwm-i mfvq mycvwik jvf K‡i‡Q¦ eZ©gv‡b c~YM©wVZ we‡kl ms‡kvwaZ wWwcwc-wU ¯’vbxq miKvi wefv‡M cÖwµqvaxb Av‡Q¦
|  |  | L) | FY Pyw³i Kvh©KvwiZvi ZvwiL t cÖ‡hvR¨ b‡n ¦
|  |  | M) | Dc‡`óv dvg© wb‡qv‡Mi ZvwiL t cÖ‡hvR¨ b‡n ¦
03 | ms¯’v I gš¿bvj‡qi bvg | t |  | ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
|  |  |  | gš¿Yvjq | t | ¯’vbxq miKvi, cj­x Dbœqb I mgevq gš¿bvjq, ¯’vbxq miKvi wefvM
04 | cÖK‡íi D‡Ïk¨ | t | 1) | ‡mZy/KvjfvU© mn Dc‡Rjv moK I BDwbqb moK Dbœq‡bi gva¨‡g e„nËi h‡kvi ‡Rjvq mvwe©K e¨e¯’v Dbœqb Ges ‡hvMv‡hvM e¨e¯’v Dbœqb Ges ‡MÖv_ ‡m›Uvi I ¸i“Z¡c~Y© nvU evRv†ii AeKvVv‡gv (‡fŠZ myweavw`) Dbœq‡bi gva¨‡g MÖvgxY A_©bxwZ‡K ‡eMevb KivB cÖK‡íi D†Ïk¨ ¦
|  |  | 2) | cÖKífy³ Kvh©µ‡gi g‡a¨ ‡mZy/KvjfvU©mn Dc‡Rjv moK I BDwbqb moK Dbœqb, ‡MÖv_ ‡m›Uvi I nvUevRvi Dbœqb, mo‡Ki cv‡k¦© e„¶‡ivcY Ges GbwRI‡`i gva¨‡g `wi`ª‡`i Rb¨ `¶Zv e„w×i cÖwk¶Ymn ÷vd cÖwk¶Y Kvh©µg AšÍ©f~³ iwnqv‡Q ¦
05 | ev¯Íevqb Kvj | [7 empty] | g~j |  | 1g ms‡kvwaZ wWwcwc | 2q ms‡kvwaZ wWwcwc (Abby‡gvw`Z)
|  | t | K) KvR Avi‡¤^i ZvwiL | [5 empty] | 1 RyjvB/1998 Bs |  | 1 RyjvB/1998 Bs | 1 RyjvB/1998 Bs
|  | t | L) cÖKí mgvwßi ZvwiL | [5 empty] | 30 Ryb/2002 Bs |  | 30 Ryb/2008 Bs | 30 Ryb/2009 Bs
06 | cÖv°wjZ e¨q (j¶ UvKvq) | t |  | ‡gvU |  |  | x | 15200.00 j¶ UvKv |  |  | 16650.00 j¶ UvKv | 18140.70 j¶ UvKv
|  |  |  | UvKv |  |  |  | 15200.00 j¶ UvKv |  |  | 16650.00 j¶ UvKv | 18140.70 j¶ UvKv
|  |  |  | cÖKí mvnvh¨ |  |  |  | (-) |  |  | (-) | (-)
|  |  |  | cÖKí mvnv‡h¨i UvKvsk |  |  |  | (-) |  |  | (-) | (-)
07 | cÖKí mvnv‡h¨i Drm | t |  | evsjv‡`k miKvi (wRIwe)
3(1)

## PR(P-2)
08 | e¨q ( j¶ UvKvq ) t
[8 empty] | (j¶ UvKvq) |  | 6459.31
|  | ‡gvU | UvKv (wRIwe) | cÖKí mvnvh¨ |  | ïé | FY cwi‡kva | gšÍe¨
|  |  |  | ‡gvU | UvKvsk (AviwcG) |  |  |  | 9802.95
42777.4
(K) | 2017-2018Bs A_© erm‡ii ms‡kvwaZ GwWwc eivÏ¦ | 40932 | 7756 | 33176 |  | 350 |  |  | -79333.87 | 41750 | 2007 mv‡ji eb¨v DËi c~Ye©vm‡bi Rb¨ cÖK‡íi †gqv` Ryb/2009Bs ch©šÍ e„w×mn we‡kl ms‡kvwaZ wWwcwcwU ¯’vbxq miKvi wefvM KZ…©K MZ 14-12-08Bs Zvwi‡L GjwR/cwi-1/GjwRBwW-7/98(Ask-1)/699 bs ¯§viK c‡Î cÖkvmwbK Aby‡gv`b cÖ`vb Kiv n‡q‡Q¦
[5 empty] | 29334 |  |  |  | 509.54
(L) | 2017-2018Bs A_© erm‡ii Ryb /2018Bs ch©šÍ Aegyw³ ¦ | 40932 | 7756 | 33176 |  | 350 |  |  | 89136.82
[5 empty] | 29334 |  |  |  | 1336.85
(M) | 2017-2018Bs A_© erm‡ii Ryb /2018Bs ch©šÍ e¨q ¦ | 40927.51 | 7751.51 | 33176 |  | 350 |  |  | 30.2877
[5 empty] | 29334 |  |  |  | 30.2877
(N) | cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q ¦ | 89136.82 | 14210.82 | 74926 |  | 366.77 |  |  | 3098 | -61749.88
[5 empty] | 62734 |  |  |  | 10849.51
[9 empty] | 1939 | 3878
5177
09 | cÖKí mvnvh¨ UvKvsk e¨q, `vex I cÖvwß (j¶ UvKvq)
welq |  | PjwZ A_© erm‡ii µgcywÄZ |  |  | µgcywÄZ
(K) | e¨q | 29334 |  |  | 62734
(L) | `vexK…Z | 29318.52 |  |  | 62727.55
(M) | cÖvwß | 29315.03 |  |  | 62719.7
|  |  | 119 | -2

## PR(P-3&4)
| 10 | cÖavb cÖavb As‡Mi j¶¨gvÎv I AMÖMwZ t
(j¶ UvKvq)
As‡Mi bvg |  |  | wWwcwc Abymv‡i j¶¨gvÎv |  |  | I‡q‡UU ev¯Íe | c~e©eZx© erm‡ii Ryb/2017 ch©šÍ µgc~wÄZ AMÖMwZ |  |  |  | PjwZ erm‡ii ms‡kvwaZ j¶¨gvÎv (cwigvY I wcwci %) |  |  |  |  | cÖwZ‡e`b Kvj ch©šÍ AMÖMwZ (cwigvY I j¶¨gvÎvi %) |  |  |  | cÖKí cwiPvjK/Kg©KZ©v KZ…©K cÖKí GjvKv cwi`k©‡bi ZvwiL | gšÍe¨
[22 empty] | µgcywÄZ | wWwcwc ‡iU | PjwZ †iU
|  |  | ev¯Íe |  | Avw_©K |  | ev¯Íe |  | I‡q‡UU ev¯Íe | Avw_©K | ev¯Íe |  | I‡q‡UU ev¯Íe | Avw_©K | I‡q‡UU Avw_©K jÿgvÎv | ev¯Íe |  | I‡q‡UU ev¯Íe | Avw_©K
1 |  |  | 2 |  | 3 |  | 4 |  |  | 5 | 6 |  |  | 7 |  | 8 |  |  | 9 | 10 | 11
1 | Kg©KZ©v‡`i †eZb |  | 2376 | Rbgvm | 748.85 |  | 251 | Rbgvm |  | 89.3753 | 120 | Rbgvm |  | 48 |  | 120 | Rbgvm |  | 47.44 | wcwW PÆMÖvg: 06/06/18 n‡Z 07/06/18 ch©šÍ Kzwgjøv : 13/06/18 n‡Z 14/06/18 ch©šÍ iscyi: 23/06/18 n‡Z 24/06/18 ch©šÍ wWwcwW-1 MvRxcyi: 03/06/18 n‡Z 04/06/18 ch©šÍ bvivqYMÄ: 20/06/18 n‡Z 21/06/18 ch©šÍ iscyi: 25/06/18 n‡Z 26/06/18 ch©šÍ wWwcwW-2 iscyi: 06/006/18 n‡Z 08/06/18 ch©šÍ PUªªMÖvg: 11/06/18 n‡Z 13/06/18 ch©šÍ PUªªMÖvg: 24/06/18 n‡Z 25/06/18 ch©šÍ Kzwgjøv: 26/06/2018 |  | 136.8153
[6 empty] | 0.0025445 | 10.56% |  | 0.02688% | 11.94% | 5.051% |  | 0.01285% | 6.41% | 0.1173% | 100% |  | 0.1173% | 98.83%
2 | Kg©Pvix‡`i †eZb |  | 1368 | Rbgvm | 250.48 |  | 104 | Rbgvm |  | 17.701 | 36 | Rbgvm |  | 13.22 |  | 36 | Rbgvm |  | 13.22 |  |  | 30.921
[6 empty] | 0.0008511 | 7.602% |  | 0.00647% | 7.067% | 2.632% |  | 0.00224% | 5.278% | 0.0323% | 100% |  | 0.0323% | 100%
3 | fvZvw` |  | 3744 | Rbgvm | 1238.13 |  | 355 | Rbgvm |  | 85.0301 | 156 | Rbgvm |  | 51.09 |  | 156 | Rbgvm |  | 48.01 |  |  | 133.0401
[6 empty] | 0.004207 | 6.868% |  | 0.02889% | 6.868% | 4.126% |  | 0.01736% | 4.126% | 0.1248% | 100% |  | 0.1248% | 93.97%
4 | mieivn I †mev |  | 0 | ‡_vK | 38218.07 |  | 0 | ‡_vK |  | 10183.9723 | 0 | ‡_vK |  | 4425.69 |  | 0 | ‡_vK |  | 4424.909 |  |  | 14608.8813
[6 empty] | 0.12986 | 26.65% |  | 3.46% | 26.65% | 11.58% |  | 1.504% | 11.58% | 10.81% | 99.98% |  | 10.81% | 99.98%
5 | ‡givgZ msiÿY I cybe©vmb |  | 0 | ‡_vK | 424 |  | 0 | ‡_vK |  | 23.9789 | 0 | ‡_vK |  | 33 |  | 0 | ‡_vK |  | 32.94 |  |  | 56.9189
[6 empty] | 0.0014407 | 5.655% |  | 0.008148% | 5.655% | 7.783% |  | 0.01121% | 7.783% | 0.08062% | 99.82% |  | 0.08047% | 99.82% |  |  | 4566.519
6 | ‡_vK eivÏ |  | 0 | ‡_vK | 40 |  | 0 | ‡_vK |  | 0.5 | 0 | ‡_vK |  | 1e-65 |  | 0 | ‡_vK |  | 0 |  |  | 0.5
[6 empty] | 0.00013592 | 1.25% |  | 0.0001699% | 1.25% | 2.5e-65% |  | 3.398e-69% | 2.5e-65% | 2.443e-68% | 0% |  | 0% | 0%
7 | m¤ú` msMÖn/µq |  | 0 | ‡_vK | 6064.74 |  | 0 | ‡_vK |  | 1805.3298 | 0 | ‡_vK |  | 1455 |  | 0 | ‡_vK |  | 1455 |  |  | 3260.3298
[6 empty] | 0.020607 | 29.77% |  | 0.6134% | 29.77% | 23.99% |  | 0.4944% | 23.99% | 3.555% | 100% |  | 3.555% | 100%
8 | f‚wg AwaMÖnY / µq |  | 0 | ‡_vK | 1374.01 |  | 0 | ‡_vK |  | 0 | 1e-44 | ‡_vK |  | 1e-31 |  | 0 | ‡_vK |  | 0 |  |  | 0
[6 empty] | 0.0046687 | 0% |  | 0% | 0% | 7.278e-33% |  | 3.398e-35% | 7.278e-33% | 2.443e-34% | 0% |  | 0% | 0%
9 wbg©vY I c~Z© | K) Awdm feb(¯‹zj Kvg mvB‡K¬vb †mëvi) |  | 8 | wU | 11445.47 |  | 0 | wU |  | 0 | 3 | wU |  | 3635.21 |  | 3 | wU |  | 3635.21 |  |  | 3635.21 | 1430.6837 | 1211.7367
[6 empty] | 0.03889 | 0% |  | 0% | 0% | 37.5% |  | 1.458% | 31.76% | 8.881% | 100% |  | 8.881% | 100%
| L) Awdm feb(KwgDwbwU wi‡mvm© †m›Uvi) |  | 10 | wU | 1027.93 |  | 0 | wU |  | 0 | 0 | wU |  | 1e-32 |  | 0 | wU |  | 0 |  |  | 0
[6 empty] | 0.0034928 | 0% |  | 0% | 0% | 0% |  | 0% | 9.728e-34% | 2.443e-35% | 0% |  | 0% | 0%
| M) moK I gnvmoK |  | 589 | wKtwgt | 82666.47 |  | 128.5 | wKtwgt |  | 17476.47 | 98 | wKtwgt |  | 13726.79 |  | 98 | wKtwgt |  | 13726.791 |  |  | 31203.261 | 140.3505 | 140.0693
[6 empty] | 0.28089 | 21.82% |  | 6.128% | 21.14% | 16.64% |  | 4.674% | 16.61% | 33.54% | 100% |  | 33.54% | 100%
| N) †mZz |  | 706 | wgt | 26046.7 |  | 152 | wgt |  | 1923.29 | 168 | wgt |  | 6186.93 |  | 168 | wgt |  | 6186.93 |  |  | 8110.22 | 36.8933 | 167.6977
[6 empty] | 0.088504 | 21.53% |  | 1.905% | 7.384% | 23.8% |  | 2.106% | 23.75% | 15.12% | 100% |  | 15.12% | 100%
| O) cvwb wb®‹vkb AeKvVv‡gv |  | 99 | wKtwgt | 51886.03 |  | 26 | wKtwgt |  | 13254.41 | 19 | wKtwgt |  | 9924.96 |  | 19 | wKtwgt |  | 9924.96 |  |  | 23179.37 | 524.1013 | 18.9371
[6 empty] | 0.1763 | 26.26% |  | 4.63% | 25.55% | 19.19% |  | 3.384% | 19.13% | 24.25% | 100% |  | 24.25% | 100%
| P) ¯^v¯’¨ cwiPh©v I cvwb mieivn |  | 237 | wKtwgt | 11774.3 |  | 0 | wKtwgt |  | 0 | 0 | wKtwgt |  | 1e-30 |  | 0 | wKtwgt |  | 0 |  |  | 0
[6 empty] | 0.040008 | 0% |  | 0% | 0% | 0% |  | 0% | 8.493e-33% | 2.443e-33% | 0% |  | 0% | 0%
| Q) bjK‚c ¯’vcb |  | 57 | wU | 1653.63 |  | 0 | wU |  | 0 | 0 | wU |  | 1e-37 |  | 0 | wU |  | 0 |  |  | 0
[6 empty] | 0.0056189 | 0% |  | 0% | 0% | 0% |  | 0% | 6.047e-39% | 2.443e-40% | 0% |  | 0% | 0%
| R) ˆe`¨wZK ¯’vcbv |  | 11170 | wgt | 9735.2 |  | 3257 | wgt |  | 2832.48 | 754 | wgt |  | 657.11 |  | 754 | wgt |  | 657.11 |  |  | 3489.59 | 0.87155 | 753.9566
[6 empty] | 0.033079 | 29.16% |  | 0.9645% | 29.1% | 6.75% |  | 0.2233% | 6.75% | 1.605% | 100% |  | 1.605% | 100%
| S) `wi`ª‡`i Rb¨ Ab¨vb¨ †cŠi †mev |  | 0 | †_vK | 1675.98 |  | 0 | †_vK |  | 250 | 0 | †_vK |  | 325 |  | 0 | †_vK |  | 325 |  |  | 575
[6 empty] | 0.0056948 | 14.92% |  | 0.08495% | 14.92% | 19.39% |  | 0.1104% | 19.39% | 0.794% | 100% |  | 0.794% | 100%
10 | FY I AwMÖg |  | 0 | ‡_vK | 500 |  | 0 | ‡_vK |  | 250 | 0 | ‡_vK |  | 100 |  | 0 | ‡_vK |  | 100 |  |  | 350
[6 empty] | 0.0016989 | 50% |  | 0.08495% | 50% | 20% |  | 0.03398% | 20% | 0.2443% | 100% |  | 0.2443% | 100%
11 | K) Avg`vbx ïé I wmwW/f¨vU |  | 0 | ‡_vK | 1520 |  | 0 | ‡_vK |  | 16.77 | 0 | ‡_vK |  | 350 |  | 0 | ‡_vK |  | 350 |  |  | 366.77
[6 empty] | 0.0051648 | 1.103% |  | 0.005698% | 1.103% | 23.03% |  | 0.1189% | 23.03% | 0.8551% | 100% |  | 0.8551% | 100%
| L) wewea g~jab e¨q |  | 0 | ‡_vK | 100 |  | 0 | ‡_vK |  | 0 | 0 | ‡_vK |  | 1e-43 |  | 0 | ‡_vK |  | 0 |  |  | 0
[6 empty] | 0.00033979 | 0% |  | 0% | 0% | 1e-43% |  | 3.398e-47% | 1e-43% | 2.443e-46% | 0% |  | 0% | 0%
12 | K) cÖvBR Kw›Ub‡RwÝ |  | 0 | ‡_vK | 24590 |  | 0 | h gg |  | 0 | 0 | ‡_vK |  | 1e-40 |  | 0 | ‡_vK |  | 0 |  |  | 0
[6 empty] | 0.083554 | 0% |  | 0% | 0% | 4.067e-43% |  | 3.398e-44% | 4.067e-43% | 2.443e-43% | 0% |  | 0% | 0%
| L) wdwRK¨vj Kw›Ub‡RwÝ |  | 0 | ‡_vK | 21320 |  | 0 | ‡_vK |  | 0 | 0 | ‡_vK |  | 1e-53 |  | 0 | ‡_vK |  | 0 |  |  | 0 |  | 17782.389
[6 empty] | 0.072443 | 0% |  | 0% | 0% | 4.69e-56% |  | 3.398e-57% | 4.69e-56% | 2.443e-56% | 0% |  | 0% | 0% |  |  | 36361.001 |  | 23145.131
‡gvU = |  |  | ` |  | 294299.99 |  |  |  |  | 48209.3074 |  |  |  | 40932 |  |  |  |  | 40927.52 |  |  | 89136.8274 | 2014-15
[7 empty] | 17.95% |  |  | 16.38% | 16% |  |  | 13.91% |  | 100% |  |  | 99.99% |  |  |  | Rev.= | 88.9
[23 empty] | Capital= | 210.99
| ** | cÖKí ïiæ ‡_‡K G ch©šÍ µgc~wÄZ ‡fŠZ AMÖMwZ |  | t | 33% | [13 empty] | 99.99% |  |  |  | Total= | 299.89
| ** | cÖKí ïiæ ‡_‡K G ch©šÍ µgc~wÄZ Avw_©K AMÖMwZ |  | t | 31% | [8 empty] | 0 |  |  |  |  | 4.48
30.29%
[8 empty] | 119 |  | -4
(ms‡kvwaZ)
Note on G57: Eaar Uddin: data
Note on P55: Eaar Uddin: data
Note on U13: Eaar Uddin: Tk. 24.88897 of Training and bme less exp amount which was disbursed to CW is has been added , as of instruction of PD si sir. 24-06-2018
Note on U27: Eaar Uddin: Tk. 24.88897 of Training and bme less exp amount which was disbursed to CW is has been minused, as of instruction of PD si sir. 24-06-2018
Note on U54: Eaar Uddin: data
Note on U55: Eaar Uddin: data

## PR(P-5)
µq msµvšÍ Z_¨vejx t 2017-18 A_© eQ‡ii AMÖMwZ (Ryb /2018Bs)
gš¿Yvjq/wefvM t ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq/ ¯’vbxq miKvi wefvM¦
(j¶ UvKvq)
µt bs | cÖK‡íi bvg | gvjvgvj |  |  |  |  | c~Z© |  |  |  |  | ‡mev |  |  |  |  | K) wmwW f¨vUmn µqLv‡Z †gvU eivÏ (2017-18) L) wmwW f¨vU |  | K) wmwW f¨vUmn µqLv‡Z †gvU e¨q L) wmwW f¨vU |  | µqLv‡Z Ae¨wqZ eivÏ (18-19) | †gvU GwWwc eivÏ | µqLv‡Z eivÏ †gvU GwWwc eiv‡Ïi %
|  | MZ A_©eQ‡i ev c~‡e© cÖ`vbK…Z |  | Ryb /2018 mgqKv‡j cÖ`vbK…Z |  | Ryb/18 n‡Z Ryb/18 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_©eQ‡i ev c~‡e© cÖ`vbK…Z |  | Ryb /2018 mgqKv‡j cÖ`vbK…Z |  | Ryb/18 n‡Z Ryb/18 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_©eQ‡i ev c~‡e© cÖ`vbK…Z |  | Ryb /2018 mgqKv‡j cÖ`vbK…Z |  | Ryb/18 n‡Z Ryb/18 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v
|  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2016-17 A_©eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2016-17 A_©eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2016-17 A_©eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 |  | 20 | 21 | 22
| ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦ | 29 | 1805.3298 | 0 | 0 | 0 | 88 | 35736.65 | 0 | 0 | 0 | 12 | 10183.9723 | 0 | 0 | 0 | (K) | 40819.69 | (K) | 40818.85 | 0.84 | 40932 | 99.73%
[17 empty] | (L) | 350 | (L) | 350 | 0
[10 empty] | 119 | -5

## PR(P-6)
SCHEME STATUS REPORT
Project Title: “City Governance Project”.
Reporting Month :June/2018
(Taka in lakh)
Sl.No. | Name of project (Name of Development Assistance \Partner) | ADP Fund (GOB+RPA) |  |  | No. of Schemes/Contracts |  |  | Work-Plan Target |  | ACHIEVEMENT | [5 empty] | Physical Progress | Total fund Spent (GOB+PA) |  |  | Remarks
[5 empty] | New Schemes/Contracts | Carried over Contracts/ Excess of Previous year | Total | Last Date for awarding | Last Date for works Commen-cement | Schemes prepared | Schemes preparation under | Tender Called | Tender Evaluation Under | Works going on | Schemes Completed
[5 empty] | (No.) | (No.) | (No.) |  |  | (No.) | (No.) | (No.) | (No.) | (No.) | (No.) | (%)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 17
1 | “City Governance Project” (JICA) | 294300 |  |  | 23 | 88 | 111 | 15-03-2018 | 25-03-2018 | 0 | 0 | 0 | 0 | 64 | 47 | 100% | 40927.52
|  | 54531 | + | 227262 | 16: 7751.51 | + | 33176
[9 empty] | 119 | -6

## PR(P-7)
2017-18 A_©eQ‡ii evwl©K Dbœqb Kg©m~wP‡Z eivÏ
cÖKí Iqvix gvwmK AMÖMwZ cÖwZ‡e`b
(K) gš¿Yvjq / wefvM t ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿bvjq/ ¯’vbxq miKvi wefvM¦
(L) ms¯’vi bvg t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
(M) cÖwZ‡e`b Kvj (gvm) t Ryb/2018Bs¦
(j¶ UvKvq)
µt bst | †KvW I cÖK‡íi bvg (cÖKí e¨q) (ev¯Zevqb Kvj) (ms‡kvwaZ) | Aby‡gv`b ch©vq | GwWwcÕi c„ôv I µwgK bs | 2017-18 A_©eQ‡ii ms‡kvab evwl©K Dbœqb Kg©m~wP‡Z ms‡kvwaZ eivÏ |  |  |  |  | Aegyw³ |  |  |  |  | e¨q |  |  |  |  | cÖKí mvnv‡h¨i UvKvsk |  | AMÖMwZ (%) |  |  |  | cÖK‡íi mvnv‡h¨i Drm | gšÍe¨
|  |  |  | †gvU | UvKv (wmwW f¨vU) |  | cÖKí mvnvh¨ |  | †gvU |  |  | cÖKí mvnvh¨ |  | †gvU |  |  | cÖKí mvnvh¨ |  |  |  | †fŠZ |  | Avw_©K
[7 empty] | †gvU | UvKvsk |  | UvKv (wmwW f¨vU) |  | †gvU | UvKvsk |  | UvKv (wmwW f¨vU) |  | †gvU | UvKvsk | `vexK…Z | cÖvwß | j¶gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK) | j¶gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK)
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| 5118 ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí (2014-15 nB‡Z 2019-20) | Aby‡gvw`Z |  | 40932 | 7756 | 350 | 33176 | 29334 | 40932 | 7756 | 350 | 33176 | 29334 | 40927.52 | 40927.52 | 350 | 33176 | 29334 | 29318.52 | 29315.03 | 25% | 100% | 25% | 99.99% | RvBKv
119 | bar: 15

## 23 Colm Report (P-8)
2017-18 A_© eQ‡i ¯’vbxq miKvi wefv‡Mi AvIZvq AviGwWwcf~³ ev¯Íevqbvaxb cÖKímg~‡ni AMÖMwZi ch©v‡jvPbv QK - 1
gv‡mi bvg t Ryb /2018Bs
ms¯’v t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦ | [22 empty] | (j¶ UvKvq)
µt bs | cÖK‡íi bvg (†gqv`Kvj) (ms‡kvwaZ) | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q | Ryb/2017 ch©šÍ µgc~wÄZ e¨q | Aby‡gvw`Z wWwcwc/ AviwWwcwcÕi Procurement Plan Abyhvqx c¨v‡KR msL¨v/cÖv°wjZ e¨q | Ryb/2017 ch©šÍ µgc~wÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | 2016-17 A_©erm‡i evwl©K Dbœqb Kg©m~Px | [11 empty] | K) µgcywÄZ c~bf©ib e¨q L) †gvU cybf©iY e¨q (17-18 GwWwc) M) †gvU cybf©iY `vex †ck (17-18 GwWwc) N) †gvU c~bf©iY cÖvwß (17-18 GwWwc) |  | cÖK‡íi ïiæ n‡Z ch©v‡jvPbaxb gvm ch©šÍ µgcywÄZ Avw_©K e¨q/AMÖMwZ | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ ‡fŠZ AMÖMwZ | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q Abyhvqx AeivÏK…Z UvKv | Ryb,2017 n‡Z cÖK‡íi Aewkó †gqv`Kvj | cÖKí mvnv‡h¨i Drm
[6 empty] | 2017-18 GwWwc eivÏ | 2017-18 AviGwWwc eivÏ | Kg© cwiKíbv |  |  |  |  | msMÖn cwiKíbv |  |  |  | ch©v‡jvPbvaxb gv‡m Kvh©v‡`k cÖ`vb Avw_©K I ˆfvZ j¶¨gvÎv ARx©Z bv nIqvi KviY
[8 empty] | ch©v‡jvPbvaxb gvm ch©šÍ A_© Aegyw³ | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨‡qi j¶¨gvÎv | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨q / AMÖMwZ | ch©v‡jvPbvaxb gvm ch©šÍ ‡fŠZ j¶¨gvÎv I AMÖMwZ |  | evwl©K msMÖn cwiKíbv Abyhvqx c¨v‡KR msL¨v/e¨vq | ch©v‡jvPbvaxb gvm ch©šÍ ‡UÛvi Avnev‡bi j¶¨gvÎv Abymv‡i c¨v‡KR msL¨v/e¨q | ch©v‡jvPbvaxb gvm ch©šÍ ‡UÛvi AvnevbK…Z c¨v‡KR msL¨v/e¨q | ch©v‡jvPbvaxb gvm ch©šÍ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | [8 empty] | y
|  | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | j¶gvÎv (%) | AMÖMwZ (%) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) |  |  |  | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | (%) | (‡gvU) (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | eQi / gvm
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22 | 23
88 | ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦ (RyjvB/2014 Bs n‡Z Ryb/2020 Bs) | 294300 | 48209.31 | 213 | 129 | 31532 | 40932 | 40932 | 40932 | 40927.52 | 100% | 100% | 44 | 44 | 44 | 41 | - | K) | 62734 | 89136.82 | 33% | 205158.69 | 3eQi | RvBKv
|  | 54531 | 6459.31 | 292032.53 | 47725.9521 | 2770 | 7756 | 100% | 100% | 99.99% |  |  | 27148 | 37379.791 | 37379.791 | 6559 |  |  |  | 31% |  | 40315.69
|  | 239769 | 41750 |  |  | 28762 | 33176 | [10 empty] | L) | 29318.52 |  |  | 164843
|  | 227262 | 33400 | 67 | 29 | 25280 | 29334 | 7756 | 7756 | 7751.51 |  |  | 21 | 21 | 21 | 21 |  |  |  | 14210.82 |  | 164528
|  |  |  | 7605.59 | 1805.3298 |  |  | 100% | 100% | 99.94% |  |  | 1823 | 1287 | 1287 | 1287 |  | M) | 29318.52 | 26.06%
|  |  |  | 134 | 88 |  |  | 33176 | 33176 | 33176 |  |  | 23 | 23 | 23 | 20 |  | N) | 29315.03 | 74926
|  |  |  | 197911.11 | 35736.65 |  |  | 100% | 100% | 100% |  |  | 25325 | 30820.791 | 30820.791 | 0 |  |  |  | 31.25%
|  |  |  | 12 | 12 |  |  | 29334 | 29334 | 29334 |  |  | 0 | 0 | [5 empty] | 62734
|  |  |  | 86515.83 | 10183.9723 |  |  | 100% | 100% | 100% |  |  | 0 | 5272 | 5272 | 5272 |  |  |  | 27.6%
[9 empty] | 119 | -8
|  |  | 2008-09 | 45
|  |  | 2009-10 | 111
|  |  | Total = | 156 | 47725.9521 | [8 empty] | #VALUE!
[15 empty] | 0 | 0
#VALUE!
[5 empty] | 3100 | [9 empty] | 1075.25
c~b
70
47795.9521
[5 empty] | 16 | 339
[5 empty] | 260 | 5941
[5 empty] | 342 | 6041
[5 empty] | 195 | 3385.5
[5 empty] | 813 | 15706.5

## PIB(1)
wc, AvB, we 01/76 (ms‡kvwaZ)
ÓcÖwZ‡e`b QKÓ
cÖ_g LÛ t mvavib Z_¨vejx I Avw_©K weeibx¦
1¦ | mvaviY Z_¨vejx
| K) cÖwZ‡e`b Kvj | t | Ryb /2018Bs
| L) cÖKí wk‡ivbvg | t | ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦
| M) cÖKí Ae¯’vb | t | 5wU wmwU K‡c©v‡ikb h_vt- bvivqYMÄ, MvRxcyi, Kzwgjøøv, PÆMÖvg I iscyi¦
| N) PjwZ evwl©K Dbœqb Kg©m~Px‡Z | t | AšÍf©~³
| O) wbe©vnx ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
| P) gš¿Yvjq | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq/¯’vbxq miKvi wefvM
| Q) Aby‡gv`b w¯’wZ | t | cÖ‡hvR¨ †Lv‡c (√) wPý w`b
|  |  | Aby‡gvw`Z | √ | Abby‡gvw`Z | ms‡kvwaZ AbAbygvw`Z
| R) Aby‡gv`‡bi ZvwiL | t | A) g~j t 15/07/2014Bs Zvwi‡Li GK‡bK mfvq Aby‡gvw`Z¦ |  |  | Av) ms‡kvwaZ t cÖ‡hvR¨ b‡n¦
| S) ev¯Íevqb Avi‡¤¢i ZvwiL | t | RyjvB/ 2014
| T) mgvwßi ZvwiL | t | Ryb / 2020
| U) cÖKí e¨q (j¶ UvKvq) | t | A) g~j t 294300.00 j¶ UvKv |  | Av) ms‡kvwaZ t cÖ‡hvR¨ b‡n¦
|  |  |  | 119 | -9

## PIB(2)
2¦ Avw_©K weeibx eivÏ Aegyw³, Avq/e¨q (j¶ UvKvq)
K) | eivÏ t
µwgK bs | weeiYx | ‡gvU | UvKv | g~jab | ivR¯^ | ‰e‡`wkK gy`ªv
[6 empty] | ‡gvU | cÖKí mvnvh¨ |  | Ab¨vb¨ | e¨e¯’vK…Z
[7 empty] | ‡gvU | UvKvsk |  | cÖKí mvnvh¨ | Ab¨vb¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A) | PjwZ Avw_©K erm‡ii AviGwWwc eivÏ | 40932 | 7756 | 36361 | 4571 | 33176 | 33176 | 29334 | - | - | - | 48209.31
Av) | PjwZ Avw_©K ermi ch©šÍ µgcywÄZ eivÏ | 89141.31 | 14215.31 | 74170 | 14971.5576 | 74926 | 74926 | 62734 | - | - | -
(L) | Aegyw³ t
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A) | eZ©gvb Avw_©K eQ‡i cÖwZ‡e`b Kvj ch©šÍ cÖkvmwbK gš¿Yvjq KZ©„K Aegyw³ | 40932 | 7756 | 30109.6 | 10822.4 | 33176 | 33176 | 29334 | - | - | -
Av) | c~e©eZ©x A_© eQ‡i Aegyw³ †_‡K D×„Z | - | - | - | - | - | - | - | - | - | -
B) | eZ©gvb Avw_©K eQ‡i cÖwZ‡e`b Kvj ch©šÍ †gvU jf¨ A‡_©i cwigvb (A+Av) | 40932 | 7756 | 30109.6 | 10822.4 | 33176 | 33176 | 29334 | 0 | 0 | 0
C) | cÖwZ‡e`b Kvj ch©šÍ cÖkvmwbK gš¿Yvjq KZ©„K µgcywÄZ Aegyw³ | 89141.31 | 14215.31 | 64155.531 | 24985.779 | 74926 | 74926 | 62734 | 0 | 0 | 0
|  |  |  | 119 | -10
Note on E11: Eaar Uddin: There is some problem for formula, how is this formul can used. Since sayedul shaheb use and kept it. So I kept it . 27-05-2018
Note on F11: Eaar Uddin: There is some problem for formula, how is this formul can used. Since sayedul shaheb use and kept it. So I kept it . 27-05-2018

## PIB(3)
M) | e¨q t
µwgK bs | weeiY | ‡gvU | UvKv | g~jab | ivR¯^ | ‰e‡`wkK gy`ªv
[6 empty] | ‡gvU | cÖKí mvnvh¨ |  | Ab¨vb¨ | e¨e¯’vK…Z
[7 empty] | ‡gvU | UvKvsk |  | cÖKí mvnvh¨ | Ab¨vb¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A) | cÖwZ‡e`b Kvjxb e¨q
| 1¦ AvmevecÎ I hš¿cvwZ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | -
| 2¦ `vjvb I BgviZ (c~Z©KvR) | 33176 | 0 | 33176 | 0 | 33176 | 33176 | 29334 | - | - | - | 51.69
| 3¦ ms¯’vcb | 141.61 | 141.61 | 0 | 141.61 | 0 | 0 | 0 | - | - | - | 2039.24
| 4¦ Rixc I AbymÜvb | 0 | 0 | 0 |  | 0 | 0 | 0 | - | - | -
| 5¦ Ab¨vb¨ (mieivn †mev/ KbmvjU¨v›U) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 509.54
| 6¦ m`i Dcwi e¨q | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | -
| 7¦ ‡gvU (1 †_‡K 6) | 33317.61 | 141.61 | 33176 | 141.61 | 33176 | 33176 | 29334 | - | - | - | 3842
Av) | eZ©gvb Avw_©K eQ‡i †gvU e¨q | 33317.61 | 141.61 | 33176 | 141.61 | 33176 | 33176 | 29334 | - | - | - | 31228.57
B) | cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q | 89136.82 | 14215.31 | 88906.31 | 230.51 | 74926 | 74926 | 62734 | - | - | - | 9293.41
C) | AsMxKviK…Z e¨q (hv cÖwZ‡e`b Kvj ch©šÍ cwi‡kva Kiv nqwb) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 509.54
N) | Avq (†h mKj cÖK‡íi †Kvb Avq †bB †m mKj cÖK‡íi †¶‡Î GB Aby‡gv`‡bi wecix‡Z Òïb¨Ó wj‡L c~iY Kwi‡Z nB‡e)
A) | cÖwZ‡e`b Kv‡j cÖKí †_‡K Avq t | k~b¨
Av) | eZ©gvb Avw_©K eQ‡i cÖwZ‡e`b Kvj ch©šÍ †gvU Avq t | k~b¨
B) | cÖwZ‡e`b Kvj ch©šÍ cÖK‡íi µgcywÄZ Avq t | k~b¨
cÖKí cwiPvjK/e¨e¯’vcK Gi ¯^v¶i
bvg
c`ex
2¦ | cÖkvmwbK gš¿Yvj‡qi gšÍe¨ t
Avcwb wK 2 (L) Aby‡”Q‡` I cÖ`Ë A_© Aegyw³ msµvšÍ Z_¨vejxi mv‡_ GKgZ (cÖ‡hvR¨ †Lv‡c wPý w`b) nu¨v/bv¦
( n¨vu ) cÖ‡qvRb‡ev‡a mg AvKv‡ii AwZwi³ KvMR e¨envi Kiæb¦
gš¿bvjq cwiKíbv /ev¯Íevqb †Kvm©
cÖav‡bi ¯^v¶i
bvg
|  |  |  | 119 | -11 |  | c`ex

## Aid & Dis.
Information of Project Aid & Disbursement Status
For the Year 2017-2018
| Administrative Ministry | Name of the Ministry / Division : LGRD & Co-operatives / LGD.
| Reporting Agency | Local Government Engineering Department (LGED) | [10 empty] | (Tk. In Lac)
| Reporting Period: | 2018-06-01 | [10 empty] | (Others in million)
Sl No. | Name of the Project | Project Aid | [13 empty] | Remarks
|  | As per DPP |  |  | As per Agreement |  |  | Disbursed Amount
[8 empty] | In Original Currency |  |  |  | In US$ |  | In Tk.
|  | In Original Currency | In US$ | In Tk. | In Original Currency | In US$ | In Tk. | Up to June/18 |  | Current Years |  | Up to June/18 | Current Years | Up to June/18 | Current Years
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 |  | 11 | 12 | 13 | 14 | 15
80 | City Governance Project(CGP) | ¥ 30690.432 | 308.1864 | 239769 | ¥ 30690 | 308.1864 | 239769 | ¥ | 13086.51 | ¥ | 4362.92 | 117.89 | 41.85 | 93174.12 | 33684.15
** | 1 BDT = 1.28 ¥
*** | 1 US$ = 77.8 BDT
[6 empty] | 119 | -12

## Monthly Dis.
MONTHLY DISBURSEMENT OF FOREIGN AID (FY 2017-2018)
Proforma No-1
Administrative Ministry |  | : | Name of the Ministry / Division : LGRD & Co-operatives / LGD. |  |  |  | Prepared by Project Director
Reporting Agency |  | : | Local Government Engineering Department (LGED) |  |  |  | City Governance Project(CGP)
Reporting Period |  | : | 2018-06-01 |  |  |  | Telephone No : 9131340
( Figures in Million ¥ )
Name of the Project | Name of Donor | Loan or Grant | Loan or Grant No. Date of agreement | Amount of allocation | Opening pipeline as on 1-7-2017 (Allocation minus disbursement up to 30-06-2017) | Fresh commitment allocation during the reporting period | Total available period | Amount disbursed during the reporting period | Closing pipeline
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 (6+7) | 9 | 10 (8-9)
City Governance Project(CGP) | JICA | LOAN | Loan no-JICA Loan Agrement BD-P79 16.06.2014 | 30690 | 21966.41 | 0 | 21966.41 | 4362.92 | 17603.49
-4.53
[5 empty] | 119 | -13

## RPA
¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq
cÖKí mvnvh¨ cybf©i‡Yi gvwmK cÖwZ‡e`b
A_© eQi-2017-18
AviwcG Gi cybf©i‡bi AMÖMwZ cÖwZ‡e`b weeiYx t
gš¿Yvjq/wefv‡Mi bvg |  | t ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq
cÖwZ‡e`b Kvj |  | Ryb /2018Bs
ev¯ÍevqbKvix KZ©„c‡¶i bvg |  | t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦
j¶ UvKvq
cÖK‡íi bvg I `vZv ms¯’vi bvg (ev¯Íevqb Kvj) | cÖK‡íi ïiæi ermi †_‡K eZ©gvb A_© ermi ch©šÍ †gvU AviwcG eiv‡Ïi cwigvb | cÖK‡íi ïiy †_‡K PjwZ gvmch©šÍ AviwcG Lv‡Z cÖK…Z e¨q | PjwZ gvm ch©šÍ cybf©i‡Yi `vex †c‡ki cwigvY | `vexi wecix‡Z cybf©i‡bi cwigvb | `vexi †c‡ki A‡c¶vq Av‡Q Gi cwigvb (3-4) | `vexi A‡_©i g‡a¨ cybf©i‡bi A‡c¶vq Av‡Q Gi cwigvb (4-5) | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦ (RyjvB/2014 Bs n‡Z Ryb/2020 Bs) | 62734 | 62734 | 62727.55 | 62719.7 | 6.45 | 7.85
|  | 119 | -14

## IMED. M(P-1)
Progress Report of Ongoing Development Project Operational Plan
(Format 05)
(All financial figures in lakh Tk).
Reporting Period : |  | 2018-06-01
Part-A : Monthly Report.
Name of the Ministry/Division/Organization t |  |  |  | t | Ministry of Local Government Rural Development & Co-operatives (LGRD & C) / Local Government Division (LGD) / Local Government Engineering Department (LGED)
1 | Name of the Project/Operational Plan |  |  | t | “City Governance Project”.
2 | Objectives of the Project/Operational Plan (in Brief) |  |  | t | i) | To improve the public services in the target five (5) City Corporations (CC).
[5 empty] | ii) | To strengthen the city governments’ administrative capacity and their governance improvement through ICGIAP.
[5 empty] | iii) | To promote living environment and quality of life through IDPCC.
[5 empty] | iv) | To create economic opportunities for CC’s to ensure the progressive revenue and economic growth by providing infrastructures in different sectors in the target City Corporations.
3 | Location of the Project/Operational Plan |  |  | t | The Project area covers 5 City Corporations namely Nayangonj, Comilla, Cittagong, Gazipur & Rangpur City Corporation.
4 | Project Approval Status & Cost
| DPP/TPP | Date of Approval | Implementation period |  |  | Total Cost | GOB | Project Aid (RPA)
| 1 | 2 | 3 |  |  | 4 | 5 | 6
| 1. Original | 16-07-2014 | July/14 - June/20 |  |  | 294300 | 54531 | 239769
227262
2. Revised
5 | Progress of Fund Release
| Quarter-wise | Proposal Sending to Ministry/Division | Issue of order by Ministry |  |  | Issue of order from Finance Division | Amount Released | Date of issue of Chaque from CAO (in case of Autonomous body)
| 1 | 2 | 3 |  |  | 4 | 5 | 6
| 1st quarter | 2017-11-07 | 27-07-2017 |  |  | 13-08-2017 | 33753.25 | -
| 2nd quarter | 2017-02-11 | 13-11-2017 |  |  |  | 622.58
| 3rd quarter | 2018-08-01 | 2018-06-02 |  |  |  | 844.34 | -
| 4th quarter | 2018-04-02 | 2018-05-27 |  |  | 2018-05-06 | 5711.83 | -
| Total= | [5 empty] | 40932
|  | 119 | -15

## IMED M(P-2)
6. Target and Achievement of the main Components of the Project :
Name of Important Components (With quantity) | Cost as per DPP/TPP | Achievement up to last June |  | Target of current year |  | Progress up to the reporting month of current year |  | Unspent/unfinished balance against PP targets
|  | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical
|  | a) Total b) Taka | (% of the component) | a) Total b) Taka | (% of the component) | a) Total b) Taka | (% of the component) | a) Total b) Taka 2-(3+7) | (% of the component)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Revenue
1) Pay & Allowances
a) Pay of Officers | 748.85 | 89.3753 | 11.94% | 48 | 6.41% | 47.44 | 100% | 612.0347 | 81.73%
b) Pay of Establishment | 250.48 | 17.701 | 7.067% | 13.22 | 5.278% | 13.22 | 100% | 219.559 | 87.66%
c) Allowances | 1238.13 | 85.0301 | 6.868% | 51.09 | 4.126% | 48.01 | 100% | 1105.0899 | 89.25%
Sub-Total= (1a-c) | 2237.46 | 192.1064 |  | 112.31 |  | 108.67 |  | 1936.6836
2) Supply & Services
a) Supply (Stationary & others) | 38218.07 | 10183.9723 | 26.65% | 4425.69 | 11.58% | 4424.909 | 99.98% | 23609.1888 | 61.77%
Sub total(2a) | 38218.07 | 10183.9723 |  | 4425.69 |  | 4424.909 |  | 23609.1888
3) Repair, Maintenance & Rehabilitation
a) Vehicles & Equipment | 424 | 23.9789 | 5.655% | 33 | 7.783% | 32.94 | 99.82% | 367.0811 | 86.58%
Sub total(3a) | 424 | 23.9789 |  | 33 |  | 32.94 |  | 367.0811
4) Block Allocation | 40 | 0.5 | 1.25% | 1e-65 | 2.5e-65% | 0 | 0% | 39.5 | 98.75%
Sub total(4a) | 40 | 0.5 | 1.25% | 1e-65 | 2.5e-65% | 0 |  | 39.5 | 98.75%
Sub total (Revenue)= | 40919.53 | 10400.5576 |  | 4571 |  | 4566.519 |  | 25952.4535
Capital
5) Acquisition of Assets
a) Acquisition of Assets | 6064.74 | 1805.3298 | 29.77% | 1455 | 23.99% | 1455 | 100% | 2804.4102 | 46.24%
Sub total(5a) | 6064.74 | 1805.3298 |  | 1455 |  | 1455 |  | 2804.4102
6) Acquisition of Land (269.40ha) | 1374.01 | 0 | 0% | 1e-31 | 7.278e-33% | 0 | 0% | 1374.01 | 100%
Sub total(6) | 1374.01 | 0 |  | 1e-31 |  | 0 |  | 1374.01
Physical Works
7) Upgrading of Union Roads
a) Office Building (School cum Cyclone shelter) | 11445.4749 | 0 | 0% | 3635.21 | 31.76% | 3635.21 | 100% | 7810.2649 | 68.24%
b) Office Building (Community Resource Centre) | 1027.931 | 0 | 0% | 1e-32 | 9.728e-34% | 0 | 0% | 1027.931 | 100%
c) Urban transport/Roads | 82666.467 | 17476.47 | 21.14% | 13726.79 | 16.61% | 13726.791 | 100% | 51463.206 | 62.25%
d) Urban transport/ bridges/overpass | 26046.7039 | 1923.29 | 7.384% | 6186.93 | 23.75% | 6186.93 | 100% | 17936.4839 | 68.86%
e) Drainage Structures/ Drain/Canal/Khal | 51886.0335 | 13254.41 | 25.55% | 9924.96 | 19.13% | 9924.96 | 100% | 28706.6635 | 55.33%
f) Sanitation & Water Supply/ Pipeline/ overhead tank | 11774.3017 | 0 | 0% | 1e-30 | 8.493e-33% | 0 | 0% | 11774.3017 | 100%
g) Sinking/Installation of Tubewell | 1653.6313 | 0 | 0% | 1e-37 | 6.047e-39% | 0 | 0% | 1653.6313 | 100%
h) Electrical Installation | 9735.1955 | 2832.48 | 29.1% | 657.11 | 6.75% | 657.11 | 100% | 6245.6055 | 64.15%
i) Others Municipal Services/ Basic services for urban poor(footpath/ drain/latrine/streetlight/tubewell | 1675.9777 | 250 | 14.92% | 325 | 19.39% | 325 | 100% | 1100.9777 | 65.69%
Sub total(8a-h) | 197911.7165 | 35736.65 |  | 34456 |  | 34456.001 |  | 127719.0655
8) Other Loan
a) Micro credit operation | 500 | 250 | 50% | 100 | 20% | 100 | 100% | 150 | 30%
Sub total(5a) | 500 | 250 |  | 100 |  | 100 |  | 150
|  |  | 119 | -16
9) Development Import Duty and VAT
a) Development Import Duty and CD/VAT | 1520 | 16.77 | 1.103% | 350 | 23.03% | 350 | 100% | 1153.23 | 75.87%
b) Miscellaneous Capital Expenditure(IDC) | 100 | 0 | 0% | 1e-43 | 1e-43% | 0 | 0% | 100 | 100%
Sub total(9a-b) | 1620 | 16.77 |  | 350 |  | 350 |  | 1253.23
10) Contingency
a) Price Escalation/Contingency | 24590 | 0 | 0% | 1e-40 | 4.067e-43% | 0 | 0% | 24590 | 100%
b) Physical Contingency | 21320 | 0 | 0% | 1e-53 | 4.69e-56% | 0 | 0% | 21320 | 100%
Sub total(10a) | 45910 | 0 |  | 1e-53 |  | 0 |  | 45910
Sub total (Capital)= | 253380.4665 | 37808.7498 |  | 36361 |  | 36361.001 |  | 179210.7157
Grand Total= | 294299.9965 | 48209.3074 | 17.95% | 40932 | 16% | 40927.52 | 100% | 205163.1691
7. Progress of Procurement in Current FY: 2017-18
|  |  |  | Goods | Works | Services | Total
a) Work Order (WO) issued in last year or before
I. Number of WOs. |  |  |  | 29 | 88 | 12 | 129
II. Expenditure |  |  |  | 1805.3298 | 35736.65 | 10183.9723 | 47725.9521
b) Work Orders (WO) issued during the reporting Period, 2016-17
I. Number of WOs. |  |  |  | 0 | 0 | 0 | 0
II. Expenditure in current FY. |  |  |  | 0 | 0 | 0 | 0
C) WOs to be issued during the rest the period of the FY. |  |  |  | 21 | 23 | 0 | 44
d) Total expenditure for procurement up to reporting month, 2016-17 (a ii + b ii). |  |  |  | 1805.3298 | 35736.65 | 10183.9723 | 47725.9521
e) Total budget/allocation for Procurement,2016-17 |  |  |  | 1823 | 25325 | 0 | 27148
f) Cumulative expenditure up to last year. |  |  |  | 1805.3298 | 35736.65 | 0 | 37541.9798
g) Total allocation as per DPP/TPP |  |  |  | 7605.59 | 197911.11 | 86515.83 | 292032.53
h) Unspent amount as per DPP/TPP. |  |  |  | 5800.2602 | 162174.46 | 76331.8577 | 244306.5779
8. Particulars of reimbursement claim and receipts:
| Initial advance Receipt with date | Up to 30/06/2015 |  |  | During 2015-16
|  | Expenditure |  | Reimbursement claimed | Expenditure |  | Reimbursement claimed
|  | Direct payment | payment from project account |  | Direct payment | payment from project account
| 1 | 2 | 3 | 4 | 5 | 6 | 7
| 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 119 | -17

## IMED-Q(1)
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003(Revised) (Page 1 of 4)
(Quarterly Progress Report)
ADP: FY 2017- 2018, Reporting Quarter : 4th Quarter (April-June/2018)
A. Quarterly Financial Progress Report
Code
A.1. | a) Project Title: | “City Governance Project”. |  |  |  |  | 3731 | 5118
b) Ministry: Ministry of Local Government Rural Development & Co-operatives (LGRD & C) / Local Government Division (LGD) / Local Government Engineering Department (LGED)
c) Division: Local Government Division (LGD).
d) Agency Name : Local Government Engineering Department (LGED)
A.2. | Quaterly Financial Progress :
130.701
Head |  | Release for the Quarter |  | Expenditure for the Quarter |  | Current Year Expenditure |  |  |  | 1200
|  | GOB | RPA | GOB | RPA | GOB | RPA | DPA |  | 107.01
Revenue |  | 644.07 | 0 | 639.58 | 32.34 | 2045.51 | 109.11 | 2387
Capital |  | 5067.25 | 0 | 5067.25 | 18824.89 | 5706 | 29224.89 | 1455 |  | =
Grand Total |  | 5711.32 | 0 | 5706.83 | 18857.23 | 7751.51 | 29334 | 3842
580
565
Cash Foreign Exchange Spent |  |  | Spent from Own Resources |  | CD/VAT | [5 empty] | 1289.25
|  |  | Cash | Kind
N/A
RPA Spent (Cumulative to Date) |  |  | RPA Claimed |  | RPA Reimbusrsef
|  |  | Reporting Quarter | Cumulative to Date | Reporting Quarter | Cumulative to Date
N/A
|  |  | 119 | -18
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003(Revised) (Page 1 of 4)
(Quarterly Progress Report)
ADP: FY 2007- 2008, Reporting Quarter : April - June / 2009
A. Quarterly Financial Progress Report
Code
A.1. | a) Project Title: | “Union Road & Other Infrastructure Development Project : Greater Jessore & Kushtia District ”. |  |  |  |  | 5085 | 2008-09
| b) Ministry: Local Government Rural Development & Co-operatives.(LGED & C) | [5 empty] | 3700 | 2008-09
| c) Division: Local Government Division (LGD). | [5 empty] | 3700 | 2008-09
| d) Agency Name : Local Government Engineering Department (LGED) | [5 empty] | 3731 | 2008-09
A.2. | Quaterly Financial Progress :
Head |  | Release for the Quarter |  | Expenditure for the Quarter |  | Current Year Expenditure
|  | GOB | RPA | GOB | RPA | GOB | RPA | DPA
Revenue |  | 10 | 0 | 9.66 | 0 | 9.66 | 0 | 0
Capital |  | 390 | 0 | 390 | 0 | 390 | 0 | 0
Grand Total |  | 400 | 0 | 399.66 | 0 | 399.66 | 0 | 0
Cash Foreign Exchange Spent |  |  | Spent from Own Resources |  | CD/VAT
|  |  | Cash | Kind
N/A
RPA Spent (Cumulative to Date) |  |  | RPA Claimed |  | RPA Reimbusrsef
|  |  | Reporting Quarter | Cumulative to Date | Reporting Quarter | Cumulative to Date
N/A
45(1)
Note on C22: Eaar Uddin: data from ADP Allotment Register (GOB)
Note on E22: Eaar Uddin: Data by calculated
Note on F22: Eaar Uddin: data from Cash Book Sonali Bank
Note on G22: Eaar Uddin: Data from ADP Accounts Register
Note on H22: Eaar Uddin: Data from ADP Accounts Register
Note on I22: Eaar Uddin: Data from ADP Accounts Register

## IMED-Q(2)
Project Monitoring Form: IMED 03/2003(Revised) (Page 2 of 4)
(Quarterly Progress Report)
ADP: FY 2017- 2018, Reporting Quarter : 4th Quarter (April-June/2018)
B. Quarterly Component-wise Progress
Code
B.1. | Project Title: “City Governance Project”. | [9 empty] | 3731 | 5118
B.2. | Quarterly Component-wise Progress
(In lakh Taka)
Sl. No. | Name of the Component | Unit | Cumulative Progress up to Last June |  |  | Yearly Target |  |  | Progress in Current Quarter |  |  | Current Year's Progress
|  |  | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial
|  |  | Qtty. | % |  | Qtty. | % |  | Qtty. | % |  | Qtty. | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 1) Pay & Allowances
| a) Pay of Officers | 2376 MM | 0.10564 | 0.02348% | 0.11935 | 120 MM | 6.41% | 48 | 30 MM | 25% | 6.6444 | 120 | 100% | 47.44
| b) Pay of Establishment | 1368 MM | 104 | 23.11% | 17.701 | 36 MM | 5.278% | 13.22 | 9 MM | 25% | 7.8626 | 36 | 100% | 13.22
| c) Allowances | 3744 MM | 0.076023 | 0.01689% | 0.070668 | 156 MM | 4.126% | 51.09 | 39 MM | 25% | 28.5539 | 156 | 100% | 48.01
| Sub-Total= (1a-c) |  | 355 | 78.89% | 85.0301 |  | 0% | 112.31 |  | 0% | 43.0609 |  | 0% | 108.67
2 | 2) Supply & Services
| a) Supply (Stationary & others) |  | 0 | 0% | 10183.9723 |  | 11.58% | 4425.69 |  | 25% | 2631.7137 |  | 99.98% | 4424.909
| Sub total(2a) |  | 0.26647 | 0.05922% | 0.26647 |  | 0% | 4425.69 |  | 0% | 2631.7137 |  | 0% | 4424.909
3 | 3) Repair, Maintenance & Rehabilitation
| a) Vehicles & Equipment |  | 0.056554 | 0.01257% | 0.056554 |  | 7.783% | 33 |  | 24.95% | 19.5911 |  | 99.82% | 32.94
| Sub total(3a) |  | 0 | 0% | 0.5 |  | 0% | 33 |  | 0% | 19.5911 |  | 0% | 32.94
4 | 4) Block Allocation
| Sub total(4a) |  | 0.29768 | 0.06615% | 0.29768 |  | 2.5e-65% | 1e-65 |  | 0% | 0 |  | 0% | 0
| Sub total (Revinue)= |  | 0 | 0% | 0 |  | 0% | 4571 |  | 0% | 2694.3657 |  | 0% | 4566.519
Capital
5 | 5) Acquisition of Assets
| a) Acquisition of Assets |  | 0 | 0% | 0 |  | 23.99% | 1455 |  | 25% | 0 |  | 100% | 1455
| Sub total(5a) |  | 0 | 0% | 0 |  | 0% | 1455 |  | 0% | 0 |  | 0% | 1455
6 | 6) Acquisition of Land (269.40ha) |  | 0 | 0% | 0 |  | 7.278e-33% | 1e-31 |  | 0% | 0 |  | 0% | 0
| Sub total(6) |  | 0 | 0 | 0 |  | 0% | 1e-31 |  | 0% | 0 |  | 0% | 0
Physical Works
7 | 7) Upgrading of Union Roads
| a) Office Building (School cum Cyclone shelter) | 8 nos. | 0.2153 | 0.04784% | 0.07384 | 0 nos. | 31.76% | 3635.21 | 8 nos. | 25% | 0 | 0 nos. | 100% | 3635.21
| b) Office Building (Community Resource Centre) | 10 nos. | 26 | 5.778% | 13254.41 | 0 nos. | 9.728e-34% | 1e-32 | 10 nos. | 0% | 0 | 0 nos. | 0% | 0
| c) Urban transport/Roads | 589 km | 0.26263 | 0.05836% | 0.25545 | 6.06km | 16.61% | 13726.79 | 589 km | 25% | 0 | 98 | 100% | 13726.791
| d) Urban transport/ bridges/overpass | 15 nos. | 0 | 0% | 0 | 0.11 nos. | 23.75% | 6186.93 | 15 nos. | 25% | 0 | 168 | 100% | 6186.93
| e) Drainage Structures/ Drain/Canal/Khal | 99 km | 0 | 0% | 0 | 1.34 km | 19.13% | 9924.96 | 99 km | 25% | 0 | 19 | 100% | 9924.96
| f) Sanitation & Water Supply/ Pipeline/ overhead tank | 237 km | 0 | 0% | 0 | 0 km | 8.493e-33% | 1e-30 | 237 km | 0% | 0 | 0 | 0% | 0
| g) Sinking/Installation of Tubewell | 57 nos. | 0 | 0% | 0 | 0 nos. | 6.047e-39% | 1e-37 | 57 nos. | 0% | 0 | 0 | 0% | 0
| h) Electrical Installation | 10170nos. | 3257 | 723.8% | 2832.48 | 465nos. | 6.75% | 657.11 | 10170nos. | 25% | 0 | 754 | 100% | 657.11
| i) Others Municipal Services/ Basic services for urban poor(footpath/ drain/latrine/streetlight/tubewell |  | 0.29158 | 0.0648% | 0.29095 |  | 19.39% | 325 |  | 25% | 0 | 0 | 100% | 325
| Sub total(8a-h) |  | 0 | 0% | 250 |  | 0% | 34456 |  | 0% | 0 |  | 0% | 34456.001
8 | 8) Other Loan
| a) Micro credit operation |  | 0 | 0% | 250 |  | 20% | 100 |  | 25% | 0 |  | 100% | 100
| Sub total(5a) |  | 0.5 | 0.1111% | 0.5 |  | 0% | 100 |  | 0% | 0 |  | 0% | 100
9 | 9) Development Import Duty and VAT
| a) Development Import Duty and CD/VAT |  | 0 | 0% | 0 |  | 23.03% | 350 |  | 25% | 0 |  | 100% | 350
| b) Miscellaneous Capital Expenditure(IDC) |  | 0 | 0% | 0 |  | 1e-43% | 1e-43 |  | 0% | 0 |  | 0% | 0
| Sub total(9a-b) |  | 0 | 0% | 0 |  | 0% | 350 |  | 0% | 0 |  | 0% | 350
10 | 10) Contingency
| a) Price Escalation/Contingency |  | 0 | 0% | 0 |  | 4.067e-43% | 1e-40 |  | 0% | 0 |  | 0% | 0
| b) Physical Contingency |  | 0 | 0% | 48209.3074 |  | 4.69e-56% | 1e-53 |  | 0% | 0 |  | 0% | 0
| Sub total(10a) |  | 0.17948 | 0.03989% | 0.1638 |  | 0% | 1e-53 |  | 0% | 0 |  | 0% | 0
| Sub total (Capital)= |  | 0 | 0% | 0 |  | 0% | 36361 |  | 0% | 0 | 74.06 | 0% | 36361.001
| Grand Total= |  | 0 | 0% | 0 |  | 16% | 40932 |  | 100% | 0 | 98.44 | 100% | 40927.52
[5 empty] | 119 | -19

## IMED-Q(3)
Project Monitoring Form: IMED 03/2003 (Revised) (Page 3 of 4)
(Quarterly Progress Report)
ADP: FY 2017- 2018, Reporting Quarter : 4th Quarter (April-June/2018)
C. Implementation Problems & Suggested Measures
Code
C.1. | Project Title: | “City Governance Project”. | [6 empty] | 3731 | 5118
C.2. | Implementation Problems : Nil.
| Problem Number | Problem Type |  |  | Description of Problem
| 1 | Approval Process
| 2 | Procurement
| 3 | Management
| 4 | Fund Allocation/Release
| 5 | Manpower Recruitment
| 6 | Oters (Specify)
C.3. | Suggested Measures: (In brief & specific)
| Problem Number | Measures Suggested
1
2
3
4
5
6
Others
None
C.4. | Is the project declared completed | [6 empty] | Yes | No
| Project Director/ | [6 empty] | Head of the Agency/
| Authorized Signature | [6 empty] | Authorized Signature
| Date | [6 empty] | Date
Secretary/Head of Planning Wing/Branch
Authorized Signature
Date
[6 empty] | 119 | -20
√

## IMED-Q(4)
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003(Revised) (Page 4 of 4)
(Quarterly Progress Report)
ADP: FY 2017- 2018, Reporting Quarter : 4th Quarter (April-June/2018)
D. Contract Implemention Report
(Please fill-in this form for goods and works contract of value above Tk.200.00 lakh and consultancy contract of value above Tk. 100.00 lakh)
Code
D.1. | Project Title: | “City Governance Project”. | [6 empty] | 3731 | 5118
D.2. | Contract Implemention |  |  | Not Applicable
| Description of contracts (as per tender document) |  |  | Contract value | Date of work order/contract agreement |  | Completion date as per contract |  | Progress
[9 empty] | Amount paid | Physical (%)
D.3. | Problems/Reasons for Delay in Contract Implementation (if any) :
| Sl. No. | Description
| 1 | Annual Budget Allocation is insufficient as per DPP
| Project Director/ | [6 empty] | Head of the Agency/
| Authorized Signature | [6 empty] | Authorized Signature
| Date | [7 empty] | Date
Secretary/Head of Planning Wing/Branch
Authorized Signature
Date
[6 empty] | 119 | -21

## Work Plan
¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
evwl©K Kg© cwiKíbv (Work Plan) QK (2017-2018)
cÖK‡íi bvg t ÒwmwU Mfvi‡bÝ cÖ‡R±Ó
†gqv` Kvj t RyjvB/2014 Bs n‡Z Ryb/2020 Bs
cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q (j¶ UvKvq) t |  |  |  |  | †gvUt | 294300 |  |  | wRIwet | 54531 |  |  | cÖKí mvnvh¨ t |  | 239769
Ryb 2017 ch©šÍ µgcywÄZ e¨q (j¶ UvKvq) t |  |  |  |  | †gvUt | 48209.31 |  |  | wRIwet | 6459.31 |  |  | cÖKí mvnvh¨ t |  | 41750
2017-18 A_©eQ‡ii GwWwc‡Z eivÏ (j¶ UvKvq)t |  |  |  |  | †gvUt | 31532 |  |  | wRIwet | 2770 |  |  | cÖKí mvnvh¨ t |  | 28762
cÖKíwU G A_©eQ‡i mgvwßi Rb¨ wbav©wiZ t |  |  |  | bv
cÖKíwU G A_©eQ‡i mgvß n‡e t |  |  |  | bv
ms‡kvwaZ GwWwc‡Z eivÏ nªvm/e„w×i cÖ‡qvRb n‡et |  |  | n¨vu
(j¶ UvKvq)
As‡Mi bvg | RyjvB 2017 gv‡m j¶¨gvÎv |  |  |  | AvMó 2017 gv‡m j¶¨gvÎv |  |  |  | †m‡Þ¤¦i 2017 gv‡m j¶¨gvÎv |  |  |  | A‡±vei 2017 gv‡m j¶¨gvÎv |  |  |  | b‡f¤¦i 2017 gv‡m j¶¨gvÎv |  |  |  | wW‡m¤¦i 2017 gv‡m j¶¨gvÎv |  |  |  | Rvbyqvix 2018 gv‡m j¶¨gvÎv
| †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq)
| j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí
| (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨
| Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm,
| wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt,
| BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw`
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
K) ivRm¦ AsMmgyn t
4500 Awdmvi‡`i †eZb | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4
4600 cªwZôvb Kg©Pvix‡`i †eZb | 5 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667
4700 fvZvw` | 15 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667
4800 mieivn I †mev |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333
4900 ‡givgZ I msi¶b |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833
Dc-‡gvU (K) t |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333
L) g~jab AsMmgyn t
6800 m¤ú` msMªn / µq | [20 empty] | 3 | 70.5 | 70.5 |  | 7 | 600 |  | 600
7000 wbg©vY I c~Z© | [8 empty] | 28 | 6331.25 | 81.25 | 6250 |  |  |  |  | 24 | 2532.5 | 32.5 | 2500 | 28 | 3798.75 | 48.75 | 3750 | 12 | 1266.25 | 16.25 | 1250
7300 FY I AwMÖg | [8 empty] | 1 | 20 | 20 | [5 empty] | 2 | 40 | 40
7900 g~jab Lv‡Z wmwW f¨vU | [8 empty] | 1 | 80 | 80 | [5 empty] | 1 | 80 | 80
Dc-‡gvU (L) t |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6431.25 | 181.25 | 6250 |  | 0 | 0 | 0 |  | 2652.5 | 152.5 | 2500 |  | 3869.25 | 119.25 | 3750 |  | 1866.25 | 16.25 | 1850
me©‡gvU (K+L) t |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 6761.5833 | 338.25 | 6423.3333 |  | 330.3333 | 157 | 173.3333 |  | 2982.8333 | 309.5 | 2673.3333 |  | 4199.5833 | 276.25 | 3923.3333 |  | 2196.5833 | 173.25 | 2023.3333
As‡Mi bvg | †deªyqvix, 2018 gv‡m j¶¨gvÎv |  |  |  | gvP©, 2018 gv‡m j¶¨gvÎv |  |  |  | GwcÖj, 2018 gv‡m j¶¨gvÎv |  |  |  | †g, 2018 gv‡m j¶¨gvÎv |  |  |  | Ryb, 2018 gv‡m j¶¨gvÎv |  |  |  | †gvU j¶¨gvÎv
| †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq)
| j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí
| (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨
| Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm,
| wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt,
| BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw`
1 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
K) ivRm¦ AsMmgyn t
4500 Awdmvi‡`i †eZb | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 10 | 4 | 4 |  | 120 | 48 | 48 | 0
4600 cªwZôvb Kg©Pvix‡`i †eZb | 5 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 10 | 0.91667 | 0.91667 |  | 110 | 11 | 11 | 0
4700 fvZvw` | 15 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 20 | 4.6667 | 4.6667 |  | 230 | 56 | 56 | 0
4800 mieivn I †mev |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 319.6667 | 146.3333 | 173.3333 |  | 3836 | 1756 | 2080
4900 ‡givgZ I msi¶b |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 1.0833 | 1.0833 |  |  | 13 | 13 | 0
Dc-‡gvU (K) t |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 330.3333 | 157 | 173.3333 |  | 3964 | 1884 | 2080
L) g~jab AsMmgyn t
6800 m¤ú` msMªn / µq |  |  |  |  | 2 | 35.25 | 35.25 | 0 |  |  |  |  | 9 | 1117.25 | 35.25 | 1082 |  |  |  |  | 21 | 1823 | 141 | 1682
7000 wbg©vY I c~Z© | 12 | 2532.5 | 32.5 | 2500 | 12 | 2532.5 | 32.5 | 2500 |  |  |  |  | 25 | 3798.75 | 48.75 | 3750 | 20 | 2532.5 | 32.5 | 2500 | 104 | 25325 | 325 | 25000
7300 FY I AwMÖg | 1 | 20 | 20 | [9 empty] | 1 | 20 | 20 | [5 empty] | 5 | 100 | 100 | 0
7900 g~jab Lv‡Z wmwW f¨vU | 1 | 80 | 80 | [9 empty] | 1 | 80 | 80 | [5 empty] | 4 | 320 | 320 | 0
Dc-‡gvU (L) t |  | 2632.5 | 132.5 | 2500 |  | 2567.75 | 67.75 | 2500 |  | 0 | 0 | 0 |  | 5016 | 184 | 4832 |  | 2532.5 | 32.5 | 2500 |  | 27568 | 886 | 26682
me©‡gvU (K+L) t | [21 empty] | 31532 | 2770 | 28762
wet`ªt Microsoft Excel I SutonnyMJ Font G Soft Copy mn Z_¨vw` cvVv‡Z n‡e¦
* 2016-17 A_©eQ‡ii †h mKj ¯‹xg GLbI Pjgvb Av‡Q †m¸‡jvi Z_¨ Ges eZ©gvb 2017-18 A_©eQ‡i Kvh©v‡`k cÖ`vbK…Z ¯‹x‡gi Z_¨ mswkøó gv‡mi Q‡K Avm‡e¦

## Procurement Plan
¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
evwl©K msMÖn/µq cwiKíbv (2017-18)
* cÖK‡íi bvg t ÒwmwU Mfvi‡bÝ cÖ‡R±Ó
* †gqv` Kvj t RyjvB/2014 Bs n‡Z Ryb/2020 Bs
* cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q (j¶ UvKvq) t | [9 empty] | †gvUt | 294300 |  |  | wRIwet | 54531 |  |  | cÖKí mvnvh¨ t | 239769
(j¶ UvKv)
[9 empty] | †gvU |  |  |  | cY¨ |  |  |  | c~Z© |  |  |  | ‡mev
* Aby‡gvw`Z wWwcwc/wUwcwc/AviwUwcwcÕi cÖwµDi‡g›U cø¨vb | [8 empty] | msL¨v |  | e¨q |  | msL¨v |  | e¨q |  | msL¨v |  | e¨q |  | msL¨v |  | e¨q
Abyhvqx c¨v‡K‡Ri msL¨v I cÖv°wjZ e¨q t | [8 empty] | 213 |  | 292032.53 |  | 67 |  | 7605.59 |  | 134 |  | 197911.11 |  | 12 |  | 86515.83
* Ryb 2017 ch©šÍ µgcywÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v I e¨q t | [8 empty] | 129 |  | 45760.33 |  | 29 |  | 1801.45 |  | 88 |  | 33723.84 |  | 12 |  | 10235.04
* 2017-18 A_©eQ‡ii GwWwc‡Z eivÏ Abymv‡i Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q t | [8 empty] | 44 |  | 27148 |  | 21 |  | 1823 |  | 23 |  | 25325 |  | 0 |  | 0
(j¶ UvKvq)
µwgK bs | cÖK‡íi bvg | RyjvB 2017 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | AvMó 2017 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | ‡m‡Þ¤^i 2017 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | A‡±vei 2017 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | b‡f¤^i 2017 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | wW‡m¤^i 2017 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | Rvbyqvix 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q
|  | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  | 0 |  | 0 | 0 | 0 | 0 | 3 | 0 | 4 | 0 | 4 | 0 | 9 | 5 | 4 | 0 | 12 | 5 | 7 | 0 | 5 | 6 | 5 | 0 | 8 | 3 | 5 | 0
|  | 0 |  | 0 | 0 | 3303.2609 | 0 | 3303.2609 | 0 | 4404.3478 | 0 | 4404.3478 | 0 | 4838.3954 | 434.0476 | 4404.3478 | 0 | 8141.6563 | 434.0476 | 7707.6087 | 0 | 6026.2919 | 520.8571 | 5505.4348 | 0 | 260.4286 | 260.4286 | 0 | 0
µwgK bs | cÖK‡íi bvg | ‡deªæqvix 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | gvP© 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | GwcÖj 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | ‡g 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | Ryb 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | ‡gvU
|  | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q)
|  | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
|  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 21 | 23 | 0
|  | 173.619 | 173.619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27148 | 1823 | 25325 | 0
wet`ªt Microsoft Excel I SutonnyMJ Font G Soft Copy mn Z_¨vw` cvVv‡Z n‡e¦
* 2016-17 A_©eQ‡ii †h mKj ¯‹xg (cY¨/c~Z©/†mev) GLbI Pjgvb Av‡Q †m¸‡jvi Z_¨ GB Q‡K Avm‡e bv¦ ïaygvÎ †hmKj `icÎ AvnŸvb Kiv n‡e I Kvh©v‡`k cÖ`vb Kiv n‡e †m¸‡jvi Z_¨ Avm‡e¦