## Urban
cÖKí msµvšÍ gvwmK AMÖMwZi cÖwZ‡e`b
wW‡m¤^i/2018Bs¦
cÖK‡íi bvg t wmwU Mfvib¨vÝ cÖ‡R± (CGP) (cÖKí †KvW- byZb 224047800 cyivZb 5118)
cÖv°wjZ e¨q (j¶ UvKvq) |  | t | g~j t | 294300 |  |  | ms‡kvwaZ t -
ev¯ÍevqbKvjt |  | t | g~j t | Ryjv&B/2014 n‡Z Ryb/2020 ch©šÍ |  |  | ms‡kvwaZ t -
cÖKí ïiæ †_‡K cÖvß nvjbvMv` †gvU eivÏ |  | t | †gvU t | 135888 | { wRIwe t | 21834 | cÖK‡íi mvnvh¨ t | 114054 | (AviwcGt | 99462 |  | wWwcG t | 14592 |  | )}
eZ©gvb A_© eQ‡i eivÏ |  | t | †gvU t | 46744 | { wRIwe t | 7616 | cÖK‡íi mvnvh¨ t | 39128 | (AviwcGt | 36728 |  | wWwcG t | 2400 |  | )}
eZ©gvb A_© eQ‡i Aegyw³ |  | t | †gvU t | 43035.985 | { wRIwe t | 3907.985 | cÖK‡íi mvnvh¨ t | 39128 | (AviwcGt | 36728 |  | wWwcG t | 2400 |  | )}
eZ©gvb A_© eQ‡i e¨q |  | t | †gvU t | 21592.71 | { wRIwe t | 3338.79 | cÖK‡íi mvnvh¨ t | 18253.92 | (AviwcGt | 17143.45 |  | wWwcG t | 1110.47 |  | )}
µgcywÄZ nvjbvMv` ‡fŠZ AMÖMwZ |  | t |  | 41.5%
µgcywÄZ nvjbvMv` e¨q |  | t |  | 110729.5374
µwgK bs | wWwcwc Abymv‡i As‡Mi bvg (cwigvb/msL¨v) | wWwcwc Abymv‡i eivÏ (j¶ UvKvq) | eZ©gvb A_© eQ‡i GwWwc Abyhvqx j¶¨gvÎv |  |  | PjwZ gv‡mi AMÖMwZ |  |  |  |  | PjwZ A_© eQ‡ii µgcywÄZ AMÖMwZ |  | PjwZ gvm ch©šÍ µgcywÄZ Pyw³g~j¨ |  | gšÍe¨ | c~‡e©i gvm ch©šÍ LiP
|  |  | ‡fŠZ | Avw_©K |  | †fŠZ |  | Avw_©K
[11 empty] | ‡fŠZ | Avw_©K
1 | 2 | 3 | 4 | 5 |  | 6 |  | 7 |  |  | 8 | 9 | 10 |  | 11
(K) ivR¯^ eivÏ
1 | Kg©KZ©v‡`i †eZb | 748.85 |  | 50 | 12.5 | 50% |  | 6.61 |  |  |  | 29.29 |  |  |  | 22.68 | 6.61
2 | Kg©Pvix‡`i †eZb | 250.48 |  | 10 | 2.5 | 50% |  | 0.38 |  |  |  | 3.38 |  |  |  | 3
3 | fvZvw` | 1238.13 |  | 53 | 13.25 | 50% |  | 3.55 |  |  |  | 24.29 |  |  |  | 20.74
4 | mieivn I †mev | 38218.07 |  | 4529 | 1132.25 |  |  | 501.55 |  |  |  | 1788.3 |  |  |  | 1286.75
5 | ‡givgZ msiÿY I cybe©vmb | 424 |  | 38 | 9.5 |  |  | 1.86 |  |  |  | 13.7 |  |  |  | 11.84
6 | ‡_vK eivÏ | 40 |  | 1e-65 |  |  |  | 0 |  |  |  | 0
| †gvU (K) ivR¯^ = | 40919.53 |  | 4680 | 1170 |  |  | 513.95 |  |  |  | 1858.96 |  | 0 |  | 1345.01
(L) g~jab eivÏ
| m¤ú` msMÖn/µq | 6064.74 |  | 155 | 38.75 |  |  | 0 |  |  |  | 0
| Dc-‡gvU m¤ú` msMÖn/µq = | 6064.74 |  | 155 | 38.75 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| f‚wg AwaMÖnY/µq | 1374.01 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| Dc-‡gvU f‚wg AwaMÖnY/µq = | 1374.01 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
wbg©vY I c~Z©
| Awdm feb t (¯‹zj Kvg mvB‡K¬vb †mëvi) | 11445.4749 |  | 7810 | 3905 | 60% |  | 660.92 |  |  | 60% | 4476.26 |  | 7033.67 |  | 3815.34
| Awdm feb t (KwgDwbwU wi‡mvvm© †m›Uvi) | 1027.931 |  | 0 | 0 |  |  | 0 |  |  | 0% | 0 |  |  |  | 0
| moK I gnvmoK | 82666.467 |  | 15563 | 3890.75 | 41.44% |  | 692.48 |  |  | 41.44% | 5620.82 |  | 50625 |  | 4928.34 |  | 67500
| ‡mZz | 26046.7039 |  | 9196 | 2299 | 45.38% |  | 617.97 |  |  | 45.38% | 4185.39 |  | 16875 |  | 3567.42
| cvwb wb®‹vkb AeKvVv‡gv | 51886.0335 |  | 8045 | 2011.25 | 46.67% |  | 564.15 |  |  | 46.67% | 3820.87 |  | 37960 |  | 3256.72
| ¯^v¯’¨ cwiPhv© I cvwb mieivn | 11774.3017 |  | 615 | 153.75 | 58.33% |  | 52.99 |  |  | 58.33% | 358.86 |  | 3807.8 |  | 305.87
| bjK‚c ¯’vcb | 1653.6313 |  | 0 | 0 | 0% |  | 0 |  |  | 0% | 0 |  |  |  | 0
| ˆe`y¨wZK ¯’vcbv | 9735.1955 |  | 230 | 57.5 | 377.7% |  | 98.32 |  |  | 49.24% | 113.32 |  | 4782 |  | 15
| Ab¨vb¨ | 1675.9777 |  | 300 | 75 | 377.7% |  | 983.23 |  |  | 377.7% | 1133.23 |  |  |  | 150
| Dc-‡gvU wbg©vY I c~Z© = | 197911.7165 |  | 41759 | 12392.25 |  |  | 3670.06 |  |  |  | 19708.75 |  | 121083.47 |  | 16038.69
FY I AwMÖg
| Ab¨vb¨ FY | 500 |  | 50 | 25 |  |  | 0 |  |  |  | 25 |  |  |  | 25
| Dc-‡gvU FY I AwMÖg = | 500 |  | 50 | 25 |  |  | 0 |  |  |  | 25 |  | 0 |  | 25
wmwW f¨vU
| Avg`vbx ïé I f¨vU | 1520 |  | 100 | 25 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| wewea g~jab e¨q | 100 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| Dc-‡gvU g~jab LvZ I wmwW f¨vU = | 1620 |  | 100 | 25 |  |  | 0 |  |  |  | 0 |  |  |  | 0
| ‡gvU (L) g~jab A½ = | 207470.4665 |  | 42064 | 12481 |  |  | 3670.06 |  |  |  | 19733.75 |  | 121083.47 |  | 16063.69
| (M) wewea g~jab e¨q : cÖvBm Kw›U‡RÝx | 24590 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| (N) wewea g~jab e¨q : wdwRK¨vj Kw›U‡RÝx | 21320 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| Dc-‡gvU (M) + (N) = | 45910 |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  | 0 |  | 0
| me©‡gvU (K + L + M + N ) = | 294299.9965 |  | 46744 | 13651 |  |  | 4184.01 |  |  |  | 21592.71 |  | 121083.47 |  | 17408.7
| ‡gvU (%) = | [6 empty] | 8.95% |  |  | 48.25% | 46.19% |  |  |  |  | 4184.01
wPwýZ mgm¨v t- Team Leader mn wKQz wKQz ¸iæZ¡c~Y© c‡` we‡`kx civgk©KMY RyjvB 2016 gvm †_‡K Abycw¯’Z wQ‡jb¦ d‡j Design I Resettlement Action Plan ˆZix wejw¤^Z n‡q‡Q n‡”Q weavq mvwe©Kfv‡e cÖK‡íi AMÖMwZI wejw¤^Z n‡q‡Q¦
(‡gvt mwn`yj Bmjvg)
wbim‡bi mycvwik t- | [11 empty] | cÖKí cwiPvjK
wmwU Mfvib¨vÝ cÖ‡R± (wmwRwc)
Note on H19: Eaar Uddin: all bellow data
Note on L54: Eaar Uddin: Current Month minus last month
Note on Y34: Eaar Uddin: don't delet sae-2 mohichhunul. 26-06-2018

## PR(P-1)
cÖKí ev¯Íevqb cÖwZ‡e`b
cªwZ‡e`b Kvj : wW‡m¤^i/2018Bs¦
01 | cÖK‡íi bvg | t |  | ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦
02 | Aby‡gv`b ch©vq | t | K) | 15-07-2014 Bs Zvwi‡L AbywôZ ECNEC mfv (¯§viK bs 20.00.0000.411.14.041.14-614 ZvwiL t 26-10-2014Bs) KZ…©K Aby‡gvw`Z nq¦ ¯’vbxq miKvi wefv‡Mi 05-11-2014Bs Zvwi‡Li ¯§viK bs 46.093.014.01.00.044.2013-1267 †gvZv‡eK Ò wmwU Mfvi‡bÝ cÖ‡R±Ó kxl©K cÖKí wWwcwci cÖkvmwbK Aby‡gv`b cÖ`vb Kiv nq¦
|  |  | L) | FY Pyw³i Kvh©KvwiZvi ZvwiL t 16/06/2014 Bs ¦
|  |  | M) | Dc‡`óv dvg© wb‡qv‡Mi ZvwiL t weMZ 12/07/2015Bs Zvwi‡L wRAvBAvB As‡ki Pzw³ m¤úv`b Kiv n‡q‡Q I MZ 06/08/2015 ZvwiL n‡Z KvR Avi¤¢ n‡q‡Q Ges MZ 01/09/2015 n‡Z weGgB As‡ki KvR ïiæ n‡q‡Q¦
03 | ms¯’v I gš¿bvj‡qi bvg | t |  | ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
|  |  |  | gš¿Yvjq | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿bvjq, ¯’vbxq miKvi wefvM¦
04 | cÖK‡íi D‡Ïk¨ | t | K) | cÖKíf‚³ 5wU wmwU K‡c©v‡ik‡bi cvewjK mvwf©m Dbœqb;
|  |  | L) | BbK¬zwmf wmwU Mfvib¨vÝ m¤ú‡K© cÖwkÿ‡Yi gva¨‡g †mevi gvb e„w×;
|  |  | M) | wmwU K‡c©v‡ikb mg~‡ni cÖkvmwbK `ÿZv e„w×; Ges
|  |  | N) | bMi AeKvVv‡gv AviI kw³kvjxKiY¦
05 | ev¯Íevqb Kvj | [7 empty] | g~j
|  | t | K) KvR Avi‡¤¢i ZvwiL | [5 empty] | RyjvB/2014 Bs
|  | t | L) cÖKí mgvwßi ZvwiL | [5 empty] | Ryb/2020 Bs
06 | cÖv°wjZ e¨q (j¶ UvKvq) | t |  | ‡gvU |  |  | x |  | 294300 | j¶ UvKv
|  |  |  | UvKv |  |  |  |  | 54531 | j¶ UvKv
|  |  |  | cÖKí mvnvh¨ |  |  |  |  | 239769 | j¶ UvKv
|  |  |  | cÖKí mvnv‡h¨i UvKvsk |  |  |  |  | 227262 | j¶ UvKv
07 | cÖKí mvnv‡h¨i Drm | t |  | RvBKv
[9 empty] | 99 | -1
cÖKí ev¯Íevqb cÖwZ‡e`b
cªwZ‡e`b Kvj : A‡±vei - 2008 Bs
01 | cÖK‡íi bvg | t |  | e„nËi h‡kvi ‡Rjv AeKvVv‡gv Db&œqb cÖÖKí
02 | Aby‡gv`b ch©vq | t | K) | 11-11-1998 Bs Zvwi‡L ECNEC KZ…©K PCP Ges 24-04-1999 Bs Zvwi‡L DPEC KZ…©K PP Aby‡gvw`Z¦ 20-05-2007Bs Zvwi‡L 1g ms‡kvwaZ wWwcwc Aby‡gvw`Z (15-05-2007Bs Zvwi‡L ¯’vbxq miKvi cj­x Dbœqb I mgevq gš¿Yvj‡qi `vwq‡Z¡ wb‡qvwRZ gvbbxq Dc‡`óv 1g ms‡kvwaZ wWwcwc Aby‡gv`b K‡i‡Qb)¦ 2007 mv‡ji eb¨v DËi c~Ye©vm‡bi Rb¨ cÖK‡íi †gqv` Ryb/2009 ch©šÍ e„w×mn we‡kl ms‡kvwaZ wWwcwc MZ 07-09-08Bs Zvwi‡L cwiKíbv Kwgk‡b AbywôZ wcBwm-i mfvq mycvwik jvf K‡i‡Q¦ eZ©gv‡b c~YM©wVZ we‡kl ms‡kvwaZ wWwcwc-wU ¯’vbxq miKvi wefv‡M cÖwµqvaxb Av‡Q¦
|  |  | L) | FY Pyw³i Kvh©KvwiZvi ZvwiL t cÖ‡hvR¨ b‡n ¦
|  |  | M) | Dc‡`óv dvg© wb‡qv‡Mi ZvwiL t cÖ‡hvR¨ b‡n ¦
03 | ms¯’v I gš¿bvj‡qi bvg | t |  | ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
|  |  |  | gš¿Yvjq | t | ¯’vbxq miKvi, cj­x Dbœqb I mgevq gš¿bvjq, ¯’vbxq miKvi wefvM
04 | cÖK‡íi D‡Ïk¨ | t | 1) | ‡mZy/KvjfvU© mn Dc‡Rjv moK I BDwbqb moK Dbœq‡bi gva¨‡g e„nËi h‡kvi ‡Rjvq mvwe©K e¨e¯’v Dbœqb Ges ‡hvMv‡hvM e¨e¯’v Dbœqb Ges ‡MÖv_ ‡m›Uvi I ¸i“Z¡c~Y© nvU evRv†ii AeKvVv‡gv (‡fŠZ myweavw`) Dbœq‡bi gva¨‡g MÖvgxY A_©bxwZ‡K ‡eMevb KivB cÖK‡íi D†Ïk¨ ¦
|  |  | 2) | cÖKífy³ Kvh©µ‡gi g‡a¨ ‡mZy/KvjfvU©mn Dc‡Rjv moK I BDwbqb moK Dbœqb, ‡MÖv_ ‡m›Uvi I nvUevRvi Dbœqb, mo‡Ki cv‡k¦© e„¶‡ivcY Ges GbwRI‡`i gva¨‡g `wi`ª‡`i Rb¨ `¶Zv e„w×i cÖwk¶Ymn ÷vd cÖwk¶Y Kvh©µg AšÍ©f~³ iwnqv‡Q ¦
05 | ev¯Íevqb Kvj | [7 empty] | g~j |  | 1g ms‡kvwaZ wWwcwc | 2q ms‡kvwaZ wWwcwc (Abby‡gvw`Z)
|  | t | K) KvR Avi‡¤^i ZvwiL | [5 empty] | 1 RyjvB/1998 Bs |  | 1 RyjvB/1998 Bs | 1 RyjvB/1998 Bs
|  | t | L) cÖKí mgvwßi ZvwiL | [5 empty] | 30 Ryb/2002 Bs |  | 30 Ryb/2008 Bs | 30 Ryb/2009 Bs
06 | cÖv°wjZ e¨q (j¶ UvKvq) | t |  | ‡gvU |  |  | x | 15200.00 j¶ UvKv |  |  | 16650.00 j¶ UvKv | 18140.70 j¶ UvKv
|  |  |  | UvKv |  |  |  | 15200.00 j¶ UvKv |  |  | 16650.00 j¶ UvKv | 18140.70 j¶ UvKv
|  |  |  | cÖKí mvnvh¨ |  |  |  | (-) |  |  | (-) | (-)
|  |  |  | cÖKí mvnv‡h¨i UvKvsk |  |  |  | (-) |  |  | (-) | (-)
07 | cÖKí mvnv‡h¨i Drm | t |  | evsjv‡`k miKvi (wRIwe)
3(1)

## PR(P-2)
08 | e¨q ( j¶ UvKvq ) t
[8 empty] | (j¶ UvKvq) |  | 14210.82
|  | ‡gvU | UvKv (wRIwe) | cÖKí mvnvh¨ |  | ïé | FY cwi‡kva | gšÍe¨
|  |  |  | ‡gvU | UvKvsk (AviwcG) |  |  |  | 9802.95
23442.6
(K) | 2018-19Bs A_© erm‡ii GwWwc eivÏ¦ | 46744 | 7616 | 39128 |  | 100 |  |  | -100926.58 | 74926 | 2007 mv‡ji eb¨v DËi c~Ye©vm‡bi Rb¨ cÖK‡íi †gqv` Ryb/2009Bs ch©šÍ e„w×mn we‡kl ms‡kvwaZ wWwcwcwU ¯’vbxq miKvi wefvM KZ…©K MZ 14-12-08Bs Zvwi‡L GjwR/cwi-1/GjwRBwW-7/98(Ask-1)/699 bs ¯§viK c‡Î cÖkvmwbK Aby‡gv`b cÖ`vb Kiv n‡q‡Q¦
[5 empty] | 36728 |  |  |  | 509.54
(L) | 2018-19Bs A_© erm‡ii wW‡m¤^i /2018Bs ch©šÍ Aegyw³ ¦ | 43035.985 | 3907.985 | 39128 |  | 100 |  |  | 110729.53
[5 empty] | 36728 |  |  |  | 1336.85
(M) | 2018-19Bs A_© erm‡ii wW‡m¤^i /2018Bs ch©šÍ e¨q ¦ | 21592.71 | 3338.79 | 18253.92 |  | 0 |  |  | 37.6247
[5 empty] | 17143.45 |  |  |  | 37.6247
(N) | cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q ¦ | 110729.53 | 17549.61 | 93179.92 |  | 366.77 |  |  | 3098 | -83342.59
[5 empty] | 79877.45 |  |  |  | 6436.79
[9 empty] | 1904 | 3808
5177
09 | cÖKí mvnvh¨ UvKvsk e¨q, `vex I cÖvwß (j¶ UvKvq)
welq |  | PjwZ A_© erm‡ii µgcywÄZ |  |  | µgcywÄZ
(K) | e¨q | 17143.45 |  |  | 79877.45
(L) | `vexK…Z | 17134.89 |  |  | 79871
(M) | cÖvwß | 17125.97 |  |  | 79862.06
|  |  | 99 | -2

## PR(P-3&4)
| 10 | cÖavb cÖavb As‡Mi j¶¨gvÎv I AMÖMwZ t
(j¶ UvKvq)
As‡Mi bvg |  |  | wWwcwc Abymv‡i j¶¨gvÎv |  |  | I‡q‡UU ev¯Íe | c~e©eZx© erm‡ii Ryb/2018 ch©šÍ µgc~wÄZ AMÖMwZ |  |  |  | PjwZ erm‡ii j¶¨gvÎv (cwigvY I wcwci %) |  |  |  |  | cÖwZ‡e`b Kvj ch©šÍ AMÖMwZ (cwigvY I j¶¨gvÎvi %) |  |  |  | cÖKí cwiPvjK/Kg©KZ©v KZ…©K cÖKí GjvKv cwi`k©‡bi ZvwiL | gšÍe¨
[22 empty] | µgcywÄZ | wWwcwc ‡iU | PjwZ †iU
|  |  | ev¯Íe |  | Avw_©K |  | ev¯Íe |  | I‡q‡UU ev¯Íe | Avw_©K | ev¯Íe |  | I‡q‡UU ev¯Íe | Avw_©K | I‡q‡UU Avw_©K jÿgvÎv | ev¯Íe |  | I‡q‡UU ev¯Íe | Avw_©K
1 |  |  | 2 |  | 3 |  | 4 |  |  | 5 | 6 |  |  | 7 |  | 8 |  |  | 9 | 10 | 11
1 | Kg©KZ©v‡`i †eZb |  | 2376 | Rbgvm | 748.85 |  | 371 | Rbgvm |  | 136.8153 | 120 | Rbgvm |  | 50 |  | 60 | Rbgvm |  | 29.29 | wcwW Kzwgjøv 02/12/2018 n‡Z 04/12/2018 ch©šÍ bvivqYMÄ: 10/12/18 n‡Z 11/12/2018 ch©šÍ iscyi 18/12/2018 n‡Z 20/12/2018 ch©›` wWwcwW-1 bvivqYMÄ : 05/12/18 n‡Z 6/12/2018 ch©šÍ MvRxcyi: 18/12/2018 n‡Z 19/12/2018 ch©šÍ wWwcwW-2 iscyi: 05/12/18 n‡Z 07/12/18 ch©šÍ PÆMÖvg : 11/12/18 n‡Z 13/12/18 ch©šÍ Kzwgjøv: 19/12/2018 n‡Z 20/12/2018 ch©šÍ |  | 166.1053
[6 empty] | 0.0025445 | 15.61% |  | 0.03973% | 18.27% | 5.051% |  | 0.01285% | 6.677% | 0.107% | 50% |  | 0.05348% | 58.58%
2 | Kg©Pvix‡`i †eZb |  | 1368 | Rbgvm | 250.48 |  | 140 | Rbgvm |  | 30.921 | 36 | Rbgvm |  | 10 |  | 18 | Rbgvm |  | 3.38 |  |  | 34.301
[6 empty] | 0.0008511 | 10.23% |  | 0.00871% | 12.34% | 2.632% |  | 0.00224% | 3.992% | 0.02139% | 50% |  | 0.0107% | 33.8%
3 | fvZvw` |  | 3744 | Rbgvm | 1238.13 |  | 511 | Rbgvm |  | 133.0401 | 156 | Rbgvm |  | 53 |  | 78 | Rbgvm |  | 24.29 |  |  | 157.3301
[6 empty] | 0.004207 | 10.75% |  | 0.04521% | 10.75% | 4.281% |  | 0.01801% | 4.281% | 0.1134% | 50% |  | 0.05669% | 45.83%
4 | mieivn I †mev |  | 0 | ‡_vK | 38218.07 |  | 0 | ‡_vK |  | 14583.9923 | 0 | ‡_vK |  | 4529 |  | 0 | ‡_vK |  | 1788.3 |  |  | 16372.2923
[6 empty] | 0.12986 | 38.16% |  | 4.955% | 38.16% | 11.85% |  | 1.539% | 11.85% | 9.689% | 39.49% |  | 3.826% | 39.49%
5 | ‡givgZ msiÿY I cybe©vmb |  | 0 | ‡_vK | 424 |  | 0 | ‡_vK |  | 56.9189 | 0 | ‡_vK |  | 38 |  | 0 | ‡_vK |  | 13.7 |  |  | 70.6189
[6 empty] | 0.0014407 | 13.42% |  | 0.01934% | 13.42% | 8.962% |  | 0.01291% | 8.962% | 0.08129% | 36.05% |  | 0.02931% | 36.05% |  |  | 1858.96
6 | ‡_vK eivÏ |  | 0 | ‡_vK | 40 |  | 0 | ‡_vK |  | 0.5 | 0 | ‡_vK |  | 1e-65 |  | 0 | ‡_vK |  | 0 |  |  | 0.5
[6 empty] | 0.00013592 | 1.25% |  | 0.0001699% | 1.25% | 2.5e-65% |  | 3.398e-69% | 2.5e-65% | 2.139e-68% | 0% |  | 0% | 0%
7 | m¤ú` msMÖn/µq |  | 0 | ‡_vK | 6064.74 |  | 0 | ‡_vK |  | 3260.3298 | 0 | ‡_vK |  | 155 |  | 0 | ‡_vK |  |  |  |  | 3260.3298
[6 empty] | 0.020607 | 53.76% |  | 1.108% | 53.76% | 2.556% |  | 0.05267% | 2.556% | 0.3316% | 0% |  | 0% | 0%
8 | f‚wg AwaMÖnY / µq |  | 0 | ‡_vK | 1374.01 |  | 0 | ‡_vK |  | 0 | 1e-44 | ‡_vK |  | 1e-31 |  | 0 | ‡_vK |  | 0 |  |  | 0
[6 empty] | 0.0046687 | 0% |  | 0% | 0% | 7.278e-33% |  | 3.398e-35% | 7.278e-33% | 2.139e-34% | 0% |  | 0% | 0%
9 wbg©vY I c~Z© | K) Awdm feb(¯‹zj Kvg mvB‡K¬vb †mëvi) |  | 8 | wU | 11445.47 |  | 3 | wU |  | 3635.21 | 5 | wU |  | 7810 |  | 3 | wU |  | 4476.26 |  |  | 8111.47 | 1430.6837 | 1492.0867
[6 empty] | 0.03889 | 37.5% |  | 1.458% | 31.76% | 62.5% |  | 2.431% | 68.24% | 16.71% | 60% |  | 10.02% | 57.31%
| L) Awdm feb(KwgDwbwU wi‡mvm© †m›Uvi) |  | 10 | wU | 1027.93 |  | 0 | wU |  | 0 | 0 | wU |  |  |  | 0 | wU |  |  |  |  | 0
[6 empty] | 0.0034928 | 0% |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% |  | 0% | 0%
| M) moK I gnvmoK |  | 589 | wKtwgt | 82666.47 |  | 226.5 | wKtwgt |  | 31228.15 | 111 | wKtwgt |  | 15563 |  | 46 | wKtwgt |  | 5620.82 |  |  | 36848.97 | 140.3505 | 122.1917
[6 empty] | 0.28089 | 38.46% |  | 10.8% | 37.78% | 18.85% |  | 5.294% | 18.83% | 33.29% | 41.44% |  | 13.8% | 36.12%
| N) †mZz |  | 706 | wgt | 26046.7 |  | 320 | wgt |  | 8110.22 | 249 | wgt |  | 9196 |  | 113 | wgt |  | 4185.39 |  |  | 12295.61 | 36.8933 | 249.2591
[6 empty] | 0.088504 | 45.33% |  | 4.012% | 31.14% | 35.27% |  | 3.121% | 35.31% | 19.67% | 45.38% |  | 8.928% | 45.51%
| O) cvwb wb®‹vkb AeKvVv‡gv |  | 99 | wKtwgt | 51886.03 |  | 45 | wKtwgt |  | 23179.37 | 15 | wKtwgt |  | 8045 |  | 7 | wKtwgt |  | 3820.87 |  |  | 27000.24 | 524.1013 | 15.3501
[6 empty] | 0.1763 | 45.45% |  | 8.014% | 44.67% | 15.15% |  | 2.671% | 15.51% | 17.21% | 46.67% |  | 8.032% | 47.49%
| P) ¯^v¯’¨ cwiPh©v I cvwb mieivn |  | 237 | wKtwgt | 11774.3 |  | 0 | wKtwgt |  | 0 | 12 | wKtwgt |  | 615 |  | 7 | wKtwgt |  | 358.86 |  |  | 358.86
[6 empty] | 0.040008 | 0% |  | 0% | 0% | 5.063% |  | 0.2026% | 5.223% | 1.316% | 58.33% |  | 0.7675% | 58.35%
| Q) bjK‚c ¯’vcb |  | 57 | wU | 1653.63 |  | 0 | wU |  | 0 | 0 | wU |  | 0 |  | 0 | wU |  |  |  |  | 0
[6 empty] | 0.0056189 | 0% |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% |  | 0% | 0%
| R) ˆe`¨wZK ¯’vcbv |  | 11170 | wgt | 9735.2 |  | 4011 | wgt |  | 3489.59 | 264 | wgt |  | 230 |  | 130 | wgt |  | 113.32 |  |  | 3602.91 | 0.87155 | 263.898
[6 empty] | 0.033079 | 35.91% |  | 1.188% | 35.85% | 2.363% |  | 0.07818% | 2.363% | 0.492% | 49.24% |  | 0.2423% | 49.27%
| S) `wi`ª‡`i Rb¨ Ab¨vb¨ †cŠi †mev |  | 0 | †_vK | 1675.98 |  | 0 | †_vK |  | 575 | 0 | †_vK |  | 300 |  | 0 | †_vK |  | 1133.23 |  |  | 1708.23
[6 empty] | 0.0056948 | 34.31% |  | 0.1954% | 34.31% | 17.9% |  | 0.1019% | 17.9% | 0.6418% | 377.7% |  | 2.424% | 377.7%
10 | FY I AwMÖg |  | 0 | ‡_vK | 500 |  | 0 | ‡_vK |  | 350 | 0 | ‡_vK |  | 50 |  | 0 | ‡_vK |  | 25 |  |  | 375
[6 empty] | 0.0016989 | 70% |  | 0.1189% | 70% | 10% |  | 0.01699% | 10% | 0.107% | 50% |  | 0.05348% | 50%
11 | K) Avg`vbx ïé I wmwW/f¨vU |  | 0 | ‡_vK | 1520 |  | 0 | ‡_vK |  | 366.77 | 0 | ‡_vK |  | 100 |  | 0 | ‡_vK |  |  |  |  | 366.77
[6 empty] | 0.0051648 | 24.13% |  | 0.1246% | 24.13% | 6.579% |  | 0.03398% | 6.579% | 0.2139% | 0% |  | 0% | 0%
| L) wewea g~jab e¨q |  | 0 | ‡_vK | 100 |  | 0 | ‡_vK |  | 0 | 0 | ‡_vK |  |  |  | 0 | ‡_vK |  | 0 |  |  | 0
[6 empty] | 0.00033979 | 0% |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% |  | 0% | 0%
12 | K) cÖvBR Kw›Ub‡RwÝ |  | 0 | ‡_vK | 24590 |  | 0 | h gg |  | 0 | 0 | ‡_vK |  |  |  | 0 | ‡_vK |  |  |  |  | 0
[6 empty] | 0.083554 | 0% |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% |  | 0% | 0%
| L) wdwRK¨vj Kw›Ub‡RwÝ |  | 0 | ‡_vK | 21320 |  | 0 | ‡_vK |  | 0 | 0 | ‡_vK |  |  |  | 0 | ‡_vK |  | 0 |  |  | 0 |  | 15074.83
[6 empty] | 0.072443 | 0% |  | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% |  | 0% | 0% |  |  | 19733.75 |  | 6517.88
‡gvU = |  |  |  |  | 294299.99 |  |  |  |  | 89136.8274 |  |  |  | 46744 |  |  |  |  | 21592.71 |  |  | 110729.5374 | 2014-15
[7 empty] | 33.09% |  |  | 31% | 17.44% |  |  | 15.88% |  | 48.25% |  |  | 46.19% |  |  |  | Rev.= | 88.9
[23 empty] | Capital= | 210.99
| ** | cÖKí ïiæ ‡_‡K G ch©šÍ µgc~wÄZ ‡fŠZ AMÖMwZ |  | t | 41.5% | [13 empty] | 46.19% |  |  |  | Total= | 299.89
| ** | cÖKí ïiæ ‡_‡K G ch©šÍ µgc~wÄZ Avw_©K AMÖMwZ |  | t | 39.44% | [8 empty] | -5812 |  |  |  |  | 25151.29
(‡gvt mwn`yj Bmjvg)
[8 empty] | 99 |  | -4 | [9 empty] | cÖKí cwiPvjK
(ms‡kvwaZ)
[5 empty] | 2.057% | [10 empty] | 48.25
46.19
2.06
Note on M23: Eaar Uddin: excess than dpp. Now rectified. 21-7-2018.
Note on P13: Eaar Uddin: total revenue minus off sal minus staff sal minus allowanc minus repair = supply and services
Note on P23: Eaar Uddin: excess than dpp. It would be reduced during RADP. 21-07-2018 at 06.11Pm. - now rectified reduced by 1275 lakh taka. 21-7-2018:06.18pm.
Note on P55: Eaar Uddin: data
Note on U54: Eaar Uddin: data
Note on U55: Eaar Uddin: data

## PR(P-5)
µq msµvšÍ Z_¨vejx t 2018-19 A_© eQ‡ii AMÖMwZ (wW‡m¤^i/2018Bs)
gš¿Yvjq/wefvM t ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq/ ¯’vbxq miKvi wefvM¦
(j¶ UvKvq)
µt bs | cÖK‡íi bvg | gvjvgvj |  |  |  |  | c~Z© |  |  |  |  | ‡mev |  |  |  |  | K) wmwW f¨vUmn µqLv‡Z †gvU eivÏ (2018-19) L) wmwW f¨vU |  | K) wmwW f¨vUmn µqLv‡Z †gvU e¨q L) wmwW f¨vU |  | µqLv‡Z Ae¨wqZ eivÏ (18-19) | †gvU GwWwc eivÏ | µqLv‡Z eivÏ †gvU GwWwc eiv‡Ïi %
|  | MZ A_©eQ‡i ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i /2018 mgqKv‡j cÖ`vbK…Z |  | Rvbyqvix/18 n‡Z Ryb/19 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_©eQ‡i ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i /2018 mgqKv‡j cÖ`vbK…Z |  | Rvbyqvix/18 n‡Z Ryb/19 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v | MZ A_©eQ‡i ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^ii /2018 mgqKv‡j cÖ`vbK…Z |  | Rvbyqvix /18 n‡Z Ryb/19 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`‡ki msL¨v
|  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2017-18 A_©eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2017-18 A_©eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq 2017-18 A_©eQi ch©šÍ cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 |  | 20 | 21 | 22
| ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦ | 33 | 3260.3298 |  | 0 | 3 | 102 | 70217.54 | 21 | 13617.625 | 3 | 12 | 14583.9923 | 0 | 0 | 0 | (K) | 46631 | (K) | 21535.75 | 25095.25 | 46744 | 99.76%
[17 empty] | (L) | 100 | (L) | 0 | 100
[10 empty] | 99 | -5
Note on J9: Eaar Uddin: -It is to be discussed with Mahfuz sir of which month we have to complete contract. 26.08.18 - Discussion has been done. It would be completed with in October. 27.08.18

## PR(P-6)
SCHEME STATUS REPORT
Project Title: “City Governance Project”.
Reporting Month : December /2018
(Taka in lakh)
Sl.No. | Name of project (Name of Development Assistance \Partner) | ADP Fund (GOB+RPA) |  |  | No. of Schemes/Contracts |  |  | Work-Plan Target |  | ACHIEVEMENT | [5 empty] | Physical Progress | Total fund Spent (GOB+PA) |  |  | Remarks
[5 empty] | New Schemes/Contracts | Carried over Contracts/ Excess of Previous year | Total | Last Date for awarding | Last Date for works Commen-cement | Schemes prepared | Schemes preparation under | Tender Called | Tender Evaluation Under | Works going on | Schemes Completed
[5 empty] | (No.) | (No.) | (No.) |  |  | (No.) | (No.) | (No.) | (No.) | (No.) | (No.) | (%)
1 | 2 | 3 |  |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  |  | 17
1 | “City Governance Project” (JICA) | 46744 |  |  | 24 | 54 | 78 | 15-11-2018 | 22-11-2018 | 0 | 1 | 0 | 2 | 45 | 30 | 48.25% | 21592.71
|  | 7616 | + | 36728 | 16: 3338.79 | + | 18253.92
[9 empty] | 99 | -6
Note on G11: Eaar Uddin: - My assamption is that carried over contract can not be upto last year. So I assumed as lampsum. 26-7-2018 - as of shakhawat shaheb report July 18, 48 packages 100% completed. So total contract package 102 minus complete 48 = 54 incompleted which are carried over. 27.08.2018

## PR(P-7)
2018-19 A_©eQ‡ii evwl©K Dbœqb Kg©m~wP‡Z eivÏ
cÖKí Iqvix gvwmK AMÖMwZ cÖwZ‡e`b
(K) gš¿Yvjq / wefvM t ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿bvjq/ ¯’vbxq miKvi wefvM¦
(L) ms¯’vi bvg t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
(M) cÖwZ‡e`b Kvj (gvm) t wW‡m¤^i/2018Bs¦
(j¶ UvKvq)
µt bst | †KvW I cÖK‡íi bvg (cÖKí e¨q) (ev¯Zevqb Kvj) (ms‡kvwaZ) | Aby‡gv`b ch©vq | GwWwcÕi c„ôv I µwgK bs | 2018-19 A_©eQ‡ii evwl©K Dbœqb Kg©m~wP‡Z eivÏ |  |  |  |  | Aegyw³ |  |  |  |  | e¨q |  |  |  |  | cÖKí mvnv‡h¨i UvKvsk |  | AMÖMwZ (%) |  |  |  | cÖK‡íi mvnv‡h¨i Drm | gšÍe¨
|  |  |  | †gvU | UvKv (wmwW f¨vU) |  | cÖKí mvnvh¨ |  | †gvU |  |  | cÖKí mvnvh¨ |  | †gvU |  |  | cÖKí mvnvh¨ |  |  |  | †fŠZ |  | Avw_©K
[7 empty] | †gvU | UvKvsk |  | UvKv (wmwW f¨vU) |  | †gvU | UvKvsk |  | UvKv (wmwW f¨vU) |  | †gvU | UvKvsk | `vexK…Z | cÖvwß | j¶gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK) | j¶gvÎv (ˆÎgvwmK) | AMÖMwZ (gvwmK)
1 | 2 | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
| 5118 ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí (2014-15 nB‡Z 2019-20) | Aby‡gvw`Z | 302 | 46744 | 7616 | 100 | 39128 | 36728 | 43035.985 | 3907.985 | 100 | 39128 | 36728 | 21592.71 | 21592.71 | 0 | 18253.92 | 17143.45 | 17134.89 | 17125.97 | 25% | 30.23% | 25% | 31.17% | RvBKv
99 | bar: 15

## 23 Colm Report (P-8)
2018-19 A_© eQ‡i ¯’vbxq miKvi wefv‡Mi AvIZvq AviGwWwcf~³ ev¯Íevqbvaxb cÖKímg~‡ni AMÖMwZi ch©v‡jvPbv QK - 1
gv‡mi bvg t wW‡m¤^i /2018Bs
ms¯’v t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦ | [22 empty] | (j¶ UvKvq)
µt bs | cÖK‡íi bvg (†gqv`Kvj) (ms‡kvwaZ) | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q | Ryb/2018 ch©šÍ µgc~wÄZ e¨q | Aby‡gvw`Z wWwcwc/ AviwWwcwcÕi Procurement Plan Abyhvqx c¨v‡KR msL¨v/cÖv°wjZ e¨q | Ryb/2018 ch©šÍ µgc~wÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | 2018-19 A_©erm‡i evwl©K Dbœqb Kg©m~Px | [11 empty] | K) µgcywÄZ c~bf©ib e¨q L) †gvU cybf©iY e¨q (18-19 GwWwc) M) †gvU cybf©iY `vex †ck (18-19 GwWwc) N) †gvU c~bf©iY cÖvwß (18-19 GwWwc) |  | cÖK‡íi ïiæ n‡Z ch©v‡jvPbaxb gvm ch©šÍ µgcywÄZ Avw_©K e¨q/AMÖMwZ | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ ‡fŠZ AMÖMwZ | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q Abyhvqx AeivÏK…Z UvKv | Ryb,2018 n‡Z cÖK‡íi Aewkó †gqv`Kvj | cÖKí mvnv‡h¨i Drm
[6 empty] | 2018-19 GwWwc eivÏ | 2018-19 AviGwWwc eivÏ | Kg© cwiKíbv |  |  |  |  | msMÖn cwiKíbv |  |  |  | ch©v‡jvPbvaxb gv‡m Kvh©v‡`k cÖ`vb Avw_©K I ˆfvZ j¶¨gvÎv ARx©Z bv nIqvi KviY
[8 empty] | ch©v‡jvPbvaxb gvm ch©šÍ A_© Aegyw³ | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨‡qi j¶¨gvÎv | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨q / AMÖMwZ | ch©v‡jvPbvaxb gvm ch©šÍ ‡fŠZ j¶¨gvÎv I AMÖMwZ |  | evwl©K msMÖn cwiKíbv Abyhvqx c¨v‡KR msL¨v/e¨vq | ch©v‡jvPbvaxb gvm ch©šÍ ‡UÛvi Avnev‡bi j¶¨gvÎv Abymv‡i c¨v‡KR msL¨v/e¨q | ch©v‡jvPbvaxb gvm ch©šÍ ‡UÛvi AvnevbK…Z c¨v‡KR msL¨v/e¨q | ch©v‡jvPbvaxb gvm ch©šÍ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | [8 empty] | y
|  | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | j¶gvÎv (%) | AMÖMwZ (%) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) | ‡gvU (cY¨) (c~Z© ) (†mev) |  |  |  | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) (%) | (%) | (‡gvU) (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | eQi / gvm
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22 | 23
88 | ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦ (RyjvB/2014 Bs n‡Z Ryb/2020 Bs) | 294300 | 89136.83 | 213 | 147 | 46744 | 0 | 43035.985 | 21592.71 | 21592.71 | 52.25% | 48.25% | 27 | 27 | 26 | 24 | - | K) | 79877.45 | 110729.54 | 41.5% | 158419.17 | 2eQi | RvBKv
|  | 54531 | 14210.83 | 292032.53 | 88061.8621 | 7616 | 0 | 92.07% | 46.19% | 46.19% |  |  | 41914 | 15232.49 | 15232.49 | 13617.625 |  |  |  | 39.44% |  | 32704.17
|  | 239769 | 74926 |  |  | 39128 | 0 | [10 empty] | L) | 17134.89 |  |  | 125715
|  | 227262 | 62734 | 67 | 33 | 36728 | 0 | 3907.985 | 3338.79 | 3338.79 |  |  | 3 | 3 | 3 | 3 |  |  |  | 17549.62 |  | 127800
|  |  |  | 7605.59 | 3260.3298 |  |  | 51.31% | 43.84% | 43.84% |  |  | 155 | 0 | 0 | 0 |  | M) | 17134.89 | 32.18%
|  |  |  | 134 | 102 |  |  | 39128 | 18253.92 | 18253.92 |  |  | 24 | 24 | 23 | 21 |  | N) | 17125.97 | 93179.92
|  |  |  | 197911.11 | 70217.54 |  |  | 100% | 46.65% | 46.65% |  |  | 41759 | 15232.49 | 15232.49 | 13617.625 |  |  |  | 38.86%
|  |  |  | 12 | 12 |  |  | 36728 | 17143.45 | 17143.45 |  |  | 0 | 0 | [5 empty] | 79877.45
|  |  |  | 86515.83 | 14583.9923 |  |  | 100% | 46.68% | 46.68% |  |  | 0 | 0 | 0 | 0 |  |  |  | 35.15%
[9 empty] | 99 | -8
|  |  | 2008-09 | 45
|  |  | 2009-10 | 111
|  |  | Total = | 156 | 88061.8621 | [8 empty] | #VALUE!
[15 empty] | 0 | 0
#VALUE!
[5 empty] | 3100 | [9 empty] | 1075.25
c~b
70
88131.8621
[5 empty] | 16 | 339
[5 empty] | 260 | 5941
[5 empty] | 342 | 6041
[5 empty] | 195 | 3385.5
[5 empty] | 813 | 15706.5

## PIB(1)
wc, AvB, we 01/76 (ms‡kvwaZ)
ÓcÖwZ‡e`b QKÓ
cÖ_g LÛ t mvavib Z_¨vejx I Avw_©K weeibx¦
1¦ | mvaviY Z_¨vejx
| K) cÖwZ‡e`b Kvj | t | wW‡m¤^i /2018Bs
| L) cÖKí wk‡ivbvg | t | ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦
| M) cÖKí Ae¯’vb | t | 5wU wmwU K‡c©v‡ikb h_vt- bvivqYMÄ, MvRxcyi, Kzwgjøøv, PÆMÖvg I iscyi¦
| N) PjwZ evwl©K Dbœqb Kg©m~Px‡Z | t | AšÍf©~³
| O) wbe©vnx ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
| P) gš¿Yvjq | t | ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq/¯’vbxq miKvi wefvM
| Q) Aby‡gv`b w¯’wZ | t | cÖ‡hvR¨ †Lv‡c (√) wPý w`b
|  |  | Aby‡gvw`Z | √ | Abby‡gvw`Z | ms‡kvwaZ AbAbygvw`Z
| R) Aby‡gv`‡bi ZvwiL | t | A) g~j t 15/07/2014Bs Zvwi‡Li GK‡bK mfvq Aby‡gvw`Z¦ |  |  | Av) ms‡kvwaZ t cÖ‡hvR¨ b‡n¦
| S) ev¯Íevqb Avi‡¤¢i ZvwiL | t | RyjvB/ 2014
| T) mgvwßi ZvwiL | t | Ryb / 2020
| U) cÖKí e¨q (j¶ UvKvq) | t | A) g~j t 294300.00 j¶ UvKv |  | Av) ms‡kvwaZ t cÖ‡hvR¨ b‡n¦
|  |  |  | 99 | -9

## PIB(2)
2¦ Avw_©K weeibx eivÏ Aegyw³, Avq/e¨q (j¶ UvKvq)
K) | eivÏ t
µwgK bs | weeiYx | ‡gvU | UvKv | g~jab | ivR¯^ | ‰e‡`wkK gy`ªv
[6 empty] | ‡gvU | cÖKí mvnvh¨ |  | Ab¨vb¨ | e¨e¯’vK…Z
[7 empty] | ‡gvU | UvKvsk |  | cÖKí mvnvh¨ | Ab¨vb¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A) | PjwZ Avw_©K erm‡ii GwWwc eivÏ | 46744 | 7616 | 42064 | 4680 | 39128 | 39128 | 36728 | - | - | - | 42392.83
Av) | PjwZ Avw_©K ermi ch©šÍ µgcywÄZ eivÏ | 89136.83 | 14210.83 | 69515 | 19622.1876 | 74926 | 74926 | 62734 | - | - | -
(L) | Aegyw³ t
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A) | eZ©gvb Avw_©K eQ‡i cÖwZ‡e`b Kvj ch©šÍ cÖkvmwbK gš¿Yvjq KZ©„K Aegyw³ | 43035.985 | 3907.985 | 37118.7985 | 5917.1865 | 39128 | 39128 | 36728 | - | - | -
Av) | c~e©eZ©x A_© eQ‡i Aegyw³ †_‡K D×„Z | - | - | - | - | - | - | - | - | - | -
B) | eZ©gvb Avw_©K eQ‡i cÖwZ‡e`b Kvj ch©šÍ †gvU jf¨ A‡_©i cwigvb (A+Av) | 43035.985 | 3907.985 | 37118.7985 | 5917.1865 | 39128 | 39128 | 36728 | 0 | 0 | 0
C) | cÖwZ‡e`b Kvj ch©šÍ cÖkvmwbK gš¿Yvjq KZ©„K µgcywÄZ Aegyw³ | 132172.815 | 18118.815 | 101273.8815 | 30898.9335 | 114054 | 114054 | 99462 | 0 | 0 | 0
|  |  |  | 99 | -10
Note on E11: Eaar Uddin: There is some problem for formula, how is this formul can used. Since sayedul shaheb use and kept it. So I kept it . 27-05-2018
Note on F11: Eaar Uddin: There is some problem for formula, how is this formul can used. Since sayedul shaheb use and kept it. So I kept it . 27-05-2018

## PIB(3)
M) | e¨q t
µwgK bs | weeiY | ‡gvU | UvKv | g~jab | ivR¯^ | ‰e‡`wkK gy`ªv
[6 empty] | ‡gvU | cÖKí mvnvh¨ |  | Ab¨vb¨ | e¨e¯’vK…Z
[7 empty] | ‡gvU | UvKvsk |  | cÖKí mvnvh¨ | Ab¨vb¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A) | cÖwZ‡e`b Kvjxb e¨q
| 1¦ AvmevecÎ I hš¿cvwZ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | -
| 2¦ `vjvb I BgviZ (c~Z©KvR) | 18253.92 | 0 | 18253.92 | 0 | 18253.92 | 18253.92 | 17143.45 | - | - | - | 51.69
| 3¦ ms¯’vcb | 70.66 | 70.66 | 0 | 70.66 | 0 | 0 | 0 | - | - | - | 2039.24
| 4¦ Rixc I AbymÜvb | 0 | 0 | 0 |  | 0 | 0 | 0 | - | - | -
| 5¦ Ab¨vb¨ (mieivn †mev/ KbmvjU¨v›U) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 509.54
| 6¦ m`i Dcwi e¨q | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | -
| 7¦ ‡gvU (1 †_‡K 6) | 18324.58 | 70.66 | 18253.92 | 70.66 | 18253.92 | 18253.92 | 17143.45 | - | - | - | 1110.47
Av) | eZ©gvb Avw_©K eQ‡i †gvU e¨q | 18324.58 | 70.66 | 18253.92 | 70.66 | 18253.92 | 18253.92 | 17143.45 | - | - | - | 19038.02
B) | cÖwZ‡e`b Kvj ch©šÍ µgcywÄZ e¨q | 110729.53 | 18118.815 | 95716.68 | 15012.85 | 93179.92 | 93179.92 | 79877.45 | - | - | - | 9293.41
C) | AsMxKviK…Z e¨q (hv cÖwZ‡e`b Kvj ch©šÍ cwi‡kva Kiv nqwb) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | 509.54
N) | Avq (†h mKj cÖK‡íi †Kvb Avq †bB †m mKj cÖK‡íi †¶‡Î GB Aby‡gv`‡bi wecix‡Z Òïb¨Ó wj‡L c~iY Kwi‡Z nB‡e)
A) | cÖwZ‡e`b Kv‡j cÖKí †_‡K Avq t | k~b¨
Av) | eZ©gvb Avw_©K eQ‡i cÖwZ‡e`b Kvj ch©šÍ †gvU Avq t | k~b¨
B) | cÖwZ‡e`b Kvj ch©šÍ cÖK‡íi µgcywÄZ Avq t | k~b¨
cÖKí cwiPvjK/e¨e¯’vcK Gi ¯^v¶i
bvg
c`ex
2¦ | cÖkvmwbK gš¿Yvj‡qi gšÍe¨ t
Avcwb wK 2 (L) Aby‡”Q‡` I cÖ`Ë A_© Aegyw³ msµvšÍ Z_¨vejxi mv‡_ GKgZ (cÖ‡hvR¨ †Lv‡c wPý w`b) nu¨v/bv¦
( n¨vu ) cÖ‡qvRb‡ev‡a mg AvKv‡ii AwZwi³ KvMR e¨envi Kiæb¦
gš¿bvjq cwiKíbv /ev¯Íevqb †Kvm©
cÖav‡bi ¯^v¶i
bvg
|  |  |  | 99 | -11 |  | c`ex

## Aid & Dis.
Information of Project Aid & Disbursement Status
For the Year 2018-2019
| Administrative Ministry | Name of the Ministry / Division : LGRD & Co-operatives / LGD.
| Reporting Agency | Local Government Engineering Department (LGED) | [10 empty] | (Tk. In Lac)
| Reporting Period: | 2018-12-01 | [10 empty] | (Others in million)
Sl No. | Name of the Project | Project Aid | [13 empty] | Remarks
|  | As per DPP |  |  | As per Agreement |  |  | Disbursed Amount
[8 empty] | In Original Currency |  |  |  | In US$ |  | In Tk.
|  | In Original Currency | In US$ | In Tk. | In Original Currency | In US$ | In Tk. | Up to December/18 |  | Current Years |  | Up to December/18 | Current Years | Up to December/18 | Current Years
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | 10 |  | 11 | 12 | 13 | 14 | 15
80 | City Governance Project (CGP) | ¥ 30690.432 | 308.1864 | 239769 | ¥ 30690 | 308.1864 | 239769 | ¥ | 13206.1127 | ¥ | 119.8866 | 118.9436 | 1.0547 | 94039.16 | 865.04
** | 1 BDT = 1.28 ¥
*** | 1 US$ = 77.8 BDT
[6 empty] | 99 | -12

## Monthly Dis.
MONTHLY DISBURSEMENT OF FOREIGN AID (FY 2018-2019)
Proforma No-1
Administrative Ministry |  | : | Name of the Ministry / Division : LGRD & Co-operatives / LGD. |  |  |  | Prepared by Project Director
Reporting Agency |  | : | Local Government Engineering Department (LGED) |  |  |  | City Governance Project(CGP)
Reporting Period |  | : | 2018-12-01 |  |  |  | Telephone No : 9131340
( Figures in Million ¥ )
Name of the Project | Name of Donor | Loan or Grant | Loan or Grant No. Date of agreement | Amount of allocation | Opening pipeline as on 1-7-2018 (Allocation minus disbursement up to 30-06-2017) | Fresh commitment allocation during the reporting period | Total available period | Amount disbursed during the reporting period | Closing pipeline
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 (6+7) | 9 | 10 (8-9)
City Governance Project(CGP) | JICA | LOAN | Loan no-JICA Loan Agrement BD-P79 16.06.2014 | 30690 | 17603.49 | 0 | 17603.49 | 119.8866 | 17483.6034
[5 empty] | 99 | -13

## RPA
¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq
cÖKí mvnvh¨ cybf©i‡Yi gvwmK cÖwZ‡e`b
A_© eQi-2018-19
AviwcG Gi cybf©i‡bi AMÖMwZ cÖwZ‡e`b weeiYx t
gš¿Yvjq/wefv‡Mi bvg |  | t ¯’vbxq miKvi, cjøx Dbœqb I mgevq gš¿Yvjq
cÖwZ‡e`b Kvj |  | wW‡m¤^i /2018Bs
ev¯ÍevqbKvix KZ©„c‡¶i bvg |  | t ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦
j¶ UvKvq
cÖK‡íi bvg I `vZv ms¯’vi bvg (ev¯Íevqb Kvj) | cÖK‡íi ïiæi ermi †_‡K eZ©gvb A_© ermi ch©šÍ †gvU AviwcG eiv‡Ïi cwigvb | cÖK‡íi ïiy †_‡K PjwZ gvmch©šÍ AviwcG Lv‡Z cÖK…Z e¨q | PjwZ gvm ch©šÍ cybf©i‡Yi `vex †c‡ki cwigvY | `vexi wecix‡Z cybf©i‡bi cwigvb | `vexi †c‡ki A‡c¶vq Av‡Q Gi cwigvb (3-4) | `vexi A‡_©i g‡a¨ cybf©i‡bi A‡c¶vq Av‡Q Gi cwigvb (4-5) | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
ÒwmwU Mfvib¨vÝ cÖ‡R±Ó kxl©K cÖÖKí¦ (RyjvB/2014 Bs n‡Z Ryb/2020 Bs) | 62734 | 79877.45 | 79871 | 79862.06 | 6.45 | 8.94
|  | 99 | -14

## IMED. M(P-1)
Progress Report of Ongoing Development Project Operational Plan
(Format 05)
(All financial figures in lakh Tk).
Reporting Period : |  | 2018-12-01
Part-A : Monthly Report.
Name of the Ministry/Division/Organization t |  |  |  | t | Ministry of Local Government Rural Development & Co-operatives (LGRD & C) / Local Government Division (LGD) / Local Government Engineering Department (LGED)
1 | Name of the Project/Operational Plan |  |  | t | “City Governance Project”.
2 | Objectives of the Project/Operational Plan (in Brief) |  |  | t | i) | To improve the public services in the target five (5) City Corporations (CC).
[5 empty] | ii) | To strengthen the city governments’ administrative capacity and their governance improvement through ICGIAP.
[5 empty] | iii) | To promote living environment and quality of life through IDPCC.
[5 empty] | iv) | To create economic opportunities for CC’s to ensure the progressive revenue and economic growth by providing infrastructures in different sectors in the target City Corporations.
3 | Location of the Project/Operational Plan |  |  | t | The Project area covers 5 City Corporations namely Nayangonj, Comilla, Cittagong, Gazipur & Rangpur City Corporation.
4 | Project Approval Status & Cost
| DPP/TPP | Date of Approval | Implementation period |  |  | Total Cost | GOB | Project Aid (RPA)
| 1 | 2 | 3 |  |  | 4 | 5 | 6
| 1. Original | 16-07-2014 | July/14 - June/20 |  |  | 294300 | 54531 | 239769
227262
2. Revised
5 | Progress of Fund Release
| Quarter-wise | Proposal Sending to Ministry/Division | Issue of order by Ministry |  |  | Issue of order from Finance Division | Amount Released | Date of issue of Chaque from CAO (in case of Autonomous body)
| 1 | 2 | 3 |  |  | 4 | 5 | 6
| 1st quarter | 2018-08-14 | 2018-09-04 |  |  | 2018-09-11 | 40632.375 | -
| 2nd quarter | 2017-10-18 | 13-11-2017 |  |  |  | 2403.61
| 3rd quarter | 2018-08-01 | 2018-06-02 |  |  |  | 0 | -
| 4th quarter | 2018-04-02 | 2018-05-27 |  |  | 2018-05-06 | 0 | -
| Total= | [5 empty] | 43035.985
|  | 99 | -15
Note on C33: Eaar Uddin: data
Note on C34: Eaar Uddin: data
Note on C35: Eaar Uddin: data
Note on C36: Eaar Uddin: data
Note on D33: Eaar Uddin: data
Note on D34: Eaar Uddin: data
Note on D35: Eaar Uddin: data
Note on D36: Eaar Uddin:
Note on G33: Eaar Uddin: data
Note on G34: Eaar Uddin: data
Note on G35: Eaar Uddin: data
Note on G36: Eaar Uddin: data

## IMED M(P-2)
6. Target and Achievement of the main Components of the Project :
Name of Important Components (With quantity) | Cost as per DPP/TPP | Achievement up to last June |  | Target of current year |  | Progress up to the reporting month of current year |  | Unspent/unfinished balance against DPP targets
|  | Financial | Physical | Financial | Physical | Financial | Physical | Financial | Physical
|  | a) Total b) Taka | (% of the component) | a) Total b) Taka | (% of the component) | a) Total b) Taka | (% of the component) | a) Total b) Taka 2-(3+7) | (% of the component)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Revenue
1) Pay & Allowances
a) Pay of Officers | 748.85 | 136.8153 | 18.27% | 50 | 6.677% | 29.29 | 50% | 582.7447 | 77.82%
b) Pay of Establishment | 250.48 | 30.921 | 12.34% | 10 | 3.992% | 3.38 | 50% | 216.179 | 86.31%
c) Allowances | 1238.13 | 133.0401 | 10.75% | 53 | 4.281% | 24.29 | 50% | 1080.7999 | 87.29%
Sub-Total= (1a-c) | 2237.46 | 300.7764 |  | 113 |  | 56.96 |  | 1879.7236
2) Supply & Services
a) Supply (Stationary & others) | 38218.07 | 14583.9923 | 38.16% | 4529 | 11.85% | 1788.3 | 39.49% | 21845.7777 | 57.16%
Sub total(2a) | 38218.07 | 14583.9923 |  | 4529 |  | 1788.3 |  | 21845.7777
3) Repair, Maintenance & Rehabilitation
a) Vehicles & Equipment | 424 | 56.9189 | 13.42% | 38 | 8.962% | 13.7 | 36.05% | 353.3811 | 83.34%
Sub total(3a) | 424 | 56.9189 |  | 38 |  | 13.7 |  | 353.3811
4) Block Allocation | 40 | 0.5 | 1.25% | 1e-65 | 2.5e-65% | 0 | 0% | 39.5 | 98.75%
Sub total(4a) | 40 | 0.5 | 1.25% | 1e-65 | 2.5e-65% | 0 |  | 39.5 | 98.75%
Sub total (Revenue)= | 40919.53 | 14942.1876 |  | 4680 |  | 1858.96 |  | 24118.3824
Capital
5) Acquisition of Assets
a) Acquisition of Assets | 6064.74 | 3260.3298 | 53.76% | 155 | 2.556% | 0 | 0% | 2804.4102 | 46.24%
Sub total(5a) | 6064.74 | 3260.3298 |  | 155 |  | 0 |  | 2804.4102
6) Acquisition of Land (269.40ha) | 1374.01 | 0 | 0% | 1e-31 | 7.278e-33% | 0 | 0% | 1374.01 | 100%
Sub total(6) | 1374.01 | 0 |  | 1e-31 |  | 0 |  | 1374.01
Physical Works
7) Upgrading of Union Roads
a) Office Building (School cum Cyclone shelter) | 11445.4749 | 3635.21 | 31.76% | 7810 | 68.24% | 4476.26 | 60% | 3334.0049 | 29.13%
b) Office Building (Community Resource Centre) | 1027.931 | 0 | 0% | 0 | 0% | 0 | 0% | 1027.931 | 100%
c) Urban transport/Roads | 82666.467 | 31228.15 | 37.78% | 15563 | 18.83% | 5620.82 | 41.44% | 45817.497 | 55.42%
d) Urban transport/ bridges/overpass | 26046.7039 | 8110.22 | 31.14% | 9196 | 35.31% | 4185.39 | 45.38% | 13751.0939 | 52.79%
e) Drainage Structures/ Drain/Canal/Khal | 51886.0335 | 23179.37 | 44.67% | 8045 | 15.51% | 3820.87 | 46.67% | 24885.7935 | 47.96%
f) Sanitation & Water Supply/ Pipeline/ overhead tank | 11774.3017 | 0 | 0% | 615 | 5.223% | 358.86 | 58.33% | 11415.4417 | 96.95%
g) Sinking/Installation of Tubewell | 1653.6313 | 0 | 0% | 0 | 0% | 0 | 0% | 1653.6313 | 100%
h) Electrical Installation | 9735.1955 | 3489.59 | 35.85% | 230 | 2.363% | 113.32 | 49.24% | 6132.2855 | 62.99%
i) Others Municipal Services/ Basic services for urban poor(footpath/ drain/latrine/streetlight/tubewell | 1675.9777 | 575 | 34.31% | 300 | 17.9% | 1133.23 | 377.7% | -32.2523 | -1.924%
Sub total(8a-h) | 197911.7165 | 70217.54 |  | 41759 |  | 19708.75 |  | 107985.4265
8) Other Loan
a) Micro credit operation | 500 | 350 | 70% | 50 | 10% | 25 | 50% | 125 | 25%
Sub total(5a) | 500 | 350 |  | 50 |  | 25 |  | 125
|  |  | 99 | -16
9) Development Import Duty and VAT
a) Development Import Duty and CD/VAT | 1520 | 366.77 | 24.13% | 100 | 6.579% | 0 | 0% | 1153.23 | 75.87%
b) Miscellaneous Capital Expenditure(IDC) | 100 | 0 | 0% | 0 | 0% | 0 | 0% | 100 | 100%
Sub total(9a-b) | 1620 | 366.77 |  | 100 |  | 0 |  | 1253.23
10) Contingency
a) Price Escalation/Contingency | 24590 | 0 | 0% | 0 | 0% | 0 | 0% | 24590 | 100%
b) Physical Contingency | 21320 | 0 | 0% | 0 | 0% | 0 | 0% | 21320 | 100%
Sub total(10a) | 45910 | 0 |  | 0 |  | 0 |  | 45910
Sub total (Capital)= | 253380.4665 | 74194.6398 |  | 42064 |  | 19733.75 |  | 159452.0767
Grand Total= | 294299.9965 | 89136.8274 | 33.09% | 46744 | 17.44% | 21592.71 | 48.25% | 183570.4591
7. Progress of Procurement in Current FY: 2018-19
|  |  |  | Goods | Works | Services | Total
a) Work Order (WO) issued in last year or before
I. Number of WOs. |  |  |  | 33 | 102 | 12 | 147
II. Expenditure |  |  |  | 3260.3298 | 70217.54 | 14583.9923 | 88061.8621
b) Work Orders (WO) issued during the reporting Period, 2018-19
I. Number of WOs. |  |  |  | 0 | 21 | 0 | 21
II. Expenditure in current FY. |  |  |  | 0 | 13617.625 | 0 | 13617.625
C) WOs to be issued during the rest period of the FY. |  |  |  | 3 | 3 | 0 | 6
d) Total expenditure for procurement up to reporting month, 2018-19 (a ii + b ii). |  |  |  | 3260.3298 | 83835.165 | 14583.9923 | 101679.4871
e) Total budget/allocation for Procurement,2018-19 |  |  |  | 155 | 41759 | 0 | 41914
f) Cumulative expenditure up to last year. |  |  |  | 3260.3298 | 70217.54 | 0 | 73477.8698
g) Total allocation as per DPP/TPP |  |  |  | 7605.59 | 197911.11 | 86515.83 | 292032.53
h) Unspent amount as per DPP/TPP. |  |  |  | 4345.2602 | 114075.945 | 71931.8377 | 190353.0429
8. Particulars of reimbursement claim and receipts:
| Initial advance Receipt with date | Up to 30/06/2015 |  |  | During 2015-16
|  | Expenditure |  | Reimbursement claimed | Expenditure |  | Reimbursement claimed
|  | Direct payment | payment from project account |  | Direct payment | payment from project account
| 1 | 2 | 3 | 4 | 5 | 6 | 7
| 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 99 | -17

## IMED-Q(1)
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003(Revised) (Page 1 of 4)
(Quarterly Progress Report)
ADP: FY 2018- 2019, Reporting Quarter : 1st Quarter (October-December/2018)
A. Quarterly Financial Progress Report
Code
A.1. | a) Project Title: | “City Governance Project”. |  |  |  |  | 3731 | 5118
b) Ministry: Ministry of Local Government Rural Development & Co-operatives (LGRD & C) / Local Government Division (LGD) / Local Government Engineering Department (LGED)
c) Division: Local Government Division (LGD).
d) Agency Name : Local Government Engineering Department (LGED)
A.2. | Quaterly Financial Progress :
130.701
Head |  | Release for the Quarter |  | Expenditure for the Quarter |  | Current Year Expenditure |  |  |  | 1200
|  | GOB | RPA | GOB | RPA | GOB | RPA | DPA |  | 107.01
Revenue |  | 764.86 | 0 | 540.47 | 27.81 | 705.04 | 43.45 | 1110.47
Capital |  | 1638.75 | 0 | 1361.25 | 12080 | 2633.75 | 17100 | 0 |  | =
Grand Total |  | 2403.61 | 0 | 1901.72 | 12107.81 | 3338.79 | 17143.45 | 1110.47
580
565
Cash Foreign Exchange Spent |  |  | Spent from Own Resources |  | CD/VAT | [5 empty] | 1289.25
|  |  | Cash | Kind
N/A
RPA Spent (Cumulative to Date) |  |  | RPA Claimed |  | RPA Reimbusrsef
|  |  | Reporting Quarter | Cumulative to Date | Reporting Quarter | Cumulative to Date
N/A
|  |  | 99 | -18
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003(Revised) (Page 1 of 4)
(Quarterly Progress Report)
ADP: FY 2007- 2008, Reporting Quarter : April - June / 2009
A. Quarterly Financial Progress Report
Code
A.1. | a) Project Title: | “Union Road & Other Infrastructure Development Project : Greater Jessore & Kushtia District ”. |  |  |  |  | 5085 | 2008-09
| b) Ministry: Local Government Rural Development & Co-operatives.(LGED & C) | [5 empty] | 3700 | 2008-09
| c) Division: Local Government Division (LGD). | [5 empty] | 3700 | 2008-09
| d) Agency Name : Local Government Engineering Department (LGED) | [5 empty] | 3731 | 2008-09
A.2. | Quaterly Financial Progress :
Head |  | Release for the Quarter |  | Expenditure for the Quarter |  | Current Year Expenditure
|  | GOB | RPA | GOB | RPA | GOB | RPA | DPA
Revenue |  | 10 | 0 | 9.66 | 0 | 9.66 | 0 | 0
Capital |  | 390 | 0 | 390 | 0 | 390 | 0 | 0
Grand Total |  | 400 | 0 | 399.66 | 0 | 399.66 | 0 | 0
Cash Foreign Exchange Spent |  |  | Spent from Own Resources |  | CD/VAT
|  |  | Cash | Kind
N/A
RPA Spent (Cumulative to Date) |  |  | RPA Claimed |  | RPA Reimbusrsef
|  |  | Reporting Quarter | Cumulative to Date | Reporting Quarter | Cumulative to Date
N/A
45(1)
Note on C22: Eaar Uddin: data from ADP Allotment Register (GOB)
Note on E22: Eaar Uddin: Data from adp accounts register
Note on F22: Eaar Uddin: data from adp accounts register
Note on G22: Eaar Uddin: Data from ADP Accounts Register
Note on H22: Eaar Uddin: Data from ADP Accounts Register
Note on I22: Eaar Uddin: Data from ADP Accounts Register

## IMED-Q(2)
Project Monitoring Form: IMED 03/2003(Revised) (Page 2 of 4)
(Quarterly Progress Report)
ADP: FY 2018- 2019, Reporting Quarter : 1st Quarter (October-December/2018)
B. Quarterly Component-wise Progress
Code
B.1. | Project Title: “City Governance Project”. | [9 empty] | 3731 | 5118
B.2. | Quarterly Component-wise Progress
(In lakh Taka)
Sl. No. | Name of the Component | Unit | Cumulative Progress up to Last June |  |  | Yearly Target |  |  | Progress in Current Quarter |  |  | Current Year's Progress
|  |  | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial | Physical |  | Financial
|  |  | Qtty. | % |  | Qtty. | % |  | Qtty. | % |  | Qtty. | %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 1) Pay & Allowances
| a) Pay of Officers | 2376 MM | 0.15614 | 0.0347% | 136.8153 | 120 MM | 6.677% | 50 | 30 MM | 12.5% | 14.645 | 60 | 50% | 29.29
| b) Pay of Establishment | 1368 MM | 140 | 31.11% | 30.921 | 36 MM | 3.992% | 10 | 9 MM | 12.5% | 1.69 | 18 | 50% | 3.38
| c) Allowances | 3744 MM | 0.10234 | 0.02274% | 133.0401 | 156 MM | 4.281% | 53 | 39 MM | 12.5% | 12.145 | 78 | 50% | 24.29
| Sub-Total= (1a-c) |  |  |  | 300.7764 |  |  |  |  | 0% | 28.48 |  | 0% | 56.96
2 | 2) Supply & Services
| a) Supply (Stationary & others) |  | 0 | 0% | 14583.9923 |  | 11.85% | 4529 |  | 9.871% | 894.15 |  | 39.49% | 1788.3
| Sub total(2a) |  |  |  | 14583.9923 |  | 0% | 4529 |  | 0% | 894.15 |  | 0% | 1788.3
3 | 3) Repair, Maintenance & Rehabilitation
| a) Vehicles & Equipment |  | 0.13424 | 0.02983% | 56.9189 |  | 8.962% | 38 |  | 9.013% | 6.85 |  | 36.05% | 13.7
| Sub total(3a) |  |  |  | 56.9189 |  | 0% | 38 |  | 0% | 6.85 |  | 0% | 13.7
4 | 4) Block Allocation
| Sub total(4a) |  | 0.53759 | 0.1195% | 0.5 |  | 2.5e-65% | 1e-65 |  | 0% | 0 |  | 0% | 0
| Sub total (Revinue)= |  | 0 | 0% | 14942.1876 |  | 0% | 4680 |  | 0% | 929.48 |  | 0% | 1858.96
Capital
5 | 5) Acquisition of Assets
| a) Acquisition of Assets |  |  |  | 3260.3298 |  | 2.556% | 155 |  | 0% | 0 |  | 0% | 0
| Sub total(5a) |  |  |  | 3260.3298 |  | 0% | 155 |  | 0% | 0 |  | 0% | 0
6 | 6) Acquisition of Land (269.40ha) |  | 0 | 0% | 0 |  | 7.278e-33% | 1e-31 |  | 0% | 0 |  | 0% | 0
| Sub total(6) |  | 0 | 0 | 0 |  | 0% | 1e-31 |  | 0% | 0 |  | 0% | 0
Physical Works
7 | 7) Upgrading of Union Roads
| a) Office Building (School cum Cyclone shelter) | 8 nos. | 3 | 53.76% | 3635.21 | 0 nos. | 68.24% | 7810 | 8 nos. | 15% | 2238.13 | 0 nos. | 60% | 4476.26
| b) Office Building (Community Resource Centre) | 10 nos. | 0 | 0% | 0 | 0 nos. | 0% | 0 | 10 nos. | 0% | 0 | 0 nos. | 0% | 0
| c) Urban transport/Roads | 589 km | 226.5 | 38.46% | 31228.15 | 6.06km | 18.83% | 15563 | 589 km | 10.36% | 2810.41 | 46 | 41.44% | 5620.82
| d) Urban transport/ bridges/overpass | 15 nos. | 320 | 45.33% | 8110.22 | 0.11 nos. | 35.31% | 9196 | 15 nos. | 11.35% | 2092.695 | 113 | 45.38% | 4185.39
| e) Drainage Structures/ Drain/Canal/Khal | 99 km | 45 | 45.45% | 23179.37 | 1.34 km | 15.51% | 8045 | 99 km | 11.67% | 1910.435 | 7 | 46.67% | 3820.87
| f) Sanitation & Water Supply/ Pipeline/ overhead tank | 237 km | 0 | 0% | 0 | 0 km | 5.223% | 615 | 237 km | 14.58% | 179.43 | 7 | 58.33% | 358.86
| g) Sinking/Installation of Tubewell | 57 nos. | 0 | 0% | 0 | 0 nos. | 0% | 0 | 57 nos. | 0% | 0 | 0 | 0% | 0
| h) Electrical Installation | 10170nos. | 4011 | 35.91% | 3489.59 | 465nos. | 2.363% | 230 | 10170nos. | 12.31% | 56.66 | 130 | 49.24% | 113.32
| i) Others Municipal Services/ Basic services for urban poor(footpath/ drain/latrine/streetlight/tubewell |  | 0 | 34.31% | 575 |  | 17.9% | 300 |  | 94.44% | 566.615 | 0 | 377.7% | 1133.23
| Sub total(8a-h) |  |  |  | 70217.54 |  | 0% | 41759 |  | 0% | 9854.375 |  | 0% | 19708.75
8 | 8) Other Loan
| a) Micro credit operation |  | 0 | 0% | 350 |  | 10% | 50 |  | 12.5% | 0 |  | 50% | 25
| Sub total(5a) |  |  |  | 350 |  | 0% | 50 |  | 0% | 0 |  | 0% | 25
9 | 9) Development Import Duty and VAT
| a) Development Import Duty and CD/VAT |  | 0 | 0% | 366.77 |  | 6.579% | 100 |  | 0% | 0 |  | 0% | 0
| b) Miscellaneous Capital Expenditure(IDC) |  | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0
| Sub total(9a-b) |  |  |  | 366.77 |  | 0% | 100 |  | 0% | 0 |  | 0% | 0
10 | 10) Contingency
| a) Price Escalation/Contingency |  | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0
| b) Physical Contingency |  | 0 | 0% | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0
| Sub total(10a) |  |  |  | 0 |  | 0% | 0 |  | 0% | 0 |  | 0% | 0
| Sub total (Capital)= |  |  |  | 74194.6398 |  | 0% | 42064 |  | 0% | 9854.375 | 74.06 | 0% | 19733.75
| Grand Total= |  | 0 | 0% | 89136.8274 |  | 17.44% | 46744 |  | 48.25% | 10783.855 | 98.44 | 48.25% | 21592.71
[5 empty] | 99 | -19
Note on L15: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.
Note on L16: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.
Note on L17: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.
Note on L20: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.
Note on L23: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.
Note on L27: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.
Note on L31: Eaar Uddin: one qrt so divided by 1, for 2 qrt then divided by 2.

## IMED-Q(3)
Project Monitoring Form: IMED 03/2003 (Revised) (Page 3 of 4)
(Quarterly Progress Report)
ADP: FY 2018- 2019, Reporting Quarter : 1st Quarter (October-December/2018)
C. Implementation Problems & Suggested Measures
Code
C.1. | Project Title: | “City Governance Project”. | [6 empty] | 3731 | 5118
C.2. | Implementation Problems : Nil.
| Problem Number | Problem Type |  |  | Description of Problem
| 1 | Approval Process
| 2 | Procurement
| 3 | Management
| 4 | Fund Allocation/Release
| 5 | Manpower Recruitment
| 6 | Oters (Specify)
C.3. | Suggested Measures: (In brief & specific)
| Problem Number | Measures Suggested
1
2
3
4
5
6
Others
None
C.4. | Is the project declared completed | [6 empty] | Yes | No
| Project Director/ | [6 empty] | Head of the Agency/
| Authorized Signature | [6 empty] | Authorized Signature
| Date | [6 empty] | Date
Secretary/Head of Planning Wing/Branch
Authorized Signature
Date
[6 empty] | 99 | -20
√

## IMED-Q(4)
Government of the People’s Republic of Bangladesh
Ministry of Planning
Implementation Monitoring and Evaluation Division
Project Monitoring Form: IMED 03/2003(Revised) (Page 4 of 4)
(Quarterly Progress Report)
ADP: FY 2018- 2019, Reporting Quarter : 1st Quarter (October-December/2018)
D. Contract Implemention Report
(Please fill-in this form for goods and works contract of value above Tk.200.00 lakh and consultancy contract of value above Tk. 100.00 lakh)
Code
D.1. | Project Title: | “City Governance Project”. | [6 empty] | 3731 | 5118
D.2. | Contract Implemention |  |  | Not Applicable
| Description of contracts (as per tender document) |  |  | Contract value | Date of work order/contract agreement |  | Completion date as per contract |  | Progress
[9 empty] | Amount paid | Physical (%)
D.3. | Problems/Reasons for Delay in Contract Implementation (if any) :
| Sl. No. | Description
| 1 | Annual Budget Allocation is insufficient as per DPP
| Project Director/ | [6 empty] | Head of the Agency/
| Authorized Signature | [6 empty] | Authorized Signature
| Date | [7 empty] | Date
Secretary/Head of Planning Wing/Branch
Authorized Signature
Date
[6 empty] | 99 | -21

## Work Plan
¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
evwl©K Kg© cwiKíbv (Work Plan) QK (2018-2019)
cÖK‡íi bvg t ÒwmwU Mfvi‡bÝ cÖ‡R±Ó
†gqv` Kvj t RyjvB/2014 Bs n‡Z Ryb/2020 Bs
cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q (j¶ UvKvq) t |  |  |  |  | †gvUt | 294300 |  |  | wRIwet | 54531 |  |  | cÖKí mvnvh¨ t |  | 239769
Ryb 2018 ch©šÍ µgcywÄZ e¨q (j¶ UvKvq) t |  |  |  |  | †gvUt | 89136.82 |  |  | wRIwet | 14210.82 |  |  | cÖKí mvnvh¨ t |  | 74926
2018-19 A_©eQ‡ii GwWwc‡Z eivÏ (j¶ UvKvq)t |  |  |  |  | †gvUt | 46744 |  |  | wRIwet | 7616 |  |  | cÖKí mvnvh¨ t |  | 39128
cÖKíwU G A_©eQ‡i mgvwßi Rb¨ wbav©wiZ t |  |  |  | bv
cÖKíwU G A_©eQ‡i mgvß n‡e t |  |  |  | bv
ms‡kvwaZ GwWwc‡Z eivÏ nªvm/e„w×i cÖ‡qvRb n‡et |  |  | n¨vu
(j¶ UvKvq)
As‡Mi bvg | RyjvB 2018 gv‡m j¶¨gvÎv |  |  |  | AvMó 2018 gv‡m j¶¨gvÎv |  |  |  | †m‡Þ¤¦i 2018 gv‡m j¶¨gvÎv |  |  |  | A‡±vei 2018 gv‡m j¶¨gvÎv |  |  |  | b‡f¤¦i 2018 gv‡m j¶¨gvÎv |  |  |  | wW‡m¤¦i 2018 gv‡m j¶¨gvÎv |  |  |  | Rvbyqvix 2019 gv‡m j¶¨gvÎv
| †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq)
| j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí | j¶¨gvÎv, | †gvU | UvKv | cÖKí
| (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨
| Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm,
| wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt,
| BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw`
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
K) ivRm¦ AsMmgyn t
4500 Awdmvi‡`i †eZb | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667
4600 cªwZôvb Kg©Pvix‡`i †eZb | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333
4700 fvZvw` | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167
4800 mieivn I †mev |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667
4900 ‡givgZ I msi¶b |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667
Dc-‡gvU (K) t |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667
L) g~jab AsMmgyn t
6800 m¤ú` msMªn / µq |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0 | 0 |  | 3 | 155 | 155 |  |  | 0 |  |  |  | 0
7000 wbg©vY I c~Z© |  | 0 | 0 | 0 | 0 | 1737.1744 | 215.1136 | 1522.0608 | 0 | 1737.1744 | 215.1136 | 1522.0608 | 0 | 3478.5247 | 430.7443 | 3047.7804 | 0 | 5219.8708 | 646.3745 | 4573.4963 | 0 | 5219.8708 | 646.3745 | 4573.4963 | 0 | 5219.8708 | 646.3745 | 4573.4963
7300 FY I AwMÖg |  | 0 | 0 |  |  | 4.5 | 4.5 |  | 1 | 4.5 | 4.5 |  |  | 4.5 | 4.5 |  | 2 | 4.5 | 4.5 |  |  | 4.5 | 4.5 |  |  | 4.5 | 4.5
7900 g~jab Lv‡Z wmwW f¨vU |  | 0 | 0 |  |  | 0 | 0 |  | 1 | 25 | 25 |  |  | 25 | 25 |  | 1 | 25 | 25 |  |  | 25 | 25 |  |  | 0
Dc-‡gvU (L) t |  | 0 | 0 | 0 |  | 1741.6744 | 219.6136 | 1522.0608 |  | 1766.6744 | 244.6136 | 1522.0608 |  | 3508.0247 | 460.2443 | 3047.7804 |  | 5404.3708 | 830.8745 | 4573.4963 |  | 5249.3708 | 675.8745 | 4573.4963 |  | 5224.3708 | 650.8745 | 4573.4963
me©‡gvU (K+L) t |  | 390 | 178.3333 | 211.6667 |  | 2131.6744 | 397.9469 | 1733.7275 |  | 2156.6744 | 422.9469 | 1733.7275 |  | 3898.0247 | 638.5776 | 3259.4471 |  | 5794.3708 | 1009.2078 | 4785.163 |  | 5639.3708 | 854.2078 | 4785.163 |  | 5614.3708 | 829.2078 | 4785.163
As‡Mi bvg | †deªyqvix, 2019 gv‡m j¶¨gvÎv |  |  |  | gvP©, 2019 gv‡m j¶¨gvÎv |  |  |  | GwcÖj, 2019 gv‡m j¶¨gvÎv |  |  |  | †g, 2019 gv‡m j¶¨gvÎv |  |  |  | Ryb, 2019 gv‡m j¶¨gvÎv |  |  |  | †gvU j¶¨gvÎv
| †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq) |  |  | †fŠZ | Avw_©K j¶¨gvÎv (j¶ UvKvq)
| j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí | j¶¨gvÎv | †gvU | UvKv | cÖKí
| (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨ | (wU, wgt, |  |  | mvnvh¨
| Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm, |  |  |  | Rbgvm,
| wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt, |  |  |  | wKtwgt,
| BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw` |  |  |  | BZ¨vw`
1 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53
K) ivRm¦ AsMmgyn t
4500 Awdmvi‡`i †eZb | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 10 | 4.1667 | 4.1667 |  | 120 | 50 | 50 | 0
4600 cªwZôvb Kg©Pvix‡`i †eZb | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 2 | 0.83333 | 0.83333 |  | 24 | 10 | 10 | 0
4700 fvZvw` | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 12 | 4.4167 | 4.4167 |  | 144 | 53 | 53 | 0
4800 mieivn I †mev |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 377.4167 | 165.75 | 211.6667 |  | 4529 | 1989 | 2540
4900 ‡givgZ I msi¶b |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 3.1667 | 3.1667 |  |  | 38 | 38 | 0
Dc-‡gvU (K) t |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 390 | 178.3333 | 211.6667 |  | 4680 | 2140 | 2540
L) g~jab AsMmgyn t
6800 m¤ú` msMªn / µq |  | 0 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3 | 155 | 155 | 0
7000 wbg©vY I c~Z© | 0 | 3479.9027 | 430.9149 | 3048.9878 | 0 | 3479.9027 | 430.9149 | 3048.9878 | 0 | 3479.9027 | 430.9149 | 3048.9878 | 0 | 5219.8708 | 646.3745 | 4573.4963 | 0 | 3486.9367 | 431.7867 | 3055.15 | 0 | 41759.0017 | 5171.0009 | 36588.0008
7300 FY I AwMÖg |  | 4.5 | 4.5 |  |  | 4.5 | 4.5 |  |  | 4.5 | 4.5 |  |  | 4.5 | 4.5 |  |  | 5 | 5 |  | 5 | 50 | 50 | 0
7900 g~jab Lv‡Z wmwW f¨vU | 1 | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 1 | 0 |  |  |  | 0 |  |  | 4 | 100 | 100 | 0
Dc-‡gvU (L) t |  | 3484.4027 | 435.4149 | 3048.9878 |  | 3484.4027 | 435.4149 | 3048.9878 |  | 3484.4027 | 435.4149 | 3048.9878 |  | 5224.3708 | 650.8745 | 4573.4963 |  | 3491.9367 | 436.7867 | 3055.15 |  | 42064.0017 | 5476.0009 | 36588.0008
me©‡gvU (K+L) t | [21 empty] | 46744.0017 | 7616.0009 | 39128.0008
wet`ªt Microsoft Excel I SutonnyMJ Font G Soft Copy mn Z_¨vw` cvVv‡Z n‡e¦
* 2017-18 A_©eQ‡ii †h mKj ¯‹xg GLbI Pjgvb Av‡Q †m¸‡jvi Z_¨ Ges eZ©gvb 2018-19 A_©eQ‡i Kvh©v‡`k cÖ`vbK…Z ¯‹x‡gi Z_¨ mswkøó gv‡mi Q‡K Avm‡e¦

## Procurement Plan
¯’vbxq miKvi cÖ‡KŠkj Awa`ßi
evwl©K msMÖn/µq cwiKíbv (2018-19)
* cÖK‡íi bvg t ÒwmwU Mfvib¨vÝ cÖ‡R±Ó
* †gqv` Kvj t RyjvB/2014 Bs n‡Z Ryb/2020 Bs
* cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q (j¶ UvKvq) t | [9 empty] | †gvUt | 294300 |  |  | wRIwet | 54531 |  |  | cÖKí mvnvh¨ t | 239769
(j¶ UvKv)
[9 empty] | †gvU |  |  |  | cY¨ |  |  |  | c~Z© |  |  |  | ‡mev
* Aby‡gvw`Z wWwcwc/wUwcwc/AviwUwcwcÕi cÖwµDi‡g›U cø¨vb | [8 empty] | msL¨v |  | e¨q |  | msL¨v |  | e¨q |  | msL¨v |  | e¨q |  | msL¨v |  | e¨q
Abyhvqx c¨v‡K‡Ri msL¨v I cÖv°wjZ e¨q t | [8 empty] | 213 |  | 292032.53 |  | 67 |  | 7605.59 |  | 134 |  | 197911.11 |  | 12 |  | 86515.83
* Ryb 2018 ch©šÍ µgcywÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v I e¨q t | [8 empty] | 147 |  | 45760.33 |  | 33 |  | 1801.45 |  | 102 |  | 33723.84 |  | 12 |  | 10235.04
* 2018-19 A_©eQ‡ii GwWwc‡Z eivÏ Abymv‡i Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q t | [8 empty] | 27 |  | 41914 |  | 3 |  | 155 |  | 24 |  | 41759 |  | 0 |  | 0
(j¶ UvKvq)
µwgK bs | cÖK‡íi bvg | RyjvB 2018 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | AvMó 2018 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | ‡m‡Þ¤^i 2018 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | A‡±vei 2018 gv‡m ‡UÛvi Avnevb‡hvM¨ A_ev Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | b‡f¤^i 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | wW‡m¤^i 2018 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | Rvbyqvix 2019 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q
|  | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  | 0 |  | 0 | 0 | 0 | 0 | 4 | 0 | 6 | 0 | 6 | 0 | 8 | 0 | 8 | 0 | 7 | 3 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
|  | 0 |  | 0 | 0 | 6959.8333 | 0 | 6959.8333 | 0 | 10439.75 | 0 | 10439.75 | 0 | 13919.6667 | 0 | 13919.6667 | 0 | 7114.8333 | 155 | 6959.8333 | 0 | 3479.9167 | 0 | 3479.9167 | 0 | 0 | 0 | 0 | 0
µwgK bs | cÖK‡íi bvg | ‡deªæqvix 2019 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | gvP© 2019 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | GwcÖj 2019 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | ‡g 2019 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | Ryb 2019 gv‡m Kvh©v‡`k cÖ`vb‡hvM¨ c¨v‡KR msL¨v I e¨q |  |  |  | ‡gvU
|  | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q) | ‡gvU (e¨q) | cY¨ (e¨q) | c~Z© (e¨q) | ‡mev (e¨q)
|  | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 3 | 24 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41914 | 155 | 41759 | 0
wet`ªt Microsoft Excel I SutonnyMJ Font G Soft Copy mn Z_¨vw` cvVv‡Z n‡e¦
* 2017-18 A_©eQ‡ii †h mKj ¯‹xg (cY¨/c~Z©/†mev) GLbI Pjgvb Av‡Q †m¸‡jvi Z_¨ GB Q‡K Avm‡e bv¦ ïaygvÎ †hmKj `icÎ AvnŸvb Kiv n‡e I Kvh©v‡`k cÖ`vb Kiv n‡e †m¸‡jvi Z_¨ Avm‡e¦