## F-1
" cÖKí ev¯Íevqb cÖwZ‡e`b "
cÖwZ‡e`b gvm: wW‡m¤^i/2018Bs
1¦ |  | cÖK‡íi bvg | t | dwi`cyi †Rjvi ¸iæZ¡c~Y© cjøx AeKvVv‡gv Dbœqb cÖKí (1g ms‡kvwaZ)
2¦ |  | Aby‡gv`‡bi ch©vq | t | AviwWwcwc 04-11-2018 Bs Zvwi‡L GK‡bK KZ©„K Aby‡gvw`Z¦
3¦ |  | ms¯’v I gš¿Yvj‡qi bvg | t | ms¯’v | t | ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi¦
|  |  |  | gš¿Yvjq | t | ¯’vbxq miKvi wefvM, ¯’vbxq miKvi cjøx Dbœqb I mgevq gš¿Yvjq¦
4¦ |  | cÖK‡íi D‡Ïk¨ | t | K¦ ‡hvMv‡hvM e¨e¯’vi mvwe©K Dbœqb ; K…wl I AK…wl c‡Y¨i Drcv`b I wecbb mnRZi Ges Av_© mvgvwRK Ae¯’vi Dbœqb mvab Kiv¦
L¦ MÖvgxY cwienb I evRviRvZKi‡b AbMÖmi GjvKvq mv‡_ e„nËg moK †bUIqv‡K©i ms‡hvM ¯’vcb¦
M¦ ¯^í I `xN© †gqv`x Kg©ms¯’v‡bi my‡hvM m„wó Kiv¦
5¦ |  | ev¯ÍevqbKvj | t | RyjvB/2016Bs n‡Z Ryb/2021 Bs ch©šÍ¦
wWwcwc Abyhvqx
6¦ | cÖv°wjZ e¨q t |  | t | ‡gvU |  |  | t | 110600 |  | jÿ UvKv¦
|  |  |  | UvKv (wRIwe) |  |  | t | 110600 |  | jÿ UvKv¦
|  |  |  | cÖKí mvnvh¨ |  |  | t | -
|  |  |  | cÖKí mvnvh¨ UvKvsk |  |  | t | -
7¦ |  | cÖKí mvnv‡h¨i Drm | t | wRIwe
42

## F-2
8¦ | e¨q (j¶ UvKvq) t
| ‡gvU | [6 empty] | UvKv |  |  | cÖKí mvnvh¨ |  | ïé | FY
[11 empty] | ‡gvU | UvKvsk |  | cwi‡kva | gšÍe¨
| K) | 2018-19Bs A_© erm‡i GwWwc‡Z eivÏ |  |  |  | t | 12000 | 12000 |  |  | - | - | - | -
| L) | PjwZ A_© erm‡ii wW‡m¤^i/2018Bs ch©šÍ Aegyw³ |  |  |  | t | 6000 | 6000 |  |  | - | - | - | -
| M) | PjwZ A_© erm‡ii wW‡m¤^i/2018Bs ch©šÍ e¨q |  |  |  | t | 5439.96 | 5439.96 |  |  | - | - | - | -
| N) | cÖwZ‡e`bKvj ch©šÍ µgcywÄZ e¨q |  |  |  | t | 23939.89 | 23939.89 |  |  | - | - | - | -
9¦ | cÖKí mvnv‡h¨i UvKvsk, e¨q `vex I cÖvwß (j¶ UvKvq) t |  |  |  |  | cÖ‡hvR¨ b‡n¦
|  |  | welq |  | PjwZ A_© erm‡ii |  |  |  |  | µgcywÄZ
|  | 1) |  | e¨q | - |  |  |  |  | -
|  | 2) |  | `vexK…Z | - |  |  |  |  | -
|  | 3) |  | cÖvwß | - |  |  |  |  | -
42(2)

## F-3
10¦ |  |  |  | cÖavb cÖavb A‡½i j¶¨gvÎv I AMÖMwZ
| A‡½i bvg |  |  |  |  | AviwWwcwc Abymv‡i |  |  | Ryb/2018 ch©šÍ | [6 empty] | PjwZ A_© erm‡ii | [5 empty] | cÖwZ‡e`b ch©šÍ AMÖMwZ | [5 empty] | cÖKí cwiPvjK/ | gšÍe¨
[6 empty] | j¶¨gvÎv |  |  | µgcywÄZ AMÖMwZ I wWwcwci % | [6 empty] | j¶¨gvÎv cwigvb I AviwWwcwc % | [5 empty] | (cwigvb I eiv‡Ïi %) | [5 empty] | Kg©KZ©v KZ©„K
[6 empty] | ev¯Íe |  | Avw_©K | ev¯Íe |  |  | Avw_©K |  |  |  | ev¯Íe |  |  | Avw_©K |  |  | ev¯Íe |  |  | Avw_©K |  |  | cÖKí GjvKv
cwi`k©‡bi ZvwiL
| 1 |  |  |  |  | 2 |  | 3 | 4 |  |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10 | 11
| 01¦ |  | c~Z© KvR |  | t
|  |  | K) | Dc‡Rjv moK wewm Øviv Dbœqb¦ |  | 38.09 | wKtwgt | 2748.95 |  | 10 | wKtwgt |  | 800 |  |  |  | 4.4 | wKtwgt |  | 352 |  |  | 3 |  |  | 200 |  |  |  | 240 | 240
[14 empty] | ) |  | ( | 11.55% | ) | ( | 12.8% | ) | ( | 68.18% | ) | ( | 56.82% | ) |  |  |  |  | 1840
|  |  | (L) | BDwbqb moK wewm Øviv Dbœqb ¦ |  | 67.65 | wKtwgt | 4300.07 |  | 16 | wKtwgt |  | 1088 |  |  |  | 5.6 | wKtwgt |  | 380.8 |  |  | 2.5 |  |  | 140 |  |  |  | 170 | 170
[14 empty] | ) |  | ( | 8.278% | ) | ( | 8.856% | ) | ( | 44.64% | ) | ( | 36.76% | )
|  |  | (M) | MÖvg moK-G wewm Øviv Dbœqb¦ |  | 231.18 | wKtwgt | 15875.72 |  | 54 | wKtwgt |  | 3672 |  |  |  | 31.48 | wKtwgt |  | 2140.95 |  |  | 24 |  |  | 1408 |  |  |  | 1632 | 1632.2363
[14 empty] | ) |  | ( | 13.62% | ) | ( | 13.49% | ) | ( | 76.24% | ) | ( | 65.77% | )
|  |  | (N) | MÖvg moK-we wewm Øviv Dbœqb¦ |  | 216.34 | wKtwgt | 15094.83 |  | 44 | wKtwgt |  | 2973 |  |  |  | 27 | wKtwgt |  | 1836 |  |  | 10 |  |  | 580 |  |  |  | 680 | 680
[16 empty] | ( | 12.48% | ) | ( | 12.16% |  | ( | 37.04% | ) | ( | 31.59% | ) |  |  | 96 | 2722.2363
|  |  | (O) | BDwbqb moK GBPwewe Øviv Dbœqb ¦ |  | 16.8 | wKtwgt | 793.83 |  | 11.48 | wKtwgt |  | 544 |  |  |  | 4.43 | wKtwgt |  | 212.64 | ) |  | 2 |  |  | 85
[16 empty] | ( | 26.37% | ) | ( | 26.79% |  | ( | 45.15% | ) | ( | 39.97% | ) |  |  |  | 2.4613
|  |  | (P) | MÖvg moK-G GBPwewe Øviv Dbœqb¦ |  | 241.71 | wKtwgt | 11807.51 |  | 53 | wKtwgt |  | 2545 |  |  |  | 32.49 | wKtwgt |  | 1558.6 |  |  | 19 |  |  | 984.53 |  |  |  | 912
[16 empty] | ( | 13.44% | ) | ( | 13.2% | ) | ( | 58.48% | ) | ( | 63.17% | )
|  |  | (Q) | MÖvg moK-we GBPwewe Øviv Dbœqb¦ |  | 313.53 | wKtwgt | 15814.65 |  | 46 | wKtwgt |  | 2220 |  |  |  | 28.5 | wKtwgt |  | 1368 |  |  | 12 |  |  | 500 |  |  |  | 576
[16 empty] | ( | 9.09% | ) | ( | 8.65% | ) | ( | 42.11% | ) | ( | 36.55% | )
|  |  | (R) | moK cÖk¯’ KiY¦ |  | 19.01 | wKtwgt | 914.54 |  | 0 | wKtwgt |  | 0 |  |  |  | 6.17 | wKtwgt |  | 308.5 |  |  | 2 |  |  | 80
[16 empty] | ( | 32.46% | ) | ( | 33.73% | ) | ( | 32.41% | ) | ( | 25.93% | )
|  |  | (S) | eªxR wbg©vY |  | 3892 | wgt | 28675.53 |  | 660 | wgt |  | 3627 |  |  |  | 235 | wgt |  | 1292.5 |  |  | 180 |  |  | 850
[16 empty] | ( | 6.038% | ) | ( | 4.507% | ) | ( | 76.6% | ) | ( | 65.76% | )
|  |  | (T) | KvjfvU© wbg©vY |  | 389.8 | wgt | 1265.24 |  | 0 | wgt |  | 0 |  |  |  | 80 | wgt |  | 240 |  |  | 50 |  |  | 150
[16 empty] | ( | 20.52% | ) | ( | 18.97% | ) | ( | 62.5% | ) | ( | 62.5% | )
|  |  | U) †MÖv_ ‡m›Uvi/MÖvgxY evRvi Dbœqb ¦ |  |  | 26 | wU | 780 |  |  |  |  | 0 |  |  |  | 6 | wU |  | 150 |  |  | 3 |  |  | 30 |  |  |  | 50.5
[14 empty] | ) |  | ( | 23.08% | ) | ( | 19.23% | ) | ( | 50% | ) | ( | 20% | )
|  |  | V) ‡evU j¨vwÐs i¨v¤ú wbg©vY¦ |  |  | 36 | wU | 882 |  |  |  |  | 0 |  |  |  | 5 | wU |  | 125 |  |  | 3 |  |  | 62 |  |  |  | 4356.5
[16 empty] | ( | 13.89% | ) | ( | 14.17% | ) |  | 60% | ) | ( | 49.6% |  |  |  | 2500
|  |  | W) moK iÿYv‡eÿY |  |  | 285.56 | wKtwgt | 9569.95 |  | 48 |  |  | 851 |  |  |  | 74.22 | wKtwgt |  | 1885.01 |  |  | 14 |  |  | 315
[16 empty] | ( | 25.99% | ) | ( | 19.7% | ) | ( | 18.86% | ) | ( | 16.71% | ) |  |  | 174.3%
| 02¦ |  | Rxc Mvox µq,AvmevecÎ, †Uwj‡dvb G¨vÛ |  | t |  | ‡_vK | 117 |  | - |  |  | 14.995 |  |  |  | ‡_vK |  |  | 0 | [5 empty] | 0
|  |  | d¨v·,Kw¤úDUvi I hš¿vsk | [10 empty] | ) |  |  |  |  | ( | 0% | ) |  |  |  | ( | 0% | )
Ges d‡UvKwcqvi,BZ¨vw` msMÖn
42(3)
| A‡½i bvg |  |  |  |  | wWwcwc Abymv‡i |  |  | Ryb/2018 ch©šÍ | [6 empty] | PjwZ A_© erm‡ii | [5 empty] | cÖwZ‡e`b ch©šÍ AMÖMwZ | [5 empty] | cÖKí cwiPvjK/ | gšÍe¨
[6 empty] | j¶¨gvÎv |  |  | µgcywÄZ AMÖMwZ I wWwcwci % | [6 empty] | j¶¨gvÎv cwigvb I wWwcwc % | [5 empty] | (cwigvb I eiv‡Ïi %) | [5 empty] | Kg©KZ©v KZ©„K
[6 empty] | ev¯Íe |  | Avw_©K | ev¯Íe |  |  | Avw_©K |  |  |  | ev¯Íe |  |  | Avw_©K |  |  | ev¯Íe |  |  | Avw_©K |  |  | cÖKí GjvKv
cwi`k©‡bi ZvwiL
| 1 |  |  |  |  | 2 |  | 3 | 4 |  |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10 | 11
| 03¦ |  | ‡givgZ I i¶Yv‡e¶Y |  | t |  | ‡_vK | 35 |  | - |  |  | 5.25 |  |  |  | ‡_vK |  |  | 7 | [5 empty] | 1.48
|  |  | (hvbevnb, Kw¤úDUvi I Awdm miÄvg ) | [10 empty] | ) |  |  |  |  | ( | 20% | ) |  |  |  | ( | 21.14% | )
| 04¦ |  | mieivn I †mev (‡Uwj‡dvb, †UwjMÖvg, we`y¨r, |  | t |  | ‡_vK | 684 |  | - |  |  | 113.93 |  |  |  | ‡_vK |  |  | 91.34 | [5 empty] | 50.5
|  |  | R¡vjvbx, †c‡Uªvj, jyweª‡K›U, wcÖw›Us, cÖPvi | [10 empty] | ) |  |  |  |  | ( | 13.35% | ) |  |  |  | ( | 55.29% | )
weÁvcb,†ókbvix, mv‡f©, Kbmvj‡Uýx I Ab¨vb¨)¦
| 05¦ |  | Rbej |  | t | 11 | msL¨v | 274 |  |  |  |  | 45.72 |  |  |  | ‡_vK |  |  | 51 | [5 empty] | 3.45
[14 empty] | ) |  |  |  |  | ( | 66% | ) |  |  |  | ( | 6.765% | )
| 06¦ f‚wg AwaMÖnY |  |  |  | t | 0.50 †n±i |  | 68.8
| 07¦ |  | g~jab |  | t |  | ‡_vK | 898.38
ivR¯^
| ‡gvU | [10 empty] | 18499.93 | [5 empty] | - | 12000 |  |  |  | - |  |  | 5439.96 | [6 empty] | 250 | 8237.5
[8 empty] | 110600 | ( | 32.25% | ) | ( | 29.6% | ) | ) | ( | 10.85% | ) | ( | 10.85% | ) | ( | 52.35% | ) | ( | 45.33% | )
| cÖwZ‡e`b gvm ch©šÍ µzgcywÄZ ev¯Íe AMÖMwZ |  |  |  | t | 30.41%
| cÖwZ‡e`b gvm ch©šÍ µgcywÄZ Avw_©K AMÖMwZ |  |  |  | t | 21.65%
| 11¦ |  | wewea mgm¨v |  | t
| 12¦ |  | mgvavb |  | t
wet`ªt cÖKíwU MZ 04-11-2018 Zvwi‡L GK‡bK mfvq Aby‡gvw`Z n‡q‡Q¦
42(4)

## Scheme Status report
SCHEME STATUS REPORT
FY: 2018-19
Progress Report for the Month: December/ 2018
( Taka in lakh)
SL. | Name of Project | ADP Provision | No. of Schemes/Contracts |  |  | Work Plan Target |  |  |  | Achievement |  |  |  | Current | Total | Remarks
No. | ( Name of Development | & Total Fund | New | Carried | Total | Last date | Last date | Schemes | Schemes | Tender | Tender | Works | Schemes | Year | Fund
| Assistance Patner) | Released | Scheme/Contracts | over |  | for | for | Prepared | Preparation | called | Evaluation | going | Completed | Physical | Spent
|  | ( GOB+RPA) |  | Contracts/Excess |  | awarding | Commen- |  | under process |  | under | on |  | Progress | (GOB+RPA)
|  |  |  | Programmes |  | Contract | cement |  |  |  | process
of
Previous
|  |  |  | Year | (No.) |  |  | (No.) | (No.) | (No.) | (No.) | (No.) | (No.)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
63 | Faridpur District Important Rural Infrastructure Development Project (1st Revised). | 12000 | 140 | 100 | 240 | 2018-12-30 | 2019-01-15 | 25 | 30 | 40 | 15 | 100 | 0 | 52.35% | 5439.96
2013

## Sheet-Sanstha Vittik
ms¯’v wfwËK AMÖMwZ
cÖwZ‡e`b Kvj t wW‡m¤^i/ 2018
( jÿ UvKv)
µwgK bs | cÖK‡íi bvg | Aby‡gv`‡bi ch©vq | GwWwc eB‡qi c„ôv I µwgK bs | PjwZ erm‡i evwl©K Dbœqb Kg©m~Px‡Z eivÏ |  |  |  | Aegyw³ |  |  |  | e¨q |  |  |  | AMÖMwZ % |  |  |  | cÖKí mvnvh¨ ( UvKvsk) |  | cÖKí mvnv‡h¨i Drm | gšÍe¨
|  |  |  | ‡gvU | UvKv (wmwWGmwU) | cÖKí mvnvh¨ |  | ‡gvU | UvKv (wmwWGmwU) | cÖKí mvnvh¨ |  | ‡gvU | UvKv (wmwWGmwU) | cÖKí mvnvh¨ |  | ‡fŠZ |  | Aw_©K
[6 empty] | †gvU | UvKvsk |  |  | †gvU | UvKvsk |  |  | †gvU | UvKvsk | jÿgvÎv ( ˆÎgvwmK) | AMÖMwZ | jÿgvÎv ( ˆÎgvwmK) | AMÖMwZ | `vexK…Z | cÖvß
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
63 | dwi`cyi †Rjvi ¸iæZ¡c~Y© cjøx AeKvVv‡gv Dbœqb cÖKí (1g ms‡kvwaZ)¦ | Aby‡gvw`Z | - | 12000 | 0 | - | - | 12000 | 6000.00 (-) | - | - | 5439.96 | 5439.96 (-) | - | - | 75% | 52.35% | 75% | 45.33% | - | - | wRIwe

## Perchage
µq msµvšÍ Z_¨vejxt 2018-19 A_©eQ‡ii AMÖMwZ (wW‡m¤^i/2018 ch©šÍ)
(j¶ UvKvq)
cÖK‡íi bvg | gvjvgvj |  |  |  |  | c~Z© |  |  |  |  | ‡mev |  |  |  |  | K) wmwW f¨vU mn µqLv‡Z †gvU eivÏ (2018-19) |  |  | K) wmwW f¨vU mn µq Lv‡Z †gvU e¨q
| MZ A_©eQ‡ii ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i/18 mgqKv‡j cÖ`vbK…Z |  | wW‡m¤^i/18 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`k msL¨v | MZ A_©eQ‡ii ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i/18 mgqKv‡j cÖ`vbK…Z |  | wW‡m¤^i/18 mgqKv‡j cÖ`vb‡hvM¨ Kvh©v‡`k msL¨v | MZ A_©eQ‡ii ev c~‡e© cÖ`vbK…Z |  | wW‡m¤^i/18 mgqKv‡j cÖ`vbK…Z |  | wW‡m¤^i/18 mgqKv‡j cÖ`vbK…Z Kvh©v‡`k msL¨v |  |  |  |  | µqLv‡Z Ae¨vwqZ eivÏ (18-19) | ‡gvU GwWwc eivÏ | µqLv‡Z eivÏ †gvU GwWwc eiv‡Ïi %
| Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q | Kvh©v‡`k msL¨v | D³ Kvh©v‡`‡ki AvIZvq cÖK…Z e¨q |  |  | L) wmwW f¨vU |  | L) wmwW f¨vU
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 |  | 17 |  | 18 | 19 | 20 | 21
dwi`cyi †Rjvi ¸iæZ¡c~Y© cjøx AeKvVv‡gv Dbœqb cÖKí (1g ms‡kvwaZ)¦ |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | K) | 11850 | K) | 2500 | 9350 | 12000 | 98.75%
[16 empty] | L) | 0 | L) | 0

## march
2018-19 A_© eQ‡i ¯’vbxq miKvi wefv‡Mi AvIZvq GwWwcfz³ ev¯Íevqbvaxb cÖKí mgy‡ni AMÖMwZi ch©v‡jvPbv QK- 1
gv‡mi bvgt wW‡m¤^i/2018Bs¦
ms¯’vt ¯’vbxq miKvi cÖ‡KŠkj Awa`ßi (GjwRBwW)¦ | [21 empty] | (j¶ UvKvq)
µwgK bs | cÖK‡íi bvg (†gqv`Kvj) | cÖK‡íi cÖv°wjZ e¨q | Ryb/18 ch©šÍ µgcywÄZ e¨q | Aby‡gvw`Z wWwcwc/AviwWwcwci Procurement plan Abyhvqx c¨v‡KR msL¨v/cÖv°wjZ e¨q | Ryb/2018 ch©šÍ µgcywÄZ Kvh©v‡`k cÖ`vbK…Z c¨v‡KR msL¨v/e¨q | 2018-2019 evwl©K Dbœqb Kg©m~Px | [11 empty] | K) µgcywÄZ cybf©iY e¨q (Ryb/18 ch©šÍ) L) ‡gvU cybf©iY e¨q (18-19 GwWwc) M) ‡gvU cybf©iY `vex †ck (18-19 GwWwc) N) ‡gvU cybf©iY cÖvwß (18-19 GwWwc) | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ Avw_©K e¨q/AMÖMwZ | cÖK‡íi ïiæ n‡Z ch©v‡jvPbvaxb gvm ch©šÍ µgcywÄZ ‡fŠZ AMÖMwZ | cÖK‡íi Aby‡gvw`Z cÖv°wjZ e¨q Abyhvqx AeivÏK…Z UvKv | A‡±vei/18 n‡Z cÖK‡íi Aewkó †gqv`Kvj | cÖKí mvnv‡h¨i Drm
[6 empty] | 2018-19 GwWwc eivÏ | 2018-19 AviGwWwc eivÏ | Kg© cwiKíbv |  |  |  |  | msMÖn cwiKíbv |  |  |  | ch©v‡jvPbvaxb gv‡m Kvh©v‡`kmn Avw_©K I †fŠZ j¶gvÎv M„nxZ bv nIqvi KviY (18-19 GwWwc)
[8 empty] | ch©v‡jvPbvaxb gvm ch©šÍ A_© Aegyw³ (18-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨‡qi j¶¨gvÎv (18-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Avw_©K e¨q/AMÖMwZ (18-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ ‡fŠZ j¶¨gvÎv I AMÖMwZ (18-19 GwWwc) |  | evwl©K msMÖn cwiKíbv Abyhvqx c¨v‡KR msL¨v/e¨q (18-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ ‡UÛvi Avnev‡bi j¶¨gvÎv Abymv‡i c¨v‡KR msL¨v/e¨q (18-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ ‡UÛvi AvnevbK…Z c¨v‡KR msL¨v/e¨q (18-19 GwWwc) | ch©v‡jvPbvaxb gvm ch©šÍ Kvh©v‡`k cÖ`vbK…Z msL¨v/e¨q (18-19 GwWwc)
|  | †gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | †gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | †gvU (cY¨) (c~Z©) (‡mev) | †gvU (cY¨) (c~Z©) (‡mev) | †gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | †gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | †gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) UvKvsk (%) | †gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) | †gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) (UvKvsk) | j¶¨gvÎv (%) | AMÖMwZ (%) | †gvU (cY¨) (c~Z©) (‡mev) | †gvU (cY¨) (c~Z©) (‡mev) | †gvU (cY¨) (c~Z©) (‡mev) | †gvU (cY¨) (c~Z©) (‡mev) |  |  | ‡gvU (%) wRIwe (%) cÖKí mvnvh¨ (%) UvKvsk (%) | (%) | ‡gvU (wRIwe) (cÖKí mvnvh¨) (UvKvsk) | eQi/gvm
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
63 | dwi`cyi †Rjvi ¸iæZ¡c~Y© cjøx AeKvVv‡gv Dbœqb cÖKí (1g ms‡kvwaZ)¦ ( RyjvB/2016Bs n‡Z Ryb/2020 Bs ch©©šÍ) | 110600 | - | 2500(108708.78) | - | 12000 | - | 6000 | 75% | 45.33% | 75% | 52.35% | 140/12000.00 11850.00 | - | - | 0 |  |  | 23939.89 (21.65%) | 30.41% | 78352.98 | 2 eQi 06 gvm | wRIwe
|  | (110600.00) |  | 15/(185.80) | - | [7 empty] | 0/0.00 |  |  | 0 |  |  | 23939.89 (21.65%)
|  | (-) |  | 2485(105522.98) | [8 empty] | 140/12000.00 11850.00 |  |  | 0
[14 empty] | - | - | -

## Monthly IMED-September-2018
Progress Report of On-going Development Projects/Operational Plan (Format 05/2008)
Reporting Period: December/2018
(All Financial figures in Lakh Tk.)
Part-A: Monthly Report
Name of the Ministry/Division/Organization : | [6 empty] | Local Government Rural Development & Co-operatives/Local Government Division/Local Government Engineering Department.
1. | Name of the Project/Operational Plan : | [5 empty] | Faridpur District Important Rural Infrastructure Development Project (1st Revised).
2. | Objectioves of the Project/Operational Plan (in Brief) : | [5 empty] | a. Overall improvement of the communication network to facilitate production and marketing of agricultural and nonagricultural products anf socio-economic development of the project area.
b. To remove physical bottlenecks and reduce costs of rural transportation and marketing.
c. Create both short term and long termemployment opportunities.
3. | Location of the Project/Operational Plan : | [5 empty] | Faridpur District (9 upazila)
4. | Project Approval Status & Cost :
| DPP/TPP | Date of Approval |  | Implementation Period |  |  | Total Cost |  | GOB |  |  | Project Aid (RPA)
| i. Original | 2016-08-09 |  | July/2016- to June/2020 |  |  | 62500 |  | 62500 |  |  | -
| ii. Revised | 2018-11-04 |  | July/2016- to June/2021 |  |  | 110600 |  | 110600 |  |  | -
5. | Progress of Fund Release:
| Quarter-wise | Date of | [5 empty] | Amount Released |  |  | Date of issue of Cheque from CAO (in case of Autonomous body)
|  | Proposal Sending to Ministry/ Division |  | Issue of order by Ministry |  | Issue of order from Finance division
| 1 | 2 |  | 3 |  | 4 |  | 5 |  |  | 6
| 1st quarter | - |  | - |  | - |  | 3000
| 2nd quarter | [6 empty] | 3000
3rd quarter
4th quarter
2125
42(1)
6. | Target and Achievement of the main Components of the Project:
| Name of Important Components (With quantity) | Cost as per DPP/ RDPP/ TPP | Achievement upto last June/ 2018 |  |  | Target of current year |  |  | Progress upto the reporting month of current year |  |  | Unspent/unfinsidhed balance against PP targets |  |  |  | Imput Data
|  |  | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical | Financial |  | Physical
|  |  | a) Total |  | (% of the compt. | a) Total |  | (% of the compt. | a) Total |  | (% of the compt. | a) Total |  | (% of the compt.
|  |  | b) Taka |  |  | b) Taka |  |  | b) Taka |  |  | b) Taka
2-(3+7)
| 1 | 2 | 3 |  | 4 | 5 |  | 6 | 7 |  | 8 | 9 |  | 10
(a) | Impro. Of UZR Road by BC (30.695 km) | 2455.6 | a) | 800 | 10 | a) | 352 | 4.4 | a) | 200 | 3 | a)
|  |  | b) | 0 | 0.2364% | b) | 12.8% | 11.55% | b) | 56.82% | 68.18% | b)
(b) | Impro. Of UNR Road by BC (56.095 km) | 3814.46 | a) | 1088 | 16 | a) | 380.8 | 5.6 | a) | 140 | 2.5 | a)
|  |  | b) | 0 | 0.3783% | b) | 8.856% | 8.278% | b) | 36.76% | 44.64% | b)
(c) | Impro. Of VRA Road by BC (150.80 km) | 10254.06 | a) | 3672 | 54 | a) | 2140.95 | 31.48 | a) | 1408 | 24 | a)
|  |  | b) |  | 1.277% | b) | 13.49% | 13.62% | b) | 65.77% | 76.24% | b)
(d) | Impro. Of VRB Road by BC (117.099 km) | 7962.73 | a) | 2973 | 44 | a) | 1836 | 27 | a) | 580 | 10 | a)
|  |  | b) |  | 1.04% | b) | 12.16% | 12.48% | b) | 31.59% | 37.04% | b)
(e) | Impro. Of UNR Road by HBB (23.820 km) | 1143.36 | a) | 544 | 11.48 | a) | 212.64 | 4.43 | a) | 85 | 2 | a)
|  |  | b) |  | 0.2714% | b) | 26.79% | 26.37% | b) | 39.97% | 45.15% | b)
(f) | Impro. Of VRA Road by HBB (167.015km) | 8016.72 | a) | 2545 | 53 | a) | 1558.6 | 32.49 | a) | 984.53 | 19 | a)
|  |  | b) |  | 1.253% | b) | 13.2% | 13.44% | b) | 63.17% | 58.48% | b)
(g) | Impro. Of VRB Road by HBB (140.160 km) | 6727.68 | a) | 2220 | 46 | a) | 1368 | 28.5 | a) | 500 | 12 | a)
|  |  | b) |  | 1.087% | b) | 8.65% | 9.09% | b) | 36.55% | 42.11% | b)
(h) | Road Wedening (16.610 km) | 830.5 | a) | 0 | 0 | a) | 308.5 | 6.17 | a) | 80 | 2 | a)
|  |  | b) |  | 0% | b) | 33.73% | 32.46% | b) | 25.93% | 32.41% | b)
(i) | Const. of Bridge (2685.00m) | 14767.5 | a) | 3627 | 660 | a) | 1292.5 | 235 | a) | 850 | 180 | a)
|  |  | b) |  | 15.6% | b) | 4.507% | 6.038% | b) | 65.76% | 76.6% | b) |  |  |  | 7.2185
(j) | Const. of Culvert (292.400 m) | 877.2 | a) | 0 | 0 | a) | 240 | 80 | a) | 150 | 50 | a)
|  |  | b) |  | 0% | b) | 18.97% | 20.52% | b) | 62.5% | 62.5% | b)
(k) | Dev. Of GC/Rural Market (14 Nos.) | 350 | a) | 0 | 0 | a) | 150 | 6 | a) | 30 | 3 | a)
|  |  | b) |  | 0% | b) | 19.23% | 23.08% | b) | 20% | 50% | b)
(l) | Const. Of Boat landing Ramp (14 Nos.) | 350 | a) | 0 | 0 | a) | 125 | 5 | a) | 62 | 3 | a)
|  |  | b) |  | 0% | b) | 14.17% | 13.89% | b) | 6200% | 300% | b)
(m) | Road Rehabilitaton (Backlog Maintance) (160.64 km) | 4016 | a) | 851 | 48 | a) | 1885.01 | 74.22 | a) | 315 | 14 | a)
|  |  | b) |  | 1.135% | b) | 19.7% | 25.99% | b) | 5.31% | 6.74% | b)
3 | Physical Contingency (LS) | 110.59 | a) | 0 |  | a) | 0 | - | a) |  | - | a)
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
4 | Price Contingency (LS) | 226 | a) | 0 |  | a) | 0 |  | a) |  | - | a)
|  |  | b) |  |  | b) |  |  | b) |  |  | b)
|  | 61902.4 | 18320 |  | 32.25% | 11850 |  |  | 5384.53 | [5 empty] | 0% | 0.072185
42(2)
7. | Progress of Procurement in current FY:
[8 empty] | Goods | Works |  | Services |  | Total
| a) Work Orders (WO) issued in last year or before | [6 empty] | 0 | 0 |  | 0 |  | 0
i) Number of WOs.
| ii) Expenditure in current FY 18-19 | [6 empty] | 0 | 5384.53 |  | 0 |  | 5384.53
b) Work orders (WO) issued during the reporting period , 18-19
i) Number of WOs.
| ii) Expenditure in current FY 2018-19. | [6 empty] | 0 | 5384.53 |  | 0 |  | 5384.53
| c) WOs to be issued during the rest of the period of the FY 2018-19 | [6 empty] | 0 | 140 |  | 0 |  | 140
d) Total expenditure for procurement up to reporting month, 2018-19 (aii+bii).
| e) Total budget/Allocation for proecurement, 2018-19 | [6 empty] | 0 | 11850 |  | 0 |  | 11850
| f) Cumulative expenditure upto last year. | [6 empty] | 15 | 18320 |  | 164.9 |  | 18499.9
| g) Total allocation as per DPP | [11 empty] | 110600
| h) Unspent amount as per DPP | [11 empty] | 78352.98
8. | Particulars of reimbursement claim and receipts : N/A
| Initial Advance Receipt with date | Upto date | [5 empty] | During date
|  | Expenditure |  |  | Reimburs-ement Claimed |  | Expenditure | [5 empty] | Reimburs-ement Claimed
|  | Direct Payment |  | Payment from project account |  |  | Direct Payment |  |  |  | Payment from project account
| 1 | 2 |  | 3 | 4 |  | 5 |  |  |  | 6 |  | 7
| N/A |  |  | N/A | N/A | [5 empty] | N/A |  | N/A
42(3)