## phy. progress details
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Kotalipara
Pourashava Code : 199
| 24.Kotalipara |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
| UGIIP-III-I / KOTA / UT / 01 / 2015(Lot-01 ) | Improvement of Road by HBB from north side of Bridge in front of Pourashava office Via Rarir Bill & H/O Amor Ratno upto Parkona Mondiur Roads. Ch.00-1360m . Improvement of Road by DBC from the Sikir Bazar School BC Road Via H/O Achahak Member upto Parkona-Boluher Road . Ch.00-785m, Connecting Road from H/O Kamal Kha to Ishaque Member Ch. 00-288m. Improvement of Road by DBC from the BC Road in front of Karitas office upto H/O Profullaw Gharami. Ch.00-565m. Part A : Improvement of Road by HBB starting from Sonatiya BC Road in front of H/O Habib Shah upto Choto Dakhinpara Madrasha. ( Ch. 00.0 m to Ch.340.0 m ). Part B : Improvement of Road by HBB starting from Choto Dakhinpara road via Rokon Hazra upto Madanpara Deghi ( Ch. 00.0 m to Ch.470.0 m ). Part C : Construction of 1 * 3.00 m * 3.00 m single vent RCC Box Culvert & 2 * 3.50 m * 4.00 m double vent RCC Box Culverts. Improvement of Road by HBB from Sarder Bari CC Road Via H/O Taieb Sarder upto HBB Road in front of Riajul Munshi. Ch.00-635m Rehabilitation of Road by CC & HBB from the Kurpala road Via H/O Kazi Firoz East Side of Ghagor River upto Ghatla of main Bazar Road. Ch.00-575m & Conneccting road main road Ch 108 to existing HBB road. Ch. 00-106m Improvement of Road by HBB from the North Boundary of Pourashava Via H/O Mokbul mullah & Koykha Bridge upto H/O Anu mollah.Ch.00-955m Improvement of Road by HBB from the Koykha Madrasha Road Adjacent to Sanko Via H/O Haji Abdul Hakimi upto H/O Abul kalam azad. Ch.00-325m, & Connecting road upto Mosque-Ch 00-35m | 6.449 | 0 | 53974153.8 | Ha-Mim International, Dhanmondi, Dhaka | 46589371.8605 | 2016-04-07 | 2017-04-07 | 87.5% | 2879619.5 | 23641905.89
| UGIIP-III-I / KOTA / UT / 01 / 2015(Lot- 02) | Improvement of Road by HBB from the CC Road In Front of H/O Akub Ali Via Daharpara Jameh Mosque upto BC Road. Ch.00-400m Improvement of Road by CC starting from the AC Land Office Road Via Seba Clinic upto Mosque. Ch.00-144m & Connecting road start Seba Clinic to Main road. Ch.00-47m Part A : Improvement of Road by HBB From the Sawmill of Khalek Chairman Up to Parkona Shashanghat ( Rajoir-kotalipara road ). Ch. 00-1900.0 m. Part B : Construction of 1 * 2.50 m * 2.50 m single vent Box Culvert ( 2 Nos.). Part C: Construction of 2 * 3.50 m * 4.00 m double vent RCC Box Culverts at the Ch. 1090.0 m, 1230.0 m, 1380.0 m & 1590.0 m Part-A: Rehabilitationt of Road by DBC from the Gopalgonj – Poisarhat Road adjacent to Mukttijhodda office upto Sarder Bari Road. Ch.00-700m. Part-B: Rehabilitation of road from Main road Ch 382 to Kotalipara – Kandi Road. Ch.00-140m, &connecting to Clinic. Ch. 00-65m Improvement of Road by HBB in front of BC Road ( H/O Mosarraf Counsilor ) up to Sarder Bari CC Road.Ch.00-325m Part A : Improvement of Road by DBC from Gopalgonj- Paissarhat Sarak upto Munsur Tahshilder Sarak.Ch. 00-1015m & Connecting Road upto Kabi Sukanto Road. Ch. 00-160m . Part B : Construction of 1 * 3.00 m * 3.00 m single vent Box Culvert ( 2 Nos ) Improvement of Road by DBC from Ferdhara Primary School Via Kalimondir upto South boundary of Pourashava. Ch.00-1148m. Rehabilitation of Road by DBC from Tarashi Bazar ( Bus Stand ) upto Kheaghat / Food Godown. Ch.00-485m | 6.541 | 0 | 45282356.21 | M/s KB & FT (JV), 253, Mohammadpara, Gopalgonj | 36212910.8204 | 2016-04-10 | 2017-04-10 | 70% | 4388502.94 | 19273560.75
| UGIIP-III-2/KOTA/UT+DR/01/2016 (T.ID:79406) | Improvement of RCC road starting from DB road to H/O Khokon das Ch.00-242m Improvement of RCC road starting from DB road to H/O Omar mia house Ch.00-165m Improvement of RCC road starting from Kotalipara- kandi road upto Via Sarder bari & Munshi bari Ch.00-1170m Part-A:Improvement of RCC road from Darani Bazar upto Kotalipara Kandi road via H/O Gurongo Dev Ch.00-710m. Part-B: Improvement of Connecting road starting from Main road at Ch.400 to Main road at Ch. 190m. Ch.00-240m) Part-A:Improvement of BC road from Katalipara Kandi road near H/O Mujbul Haque to Kotalipara Kandi road near general Hospital via H/O Monsur Toshioldar Ch.00-1110, Part-B: Improvement of connecting road starting from Kotalipara Kandi road to Proposed main road Ch.00-240m Improvement of road by RCC starting from Monsur Toshilder road via Bandol Mosque upto H/O Idris sikder. Ch.00 - 615m Improvement of BC road starting from Komol Kuri school upto H/O Madob bishas road Ch.00-1000m Improvement of BC road starting from H/O Telam Mia to Ghachapara BC road Ch.00-1170m Part-A:Imrovement of road by HBB starting from H/O Said gazi to Ruhul Amin gazi Ch.00-460m, Part-B: Improvement of connecting road by HBB staritng from Main road to madha Koykha madrasha. Ch.00-40m) Part-A: Improvement of road by RCC starting from infront of H/O Aliur councilor east side of Ghagor river upto H/O Zhilu Sheikh . Ch.00-695m. Part-B: Improvement of road by RCC starting from Proposed main road (Part-A) to Kurpala road by RCC Ch.00-155m Part-A: Construction of RCC drain starting from the Gopalgonj-Paisharhat road Adjacent to Muktijodha Upto Khal infront of H/O Moshrraf councillor.Ch.00-400m , Part-B: Construction of RCC drain starting from Kotalipara Kandi road to Proposed RCC drain (Part-A).Ch.00-200m | 8.012 | 0.6 | 74374873.11 | Ha-Mim International & Mohiuddin Ahmed JV, Authorized Exicutive, Lubna khanam , Pro; Ha-Mim International , Kulpaddi, Madaripur | 61788716.7907 | 2017-06-12 | 2018-06-12 | 52.5% | 2988283.2 | 24401354.4
| UGIIP-III-2/KOTA /UT+DR/02/2016 (T.ID:79408) | Improvement of Road by RCC from Kurpala road Upto H/O Muzibor Chairman Ch.00-372m Improvement of RCC road from DB road H/O Shahjahan mia via office of World vision.Ch.00-290m Improvement of road by HBB from culvert infront of H/O Ananda Das to H/O Mithu Howladar via Bala bari including 02 Nos RCC box culvert.Ch.00-560m Improvement of rod by RCC from Sharder bari mosque to H/O Toyab Sharder via H/O Esken Sharder with 01 no. RCC box culvert. Ch.00-265m Part-A;Construction of HBB road starting from Kupala BC road upto H/O Didar Howladar. Ch.00-230m, Part-B; Construction of connecting road starting from main road to Morshed house. Ch.00-40m Construction of road by HBB from North side of bridge Infront of Pourashava office upto Rajoyor Kotalipara road. Ch.00-465m Improvement of road by RCC from Rajoyer Kotallipara upto H/O Atiyer mia via H/O Samsu Chairman and H/O Monu Ratna. Ch.00-348m Construction of HBB road starting from food godown road upto Tarashi Graveyard. Ch.00-450m Improvement of road by RCC from Helal market upto H/O Selim Talukder via Uttarpara madrasa. Ch.00-315m Part-A: Improvement of road by RCC starting from Helal Market Upto H/O Selim Talukder via Uttarpara madrasa. Ch 315-450m. Part-B: Improvement of connecting road starting from proposed main road (part-A) to Govt. School. Ch.00-66m Construction of HBB road starting from H/O Prof. Harun Hazra upto H/O Mantu Karmokar. Ch.00-500m Improvement of road by RCC starting from Derani Bazar Sheikh Rashel Shriti Shangho upto Derani Bazar BC road via H/O Aziz Hazra and H/O Aziz master. Ch.00-320m Improvement of road by DBC starting from H/O Upazila Vice Chairman upto Hazra bari.00-470m Improvement of road by RCC starting from Mahua rest house to Old Ferry Ghat. Ch.00-212m. Part-B:Drain Part-A: Constructon of RCC drain starting from infront of Mohua rest house upto Ghagor river. Ch.00-500m part-B: Construction of RCC drain straring from infront of Mohua rest house to proposed RCC drain (Part-A) Ch.00-200m incluiding 01 no. cross drain. Construction of RCC drain starting from Ghagor bazar Main road upto old Ferry ghat road side drain Ch.00-200m , including 02 nos. RCC cross drain. | 5.038 | 0.9 | 71842472.41 | Ha-Mim International & Mohiuddin Ahmed JV, Authorized Exicutive, Lubna khanam , Pro; Ha-Mim International , Kulpaddi, Madaripur | 59811075.4004 | 2017-06-12 | 2018-06-12 | 36.35% | 1888924.6 | 0
| UGIIP-III-2/KOTA/WS/01/2017 (T.ID:150302) | Installation of 1 nr. Production Well Construction of 1 nr.Pump house (Civil works) Construction of 01 nr.Pump house (Sanitary works) Construction of Boundary wall for 1 nr.pump house 1 set Mechanical works of Pump-motor Electric works for Pump and Pump house Supply of3 sets Operation and Maintanace Tools Environmental Mitigation Enhancement Works. 1 Sub-Component: 02 :Pipeline Installation of 24000 m distribution Pipeline 1 Sub-Component: 03 :Domestic Water Meter Supply and Installation of1200nos Donmestic Water Meter (13mm dia.=886 nos. ,20mm dia.=257 nos. and 25mm dia.=57 nos.) | 0 | 0 | 40007299.26 | M/s. Farjana Khan-Rana Builders(Pvt) Ltd.Joint Venture,Authorized executive Md. Alamgir Khan, Prop: M/s.Farjana Khan ,Puranbazar Madaripur. | 34000444.73 | 0 | 0 | 0% | 0 | 0
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Tungipara.
Pourashava Code : 201.
| 31. Tungipara. |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
| UGIIP-III-I / TUNG/ UT+DR / 01 / 2015 | Part-A: Construction of RCC road from Tungipara Upazila Parishad Gagated Quarter (New Building) to UP Mosque (G.Q Main Gate). Ch 00-350m & 3 Nos.Upazila Quarter connecting road Ch 00-35m.(Total-105m).and Connecting road up to PH Building. Ch 00-50m.Part-B: Construction of RCC road from Tungipara Upazila Parishad old Building to RHD via Helipad. Ch 00-199m & 3 Nos. connecting road H1,H2 &H3. (Length-69m) Construction of RCC road starting from Tungipara main road (Sakel Sheikh) to SP Mizan house. Ch 00-305m Construction of HBB road from Patgati RHD road to Poura market RHD. Ch 00-235m Part-A: Improvement of road by RCC & HBB starting from Patgati Abu Taleb shop (Front of Modhumoti market) to front of new Chandina to Sheikh Lutfar Rahman Bridge approach road. Ch. 220-710m = 490 & Connecting to New Chandina. Ch 00-22m. Part-B: Improvement of HBB road from main road Ch 520 to RHD. Ch 00-160m Construction of RCC Platform at Patgati Bazar & infront of Poura market. (Area-2178sqm) 5 Municipal Facilities a) Construction of 2 (Two) Storied Tungipara Poura Bus Terminal (area-927.50m2)at Tungipara, Gopalgonj. b) Construction of Workshop Building at Tungipara Poura Bus Terminal(area-172.17m2), Tungipara, Gopalgonj. c) Construction of 2 nr.Gate House at Tungipara Poura Bus Terminal, Tungipara, Gopalgonj. d) Construction of460m Boundary Wall at Tungipara Poura Bus Terminal, Tungipara, Gopalgonj. e) Construction of 4 nrs.Wellcome Board at Tungipara Poura Entry and Exit Point, Tungipara, Gopalgonj. f) Construction of 1 nr.Bus Wash System at Tungipara Poura Bus Terminal, Tungipara, Gopalgonj. g) Construction of Toilet Building at Tungipara Poura Bus Terminal(60m2), Tungipara, Gopalgonj. | 4.163 | 0 | 61276907.08 | Md. Wahid Miah, Karim Chamber, Mujib road, Faridpur | 65319977.1399 | 2016-04-17 | 2017-06-16 | 100% | 803803.23 | 62000000
| UGIIP-III-2/TUNG/MF /01/ 2017 | a) Construction of 2 (Two) Storied Tungipara Poura Bus Terminal (area-927.50m2)at Tungipara, Gopalgonj. b) Construction of Workshop Building at Tungipara Poura Bus Terminal(area-172.17m2), Tungipara, Gopalgonj. c) Construction of 2 nr.Gate House at Tungipara Poura Bus Terminal, Tungipara, Gopalgonj. d) Construction of460m Boundary Wall at Tungipara Poura Bus Terminal, Tungipara, Gopalgonj. e) Construction of 4 nrs.Wellcome Board at Tungipara Poura Entry and Exit Point, Tungipara, Gopalgonj. f) Construction of 1 nr.Bus Wash System at Tungipara Poura Bus Terminal, Tungipara, Gopalgonj. g) Construction of Toilet Building at Tungipara Poura Bus Terminal(60m2), Tungipara, Gopalgonj. | 0 | 0 | 148613702 | PBL-SB JV, PBL Tower 17, north C/A, Gulshan-2, Dhaka | 121864143.7 | 0 | 0 | 65% | 0 | 41353000
| UGIIP-III-2/TUNG/MF /02/ 2017 | Construction of 6 storied Multipurpose Super Market at Tungipara Pourashava a)Civil works b)Water Supply and sanitation works C)Electrical works D)Rain water Harvesting system | 0 | 0 | 257095337.12 | TBEL & AC (JV), 18, Gogon Babu road, 2nd lane, Khulna | 269259784.87 |  |  | 6% | 0 | 0
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Gopalgonj.
Pourashava Code : 198.
Sl. No | Package No | Name of Schemes/number of Scheme | Length of Scheme (Km) |  | Allotment Amount (Tk.) | Contractor Name | Cont.amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Materials (Tk) | Cumulative Expenditure (Tk) | Remarks
|  |  | Road | Drain
| 3. Gopalgonj. | Part-A:Road | 0 |  | 0
| UGIIP-III-2/AF/GOPA/UT-01/2017 | R-1:A) Improvement of Raghunathpur road as BC from By-pass to Burimar vita (ch00-1200.0m) B) Improvement of Dhalibari road as RCC starting from Bypass road(Ansar camp) to Raghunathpur road(Ch.00-485.00m), C) Improvement of Faringa bari road as RCC starting from Raghunathpur road (near Monir house) to Volanath house.(ch00-402),Total length=2087m R-2:Improvement of Mandertola housing connecting road as RCC from Bypass to Modle -house.(ch00-422.0m) R-17:Improvement of Govt Mohila College road as BC starting from Kalabagan more to Manikdah Bridge.(ch00-4760.0m) | 7.289 | 0 | 78835175.6937 | M/s. Niaz Traders,16/3/1 R.K. Mission road,Dhaka | 59304601.986 | 2018-05-10 | 43595 | 21.67% | 68264.784 | 0
| UGIIP-III-2/AF/GOPA/UT+DR-02/2017(T.ID:108678) | R-5:A) Improvement of BSCIC road as BC starting from BSCIC bridge to Kalabagan bridge .(ch00-890.0m) R-10:A) Improvement of DC road as BC & RCC starting from BB road to Graveyard with 3-link 1) Sawdagor road 2) Sikderpara road 3) Khamarbari road .(ch00-1255.0m+link-01-262.0m+link-02-248.0m+link-03-138.0m=1903.0m) R-15:A) Improvement of Bador road plus police line pond side road, SP Office road ,DC office road,link road as BC starting from Chandmari road to BB road(L=ch00-552.0m+LinkL1=ch00-265.00+L2=ch00-240.0+L3=ch00-113.00m+L4=ch00-112.0m=1282.0m). Part-B:Drain R-5(DR): B) Development of drainage intervention BSCIC road side drain starting from BSCIC bridge to Kalabagan bridge .(ch00-890.0m) R-10(DR): B) Development of drainage intervention of DC road side drain starting from Thanapara more to Sikderpara road via khristian para(ch00-450+248.0m=698.0m) R-15(DR): B) Development of drainage intervention of Bador road plus police line pond side drain starting from BB road to Jahanara Garden more .(ch00-355.0m) | 4.075 | 1.943 | 79415932.6729 | Noona Traders., 154, Motijheel, C/A, Dhaka Bangladesh | 60040294.602 | 2018-02-04 | 2019-02-04 | 0% | 171713.808 | 0
| UGIIP-III-2/AF/GOPA/UT+DR-03/2017(T.ID:108679) | R-9(RD):A) Improvement of Udayon road as BC starting from BB road to Public hall more via Gohata bridge .(ch00-1625.0m) ,Total length=1625m R-20:Improvement of Natun School road as BC starting from Chandmari road to Ashrom road via Khansaheb house(ch00-618.00m,)Total length=618m R-25(RD)A) Construction of Chandmari bylane road as RCC starting from Popy house to Amena School road(ch00-895.00m) B) Construction of Chandmari road side drain starting from Popy house to Amena School road .(ch00-395.0m),Total length=1290m Part-B:Drain R-9(DR):B) Construction work of Udayon bylane road RCC side drain starting from Hasib house to Profullo house via Tulu house.(ch00-160.0m) Link Battola to Hiru house (ch0.00-130m),Total length=290m R-25(DR): B) Construction of Chandmari road side drain starting from Popy house to Amena School road .(ch00-395.0m),Total length=395m Development of drainage intervention Natun School road side drain starting from Chandmati road to Panchuria khal by RCC .(ch00-332.0m),Total length=332m Development of drainage intervention Gohata road side drain starting from BB road(Judge court) to Boiragi khal by RCC .(ch00-982.0m),Total length=982m | 3.533 | 1.999 | 82205049.5459 | M/s Niaz Traders,16/3/1,R.K.Mission road,Dhaka | 62864170.42 | 2017-12-28 | 2018-12-28 | 0% | 77994.84 | 0
| UGIIP-III-2/AF/GOPA/UT+DR-04/2017(T.ID:108680) | R-11:A) Improvement of Miapara & Jermanmission road as BC starting from Miapara Puraton Sonali Bank to Graveyard and Miapara more to Jermanmission (ch00-.908m+1165.00m =2073.0); R-22:Improvement of road as RCC from Purbo Arambag By-pass to Daud's house in Ward No. 6. (Ch00-300.0m). Part-B:Drain R-11(DR): B) Construction work of Kaborstan bylane road RCC side drain starting from Kaborstan road to Jahangir munsi house (ch.00-252) link-1, kamal house to monir house (ch.00-300m) ;Total Length=552m D-05:Development of drainage interventions Miapara Road side drain starting from Kaborstan more to Bairagi Khal by RCC. Length = 710m. D-15: Development of drainage interventions Jerman mission Road side drain starting from Miapara more to Jerman mission by RCC. L= 1165m | 2.373 | 2.427 | 78868421.4915 | M/S. Dawn Corporation., 10 North Mugdha (1st floor), Sabujbag, Dhaka, Bangladesh | 55938919.054 | 2018-04-02 | 2019-04-02 | 0% | 212483.796 | 0
| UGIIP-III-2/AF/GOPA/UT+DR-05/2017(T.ID:108681) | R-13(RD):A) Improvement of Nabinbagh road as BC & CC (two parts) starting from BB road to Sufia Jame Mosque (Main-ch00- 480.0m) and link-a (Circuit house-ch00-596),(link-b-M.Bound.-ch00-470.0m),(link-c-Fishary-ch00-385.0),total=1931.0m, Improvement of Janata road as RCC starting from Battola to Bypass via Hazi Ali mia road(ch00-690.00m) Part-B:Drain R-13(DR):B) Improvement of Drainage system of Nabinbagh by lane road side Drain starting Ruhul Mia house to BDR house.(ch.0m-272m) Development of drainage intervention starting from Nabinbag Sufiya Jame mosque to Kapalipara khal by RCC .(ch00-880.0m),Link01-Circuit house road to RCC Drain(ch00-385.00m),Link-02-Medical College Boundary wall to RCC Drain.(ch00-320.0m) total Length=1585 Development of drainage intervention Janata road side drain starting from Gohata road (Ghullibari bazar)to Boiragi khal by RCC .(ch00-325.0m) | 2.621 | 2.182 | 79661846.6826 | Noona Traders, 154 Motijheel, C/A, Dhaka, Bangladesh | 64810609.278 | 2018-02-04 | 2019-02-04 | 0% | 148752.912 | 0
| UGIIP-III-2/AF/GOPA/UT+DR-06/2017(T.ID:108682) | R-6: Improvement of Charnarayondia road as BC starting from BB road to Bypass .(ch00-815.0m) R-08:A) Improvement of Girls School road as RCC starting from Bottala to Balaka Basralay& Bazar area.(ch00-466.00m+Link-252.0m+Link-70.0m) ,Total length=788m. R-14:A) Improvement of Sabujbag road as BC & RCC starting from Chandmari road to Amena School road( ch00--458(BC),0m-525.0m(RCC)) Total Length=983.0m. R-21:Improvement of Chachaniakandi road as BC starting om Chandmari road to Kalidas Hira haouse(ch00-1176.00m) R-24:Improvement of Ashrom road as BC starting from BB road to Chandmary road(ch.0m-Ch.1180m) , linked-01-Kadambari road(link01=315.00M),link-02-Maleka Academy road(280.0m),Total length=1775.0m& Islabag RCC road(ch.0m-1200.0m)' total length= 2975m R-28:A) Improvement of road as BC from Teghoria by lane road to Mandertola bridge road in ward no-8,9 (ch00-520m BC+ 0.00-1943m RCC road )Total L=2463m, Part:B(Drain) R-08(DR):B) Development of drainage intervention of Girls School road side drain starting from Battala to Balaka Basraloy & Bazar area(Sahapara road,Batasa potti road,Gengi pottiy road) .(ch00-466.0+252.0m+70.0m), Total length=788.0m R-14(DR): B)Construction of drainage intervention Sabuzbagh road side drain starting from Chandmary road to Thanda Mia house .(ch00-458.0m) R-28(DR):B) Cnstruction of Teghoria road side drain starting from Sumonto house to Panchuria khal. L=730m, Link-1, Kalachad house (ch.0.00-185m) link -2, Mosque side (ch.0.00-225m), Total length=1140m | 9.2 | 2.386 | 122618164.8248 | M/S. Niaz Traders., 16/3/1 R. K. Mission road, Dhaka, Bangladesh | 92433594.3408 | 2018-02-01 | 2019-02-01 | 0% | 558667.5192 | 0
| UGIIP-III-2/AF/GOPA/UT+DR-01/2017(T.ID:175171) | R-3:Improvement & construction of Munshipara road as RCC starting from Zila Parisad corner to Bypass(ch00-540.00m) R-4:Improvement of Miraz Khan Thakur road as BC starting from Chapail road to Dhaka-Khulna road .(ch00-927.00m) R-7:Improvement of South Moulovipara road as BC starting from Ghoserchar road to Stadium via Mohila Madrasha road .(ch00-532.0m+225.0m=757.00m) R-12:A) Improvement of Biswasbari road as RCC starting from Miapara more to Yousuf driver house and Link-01-Little Flower School road,Link-02-Ahale hadis road.(ch00-705.0m+Link-01=ch00-558.0m+Link-02-ch00-472.0m=1735.0m) Part-B:(Drain) R-12(DR):B) Development of drainage interventions Biswasbari road side drain & link-01-Little Flower School road,Link-02-Ahale Hadis road side drain starting from Miapara more to Boiragi khal via Two link road drain .(ch00-447.0+link-01=548.0m,link-02=462.0m=1457.0m) D-9:Development of drainage interventions Bador road Bankpara side drain starting from Chandmary road to Panchuria khal by RCC .(ch00-702.0m) | 3.959 | 2.159 | 79435146.0735 | M/s. Niaz Traders,16/3/1 R.K. Mission road,Dhaka | 69474572.8404 | 0 | 0 | 0% | 249122.5296 | 0
| UGIIP-III-2/AF/GOPA/DR-01/2017(T.ID:175179) | Development of drainage interventions starting from Bedgram to Boiragi khal via Bypass.(ch00-1750.0m) | 0 | 1.75 | 91086381.3704 | M/s. Kamal & Brothers-M/s.JAKYULLAH&BROTHERS(JV),BB Road,Gopalganj | 76806839.15 |  |  | 0% | 0