## Scheme Format
Project Full Name: Construction of 09 (Nine) nos. Important Bridge Project
Project Short Name: NINEBP
Project Code: 224048300
District Name: Norsingdi
Upazila Name: Monohordi
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 179 | NAR, W-13 | Construction of 162.20 m long PC Girder Bridge on Paikan Bazar - Katiadi GC via Luhajuri UP Road Over Old Bramaputra River (ID No. 368522001). | 0.1622 | 117059000 | M/S. Rezvi Construction. | 117058836.47 | 2015-10-29 | 2018-12-31 | 100 |  | 110782000
2 | 179 | NAR, W-13 a | Extention of Approach Road for 111.00m Bridge on Shidli UP Office-Paglabazar road Ch3025m over Shampur river (ID No. 372403012). | 1 | 24910000 | M/S. Rezvi Construction. | 24183053.1 | 2017-06-18 | 2019-01-31 | 95 |  | 21768000
District Name: Manikganj.
Upazila Name: Manikganj-S.
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 242 | MAN, W-14 | Construction of 456.00m PC Girder Bridge on Betila-Balirteak Upazila Road ch. 9+300 (ID No.356462002) over Kaliganga river | 0.456 | 490030000 | Navana Construction Ltd. | 474007540.68 | 2016-10-01 | 2019-03-30 | 97 |  | 421016000
District Name: Netrokona
Upazila Name: Kalmakanda
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 189 | NET, W-15 | Construction of 111.00 m Bridge on Shidli UP office - Paglabazar Road Ch. 3025.00m over Shampur River. | 0.111 | 108793000 | M/S Udayan Builders & Ashim Singh(JV) | 105495364.26 | 2015-12-23 | 2019-05-05 | 97 |  | 97985000
2 | 189 | NET, W-15 a | Extention of Approach Road for 111.00m Bridge on Shidli UP Office-Paglabazar road Ch3025m over Shampur river (ID No. 372403012) under Kalmakanda Upazila of Netrakona district. | 2 | 47337000 | FK - SI (JV) | 45957032.781 | 2017-08-07 | 2019-06-06 | 85 |  | 36082000
District Name: Magura.
Upazila Name: Magura-S.
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 271 | MAG, W-16 | Construction of 175.00 m Bridge over Nabogonga River between Parnandully Baparipara Kheyaghat - JTC Godown Ghat. | 0.175 | 102842000 | MMB-IT (JV) | 101143983.92 | 2015-08-16 | 2018-10-31 | 100 |  | 100715000
District Name: Khulna.
Upazila Name: Dacope.
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 263 | KHU, W-17 | Construction of 441.00m Long PC Girder Bridge on Kalinagar GC-Khutakhali GC Road Over Bhadra River Near Shingiora Govt. Primary School at Ch.0+00(ID No.247172004) | 0.441 | 469700000 | PTSL-MAITRE (PVT) Ltd. | 383695276.37 | 2016-08-08 | 2019-02-28 | 53 |  | 183509000
2 | 263 | KHU, W-17 a | Extention of Approach Road for 441.00m Long PC Girder Bridge on Kalinagar GC-Khutakhali GC Road Over Bhadra River Near Shingiora Govt.Primary School at Ch.0+00Km (ID No.247172004). | 3 | 15038000 | Sahid Enterprise (Pvt.) Ltd. | 14556744.68 | 2018-04-09 | 2019-02-08 | 20 |  | 1875000
District Name: B-Baria
Upazila Name: Nobinagar
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 106 | BBR, W-18 | Construction of 575.00 m Bridge at Gokorna Lunchghat at Bitghar G.C. -B.Baria via Kurighar hat road at ch.-15000m over Titas River. | 0.575 | 352404000 | M.M. Builders & Engineers Ltd, M/S. Janmabumi Nirmata & Ohiduzzaman Chowdhury(MNO) JV | 326074947.22 | 2016-01-07 | 2019-06-30 | 90 |  | 273910000
2 | 106 | BBR, W-18 a | Construction of slope protection work for 575.00m long PC Girder Bridge at Gokorna Lunchghat on Bitghar G. C.-B. Baria via Kurighar hat road at Ch. 15000m over Titas river. (ID No. 412852006). | 0.13 | 15408000 | M/S Mostafa Kamal | 14958679.5 | 2017-11-12 | 2019-06-30 | 50 |  | 3800000
District Name: Cox's Bazar.
Upazila Name: Ramu.
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 129 | COX, W-19 | Construction of 399 m long PC Girder Bridge on Kalghar Bazar - Razarkull UP Road at ch. 1500m over Bankkhali River. | 0.399 | 243211000 | UI-PTSL (JV) | 243420076.87 | 2016-03-23 | 2019-06-30 | 70 |  | 147780000
2 | 129 | COX, W-19 a | Extention of Approach Road for 399.00m long PC Girder Bridge on Kalghar Bazar-Razarkull UP Road at Ch. 1500m over Bankkhali river. (ID No. 422663012). | 2 | 27212000 | Unnayan International - M/S Bazal & Brothers (JV) | 26418600 | 2017-10-28 | 2019-06-25 | 10 |  | 0
District Name: Gaibandha.
Upazila Name: Saghata.
Sl. No. | Upazila Code | Package No | Name | Length of Scheme (km) | AllotmentAmount (Tk) | Contractor Name | Contract Amount (Tk) | Commencement Date (dd/mm/yy) | Completion Date (dd/mm/yy) | Progress (%) | Salvage Material (Tk) | Cumulative Expenditure (Tk) | Remarks
1 | 428 | GAI, W-20 | Construction of 273 m long PC Girder Bridge over Katakhali River on Barokona FRB - Banglabari Kheya ghat road at Ch. 5000m (ID No. 132883003). | 0.273 | 188981000 | SSL-Udayan (JV) | 184151665.77 | 2016-03-15 | 2019-06-30 | 80 |  | 136511000
2 | 428 | GAI, W-21 | Construction of 195 m long PC Girder Bridge over Katakhali River on Folia bazar-Panchapur road at Ch. 500m (ID No. 132885049). | 0.195 | 140873000 | M/S. Chowdhury Enterprize | 140880829 | 2015-11-23 | 2019-06-02 | 96 |  | 120258000
3 | 428 | GAI, W-20 a | Extention of Approach Road and slope protection work for 273.00m long PC Girder Bridge over Katakhali river on Barokona FRB -Bangabari Kheya ghat road at Ch. 5000m (ID No. 132883003). | Road = 4 km Culvert = 110m Slope prot.=800m | 175100000 | NN Builders Ltd. | 169999999 | 2017-11-28 | 2019-06-08 | 25 |  | 26600000
4 | 428 | GAI, W-21 a | Extention of Approach Road and slope protection work for 195.00m long PC Girder Bridge over Katakhali river on Folia bazar -Panchapur road at Ch. 500m (ID No. 132885049). | Road = 5 km Culvert = 65m Slope prot.=400m | 116834000 | Md. Moyenuddin (Bashi) | 113430694.88 | 2017-08-28 | 2019-06-30 | 40 |  | 32400000