## phy. progress details
|  |  | Length of Scheme (M) |  | Allotmtnt Amount (Tk) | Name and Address of the Contractor | Contract amount (Tk) | Date of Commencement | Date of completion | Progress (%) | Salvage cost (Tk) | Cumulative Expenditure | Remarks
Sl.No | Package No | Name of Schemes/number of Scheme | Road | Drain
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Naogaon.
Pourashava Code : 57.
1. Naogaon.
1 | UGIIP-III-I/ NAOG / UT / 01 / 2014 | Rehabilitation of existing B C Road l from R&H office to Durgapur road via dayaler moar towards Ali pasaris house by Dense Bituminous Carpeting with Brick toe wall. (Ch. 0+0 m to 1+225 m) Rehabilitation of existng B.C Road from Kalitala moar to Napit para moar Dense Bituminous Carpeting. (Ch. 0+0 m to 0+670 m) Rehabilitation of existing B C Road from main road (R&H) to Sutikalitala via Sanyalbari at Sultanpur by Dense Bituminous Carpeting . (Ch. 0+0 m to 2+550 m ) Rehabilitation of existing B C Road from Naogaon Policr Station to Sarishatir moar via Toropdarpara including Jatica Sangsad by CC Dense Bituminous Carpeting . (Ch. 0+0 m to 0+351 m & Ch. 0+0 m to 0+260 m) Rehabilitation of existing BC Road from Sherpur Mosque to Chakprosad School via Chakprosad Hindu para by Dense Bituminous Carpeting . (Ch. 0+0 m to 2+076 m) Rehabilitation of existing BC Road from Tajer moar towards Khalishakury by Dense Bituminous Carpeting. (Ch. 0+0 m to 1+200 m & Ch. 1+400 m to 1+951 m) Rehabilitation of existing BC Road from Sharisahati moar towards Duragapur via Bulu's Housiing Scheme including three Link road by Dense Bituminous Carpeting. (Ch. 0+0 m to 0+955 m & Link raod = 305 m + 480 m + 165 m = 950 m ) Construction of existing Kacha road from Idue's Battaly to Anandanagar road by CC. (Ch. 0+0 m to 0+732 m) Construction of existing Kacha road with side drain from infront of LGED ofice to Alom House via Abdul Gaffar House by CC. (Ch. 0+0 m to 0+375 m & Link = 50 m) Rehbilitation of existing BFS & Kacha road from the House of Late Sharf Uddin to Sahapur road by CC. (Ch. 0+0 m to 0+640 m) 10 Rehabilitation of existing B C Road l from R&H office to Durgapur road via dayaler moar towards Ali pasaris house by Dense Bituminous Carpeting with Brick toe wall. (Ch. 0+0 m to 1+225 m) | 12585 | 0 | 81179689.56 | Ethen-Farid (JV), Main Road, Naogaon | 86519737.3983 | 2015-07-05 | 29/06/2016 | 100% | 1002804 | 86267082.98 | 0
| UGIIP-III-I/ NAOG /DR+MF/01/ 2014 | Construction of RCC drain from Ukilpara sluicegate to Durgapur Beel. (Ch. 0+0 m to 1+800 m) & Link drain ch.0m-ch.300m Construction of RCC drain from Janaklyan culvert to Humayun Kabir’s Bat-tala at Chakdev. (Ch. 0+0 m to 0+595 m) Improvement of "Choto Jamuna" river bank with footpath and street light 3 Construction of RCC drain from Ukilpara sluicegate to Durgapur Beel. (Ch. 0+0 m to 1+800 m) & Link drain ch.0m-ch.300m | 0 | 2695 | 68347889 | M/s A.S Construction,E-799,Katirganj, Rajshahi | 72400190.0891 | 2015-10-07 | 2016-05-07 | 100% | 0 | 57391166 | 0
| UGIIP-III-2/NAOG/UT+DR /01/2016(T.ID:72753) | Part-01: Rehabilitation of B.C road starting from Tulshigonga bridge to Taltola bypass road via Sheikhpura Primary School. Ch.00-2020m, Part-02:Rehabilitation of B.C road starting from Sheikhpura Primary School to Variapara Culvert. Ch.00-770m Part-01:Rehabilitation of B.C road starting from Arji-Naogaon Latapara mour to Arji naogaon dangapara mour Ch.00-470m , Part-02:Rehabilitation of B.C road starting from Tetultala to Daptoripara.Ch.00-600, 2 Part-B:Drain Construction of RCC drain starting from Degree College to DPHE office Ch.00-600m Extensional work of newly constructed Shuormary RCC drain upto the outfall at Durgapur Bridge. Ch.1375-2465m Extensional work of newly constucted Janokalyan drain up to the outfall at Durgapur Beel. Ch.300-710m Construction of RCC drain starting from Red crisent to Kazir mour upto Shourmari Khal via ATM math janata Bank Part-1:Ch.00-600m Part-2: Ch.00-179m and Part-3:00-390m 4 6Part-01:Rehabilitation of B.C road starting from Arji-Naogaon Latapara mour to Arji naogaon dangapara mour Ch.00-470m , Part-02:Rehabilitation of B.C road starting from Tetultala to Daptoripara.Ch.00-600, | 3860 | 3269 | 81328418.32 | MT-DC-MRC (JV),Dewan Bazar,Main Road, Naogoan | 80469724.0007 | 2017-04-02 | 27-03-2018 | 100% | 348096 | 76767514.48 | 0
| UGIIP-III-2/ NAOG/UT+DR /02/2016 (T.ID:72757) | Part-A:Road: Part-01:Rehabilitation of BC road starting from K.D mour to By-pass mour via Degree college in/c road side drain Ch.0.00-3105m, Part-02: Construction of RCC road starting from Coloney Bazar to Solimullah Khan’s house. Ch.00-260m Construction of road Starting from bridge moar to Nabab Optical store by CC . Ch.00-308 Rehabilitation of road starting from Arji naogaon Daptory para mour to the Co operative Training Institute Via Kuddus shop by BC Ch. 00-680m Part-01:Construction of Road starting from Hotel Abakash to Sanyalbari mour by RCC Ch.00-530m. Part-02: Construction of road from Siraj Bazar's house to Sultanpur Purbopara by RCC. Ch.00-1100 Including 03 Nos. RCC cross drain Part-01:Construction of road starting from Infront of Uttara Primary School to B.A.V.S road by RCC Ch.00-325m, Part-02: Construction of road starting from Palal Nibash to Maleka clinic by RCC. Ch.00-90m, Part-03: Construction of Income tax road Ch.00-100m Part-01:Construction of road starting from park road to Naogaon main road via Iqbal house by RCC Ch.00-510m, Part-02:Construction of road starting from Cold storage to Park road near Gudai house by RCC . Ch.00-145m Rehabilitation of BC road starting from Nabab Optical store to Muktir mour via K.D School,Ch,00-985m. Including both side footpath Ch.00-985m 7 Part-B:Drain Construction of RCC drain beside the road K.D moar to By pass Mour via Degree College. Ch.795-1585m Construction of RCC drain beside the roadBridge mour to Nabab optical store (Ch.00-308m) and Outfall drain Ch.00--100m Construction of RCC drain beside the road Arji-naogaon Daptory para mour to the Co-operative Training Institute Via Kuddus shop. Ch.00-680m Part-01:Construction of RCC drain beside the roadstarting from Infront of Uttara Primary School to B.A.V.S road by CC Ch.00-325m, Part-02:Construction of RCC drain beside the road starting from Palal Nibash to Maleka clinic by CC. Ch.00-90m, Construction of RCC drain beside the Road Nabab optical store to Muktir mour via K.D school. Ch.00-400m Construction of RCC drain beside the road from park road to Naogaon main road via Iqbal house Ch.00-330 6 13 Part-01:Rehabilitation of BC road starting from K.D mour to By-pass mour via Degree college in/c road side drain Ch.0.00-3105m, Part-02: Construction of RCC road starting from Coloney Bazar to Solimullah Khan’s house. Ch.00-260m | 8138 | 3023 | 82758427.59 | Ethen-PMPL-JV,Main Road, Naogaon | 81922917.6908 | 2017-03-30 | 27-03-2018 | 100% | 757400.75 | 77840023.67 | 0
| UGIIP-III-2/NAOG/UT+DR/ 03/2016(AF)(T.ID:72759) | Additional financing Part-A:Road: Rehabilitation of CC road starting from District educational office to Ali Pasari house. Ch.00-900m Part-01;Rehabilitation of CC road starting from Hasan Maker's house to Keranipara Monir house Ch.00-965m, Part-02:Rehabilitation of CC road starting from Mahmud house to Mamun house Ch.00-210m,, Part-03:Rehabilitation of CC road starting from Firoj house to Jahangir house Ch.00-210m, Rehabilitation of BC road starting from North Bangal Grain Industries to Durgapur Chowrasta mour. Ch.00-2000m Part-01:Rehabilitation of BC road starting from Boys home to Textile Technical Institute Ch.00-1100m, Part-02:Construction of CC road From Nabir's house to Benu's house. Ch.00-500m Rehabilitation of B.C road starting from Balihar house to Kazir mour Ch.00-580m Including 03 Nos RCC Cross drain. Rehabilitation of BC and CC road starting from vocational school to circuit house. Ch.00-2200 6 Part-B:Drain Construction of RCC drain beside the road Disrict educational office to Ali Pasari house. Ch.100-475m Part-01:Construction of RCC drain beside the road Hasan Makar's house to Keranipara Monir house Ch.00-690m, Part-02: Construction of drain starting from firoj house to Jahangir house. Ch.00-210m Construction of RCC drain starting from KD school moar to Kazir mour janata bank bhaban. Ch.00-810m Construction of RCC drain Part-A: starting from stadium gate to dibetic hospital (Ch.00-250m), Part-B: Starting from Northern side of stdium to Diabetic hospital Ch.00-413m, Part-C: Starting from southern side of stadium to Dibetic hospital.Ch.450-600 and Part-D: Starting from Dibetic hospital to Tulshiganga river Ch.650-1240m. Construction of RCC drain starting from Mr. jalal's house to Sultanpur road side drain near Al-hajj Mukul's house at Sultanpur Ch.00-250m Construction of RCC drain Beside the road boys home to Textile Technical Institute. Ch.480-1100m Constuction of RCC drain beside the road Abdul Jalil primary school to Circuit house road.Ch.00-350m Constuction of RCC drain beside Kalitola road starting from Kalitola mour to Gusto hatir mour. Ch.00-500m 8 14Rehabilitation of CC road starting from District educational office to Ali Pasari house. Ch.00-900m | 8665 | 5208 | 88891832.942 | MT-DC-MRC (JV),Dewan Bazar,Main Road, Naogoan | 87957150.9323 | 2017-07-30 | 2018-07-27 | 99.92% | 1020104.46 | 83134584.02 | 0
| UGIIP-III-2/AF/NAOG/SWM+SN/ 01/2017 | Name of Package: Construction of 01 Nr. Sanitary Landfill (22588 Sqm), 06 Nos Public Toilet & 01Nr. Fecal Sludge Treatment Plant (FSTP) in Naogaon Pourashava under Naogaon District. Sub-Component-01: Sanitary Landfill Construction of 22588 Sqm Sanitary Landfill. Construction of 01 number Landfill Gate. Construction of 862.65 meter Landfill Fence. Construction of 01 number Dump Truck Cleaning Facility. Installation of 01 number Tube Well. Construction of 01 number Control Building. Construction of 01 number Waste Segregation and Equipment Facility. Installation of 21 no Street Light. Environmental Mitigation Enhancement Works. 10 Sub-Component-02: Public Toilet Construction of 1 no Public Toilet (Degree College Morr). Construction of 1 no Public Toilet (Naogaon kitchen market). Construction of 1 no Public Toilet (Muktir Morr). Construction of 1 no Public Toilet (Shopari Putti). Construction of 1 no Public Toilet (Tulshiganga morr). Construction of 1 no Public Toilet (Dowaler Morr, Kacha Bazar). 6 Sub-Component-03: Fecal Sludge Treatment Plant Construction of 06 numbers Screening Chamber. Construction of 03 numbers Planted Drying Bed. Construction of 01 number Settler and Anaerobic Filter. Construction of 01 number Polishing Pond. 4 20 Name of Package: Construction of 01 Nr. Sanitary Landfill (22588 Sqm), 06 Nos Public Toilet & 01Nr. Fecal Sludge Treatment Plant (FSTP) in Naogaon Pourashava under Naogaon District. | 0 | 0 | 62125584.81 | 0 | 0 |  |  | 0% | 0
| Pkg.total:LUGIIP-III-2/AF/NAOG/SI/ 01-06/2018(Lot-01 & Lot-06) | Name of works: Construction of 03 numbers double unit (type-A) toilet with septic tank & soak well, 09 numbers single unit (type-B) toilet with 2 nos sock pit, 830 meter footpath (A=273m, B=237m & C=320m), & 04 numbers tube well. work in Rajakpur Bou-bazar Khalifa Para Slum, Word no-09, Naogaon Pourashava under Naogaon District. Construction of 03 numbers double unit (type-A) toilet with septic tank & soak well. Construction of 09 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 830 meter footpath (A=273m, B=237m & C=320m). Installation of 04 numbers tube well. 4 Name of works: Construction of 04 numbers double unit (type-A) toilet with septic tank & soak well, 11 numbers single unit (type-B) toilet with 2 nos sock pit, 737 meter footpath (A=477m & B=260m), 98 meter brick drain, 05 numbers tube well. work in Sultanpur Dilar Para Slum, Word no-08, Naogaon Pourashava under Naogaon District. Construction of 04 numbers double unit (type-A) toilet with septic tank & soak well. Construction of 11 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 737 meter footpath (A=477m & B=260m). Construction of 98 meter brick drain. Installation of 05 numbers tube well. 5 Name of works: Construction of 03 numbers double unit (type-A) toilet with septic tank & soak well, 10 numbers single unit (type-B) toilet with 2 nos sock pit, 694 meter footpath (A=301m, B=208m & C=185m), 108 meter brick drain (A=74m & B=34m), & 07 numbers tube well. work in Boyaliya Mondol Para Slum, Word no-09, Naogaon Pourashava under Naogaon District. Construction of 03 numbers double unit (type-A) toilet with septic tank & soak well. Construction of 10 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 694 meter footpath (A=301m, B=208m & C=185m). Construction of 108 meter brick drain (A=74m & B=34m). Installation of 07 numbers tube well. 5 Name of works: Construction of 03 numbers double unit (type-A) toilet with septic tank & soak well, 08 numbers single unit (type-B) toilet with 2 nos sock pit, 650 meter footpath (A=163m, B=186m & C=301m), 98 meter brick drain & 07 numbers tube well. work in T & T Para Slum, Word no-08, Naogaon Pourashava under Naogaon District. Construction of 03 number double unit (type-A) toilet with septic tank & soak well. Construction of 08 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 650 meter footpath (A=163m, B=186m & C=301m). Construction of 98 meter brick drain. Installation of 07 numbers tube well. 5 Name of works: Construction of 09 numbers single unit (type-B) toilet with 2 nos sock pit, 547 meter footpath, 202 meter brick drain, 07 numbers solar street light & 06 numbers tube well. work in Per-naogaon Sardar Para Slum, Word no-09, Naogaon Pourashava under Naogaon District. Construction of 09 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 547 meter footpath. Construction of 202 meter brick drain. Instrolation of 07 numbers solar street light. Installation of 06 numbers tube well. 5 Name of works: Construction of 13 numbers single unit (type-B) toilet with 2 nos sock pit, 419 meter footpath (A=243m & B=176m), 110 meter brick drain & 03 numbers tube well. work in Per-naogaon Madrasha Para Slum, Word no-07, Naogaon Pourashava under Naogaon District Construction of 13 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 419 meter footpath (A=243m & B=176m). Construction of 110 meter brick drain. Installation of 03 numbers tube well. 4 28Name of works: Construction of 03 numbers double unit (type-A) toilet with septic tank & soak well, 09 numbers single unit (type-B) toilet with 2 nos sock pit, 830 meter footpath (A=273m, B=237m & C=320m), & 04 numbers tube well. work in Rajakpur Bou-bazar Khalifa Para Slum, Word no-09, Naogaon Pourashava under Naogaon District. | 0 | 0 | 33179906.45 | [5 empty] | 0
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Charghat
Pourashava Code : 48
2. Charghat
| PKG Total:UGIIP-III-I/ CHAR / UT+DR / 01 / 2014(Lot-01&2) | Construction of Footpath from Charghat Pourashava to Health Complex & Widening of BC road from Miapur Culvert to Charghat Upazilla Complex with Foot path by Dense Bituminous Carpeting (Ch. 0+0 m to 1+180 m) & Construction of RCC U Drain (Ch. 0+0 m to 1+300 m) & RCC U Drain via Charghat Bazar More (Ch. 0+0 m to 1+160 m) under Ward No - 6. Construction of road from Shaheen’s house to Kadir’s house & link Raza Master’s house to Salim Daroga’s house via kadir’s house & Emal’s house to Nur Mohammad`s shop with G.Wall by Dense Bituminous Carpeting. (Ch. 0+0 m to 0+885.52 m) & 1 Cross drain at Thanapara with Side Tertiary Drain (Ch. 0+0 m to 0+900 m) Under Ward No - 5. 2 Construction of RCC primary drain from Meramatpur cinema hall to the Padma river. (Ch-0.00 to 0+888.73 m). Construction of RCC primary drain from Miapur Waz’s house to the Baral river. (Ch:-0.00 to 0+730 m) 2 4 Construction of Footpath from Charghat Pourashava to Health Complex & Widening of BC road from Miapur Culvert to Charghat Upazilla Complex with Foot path by Dense Bituminous Carpeting (Ch. 0+0 m to 1+180 m) & Construction of RCC U Drain (Ch. 0+0 m to 1+300 m) & RCC U Drain via Charghat Bazar More (Ch. 0+0 m to 1+160 m) under Ward No - 6. Construction of road from Shaheen’s house to Kadir’s house & link Raza Master’s house to Salim Daroga’s house via kadir’s house & Emal’s house to Nur Mohammad`s shop with G.Wall by Dense Bituminous Carpeting. (Ch. 0+0 m to 0+885.52 m) & 1 Cross drain at Thanapara with Side Tertiary Drain (Ch. 0+0 m to 0+900 m) Under Ward No - 5. 2 Construction of Footpath from Charghat Pourashava to Health Complex & Widening of BC road from Miapur Culvert to Charghat Upazilla Complex with Foot path by Dense Bituminous Carpeting (Ch. 0+0 m to 1+180 m) & Construction of RCC U Drain (Ch. 0+0 m to 1+300 m) & RCC U Drain via Charghat Bazar More (Ch. 0+0 m to 1+160 m) under Ward No - 6. | 5425.52 | 1618.73 | 104199980.59 | F.A.R (JV), A/102,Upashahar,Sopura Boalia,Rajshahi | 110419143.1093 |  |  | 100% | 936363 | 91230038 | 0
| UGIIP-III-2/CHAR/ UT+DR /01/2016(T.ID:77914) | Improvement & Rehabilitation of road by DBS from Miapur Shamsul’s mill to Elahi Box’s house via Gafur’s house by DBC (Ch.00-1566m) with Link-01: Graveyard road by DBC (Ch.00-183m) Link-02: Alam mistry’s house to Rahila’s house by DBC (Ch.00-980m) Rehabilitation of road by DBS Starting from Bagha road to Arani road by DBC (Ch.00-180m) Rehabilitation of road by DBS Part-A: Starting from Ashkarpur Anes’s house to Siddik’s house by DBC (Ch.00-930m) with Link-L: Mozaffar’s house to Dulal’s house by DBC (Ch.00-60m) Part-B: Starting from Ashkarpur Mosque to Matin’s house by DBC (Ch.00-411m) with Link-1: Sultan’s house to Faruk’s house by DBC (Ch.00-45m) & T-Junction Near Enamul’s house (Ch.00-10.00m) Rehabilitation of road Starting from Kuthhipara T&T More to PA Boudary by (Ch00-530m) Construction & Rehabilitation of road by DBS Part-A: Starting from Polly biddut more to P/A Boundary wall attached Swallows by DBC (Ch.00-720m) Part-B: House of Togor to P/A Boundary wall by DBC (Ch.00-347m) Construction of Footpath at Mokterpur Traffic More (Ch.00-600m) Shardah Bazar(Ch.00-660m) & Pourashava to Pally Biddut More (Ch.00-200m) Rehabilitation of road Starting from Shardah Bazar to Shadipur Madrasa by DBC (Ch.00-1490m) Improvement of road Part-A: Starting from Sarkar para road to Moktarpur road by DBC (Ch.00-735) & Part-B: Starting from Sreekhandi road to EX. BC Bagha road by DBC (Ch.00-1074) With T-Junction (Ch.00-10m) at Moktarpur. Improvement of road Starting from Gani Kasai’s house to Charghat Thana/ Police Station by DBC (Ch.00-225m) Improvement of road Starting from Sattar's house to Aynal Pramanik’s Pond by DBC (Ch.00-510m) 10 Construction of RCC Drain beside Road Starting from T&T more Police to Academy Boundary wall (Ch. 530 to 00m) Construction of RCC Secondary Drain from Askerpur Anis house to Askerpur mosque (Ch.00-950m) Link-01: (Ch.00-80m) Construction of RCC Drain Starting from Sarda Bazar moor to Askerpur mosque (Ch.00-120m) Construction of RCC Drain beside road Starting from Charghat Gani Baocher’s house to Boral River via Charghat Thana (Ch.00-435m) Construction of RCC Drain Beside road Starting from Police Academy gare No.-1 to Pally Biddut moor (Ch. 720 to 00m) 5 15Improvement & Rehabilitation of road by DBS from Miapur Shamsul’s mill to Elahi Box’s house via Gafur’s house by DBC (Ch.00-1566m) with Link-01: Graveyard road by DBC (Ch.00-183m) Link-02: Alam mistry’s house to Rahila’s house by DBC (Ch.00-980m) | 11466 | 2835 | 82570835.561 | Liton Traders,Pro:Md. Mizanur rahman, Modon mohon Para,Jhenaidha | 81265242.3614 | 0 | 2018-05-17 | 54.09% | 1992813.49 | 49473905
| UGIIP-III-2/CHAR/ UT+DR /02/2016(T.ID:77913) | Improvement of road Starting from Dafadarpara Gani's house to Mafiz's house by DBC (Ch.00-300m) Rehabilitation of road Part-A: Starting from H/O Polan to H/O Mongla via Earsad’s Pond by DBC (Ch.00-875m) With Link(a)-1:H/O Murad to H/O Siraz by DBC (Ch.00-75m) & Link(a)-2: H/O Tushar to Cadet College road by DBC (Ch.00-210m) Part-B: Earsad’s Pond to H/O Samsul Police via H/O Bakkar Cou. by DBC (Ch.00-574m) With Link(b)-1: H/O Tahaz to H/O Mokbul by DBC (Ch.00-60m) & Link(b)-2: H/O Tushar to Cadet College road by DBC (Ch.00-150m) Part-C: Pakianpara Mosque to H/O Hakim by DBC (Ch.00-170m) Improvement of road Part-A: Starting from H/O Manu mistry attached High way To T&T by DBC (Ch.00-823) Part-B: Starting from Warid Tawer to Padma river by DBC (Ch.00-510) Part-C: Starting from Hashu vila to Kandu member by DBC (Ch.00-180) & Part-D: Starting from Bablu’s shop to H/O Jamal Khalifa by DBC (Ch.00-260m) Construction & Rehabilitation of Internal road Charghat Upazilla Parishad by DBC Total Length=716m Improvement of road Starting from Hasor's house to Gofur's house by DBC (Ch.00-190m) & Connecting road starting from Ramjan's house to Chairman Aftab Sarker's house by DBC (Ch.230-550m) 5 Construction of RCC Drain beside Upazila Parishad road Part-A: (Ch.00-168m) Link: (Ch.00+35m) Part-B: (Ch.00-276m) Construction of RCC Primary Drain from Shardah Bazar to Boral River(Ch. 0.00-1+930.00m) 2 7Improvement of road Starting from Dafadarpara Gani's house to Mafiz's house by DBC (Ch.00-300m) | 5413 | 2409 | 83742138.49 | MMWH-MMS JV,Pro; Md. Shamsuzzaman,D-119,Dorgapara,Rajshahi | 83541266.1702 | 0 | 2018-05-18 | 72.46% | 1426549.15 | 3058980.83 | 0
| UGIIP-III-2/AF/CHAR/WS/01/2017(T.ID:148738) | water Supply Construction and Installation of 5 nos Production Tube-wells with pump house &rehabilitation of existing 1 no existing PTW,1 nr Overhead Tank(Capacity 680m3),50 nrs hand Tube-well/ 25,500m distribution Pipeline/1500 nos water metering and others in different places of Charghat Pourashava, Rajshahi. Sub-Component: 01 : Production Tube-Well (A) Installation of 05 nr. Test and 05 nr. Observation Well (B) Installation of 05 nr. Production Wells (C ) Construction of 05 nr. Pump houses (D) Construction of Boundary wall for 03 Pump Houses (E ) 05 sets Mechanical works of Pump-motor ( F) 05 sets Electric works for Pump and Pump houses ( G ) 01 set Rehabilitation works for PTW 8 Sub-Component: 02 :Pipeline Installation of 25,500 meter Pipeline (Distrbution =110mm dia.=19,000 meter and 160mm dia.=5,000 meter and Transmision=160mm dia.=1,500 meter) 1 Sub-Component: 03 :Domestic Water Meter Supply and Installation of 1,500 nr. Donmestic Water Meter (13 mm dia.= 375 nr.,20mm dia=850 nr. and 25mm dia=275 nr.) 1 Sub-Component: 04 :Construction of Overhead Tank (OHT) 01 nr. Overhead Tank (Capacity 680 m3) 1 Sub-Component: 05 : Installation of Hand Tube-well (HTW) Installation of 50 nr. Hand Tube-well (HTW) 1 12Construction and Installation of 5 nos Production Tube-wells with pump house &rehabilitation of existing 1 no existing PTW,1 nr Overhead Tank(Capacity 680m3),50 nrs hand Tube-well/ 25,500m distribution Pipeline/1500 nos water metering and others in different places of Charghat Pourashava, Rajshahi. | 0 | 0 | 82837339.67 | Mukta Construction Limited,Prop:Sayed abdur Rauf Mukta,Eastern Mantion,67/9(Ist floor),Pionear road,Kakrail,Dhaka | 74250000 | 0 | 0 | 12.16% | 0 | 0 | 0
| UGIIP-III-2/AF/CHAR/SWM+SN/01/2017 | Construction of 1 Nr. Sanitary Landfill(7808m2) &1 nr. Faecal Sludge Treatment Plant &6 no Public toilet in Charghat Pourashava under Rajshahi District. Sub-Component-01: Sanitary Landfill Construction of 7808 Sqm Sanitary Landfill. Construction of 01 number Landfill Gate. Construction of 505.44 meter Landfill Fence. Construction of 01 number Dump Truck Cleaning Facility. Installation of 01 number Tube Well. Construction of 01 number Control Building. Construction of 01 number Waste Segregation and Equipment Facility. Environmental Mitigation Enhancement Works. 1 Sub-Component-02: Public Toilet Construction of Public Toilet (Charghat Bazar). Construction of Public Toilet (Charghat Shaheed Minar). Construction of Public Toilet (Shardah Bazar). Construction of Public Toilet (Mokterpur Traffic Morr). Construction of Public Toilet (Kakramari Bazar). Construction of Public Toilet (Mokterpur Bazar). 6 Sub-Component-03: Fecal Sludge Treatment Plant Construction of 06 numbers Screening Chamber. Construction of 03 numbers Planted Drying Bed. Construction of 01 number Settler and Anaerobic Filter. Construction of 01 number Polishing Pond. 1 8Construction of 1 Nr. Sanitary Landfill(7808m2) &1 nr. Faecal Sludge Treatment Plant &6 no Public toilet in Charghat Pourashava under Rajshahi District. | 0 | 0 | 39587690.69 | 0 | 0 |  |  | 0% | 0 | 0 | 0
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Bera
Pourashava Code : 74
| 3. Bera |  |  |  | 0 | [5 empty] | 0
| PKG Total :UGIIP-III-I/ BERA / UT+DR / 01 / 2014(Lot-01(UT)& Lot-02(DR.): | Construction of Road from Professor Abu sayed house to Bakker’s house by Dense Bituminous Carpeting. (Ch. 0+0 m to 0+777 m) Construction of Road from Advocate Samsul Haque Iuku house to WDB Bridge via High house by Dense Bituminous Carpeting. (Ch. 0+0 m to 1+500 m) Improvement of Road from Bera Pumping Station wall to Moin Daroga Shorok by Dense Bituminous Carpeting. (Ch. 0+0 m to 0+550 m) Construction of road starting from Bonogram Unus Mia house to Uttar Takurbari bylane Anawer Kha house by RCC. (Ch. 0+0 m to 0+803 m). Improvement of Road from house of Benu Datta to Upazila main road by Dense Bituminous Carpeting. (Ch 0+0 m to 1+000 m). Improvement of Road from Kanaibari moar to Taghori by Dense Bituminous Carpeting. (Ch. 0+0 m to 2+685 m) Improvement of Road from Hatigara milk society to Paina Chapra mosque by Dense Bituminous Carpeting. (Ch. 0+0 m to 1+781 m) Improvement of Road from WDB flood control embankment near Khaleque Driver house to Paikhando WDB Embankment via Eidgha by Dense Bituminous Carpeting. (Ch. 0+0 m to 1+095 m) Construction of road starting from Nawser house to Paikhando Natunpara Hamid house by RCC. (Ch. 0+0 m to 0+400 m). Construction of road starting from Paikhando Primary school to Hura Sagor river via Amjad house by RCC. (Ch. 0+0 m to 0+500 m). 10 Construction of RCC drains from Professor Abu sayed house to Bakker’s house. (Ch. 0+0 m to 0+777 m) Construction of RCC drains from Brishalikha Azim Pramanic house to WDB Embankment. (Ch. 0+0 m to 0+300 m) Construction of RCC drains from Nurul Chatal to Kader Dr. moar (Bera Bazer Baser Hazi shop to Dhaniahat Bridge. (Ch. 0+500 m to 0+800 m) Construction of RCC drains from Isamoti Cinema Hall to Shahid Abdul Khaleque Stadium. (Ch. 0+0 m to 1+130 m) Construction of RCC drains from Dhaniahat Bridge to Kanaibari mour. (Ch. 0+0 to 0+700) 5 Construction of Road from Professor Abu sayed house to Bakker’s house by Dense Bituminous Carpeting. (Ch. 0+0 m to 0+777 m) | 11091 | 3207 | 113939009.97 | M/s Khandaker Shahin Ahmed,Puran Palton,Dhaka | 119793750.3319 | 30/05/15 | 27/05/15 | 100% | 2224768 | 109396492.22 | 0
| UGIIP-III-2/ BERA/ UT+DR /01 /2016 | Improvement of road Starting from Bera C&B near Nazim house to Mohongang three way junction by DBC (Ch.00-7540m) 1 Construction of footpath cum RCC Drain Starting from Bangabaria khas pond to Boroshila main road (Ch.00-1000m) 1 2Improvement of road Starting from Bera C&B near Nazim house to Mohongang three way junction by DBC (Ch.00-7540m) | 7540 | 1000 | 118401400.83 | M/s Shahid-M.A Enterprise-JV,Elid house,54, Matijil,Dhaka | 122392874.539 | 2017-05-10 | 2018-05-02 | 77.75% | 0 | 95224256.68
| UGIIP-III-2/ BERA/ UT+DR /02 /2016 | Improvement of road starting from Isamoti Cinema Hall near Bera-Mathpur road to shahid Abdul khaleque stadium by DBC (Ch.00-1125m) Improvement of road starting from Kader Doctor mooar to WDB Embankment near Hurul Chatal at Bonogram by DBC (Ch.00-1190m) Construction of road starting from Brishalikha Entaz house to Brishalikha footpath field via Azim Pramanic house house by RCC (Ch.00-1500m) 3 Construction of RCC Drain starting from Dak Bangla to Abu Sayed house. Ch.00-500m Construction of RCC Drain starting from Taltola Moor to Abu Sayed house. Ch.00-435m Construction of RCC Drain starting from Stadium to Bera High School. Ch.00-650m Construction of RCC Drain starting from Isamati Cenema Hall to Bera Girls School. Ch.00-525m Construction of RCC Drain starting from Hospital Canal to C&B Ch.00-600m Construction of RCC Drain starting from Fokir Chatal to H. Canal. Ch.00-220m Construction of RCC Drain starting from Fokir Chatal to Fokir Plaza Ch. 0+000 to 0+350 km. Construction of RCC Drain starting from Fokir Existing Drain to kader DR Moor Ch. 0+000 to 0+570 km. 8 11 Improvement of road starting from Isamoti Cinema Hall near Bera-Mathpur road to shahid Abdul khaleque stadium by DBC (Ch.00-1125m) | 3815 | 3850 | 89215830.34 | Mohammad Eunus & Brothers(Pvt) Ltd.,67 Panchlaish R/A, chittagong | 92843412.9494 | 2017-05-10 | 2018-05-02 | 100% | 79213.68 | 92922626.7
| UGIIP-III-2/AF/ BERA/ SWM+SN /01 /2017 | Additional Financing Construction of 01 Nr. Sanitary Landfill (12540 Sqm), 09 Nos Public Toilet & 01Nr. Fecal Sludge Treatment Plant (FSTP). Work in Bera Pourashava under Pabna District. Sub-Component-01: Sanitary Landfill. a)Construction of 12540 sqm sanitary landfill. b)Construction of 01 number landfill gate. c)Construction of 466.56 meter landfill fence. d)Construction of 01 number dump truck cleaning facility. e)Installation of 01 number tube well. f)Construction of 01 number control building. g)Construction of 01 number waste segregation and equipment facility. h)Construction of 01 number waste transfer station (brishalikha). i)Installation of 20 numbers street light. j)Environmental mitigation enhancement works. 9 Sub-Component-02: Public Toilet. a)Construction of 01 number public toilet (mohanganj bazar). b)Construction of 01 number public toilet (neyamotganj siddiqueya hafiziya madrasha). c)Construction of 01 number public toilet (dak bangla bazar). d)Construction of 01 number public toilet (dak bangla chicken market). e)Construction of 01 number public toilet (bishalikha growth centre). f)Construction of 01 number public toilet (bera bazar east side). g)Construction of 01 number public toilet (bera bazar west side). h)Construction of 01 number public toilet (kanai bazar morr). i)Construction of 01 number public toilet (bera bazar near BB school). 9 Sub-Component-03: Fecal Sludge Treatment Plant. a)Construction of 06 numbers screening chamber of faecal sludge treatment plant (FSTP). b)Construction of 03 numbers planted drying bed of faecal sludge treatment plant (FSTP). c)Construction of 01 number settler and anaerobic of faecal sludge treatment plant (FSTP). d)Construction of 01 number polishing pond of faecal sludge treatment plant (FSTP). 1 19 Construction of 01 Nr. Sanitary Landfill (12540 Sqm), 09 Nos Public Toilet & 01Nr. Fecal Sludge Treatment Plant (FSTP). Work in Bera Pourashava under Pabna District. | 0 | 0 | 67749734.11 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0
| UGIIP-III-2/AF/ BERA/WS /01 /2017 | Construction and Installation of 01 nos. Pump House, 22.5 km Pipeline, Supply and Installation of 2,000 domestic water meters for metering of existing non-metered service connections and proposed new service connections and others in different places of Bera Pourashava, Pabna. Sub-Component: 01 : Production Tube-Well (A)Construction of 01 nr. Pump houses (B)Construction of Boundary wall for 01 Pump Houses (C)02 sets Mechanical works of Pump-motor (D)02 sets Electric works for Pump and Pump houses 4 Sub-Component: 02 :Pipeline Supply and Installation of 2,000 nr. Donmestic Water Meter (13 mm dia.= 635 nr.,20mm dia=1319 nr., and 25mm dia=46 nr.) 1 Sub-Component: 03 :Domestic Water Meter Installation of 22,550 meter Pipeline (Distrbution =110mm dia.=11,500 meter, 160mm dia.=11,000 meter and Transmision=225mm dia. = 50 meter) 1 Construction and Installation of 01 nos. Pump House, 22.5 km Pipeline, Supply and Installation of 2,000 domestic water meters for metering of existing non-metered service connections and proposed new service connections and others in different places of Bera Pourashava, Pabna. | 0 | 0 | 54720620.73 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0
| UGIIP-III-2/AF/ BERA/ UT+DR /03/2018 | Name of works: Rehabilitation of 4645.00 m. Road including 4145.00 m. slope protection work in 02 Locations & Construction of 100m Drain in 01 Location at Bera Pourashava under Pabna District. Part:A:Road Rehabilitation & widening of road starting from Paina Sapra Mosque to Mohongang Three way Junction by DBC. (Ch.0+00 to 3+000 km) & Including 2+500km slope protection work Rehabilitation & widening of road starting from Bera C&B Isamoti Bridge to Brishalikha Isamoti Closer by DBC. (Ch.0+00 to 1+645 km) & Including 1+645km slope protection work 2 Part-B:Drain Construction of RCC drain starting from Bishalika WDB Embankment to Kalibari. Ch 325-425m 1 3Name of works: Rehabilitation of 4645.00 m. Road including 4145.00 m. slope protection work in 02 Locations & Construction of 100m Drain in 01 Location at Bera Pourashava under Pabna District. | 4645 | 100 | 153552643.87 | Mohammad Eunus & Brothers(Pvt) Ltd.,67 Panchlaish R/A, chittagong | 0 |  |  | 0% | 120960 | 0 | 0
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
PourashavaName : Ishwardi
Pourashava Code : 73
| 4. Ishwardi |  | 0 | 0 | 0 |  | 0 |  |  |  | 0
| UGIIP-III-I/ ISHW / UT+DR / 01 / 2015(Lot-01(Ut+DR) | Lot-01(UT+DR):Part-A : Road Rehabilitation & widening of College road starting from chad Ali More Thakur bari Mondir to Pabna Road Via Aronkola Hat by DBC (Ch-0+00-3+300m.) & one no. X-Drain at Ch 1000 m Improvement of Naricha Notun Para connecting road starting from Nowab Shirajdoulla road to Islampur B.C road by DBC. (Ch. 0+00-0+505m) Improvement & Rehabilitation of Valupara Madrasha road. (ch. 0+00-1+080m.) and connecting road starting from I.K road to main road ch. 280m.(ch. 0+00-0+232m.) by DBC. & six nos. X-Drain. Part-A: Improvement of conecting road by DBC starting from college road to Bongobondhu school road (ch. 0+00-0+260m) Part-B: Improvement of connecting road by DBC starting from Bongobondhu school (Betu House) to Mosuria Para road (ch. 0+00-0+305m) Improvement of Rupnagor connecting road by CC Starting form College road to Khot Khoti Para BC Road (ch. 0+00-0+410m) Part(A): Improvement of Madrasha connecting road by DBC starting from Idgha BC road to Ambagan BC road (ch. 0+00-0+145m) Part(B): Improvement of Jona Kobiraj connecting road by CC starting from Ambagan road to Idgaha road. (ch. 0+00-0+116m) 7 Lot-01(UT+DR):Part-B : Drain Constrution road side drain from college road to Mosuria para road via Bongobondhu school road (ch. 0+00-0+560m) Construction of R.C.C. Drain starting from Bokul More to Aronkola Khal. (ch. 0+00-1+038m) 2 9Rehabilitation & widening of College road starting from chad Ali More Thakur bari Mondir to Pabna Road Via Aronkola Hat by DBC (Ch-0+00-3+300m.) & one no. X-Drain at Ch 1000 m | 6353 | 1598 | 68221875.27 | Dhrubo Construction Ltd., Krishnapur, Pabna | 69423744.2399 | 2016-03-10 | 2017-03-09 | 100% | 1463581.39 | 54485710.75
| UGIIP-III-I/ ISHW / UT+DR / 01 / 2015(Lot-02(UT+DR)) | Lot-02(UT+DR):Part-A : Road Improvement of Girls school road starting from girls school More to Nofel House Bottola via Moubaria Mondir by DBC (ch. 0+00-1+590m) Improvement of Connecting road by CC starting from Airport Road to babu para BC road via Mohosin Riaji House ( ch. 0+00-0+216m) Construction of road starting from Shoylopara Sugarcane perches center to airport boundary road by DBC (ch.0+00-0+515m) Rehabilitation of Tipusultan Road starting from Rail Gate to Taltola More by DBC. (ch.0+00-0+3000m.& one no. X-Drain at Ch 1800 m Improvement of Shara Gopalpur Moulobepara Road by DBC starting from Tipusultan road to Culvert (ch.0+00-0+530m) Improvement of Piarakhali Majdia road by DBC starting from Mofiz (Bodor) House to the end of Pourashava Boundary (ch.0+00-0+500m.) Rehabilitation & widening of Loco road from chad Ali More to Fotemohammadpur rail gate Via Fotamohammodpur Graveyard by DBC (ch.0+00-2+085m) Rehabilitation connecting road starting from Loco road to Benaroshipolly BC road by DBC (ch. 0+00-0+500m.) Improvement Loco Behari Bazar connecting road by CC starting from Faruk road to Loco main road (ch. 0-00-0+780m) & two nos. X-Drain at Ch 330m & 740m Rehabilitation of Stadium Road by DBC starting from Shersha Road to Umirpur Ista road (ch. 0+00-2+442m) Improvement of connecting road by CC starting from Shersha Raod Near Gini House to Hospital road (ch. 0+00-0+163m) 11 Lot-02(UT+DR):Part-B : Drain Construction of road side drain at Loco road from chad Ali More to Fotemohammadpur rail gate Via Fotamohammodpur Graveyard (ch.0+636-0+779m) & one no. X-Drain Construction of road side connecting drain starting from Shersha Raod Near Gini House to Hospital road (ch. 0+00-0+156m) Construction of R.C.C. main Drain from S.M High School to Hospital road culvert. (ch. 3+215-3+312m), (ch. 3+697-3+835m) & (ch. 3+915-4+055m) 3 14 Improvement of Girls school road starting from girls school More to Nofel House Bottola via Moubaria Mondir by DBC (ch. 0+00-1+590m) | 12321 | 674 | 57495402.29 | RE & AR JV, Baghail, Paksey, Pabna | 60367344.2996 | 2016-03-10 | 2017-03-09 | 100% | 738914.18 | 49045780.77 | 0
4.Ishwardi
| UGIIP-III-2/ISHW/UT+DR/01/2016(T.ID:80140) | Part(B): Rehabilitation & Widening of road by DBC from College road (Bokul Morr) to Coba Mosque via Alobug Pabna Road (Ch. 0.00-1080)m. & Connecting Road from Ali Bordi Road to Shefa House (Ch. 0.00-205)m. Part(A): Rehabilitation of road by DBC from A.K. Shadi road to College road & Shafa house to Alibordi road. (Ch. 0.00-1025)m & Connecting Road from (Ch. 0.00-120, Ch. 0.00-75, Ch. 0.00-245 & Ch. 0.00-145)m & Part-(B) Construction of road by CC from College Road by Len Tofazzol House Via Jigatola Road (Ch. 00-530)m Rehabilitation of road by DBC. Shoylopara By-pass station road (Ch. 0.00-1290)m & Connecting Road from Shoylopara Graveyard morr to Loco road (ch. 0.00-78)m Rehabilition of Babupara Road by DBC. from Kholil morr to Joshim Mondol House road (Ch. 0.00-640)m & Connecting road from Babupara Mosque to Goni Guard House (Ch. 0.00-505)m. Part(A): Rehabilitation of road by DBC. Aronkhola Hate Madrasha road (Ch. 0.00-450)m & Connecting road from Madrasha road to Miaprara Mosque (Ch. 0.00-480)m. & Part-(B) Construction of RCC X-Drain (Ch. 05)m & (Ch. 230)m. 5 part-B:road "Part-(B): Construction of RCC. main drain from S.M School to Alhaz morr via Hospital road (Ch. 0.00-25)m, (Ch. 1087-1119.50)m, (Ch. 1147.25-1227.25)m, (Ch. 1456.25-1614.20)m, (Ch. 1650.75-1687)m. " "Construction of road side RCC Drain from College road to Zigatala (Ch. 0.00-490)m & Connecting Drain from (a) Zigatal road to Girls School (Ch. 0.00-210)m, (b) Zigatala road to Azahar Propffeser House (Ch. 0.00-250)m, (c) Zigatala road to Hospital road via Zia House (Ch. 0.00-350)m, (d) Zigatala road to Khatkhati Para (Ch. 0.00-160)m, (e) Shersha road Nasimur Rahman Shorif House to A.K. Sadi road Drain (Ch. 0.00-350)m. & Construction of RCC X-Drain (Ch. 210)m, (Ch. 250)m, (Ch. 350)m & (Ch. 160)m. " Part-(A): Construction of road side RCC Drain from Jamtala Abul Hossain House to Tohshil Office Culvert (Ch. 0.00-1150)m & Connecting road from (a) Don House to Shohid House (Ch. 0.00-400)m. "Part-(A): Construction of R.C.C Drain from Lotu guard house to hospital road culvert via Fozlu house (Ch. 0.00-170)m. & Construction of RCC X-Drain (Ch. 110)m, & (Ch. 155)m. " "Part-(A): Construction of RCC road side Drain from Babupara Kholil morr to Jashim Moldil House (Ch. 0.00-620)m & Connecting Drain from (a) Babupara Mosjid to Kamimi Hospital Culvert (Ch. 0.00-80)m & (b) Chamon House to Main road (Ch. 0.00-85)m. & Construction of RCC X-Drain (Ch. 410)m. " 5 10 Part(B): Rehabilitation & Widening of road by DBC from College road (Bokul Morr) to Coba Mosque via Alobug Pabna Road (Ch. 0.00-1080)m. & Connecting Road from Ali Bordi Road to Shefa House (Ch. 0.00-205)m. | 6868 | 4646.7 | 79153790.88 | Infinity Engineering Ltd.,Chairman Md. Feroz Alam Patwari,144 no. Cantonment Super Market,Nabinaghar ,Ashulia, dhaka | 71099877.8606 | 2017-06-20 | 2018-06-14 | 61.18% | 1382639.33 | 26752923.54 | 0
| UGIIP-III-2/ISHW/UT+DR/02/2016(T.ID:80166) | Part-A:Road R-01(PDP-31): Part(A): Rehabilitation of Biman Bondor road by DBC. from Kobi Mokbul Shorok of Daffodil to Oshit Professor House road (Ch. 0.00-1250) & Connecting road from (a) Bimanbondor road (Ch. 0.00-350)m, (b) Piarakhali morr to Piarakhali Graveyard (Ch. 0.00-380)m, (c) Piarakhali Mosque to Jhontur morr (Ch. 0.00-120) & (d) Chomon morr to Babupara road (Ch. 0.00-60)m. Part(B): Rehabilition & Widening of road by DBC. from Vhutargari morr to Naricha Zinna house (Ch. 0.00-615)m & Cannecting road from (a) Zinna house road to Vhuter Gari Mosque (Ch. 0.00-840)m & (b) Vhuter Gari Mosque road to Ahad Councilor house. (Ch. 0.00-120)m. Part(C): Construction of RCC X-Drain from Vhutergari more to Zinna House road (Ch. 485)m, Connecting road (a) Stating from Zinna House road to Vhutergari Mosque road (Ch. 20)m, Connecting (b) Zinna House Road - Ahead Commissioner House Road. Part(A): Rehabilitation of road by DBC. from Poura Para Pourashava Mosque Road to Pabna Road (Ch. 0.00-760)m & Connecting road (a) Robi House (Ch. 0.00-225)m, (b) Baby House (Ch. 0.00-90)m. "Part-(A): Rehabilitation of road by DBC. from Loco Tanki Morr to Banarossi Polly & Primari school Road (Ch. 0.00-1250)m & Cannecting Road (a) Karim House (Ch. 0.00-337)m, (b) Banarossi Polly road (Ch. 0.00-394)m, (c) Pramanik Para (Ch. 0.00-360)m & (d) Fotemahammadpur Math Para (Ch. 0.00-325)m. Part-(B): Construction of RCC X-Drain (Ch. 350)m. " "Part-(A): Rehabilitation of road by DBC. from Ista Velupara Mosjid Morr to I K road (Ch. 0.00-1202)m & Connecting road from Velupara Masjid Road to Graveyard road (Ch. 0.00-136)m. Part-(B): Construction of RCC X-Drain (Ch. 333)m, (Ch. 381)m, (Ch. 470)m & (Ch. 785)m. " 5 Part-B:Drain "Part-(A): Construction of RCC road side Drain from School Para Rahim Sir House to Kamini Hospita Culvert (Ch. 0.00-900)m. & Connecting Drain from (a) Montu Mia House to Kamini Hospital road side Drain (Ch. 0.00-400 m). & Construction of RCC X-Drain (Ch. 400)m, (Ch. 583)m, (Ch. 207)m & (Ch. 400)m. " Part-(A): Construction of road side RCC Drain from Pabna road to Culvert (Ch. 0.00-520)m. & Connecting Drian Refuji Camp 1no. Goli (Ch. 0.00-270)m. & Construction of RCC X-Drain (Ch. 270)m. & (Ch. 320)m. Part-(B): Construction of RCC road side Drain Hospita road Tula Babu House Graved Yeard (Ch. 0.00-150)m. & Connecting Drain from (a) Tula Babu House to Basher House (Ch. 0.00-98)m & (b) BMDF Drain to T.T.E House (Ch. 0.00-60)m. & Construction of RCC X-Drain (Ch. 150)m. Part-(A): Construction of RCC road side Drain from Pourashova road to Stadiam (Ch. 500-960)m. & Connecting Drain from (a) Pourashava Gate to Moddho Aron Khola Afser House (Ch. 0.00-650)m & Construction of RCC X-Drain (Ch. 620)m. 4 9 R-01(PDP-31): Part(A): Rehabilitation of Biman Bondor road by DBC. from Kobi Mokbul Shorok of Daffodil to Oshit Professor House road (Ch. 0.00-1250) & Connecting road from (a) Bimanbondor road (Ch. 0.00-350)m, (b) Piarakhali morr to Piarakhali Graveyard (Ch. 0.00-380)m, (c) Piarakhali Mosque to Jhontur morr (Ch. 0.00-120) & (d) Chomon morr to Babupara road (Ch. 0.00-60)m. | 8814 | 3508 | 64751173.64 | Khan & Sons Bangladesh limited & M/s Hossain Brothers (JV),Director Md. Mojibur Rahman,10 Dilkhusha,C/A. Dhaka | 54401025.8901 | 2017-06-20 | 2018-06-14 | 66.78% | 969842.16 | 26579616.47 | 0
| UGIIP-III-2/ISHW/UT+DR/03/2016(T.ID:80148) | Part-A:Road Rehabilitation of road by DBC. from Mosuria Para Nabab Sherajuddula Road to Nur Mohallah Via Dr. Mannan Mosque (Ch. 0.00-850)m, Connecting (Ch. 0.00-100)m. & Connecting road from (a) Mannan House to Amirul House by CC. (Ch. 00-350)m, (b) Sheraj house Runu Mondol Rice Mill Road by CC. (Ch. 60-330m) & (c) Azahar Pond to Mohoshin House by CC. (Ch. 0.00-370)m. Part-(B): Rehabilitation & Improvement of road by DBC. from Sherajuddula road infront of By Lane Kamarpara Substation via Lalu Driver House to Aminul Commessonar House road (Ch. 0.00-612)m & Connecting road from Lalu Driver House to Existing Pouro Road (Ch. 00-80)m. Part-(C): Construction of RCC X-Drain (Ch. 25)m. & (Ch. 75)m. Part-(B): Improvement & Rehabilitation of road by DBC. from Upazila road Bablu house to Lalu Kha house road (Ch. 0.00-945)m. & Connecting road from (a) Bablu House to Albus Rice Mill road (Ch. 0.00-90)m, (b) Shohrab House to Lalu Kha House (Ch. 0.00-847)m. Part-(A): Improvement & Rehabilitation of Mintu road (Ch. 0.00-298)m & Connecting road from (a) Minto road to Aminul Councilor House (Ch. 0.00-330) & (b) Minto road to Lalu Driver House (Ch. 0.00-235)m. "Part-(A): Construction of road by CC. from ATI Gate bokul morr to Naricha road via Kismot house (Ch. 0.00-500)m. Part-(B): Construction of RCC X-Drain (Ch. 95)m & (Ch. 108)m. " Part-(A): Construction of road by CC. from Naricha road to Aronkola Vhatapara Mosque Babu Doctor House (Ch. 0.00-850)m. "Part-(A): Rehabilitation of road from Piarakhali Graveyard road Kasfol tola to Piarpur morr road by DBC. (Ch. 0.00-1282)m. " "Part-(B): Rehabilitation of road by DBC. from Shershah road to Candrio Eidgah via Fakirer Bottala road (Ch. 0.00-945)m & Connecting road from (a) Candrio Graved Yeard to Hospital road (Ch. 0.00-327)m, (b) Candrio Eidgha to College (Ch. 0.00-230)m. & (c) Fakir morr to Candrio Moaque (Ch. 0.00-95)m. " 8 Part-B:Drain Construction of road side RCC Drain from Mannan Dr. Mosque to Patilakhali Primary Drain (Ch. 0.00-980)m. & Connecting Drain from Shirajuddowla road to Proposed main Drain (Ch. 0.00-250 m). & Construction of RCC X-Drain (Ch. 250)m. Part-(A): Construction of RCC road side Drain from Sharsha road to Eidgha road via Dr. Bachu House (Ch. 0.00-125m) & Connecting Drain from (a) Ratan House to Nasrin House (Ch. 0.00-90)m. & Construction of RCC X-Drain (Ch. 125)m. Construction of road side RCC Drain from Golum Hossain School to Bokul morr Via Taltala Mosque (Ch. 0.00-840)m. & Construction of RCC X-Drain (Ch. 380)m & (Ch. 840)m. Construction of road side RCC Drain from Nur Mohallah Alam House to Khayer House (Ch. 0.00-500)m. Construction of road side RCC Drain from Purbo Tengri Gorosthan Para to Six TTE House via College Road (Ch. 0.00-500)m. 5 13 Rehabilitation of road by DBC. from Mosuria Para Nabab Sherajuddula Road to Nur Mohallah Via Dr. Mannan Mosque (Ch. 0.00-850)m, Connecting (Ch. 0.00-100)m. & Connecting road from (a) Mannan House to Amirul House by CC. (Ch. 00-350)m, (b) Sheraj house Runu Mondol Rice Mill Road by CC. (Ch. 60-330m) & (c) Azahar Pond to Mohoshin House by CC. (Ch. 0.00-370)m. | 9606 | 3285 | 65829502.13 | Md.Zinnat Ali Zinna,Pro:Md.Zinnat Ali Zinna,Paticabari, Himtpur, Pabna | 58617287.8502 | 2017-08-10 | 2018-08-03 | 70.85% | 616118.83 | 34328669.83 | 0
| UGIIP-III-2/AF/ISHW/SWM+SN/01/2017(T.ID:123256) | Component: 01 (Sanitary Landfill) Construction of 12901m2 sanitary landfill. Construction of 1 no Land fill gate . Construction of 515.8 m landfill fence. Construction of 1 no Dump truck cleaning facility. Instalation of 1 no tube well & monitoring well. Construction of 1 no control building. Environmental mitigation enhancement works. 7 Component: 02 (Fecal Sludge Treatment Plant) Construction of 6 nos FSTP (screening chamber). Construction of 3 nos FSTP (planted drying bed). Construction of 1 nos FSTP (settler and anaerobic filter). Construction of 1 nos FSTP (polishing pond). 4 11 Construction of 12901m2 sanitary landfill. | 0 | 0 | 34927957.44 | Dhrubo Construction Ltd.,Pro;Saiful Ala Swapon Chowdhury, Krishnapur, Pabna | 38419993.8499 | 0 | 2019-07-12 | 0% | 0 | 0 | 0
| UGIIP-III-2/AF/ISHW/WS/01/2017 | Name of Pkg:.Replacement of 04 set Pump-motor & 6 nos Transformer ,Supply and Installation of 3,000 nos water metering in different places under Ishwardi Pourashava, Pabna. Sub-Component: 01 : Replacement of 04 set Pump-motor and Supply & Installation of 06nos. Transformer. 4 Sub-Component: 02 :Pipeline Supply and Installation of 3,000 nr. Donmestic Water Meter (13 mm dia.= 635 nr.,20mm dia=1319 nr., and 25mm dia=46 nr.) 1 5 Name of works: Construction of 40 numbers latrines, 10 nos. dustbin, 2712 m footpath, 1757 m RCC drains and instalation of 53 nos. street lights & 45 nos. tube wells in 5 slums(Bilpara ,Bastipara , Ambagan, Mahatab Coloni and Thana Para Slum) with 5 lots for one package under Ishwardi Pourashava. Name of Slum: Bilpara Slum Name of works: Construction of 08 numbers single unit (type-B) toilet with 2 nos soak pit., 02 numbers Dustbin, Construction of 926 meter Footpath, Construction of 125 meter RCC drain, 10 numbers Solar Street Light, 11 numbers Tubewell at Bilpara Slum under Ishwardi Pourashava. Construction of 08 numbers single unit (type-B) toilet with 2 nos sock pit. Construction of 02 numbers Dustbin Construction of 926 meter footpath Construction of 125 meter RCC drain Installation of 10 numbers Solar Street Light Installation of 11 numbers Tubewell 6 Name of Slum: Bastipara Slum Name of works: Construction of 06 numbers single unit (type-B) toilet with 2 nos soak pit., 02 numbers Dustbin, Construction of 606 meter Footpath, Construction of 452 meter Rcc drain, 15 numbers Solar Street Light, 07 numbers Tubewell at Bastipara Slumunder Ishwardi Pourashava. Construction of 06 numbers single unit (type-B) toilet with 2 nos soak pit. Construction of 02 numbers Dustbin Construction of 606 meter Footpath Construction of 452 meter Rcc drain Installation 15 numbers Solar Street Light Construction of 07 numbers Tubewell 6 Name of Slum: Ambagan Slum Name of works: Construction of 08 numbers single unit (type-B) toilet with 2 nos soak pit., 02 numbers Dustbin, Construction of 350 meter Footpath, Construction of 350 meter Rcc drain, 08 numbers Solar Street Light, 08 numbers Tubewell at Ambagan Slum under Ishwardi Pourashava. Construction of 08 numbers Single unit (type-B) toilet with 2 nos soak pit Construction of 02 numbers Dustbin Construction of 350 meter Footpath Construction of 350 meter RCC drain Installation of 08 numbers Solar Street Light Installation of 08 numbers Tubewell 6 Name of Slum: Mahatab Coloni Slum Name of works: Construction of 10 numbers single unit (type-B) toilet with 2 nos soak pit., 02 numbers Dustbin, Construction of 430 meter Footpath, Construction of 430 meter Rcc drain, 10 numbers Solar Street Light, 11 numbers Tubewell at Mahatab Coloni Slum under Ishwardi Pourashava. Construction of 10 numbers single unit (type-B) toilet with 2 nos soak pit. Construction of 02 numbers Dustbin Construction of 430 meter footpath Construction of 430 meter RCC drain Installation of 10 numbers Solar Street Light Installation of 11 numbers Tubewell 6 Name of Slum: Thana Para Slum Name of works: Construction of 08 numbers single unit (type-B) toilet with 2 nos soak pit., 02 numbers Dustbin, Construction of 400 meter Footpath, Construction of 400 meter Rcc drain, 10 numbers Solar Street Light, 08 numbers Tubewell at Thana Para Slum under Ishwardi Pourashava. Construction of 08 numbers single unit (type-B) toilet with 2 nos soak pit. Construction of 02 numbers Dustbin Construction of 400 meter footpath Construction of 400 meter RCC drain Installation of 10 numbers Solar Street Light Installation of 08 numbers Tubewell 6 30 Name of Pkg:.Replacement of 04 set Pump-motor & 6 nos Transformer ,Supply and Installation of 3,000 nos water metering in different places under Ishwardi Pourashava, Pabna. | 0 | 0 | 36426187.69 | 0 | 36426187.69 |  |  | 0% | 0 | 0 | 0
Project Full Name : Third Urban Governance Infrastracture Improvement (Sector) Project (UGIIP-III)
Project Short Name : UGIIP-III
Project Code : 224048000
Pourashava Name : Shahajadpur
Pourashava Code : 82
| 5. Shahajadpur |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 34328669.83 | 0
| UGIIP-III-I/SHAH / UT+DR / 01 / 2015(Lot-01) | Lot-01(UT): Road Re-Construction & Rehabilitation of RCC road starting from UpazilaParishad to DabariaKorotoa river (Ch 00-1132.00)m (A)Re-Construction of BC road starting from Kakilamari Grid office to kakilamari Milk Co-operative Centre byBC(Ch00-430)m(B) Construction of RCC road starting from Dariapur R&H to DariapurModdhapara BC road (Ch 00-180)m Re-Construction of BC road starting from DariapurNobo Kumar bridge to Dilruba bus stand by BC (Ch 00-253)m Rehabilitation & Repair of road starting from Shahjadpur Press club to Afzal more via Sawdagor house (Ch 00-1200)m by BC. Re-Construction of RCC Road starting from MonirampurUyadayan Kinder garden to Rambarikamarbari(Ch00-755.0)m. Rehabilitation of BC road starting from Shahparakesta house to DargaparaMadrasha by BC (Ch 00-573)m Re-Construction of RCC road Starting from DariapurShafi shop to Borobari Mosque(Ch.00-290)m Re-habilitation& repair road starting from KandaparaDilruba Bus-stand to Mukkhada more (Ch 00-1017)m & Connecting road starting from BokkarDr. shop to Yousuf Plaza (Ch 00-117)m by BC Rehabilitation of Dariapur road starting from MoniharCenema Hall to Haluaghat Bridge N/Highway (Ch 00-684)m by BC. Rehabilitation of road starting from Parkola Akbar house to KhanjandiarProgoti Sango (Ch 00-2325)m by BC 10 Lot-02(UT+DR): Part-A:Road Rehabilitation& Re-construction of BC road starting from Haluaghat Bridge to BarabillDakkhin Para Hafezia Madrasha by BC (Ch 00-2200)m Re-construction of RCC road starting from PrannathpurIman house to PukurparHaziKobad house (Ch 00-946)m &. Link road (Ch 00-95)m Rehabilitation BC road & Construction of RCC road starting from ShaktipurNagorbari High way to BarabillUttor Para BC road(Ch 00-570m) & Link road Tat board road(Ch 00-77)m 3 Lot-02(UT+DR): Part-B:drain Construction of RCC drain starting from Hira furniture to Shahjadpur Press Club (Ch 00-220)m & Construction of footpath infront of MuktiJoddha Sangsod (Ch 00-209) m Construction Of RCC drain starting from Dariapur bazar HaziMoniruddin shop to yalid cloth shop via Mala store (Ch 00-55m) Construction of RCC drain starting from DariapurLovelulodi house to Haluaghat bridge(Ch 00-288)m Construction of RCC side Drain Starting from ShahparaTita house to Pathanpara Azad house.(Ch.00-412) Construction of RCC drain starting from ShaktipurSamsad house to Ghopkhal (Ch00-400)m with existing drain top slab of length 77m 5 8 18 Re-Construction & Rehabilitation of RCC road starting from UpazilaParishad to DabariaKorotoa river (Ch 00-1132.00)m | 12844 | 1375 | 99212970.31 | Mir Habibul Alam,Uttar Barogacha, Natore | 105426888.1846 |  |  | 91.17% | 5263334.5 | 84450451.75
| UGIIP-III-2/SHAH/UT+DR/01/2016(T.ID:79831) | Improvement of road starting from Barabill Shamsul house to Nalua Shahjahan house (Ch.00-1851m) & Connecting road Starting from Nalua Milk Co-oparative Centre to Hannan house by RCC (Ch.00-200m) Improvement of road starting from Barabill Mortoz daroga house to Barabill uttor para Mosque by RCC (Ch.00-1279m) Improvement of road starting from Shahzadpur Dak-Banglo to Dabaria High way via Dabaria Mosque by DBC (ch 00-1795m) Improvement of road starting from Shaktipur BC Road to Pukurpar kaseem Zadda BC more via Pukurpar Aziz more by DBC (ch 00-926m). Improvement of road starting from Pukur par Aziz more to Pukurpar Golam Nabi house DBC (ch 00-665m) Improvement of road starting from Rambari Monihar Cinema hall to Hazir ghat Mosque by DBC (Ch.00-545m) Improvement of road starting from Part: (A) Kandapara Upazila gate to Shishu Hospital by DBC (Ch.00-307m) Part: (B) Zila porished market to Varuadha Samsia Rokib Hospital by DBC (Ch.00-458m). Part: C) Upazila DPHE office to mokkhoad more by DBC (Ch.00-238m) Part:(D) Bangabandhu Soroni by DBC (Ch.00-186m) Improvement of road starting from Barabill patchpara Jailal house to Bayan house by HBB (ch 00-375)m. & Connecting road starting from Hazi Julfiquer house to Barabill sarder para Mosque by HBB (ch 00-35m) Improvement of road starting from Monirampur Darul Ulum Madrasha to Batar more by DBC (ch 00-570m) 9 Construction of RCC Drain Starting from Monirampur Sobahan shop to Monirampur Darul Ulum Madrasha. (Ch.00-213m) 1 Improvement of road starting from Barabill Shamsul house to Nalua Shahjahan house (Ch.00-1851m) & Connecting road Starting from Nalua Milk Co-oparative Centre to Hannan house by RCC (Ch.00-200m) | 9430 | 213 | 74606067.49 | M/s Islam Construction & Mir Habibul Alam(JV),Uttor Borogacha,PO+PS: Natore, | 70052548.8507 | 2017-08-30 | 2018-08-22 | 65.29% | 4445666.15 | 28879456.16 | 0
| UGIIP-III-2/SHAH/ UT+DR / 02 / 2016 | Improvement of road starting from Nalua Taltola to Nalua Milk Co-oparative centre via Nalua Madrasha to Barabill Patchpara Hazi hassen house by RCC (ch 00-1000m) Connecting road starting frrom Barabill patch para more to Barabill Nasir house by RCC (ch 00-370m) Improvement of road starting from Part: (A) Kandapara Hazi Akter house to Kandapara G,primary school by HBB(ch 00-355m). Part: (B)Kandapara Mojnu house to Kandapara Greaveyeard by HBB (ch.00-330m). Part: C) Kandapara Ad Masud house to saifuddin house by HBB (Ch.00- 310m) Improvement of road starting from Part: (A) Parkola Jalal mir Bridge to Enjed house by HBB (ch 00-400m) Part: (B) Parkola Gobindo Master house to Parkola Hanif Prosess mill road by HBB (ch 00-280m) Part: (C) Bisic G,P, Tower to Aigbari shaktipur Mannan house by HBB ( ch 00-180m). Improvement of road starting from Part: (A) Kandapara Nagor Bari High way to Laily house by HBB (ch 00-185)m. Connecting road starting from Kandapara New Mosque to Baher house by HBB (ch 00-204m) Part: (B) Shearkhali Ad. Hakim house to Shearkhali mainal house by HBB (ch 00-190m) Part: (c) Upazila DPHE Office to shearkhali Abdul Hamid house by HBB (ch 00-264)m.Connecting road starting from Shearkhali Ripon house to Golam house by HBB (ch 00-135m) Improvement of road starting from Part: (A) Barabill dakkhin para HBB Road to Lovelu house by HBB (ch 00-140m) Part: (B) Barabill dakkhin para HBB Road to Bridge via Nurul PK by HBB (ch 00-160m) Improvement of road starting from Barabill Abu Soma house to Barabill Moddhapara Mosque via Barabill Greave yeard by HBB (ch 00-610m) Improvement of road starting from dabaria Ali Akbar house to dabaria Taher house via Dabaria Graveyeard by HBB (ch 00-605m) Improvement of road starting from Shaktipur sarkar Bari Mosque to G.Primary School by HBB (ch 00-378)m. Connecting road starting from Shaktipur Bridge to mozid house by HBB (ch 00-22m) Improvement of road starting from Dargapara Madrasha to Ruppur Pir Shahab vita by DBC (ch 00-1015m) Improvement of road starting from Aigbari Parkola High way to Prannathpur kalidash more by DBC (ch 00-645m). Construction of road starting from Prannathpur Poschim para Mosque to Taltola BC road by RCC (ch 00-485m) & Connecting road starting from Taltola Robi Lal house to Taltola Sakowat house by RCC (ch 00-80m) 11 (a) Construction of RCC Drain starting from dariapur Mannan Bishwas house to dariapur charokkhola Existing RCC drain Ch(00-253)m. (b) Construction of RCC Drain starting from dariapur Rashia Professor house to Shahdat shop. (Ch.00-80m) 1 12Improvement of road starting from Nalua Taltola to Nalua Milk Co-oparative centre via Nalua Madrasha to Barabill Patchpara Hazi hassen house by RCC (ch 00-1000m) Connecting road starting frrom Barabill patch para more to Barabill Nasir house by RCC (ch 00-370m) | 8343 | 333 | 80105407.08 | M/s Islam Construction & Mir Habibul Alam(JV),Uttor Borogacha,PO+PS: Natore, | 75509244.5107 | 2017-08-30 | 2018-08-22 | 28.85% | 2051336.78 | 12455259.42 | 0
| UGIIP-III-2/AF/SHAH /WS / 01 / 2017(ID:216868) | Component: 01 : Domestic Meter Supply and Installation of 1,000 Nr. Donmestic Water Meter (13 mm dia.=250 Nr.,20mm dia=600 Nr. and 25mm dia=150 Nr.) 1 1 Supply and Installation of 1,000 Nr. Donmestic Water Meter (13 mm dia.=250 Nr.,20mm dia=600 Nr. and 25mm dia=150 Nr.) |  |  | 8575043 | M/S Noor & Co., 5 Shantibagh, Dhaka Bangladesh | 7866352.65 |  |  | 0% | 0