## On Going
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [16 empty] | Reporting Month: November/19
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/UZ-ST/01 | Construction of 30.00m PSC Girder Bridge on Barti Bazar to Gournadi GC at Ch.5000km over Anandhapur Khal under Gournadi UpazilaDistrict-Barisal | 506322005 | [5 empty] | 30 | 24934266.46 |  | 27173350.5 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 98% | 26212000 | 96.46%
2 | BDRIDP/BAR/GOR/UZ-ST/02 | Construction of 32.00m PSC Girder Bridge on Barti BazarNHW to Gournadi GC via Torky GC at Ch.9340km over Kashba Khal under Gournadi Upazila District-Barisal | 506322005 | [5 empty] | 32 | 24196878.89 |  | 26369588.63 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 98% | 24600000 | 93.29%
3 | BDRIDP/BAR/GOR/UZ-RdR/05 | Periodic Maintenance of Batazore-Agarpur-Sarikal via Hosnabad Nalchira-Miarchar road. a Earthwark from Ch. 8725- 17177m.b Carpeting DC 17361.14 sqm.c 12mm SC-13906.56 sqm. Under Gournadi Upazila District - Barishal. | 506322002 |  | 8.45 |  |  |  |  | 16020946.84 |  | 16821994.18 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 0% |  | 0%
4 | BDRIDP/BAR/GOR/UZ-RdR/06 | Periodic Maintenance of iIlah Bas stand NHW to Agailjhara H/Q via Bakai & Rajihar Bazar in/c Nutun Bazar Connecting road.a Earthwark from Ch. 0- 3832m.b Carpeting DC 3224.409 sqm.c 12mm SC-11191.1 sqm. Under Gournadi Upazila District - Barishal. | 506322006 |  | 3.832 |  |  |  |  | 5915176.68 |  | 6210935.51 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 0% |  | 0%
5 | BDRIDP/BAR/GOR/UZ-RdR/07 | Periodic Maintenance of Batazore GCNHW to Dhamura GC via Solak Bazar road.a Earthwark from Ch. 0- 2145m.b Carpeting 40mm-DC 6403.2 sqm.c Palisading Work297.00m. Under Gournadi Upazila District - Barishal. | 506322011 |  | 2.145 |  |  |  |  | 8824294.58 |  | 9265509.3 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 0% |  | 0%
6 | BDRIDP/BAR/GOR/UN-RdR/05 | Periodic Maintenance of Chadshi UP Office-Goila UP Office Road.a Earthwark from Ch. 0- 830m.b Carpeting DC 322.5 sqm.c 12mm SC-2208.35 sqm. Under Gournadi Upazila District - Barishal. | 506323020 |  | 0.83 |  |  |  |  | 1001243.79 |  | 1051305.98 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 0% |  | 0%
7 | BDRIDP/BAR/GOR/UN-RdR/06 | A Maintenance Nathai BazarDR to Bauthi UP Office via Chandsi a Earthwark Ch.00m-1150m.b Carpeting DC Ch.00m-1150m. B Maintenance Badarpur Bazar to Sarikal UP Office a Earthwark Ch.00m-4787m.b Carpeting DC Ch.00m-4787m. c Palsading 50m. | 506323003 506323009 |  | 5.937 |  |  |  |  | 11855719 | [10 empty] | E-Tender Under Process.
8 | BDRIDP/BAR/GOR/CC-Rd/04 | Improvement of road with BC from Steemar Ghat to Hosnabad hat road from at Ch.00m-630m | 506324041 |  | 0.63 |  |  |  |  | 4471349 | [10 empty] | E-Tender Under Process.
9 | BDRIDP/BAR/GOR/ CCA-Rd/05 | A Improvement of Road Batazore NHW to Jissorekati GPS. a Earthwark Ch.500m-1307m.b Carpeting BC Ch. 500m-1307m. c Construction of 01 Nos U-Drain at Ch.778m. d Palsading 107m. B Improvement of road by BC from Nalchira UP Office of Kalabaria Bazar via Pingolakati Model GPS. Salvaged Cost TK 11294.00a Earthwark Ch.500m-2056m.b Carpeting BC Ch.500m-2056m | 506324018 506324060 |  | 2.363 |  |  |  |  | 17836679 | [10 empty] | E-Tender Under Process.
10 | BDRIDP/ BAR/GOR/ UN-Rd/07 | Improvement of Road from Chandshi UP Office-Uttar Pallordi GPS Ramshiddi Bazarvia Chadshi High School. a Earthwark Ch.900m-1353m.b Carpeting BC Ch. 900m-1353m.c Construction of 01 No 1-Vent RCC Box Culvert 1.3mx1.3m at Ch.1266m. d Palsading 52m | 506323027 |  | 0.453 |  |  |  | 1.3 | 4140788 | [10 empty] | E-Tender Under Process.
11 | BDRIDP/BAR/GOR/UZ-Rd/08 | Improvement of Road by BC from Barthi Bazar NHW Bhurghata Bus Stand NHW via Amanathgonj Hat. Salvaged Cost TK 2742324.00a Earthwark Ch.5388m-7450m.b Carpeting BC Ch. 5388m-7450m.c Construction of 02 Nos U-Drain at Ch.6200m & 7350m. d Palsading 120m. | 506322017 |  | 2.062 |  |  |  |  | 16418601 | [10 empty] | E-Tender Under Process.
12 | BDRIDP/BAR/GOR/CCA-Rd/06 | A Improvement of Road Borobari NHW to Sarifabad via Sarifabad Hapania GPS. a Earthwark Ch.00m-1500m.b Carpeting BC Ch. 00m-1500m. c Palsading 67m. Under Gournadi Upazila Barishal DistrictB Improvement of Bagat Sarifabad road. a Earthwark Ch.1070m-1520m. b Carpeting BC Ch.1070m-1520m.c Palsading 25m | 506324084 506324119 |  | 1.95 |  |  |  |  | 15243061 | [10 empty] | E-Tender Under Process.
12 |  |  |  | 0 | 28.652 | 0 | 0 | 0 | 63.3 | 150859004.24 | 0 | 86892684.1 | [6 empty] | 50812000 |  |  |  | #REF!
Upazila: Agailjhara
1 | BDRIDP/BAR/AGL/UZ-RdR/03 | Maintenance of Barthi- Valiukshi-Magura Bakal Hat Roada Earthwark from Ch. 9860- 11860m.b Carpeting DC 21.3 sqm.c 12mm SC-5237.7 sqm. d Palisading Work 103.00m. Under Agailjhara Upazila District- Barishal. | 506022008 |  | 2 |  |  |  |  | 2265178.34 |  | 2377531.18 | M/S Yeamin Traders | 15/08/19 | 2019-02-09 | 2019-02-03 |  | 0% |  | 0%
2 | BDRIDP/BAR/AGL/ UZ-RdR/04 | Maintenance of Road From Nimtola RHD-Dhamura GC viaRatnapur UP Road at Ch 5265m-7383m Agailjhara Under Agailjhara Upazila District- Barishal. | 506022010 |  | 2.118 |  |  |  |  | 2649883 |  | 2781847.17 | M/S Sharif Enterprise | 20/08/19 | 27/08/19 | 27/02/20 |  | 0% |  | 0%
3 | BDRIDP/BAR/AGL/UN-RdR/03 | Maintenance of Road From Goila UP Office to Billogram Bazar via Rajer Bari Road at Ch 00m-2000mm Agailjhara Under Agailjhara Upazila District- Barishal. | 506023008 |  | 2 |  |  |  |  | 2890888.53 |  | 3033987.51 | M/S Sarder Enterprise | 22/08/19 | 29/08/19 | 29/02/20 |  | 10% |  | 0%
4 | BDRIDP/BAR/AGL/UN-RdR/02 | Maintenance of Road From Basail Hat Rajihar UP-Batra Bazar viiiia Basail Pachchim Para Bazar Road at Ch 00m-1000m Agailjhara Under Agailjhara Upazila District - Barishal. | 506023006 |  | 1 |  |  |  |  | 3511387.07 |  | 3685551.86 | M/S Yeamin Traders | 15/08/19 | 2019-02-09 | 2019-02-03 |  | 15% |  | 0%
5 | BDRIDP/ BAR/AGL/ CCA-Rd/09 | A Improvement of Temar Bastaila Nagar GPS-West Mollapara-Ohchiarmad Bazar. i Earthwark Ch.650m-1865m.ii Carpeting DC Ch. 650m-1865m. iii Palsading 641m.B Choto Basail Kader Bepari House to East Valukshi Bridge.Salvaged Cost Tk 37835.00i Earthwark Ch.0.00m-360m.ii Carpeting DC Ch.0.00m-360m. iii Palsading 120m. Under Agailjhara upazila District Barishal. | 506024009 506025045 |  | 1.575 |  |  |  |  | 15112800 | [10 empty] | Evaluation Send to H/Q for Approval
6 | BDRIDP/BAR/AGL/CCA- Rd/10 | Improvement of Alloshika-Ramanonder AK Bazar-Batra Bazar Ramsell road from Ch.1000m-1800m | 506025050 |  | 0.8 |  |  |  |  | 7433677 |  | 7803874.95 | M/S Sarder Enterprise | 24/10/19 | 2019-01-11 | 2019-01-05 |  | 0% |  | 0%
7 | BDRIDP/BAR/AGL/CCA- Rd/11 | Improvement of Road from Boramagra Switch gate Bazarvia Kodaldhoa Bazar to Ramshil bazar.a Earthwark Ch. 1000-5250m.b Carpeting DC Ch. 1000-5250m. c Palsading 556m | 506024034 |  | 4.25 |  |  |  |  | 31659786 | [10 empty] | E-Tender Under Process.
8 | BDRIDP/BAR/AGL/CCA-Rd/12 | A Improvement of Ghatoker Poll-Daspottry Janata Bazar- Patihal Gomosta Bari Box Culvert via Janata GPS New. a Earthwark Ch. 600m-1600m.b Carpeting BC Ch. 600m-1600m.c Palsading 300m.B Improvement of Ambulla Switchgate to Kotalipara Border Road. Salvaged Cost Tk 522605.00a Earthwark Ch. 1194m-1773m.b Carpeting BC Ch. 1194m-1773m. c Construction of 01 Nos U-Drain 1125mx600m at Ch.618m. d Palsading 160m | 506024043 506024045 |  | 1.579 |  |  |  | 0.6 | 14930337 | [10 empty] | E-Tender Under Process.
9 | BDRIDP/BAR/AGL/CCA-Rd/13 | A Improvement of Mollapara Saw Mill-Taler Bazar-Ramar Bazar Kalurpar Bazar road. Salvaged Cost Tk 535334.00 a Earthwark Ch. 1000m-2230m.b Carpeting BC Ch. 1000m-2230m.B Improvement of Goila Baby home- Nathoy Road via Abu Hanif Sarkers Bari. a Earthwark Ch. 700m-1100m.b Carpeting BC Ch. 700m-1100m.c Palsading 5m | 506024041 506025124 |  | 1.63 |  |  |  |  | 11826330 | [10 empty] | E-Tender Under Process.
10 | BDRIDP/BAR/AGL/UZ-Rd/05 | Improvement of Mahilara-Chaygram-Amboula-Paisarhar Road. Salvaged Cost Tk 1100033.00 a Earthwark Ch. 22280m-23226m.b Carpeting BC Ch. 22280m-23226m.c Palsading 148m. | 506022006 |  | 0.946 |  |  |  |  | 8037695 | [10 empty] | E-Tender Under Process.
11 | BDRIDP/BAR/AGL/UZ-Rd/14 | Improvement of Agailjhara-Sujankathi via Nilkanda road. Salvaged Cost - Tk 1833963.00a Earthwark Ch. 600m-1725m.b Carpeting DC Ch. 600m-1725m. c Construction of 01 Nos 2 vent 4.0mx4.0m RCC Box Culvert at Ch.1025m. d Palsading 333m | 506024019 |  | 1.125 |  |  |  |  | 12773520 | [10 empty] | E-Tender Under Process.
12 | BDRIDP/BAR/AGL/ CCA-Rd/15 | Improvement of Sobikharpar RHD to Askar Hat UZR. a Earthwark Ch.1583m-2968m.b Carpeting BC Ch.1583m-2968m. C Palsading 288m | 506024052 |  | 1.385 |  |  |  |  | 11179100 | [10 empty] | E-Tender Under Process.
13 | BDRIDP/ BAR/AGL/ CCA-St/02 | Construction of 15.00m RCC Girder Bridge on Shaheber hat - Ramer Bazar to Gurucharan Babu House | 506024017 | [5 empty] | 15 | 16143882 | [10 empty] | E-Tender Under Process.
14 | BDRIDP/BAR/AGL/CCA-St/03 | Construction of 14.00m RCC Slab Bridge on Despotty Janata Bazar - Patihar Sluice via Despotty Janata GPS Ghatoker Poll - Despotty Janata Bazar - Patihar Gomosta Bari Box Culvert via Janata GPS NEW at Ch.410m | 506024043 | [5 empty] | 14 | 15451567 | [10 empty] | E-Tender Under Process.
15 | BDRIDP/BAR/AGL/CCA-St/04 | Construction of 16.00m RCC Pedestrain Bridge near of Shahid Fakir home at Khajuria Khajuria Rucca Road to Gogwsar Masters Bari | 506025114 | [5 empty] | 16 | 11082682 | [10 empty] | E-Tender Under Process.
16 | BDRIDP/BAR/AGL/CCA-Rd/16 | Improvement of Bakal Wapda Embankment to Bakal Hat. a Earthwark Ch.1400m-2455m & 3253m-4260m.b Carpeting BC Ch. 1400m-2455m & 3253m-4260m.c Construction of 2 Nos U-Drain 1.125mx0.60m At Ch. 2943m & 4145m. d Palsading 553m. Salvaged Cost Tk 364102.00 | 506024006 |  | 2.062 |  |  |  | 1.125 | 17608532 | [10 empty] | E-Tender Under Process.
17 | BDRIDP/BAR/AGL/CCA-Rd/17 | A Improvement of Moulabi Bazar hat-Kumarvanga Bazar Uttar Shehipasha Joynal Sarders Bari Salvaged Cost Tk 507417 a Earthwark Ch. 150m-1185m.b Carpeting BC Ch. 150m-1185m.c Construction of 01 Nos Single-Vent 2.00mx2.00m RCC Box Culvert At Ch. 927md Palsading 94m. B Improvement of Amboyla Hobi Howladers Bari Pachchim Amboyla road. Salvaged Cost Tk 46969.00 a Earthwark Ch.00m-905m.b Carpeting BC Ch. 00m-905m. c Construction of 01 Nos U-Drain Size 1125mmx600mm at Ch. 800m.d Palsading 175m. Total Salvaged Cost Tk 554386.00 | 506025038 506025097 |  | 1.985 |  |  |  | 3.125 | 16009406 | [10 empty] | E-Tender Under Process.
17 |  |  |  | 0 | 24.455 | 0 | 0 | 0 | 49.85 | 200566650.94 | 0 | 19682792.67 | [6 empty] | 0 |  |  |  | #REF!
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 506942007 |  | 2.605 |  |  |  |  | 18314961 | 18314961 | 14275617.27 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 60% | 7750000 | 54.29%
2 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 506942015 |  | 2.296 |  |  |  |  | 14753928 | 14753928 | 11501091.23 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 77% | 8635000 | 75.08%
3 | BDRIDP/BAR/UZP/UZ-RdR/04 | Rehabilitation of Harta Chowmuhani Bisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 | 506942009 |  | 2.6 |  |  |  | 2.5 | 17827349 |  | 18399998.87 | M/S S H Enterprise | 2018-08-03 | 15/03/18 | 15/03/19 |  | 70% | 5100000 | 27.72%
4 | BDRIDP/BAR/UZP/UN-Rd/01 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m. | 506943007 506942018 |  | 2.34 |  |  |  | 1.2 | 15060662.42 |  | 13554596.17 | M/S Niaz Traders | 2017-02-10 | 2017-09-10 | 2018-09-08 |  | 40% | 4254441 | 31.39%
5 | BDRIDP/BAR/UZP/CCA-Rd/04 | Improvement of Old Sikerpur Bandar-Abul Hasan Mridhas House Connecting road under Uzirpur Upazila Barisal a Earthwork Ch.0.0m - 360m b Bituminous Carpetting Ch.0.0m - 360m c U-Drain 01 no at Ch.117. | 506945281 |  | 0.36 |  |  |  | 1 | 2738720.64 |  | 2464848.57 | M/S Kohinoor Enterprise | 22/04/18 | 29/04/18 | 29/08/18 |  | 60% | 1200000 | 48.68%
6 | BDRIDP/BAR/UZP/CCA-Rd/03 | Improvement of road from Guthia kakradhari Connecting road North side of Khaleque Mollas House of Dahorpara GPS via Mojid Masters House under Uzirpur Upazila Barisal a Earthwork Ch.0.0m -1550m b Bituminous Carpetting Ch.0.0m - 1550m c U-Drain 04 nos at Ch.130m476m655m1230m & 2Nos 1-Vent 4m x 4m RCC Box Culvert at ch.755m & 1540m | 506944084 |  | 1.55 |  |  |  | 16 | 12042875.78 |  | 10838588.2 | Md. Mahafuz Khan | 2018-03-05 | 2018-10-05 | 2019-10-03 |  | 60% | 2600000 | 23.99%
7 | BDRIDP/BAR/UZP/CCA-Rd/05 | Part A Improvement of road from Muktijodda Milon Kendra Connecting road Harasia road.i Carpeting DC Ch. 0.00m-900m. ii 3 Nos.0.625mx0.600m U-Drain at Ch.10m365m665m.Part B Improvement of road from East Joysree Village road.i Carpeting DC Ch. 0.00m-1000m.ii 2 Nos.0.625mx0.600m U-Drain at Ch.605m865m. Salvaged Cost Tk 141267.00Part C Improvement of road from Jugihati-Chokder bari Jame Mosque to Damodarkathi Tri mukhi Atok road by DC at Ch.0.00m-1050.00m with 1 No.4.30mx4.30m RCC Box Culvert at Ch.560m. 3 Nos.0.625mx0.600m U-Drain at Ch.130m760m & 835m. Under Uzirpur Upazila Barishal District. | 506945170 506945028 506945172 |  | 2.95 |  |  |  | 9.295 | 23428700 |  | 21586749.471 | M/S Mudasser Ali Mallick | 23/05/19 | 30/05/19 | 30/11/19 |  | 15% |  | 0%
7 |  | Sub-Total: |  | 0 | 14.701 | 0 | 0 | 0 | 29.995 | 104167196.84 | 33068889 | 92621489.781 | [6 empty] | 29539441 |  |  |  | #REF!
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 506102003 | 0 | 1 | 0 | 0 | 0 | 0 | 7013799 | 7013799 | 5349539.02 | M/S Saleha Enterprise | 29/01/17 | 2017-06-02 | 2017-06-06 |  | 50% | 1300000 | 24.3% |  | 40% | 839815.608
2 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 11850164.61 |  | 10665148 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 95% | 9450000 | 88.61%
3 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 9814374 |  | 8832936 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 92% | 8164776 | 92.44%
4 | BDRIDP/ BAR/BAN/ CCA-Rd/01 | Improvement of road by BC Gordder Abu Taher Shop to Kachua Madrasha. Salvaged Cost Tk 448135.00i Earthwark Ch.600m-1600m. ii Carpeting DC Ch.600m-1600m. iii Construction of 03 Nos. 1.5mx1.5m Box Culvert at Ch.667m742m & 938m & U-Drain 0.6mx0.6m at Ch.870m973m & 1550m. under Banaripara UpazilaBarishal District | 506105098 |  | 1 |  |  |  | 5.1 | 8974998.66 | [10 empty] | Evaluation Send to H/Q for Approval
5 | BDRIDP/BAR/BAN/ CCA-Rd/02 | Improvement of Read from West Chakhar Gotarer bari Bridge to Purbo Goailbari GPS road Maszidbari Lance Ghat to Modhow Sayedkati Rgd P. School. Salvaged Cost Tk 776408.00 a Earthwark Ch.00m-1000m.b Carpeting BC Ch.00m-1000m. c Construction of 01 Nos RCC Box Culvert 2.0mx2.0m at Ch.179m0 02 Nos RCC Box Culvert 1.5mx1.5m at Ch.440m & 696m. 07 Nos U-Drain 0.6mx0.6m at Ch.235m 308m 510m 612m 726m 925m & 940m. d Palsading 35m | 506104045 |  | 1 |  |  |  | 9.2 | 9604310.25 |  | 9124094.73 | M/S Sun Bulders | 02/10/19 | 09/10/19 | 09/04/20 |  | 0% |  | 0%
5 |  |  |  | 0 | 3 | 0 | 0 | 0 | 44.3 | 47257646.52 | 7013799 | 33971717.75 | [6 empty] | 18914776 |  |  |  | 839815.608
Upazila: Babugonj
1 | BDRIDP/ BAR/BAB/ CCA-Rd/08 | Improvement of Road from Ramjankathi GPS to Charalgi GPS. a Earthwark from Ch. 0- 1500m.b Carpeting DC from Ch. 0- 1500m.c Construction of 2 Nos 625mmx600mm U-Drain at Ch. 736m & 1285m.d Palisading Work 150.00m. Under Babuganj District- Barishal. | 506035132 |  | 1.5 |  |  |  | 1.25 | 11562581.55 |  | 10984852.47 | M/S Sharif Enterprise | 2019-04-04 | 2019-11-04 | 2019-11-10 |  | 50% | 3700000 | 33.68%
2 | BDRIDP/ BAR/BAB/ CCA-Rd/09 | Improvement of from Khudrokathi Freedom Fighter Mogibor Rahaman Sikder House to Baige Comander Abdul Mojid Khan house. At Ch. 00m-1100m.Salvaged Cost Tk 285357.00i Earthwark Ch.0.00m-1100m.ii Carpeting DC Ch.0.00m-1100m. iii Construction of 02 Nos 0.625mx0.600m U-Drain. at Ch.110m & 400m.iv Palsading 46m.Under Babuganj Upazila Barishal District. | 506034155 |  | 1.1 |  |  |  | 1.25 | 7945251 |  | 7547988.86 | M/S Yousuf Ali Sikder | 20/06/19 | 27/06/19 | 27/12/19 |  | 0% |  | 0%
2 |  |  |  | 0 | 2.6 | 0 | 0 | 0 | 2.5 | 19507832.55 | 0 | 18532841.33 | [6 empty] | 3700000 |  |  |  | #REF!
Upazila: Muladi
1 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. | 506692002 | [5 empty] | 45 | 24434851.86 |  | 21991136.67 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 95% | 17136746 | 77.93%
2 | BDRIDP/BAR/MUL/CCA-Rd/07 | Improvement of road from Muladi-Mirdar Hat GCCR Kazi Ali Ahmed Bari Grostan Alauddin Dewan Bari under Muladi UpazilaBarisal.a Bituminus Surfacing wearing courseDC 0.0m - 375mb 1 No.1.3m x 1.3m RCC Box Culvert at ch.170m | 506695137 |  | 0.375 |  |  |  | 1.3 | 2591153.77 |  | 2332038.39 | M/S Kohinoor Enterprise | 19/01/18 | 25/01/18 | 25/07/18 |  | 65% | 350000 | 15.01%
3 | BDRIDP/BAR/MUL/UZ-Rd/02 | a Improvement of Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road from Ch.2150m - 4415m under Muladi Upazila Barisal District.b Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch.2800m.c Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch. 3900m. | 506692002 |  | 2.265 |  |  |  | 4 | 17170059.9 |  | 15453053.91 | Orien Trading & Builders | 2018-03-05 | 2018-10-05 | 2019-10-05 |  | 95% | 9000000 | 58.24%
4 | BDRIDP/BAR/MUL/CCA-Rd/09 | Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000m under Muladi Upazila Barisal District.Salvaged Cost Tk 591644.00Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000mID No.506694016 under Muladi Upazila Barisal District. | 506694016 |  | 1 |  |  |  |  | 5885104.61 |  | 5296594.14 | Orien Trading & Builders | 2018-03-05 | 2018-10-05 | 2019-10-02 |  | 60% | 1150000 | 21.71%
5 | BDRIDP/BAR/MUL/CCA-Rd/08 | Improvement of road from Batamara Paderhat Launch Ghat -Salimpur Bazar via Batamara Regd.Primary School via Aminul Haque Kabir Bari by BC at ch.200m - 1252m under Muladi Upazila Barisal. | 506695001 |  | 1.05 |  |  |  |  | 6000000 |  | 5400000 | Md. Mahafuz Khan | 2018-03-05 | 2018-10-05 | 2018-10-02 |  | 30% |  | 0%
6 | BDRIDP/BAR/MUL/CCA-Rd/10 | Improvement of road from Balarmpur Bazar-Dumurtala GPS-Char Dumuritala Bissas Bari Mosque UNRG by BC at Ch. 0.000km-1.000km. under muladi upazila Barisal District | 506694094 |  | 1 |  |  |  |  | 5702035.96 |  | 5416934.16 | M/S Ferdousi Construction | 2018-05-06 | 2018-12-06 | 2019-12-03 |  | 50% | 2500000 | 46.15%
7 | BDRIDP/BAR/MUL/CCA-Rd/11 | Improvement of road from Muladi-Bara Patarchar Ferry Ghat M by BC at Ch. 3.500km-4.065km. ID No.506694017 under muladi upazila Barisal District |  |  | 0.565 |  |  |  |  | 3338552.94 |  | 3171625.29 | M/S AK Buidlers | 2018-09-06 | 14/06/18 | 14/11/18 |  | 70% | 1500000 | 47.29%
8 | BDRIDP/BAR/MUL/CCA-Rd/12 | Improvement of road from Haraz Sikder Bari to Laxmipur Nutun hat via Rashid Dhali Bari by BC at Ch. 0.900km-2.400km under muladi upazila Barisal District.Salvaged cost Tk.888105.00 | 506695010 |  | 1.5 |  |  |  |  | 9147339.59 |  | 8689972.61 | M/S R.S Construction | 31/05/18 | 2018-07-06 | 2018-07-12 |  | 25% |  | 0%
9 | BDRIDP/ BAR/MUL/Ghat/01 | Construction of RCC Ghat at Muladi Bandar under Muladi UpazilaBarishal District. | [7 empty] | 3822927.39 |  | 3631781.02 | M/S ARB Construction | 2019-10-06 | 17/06/19 | 17/12/19 |  | 0% |  | 0%
10 | BDRIDP/BAR/MUL/CCA-St/06 | Construction of 23.00m RCC Girder Bridge on Madrasha Hat Start from Char kalekhan College gate to Charmalia Bepari Hat road at ch.3670m | 506694001 | [5 empty] | 23 | 16173766 |  | 14133678.509 | M/S. Lutful Kabir |  |  |  |  | 15% |  | 0%
11 | BDRIDP/BAR/MUL/CCA- Rd/13 | A Improvement of Kazir Char High School to Moddho Kazirchar Dakhil Madrasah. Salvaged Cost Tk 1848817a Earthwark Ch.1000m-2000m.b Carpeting BC Ch. 1000m-2000m. c Palsading 70m.B Improvement of Road by BC from Char Comissioner Colam Khan Bari-Muladi Boarder via Sadak Khan Khal K.a Earthwark Ch.500m-1150m.b Carpeting BC Ch.500m-1150m. c Construction of 01 No 1-Vent RCC Box Culvert 4.0mx4.0m at Ch.572m. d Palsading 45m | 506694082 506695052 |  | 1.65 |  |  |  | 4 | 14840130 |  | 13710063 | M/S S H Enterprise | 24/09/19 | 01/10/19 | 01/04/20 |  | 10% |  | 0%
12 | BDRIDP/BAR/MUL/UN- Rd/01 | A Improvement of Road by BC from Talukder Hat Khajurala to Safipur UP via Charkaiakhan UP-Beparirhat. Salvaged cost Tk 3421194.00a Earthwark Ch.11750m-13250m.b Carpeting BC Ch.11750m-13250m.B Improvement of Road by BC from Kazir Char UP to Ekaterhat UP to Muladi Border. Salvaged cost Tk 2190786.00a Earthwark Ch.00m-1000m.b Carpeting BC Ch.00m-1000m. c Palsading 70m | 506693001 506693004 |  | 2.5 |  |  |  |  | 18468196 |  | 16991019.04 | M/S S H Enterprise | 24/09/19 | 01/10/19 | 01/04/20 |  | 0% |  | 0%
13 | BDRIDP/BAR/MUL/CCA-Rd/14 | A Improvement of Road from Shah alam Sarif Bari- Jabbar Sikder Bari via Bhahadurpur H/S. K.a Earthwark Ch.00m-550m.b Carpeting BC Ch. 00m-550m. B Improvement of road from Padarhat to Delower Howlader Bari via Harun Dr. BariK.a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of 02 Nos Single-Vent 3.00mx3.00m RCC Box Culvert At Ch. 625m & 976m | 506695059 506695102 |  | 1.5 |  |  |  | 6 | 13519203 | [10 empty] | E-Tender Under Process.
14 | BDRIDP/BAR/MUL/CCA-Rd/15 | A Improvement of Road from Padar Hat Esahak Howladers Bari.a Earthwark Ch. 500m-1500m.b Carpeting BC Ch. 500m-1500m.c Palsading 55m.B Improvement of Road from Char Comissioner R&H-Dholu Sikder Bari K a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Palsading 100m | 506694092 506695053 |  | 2 |  |  |  |  | 15288444 | [10 empty] | E-Tender Under Process.
14 |  | Sub Total: |  | 0 | 15.405 | 0 | 0 | 0 | 83.3 | 156381765.02 | 0 | 116217896.739 | [6 empty] | 31636746 |  |  |  | #REF!
Upazila: Hizla
1 | BDRIDP/BAR/HZL/CCA-Rd/01 | Improvement of Kowria- Moulavirhat UZR Poschim koralia road under Hizla Upazila District Barisal aEarth work from Ch.0.0 -900m b Dense Carpeting Ch.0.0 -900m c Two vent 4m x 4m RCC Box Culvert at Ch.252m | 506364033 |  | 0.9 |  |  |  | 8 | 8833997.83 |  | 7950598.407 | Md. Mahafuz Khan | 2018-04-04 | 2018-11-04 | 2019-01-02 |  | 35% |  | 0%
2 | BDRIDP/BAR/HZL/CCA-Rd/02 | Improvement of Hizla Muladi road to Motiar Dewan Bari via Sergent Dula Bari roadRHD via Surgeant Dulal- Kathal BeganUZR under Hizla Upazila Barisal District.ID No.506364003 Salvaged Cost Tk.2186650.00a Earth work Ch.0.0 - 1500mb Carpetting Ch. 0.0 - 1500mc Construction of 2 nos U-Drain on the same road at Ch.777m & 1275m |  |  | 1.5 |  |  |  | 1.8 | 10053464.17 |  | 9550790.96 | M/S R S Construction | 21/06/18 | 28/06/18 | 28/12/18 |  | 40% |  | 0%
3 | BDRIDP/BAR/HZL/CCA-Rd/03 | Improvement of Khunna Hospital RHD via Kawmi Madrasha - Baherchar UZR Barajalia Board GPS CS Connecting road a Earthwork from Ch.850 -1820m b Carpetting BC from Ch.850 -1820m under Hizla Upazila District Barishal Salvaged Cost TK 2343371.00 | 506365049 |  | 0.97 |  |  |  |  | 6797662.78 |  | 6457779.64 | M/S Munny Enterprise | 17/02/19 | 24/02/19 | 24/08/19 |  | 55% | 1000000 | 15.49%
4 | BDRIDP/BAR/HZL/CCA-Rd/04 | Improvement of road from Horinathpur Koshaipotti UZR - Zetighat GPS UZR ID No. a Earthwork from Ch.0.0 -1500m b Carpetting BC from Ch.0.0 -1500m under Hizla Upazila District Barishal Salvaged Cost TK 112128.00 | 506365056 |  | 1.5 |  |  |  |  | 9936759.78 |  | 9439921.79 | M/S Esad & Emad Enterprise | 29/01/19 | 2019-06-02 | 2019-06-07 |  | 70% | 5700000 | 60.38%
5 | BDRIDP/ BAR/HZL/ CCA-Rd/05 | Improvement of road from UZR -6 Mohishkhola Madrasha to VRA-15 Uttor Guabaria GPS via house of Abdul Gafur Sarder road by BC From Ch. 00m-1760.00m. Salvage Amount TK 296023.00 Under Hizla Upazila District- Barishal. | 506364034 |  | 1.76 |  |  |  |  | 12738507.36 |  | 12101581.992 | M/S. Nazrul Enterprise | 2019-04-04 | 2019-11-04 | 2019-11-10 |  | 35% |  | 0%
6 | BDRIDP/BAR/HZL/CCA-Rd/06 | Improvement of Kawria Bazar Danushikder hat road - Noroshingpur road Start Mollah Bari Shop Salvaged Cost Tk.309333.54 i Earth work Ch.0.0 - 760miiCarpeting DC Ch.0.0 - 760m under Hizla Upazila District Barishal. | 506365051 |  | 0.76 |  |  |  |  | 5255934.36 |  | 4993137.642 | M/S Jeon Trading & C0 | 2019-02-05 | 2019-09-05 | 2019-09-11 |  | 20% |  | 0%
7 | BDRIDP/BAR/HZL/UZ-St/01 | Dhunusikder Hat to Memania Taker Hat road via Abupur Kheyaghat i Construction of Diuble vent 2 x 4.50 x 6.50m RCC Box Culvert at Ch.2600mii Construction of Diuble vent 2 x 4.00 x 5.00m RCC Box Culvert at Ch.3380mUnder Hizla Upazila Barishal District. | 506362005 | [5 empty] | 17 | 5693472 |  | 5408798.4 | M/S Ladis Corner | 25/04/19 | 2019-02-05 | 2020-02-05 |  | 60% | 1800000 | 33.28%
8 | BDRIDP/ BAR/HZL/ CCA-Rd/07 | Improvement of Purbo Kandi WDB Embt. Salvaged Cost Tk 257546.00i Earthwark Ch.0.00m-900m. ii Carpeting DC Ch.0.00m-900m. iii Palsading 95m.Under Hizla Upazila Barishal District. | 506365003 |  | 0.9 |  |  |  |  | 6755327.72 |  | 6417561.33 | M/S Yousuf Ali Sikder | 20/06/19 | 27/06/19 | 27/12/19 |  | 51% |  | 0%
9 | BDRIDP/BAR/HZL/UZ- Rd/02 | Improvement of Dhanushikder hat-Muladi Upazila road. Salvaged Cost TK 1488901.00 a Earthwark Ch.1000m-2000m. b Carpeting BC Ch.1000m-2000m. c Palsading 97m. | 506362009 |  | 1 |  |  |  |  | 9936388.93 |  | 9439521.98 | M/S Kazi Popy Enterprise | 02/09/19 | 09/09/19 | 09/03/20 |  | 50% |  | 0%
9 |  |  |  | 0 | 9.29 | 0 | 0 | 0 | 26.8 | 76001514.93 | 0 | 71759692.141 | [6 empty] | 8500000 |  |  |  | #REF!
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 506624016 |  | 1.61 |  |  |  |  | 6864308 | 6864308 | 6860287.95 | M/S Hasan Construction | 2017-12-01 | 19/01/17 | 19/09/17 |  | 70% | 3325000 | 48.47%
2 | BDRIDP/BAR/MHN/GC/01 | Constructionof Langutia G C (i) Fish Shed (Size : 12m x 6m) (ii) 2 Nos Waste collection Pit (Dustbin) (Size : 1.4m x 1.4m) (iii) Multipurpose Shed (Size : 12m x 6m) (iv) Logistic Support for Langutia Bazar (v) Toilet Block (Size : 5.75m x 3.07m) (vi) 2 Nos Deep Hand Tube well (vii) CC road without side drain : 100m (viii) RCC Ghat at Langutia Bazar Under Mehendigonj, Barishal District | [7 empty] | 4989791 |  | 4740301.45 | M/S Oshin Enterprise | 2019-04-01 | 2019-11-01 | 2019-04-07 |  | 0% |  | 0%
3 | BDRIDP/BAR/MHN/UN-Rd/01 | Improvement of road from Chanpur UP Saduaghata - Kazir Hat Bazar via Muktijodda H/S Salvage Amount Tk. 1000267.00 Road i Earth Work Ch. 00m-1300m ii Carpeting BC Ch. 00m-1300m iii Construction of 01 No 0.625mx0.600m U-Drain at Ch.1234m iv Palisading 27m. Under Mehendiganj Upazila District- Barishal. | 506623016 |  | 1.3 |  |  |  | 0.625 | 9582341.77 |  | 9103224.68 | M/S Refat Enterprise | 21/07/19 | 28/07/19 | 28/01/20 |  | 0% |  | 0%
4 | BDRIDP/BAR/MHN/CCA-Rd/04 | Part - A Improvement of road by BC from Paterhat RC College - Charerhat Via Sadekpur Madrasha at Ch. 700m-1700m. Salvage Amount Tk. 1248231.00 i Earth Work Ch. 700m-1700m. ii Carpeting BC Ch.700m-1700m. iii Construction of 01 No 0.625mx0.600m U-Drain at Ch.1686m Under Mehendiganj Upazila District- Barishal. Part- B Improvement of road from Nasirkha Khayaghat - Hashamuddi Bazar i Earth Work Ch. 00m-1000m. ii Carpeting BC Ch. 00m-1000m Under Mehendiganj Upazila District- Barishal. Part - C Improvement of road from Rowshanara Dhakil Madrasha H/O Hasem Molla Via H/O Dolil Uddin Bepari. Salvage Amount Tk. 199562.00 i Earth Work Ch. 00m-900m. ii Carpeting DC Ch. 00m-900m | 506625130 506625140 506625236 |  | 2.9 |  |  |  | 0.6 | 20719155.66 |  | 20716818.21 | M/S Amir Engineering Corporation | 17/09/19 | 24/09/19 | 24/03/20 |  | 0% |  | 0%
4 |  |  |  | 0 | 5.81 | 0 | 0 | 0 | 1.225 | 42155596.43 | 6864308 | 41420632.29 | [6 empty] | 3325000 |  |  |  | #REF!
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/UN-Rd/01 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road. | 506513003 |  | 2.76 |  |  |  | 8.8 | 18760504 |  | 16884454 | Md Mafuz Khan | 18/01/18 |  | 31/11/18 |  | 20%
2 | BDRIDP/BAR/SDR/UZ-Rd/01 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal. | 506512003 |  | 0.579 |  |  |  |  | 4209569.27 |  | 3788612.34 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 70% | 1700000 | 44.87%
3 | BDRIDP/BAR/SDR/CCA-Rd(R)/11 | Improvement of road from Charmonai Talukder Bari-West Razarchar Club by BC. at Ch. 0.00m-1203.00m under Charmonai Union, Upazila : Sadar, Dist-Barisal [Salvaged cost- Tk 231155.00] | 506515109 |  | 1.203 |  |  |  |  | 8769166.6 |  | 7892249.94 | M/S Kohinoor Enterprise | 18/01/18 | 25/01/18 | 25/11/18 |  | 40% | 1200000 | 15.2%
4 | BDRIDP/BAR/SDR/CCA-Rd/13 | Improvement of Shibpasha Sarder bari Sholna Tarunclub Road Road Part-A Earth work at Ch. 0.00 -1505.00m Part-B Carpeting BC work at Ch. 0.00-1505.00m Salvage Amount Tk. 2626839.00 Part-C Construction of 2Nos U-Drain 1.00mx1.00m at Ch. 140m & 380m Under Barisal Sadar Upazila District - Barisal. | 506514007 |  | 1.505 |  |  |  | 2 | 10603941.33 |  | 10073944.25 | M/S Noor & Sons | 2018-11-06 | 18/06/18 | 18/05/19 |  | 65% | 3300000 | 32.76%
5 | BDRIDP/BAR/SDR/CCA-RdR/14 | Improvement of Shibpasha Sarder bari-Sholna Tarunclub road a Earth work at Ch.1505-2392m b Carpetting BC Ch.1505 -2392m c Construction of 1 No Double vent Box culvert 4.0m x 4.0m at ch.1901m d Protective worksPalisading 134m e Link Road Baitul Mamur Jame Mosque 167.00m under Bakergonj Upazila Barishal District.Salvaged Cost TK 1935498.00 | 506514007 |  | 1.054 |  |  |  | 8 | 10111914.02 |  | 9606318.31 | M/S H R Enterprise | 20/02/19 | 27/02/19 | 27/08/19 |  | 30% | 2100000 | 21.86%
6 | BDRIDP/ BAR/SDR/ CCA-Rd/15 | Improvement of Read from Borthan Khan Bari-Dr. Omar bari-Gogan Ali Howladar Bari to Godanga Chandpura UP Hijaltala Baran Khan Bari-Sanjib Daser Bari-Eunus Munshi Bari. a Earthwark Ch.00m-1060m.b Carpeting DC Ch.00m-1060m. c Construction of 02 Nos U-Drain 1.0mx1.0m at Ch.107.00m & 180.00m. d Palsading 350m | 506515174 |  | 1.06 |  |  |  | 2 | 8603655 |  | 8173473.08 | M/S Alif Enterprise |  |  |  |  | 0% |  | 0%
7 | BDRIDP/BAR/SDR/CCA-Rd/16 | Improvement of Road from Char Aicha Mollar Hat Kheya Ghat to Board School via Jokkhali. a Earthwark Ch.00m-530m.b Carpeting BC Ch. 00m-530m. c Palsading 93m | 506514145 |  | 0.53 |  |  |  |  | 4345799 | [10 empty] | E-Tender Under Process.
8 | BDRIDP/BAR/SDR/UN-Rd/03 | Improvement of Jagua Union Parishad-Karapur Steel Bridge-Bousherhat GC.a Earthwark Ch. 4905m-6765m.b Carpeting BC Ch. 4905m-6765m.. c Construction of U-Drain 1.00mx1.00m At Ch. 5645m & 1.60x1.60m RCC Box Culvert at Ch.6583md Palsading 42m. | 506513012 |  | 1.86 |  |  |  | 2.6 | 13430037 | [10 empty] | E-Tender Under Process.
8 |  | Sub-Total: |  | 0 | 10.551 | 0 | 0 | 0 | 23.4 | 78834586.22 | 0 | 56419051.92 | [6 empty] | 8300000 |  |  |  | #REF!
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 | 506073023 |  | 1 |  |  |  |  | 4566907 |  | 3523866.83 | M/S Khondokear Brothers | 21/07/15 | 28/07/15 | 27/04/16 |  | 75% | 1150000 | 32.63% | Prepared for Cancelled
2 | BDRIDP/BAR/BAK/CCA-Rd/07 | Improvement of road from Sampur Ray Barir Culvert to Birangal Digirpar Kader Hohlade Bari via Karim Gaji Bari a Earth work 0.0 - 1500m b Bituminous Surfacing - wearing course DC 0.0m - 1500m c 1.5 m x 1.5m RCC Box Culvert at Ch.900m | 506075125 |  | 1.5 |  |  |  | 1.5 | 9125908.56 |  | 8213317.7 | M/S Abul Kalam Azad | 22/01/18 | 29/01/18 | 29/10/18 |  | 70% | 5500000 | 66.96%
3 | BDRIDP/BAR/BAK/UZ-Rd/01 | Improvement of Rahamgonj RHD via Dhokati GPS & Bakergonj-Sampur Road to BoaliaGC Bakergonj-Sampur Road Mill Ghar to Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini a Earth work at Ch.1913-2775mb CarpetingBC at Ch.1913-2775mc Construction of 1No. Box culvert1.06m x 1.06m at Ch.2549m on the same roadd Protective worksSite Facilities& Road Safety works under Bakergonj UpazilaBarishal District.Salvaged cost Tk 921239.00 | 506072014 |  | 0.862 |  |  |  | 1.06 | 8583037 |  | 7995234.286 | M/s Kazi Holdings | 27/08/18 | 2018-04-09 | 2019-04-06 |  | 95% | 4325000 | 54.09%
4 | BDRIDP/BAR/BAK/UZ-St/01 | Construction of 23.00m Long RCC Girder Bridge over road from Kamarkali GC to Baharchar GC via Sarsi Pollice Farry Patkati L/G Faridpur UP Office & Janota Bajarat at Ch. 5847m Under Bakerganj Upazila District Barisal Road ID 506072012 | [6 empty] | 23 | 13048406.72 |  | 12395986.384 | M/S SUN TRADERS | 23/08/18 | 30/08/18 | 2019-04-08 |  | 92% | 11150000 | 89.95%
5 | BDRIDP/BAR/BAK/CCA-RdR/10 | Improvement of Road from Hanua UP Office Bridge to Sarder Bari Foot Bridge via Jainpuri Khanka Sarif Bari & Khodaboxkati Eshak Member Bari Char a Earth work at Ch.0.0 - 2000m b CarpettingBC Ch.0.0 -2000m c Construction of 1 No Box culvert 1.0m x 1.0m at ch.1310m d Protective worksPalisading 60m under Bakergonj UpazilaBarishal District. Salvaged Cost TK.1943192.00 | 506074199 |  | 2 |  |  |  | 1 | 14520624.67 |  | 13794593.43 | M/S Sikder Enterprise | 19/02/19 | 26/02/19 | 19/08/19 |  | 50% | 4002602 | 29.02%
6 | BDRIDP/BAR/BAK/CCA-Rd/11 | Improvement of Road from Goma Amtala to Chatra Hat via Gajir Hat DKP High School & Sowdakar Bari Road by BC at Ch. 1600m-2100. Effective Length 500m.Under Bakerganj Upazila District- Barishal. | 506074136 |  | 0.5 |  |  |  |  | 3243472.3 |  | 3081298.68 | Easy Max | 17/04/19 | 24/04/19 | 24/10/19 |  | 33% | 975000 | 31.64%
7 | BDRIDP/BAR/BAK/CCA-Rd/12 | Improvement of road from Kabiraj Altaf Chairman Bari near Madrasha to East Dhudal Community Pry School via Shahajahan Howlader & Alomgir Mollik Bari road by BC Ch. 736m-2000m. Under Bakerganj Upazila District- Barishal. | 506074148 |  | 1.264 |  |  |  |  | 8566686.78 |  | 8138352.441 | M/S Farhad Enterprise | 2019-04-04 | 2019-11-04 | 2019-11-10 |  | 30% | 2375000 | 29.18%
8 | BDRIDP/BAR/BAK/CCA-Rd/13 | Improvement of Road from Kabai Dhola Riazuddin Madrasha to Khodaboxkati Govt. Pry. School by BC work at Ch.00m-500 with 1 No. 900mx900m U-Drain. Under Bakerganj Upazila District- Barishal. | 506075432 |  | 0.5 |  |  |  | 0.9 | 3857006.71 |  | 3664146.37 | M/S Setu Traders | 2019-09-04 | 16/04/19 | 16/10/19 |  | 50% | 1800000 | 49.12%
9 | BDRIDP/BAR/BAK/CCA-Rd/14 | A Improvement of road from Rabipur Ali Hossain Khan Bari UZR to Sharif Bari via Ayeb Boyati Bari i Earthwork Ch.0.0m-500m ii CarpetingDC Ch.0.0 - 500m.iii Palisading work-50m B Improvement of road from S/Side of Kabai HatNear Chunakhali Sluice Get to E/S of Pearpur Iron BridgeUZR via Chunakhali HatDhola Madrasa & Dhola Sluice Get i Earthwork Ch.4000m-5000m ii Carpeting DC Ch.4000m-5000m iii Construction of 2Nos 1.0m x 1.0m Box Culvert at Ch.4666m 4951m & 1No. U-Drain at Ch.4830m iv Palisading work-55m Under Bakergonj Upazila Barishal District | 506075099 506074155 |  | 1.5 |  |  |  | 2.625 | 11940345.81 |  | 11939429.937 | M/S. Amir Engineering Corporation | 19/05/19 | 26/05/19 | 26/11/19 |  | 72% | 8500000 | 71.19%
10 | BDRIDP/BAR/BAK/CCA-Rd/15 | Improvement of road East Bathsala UZR to Dhulia River Bank via Bathsala Karikornagar GPS infront of Amir Khan Bari Mosque Salvaged Cost Tk 331586.00 i Earthwark Ch.0.00m-1450m. ii Carpeting DC Ch.0.00m-1450m. iii Construction of 01 No U-Drain 0.9mx0.9m at Ch.1250m.iv Palasading 79m. Under Bakergonj Upazila Barishal District. | 506075379 |  | 1.45 |  |  |  | 0.9 | 10466500 |  | 10414223.243 | M/S ISLAM BROTHERS LTD | 2019-12-06 | 19/06/19 | 19/12/19 |  | 60% | 5450000 | 52.33%
11 | BDRIDP/BAR/BAK/CCA-Rd/16 | Part A Improvement of road from H/O Sujauddin Halta F.H. high School. Halta Mouza Sholoshath to Surath Memorial GPS. i Earthwark Ch.0.00m-850m. ii Carpeting DC Ch.0.00m-850m. iii Construction of 02 Nos RCC Culvert1.6mx1.6m at Ch 4m845m 3 Nos U-Drain 0.9mx0.9m at Ch.120m190m235m.iv Palsading 96mPart B Improvement of road from Mokimabad Bajar S/Side of Culvert to East Side of BIP Siuce Get via Dilip Master Bari.Oza Bari to Thakur Bari via Naboraz Biswas bari i Earthwark Ch.2500m-3250m. ii Carpeting DC Ch. 2500m-3250m. iii Construction of 01 No RCC Culvert 1.6mx1.6m at Ch 3125m.iv Palsading 38m.Under Bakergonj Upazila District Barishal. | 506075180 506075229 |  | 1.575 |  |  |  | 7.5 | 14776000 |  | 13806417.904 | M/S Rupali Construction | 14/05/19 | 21/05/19 | 21/11/19 |  | 35% | 4525000 | 32.77%
12 | BDRIDP/BAR/BAK/CCA-Rd/17 | Part A Improvement of road from Padrishibpur GPSUZR to Bismillah Bazar via Sikder Bari Kowabunia khal & Dhulal sadu Bari Salvaged Cost Tk 921459.76i Earthwark Ch.0.0m-900m. ii Carpeting DC Ch. 0.0 - 900m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert & 1No.U-Drain at Ch 482m.& 28m iv Palsading 59m.Under Bakergonj Upazila District Barishal. Part B Improvement of road from East side of Bangla bazar Box Culvert to Wapder Khal Ghorar Bridge Bothra via Biharipur Madrasha road. i Earthwark Ch.3250m-3850m. ii Carpeting DC Ch.3250m-3850m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert at Ch.3255m & 01 No 1.6 m x 1.6m RCC Box Culvert at Ch.3716m iv Palsading 28m.Under Bakergonj Upazila District Barishal.Part C Improvement of road from Padrishibpur Sunddartala Baily Bridge UZR to Aowal Sikderbari i Earthwark Ch.0.0m-500m. ii Carpeting DC Ch. 0.0 - 500m. Under Bakergonj Upazila District Barishal. | 506074057 506074182 506075155 |  | 2 |  |  |  | 6.225 | 16442515.41 |  | 14202513.2 | M/S S H Enterprise | 23/07/19 | 30/07/19 | 30/01/20 |  | 0% |  | 0%
13 | BDRIDP/ BAR/BAK/ CCA-Rd/18 | Improvement of Road UZR Rabipur GPS UNR Younous Sharif Bari Via Rabipur. Salvaged Cost Tk 641271.00i Earthwark Ch.0.00m-500m. ii Carpeting DC Ch.0.00m-500m. iii Palsading 50m. Under Bakergonj Upazila Barishal District. | 506074267 |  | 0.5 |  |  |  |  | 3691293.53 |  | 3506728.85 | M/S Bushra Traders | 2019-10-06 | 17/06/19 | 17/10/19 |  | 70% | 1400000 | 39.92%
14 | BDRIDP/BAR/BAK/ CCA-Rd/19 | A Improvement of Road from Dhaporkati Khayaghat Kabai to Chunakhall Bridge via Najam Master Laxmipasa Senior Madrasha & south Hanua Regd. Pry. School a Earthwark Ch. 1286m-2286m.b Carpeting BC Ch. 1286m-2286m.c Construction of 01 No 1-Vent RCC Box Culvert 1.6mx1.6m at Ch.1386m & 01 No. U-Drain. At Ch. 1652m. d Palsading 47m.B Improvement of Road from Krishnokati Anser Howlader Bari to Nijamkhali Khal over Iron Foot Bridge. Salvaged Cost Tk. 361295.00a Earthwark Ch. 00m-898m.b Carpeting DC Ch. 00m-898m.c Construction of 01 No. U-Drain. At Ch. 197m.d Palsading 64m | 506074154 506075313 |  | 1.898 |  |  |  | 2.8 | 15171756 | [10 empty] | E-Tender Under Process.
15 | BDRIDP/BAR/BAK/CCA-Rd/20 | Improvement of Road from Balaikati Dhanshiri NGO to Kalitara Govt. Pry. School via Howlader bari.ID No-506074188a Earthwark Ch. 00m-1000m.b Carpeting DC Ch. 00m-1000m.c Construction of 01 No 1-Vent RCC Box Culvert 1.6mx1.6m at Ch.510m & 01 No. U-Drain. At Ch. 370m. d Palsading 15m |  |  | 1 |  |  |  | 2.2 | 7695899 | [10 empty] | E-Tender Under Process.
16 | BDRIDP/BAR/BAK/CCA-Rd/21 | Improvement of Road from South kazlakati Arjina Govt. Pry. School to Ukiler Hat road a Earthwark Ch. 00m-900m. b Carpeting BC Ch. 00m-900m. c Construction of 01 Nos RCC Box Culvert 1.6mx1.6m at Ch.234m | 506074039 |  | 0.9 |  |  |  | 1.6 | [11 empty] | E-Tender Under Process
17 | BDRIDP/BAR/BAK/CCA-Rd/22 | Improvement of Road from Dhaporkati khaya Ghat Kabai to Chunakhali Bridge via Najam Master Laxmipasha Senior Madrasha & South Hanua Regd. Pry.School road a Earthwark Ch. 00m-1300m. b Carpeting BC Ch. 00m-1300m. c Linkroad up to H/O Madrasha Quarter 55m d Palisading 70m e Construction of 2 Nos U-Drain 900mm x 900mm at Ch.290m & 1084m | 506074154 |  | 1.3 |  |  |  | 1.8 | [11 empty] | E-Tender Under Process
18 | BDRIDP/ BAR/BAK/ CCA-Rd/23 | Improvement of Road From Mudukhali-Kazlakati Talukder hat.ID No-506075235a Earthwark Ch. 00m-780m.b Carpeting BC Ch. 00m-780m.c Construction of U-Drain 900mmx900mm at Ch. 497m & 01 No 3mx3m RCC Box Culvert at Ch. 780m.d Palsading 74m. | 506075235 |  | 0.78 |  |  |  | 3.3 | [11 empty] | E-Tender Under Process
19 | BDRIDP/ BAR/BAK/ UN-Rd/04 | A Improvement of Road Khayrabath hat Garuria UP to Dhaparkati Bazar Godown via Nilgonj Bazar.ID No-506073001 Salvaged Cost TK 1488714.00a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of RCC Box Culvert 1.50mx1.50m at Ch.520m.d Palsading 100m. B Improvement of Road From Khayrabad UP Garuria UP Office via Khayrabath High School Runsiposor RNGPS west side of Dinger hat. Salvaged Cost TK 1459641.00ID No-506073010a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of RCC Box Culvert 1.50mx1.50m at Ch.760m.d Palsading 90m. | 506073001 506073010 |  | 2 |  |  |  | 1.5 | [11 empty] | E-Tender Under Process
19 |  |  |  | 0 | 22.529 | 0 | 0 | 0 | 57.91 | 145696359.49 | 0 | 114676109.255 | [6 empty] | 51152602 |  |  |  | #REF!
97 |  |  |  | 0 | 136.993 | 0 | 0 | 0 | 382.58 | 1021428153.18 | 46946996 | 652194907.976 | [6 empty] | 205880565 |  |  |  | #VALUE!
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal

## Information
ÒQKÓ
Òewikvj wefvM cjøx AeKvVv‡gv Dbœqb (2q ms‡kvwaZ)Ó kxl©K cÖK‡íi AvIZvq ev¯ÍevwqZ/ev¯Íevqbvaxb ¯‹xgmg~‡ni Z_¨vw`t
Dc‡Rjvi bvgt
µwgK bs | ¯‹x‡gi bvg (AvBwW mn) | wVKv`v‡ii bvg | ¯‹xg Aby‡gv`b ¯§viK I ZvwiL | Pzw³g~j¨ | KvR ïiæi ZvwiL | KvR mgvwßi ZvwiL (cÖK…Z) | nvjbvMv` cwi‡kvwaZ UvKv | ‡fŠZ AMÖMwZ (%) | gšÍe¨
1 | 2 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Upazila: Gournodi
1 | Improvement of road from Gournadi Highway Thana Connecting road under Gournadi Upazila. (Road ID: 506325047) | M/S Tamim Enterprise | Memo No: 264, Date: 18/04/2014 | 1621153 | 21/06/15 | 15/03/16 | 1612193 | 100% | Final | 50% | -801616.5
2 | (a) Improvement of Road from Sarikal GC to Shaheber char Bazar via Nalchira Bazar ch. 5555m-7055m), (b) Construction of 2 nos U-drain at ch.599m & 6555m on the same road Under Gournadi Upazila, District-Barisal (Road ID: 506323013) | M/S Islam Brothers | Memo No: 465, Date: 22/07/2014 | 10357650.8 | 23/11/14 | 22/07/15 | 10353584 | 100% | Final | 60% | -4138993.52
3 | (a) Improvement of Road from Gournadi Bandar GC to Muladi GC via Kutubpur Bazar at ch. 0m-630m), (b) Construction of 2 nos U-drain at ch. 205m & 364m on the same road Under Gournadi Upazila, District-Barisal. (Road ID: 506322016) | M/S Islam Brothers | Memo No: 465, Date: 22/07/2014 | 5399315 | 23/11/14 | 25/05/15 | 5356652 | 100% | Final | 60% | -2117063
4 | Improvement of illah (NHW) to Kalkini Upazila HQ via Tulatala Bazar at ch.2413m-3213m), Under Gournadi Upazila, District-Barisal (Road ID: 506322013) | M/S Sadman Builders | Memo No: 465, Date: 22/07/2014 | 4898705 | 16/11/14 | 27/07/15 | 4667277 | 100% | Final | 40% | -2707795
5 | (a) Improvement of Batazore GC to Pinglakathi Bazar via Pachim Chandrahar GPS at ch. 0m-1000m), (b)Construction of 1 nos U-drain at at ch.14m on the same road, (c) Construction 1v-2.3mx2.30m RCC Box Culvert at ch.527m & 1583m on the same road Under Gournadi Upazila, District-Barisal (Road ID: 506323001) | M/S Islam Brothers | Memo No: 465, Date: 22/07/2014 | 8236744 | 23/11/14 | 22/07/15 | 8218516 | 100% | Final | 50% | -4100144
6 | Improvement of road from Maddam Hosnabad Nabarun RPS to Nezamuddin College by HBB at Ch.481-1492m (Nizamuddin Degree College road from freedom fighter Nizamuddin Shaheber Kaborstan via Madha hosnabad UP Member Md.Matiur Rahman Sarif Bari Bridge under Gouranadi upazila, Barisal District (Road ID: 506324040) | Md. Sirazul Islam Hanif | Memo No: 236, Date: 24/04/2014 | 2601109.88 | 27/11/14 | 09/07/15 | 2583729 | 100% | Final | 100% | 17380.88
7 | Improvement of Barthi Bazar (NHW) to Gournadi GC via Torky GC at ch.2150 - 4150m (Road ID: 506322005) | M/S Santu Traders | Memo No: 526, Date: 11/08/2014 | 13801595 | 15/07/15 | 07/02/16 | 13799645 | 100% | Final
8 | Rehabilitation of road from Mahilara UP Office to Chadshi Hat via Bilogram Bazar (A. Rob Chokder House to Chadshi Hat road) road By BC from Ch. 5370-6900m (Road ID: 506323019) | M/S Santu Traders | Memo No: 1059, Date: 11/12/2014 | 6124969 | 15/07/15 | 30/06/16 | 6121962 | 100% | Final
9 | Rehabilitation of road from Mahilara UP office to Chadshi hat via Billogram Bazar road from Ch. 3740-4850m (Salvage Material Cost Tk. 11,01,418.00) (Road ID: 506323019) | M/S Santu Traders | Memo No: 150, Date: 18/02/2015 | 5623536 | 15/07/15 | 21/01/17 | 4522118 | 100%
10 | Construction of 2-Vent 4.30mx4.30m RCC Box Culvert on Mahilara UP office to Chadshi hat via Billogram Bazar road at Ch. 4200m (Road ID: 506323019) | M/S Santu Traders | Memo No: 149, Date: 18/02/2015 | 2069109 | 15/07/15 | 08/06/16 | 2036343 | 100% | Final
11 | Construction of 3 Nos Single Vent 4.30mx4.30m RCC Box Culvert & 2 nos U-Drain on Battala Kapali bari Bridge (NHW) to Khanjapur High School road at ch. 95m,270m,1276m564m&970m Under Gournadi Upazila, District-Barisal e-ID : 22284 (Road ID: 506324136) | M/S Siam Enterprise | Memo No: 110, Date: 09/02/2015 | 6946789.2 | 2015-08-07 | 25/05/16 | 6943287 | 100% | Final
12 | Improvement of road from Battala Kapali bari Bridge (NHW) to Khanjapur High School road by BC from Ch.00 - 1656m Under Gournadi Upazila, District-Barisal e-ID : 22285 (Road ID: 506324136) | M/S Siam Enterprise | Memo No: 109, Date: 09/02/2015 | 7343257.29 | 2015-08-07 | 24/12/16 | 7343257 | 100% | Final
13 | Improvement of Barthi Bazar (NHW) to Burghata bus Stand (NHW) via Amanagong hat at Ch. 450-2450m. e-ID : 19611 | M/S Howlader Constructure | Memo No: 526, Date: 11/08/2014 | 13172831.8 | 2015-08-07 | 19/09/16 | 13168763 | 100% | Final
14 | Construction of 30.00m PSC Girder Bridge on Barti Bazar to Gournadi GC at Ch.5000km over Anandhapur Khal under Gournadi UpazilaDistrict-Barisal (Road ID: 506322005) | M/S Kohinoor Enterprise | Memo No: 647, Date: 31/07/2017 | 27173350.5 | 18/03/18 |  | 26212000 | 97%
15 | Construction of 32.00m PSC Girder Bridge on Barti BazarNHW to Gournadi GC via Torky GC at Ch.9340km over Kashba Khal under Gournadi Upazila District-Barisal (Road ID: 506322005) | M/S Kohinoor Enterprise | Memo No: 647, Date: 31/07/2017 | 26369588.63 | 18/03/18 |  | 25470000 | 94%
16 | Periodic Maintenance of Batazore-Agarpur-Sarikal via Hosnabad Nalchira-Miarchar road. a Earthwark from Ch. 8725- 17177m.b Carpeting DC 17361.14 sqm.c 12mm SC-13906.56 sqm. Under Gournadi Upazila District - Barishal (Road ID: 506322002) | M/S Mega/Repa Enterprise | Memo No: 795, Date: 18/11/2018 | 16821994.18 | 2019-12-08 |  |  | 0%
17 | Periodic Maintenance of iIlah Bas stand NHW to Agailjhara H/Q via Bakai & Rajihar Bazar in/c Nutun Bazar Connecting road.a Earthwark from Ch. 0- 3832m.b Carpeting DC 3224.409 sqm.c 12mm SC-11191.1 sqm. Under Gournadi Upazila District - Barishal (Road ID: 506322006) | M/S Mega/Repa Enterprise | Memo No: 795, Date: 18/11/2018 | 6210935.51 | 2019-12-08 |  |  | 0%
18 | Periodic Maintenance of Batazore GCNHW to Dhamura GC via Solak Bazar road.a Earthwark from Ch. 0- 2145m.b Carpeting 40mm-DC 6403.2 sqm.c Palisading Work297.00m. Under Gournadi Upazila District - Barishal (Road ID: 506322011) | M/S Mega/Repa Enterprise | Memo No: 795, Date: 18/11/2018 | 9265509.3 | 2019-12-08 |  |  | 0%
19 | Periodic Maintenance of Chadshi UP Office-Goila UP Office Road.a Earthwark from Ch. 0- 830m.b Carpeting DC 322.5 sqm.c 12mm SC-2208.35 sqm. Under Gournadi Upazila District - Barishal (Road ID: 506323020) | M/S Mega/Repa Enterprise | Memo No: 795, Date: 18/11/2018 | 1051305.98 | 2019-12-08 |  |  | 0%
20 | A Maintenance Nathai BazarDR to Bauthi UP Office via Chandsi a Earthwark Ch.00m-1150m.b Carpeting DC Ch.00m-1150m. B Maintenance Badarpur Bazar to Sarikal UP Office a Earthwark Ch.00m-4787m.b Carpeting DC Ch.00m-4787m. c Palsading 50m (Road ID: 506323003, 506323009) |  | Memo No: 305, Date: 15/04/2019 | 11855719.7 |  |  |  |  | E-Tender Under Process.
21 | Improvement of road with BC from Steemar Ghat to Hosnabad hat road from at Ch.00m-630m (Road ID: 506324041) |  | Memo No: 306, Date: 15/04/2019 | 4471349.78 |  |  |  |  | E-Tender Under Process.
22 | A Improvement of Road Batazore NHW to Jissorekati GPS. a Earthwark Ch.500m-1307m.b Carpeting BC Ch. 500m-1307m. c Construction of 01 Nos U-Drain at Ch.778m. d Palsading 107m. B Improvement of road by BC from Nalchira UP Office of Kalabaria Bazar via Pingolakati Model GPS. Salvaged Cost TK 11294.00a Earthwark Ch.500m-2056m.b Carpeting BC Ch.500m-2056m (Road ID: 506324018, 506324060) |  | Memo No: 393, Date: 21/05/2019 | 17836679.64 |  |  |  |  | E-Tender Under Process.
23 | Improvement of Road from Chandshi UP Office-Uttar Pallordi GPS Ramshiddi Bazarvia Chadshi High School. a Earthwark Ch.900m-1353m.b Carpeting BC Ch. 900m-1353m.c Construction of 01 No 1-Vent RCC Box Culvert 1.3mx1.3m at Ch.1266m. d Palsading 52m (Road ID: 506323027) |  | Memo No: 395, Date: 21/05/2019 | 4140788.45 |  |  |  |  | E-Tender Under Process.
24 | Improvement of Road by BC from Barthi Bazar NHW Bhurghata Bus Stand NHW via Amanathgonj Hat. Salvaged Cost TK 2742324.00a Earthwark Ch.5388m-7450m.b Carpeting BC Ch. 5388m-7450m.c Construction of 02 Nos U-Drain at Ch.6200m & 7350m. d Palsading 120m (Road ID: 506322017) |  | Memo No: 395, Date: 21/05/2019 | 16418601.51 |  |  |  |  | E-Tender Under Process.
25 | A Improvement of Road Borobari NHW to Sarifabad via Sarifabad Hapania GPS. a Earthwark Ch.00m-1500m.b Carpeting BC Ch. 00m-1500m. c Palsading 67m. Under Gournadi Upazila Barishal DistrictB Improvement of Bagat Sarifabad road. a Earthwark Ch.1070m-1520m. b Carpeting BC Ch.1070m-1520m.c Palsading 25m (Road ID: 506324084, 506324119) |  | Memo No: 431, Date: 29/05/2019 | 15243061.87 |  |  |  |  | E-Tender Under Process.
26 | A Improvement of road from Aduna Battala Aduna GPS road from Under Gournadi Upazila Barishal District. Salvaged Cost. Tk 1270072.00. a Earthwark Ch. 00m-850m.b Carpeting BC Ch. 00m-850m.c Construction of 01 Nos U-Drain0.625m x 0.600m At Ch. 643m B Improvement of road from Kutubpur High Bridge Kalabaria Bazar via Sankorpasha GPS road from. Under Gournadi Upazila Barishal District. a Earthwark Ch. 00m-2050m.b Carpeting BC Ch. 00m-2050m. c Construction of 01 Nos U-Drain0.625m x 0.600m At Ch. 1481m |  |  | 23201500 |  |  |  |  | E-Tender Under Process.
27 | Improvement of road From NHW at Kasba Hat to Billogram hat via Badamtala Road. Under Gournadi Upazila Barishal District. Salvaged Cost. Tk 539572.00 a Earthwark Ch. 00m-90m & 3290m-4900m.b Carpeting BC Ch. 00m-90m & 3290m-4900m. Improvement of road from Kutubpur Bazar-Badurpur Bazar road. Under Gournadi Upazila Barishal District. Salvaged Cost. Tk 234974.00a Earthwark Ch. 00m-950m.b Carpeting BC Ch. 00m-950m. c 1No. U -Drain 0.625m x 0.600m at Ch.500m |  |  | 21970500 |  |  |  |  | E-Tender Under Process.
27 |  |  |  | 290227650.02 |  |  | 138409326 |  |  |  | -13848231.14
1 | Improvement of road from Mahilara UP Office to Chadshi hat via Billogram Bazar road By Earth Filling Work from Ch. 3740m-4850m (Road ID: 506323019) | Anjur Ali Sarder LCS No-1 | Memo No: 148, Date: 18/02/2015 | 349519 | 15/11/15 | 30/03/16 | 349399 | 100%
2 | Resectioning of road from Brthi Bazar (NHW) to Gournadi GC via Torky GC at Ch. 2150m-4150m by earth (Road ID: 506322005) | Md Shalim Khalifa LCS-1 | Memo No: 647, Date: 21/06/2016 | 223623 | 2016-10-10 | 10/01/17 | 223598 | 100%
3 |  | Sunil Joydhar LCS-2 | Memo No: 647, Date: 21/06/2016 | 69892 | 2016-10-10 | 10/01/17 | 69822 | 100%
4 | Resectioning of road from Brthi Bazar (NHW) to Burghata Bus Stand (NHW) via Amanothgonj hat at Ch. 450m-2450m by earth (Road ID: 506322017) | Md Mahabub Khan LCS-1 | Memo No: 647, Date: 21/06/2016 | 300092 | 2016-10-10 | 10/01/17 | 299749 | 100%
5 |  | Md Mohasin Sharder LCS-2 | Memo No: 647, Date: 21/06/2016 | 209955 | 2016-10-10 | 10/01/17 | 209849 | 100%
5 |  |  |  | 1153081 |  |  | 1152417 |  |  |  | 0
32 |  |  |  | 291380731.02 |  |  | 139561743 |  |  |  | -13848231.14
Upazila: Agailjhara
1 | Improvement of Road by BC from Rathkhola Bazar-Bhadrapara Road (ch. 0m-1000m) Under Agailjhara Upazila, District-Barisal (Road ID: 506024008) | M/S Talukder Enterprise | Memo No: 465, Date: 22/07/2014 | 5599756.34 | 30/10/14 | 25/05/15 | 5597543 | 100% | Final
2 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila, Barisal (Road ID: 506025048) | M/S Mitushi Traders | Memo No: 589, Date: 27/08/2014 | 4583839 | 2014-08-12 |  |  | 100% | W/O Cancel
3 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m (Road ID: 506025056) | M/S Sharif Enterprise | Memo No: 891, Date: 18/12/2014 | 5158284.22 | 29/04/15 | 27/02/17 | 5157868 | 100% | Final | 50% | -2578725.89
4 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m (Road ID: 506025058) | M/S Sharif Enterprise | Memo No: 760, Date: 21/10/2014 | 1771918.99 | 2015-04-06 | 18/12/16 | 1693392 | 100% | Final
5 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m (Road ID: 506023001) | M/S Sharif Enterprise | Memo No: 848, Date: 12/11/2014 | 15592739.8 | 2015-06-06 | 10/05/17 | 15592732 | 100% |  | 20% | -12474184.04
6 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by BC from Ch. 3800m-5800m (Road ID: 506022003) | M/S Sraboni Construction | Memo No: 848, Date: 12/11/2014 | 11288255.96 | 2015-04-06 | 10/12/15 | 11286798 | 100% | Final | 60% | -4513844.424
7 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m (Road ID: 506024034) | M/S Sarniabad Enterprise | Memo No: 762, Date: 21/10/2014 | 6375868.44 | 2015-01-06 | 15/04/17 | 6375048 | 100% | Final | 60% | -2549526.936
8 | Improvement of road from Poiser hat GC-Ramshil Bazar via Trimukhi road by BC from Ch. 0.00m-1000m (Road ID: 506024040) | M/S Shafique Brothers | Memo No: 762, Date: 21/10/2014 | 5538660.26 | 28/05/15 | 06/06/16 | 5554952 | 100% | Final | 70% | -1677889.818
9 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m (Road ID: 506025058) | M/S Helal Traders | Memo No: 762, Date: 21/10/2014 | 4400152.34 | 2015-09-07 | 10/06/17 | 3950000 | 100% |  | 30% | -2629954.298
10 | Rehabilitation of Barthi - Valukshi - Magura- Ambari-Bakalhat road by BC at ch.5870-7880m (Road ID: 506022008) | M/S Santu Traders | Memo No: 526, Date: 11/08/2014 | 13383052 | 15/07/15 | 20/12/16 | 13383025 | 100% | Final
11 | Improvement of road from Biplob Serniabad House to Hazi Musa House road By BC from ch.00-400m (Road ID: 506025084) | M/S Serniabad Enterprise | Memo No: 150, Date: 18/02/2015 | 2012714.3 | 2015-08-07 | 05/12/16 | 2012370 | 100% | Final
12 | Improvement of road from Seral - Goila road via Shahid Serniabad House - Tamer Jame Mosjid(Tamer Girls High School-Seral Community Center) by BC (Ch.0.0 - 975m) under Agailjhara Upazila, Barisal (Road ID: 506025048) | M/S Serniabad Traders | Memo No: 787, Date: 08/11/2016 | 7230073.2 | 16/03/17 | 15/01/18 | 7153140 | 100% | Final
13 | Improvement of road from Hazi Mokbul Sardar House via Sardar Mohabubul Alom & Sardar Harun - Jainger Gomosta House road. at Ch.00 to 208m under Agailjhara Upazila Barisal (Road ID: 506025088) | M/S Sharif Enterprise | Memo No: 873, Date: 02/11/2017 | 2276707.38 | 22/03/18 | 26/01/18 | 2162693 | 100%
14 | Construction of Ghat at Paisarhat Paschim par under Agailjhara Upazila Barisal | M/S Sharif Enterprise | Memo No: 797, Date: 10/12/2017 | 2958070.38 | 29/03/18 | 25/03/19 | 2946824 | 100%
15 | Maintenance of Barthi- Valiukshi-Magura Bakal Hat Roada Earthwark from Ch. 9860- 11860m.b Carpeting DC 21.3 sqm.c 12mm SC-5237.7 sqm. d Palisading Work 103.00m. Under Agailjhara Upazila District- Barishal (Road ID: 506022008) | M/S Yeamin Traders | Memo No: 794, Date: 18/11/2018 | 2377531.18 | 2019-02-09 |  |  | 0%
16 | Maintenance of Road From Nimtola RHD-Dhamura GC viaRatnapur UP Road at Ch 5265m-7383m Agailjhara Under Agailjhara Upazila District- Barishal (Road ID: 506022010) | M/S Sharif Enterprise | Memo No: 794, Date: 18/11/2018 | 2781847.17 | 27/08/19 |  |  | 0%
17 | Maintenance of Road From Goila UP Office to Billogram Bazar via Rajer Bari Road at Ch 00m-2000mm Agailjhara Under Agailjhara Upazila District- Barishal (Road ID: 506023008) | M/S Sarder Enterprise | Memo No: 794, Date: 18/11/2018 | 3033987.51 | 29/08/19 |  |  | 0%
18 | Maintenance of Road From Basail Hat Rajihar UP-Batra Bazar viiiia Basail Pachchim Para Bazar Road at Ch 00m-1000m Agailjhara Under Agailjhara Upazila District - Barishal (Road ID: 506023006) | M/S Yeamin Traders | Memo No: 794, Date: 18/11/2018 | 3685551.86 | 2019-02-09 |  | 2500000 | 0%
19 | A Improvement of Temar Bastaila Nagar GPS-West Mollapara-Ohchiarmad Bazar. i Earthwark Ch.650m-1865m.ii Carpeting DC Ch. 650m-1865m. iii Palsading 641m.B Choto Basail Kader Bepari House to East Valukshi Bridge.Salvaged Cost Tk 37835.00i Earthwark Ch.0.00m-360m.ii Carpeting DC Ch.0.00m-360m. iii Palsading 120m. Under Agailjhara upazila District Barishal (Road ID: 506024009, 506025045) |  | Memo No: 171, Date: 18/02/2019 | 15112757.21 |  |  |  |  | Evaluation Send to H/Q for Approval
20 | Improvement of Alloshika-Ramanonder AK Bazar-Batra Bazar Ramsell road from Ch.1000m-1800m (Road ID: 506025050) | M/S Sarder Enterprise | Memo No: 304, Date: 15/04/2019 | 7803874.95 | 2019-01-11 |  | 1500000
21 | Improvement of Road from Boramagra Switch gate Bazarvia Kodaldhoa Bazar to Ramshil bazar.a Earthwark Ch. 1000-5250m.b Carpeting DC Ch. 1000-5250m. c Palsading 556m (Road ID: 506024034) |  | Memo No: 325, Date: 23/04/2019 | 31659786.62 |  |  |  |  | E-Tender Under Process.
22 | A Improvement of Ghatoker Poll-Daspottry Janata Bazar- Patihal Gomosta Bari Box Culvert via Janata GPS New. a Earthwark Ch. 600m-1600m.b Carpeting BC Ch. 600m-1600m.c Palsading 300m.B Improvement of Ambulla Switchgate to Kotalipara Border Road. Salvaged Cost Tk 522605.00a Earthwark Ch. 1194m-1773m.b Carpeting BC Ch. 1194m-1773m. c Construction of 01 Nos U-Drain 1125mx600m at Ch.618m. d Palsading 160m (Road ID: 506024043, 506024045 |  | Memo No: 355, Date: 12/05/2019 | 13933337.2 |  |  |  |  | E-Tender Under Process.
23 | A Improvement of Mollapara Saw Mill-Taler Bazar-Ramar Bazar Kalurpar Bazar road. Salvaged Cost Tk 535334.00 a Earthwark Ch. 1000m-2230m.b Carpeting BC Ch. 1000m-2230m.B Improvement of Goila Baby home- Nathoy Road via Abu Hanif Sarkers Bari. a Earthwark Ch. 700m-1100m.b Carpeting BC Ch. 700m-1100m.c Palsading 5m (Road ID: 506024041, 506025124) |  | Memo No: 354, Date: 12/05/2019 | 11826330.04 |  |  |  |  | E-Tender Under Process.
24 | Improvement of Mahilara-Chaygram-Amboula-Paisarhar Road. Salvaged Cost Tk 1100033.00 a Earthwark Ch. 22280m-23226m.b Carpeting BC Ch. 22280m-23226m.c Palsading 148m (Road ID: 506022006) |  | Memo No: 353, Date: 12/05/2019 | 8037695.77 |  |  |  |  | E-Tender Under Process.
25 | Improvement of Agailjhara-Sujankathi via Nilkanda road. Salvaged Cost - Tk 1833963.00a Earthwark Ch. 600m-1725m.b Carpeting DC Ch. 600m-1725m. c Construction of 01 Nos 2 vent 4.0mx4.0m RCC Box Culvert at Ch.1025m. d Palsading 333m (Road ID: 506024019) |  | Memo No: 353, Date: 12/05/2019 | 12773520.12 |  |  |  |  | E-Tender Under Process.
26 | Improvement of Sobikharpar RHD to Askar Hat UZR. a Earthwark Ch.1583m-2968m.b Carpeting BC Ch.1583m-2968m. C Palsading 288m (Road ID: 506024052) |  | Memo No: 429, Date: 29/05/2019 | 11179100.39 |  |  |  |  | E-Tender Under Process.
27 | Construction of 15.00m RCC Girder Bridge on Shaheber hat - Ramer Bazar to Gurucharan Babu House (Road ID: 506024017) |  | Memo No: 432, Date: 29/05/2019 | 16443882.21 |  |  |  |  | E-Tender Under Process.
28 | Construction of 14.00m RCC Slab Bridge on Despotty Janata Bazar - Patihar Sluice via Despotty Janata GPS Ghatoker Poll - Despotty Janata Bazar - Patihar Gomosta Bari Box Culvert via Janata GPS NEW at Ch.410m (Road ID: 506024043) |  | Memo No: 432, Date: 29/05/2019 | 15451567.02 |  |  |  |  | E-Tender Under Process.
29 | Construction of 16.00m RCC Pedestrain Bridge near of Shahid Fakir home at Khajuria Khajuria Rucca Road to Gogwsar Masters Bari (Road ID: 506025114) |  | Memo No: 432, Date: 29/05/2019 | 11082682.03 |  |  |  |  | E-Tender Under Process.
30 | Improvement of Bakal Wapda Embankment to Bakal Hat. a Earthwark Ch.1400m-2455m & 3253m-4260m.b Carpeting BC Ch. 1400m-2455m & 3253m-4260m.c Construction of 2 Nos U-Drain 1.125mx0.60m At Ch. 2943m & 4145m. d Palsading 553m. Salvaged Cost Tk 364102.00 (Road ID: 506024006) |  | Memo No: 629, Date: 02/07/2019 | 17608532.09 |  |  |  |  | E-Tender Under Process.
31 | A Improvement of Moulabi Bazar hat-Kumarvanga Bazar Uttar Shehipasha Joynal Sarders Bari Salvaged Cost Tk 507417 a Earthwark Ch. 150m-1185m.b Carpeting BC Ch. 150m-1185m.c Construction of 01 Nos Single-Vent 2.00mx2.00m RCC Box Culvert At Ch. 927md Palsading 94m. B Improvement of Amboyla Hobi Howladers Bari Pachchim Amboyla road. Salvaged Cost Tk 46969.00 a Earthwark Ch.00m-905m.b Carpeting BC Ch. 00m-905m. c Construction of 01 Nos U-Drain Size 1125mmx600mm at Ch. 800m.d Palsading 175m. Total Salvaged Cost Tk 554386.00 (Road ID: 506025038, 506025097) |  | Memo No: 628, Date: 02/07/2019 | 16009406.06 |  |  |  |  | E-Tender Under Process.
32 | A Improvement of BC Road from Goila Bazar-Rothkhola Bazar-Nonapukurpar-Bhadrapara road Taler Bazar-UZR Salvaged Cost. Tk . 1777935.00 Under Agailjhara Upazila Barishal District.a Earthwark Ch. 1440m-2777m.b Carpeting BC Ch. 1440m-2777m.c Palsading 574m. B Improvement of BC road from Ratnapur UP GPS-Kalarmore Uzirpur Border Box Culvert. Under Agailjhara Upazila Barishal District.a Earthwark Ch.1000m-1600m.b Carpeting BC Ch. 1000m-1600m. c Construction 01 No 1x1.60mx1.60m RCC Box Culvert at Ch. 1435md Palsading 99m. C Improvement of BC road from west Mohjonkathi GPS to Ratnapur Sluice Gate UZRroad. Under Agailjhara Upazila Barishal District. a Earthwark Ch.500m-2000m.b Carpeting BC Ch. 500m-2000m. c Palsading 162m. |  |  | 32138000 |  |  |  |  | E-Tender Under Process.
33 | A Improvement of BC road from Chandarvanga UNRBC Road-Pakurita Rathbari R&H road Under Agailjhara Upazila Barishal District Salvaged Tk.2031168.00 a Earthwark Ch. 500m-2021m.b Carpeting BC Ch. 500m-2021m.c Palsading 239m. B Improvement of BC Road from Fullashree R&H Post Office to Gupterhat via Uttar Shipasha High School Under Agailjhara Upazila Barishal District. a Earthwark Ch. 800m-1450m.b Carpeting BC Ch. 800m-1450m.c Construction of 01 Nos U-Drain At Ch. 1030md Palsading 87m. |  |  | 19372546.46 |  |  |  |  | E-Tender Under Process.
34 | A Improvement of Kandirpar Changutia Kamal Howlader Bari to Jalil maulanas bari via Dakkin par Eid gha road at Ch. 785.00m-1750.00m. including 01 No- U-Drain 0.625mx0.600m at Ch. 1630.00m. Salvaged Cost Tk 106371.00B Improvement of Changutia to kazigram road at Ch. 0.00m-645.00m including 01 no. U-Drain 0.625mx0.600m at Ch. 35.00m. Salvaged Cost Tk 88433.00 under Agailjhara Upazila Barishal District Total Salvaged Cost Tk 194804 |  |  | 13872241.11 |  |  |  |  | E-Tender Under Process.
35 | A Improvement of Road from Baropaika Karim Bazar R&H Dhafar per GPS-Baro Paika Deghir Par Road. at Ch. 00.00-803.00m including 01 No U-Drain 1.125mx0.60m at Ch. 210.00m. Salvaged Cost Tk 157731.00 B Improvement of Road from Jobarpar-Askor Road. at Ch. 1500.00-1915.00m. C Improvement of Road from Kathira Old UNR Bazar S/S-CCDP Morer Road. at Ch. 500.00-1045.00m. under Agailjhara Upazila Barishal District Salvaged Cost TK 91656.00 Total Salvaged Cost TK 249387.00 |  |  | 17782745 |  |  |  |  | E-Tender Under Process.
35 |  |  |  | 372137014.61 |  |  | 86866385 |  |  |  | -26424125.406
1 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal (Road ID: 506024034) | Ramesh Chandra Shikari LCS No-1 | Memo No: 761, Date: 21/10/2014 | 153224 | 20/02/15 |  | 119075 | 100%
2 |  | Md Halim Talukder LCS No-2 | Memo No: 761, Date: 21/10/2014 | 148896 | 20/02/15 |  | 122647 | 100%
3 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal (Road ID: 506025058) | Abdul Hakim Molla LCS No-1 | Memo No: 761, Date: 21/10/2014 | 216905 | 2015-05-02 |  | 140432 | 100%
4 |  | Anukul Chandra Barai LCS No-2 | Memo No: 761, Date: 21/10/2014 | 231753 | 2015-05-02 |  | 185062 | 100%
5 | Resectioning of road from Temar Bastala to Hawla Bridge via Nagar GPS-Talbazar-lichermath Bazar road from Ch. 3840-4840m. | Nolini Halder LCS No-1 | Memo No: 362, Date: 01/06/2016 | 344680 | 15/01/17 |  | 306262 | 100%
6 |  | Susen Bala LCS No-2 | Memo No: 362, Date: 01/06/2016 | 230350 | 15/01/17 |  | 226669 | 100%
7 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal (Road ID: 506022009) | Md. Sohrab Howlader LCS No-1 |  | 124341 | 20/02/15 |  | 124340 | 100% | Final
8 |  | Md. Mosharef Sheikh LCS No-2 |  | 307876 | 20/02/15 |  | 307875 | 100% | Final
9 |  | Abdul Rashid Howlader LCS No-3 |  | 329106 | 20/02/15 |  | 329106 | 100% | Final
10 |  | Matleb Howlader LCS No-4 |  | 330529 | 20/02/15 |  | 329457 | 100% | Final
11 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal (Road ID: 506023001) | Mahim Baishnab LCS No-1 |  | 201404 | 20/02/15 |  | 201396 | 100%
12 |  | Sudhir Kumar Ojha LCS No-2 |  | 289300 | 20/02/15 |  | 288996 | 100%
13 |  | Banendra Nath Panday LCS No-3 |  | 288022 | 20/02/15 |  | 287780 | 100%
14 |  | Rabindranath Sarker LCS No-4 |  | 207336 | 20/02/15 |  | 207335 | 100%
15 |  | Nirmal Ghatak LCS No-5 |  | 205837 | 20/02/15 |  | 205837 | 100%
16 |  | Bebek Pandey LCS No-6 |  | 207632 | 20/02/15 |  | 207631 | 100%
17 |  | Pangkoj Joydhor LCS No-7 |  | 205952 | 20/02/15 |  | 205952 | 100%
18 | Resectioning of Road from Seral-Goila road via Shahid Serniabad House-Tamer Jame Mosjid (Tamer Girls High School-Seral Community Center) by Earth at Ch. 0.00m-975m (Road ID: 506025048) | Md. Babul Sikder | Memo No: 786, Date: 08/11/2016 | 317636 | 30/03/17 | 15/02/18 | 310599 | 100%
18 |  |  |  | 4340779 |  |  | 4106451 |  |  |  | 0
53 |  |  |  | 376477793.61 |  |  | 90972836 |  |  |  | -26424125.406
Upazila: Uzirpur.
1 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. | M/S Safi Enterprise | Memo No: 14, Date: 15/01/2014 | 5567698.82 | 18/06/14 | 25/12/16 | 5512198 | 100% | Final |  | 5567698.82
2 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m (Road ID: 506945205) | Md Zakir Hossain Mia | Memo No: 588, Date: 27/08/2014 | 2015457.24 | 30/11/14 | 25/05/15 | 1973907 | 100% | Final |  | 41550.24
3 | Improvement of road from Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market, Nurani Madrasha & H/O Mr.Habibur Rahman (Beer Protik) by BC from Ch.0.00-1500m under Uzirpur Upazila, Barisal (Road ID: 506945205) | Md Sirazul Islam Hanif | Memo No: 589, Date: 27/08/2014 | 5166258 | 2014-08-12 | 25/05/15 | 5166254 | 100% | Final | 70% | -1549873.4
4 | Improvement of road from Paschim Satla WAPDA to Satla Kheyaghat via H/O Fazlul Hoque Hawlader & Mosque By HBB from Ch. 0.00-375m (Road ID: 506945204) | M/S Lutful Kabir | Memo No: 739, Date: 15/10/2014 | 1225909.58 | 2015-12-04 | 30/08/15 | 1223186 | 100% | Final | 100% | 2723.58
5 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m (Road ID: 506945129) | Md Zakir Hossain Mia | Memo No: 968, Date: 02/12/2014 | 2682855.6 | 18/05/15 | 18/10/15 | 2674595 | 100% | Final | 70% | -796596.08
6 | Rehabilitation of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) road from Ch. 0.00m-2100m (Road ID: 506942005) | M/S G M Construction | Memo No: 447, Date: 19/05/2015 | 8522561.6 | 2015-05-10 | 20/05/15 | 8522424 | 100% | Final
7 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal (Road ID: 506942007) | M/S Hasan Construction | Memo No: 814, Date: 13/12/2016 | 14275617.27 | 2017-08-03 |  | 7750000 | 60%
8 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal (Road ID: 506942015) | M/S Hasan Construction | Memo No: 814, Date: 13/12/2016 | 11501091.23 | 2017-08-03 |  | 8635000 | 77%
9 | Rehabilitation of Harta Chowmuhani Bisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 (Road ID: 506942009) | M/S S H Enterprise | Memo No: 315, Date: 17/04/2017 | 18399998.87 | 15/03/18 |  | 6750000 | 70%
10 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m (Road ID: 506943007 506942018) | M/S Niaz Traders | Memo No: 423, Date: 18/05/2017 | 13554596.17 | 2017-09-10 |  | 6054441 | 40%
11 | Construction of 12.00m Long RCC Girder Bridge over Chowdhuri Hat - Hasti Shundi via Daberkul road infront of A. Latif MasterDaberkul Chowmohani - Chowmohini Sere Bangla road at ch. 00.0m under Uzirpur Upazila Barisal District (Road ID: 506943004) | M.M Builders & Engineers | Memo No: 822, Date: 16/10/2017 | 7535398.53 | 2018-07-02 |  | 7535398 | 100%
12 | Improvement of Old Sikerpur Bandar-Abul Hasan Mridhas House Connecting road under Uzirpur Upazila Barisal a Earthwork Ch.0.0m - 360m b Bituminous Carpetting Ch.0.0m - 360m c U-Drain 01 no at Ch.117 (Road ID: 506945281) | M/S Kohinoor Enterprise | Memo No: 13, Date: 03/01/2018 | 2464848.57 | 29/04/18 | 11/10/19 | 2183531 | 60%
13 | Improvement of road from Guthia kakradhari Connecting road North side of Khaleque Mollas House of Dahorpara GPS via Mojid Masters House under Uzirpur Upazila Barisal a Earthwork Ch.0.0m -1550m b Bituminous Carpetting Ch.0.0m - 1550m c U-Drain 04 nos at Ch.130m476m655m1230m & 2Nos 1-Vent 4m x 4m RCC Box Culvert at ch.755m & 1540m (Road ID: 506944084) | Md. Mahafuz Khan | Memo No: 13, Date: 03/01/2018 | 10838588.2 | 2018-10-05 |  | 2600000 | 60%
14 | Construction of Typical Ghat at Satla Bazar under Uzirpur Upazila Barisal . | M/S S H Enterprise | Memo No: 979, Date: 10/12/2017 | 2460575.82 | 2018-12-05 | 20/06/19 | 2200000 | 100%
15 | Part A Improvement of road from Muktijodda Milon Kendra Connecting road Harasia road.i Carpeting DC Ch. 0.00m-900m. ii 3 Nos.0.625mx0.600m U-Drain at Ch.10m365m665m.Part B Improvement of road from East Joysree Village road.i Carpeting DC Ch. 0.00m-1000m.ii 2 Nos.0.625mx0.600m U-Drain at Ch.605m865m. Salvaged Cost Tk 141267.00Part C Improvement of road from Jugihati-Chokder bari Jame Mosque to Damodarkathi Tri mukhi Atok road by DC at Ch.0.00m-1050.00m with 1 No.4.30mx4.30m RCC Box Culvert at Ch.560m. 3 Nos.0.625mx0.600m U-Drain at Ch.130m760m & 835m. Under Uzirpur Upazila Barishal District (Road ID: 506945170, 506945028, 506945172) | M/S Mudasser Ali Mallick | Memo No: 99, Date: 31/01/2019 | 21586749.471 | 30/05/19 |  | 1500000 | 10%
16 | A Improvement of road from Uttar Dhamura WAPDA-H/O Santu Molla road. at Ch. 0.00m-775m including of 03 Nos U-Drain 0.625mx0.600m at Ch. 38.00m 260.00m & 680.00m. B Improvement of road from Uttar Dhamura WAPDA-H/O Kadam Ali-H/O Mobarok Sikder road at Ch. 1200m-1885m. under Uzirpur Upazila Barishal District |  |  | 12481301.91 |  |  |  |  | E-Tender Under Process.
16 | Sub-Total: |  |  | 140279506.881 |  |  | 70280934 |  |  |  | 3265503.16
1 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 0.00m-700m (Road ID: 506942005) | Yasin Sarder LCS No-1 | Memo No: 446, Date: 19/05/2015 | 258990 | 15/02/16 | 30/04/16 | 241309 | 100% | Final
2 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 700m-1400m (Road ID: 506942005) | Iqbal Hossan LCS No-2 | Memo No: 446, Date: 19/05/2015 | 284900 | 15/02/16 | 30/04/16 | 271670 | 100% | Final
3 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 1400m-2100m (Road ID: 506942005) | Supian LCS No-3 | Memo No: 446, Date: 19/05/2015 | 278170 | 15/02/16 | 30/04/16 | 275956 | 100% | Final
4 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 0.00m-1100m (Road ID: 506942007) | Md. Shahidul Islam LCS No-1 | Memo No: 815, Date: 13/11/2016 | 418543 | 2017-01-02 | 30/04/17 | 251299 | 100%
5 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1100m-1900m (Road ID: 506942007) | Md. Khalilur Rahman LCS No-2 | Memo No: 815, Date: 13/11/2016 | 451503 | 2017-01-02 | 30/04/17 | 271244 | 100%
6 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1900m-2605m (Road ID: 506942007) | Habibur Bapari LCS No-3 | Memo No: 815, Date: 13/11/2016 | 491755 | 2017-01-02 | 30/04/17 | 296067 | 100%
7 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 1754m-2850m (Road ID: 506942015) | Kamrun Nesa LCS No-1 | Memo No: 816, Date: 13/11/2016 | 421703 | 18/12/16 | 18/03/17 | 303105 | 100%
8 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 2850m-3650m (Road ID: 506942015) | Rubina Begum LCS No-2 | Memo No: 816, Date: 13/11/2016 | 466527 | 18/12/16 | 18/03/17 | 329485 | 100%
9 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 3650m-4050m (Road ID: 506942015) | Monzu Begum LCS No-3 | Memo No: 816, Date: 13/11/2016 | 342538 | 18/12/16 | 18/03/17 | 245583 | 100%
10 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3400m-3900m By Earth (Road ID: 506943007, 506942018) | Md. Ziaul Haque LCS No-1 | Memo No: 424, Date: 18/05/2017 | 434519 | 31/05/17 | 31/10/17 | 430783 | 100% | Final
11 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3900m-4300m By Earth (Road ID: 506943007, 506942018) | Khokon Sharder LCS No-2 | Memo No: 424, Date: 18/05/2017 | 437099 | 31/05/17 | 31/10/17 | 435285 | 100% | Final
12 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4300m-4900m By Earth (Road ID: 506943007, 506942018) | Rofiqul Islam LCS No-3 | Memo No: 424, Date: 18/05/2017 | 461279 | 31/05/17 | 31/10/17 | 459873 | 100% | Final
13 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4900m-5740m By Earth (Road ID: 506943007, 506942018) | Nurul Hoq Sikder LCS No-4 | Memo No: 424, Date: 18/05/2017 | 310321 | 31/05/17 | 31/10/17 | 310041 | 100% | Final
14 | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 0.00m-1000m (Road ID: 506942009) | Shilpi Biswas LCS No-1 | Memo No: 310, Date: 17/04/2017 | 512862 | 30/10/17 | 30/03/18 | 511764 | 100%
15 | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 1000m-1700m (Road ID: 506942009) | Namita Rani Biswas LCS No-2 | Memo No: 310, Date: 17/04/2017 | 380788 | 30/10/17 | 30/03/18 | 113000 | 100%
16 | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 1700m-2500m (Road ID: 506942009) | Sabika Das LCS No-3 | Memo No: 310, Date: 17/04/2017 | 461975 | 30/10/17 | 30/03/18 | 458856 | 100% | Final
16 | Sub-Total: |  |  | 6413472 |  |  | 5205320 |  |  |  | 0
32 | Grand Total: |  |  | 146692978.881 |  |  | 75486254 |  |  |  | 3265503.16
Upazila: Banaripara
1 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal (Road ID: 506102003) | M/S Saleha Enterprise | Memo No: 678, Date: 25/09/2016 | 5349539.02 | 2017-06-02 |  | 1300000 | 50% |  | 40% | 839815.608
2 | Construction of 1No.2.0m x 2.0m,1 No.3.0m x 3.0m, 2Nos.4.0m x 4.0m, 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road (Road ID: 506102003) | M/S Soma Enterprise | Memo No: 679, Date: 25/09/2016 | 5461652.5 | 2017-02-02 |  | 5200000 | 100%
3 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara Upazila Barisal District (Road ID: 506102003) | Md Mahfuz Khan | Memo No: 314, Date: 17/04/2017 | 10665148 | 2017-05-10 |  | 9450000 | 95%
4 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara Upazila Barisal District (Road ID: 506102003) | Md Mahfuz Khan | Memo No: 314, Date: 17/04/2017 | 8832936 | 2017-05-10 |  | 8164776 | 92%
5 | Construction of RCC Ghat at Mohish Katakhali Kheya Ghat under Banaripara Upazila Barisal . | M/S Amir Engineering Corporation | Memo No: 979, Date: 10/12/2017 | 2620739.69 | 2018-10-06 |  | 2618986 | 100%
6 | Improvement of road by BC Gordder Abu Taher Shop to Kachua Madrasha. Salvaged Cost Tk 448135.00i Earthwark Ch.600m-1600m. ii Carpeting DC Ch.600m-1600m. iii Construction of 03 Nos. 1.5mx1.5m Box Culvert at Ch.667m742m & 938m & U-Drain 0.6mx0.6m at Ch.870m973m & 1550m. under Banaripara Upazila Barishal District (Road ID: 506105098) | M/S Alif Enterprise | Memo No: 100, Date: 31/01/2019 | 8870774.58 | 19/06/19 |  |  | 0%
7 | Improvement of Read from West Chakhar Gotarer bari Bridge to Purbo Goailbari GPS road Maszidbari Lance Ghat to Modhow Sayedkati Rgd P. School. Salvaged Cost Tk 776408.00 a Earthwark Ch.00m-1000m.b Carpeting BC Ch.00m-1000m. c Construction of 01 Nos RCC Box Culvert 2.0mx2.0m at Ch.179m0 02 Nos RCC Box Culvert 1.5mx1.5m at Ch.440m & 696m. 07 Nos U-Drain 0.6mx0.6m at Ch.235m 308m 510m 612m 726m 925m & 940m. d Palsading 35m (Road ID: 506104045) | M/S Sun Bulders | Memo No: 356, Date: 12/05/2019 | 9124094.73 | 09/10/19 |  |  | 0%
7 |  |  |  | 50924884.52 |  |  | 26733762 |  |  |  | 839815.608
1 | Resectioning of Banaripara-Harta Road at Ch. 4665m-6066m (Road ID: 506102003) | Zakir Hossain LCS No: 1 | Memo No: 677, Date: 25/09/2016 | 441816.72 | 2016-10-11 | 30/03/17 | 437075 | 100%
2 | Resectioning of Banaripara-Harta Road at Ch. 6066m-7252m (Road ID: 506102003) | Kohinoor Begum LCS No: 2 | Memo No: 677, Date: 25/09/2016 | 415870.76 | 2016-10-11 | 30/03/17 | 415280 | 100%
3 | Resectioning of Banaripara-Harta Road at Ch. 7252m-7702m (Road ID: 506102003) | Baschu Forazi LCS No: 3 | Memo No: 677, Date: 25/09/2016 | 398985.83 | 2016-10-11 | 30/03/17 | 397904 | 100%
4 | Resectioning of Banaripara-Harta Road at Ch. 7702m-8152m (Road ID: 506102003) | Abdul Karim LCS No: 4 | Memo No: 677, Date: 25/09/2016 | 384544.28 | 2016-10-11 | 30/03/17 | 382564 | 100%
5 | Resectioning of Banaripara-Harta Road at Ch. 8152m-8752m (Road ID: 506102003) | Horolal Mondol LCS No: 5 | Memo No: 677, Date: 25/09/2016 | 463598.7 | 2016-10-11 | 30/03/17 | 463243 | 100%
6 | Resectioning of Banaripara-Harta Road at Ch. 8752m-9352m (Road ID: 506102003) | Mithu Howlader LCS No: 6 | Memo No: 677, Date: 25/09/2016 | 461929.48 | 2016-10-11 | 30/03/17 | 461929 | 100%
7 | Resectioning of Banaripara-Harta Road at Ch. 9352m-9760m (Road ID: 506102003) | Md. Khairul Islam LCS No: 7 | Memo No: 677, Date: 25/09/2016 | 374441.97 | 2016-10-11 | 30/03/17 | 373462 | 100%
7 |  |  |  | 2941187.74 |  |  | 2931457
14 |  |  |  | 53866072.26 |  |  | 29665219
Upazila: Babugonj
1 | Improvement of road from Babugonj Agorpur GC to Mr. Younusur Rahman (Divisional Commissioner) house via Clubgonj hat by Carpeting from Ch. 750-1400m & 0.00-1550m (Road ID: 506034025) | M/S Lutful Kobir | Memo No: 166, Date: 01/04/2014 | 10750396.05 | 17/07/14 | 07/11/15 | 10748336 | 100% | Final | 90% | -1072979.555
2 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km (Road ID: 506035070) | M/S Atique Construction | Memo No: 983, Date: 04/12/2014 | 10173103.86 | 2015-01-04 | 20/05/17 | 10173094 | 100% | Final | 60% | -4069231.684
3 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km (Road ID: 506034095) | M/S Atique Construction | Memo No: 983, Date: 04/12/2014 | 19386557.17 | 2015-01-04 | 02/06/17 | 19386554 | 100% | Final | 60% | -7754619.698
4 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km (Road ID: 506035006) | M/S Atique Construction | Memo No: 983, Date: 04/12/2014 | 10428682 | 2015-01-04 | 05/06/17 | 10422370 | 100% | Final | 60% | -4165160.8
5 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m (Road ID: 506035070) | M/S Atique Construction | Memo No: 985, Date: 04/12/2014 | 3071060.04 | 2015-01-04 | 13/06/17 | 3070368 | 100% | Final | 60% | -1227731.976
6 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m (Road ID: 506034095) | M/S Atique Construction | Memo No: 985, Date: 04/12/2014 | 4968549.43 | 2015-01-04 | 16/06/17 | 4965087 | 100% | Final | 60% | -1983957.342
7 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m (Road ID: 506035006) | M/S Atique Construction | Memo No: 985, Date: 04/12/2014 | 2095536.41 | 2015-01-04 | 01/04/16 | 1895463 | 100% | Final | 60% | -638141.154
8 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m (Road ID: 506034024} | M/S Atique Construction | Memo No: 1041, Date: 11/12/2014 | 2076355.09 | 2015-01-04 | 07/06/17 | 1875359 | 100% | Final | 60% | -629545.946
9 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m (Road ID: 506033006) | M/S Lutful Kobir | Memo No: 1010, Date: 08/12/2014 | 1029755.17 | 2015-06-05 | 23/10/15 | 986117 | 100% | Final | 60% | -368263.898
10 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m (Road ID: 506033006) | M/S Alvi Construction | Memo No: 1011, Date: 08/12/2014 | 5193526.54 | 2015-12-05 | 18/04/17 | 5143354 | 100% | Final | 60% | -2027238.076
11 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District (Road ID: 506034024) | M/S Atique Construction | Memo No: 2/2013, Date: 09/12/2014 | 14979470.55 | 2015-01-04 | 10/05/17 | 14979470 | 100% | Final | 60% | -5991787.67
12 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m (Road ID: 506033007) | M/S Hasan Construction | Memo No: 277, Date: 03/05/2016 | 11570042.22 | 29/11/16 | 13/11/17 | 11570042 | 100% | Final
13 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m (Road ID: 506033007) | M/S Saifuddin Traders | Memo No: 272, Date: 03/05/2016 | 4179759.25 | 20/11/16 | 19/09/17 | 4095279 | 100% | Final
14 | Improvement of Road from Telerchar GPS -Najamrari Bari - Jahungirnagar UP road Start ch.1700m Satter Mirar Bari -Thakur. From Ch.0.0m - 550mSalvaged Cost Tk 192766.00 (Road ID: 506035103, 506034109) | M/S Niaz Traders | Memo No: 728, Date: 18/09/2017 | 3156880.761 | 18/01/18 | 30/03/19 | 3152957 | 100% | Final
15 | Improvement of road from Jahapur Shilondia Bridge -Uttor Mujafforpur Peda Master bari under Jahangir Nagar Union a Bituminous Surfacing -wearing courseDC ch.190m -1190m b 1No. 2.0m x 2.0m & 1No.1.0m x1.0m RCC Box Culvert at Ch.273m & 615m under Babuganj Upazila Barisal District (Road ID: 506035018) | M/S Amir Engineering Corporation | Memo No: 824, Date: 16/10/2017 | 6949870.12 | 2018-04-03 | 11/01/19 | 6926903 | 100%
16 | Improvement of Road from Ramjankathi GPS to Charalgi GPS. a Earthwark from Ch. 0- 1500m.b Carpeting DC from Ch. 0- 1500m.c Construction of 2 Nos 625mmx600mm U-Drain at Ch. 736m & 1285m.d Palisading Work 150.00m. Under Babuganj District- Barishal (Road ID: 506035132) | M/S Sharif Enterprise | Memo No: 792, Date: 18/11/2018 | 10984452 | 2019-11-04 |  | 3700000 | 0%
17 | Improvement of from Khudrokathi Freedom Fighter Mogibor Rahaman Sikder House to Baige Comander Abdul Mojid Khan house. At Ch. 00m-1100m.Salvaged Cost Tk 285357.00i Earthwark Ch.0.00m-1100m.ii Carpeting DC Ch.0.00m-1100m. iii Construction of 02 Nos 0.625mx0.600m U-Drain. at Ch.110m & 400m.iv Palsading 46m.Under Babuganj Upazila Barishal District (Road ID: 506034155) | M/S Yousuf Ali Sikder | Memo No: 172, Date: 18/02/2019 | 7547988.86 | 27/06/19 |  |  | 0%
17 |  |  |  | 128541985.521 |  |  | 113090753 |  |  |  | -29928657.799
1 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m (Road ID: 506033006) | Md. Masum Hossain Gazi LCS No-1 | Memo No: 1009, Date: 08/12/2014 | 195850 | 15/05/15 | 30/09/15 | 185240 | 100% | Final
2 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km (Road ID: 506035070) | Taslima LCS No-1 | Memo No: 984, Date: 04/12/2014 | 285121 | 15/05/15 | 30/09/15 | 270738 | 100% | Final
3 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km (Road ID: 506034095) | Rajib Hossain LCS No-1 | Memo No: 984, Date: 04/12/2014 | 381065 | 15/05/15 |  | 38100 | 100%
4 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km (Road ID: 506035006) | Md. Liton Hossain LCS No-1 | Memo No: 984, Date: 04/12/2014 | 300535 | 15/05/15 |  | 279799 | 100% | Final
5 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m (Road ID: 506034024) | Md. Kabir Sikder LCS No-1 | Memo No: 984, Date: 04/12/2014 | 354810 | 15/05/15 | 30/09/15 | 203192 | 100%
6 | Resectioning of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m (Road ID: 506033007) | Md. Habibur Rohman LCS No-1 | Memo No: 276, Date: 03/05/2016 | 290672 | 20/06/16 | 20/10/16 | 290503 | 100%
6 |  |  |  | 1808053 |  |  | 1267572 |  |  |  | 0
23 |  |  |  | 130350038.521 |  |  | 114358325 |  |  |  | -29928657.799
Upazila: Muladi
1 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m (Road ID: 506692004) | M/S Misi Construction | Memo No: 187, Date: 09/04/2014 | 8772459.2 | 28/07/14 | 24/06/15 | 8713982 | 100% | Final |  | 58477.2
2 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m (Road ID: 506692004) | M/S Lutful Kobir | Memo No: 188, Date: 09/04/2014 | 20744407.41 | 20/08/14 | 18/10/16 | 20716273 | 100% | Final | 100% | 28134.41
3 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District (Road ID: 506695135) | M/S Santu Traders | Memo No: 339, Date: 08/06/2014 | 3545269 | 27/11/14 | 13/03/17 | 3539794 | 100% | Final | 100% | 5475
4 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District (Road ID: 506695127) | M/S Santu Traders | Memo No: 339, Date: 08/06/2014 | 2347546 | 27/11/14 | 26/02/17 | 2217470 | 100% | Final | 100% | 130076
5 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m (Road ID: 506694001) | M/S Lutful Kobir | Memo No: 2014, Date: 20/11/2014 | 1762404.98 | 2015-06-05 | 16/06/16 | 1761528 | 100% | Final | 100% | 876.98
6 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m (Road ID: 506694060) | M/S Lutful Kobir | Memo No: 2014, Date: 20/11/2014 | 3683201.71 | 2015-06-05 | 30/03/17 | 3680151 | 100% | Final | 60% | -1470229.974
7 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m (Road ID: 506694001) | M/S Topu Enterprise | Memo No: 912, Date: 20/11/2014 | 7104572.13 | 18/05/15 | 26/06/16 | 6981690 | 100% | Final | 80% | -1298032.296
8 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m (Road ID: 506694060) | M/S Topu Enterprise | Memo No: 912, Date: 20/11/2014 | 4824539 | 18/05/15 | 06/08/16 | 4773001 | 100% | Final | 80% | -913369.8
9 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m (Road ID: 506694063) | Md Sirazul Islam Hanif | Memo No: 667, Date: 17/09/2014 | 2947338.02 | 25/05/15 | 25/08/16 | 2910009 | 100% | Final | 100% | 37329.02
10 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m (Road ID: 506694063) | M/S Sraboni Enterprise | Memo No: 665, Date: 17/09/2014 | 368648.25 | 28/06/15 | 06/03/16 | 368633 | 100% | Final | 100% | 15.25
11 | Improvement of road from Char Kalekhan Goni Bari-Khalil Bepari Bari road by BC from Ch. 0.00m-1550m (Road ID: 56695075) | Md. Khair Hossain | Memo No: 490, Date: 31/05/2015 | 7059418.41 | 15/10/15 | 21/06/16 | 7059417 | 100% | Final | 70% | #VALUE!
12 | Construction of 1 vent 4.00m×4.00m and 1 vent 1.00m×1.00m RCC Box Culvert on Char Kalekhan Goni Bari-Khalil Bepari Bari road at Ch.182m & 330m (Road ID: 56695075) | Md. Khair Hossain | Memo No: 491, Date: 31/05/2015 | 1462533.11 | 15/10/15 | 12/04/16 | 1455972 | 100% | Final | 50% | #VALUE!
13 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal (Road ID: 506694043) | M/S Shafi Enterprise | Memo No: 713, Date: 05/10/2016 | 7727638.21 | 13/02/17 | 02/03/18 | 7624583 | 100% | Final
14 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District (Road ID: 506693005) | PTSL-MOTREE (PVT) LTD | Memo No: 210, Date: 15/03/2017 | 12881428.65 | 16/08/17 |  | 11600000 | 100%
15 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District (Road ID: 506692004) | PTSL-MOTREE (PVT) LTD | Memo No: 210, Date: 15/03/2017 | 16131650.67 | 16/08/17 |  | 15200000 | 100%
16 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District (Road ID: 506693005) | M/S Islam Brothers | Memo No: 210, Date: 15/03/2017 | 14216012.55 | 2017-07-08 | 15/06/19 | 14206186 | 100%
17 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District (Road ID: 506692002) | M/S Islam Brothers | Memo No: 210, Date: 15/03/2017 | 21991136.67 | 2017-07-08 |  | 17136746 | 85%
18 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal (Road ID: 506692004) | Orien Trading & Builders | Memo No: 252, Date: 28/03/2017 | 21153309.3 | 2017-10-08 | 10/05/19 | 21146921 | 100%
19 | Construction of 30.00m PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at Ch.7620km over Banimardhan Khal under Muladi UpazilaDistrict-Barisal (Road ID: 506692004) | M/S Amir Engineering Corporation and M.M Builders & Engineers | Memo No: 692, Date: 28/08/2017 | 18919977.37 | 2018-11-02 | 20/06/19 | 18919123 | 100%
20 | Improvement of road from Muladi-Mirdar Hat GCCR Kazi Ali Ahmed Bari Grostan Alauddin Dewan Bari under Muladi UpazilaBarisal.a Bituminus Surfacing wearing courseDC 0.0m - 375mb 1 No.1.3m x 1.3m RCC Box Culvert at ch.170m (Road ID: 506695137) | M/S Kohinoor Enterprise | Memo No: 841, Date: 22/10/2017 | 2332038.39 | 25/01/18 |  | 1450000 | 40%
21 | a Improvement of Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road from Ch.2150m - 4415m under Muladi Upazila Barisal District.b Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch.2800m.c Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch. 3900m (Road ID: 506692002) | Orien Trading & Builders | Memo No: 501, Date: 04/05/2017 | 15453053.91 | 2018-10-05 |  | 9000000 | 70%
22 | Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000m under Muladi Upazila Barisal District.Salvaged Cost Tk 591644.00Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000mID No.506694016 under Muladi Upazila Barisal District (Road ID: 506694016) | Orien Trading & Builders | Memo No: 80, Date: 21/01/2018 | 5296594.14 | 2018-10-05 |  | 2150000 | 60%
23 | Improvement of road from Batamara Paderhat Launch Ghat -Salimpur Bazar via Batamara Regd.Primary School via Aminul Haque Kabir Bari by BC at ch.200m - 1252m under Muladi Upazila Barisal. | Md. Mahafuz Khan | Memo No: 49, Date: 14/01/2018 | 5400000 | 2018-10-05 |  |  | 30%
24 | Improvement of road from Balarmpur Bazar-Dumurtala GPS-Char Dumuritala Bissas Bari Mosque UNRG by BC at Ch. 0.000km-1.000km. under muladi upazila Barisal District (Road ID: 506694094) | M/S Ferdousi Construction | Memo No: 111, Date: 30/01/18 | 5416934.16 | 2018-12-06 |  | 2500000 | 50%
25 | Improvement of road from Muladi-Bara Patarchar Ferry Ghat M by BC at Ch. 3.500km-4.065km under muladi upazila Barisal District (Road ID: 506694017) | M/S AK Buidlers | Memo No: 111, Date: 30/01/18 | 3171625.29 | 14/06/18 |  | 1500000 | 70%
26 | Improvement of road from Haraz Sikder Bari to Laxmipur Nutun hat via Rashid Dhali Bari by BC at Ch. 0.900km-2.400km under muladi upazila Barisal District.Salvaged cost Tk.888105.00 (Road ID: 506695010) | M/S R.S Construction | Memo No: 111, Date: 30/01/18 | 8689972.61 | 2018-07-06 |  |  | 25%
27 | Construction of RCC Ghat at Muladi Bandar under Muladi UpazilaBarishal District. | M/S ARB Construction | Memo No: 196, Date: 25/02/19 | 3631781.02 | 17/06/19 |  |  | 0%
28 | Construction of 23.00m RCC Girder Bridge on Madrasha Hat Start from Char kalekhan College gate to Charmalia Bepari Hat road at ch.3670m (Road ID: 506694001) | M/S. Lutful Kabir | Memo No: 326, Date: 23/04/19 | 14133678.509 |  |  | 4000000 | 0%
29 | A Improvement of Kazir Char High School to Moddho Kazirchar Dakhil Madrasah. Salvaged Cost Tk 1848817a Earthwark Ch.1000m-2000m.b Carpeting BC Ch. 1000m-2000m. c Palsading 70m.B Improvement of Road by BC from Char Comissioner Colam Khan Bari-Muladi Boarder via Sadak Khan Khal K.a Earthwark Ch.500m-1150m.b Carpeting BC Ch.500m-1150m. c Construction of 01 No 1-Vent RCC Box Culvert 4.0mx4.0m at Ch.572m. d Palsading 45m (Road ID: 506694082, 506695052) | M/S S H Enterprise | Memo No: 323, Date: 23/04/19 | 13710063 | 01/10/19 |  |  | 5%
30 | A Improvement of Road by BC from Talukder Hat Khajurala to Safipur UP via Charkaiakhan UP-Beparirhat. Salvaged cost Tk 3421194.00a Earthwark Ch.11750m-13250m.b Carpeting BC Ch.11750m-13250m.B Improvement of Road by BC from Kazir Char UP to Ekaterhat UP to Muladi Border. Salvaged cost Tk 2190786.00a Earthwark Ch.00m-1000m.b Carpeting BC Ch.00m-1000m. c Palsading 70m (Road ID: 506693001, 506693004) | M/S S H Enterprise | Memo No: 324, Date: 23/04/19 | 16991019.04 | 01/10/19 |  |  | 0%
31 | A Improvement of Road from Shah alam Sarif Bari- Jabbar Sikder Bari via Bhahadurpur H/S. K.a Earthwark Ch.00m-550m.b Carpeting BC Ch. 00m-550m. B Improvement of road from Padarhat to Delower Howlader Bari via Harun Dr. BariK.a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of 02 Nos Single-Vent 3.00mx3.00m RCC Box Culvert At Ch. 625m & 976m (Road ID: 506695059, 506695102) |  | Memo No: 578, Date: 19/06/19 | 13519203.34 |  |  |  |  | E-Tender Under Process.
32 | A Improvement of Road from Padar Hat Esahak Howladers Bari.a Earthwark Ch. 500m-1500m.b Carpeting BC Ch. 500m-1500m.c Palsading 55m.B Improvement of Road from Char Comissioner R&H-Dholu Sikder Bari K a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Palsading 100m (Road ID: 506694092, 506695053) |  | Memo No: 579, Date: 19/06/19 | 15288444.02 |  |  |  |  | E-Tender Under Process.
33 | Improvement of road from Jamaddar Bari to Akoter Hat via Bahadurpur H/S at Ch. 4488m - 5300m. Under Muladi Upazila Barishal District. |  |  | 6568814.38 |  |  |  |  | E-Tender Under Process.
34 | Construction of 20m long RCC Girder Bridge on Mirda hat GC - Nazirpur GC via Madrashar hat Bangla Bazar road over Banimardhan Khal at Ch 10560m Under Muladi Upazila Barishal District |  |  | 22750000 |  |  |  |  | E-Tender Under Process.
34 | Sub Total: |  |  | 329996712.449 |  |  | 190611479 |  |  |  | -3421248.21
1 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m (Road ID: 506692004) | Khorshed Khan LCS No-1 | Memo No: 186, Date: 09/04/14 | 334778 | 22/05/14 | 21/10/14 | 327963 | 100% | Final
2 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m (Road ID: 506692004) | Md. Alamgir Hossain LCS No-2 | Memo No: 186, Date: 09/04/14 | 403489 | 22/05/14 | 22/10/14 | 396479 | 100% | Final
3 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m (Road ID: 506692004) | Md. Baschu Sharder LCS No-3 | Memo No: 186, Date: 09/04/14 | 386512 | 22/05/14 | 22/10/14 | 384690 | 100% | Final
4 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m (Road ID: 506692004) | Abdus Salam Sharder LCS No-4 | Memo No: 186, Date: 09/04/14 | 371303 | 22/05/14 | 22/10/14 | 364872 | 100% | Final
5 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m (Road ID: 506692004) | Md. Bakiullah Sharder LCS No-5 | Memo No: 186, Date: 09/04/14 | 372013 | 22/05/14 | 22/10/14 | 367905 | 100% | Final
6 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m (Road ID: 506692004) | Md. Shalim LCS No-6 | Memo No: 186, Date: 09/04/14 | 374943 | 22/05/14 | 22/10/14 | 373728 | 100% | Final
7 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m (Road ID: 506692004) | Sukkur Ahmed Khan LCS No-7 | Memo No: 186, Date: 09/04/14 | 374353 | 22/05/14 | 22/10/14 | 370690 | 100%
8 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m (Road ID: 506692004) | Nazma LCS No-8 | Memo No: 186, Date: 09/04/14 | 396858 | 22/05/14 | 22/10/14 | 387880 | 100%
9 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m (Road ID: 506692004) | Most. Jasmin Akter LCS No-9 | Memo No: 186, Date: 09/04/14 | 397315 | 22/05/14 | 22/10/14 | 390259 | 100%
10 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m (Road ID: 506692004) | Rashida LCS No-10 | Memo No: 186, Date: 09/04/14 | 428100 | 22/05/14 | 22/10/14 | 417470 | 100%
11 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District (Road ID: 506695135) | Md Fazlu Tafader LCS No-1 |  | 221909 | 18/11/14 | 22/10/14 | 221206 | 100% | Final
12 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District (Road ID: 506695127) | Md Kabir Hossain LCS No-1 |  | 239879 | 18/11/14 | 22/10/14 | 239119 | 100% | Final
13 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District (Road ID: 506694063) | Fokrul Ahosan LCS No-1 | Memo No: 666, Date: 17/09/14 | 323312 | 31/05/15 | 30/09/15 | 32000 | 100%
14 | Resectioning of road from Char Kalekhan Goni Bari-khalil Bepari bari road by Earth work from Ch. 0.00m-1550m (Road ID: 56695075) | Md. Mojibor Rohman LCS No-1 |  | 101268 | 30/08/15 |  | 97476 | 100% | Final
15 | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 2150m-2750m (Road ID: 506692002) | LCS No-1 | Memo No: 500, Date: 05/06/17 | 249672 |  | 30/03/18 | 242558 | 100% | Final
16 | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 2750m-3350m (Road ID: 506692002) | LCS No-2 | Memo No: 500, Date: 05/06/17 | 284170 |  | 30/03/18 | 284170 | 100% | Final
17 | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 3350m-3950m (Road ID: 506692002) | LCS No-3 | Memo No: 500, Date: 05/06/17 | 319301 |  | 30/03/18 | 269469 | 100%
18 | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 3950m-4412m (Road ID: 506692002) | LCS No-4 | Memo No: 500, Date: 05/06/17 | 163854 |  | 30/03/18 | 160742 | 100% | Final
18 | Sub Total: |  |  | 5743029 |  |  | 5328676 |  |  |  | 0
52 | Grand Total: |  |  | 335739741.449 |  |  | 195940155 |  |  |  | -3421248.21
Upazila: Hizla
1 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m (Road ID: 506362009) | M/S Oshin Enterprise | Memo No: 980, Date: 18/11/14 | 5645230.7 | 28/05/15 | 25/06/16 | 5645230 | 100% | Final | 40% | -3387137.72
2 | Improvement of Kowria- Moulavirhat UZR Poschim koralia road under Hizla Upazila District Barisal aEarth work from Ch.0.0 -900m b Dense Carpeting Ch.0.0 -900m c Two vent 4m x 4m RCC Box Culvert at Ch.252m (Road ID: 506364033) | Md. Mahafuz Khan | Memo No: 968, Date: 18/11/17 | 7950598.407 | 2018-11-04 |  |  | 35%
3 | Improvement of Hizla Muladi road to Motiar Dewan Bari via Sergent Dula Bari roadRHD via Surgeant Dulal- Kathal BeganUZR under Hizla Upazila Barisal District. Salvaged Cost Tk.2186650.00a Earth work Ch.0.0 - 1500mb Carpetting Ch. 0.0 - 1500mc Construction of 2 nos U-Drain on the same road at Ch.777m & 1275m (Road ID: 506364003) | M/S R S Construction | Memo No: 308, Date: 03/04/18 | 9550790.96 | 28/06/18 |  |  | 40%
4 | Construction of RCC Boat land Station at Abupur Ghat under Hizla Upazila Barisal | M/S S H Enterprise | Memo No: 797, Date: 10/12/17 | 3146706.64 | 2018-12-05 | 24/01/19 | 3119743 | 100%
5 | Improvement of Khunna Hospital RHD via Kawmi Madrasha - Baherchar UZR Barajalia Board GPS CS Connecting road a Earthwork from Ch.850 -1820m b Carpetting BC from Ch.850 -1820m under Hizla Upazila District Barishal Salvaged Cost TK 2343371.00 (Road ID: 506365049) | M/S Munny Enterprise | Memo No: 752, Date: 30/10/18 | 6457779.64 | 24/02/19 |  | 1000000 | 55%
6 | Improvement of road from Horinathpur Koshaipotti UZR - Zetighat GPS UZR ID No. a Earthwork from Ch.0.0 -1500m b Carpetting BC from Ch.0.0 -1500m under Hizla Upazila District Barishal Salvaged Cost TK 112128.00 (Road ID: 506365056) | M/S Esad & Emad Enterprise | Memo No: 752, Date: 30/10/18 | 9439921.79 | 2019-06-02 |  | 5700000 | 70%
7 | Improvement of road from UZR -6 Mohishkhola Madrasha to VRA-15 Uttor Guabaria GPS via house of Abdul Gafur Sarder road by BC From Ch. 00m-1760.00m. Salvage Amount TK 296023.00 Under Hizla Upazila District- Barishal (Road ID: 506364034) | M/S. Nazrul Enterprise | Memo No: 783, Date: 06/11/18 | 12101581.992 | 2019-11-04 |  |  | 30%
8 | Improvement of Kawria Bazar Danushikder hat road - Noroshingpur road Start Mollah Bari Shop Salvaged Cost Tk.309333.54 i Earth work Ch.0.0 - 760miiCarpeting DC Ch.0.0 - 760m under Hizla Upazila District Barishal (Road ID: 506365051) | M/S Jeon Trading & C0 | Memo No: 37, Date: 08/01/19 | 4993137.642 | 2019-09-05
9 | Dhunusikder Hat to Memania Taker Hat road via Abupur Kheyaghat i Construction of Diuble vent 2 x 4.50 x 6.50m RCC Box Culvert at Ch.2600mii Construction of Diuble vent 2 x 4.00 x 5.00m RCC Box Culvert at Ch.3380mUnder Hizla Upazila Barishal District (Road ID: 506362005) | M/S Ladis Corner | Memo No: 36, Date: 08/01/19 | 5408798.4 | 2019-02-05 |  | 1800000 | 60%
10 | Improvement of Purbo Kandi WDB Embt. Salvaged Cost Tk 257546.00i Earthwark Ch.0.00m-900m. ii Carpeting DC Ch.0.00m-900m. iii Palsading 95m.Under Hizla Upazila Barishal District (Road ID: 506365003) | M/S Yousuf Ali Sikder | Memo No: 173, Date: 18/02/19 | 6417561.33 | 27/06/19 |  |  | 51%
11 | Improvement of Dhanushikder hat-Muladi Upazila road. Salvaged Cost TK 1488901.00 a Earthwark Ch.1000m-2000m. b Carpeting BC Ch.1000m-2000m. c Palsading 97m (Road ID: 506362009) | M/S Kazi Popy Enterprise | Memo No: 322, Date: 23/04/19 | 9439521.98 | 09/09/19 |  | 2500000 | 35%
12 | Improvement of Guabaria UP Office-Bhanderhat road Old Zila Parished road to Guabaria UP Office via Mofiz Uddin road at Ch. 1650m-2480m. Under Hizla Upazila Barishal District. Salvaged Cost TK 657763.00 |  |  | 7002119.66 |  |  |  |  | E-Tender Under Process.
12 |  |  |  | 87553749.141 |  |  | 19764973 |  |  |  | -3387137.72
1 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 0.00m-325m (Road ID: 506362009) | Md. Humaun Kabir LCS No-1 |  | 226562 | 15/11/15 |  | 225780 | 100%
2 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 325m-650m (Road ID: 506362009) | Md. Monju Noli LCS No-2 |  | 220227 | 15/11/15 |  | 218498 | 100%
3 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 650m-1000m (Road ID: 506362009) | Md. Parvaz LCS No-3 |  | 217087 | 15/11/15 |  | 214482 | 100%
3 |  |  |  | 663876 |  |  | 658760
15 |  |  |  | 88217625.141 |  |  | 20423733
Upazila: Mehendigonj
1 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal (Road ID: 506622005) | M/S Santu Traders |  | 4973018 | 27/11/14 | 13/04/17 | 4973018 | 100% | Final | 60% | -1989207.2
2 | Improvement of Mothertoli Bazar - Uttarchar road via Charekkaria road by BC (Ch.2170-3220m, Road Under Mehendigonj Upazila, District-Barisal (Road ID: 506625079) | M/S Nahid Enterprise | Memo No: 356, Date: 12/06/14 | 4515030 | 23/11/14 | 30/04/16 | 4514924 | 100% | Final | 60% | -1805906
3 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal (Road ID: 506625079) | M/S Hasib Enterprise | Memo No: 357, Date: 12/06/14 | 184788 | 16/11/14 | 04/01/15 | 167876 | 100% | Final
4 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m (Road ID: 506624016) | M/S Hasan Construction | Memo No: 710, Date: 05/10/16 | 6860287.95 | 19/01/17 |  | 3325000 | 70%
5 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila,Barisal (Road ID: 506622007) | M/S Lutful Kabir | Memo No: 65, Date: 24/01/17 | 10492643.13 | 14/05/17 |  | 8700000 | 100%
6 | Improvement of Road from Posshim Yearbeg Dadpur GPS under Mehendiganj Upazila District Barisal aEarthwork Ch.1000 2760m b HBB Ch.1000 -2760m (Road ID: 506625062) | M/S Amir Engineering Corporation | Memo No: 953, Date: 29/11/17 | 5661508 | 2018-05-04 | 04/01/19 | 5566643 | 100%
7 | Constructionof Langutia G C (i) Fish Shed (Size : 12m x 6m) (ii) 2 Nos Waste collection Pit (Dustbin) (Size : 1.4m x 1.4m) (iii) Multipurpose Shed (Size : 12m x 6m) (iv) Logistic Support for Langutia Bazar (v) Toilet Block (Size : 5.75m x 3.07m) (vi) 2 Nos Deep Hand Tube well (vii) CC road without side drain : 100m (viii) RCC Ghat at Langutia Bazar Under Mehendigonj, Barishal District | M/S Oshin Enterprise | Memo No: 656, Date: 24/09/18 | 4740301.45 | 2019-11-01 |  |  | 0%
8 | Improvement of road from Chanpur UP Saduaghata - Kazir Hat Bazar via Muktijodda H/S Salvage Amount Tk. 1000267.00 Road i Earth Work Ch. 00m-1300m ii Carpeting BC Ch. 00m-1300m iii Construction of 01 No 0.625mx0.600m U-Drain at Ch.1234m iv Palisading 27m. Under Mehendiganj Upazila District- Barishal (Road ID: 506623016) | M/S Refat Enterprise | Memo No: 219, Date: 05/03/19 | 9103224.68 | 28/07/19 |  |  | 0%
9 | Part - A Improvement of road by BC from Paterhat RC College - Charerhat Via Sadekpur Madrasha at Ch. 700m-1700m. Salvage Amount Tk. 1248231.00 i Earth Work Ch. 700m-1700m. ii Carpeting BC Ch.700m-1700m. iii Construction of 01 No 0.625mx0.600m U-Drain at Ch.1686m Under Mehendiganj Upazila District- Barishal. Part- B Improvement of road from Nasirkha Khayaghat - Hashamuddi Bazar i Earth Work Ch. 00m-1000m. ii Carpeting BC Ch. 00m-1000m Under Mehendiganj Upazila District- Barishal. Part - C Improvement of road from Rowshanara Dhakil Madrasha H/O Hasem Molla Via H/O Dolil Uddin Bepari. Salvage Amount Tk. 199562.00 i Earth Work Ch. 00m-900m. ii Carpeting DC Ch. 00m-900m (Road ID: 506625130, 506625140, 506625236) | M/S Amir Engineering Corporation | Memo No: 220, Date: 05/03/19 | 20716818.21 | 24/09/19 |  | 2000000 | 0%
10 | Improvement of road by BC on Chargopalpur UP-Jalirchar Bazar Maskata River. Under Mehendigonj Upazila Barishal District. Salvaged Cost Tk.1116804.00 a Earthwark Ch. 3300m-4600m.b Carpeting BC Ch. 3300m-4600m. |  |  | 9188736.41 |  |  |  |  | E-Tender Under Process.
11 | Improvement of road by BC from H/O. Malek Mia Durgapur S/O. Azom Mia GCCR road via Varanirpul to Ramizuddin High School. Under Mehendigonj Upazila Barishal District. a Earthwark Ch. 00m-1050m.b Carpeting BC Ch. 00m-1050m. c 2Nos U-Drain 0.625m x 0.600m at Ch.172m 750m |  |  | 7922183.69 |  |  |  |  | E-Tender Under Process.
12 | Construction of 20m RCC Bridge on Patherhat GC Road Khejor Toli Bridge at Ch.1961m under Mehendigonj Upazila Barishal District. |  |  | 15380000 |  |  |  |  | E-Tender Under Process.
12 |  |  |  | 67247619.42 |  |  | 29247461 |  |  |  | -3795113.2
1 | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 0.00m-600m by Earth (Road ID: 506624016) | Nizam Uddin Talukder LCS No-1 | Memo No: 711, Date: 05/11/16 | 346489 | 18/12/16 | 18/03/17 | 345129 | 100%
2 | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 600m-1200m by Earth (Road ID: 506624016) | Md. Sadak LCS No-2 | Memo No: 711, Date: 05/11/16 | 421652 | 18/12/16 | 18/03/17 | 419139 | 100%
3 | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 1200m-1610m by Earth (Road ID: 506624016) | Md. Faruk Buiya LCS No-3 | Memo No: 711, Date: 05/11/16 | 258058 | 18/12/16 | 18/03/17 | 256220 | 100%
4 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1000m-1600m (Road ID: 506622007) | LCS No-1 | Memo No: 65, Date: 24/10/17 | 164958 |  | 30/04/17 | 159113 | 100%
5 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1600m-2350m (Road ID: 506622007) | LCS No-2 | Memo No: 65, Date: 24/10/17 | 379812 |  | 30/04/17 | 373997 | 100%
6 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 2350m-3250m (Road ID: 506622007) | LCS No-3 | Memo No: 65, Date: 24/10/17 | 297385 |  | 30/04/17 | 290652 | 100%
7 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 3250m-4000m (Road ID: 506622007) | LCS No-4 | Memo No: 65, Date: 24/10/17 | 254707 |  | 30/04/17 | 249233 | 100%
7 |  |  |  | 2123061 |  |  | 2093483
19 |  |  |  | 69370680.42 |  |  | 31340944
Upazila: Barisal Sadar
1 | Improvement of Bukhainagar Bridge to Abdul Aziz Khan's House via Shaluka GPS Road (Ch. 00-500m) (Road ID: 506514170) | M/S Talukder Enterprise | Memo No: 43, Date: 30/01/14 | 1613223.41 | 16/06/14 | 09/06/15 | 1607918 | 100% | Final
2 | Improvement of Chandpura Mojidderhat-Saheberhat via Khontakhali School road from Ch. 1635-3192m (Road ID: 506514154) | M/S G M Construction | Memo No: 165, Date: 01/04/14 | 6279530.87 | 17/08/14 | 10/06/15 | 6266613 | 100% | Final
3 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m (Road ID: 506514148) | M/S Serajul Islam Hanif | Memo No: 221, Date: 20/04/14 | 2294335.91 | 2014-01-08 | 31/07/17 | 1954150 | 100% | Final | 100% | 340185.91
4 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m (Road ID: 506514059) | M/S Khondokar Borthers | Memo No: 676, Date: 22/09/14 | 2238782.5 | 28/07/15 | 13/01/17 | 2179525 | 100% | Final
5 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m (Road ID: 506513002) | M/S Rupali Construction | Memo No: 677, Date: 22/09/14 | 10088368.67 | 17/03/15 |  | 8800000 | 100% |  |  | 10088368.67
6 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366m (Road ID: 506515102) | M/S Lutful Kabir | Memo No: 777, Date: 26/10/14 | 4037481 | 2015-12-04 | 25/02/17 | 3913837 | 100% | Final | 50% | -1895096.5
7 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m (Road ID: 506514048) | M/S Khondokar Borthers | Memo No: 966, Date: 02/12/14 | 1027297.63 | 28/07/15 | 20/12/15 | 1027297 | 100% | Final
8 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m (Road ID: 506514048) | M/S Hasan Construction | Memo No: 967, Date: 02/12/14 | 8773072.65 | 17/05/15 |  | 5512074 | 100% | Cancelled | 70% | 629076.855
9 | Construction of 1.0 x 1.0m and 1.6 x1.6m RCC Box culvert on Kasem Defader Bari - Karnokati High School & College road at ch.773m & 526m e-ID: 17457 (Road ID: 506514176) | M/S Khondokar Borthers | Memo No: 1061, Date: 11/12/14 | 428108.82 | 23/06/15 | 20/03/16 | 425862 | 100% | Final
10 | Rehabilitation of road from Kasem Defader Bari - Karnokati High School & College road By BC from ch.310 - 1125m under Sadar upazila ,Barisal District [Salvaged Cost-Tk 4,97,038.00] (Road ID: 506514176) | M/S Oshin Enterprise | Memo No: 1060, Date: 11/12/14 | 3216111 | 18/05/15 | 25/02/16 | 3216111 | 100% | Final
11 | Improvement of road from Charkawa Nayani - Shaberhat via Durgapur hat (Barisal Sadar Upazila 7no. Charkawa union 1no.word nurul islam to Bank Jalal Bari Pull) road By HBB from Ch.0.0 - 1000m under Barisal-S Upazila,Barisal District. e-ID : 29367 (Road ID: 506514136) | M/S Apu Enterprise | Memo No: 288, Date: 09/04/15 | 2063060.77 | 2015-10-11 | 24/06/16 | 2063045 | 100% | Final
12 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari (Road ID: 506515006) | M/S Khondokear Enterprise | Memo No: 69A, Date: 07/02/15 | 10801668.14 | 30/06/16 | 28/12/17 | 9822562 | 100% |  | 285845
13 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila,Barisal (Road ID: 506514137) | M/S Sirajul Alam Sikder | Memo No: 31, Date: 09/01/17 | 8550422.1 | 29/05/17 | 30/05/19 | 8530424 | 100%
14 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road (Road ID: 506513003) | Md Mafuz Khan | Memo No: 573, Date: 19/06/17 | 16884454 |  |  |  | 20%
15 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal (Road ID: 506512003) | M/S Niaz Traders | Memo No: 571, Date: 19/06/17 | 3788612.34 | 2018-09-02 |  | 1700000 | 70%
16 | Improvement of Charkawa Kheyaghat - Durgapur hat road from Ch. 3000m - 3600m.under Sadar Upazila Barisal District (Road ID: 506513004) | M/S Niaz Traders | Memo No: 574, Date: 19/06/17 | 3118182.38 | 2018-09-02 | 03/06/19 | 3117413 | 100%
17 | Improvement of road from Charmonai Talukder Bari-West Razarchar Club by BC. at Ch. 0.00m-1203.00m under Charmonai Union, Upazila : Sadar, Dist-Barisal [Salvaged cost- Tk 231155.00] (Road ID: 506515109) | M/S Kohinoor Enterprise | Memo No: 771, Date: 02/10/17 | 7892249.94 | 25/01/18 |  | 1200000 | 40%
18 | Improvement of road Shibpasha - Sholna Talukder bari via H/O Malek Police at ch.1600km - 2020km under Sadar Upazila Barisal (Road ID: 506515006) | M/S Kohinoor Enterprise | Memo No: 872, Date: 02/10/17 | 2448014.04 | 2018-11-02 | 23/10/18 | 1538816 | 100% | Final
19 | Construction of Ghat & CC Road at Shaheber Bazar under Sadar Upazila Barisal . | M/S S H Enterprise | Memo No: 979, Date: 10/12/17 | 3102813.825 | 2018-12-05 |  | 2488686 | 100%
20 | Improvement of Shibpasha Sarder bari Sholna Tarunclub Road Road Part-A Earth work at Ch. 0.00 -1505.00m Part-B Carpeting BC work at Ch. 0.00-1505.00m Salvage Amount Tk. 2626839.00 Part-C Construction of 2Nos U-Drain 1.00mx1.00m at Ch. 140m & 380m Under Barisal Sadar Upazila District - Barisal (Road ID: 506514007) | M/S Noor & Sons | Memo No: 332, Date: 08/04/18 | 10073944.25 | 18/06/18 | 06/12/19 | 6500000 | 65%
21 | Improvement of Shibpasha Sarder bari-Sholna Tarunclub road a Earth work at Ch.1505-2392m b Carpetting BC Ch.1505 -2392m c Construction of 1 No Double vent Box culvert 4.0m x 4.0m at ch.1901m d Protective worksPalisading 134m e Link Road Baitul Mamur Jame Mosque 167.00m under Bakergonj Upazila Barishal District.Salvaged Cost TK 1935498.00 (Road ID: 506514007) | M/S H R Enterprise | Memo No: 651, Date: 20/09/18 | 9606318.31 | 27/02/19 |  | 2100000 | 30%
22 | Remaining work for rehabilitation of road from Patang- Jaliabari Pool via Mujaffar Hazi Bari road.From Ch.0.0m -2782m (Road ID: 506514048) | M/S Md Yousuf Ali Sikder | Memo No: 250, Date: 25/03/19 | 4649456.351 |  | 21/11/19 | 4642776 | 45%
23 | Improvement of Read from Borthan Khan Bari-Dr. Omar bari-Gogan Ali Howladar Bari to Godanga Chandpura UP Hijaltala Baran Khan Bari-Sanjib Daser Bari-Eunus Munshi Bari. a Earthwark Ch.00m-1060m.b Carpeting DC Ch.00m-1060m. c Construction of 02 Nos U-Drain 1.0mx1.0m at Ch.107.00m & 180.00m. d Palsading 350m (Road ID: 506515174) | M/S Alif Enterprise | Memo No: 307, Date: 15/04/19 | 8173473.08 |  |  | 800000 | 15%
24 | Improvement of Road from Char Aicha Mollar Hat Kheya Ghat to Board School via Jokkhali. a Earthwark Ch.00m-530m.b Carpeting BC Ch. 00m-530m. c Palsading 93m (Road ID: 506514145) |  | Memo No: 576, Date: 19/06/19 | 4245799.81 |  |  |  |  | E-Tender Under Process.
25 | Improvement of Jagua Union Parishad-Karapur Steel Bridge-Bousherhat GC.a Earthwark Ch. 4905m-6765m.b Carpeting BC Ch. 4905m-6765m.. c Construction of U-Drain 1.00mx1.00m At Ch. 5645m & 1.60x1.60m RCC Box Culvert at Ch.6583md Palsading 42m. (Road ID: 506513012) |  | Memo No: 627, Date: 02/07/19 | 13430037.3 |  |  |  |  | E-Tender Under Process.
26 | A Improvement of Patang-Shaheber Hat road. Under Sadar Upazila Barishal District. Salvaged Cost. Tk 1937174.00a Earthwark Ch. 00m-1200m.b Carpeting BC Ch. 00m-1200m.B Rehabilitaton work of Patang-Nehalgonj Under Sadar Upazila Barishal District.a Earthwark Ch. 00m-1816m.b Carpeting BC Ch. 00m-1816m.c Palsading 12m. C Jagua Sher-E Bangla Hat-Jashim Uddin Talukder House Under Sadar Upazila Barishal District. a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m. |  |  | 23791100 |  |  |  |  | E-Tender Under Process.
26 | Sub-Total: |  |  | 172615919.096 |  |  | 79407109 |  |  |  | 9162534.935
1 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m (Road ID: 506514059) | Md. Giush Uddin LCS No-1 |  | 238242 | 15/02/15 |  | 190934 | 100% | Final
2 | Resectioning of road from Charkawa Nayami-Shaheber hat via Durgapur hat (Barisal Sadar Upzila 7no. Charkawa union 1no word nurul islam to Bank Jalal Bari Pull) road from Ch. 0.00m-1000m (Road ID: 506514136) | Md. Anowar Hossain Mridha LCS No-1 | Memo No: 289, Date: 09/04/15 | 155407 | 16/04/15 |  | 100881 | 100%
3 |  | Md. Jasim Uddin Milon LCS No-2 | Memo No: 289, Date: 09/04/15 | 228280 | 16/04/15 |  | 132596 | 100%
4 | Resectioning of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (Road ID: 506515006) | Fatema Begum LCS No-1 | Memo No: 289, Date: 09/04/15 | 400044 | 29/02/16 |  | 362610 | 100%
5 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 2557m-3280m. | Md. Hemayet Howlader LCS No-1 | Memo No: 32, Date: 08/11/16 | 305905 | 28/03/17 |  | 30000 | 100%
6 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 3280m-4580m | Md. Mojibor Rohman Sikder LCS No-2 | Memo No: 32, Date: 08/11/16 | 256209 | 28/03/17 | 30/04/17 | 117852 | 100%
7 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 4580m-6647m | Mosharof Hossain Shikder LCS No-3 | Memo No: 32, Date: 08/11/16 | 189642 | 28/03/17 | 30/04/17 | 172057 | 100%
8 | Resectioning of Road from Gilatali Kheyaghat-Biswasherhat via Model Madrasha at Ch. 1500m-2700m | LCS No-1 | Memo No: 572, Date: 19/06/17 | 438144 | 30/10/17 | 30/03/18 | 410512 | 100% | Final
9 | Resectioning of Road from Gilatali Kheyaghat-Biswasherhat via Model Madrasha at Ch. 2700m-4260m | LCS No-2 | Memo No: 572, Date: 19/06/17 | 426063 | 30/10/17 | 30/03/18 | 325495 | 100% | Final
10 | Resectioning of Shehaber Hat-Singherkati Chandramohon Road at Ch. 729m-1009m (Road ID: 506512003) | LCS No-1 | Memo No: 570, Date: 19/06/17 | 255149 | 23/11/17 | 30/03/18 | 250500 | 100% | Final
11 | Resectioning of Shehaber Hat-Singherkati Chandramohon Road at Ch. 1009m-1309m (Road ID: 506512003) | LCS No-2 | Memo No: 570, Date: 19/06/17 | 355749 | 23/11/17 | 30/03/18 | 350500 | 100% | Final
11 | Sub-Total: |  |  | 3248834 |  |  | 2443937 |  |  |  | 0
37 | Grand Total: |  |  | 175864753.096 |  |  | 81851046 |  |  |  | 9162534.935
Upazila: Bakergonj
1 | Improvement of road from South side Dhola Sluice Gate to Alim Meridha Bari (Vary) via Sikder Bari, Manik Member Bari, Shatghor & Mannan Princhpal Bari (East side of Hanua Bridge to Shatghor via Shikder Bari) By HBB from Ch. 0.00-1013m (Road ID: 506075221) | M/S Nahid Enterprise | Memo No: 176, Date: 06/04/14 | 3985608.82 | 24/07/14 | 23/06/15 | 3976779 | 100% | Final | 100% | 8829.82
2 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 (Road ID: 506073023) | M/S Khondokear Brothers | Memo No: 117, Date: 11/02/15 | 5345279.54 | 21/06/15 | 26/06/16 | 5098903 | 100% | Final
3 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 (Road ID: 506073023) | M/S Khondokear Brothers | Memo No: 118, Date: 11/02/15 | 3523866.83 | 28/07/15 |  | 1150000 | 75% | Prepared for Cancelled
4 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 1000m-4870m. e-ID : 22667 (Road ID: 506073023) | M/S Khondokear Brothers | Memo No: 118, Date: 11/02/15 | 14682769.7 | 2015-06-08 | 03/05/17 | 14478871 | 100% | Final
5 | Rehabilitation of road from Gavikola Mannan Sikder Bari Foot Bridge to West side of Nilganj Foot Bridge via Moksad Khan,Kumarghudi & Kaptain Saye Bari by BC from Ch.00-810m [Salvaged Value Tk.10,53,654.00] e-ID : 29366 (Road ID: 506075079) | Md. Nasir Uddin | Memo No: 492, Date: 30/05/15 | 2619513.44 | 2015-12-11 | 17/07/16 | 2549020 | 100% | Final
6 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal (Road ID: 506074120) | Md. Sumsudhoa Mollick | Memo No: 747, Date: 19/10/16 | 1391779.83 | 28/12/16 | 30/03/18 | 13912533 | 100% | Final
7 | Improvement of road from Faridpur Hat Kheya Ghat Durgapasa UP office Gobindapur Bothtala via Kakordha Bazar Road, a Earth Work from Ch. 4860m 7320m.b Bituminus Carpeting from Ch. 4860m 7470m.c Construction of 1 No. 1.60mx1.60m RCC Box Culvert at Ch. 7435m. under Bakergonj upazila Barisal District. Salvage Cost Tk. 3733841.00 (Road ID: 506073020) | Md Mafuz Khan | Memo No: 517, Date: 08/06/17 | 14813801.84 | 2018-04-01 | 18/11/18 | 14808294 | 100% | Final
8 | Improvement of road from west Faridpur Ajgor Sikder Bari to DC road Ferry-ghat via H/O Rahim Mrida Road, a Earth Work from Ch. 0.0 - 1300.00m. b Bituminus Carpeting from Ch. 0.0 - 1300m c Construction of 1 No. 4.0m x 4.0m RCC Box Culvert at Ch. 425m. under Bakergonj upazila Barisal District (Road ID: 506074151) | M/S Islam Brothers | Memo No: 517, Date: 08/06/17 | 8994687.7 | 2018-09-01 | 02/12/18 | 8941520 | 100%
9 | Improvement of road from Shashi Bazar Bridge-Telani Lunch Ghat Najrul Talukder Bari. under Bakergonj Upazila Dist:Barisal. a) HBB from Ch. 00m-1000m b) Protection Work 108m c) Earth work from Ch. 00m-1000m (Road ID: 506074100) | Md. Zakir Hossain Mia | Memo No: 804, Date: 11/10/17 | 4563267.91 | 24/01/18 | 05/08/18 | 4548499 | 100%
10 | Improvement of road from ATIMKHANA to Bothra Road via Mr. Matiur Rahman (ASP) at Ch. 0.00m-500.00m (Efective Length= 475.00m) (ID No.506074225) under Bakergonj Upazila, Dist : Barisal [Salvaged cost : Tk1049647.00] (Road ID: 506074100) | M/S Osin Enterprise | Memo No: 771, Date: 02/10/17 | 2974381.2 | 24/01/18 | 02/11/18 | 2967278 | 100%
11 | Improvement of road from Sampur Ray Barir Culvert to Birangal Digirpar Kader Hohlade Bari via Karim Gaji Bari a Earth work 0.0 - 1500m b Bituminous Surfacing - wearing course DC 0.0m - 1500m c 1.5 m x 1.5m RCC Box Culvert at Ch.900m (Road ID: 506075125) | M/S Abul Kalam Azad | Memo No: 825, Date: 16/10/17 | 8213317.7 | 29/01/18 |  | 5500000 | 70%
12 | Improvement of Extended Portion of Dudhalmou Ferryghat (RHD) to Kanki Govt. Pry. School Road (Connecting Road Sheikh Hasina Cantonment) (Road ID: 506074120) | M/S Amir Engineering Corporation | Memo No: 318, Date: 03/04/18 | 2878392 | 20/01/18 | 06/02/18 | 2878392 | 100% | Final
13 | Improvement of Aulia DargabariRHD to Shyampur Hat via Dhokati Madrasha & Dhokati Govt.Pry.school Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini to Syampur Hat via Ali Khan Bari a Earth work at Ch.4500-6000m b Carpeting BC at Ch.4500 - 6000m c Construction of 1No. Box culvert1.06m x 1.06m at Ch.85m & 3 nos U-Drain 900mm x 900mm at Ch.4620m4800m & 5135m on the same road d Protective worksSite Facilities& Road Safety works under Bakergonj Upazila Barishal District. Salvaged cost Tk 854269.00 (Road ID: 506074119) | Md. Nasir Uddin | Memo No: 445, Date: 29/05/18 | 13742664.31 | 2018-02-09 | 16/06/19 | 13739681 | 100%
14 | Improvement of Rahamgonj RHD via Dhokati GPS & Bakergonj-Sampur Road to BoaliaGC Bakergonj-Sampur Road Mill Ghar to Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini a Earth work at Ch.1913-2775mb CarpetingBC at Ch.1913-2775mc Construction of 1No. Box culvert1.06m x 1.06m at Ch.2549m on the same roadd Protective worksSite Facilities& Road Safety works under Bakergonj UpazilaBarishal District.Salvaged cost Tk 921239.00 (Road ID: 506072014) | M/s Kazi Holdings | Memo No: 445, Date: 29/05/18 | 7995234.286 | 2018-04-09 |  | 4325000 | 95%
15 | Construction of Ghatla at Kaligonj Bazar Khal under Bakergonj Upazila Barisal . | M/S S H Enterprise | Memo No: 979, Date: 10/12/17 | 1885106.37 | 2018-12-05 | 28/02/19 | 1884421 | 100%
16 | Construction of 23.00m Long RCC Girder Bridge over road from Kamarkali GC to Baharchar GC via Sarsi Pollice Farry Patkati L/G Faridpur UP Office & Janota Bajarat at Ch. 5847m Under Bakerganj Upazila District Barisal Road ID 506072012 | M/S SUN TRADERS | Memo No: 384, Date: 25/04/18 | 12395986.384 | 30/08/18 |  | 11150000 | 92%
17 | Improvement of Road from Hanua UP Office Bridge to Sarder Bari Foot Bridge via Jainpuri Khanka Sarif Bari & Khodaboxkati Eshak Member Bari Char a Earth work at Ch.0.0 - 2000m b CarpettingBC Ch.0.0 -2000m c Construction of 1 No Box culvert 1.0m x 1.0m at ch.1310m d Protective worksPalisading 60m under Bakergonj UpazilaBarishal District. Salvaged Cost TK.1943192.00 (Road ID: 506074199) | M/S Sikder Enterprise | Memo No: 716, Date: 17/10/18 | 13794593.43 | 26/02/19 |  | 4002602 | 50%
18 | Improvement of Road from Goma Amtala to Chatra Hat via Gajir Hat DKP High School & Sowdakar Bari Road by BC at Ch. 1600m-2100. Effective Length 500m.Under Bakerganj Upazila District- Barishal (Road ID: 506074136) | Easy Max | Memo No: 793, Date: 18/11/18 | 3081298.68 | 24/04/19 |  | 975000 | 33%
19 | Improvement of road from Kabiraj Altaf Chairman Bari near Madrasha to East Dhudal Community Pry School via Shahajahan Howlader & Alomgir Mollik Bari road by BC Ch. 736m-2000m. Under Bakerganj Upazila District- Barishal (Road ID: 506074148) | M/S Farhad Enterprise | Memo No: 793, Date: 18/11/18 | 8138352.441 | 2019-11-04 |  | 2375000 | 30%
20 | Improvement of Road from Kabai Dhola Riazuddin Madrasha to Khodaboxkati Govt. Pry. School by BC work at Ch.00m-500 with 1 No. 900mx900m U-Drain. Under Bakerganj Upazila District- Barishal (Road ID: 506075432) | M/S Setu Traders | Memo No: 793, Date: 18/11/18 | 3664146.37 | 16/04/19 |  | 1800000 | 50%
21 | A Improvement of road from Rabipur Ali Hossain Khan Bari UZR to Sharif Bari via Ayeb Boyati Bari i Earthwork Ch.0.0m-500m ii CarpetingDC Ch.0.0 - 500m.iii Palisading work-50m B Improvement of road from S/Side of Kabai HatNear Chunakhali Sluice Get to E/S of Pearpur Iron BridgeUZR via Chunakhali HatDhola Madrasa & Dhola Sluice Get i Earthwork Ch.4000m-5000m ii Carpeting DC Ch.4000m-5000m iii Construction of 2Nos 1.0m x 1.0m Box Culvert at Ch.4666m 4951m & 1No. U-Drain at Ch.4830m iv Palisading work-55m Under Bakergonj Upazila Barishal District (Road ID: 506075099, 506074155) | M/S. Amir Engineering Corporation | Memo No: 38, Date: 08/01/19 | 11939429.937 | 26/05/19 |  | 9350000 | 72%
22 | Improvement of road East Bathsala UZR to Dhulia River Bank via Bathsala Karikornagar GPS infront of Amir Khan Bari Mosque Salvaged Cost Tk 331586.00 i Earthwark Ch.0.00m-1450m. ii Carpeting DC Ch.0.00m-1450m. iii Construction of 01 No U-Drain 0.9mx0.9m at Ch.1250m.iv Palasading 79m. Under Bakergonj Upazila Barishal District (Road ID: 506075379) | M/S ISLAM BROTHERS LTD | Memo No: 101, Date: 31/01/19 | 10414223.243 | 19/06/19 |  | 5450000 | 60%
23 | Part A Improvement of road from H/O Sujauddin Halta F.H. high School. Halta Mouza Sholoshath to Surath Memorial GPS. i Earthwark Ch.0.00m-850m. ii Carpeting DC Ch.0.00m-850m. iii Construction of 02 Nos RCC Culvert1.6mx1.6m at Ch 4m845m 3 Nos U-Drain 0.9mx0.9m at Ch.120m190m235m.iv Palsading 96mPart B Improvement of road from Mokimabad Bajar S/Side of Culvert to East Side of BIP Siuce Get via Dilip Master Bari.Oza Bari to Thakur Bari via Naboraz Biswas bari i Earthwark Ch.2500m-3250m. ii Carpeting DC Ch. 2500m-3250m. iii Construction of 01 No RCC Culvert 1.6mx1.6m at Ch 3125m.iv Palsading 38m.Under Bakergonj Upazila District Barishal (Road ID: 506075180, 506075229) | M/S Rupali Construction | Memo No: 97, Date: 31/01/19 | 13806417.904 | 21/05/19 |  | 4525000 | 35%
24 | Part A Improvement of road from Padrishibpur GPSUZR to Bismillah Bazar via Sikder Bari Kowabunia khal & Dhulal sadu Bari Salvaged Cost Tk 921459.76i Earthwark Ch.0.0m-900m. ii Carpeting DC Ch. 0.0 - 900m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert & 1No.U-Drain at Ch 482m.& 28m iv Palsading 59m.Under Bakergonj Upazila District Barishal. Part B Improvement of road from East side of Bangla bazar Box Culvert to Wapder Khal Ghorar Bridge Bothra via Biharipur Madrasha road. i Earthwark Ch.3250m-3850m. ii Carpeting DC Ch.3250m-3850m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert at Ch.3255m & 01 No 1.6 m x 1.6m RCC Box Culvert at Ch.3716m iv Palsading 28m.Under Bakergonj Upazila District Barishal.Part C Improvement of road from Padrishibpur Sunddartala Baily Bridge UZR to Aowal Sikderbari i Earthwark Ch.0.0m-500m. ii Carpeting DC Ch. 0.0 - 500m. Under Bakergonj Upazila District Barishal (Road ID: 506074057, 506074182, 506075155) | M/S S H Enterprise | Memo No: 155, Date: 12/02/19 | 14202513.2 | 30/07/19 |  |  | 0%
25 | Improvement of Road UZR Rabipur GPS UNR Younous Sharif Bari Via Rabipur. Salvaged Cost Tk 641271.00i Earthwark Ch.0.00m-500m. ii Carpeting DC Ch.0.00m-500m. iii Palsading 50m. Under Bakergonj Upazila Barishal District (Road ID: 506074267) | M/S Bushra Traders | Memo No: 174, Date: 18/02/19 | 3506728.85 | 17/06/19 |  | 1400000 | 70%
26 | A Improvement of Road from Dhaporkati Khayaghat Kabai to Chunakhall Bridge via Najam Master Laxmipasa Senior Madrasha & south Hanua Regd. Pry. School a Earthwark Ch. 1286m-2286m.b Carpeting BC Ch. 1286m-2286m.c Construction of 01 No 1-Vent RCC Box Culvert 1.6mx1.6m at Ch.1386m & 01 No. U-Drain. At Ch. 1652m. d Palsading 47m.B Improvement of Road from Krishnokati Anser Howlader Bari to Nijamkhali Khal over Iron Foot Bridge. Salvaged Cost Tk. 361295.00a Earthwark Ch. 00m-898m.b Carpeting DC Ch. 00m-898m.c Construction of 01 No. U-Drain. At Ch. 197m.d Palsading 64m (Road ID: 506074154, 506075313) |  | Memo No: 394, Date: 21/05/19 | 15171756.48 |  |  |  |  | E-Tender Under Process.
27 | Improvement of Road from Balaikati Dhanshiri NGO to Kalitara Govt. Pry. School via Howlader bari.ID No-506074188a Earthwark Ch. 00m-1000m.b Carpeting DC Ch. 00m-1000m.c Construction of 01 No 1-Vent RCC Box Culvert 1.6mx1.6m at Ch.510m & 01 No. U-Drain. At Ch. 370m. d Palsading 15m | M/S Muhib Construction | Memo No: 430, Date: 29/05/19 | 7311104.18 | 27/11/19 |  |  | 0%
28 | Improvement of Road from South kazlakati Arjina Govt. Pry. School to Ukiler Hat road a Earthwark Ch. 00m-900m. b Carpeting BC Ch. 00m-900m. c Construction of 01 Nos RCC Box Culvert 1.6mx1.6m at Ch.234m (Road ID: 506074039) |  | Memo No: 657, Date: 28/07/19 | 6889481.76 |  |  |  |  | E-Tender Under Process
29 | Improvement of Road from Dhaporkati khaya Ghat Kabai to Chunakhali Bridge via Najam Master Laxmipasha Senior Madrasha & South Hanua Regd. Pry.School road a Earthwark Ch. 00m-1300m. b Carpeting BC Ch. 00m-1300m. c Linkroad up to H/O Madrasha Quarter 55m d Palisading 70m e Construction of 2 Nos U-Drain 900mm x 900mm at Ch.290m & 1084m (Road ID: 506074154) |  | Memo No: 672, Date: 07/08/19 | 10622639.7 |  |  |  |  | E-Tender Under Process
30 | Improvement of Road From Mudukhali-Kazlakati Talukder hat.ID No-506075235a Earthwark Ch. 00m-780m.b Carpeting BC Ch. 00m-780m.c Construction of U-Drain 900mmx900mm at Ch. 497m & 01 No 3mx3m RCC Box Culvert at Ch. 780m.d Palsading 74m (Road ID: 506075235) |  |  | 7513234.74 |  |  |  |  | E-Tender Under Process
31 | A Improvement of Road Khayrabath hat Garuria UP to Dhaparkati Bazar Godown via Nilgonj Bazar.ID No-506073001 Salvaged Cost TK 1488714.00a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of RCC Box Culvert 1.50mx1.50m at Ch.520m.d Palsading 100m. B Improvement of Road From Khayrabad UP Garuria UP Office via Khayrabath High School Runsiposor RNGPS west side of Dinger hat. Salvaged Cost TK 1459641.00ID No-506073010a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of RCC Box Culvert 1.50mx1.50m at Ch.760m.d Palsading 90m (Road ID: 506073001, 506073010) |  |  | 17308000 |  |  |  |  | E-Tender Under Process
32 | A Improvement of road from Dudhalmow Ferryghat RHD to Kanki Govt. Pry. School. under Bakergonj upazila Barishal District.a Earthwark Ch. 980m-3100m.b Carpeting BC Ch. 980m-3100m.c Palsading 85m. B Improvement of Dhaporkati High School-Kalukhan Bari via Khandoker Bari. under Bakergonj upazila Barishal District.a Earthwark Ch. 00m-700m.b Carpeting BC Ch. 00m-700m.c Construction of 01 No 1.50mx1.50m RCC Box Culvert at Ch. 605m. d Palsading 82m. C Improvement of Khajuria Vhorpasha-Emdad Talukdar Bari-Warase Hopwlader Bari. under Bakergonj upazila Barishal District.a Earthwark Ch. 00m-800m.b Carpeting BC Ch. 00m-800m.c Palsading 50m. |  |  | 29371000 |  |  |  |  | E-Tender Under Process
33 | A Improvement of road from UZR Middle Baily Bridge to Badalpara Hat Road by BC. under Bakergonj upazila Barishal District Salvaged Tk. 2030121.00a Earthwark Ch. 00m-850m.b Carpeting BC Ch. 00m-850m.c Construction of 02 Nos 2.00mx2.00m RCC Box Culvert at Ch. 330m & 502m. U-Drain 900mmx900mm at Ch. 655m.d Palsading 15m. B Improvement of road from Bairom Kha Digir per to RHD via Rashed Pada & Fakir Bari. under Bakergonj upazila Barishal Districta Earthwark Ch. 00m-625m.b Carpeting BC Ch. 00m-625m.c Palsading 90m. under |  |  | 13148996.33 |  |  |  |  | E-Tender Under Process
34 | A Improvement of Road from Ghopar Hat to Satikola High School via Nazirpur Islam Bari & Satikola GPS. at Ch. 1130m-1760m including 01 No-1.50mx1.50m at Ch. 1620.00m. B Improvement of Road from Mohespur Hat Ruper Jore Govt Primary School. at Ch. 0.00m-780m including 01 No-1.50mx1.50m at Ch. 780.00m. Under Bakergonj Upazila Barishal District Salvaged Cost Tk 1102166.00 |  |  | 12778386.93 |  |  |  |  | E-Tender Under Process
35 | Construction of 30m long PSC Girder Bridge over road from Kamarkhali GC to Baherchar GC via Sarsi Police Farry Patkati L/G Faridpur UP Office & Janota Bazar at Ch 9200m Under Bakergonj Upazila Barishal District |  |  | 30402000 |  |  |  |  | E-Tender Under Process
35 |  |  |  | 343069962.035 |  |  | 141786793 |  |  |  | 8829.82
1 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m (Road ID: 506073023) | Anwar Hossain LCS No-01 | Memo No: 228, Date: 24/03/15 | 131861 | 16/04/15 | 16/05/15 | 131399 | 100% | Final
2 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m (Road ID: 506073023) | Md. Babul Howlader LCS No-02 | Memo No: 228, Date: 24/03/15 | 256728 | 16/04/15 | 16/05/15 | 255288 | 100% | Final
3 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m (Road ID: 506073023) | Md. Joynal Abadin LCS No-03 | Memo No: 228, Date: 24/03/15 | 230734 | 16/04/15 | 16/05/15 | 230617 | 100% | Final
4 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m (Road ID: 506073023) | Md. Royon Mollah LCS No-04 | Memo No: 228, Date: 24/03/15 | 224792 | 16/04/15 | 16/05/15 | 224421 | 100% | Final
5 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m (Road ID: 506073023) | Md. Shahidul Sharif LCS No-05 | Memo No: 228, Date: 24/03/15 | 233429 | 16/04/15 | 16/05/15 | 226102 | 100% | Final
6 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m (Road ID: 506073023) | H M Shamsul Huda LCS No-06 | Memo No: 228, Date: 24/03/15 | 205799 | 16/04/15 | 16/05/15 | 205740 | 100% | Final
7 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m (Road ID: 506073023) | Md. Hanif LCS No-07 | Memo No: 228, Date: 24/03/15 | 243498 | 16/04/15 | 16/05/15 | 243355 | 100% | Final
8 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m (Road ID: 506073023) | Md. Amir Ali Khan LCS No-08 | Memo No: 228, Date: 24/03/15 | 230149 | 16/04/15 | 16/05/15 | 230032 | 100% | Final
9 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m (Road ID: 506073023) | Md. Monir Hossain LCS No-09 | Memo No: 228, Date: 24/03/15 | 249498 | 16/04/15 | 16/05/15 | 249382 | 100% | Final
10 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m (Road ID: 506073023) | Md. Shalim Mridha LCS No-10 | Memo No: 228, Date: 24/03/15 | 222257 | 16/04/15 | 16/05/15 | 221327 | 100% | Final
10 | Sub Total: |  |  | 2228745 |  |  | 2217663 |  |  |  | 0
45 | Grand Total: |  |  | 345298707.035 |  |  | 144004456 |  |  |  | 8829.82
322 |  |  |  | 2013259121.433 |  |  | 923604711 |  |  |  | -68367645.56

## Progres
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [16 empty] | Reporting Month: December/2020
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/CCA-Rd/02 | Improvement of road from Gournadi Highway Thana Connecting road under Gournadi Upazila. | 506325047 | [6 empty] | 1544297 |  | 1612193 | M/S Tamim Enterprise | 14/06/15 | 21/06/15 | 20/11/15 |  | 100% | 1612193 | 100% | Final | 50% | -806096.5
2 | BDRIDP/BAR /GOU/UN-Rd/01 | (a) Improvement of Road from Sarikal GC to Shaheber char Bazar via Nalchira Bazar ch. 5555m-7055m), (b) Construction of 2 nos U-drain at ch.599m & 6555m on the same road Under Gournadi Upazila, District-Barisal. | 506323013 |  | 1.5 |  |  |  | 1.8 | 9785485 |  | 10357650.8 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 10353584 | 99.96% | Final | 60% | -4138993.52
3 | BDRIDP/BAR /GOU/UZ-Rd/01 | (a) Improvement of Road from Gournadi Bandar GC to Muladi GC via Kutubpur Bazar at ch. 0m-630m), (b) Construction of 2 nos U-drain at ch. 205m & 364m on the same road Under Gournadi Upazila, District-Barisal. | 506322016 |  | 0.63 |  |  |  | 1.8 | 5122695 |  | 5399315 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 5356652 | 100% | Final | 60% | -2117063
4 | BDRIDP/BAR /GOU/UZ-Rd/02 | Improvement of illah (NHW) to Kalkini Upazila HQ via Tulatala Bazar at ch.2413m-3213m), Under Gournadi Upazila, District-Barisal. | 506322013 |  | 0.8 |  |  |  |  | 4643337 |  | 4898705 | M/S Sadman Builders | 2014-09-11 | 16/11/14 | 15/05/15 |  | 100% | 4667277 | 95.28% | Final | 40% | -2707795
5 | BDRIDP/BAR /GOU/UN-Rd/02 | (a) Improvement of Batazore GC to Pinglakathi Bazar via Pachim Chandrahar GPS at ch. 0m-1000m), (b)Construction of 1 nos U-drain at at ch.14m on the same road, (c) Construction 1v-2.3mx2.30m RCC Box Culvert at ch.527m & 1583m on the same road Under Gournadi Upazila, District-Barisal. | 506323001 |  | 1 |  |  |  | 2.2 | 7805159 |  | 8236744 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 8218516 | 99.78% | Final | 50% | -4100144
6 | BDRIDP/BAR/GOR/CCA-Rd/01 | Improvement of road from Maddam Hosnabad Nabarun RPS to Nezamuddin College by HBB at Ch.481-1492m (Nizamuddin Degree College road from freedom fighter Nizamuddin Shaheber Kaborstan via Madha hosnabad UP Member Md.Matiur Rahman Sarif Bari Bridge under Gouranadi upazila, Barisal District. | 506324040 |  |  | 1.011 |  |  |  | 2839204 |  | 2601109.88 | Md. Sirazul Islam Hanif | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 2583729 | 100% | Final | 100% | 17380.88
7 | BDRIDP/BAR/GOR/UZ-Rd/03 | Improvement of Barthi Bazar (NHW) to Gournadi GC via Torky GC at ch.2150 - 4150m. | 506322005 |  | 2 |  |  |  |  | 13145679 |  | 13801595 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 100% | 13799645 | 99.99% | Final
8 | BDRIDP/BAR/GOR/UN-Rd/03 | Rehabilitation of road from Mahilara UP Office to Chadshi Hat via Bilogram Bazar (A. Rob Chokder House to Chadshi Hat road) road By BC from Ch. 5370-6900m. | 506323019 |  | 1.53 |  |  |  |  | 5834483 |  | 6124969 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 100% | 6121962 | 99.95% | Final
9 | BDRIDP/BAR/GOR/UN-Rd(R)/04 | Rehabilitation of road from Mahilara UP office to Chadshi hat via Billogram Bazar road from Ch. 3740-4850m (Salvage Material Cost Tk. 11,01,418.00) | 506323019 |  | 1.11 |  |  |  |  | 5359476 |  | 5623536 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 100% | 5623536 | 100%
10 | BDRIDP/BAR/GOR/UN-St/01 | Construction of 2-Vent 4.30mx4.30m RCC Box Culvert on Mahilara UP office to Chadshi hat via Billogram Bazar road at Ch. 4200m. | 506323019 | [5 empty] | 8.6 | 1970942 |  | 2069109 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/12/15 |  | 100% | 2036343 | 100% | Final
11 | BDRIDP/BAR/GOR/CCA-St/01 | Construction of 3 Nos Single Vent 4.30mx4.30m RCC Box Culvert & 2 nos U-Drain on Battala Kapali bari Bridge (NHW) to Khanjapur High School road at ch. 95m,270m,1276m564m&970m Under Gournadi Upazila, District-Barisal e-ID : 22284 | 506324136 | [5 empty] | 14.9 | 6680560 |  | 6946789.2 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 100% | 6943287 | 99.95% | Final
12 | BDRIDP/BAR/GOR/CCA-Rd/03 | Improvement of road from Battala Kapali bari Bridge (NHW) to Khanjapur High School road by BC from Ch.00 - 1656m Under Gournadi Upazila, District-Barisal e-ID : 22285 | 506324136 |  | 1.656 |  |  |  |  | 7060824 |  | 7343257.29 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 100% | 7343257 | 100% | Final
13 | BDRIDP/BAR/GOR/UZ-Rd/04 | Improvement of Barthi Bazar (NHW) to Burghata bus Stand (NHW) via Amanagong hat at Ch. 450-2450m. e-ID : 19611 | 506322017 |  | 2 |  |  |  |  | 12874579 |  | 13172831.8 | M/S Howlader Constructure | 2015-07-07 | 2015-08-07 | 2016-06-07 |  | 100% | 13168763 | 99.97% | Final
14 | BDRIDP/BAR/GOR/UZ-ST/01 | Construction of 30.00m PSC Girder Bridge on Barti Bazar to Gournadi GC at Ch.5000km over Anandhapur Khal under Gournadi UpazilaDistrict-Barisal | 506322005 | [5 empty] | 30 | 24934266.46 |  | 27947198 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 100% | 27946271 | 100% | Final
15 | BDRIDP/BAR/GOR/UZ-ST/02 | Construction of 32.00m PSC Girder Bridge on Barti BazarNHW to Gournadi GC via Torky GC at Ch.9340km over Kashba Khal under Gournadi Upazila District-Barisal | 506322005 | [5 empty] | 32 | 24196878.89 |  | 27086534.08 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 100% | 27086354 | 100%
16 | BDRIDP/BAR/GOR/UZ-RdR/05 | Periodic Maintenance of Batazore-Agarpur-Sarikal via Hosnabad Nalchira-Miarchar road. a Earthwark from Ch. 8725- 17177m.b Carpeting DC 17361.14 sqm.c 12mm SC-13906.56 sqm. Under Gournadi Upazila District - Barishal. | 506322002 |  | 8.45 |  |  |  |  | 16020946.84 |  | 16821994.18 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 100% | 8500000 | 50.53%
17 | BDRIDP/BAR/GOR/UZ-RdR/06 | Periodic Maintenance of iIlah Bas stand NHW to Agailjhara H/Q via Bakai & Rajihar Bazar in/c Nutun Bazar Connecting road.a Earthwark from Ch. 0- 3832m.b Carpeting DC 3224.409 sqm.c 12mm SC-11191.1 sqm. Under Gournadi Upazila District - Barishal. | 506322006 |  | 3.832 |  |  |  |  | 5915176.68 |  | 6210935.51 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 100% | 6209670 | 99.98%
18 | BDRIDP/BAR/GOR/UZ-RdR/07 | Periodic Maintenance of Batazore GCNHW to Dhamura GC via Solak Bazar road.a Earthwark from Ch. 0- 2145m.b Carpeting 40mm-DC 6403.2 sqm.c Palisading Work297.00m. Under Gournadi Upazila District - Barishal. | 506322011 |  | 2.145 |  |  |  |  | 8824294.58 |  | 9265509.3 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 40% |  | 0%
19 | BDRIDP/BAR/GOR/UN-RdR/05 | Periodic Maintenance of Chadshi UP Office-Goila UP Office Road.a Earthwark from Ch. 0- 830m.b Carpeting DC 322.5 sqm.c 12mm SC-2208.35 sqm. Under Gournadi Upazila District - Barishal. | 506323020 |  | 0.83 |  |  |  |  | 1001243.79 |  | 1051305.98 | M/S Mega/Repa Enterprise | 2019-05-08 | 2019-12-08 | 2020-12-02 |  | 100% | 1035083 | 100%
20 | BDRIDP/BAR/GOR/UN-RdR/06 | A Maintenance Nathai BazarDR to Bauthi UP Office via Chandsi a Earthwark Ch.00m-1150m.b Carpeting DC Ch.00m-1150m. B Maintenance Badarpur Bazar to Sarikal UP Office a Earthwark Ch.00m-4787m.b Carpeting DC Ch.00m-4787m. c Palsading 50m. | 506323003 506323009 |  | 5.937 |  |  |  |  | 11855719.7 |  | 11855717.279 | M/S Mother Engineering | 13/02/20 | 20/02/20 | 20/08/20 |  | 0% |  | 0%
21 | BDRIDP/BAR/GOR/CC-Rd/04 | Improvement of road with BC from Steemar Ghat to Hosnabad hat road from at Ch.00m-630m | 506324041 |  | 0.63 |  |  |  |  | 4471349.78 |  | 4692681.594 | M/S.Mother Engineering | 27/01/20 | 2020-04-02 | 2020-04-08 |  | 20% |  | 0%
22 | BDRIDP/BAR/GOR/ CCA-Rd/05 | A Improvement of Road Batazore NHW to Jissorekati GPS. a Earthwark Ch.500m-1307m.b Carpeting BC Ch. 500m-1307m. c Construction of 01 Nos U-Drain at Ch.778m. d Palsading 107m. B Improvement of road by BC from Nalchira UP Office of Kalabaria Bazar via Pingolakati Model GPS. Salvaged Cost TK 11294.00a Earthwark Ch.500m-2056m.b Carpeting BC Ch.500m-2056m | 506324018 506324060 |  | 2.363 |  |  |  |  | 17836679.64 |  | 17835597.963 | M/S.Mother Engineering | 25/03/20 | 2020-02-04 | 2020-02-11 |  | 30% |  | 0%
23 | BDRIDP/ BAR/GOR/ UN-Rd/07 | Improvement of Road from Chandshi UP Office-Uttar Pallordi GPS Ramshiddi Bazarvia Chadshi High School. a Earthwark Ch.900m-1353m.b Carpeting BC Ch. 900m-1353m.c Construction of 01 No 1-Vent RCC Box Culvert 1.3mx1.3m at Ch.1266m. d Palsading 52m | 506323027 |  | 0.453 |  |  |  | 1.3 | 4140788.45 |  | 4345757.478 | M/S.Mother Engineering | 27/01/20 | 2020-04-02 | 2020-04-08 |  | 20% |  | 0%
24 | BDRIDP/BAR/GOR/UZ-Rd/08 | Improvement of Road by BC from Barthi Bazar NHW Bhurghata Bus Stand NHW via Amanathgonj Hat. Salvaged Cost TK 2742324.00a Earthwark Ch.5388m-7450m.b Carpeting BC Ch. 5388m-7450m.c Construction of 02 Nos U-Drain at Ch.6200m & 7350m. d Palsading 120m. | 506322017 |  | 2.062 |  |  |  |  | 16418601.51 |  | 16415649.213 | M/S.Mother Engineering | 25/03/20 | 2020-02-04 | 2020-02-11 |  | 40% |  | 0%
25 | BDRIDP/BAR/GOR/CCA-Rd/06 | A Improvement of Road Borobari NHW to Sarifabad via Sarifabad Hapania GPS. a Earthwark Ch.00m-1500m.b Carpeting BC Ch. 00m-1500m. c Palsading 67m. Under Gournadi Upazila Barishal DistrictB Improvement of Bagat Sarifabad road. a Earthwark Ch.1070m-1520m. b Carpeting BC Ch.1070m-1520m.c Palsading 25m | 506324084 506324119 |  | 1.95 |  |  |  |  | 15243061.87 |  | 15242429.34 | M/S.Mother Engineering | 25/03/20 | 2020-02-04 | 2020-02-11 |  | 20% |  | 0%
26 | BDRIDP/ BAR/GOR/ CCA-Rd/07 | A Improvement of road from Aduna Battala Aduna GPS road from Under Gournadi Upazila Barishal District. Salvaged Cost. Tk 1270072.00. a Earthwark Ch. 00m-850m.b Carpeting BC Ch. 00m-850m.c Construction of 01 Nos U-Drain0.625m x 0.600m At Ch. 643m B Improvement of road from Kutubpur High Bridge Kalabaria Bazar via Sankorpasha GPS road from. Under Gournadi Upazila Barishal District. a Earthwark Ch. 00m-2050m.b Carpeting BC Ch. 00m-2050m. c Construction of 01 Nos U-Drain0.625m x 0.600m At Ch. 1481m | 506324044 506324150 |  | 2.9 |  |  |  | 1.2 | 23201500 |  | 23199999.999 | M/S.Mother Engineering | 2020-03-06 | 2020-10-06 | 2020-10-12 |  | 20% |  | 0%
27 | BDRIDP/ BAR/GOR/ CCA-Rd/08 | Improvement of road From NHW at Kasba Hat to Billogram hat via Badamtala Road. Under Gournadi Upazila Barishal District. Salvaged Cost. Tk 539572.00 a Earthwark Ch. 00m-90m & 3290m-4900m.b Carpeting BC Ch. 00m-90m & 3290m-4900m. Improvement of road from Kutubpur Bazar-Badurpur Bazar road. Under Gournadi Upazila Barishal District. Salvaged Cost. Tk 234974.00a Earthwark Ch. 00m-950m.b Carpeting BC Ch. 00m-950m. c 1No. U -Drain 0.625m x 0.600m at Ch.500m | 506324002 506324057 |  | 2.65 |  |  |  | 0.625 | 21970500 |  | 21970000 | M/S.Mother Engineering | 2020-03-06 | 2020-10-06 | 2020-10-12 |  | 20% |  | 0%
27 |  |  |  | 0 | 40.878 | 1.011 | 0 | 0 | 92.6 | 280697728.19 | 0 | 292129114.886 | [6 empty] | 158606122 |  |  |  | -13852711.14
1 | BDRIDP/BAR/GOR/UN-EW/01 | Improvement of road from Mahilara UP Office to Chadshi hat via Billogram Bazar road By Earth Filling Work from Ch. 3740m-4850m. | 506323019 | 1756 | [5 empty] | 349519 |  | 349519 | Anjur Ali Sarder LCS No-1 | 2015-10-11 | 15/11/15 | 30/03/16 |  | 100% | 334291 | 100%
2 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Gournadi GC via Torky GC at Ch. 2150m-4150m by earth . | 506322005 | 1603.375 | [5 empty] | 223623 |  | 223623 | Md Shalim Khalifa LCS-1 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 223598 | 99.99%
3 |  |  |  | 501.125 | [5 empty] | 69892 |  | 69892 | Sunil Joydhar LCS-2 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 69822 | 99.9%
4 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Burghata Bus Stand (NHW) via Amanothgonj hat at Ch. 450m-2450m by earth. | 506322017 | 2151.655 | [5 empty] | 300092 |  | 300092 | Md Mahabub Khan LCS-1 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 299749 | 99.89%
5 |  |  |  | 1505.375 | [5 empty] | 209955 |  | 209955 | Md Mohasin Sharder LCS-2 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 209849 | 99.95%
5 |  |  |  | 7517.53 | 0 | 0 | 0 | 0 | 0 | 1153081 | 0 | 1153081 | [6 empty] | 1137309 |  |  |  | 0
32 |  |  |  | 7517.53 | 40.878 | 1.011 | 0 | 0 | 92.6 | 281850809.19 | 0 | 293282195.886 | [6 empty] | 159743431 |  |  |  | -13852711.14
Upazila: Agailjhara
1 | BDRIDP/BAR/AGL/CCA-Rd/01 | Improvement of Road by BC from Rathkhola Bazar-Bhadrapara Road (ch. 0m-1000m) Under Agailjhara Upazila, District-Barisal. | 506024008 |  | 1 |  |  |  |  | 5097636 |  | 5599756.34 | M/S Talukder Enterprise | 23/10/14 | 30/10/14 | 30/04/15 |  | 100% | 5597543 | 99.96% | Final
2 | BDRIDP/BAR/AGL/CCA-Rd/02 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 5527014 |  | 4583839 | M/S Mitushi Traders | 27/11/14 | 2014-08-12 | 2015-04-06 |  | 100% |  | 0% | W/O Cancel
3 | BDRIDP/BAR/AGL/CCA-Rd(R)/06 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m. | 506025056 |  | 1 |  |  |  | 2.7 | 4914057 | 196459 | 5158284.22 | M/S Sharif Enterprise | 22/04/15 | 29/04/15 | 28/01/16 |  | 100% | 5157868 | 99.99% | Final | 50% | -2578725.89
4 | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. | 506025058 | [5 empty] | 8.9 | 1677674 |  | 1771918.99 | M/S Sharif Enterprise | 28/05/15 | 2015-04-06 | 2015-04-12 |  | 100% | 1693392 | 100% | Final
5 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 506023001 |  | 2.76 |  |  |  |  | 14739342 | 791797 | 15592739.8 | M/S Sharif Enterprise | 25/05/15 | 2015-06-06 | 30/05/15 |  | 100% | 15592732 | 100% |  | 20% | -12474184.04
6 | BDRIDP/BAR/AGL/UZ-Rd/02 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by BC from Ch. 3800m-5800m. | 506022003 |  | 2 |  |  |  |  | 10771206 |  | 11288255.96 | M/S Sraboni Construction | 27/05/15 | 2015-04-06 | 2016-03-06 |  | 100% | 11286798 | 99.99% | Final | 60% | -4513844.424
7 | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m | 506024034 |  | 1.28 |  |  |  |  | 6017149 |  | 6375868.44 | M/S Sarniabad Enterprise | 25/05/15 | 2015-01-06 | 2015-01-12 |  | 100% | 6375048 | 99.99% | Final | 60% | -2549526.936
8 | BDRIDP/BAR/AGL/CCA-Rd/04 | Improvement of road from Poiser hat GC-Ramshil Bazar via Trimukhi road by BC from Ch. 0.00m-1000m. | 506024040 |  | 1 |  |  |  |  | 4926273 |  | 5538660.26 | M/S Shafique Brothers | 21/05/15 | 28/05/15 | 28/11/15 |  | 100% | 5554952 | 100.3% | Final | 70% | -1677889.818
9 | BDRIDP/BAR/AGL/CCA-Rd(R)/05 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m. | 506025058 |  |  | 1.2 |  |  |  | 4159274 | 288401 | 4400152.34 | M/S Helal Traders | 2015-02-07 | 2015-09-07 | 2016-09-01 |  | 100% | 4350867 | 100% | Final | 30% | -3030821.298
10 | BDRIDP/BAR/AGL/UZ-Rd(R)/01 | Rehabilitation of Barthi - Valukshi - Magura- Ambari-Bakalhat road by BC at ch.5870-7880m. | 506022008 |  | 2.01 |  |  |  |  | 12746908 |  | 13383052 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 100% | 13383025 | 100% | Final
11 | BDRIDP/BAR/AGL/CCA-Rd/07 | Improvement of road from Biplob Serniabad House to Hazi Musa House road By BC from ch.00-400m. | 506025084 |  | 0.4 |  |  |  |  | 1917053 |  | 2012714.3 | M/S Serniabad Enterprise | 2015-07-07 | 2015-08-07 | 2015-08-12 |  | 100% | 2012370 | 99.98% | Final
12 | BDRIDP/BAR/AGL/CCA-Rd/ 02 | Improvement of road from Seral - Goila road via Shahid Serniabad House - Tamer Jame Mosjid(Tamer Girls High School-Seral Community Center) by BC (Ch.0.0 - 975m) under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 7232587 | 7232587 | 7230073.2 | M/S Serniabad Traders | 2017-09-03 | 16/03/17 | 16/10/17 |  | 100% | 7153140 | 100% | Final
13 | BDRIDP/BAR/AGL/CCA-Rd/08 | Improvement of road from Hazi Mokbul Sardar House via Sardar Mohabubul Alom & Sardar Harun - Jainger Gomosta House road. at Ch.00 to 208m under Agailjhara Upazila Barisal. | 506025088 |  | 0.208 |  |  |  |  | 2168362.12 |  | 2276707.38 | M/S Sharif Enterprise | 15/03/18 | 22/03/18 | 22/09/18 |  | 100% | 2162693 | 94.99%
14 | BDRIDP/BAR/AGL/Gha/01 | Construction of Ghat at Paisarhat Paschim par under Agailjhara Upazila Barisal | [7 empty] | 2900067.47 |  | 2958070.38 | M/S Sharif Enterprise | 22/03/18 | 29/03/18 | 29/09/18 |  | 100% | 2946824 | 99.62%
15 | BDRIDP/BAR/AGL/UZ-RdR/03 | Maintenance of Barthi- Valiukshi-Magura Bakal Hat Roada Earthwark from Ch. 9860- 11860m.b Carpeting DC 21.3 sqm.c 12mm SC-5237.7 sqm. d Palisading Work 103.00m. Under Agailjhara Upazila District- Barishal. | 506022008 |  | 2 |  |  |  |  | 2265178.34 |  | 2377531.18 | M/S Yeamin Traders | 15/08/19 | 2019-02-09 | 2019-02-03 |  | 100% | 1200000 | 50.47%
16 | BDRIDP/BAR/AGL/ UZ-RdR/04 | Maintenance of Road From Nimtola RHD-Dhamura GC viaRatnapur UP Road at Ch 5265m-7383m Agailjhara Under Agailjhara Upazila District- Barishal. | 506022010 |  | 2.118 |  |  |  |  | 2649883 |  | 2781847.17 | M/S Sharif Enterprise | 20/08/19 | 27/08/19 | 27/02/20 |  | 100% | 2500000 | 89.87%
17 | BDRIDP/BAR/AGL/UN-RdR/03 | Maintenance of Road From Goila UP Office to Billogram Bazar via Rajer Bari Road at Ch 00m-2000mm Agailjhara Under Agailjhara Upazila District- Barishal. | 506023008 |  | 2 |  |  |  |  | 2890888.53 |  | 3033987.51 | M/S Sarder Enterprise | 22/08/19 | 29/08/19 | 29/02/20 |  | 100% | 1500000 | 49.44%
18 | BDRIDP/BAR/AGL/UN-RdR/02 | Maintenance of Road From Basail Hat Rajihar UP-Batra Bazar viiiia Basail Pachchim Para Bazar Road at Ch 00m-1000m Agailjhara Under Agailjhara Upazila District - Barishal. | 506023006 |  | 1 |  |  |  |  | 3511387.07 |  | 3685551.86 | M/S Yeamin Traders | 15/08/19 | 2019-02-09 | 2019-02-03 |  | 100% | 3463792 | 93.98%
19 | BDRIDP/ BAR/AGL/ CCA-Rd/09 | A Improvement of Temar Bastaila Nagar GPS-West Mollapara-Ohchiarmad Bazar. i Earthwark Ch.650m-1865m.ii Carpeting DC Ch. 650m-1865m. iii Palsading 641m.B Choto Basail Kader Bepari House to East Valukshi Bridge.Salvaged Cost Tk 37835.00i Earthwark Ch.0.00m-360m.ii Carpeting DC Ch.0.00m-360m. iii Palsading 120m. Under Agailjhara upazila District Barishal. | 506024009 506025045 |  | 1.575 |  |  |  |  | 15112800 |  | 15868063.678 | M/S Sharif Enterprise- M/S. Serniabad Traders (JV) | 2020-09-02 | 16/02/20 | 16/08/20 |  | 50% | 3500000 | 22.06%
20 | BDRIDP/BAR/AGL/CCA- Rd/10 | Improvement of Alloshika-Ramanonder AK Bazar-Batra Bazar Ramsell road from Ch.1000m-1800m | 506025050 |  | 0.8 |  |  |  |  | 7433677 |  | 7803874.95 | M/S Sarder Enterprise | 24/10/19 | 2019-01-11 | 2019-01-05 |  | 100% | 5900000 | 75.6%
21 | BDRIDP/BAR/AGL/CCA- Rd/11 | Improvement of Road from Boramagra Switch gate Bazarvia Kodaldhoa Bazar to Ramshil bazar.a Earthwark Ch. 1000-5250m.b Carpeting DC Ch. 1000-5250m. c Palsading 556m | 506024034 |  | 4.25 |  |  |  |  | 31659786 |  | 33235957.18 | M/S Sharif Enterprise | 2020-09-02 | 16/02/20 | 16/08/20 |  | 50% | 4300000 | 12.94%
22 | BDRIDP/BAR/AGL/CCA-Rd/12 | A Improvement of Ghatoker Poll-Daspottry Janata Bazar- Patihal Gomosta Bari Box Culvert via Janata GPS New. a Earthwark Ch. 600m-1600m.b Carpeting BC Ch. 600m-1600m.c Palsading 300m.B Improvement of Ambulla Switchgate to Kotalipara Border Road. Salvaged Cost Tk 522605.00a Earthwark Ch. 1194m-1773m.b Carpeting BC Ch. 1194m-1773m. c Construction of 01 Nos U-Drain 1125mx600m at Ch.618m. d Palsading 160m | 506024043 506024045 |  | 1.579 |  |  |  | 0.6 | 13930337.2 |  | 13928246.306 | M/S.Sharif Enterprise | 2020-05-02 | 2020-12-02 | 2020-12-08 |  | 10% |  | 0%
23 | BDRIDP/BAR/AGL/CCA-Rd/13 | A Improvement of Mollapara Saw Mill-Taler Bazar-Ramar Bazar Kalurpar Bazar road. Salvaged Cost Tk 535334.00 a Earthwark Ch. 1000m-2230m.b Carpeting BC Ch. 1000m-2230m.B Improvement of Goila Baby home- Nathoy Road via Abu Hanif Sarkers Bari. a Earthwark Ch. 700m-1100m.b Carpeting BC Ch. 700m-1100m.c Palsading 5m | 506024041 506025124 |  | 1.63 |  |  |  |  | 11826330 |  | 11818488.17 | M/S Sharif Enterprise | 13/02/20 | 20/02/2020 | 20/08/2020 |  | 60% | 2900000 | 24.54%
24 | BDRIDP/BAR/AGL/UZ-Rd/05 | Improvement of Mahilara-Chaygram-Amboula-Paisarhar Road. Salvaged Cost Tk 1100033.00 a Earthwark Ch. 22280m-23226m.b Carpeting BC Ch. 22280m-23226m.c Palsading 148m. | 506022006 |  | 0.946 |  |  |  |  | 8037695 |  | 8036490.91 | M/S S R Engineering | 19/01/2020 | 26/01/2020 | 26/07/2020 |  | 40% | 600000 | 7.466%
25 | BDRIDP/BAR/AGL/UZ-Rd/14 | Improvement of Agailjhara-Sujankathi via Nilkanda road. Salvaged Cost - Tk 1833963.00a Earthwark Ch. 600m-1725m.b Carpeting DC Ch. 600m-1725m. c Construction of 01 Nos 2 vent 4.0mx4.0m RCC Box Culvert at Ch.1025m. d Palsading 333m | 506024019 |  | 1.125 |  |  |  |  | 12773520 |  | 12763961.38 | M/S Yeamin Traders | 2020-03-02 | 2020-10-02 | 2020-10-08 |  | 35% | 3550000 | 27.81%
26 | BDRIDP/BAR/AGL/ CCA-Rd/15 | Improvement of Sobikharpar RHD to Askar Hat UZR. a Earthwark Ch.1583m-2968m.b Carpeting BC Ch.1583m-2968m. C Palsading 288m | 506024052 |  | 1.385 |  |  |  |  | 11179100 |  | 11169145.4 | M/S Yeamin Traders | 2020-06-02 | 13/02/2020 | 13/08/2020 |  | 40% | 1900000 | 17.01%
27 | BDRIDP/ BAR/AGL/ CCA-St/02 | Construction of 15.00m RCC Girder Bridge on Shaheber hat - Ramer Bazar to Gurucharan Babu House | 506024017 | [5 empty] | 15 | 16143882 |  | 16141736.55 | M/S Sharif Enterprise | 2020-10-02 | 17/02/2020 | 17/12/2020 |  | 65% | 9500000 | 58.85%
28 | BDRIDP/BAR/AGL/CCA-St/03 | Construction of 14.00m RCC Slab Bridge on Despotty Janata Bazar - Patihar Sluice via Despotty Janata GPS Ghatoker Poll - Despotty Janata Bazar - Patihar Gomosta Bari Box Culvert via Janata GPS NEW at Ch.410m | 506024043 | [5 empty] | 14 | 15451567 |  | 15449228.36 | M/S Serniabad Enterprise | 19/02/20 | 26/02/2020 | 26/12/2020 |  | 78% | 13829650 | 89.52%
29 | BDRIDP/BAR/AGL/CCA-St/04 | Construction of 16.00m RCC Pedestrain Bridge near of Shahid Fakir home at Khajuria Khajuria Rucca Road to Gogwsar Masters Bari | 506025114 | [5 empty] | 16 | 11082682 |  | 11080418.981 | M/S.Sharif Enterprise | 2020-05-02 | 2020-12-02 | 2020-12-12 |  | 60% | 3500000 | 31.59%
30 | BDRIDP/BAR/AGL/CCA-Rd/16 | Improvement of Bakal Wapda Embankment to Bakal Hat. a Earthwark Ch.1400m-2455m & 3253m-4260m.b Carpeting BC Ch. 1400m-2455m & 3253m-4260m.c Construction of 2 Nos U-Drain 1.125mx0.60m At Ch. 2943m & 4145m. d Palsading 553m. Salvaged Cost Tk 364102.00 | 506024006 |  | 2.062 |  |  |  | 1.125 | 17608532 |  | 17590922.801 | M/S.Shraboni Construction | 18/02/20 | 25/02/20 | 25/08/20 |  | 50% | 2900000 | 16.49%
31 | BDRIDP/BAR/AGL/CCA-Rd/17 | A Improvement of Moulabi Bazar hat-Kumarvanga Bazar Uttar Shehipasha Joynal Sarders Bari Salvaged Cost Tk 507417 a Earthwark Ch. 150m-1185m.b Carpeting BC Ch. 150m-1185m.c Construction of 01 Nos Single-Vent 2.00mx2.00m RCC Box Culvert At Ch. 927md Palsading 94m. | 506025038 |  | 1.035 |  |  |  | 2 | 8524020.71 |  | 8515042 | M/S S R Engineering | 2020-06-02 | 13/03/2020 | 13/12/2020 |  | 25% | 1050000 | 12.33%
32 | BDRIDP/ BAR/AGL/ CCA-Rd/18 | A Improvement of BC Road from Goila Bazar-Rothkhola Bazar-Nonapukurpar-Bhadrapara road Taler Bazar-UZR Salvaged Cost. Tk . 1777935.00 Under Agailjhara Upazila Barishal District.a Earthwark Ch. 1440m-2777m.b Carpeting BC Ch. 1440m-2777m.c Palsading 574m. B Improvement of BC road from Ratnapur UP GPS-Kalarmore Uzirpur Border Box Culvert. Under Agailjhara Upazila Barishal District.a Earthwark Ch.1000m-1600m.b Carpeting BC Ch. 1000m-1600m. c Construction 01 No 1x1.60mx1.60m RCC Box Culvert at Ch. 1435md Palsading 99m. C Improvement of BC road from west Mohjonkathi GPS to Ratnapur Sluice Gate UZRroad. Under Agailjhara Upazila Barishal District. a Earthwark Ch.500m-2000m.b Carpeting BC Ch. 500m-2000m. c Palsading 162m. | 506024008 506024053 506025071 |  | 3.437 |  |  |  | 1.6 | 32138000 |  | 32136722.701 | M/S.Sharif Enterprise | 2020-08-04 | 15/04/20 | 15/10/20 |  | 25% | 900000 | 2.801%
33 | BDRIDP/ BAR/AGL/ CCA-Rd/19 | A Improvement of BC road from Chandarvanga UNRBC Road-Pakurita Rathbari R&H road Under Agailjhara Upazila Barishal District Salvaged Tk.2031168.00 a Earthwark Ch. 500m-2021m.b Carpeting BC Ch. 500m-2021m.c Palsading 239m. B Improvement of BC Road from Fullashree R&H Post Office to Gupterhat via Uttar Shipasha High School Under Agailjhara Upazila Barishal District. a Earthwark Ch. 800m-1450m.b Carpeting BC Ch. 800m-1450m.c Construction of 01 Nos U-Drain At Ch. 1030md Palsading 87m. | 506024002 506024010 |  | 2.171 |  |  |  | 0.6 | 19372546.46 |  | 19371241.651 | M/S.Sharif Enterprise | 2020-08-04 | 15/04/20 | 16/10/20 |  | 40% | 3300000 | 17.04%
34 | BDRIDP/ BAR/AGL/ CCA-Rd/20 | A Improvement of Kandirpar Changutia Kamal Howlader Bari to Jalil maulanas bari via Dakkin par Eid gha road at Ch. 785.00m-1750.00m. including 01 No- U-Drain 0.625mx0.600m at Ch. 1630.00m. Salvaged Cost Tk 106371.00B Improvement of Changutia to kazigram road at Ch. 0.00m-645.00m including 01 no. U-Drain 0.625mx0.600m at Ch. 35.00m. Salvaged Cost Tk 88433.00 under Agailjhara Upazila Barishal District Total Salvaged Cost Tk 194804 | 506025093 506024021 | [6 empty] | 13872241.11 |  | 14561691.493 | M/S.Yeamin Traders | 2020-07-09 | 14/09/20 | 14/02/21 |  | 0% |  | 0%
35 | BDRIDP/ BAR/AGL/ CCA-Rd/21 | A Improvement of Road from Baropaika Karim Bazar R&H Dhafar per GPS-Baro Paika Deghir Par Road. at Ch. 00.00-803.00m including 01 No U-Drain 1.125mx0.60m at Ch. 210.00m. Salvaged Cost Tk 157731.00 B Improvement of Road from Jobarpar-Askor Road. at Ch. 1500.00-1915.00m. C Improvement of Road from Kathira Old UNR Bazar S/S-CCDP Morer Road. at Ch. 500.00-1045.00m. under Agailjhara Upazila Barishal District Salvaged Cost TK 91656.00 Total Salvaged Cost TK 249387.00 | 506024042 506025014 506025026 | [6 empty] | 17782745 |  | 17776406.932 | M/S.Sharif Enterprise |  |  |  |  | 0% |  | 0%
36 | BDRIDP/ BAR/AGL/ CCA-St/05 | Construction of 20.00m RCC Girder Bridge on Taler Bazar to Howla-1 via west Mollapara & Oichamath Mission at Ch.4907m Temar Bastalla-Nagar GPS west Mollapara-Ohchiarmad Bazar Howla Box Culvert Disamit Bazar under Agailjhara Upazila Barishal District | 506024009 | [6 empty] | 21379000 |  | 21370237.812 | M/S Sharif MAT - MSE(JV) | 29/09/20 | 2020-06-10 | 2021-06-04 |  | 0% |  | 0%
37 | BDRIDP/ BAR/AGL/ CCA-St/06 | Construction of 20.00m RCC Girder Bridge on Taler Bazar to Howla-2 via west Mollapara & Oichamath Mission at Ch.5224m Temar Bastalla-Nagar GPS west Mollapara-Ohchiarmad Bazar Howla Box Culvert Disamit Bazar under Agailjhara Upazila Barishal District | 506024009 | [6 empty] | 17559000 |  | 17552158.126 | M/S Sharif MAT - MSE(JV) | 29/09/20 | 2020-06-10 | 2021-06-04 |  | 0% |  | 0%
38 | BDRIDP/ BAR/AGL/ CCA-St/07 | Construction of 15.00m RCC Girder Bridge on Taler Bazar to Howla-3 via west Mollapara & Oichamath Mission at Ch.6340m Temar Bastalla-Nagar GPS west Mollapara-Ohchiarmad Bazar Howla Box Culvert Disamit Bazar under Agailjhara Upazila District Barishal | 506024009 | [6 empty] | 16982000 |  | 16976289.905 | M/S Sharif MAT - MSE(JV) | 29/09/20 | 2020-06-10 | 2021-06-04 |  | 0% |  | 0%
39 | BDRIDP/ BAR/AGL/ UN-St/01 | A Construction of 1x4.50m Single vent RCC Box Culvert on Bagda Union Parishad to Askar Bazar Kali Bari road. at Ch.2470m.B Construction of 3x3.70mx5.00m Three vent RCC Box Culvert on the same road at Ch.2670m.C Construction of 2x4.50mx4.50m Two vent RCC Box Culvert on the same road at Ch.2800m under Agailjhara Upazila District Barishal | 506023014 | [6 empty] | 9449148.57 |  | 9446313.825 | M/S MOHAN MADINA ENTERPRISE |  |  |  |  | 0% |  | 0%
40 | BDRIDP/ BAR/AGL/ CCA-St/08 | A Construction of 2x4.50mx4.50m Two vent RCC Box Culvert on Boromagra Sluicegate Bazar via Kodaldhoa Bazar to Ramshil Bazar at Ch.3335m.B Construction of 3x4.500mx5.00m Three vent RCC Box Culvert on the same road at Ch.3497m. under Agailjhara Upazila District Barishal | 506024034 | [6 empty] | 7403872.06 |  | 7401576.86 | M/S.Naim Enterprise | 14/09/20 | 21/09/20 | 21/01/21 |  | 0% |  | 0%
40 |  |  |  | 0 | 42.721 | 1.2 | 0 | 0 | 62.525 | 432814421.64 | 8509244 | 440043226.301 | [6 empty] | 149560694 |  |  |  | -26824992.406
1 | BDRIDP/BAR/AGL/CCA-EW/01 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal. | 506024034 | 2209.995 | [5 empty] | 153224 |  | 153224 | Ramesh Chandra Shikari LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 119075 | 77.71%
2 |  |  | 506024034 | 2209.995 | [5 empty] | 148896 |  | 148896 | Md Halim Talukder LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 122647 | 82.37%
3 | BDRIDP/BAR/AGL/CCA-EW/02 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 216905 |  | 216905 | Abdul Hakim Molla LCS No-1 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 140432 | 64.74%
4 |  | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 231753 |  | 231753 | Anukul Chandra Barai LCS No-2 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 185062 | 79.85%
5 | BDRIDP/BAR/AGL/CCA-EW/03 | Resectioning of road from Temar Bastala to Hawla Bridge via Nagar GPS-Talbazar-lichermath Bazar road from Ch. 3840-4840m. | [7 empty] | 344680 |  | 344680 | Nolini Halder LCS No-1 | 2017-11-01 | 15/01/17 | 30/04/17 |  | 100% | 306262 | 100%
6 | [9 empty] | 230350 |  | 230350 | Susen Bala LCS No-2 | 2017-11-01 | 15/01/17 | 30/04/17 |  | 100% | 226669 | 100%
7 | BDRIDP/BAR/AGL/UZ-EW/01 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal. | 506022009 | 6543.5 | [5 empty] | 124341 |  | 124341 | Md. Sohrab Howlader LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 124340 | 100% | Final
8 |  |  | 506022009 | 6543.5 | [5 empty] | 307876 |  | 307876 | Md. Mosharef Sheikh LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 307875 | 100% | Final
9 |  |  | 506022009 | 6543.5 | [5 empty] | 329106 |  | 329106 | Abdul Rashid Howlader LCS No-3 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 329106 | 100% | Final
10 |  |  | 506022009 | 6543.5 | [5 empty] | 330529 |  | 330529 | Matleb Howlader LCS No-4 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 329457 | 99.68% | Final
11 | BDRIDP/BAR/AGL/UN-EW/01 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal. | 506023001 | 11301.706 | [5 empty] | 201404 |  | 201404 | Mahim Baishnab LCS No-1 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 201396 | 100%
12 |  |  | 506023001 | 11301.706 | [5 empty] | 289300 |  | 289300 | Sudhir Kumar Ojha LCS No-2 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 288996 | 99.89%
13 |  |  | 506023001 | 11301.706 | [5 empty] | 288022 |  | 288022 | Banendra Nath Panday LCS No-3 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 287780 | 99.92%
14 |  |  | 506023001 | 11301.706 | [5 empty] | 207336 |  | 207336 | Rabindranath Sarker LCS No-4 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207335 | 100%
15 |  |  | 506023001 | 11301.706 | [5 empty] | 205837 |  | 205837 | Nirmal Ghatak LCS No-5 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205837 | 100%
16 |  |  | 506023001 | 11301.706 | [5 empty] | 207632 |  | 207632 | Bebek Pandey LCS No-6 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207631 | 100%
17 |  |  | 506023001 | 11301.706 | [5 empty] | 205952 |  | 205952 | Pangkoj Joydhor LCS No-7 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205952 | 100%
18 | BDRIDP/BAR/AGL/CCA-EW/01 | Resectioning of Road from Seral-Goila road via Shahid Serniabad House-Tamer Jame Mosjid (Tamer Girls High School-Seral Community Center) by Earth at Ch. 0.00m-975m. | 506025048 | [6 empty] | 317636 |  | 317636 | Md. Babul Sikder | 30/03/17 | 30/03/17 | 30/04/17 |  | 100% | 310599 | 100%
18 |  |  |  | 116932.232 | 0 | 0 | 0 | 0 | 0 | 4340779 | 0 | 4340779 | [6 empty] | 4106451 |  |  |  | 0
58 |  |  |  | 116932.232 | 42.721 | 1.2 | 0 | 0 | 62.525 | 437155200.64 | 8509244 | 444384005.301 | [6 empty] | 153667145 |  |  |  | -26824992.406
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. | [6 empty] | 15 | 6544168 |  | 5567698.82 | M/S Safi Enterprise | 2014-11-06 | 18/06/14 | 17/06/15 |  | 100% | 5512198 | 100% | Final |  | 5567698.82
2 | BDRIDP/BAR/UZP/CCA-St/02 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m. | 506945205 | [5 empty] | 8.625 | 2586217 |  | 2015457.24 | Md Zakir Hossain Mia | 23/11/14 | 30/11/14 | 30/05/15 |  | 100% | 1973907 | 100% | Final |  | 41550.24
3 | BDRIDP/BAR/UZP/CCA-Rd/01 | Improvement of road from Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market, Nurani Madrasha & H/O Mr.Habibur Rahman (Beer Protik) by BC from Ch.0.00-1500m under Uzirpur Upazila, Barisal. | 506945205 |  | 1.5 |  |  |  |  | 6378273 |  | 5167677 | Md Sirazul Islam Hanif | 2014-01-12 | 2014-08-12 | 2015-07-06 |  | 100% | 5166254 | 99.97% | Final | 70% | -1548880.1
4 | BDRIDP/BAR/UZP/CCA-Rd/02 | Improvement of road from Paschim Satla WAPDA to Satla Kheyaghat via H/O Fazlul Hoque Hawlader & Mosque By HBB from Ch. 0.00-375m. | 506945204 |  |  | 0.375 |  |  |  | 1316117 |  | 1225909.58 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2015-11-09 |  | 100% | 1223186 | 99.78% | Final | 100% | 2723.58
5 | BDRIDP/BAR/UZP/CCA-St/03 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m. | 506945129 | [5 empty] | 4 | 3397103 |  | 2682855.6 | Md Zakir Hossain Mia | 2015-11-05 | 18/05/15 | 18/10/15 |  | 100% | 2674595 | 99.69% | Final | 70% | -796596.08
6 | BDRIDP/BAR/UZP/UZ-Rd(R)/01 | Rehabilitation of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) road from Ch. 0.00m-2100m. | 506942005 |  | 2.1 |  |  |  |  | 10215215 |  | 8522561.6 | M/S G M Construction | 28/09/15 | 2015-05-10 | 2016-05-04 |  | 100% | 8522424 | 100% | Final
7 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 506942007 |  | 2.605 |  |  |  |  | 18314961 | 18314961 | 14275617.27 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 75% | 7750000 | 54.29%
8 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 506942015 |  | 2.296 |  |  |  |  | 14753928 | 14753928 | 11501091.23 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 77% | 8635000 | 75.08%
9 | BDRIDP/BAR/UZP/UZ-RdR/04 | Rehabilitation of Harta Chowmuhani Bisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 | 506942009 |  | 2.6 |  |  |  | 2.5 | 17827349 |  | 18399998.87 | M/S S H Enterprise | 2018-08-03 | 15/03/18 | 15/03/19 |  | 100% | 10250000 | 55.71%
10 | BDRIDP/BAR/UZP/UN-Rd/01 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m. | 506943007 506942018 |  | 2.34 |  |  |  | 1.2 | 15060662.42 |  | 13554596.17 | M/S Niaz Traders | 2017-02-10 | 2017-09-10 | 2018-09-08 |  | 65% | 8742112 | 64.5%
11 | BDRIDP/BAR/UZP/UN-St/01 | Construction of 12.00m Long RCC Girder Bridge over Chowdhuri Hat - Hasti Shundi via Daberkul road infront of A. Latif MasterDaberkul Chowmohani - Chowmohini Sere Bangla road at ch. 00.0m under Uzirpur Upazila Barisal District. | 506943004 | [5 empty] | 12 | 8372665.04 |  | 7535398.53 | M.M Builders & Engineers | 30/01/18 | 2018-07-02 | 2018-07-12 |  | 100% | 7535398 | 100%
12 | BDRIDP/BAR/UZP/CCA-Rd/04 | Improvement of Old Sikerpur Bandar-Abul Hasan Mridhas House Connecting road under Uzirpur Upazila Barisal a Earthwork Ch.0.0m - 360m b Bituminous Carpetting Ch.0.0m - 360m c U-Drain 01 no at Ch.117. | 506945281 |  | 0.36 |  |  |  | 1 | 2738720.64 |  | 2464848.57 | M/S Kohinoor Enterprise | 22/04/18 | 29/04/18 | 29/08/18 |  | 100% | 2183531 | 88.59%
13 | BDRIDP/BAR/UZP/CCA-Rd/03 | Improvement of road from Guthia kakradhari Connecting road North side of Khaleque Mollas House of Dahorpara GPS via Mojid Masters House under Uzirpur Upazila Barisal a Earthwork Ch.0.0m -1550m b Bituminous Carpetting Ch.0.0m - 1550m c U-Drain 04 nos at Ch.130m476m655m1230m & 2Nos 1-Vent 4m x 4m RCC Box Culvert at ch.755m & 1540m | 506944084 |  | 1.55 |  |  |  | 16 | 12042875.78 |  | 10838588.2 | Md. Mahafuz Khan | 2018-03-05 | 2018-10-05 | 2019-10-03 |  | 50% | 2600000 | 23.99%
14 | BDRIDP/BAR/UZP/Gha/01 | Construction of Typical Ghat at Satla Bazar under Uzirpur Upazila Barisal . | [7 empty] | 2565467.67 |  | 2460575.82 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 100% | 2456488 | 99.83%
15 | BDRIDP/BAR/UZP/CCA-Rd/05 | Part A Improvement of road from Muktijodda Milon Kendra Connecting road Harasia road.i Carpeting DC Ch. 0.00m-900m. ii 3 Nos.0.625mx0.600m U-Drain at Ch.10m365m665m.Part B Improvement of road from East Joysree Village road.i Carpeting DC Ch. 0.00m-1000m.ii 2 Nos.0.625mx0.600m U-Drain at Ch.605m865m. Salvaged Cost Tk 141267.00Part C Improvement of road from Jugihati-Chokder bari Jame Mosque to Damodarkathi Tri mukhi Atok road by DC at Ch.0.00m-1050.00m with 1 No.4.30mx4.30m RCC Box Culvert at Ch.560m. 3 Nos.0.625mx0.600m U-Drain at Ch.130m760m & 835m. Under Uzirpur Upazila Barishal District. | 506945170 506945028 506945172 |  | 2.95 |  |  |  | 9.295 | 23428700 |  | 21586749.471 | M/S Mudasser Ali Mallick | 23/05/19 | 30/05/19 | 30/11/19 |  | 60% | 6000000 | 27.79%
16 | BDRIDP/ BAR/UZP/ CCA-Rd/06 | A Improvement of road from Uttar Dhamura WAPDA-H/O Santu Molla road. at Ch. 0.00m-775m including of 03 Nos U-Drain 0.625mx0.600m at Ch. 38.00m 260.00m & 680.00m. B Improvement of road from Uttar Dhamura WAPDA-H/O Kadam Ali-H/O Mobarok Sikder road at Ch. 1200m-1885m. under Uzirpur Upazila Barishal District | 506945341 506945342 |  | 1.46 |  |  |  | 1.8 | 12481301.91 |  | 11857236.815 | M/S.Talukder Enterprise | 2020-11-05 | 18/05/20 | 18/11/20 |  | 0% |  | 0%
16 |  | Sub-Total: |  | 0 | 18.301 | 0.375 | 0 | 0 | 71.42 | 158023724.46 | 33068889 | 139656860.786 | [6 empty] | 81225093 |  |  |  | 3266496.46
1 | BDRIDP/BAR/UZP/UZ-EW/01 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 0.00m-700m. | 506942005 | [6 empty] | 258990 | 258990 | 258990 | Yasin Sarder LCS No-1 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 241309 | 100% | Final
2 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 700m-1400m. | [7 empty] | 284900 | 284900 | 284900 | Iqbal Hossan LCS No-2 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 271670 | 100% | Final
3 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 1400m-2100m. | [7 empty] | 278170 | 278170 | 278170 | Supian LCS No-3 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 275956 | 100% | Final
4 | BDRIDP/BAR/UZP/UZ-EW/02 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 0.00m-1100m. | 506942007 | 9764.116 | [5 empty] | 418543 | 418543 | 418543 | Md. Shahidul Islam LCS No-1 | 30/01/17 | 2017-01-02 | 30/04/17 |  | 100% | 251299 | 60.04%
5 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1100m-1900m. | [7 empty] | 451503 | 451503 | 451503 | Md. Khalilur Rahman LCS No-2 | 30/01/17 | 2017-01-02 | 30/04/17 |  | 100% | 271244 | 60.08%
6 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1900m-2605m. | [7 empty] | 491755 | 491755 | 491755 | Habibur Bapari LCS No-3 | 30/01/17 | 2017-01-02 | 30/04/17 |  | 100% | 296067 | 60.21%
7 | BDRIDP/BAR/UZP/UZ-EW/03 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 1754m-2850m. | 506942015 | [6 empty] | 421703 | 421703 | 421703 | Kamrun Nesa LCS No-1 | 2016-12-12 | 18/12/16 | 18/03/17 |  | 100% | 418953 | 100% | Final
8 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 2850m-3650m. | [7 empty] | 466527 | 466527 | 466527 | Rubina Begum LCS No-2 | 2016-12-12 | 18/12/16 | 18/03/17 |  | 100% | 463877 | 100% | Final
9 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 3650m-4050m. | [7 empty] | 342538 | 342538 | 342538 | Monzu Begum LCS No-3 | 2016-12-12 | 18/12/16 | 18/03/17 |  | 100% | 340237 | 100% | Final
10 | BDRIDP/BAR/UZP/UN-EW/01 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3400m-3900m By Earth. | 506943007 506942018 | [6 empty] | 434519 | 434519 | 434519 | Md. Ziaul Haque LCS No-1 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 430783 | 100% | Final
11 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3900m-4300m By Earth. | [7 empty] | 437099 | 437099 | 437099 | Khokon Sharder LCS No-2 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 435285 | 99.58% | Final
12 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4300m-4900m By Earth. | [7 empty] | 461279 | 461279 | 461279 | Rofiqul Islam LCS No-3 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 459873 | 99.7% | Final
13 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4900m-5740m By Earth. | [7 empty] | 310321 | 310321 | 310321 | Nurul Hoq Sikder LCS No-4 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 310041 | 99.91% | Final
14 | BDRIDP/BAR/UZP/UZ-EW/04 | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 0.00m-1000m | 506942009 | [6 empty] | 512862 | 512862 | 512862 | Shilpi Biswas LCS No-1 | 30/10/17 | 30/10/17 | 30/03/18 |  | 100% | 511764 | 99.79% | Final
15 |  | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 1000m-1700m | [7 empty] | 380788 | 380788 | 380788 | Namita Rani Biswas LCS No-2 | 30/10/17 | 30/10/17 | 30/03/18 |  | 100% | 379253 | 99.6% | Final
16 |  | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 1700m-2500m | [7 empty] | 461975 | 461975 | 461975 | Sabika Das LCS No-3 | 30/10/17 | 30/10/17 | 30/03/18 |  | 100% | 458856 | 100% | Final
16 |  | Sub-Total: |  | 9764.116 | 0 | 0 | 0 | 0 | 0 | 6413472 | 6413472 | 6413472 | [6 empty] | 5816467 |  |  |  | 0
32 |  | Grand Total: |  | 9764.116 | 18.301 | 0.375 | 0 | 0 | 71.42 | 164437196.46 | 39482361 | 146070332.786 | [6 empty] | 87041560 |  |  |  | 3266496.46
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 506102003 | 0 | 1 | 0 | 0 | 0 | 0 | 7013799 | 7013799 | 5349539.02 | M/S Saleha Enterprise | 29/01/17 | 2017-06-02 | 2017-06-06 |  | 100% | 2012608 | 100% | Cancelled | 40% | 127207.608
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m,1 No.3.0m x 3.0m, 2Nos.4.0m x 4.0m, 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 506102003 | 0 | 0 | 0 | 0 | 0 | 11 | 7531517 | 7531517 | 5461652.5 | M/S Soma Enterprise | 25/01/17 | 2017-02-02 | 2017-02-10 |  | 100% | 5200000 | 95.21%
3 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 11850164.61 |  | 10665148 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 100% | 10322698 | 96.79%
4 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 9814374 |  | 8832936 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 100% | 8814725 | 99.79% | Final
5 | BDRIDP/BAR/BAN/Gha/01 | Construction of RCC Ghat at Mohish Katakhali Kheya Ghat under Banaripara Upazila Barisal . | [7 empty] | 2911932.99 |  | 2620739.69 | M/S Amir Engineering Corporation | 2018-03-05 | 2018-10-06 | 2018-10-12 |  | 100% | 2618986 | 99.93%
6 | BDRIDP/ BAR/BAN/ CCA-Rd/01 | Improvement of road by BC Gordder Abu Taher Shop to Kachua Madrasha. Salvaged Cost Tk 448135.00i Earthwark Ch.600m-1600m. ii Carpeting DC Ch.600m-1600m. iii Construction of 03 Nos. 1.5mx1.5m Box Culvert at Ch.667m742m & 938m & U-Drain 0.6mx0.6m at Ch.870m973m & 1550m. under Banaripara UpazilaBarishal District | 506105098 |  | 1 |  |  |  | 5.1 | 9337657.46 |  | 8870774.587 | M/S Alif Enterprise | 2019-12-06 | 19/06/19 | 19/12/19 |  | 70% | 2800000 | 31.56%
7 | BDRIDP/BAR/BAN/ CCA-Rd/02 | Improvement of Read from West Chakhar Gotarer bari Bridge to Purbo Goailbari GPS road Maszidbari Lance Ghat to Modhow Sayedkati Rgd P. School. Salvaged Cost Tk 776408.00 a Earthwark Ch.00m-1000m.b Carpeting BC Ch.00m-1000m. c Construction of 01 Nos RCC Box Culvert 2.0mx2.0m at Ch.179m0 02 Nos RCC Box Culvert 1.5mx1.5m at Ch.440m & 696m. 07 Nos U-Drain 0.6mx0.6m at Ch.235m 308m 510m 612m 726m 925m & 940m. d Palsading 35m | 506104045 |  | 1 |  |  |  | 9.2 | 9604310.25 |  | 9124094.73 | M/S Sun Bulders | 02/10/19 | 09/10/19 | 09/04/20 |  | 25% |  | 0%
8 | BDRIDP/ BAR/ BAN/ UZ-St/04 | Part A Construction of 35.06m Long RCC Girder Bridge on Banaripara to Harta Road over B.Baria Khal at Ch. 7998m under Banaripara Upazila Barishal DistrictPart B Construction of 30.06m Long RCC Girder Bridge on Banaripara to Harta Road over Poschim Inderhawla Khal at Ch. 6668m under Banaripara Upazila Barishal District | 506102003 506102003 | [6 empty] | 59700000 |  | 59630016.556 | M/S.Kohinoor Enterprise |  |  |  |  | 0% |  | 0%
8 |  |  |  | 0 | 3 | 0 | 0 | 0 | 55.3 | 117763755.31 | 14545316 | 110554901.083 | [6 empty] | 31769017 |  |  |  | 127207.608
1 | BDRIDP/BAR/BAN/UZ-EW/01 | Resectioning of Banaripara-Harta Road at Ch. 4665m-6066m. | 506102003 | 3655.305 | [5 empty] | 441816.72 | 441816.72 | 441816.72 | Zakir Hossain LCS No: 1 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 437075 | 100%
2 |  | Resectioning of Banaripara-Harta Road at Ch. 6066m-7252m. |  | 3440.645 | [5 empty] | 415870.76 | 415870.76 | 415870.76 | Kohinoor Begum LCS No: 2 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 415280 | 99.86%
3 |  | Resectioning of Banaripara-Harta Road at Ch. 7252m-7702m. |  | 3300.95 | [5 empty] | 398985.83 | 398985.83 | 398985.83 | Baschu Forazi LCS No: 3 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 397904 | 99.73%
4 |  | Resectioning of Banaripara-Harta Road at Ch. 7702m-8152m. |  | 3181.47 | [5 empty] | 384544.28 | 384544.28 | 384544.28 | Abdul Karim LCS No: 4 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 382564 | 100%
5 |  | Resectioning of Banaripara-Harta Road at Ch. 8152m-8752m. |  | 3835.515 | [5 empty] | 463598.7 | 463598.7 | 463598.7 | Horolal Mondol LCS No: 5 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 463243 | 99.92%
6 |  | Resectioning of Banaripara-Harta Road at Ch. 8752m-9352m. |  | 3821.705 | [5 empty] | 461929.48 | 461929.48 | 461929.48 | Mithu Howlader LCS No: 6 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 461929 | 100%
7 |  | Resectioning of Banaripara-Harta Road at Ch. 9352m-9760m. |  | 3097.89 | [5 empty] | 374441.97 | 374441.97 | 374441.97 | Md. Khairul Islam LCS No: 7 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 373462 | 99.74%
7 |  |  |  | 24333.48 | [5 empty] | 2941187.74 | 2941187.74 | 2941187.74 | [6 empty] | 2931457
15 |  |  |  | 24333.48 | 3 | 0 | 0 | 0 | 55.3 | 120704943.05 | 17486503.74 | 113496088.823 | [6 empty] | 34700474
Upazila: Babugonj
1 | BDRIDP/BAR/BABU/CCA-Rd/01 | Improvement of road from Babugonj Agorpur GC to Mr. Younusur Rahman (Divisional Commissioner) house via Clubgonj hat by Carpeting from Ch. 750-1400m & 0.00-1550m. | 506034025 |  | 2.2 |  |  |  |  | 9792326 | 944029 | 10750396.05 | M/S Lutful Kobir | 2014-10-07 | 17/07/14 | 16/04/15 |  | 100% | 10748336 | 100% | Final | 90% | -1072979.555
2 | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km (Road ID: 506035070) | 506035070 |  | 2.35 |  |  |  |  | 9718891 | 421856 | 10173103.86 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 10173094 | 100% | Final | 60% | -4069231.684
3 | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 506034095 |  | 4.32 |  |  |  |  | 18518441 | 1035938 | 19386557.17 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 19386554 | 100% | Final | 60% | -7754619.698
4 | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. | 506035006 |  | 2.6 |  |  |  |  | 9959477 |  | 10428682 | M/S Atique Construction | 25/03/15 | 2015-01-04 |  |  | 100% | 10422370 | 99.94% | Final | 60% | -4165160.8
5 | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 506035070 | [5 empty] | 8.3 | 2931768 | 184122 | 3071060.04 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 3070368 | 99.98% | Final | 60% | -1227731.976
6 | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 506034095 | [5 empty] | 18.2 | 4744358 | 199349 | 4968549.43 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 4965087 | 99.93% | Final | 60% | -1983957.342
7 | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 506035006 | [5 empty] | 7.6 | 2001016 | 62866 | 2095536.41 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 1895463 | 100% | Final | 60% | -638141.154
8 | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 506034024 | [5 empty] | 12 | 1982458 | 150637 | 2076355.09 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 1875359 | 100% | Final | 60% | -629545.946
9 | BDRIDP/BAR/BAB/UN-St/01 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m. | 506033006 | [5 empty] | 7.6 | 1443386 | 41933 | 1029755.17 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 986117 | 100% | Final | 60% | -368263.898
10 | BDRIDP/BAR/BAB/UN-Rd(R)/01 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m. | 506033006 |  | 1.78 |  |  |  |  | 6457205 | 2442317 | 5193526.54 | M/S Alvi Construction | 2015-05-05 | 2015-12-05 | 2016-12-02 |  | 100% | 5143354 | 100% | Final | 60% | -2027238.076
11 | BDRIDP/BAR/BAB/CCA-Rd/05 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District. | 506034024 |  | 3.8 |  |  |  |  | 14308351 |  | 14979470.55 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 14979470 | 100% | Final | 60% | -5991787.67
12 | BDRIDP/BAR/BAB/UN-RD/02 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 |  | 2.11 |  |  |  |  | 12421386 |  | 11570042.22 | M/S Hasan Construction | 22/11/16 | 29/11/16 | 28/06/17 |  | 100% | 11570042 | 100% | Final
13 | BDRIDP/BAR/BAB/UN-St/02 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m. | 506033007 | [5 empty] | 15.2 | 4182978 |  | 4179759.25 | M/S Saifuddin Traders | 14/11/16 | 20/11/16 | 19/09/17 |  | 100% | 4095279 | 100% | Final
14 | BDRIDP/BAR/BAB/CCA-RdR/06 | Improvement of Road from Telerchar GPS -Najamrari Bari - Jahungirnagar UP road Start ch.1700m Satter Mirar Bari -Thakur. From Ch.0.0m - 550mSalvaged Cost Tk 192766.00 | 506035103 506034109 |  | 1.7 |  |  |  |  | 3507645.29 |  | 3156880.761 | M/S Niaz Traders | 2018-11-01 | 18/01/18 | 18/07/18 |  | 100% | 3152957 | 99.88% | Final
15 | BDRIDP/BAR/BAB/CCA-Rd/07 | Improvement of road from Jahapur Shilondia Bridge -Uttor Mujafforpur Peda Master bari under Jahangir Nagar Union a Bituminous Surfacing -wearing courseDC ch.190m -1190m b 1No. 2.0m x 2.0m & 1No.1.0m x1.0m RCC Box Culvert at Ch.273m & 615m under Babuganj Upazila Barisal District. | 506035018 |  | 1.1 |  |  |  | 3 | 6955230.78 |  | 6949870.12 | M/S Amir Engineering Corporation | 27/02/18 | 2018-04-03 | 2018-04-12 |  | 100% | 6926903 | 99.67%
16 | BDRIDP/ BAR/BAB/ CCA-Rd/08 | Improvement of Road from Ramjankathi GPS to Charalgi GPS. a Earthwark from Ch. 0- 1500m.b Carpeting DC from Ch. 0- 1500m.c Construction of 2 Nos 625mmx600mm U-Drain at Ch. 736m & 1285m.d Palisading Work 150.00m. Under Babuganj District- Barishal. | 506035132 |  | 1.5 |  |  |  | 1.25 | 11562581.55 |  | 10984852.47 | M/S Sharif Enterprise | 2019-04-04 | 2019-11-04 | 2019-11-10 |  | 75% | 5800000 | 52.8%
17 | BDRIDP/ BAR/BAB/ CCA-Rd/09 | Improvement of from Khudrokathi Freedom Fighter Mogibor Rahaman Sikder House to Baige Comander Abdul Mojid Khan house. At Ch. 00m-1100m.Salvaged Cost Tk 285357.00i Earthwark Ch.0.00m-1100m.ii Carpeting DC Ch.0.00m-1100m. iii Construction of 02 Nos 0.625mx0.600m U-Drain. at Ch.110m & 400m.iv Palsading 46m.Under Babuganj Upazila Barishal District. | 506034155 |  | 1.1 |  |  |  | 1.25 | 7945251 |  | 7547988.86 | M/S Yousuf Ali Sikder | 20/06/19 | 27/06/19 | 27/12/19 |  | 20% |  | 0%
17 |  |  |  | 0 | 24.56 | 0 | 0 | 0 | 74.4 | 128432749.62 | 5483047 | 128542385.991 | [6 empty] | 115190753 |  |  |  | -29928657.799
1 | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. | 506033006 | [6 empty] | 195850 |  | 195850 | Md. Masum Hossain Gazi LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 185240 | 100% | Final
2 | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km. | 506035070 | [6 empty] | 285121 |  | 285121 | Taslima LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 270738 | 100% | Final
3 | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km. | 506034095 | [6 empty] | 381065 |  | 381065 | Rajib Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 38100 | 9.998%
4 | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km. | 506035006 | [6 empty] | 300535 |  | 300535 | Md. Liton Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 279799 | 100% | Final
5 | BDRIDP/BAR/BAB/CCA-EW/04 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m. | 506034024 | [6 empty] | 354810 |  | 354810 | Md. Kabir Sikder LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 203192 | 57.27%
6 | BDRIDP/BAR/BAB/UN-EW/02 | Resectioning of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 | 2404.83 | [5 empty] | 290672 | 290672 | 290672 | Md. Habibur Rohman LCS No-1 | 16/06/16 | 20/06/16 | 20/10/16 |  | 100% | 290503 | 99.94%
6 |  |  |  | 2404.83 | 0 | 0 | 0 | 0 | 0 | 1808053 | 290672 | 1808053 | [6 empty] | 1267572 |  |  |  | 0
23 |  |  |  | 2404.83 | 24.56 | 0 | 0 | 0 | 74.4 | 130240802.62 | 5773719 | 130350438.991 | [6 empty] | 116458325 |  |  |  | -29928657.799
Upazila: Muladi
1 | BDRIDP/BAR/MUL/UZ-St/01 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m. | 506692004 | [5 empty] | 20 | 7798117 |  | 8772459.2 | M/S Misi Construction | 21/07/14 | 28/07/14 | 27/03/15 |  | 100% | 8713982 | 100% | Final |  | 58477.2
2 | BDRIDP/BAR/MUL/UZ-Rd/01 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m. | 506692004 |  | 3.45 |  |  |  |  | 24406349 |  | 20744407.41 | M/S Lutful Kobir | 13/08/14 | 20/08/14 | 20/05/15 |  | 100% | 20716273 | 100% | Final | 100% | 28134.41
3 | BDRIDP/BAR/MUL/CCA-Rd/01 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District. | 506695135 |  | 1 |  |  |  |  | 4172838 |  | 3545269 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 3539794 | 100% | Final | 100% | 5475
4 | BDRIDP/BAR/MUL/CCA-Rd/02 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District. | 506695127 |  | 0.585 |  |  |  |  | 2763145 |  | 2347546 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 2217470 | 100% | Final | 100% | 130076
5 | BDRIDP/BAR/MUL/CCA-St/02 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m. | 506694001 | [5 empty] | 12 | 2543802 |  | 1762404.98 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 1761528 | 99.95% | Final | 100% | 876.98
6 | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m | 506694060 | [5 empty] | 16 | 5115590 |  | 3683201.71 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 3680151 | 99.92% | Final | 60% | -1470229.974
7 | BDRIDP/BAR/MUL/CCA-Rd(R)/04 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m. | 506694001 |  | 2.175 |  |  |  |  | 8969284 | 1518637 | 7104572.13 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 100% | 6981690 | 100% | Final | 80% | -1298032.296
8 | BDRIDP/BAR/MUL/CCA-Rd/05 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m. | 506694060 |  | 1.575 |  |  |  |  | 5450114 |  | 4824539 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 100% | 4773001 | 100% | Final | 80% | -913369.8
9 | BDRIDP/BAR/MUL/CCA-Rd/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m. | 506694063 |  | 1.25 |  |  |  |  | 3310397 |  | 2947338.02 | Md Sirazul Islam Hanif | 18/05/15 | 25/05/15 | 25/05/16 |  | 100% | 2910009 | 100% | Final | 100% | 37329.02
10 | BDRIDP/BAR/MUL/CCA-St/01 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m | 506694063 | [5 empty] | 2 | 505514 |  | 368648.25 | M/S Sraboni Enterprise | 21/06/15 | 28/06/15 | 27/12/15 |  | 100% | 368633 | 100% | Final | 100% | 15.25
11 | BDRIDP/BAR/MUL/CCA-Rd/06 | Improvement of road from Char Kalekhan Goni Bari-Khalil Bepari Bari road by BC from Ch. 0.00m-1550m. | 56695075 |  | 1.55 |  |  |  |  | 8933193 |  | 7059418.41 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 100% | 7059417 | 100% | Final | 70% | -806181.9
12 | BDRIDP/BAR/MUL/CCA-St/04 | Construction of 1 vent 4.00m×4.00m and 1 vent 1.00m×1.00m RCC Box Culvert on Char Kalekhan Goni Bari-Khalil Bepari Bari road at Ch.182m & 330m. | 56695075 | [5 empty] | 5 | 1937445 |  | 1462533.11 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 100% | 1455972 | 99.55% | Final | 50% | -487249.5
13 | BDRIDP/BAR/MUL/CCA-St/05 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal. | 506694043 | [5 empty] | 12 | 10068184 | 10068184 | 7727638.21 | M/S Shafi Enterprise | 2017-06-02 | 13/02/17 | 13/12/17 |  | 100% | 7624583 | 100% | Final
14 | BDRIDP/BAR/MUL/UN-St/02 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District. | 506693005 | [5 empty] | 20 | 14312698.5 |  | 12881428.65 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 100% | 12877875 | 99.97% | Final
15 | BDRIDP/BAR/MUL/UZ-St/03 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District. | 506692004 | [5 empty] | 20 | 17924056.31 |  | 16131650.67 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 100% | 16105676 | 99.84% | Final
16 | BDRIDP/BAR/MUL/UN-St/01 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District. | 506693005 | [5 empty] | 21 | 15795569.51 |  | 14216012.55 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 100% | 14206186 | 99.93% | Final
17 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. | 506692002 | [5 empty] | 45 | 24434851.86 |  | 21991136.67 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 100% | 21990747 | 100% | Final
18 | BDRIDP/BAR/MUL/UZ-St/04 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal. | 506692004 | [5 empty] | 25 | 23503677 |  | 21153309.3 | Orien Trading & Builders | 2017-03-08 | 2017-10-08 | 2018-10-08 |  | 100% | 21146921 | 99.97%
19 | BDRIDP/BAR/MUL/UZ-St/05 | Construction of 30.00m PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at Ch.7620km over Banimardhan Khal under Muladi UpazilaDistrict-Barisal | 506692004 | [5 empty] | 30 | 21022197.08 |  | 18919977.37 | M/S Amir Engineering Corporation and M.M Builders & Engineers | 2018-04-02 | 2018-11-02 | 2018-11-12 |  | 100% | 18919123 | 100%
20 | BDRIDP/BAR/MUL/CCA-Rd/07 | Improvement of road from Muladi-Mirdar Hat GCCR Kazi Ali Ahmed Bari Grostan Alauddin Dewan Bari under Muladi UpazilaBarisal.a Bituminus Surfacing wearing courseDC 0.0m - 375mb 1 No.1.3m x 1.3m RCC Box Culvert at ch.170m | 506695137 |  | 0.375 |  |  |  | 1.3 | 2591153.77 |  | 2332038.39 | M/S Kohinoor Enterprise | 19/01/18 | 25/01/18 | 25/07/18 |  | 100% | 2242182 | 96.15%
21 | BDRIDP/BAR/MUL/UZ-Rd/02 | a Improvement of Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road from Ch.2150m - 4415m under Muladi Upazila Barisal District.b Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch.2800m.c Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch. 3900m. | 506692002 |  | 2.265 |  |  |  | 4 | 17170059.9 |  | 15453053.91 | Orien Trading & Builders | 2018-03-05 | 2018-10-05 | 2019-10-05 |  | 100% | 15100000 | 97.72%
22 | BDRIDP/BAR/MUL/CCA-Rd/09 | Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000m under Muladi Upazila Barisal District.Salvaged Cost Tk 591644.00Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000mID No.506694016 under Muladi Upazila Barisal District. | 506694016 |  | 1 |  |  |  |  | 5885104.61 |  | 5296594.14 | Orien Trading & Builders | 2018-03-05 | 2018-10-05 | 2019-10-02 |  | 100% | 4450000 | 84.02%
23 | BDRIDP/BAR/MUL/CCA-Rd/08 | Improvement of road from Batamara Paderhat Launch Ghat -Salimpur Bazar via Batamara Regd.Primary School via Aminul Haque Kabir Bari by BC at ch.200m - 1252m under Muladi Upazila Barisal. | 506695001 |  | 1.05 |  |  |  |  | 6000000 |  | 5400000 | Md. Mahafuz Khan | 2018-03-05 | 2018-10-05 | 2018-10-02 |  | 65% | 1200000 | 22.22%
24 | BDRIDP/BAR/MUL/CCA-Rd/10 | Improvement of road from Balarmpur Bazar-Dumurtala GPS-Char Dumuritala Bissas Bari Mosque UNRG by BC at Ch. 0.000km-1.000km. under muladi upazila Barisal District | 506694094 |  | 1 |  |  |  |  | 5702035.96 |  | 5416934.16 | M/S Ferdousi Construction | 2018-05-06 | 2018-12-06 | 2019-12-03 |  | 100% | 5000000 | 92.3%
25 | BDRIDP/BAR/MUL/CCA-Rd/11 | Improvement of road from Muladi-Bara Patarchar Ferry Ghat M by BC at Ch. 3.500km-4.065km. ID No.506694017 under muladi upazila Barisal District |  |  | 0.565 |  |  |  |  | 3338552.94 |  | 3171625.29 | M/S AK Buidlers | 2018-09-06 | 14/06/18 | 14/11/18 |  | 100% | 1500000 | 47.29%
26 | BDRIDP/BAR/MUL/CCA-Rd/12 | Improvement of road from Haraz Sikder Bari to Laxmipur Nutun hat via Rashid Dhali Bari by BC at Ch. 0.900km-2.400km under muladi upazila Barisal District.Salvaged cost Tk.888105.00 | 506695010 |  | 1.5 |  |  |  |  | 9147339.59 |  | 8689972.61 | M/S R.S Construction | 31/05/18 | 2018-07-06 | 2018-07-12 |  | 40% |  | 0%
27 | BDRIDP/ BAR/MUL/Ghat/01 | Construction of RCC Ghat at Muladi Bandar under Muladi UpazilaBarishal District. | [7 empty] | 3822927.39 |  | 3631781.02 | M/S ARB Construction | 2019-10-06 | 17/06/19 | 17/12/19 |  | 80% | 2800000 | 77.1%
28 | BDRIDP/BAR/MUL/CCA-St/06 | Construction of 23.00m RCC Girder Bridge on Madrasha Hat Start from Char kalekhan College gate to Charmalia Bepari Hat road at ch.3670m | 506694001 | [5 empty] | 23 | 16173766 |  | 14133678.509 | M/S. Lutful Kabir | 26/09/19 | 2019-03-10 | 2020-03-10 |  | 95% | 12310000 | 87.1%
29 | BDRIDP/BAR/MUL/CCA- Rd/13 | A Improvement of Kazir Char High School to Moddho Kazirchar Dakhil Madrasah. Salvaged Cost Tk 1848817a Earthwark Ch.1000m-2000m.b Carpeting BC Ch. 1000m-2000m. c Palsading 70m.B Improvement of Road by BC from Char Comissioner Colam Khan Bari-Muladi Boarder via Sadak Khan Khal K.a Earthwark Ch.500m-1150m.b Carpeting BC Ch.500m-1150m. c Construction of 01 No 1-Vent RCC Box Culvert 4.0mx4.0m at Ch.572m. d Palsading 45m | 506694082 506695052 |  | 1.65 |  |  |  | 4 | 14840130 |  | 13710063 | M/S S H Enterprise | 24/09/19 | 01/10/19 | 01/04/20 |  | 60% | 1050000 | 7.659%
30 | BDRIDP/BAR/MUL/UN- Rd/01 | A Improvement of Road by BC from Talukder Hat Khajurala to Safipur UP via Charkaiakhan UP-Beparirhat. Salvaged cost Tk 3421194.00a Earthwark Ch.11750m-13250m.b Carpeting BC Ch.11750m-13250m.B Improvement of Road by BC from Kazir Char UP to Ekaterhat UP to Muladi Border. Salvaged cost Tk 2190786.00a Earthwark Ch.00m-1000m.b Carpeting BC Ch.00m-1000m. c Palsading 70m | 506693001 506693004 |  | 2.5 |  |  |  |  | 18468196 |  | 16991019.04 | M/S S H Enterprise | 24/09/19 | 01/10/19 | 01/04/20 |  | 60% | 1300000 | 7.651%
31 | BDRIDP/BAR/MUL/CCA-Rd/14 | A Improvement of Road from Shah alam Sarif Bari- Jabbar Sikder Bari via Bhahadurpur H/S. K.a Earthwark Ch.00m-550m.b Carpeting BC Ch. 00m-550m. B Improvement of road from Padarhat to Delower Howlader Bari via Harun Dr. BariK.a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of 02 Nos Single-Vent 3.00mx3.00m RCC Box Culvert At Ch. 625m & 976m | 506695059 506695102 |  | 1.5 |  |  |  | 6 | 13519203 |  | 12345108 | M/S. Lutful Kabir | 21/12/19 | 28/12/19 | 28/06/20 |  | 60% | 2350000 | 19.04%
32 | BDRIDP/BAR/MUL/CCA-Rd/15 | A Improvement of Road from Padar Hat Esahak Howladers Bari.a Earthwark Ch. 500m-1500m.b Carpeting BC Ch. 500m-1500m.c Palsading 55m.B Improvement of Road from Char Comissioner R&H-Dholu Sikder Bari K a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Palsading 100m | 506694092 506695053 |  | 2 |  |  |  |  | 15288444 |  | 13727146.51 | M/S Esad & Emad Enterprise-M/S S S Construction (JV) | 19/12/19 | 25/12/19 | 25/11/20 |  | 40% | 2800000 | 20.4%
33 | BDRIDP/ BAR/MUL/ CCA-Rd/16 | Improvement of road from Jamaddar Bari to Akoter Hat via Bahadurpur H/S at Ch. 4488m - 5300m. Under Muladi Upazila Barishal District. | 506695025 |  | 0.812 |  |  |  |  | 6568814.38 |  | 6240373.661 | M/S. Mintu Enterprise | 26/04/20 | 2020-03-05 | 2020-03-09 |  | 50% | 1900000 | 30.45%
34 | BDRIDP/ BAR/MUL/ UZ-St/06 | Construction of 20m long RCC Girder Bridge on Mirda hat GC - Nazirpur GC via Madrashar hat Bangla Bazar road over Banimardhan Khal at Ch 10560m Under Muladi Upazila Barishal District | 506692004 | [5 empty] | 20 | 22750000 |  | 19141490.416 | M/S. Amir Engineering Corporation |  |  |  |  | 0% |  | 0%
34 |  | Sub Total: |  | 0 | 27.802 | 0 | 0 | 0 | 286.3 | 364232749.8 | 11586821 | 323324369.296 | [6 empty] | 231051213 |  |  |  | -3421248.21
1 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m. | 506692004 | 2490.25 | [5 empty] | 334778 |  | 334778 | Khorshed Khan LCS No-1 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 327963 | 100% | Final
2 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m. | 506692004 | 3042.25 | [5 empty] | 403489 |  | 403489 | Md. Alamgir Hossain LCS No-2 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 396479 | 100% | Final
3 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m. | 506692004 | 2886.92 | [5 empty] | 386512 |  | 386512 | Md. Baschu Sharder LCS No-3 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 384690 | 100% | Final
4 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m. | 506692004 | 2770 | [5 empty] | 371303 |  | 371303 | Abdus Salam Sharder LCS No-4 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 364872 | 100% | Final
5 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m. | 506692004 | 2775.75 | [5 empty] | 372013 |  | 372013 | Md. Bakiullah Sharder LCS No-5 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 367905 | 100% | Final
6 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m. | 506692004 | 2798.21 | [5 empty] | 374943 |  | 374943 | Md. Shalim LCS No-6 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 373728 | 99.68% | Final
7 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m. | 506692004 | 2793.69 | [5 empty] | 374353 |  | 374353 | Sukkur Ahmed Khan LCS No-7 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 370690 | 99.02%
8 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m. | 506692004 | 0.3 | [5 empty] | 396858 | 396858 | 396858 | Nazma LCS No-8 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 387880 | 97.74%
9 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m. | 506692004 | 2969.75 | [5 empty] | 397315 |  | 397315 | Most. Jasmin Akter LCS No-9 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 390259 | 98.22%
10 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m. | 506692004 | 3207.06 | [5 empty] | 428100 |  | 428100 | Rashida LCS No-10 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 417470 | 97.52%
11 | BDRIDP/BAR/MUL/CCA-EW/01 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District. | 506695135 | 2052.81 | [5 empty] | 221909 |  | 221909 | Md Fazlu Tafader LCS No-1 | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 221206 | 100% | Final
12 | BDRIDP/BAR/MUL/CCA-EW/02 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District. | 506695127 | 2219.05 | [5 empty] | 239879 |  | 239879 | Md Kabir Hossain LCS No-1 | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 239119 | 100% | Final
13 | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. | 506694063 | 2210.3 | [5 empty] | 323312 |  | 323312 | Fokrul Ahosan LCS No-1 | 31/05/15 | 31/05/15 | 30/09/15 |  | 100% | 32000 | 9.898%
14 | BDRIDP/BAR/MUL/CCA-EW/04 | Resectioning of road from Char Kalekhan Goni Bari-khalil Bepari bari road by Earth work from Ch. 0.00m-1550m. | 56695075 | 2237.625 | [5 empty] | 101268 | 101268 | 101268 | Md. Mojibor Rohman LCS No-1 | 28/07/15 | 30/08/15 | 30/12/15 |  | 100% | 97476 | 100% | Final
15 | BDRIDP/BAR/MUL/UN-EW/01 | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 2150m-2750m. | 506692002 | [6 empty] | 249672 | 249672 | 249672 | LCS No-1 |  |  |  |  | 100% | 242558 | 97.15% | Final
16 |  | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 2750m-3350m | [7 empty] | 284170 | 284170 | 284170 | LCS No-2 |  |  |  |  | 100% | 284170 | 100% | Final
17 |  | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 3350m-3950m | [7 empty] | 319301 | 319301 | 319301 | LCS No-3 |  |  |  |  | 100% | 269469 | 84.39%
18 |  | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 3950m-4412m | [7 empty] | 163854 | 163854 | 163854 | LCS No-4 |  |  |  |  | 100% | 160742 | 98.1% | Final
18 |  | Sub Total: |  | 34453.965 | 0 | 0 | 0 | 0 | 0 | 5743029 | 498126 | 5743029 | [6 empty] | 5328676 |  |  |  | 0
52 |  | Grand Total: |  | 34453.965 | 27.802 | 0 | 0 | 0 | 286.3 | 369975778.8 | 12084947 | 329067398.296 | [6 empty] | 236379889 |  |  |  | -3421248.21
Upazila: Hizla
1 | BDRIDP/BAR/HZL/UZ-Rd(R)/01 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m. | 506362009 |  | 1 |  |  |  |  | 7094634 | 1476772 | 5645230.7 | M/S Oshin Enterprise | 21/05/15 | 28/05/15 | 28/02/16 |  | 100% | 5645230 | 100% | Final | 40% | -3387137.72
2 | BDRIDP/BAR/HZL/CCA-Rd/01 | Improvement of Kowria- Moulavirhat UZR Poschim koralia road under Hizla Upazila District Barisal aEarth work from Ch.0.0 -900m b Dense Carpeting Ch.0.0 -900m c Two vent 4m x 4m RCC Box Culvert at Ch.252m | 506364033 |  | 0.9 |  |  |  | 8 | 8833997.83 |  | 7950598.407 | Md. Mahafuz Khan | 2018-04-04 | 2018-11-04 | 2019-01-02 |  | 40% |  | 0%
3 | BDRIDP/BAR/HZL/CCA-Rd/02 | Improvement of Hizla Muladi road to Motiar Dewan Bari via Sergent Dula Bari roadRHD via Surgeant Dulal- Kathal BeganUZR under Hizla Upazila Barisal District.ID No.506364003 Salvaged Cost Tk.2186650.00a Earth work Ch.0.0 - 1500mb Carpetting Ch. 0.0 - 1500mc Construction of 2 nos U-Drain on the same road at Ch.777m & 1275m |  |  | 1.5 |  |  |  | 1.8 | 10053464.17 |  | 9550790.96 | M/S R S Construction | 21/06/18 | 28/06/18 | 28/12/18 |  | 50% |  | 0%
4 | BDRIDP/BAR/HZL/Gha/01 | Construction of RCC Boat land Station at Abupur Ghat under Hizla Upazila Barisal | [7 empty] | 3254666.63 |  | 3146706.64 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 100% | 3119743 | 100%
5 | BDRIDP/BAR/HZL/CCA-Rd/03 | Improvement of Khunna Hospital RHD via Kawmi Madrasha - Baherchar UZR Barajalia Board GPS CS Connecting road a Earthwork from Ch.850 -1820m b Carpetting BC from Ch.850 -1820m under Hizla Upazila District Barishal Salvaged Cost TK 2343371.00 | 506365049 |  | 0.97 |  |  |  |  | 6797662.78 |  | 6457779.64 | M/S Munny Enterprise | 17/02/19 | 24/02/19 | 24/08/19 |  | 100% | 2600000 | 40.26%
6 | BDRIDP/BAR/HZL/CCA-Rd/04 | Improvement of road from Horinathpur Koshaipotti UZR - Zetighat GPS UZR ID No. a Earthwork from Ch.0.0 -1500m b Carpetting BC from Ch.0.0 -1500m under Hizla Upazila District Barishal Salvaged Cost TK 112128.00 | 506365056 |  | 1.5 |  |  |  |  | 9936759.78 |  | 9439921.79 | M/S Esad & Emad Enterprise | 29/01/19 | 2019-06-02 | 2019-06-07 |  | 100% | 9439349 | 99.99%
7 | BDRIDP/ BAR/HZL/ CCA-Rd/05 | Improvement of road from UZR -6 Mohishkhola Madrasha to VRA-15 Uttor Guabaria GPS via house of Abdul Gafur Sarder road by BC From Ch. 00m-1760.00m. Salvage Amount TK 296023.00 Under Hizla Upazila District- Barishal. | 506364034 |  | 1.76 |  |  |  |  | 12738507.36 |  | 12101581.992 | M/S. Nazrul Enterprise | 2019-04-04 | 2019-11-04 | 2019-11-10 |  | 70% | 4300000 | 35.53%
8 | BDRIDP/BAR/HZL/CCA-Rd/06 | Improvement of Kawria Bazar Danushikder hat road - Noroshingpur road Start Mollah Bari Shop Salvaged Cost Tk.309333.54 i Earth work Ch.0.0 - 760miiCarpeting DC Ch.0.0 - 760m under Hizla Upazila District Barishal. | 506365051 |  | 0.76 |  |  |  |  | 5255934.36 |  | 4993137.642 | M/S Jeon Trading & C0 | 2019-02-05 | 2019-09-05 | 2019-09-11 |  | 70% | 1600000 | 32.04%
9 | BDRIDP/BAR/HZL/UZ-St/01 | Dhunusikder Hat to Memania Taker Hat road via Abupur Kheyaghat i Construction of Diuble vent 2 x 4.50 x 6.50m RCC Box Culvert at Ch.2600mii Construction of Diuble vent 2 x 4.00 x 5.00m RCC Box Culvert at Ch.3380mUnder Hizla Upazila Barishal District. | 506362005 | [5 empty] | 17 | 5693472 |  | 5408798.4 | M/S Ladis Corner | 25/04/19 | 2019-02-05 | 2020-02-05 |  | 100% | 5406712 | 99.96%
10 | BDRIDP/ BAR/HZL/ CCA-Rd/07 | Improvement of Purbo Kandi WDB Embt. Salvaged Cost Tk 257546.00i Earthwark Ch.0.00m-900m. ii Carpeting DC Ch.0.00m-900m. iii Palsading 95m.Under Hizla Upazila Barishal District. | 506365003 |  | 0.9 |  |  |  |  | 6755327.72 |  | 6417561.33 | M/S Yousuf Ali Sikder | 20/06/19 | 27/06/19 | 27/12/19 |  | 60% | 2000000 | 31.16%
11 | BDRIDP/BAR/HZL/UZ- Rd/02 | Improvement of Dhanushikder hat-Muladi Upazila road. Salvaged Cost TK 1488901.00 a Earthwark Ch.1000m-2000m. b Carpeting BC Ch.1000m-2000m. c Palsading 97m. | 506362009 |  | 1 |  |  |  |  | 9936388.93 |  | 9439521.98 | M/S Kazi Popy Enterprise | 02/09/19 | 09/09/19 | 09/03/20 |  | 70% | 3800000 | 40.26%
12 | BDRIDP/ BAR/HZL/ CCA-Rd/08 | Improvement of Guabaria UP Office-Bhanderhat road Old Zila Parished road to Guabaria UP Office via Mofiz Uddin road at Ch. 1650m-2480m. Under Hizla Upazila Barishal District. Salvaged Cost TK 657763.00 | New ID No-506363004 Old ID No-506365092 |  | 0.83 |  |  |  |  | 7002119.66 |  | 6652013.677 | M/S. Layla Builders | 03/05/20 | 10/05/20 | 10/11/20 |  | 0% |  | 0%
13 | BDRIDP/ BAR/HZL/ CCA-St/01 | Construction of Single vent 4.30mx3.60m RCC Box Culvert at Barojalia Board GPS cum CS road at Ch.00m under Hizla Upazila Barishal District. | 506365049 | [6 empty] | 2310296.92 |  | 2194782.074 | M/S Ahana Enterprise | 12/08/20 | 18/08/20 | 18/12/20 |  | 0% |  | 0%
14 | BDRIDP/ BAR/HZL/ UZ/St/02 | Construction of 21.00m RCC Girder Bridge on Kawria - Memania Takerhat road at Ch.7800m under Hizla Upazila Barishal District | 506362003 | [6 empty] | 16915000 |  | 14242474.754 | M/S. Amir Engineering Corporation |  |  |  |  | 0% |  | 0%
14 |  |  |  | 0 | 11.12 | 0 | 0 | 0 | 26.8 | 112578232.14 | 1476772 | 103640899.986 | [6 empty] | 37911034 |  |  |  | -3387137.72
1 | BDRIDP/BAR/HZL/UZ-EW/01 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 0.00m-325m | 506362009 | [6 empty] | 226562 | 226562 | 226562 | Md. Humaun Kabir LCS No-1 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 225780 | 99.65%
2 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 325m-650m | [7 empty] | 220227 | 220227 | 220227 | Md. Monju Noli LCS No-2 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 218498 | 100%
3 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 650m-1000m | [7 empty] | 217087 | 217087 | 217087 | Md. Parvaz LCS No-3 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 214482 | 100%
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 663876 | 663876 | 663876 | [6 empty] | 658760
17 |  |  |  | 0 | 11.12 | 0 | 0 | 0 | 26.8 | 113242108.14 | 2140648 | 104304775.986 | [6 empty] | 38569794
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/UZR(R)-Rd/01 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal. | 506622005 |  | 1.11 |  |  |  |  | 5853739 |  | 4973018 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 4973018 | 100% | Final | 60% | -1989207.2
2 | BDRIDP/BAR/MHN/CCA-Rd/01 | Improvement of Mothertoli Bazar - Uttarchar road via Charekkaria road by BC (Ch.2170-3220m, Road Under Mehendigonj Upazila, District-Barisal. | 506625079 |  | 1.05 |  |  |  |  | 5327472 |  | 4515030 | M/S Nahid Enterprise | 16/11/14 | 23/11/14 | 23/04/15 |  | 100% | 4514924 | 100% | Final | 60% | -1805906
3 | BDRIDP/BAR/MHN/CCA-St/01 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal. | 506625079 | [5 empty] | 1 | 222783 |  | 184788 | M/S Hasib Enterprise | 2014-09-11 | 16/11/14 | 15/03/15 |  | 100% | 167876 | 100% | Final
4 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 506624016 |  | 1.61 |  |  |  |  | 6864308 | 6864308 | 6860287.95 | M/S Hasan Construction | 2017-12-01 | 19/01/17 | 19/09/17 |  | 55% | 3625000 | 52.84%
5 | BDRIDP/BAR/MHN/UZ-Rd/02 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila,Barisal. | 506622007 |  | 3 |  |  |  |  | 10545370 |  | 10492643.13 | M/S Lutful Kabir | 2017-07-05 | 14/05/17 | 14/02/18 |  | 100% | 9400000 | 89.59%
6 | BDRIDP/BAR/MHN/CCA-Rd/03 | Improvement of Road from Posshim Yearbeg Dadpur GPS under Mehendiganj Upazila District Barisal aEarthwork Ch.1000 2760m b HBB Ch.1000 -2760m | 506625062 |  |  | 1 |  |  |  | 5960375.56 |  | 5661508 | M/S Amir Engineering Corporation | 28/03/18 | 2018-05-04 | 2019-05-01 |  | 100% | 5566643 | 98.32%
7 | BDRIDP/BAR/MHN/GC/01 | Constructionof Langutia G C (i) Fish Shed (Size : 12m x 6m) (ii) 2 Nos Waste collection Pit (Dustbin) (Size : 1.4m x 1.4m) (iii) Multipurpose Shed (Size : 12m x 6m) (iv) Logistic Support for Langutia Bazar (v) Toilet Block (Size : 5.75m x 3.07m) (vi) 2 Nos Deep Hand Tube well (vii) CC road without side drain : 100m (viii) RCC Ghat at Langutia Bazar Under Mehendigonj, Barishal District | [7 empty] | 4989791 |  | 4740301.45 | M/S Oshin Enterprise | 2019-04-01 | 2019-11-01 | 2019-04-07 |  | 55% | 2124820 | 44.82%
8 | BDRIDP/BAR/MHN/UN-Rd/01 | Improvement of road from Chanpur UP Saduaghata - Kazir Hat Bazar via Muktijodda H/S Salvage Amount Tk. 1000267.00 Road i Earth Work Ch. 00m-1300m ii Carpeting BC Ch. 00m-1300m iii Construction of 01 No 0.625mx0.600m U-Drain at Ch.1234m iv Palisading 27m. Under Mehendiganj Upazila District- Barishal. | 506623016 |  | 1.3 |  |  |  | 0.625 | 9582341.77 |  | 9103224.68 | M/S Refat Enterprise | 21/07/19 | 28/07/19 | 28/01/20 |  | 50% | 2900000 | 31.86%
9 | BDRIDP/BAR/MHN/CCA-Rd/04 | Part - A Improvement of road by BC from Paterhat RC College - Charerhat Via Sadekpur Madrasha at Ch. 700m-1700m. Salvage Amount Tk. 1248231.00 i Earth Work Ch. 700m-1700m. ii Carpeting BC Ch.700m-1700m. iii Construction of 01 No 0.625mx0.600m U-Drain at Ch.1686m Under Mehendiganj Upazila District- Barishal. Part- B Improvement of road from Nasirkha Khayaghat - Hashamuddi Bazar i Earth Work Ch. 00m-1000m. ii Carpeting BC Ch. 00m-1000m Under Mehendiganj Upazila District- Barishal. Part - C Improvement of road from Rowshanara Dhakil Madrasha H/O Hasem Molla Via H/O Dolil Uddin Bepari. Salvage Amount Tk. 199562.00 i Earth Work Ch. 00m-900m. ii Carpeting DC Ch. 00m-900m | 506625130 506625140 506625236 |  | 2.9 |  |  |  | 0.6 | 20719155.66 |  | 20716818.21 | M/S Amir Engineering Corporation | 17/09/19 | 24/09/19 | 24/03/20 |  | 50% | 3000000 | 14.48%
10 | BDRIDP/ BAR/MHN/ UN-Rd/02 | Improvement of road by BC on Chargopalpur UP-Jalirchar Bazar Maskata River. Under Mehendigonj Upazila Barishal District. Salvaged Cost Tk.1116804.00 a Earthwark Ch. 3300m-4600m.b Carpeting BC Ch. 3300m-4600m. | 506623014 |  | 1.3 |  |  |  |  | 9188736.41 |  | 8729299.59 | M/S. Raisha Construction | 20/04/20 | 27/04/20 | 27/10/20 |  | 0% |  | 0%
11 | BDRIDP/ BAR/MHN/ CCA-Rd/05 | Improvement of road by BC from H/O. Malek Mia Durgapur S/O. Azom Mia GCCR road via Varanirpul to Ramizuddin High School. Under Mehendigonj Upazila Barishal District. a Earthwark Ch. 00m-1050m.b Carpeting BC Ch. 00m-1050m. c 2Nos U-Drain 0.625m x 0.600m at Ch.172m 750m | 506625110 |  | 1.05 |  |  |  | 1.2 | 7922183.69 |  | 7526074.506 | M/S. Howlader Construction | 13/05/20 | 20/05/20 | 20/11/20 |  | 0% |  | 0%
12 | BDRIDP/ BAR/MHN/CCA-St/02 | Construction of 20m RCC Bridge on Patherhat GC Road Khejor Toli Bridge at Ch.1961m under Mehendigonj Upazila Barishal District. | 506622001 | [5 empty] | 20 | 15380000 |  | 12983216.656 | M/S. Shahil Enterprise | 17/05/20 | 24/05/20 | 24/12/20 |  | 0% |  | 0%
13 | BDRIDP/ BAR/MHN/ UZ/St/01 | Construction of 20.00m RCC Girder Bridge on Ulania GC - Aligonj GC road at Ch.1700m. ID No-506622007 under Mehendigonj Upazila Barishal District | [6 empty] | 20 | 12870183.12 |  | 12226673.964 | DESHI TRAVELS & CO | 09/08/20 | 16/08/20 | 16/01/21 |  | 0% |  | 0%
14 | BDRIDP/ BAR/MHN/ CCA-St/03 | Construction of 25.00m RCC Girder Bridge at College-Maskata River West side of Alimabed 7 No Word Saed Doctor Bari Khal. at Ch. 13m.ID No-506625121 under Mehendigonj Upazila Barishal District | [6 empty] | 25 | 16321000 |  | 13592624.77 | [5 empty] | 0% |  |  | E-Tender under Process.
15 | BDRIDP/ BAR/MHN/ UZ-St/02 | Construction of 30.00m PSC Girder Bridge on Ulania GC-Aligonj GC road at Ch. 1000m.ID No-506622007 under Mehendigonj upazila Barishal District | [6 empty] | 30 | 22063000 |  | 19194810 | [5 empty] | 0% |  |  | E-Tender under Process.
15 |  |  |  | 0 | 13.32 | 1 | 0 | 0 | 98.425 | 153810439.21 | 6864308 | 141500318.906 | [6 empty] | 36272281 |  |  |  | -3795113.2
1 | BDRIDP/BAR/MHN/CCA-EW/01 | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 0.00m-600m by Earth. | 506624016 | [6 empty] | 346489 | 346489 | 346489 | Nizam Uddin Talukder LCS No-1 | 2016-06-12 | 18/12/16 | 18/03/17 |  | 100% | 345129 | 99.61%
2 |  | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 600m-1200m by Earth. | [7 empty] | 421652 | 421652 | 421652 | Md. Sadak LCS No-2 | 2016-06-12 | 18/12/16 | 18/03/17 |  | 100% | 419139 | 99.4%
3 |  | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 1200m-1610m by Earth. | [7 empty] | 258058 | 258058 | 258058 | Md. Faruk Buiya LCS No-3 | 2016-06-12 | 18/12/16 | 18/03/17 |  | 100% | 256220 | 99.29%
4 | BDRIDP/BAR/MHN/UZ-EW/01 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1000m-1600m | 506622007 | [6 empty] | 164958 | 164958 | 164958 | LCS No-1 |  |  |  |  | 100% | 159113 | 96.46%
5 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1600m-2350m | [7 empty] | 379812 | 379812 | 379812 | LCS No-2 |  |  |  |  | 100% | 379497 | 99.92%
6 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 2350m-3250m | [7 empty] | 297385 | 297385 | 297385 | LCS No-3 |  |  |  |  | 100% | 290652 | 97.74%
7 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 3250m-4000m | [7 empty] | 254707 | 254707 | 254707 | LCS No-4 |  |  |  |  | 100% | 249233 | 97.85%
7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2123061 | 2123061 | 2123061 | [6 empty] | 2098983
22 |  |  |  | 0 | 13.32 | 1 | 0 | 0 | 98.425 | 155933500.21 | 8987369 | 143623379.906 | [6 empty] | 38371264
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/CCA-Rd/01 | Improvement of Bukhainagar Bridge to Abdul Aziz Khan's House via Shaluka GPS Road (Ch. 00-500m). | 506514170 |  | 0.5 |  |  |  |  | 2045654 |  | 1613223.41 | M/S Talukder Enterprise | 2014-09-06 | 16/06/14 | 16/09/14 |  | 100% | 1607918 | 99.67% | Final
2 | BDRIDP/BAR/SDR/CCA-Rd/02 | Improvement of Chandpura Mojidderhat-Saheberhat via Khontakhali School road from Ch. 1635-3192m. | 506514154 |  | 1.557 |  |  |  |  | 7466730 |  | 6279530.87 | M/S G M Construction | 2014-10-08 | 17/08/14 | 16/05/15 |  | 100% | 6266613 | 100% | Final
3 | BDRIDP/BAR/SDR/CCA-Rd/03 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m | 506514148 |  | 0.513 |  |  |  |  | 2809559 |  | 2294335.91 | M/S Serajul Islam Hanif | 24/07/14 | 2014-01-08 | 2015-01-02 |  | 100% | 1954150 | 100% | Final | 100% | 340185.91
4 | BDRIDP/BAR/SDR/CCA-Rd/04 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 |  | 0.732 |  |  |  |  | 2900881 | 1230068 | 2238782.5 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 100% | 2179525 | 100% | Final
5 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 100% | 8800000 | 87.23% |  |  | 10088368.67
6 | BDRIDP/BAR/SDR/CCA-Rd/04 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366m. | 506515102 |  | 1 |  |  |  | 1.6 | 4543594 |  | 4037481 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2016-11-04 |  | 100% | 3913837 | 100% | Final | 50% | -1895096.5
7 | BDRIDP/BAR/SDR/CCA-St/04 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m. | 506514048 | [5 empty] | 8 | 1333966 |  | 1027297.63 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 100% | 1027297 | 100% | Final
8 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 506514048 |  | 2.782 |  |  |  |  | 10910419 | 207108 | 8773072.65 | M/S Hasan Construction | 2015-10-05 | 17/05/15 | 17/02/16 |  | 100% | 5512074 | 100% | Cancelled | 70% | 629076.855
9 | BDRIDP/BAR/SDR/CCA-St/02 | Construction of 1.0 x 1.0m and 1.6 x1.6m RCC Box culvert on Kasem Defader Bari - Karnokati High School & College road at ch.773m & 526m e-ID: 17457 | 506514176 | [5 empty] | 1.6 | 516289 |  | 428108.82 | M/S Khondokar Borthers | 15/06/15 | 23/06/15 | 22/12/15 |  | 100% | 425862 | 100% | Final
10 | BDRIDP/BAR/SDR/CCA-Rd(R)/06 | Rehabilitation of road from Kasem Defader Bari - Karnokati High School & College road By BC from ch.310 - 1125m under Sadar upazila ,Barisal District [Salvaged Cost-Tk 4,97,038.00] | 506514176 |  | 0.815 |  |  |  |  | 3385819 |  | 3216111 | M/S Oshin Enterprise | 2015-11-05 | 18/05/15 | 18/02/16 |  | 100% | 3216111 | 100% | Final
11 | BDRIDP/BAR/SDR/CCA-Rd/07 | Improvement of road from Charkawa Nayani - Shaberhat via Durgapur hat (Barisal Sadar Upazila 7no. Charkawa union 1no.word nurul islam to Bank Jalal Bari Pull) road By HBB from Ch.0.0 - 1000m under Barisal-S Upazila,Barisal District. e-ID : 29367 | 506514136 |  |  | 1 |  |  |  | 2430847 |  | 2063060.77 | M/S Apu Enterprise | 2015-03-11 | 2015-10-11 | 2016-10-05 |  | 100% | 2063045 | 100% | Final
12 | BDRIDP/BAR/SDR/CCA-Rd/09 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari. | 506515006 |  | 1.6 |  |  |  | 1.6 | 12590432 | 937125 | 10801668.14 | M/S Khondokear Enterprise | 30/06/16 | 30/06/16 | 26/06/17 |  | 100% | 9822562 | 90.94% |  | 285845
13 | BDRIDP/BAR/SDR/CCA-Rd/10 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila,Barisal. | 506514137 |  | 1.544 |  |  |  | 4 | 9500469 |  | 8550422.1 | M/S Sirajul Alam Sikder | 22/05/17 | 29/05/17 | 29/02/18 |  | 100% | 8530424 | 99.77%
14 | BDRIDP/BAR/SDR/UN-Rd/01 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road. | 506513003 |  | 2.76 |  |  |  | 8.8 | 18760504 |  | 16884454 | Md Mafuz Khan | 18/01/18 |  | 31/11/18 |  | 30% | 2400000 | 14.21%
15 | BDRIDP/BAR/SDR/UZ-Rd/01 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal. | 506512003 |  | 0.579 |  |  |  |  | 4209569.27 |  | 3788612.34 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 100% | 1700000 | 44.87%
16 | BDRIDP/BAR/SDR/UN-Rd/02 | Improvement of Charkawa Kheyaghat - Durgapur hat road from Ch. 3000m - 3600m.under Sadar Upazila Barisal District. | 506513004 |  | 0.6 |  |  |  |  | 3464647.09 |  | 3118182.38 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 100% | 3117413 | 99.98%
17 | BDRIDP/BAR/SDR/CCA-Rd(R)/11 | Improvement of road from Charmonai Talukder Bari-West Razarchar Club by BC. at Ch. 0.00m-1203.00m under Charmonai Union, Upazila : Sadar, Dist-Barisal [Salvaged cost- Tk 231155.00] | 506515109 |  | 1.203 |  |  |  |  | 8769166.6 |  | 7892249.94 | M/S Kohinoor Enterprise | 18/01/18 | 25/01/18 | 25/11/18 |  | 40% | 1200000 | 15.2%
18 | BDRIDP/BAR/SDR/CCA-RdR/12 | Improvement of road Shibpasha - Sholna Talukder bari via H/O Malek Police at ch.1600km - 2020km under Sadar Upazila Barisal. | 506515006 |  | 0.42 |  |  |  |  | 2720015.56 |  | 2448014.04 | M/S Kohinoor Enterprise | 2018-04-02 | 2018-11-02 | 2018-11-08 |  | 100% | 1538816 | 62.86% | Final
19 | BDRIDP/BAR/SDR/Gha/01 | Construction of Ghat & CC Road at Shaheber Bazar under Sadar Upazila Barisal . | [7 empty] | 3278780.89 |  | 3102813.825 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 100% | 3088988 | 99.55%
20 | BDRIDP/BAR/SDR/CCA-Rd/13 | Improvement of Shibpasha Sarder bari Sholna Tarunclub Road Road Part-A Earth work at Ch. 0.00 -1505.00m Part-B Carpeting BC work at Ch. 0.00-1505.00m Salvage Amount Tk. 2626839.00 Part-C Construction of 2Nos U-Drain 1.00mx1.00m at Ch. 140m & 380m Under Barisal Sadar Upazila District - Barisal. | 506514007 |  | 1.505 |  |  |  | 2 | 10603941.33 |  | 10073944.25 | M/S Noor & Sons | 2018-11-06 | 18/06/18 | 18/05/19 |  | 100% | 7106651 | 70.54%
21 | BDRIDP/BAR/SDR/CCA-RdR/14 | Improvement of Shibpasha Sarder bari-Sholna Tarunclub road a Earth work at Ch.1505-2392m b Carpetting BC Ch.1505 -2392m c Construction of 1 No Double vent Box culvert 4.0m x 4.0m at ch.1901m d Protective worksPalisading 134m e Link Road Baitul Mamur Jame Mosque 167.00m under Bakergonj Upazila Barishal District.Salvaged Cost TK 1935498.00 | 506514007 |  | 1.054 |  |  |  | 8 | 10111914.02 |  | 9606318.31 | M/S H R Enterprise | 20/02/19 | 27/02/19 | 27/08/19 |  | 40% | 2100000 | 21.86%
22 | BDRIDP/BAR/SDR/CCA-RdR/05REM | Remaining work for rehabilitation of road from Patang- Jaliabari Pool via Mujaffar Hazi Bari road.From Ch.0.0m -2782m | 506514048 |  | 2.782 |  |  |  |  | 4894164.58 |  | 4649456.351 | M/S Md Yousuf Ali Sikder | 21/07/19 | 28/07/19 | 28/01/20 |  | 100% | 4642776 | 99.86%
23 | BDRIDP/ BAR/SDR/ CCA-Rd/15 | Improvement of Read from Borthan Khan Bari-Dr. Omar bari-Gogan Ali Howladar Bari to Godanga Chandpura UP Hijaltala Baran Khan Bari-Sanjib Daser Bari-Eunus Munshi Bari. a Earthwark Ch.00m-1060m.b Carpeting DC Ch.00m-1060m. c Construction of 02 Nos U-Drain 1.0mx1.0m at Ch.107.00m & 180.00m. d Palsading 350m | 506515174 |  | 1.06 |  |  |  | 2 | 8603655 |  | 8173473.08 | M/S Alif Enterprise |  |  |  |  | 50% | 1900000 | 23.25%
24 | BDRIDP/BAR/SDR/CCA-Rd/16 | Improvement of Road from Char Aicha Mollar Hat Kheya Ghat to Board School via Jokkhali. a Earthwark Ch.00m-530m.b Carpeting BC Ch. 00m-530m. c Palsading 93m | 506514145 |  | 0.53 |  |  |  |  | 4245799 |  | 4033509.81 | M/S Khan Construction | 23/01/20 | 30/01/2020 | 30/07/2020 |  | 0% | 0 | 0%
25 | BDRIDP/BAR/SDR/UN-Rd/03 | Improvement of Jagua Union Parishad-Karapur Steel Bridge-Bousherhat GC.a Earthwark Ch. 4905m-6765m.b Carpeting BC Ch. 4905m-6765m.. c Construction of U-Drain 1.00mx1.00m At Ch. 5645m & 1.60x1.60m RCC Box Culvert at Ch.6583md Palsading 42m. | 506513012 |  | 1.86 |  |  |  | 2.6 | 13430037 |  | 12265012.42 | M/S Esad & Emad Enterprise-M/S S S Construction (JV) | 19/12/19 | 25/12/19 | 25/11/20 |  | 30% | 2200000 | 17.94%
26 | BDRIDP/ BAR/SDR/ CCA-Rd/17 | A Improvement of Patang-Shaheber Hat road. Under Sadar Upazila Barishal District. Salvaged Cost. Tk 1937174.00a Earthwark Ch. 00m-1200m.b Carpeting BC Ch. 00m-1200m.B Rehabilitaton work of Patang-Nehalgonj Under Sadar Upazila Barishal District.a Earthwark Ch. 00m-1816m.b Carpeting BC Ch. 00m-1816m.c Palsading 12m. C Jagua Sher-E Bangla Hat-Jashim Uddin Talukder House Under Sadar Upazila Barishal District. a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m. | 506514030 506514031 506514118 |  | 4.016 |  |  |  |  | 23791100 |  | 22115845.663 | M/S. S.S. CONSTRUCTION- M/S Esad & Emad Enterprise(jv) | 2020-11-05 | 18/05/20 | 18/11/20 |  | 10% | 1200000 | 5.426%
26 |  | Sub-Total: |  | 0 | 29.412 | 1 | 0 | 0 | 60.2 | 190090807.34 | 2374301 | 169563349.879 | [6 empty] | 87514062 |  |  |  | 9162534.935
1 | BDRIDP/BAR/SDR/CCA-EW/01 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 | 2126.54 | [5 empty] | 238242 |  | 238242 | Md. Giush Uddin LCS No-1 | 29/01/15 | 15/02/15 | 30/04/15 |  | 100% | 190934 | 100% | Final
2 | BDRIDP/BAR/SDR/CCA-EW/02 | Resectioning of road from Charkawa Nayami-Shaheber hat via Durgapur hat (Barisal Sadar Upzila 7no. Charkawa union 1no word nurul islam to Bank Jalal Bari Pull) road from Ch. 0.00m-1000m. | 506514136 | 1311.25 | [5 empty] | 155407 | 155407 | 155407 | Md. Anowar Hossain Mridha LCS No-1 | 16/04/15 | 16/04/15 | 16/05/15 |  | 100% | 100881 | 64.91%
3 | [9 empty] | 228280 | 228280 | 228280 | Md. Jasim Uddin Milon LCS No-2 | 16/04/15 | 16/04/15 | 16/05/15 |  | 100% | 132596 | 58.08%
4 | BDRIDP/BAR/SDR/CCA-EW/03 | Resectioning of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge). | 506515006 | 3309.7 | [5 empty] | 400044 |  | 400044 | Fatema Begum LCS No-1 | 25/02/16 | 29/02/16 | 30/04/16 |  | 100% | 362610 | 90.64%
5 | BDRIDP/BAR/SDR/CCA-EW/04 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 2557m-3280m. | [7 empty] | 305905 | 305905 | 305905 | Md. Hemayet Howlader LCS No-1 | 16/03/17 | 28/03/17 | 30/04/17 |  | 100% | 30000 | 9.807%
6 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 3280m-4580m | [7 empty] | 256209 | 256209 | 256209 | Md. Mojibor Rohman Sikder LCS No-2 | 16/03/17 | 28/03/17 | 30/04/17 |  | 100% | 117852 | 46%
7 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 4580m-6647m | [7 empty] | 189642 | 189642 | 189642 | Mosharof Hossain Shikder LCS No-3 | 16/03/17 | 28/03/17 | 30/04/17 |  | 100% | 172057 | 100%
8 | BDRIDP/BAR/SDR/UN-EW/01 | Resectioning of Road from Gilatali Kheyaghat-Biswasherhat via Model Madrasha at Ch. 1500m-2700m | [7 empty] | 438144 |  | 438144 | LCS No-1 |  |  |  |  | 100% | 410512 | 100% | Final
9 |  | Resectioning of Road from Gilatali Kheyaghat-Biswasherhat via Model Madrasha at Ch. 2700m-4260m | [7 empty] | 426063 |  | 426063 | LCS No-2 |  |  |  |  | 100% | 325495 | 100% | Final
10 | BDRIDP/BAR/SDW/UZ-Ew/01 | Resectioning of Shehaber Hat-Singherkati Chandramohon Road at Ch. 729m-1009m | 506512003 | [6 empty] | 255149 |  | 255149 | LCS No-1 |  |  |  |  | 100% | 250500 | 100% | Final
11 |  | Resectioning of Shehaber Hat-Singherkati Chandramohon Road at Ch. 1009m-1309m | [7 empty] | 355749 |  | 355749 | LCS No-2 |  |  |  |  | 100% | 350500 | 100% | Final
12 | BDRIDP/BAR/SDR/UZ-Tree/01 | Sheheber Hat-Singerkathi to Chandromohan Road Ch. 0.00-600m, 1000-1500m, 1600-2000m & 2500-3000m under Sadar Upazila, District: Barisal. | 506512003 | [6 empty] | 266000 |  | 266000 | LCS |  |  |  |  | 71% | 187600 | 70.53%
13 | BDRIDP/BAR/SDR/UN-Tree/01 | Gilatoli Kheyaghat-Biswasher Hat via Model Madrasha Road Ch. 0.00-500m, 1000m-1500m, 2000-2500m under Sadar Upazila, District: Barisal. | 506513003 | [6 empty] | 236000 |  | 236000 | LCS |  |  |  |  | 92% | 217600 | 92.2%
13 |  | Sub-Total: |  | 6747.49 | 0 | 0 | 0 | 0 | 0 | 3750834 | 1135443 | 3750834 | [6 empty] | 2849137 |  |  |  | 0
39 |  | Grand Total: |  | 6747.49 | 29.412 | 1 | 0 | 0 | 60.2 | 193841641.34 | 3509744 | 173314183.879 | [6 empty] | 90363199 |  |  |  | 9162534.935
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/CCA-Rd/01 | Improvement of road from South side Dhola Sluice Gate to Alim Meridha Bari (Vary) via Sikder Bari, Manik Member Bari, Shatghor & Mannan Princhpal Bari (East side of Hanua Bridge to Shatghor via Shikder Bari) By HBB from Ch. 0.00-1013m. | 506075221 |  |  | 1.013 |  |  |  | 3558576 |  | 3985608.82 | M/S Nahid Enterprise | 17/07/14 | 24/07/14 | 24/01/15 |  | 100% | 3976779 | 99.78% | Final | 100% | 8829.82
2 | BDRIDP/BAR/BAK/UN-St/01 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 | 506073023 | [5 empty] | 27.2 | 7339681 |  | 5345279.54 | M/S Khondokear Brothers | 14/06/15 | 21/06/15 | 20/06/16 |  | 100% | 5098903 | 100% | Final
3 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 | 506073023 |  | 1 |  |  |  |  | 4566907 |  | 3523866.83 | M/S Khondokear Brothers | 21/07/15 | 28/07/15 | 27/04/16 |  | 75% | 1150000 | 32.63% | Prepared for Cancelled
4 | BDRIDP/BAR/BAK/UN-Rd(R)/02 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 1000m-4870m. e-ID : 22667 | 506073023 |  | 3.87 |  |  |  |  | 18093128 |  | 14682769.7 | M/S Khondokear Brothers | 14/06/15 | 2015-06-08 | 2016-06-05 |  | 100% | 14478871 | 100% | Final
5 | BDRIDP/BAR/BAK/CCA-Rd(R)/02 | Rehabilitation of road from Gavikola Mannan Sikder Bari Foot Bridge to West side of Nilganj Foot Bridge via Moksad Khan,Kumarghudi & Kaptain Saye Bari by BC from Ch.00-810m [Salvaged Value Tk.10,53,654.00] e-ID : 29366 | 506075079 |  | 0.81 |  |  |  |  | 3553958 |  | 2619513.44 | Md. Nasir Uddin | 2015-05-11 | 2015-12-11 | 2016-11-05 |  | 100% | 2549020 | 100% | Final
6 | BDRIDP/BAR/BAK/CCA-Rd/03 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal. | 506074120 | [6 empty] | 17641663 |  | 16139041.07 | Md. Sumsudhoa Mollick | 21/12/16 | 28/12/16 | 27/06/17 |  | 100% | 13912533 | 100% | Final
7 | BDRIDP/BAR/BAK/UN-Rd/03 | Improvement of road from Faridpur Hat Kheya Ghat Durgapasa UP office Gobindapur Bothtala via Kakordha Bazar Road, a Earth Work from Ch. 4860m 7320m.b Bituminus Carpeting from Ch. 4860m 7470m.c Construction of 1 No. 1.60mx1.60m RCC Box Culvert at Ch. 7435m. under Bakergonj upazila Barisal District. Salvage Cost Tk. 3733841.00 | 506073020 |  | 2.46 | 2.61 |  |  | 1.6 | 16459779.83 |  | 14813801.84 | Md Mafuz Khan | 2018-04-01 |  | 30/11/18 |  | 100% | 14808294 | 99.96% | Final
8 | BDRIDP/BAR/BAK/CCA-Rd/04 | Improvement of road from west Faridpur Ajgor Sikder Bari to DC road Ferry-ghat via H/O Rahim Mrida Road, a Earth Work from Ch. 0.0 - 1300.00m. b Bituminus Carpeting from Ch. 0.0 - 1300m c Construction of 1 No. 4.0m x 4.0m RCC Box Culvert at Ch. 425m. under Bakergonj upazila Barisal District. | 506074151 |  | 1.3 | 1.3 |  |  | 4 | 9994097.44 |  | 8994687.7 | M/S Islam Brothers | 2018-02-01 | 2018-09-01 | 2018-09-10 |  | 100% | 8941520 | 99.41%
9 | BDRIDP/BAR/BAK/CCA-Rd/06 | Improvement of road from Shashi Bazar Bridge-Telani Lunch Ghat Najrul Talukder Bari. under Bakergonj Upazila Dist:Barisal. a) HBB from Ch. 00m-1000m b) Protection Work 108m c) Earth work from Ch. 00m-1000m | 506074100 |  |  | 1 |  |  |  | 4609416.97 |  | 4563267.91 | Md. Zakir Hossain Mia | 17/01/18 | 24/01/18 | 24/07/18 |  | 100% | 4548499 | 99.68%
10 | BDRIDP/BAR/BAK/CCA-Rd(R)/05 | Improvement of road from ATIMKHANA to Bothra Road via Mr. Matiur Rahman (ASP) at Ch. 0.00m-500.00m (Efective Length= 475.00m) (ID No.506074225) under Bakergonj Upazila, Dist : Barisal [Salvaged cost : Tk1049647.00] |  |  | 0.5 |  |  |  |  | 3304868 |  | 2974381.2 | M/S Osin Enterprise | 17/01/18 | 24/01/18 | 24/05/18 |  | 100% | 2967278 | 99.76%
11 | BDRIDP/BAR/BAK/CCA-Rd/07 | Improvement of road from Sampur Ray Barir Culvert to Birangal Digirpar Kader Hohlade Bari via Karim Gaji Bari a Earth work 0.0 - 1500m b Bituminous Surfacing - wearing course DC 0.0m - 1500m c 1.5 m x 1.5m RCC Box Culvert at Ch.900m | 506075125 |  | 1.5 |  |  |  | 1.5 | 9125908.56 |  | 8213317.7 | M/S Abul Kalam Azad | 22/01/18 | 29/01/18 | 29/10/18 |  | 100% | 6850000 | 83.4%
12 | BDRIDP/BAR/BAK/CCA-Rd/08 | Improvement of Extended Portion of Dudhalmou Ferryghat (RHD) to Kanki Govt. Pry. School Road (Connecting Road Sheikh Hasina Cantonment). | 506074120 | [6 empty] | 4332834.63 |  | 2878392 | M/S Amir Engineering Corporation | 18/01/18 | 20/01/18 | 15/02/18 |  | 100% | 2878392 | 100% | Final
13 | BDRIDP/BAR/BAK/CCA-Rd/09 | Improvement of Aulia DargabariRHD to Shyampur Hat via Dhokati Madrasha & Dhokati Govt.Pry.school Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini to Syampur Hat via Ali Khan Bari a Earth work at Ch.4500-6000m b Carpeting BC at Ch.4500 - 6000m c Construction of 1No. Box culvert1.06m x 1.06m at Ch.85m & 3 nos U-Drain 900mm x 900mm at Ch.4620m4800m & 5135m on the same road d Protective worksSite Facilities& Road Safety works under Bakergonj Upazila Barishal District. Salvaged cost Tk 854269.00 | 506074119 |  | 1.5 |  |  |  | 3.76 | 14791503 |  | 13742664.31 | Md. Nasir Uddin | 26/08/18 | 2018-02-09 | 2019-02-08 |  | 100% | 13739681 | 99.98%
14 | BDRIDP/BAR/BAK/UZ-Rd/01 | Improvement of Rahamgonj RHD via Dhokati GPS & Bakergonj-Sampur Road to BoaliaGC Bakergonj-Sampur Road Mill Ghar to Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini a Earth work at Ch.1913-2775mb CarpetingBC at Ch.1913-2775mc Construction of 1No. Box culvert1.06m x 1.06m at Ch.2549m on the same roadd Protective worksSite Facilities& Road Safety works under Bakergonj UpazilaBarishal District.Salvaged cost Tk 921239.00 | 506072014 |  | 0.862 |  |  |  | 1.06 | 8583037 |  | 7995234.286 | M/s Kazi Holdings | 27/08/18 | 2018-04-09 | 2019-04-06 |  | 70% | 4325000 | 54.09%
15 | BDRIDP/BAR/BAK/Gha/01 | Construction of Ghatla at Kaligonj Bazar Khal under Bakergonj Upazila Barisal . | [7 empty] | 1933397.79 |  | 1885106.37 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 100% | 1884421 | 99.96%
16 | BDRIDP/BAR/BAK/UZ-St/01 | Construction of 23.00m Long RCC Girder Bridge over road from Kamarkali GC to Baharchar GC via Sarsi Pollice Farry Patkati L/G Faridpur UP Office & Janota Bajarat at Ch. 5847m Under Bakerganj Upazila District Barisal Road ID 506072012 | [6 empty] | 23 | 13048406.72 |  | 12395986.384 | M/S SUN TRADERS | 23/08/18 | 30/08/18 | 2019-04-08 |  | 100% | 12003476 | 96.83%
17 | BDRIDP/BAR/BAK/CCA-RdR/10 | Improvement of Road from Hanua UP Office Bridge to Sarder Bari Foot Bridge via Jainpuri Khanka Sarif Bari & Khodaboxkati Eshak Member Bari Char a Earth work at Ch.0.0 - 2000m b CarpettingBC Ch.0.0 -2000m c Construction of 1 No Box culvert 1.0m x 1.0m at ch.1310m d Protective worksPalisading 60m under Bakergonj UpazilaBarishal District. Salvaged Cost TK.1943192.00 | 506074199 |  | 2 |  |  |  | 1 | 14520624.67 |  | 13794593.43 | M/S Sikder Enterprise | 19/02/19 | 26/02/19 | 19/08/19 |  | 70% | 5802602 | 42.06%
18 | BDRIDP/BAR/BAK/CCA-Rd/11 | Improvement of Road from Goma Amtala to Chatra Hat via Gajir Hat DKP High School & Sowdakar Bari Road by BC at Ch. 1600m-2100. Effective Length 500m.Under Bakerganj Upazila District- Barishal. | 506074136 |  | 0.5 |  |  |  |  | 3243472.3 |  | 3081298.68 | Easy Max | 17/04/19 | 24/04/19 | 24/10/19 |  | 70% | 1475000 | 47.87%
19 | BDRIDP/BAR/BAK/CCA-Rd/12 | Improvement of road from Kabiraj Altaf Chairman Bari near Madrasha to East Dhudal Community Pry School via Shahajahan Howlader & Alomgir Mollik Bari road by BC Ch. 736m-2000m. Under Bakerganj Upazila District- Barishal. | 506074148 |  | 1.264 |  |  |  |  | 8566686.78 |  | 8138352.441 | M/S Farhad Enterprise | 2019-04-04 | 2019-11-04 | 2019-11-10 |  | 60% | 4175000 | 51.3%
20 | BDRIDP/BAR/BAK/CCA-Rd/13 | Improvement of Road from Kabai Dhola Riazuddin Madrasha to Khodaboxkati Govt. Pry. School by BC work at Ch.00m-500 with 1 No. 900mx900m U-Drain. Under Bakerganj Upazila District- Barishal. | 506075432 |  | 0.5 |  |  |  | 0.9 | 3857006.71 |  | 3664146.37 | M/S Setu Traders | 2019-09-04 | 16/04/19 | 16/10/19 |  | 100% | 2800000 | 76.42%
21 | BDRIDP/BAR/BAK/CCA-Rd/14 | A Improvement of road from Rabipur Ali Hossain Khan Bari UZR to Sharif Bari via Ayeb Boyati Bari i Earthwork Ch.0.0m-500m ii CarpetingDC Ch.0.0 - 500m.iii Palisading work-50m B Improvement of road from S/Side of Kabai HatNear Chunakhali Sluice Get to E/S of Pearpur Iron BridgeUZR via Chunakhali HatDhola Madrasa & Dhola Sluice Get i Earthwork Ch.4000m-5000m ii Carpeting DC Ch.4000m-5000m iii Construction of 2Nos 1.0m x 1.0m Box Culvert at Ch.4666m 4951m & 1No. U-Drain at Ch.4830m iv Palisading work-55m Under Bakergonj Upazila Barishal District | 506075099 506074155 |  | 1.5 |  |  |  | 2.625 | 11940345.81 |  | 11939429.937 | M/S. Amir Engineering Corporation | 19/05/19 | 26/05/19 | 26/11/19 |  | 100% | 11450000 | 95.9%
22 | BDRIDP/BAR/BAK/CCA-Rd/15 | Improvement of road East Bathsala UZR to Dhulia River Bank via Bathsala Karikornagar GPS infront of Amir Khan Bari Mosque Salvaged Cost Tk 331586.00 i Earthwark Ch.0.00m-1450m. ii Carpeting DC Ch.0.00m-1450m. iii Construction of 01 No U-Drain 0.9mx0.9m at Ch.1250m.iv Palasading 79m. Under Bakergonj Upazila Barishal District. | 506075379 |  | 1.45 |  |  |  | 0.9 | 10466500 |  | 10414223.243 | M/S ISLAM BROTHERS LTD | 2019-12-06 | 19/06/19 | 19/12/19 |  | 100% | 9932365 | 95.37%
23 | BDRIDP/BAR/BAK/CCA-Rd/16 | Part A Improvement of road from H/O Sujauddin Halta F.H. high School. Halta Mouza Sholoshath to Surath Memorial GPS. i Earthwark Ch.0.00m-850m. ii Carpeting DC Ch.0.00m-850m. iii Construction of 02 Nos RCC Culvert1.6mx1.6m at Ch 4m845m 3 Nos U-Drain 0.9mx0.9m at Ch.120m190m235m.iv Palsading 96mPart B Improvement of road from Mokimabad Bajar S/Side of Culvert to East Side of BIP Siuce Get via Dilip Master Bari.Oza Bari to Thakur Bari via Naboraz Biswas bari i Earthwark Ch.2500m-3250m. ii Carpeting DC Ch. 2500m-3250m. iii Construction of 01 No RCC Culvert 1.6mx1.6m at Ch 3125m.iv Palsading 38m.Under Bakergonj Upazila District Barishal. | 506075180 506075229 |  | 1.575 |  |  |  | 7.5 | 14776000 |  | 13806417.904 | M/S Rupali Construction | 14/05/19 | 21/05/19 | 21/11/19 |  | 60% | 5925000 | 42.91%
24 | BDRIDP/BAR/BAK/CCA-Rd/17 | Part A Improvement of road from Padrishibpur GPSUZR to Bismillah Bazar via Sikder Bari Kowabunia khal & Dhulal sadu Bari Salvaged Cost Tk 921459.76i Earthwark Ch.0.0m-900m. ii Carpeting DC Ch. 0.0 - 900m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert & 1No.U-Drain at Ch 482m.& 28m iv Palsading 59m.Under Bakergonj Upazila District Barishal. Part B Improvement of road from East side of Bangla bazar Box Culvert to Wapder Khal Ghorar Bridge Bothra via Biharipur Madrasha road. i Earthwark Ch.3250m-3850m. ii Carpeting DC Ch.3250m-3850m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert at Ch.3255m & 01 No 1.6 m x 1.6m RCC Box Culvert at Ch.3716m iv Palsading 28m.Under Bakergonj Upazila District Barishal.Part C Improvement of road from Padrishibpur Sunddartala Baily Bridge UZR to Aowal Sikderbari i Earthwark Ch.0.0m-500m. ii Carpeting DC Ch. 0.0 - 500m. Under Bakergonj Upazila District Barishal. | 506074057 506074182 506075155 |  | 2 |  |  |  | 6.225 | 16442515.41 |  | 14202513.2 | M/S S H Enterprise | 23/07/19 | 30/07/19 | 30/01/20 |  | 60% | 4100000 | 28.87%
25 | BDRIDP/ BAR/BAK/ CCA-Rd/18 | Improvement of Road UZR Rabipur GPS UNR Younous Sharif Bari Via Rabipur. Salvaged Cost Tk 641271.00i Earthwark Ch.0.00m-500m. ii Carpeting DC Ch.0.00m-500m. iii Palsading 50m. Under Bakergonj Upazila Barishal District. | 506074267 |  | 0.5 |  |  |  |  | 3691293.53 |  | 3506728.85 | M/S Bushra Traders | 2019-10-06 | 17/06/19 | 17/10/19 |  | 100% | 1400000 | 39.92%
26 | BDRIDP/BAR/BAK/ CCA-Rd/19 | A Improvement of Road from Dhaporkati Khayaghat Kabai to Chunakhall Bridge via Najam Master Laxmipasa Senior Madrasha & south Hanua Regd. Pry. School a Earthwark Ch. 1286m-2286m.b Carpeting BC Ch. 1286m-2286m.c Construction of 01 No 1-Vent RCC Box Culvert 1.6mx1.6m at Ch.1386m & 01 No. U-Drain. At Ch. 1652m. d Palsading 47m.B Improvement of Road from Krishnokati Anser Howlader Bari to Nijamkhali Khal over Iron Foot Bridge. Salvaged Cost Tk. 361295.00a Earthwark Ch. 00m-898m.b Carpeting DC Ch. 00m-898m.c Construction of 01 No. U-Drain. At Ch. 197m.d Palsading 64m | 506074154 506075313 |  | 1.898 |  |  |  | 2.8 | 15171756 |  | 13468196.31 | M/S Jakiullah & Builders | 30/12/19 | 2020-07-01 | 2020-07-07 |  | 10% |  | 0%
27 | BDRIDP/BAR/BAK/CCA-Rd/20 | Improvement of Road from Balaikati Dhanshiri NGO to Kalitara Govt. Pry. School via Howlader bari.ID No-506074188a Earthwark Ch. 00m-1000m.b Carpeting DC Ch. 00m-1000m.c Construction of 01 No 1-Vent RCC Box Culvert 1.6mx1.6m at Ch.510m & 01 No. U-Drain. At Ch. 370m. d Palsading 15m | 506074188 |  | 1 |  |  |  | 2.2 | 7695899 |  | 7311104.18 | M/S Muhib Construction | 20/11/19 | 27/11/19 | 27/05/20 |  | 100% | 4500000 | 61.55%
28 | BDRIDP/BAR/BAK/CCA-Rd/21 | Improvement of Road from South kazlakati Arjina Govt. Pry. School to Ukiler Hat road a Earthwark Ch. 00m-900m. b Carpeting BC Ch. 00m-900m. c Construction of 01 Nos RCC Box Culvert 1.6mx1.6m at Ch.234m | 506074039 |  | 0.9 |  |  |  | 1.6 | 6889481.76 |  | 6545007.67 | M/S Swa Construction | 22/12/19 | 29/12/19 | 29/06/20 |  | 60% | 1800000 | 27.5%
29 | BDRIDP/BAR/BAK/CCA-Rd/22 | Improvement of Road from Dhaporkati khaya Ghat Kabai to Chunakhali Bridge via Najam Master Laxmipasha Senior Madrasha & South Hanua Regd. Pry.School road a Earthwark Ch. 00m-1300m. b Carpeting BC Ch. 00m-1300m. c Linkroad up to H/O Madrasha Quarter 55m d Palisading 70m e Construction of 2 Nos U-Drain 900mm x 900mm at Ch.290m & 1084m | 506074154 |  | 1.3 |  |  |  | 1.8 | 10622639.7 |  | 10091507.71 | M/S Salim Enterprise | 29/12/19 | 2020-06-01 | 2020-06-07 |  | 60% | 3200000 | 31.71%
30 | BDRIDP/ BAR/BAK/ CCA-Rd/23 | Improvement of Road From Mudukhali-Kazlakati Talukder hat.ID No-506075235a Earthwark Ch. 00m-780m.b Carpeting BC Ch. 00m-780m.c Construction of U-Drain 900mmx900mm at Ch. 497m & 01 No 3mx3m RCC Box Culvert at Ch. 780m.d Palsading 74m. | 506075235 |  | 0.78 |  |  |  | 3.3 | 7513234.74 |  | 7137573.003 | M/S. Golam Kabir | 29/04/20 | 2020-06-05 | 2020-06-11 |  | 0% |  | 0%
31 | BDRIDP/ BAR/BAK/ UN-Rd/04 | A Improvement of Road Khayrabath hat Garuria UP to Dhaparkati Bazar Godown via Nilgonj Bazar.ID No-506073001 Salvaged Cost TK 1488714.00a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of RCC Box Culvert 1.50mx1.50m at Ch.520m.d Palsading 100m. B Improvement of Road From Khayrabad UP Garuria UP Office via Khayrabath High School Runsiposor RNGPS west side of Dinger hat. Salvaged Cost TK 1459641.00ID No-506073010a Earthwark Ch. 00m-1000m.b Carpeting BC Ch. 00m-1000m.c Construction of RCC Box Culvert 1.50mx1.50m at Ch.760m.d Palsading 90m. | 506073001 506073010 |  | 2 |  |  |  | 1.5 | 17308000 |  | 15862509.98 | M/S. Sifat Enterprise |  |  |  |  | 20% |  | 0%
32 | BDRIDP/BAR/BAK/ CCA-Rd/24 | A Improvement of road from Dudhalmow Ferryghat RHD to Kanki Govt. Pry. School. under Bakergonj upazila Barishal District.a Earthwark Ch. 980m-3100m.b Carpeting BC Ch. 980m-3100m.c Palsading 85m. B Improvement of Dhaporkati High School-Kalukhan Bari via Khandoker Bari. under Bakergonj upazila Barishal District.a Earthwark Ch. 00m-700m.b Carpeting BC Ch. 00m-700m.c Construction of 01 No 1.50mx1.50m RCC Box Culvert at Ch. 605m. d Palsading 82m. C Improvement of Khajuria Vhorpasha-Emdad Talukdar Bari-Warase Hopwlader Bari. under Bakergonj upazila Barishal District.a Earthwark Ch. 00m-800m.b Carpeting BC Ch. 00m-800m.c Palsading 50m. | 506074120 506074161 506075418 | [6 empty] | 29371000 |  | 27624184.691 | M/S. Amir Engineering Corporation | 2020-03-06 | 2020-10-06 | 2020-10-12 |  | 10% |  | 0%
33 | BDRIDP/BAR/BAK/CCA-Rd/25 | A Improvement of road from UZR Middle Baily Bridge to Badalpara Hat Road by BC. under Bakergonj upazila Barishal District Salvaged Tk. 2030121.00a Earthwark Ch. 00m-850m.b Carpeting BC Ch. 00m-850m.c Construction of 02 Nos 2.00mx2.00m RCC Box Culvert at Ch. 330m & 502m. U-Drain 900mmx900mm at Ch. 655m.d Palsading 15m. B Improvement of road from Bairom Kha Digir per to RHD via Rashed Pada & Fakir Bari. under Bakergonj upazila Barishal Districta Earthwark Ch. 00m-625m.b Carpeting BC Ch. 00m-625m.c Palsading 90m. under | 506074135 506075368 |  | 1.475 |  |  |  | 4.9 | 13148996.33 |  | 12491546.514 | M/S. Sharmin Traders | 19/04/20 | 26/04/20 | 26/10/20 |  | 20% |  | 0%
34 | BDRIDP/ BAR/BAK/ CCA-Rd/26 | A Improvement of Road from Ghopar Hat to Satikola High School via Nazirpur Islam Bari & Satikola GPS. at Ch. 1130m-1760m including 01 No-1.50mx1.50m at Ch. 1620.00m. B Improvement of Road from Mohespur Hat Ruper Jore Govt Primary School. at Ch. 0.00m-780m including 01 No-1.50mx1.50m at Ch. 780.00m. Under Bakergonj Upazila Barishal District Salvaged Cost Tk 1102166.00 | 506074138 506074082 |  | 1.5 |  |  |  | 3 | 12778386.93 |  | 12139467.584 | M/S. Ashik Enterprise | 2020-11-05 | 18/05/20 | 18/11/20 |  | 20% |  | 0%
35 | BDRIDP/ BAR/BAK/ UZ-St/02 | Construction of 30m long PSC Girder Bridge over road from Kamarkhali GC to Baherchar GC via Sarsi Police Farry Patkati L/G Faridpur UP Office & Janota Bazar at Ch 9200m Under Bakergonj Upazila Barishal District | [6 empty] | 30 | 30402000 |  | 25115515.375 | M/S. Shampa Construction | 2020-11-05 | 18/05/20 | 18/04/21 |  | 20% | 14500000 | 57.73%
35 |  |  |  | 0 | 35.944 | 5.923 | 0 | 0 | 132.37 | 379343002.61 | 0 | 345087236.172 | [6 empty] | 185172634 |  |  |  | 8829.82
1 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m | 506073023 | [6 empty] | 131861 |  | 131861 | Anwar Hossain LCS No-01 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 131399 | 99.65% | Final
2 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m. | 506073023 | [6 empty] | 256728 |  | 256728 | Md. Babul Howlader LCS No-02 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 255288 | 100% | Final
3 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m | 506073023 | [6 empty] | 230734 |  | 230734 | Md. Joynal Abadin LCS No-03 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 230617 | 99.95% | Final
4 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m | 506073023 | [6 empty] | 224792 |  | 224792 | Md. Royon Mollah LCS No-04 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 224421 | 99.83% | Final
5 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m | 506073023 | [6 empty] | 233429 |  | 233429 | Md. Shahidul Sharif LCS No-05 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 226102 | 100% | Final
6 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m | 506073023 | [6 empty] | 205799 |  | 205799 | H M Shamsul Huda LCS No-06 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 205740 | 99.97% | Final
7 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m | 506073023 | [6 empty] | 243498 |  | 243498 | Md. Hanif LCS No-07 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 243355 | 99.94% | Final
8 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m | 506073023 | [6 empty] | 230149 |  | 230149 | Md. Amir Ali Khan LCS No-08 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 230032 | 99.95% | Final
9 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m | 506073023 | [6 empty] | 249498 |  | 249498 | Md. Monir Hossain LCS No-09 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 249382 | 100% | Final
10 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m | 506073023 | [6 empty] | 222257 |  | 222257 | Md. Shalim Mridha LCS No-10 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 221327 | 99.58% | Final
10 |  | Sub Total: |  | 0 | 0 | 0 | 0 | 0 | 0 | 2228745 | 0 | 2228745 | [6 empty] | 2217663 |  |  |  | 0
45 |  | Grand Total: |  | 0 | 35.944 | 5.923 | 0 | 0 | 132.37 | 381571747.61 | 0 | 347315981.172 | [6 empty] | 187390297 |  |  |  | 8829.82
335 |  |  |  | 202153.643 | 247.058 | 10.509 | 0 | 0 | 960.34 | 2348953728.06 | 97974535.74 | 2225208781.026 | [6 empty] | 1142685378 |  |  |  | -68771999.26
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal

## Progress (4)
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [18 empty] | Reporting Month: March/18
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Fund Received (Tk) | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 95% | 8800000 | 87.23% |  |  |  | 9583950.2365
2 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 506514048 |  | 2.782 |  |  |  |  | 10910419 | 207108 | 8773072.65 | M/S Hasan Construction | 2015-10-05 | 17/05/15 | 17/02/16 |  | 70% | 4885853 | 55.69% |  |  | 70% | 1255297.855
3 | BDRIDP/BAR/SDR/CCA-Rd/10 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila,Barisal. | 506514137 |  | 1.544 |  |  |  | 4 | 9500469 |  | 8550422.1 | M/S Sirajul Alam Sikder | 22/05/17 | 29/05/17 | 29/02/18 |  | 30% | 700000 | 8.187%
4 | BDRIDP/BAR/SDR/UN-Rd/01 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road. | 506513003 |  | 2.76 |  |  |  |  | 18760504 |  | 16884454 | Md Mafuz Khan | 18/01/18 |  | 31/11/18 |  | 0%
5 | BDRIDP/BAR/SDR/UZ-Rd/01 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal. | 506512003 |  | 0.579 |  |  |  |  | 4209569.27 |  | 3788612.34 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 0% |  | 0%
6 | BDRIDP/BAR/SDR/UN-Rd/02 | Improvement of Charkawa Kheyaghat - Durgapur hat road from Ch. 3000m - 3600m.under Sadar Upazila Barisal District. | 506513004 |  | 0.6 |  |  |  |  | 3464647.09 |  | 3118182.38 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 0% |  | 0%
7 | BDRIDP/BAR/SDR/CCA-Rd(R)/11 | Improvement of road from Charmonai Talukder Bari-West Razarchar Club by BC. at Ch. 0.00m-1203.00m under Charmonai Union, Upazila : Sadar, Dist-Barisal [Salvaged cost- Tk 231155.00] | 506515109 |  | 1.203 |  |  |  |  | 8769166.6 |  | 7892249.94 | M/S Kohinoor Enterprise | 18/01/18 | 25/01/18 | 25/11/18 |  | 0% |  | 0%
8 | BDRIDP/BAR/SDR/CCA-RdR/12 | Improvement of road Shibpasha - Sholna Talukder bari via H/O Malek Police at ch.1600km - 2020km under Sadar Upazila Barisal. | 506515006 |  | 0.42 |  |  |  |  | 2720015.56 |  | 2448014.04 | M/S Kohinoor Enterprise | 2018-04-02 | 2018-11-02 | 2018-11-08 |  | 20% | 400000 | 16.34%
9 | BDRIDP/BAR/SDR/Gha/01 | Construction of Ghat & CC Road at Shaheber Bazar under Sadar Upazila Barisal . | [19 empty] | Evaluation on going
9 |  | Sub-Total: |  | 0 | 9.888 | 0 | 0 | 0 | 24 | 71107644.52 | 207108 | 61543376.12 | [6 empty] | 14785853 |  | 0 |  |  | 10839248.0915
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 506942007 |  | 2.605 |  |  |  |  | 18314961 | 18314961 | 14275617.27 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 35% | 4950000 | 34.67%
2 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 506942015 |  | 2.296 |  |  |  |  | 14753928 | 14753928 | 11501091.23 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 35% | 2650000 | 23.04%
3 | BDRIDP/BAR/UZP/UZ-RdR/04 | Rehabilitation of Harta Chowmuhani Bisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 | 506942009 |  | 2.6 |  |  |  | 2.5 | 17827349 |  | 18399998.87 | M/S S H Enterprise | 2018-08-03 | 15/03/18 | 15/03/19 |  | 0% |  | 0%
4 | BDRIDP/BAR/UZP/UN-Rd/01 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m. | 506943007 506942018 |  | 2.34 |  |  |  | 1.2 | 15060662.42 |  | 13554596.17 | M/S Niaz Traders | 2017-02-10 | 2017-09-10 | 2018-09-08 |  | 15% |  | 0%
5 | BDRIDP/BAR/UZP/UN-St/01 | Construction of 12.00m Long RCC Girder Bridge over Chowdhuri Hat - Hasti Shundi via Daberkul road infront of A. Latif MasterDaberkul Chowmohani - Chowmohini Sere Bangla road at ch. 00.0m under Uzirpur Upazila Barisal District. | 506943004 | [5 empty] | 12 |  |  | 7535398.53 | M.M Builders & Engineers | 30/01/18 | 2018-07-02 | 2018-07-12 |  | 40% | 2800000 | 37.16%
6 | BDRIDP/BAR/UZP/CCA-Rd/04 | Improvement of Old Sikerpur Bandar-Abul Hasan Mridhas House Connecting road under Uzirpur UpazilaBarisal ID -506945281 a Earthwork Ch.0.0m - 360m b Bituminous Carpetting Ch.0.0m - 360m c U-Drain 01 no at Ch.117. | [19 empty] | E-Tender Under Process.
7 | BDRIDP/BAR/UZP/CCA-Rd/03 | Improvement of road from Guthia kakradhari Connecting road North side of Khaleque Mollas House of Dahorpara GPS via Mojid Masters House under Uzirpur Upazila Barisal ID -506944084 a Earthwork Ch.0.0m -1550m b Bituminous Carpetting Ch.0.0m - 1550m c U-Drain 04 nos at Ch.130m476m655m1230m & 2Nos 1-Vent 4m x 4m RCC Box Culvert at ch.755m & 1540m | [19 empty] | E-Tender Under Process.
8 | BDRIDP/BAR/UZP/Gha/01 | Construction of Typical Ghat at Satla Bazar under Uzirpur Upazila Barisal . | [19 empty] | Evaluation on going
8 |  | Sub-Total: |  | 0 | 9.841 | 0 | 0 | 0 | 15.7 | 65956900.42 | 33068889 | 65266702.07 | [6 empty] | 10400000 |  | 0 |  |  | #REF!
Upazila: Muladi
1 | BDRIDP/BAR/MUL/CCA-St/05 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal. | 506694043 | [5 empty] | 12 | 10068184 | 10068184 | 7727638.21 | M/S Shafi Enterprise | 2017-06-02 | 13/02/17 | 13/12/17 |  | 95% | 7100000 | 91.88%
2 | BDRIDP/BAR/MUL/UN-St/02 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District. | 506693005 | [5 empty] | 20 | 14312698.5 |  | 12881428.65 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 5% |  | 0%
3 | BDRIDP/BAR/MUL/UZ-St/03 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District. | 506692004 | [5 empty] | 20 | 17924056.31 |  | 16131650.67 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 45% | 6800000 | 42.15%
4 | BDRIDP/BAR/MUL/UN-St/01 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District. | 506693005 | [5 empty] | 21 | 15795569.51 |  | 14216012.55 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 5% |  | 0%
5 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. | 506692002 | [5 empty] | 45 | 24434851.86 |  | 21991136.67 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 5% |  | 0%
6 | BDRIDP/BAR/MUL/UZ-St/04 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal. | 506692004 | [5 empty] | 25 | 23503677 |  | 21153309.3 | M/S Orien Trading & Builders | 2017-03-08 | 2017-10-08 | 2018-10-08 |  | 50% | 9600000 | 45.38%
7 | BDRIDP/BAR/MUL/UZ-St/05 | Construction of 30.00m PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at Ch.7620km over Banimardhan Khal under Muladi UpazilaDistrict-Barisal | 506692004 | [5 empty] | 30 | 21022197.08 |  | 18919977.37 | M/S Amir Engineering Corporation and M.M Builders & Engineers | 2018-04-02 | 2018-11-02 | 2018-11-12 |  | 0% |  | 0%
8 | BDRIDP/BAR/MUL/CCA-Rd/07 | Improvement of road from Muladi-Mirdar Hat GCCR Kazi Ali Ahmed Bari Grostan Alauddin Dewan Bari under Muladi UpazilaBarisal.a Bituminus Surfacing wearing courseDC 0.0m - 375mb 1 No.1.3m x 1.3m RCC Box Culvert at ch.170m | 506695137 |  | 0.375 |  |  |  | 1.3 | 2591153.77 |  | 2332038.39 | M/S Kohinoor Enterprise | 19/01/18 | 25/01/18 | 25/07/18 |  | 0% |  | 0%
9 | BDRIDP/BAR/MUL/UZ-Rd/02 | a Improvement of Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road from Ch.2150m - 4415m ID No.506692002 under Muladi Upazila Barisal District.b Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch.2800m.c Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch. 3900m. | [19 empty] | E-Tender Under Process.
10 | BDRIDP/BAR/MUL/CCA-Rd/09 | Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000mID No.506694016 under Muladi Upazila Barisal District.Salvaged Cost Tk 591644.00Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000mID No.506694016 under Muladi Upazila Barisal District. | [19 empty] | E-Tender Under Process.
11 | BDRIDP/BAR/MUL/CCA-Rd/08 | Improvement of road from Batamara Paderhat Launch Ghat -Salimpur Bazar via Batamara Regd.Primary School via Aminul Haque Kabir Bari by BC at ch.200m - 1252m ID - 506695001 under Muladi Upazila Barisal. | [19 empty] | E-Tender Under Process.
12 | BDRIDP/BAR/MUL/CCA-Rd/10 | Improvement of road from Balarmpur Bazar-Dumurtala GPS-Char Dumuritala Bissas Bari Mosque UNRG by BC at Ch. 0.000km-1.000km. ID No.506694094. under muladi upazila Barisal District | [19 empty] | E-Tender Under Process.
13 | BDRIDP/BAR/MUL/CCA-Rd/11 | Improvement of road from Muladi-Bara Patarchar Ferry Ghat M by BC at Ch. 3.500km-4.065km. ID No.506694017 under muladi upazila Barisal District | [19 empty] | E-Tender Under Process.
14 | BDRIDP/BAR/MUL/CCA-Rd/12 | Improvement of road from Haraz Sikder Bari to Laxmipur Nutun hat via Rashid Dhali Bari by BC at Ch. 0.900km-2.400km ID No.506695010 under muladi upazila Barisal District.Salvaged cost Tk.888105.00 | [19 empty] | E-Tender Under Process.
14 |  | Sub Total: |  | 0 | 0.375 | 0 | 0 | 0 | 174.3 | 129652388.03 | 10068184 | 115353191.81 | [6 empty] | 23500000 |  | 0 |  |  | #REF!
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 | 506073023 |  | 1 |  |  |  |  | 4566907 |  | 3523866.83 | M/S Khondokear Brothers | 21/07/15 | 28/07/15 | 27/04/16 |  | 75% | 1150000 | 32.63%
2 | BDRIDP/BAR/BAK/CCA-Rd/03 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal. | 506074120 | [6 empty] | 17641663 |  | 16139041.07 | Md. Sumsudhoa Mollick | 21/12/16 | 28/12/16 | 27/06/17 |  | 95% | 11950000 | 74.04%
3 | BDRIDP/BAR/BAK/UN-Rd/03 | Improvement of road from Faridpur Hat Kheya Ghat Durgapasa UP office Gobindapur Bothtala via Kakordha Bazar Road, a Earth Work from Ch. 4860m 7320m.b Bituminus Carpeting from Ch. 4860m 7470m.c Construction of 1 No. 1.60mx1.60m RCC Box Culvert at Ch. 7435m. under Bakergonj upazila Barisal District. Salvage Cost Tk. 3733841.00 | 506073020 |  | 2.46 | 2.61 |  |  | 1.6 | 16459779.83 |  | 14813801.84 | Md Mafuz Khan | 2018-04-01 |  | 30/11/18 |  | 20% |  | 0%
4 | BDRIDP/BAR/BAK/CCA-Rd/04 | Improvement of road from west Faridpur Ajgor Sikder Bari to DC road Ferry-ghat via H/O Rahim Mrida Road, a Earth Work from Ch. 0.0 - 1300.00m. b Bituminus Carpeting from Ch. 0.0 - 1300m c Construction of 1 No. 4.0m x 4.0m RCC Box Culvert at Ch. 425m. under Bakergonj upazila Barisal District. | 506074151 |  | 1.3 | 1.3 |  |  | 4 | 9994097.44 |  | 8994687.7 | M/S Islam Brothers | 2018-02-01 | 2018-09-01 | 2018-09-10 |  | 0% |  | 0%
5 | BDRIDP/BAR/BAK/CCA-Rd/06 | Improvement of road from Shashi Bazar Bridge-Telani Lunch Ghat Najrul Talukder Bari. under Bakergonj Upazila Dist:Barisal. a) HBB from Ch. 00m-1000m b) Protection Work 108m c) Earth work from Ch. 00m-1000m | 506074100 |  |  | 1 |  |  |  | 4609416.97 |  | 4563267.91 | Md. Zakir Hossain Mia | 17/01/18 | 24/01/18 | 24/07/18 |  | 20% |  | 0%
6 | BDRIDP/BAR/BAK/CCA-Rd(R)/05 | Improvement of road from ATIMKHANA to Bothra Road via Mr. Matiur Rahman (ASP) at Ch. 0.00m-500.00m (Efective Length=475.00m) (ID No.506074225) under Bakergonj Upazila,Dist : Barisal [Salvaged cost : Tk1049647.00] |  |  | 0.5 |  |  |  |  | 3304868 |  | 2974381.2 | M/S Osin Enterprise | 17/01/18 | 24/01/18 | 24/05/18 |  | 15% |  | 0%
7 | BDRIDP/BAR/BAK/CCA-Rd/07 | Improvement of road from Sampur Ray Barir Culvert to Birangal Digirpar Kader Hohlade Bari via Karim Gaji Bari a Earth work 0.0 - 1500m b Bituminous Surfacing - wearing course DC 0.0m - 1500m c 1.5 m x 1.5m RCC Box Culvert at Ch.900m | 506075125 |  | 1.5 |  |  |  |  | 9125908.56 |  | 8213317.7 | M/S Abul Kalam Azad | 22/01/18 | 29/01/18 | 29/10/18 |  | 30% |  | 0%
8 | BDRIDP/BAR/BAK/Gha/01 | Construction of Ghatla at Kaligonj Bazar Khal under Bakergonj Upazila Barisal . | [19 empty] | Evaluation on going
8 |  |  |  | 0 | 6.76 | 4.91 | 0 | 0 | 5.6 | 65702640.8 | 0 | 59222364.25 | [6 empty] | 13100000 |  | 0 |  |  | #REF!
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/UZ-ST/01 | Construction of 30.00m PSC Girder Bridge on Barti Bazar to Gournadi GC at Ch.5000km over Anandhapur Khal under Gournadi UpazilaDistrict-Barisal | 506322005 | [5 empty] | 30 | 24934266.46 |  | 27173350.5 | M/S Kohinoor Enterprise | [8 empty] | P.S Submit
2 | BDRIDP/BAR/GOR/UZ-ST/02 | Construction of 32.00m PSC Girder Bridge on Barti BazarNHW to Gournadi GC via Torky GC at Ch.9340km over Kashba Khal under Gournadi Upazila District-Barisal | 506322005 | [5 empty] | 32 | 24196878.89 |  | 26369588.63 | M/S Kohinoor Enterprise | [8 empty] | P.S Submit
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 62 | 49131145.35 | 0 | 53542939.13 | [6 empty] | 0 |  | 0 |  |  | #REF!
Upazila: Agailjhara
1 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 506023001 |  | 2.76 |  |  |  |  | 14739342 | 791797 | 15592739.8 | M/S Sharif Enterprise | 25/05/15 | 2015-06-06 | 30/05/15 |  | 95% | 11500000 | 73.75% |  |  | 20% | -8381452.04
2 | BDRIDP/BAR/AGL/CCA-Rd/08 | Improvement of road from Hazi Mokbul Sardar House via Sardar Mohabubul Alom & Sardar Harun - Jainger Gomosta House road. at Ch.00 to 208m under Agailjhara Upazila Barisal. | 506025088 | [18 empty] | E-Tender Under Process.
3 | BDRIDP/BAR/AGL/Gha/01 | Construction of Ghat at Paisarhat Paschim par under Agailjhara Upazila Barisal | [19 empty] | E-Tender Under Process.
3 |  |  |  | 0 | 2.76 | 0 | 0 | 0 | 0 | 14739342 | 791797 | 15592739.8 | [6 empty] | 11500000 |  | 0 |  |  | -8381452.04
Upazila: Babugonj
1 | BDRIDP/BAR/BAB/CCA-RdR/06 | Improvement of Road from Telerchar GPS -Najamrari Bari - Jahungirnagar UP road Start ch.1700m Satter Mirar Bari -Thakur. From Ch.0.0m - 550mSalvaged Cost Tk 192766.00 | 506035103 506034109 |  | 1.7 |  |  |  |  | 3507645.29 |  | 3156880.761 | M/S Niaz Traders | 2018-11-01 | 18/01/18 | 18/07/18 |  | 0% |  | 0%
2 | BDRIDP/BAR/BAB/CCA-Rd/07 | Improvement of road from Jahapur Shilondia Bridge -Uttor Mujafforpur Peda Master bari under Jahangir Nagar Union a Bituminous Surfacing -wearing courseDC ch.190m -1190m b 1No. 2.0m x 2.0m & 1No.1.0m x1.0m RCC Box Culvert at Ch.273m & 615m under Babuganj Upazila Barisal District. | 506035018 |  | 1.1 |  |  |  | 3 | 6955230.78 |  | 6949470.12 | M/S Amir Engineering Corporation | [6 empty] | 0% |  | P.S Submit
2 |  |  |  | 0 | 2.8 | 0 | 0 | 0 | 3 | 10462876.07 | 0 | 10106350.881 | [6 empty] | 0 |  | 0 |  |  | #REF!
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 506624016 |  | 1.61 |  |  |  |  | 6864308 | 6864308 | 6860287.95 | M/S Hasan Construction | 2017-12-01 | 19/01/17 | 19/09/17 |  | 30% | 1875000 | 27.33%
2 | BDRIDP/BAR/MHN/UZ-Rd/02 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila,Barisal. | 506622007 |  | 3 |  |  |  |  | 10545370 |  | 10492643.13 | M/S Lutful Kabir | 2017-07-05 | 14/05/17 | 14/02/18 |  | 10% |  | 0%
3 | BDRIDP/BAR/MHN/CCA-Rd/03 | Improvement of Road from Posshim Yearbeg Dadpur GPS under Mehendiganj Upazila District Barisal ID 506625062aEarthwork Ch.1000 2760m b HBB Ch.1000 -2760m | [19 empty] | E-Tender Under Process.
3 |  |  |  | 0 | 4.61 | 0 | 0 | 0 | 0 | 17409678 | 6864308 | 17352931.08 | [6 empty] | 1875000 |  | 0 |  |  | #REF!
Upazila: Hizla
1 | BDRIDP/BAR/HZL/CCA-Rd/01 | Improvement of Kowria- Moulavirhat UZR Poschim koralia road under Hizla Upazila District Barisal ID 506364033aEarth work from Ch.0.0 -900m b Dense Carpeting Ch.0.0 -900m c Two vent 4m x 4m RCC Box Culvert at Ch.252m | [19 empty] | Evaluation on going
2 | BDRIDP/BAR/HZL/Gha/01 | Construction of RCC Boat land Station at Abupur Ghat under Hizla Upazila Barisal | [19 empty] | Evaluation on going
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 |  | 0 |  |  | #REF!
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 506102003 | 0 | 1 | 0 | 0 | 0 | 0 | 7013799 | 7013799 | 5349539.02 | M/S Saleha Enterprise | 29/01/17 | 2017-06-02 | 2017-06-06 |  | 35% | 1300000 | 24.3% |  |  | 40% | 839815.608
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m ,1 No.3.0m x 3.0m , 2Nos.4.0m x 4.0m , 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 506102003 | 0 | 0 | 0 | 0 | 0 | 11 | 7531517 | 7531517 | 5461652.5 | M/S Soma Enterprise | 25/01/17 | 2017-02-02 | 2017-02-10 |  | 70% | 2000000 | 36.62%
3 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 11850164.61 |  | 10665148 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 20% |  | 0%
4 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 9814374 |  | 8832936 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 20% |  | 0%
5 | BDRIDP/BAR/BAN/Gha/01 | Estimate for Construction of RCC Ghat at Mohish Katakhali Kheya Ghat under Banaripara Upazila Barisal . | [19 empty] | Evaluation on going
5 |  |  |  | 0 | 1 | 0 | 0 | 0 | 41 | 36209854.61 | 14545316 | 30309275.52 | [6 empty] | 3300000 |  | 0 |  |  | 839815.608
56 |  |  |  | 0 | 38.034 | 4.91 | 0 | 0 | 325.6 | 460372469.8 | 65545602 | 428289870.661 | [6 empty] | 78460853 |  | 0 |  |  | #VALUE!
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal

## Progress (3)
Barisal Division Rural Infrastructure Development Project
µwgK bs | c¨v‡KR bs | ¯‹x‡gi bvg | Salvage Materials | Pzw³g~j¨ | Dc‡Rjv/Avmb | wVKv`v‡ii bvg | AMÖMwZ | mgm¨v | gšÍe¨
1 | 2 | 3 | 4 | 4 | 5 | 6 | 7 | 8 | 9
Upazila: Agailjhara
1 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 791797 | 15592739.8 | Av‰MjSvov ewikvj-1 | M/S Sharif Enterprise | 95%
2 | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m |  | 6375868.44 | Av‰MjSvov ewikvj-1 | M/S Sarniabad Enterprise | 86%
3 | BDRIDP/BAR/AGL/CCA-Rd/ 02 | Improvement of road from Seral - Goila road via Shahid Serniabad House - Tamer Jame Mosjid(Tamer Girls High School-Seral Community Center) by BC (Ch.0.0 - 975m) under Agailjhara Upazila,Barisal. | 7232587 | 7230073.2 | Av‰MjSvov ewikvj-1 | M/S Serniabad Traders | 50%
3 |  |  | 791797 | 29198681.44
1 | BDRIDP/BAR/AGL/CCA-EW/01 | Resectioning of Road from Seral-Goila road via Shahid Serniabad House-Tamer Jame Mosjid (Tamer Girls High School-Seral Community Center) by Earth at Ch. 0.00m-975m. |  | 317636 | Av‰MjSvov ewikvj-1 | LCS No-1 | 50%
1 |  |  | #REF! | 317636
4 |  |  | #REF! | 29516317.44
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 18314961 | 14275617.27 | DwRicyi ewikvj-2 | M/S Hasan Construction | 30%
2 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 14753928 | 11501091.23 | DwRicyi ewikvj-2 | M/S Hasan Construction | 30%
3 | BDRIDP/BAR/UZP/UZ-RdR/04 | Rehabilitation of Harta ChowmuhaniBisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 |  |  | DwRicyi ewikvj-2 |  |  |  | Evaluation on going
4 | BDRIDP/BAR/UZP/UN-Rd/01 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m. |  |  | DwRicyi ewikvj-2 |  |  |  | Evaluation on going
4 |  | Sub-Total: | 33068889 | 25776708.5
1 | BDRIDP/BAR/UZP/UZ-EW/02 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 0.00m-1100m. | 418543 | 418543 | DwRicyi ewikvj-2 | Md. Shahidul Islam LCS No-1 | 70%
2 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1100m-1900m. | 451503 | 451503 | DwRicyi ewikvj-2 | Md. Khalilur Rahman LCS No-2 | 70%
3 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1900m-2605m. | 491755 | 491755 | DwRicyi ewikvj-2 | Habibur Bapari LCS No-3 | 70%
4 | BDRIDP/BAR/UZP/UZ-EW/03 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 1754m-2850m. | 421703 | 421703 | DwRicyi ewikvj-2 | Kamrun Nesa LCS No-1 | 65%
5 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 2850m-3650m. | 466527 | 466527 | DwRicyi ewikvj-2 | Rubina Begum LCS No-2 | 65%
6 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 3650m-4050m. | 342538 | 342538 | DwRicyi ewikvj-2 | Monzu Begum LCS No-3 | 65%
7 | BDRIDP/BAR/UZP/UN-EW/01 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3400m-3900m By Earth. | 434519 | 434519 | DwRicyi ewikvj-2 | Md. Ziaul Haque LCS No-1 | 10%
8 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3900m-4300m By Earth. | 437099 | 437099 | DwRicyi ewikvj-2 | Khokon Sharder LCS No-2 | 10%
9 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4300m-4900m By Earth. | 461279 | 461279 | DwRicyi ewikvj-2 | Rofiqul Islam LCS No-3 | 10%
10 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4900m-5740m By Earth. | 310321 | 310321 | DwRicyi ewikvj-2 | Nurul Hoq Sikder LCS No-4 | 10%
10 |  | Sub-Total: | 4235787 | 4235787
14 |  | Grand Total: | 37304676 | 30012495.5
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 7013799 | 5349539.02 | evbvixcvov ewikvj-2 | M/S Saleha Enterprise | 35%
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m ,1 No.3.0m x 3.0m , 2Nos.4.0m x 4.0m , 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 7531517 | 5461652.5 | evbvixcvov ewikvj-2 | M/S Soma Enterprise | 60%
3 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District |  |  | evbvixcvov ewikvj-2 |  |  |  | Evaluation on going
4 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District |  |  | evbvixcvov ewikvj-2 |  |  |  | Evaluation on going
4 |  |  | 14545316 | 10811191.52
Upazila: Babugonj
1 | BDRIDP/BAR/BAB/UN-RD/02 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m |  | 11570042.22 | eveyMÄ ewikvj-3 | M/S Hasan Construction | 70%
2 | BDRIDP/BAR/BAB/UN-St/02 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m. |  | 4179759.25 | eveyMÄ ewikvj-3 | M/S Saifuddin Traders | 80%
2 |  |  | #REF! | 15749801.47
1 | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. |  | 195850 | eveyMÄ ewikvj-3 | Md. Masum Hossain Gazi LCS No-1 | 80%
2 | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km. |  | 285121 | eveyMÄ ewikvj-3 | Taslima LCS No-1 | 60%
3 | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km. |  | 381065 | eveyMÄ ewikvj-3 | Rajib Hossain LCS No-1 | 40%
4 | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km. |  | 300535 | eveyMÄ ewikvj-3 | Md. Liton Hossain LCS No-1 | 55%
5 | BDRIDP/BAR/BAB/CCA-EW/04 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m. |  | 354810 | eveyMÄ ewikvj-3 | Md. Kabir Sikder LCS No-1 | 80%
6 | BDRIDP/BAR/BAB/UN-EW/02 | Resectioning of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 290672 | 290672 | eveyMÄ ewikvj-3 | Md. Habibur Rohman LCS No-1 | 17%
6 |  |  | 290672 | 1808053
8 |  |  | #REF! | 17557854.47
Upazila: Muladi
1 | BDRIDP/BAR/MUL/CCA-St/05 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal. | 10068184 | 7727638.21 | gyjv`x ewikvj-3 | M/S Shafi Enterprise | 50%
2 | BDRIDP/BAR/MUL/UN-St/02 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District. |  | 12881428.65 | gyjv`x ewikvj-3 | PTSL-MOTREE (PVT) LTD | 0%
3 | BDRIDP/BAR/MUL/UZ-St/03 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District. |  | 16131650.67 | gyjv`x ewikvj-3 | PTSL-MOTREE (PVT) LTD | 0%
4 | BDRIDP/BAR/MUL/UN-St/01 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District. |  | 14216012.55 | gyjv`x ewikvj-3 | M/S Islam Brothers | 0%
5 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. |  | 219911366.67 | gyjv`x ewikvj-3 | M/S Islam Brothers | 0%
6 | BDRIDP/BAR/MUL/UZ-St/04 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal. |  | 21153309.3 | gyjv`x ewikvj-3 | M/S Orien Trading & Builders |  |  | P.S Submit
6 |  | Sub Total: | 10068184 | 292021406.05
1 | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. |  | 323312 | gyjv`x ewikvj-3 | Fokrul Ahosan LCS No-1 | 30%
1 |  | Sub Total: | 0 | 323312
7 |  | Grand Total: | 10068184 | 292344718.05
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 6864308 | 6860287.95 | ‡g‡nw›`MÄ ewikvj-4 | M/S Hasan Construction | 30%
2 | BDRIDP/BAR/MHN/UZ-Rd/02 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila,Barisal. |  | 10492643.13 | ‡g‡nw›`MÄ ewikvj-4 | M/S Lutful Kabir | 0%
2 |  |  | 6864308 | 17352931.08
1 | BDRIDP/BAR/MHN/UZ-EW/01 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1000m-1600m | 164958 | 164958 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-1 | 40%
2 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1600m-2350m | 379812 | 379812 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-2 | 55%
3 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 2350m-3250m | 297385 | 297385 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-3 | 50%
4 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 3250m-4000m | 254707 | 254707 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-4 | 55%
4 |  |  | 1096862 | 1096862
6 |  |  | 7961170 | 18449793.08
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. |  | 10088368.67 | ewikvj m`i ewikvj-5 | M/S Rupali Construction | 95%
2 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 207108 | 8773072.65 | ewikvj m`i ewikvj-5 | M/S Hasan Construction | 60%
3 | BDRIDP/BAR/SDR/CCA-Rd/09 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari. | 937125 | 10801668.14 | ewikvj m`i ewikvj-5 | M/S Khondokear Enterprise | 70%
4 | BDRIDP/BAR/SDR/CCA-Rd/10 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila,Barisal. |  | 8550422.1 | ewikvj m`i ewikvj-5 | M/S Sirajul Alam Sikder | 0%
5 | BDRIDP/BAR/SDR/UN-Rd/01 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road. |  |  | ewikvj m`i ewikvj-5 |  |  |  | E-Tender Under Process.
6 | BDRIDP/BAR/SDR/UZ-Rd/01 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal. |  |  | ewikvj m`i ewikvj-5 |  |  |  | E-Tender Under Process.
7 | BDRIDP/BAR/SDR/UN-Rd/02 | Improvement of Charkawa Kheyaghat - Durgapur hat road from Ch. 3000m - 3600m.under Sadar Upazila Barisal District. |  |  | ewikvj m`i ewikvj-5 |  |  |  | E-Tender Under Process.
7 |  | Sub-Total: | 1144233 | 38213531.56
1 | BDRIDP/BAR/SDR/CCA-EW/03 | Resectioning of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge). |  | 400044 | ewikvj m`i ewikvj-5 | Fatema Begum LCS No-1 | 92%
2 | BDRIDP/BAR/SDR/CCA-EW/04 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 2557m-3280m. | 305905 | 305905 | ewikvj m`i ewikvj-5 | Md. Hemayet Howlader LCS No-1 | 10%
3 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 3280m-4580m | 256209 | 256209 | ewikvj m`i ewikvj-5 | Md. Mojibor Rohman Sikder LCS No-2 | 50%
4 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 4580m-6647m | 189642 | 189642 | ewikvj m`i ewikvj-5 | Mosharof Hossain Shikder LCS No-3 | 60%
4 |  | Sub-Total: | 751756 | 1151800
11 |  | Grand Total: | 1895989 | 39365331.56
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 |  | 3523866.83 | ev‡KiMÄ ewikvj-6 | M/S Khondokear Brothers | 75%
2 | BDRIDP/BAR/BAK/CCA-Rd/03 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal. |  | 16139041.07 | ev‡KiMÄ ewikvj-6 | Md. Sumsudhoa Mollick | 42%
3 | BDRIDP/BAR/BAK/UN-Rd/03 | Improvement of road from Faridpur Hat Kheya Ghat Durgapasa UP office Gobindapur Bothtala via Kakordha Bazar Road, a Earth Work from Ch. 4860m 7320m.b Bituminus Carpeting from Ch. 4860m 7470m.c Construction of 1 No. 1.60mx1.60m RCC Box Culvert at Ch. 7435m. under Bakergonj upazila Barisal District. Salvage Cost Tk. 3733841.00 |  |  | ev‡KiMÄ ewikvj-6 |  |  |  | E-Tender Under Process.
4 | BDRIDP/BAR/BAK/CCA-Rd/04 | Improvement of road from west Faridpur Ajgor Sikder Bari to DC road Ferry-ghat via H/O Rahim Mrida Road, a Earth Work from Ch. 0.0 - 1300.00m. b Bituminus Carpeting from Ch. 0.0 - 1300m c Construction of 1 No. 4.0m x 4.0m RCC Box Culvert at Ch. 425m. under Bakergonj upazila Barisal District. |  |  | ev‡KiMÄ ewikvj-6 |  |  |  | E-Tender Under Process.
4 |  |  | 0 | 19662907.9
1 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m |  | 131861 | ev‡KiMÄ ewikvj-6 | Anwar Hossain LCS No-01 | 92%
2 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m. |  | 256728 | ev‡KiMÄ ewikvj-6 | Md. Babul Howlader LCS No-02 | 90%
3 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m |  | 230734 | ev‡KiMÄ ewikvj-6 | Md. Joynal Abadin LCS No-03 | 90%
4 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m |  | 224792 | ev‡KiMÄ ewikvj-6 | Md. Royon Mollah LCS No-04 | 90%
5 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m |  | 233429 | ev‡KiMÄ ewikvj-6 | Md. Shahidul Sharif LCS No-05 | 95%
6 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m |  | 205799 | ev‡KiMÄ ewikvj-6 | H M Shamsul Huda LCS No-06 | 95%
7 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m |  | 243498 | ev‡KiMÄ ewikvj-6 | Md. Hanif LCS No-07 | 99%
8 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m |  | 230149 | ev‡KiMÄ ewikvj-6 | Md. Amir Ali Khan LCS No-08 | 90%
9 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m |  | 249498 | ev‡KiMÄ ewikvj-6 | Md. Monir Hossain LCS No-09 | 90%
10 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m |  | 222257 | ev‡KiMÄ ewikvj-6 | Md. Shalim Mridha LCS No-10 | 90%
10 |  | Sub Total: | 0 | 2228745
14 |  | Grand Total: | 0 | 21891652.9

## Progress (2)
Barisal Division Rural Infrastructure Development Project
µwgK bs | c¨v‡KR bs | ¯‹x‡gi bvg | Salvage Materials | Pzw³g~j¨ | Dc‡Rjv/Avmb | wVKv`v‡ii bvg | AMÖMwZ | mgm¨v | gšÍe¨
1 | 2 | 3 | 4 | 4 | 5 | 6 | 7 | 8 | 9
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/CCA-Rd/02 | Improvement of road from Gournadi Highway Thana Connecting road under Gournadi Upazila. |  | 1612193 | ‡MŠib`x ewikvj-1 | M/S Tamim Enterprise | 100% |  | Final
2 | BDRIDP/BAR /GOU/UN-Rd/01 | (a) Improvement of Road from Sarikal GC to Shaheber char Bazar via Nalchira Bazar ch. 5555m-7055m), (b) Construction of 2 nos U-drain at ch.599m & 6555m on the same road Under Gournadi Upazila, District-Barisal. |  | 10357650.8 | ‡MŠib`x ewikvj-1 | M/S Islam Brothers | 100% |  | Final
3 | BDRIDP/BAR /GOU/UZ-Rd/01 | (a) Improvement of Road from Gournadi Bandar GC to Muladi GC via Kutubpur Bazar at ch. 0m-630m), (b) Construction of 2 nos U-drain at ch. 205m & 364m on the same road Under Gournadi Upazila, District-Barisal. |  | 5399315 | ‡MŠib`x ewikvj-1 | M/S Islam Brothers | 100% |  | Final
4 | BDRIDP/BAR /GOU/UZ-Rd/02 | Improvement of illah (NHW) to Kalkini Upazila HQ via Tulatala Bazar at ch.2413m-3213m), Under Gournadi Upazila, District-Barisal. |  | 4898705 | ‡MŠib`x ewikvj-1 | M/S Sadman Builders | 100% |  | Final
5 | BDRIDP/BAR /GOU/UN-Rd/02 | (a) Improvement of Batazore GC to Pinglakathi Bazar via Pachim Chandrahar GPS at ch. 0m-1000m), (b)Construction of 1 nos U-drain at at ch.14m on the same road, (c) Construction 1v-2.3mx2.30m RCC Box Culvert at ch.527m & 1583m on the same road Under Gournadi Upazila, District-Barisal. |  | 8236744 | ‡MŠib`x ewikvj-1 | M/S Islam Brothers | 100% |  | Final
6 | BDRIDP/BAR/GOR/CCA-Rd/01 | Improvement of road from Maddam Hosnabad Nabarun RPS to Nezamuddin College by HBB at Ch.481-1492m (Nizamuddin Degree College road from freedom fighter Nizamuddin Shaheber Kaborstan via Madha hosnabad UP Member Md.Matiur Rahman Sarif Bari Bridge under Gouranadi upazila, Barisal District. |  | 2601109.88 | ‡MŠib`x ewikvj-1 | Md. Sirazul Islam Hanif | 100% |  | Final
7 | BDRIDP/BAR/GOR/UZ-Rd/03 | Improvement of Barthi Bazar (NHW) to Gournadi GC via Torky GC at ch.2150 - 4150m. |  | 13801595 | ‡MŠib`x ewikvj-1 | M/S Santu Traders | 100% |  | Final
8 | BDRIDP/BAR/GOR/UN-Rd/03 | Rehabilitation of road from Mahilara UP Office to Chadshi Hat via Bilogram Bazar (A. Rob Chokder House to Chadshi Hat road) road By BC from Ch. 5370-6900m. |  | 6124969 | ‡MŠib`x ewikvj-1 | M/S Santu Traders | 100% |  | Final
9 | BDRIDP/BAR/GOR/UN-Rd(R)/04 | Rehabilitation of road from Mahilara UP office to Chadshi hat via Billogram Bazar road from Ch. 3740-4850m (Salvage Material Cost Tk. 11,01,418.00) |  | 5623536 | ‡MŠib`x ewikvj-1 | M/S Santu Traders | 100%
10 | BDRIDP/BAR/GOR/UN-St/01 | Construction of 2-Vent 4.30mx4.30m RCC Box Culvert on Mahilara UP office to Chadshi hat via Billogram Bazar road at Ch. 4200m. |  | 2069109 | ‡MŠib`x ewikvj-1 | M/S Santu Traders | 100% |  | Final
11 | BDRIDP/BAR/GOR/CCA-St/01 | Construction of 3 Nos Single Vent 4.30mx4.30m RCC Box Culvert & 2 nos U-Drain on Battala Kapali bari Bridge (NHW) to Khanjapur High School road at ch. 95m,270m,1276m564m&970m Under Gournadi Upazila, District-Barisal e-ID : 22284 |  | 6946789.2 | ‡MŠib`x ewikvj-1 | M/S Siam Enterprise | 100% |  | Final
12 | BDRIDP/BAR/GOR/CCA-Rd/03 | Improvement of road from Battala Kapali bari Bridge (NHW) to Khanjapur High School road by BC from Ch.00 - 1656m Under Gournadi Upazila, District-Barisal e-ID : 22285 |  | 7343257.29 | ‡MŠib`x ewikvj-1 | M/S Siam Enterprise | 100% |  | Final
13 | BDRIDP/BAR/GOR/UZ-Rd/04 | Improvement of Barthi Bazar (NHW) to Burghata bus Stand (NHW) via Amanagong hat at Ch. 450-2450m. e-ID : 19611 |  | 13172831.8 | ‡MŠib`x ewikvj-1 | M/S Howlader Constructure | 100%
13 |  |  | 0 | 88187804.97
1 | BDRIDP/BAR/GOR/UN-EW/01 | Improvement of road from Mahilara UP Office to Chadshi hat via Billogram Bazar road By Earth Filling Work from Ch. 3740m-4850m. |  | 349519 | ‡MŠib`x ewikvj-1 | Anjur Ali Sarder LCS No-1 | 100%
2 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Gournadi GC via Torky GC at Ch. 2150m-4150m by earth . |  | 223623 | ‡MŠib`x ewikvj-1 | Md Shalim Khalifa LCS-1 | 100%
3 |  |  |  | 69892 | ‡MŠib`x ewikvj-1 | Sunil Joydhar LCS-2 | 100%
4 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Burghata Bus Stand (NHW) via Amanothgonj hat at Ch. 450m-2450m by earth. |  | 300092 | ‡MŠib`x ewikvj-1 | Md Mahabub Khan LCS-1 | 100%
5 |  |  |  | 209955 | ‡MŠib`x ewikvj-1 | Md Mohasin Sharder LCS-2 | 100%
5 |  |  | 0 | 1153081
18 |  |  | 0 | 89340885.97
Upazila: Agailjhara
1 | BDRIDP/BAR /AGL/CCA-Rd/01 | Improvement of Road by BC from Rathkhola Bazar-Bhadrapara Road (ch. 0m-1000m) Under Agailjhara Upazila, District-Barisal. |  | 5599756.34 | Av‰MjSvov ewikvj-1 | M/S Talukder Enterprise | 100% |  | Final
2 | BDRIDP/BAR/AGL/CCA-Rd/02 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila,Barisal. |  | 4583839 | Av‰MjSvov ewikvj-1 | M/S Mitushi Traders | 0% |  | W/O Cancel
3 | BDRIDP/BAR/AGL/CCA-Rd(R)/06 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m. | 196459 | 5158284.22 | Av‰MjSvov ewikvj-1 | M/S Sharif Enterprise | 100% |  | Final
4 | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. |  | 1771918.99 | Av‰MjSvov ewikvj-1 | M/S Sharif Enterprise | 100%
5 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 791797 | 15592739.8 | Av‰MjSvov ewikvj-1 | M/S Sharif Enterprise | 95%
6 | BDRIDP/BAR/AGL/UZ-Rd/02 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by BC from Ch. 3800m-5800m. |  | 11288255.96 | Av‰MjSvov ewikvj-1 | M/S Sraboni Construction | 100% |  | Final
7 | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m |  | 6375868.44 | Av‰MjSvov ewikvj-1 | M/S Sarniabad Enterprise | 86%
8 | BDRIDP/BAR/AGL/CCA-Rd/04 | Improvement of road from Poiser hat GC-Ramshil Bazar via Trimukhi road by BC from Ch. 0.00m-1000m. |  | 5538660.26 | Av‰MjSvov ewikvj-1 | M/S Shafique Brothers | 100% |  | Final
9 | BDRIDP/BAR/AGL/CCA-Rd(R)/05 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m. | 288401 | 4400152.34 | Av‰MjSvov ewikvj-1 | M/S Helal Traders | 100%
10 | BDRIDP/BAR/AGL/UZ-Rd(R)/01 | Rehabilitation of Barthi - Valukshi - Magura- Ambari-Bakalhat road by BC at ch.5870-7880m. |  | 13383052 | Av‰MjSvov ewikvj-1 | M/S Santu Traders | 100% |  | Final
11 | BDRIDP/BAR/AGL/CCA-Rd/07 | Improvement of road from Biplob Serniabad House to Hazi Musa House road By BC from ch.00-400m. e-ID : 22281 |  | 2012714.3 | Av‰MjSvov ewikvj-1 | M/S Serniabad Enterprise | 100% |  | Final
12 | BDRIDP/BAR/AGL/CCA-Rd/ 02 | Improvement of road from Seral - Goila road via Shahid Serniabad House - Tamer Jame Mosjid(Tamer Girls High School-Seral Community Center) by BC (Ch.0.0 - 975m) under Agailjhara Upazila,Barisal. | 7232587 | 7230073.2 | Av‰MjSvov ewikvj-1 | M/S Serniabad Traders | 50%
12 |  |  | 1276657 | 82935314.85
1 | BDRIDP/BAR/AGL/CCA-EW/01 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal. |  | 153224 | Av‰MjSvov ewikvj-1 | Ramesh Chandra Shikari LCS No-1 | 100%
2 |  |  |  | 148896 | Av‰MjSvov ewikvj-1 | Md Halim Talukder LCS No-2 | 100%
3 | BDRIDP/BAR/AGL/CCA-EW/02 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. |  | 216905 | Av‰MjSvov ewikvj-1 | Abdul Hakim Molla LCS No-1 | 100%
4 |  | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. |  | 231753 | Av‰MjSvov ewikvj-1 | Anukul Chandra Barai LCS No-2 | 100%
5 | BDRIDP/BAR/AGL/CCA-EW/03 | Resectioning of road from Temar Bastala to Hawla Bridge via Nagar GPS-Talbazar-lichermath Bazar road from Ch. 3840-4840m. |  | 344680 | Av‰MjSvov ewikvj-1 | Nolini Halder LCS No-1 | 100%
6 |  |  |  | 230350 | Av‰MjSvov ewikvj-1 | Susen Bala LCS No-2 | 100%
7 | BDRIDP/BAR/AGL/UZ-EW/01 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal. |  | 124341 | Av‰MjSvov ewikvj-1 | Md. Sohrab Howlader LCS No-1 | 100% |  | Final
8 |  |  |  | 307876 | Av‰MjSvov ewikvj-1 | Md. Mosharef Sheikh LCS No-2 | 100% |  | Final
9 |  |  |  | 329106 | Av‰MjSvov ewikvj-1 | Abdul Rashid Howlader LCS No-3 | 100% |  | Final
10 |  |  |  | 330529 | Av‰MjSvov ewikvj-1 | Matleb Howlader LCS No-4 | 100% |  | Final
11 | BDRIDP/BAR/AGL/UN-EW/01 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal. |  | 201404 | Av‰MjSvov ewikvj-1 | Mahim Baishnab LCS No-1 | 100%
12 |  |  |  | 289300 | Av‰MjSvov ewikvj-1 | Sudhir Kumar Ojha LCS No-2 | 100%
13 |  |  |  | 288022 | Av‰MjSvov ewikvj-1 | Banendra Nath Panday LCS No-3 | 100%
14 |  |  |  | 207336 | Av‰MjSvov ewikvj-1 | Rabindranath Sarker LCS No-4 | 100%
15 |  |  |  | 205837 | Av‰MjSvov ewikvj-1 | Nirmal Ghatak LCS No-5 | 100%
16 |  |  |  | 207632 | Av‰MjSvov ewikvj-1 | Bebek Pandey LCS No-6 | 100%
17 |  |  |  | 205952 | Av‰MjSvov ewikvj-1 | Pangkoj Joydhor LCS No-7 | 100%
18 | BDRIDP/BAR/AGL/CCA-EW/01 | Resectioning of Road from Seral-Goila road via Shahid Serniabad House-Tamer Jame Mosjid (Tamer Girls High School-Seral Community Center) by Earth at Ch. 0.00m-975m. |  | 317636 | Av‰MjSvov ewikvj-1 | LCS No-1 | 50%
18 |  |  | 0 | 4340779
30 |  |  | 1276657 | 87276093.85
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. |  | 5567698.82 | DwRicyi ewikvj-2 | M/S Safi Enterprise | 100% |  | Final
2 | BDRIDP/BAR/UZP/CCA-St/02 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m. |  | 2015457.24 | DwRicyi ewikvj-2 | Md Zakir Hossain Mia | 100% |  | Final
3 | BDRIDP/BAR/UZP/CCA-Rd/01 | Improvement of road from Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market, Nurani Madrasha & H/O Mr.Habibur Rahman (Beer Protik) by BC from Ch.0.00-1500m under Uzirpur Upazila, Barisal. |  | 5167677 | DwRicyi ewikvj-2 | Md Sirazul Islam Hanif | 100% |  | Final
4 | BDRIDP/BAR/UZP/CCA-Rd/02 | Improvement of road from Paschim Satla WAPDA to Satla Kheyaghat via H/O Fazlul Hoque Hawlader & Mosque By HBB from Ch. 0.00-375m. |  | 1225909.58 | DwRicyi ewikvj-2 | M/S Lutful Kabir | 100% |  | Final
5 | BDRIDP/BAR/UZP/CCA-St/03 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m. |  | 2682855.6 | DwRicyi ewikvj-2 | Md Zakir Hossain Mia | 100% |  | Final
6 | BDRIDP/BAR/UZP/UZ-Rd(R)/01 | Rehabilitation of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) road from Ch. 0.00m-2100m. |  | 8522561.6 | DwRicyi ewikvj-2 | M/S G M Construction | 100% |  | Final
7 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 18314961 | 14275617.27 | DwRicyi ewikvj-2 | M/S Hasan Construction | 30%
8 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 14753928 | 11501091.23 | DwRicyi ewikvj-2 | M/S Hasan Construction | 30%
9 | BDRIDP/BAR/UZP/UZ-RdR/04 | Rehabilitation of Harta ChowmuhaniBisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 |  |  | DwRicyi ewikvj-2 |  |  |  | Evaluation on going
10 | BDRIDP/BAR/UZP/UN-Rd/01 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m. |  |  | DwRicyi ewikvj-2 |  |  |  | Evaluation on going
10 |  | Sub-Total: | 33068889 | 50958868.34
1 | BDRIDP/BAR/UZP/UZ-EW/01 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 0.00m-700m. | 258990 | 258990 | DwRicyi ewikvj-2 | Yasin Sarder LCS No-1 | 100% |  | Final
2 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 700m-1400m. | 284900 | 284900 | DwRicyi ewikvj-2 | Iqbal Hossan LCS No-2 | 100% |  | Final
3 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 1400m-2100m. | 278170 | 278170 | DwRicyi ewikvj-2 | Supian LCS No-3 | 100% |  | Final
4 | BDRIDP/BAR/UZP/UZ-EW/02 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 0.00m-1100m. | 418543 | 418543 | DwRicyi ewikvj-2 | Md. Shahidul Islam LCS No-1 | 70%
5 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1100m-1900m. | 451503 | 451503 | DwRicyi ewikvj-2 | Md. Khalilur Rahman LCS No-2 | 70%
6 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1900m-2605m. | 491755 | 491755 | DwRicyi ewikvj-2 | Habibur Bapari LCS No-3 | 70%
7 | BDRIDP/BAR/UZP/UZ-EW/03 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 1754m-2850m. | 421703 | 421703 | DwRicyi ewikvj-2 | Kamrun Nesa LCS No-1 | 65%
8 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 2850m-3650m. | 466527 | 466527 | DwRicyi ewikvj-2 | Rubina Begum LCS No-2 | 65%
9 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 3650m-4050m. | 342538 | 342538 | DwRicyi ewikvj-2 | Monzu Begum LCS No-3 | 65%
10 | BDRIDP/BAR/UZP/UN-EW/01 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3400m-3900m By Earth. | 434519 | 434519 | DwRicyi ewikvj-2 | Md. Ziaul Haque LCS No-1 | 10%
11 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3900m-4300m By Earth. | 437099 | 437099 | DwRicyi ewikvj-2 | Khokon Sharder LCS No-2 | 10%
12 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4300m-4900m By Earth. | 461279 | 461279 | DwRicyi ewikvj-2 | Rofiqul Islam LCS No-3 | 10%
13 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4900m-5740m By Earth. | 310321 | 310321 | DwRicyi ewikvj-2 | Nurul Hoq Sikder LCS No-4 | 10%
13 |  | Sub-Total: | 5057847 | 5057847
23 |  | Grand Total: | 38126736 | 56016715.34
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 7013799 | 5349539.02 | evbvixcvov ewikvj-2 | M/S Saleha Enterprise | 35%
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m ,1 No.3.0m x 3.0m , 2Nos.4.0m x 4.0m , 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 7531517 | 5461652.5 | evbvixcvov ewikvj-2 | M/S Soma Enterprise | 60%
3 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District |  |  | evbvixcvov ewikvj-2 |  |  |  | Evaluation on going
4 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District |  |  | evbvixcvov ewikvj-2 |  |  |  | Evaluation on going
4 |  |  | 14545316 | 10811191.52
1 | BDRIDP/BAR/BAN/UZ-EW/01 | Resectioning of Banaripara-Harta Road at Ch. 4665m-6066m. | 441816.72 | 441816.72 | evbvixcvov ewikvj-2 | Zakir Hossain LCS No: 1 | 100%
2 |  | Resectioning of Banaripara-Harta Road at Ch. 6066m-7252m. | 415870.76 | 415870.76 | evbvixcvov ewikvj-2 | Kohinoor Begum LCS No: 2 | 100%
3 |  | Resectioning of Banaripara-Harta Road at Ch. 7252m-7702m. | 398985.83 | 398985.83 | evbvixcvov ewikvj-2 | Baschu Forazi LCS No: 3 | 100%
4 |  | Resectioning of Banaripara-Harta Road at Ch. 7702m-8152m. | 384544.28 | 384544.28 | evbvixcvov ewikvj-2 | Abdul Karim LCS No: 4 | 100%
5 |  | Resectioning of Banaripara-Harta Road at Ch. 8152m-8752m. | 463598.7 | 463598.7 | evbvixcvov ewikvj-2 | Horolal Mondol LCS No: 5 | 100%
6 |  | Resectioning of Banaripara-Harta Road at Ch. 8752m-9352m. | 461929.48 | 461929.48 | evbvixcvov ewikvj-2 | Mithu Howlader LCS No: 6 | 100%
7 |  | Resectioning of Banaripara-Harta Road at Ch. 9352m-9760m. | 374441.97 | 374441.97 | evbvixcvov ewikvj-2 | Md. Khairul Islam LCS No: 7 | 100%
7 |  |  | 2941187.74 | 2941187.74
11 |  |  | 17486503.74 | 13752379.26
Upazila: Babugonj
1 | BDRIDP/BAR/BABU/CCA-Rd/01 | Improvement of road from Babugonj Agorpur GC to Mr. Younusur Rahman (Divisional Commissioner) house via Clubgonj hat by Carpeting from Ch. 750-1400m & 0.00-1550m. | 944029 | 10750396.05 | eveyMÄ ewikvj-3 | M/S Lutful Kobir | 100% |  | Final
2 | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km. | 421856 | 10173103.86 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100% |  | Final
3 | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 1035938 | 19386557.17 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100% |  | Final
4 | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. |  | 10428682 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100% |  | Final
5 | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 184122 | 3071060.04 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100% |  | 715wgt †PB‡b‡R KvR Kiv hv‡e bv¦
6 | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 199349 | 4968549.43 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100%
7 | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 62866 | 2095536.41 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100%
8 | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 150637 | 2076355.09 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100%
9 | BDRIDP/BAR/BAB/UN-St/01 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m. | 41933 | 1029755.17 | eveyMÄ ewikvj-3 | M/S Lutful Kobir | 100% |  | Final
10 | BDRIDP/BAR/BAB/UN-Rd(R)/01 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m. | 2442317 | 5193526.54 | eveyMÄ ewikvj-3 | M/S Alvi Construction | 100% |  | Final
11 | BDRIDP/BAR/BAB/CCA-Rd/05 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District. |  | 14979470.55 | eveyMÄ ewikvj-3 | M/S Atique Construction | 100% |  | Final
12 | BDRIDP/BAR/BAB/UN-RD/02 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m |  | 11570042.22 | eveyMÄ ewikvj-3 | M/S Hasan Construction | 70%
13 | BDRIDP/BAR/BAB/UN-St/02 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m. |  | 4179759.25 | eveyMÄ ewikvj-3 | M/S Saifuddin Traders | 80%
13 |  |  | 5483047 | 99902793.78
1 | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. |  | 195850 | eveyMÄ ewikvj-3 | Md. Masum Hossain Gazi LCS No-1 | 80%
2 | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km. |  | 285121 | eveyMÄ ewikvj-3 | Taslima LCS No-1 | 60%
3 | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km. |  | 381065 | eveyMÄ ewikvj-3 | Rajib Hossain LCS No-1 | 40%
4 | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km. |  | 300535 | eveyMÄ ewikvj-3 | Md. Liton Hossain LCS No-1 | 55%
5 | BDRIDP/BAR/BAB/CCA-EW/04 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m. |  | 354810 | eveyMÄ ewikvj-3 | Md. Kabir Sikder LCS No-1 | 80%
6 | BDRIDP/BAR/BAB/UN-EW/02 | Resectioning of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 290672 | 290672 | eveyMÄ ewikvj-3 | Md. Habibur Rohman LCS No-1 | 17%
6 |  |  | 290672 | 1808053
19 |  |  | 5773719 | 101710846.78
Upazila: Muladi
1 | BDRIDP/BAR/MUL/UZ-St/01 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m. |  | 8772459.2 | gyjv`x ewikvj-3 | M/S Misi Construction | 100% |  | Final
2 | BDRIDP/BAR/MUL/UZ-Rd/01 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m. |  | 20744407.41 | gyjv`x ewikvj-3 | M/S Lutful Kobir | 100% |  | Final
3 | BDRIDP/BAR/MUL/CCA-Rd/01 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District. |  | 3545269 | gyjv`x ewikvj-3 | M/S Santu Traders | 100% |  | Final
4 | BDRIDP/BAR/MUL/CCA-Rd/02 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District. |  | 2347546 | gyjv`x ewikvj-3 | M/S Santu Traders | 100% |  | Final
5 | BDRIDP/BAR/MUL/CCA-St/02 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m. |  | 1762404.98 | gyjv`x ewikvj-3 | M/S Lutful Kobir | 100% |  | Final
6 | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m |  | 3683201.71 | gyjv`x ewikvj-3 | M/S Lutful Kobir | 100% |  | Final
7 | BDRIDP/BAR/MUL/CCA-Rd(R)/04 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m. | 1518637 | 7104572.13 | gyjv`x ewikvj-3 | M/S Topu Enterprise | 100% |  | Final
8 | BDRIDP/BAR/MUL/CCA-Rd/05 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m. |  | 4824539 | gyjv`x ewikvj-3 | M/S Topu Enterprise | 100% |  | Final
9 | BDRIDP/BAR/MUL/CCA-Rd/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m. |  | 2947338.02 | gyjv`x ewikvj-3 | Md Sirazul Islam Hanif | 100% |  | Final
10 | BDRIDP/BAR/MUL/CCA-St/01 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m |  | 368648.25 | gyjv`x ewikvj-3 | M/S Sraboni Enterprise | 100% |  | Final
11 | BDRIDP/BAR/MUL/CCA-Rd/06 | Improvement of road from Char Kalekhan Goni Bari-Khalil Bepari Bari road by BC from Ch. 0.00m-1550m. |  | 7059418.41 | gyjv`x ewikvj-3 | Md. Khair Hossain | 100% |  | Final
12 | BDRIDP/BAR/MUL/CCA-St/04 | Construction of 1 vent 4.00m×4.00m and 1 vent 1.00m×1.00m RCC Box Culvert on Char Kalekhan Goni Bari-Khalil Bepari Bari road at Ch.182m & 330m. |  | 1462533.11 | gyjv`x ewikvj-3 | Md. Khair Hossain | 100% |  | Final
13 | BDRIDP/BAR/MUL/CCA-St/05 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal. | 10068184 | 7727638.21 | gyjv`x ewikvj-3 | M/S Shafi Enterprise | 50%
14 | BDRIDP/BAR/MUL/UN-St/02 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District. |  | 12881428.65 | gyjv`x ewikvj-3 | PTSL-MOTREE (PVT) LTD | 0%
15 | BDRIDP/BAR/MUL/UZ-St/03 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District. |  | 16131650.67 | gyjv`x ewikvj-3 | PTSL-MOTREE (PVT) LTD | 0%
16 | BDRIDP/BAR/MUL/UN-St/01 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District. |  | 14216012.55 | gyjv`x ewikvj-3 | M/S Islam Brothers | 0%
17 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. |  | 219911366.67 | gyjv`x ewikvj-3 | M/S Islam Brothers | 0%
18 | BDRIDP/BAR/MUL/UZ-St/04 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal. |  | 21153309.3 | gyjv`x ewikvj-3 | M/S Orien Trading & Builders |  |  | P.S Submit
18 |  | Sub Total: | 11586821 | 356643743.27
1 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m. |  | 334778 | gyjv`x ewikvj-3 | Khorshed Khan LCS No-1 | 100% |  | Final
2 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m. |  | 403489 | gyjv`x ewikvj-3 | Md. Alamgir Hossain LCS No-2 | 100% |  | Final
3 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m. |  | 386512 | gyjv`x ewikvj-3 | Md. Baschu Sharder LCS No-3 | 100% |  | Final
4 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m. |  | 371303 | gyjv`x ewikvj-3 | Abdus Salam Sharder LCS No-4 | 100% |  | Final
5 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m. |  | 372013 | gyjv`x ewikvj-3 | Md. Bakiullah Sharder LCS No-5 | 100% |  | Final
6 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m. |  | 374943 | gyjv`x ewikvj-3 | Md. Shalim LCS No-6 | 100% |  | Final
7 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m. |  | 374353 | gyjv`x ewikvj-3 | Sukkur Ahmed Khan LCS No-7 | 100%
8 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m. |  | 369858 | gyjv`x ewikvj-3 | Nazma LCS No-8 | 100%
9 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m. |  | 397315 | gyjv`x ewikvj-3 | Most. Jasmin Akter LCS No-9 | 100%
10 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m. |  | 428100 | gyjv`x ewikvj-3 | Rashida LCS No-10 | 100%
11 | BDRIDP/BAR/MUL/CCA-EW/01 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District. |  | 221909 | gyjv`x ewikvj-3 | Md Fazlu Tafader LCS No-1 | 100% |  | Final
12 | BDRIDP/BAR/MUL/CCA-EW/02 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District. |  | 239879 | gyjv`x ewikvj-3 | Md Kabir Hossain LCS No-1 | 100% |  | Final
13 | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. |  | 323312 | gyjv`x ewikvj-3 | Fokrul Ahosan LCS No-1 | 30%
14 | BDRIDP/BAR/MUL/CCA-EW/04 | Resectioning of road from Char Kalekhan Goni Bari-khalil Bepari bari road by Earth work from Ch. 0.00m-1550m. | 101268 | 101268 | gyjv`x ewikvj-3 | Md. Mojibor Rohman LCS No-1 | 100% |  | Final
14 |  | Sub Total: | 101268 | 4699032
32 |  | Grand Total: | 11688089 | 361342775.27
Upazila: Hizla
1 | BDRIDP/BAR/HZL/UZ-Rd(R)/01 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m. | 1476772 | 5645230.7 | wnRjv ewikvj-4 | M/S Oshin Enterprise | 100% |  | Final
1 |  |  | 1476772 | 5645230.7
1 | BDRIDP/BAR/HZL/UZ-EW/01 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 0.00m-325m | 226562 | 226562 | wnRjv ewikvj-4 | Md. Humaun Kabir LCS No-1 | 100%
2 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 325m-650m | 220227 | 220227 | wnRjv ewikvj-4 | Md. Monju Noli LCS No-2 | 100%
3 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 650m-1000m | 217087 | 217087 | wnRjv ewikvj-4 | Md. Parvaz LCS No-3 | 100%
3 |  |  | 663876 | 663876
4 |  |  | 2140648 | 6309106.7
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/UZR(R)-Rd/01 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal. |  | 4973018 | ‡g‡nw›`MÄ ewikvj-4 | M/S Santu Traders | 100% |  | Final
2 | BDRIDP/BAR/MHN/CCA-Rd/01 | Improvement of Mothertoli Bazar - Uttarchar road via Charekkaria road by BC (Ch.2170-3220m, Road Under Mehendigonj Upazila, District-Barisal. |  | 4515030 | ‡g‡nw›`MÄ ewikvj-4 | M/S Nahid Enterprise | 100% |  | Final
3 | BDRIDP/BAR/MHN/CCA-St/01 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal. |  | 184788 | ‡g‡nw›`MÄ ewikvj-4 | M/S Hasib Enterprise | 100% |  | Final
4 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 6864308 | 6860287.95 | ‡g‡nw›`MÄ ewikvj-4 | M/S Hasan Construction | 30%
5 | BDRIDP/BAR/MHN/UZ-Rd/02 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila,Barisal. |  | 10492643.13 | ‡g‡nw›`MÄ ewikvj-4 | M/S Lutful Kabir | 0%
5 |  |  | 6864308 | 27025767.08
1 | BDRIDP/BAR/MHN/CCA-EW/01 | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 0.00m-600m by Earth. | 346489 | 346489 | ‡g‡nw›`MÄ ewikvj-4 | Nizam Uddin Talukder LCS No-1 | 100%
2 |  | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 600m-1200m by Earth. | 421652 | 421652 | ‡g‡nw›`MÄ ewikvj-4 | Md. Sadak LCS No-2 | 100%
3 |  | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 1200m-1610m by Earth. | 258058 | 258058 | ‡g‡nw›`MÄ ewikvj-4 | Md. Faruk Buiya LCS No-3 | 100%
4 | BDRIDP/BAR/MHN/UZ-EW/01 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1000m-1600m | 164958 | 164958 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-1 | 40%
5 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1600m-2350m | 379812 | 379812 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-2 | 55%
6 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 2350m-3250m | 297385 | 297385 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-3 | 50%
7 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 3250m-4000m | 254707 | 254707 | ‡g‡nw›`MÄ ewikvj-4 | LCS No-4 | 55%
7 |  |  | 2123061 | 2123061
12 |  |  | 8987369 | 29148828.08
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/CCA-Rd/01 | Improvement of Bukhainagar Bridge to Abdul Aziz Khan's House via Shaluka GPS Road (Ch. 00-500m). |  | 1613223.41 | ewikvj m`i ewikvj-5 | M/S Talukder Enterprise | 100% |  | Final
2 | BDRIDP/BAR/SDR/CCA-Rd/02 | Improvement of Chandpura Mojidderhat-Saheberhat via Khontakhali School road from Ch. 1635-3192m. |  | 6279530.87 | ewikvj m`i ewikvj-5 | M/S G M Construction | 100% |  | Final
3 | BDRIDP/BAR/SDR/CCA-Rd/03 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m |  | 2294335.91 | ewikvj m`i ewikvj-5 | M/S Serajul Islam Hanif | 100% |  | Final
4 | BDRIDP/BAR/SDR/CCA-Rd/04 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 1230068 | 2238782.5 | ewikvj m`i ewikvj-5 | M/S Khondokar Borthers | 100% |  | Final
6 | BDRIDP/BAR/SDR/CCA-Rd/04 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366m. |  | 4037481 | ewikvj m`i ewikvj-5 | M/S Lutful Kabir | 100% |  | Final
7 | BDRIDP/BAR/SDR/CCA-St/04 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m. |  | 1027297.63 | ewikvj m`i ewikvj-5 | M/S Khondokar Borthers | 100% |  | Final
9 | BDRIDP/BAR/SDR/CCA-St/02 | Construction of 1.0 x 1.0m and 1.6 x1.6m RCC Box culvert on Kasem Defader Bari - Karnokati High School & College road at ch.773m & 526m e-ID: 17457 |  | 428108.82 | ewikvj m`i ewikvj-5 | M/S Khondokar Borthers | 100% |  | Final
10 | BDRIDP/BAR/SDR/CCA-Rd(R)/06 | Rehabilitation of road from Kasem Defader Bari - Karnokati High School & College road By BC from ch.310 - 1125m under Sadar upazila ,Barisal District [Salvaged Cost-Tk 4,97,038.00] |  | 3116111 | ewikvj m`i ewikvj-5 | M/S Oshin Enterprise | 100% |  | Final
11 | BDRIDP/BAR/SDR/CCA-Rd/07 | Improvement of road from Charkawa Nayani - Shaberhat via Durgapur hat (Barisal Sadar Upazila 7no. Charkawa union 1no.word nurul islam to Bank Jalal Bari Pull) road By HBB from Ch.0.0 - 1000m under Barisal-S Upazila,Barisal District. e-ID : 29367 |  | 2063060.77 | ewikvj m`i ewikvj-5 | M/S Apu Enterprise | 100% |  | Final
5 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. |  | 10088368.67 | ewikvj m`i ewikvj-5 | M/S Rupali Construction | 95%
8 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 207108 | 8773072.65 | ewikvj m`i ewikvj-5 | M/S Hasan Construction | 60%
12 | BDRIDP/BAR/SDR/CCA-Rd/09 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari. | 937125 | 10801668.14 | ewikvj m`i ewikvj-5 | M/S Khondokear Enterprise | 70%
13 | BDRIDP/BAR/SDR/CCA-Rd/10 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila,Barisal. |  | 8550422.1 | ewikvj m`i ewikvj-5 | M/S Sirajul Alam Sikder | 0%
14 | BDRIDP/BAR/SDR/UN-Rd/01 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road. |  |  | ewikvj m`i ewikvj-5 |  |  |  | E-Tender Under Process.
15 | BDRIDP/BAR/SDR/UZ-Rd/01 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal. |  |  | ewikvj m`i ewikvj-5 |  |  |  | E-Tender Under Process.
16 | BDRIDP/BAR/SDR/UN-Rd/02 | Improvement of Charkawa Kheyaghat - Durgapur hat road from Ch. 3000m - 3600m.under Sadar Upazila Barisal District. |  |  | ewikvj m`i ewikvj-5 |  |  |  | E-Tender Under Process.
16 |  | Sub-Total: | 2374301 | 61311463.47
1 | BDRIDP/BAR/SDR/CCA-EW/01 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. |  | 238242 | ewikvj m`i ewikvj-5 | Md. Giush Uddin LCS No-1 | 100% |  | Final
2 | BDRIDP/BAR/SDR/CCA-EW/02 | Resectioning of road from Charkawa Nayami-Shaheber hat via Durgapur hat (Barisal Sadar Upzila 7no. Charkawa union 1no word nurul islam to Bank Jalal Bari Pull) road from Ch. 0.00m-1000m. | 155407 | 155407 | ewikvj m`i ewikvj-5 | Md. Anowar Hossain Mridha LCS No-1 | 100%
3 |  |  | 228280 | 228280 | ewikvj m`i ewikvj-5 | Md. Jasim Uddin Milon LCS No-2 | 100%
4 | BDRIDP/BAR/SDR/CCA-EW/03 | Resectioning of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge). |  | 400044 | ewikvj m`i ewikvj-5 | Fatema Begum LCS No-1 | 92%
5 | BDRIDP/BAR/SDR/CCA-EW/04 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 2557m-3280m. | 305905 | 305905 | ewikvj m`i ewikvj-5 | Md. Hemayet Howlader LCS No-1 | 10%
6 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 3280m-4580m | 256209 | 256209 | ewikvj m`i ewikvj-5 | Md. Mojibor Rohman Sikder LCS No-2 | 50%
7 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 4580m-6647m | 189642 | 189642 | ewikvj m`i ewikvj-5 | Mosharof Hossain Shikder LCS No-3 | 60%
7 |  | Sub-Total: | 1135443 | 1773729
23 |  | Grand Total: | 3509744 | 63085192.47
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/CCA-Rd/01 | Improvement of road from South side Dhola Sluice Gate to Alim Meridha Bari (Vary) via Sikder Bari, Manik Member Bari, Shatghor & Mannan Princhpal Bari (East side of Hanua Bridge to Shatghor via Shikder Bari) By HBB from Ch. 0.00-1013m. |  | 3985608.82 | ev‡KiMÄ ewikvj-6 | M/S Nahid Enterprise | 100% |  | Final
2 | BDRIDP/BAR/BAK/UN-St/01 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 |  | 5345279.54 | ev‡KiMÄ ewikvj-6 | M/S Khondokear Brothers | 100% |  | Final
3 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 |  | 3523866.83 | ev‡KiMÄ ewikvj-6 | M/S Khondokear Brothers | 75%
4 | BDRIDP/BAR/BAK/UN-Rd(R)/02 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 1000m-4870m. e-ID : 22667 |  | 14682769.7 | ev‡KiMÄ ewikvj-6 | M/S Khondokear Brothers | 100% |  | Final
5 | BDRIDP/BAR/BAK/CCA-Rd(R)/02 | Rehabilitation of road from Gavikola Mannan Sikder Bari Foot Bridge to West side of Nilganj Foot Bridge via Moksad Khan,Kumarghudi & Kaptain Saye Bari by BC from Ch.00-810m [Salvaged Value Tk.10,53,654.00] e-ID : 29366 |  | 2619513.44 | ev‡KiMÄ ewikvj-6 | Md. Nasir Uddin | 100% |  | Final
6 | BDRIDP/BAR/BAK/CCA-Rd/03 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal. |  | 16139041.07 | ev‡KiMÄ ewikvj-6 | Md. Sumsudhoa Mollick | 42%
7 | BDRIDP/BAR/BAK/UN-Rd/03 | Improvement of road from Faridpur Hat Kheya Ghat Durgapasa UP office Gobindapur Bothtala via Kakordha Bazar Road, a Earth Work from Ch. 4860m 7320m.b Bituminus Carpeting from Ch. 4860m 7470m.c Construction of 1 No. 1.60mx1.60m RCC Box Culvert at Ch. 7435m. under Bakergonj upazila Barisal District. Salvage Cost Tk. 3733841.00 |  |  | ev‡KiMÄ ewikvj-6 |  |  |  | E-Tender Under Process.
8 | BDRIDP/BAR/BAK/CCA-Rd/04 | Improvement of road from west Faridpur Ajgor Sikder Bari to DC road Ferry-ghat via H/O Rahim Mrida Road, a Earth Work from Ch. 0.0 - 1300.00m. b Bituminus Carpeting from Ch. 0.0 - 1300m c Construction of 1 No. 4.0m x 4.0m RCC Box Culvert at Ch. 425m. under Bakergonj upazila Barisal District. |  |  | ev‡KiMÄ ewikvj-6 |  |  |  | E-Tender Under Process.
8 |  |  | 0 | 46296079.4
1 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m |  | 131861 | ev‡KiMÄ ewikvj-6 | Anwar Hossain LCS No-01 | 92%
2 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m. |  | 256728 | ev‡KiMÄ ewikvj-6 | Md. Babul Howlader LCS No-02 | 90%
3 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m |  | 230734 | ev‡KiMÄ ewikvj-6 | Md. Joynal Abadin LCS No-03 | 90%
4 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m |  | 224792 | ev‡KiMÄ ewikvj-6 | Md. Royon Mollah LCS No-04 | 90%
5 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m |  | 233429 | ev‡KiMÄ ewikvj-6 | Md. Shahidul Sharif LCS No-05 | 95%
6 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m |  | 205799 | ev‡KiMÄ ewikvj-6 | H M Shamsul Huda LCS No-06 | 95%
7 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m |  | 243498 | ev‡KiMÄ ewikvj-6 | Md. Hanif LCS No-07 | 99%
8 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m |  | 230149 | ev‡KiMÄ ewikvj-6 | Md. Amir Ali Khan LCS No-08 | 90%
9 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m |  | 249498 | ev‡KiMÄ ewikvj-6 | Md. Monir Hossain LCS No-09 | 90%
10 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m |  | 222257 | ev‡KiMÄ ewikvj-6 | Md. Shalim Mridha LCS No-10 | 90%
10 |  | Sub Total: | 0 | 2228745
18 |  | Grand Total: | 0 | 48524824.4
190 |  |  | 88989465.74 | 856507648.12
Accountant | [5 empty] | Senior Assistant Engineer
LGED, Barisal | [5 empty] | LGED, Barisal

## BG
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [18 empty] | Upto Month: February/17.
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Fund Received (Tk) | Bank Guarantee Expire Date | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 5 | 12 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/CCA-Rd/01 | Improvement of Bukhainagar Bridge to Abdul Aziz Khan's House via Shaluka GPS Road (Ch. 00-500m). | 506514170 |  | 0.5 |  |  |  |  | 2045654 |  | 1613223.41 | M/S Talukder Enterprise | 2014-09-06 | 16/06/14 | 16/09/14 |  | 100% | 1607918 | 99.67% |  |  | Final
2 | BDRIDP/BAR/SDR/CCA-Rd/02 | Improvement of Chandpura Mojidderhat-Saheberhat via Khontakhali School road from Ch. 1635-3192m. | 506514154 |  | 1.557 |  |  |  |  | 7466730 |  | 6279530.87 | M/S G M Construction | 2014-10-08 | 17/08/14 | 16/05/15 |  | 100% | 5481232 | 100% |  |  | Final
3 | BDRIDP/BAR/SDR/CCA-Rd/03 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m | 506514148 |  | 0.513 |  |  |  |  | 2809559 |  | 2294335.91 | M/S Serajul Islam Hanif | 24/07/14 | 2014-01-08 | 2015-01-02 |  | 70% | 1200000 | 52.3% |  | 2015-10-07 |  | 100% | 1094335.91
4 | BDRIDP/BAR/SDR/CCA-Rd/04 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 |  | 0.732 |  |  |  |  | 2900881 | 1230068 | 2238782.5 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 100% | 949457 | 100% |  |  | Final
5 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 90% | 8800000 | 87.23% |  | 2016-01-03 |  |  | 9079531.803
6 | BDRIDP/BAR/SDR/CCA-Rd/04 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366m. | 506515102 |  | 1 |  |  |  | 1.6 | 4543594 |  | 3864872.18 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2016-11-04 |  | 70% | 2350000 | 60.8% |  | 28/09/15 |  | 50% | -417563.91
7 | BDRIDP/BAR/SDR/CCA-St/04 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m. | 506514048 | [5 empty] | 8 | 1333966 |  | 1027297.63 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 100% | 1027297 | 100% |  |  | Final
8 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 506514048 |  | 2.782 |  |  |  |  | 10910419 | 207108 | 8773072.65 | M/S Hasan Construction | 2015-10-05 | 17/05/15 | 17/02/16 |  | 60% | 4300000 | 49.01% |  | 2015-02-11 |  | 70% | 1841150.855
9 | BDRIDP/BAR/SDR/CCA-St/02 | Construction of 1.0 x 1.0m and 1.6 x1.6m RCC Box culvert on Kasem Defader Bari - Karnokati High School & College road at ch.773m & 526m e-ID: 17457 | 506514176 | [5 empty] | 1.6 | 516289 |  | 428108.82 | M/S Khondokar Borthers | 15/06/15 | 23/06/15 | 22/12/15 |  | 100% | 425862 | 100% |  |  | Final
10 | BDRIDP/BAR/SDR/CCA-Rd(R)/06 | Rehabilitation of road from Kasem Defader Bari - Karnokati High School & College road By BC from ch.310 - 1125m under Sadar upazila ,Barisal District [Salvaged Cost-Tk 4,97,038.00] | 506514176 |  | 0.815 |  |  |  |  | 3385819 |  | 2576881 | M/S Oshin Enterprise | 2015-11-05 | 18/05/15 | 18/02/16 |  | 100% | 2619073 | 100% |  |  | Final
11 | BDRIDP/BAR/SDR/CCA-Rd/07 | Improvement of road from Charkawa Nayani - Shaberhat via Durgapur hat (Barisal Sadar Upazila 7no. Charkawa union 1no.word nurul islam to Bank Jalal Bari Pull) road By HBB from Ch.0.0 - 1000m under Barisal-S Upazila,Barisal District. e-ID : 29367 | 506514136 |  |  | 1 |  |  |  | 2430847 |  | 2063060.77 | M/S Apu Enterprise | 2015-03-11 | 2015-10-11 | 2016-10-05 |  | 100% | 2063045 | 100% |  |  | Final
12 | BDRIDP/BAR/SDR/CCA-Rd/09 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari. | 506515006 |  | 1.6 |  |  |  | 1.6 | 12590432 | 937125 | 10801668.14 | M/S Khondokear Brothers | 30/06/16 | 30/06/16 | 26/06/17 |  | 40% | 700000 | 6.48% |  | 26/06/17
13 | BDRIDP/BAR/SDR/CCA-Rd/10 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila, Barisal. | 506514137 |  | 1.544 |  |  |  | 4 | 9500469 | [12 empty] | E-Tender Under Process
13 |  | Sub-Total: |  | 0 | 11.043 | 1 | 0 | 0 | 36.8 | 73207513 | 2374301 | 52049202.55 | [6 empty] | 31523884 |  | 0 |  |  |  | 11597454.658
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. | [6 empty] | 15 | 6544168 |  | 5567698.82 | M/S Safi Enterprise | 2014-11-06 | 18/06/14 | 17/06/15 |  | 95% | 5259000 | 94.46% |  |  |  |  | 5289313.879
2 | BDRIDP/BAR/UZP/CCA-St/02 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m. | 506945205 | [5 empty] | 8.625 | 2586217 |  | 2015457.24 | Md Zakir Hossain Mia | 23/11/14 | 30/11/14 | 30/05/15 |  | 100% | 1973907 | 100% |  |  | Final |  | 41550.24
3 | BDRIDP/BAR/UZP/CCA-Rd/01 | Improvement of road from Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market, Nurani Madrasha & H/O Mr.Habibur Rahman (Beer Protik) by BC from Ch.0.00-1500m under Uzirpur Upazila, Barisal. | 506945205 |  | 1.5 |  |  |  |  | 6378273 |  | 5167677 | Md Sirazul Islam Hanif | 2014-01-12 | 2014-08-12 | 2015-07-06 |  | 100% | 4700000 | 90.95% |  | 29/08/16 |  | 70% | -1082626.1
4 | BDRIDP/BAR/UZP/CCA-Rd/02 | Improvement of road from Paschim Satla WAPDA to Satla Kheyaghat via H/O Fazlul Hoque Hawlader & Mosque By HBB from Ch. 0.00-375m. | 506945204 |  |  | 0.375 |  |  |  | 1316117 |  | 1225909.58 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2015-11-09 |  | 100% | 1223186 | 99.78% |  |  | Final | 100% | 2723.58
5 | BDRIDP/BAR/UZP/CCA-St/03 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m. | 506945129 | [5 empty] | 4 | 3397103 |  | 2682855.6 | Md Zakir Hossain Mia | 2015-11-05 | 18/05/15 | 18/10/15 |  | 100% | 2674595 | 99.69% |  |  | Final | 70% | -796596.08
6 | BDRIDP/BAR/UZP/UZ-Rd(R)/01 | Rehabilitation of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) road from Ch. 0.00m-2100m. | 506942005 |  | 2.1 |  |  |  |  | 10215215 |  | 8522561.6 | M/S G M Construction | 28/09/15 | 2015-05-10 | 2016-05-04 |  | 100% | 4771617 | 100% |  |  | Final
7 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 506942007 | [6 empty] | 18314961 | 18314961 | [11 empty] | Evaluation on going
8 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 506942015 | [6 empty] | 14753928 | 14753928 | [11 empty] | Evaluation on going
8 |  | Sub-Total: |  | 0 | 3.6 | 0.375 | 0 | 0 | 27.625 | 63505982 | 33068889 | 25182159.84 | [6 empty] | 20602305 |  | 0 |  |  |  | 3454365.519
Upazila: Muladi
1 | BDRIDP/BAR/MUL/UZ-St/01 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m. | 506692004 | [6 empty] | 7798117 |  | 8772459.2 | M/S Misi Construction | 21/07/14 | 28/07/14 | 27/03/15 |  | 100% | 8713982 | 100% |  |  | Final |  | 58477.2
2 | BDRIDP/BAR/MUL/UZ-Rd/01 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m. | 506692004 |  | 3.45 |  |  |  |  | 24406349 |  | 20744407.41 | M/S Lutful Kobir | 13/08/14 | 20/08/14 | 20/05/15 |  | 100% | 20160686 | 100% |  |  | Final | 100% | 583721.41
3 | BDRIDP/BAR/MUL/CCA-Rd/01 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District. | 506695135 |  | 1 |  |  |  |  | 4172838 |  | 3545269 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 65% | 500000 | 14.1% |  | 2015-12-02 |  | 100% | 3045269
4 | BDRIDP/BAR/MUL/CCA-Rd/02 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District. | 506695127 |  | 0.585 |  |  |  |  | 2763145 |  | 2347546 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 70% | 900000 | 38.34% |  | 2015-12-02 |  | 100% | 1447546
5 | BDRIDP/BAR/MUL/CCA-St/02 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m. | 506694001 | [5 empty] | 12 | 2543802 |  | 1762404.98 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 1761528 | 99.95% |  |  | Final | 100% | 876.98
6 | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m | 506694060 | [5 empty] | 16 | 5115590 |  | 3683201.71 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 90% | 3150000 | 85.52% |  | 25/10/15 |  | 60% | -940078.974
7 | BDRIDP/BAR/MUL/CCA-Rd(R)/04 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m. | 506694001 |  | 2.175 |  |  |  |  | 8969284 | 1518637 | 7104572.13 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 100% | 4349447 | 100% |  |  | Final | 80% | 1334210.704
8 | BDRIDP/BAR/MUL/CCA-Rd/05 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m. | 506694060 |  | 1.575 |  |  |  |  | 5450114 |  | 4824539 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 100% | 4773001 | 100% |  |  | Final | 80% | -913369.8
9 | BDRIDP/BAR/MUL/CCA-Rd/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m. | 506694063 |  | 1.25 |  |  |  |  | 3310397 |  | 2947338.02 | Md Sirazul Islam Hanif | 18/05/15 | 25/05/15 | 25/05/16 |  | 95% | 2646070 | 89.78% |  | 27/10/15 |  | 100% | 301268.02
10 | BDRIDP/BAR/MUL/CCA-St/01 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m | 506694063 | [5 empty] | 2 | 505514 |  | 368648.25 | M/S Sraboni Enterprise | 21/06/15 | 28/06/15 | 27/12/15 |  | 100% | 368633 | 100% |  |  | Final | 100% | 15.25
11 | BDRIDP/BAR/MUL/CCA-Rd/06 | Improvement of road from Char Kalekhan Goni Bari-Khalil Bepari Bari road by BC from Ch. 0.00m-1550m. | 56695075 |  | 1.55 |  |  |  |  | 8933193 |  | 7059418.41 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 60% | 1950000 | 27.62% |  | 29/06/17 |  | 70% | 4303235.1
12 | BDRIDP/BAR/MUL/CCA-St/04 | Construction of 1 vent 4.00m×4.00m and 1 vent 1.00m×1.00m RCC Box Culvert on Char Kalekhan Goni Bari-Khalil Bepari Bari road at Ch.182m & 330m. | 56695075 | [5 empty] | 5 | 1937445 |  | 1462533.11 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 100% | 1200000 | 100% |  |  | Final | 50% | -231277.5
13 | BDRIDP/BAR/MUL/CCA-St/05 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal. | 506694043 | [5 empty] | 12 | 10068184 | 10068184 | 7727638.21 | M/S Shafi Enterprise | [9 empty] | W/O under Process
13 |  | Sub Total: |  | 0 | 11.585 | 0 | 0 | 0 | 47 | 85973972 | 1518637 | 72349975.43 | [6 empty] | 50473347 |  | 0 |  |  |  | 4917935.79
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/CCA-Rd/01 | Improvement of road from South side Dhola Sluice Gate to Alim Meridha Bari (Vary) via Sikder Bari, Manik Member Bari, Shatghor & Mannan Princhpal Bari (East side of Hanua Bridge to Shatghor via Shikder Bari) By HBB from Ch. 0.00-1013m. | 506075221 |  |  | 1.013 |  |  |  | 3558576 |  | 3985608.82 | M/S Nahid Enterprise | 17/07/14 | 24/07/14 | 24/01/15 |  | 100% | 3976779 | 99.78% |  |  | Final | 100% | 8829.82
2 | BDRIDP/BAR/BAK/UN-St/01 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 | 506073023 | [5 empty] | 27.2 | 7339681 |  | 5345279.54 | M/S Khondokear Brothers | 14/06/15 | 21/06/15 | 20/06/16 |  | 95% | 5000000 | 93.54% |  | 2016-10-09
3 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 | 506073023 |  | 1 |  |  |  |  | 4566907 |  | 3523866.83 | M/S Khondokear Brothers | 21/07/15 | 28/07/15 | 27/04/16 |  | 65% | 1150000 | 32.63% |  | 14/07/16
4 | BDRIDP/BAR/BAK/UN-Rd(R)/02 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 1000m-4870m. e-ID : 22667 | 506073023 |  | 3.87 |  |  |  |  | 18093128 |  | 14682769.7 | M/S Khondokear Brothers | 14/06/15 | 2015-06-08 | 2016-06-05 |  | 70% | 8800000 | 59.93% |  | 13/10/16
5 | BDRIDP/BAR/BAK/CCA-Rd(R)/02 | Rehabilitation of road from Gavikola Mannan Sikder Bari Foot Bridge to West side of Nilganj Foot Bridge via Moksad Khan,Kumarghudi & Kaptain Saye Bari by BC from Ch.00-810m [Salvaged Value Tk.10,53,654.00] e-ID : 29366 | 506075079 |  | 0.81 |  |  |  |  | 3553958 |  | 2619513.44 | Md. Nasir Uddin | 2015-05-11 | 2015-12-11 | 2016-11-05 |  | 100% | 1495366 | 100% |  |  | Final
6 | BDRIDP/BAR/BAK/CCA-Rd/03 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal. | 506074120 | [6 empty] | 17641663 |  | 16139041.07 | Md. Sumsudhoa Mollick | 21/12/16 | 28/12/16 | 27/06/17 |  | 0%
6 |  |  |  | 0 | 5.68 | 1.013 | 0 | 0 | 27.2 | 54753913 | 0 | 46296079.4 | [6 empty] | 20422145 |  | 0 |  |  |  | 8829.82
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/CCA-Rd/02 | Improvement of road from Gournadi Highway Thana Connecting road under Gournadi Upazila. | 506325047 | [6 empty] | 1544297 |  | 1612193 | M/S Tamim Enterprise | 14/06/15 | 21/06/15 | 20/11/15 |  | 100% | 1612193 | 100% |  |  | Final | 50% | -806096.5
2 | BDRIDP/BAR /GOU/UN-Rd/01 | (a) Improvement of Road from Sarikal GC to Shaheber char Bazar via Nalchira Bazar ch. 5555m-7055m), (b) Construction of 2 nos U-drain at ch.599m & 6555m on the same road Under Gournadi Upazila, District-Barisal. | 506323013 |  | 1.5 |  |  |  | 1.8 | 9785485 |  | 10357650.8 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 10353584 | 99.96% |  |  | Final | 60% | -4138993.52
3 | BDRIDP/BAR /GOU/UZ-Rd/01 | (a) Improvement of Road from Gournadi Bandar GC to Muladi GC via Kutubpur Bazar at ch. 0m-630m), (b) Construction of 2 nos U-drain at ch. 205m & 364m on the same road Under Gournadi Upazila, District-Barisal. | 506322016 |  | 0.63 |  |  |  | 1.8 | 5122695 |  | 5399315 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 5356652 | 100% |  |  | Final | 60% | -2117063
4 | BDRIDP/BAR /GOU/UZ-Rd/02 | Improvement of illah (NHW) to Kalkini Upazila HQ via Tulatala Bazar at ch.2413m-3213m), Under Gournadi Upazila, District-Barisal. | 506322013 |  | 0.8 |  |  |  |  | 4643337 |  | 4898705 | M/S Sadman Builders | 2014-09-11 | 16/11/14 | 15/05/15 |  | 100% | 4667277 | 95.28% |  |  | Final | 40% | -2707795
5 | BDRIDP/BAR /GOU/UN-Rd/02 | (a) Improvement of Batazore GC to Pinglakathi Bazar via Pachim Chandrahar GPS at ch. 0m-1000m), (b)Construction of 1 nos U-drain at at ch.14m on the same road, (c) Construction 1v-2.3mx2.30m RCC Box Culvert at ch.527m & 1583m on the same road Under Gournadi Upazila, District-Barisal. | 506323001 |  | 1 |  |  |  | 2.2 | 7805159 |  | 8236744 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 8218516 | 99.78% |  |  | Final | 50% | -4100144
6 | BDRIDP/BAR/GOR/CCA-Rd/01 | Improvement of road from Maddam Hosnabad Nabarun RPS to Nezamuddin College by HBB at Ch.481-1492m (Nizamuddin Degree College road from freedom fighter Nizamuddin Shaheber Kaborstan via Madha hosnabad UP Member Md.Matiur Rahman Sarif Bari Bridge under Gouranadi upazila, Barisal District. | 506324040 |  |  | 1.011 |  |  |  | 2839204 |  | 2601109.88 | Md. Sirazul Islam Hanif | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 2583729 | 100% |  |  | Final | 100% | 17380.88
7 | BDRIDP/BAR/GOR/UZ-Rd/03 | Improvement of Barthi Bazar (NHW) to Gournadi GC via Torky GC at ch.2150 - 4150m. | 506322005 |  | 2 |  |  |  |  | 13145679 |  | 13801595 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 100% | 13799645 | 99.99% |  |  | Final
8 | BDRIDP/BAR/GOR/UN-Rd/03 | Rehabilitation of road from Mahilara UP Office to Chadshi Hat via Bilogram Bazar (A. Rob Chokder House to Chadshi Hat road) road By BC from Ch. 5370-6900m. | 506323019 |  | 1.53 |  |  |  |  | 5834483 |  | 6124969 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 100% | 6121962 | 99.95% |  |  | Final
9 | BDRIDP/BAR/GOR/UN-Rd(R)/04 | Rehabilitation of road from Mahilara UP office to Chadshi hat via Billogram Bazar road from Ch. 3740-4850m (Salvage Material Cost Tk. 11,01,418.00) | 506323019 |  | 1.11 |  |  |  |  | 5359476 |  | 5623536 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 100% | 4522118 | 100%
10 | BDRIDP/BAR/GOR/UN-St/01 | Construction of 2-Vent 4.30mx4.30m RCC Box Culvert on Mahilara UP office to Chadshi hat via Billogram Bazar road at Ch. 4200m. | 506323019 | [5 empty] | 8.6 | 1970942 |  | 2069109 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/12/15 |  | 100% | 2036343 | 100% |  |  | Final
11 | BDRIDP/BAR/GOR/CCA-St/01 | Construction of 3 Nos Single Vent 4.30mx4.30m RCC Box Culvert & 2 nos U-Drain on Battala Kapali bari Bridge (NHW) to Khanjapur High School road at ch. 95m,270m,1276m564m&970m Under Gournadi Upazila, District-Barisal e-ID : 22284 | 506324136 | [5 empty] | 14.9 | 6680560 |  | 6946789.2 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 100% | 6943287 | 99.95% |  |  | Final
12 | BDRIDP/BAR/GOR/CCA-Rd/03 | Improvement of road from Battala Kapali bari Bridge (NHW) to Khanjapur High School road by BC from Ch.00 - 1656m Under Gournadi Upazila, District-Barisal e-ID : 22285 | 506324136 |  | 1.656 |  |  |  |  | 7060824 |  | 7343257.29 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 100% | 7343257 | 100% |  |  | Final
13 | BDRIDP/BAR/GOR/UZ-Rd/04 | Improvement of Barthi Bazar (NHW) to Burghata bus Stand (NHW) via Amanagong hat at Ch. 450-2450m. e-ID : 19611 | 506322017 |  | 2 |  |  |  | 2 | 12874579 |  | 13172831.8 | M/S Howlader Constructure | 2015-07-07 | 2015-08-07 | 2016-06-07 |  | 70% | 7900000 | 59.97% |  | 21/06/16
13 |  |  |  | 0 | 12.226 | 1.011 | 0 | 0 | 31.3 | 84666720 | 0 | 88187804.97 | [6 empty] | 81458563 |  | 0 |  |  |  | -13852711.14
Upazila: Agailjhara
1 | BDRIDP/BAR /AGL/CCA-Rd/01 | Improvement of Road by BC from Rathkhola Bazar-Bhadrapara Road (ch. 0m-1000m) Under Agailjhara Upazila, District-Barisal. | 506024008 |  | 1 |  |  |  |  | 5097636 |  | 5599756.34 | M/S Talukder Enterprise | 23/10/14 | 30/10/14 | 30/04/15 |  | 100% | 5597543 | 99.96% |  |  | Final
2 | BDRIDP/BAR/AGL/CCA-Rd/02 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 5527014 |  | 4583839 | M/S Mitushi Traders | 27/11/14 | 2014-08-12 | 2015-04-06 |  | 0% |  | 0% |  |  | W/O Cancel
3 | BDRIDP/BAR/AGL/CCA-Rd(R)/06 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m. | 506025056 |  | 1 |  |  |  | 2.7 | 4914057 | 196459 | 5158284.22 | M/S Sharif Enterprise | 22/04/15 | 29/04/15 | 28/01/16 |  | 80% | 2750000 | 53.31% |  | P.O Submit |  | 50% | -170857.89
4 | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. | 506025058 | [5 empty] | 8.9 | 1677674 |  | 1771918.99 | M/S Sharif Enterprise | 28/05/15 | 2015-04-06 | 2015-04-12 |  | 100% | 1600000 | 90.3% |  | 20/12/15
5 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 506023001 |  | 2.76 |  |  |  |  | 14739342 | 791797 | 15592739.8 | M/S Sharif Enterprise | 25/05/15 | 2015-06-06 | 30/05/15 |  | 75% | 9500000 | 60.93% |  | 19/05/16 |  | 20% | -6381452.04
6 | BDRIDP/BAR/AGL/UZ-Rd/02 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by BC from Ch. 3800m-5800m. | 506022003 |  | 2 |  |  |  |  | 10771206 |  | 11288255.96 | M/S Sraboni Construction | 27/05/15 | 2015-04-06 | 2016-03-06 |  | 100% | 11286798 | 99.99% |  |  | Final | 60% | -4513844.424
7 | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m | 506024034 |  | 1 |  |  |  | 1.375 | 6017149 |  | 6375868.44 | M/S Sarniabad Enterprise | 25/05/15 | 2015-01-06 | 2015-01-12 |  | 65% | 3900000 | 61.17% |  | 2015-01-12 |  | 60% | -74478.936
8 | BDRIDP/BAR/AGL/CCA-Rd/04 | Improvement of road from Poiser hat GC-Ramshil Bazar via Trimukhi road by BC from Ch. 0.00m-1000m. | 506024040 |  | 1 |  |  |  |  | 4926273 |  | 5538660.26 | M/S Shafique Brothers | 21/05/15 | 28/05/15 | 28/11/15 |  | 100% | 5554952 | 100.3% |  |  | Final | 70% | -1677889.818
9 | BDRIDP/BAR/AGL/CCA-Rd(R)/05 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m. | 506025058 |  |  | 1.2 |  |  |  | 4159274 | 288401 | 4400152.34 | M/S Helal Traders | 2015-02-07 | 2015-09-07 | 2016-09-01 |  | 90% | 3650000 | 82.95% |  | 28/06/16 |  | 30% | -2329954.298
10 | BDRIDP/BAR/AGL/UZ-Rd(R)/01 | Rehabilitation of Barthi - Valukshi - Magura- Ambari-Bakalhat road by BC at ch.5870-7880m. | 506022008 |  | 2.01 |  |  |  |  | 12746908 |  | 13383052 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 100% | 13240243 | 100% |  |  | Final
11 | BDRIDP/BAR/AGL/CCA-Rd/07 | Improvement of road from Biplob Serniabad House to Hazi Musa House road By BC from ch.00-400m. e-ID : 22281 | 506025084 |  | 0.4 |  |  |  |  | 1917053 |  | 2012714.3 | M/S Serniabad Enterprise | 2015-07-07 | 2015-08-07 | 2015-08-12 |  | 100% | 2012370 | 99.98% |  |  | Final
12 | BDRIDP/BAR/AGL/CCA-Rd/ 02 | Improvement of road from Seral - Goila road via Shahid Serniabad House - Tamer Jame Mosjid(Tamer Girls High School-Seral Community Center) by BC (Ch.0.0 - 975m) under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 7232587 | 7232587 | [11 empty] | Evaluation on going
12 |  |  |  | 0 | 13.12 | 1.2 | 0 | 0 | 12.975 | 79726173 | 1276657 | 75705241.65 | [6 empty] | 59091906 |  | 0 |  |  |  | -15148477.406
Upazila: Babugonj
1 | BDRIDP/BAR/BABU/CCA-Rd/01 | Improvement of road from Babugonj Agorpur GC to Mr. Younusur Rahman (Divisional Commissioner) house via Clubgonj hat by Carpeting from Ch. 750-1400m & 0.00-1550m. | 506034025 |  | 2.2 |  |  |  |  | 9792326 | 944029 | 10750396.05 | M/S Lutful Kobir | 2014-10-07 | 17/07/14 | 16/04/15 |  | 100% | 9804307 | 100% |  |  | Final | 90% | -128950.555
2 | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km. | 506035070 |  | 2.35 |  |  |  |  | 9718891 | 421856 | 10173103.86 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 92% | 9390029 | 92.3% |  | 31/08/17 |  | 60% | -3286166.684
3 | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 506034095 |  | 4.32 |  |  |  |  | 18518441 | 1035938 | 19386557.17 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 40% |  | 0% |  | 31/08/17 |  | 60% | 11631934.302
4 | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. | 506035006 |  | 2.6 |  |  |  |  | 9959477 |  | 10428682 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 96% | 10000000 | 95.89% |  | 31/08/17 |  | 60% | -3742790.8
5 | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 506035070 | [5 empty] | 8.3 | 2931768 | 184122 | 3071060.04 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 90% | 2500000 | 81.41% |  | 31/08/17 |  | 60% | -657363.976
6 | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 506034095 | [5 empty] | 18.2 | 4744358 | 199349 | 4968549.43 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 55% | 2500000 | 50.32% |  | 31/08/17 |  | 60% | 481129.658
7 | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 506035006 | [5 empty] | 7.6 | 2001016 | 62866 | 2095536.41 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 90% | 1500000 | 71.58% |  | 31/08/17 |  | 60% | -242678.154
8 | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 506034024 | [5 empty] | 12 | 1982458 | 150637 | 2076355.09 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 40% |  | 0% |  | 31/08/17 |  | 60% | 1245813.054
9 | BDRIDP/BAR/BAB/UN-St/01 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m. | 506033006 | [5 empty] | 7.6 | 1443386 | 41933 | 1029755.17 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 986117 | 100% |  |  | Final | 60% | -368263.898
10 | BDRIDP/BAR/BAB/UN-Rd(R)/01 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m. | 506033006 |  | 1.78 |  |  |  |  | 6457205 | 2442317 | 5193526.54 | M/S Alvi Construction | 2015-05-05 | 2015-12-05 | 2016-12-02 |  | 50% | 550000 | 10.59% |  | 25/10/15 |  | 60% | 2566115.924
11 | BDRIDP/BAR/BAB/CCA-Rd/05 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District. | 506034024 |  | 3.8 |  |  |  |  | 14308351 |  | 14979470.55 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 60% | 3500000 | 23.37% |  | 31/08/17 |  | 60% | 5487682.33
12 | BDRIDP/BAR/BAB/UN-RD/02 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 |  | 2.11 |  |  |  |  | 12421386 |  | 11570042.22 | M/S Hasan Construction | 22/11/16 | 29/11/16 | 28/06/17 |  | 5% |  |  |  | 30/07/17
13 | BDRIDP/BAR/BAB/UN-St/02 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m. | 506033007 | [5 empty] | 15.2 | 4182978 |  | 4179759.25 | M/S Saifuddin Traders | 14/11/16 | 20/11/16 | 19/09/17 |  | 20% |  |  |  | 27/10/17
13 |  |  |  | 0 | 19.16 | 0 | 0 | 0 | 68.9 | 98462041 | 5483047 | 99902793.78 | [6 empty] | 40730453 |  | 0 |  |  |  | 12986461.201
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/UZR(R)-Rd/01 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal. | 506622005 |  | 1.11 |  |  |  |  | 3853739 |  | 4973018 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 55% |  | 0% |  | 2015-12-02 |  | 60% | 2983810.8
2 | BDRIDP/BAR/MHN/CCA-Rd/01 | Improvement of Mothertoli Bazar - Uttarchar road via Charekkaria road by BC (Ch.2170-3220m, Road Under Mehendigonj Upazila, District-Barisal. | 506625079 |  | 1.05 |  |  |  |  | 5327472 |  | 4515030 | M/S Nahid Enterprise | 16/11/14 | 23/11/14 | 23/04/15 |  | 100% | 4514924 | 100% |  |  | Final | 60% | -1805906
3 | BDRIDP/BAR/MHN/CCA-St/01 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal. | 506625079 | [5 empty] | 1 | 222783 |  | 184788 | M/S Hasib Enterprise | 2014-09-11 | 16/11/14 | 15/03/15 |  | 100% | 167876 | 100% |  |  | Final
4 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 506624016 |  | 1.61 |  |  |  |  | 6864308 | 6864308 | 6860287.95 | M/S Hasan Construction | 2017-12-01 | 19/01/17 | 19/09/17 |  | 0% |  | 0% |  | 2017-01-10
5 | BDRIDP/BAR/MHN/UZ-Rd/02 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila, Barisal. | 506622007 |  | 3 |  |  |  |  | 10545370 | [12 empty] | E-Tender under Process
5 |  |  |  | 0 | 6.77 | 0 | 0 | 0 | 1 | 26813672 | 6864308 | 16533123.95 | [6 empty] | 4682800 |  | 0 |  |  |  | 1177904.8
Upazila: Hizla
1 | BDRIDP/BAR/HZL/UZ-Rd(R)/01 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m. | 506362009 |  | 1 |  |  |  |  | 7094634 | 1476772 | 5645230.7 | M/S Oshin Enterprise | 21/05/15 | 28/05/15 | 28/02/16 |  | 100% | 4168458 | 100% |  |  | Final | 40% | -1910365.72
1 |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 7094634 | 1476772 | 5645230.7 | [6 empty] | 4168458 |  | 0 |  |  |  | -1910365.72
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 506102003 | 0 | 1 | 0 | 0 | 0 | 0 | 7013799 | 7013799 | 5349539.02 | M/S Saleha Enterprise | [6 empty] | 0% |  |  | W/O under Process | 40% | 2139815.608
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m ,1 No.3.0m x 3.0m , 2Nos.4.0m x 4.0m , 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 506102003 | 0 | 0 | 0 | 0 | 0 | 11 | 7531517 | 7531517 | 5461652.5 | M/S Soma Enterprise | 25/01/17 | 2017-02-02 | 2017-02-10 |  | 0% |  | 0%
2 |  |  |  | 0 | 1 | 0 | 0 | 0 | 11 | 14545316 | 14545316 | 10811191.52 | [6 empty] | 0 |  | 0 |  |  |  | 2139815.608
86 |  |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 588749936 | 66607927 | 492662803.79 | [6 empty] | 313153861 |  | 0 |  |  |  | #VALUE!
Accountant |  |  | Sub-Assistant Engineer | [9 empty] | Assistant Engineer |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [9 empty] | LGED, Barisal |  | LGED, Barisal |  |  |  | LGED, Barisal

## All (5)
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Amount Spent (Tk) |  | Planed Progress | [7 empty] | Signature of the Upazila Engineer | Signature of the Contractor | Remark | Remark | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [10 empty] | In (%) | November/16 | December/16 | January/16 | February/17 | March/16 | April/16 | May/16 | June/16
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 5 | 6 | 7 | 15 | 8 | 17 | 9 | 10 | 20 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 20 | 22
Upazila: Barisal Sadar
3 | BDRIDP/BAR/SDR/CCA-Rd/03 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m | 506514148 |  | 0.513 |  |  |  |  | 2809559 |  | 2294335.91 | M/S Serajul Islam Hanif | 24/07/14 | 2014-01-08 | 2015-01-02 |  | 70% | 1200000 | 52.3% | [13 empty] | 100% | 1094335.91
4 | BDRIDP/BAR/SDR/CCA-Rd/04 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 |  | 0.732 |  |  |  |  | 2900881 | 1230068 | 2238782.5 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 20%
5 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 90% | 8800000 | 87.23% | [14 empty] | 9079531.803
6 | BDRIDP/BAR/SDR/CCA-Rd/04 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366m. | 506515102 |  | 1 |  |  |  | 1.6 | 4543594 |  | 3864872.18 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2016-11-04 |  | 70% | 2350000 | 60.8% | [13 empty] | 50% | -417563.91
8 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 506514048 |  | 2.782 |  |  |  |  | 10910419 | 207108 | 8773072.65 | M/S Hasan Construction | 2015-10-05 | 17/05/15 | 17/02/16 |  | 60% | 4300000 | 49.01% | [13 empty] | 70% | 1841150.855
12 | BDRIDP/BAR/SDR/CCA-Rd/09 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari. | 506515006 |  | 1.6 |  |  |  | 1.6 | 12590432 | 937125 | 10801668.14 | M/S Khondokear Brothers | 30/06/16 | 30/06/16 | 26/06/17 |  | 0% |  | 0%
12 |  | Sub-Total: |  | 0 | 6.627 | 0 | 0 | 0 | 23.2 | 46527739 | 2374301 | 38061100.05 | [6 empty] | 16650000 | [12 empty] | 0 |  |  | 11597454.658
1 | BDRIDP/BAR/SDR/CCA-EW/01 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 | 2126.54 | [5 empty] | 238242 |  | 238242 | Md. Giush Uddin LCS No-1 | 29/01/15 | 15/02/15 | 30/04/15 |  | 100% | 190934 | 100% | [12 empty] | Final
2 | BDRIDP/BAR/SDR/CCA-EW/02 | Resectioning of road from Charkawa Nayami-Shaheber hat via Durgapur hat (Barisal Sadar Upzila 7no. Charkawa union 1no word nurul islam to Bank Jalal Bari Pull) road from Ch. 0.00m-1000m. | 506514136 | 1311.25 | [5 empty] | 155407 | 155407 | 155407 | Md. Anowar Hossain Mridha LCS No-1 | 16/04/15 | 16/04/15 | 16/05/15 |  | 75% | 100881 | 64.91%
3 | [9 empty] | 228280 | 228280 | 228280 | Md. Jasim Uddin Milon LCS No-2 | 16/04/15 | 16/04/15 | 16/05/15 |  | 80% | 132596 | 58.08%
4 | BDRIDP/BAR/SDR/CCA-EW/03 | Resectioning of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge). | 506515006 | 3309.7 | [5 empty] | 400044 |  | 400044 | Fatema Begum LCS No-1 |  |  |  |  | 92% | 362610 | 90.64%
4 |  | Sub-Total: |  | 6747.49 | 0 | 0 | 0 | 0 | 0 | 1021973 | 383687 | 1021973 | [6 empty] | 787021 | [12 empty] | 0 |  |  | 0
16 |  | Grand Total: |  | 6747.49 | 6.627 | 0 | 0 | 0 | 23.2 | 47549712 | 2757988 | 39083073.05 | [6 empty] | 17437021 | [12 empty] | 0 |  |  | 11597454.658
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. | [6 empty] | 15 | 6544168 |  | 5567698.82 | M/S Safi Enterprise | 2014-11-06 | 18/06/14 | 17/06/15 |  | 95% | 5259000 | 94.46% | [14 empty] | 5289313.879
6 |  | Sub-Total: |  | 0 | 0 | 0 | 0 | 0 | 15 | 6544168 | 0 | 5567698.82 | [6 empty] | 5259000 | [12 empty] | 0 |  |  | 5289313.879
1 | BDRIDP/BAR/UZP/UZ-EW/01 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 0.00m-700m. | 506942005 | [6 empty] | 258990 | 258990 | 258990 | Yasin Sarder LCS No-1 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 241304 | 100% | [12 empty] | Final
2 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 700m-1400m. | [7 empty] | 284900 | 284900 | 284900 | Iqbal Hossan LCS No-2 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 271670 | 100% | [12 empty] | Final
3 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 1400m-2100m. | [7 empty] | 278170 | 278170 | 278170 | Supian LCS No-3 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 275956 | 100% | [12 empty] | Final
3 |  | Sub-Total: |  | 0 | 0 | 0 | 0 | 0 | 0 | 822060 | 822060 | 822060 | [6 empty] | 788930 | [12 empty] | 0 |  |  | 0
9 |  | Grand Total: |  | 0 | 0 | 0 | 0 | 0 | 15 | 7366228 | 822060 | 6389758.82 | [6 empty] | 6047930 | [12 empty] | 0 |  |  | 5289313.879
Upazila: Muladi
2 | BDRIDP/BAR/MUL/UZ-Rd/01 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m. | 506692004 |  | 3.45 |  |  |  |  | 24406349 |  | 20744407.41 | M/S Lutful Kobir | 13/08/14 | 20/08/14 | 20/05/15 |  | 70% | 13290000 | 64.07% | [13 empty] | 100% | 7454407.41
3 | BDRIDP/BAR/MUL/CCA-Rd/01 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District. | 506695135 |  | 1 |  |  |  |  | 4172838 |  | 3545269 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 60% | 500000 | 14.1% | [13 empty] | 100% | 3045269
4 | BDRIDP/BAR/MUL/CCA-Rd/02 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District. | 506695127 |  | 0.585 |  |  |  |  | 2763145 |  | 2347546 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 70% | 900000 | 38.34% | [13 empty] | 100% | 1447546
6 | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m | 506694060 | [5 empty] | 16 | 5115590 |  | 3683201.71 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 55% | 1850000 | 50.23% | [13 empty] | 60% | 359921.026
7 | BDRIDP/BAR/MUL/CCA-Rd(R)/04 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m. | 506694001 |  | 2.175 |  |  |  |  | 8969284 | 1518637 | 7104572.13 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 90% | 4349447 | 61.22% | [13 empty] | 80% | 1334210.704
8 | BDRIDP/BAR/MUL/CCA-Rd/05 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m. | 506694060 |  | 1.575 |  |  |  |  | 5450114 |  | 4438024 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 60% | 2500000 | 56.33% | [13 empty] | 80% | 1050419.2
9 | BDRIDP/BAR/MUL/CCA-Rd/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m. | 506694063 |  | 1.25 |  |  |  |  | 3310397 |  | 2947338.02 | Md Sirazul Islam Hanif | 18/05/15 | 25/05/15 | 25/05/16 |  | 95% | 2646070 | 89.78% | [13 empty] | 100% | 301268.02
11 | BDRIDP/BAR/MUL/CCA-Rd/06 | Improvement of road from Char Kalekhan Goni Bari-Khalil Bepari Bari road by BC from Ch. 0.00m-1550m. | 56695075 |  | 1.55 |  |  |  |  | 8933193 |  | 7059418.41 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 30% | 1950000 | 27.62% | [13 empty] | 70% | 4303235.1
12 |  | Sub Total: |  | 0 | 11.585 | 0 | 0 | 0 | 16 | 63120910 | 1518637 | 51869776.68 | [6 empty] | 27985517 | [12 empty] | 0 |  |  | 14993041.36
1 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m. | 506692004 | 2490.25 | [5 empty] | 334778 |  | 334778 | Khorshed Khan LCS No-1 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 327963 | 100% | [12 empty] | Final
2 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m. | 506692004 | 3042.25 | [5 empty] | 403489 |  | 403489 | Md. Alamgir Hossain LCS No-2 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 396479 | 100% | [12 empty] | Final
3 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m. | 506692004 | 2886.92 | [5 empty] | 386512 |  | 386512 | Md. Baschu Sharder LCS No-3 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 384690 | 100% | [12 empty] | Final
4 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m. | 506692004 | 2770 | [5 empty] | 371303 |  | 371303 | Abdus Salam Sharder LCS No-4 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 364872 | 100% | [12 empty] | Final
5 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m. | 506692004 | 2775.75 | [5 empty] | 372013 |  | 372013 | Md. Bakiullah Sharder LCS No-5 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 367905 | 100% | [12 empty] | Final
6 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m. | 506692004 | 2798.21 | [5 empty] | 374943 |  | 374943 | Md. Shalim LCS No-6 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 373728 | 99.68% | [12 empty] | Final
7 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m. | 506692004 | 2793.69 | [5 empty] | 374353 |  | 374353 | Sukkur Ahmed Khan LCS No-7 | 18/05/14 | 22/05/14 | 22/10/14 |  | 98% | 366080 | 97.79%
8 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m. | 506692004 | 0.3 | [5 empty] | 369858 |  | 369858 | Nazma LCS No-8 | 18/05/14 | 22/05/14 | 22/10/14 |  | 92% | 341332 | 92.29%
9 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m. | 506692004 | 2969.75 | [5 empty] | 397315 |  | 397315 | Most. Jasmin Akter LCS No-9 | 18/05/14 | 22/05/14 | 22/10/14 |  | 70% | 261169 | 65.73%
10 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m. | 506692004 | 3207.06 | [5 empty] | 428100 |  | 428100 | Rashida LCS No-10 | 18/05/14 | 22/05/14 | 22/10/14 |  | 75% | 287470 | 67.15%
11 | BDRIDP/BAR/MUL/CCA-EW/01 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District. | 506695135 | 2052.81 | [5 empty] | 221909 |  | 221909 | Md Fazlu Tafader LCS No-1 | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 221206 | 100% | [12 empty] | Final
12 | BDRIDP/BAR/MUL/CCA-EW/02 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District. | 506695127 | 2219.05 | [5 empty] | 239879 |  | 239879 | Md Kabir Hossain LCS No- | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 239119 | 100% | [12 empty] | Final
13 | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. | 506694063 | 2210.3 | [5 empty] | 323312 |  | 323312 | Fokrul Ahosan LCS No-1 | 31/05/15 | 31/05/15 | 30/09/15 |  | 10% | 32000 | 9.898%
14 | BDRIDP/BAR/MUL/CCA-EW/04 | Resectioning of road from Char Kalekhan Goni Bari-khalil Bepari bari road by Earth work from Ch. 0.00m-1550m. | 56695075 | 2237.625 | [5 empty] | 101268 | 101268 | 101268 | Md. Mojibor Rohman | 28/07/15 | 30/08/15 | 30/12/15 |  | 100% | 97476 | 100% | [12 empty] | Final
14 |  | Sub Total: |  | 34453.965 | 0 | 0 | 0 | 0 | 0 | 4699032 | 101268 | 4699032 | [6 empty] | 4061489 | [12 empty] | 0 |  |  | 0
26 |  | Grand Total: |  | 34453.965 | 11.585 | 0 | 0 | 0 | 16 | 67819942 | 1619905 | 56568808.68 | [6 empty] | 32047006 | [15 empty] | 14993041.36
Upazila: Bakergonj
2 | BDRIDP/BAR/BAK/UN-St/01 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 | 506073023 | [5 empty] | 27.2 | 7339681 |  | 5345279.54 | M/S Khondokear Brothers | 14/06/15 | 21/06/15 | 20/06/16 |  | 95% | 5000000 | 93.54%
3 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 | 506073023 |  | 1 |  |  |  |  | 4566907 |  | 3523866.83 | M/S Khondokear Brothers | 21/07/15 | 28/07/15 | 27/04/16 |  | 65% | 1150000 | 32.63%
4 | BDRIDP/BAR/BAK/UN-Rd(R)/02 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 1000m-4870m. e-ID : 22667 | 506073023 |  | 3.87 |  |  |  |  | 18093128 |  | 14682769.7 | M/S Khondokear Brothers | 14/06/15 | 2015-06-08 | 2016-06-05 |  | 60% | 7800000 | 53.12%
5 | BDRIDP/BAR/BAK/CCA-Rd(R)/02 | Rehabilitation of road from Gavikola Mannan Sikder Bari Foot Bridge to West side of Nilganj Foot Bridge via Moksad Khan,Kumarghudi & Kaptain Saye Bari by BC from Ch.00-810m [Salvaged Value Tk.10,53,654.00] e-ID : 29366 | 506075079 |  | 0.81 |  |  |  |  | 3553958 |  | 2619513.44 | Md. Nasir Uddin | 2015-05-11 | 2015-12-11 | 2016-11-05 |  | 70% | 1000000 | 38.18%
5 |  |  |  | 0 | 5.68 | 0 | 0 | 0 | 27.2 | 33553674 | 0 | 26171429.51 | [6 empty] | 14950000 | [12 empty] | 0 |  |  | #REF!
1 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m | 506073023 | [6 empty] | 131861 |  | 131861 | Anwar Hossain LCS No-01 | 15/04/15 | 16/04/15 | 16/05/15 |  | 92% | 118814 | 90.11%
2 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m. | 506073023 | [6 empty] | 256728 |  | 256728 | Md. Babul Howlader LCS No-02 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 226287 | 88.14%
3 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m | 506073023 | [6 empty] | 230734 |  | 230734 | Md. Joynal Abadin LCS No-03 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 203474 | 88.19%
4 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m | 506073023 | [6 empty] | 224792 |  | 224792 | Md. Royon Mollah LCS No-04 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 198427 | 88.27%
5 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m | 506073023 | [6 empty] | 233429 |  | 233429 | Md. Shahidul Sharif LCS No-05 | 15/04/15 | 16/04/15 | 16/05/15 |  | 95% | 220264 | 94.36%
6 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m | 506073023 | [6 empty] | 205799 |  | 205799 | H M Shamsul Huda LCS No-06 | 15/04/15 | 16/04/15 | 16/05/15 |  | 95% | 191913 | 93.25%
7 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m | 506073023 | [6 empty] | 243498 |  | 243498 | Md. Hanif LCS No-07 | 15/04/15 | 16/04/15 | 16/05/15 |  | 99% | 238747 | 98.05%
8 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m | 506073023 | [6 empty] | 230149 |  | 230149 | Md. Amir Ali Khan LCS No-08 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 203332 | 88.35%
9 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m | 506073023 | [6 empty] | 249498 |  | 249498 | Md. Monir Hossain LCS No-09 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 211006 | 84.57%
10 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m | 506073023 | [6 empty] | 222257 |  | 222257 | Md. Shalim Mridha LCS No-10 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 196192 | 88.27%
10 |  | Sub Total: |  | 0 | 0 | 0 | 0 | 0 | 0 | 2228745 | 0 | 2228745 | [6 empty] | 2008456 | [12 empty] | 0 |  |  | 0
15 |  | Grand Total: |  | 0 | 5.68 | 0 | 0 | 0 | 27.2 | 35782419 | 0 | 28400174.51 | [6 empty] | 16958456 | [15 empty] | #REF!
Upazila: Gournodi
9 | BDRIDP/BAR/GOR/UN-Rd(R)/04 | Rehabilitation of road from Mahilara UP office to Chadshi hat via Billogram Bazar road from Ch. 3740-4850m (Salvage Material Cost Tk. 11,01,418.00) | 506323019 |  | 1.11 |  |  |  |  | 5359476 |  | 5623536 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 50% | 2000000 | 35.56%
12 | BDRIDP/BAR/GOR/CCA-Rd/03 | Improvement of road from Battala Kapali bari Bridge (NHW) to Khanjapur High School road by BC from Ch.00 - 1656m Under Gournadi Upazila, District-Barisal e-ID : 22285 | 506324136 |  | 1.656 |  |  |  |  | 7060824 |  | 7343257.29 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 65% | 4500000 | 61.28%
13 | BDRIDP/BAR/GOR/UZ-Rd/04 | Improvement of Barthi Bazar (NHW) to Burghata bus Stand (NHW) via Amanagong hat at Ch. 450-2450m. e-ID : 19611 | 506322017 |  | 2 |  |  |  | 2 | 12874579 |  | 13172831.8 | M/S Howlader Constructure | 2015-07-07 | 2015-08-07 | 2016-06-07 |  | 60% | 6000000 | 45.55%
13 |  |  |  | 0 | 4.766 | 0 | 0 | 0 | 2 | 25294879 | 0 | 26139625.09 | [6 empty] | 12500000 | [12 empty] | 0 |  |  | #REF!
1 | BDRIDP/BAR/GOR/UN-EW/01 | Improvement of road from Mahilara UP Office to Chadshi hat via Billogram Bazar road By Earth Filling Work from Ch. 3740m-4850m. | 506323019 | 1756 | [5 empty] | 349519 |  | 349519 | Anjur Ali Sarder LCS No-1 | 2015-10-11 | 15/11/15 | 30/03/16 |  | 100% | 139777 | 39.99%
2 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Gournadi GC via Torky GC at Ch. 2150m-4150m by earth . | 506322005 | 1603.375 | [5 empty] | 223623 |  | 223623 | LCS-1
3 |  |  |  | 501.125 | [5 empty] | 69892 |  | 69892 | LCS-2
4 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Burghata Bus Stand (NHW) via Amanothgonj hat at Ch. 450m-2450m by earth. | 506322017 | 2151.655 | [5 empty] | 300092 |  | 300092 | LCS-1
5 |  |  |  | 1505.375 | [5 empty] | 209955 |  | 209955 | LCS-2
5 |  |  |  | 7517.53 | 0 | 0 | 0 | 0 | 0 | 1153081 | 0 | 1153081 | [6 empty] | 139777 | [12 empty] | 0 |  |  | 0
18 |  |  |  | 7517.53 | 4.766 | 0 | 0 | 0 | 2 | 26447960 | 0 | 27292706.09 | [6 empty] | 12639777 | [12 empty] | 0 |  |  | #REF!
Upazila: Agailjhara
2 | BDRIDP/BAR/AGL/CCA-Rd/02 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 5527014 |  | 4583839 | M/S Mitushi Traders | 27/11/14 | 2014-08-12 | 2015-04-06 |  | 0% |  | 0% | [12 empty] | W/O Cancel
3 | BDRIDP/BAR/AGL/CCA-Rd(R)/06 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m. | 506025056 |  | 1 |  |  |  | 2.7 | 4914057 | 196459 | 5158284.22 | M/S Sharif Enterprise | 22/04/15 | 29/04/15 | 28/01/16 |  | 40% | 1450000 | 28.11% | [13 empty] | 50% | 1129142.11
4 | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. | 506025058 | [5 empty] | 8.9 | 1677674 |  | 1771918.99 | M/S Sharif Enterprise | 28/05/15 | 2015-04-06 | 2015-04-12 |  | 70% | 900000 | 50.79%
5 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 506023001 |  | 2.76 |  |  |  |  | 14739342 | 791797 | 15592739.8 | M/S Sharif Enterprise | 25/05/15 | 2015-06-06 | 30/05/15 |  | 60% | 8300000 | 53.23% | [13 empty] | 20% | -5181452.04
7 | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m | 506024034 |  | 1 |  |  |  | 1.375 | 6017149 |  | 6375868.44 | M/S Sarniabad Enterprise | 25/05/15 | 2015-01-06 | 2015-01-12 |  | 65% | 3900000 | 61.17% | [13 empty] | 60% | -74478.936
9 | BDRIDP/BAR/AGL/CCA-Rd(R)/05 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m. | 506025058 |  |  | 1.2 |  |  |  | 4159274 | 288401 | 4400152.34 | M/S Helal Traders | 2015-02-07 | 2015-09-07 | 2016-09-01 |  | 90% | 3650000 | 82.95% | [13 empty] | 30% | -2329954.298
10 | BDRIDP/BAR/AGL/UZ-Rd(R)/01 | Rehabilitation of Barthi - Valukshi - Magura- Ambari-Bakalhat road by BC at ch.5870-7880m. | 506022008 |  | 2.01 |  |  |  |  | 12746908 |  | 13383052 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 70% | 9400000 | 70.24%
11 | BDRIDP/BAR/AGL/CCA-Rd/07 | Improvement of road from Biplob Serniabad House to Hazi Musa House road By BC from ch.00-400m. e-ID : 22281 | 506025084 |  | 0.4 |  |  |  |  | 1917053 |  | 2012714.3 | M/S Serniabad Enterprise | 2015-07-07 | 2015-08-07 | 2015-08-12 |  | 65% | 1200000 | 59.62%
11 |  |  |  | 0 | 8.145 | 1.2 | 0 | 0 | 12.975 | 51698471 | 1276657 | 53278569.09 | [6 empty] | 28800000 | [12 empty] | 0 |  |  | -6456743.164
1 | BDRIDP/BAR/AGL/CCA-EW/01 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal. | 506024034 | 2209.995 | [5 empty] | 302120 |  | 153224 | Ramesh Chandra Shikari LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 119075 | 77.71%
2 |  |  | 506024034 | 2209.995 | [5 empty] | 302120 |  | 148896 | Md Halim Talukder LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 122647 | 82.37%
3 | BDRIDP/BAR/AGL/CCA-EW/02 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 448658 |  | 216905 | Abdul Hakim Molla LCS No-1 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 140432 | 64.74%
4 |  | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 448658 |  | 231753 | Anukul Chandra Barai LCS No-2 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 185062 | 79.85%
5 | BDRIDP/BAR/AGL/CCA-EW/03 | Resectioning of road from Temar Bastala to Hawla Bridge via Nagar GPS-Talbazar-lichermath Bazar road from Ch. 3840-4840m. | [7 empty] | 402019 |  | 402019 | LCS
6 | BDRIDP/BAR/AGL/UZ-EW/01 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal. | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 124341 | Md. Sohrab Howlader LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 124340 | 100% | [12 empty] | Final
7 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 307876 | Md. Mosharef Sheikh LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 307875 | 100% | [12 empty] | Final
8 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 329106 | Abdul Rashid Howlader LCS No-3 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 329106 | 100% | [12 empty] | Final
9 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 330529 | Matleb Howlader LCS No-4 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 329457 | 99.68% | [12 empty] | Final
10 | BDRIDP/BAR/AGL/UN-EW/01 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal. | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 201404 | Mahim Baishnab LCS No-1 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 201396 | 100%
11 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 289300 | Sudhir Kumar Ojha LCS No-2 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 288996 | 99.89%
12 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 288022 | Banendra Nath Panday LCS No-3 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 287780 | 99.92%
13 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 207336 | Rabindranath Sarker LCS No-4 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207335 | 100%
14 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 205837 | Nirmal Ghatak LCS No-5 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205837 | 100%
15 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 207632 | Bebek Pandey LCS No-6 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207631 | 100%
16 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 205952 | Pangkoj Joydhor LCS No-7 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205952 | 100%
16 |  |  |  | 116932.232 | 0 | 0 | 0 | 0 | 0 | 3850132 | 0 | 3850132 | [6 empty] | 3262921 | [12 empty] | 0 |  |  | 0
27 |  |  |  | 116932.232 | 8.145 | 1.2 | 0 | 0 | 12.975 | 55548603 | 1276657 | 57128701.09 | [6 empty] | 32062921 | [12 empty] | 0 |  |  | -6456743.164
Upazila: Babugonj
2 | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km. | 506035070 |  | 2.35 |  |  |  |  | 9718891 | 421856 | 10173103.86 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 92% | 9390029 | 92.3% | [13 empty] | 60% | -3286166.684
3 | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 506034095 |  | 4.32 |  |  |  |  | 18518441 | 1035938 | 19386557.17 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 20% |  | 0% | [13 empty] | 60% | 11631934.302
4 | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. | 506035006 |  | 2.6 |  |  |  |  | 9959477 |  | 10428682 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 96% | 10000000 | 95.89% | [13 empty] | 60% | -3742790.8
5 | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 506035070 | [5 empty] | 8.3 | 2931768 | 184122 | 3071060.04 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 90% | 2500000 | 81.41% | [13 empty] | 60% | -657363.976
6 | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 506034095 | [5 empty] | 18.2 | 4744358 | 199349 | 4968549.43 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 55% | 2500000 | 50.32% | [13 empty] | 60% | 481129.658
7 | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 506035006 | [5 empty] | 7.6 | 2001016 | 62866 | 2095536.41 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 90% | 1500000 | 71.58% | [13 empty] | 60% | -242678.154
8 | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 506034024 | [5 empty] | 12 | 1982458 | 150637 | 2076355.09 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 25% |  | 0% | [13 empty] | 60% | 1245813.054
10 | BDRIDP/BAR/BAB/UN-Rd(R)/01 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m. | 506033006 |  | 1.78 |  |  |  |  | 6457205 | 2442317 | 5193526.54 | M/S Alvi Construction | 2015-05-05 | 2015-12-05 | 2016-12-02 |  | 50% | 550000 | 10.59% | [13 empty] | 60% | 2566115.924
11 | BDRIDP/BAR/BAB/CCA-Rd/05 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District. | 506034024 |  | 3.8 |  |  |  |  | 14308351 |  | 14979470.55 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 50% | 3500000 | 23.37% | [13 empty] | 60% | 5487682.33
12 | BDRIDP/BAR/BAB/UN-RD/02 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 |  | 2.11 |  |  |  |  | 12421386 |  | 12421386 | [20 empty] | E-Tender under Process
13 | BDRIDP/BAR/BAB/UN-St/02 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m. | 506033007 | [5 empty] | 15.2 | 4182978 |  | 4182978 | [20 empty] | E-Tender under Process
13 |  |  |  | 0 | 16.96 | 0 | 0 | 0 | 61.3 | 87226329 | 4497085 | 88977205.09 | [6 empty] | 29940029 | [12 empty] | 0 |  |  | 13483675.654
1 | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. | 506033006 | [6 empty] | 195850 |  | 195850 | Md. Masum Hossain Gazi LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 80% | 152768 | 78%
2 | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km. | 506035070 | [6 empty] | 285121 |  | 285121 | Taslima LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 60% | 158604 | 55.63%
3 | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km. | 506034095 | [6 empty] | 381065 |  | 381065 | Rajib Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 38100 | 9.998%
4 | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km. | 506035006 | [6 empty] | 300535 |  | 300535 | Md. Liton Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 55% | 159799 | 53.17%
5 | BDRIDP/BAR/BAB/CCA-EW/04 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m. | 506034024 | [6 empty] | 354810 |  | 354810 | Md. Kabir Sikder LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 35400 | 9.977%
6 | BDRIDP/BAR/BAB/UN-EW/02 | Resectioning of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 | 2404.83 | [5 empty] | 290672 | 290672 | 290672 | Md. Habibur Rohman LCS No-1 | 16/06/16 | 20/06/16 | 20/10/16 |  | 17% | 47569 | 16.37%
6 |  |  |  | 2404.83 | 0 | 0 | 0 | 0 | 0 | 1808053 | 290672 | 1808053 | [6 empty] | 592240 | [12 empty] | 0 |  |  | 0
19 |  |  |  | 2404.83 | 16.96 | 0 | 0 | 0 | 61.3 | 89034382 | 4787757 | 90785258.09 | [6 empty] | 30532269 | [15 empty] | 13483675.654
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/UZR(R)-Rd/01 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal. | 506622005 |  | 1.11 |  |  |  |  | 3853739 |  | 4973018 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 55% |  | 0% | [13 empty] | 60% | 2983810.8
3 |  |  |  | 0 | 1.11 | 0 | 0 | 0 | 0 | 3853739 | 0 | 4973018 | [6 empty] | 0 | [12 empty] | 0 |  |  | 2983810.8
Upazila: Hizla
1 | BDRIDP/BAR/HZL/UZ-Rd(R)/01 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m. | 506362009 |  | 1 |  |  |  |  | 7094634 | 1476772 | 5645230.7 | M/S Oshin Enterprise | 21/05/15 | 28/05/15 | 28/02/16 |  | 100% | 4168458 | 100% | [12 empty] | Final | 40% | -1910365.72
1 |  |  |  | 0 | 1 | 0 | 0 | 0 | 0 | 7094634 | 1476772 | 5645230.7 | [6 empty] | 4168458 | [12 empty] | 0 |  |  | -1910365.72
1 | BDRIDP/BAR/HZL/UZ-EW/01 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 0.00m-325m | 506362009 | [6 empty] | 226562 | 226562 | 226562 | Md. Humaun Kabir LCS No-1 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 225780 | 99.65%
2 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 325m-650m | [7 empty] | 220227 | 220227 | 220227 | Md. Monju Noli LCS No-2 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 218498 | 100%
3 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 650m-1000m | [7 empty] | 217087 | 217087 | 217087 | Md. Parvaz LCS No-3 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 214482 | 100%
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 663876 | 663876 | 663876 | [6 empty] | 658760
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta ,At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | [30 empty] | E-Tender Under Process. | 40% | 0
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m ,1 No.3.0m x 3.0m , 2Nos.4.0m x 4.0m , 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m,6787m,6145m,6230m,6407m,5871m,6555m & 6622m on Banaripara-Harta Road. [ID No.506102003] | [30 empty] | E-Tender Under Process.
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | [12 empty] | 0 |  |  | 0
1 | BDRIDP/BAR/BAN/UZ-EW/01 | Resectioning of Banaripara-Harta Road at Ch. 4665m-6066m. | 506102003 | 3655.305 | [5 empty] | 441816.72
2 |  | Resectioning of Banaripara-Harta Road at Ch. 6066m-7252m. |  | 3440.645 | [5 empty] | 415870.76
3 |  | Resectioning of Banaripara-Harta Road at Ch. 7252m-7702m. |  | 3300.95 | [5 empty] | 398985.83
4 |  | Resectioning of Banaripara-Harta Road at Ch. 7702m-8152m. |  | 3181.47 | [5 empty] | 384544.28
5 |  | Resectioning of Banaripara-Harta Road at Ch. 8152m-8752m. |  | 3835.515 | [5 empty] | 463598.7
6 |  | Resectioning of Banaripara-Harta Road at Ch. 8752m-9352m. |  | 3821.705 | [5 empty] | 461929.48
7 |  | Resectioning of Banaripara-Harta Road at Ch. 9352m-9760m. |  | 3097.89 | [5 empty] | 374441.97
7 |  |  |  | 24333.48 | [5 empty] | 2941187.74
9 |  |  |  | 24333.48 | 0 | 0 | 0 | 0 | 0 | 2941187.74 | 0 | 0
146 |  |  |  | 192389.527 | 55.873 | 1.2 | 0 | 0 | 157.675 | 343280622.74 | 12582955 | 316108545.03 | [6 empty] | 151763668 | [12 empty] | 0 |  |  | #REF!
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal

## All (4)
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [18 empty] | Upto Month: November/15.
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Fund Received (Tk) | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/CCA-EW/01 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 | 2126.54 | [5 empty] | 238242 |  | 238242 | Md. Giush Uddin LCS No-1 | 29/01/15 | 15/02/15 | 30/04/15 |  | 80% | 128685 | 54.01%
2 | BDRIDP/BAR/SDR/CCA-EW/02 | Resectioning of road from Charkawa Nayami-Shaheber hat via Durgapur hat (Barisal Sadar Upzila 7no. Charkawa union 1no word nurul islam to Bank Jalal Bari Pull) road from Ch. 0.00m-1000m. | 506514136 | 1311.25 | [5 empty] | 155407 | 155407 | 155407 | Md. Anowar Hossain Mridha LCS No-1 | 16/04/15 | 16/04/15 | 16/05/15 |  | 75% | 100881 | 64.91%
3 | [9 empty] | 228280 | 228280 | 228280 | Md. Jasim Uddin Milon LCS No-2 | 16/04/15 | 16/04/15 | 16/05/15 |  | 80% | 132596 | 58.08%
3 |  | Sub-Total: |  | 3437.79 | 0 | 0 | 0 | 0 | 0 | 621929 | 383687 | 621929 | [6 empty] | 362162 |  | 0 |  | 0
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZP/UZ-EW/01 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 0.00m-2100m. | 506942005 | [6 empty] | 822061 | 822061 | 822061 | LCS No-1 | [6 empty] | 0%
1 |  | Sub-Total: | [7 empty] | 822061 | 822061 | 822061 | [6 empty] | 0 |  | 0 |  | 0
Upazila: Muladi
1 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m. | 506692004 | 2490.25 | [5 empty] | 334778 |  | 334778 | Khorshed Khan LCS No-1 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 327963 | 100% |  | Final
2 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m. | 506692004 | 3042.25 | [5 empty] | 403489 |  | 403489 | Md. Alamgir Hossain LCS No-2 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 396479 | 100% |  | Final
3 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m. | 506692004 | 2886.92 | [5 empty] | 386512 |  | 386512 | Md. Baschu Sharder LCS No-3 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 384690 | 100% |  | Final
4 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m. | 506692004 | 2770 | [5 empty] | 371303 |  | 371303 | Abdus Salam Sharder LCS No-4 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 364872 | 100% |  | Final
5 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m. | 506692004 | 2775.75 | [5 empty] | 372013 |  | 372013 | Md. Bakiullah Sharder LCS No-5 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 367905 | 100% |  | Final
6 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m. | 506692004 | 2798.21 | [5 empty] | 374943 |  | 374943 | Md. Shalim LCS No-6 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 373728 | 99.68% |  | Final
7 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m. | 506692004 | 2793.69 | [5 empty] | 374353 |  | 374353 | Sukkur Ahmed Khan LCS No-7 | 18/05/14 | 22/05/14 | 22/10/14 |  | 70% | 238203 | 63.63%
8 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m. | 506692004 | 0.3 | [5 empty] | 369858 |  | 369858 | Nazma LCS No-8 | 18/05/14 | 22/05/14 | 22/10/14 |  | 70% | 226986 | 61.37%
9 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m. | 506692004 | 2969.75 | [5 empty] | 397315 |  | 397315 | Most. Jasmin Akter LCS No-9 | 18/05/14 | 22/05/14 | 22/10/14 |  | 70% | 261169 | 65.73%
10 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m. | 506692004 | 3207.06 | [5 empty] | 428100 |  | 428100 | Rashida LCS No-10 | 18/05/14 | 22/05/14 | 22/10/14 |  | 75% | 287470 | 67.15%
11 | BDRIDP/BAR/MUL/CCA-EW/01 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District. | 506695135 | 2052.81 | [5 empty] | 221909 |  | 221909 | Md Fazlu Tafader LCS No-1 | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 221206 | 100% |  | Final
12 | BDRIDP/BAR/MUL/CCA-EW/02 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District. | 506695127 | 2219.05 | [5 empty] | 239879 |  | 239879 | Md Kabir Hossain LCS No- | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 239119 | 100% |  | Final
13 | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. | 506694063 | 2210.3 | [5 empty] | 323312 |  | 323312 | Fokrul Ahosan LCS No-1 | 31/05/15 | 31/05/15 | 30/09/15 |  | 10% | 32000 | 9.898%
14 | BDRIDP/BAR/MUL/CCA-EW/04 | Resectioning of road from Char Kalekhan Goni Bari-khalil Bepari bari road by Earth work from Ch. 0.00m-1550m. | 56695075 | 2237.625 | [5 empty] | 101268 | 101268 | 101268 | Md. Mojibor Rohman | 28/07/15 | 30/08/15 | 30/12/15 |  | 100% | 97476 | 100% |  | Final
14 |  | Sub Total: |  | 34453.965 | 0 | 0 | 0 | 0 | 0 | 4699032 | 101268 | 4699032 | [6 empty] | 3819266 |  | 0 |  | 0
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m | 506073023 | [6 empty] | 131861 |  | 131861 | Anwar Hossain LCS No-01 | 15/04/15 | 16/04/15 | 16/05/15 |  | 92% | 118814 | 90.11%
2 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m. | 506073023 | [6 empty] | 256728 |  | 256728 | Md. Babul Howlader LCS No-02 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 226287 | 88.14%
3 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m | 506073023 | [6 empty] | 230734 |  | 230734 | Md. Joynal Abadin LCS No-03 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 203474 | 88.19%
4 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m | 506073023 | [6 empty] | 224792 |  | 224792 | Md. Royon Mollah LCS No-04 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 198427 | 88.27%
5 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m | 506073023 | [6 empty] | 233429 |  | 233429 | Md. Shahidul Sharif LCS No-05 | 15/04/15 | 16/04/15 | 16/05/15 |  | 95% | 220264 | 94.36%
6 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m | 506073023 | [6 empty] | 205799 |  | 205799 | H M Shamsul Huda LCS No-06 | 15/04/15 | 16/04/15 | 16/05/15 |  | 95% | 191913 | 93.25%
7 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m | 506073023 | [6 empty] | 243498 |  | 243498 | Md. Hanif LCS No-07 | 15/04/15 | 16/04/15 | 16/05/15 |  | 99% | 238747 | 98.05%
8 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m | 506073023 | [6 empty] | 230149 |  | 230149 | Md. Amir Ali Khan LCS No-08 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 203332 | 88.35%
9 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m | 506073023 | [6 empty] | 249498 |  | 249498 | Md. Monir Hossain LCS No-09 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 211006 | 84.57%
10 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m | 506073023 | [6 empty] | 222257 |  | 222257 | Md. Shalim Mridha LCS No-10 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 196192 | 88.27%
10 |  | Sub Total: |  | 0 | 0 | 0 | 0 | 0 | 0 | 2228745 | 0 | 2228745 | [6 empty] | 2008456 |  | 0 |  | 0
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/UN-EW/01 | Improvement of road from Mahilara UP Office to Chadshi hat via Billogram Bazar road By Earth Filling Work from Ch. 3740m-4850m. | 506323019 | 1756 | [5 empty] | 349519 |  | 349519 | LCS No-1 |  |  |  |  | 0% |  | 0%
1 |  |  |  | 1756 | 0 | 0 | 0 | 0 | 0 | 349519 | 0 | 349519 | [6 empty] | 0 |  | 0 |  | 0
Upazila: Agailjhara
1 | BDRIDP/BAR/AGL/CCA-EW/01 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal. | 506024034 | 2209.995 | [5 empty] | 302120 |  | 153224 | Ramesh Chandra Shikari LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 119075 | 77.71%
2 |  |  | 506024034 | 2209.995 | [5 empty] | 302120 |  | 148896 | Md Halim Talukder LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 122647 | 82.37%
3 | BDRIDP/BAR/AGL/CCA-EW/02 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 448658 |  | 216905 | Abdul Hakim Molla LCS No-1 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 140432 | 64.74%
4 |  | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 448658 |  | 231753 | Anukul Chandra Barai LCS No-2 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 185062 | 79.85%
5 | BDRIDP/BAR/AGL/CCA-EW/03 | Resectioning of road from Temar Bastala to Hawla Bridge via Nagar GPS-Talbazar-lichermath Bazar road from Ch. 3840-4840m. | [7 empty] | 402019 |  | 402019 | LCS
6 | BDRIDP/BAR/AGL/UZ-EW/01 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal. | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 124341 | Md. Sohrab Howlader LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 84836 | 68.23%
7 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 307876 | Md. Mosharef Sheikh LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 206520 | 67.08%
8 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 329106 | Abdul Rashid Howlader LCS No-3 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 224190 | 68.12%
9 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 330529 | Matleb Howlader LCS No-4 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 227035 | 68.69%
10 | BDRIDP/BAR/AGL/UN-EW/01 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal. | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 201404 | Mahim Baishnab LCS No-1 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 201396 | 100%
11 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 289300 | Sudhir Kumar Ojha LCS No-2 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 288996 | 99.89%
12 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 288022 | Banendra Nath Panday LCS No-3 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 287780 | 99.92%
13 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 207336 | Rabindranath Sarker LCS No-4 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207335 | 100%
14 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 205837 | Nirmal Ghatak LCS No-5 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205837 | 100%
15 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 207632 | Bebek Pandey LCS No-6 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207631 | 100%
16 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 205952 | Pangkoj Joydhor LCS No-7 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205952 | 100%
16 |  |  |  | 116932.232 | 0 | 0 | 0 | 0 | 0 | 17509364 | 0 | 3850132 | [6 empty] | 2914724 |  | 0 |  | 0
Upazila: Babugonj
1 | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. | 506033006 | [6 empty] | 195850 |  | 195850 | Md. Masum Hossain Gazi LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 19500 | 9.957%
2 | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km. | 506035070 | [6 empty] | 285121 |  | 285121 | Taslima LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 28500 | 9.996%
3 | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km. | 506034095 | [6 empty] | 381065 |  | 381065 | Rajib Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 38100 | 9.998%
4 | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km. | 506035006 | [6 empty] | 300535 |  | 300535 | Md. Liton Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 30000 | 9.982%
5 | BDRIDP/BAR/BAB/CCA-EW/04 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m. | 506034024 | [6 empty] | 354810 |  | 354810 | Md. Kabir Sikder LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 40% | 35400 | 9.977%
5 | [9 empty] | 1517381 | 0 | 1517381 | [6 empty] | 151500 |  | 0 |  | 0
Upazila: Hizla
1 | BDRIDP/BAR/HZL/UZ-EW/01 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 0.00m-325m | 506362009 | [6 empty] | 226562 | 226562 | 226562 | [5 empty] | 10% | 22600 | 9.975%
2 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 325m-650m | [7 empty] | 220227 | 220227 | 220227 | [5 empty] | 10% | 22000 | 9.99%
3 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 650m-1000m | [7 empty] | 217087 | 217087 | 217087 | [5 empty] | 10% | 21700 | 9.996%
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 663876 | 663876 | 663876 | [6 empty] | 66300
53 |  |  |  | 156579.987 | 0 | 0 | 0 | 0 | 0 | 28411907 | 1970892 | 14752675 | [6 empty] | 9322408 |  | 0 |  | #VALUE!
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal

## All (3)
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [18 empty] | Upto Month: November/15.
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Fund Received (Tk) | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 10% |  | 0% |  |  |  | 1008836.867
2 | BDRIDP/BAR/SDR/CCA-St/04 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m. | 506514048 | [5 empty] | 8 | 1333966 |  | 1027297.63 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 0% |  | 0%
3 | BDRIDP/BAR/SDR/CCA-St/02 | Construction of 1.0 x 1.0m and 1.6 x1.6m RCC Box culvert on Kasem Defader Bari - Karnokati High School & College road at ch.773m & 526m e-ID: 17457 | 506514176 | [5 empty] | 1.6 | 516289 |  | 828108.82 | M/S Khondokar Borthers | 15/06/15 | 23/06/15 | 22/12/15 |  | 0%
3 |  | Sub-Total: |  | 0 | 0 | 0 | 0 | 0 | 29.6 | 14623109 | 0 | 11943775.12 | [6 empty] | 0 |  | 0 |  |  | 1008836.867
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. | [6 empty] | 15 | 6544168 |  | 5567698.82 | M/S Safi Enterprise | 2014-11-06 | 18/06/14 | 17/06/15 |  | 5% |  | 0% |  |  |  | 278384.941
2 | BDRIDP/BAR/UZP/CCA-St/02 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m. | 506945205 | [5 empty] | 8.625 | 2586217 |  | 2015457.24 | Md Zakir Hossain Mia | 23/11/14 | 30/11/14 | 30/05/15 |  | 100% | 1800000 | 89.31% |  |  |  | 215457.24
3 | BDRIDP/BAR/UZP/CCA-St/03 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m. | 506945129 | [5 empty] | 4 | 3397103 |  | 2682855.6 | Md Zakir Hossain Mia | 2015-11-05 | 18/05/15 | 18/10/15 |  | 90% | 2264000 | 84.39% |  |  | 70% | -386001.08
3 |  | Sub-Total: |  | 0 | 0 | 0 | 0 | 0 | 27.625 | 12527488 | 0 | 10266011.66 | [6 empty] | 4064000 |  | 0 |  |  | 107841.101
Upazila: Muladi
1 | BDRIDP/BAR/MUL/UZ-St/01 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m. | 506692004 | [6 empty] | 7798117 |  | 8772459.2 | M/S Misi Construction | 21/07/14 | 28/07/14 | 27/03/15 |  | 100% | 8713982 | 100% |  | Final |  | 58477.2
2 | BDRIDP/BAR/MUL/CCA-St/02 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m. | 506694001 | [5 empty] | 12 | 2543802 |  | 1762404.98 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 10% |  | 0% |  |  | 100% | 1762404.98
3 | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m | 506694060 | [5 empty] | 16 | 5115590 |  | 3683201.71 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 10% |  | 0% |  |  | 60% | 2209921.026
4 | BDRIDP/BAR/MUL/CCA-St/01 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m | 506694063 | [5 empty] | 2 | 505514 |  | 368648.25 | M/S Sraboni Enterprise | 21/06/15 | 28/06/15 | 27/12/15 |  | 10% |  | 0% |  |  | 100% | 368648.25
5 | BDRIDP/BAR/MUL/CCA-St/04 | Construction of 1 vent 4.00m×4.00m and 1 vent 1.00m×1.00m RCC Box Culvert on Char Kalekhan Goni Bari-Khalil Bepari Bari road at Ch.182m & 330m. | 56695075 | [5 empty] | 5 | 1937445 |  | 1462533.11 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 0% |  | 0% |  |  | 50% | 968722.5
5 |  | Sub Total: |  | 0 | 0 | 0 | 0 | 0 | 35 | 17900468 | 0 | 16049247.25 | [6 empty] | 8713982 |  | 0 |  |  | 4399451.456
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/UN-St/01 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 | 506073023 | [5 empty] | 27.2 | 7339681 |  | 5345279.54 | M/S Khondokear Brothers | 14/06/15 | 21/06/15 | 20/06/16 |  | 0%
1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 27.2 | 7339681 | 0 | 5345279.54 | [6 empty] | 0 |  | 0 |  |  | #REF!
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/UN-St/01 | Construction of 2-Vent 4.30mx4.30m RCC Box Culvert on Mahilara UP office to Chadshi hat via Billogram Bazar road at Ch. 4200m. | 506323019 | [5 empty] | 8.6 | 1970942 |  | 2069109 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/12/15 |  | 0% |  | 0%
2 | BDRIDP/BAR/GOR/CCA-St/01 | Construction of 3 Nos Single Vent 4.30mx4.30m RCC Box Culvert & 2 nos U-Drain on Battala Kapali bari Bridge (NHW) to Khanjapur High School road at ch. 95m,270m,1276m564m&970m Under Gournadi Upazila, District-Barisal e-ID : 22284 | 506324136 | [5 empty] | 14.9 | 6680560 |  | 6946789.2 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 0% |  | 0%
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 23.5 | 8651502 | 0 | 9015898.2 | [6 empty] | 0 |  | 0 |  |  | #REF!
Upazila: Agailjhara
1 | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. | 506025058 | [5 empty] | 8.9 | 1677674 |  | 1771918.99 | M/S Sharif Enterprise | 28/05/15 | 2015-04-06 | 2015-04-12 |  | 0% |  | 0%
1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 8.9 | 1677674 | 0 | 1771918.99 | [6 empty] | 0 |  | 0 |  |  | 0
Upazila: Babugonj
1 | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 506035070 | [5 empty] | 8.3 | 2931768 | 184122 | 3071060.04 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 0% |  | 0% |  |  | 60% | 1842636.024
2 | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 506034095 | [5 empty] | 18.2 | 4744358 | 199349 | 4968549.43 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 10% |  | 0% |  |  | 60% | 2981129.658
3 | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 506035006 | [5 empty] | 7.6 | 2001016 | 62866 | 2095536.41 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 50% |  | 0% |  |  | 60% | 1257321.846
4 | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 506034024 | [5 empty] | 12 | 1982458 | 150637 | 2076355.09 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 25% |  | 0% |  |  | 60% | 1245813.054
5 | BDRIDP/BAR/BAB/UN-St/01 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m. | 506033006 | [5 empty] | 7.6 | 1443386 | 41933 | 1029755.17 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 60% |  | 0% |  |  | 60% | 617853.102
5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 53.7 | 13102986 | 638907 | 13241256.14 | [6 empty] | 0 |  | 0 |  |  | 7944753.684
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/CCA-St/01 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal. | 506625079 | [5 empty] | 1 | 222783 |  | 184788 | M/S Hasib Enterprise | 2014-09-11 | 16/11/14 | 15/03/15 |  | 100% | 167876 | 100% |  | Final
1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 222783 | 0 | 184788 | [6 empty] | 167876 |  | 0 |  |  | 0
21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 206.525 | 76045691 | 638907 | 67818174.9 | [6 empty] | 12945858 |  | 0 |  |  | #VALUE!
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal

## All (2)
MYcÖRvZš¿x evsjv‡`k miKv‡ii, gvbbxq wegvb I ch©Ub gš¿x, Rbve †gvt iv‡m` Lvb †gbb KZ…©K eveyMÄ Dc‡Rjvq D‡ØvabK…Z mo‡Ki bvg I ZvwiL
District: Barisal
µwgK bs | c¨v‡KR bs | mo‡Ki bvg | D‡Øva‡bi ZvwiL | gšÍe¨
1 | 2 | 3 | 4 | 5
Upazila: Babugonj
1 | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km. | 17/04/15Bs 4Vv †eŠkvL 1422 evs
2 | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 17/04/15Bs 4Vv †eŠkvL 1422 evs
3 | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. | 17/04/15Bs 4Vv †eŠkvL 1422 evs
4 | BDRIDP/BAR/BAB/CCA-Rd/05 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District. | 17/04/15Bs 4Vv †eŠkvL 1422 evs
5 | CCRIP/BARI/UNR/2014/W03 | Improvement work of Baherchar Hat-Baherchar Hospital Road at Ch. 750m-3350m. | 23/10/14Bs 8B KvwZ©K 1421 evs
6 | CCRIP/BARI/VR/2014/W-04 | Improvement work of Amirgar Hat-Mirzagonj via Maidaner Hat Road at Ch. 0.00m-3000m. | 24/10/14Bs 9B KvwZ©K 1421 evs
7 | CCRIP/BARI/UNR/2014/W-05 | Improvement work of Rakudia Palli Biddut sub Center (RHD), Baherchar Bazar Road at Ch. 810m-1840m & Ch. 3540m-4975m. | 23/10/14Bs 8B KvwZ©K 1421 evs

## Progress
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [18 empty] | Reporting Month: March/19
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Fund Received (Tk) | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila: Barisal Sadar
1 | BDRIDP/BAR/SDR/CCA-Rd/01 | Improvement of Bukhainagar Bridge to Abdul Aziz Khan's House via Shaluka GPS Road (Ch. 00-500m). | 506514170 |  | 0.5 |  |  |  |  | 2045654 |  | 1613223.41 | M/S Talukder Enterprise | 2014-09-06 | 16/06/14 | 16/09/14 |  | 100% | 1607918 | 99.67% |  | Final
2 | BDRIDP/BAR/SDR/CCA-Rd/02 | Improvement of Chandpura Mojidderhat-Saheberhat via Khontakhali School road from Ch. 1635-3192m. | 506514154 |  | 1.557 |  |  |  |  | 7466730 |  | 6279530.87 | M/S G M Construction | 2014-10-08 | 17/08/14 | 16/05/15 |  | 100% | 6266613 | 100% |  | Final
3 | BDRIDP/BAR/SDR/CCA-Rd/03 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m | 506514148 |  | 0.513 |  |  |  |  | 2809559 |  | 2294335.91 | M/S Serajul Islam Hanif | 24/07/14 | 2014-01-08 | 2015-01-02 |  | 100% | 1954150 | 100% |  | Final | 100% | 340185.91
4 | BDRIDP/BAR/SDR/CCA-Rd/04 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 |  | 0.732 |  |  |  |  | 2900881 | 1230068 | 2238782.5 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 100% | 2179525 | 100% |  | Final
5 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 100% | 8800000 | 87.23% |  |  |  | 10088368.67
6 | BDRIDP/BAR/SDR/CCA-Rd/04 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366m. | 506515102 |  | 1 |  |  |  | 1.6 | 4543594 |  | 4037481 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2016-11-04 |  | 100% | 3913837 | 100% |  | Final | 50% | -1895096.5
7 | BDRIDP/BAR/SDR/CCA-St/04 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m. | 506514048 | [5 empty] | 8 | 1333966 |  | 1027297.63 | M/S Khondokar Borthers | 21/07/15 | 28/07/15 | 27/01/16 |  | 100% | 1027297 | 100% |  | Final
8 | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 506514048 |  | 2.782 |  |  |  |  | 10910419 | 207108 | 8773072.65 | M/S Hasan Construction | 2015-10-05 | 17/05/15 | 17/02/16 |  | 100% | 5512074 | 100% |  | Cancelled | 70% | 629076.855
9 | BDRIDP/BAR/SDR/CCA-St/02 | Construction of 1.0 x 1.0m and 1.6 x1.6m RCC Box culvert on Kasem Defader Bari - Karnokati High School & College road at ch.773m & 526m e-ID: 17457 | 506514176 | [5 empty] | 1.6 | 516289 |  | 428108.82 | M/S Khondokar Borthers | 15/06/15 | 23/06/15 | 22/12/15 |  | 100% | 425862 | 100% |  | Final
10 | BDRIDP/BAR/SDR/CCA-Rd(R)/06 | Rehabilitation of road from Kasem Defader Bari - Karnokati High School & College road By BC from ch.310 - 1125m under Sadar upazila ,Barisal District [Salvaged Cost-Tk 4,97,038.00] | 506514176 |  | 0.815 |  |  |  |  | 3385819 |  | 3116111 | M/S Oshin Enterprise | 2015-11-05 | 18/05/15 | 18/02/16 |  | 100% | 3116111 | 100% |  | Final
11 | BDRIDP/BAR/SDR/CCA-Rd/07 | Improvement of road from Charkawa Nayani - Shaberhat via Durgapur hat (Barisal Sadar Upazila 7no. Charkawa union 1no.word nurul islam to Bank Jalal Bari Pull) road By HBB from Ch.0.0 - 1000m under Barisal-S Upazila,Barisal District. e-ID : 29367 | 506514136 |  |  | 1 |  |  |  | 2430847 |  | 2063060.77 | M/S Apu Enterprise | 2015-03-11 | 2015-10-11 | 2016-10-05 |  | 100% | 2063045 | 100% |  | Final
12 | BDRIDP/BAR/SDR/CCA-Rd/09 | (a) Improvement of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge) (b) Construction of 1.60m×1.60m Box Culvert and U-Type Culvert at Ch. 694m & 1300m on Shibpasha-Sholna Talukder Bari via Malek Police bari. | 506515006 |  | 1.6 |  |  |  | 1.6 | 12590432 | 937125 | 10801668.14 | M/S Khondokear Enterprise | 30/06/16 | 30/06/16 | 26/06/17 |  | 100% | 10108407 | 93.58% |  |  | 285845
13 | BDRIDP/BAR/SDR/CCA-Rd/10 | Improvement of Road from Shaheber Hat to Bairagibari Via Gourchandra Bridge (Bisharad GPS cum CS) from Ch.5103 - 6647m including 1 No.1.0m x1.0m U-Drain & 1No.3.m x 3.0m RCC Box Culvert at Ch.5479m & 6141m under Sadar Upazila,Barisal. | 506514137 |  | 1.544 |  |  |  | 4 | 9500469 |  | 8550422.1 | M/S Sirajul Alam Sikder | 22/05/17 | 29/05/17 | 29/02/18 |  | 65% | 1250000 | 14.62%
14 | BDRIDP/BAR/SDR/UN-Rd/01 | a .Improvement of road from Gilatali Kheyaghat - Biswasher hat via Model Madrasha. from Ch.1500 - 4260m under Sadar UpazilaDistrict-Barisal. b. Construction of 3 Nos 1.6m x 1.6m RCC Box culvert at ch.2568m 3530m & 4033m and 1No.4m x4m RCC Box Culvert at ch.3640m on the same road. | 506513003 |  | 2.76 |  |  |  | 8.8 | 18760504 |  | 16884454 | Md Mafuz Khan | 18/01/18 |  | 31/11/18 |  | 20%
15 | BDRIDP/BAR/SDR/UZ-Rd/01 | Improvement of Shehaber Hat Singherkati Chandramohon road from Ch. 729m - 1308m.under Sadar Upazila Barisal. | 506512003 |  | 0.579 |  |  |  |  | 4209569.27 |  | 3788612.34 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 70% |  | 0%
16 | BDRIDP/BAR/SDR/UN-Rd/02 | Improvement of Charkawa Kheyaghat - Durgapur hat road from Ch. 3000m - 3600m.under Sadar Upazila Barisal District. | 506513004 |  | 0.6 |  |  |  |  | 3464647.09 |  | 3118182.38 | M/S Niaz Traders | 2018-02-01 | 2018-09-02 | 2018-09-08 |  | 70% | 1370000 | 43.94%
17 | BDRIDP/BAR/SDR/CCA-Rd(R)/11 | Improvement of road from Charmonai Talukder Bari-West Razarchar Club by BC. at Ch. 0.00m-1203.00m under Charmonai Union, Upazila : Sadar, Dist-Barisal [Salvaged cost- Tk 231155.00] | 506515109 |  | 1.203 |  |  |  |  | 8769166.6 |  | 7892249.94 | M/S Kohinoor Enterprise | 18/01/18 | 25/01/18 | 25/11/18 |  | 40% |  | 0%
18 | BDRIDP/BAR/SDR/CCA-RdR/12 | Improvement of road Shibpasha - Sholna Talukder bari via H/O Malek Police at ch.1600km - 2020km under Sadar Upazila Barisal. | 506515006 |  | 0.42 |  |  |  |  | 2720015.56 |  | 2448014.04 | M/S Kohinoor Enterprise | 2018-04-02 | 2018-11-02 | 2018-11-08 |  | 100% | 2447516 | 99.98% |  | Final
19 | BDRIDP/BAR/SDR/Gha/01 | Construction of Ghat & CC Road at Shaheber Bazar under Sadar Upazila Barisal . | [7 empty] | 3278780.89 |  | 3102813.825 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 20% |  | 0%
20 | BDRIDP/BAR/SDR/CCA-Rd/13 | Improvement of Shibpasha Sarder bari Sholna Tarunclub Road Road Part-A Earth work at Ch. 0.00 -1505.00m Part-B Carpeting BC work at Ch. 0.00-1505.00m Salvage Amount Tk. 2626839.00 Part-C Construction of 2Nos U-Drain 1.00mx1.00m at Ch. 140m & 380m Under Barisal Sadar Upazila District - Barisal. | 506514007 |  | 1.505 |  |  |  | 2 | 10603941.33 |  | 10073944.25 | M/S Noor & Sons | 2018-11-06 | 18/06/18 | 18/05/19 |  | 35% | 600000 | 5.956%
21 | BDRIDP/BAR/SDR/CCA-RdR/14 | Improvement of Shibpasha Sarder bari-Sholna Tarunclub road a Earth work at Ch.1505-2392m b Carpetting BC Ch.1505 -2392m c Construction of 1 No Double vent Box culvert 4.0m x 4.0m at ch.1901m d Protective worksPalisading 134m e Link Road Baitul Mamur Jame Mosque 167.00m under Bakergonj Upazila Barishal District.Salvaged Cost TK 1935498.00 | 506514007 |  | 1.054 |  |  |  | 8 | 10111914.02 | [11 empty] | E-Tender Under Process.
21 |  | Sub-Total: |  | 0 | 19.164 | 1 | 0 | 0 | 55.6 | 135126051.76 | 2374301 | 108619734.245 | [6 empty] | 52642355 |  | 0 |  |  | 9162534.935
1 | BDRIDP/BAR/SDR/CCA-EW/01 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 | 2126.54 | [5 empty] | 238242 |  | 238242 | Md. Giush Uddin LCS No-1 | 29/01/15 | 15/02/15 | 30/04/15 |  | 100% | 190934 | 100% |  | Final
2 | BDRIDP/BAR/SDR/CCA-EW/02 | Resectioning of road from Charkawa Nayami-Shaheber hat via Durgapur hat (Barisal Sadar Upzila 7no. Charkawa union 1no word nurul islam to Bank Jalal Bari Pull) road from Ch. 0.00m-1000m. | 506514136 | 1311.25 | [5 empty] | 155407 | 155407 | 155407 | Md. Anowar Hossain Mridha LCS No-1 | 16/04/15 | 16/04/15 | 16/05/15 |  | 100% | 100881 | 64.91%
3 | [9 empty] | 228280 | 228280 | 228280 | Md. Jasim Uddin Milon LCS No-2 | 16/04/15 | 16/04/15 | 16/05/15 |  | 100% | 132596 | 58.08%
4 | BDRIDP/BAR/SDR/CCA-EW/03 | Resectioning of road Shibpasha-Sholna Talukder Bari via Malek Police Bari at Ch. 0.00m-1600m (Sholna DC Road-Tulatola-Badantola with link road Tulatola-Ghorami Bari Bridge). | 506515006 | 3309.7 | [5 empty] | 400044 |  | 400044 | Fatema Begum LCS No-1 | 25/02/16 | 29/02/16 | 30/04/16 |  | 100% | 362610 | 90.64%
5 | BDRIDP/BAR/SDR/CCA-EW/04 | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 2557m-3280m. | [7 empty] | 305905 | 305905 | 305905 | Md. Hemayet Howlader LCS No-1 | 16/03/17 | 28/03/17 | 30/04/17 |  | 100% | 30000 | 9.807%
6 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 3280m-4580m | [7 empty] | 256209 | 256209 | 256209 | Md. Mojibor Rohman Sikder LCS No-2 | 16/03/17 | 28/03/17 | 30/04/17 |  | 5% | 117852 | 46%
7 |  | Resectioning of Road from Shaheber Hat to Bairagibari via Gourchandar Bridge (Bisharad GPS cum CS) at Ch. 4580m-6647m | [7 empty] | 189642 | 189642 | 189642 | Mosharof Hossain Shikder LCS No-3 | 16/03/17 | 28/03/17 | 30/04/17 |  | 100% | 172057 | 100%
8 | BDRIDP/BAR/SDR/UN-EW/01 | Resectioning of Road from Gilatali Kheyaghat-Biswasherhat via Model Madrasha at Ch. 1500m-2700m | [7 empty] | 438144 |  | 438144 | LCS No-1 |  |  |  |  | 100% | 410512 | 100% |  | Final
9 |  | Resectioning of Road from Gilatali Kheyaghat-Biswasherhat via Model Madrasha at Ch. 2700m-4260m | [7 empty] | 426063 |  | 426063 | LCS No-2 |  |  |  |  | 100% | 325495 | 100% |  | Final
10 | BDRIDP/BAR/SDW/UZ-Ew/01 | Resectioning of Shehaber Hat-Singherkati Chandramohon Road at Ch. 729m-1009m | 506512003 | [6 empty] | 255149 |  | 255149 | LCS No-1 |  |  |  |  | 100% | 250500 | 100% |  | Final
11 |  | Resectioning of Shehaber Hat-Singherkati Chandramohon Road at Ch. 1009m-1309m | [7 empty] | 355749 |  | 355749 | LCS No-2 |  |  |  |  | 100% | 350500 | 100% |  | Final
11 |  | Sub-Total: |  | 6747.49 | 0 | 0 | 0 | 0 | 0 | 3248834 | 1135443 | 3248834 | [6 empty] | 2443937 |  | 0 |  |  | 0
32 |  | Grand Total: |  | 6747.49 | 19.164 | 1 | 0 | 0 | 55.6 | 138374885.76 | 3509744 | 111868568.245 | [6 empty] | 55086292 |  | 0 |  |  | 9162534.935
Upazila: Uzirpur.
1 | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. | [6 empty] | 15 | 6544168 |  | 5567698.82 | M/S Safi Enterprise | 2014-11-06 | 18/06/14 | 17/06/15 |  | 100% | 5512198 | 100% |  | Final |  | 5567698.82
2 | BDRIDP/BAR/UZP/CCA-St/02 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m. | 506945205 | [5 empty] | 8.625 | 2586217 |  | 2015457.24 | Md Zakir Hossain Mia | 23/11/14 | 30/11/14 | 30/05/15 |  | 100% | 1973907 | 100% |  | Final |  | 41550.24
3 | BDRIDP/BAR/UZP/CCA-Rd/01 | Improvement of road from Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market, Nurani Madrasha & H/O Mr.Habibur Rahman (Beer Protik) by BC from Ch.0.00-1500m under Uzirpur Upazila, Barisal. | 506945205 |  | 1.5 |  |  |  |  | 6378273 |  | 5167677 | Md Sirazul Islam Hanif | 2014-01-12 | 2014-08-12 | 2015-07-06 |  | 100% | 5166254 | 99.97% |  | Final | 70% | -1548880.1
4 | BDRIDP/BAR/UZP/CCA-Rd/02 | Improvement of road from Paschim Satla WAPDA to Satla Kheyaghat via H/O Fazlul Hoque Hawlader & Mosque By HBB from Ch. 0.00-375m. | 506945204 |  |  | 0.375 |  |  |  | 1316117 |  | 1225909.58 | M/S Lutful Kabir | 2015-05-04 | 2015-12-04 | 2015-11-09 |  | 100% | 1223186 | 99.78% |  | Final | 100% | 2723.58
5 | BDRIDP/BAR/UZP/CCA-St/03 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m. | 506945129 | [5 empty] | 4 | 3397103 |  | 2682855.6 | Md Zakir Hossain Mia | 2015-11-05 | 18/05/15 | 18/10/15 |  | 100% | 2674595 | 99.69% |  | Final | 70% | -796596.08
6 | BDRIDP/BAR/UZP/UZ-Rd(R)/01 | Rehabilitation of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) road from Ch. 0.00m-2100m. | 506942005 |  | 2.1 |  |  |  |  | 10215215 |  | 8522561.6 | M/S G M Construction | 28/09/15 | 2015-05-10 | 2016-05-04 |  | 100% | 8522424 | 100% |  | Final
7 | BDRIDP/BAR/UZP/UZ-Rd /02 | Improvement of Road from Satla -Chowmuhani (Bisherkandi upto Banaripara Upazila) [Satla GC (Satla H. School) -Razapur Chowmohoni-Bisherkandi GC Road) At Ch.0.0m -2605m under uzirpur Upazila, Barisal. | 506942007 |  | 2.605 |  |  |  |  | 18314961 | 18314961 | 14275617.27 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 60% | 4950000 | 34.67%
8 | BDRIDP/BAR/UZP/UZ-Rd/03 | Improvement of Road from Kalirbazar GC - Barisal Dhaka NHW - Sikerpur R & H Road at Ch.1754 - 4050m under Uzirpur Upazila, Barisal. | 506942015 |  | 2.296 |  |  |  |  | 14753928 | 14753928 | 11501091.23 | M/S Hasan Construction | 2017-01-03 | 2017-08-03 | 2017-08-12 |  | 75% | 8335000 | 72.47%
9 | BDRIDP/BAR/UZP/UZ-RdR/04 | Rehabilitation of Harta Chowmuhani Bisherkandi Harta GC - Bisharkandi GC Road at Ch.0.00m - 2600m including 04 Nos 0.625m x 0.600 Drainage CulvertU-Drain at ch.805m 933m 1148m & 1248m under Uzirpur Upazila Barisal District Salvaged Value 4053176.00 | 506942009 |  | 2.6 |  |  |  | 2.5 | 17827349 |  | 18399998.87 | M/S S H Enterprise | 2018-08-03 | 15/03/18 | 15/03/19 |  | 70% | 2600000 | 14.13%
10 | BDRIDP/BAR/UZP/UN-Rd/01 | a Improvement of Uzirpur H/Q-Bamrail UP Office -Gondesor BazarUzirpur UZHQ Girls School-Kholna More-Bamrail R&H from Ch.3400m - 5740m under Banaripara UpazilaBarisal District. b Construction of 2Nos U-Drain on the same road at Ch.4695m & 5090m. | 506943007 506942018 |  | 2.34 |  |  |  | 1.2 | 15060662.42 |  | 13554596.17 | M/S Niaz Traders | 2017-02-10 | 2017-09-10 | 2018-09-08 |  | 40% | 450000 | 3.32%
11 | BDRIDP/BAR/UZP/UN-St/01 | Construction of 12.00m Long RCC Girder Bridge over Chowdhuri Hat - Hasti Shundi via Daberkul road infront of A. Latif MasterDaberkul Chowmohani - Chowmohini Sere Bangla road at ch. 00.0m under Uzirpur Upazila Barisal District. | 506943004 | [5 empty] | 12 |  |  | 7535398.53 | M.M Builders & Engineers | 30/01/18 | 2018-07-02 | 2018-07-12 |  | 100% | 6500000 | 86.26%
12 | BDRIDP/BAR/UZP/CCA-Rd/04 | Improvement of Old Sikerpur Bandar-Abul Hasan Mridhas House Connecting road under Uzirpur Upazila Barisal a Earthwork Ch.0.0m - 360m b Bituminous Carpetting Ch.0.0m - 360m c U-Drain 01 no at Ch.117. | 506945281 |  | 0.36 |  |  |  | 1 | 2738720.64 |  | 2464848.57 | M/S Kohinoor Enterprise | 22/04/18 | 29/04/18 | 29/08/18 |  | 35% |  | 0%
13 | BDRIDP/BAR/UZP/CCA-Rd/03 | Improvement of road from Guthia kakradhari Connecting road North side of Khaleque Mollas House of Dahorpara GPS via Mojid Masters House under Uzirpur Upazila Barisal a Earthwork Ch.0.0m -1550m b Bituminous Carpetting Ch.0.0m - 1550m c U-Drain 04 nos at Ch.130m476m655m1230m & 2Nos 1-Vent 4m x 4m RCC Box Culvert at ch.755m & 1540m | 506944084 |  | 1.55 |  |  |  | 16 | 12042875.78 |  | 10838588.2 | Md. Mahafuz Khan | 2018-03-05 | 2018-10-05 | 2019-10-03 |  | 60% | 2600000 | 23.99%
14 | BDRIDP/BAR/UZP/Gha/01 | Construction of Typical Ghat at Satla Bazar under Uzirpur Upazila Barisal . | [7 empty] | 2565467.67 |  | 2460575.82 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 40% | 800000 | 32.51%
15 | BDRIDP/BAR/UZP/CCA-Rd/05 | Part A Improvement of road from Muktijodda Milon Kendra Connecting road Harasia road.i Carpeting DC Ch. 0.00m-900m. ii 3 Nos.0.625mx0.600m U-Drain at Ch.10m365m665m.Part B Improvement of road from East Joysree Village road.i Carpeting DC Ch. 0.00m-1000m.ii 2 Nos.0.625mx0.600m U-Drain at Ch.605m865m. Salvaged Cost Tk 141267.00Part C Improvement of road from Jugihati-Chokder bari Jame Mosque to Damodarkathi Tri mukhi Atok road by DC at Ch.0.00m-1050.00m with 1 No.4.30mx4.30m RCC Box Culvert at Ch.560m. 3 Nos.0.625mx0.600m U-Drain at Ch.130m760m & 835m. Under Uzirpur Upazila Barishal District. | 506945170 506945028 506945172 |  | 2.95 |  |  |  | 9.295 | 23428700 | [11 empty] | E-Tender Under Process.
15 |  | Sub-Total: |  | 0 | 18.301 | 0.375 | 0 | 0 | 69.62 | 137169757.51 | 33068889 | 106212874.5 | [6 empty] | 51307564 |  | 0 |  |  | 3266496.46
1 | BDRIDP/BAR/UZP/UZ-EW/01 | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 0.00m-700m. | 506942005 | [6 empty] | 258990 | 258990 | 258990 | Yasin Sarder LCS No-1 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 241304 | 100% |  | Final
2 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 700m-1400m. | [7 empty] | 284900 | 284900 | 284900 | Iqbal Hossan LCS No-2 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 271670 | 100% |  | Final
3 |  | Resectioning of road from Dhamura-Sholok Batajore (Upto Gouranadi Upazila Border) Road from Ch. 1400m-2100m. | [7 empty] | 278170 | 278170 | 278170 | Supian LCS No-3 | 14/01/16 | 15/02/16 | 30/04/16 |  | 100% | 275956 | 100% |  | Final
4 | BDRIDP/BAR/UZP/UZ-EW/02 | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 0.00m-1100m. | 506942007 | 9764.116 | [5 empty] | 418543 | 418543 | 418543 | Md. Shahidul Islam LCS No-1 | 30/01/17 | 2017-01-02 | 30/04/17 |  | 100% | 251299 | 60.04%
5 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1100m-1900m. | [7 empty] | 451503 | 451503 | 451503 | Md. Khalilur Rahman LCS No-2 | 30/01/17 | 2017-01-02 | 30/04/17 |  | 70% | 271244 | 60.08%
6 |  | Resectioning of Road from Satla-Chowmuhani (Bisherkandi upto Banaripara Upazila) {Satla GC (Satla H. School)-Razapur Chowmohoni-Bisherkandi GC Road} at Ch. 1900m-2605m. | [7 empty] | 491755 | 491755 | 491755 | Habibur Bapari LCS No-3 | 30/01/17 | 2017-01-02 | 30/04/17 |  | 70% | 296067 | 60.21%
7 | BDRIDP/BAR/UZP/UZ-EW/03 | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 1754m-2850m. | 506942015 | [6 empty] | 421703 | 421703 | 421703 | Kamrun Nesa LCS No-1 | 2016-12-12 | 18/12/16 | 18/03/17 |  | 75% | 303105 | 71.88%
8 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 2850m-3650m. | [7 empty] | 466527 | 466527 | 466527 | Rubina Begum LCS No-2 | 2016-12-12 | 18/12/16 | 18/03/17 |  | 75% | 330085 | 70.75%
9 |  | Resectioning of Road from Kalirbazar GC-Barisal Dhaka NHW-Sikerpur R&H Road Ch. 3650m-4050m. | [7 empty] | 342538 | 342538 | 342538 | Monzu Begum LCS No-3 | 2016-12-12 | 18/12/16 | 18/03/17 |  | 75% | 245583 | 71.7%
10 | BDRIDP/BAR/UZP/UN-EW/01 | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3400m-3900m By Earth. | 506943007 506942018 | [6 empty] | 434519 | 434519 | 434519 | Md. Ziaul Haque LCS No-1 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 430783 | 100% |  | Final
11 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 3900m-4300m By Earth. | [7 empty] | 437099 | 437099 | 437099 | Khokon Sharder LCS No-2 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 435285 | 99.58% |  | Final
12 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4300m-4900m By Earth. | [7 empty] | 461279 | 461279 | 461279 | Rofiqul Islam LCS No-3 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 459873 | 99.7% |  | Final
13 |  | Resectioning of Uzirpur H/Q Bamril UP Office-Gondesor Bazar (Uzirpur UZHQ Girls School-Kholna More-Bamril R&H) From Ch. 4900m-5740m By Earth. | [7 empty] | 310321 | 310321 | 310321 | Nurul Hoq Sikder LCS No-4 | 28/05/17 | 31/05/17 | 31/10/17 |  | 100% | 310041 | 99.91% |  | Final
14 | BDRIDP/BAR/UZP/UZ-EW/04 | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 0.00m-1000m | 506942009 | [6 empty] | 512862 | 512862 | 512862 | Shilpi Biswas LCS No-1 | 30/10/17 | 30/10/17 | 30/03/18 |  | 100% | 511764 | 99.79%
15 |  | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 1000m-1700m | [7 empty] | 380788 | 380788 | 380788 | Namita Rani Biswas LCS No-2 | 30/10/17 | 30/10/17 | 30/03/18 |  | 35% | 113000 | 29.68%
16 |  | Resectioning of Harta Chowmuhani (Bisherkandi) {Harta GC-Bisherkandi GC} Road at Ch. 1700m-2500m | [7 empty] | 461975 | 461975 | 461975 | Sabika Das LCS No-3 | 30/10/17 | 30/10/17 | 30/03/18 |  | 100% | 458856 | 100% |  | Final
16 |  | Sub-Total: |  | 9764.116 | 0 | 0 | 0 | 0 | 0 | 6413472 | 6413472 | 6413472 | [6 empty] | 5205915 |  | 0 |  |  | 0
31 |  | Grand Total: |  | 9764.116 | 18.301 | 0.375 | 0 | 0 | 69.62 | 143583229.51 | 39482361 | 112626346.5 | [6 empty] | 56513479 |  | 0 |  |  | 3266496.46
Upazila: Muladi
1 | BDRIDP/BAR/MUL/UZ-St/01 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m. | 506692004 | [5 empty] | 20 | 7798117 |  | 8772459.2 | M/S Misi Construction | 21/07/14 | 28/07/14 | 27/03/15 |  | 100% | 8713982 | 100% |  | Final |  | 58477.2
2 | BDRIDP/BAR/MUL/UZ-Rd/01 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m. | 506692004 |  | 3.45 |  |  |  |  | 24406349 |  | 20744407.41 | M/S Lutful Kobir | 13/08/14 | 20/08/14 | 20/05/15 |  | 100% | 20716273 | 100% |  | Final | 100% | 28134.41
3 | BDRIDP/BAR/MUL/CCA-Rd/01 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District. | 506695135 |  | 1 |  |  |  |  | 4172838 |  | 3545269 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 3539794 | 100% |  | Final | 100% | 5475
4 | BDRIDP/BAR/MUL/CCA-Rd/02 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District. | 506695127 |  | 0.585 |  |  |  |  | 2763145 |  | 2347546 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 2217470 | 100% |  | Final | 100% | 130076
5 | BDRIDP/BAR/MUL/CCA-St/02 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m. | 506694001 | [5 empty] | 12 | 2543802 |  | 1762404.98 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 1761528 | 99.95% |  | Final | 100% | 876.98
6 | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m | 506694060 | [5 empty] | 16 | 5115590 |  | 3683201.71 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 3680151 | 99.92% |  | Final | 60% | -1470229.974
7 | BDRIDP/BAR/MUL/CCA-Rd(R)/04 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m. | 506694001 |  | 2.175 |  |  |  |  | 8969284 | 1518637 | 7104572.13 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 100% | 6981682 | 100% |  | Final | 80% | -1298024.296
8 | BDRIDP/BAR/MUL/CCA-Rd/05 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m. | 506694060 |  | 1.575 |  |  |  |  | 5450114 |  | 4824539 | M/S Topu Enterprise | 2015-11-05 | 18/05/15 | 18/10/16 |  | 100% | 4773001 | 100% |  | Final | 80% | -913369.8
9 | BDRIDP/BAR/MUL/CCA-Rd/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m. | 506694063 |  | 1.25 |  |  |  |  | 3310397 |  | 2947338.02 | Md Sirazul Islam Hanif | 18/05/15 | 25/05/15 | 25/05/16 |  | 100% | 2910009 | 100% |  | Final | 100% | 37329.02
10 | BDRIDP/BAR/MUL/CCA-St/01 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m | 506694063 | [5 empty] | 2 | 505514 |  | 368648.25 | M/S Sraboni Enterprise | 21/06/15 | 28/06/15 | 27/12/15 |  | 100% | 368633 | 100% |  | Final | 100% | 15.25
11 | BDRIDP/BAR/MUL/CCA-Rd/06 | Improvement of road from Char Kalekhan Goni Bari-Khalil Bepari Bari road by BC from Ch. 0.00m-1550m. | 56695075 |  | 1.55 |  |  |  |  | 8933193 |  | 7059418.41 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 100% | 7059417 | 100% |  | Final | 70% | -806181.9
12 | BDRIDP/BAR/MUL/CCA-St/04 | Construction of 1 vent 4.00m×4.00m and 1 vent 1.00m×1.00m RCC Box Culvert on Char Kalekhan Goni Bari-Khalil Bepari Bari road at Ch.182m & 330m. | 56695075 | [5 empty] | 5 | 1937445 |  | 1462533.11 | Md. Khair Hossain | 2015-08-10 | 15/10/15 | 15/04/16 |  | 100% | 1455972 | 99.55% |  | Final | 50% | -487249.5
13 | BDRIDP/BAR/MUL/CCA-St/05 | Construction of 12.00m RCC Slab Bridge on Char Pakkia GPS at Ch.0+000km over Char Pakkia Khal. | 506694043 | [5 empty] | 12 | 10068184 | 10068184 | 7727638.21 | M/S Shafi Enterprise | 2017-06-02 | 13/02/17 | 13/12/17 |  | 100% | 7624583 | 100% |  | Final
14 | BDRIDP/BAR/MUL/UN-St/02 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District. | 506693005 | [5 empty] | 20 | 14312698.5 |  | 12881428.65 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 100% | 11600000 | 90.05%
15 | BDRIDP/BAR/MUL/UZ-St/03 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District. | 506692004 | [5 empty] | 20 | 17924056.31 |  | 16131650.67 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 100% | 15200000 | 94.22%
16 | BDRIDP/BAR/MUL/UN-St/01 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District. | 506693005 | [5 empty] | 21 | 15795569.51 |  | 14216012.55 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 95% | 12950000 | 91.09%
17 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. | 506692002 | [5 empty] | 45 | 24434851.86 |  | 21991136.67 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 80% | 13336746 | 60.65%
18 | BDRIDP/BAR/MUL/UZ-St/04 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal. | 506692004 | [5 empty] | 25 | 23503677 |  | 21153309.3 | Orien Trading & Builders | 2017-03-08 | 2017-10-08 | 2018-10-08 |  | 90% | 17800000 | 84.15%
19 | BDRIDP/BAR/MUL/UZ-St/05 | Construction of 30.00m PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at Ch.7620km over Banimardhan Khal under Muladi UpazilaDistrict-Barisal | 506692004 | [5 empty] | 30 | 21022197.08 |  | 18919977.37 | M/S Amir Engineering Corporation and M.M Builders & Engineers | 2018-04-02 | 2018-11-02 | 2018-11-12 |  | 95% | 14000000 | 74%
20 | BDRIDP/BAR/MUL/CCA-Rd/07 | Improvement of road from Muladi-Mirdar Hat GCCR Kazi Ali Ahmed Bari Grostan Alauddin Dewan Bari under Muladi UpazilaBarisal.a Bituminus Surfacing wearing courseDC 0.0m - 375mb 1 No.1.3m x 1.3m RCC Box Culvert at ch.170m | 506695137 |  | 0.375 |  |  |  | 1.3 | 2591153.77 |  | 2332038.39 | M/S Kohinoor Enterprise | 19/01/18 | 25/01/18 | 25/07/18 |  | 25% | 350000 | 15.01%
21 | BDRIDP/BAR/MUL/UZ-Rd/02 | a Improvement of Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road from Ch.2150m - 4415m under Muladi Upazila Barisal District.b Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch.2800m.c Construction of 1 Nos. 1vent 2.0m x 2.0m RCC box culvert on Mirdar Hat GC Bashtala Bazar - Poddar hat- dumuritala -Dhanu Shikder Hat GC Horinathpur Road at Ch. 3900m. | 506692002 |  | 2.265 |  |  |  | 4 | 17170059.9 |  | 15453053.91 | Orien Trading & Builders | 2018-03-05 | 2018-10-05 | 2019-10-05 |  | 40% |  | 0%
22 | BDRIDP/BAR/MUL/CCA-Rd/09 | Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000m under Muladi Upazila Barisal District.Salvaged Cost Tk 591644.00Improvement of road from Talukder HatKhejurtala Ali Sikder bari by BC Start Pokhi Rostom fokir bari to Nomor hat via Sumsun Nahar Chowdhury Bari at Ch.0.0m -1000mID No.506694016 under Muladi Upazila Barisal District. | 506694016 |  | 1 |  |  |  |  | 5885104.61 |  | 5296594.14 | Orien Trading & Builders | 2018-03-05 | 2018-10-05 | 2019-10-02 |  | 60% |  | 0%
23 | BDRIDP/BAR/MUL/CCA-Rd/08 | Improvement of road from Batamara Paderhat Launch Ghat -Salimpur Bazar via Batamara Regd.Primary School via Aminul Haque Kabir Bari by BC at ch.200m - 1252m under Muladi Upazila Barisal. | 506695001 |  | 1.05 |  |  |  |  | 6000000 |  | 5400000 | Md. Mahafuz Khan | 2018-03-05 | 2018-10-05 | 2018-10-02 |  | 15% |  | 0%
24 | BDRIDP/BAR/MUL/CCA-Rd/10 | Improvement of road from Balarmpur Bazar-Dumurtala GPS-Char Dumuritala Bissas Bari Mosque UNRG by BC at Ch. 0.000km-1.000km. under muladi upazila Barisal District | 506694094 |  | 1 |  |  |  |  | 5702035.96 |  | 5416934.16 | M/S Ferdousi Construction | 2018-05-06 | 2018-12-06 | 2019-12-03 |  | 10% |  | 0%
25 | BDRIDP/BAR/MUL/CCA-Rd/11 | Improvement of road from Muladi-Bara Patarchar Ferry Ghat M by BC at Ch. 3.500km-4.065km. ID No.506694017 under muladi upazila Barisal District |  |  | 0.565 |  |  |  |  | 3338552.94 |  | 3171625.29 | M/S AK Buidlers | 2018-09-06 | 14/06/18 | 14/11/18 |  | 10% |  | 0%
26 | BDRIDP/BAR/MUL/CCA-Rd/12 | Improvement of road from Haraz Sikder Bari to Laxmipur Nutun hat via Rashid Dhali Bari by BC at Ch. 0.900km-2.400km under muladi upazila Barisal District.Salvaged cost Tk.888105.00 | 506695010 |  | 1.5 |  |  |  |  | 9147339.59 |  | 8689972.61 | M/S R.S Construction | 31/05/18 | 2018-07-06 | 2018-07-12 |  | 15% |  | 0%
27 | BDRIDP/ BAR/MUL/Ghat/01 | Construction of RCC Ghat at Muladi Bandar under Muladi UpazilaBarishal District. | [7 empty] | 3822927.39 | [11 empty] | E-Tender Under Process.
27 |  | Sub Total: |  | 0 | 19.34 | 0 | 0 | 0 | 233.3 | 256624196.42 | 11586821 | 223403709.14 | [6 empty] | 157039241 |  | 0 |  |  | -3421240.21
1 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m. | 506692004 | 2490.25 | [5 empty] | 334778 |  | 334778 | Khorshed Khan LCS No-1 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 327963 | 100% |  | Final
2 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m. | 506692004 | 3042.25 | [5 empty] | 403489 |  | 403489 | Md. Alamgir Hossain LCS No-2 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 396479 | 100% |  | Final
3 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m. | 506692004 | 2886.92 | [5 empty] | 386512 |  | 386512 | Md. Baschu Sharder LCS No-3 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 384690 | 100% |  | Final
4 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m. | 506692004 | 2770 | [5 empty] | 371303 |  | 371303 | Abdus Salam Sharder LCS No-4 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 364872 | 100% |  | Final
5 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m. | 506692004 | 2775.75 | [5 empty] | 372013 |  | 372013 | Md. Bakiullah Sharder LCS No-5 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 367905 | 100% |  | Final
6 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m. | 506692004 | 2798.21 | [5 empty] | 374943 |  | 374943 | Md. Shalim LCS No-6 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 373728 | 99.68% |  | Final
7 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m. | 506692004 | 2793.69 | [5 empty] | 374353 |  | 374353 | Sukkur Ahmed Khan LCS No-7 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 370690 | 99.02%
8 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m. | 506692004 | 0.3 | [5 empty] | 396858 | 396858 | 396858 | Nazma LCS No-8 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 387880 | 97.74%
9 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m. | 506692004 | 2969.75 | [5 empty] | 397315 |  | 397315 | Most. Jasmin Akter LCS No-9 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 390259 | 98.22%
10 | LCS | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m. | 506692004 | 3207.06 | [5 empty] | 428100 |  | 428100 | Rashida LCS No-10 | 18/05/14 | 22/05/14 | 22/10/14 |  | 100% | 417470 | 97.52%
11 | BDRIDP/BAR/MUL/CCA-EW/01 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District. | 506695135 | 2052.81 | [5 empty] | 221909 |  | 221909 | Md Fazlu Tafader LCS No-1 | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 221206 | 100% |  | Final
12 | BDRIDP/BAR/MUL/CCA-EW/02 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District. | 506695127 | 2219.05 | [5 empty] | 239879 |  | 239879 | Md Kabir Hossain LCS No-1 | 17/11/14 | 18/11/14 | 18/02/15 |  | 100% | 239119 | 100% |  | Final
13 | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. | 506694063 | 2210.3 | [5 empty] | 323312 |  | 323312 | Fokrul Ahosan LCS No-1 | 31/05/15 | 31/05/15 | 30/09/15 |  | 50% | 179569 | 55.54%
14 | BDRIDP/BAR/MUL/CCA-EW/04 | Resectioning of road from Char Kalekhan Goni Bari-khalil Bepari bari road by Earth work from Ch. 0.00m-1550m. | 56695075 | 2237.625 | [5 empty] | 101268 | 101268 | 101268 | Md. Mojibor Rohman LCS No-1 | 28/07/15 | 30/08/15 | 30/12/15 |  | 100% | 97476 | 100% |  | Final
15 | BDRIDP/BAR/UZP/UN-EW/01 | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 2150m-2750m. | 506692002 | [6 empty] | 249672 | 249672 | 249672 | LCS No-1 |  |  |  |  | 100% | 242558 | 97.15% |  | Final
16 |  | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 2750m-3350m | [7 empty] | 284170 | 284170 | 284170 | LCS No-2 |  |  |  |  | 100% | 284170 | 100% |  | Final
17 |  | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 3350m-3950m | [7 empty] | 319301 | 319301 | 319301 | LCS No-3 |  |  |  |  | 40% | 121900 | 38.18%
18 |  | Resectioning of Mirdar Hat GC (Bashtala Bazar)-Poddar hat-Dumuritala-Dhanu Shikder Hat GC (Horinatpur) at Ch. 3950m-4412m | [7 empty] | 163854 | 163854 | 163854 | LCS No-4 |  |  |  |  | 100% | 160642 | 98.04% |  | Final
18 |  | Sub Total: |  | 34453.965 | 0 | 0 | 0 | 0 | 0 | 5743029 | 498126 | 5743029 | [6 empty] | 5328576 |  | 0 |  |  | 0
45 |  | Grand Total: |  | 34453.965 | 19.34 | 0 | 0 | 0 | 233.3 | 262367225.42 | 12084947 | 229146738.14 | [6 empty] | 162367817 |  |  |  |  | -3421240.21
Upazila: Bakergonj
1 | BDRIDP/BAR/BAK/CCA-Rd/01 | Improvement of road from South side Dhola Sluice Gate to Alim Meridha Bari (Vary) via Sikder Bari, Manik Member Bari, Shatghor & Mannan Princhpal Bari (East side of Hanua Bridge to Shatghor via Shikder Bari) By HBB from Ch. 0.00-1013m. | 506075221 |  |  | 1.013 |  |  |  | 3558576 |  | 3985608.82 | M/S Nahid Enterprise | 17/07/14 | 24/07/14 | 24/01/15 |  | 100% | 3976779 | 99.78% |  | Final | 100% | 8829.82
2 | BDRIDP/BAR/BAK/UN-St/01 | Construction of RCC Box Culvert over road from Kaloskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS with 7 Nos. 1.60mx1.60m at Ch. 850m, 1110m, 1456m, 1608m, 2507m, 3520m, 4245m & 2 Nos. 2vent 4.00mx4.00m at Ch. 1242m & 2606m. e-ID : 22665 | 506073023 | [5 empty] | 27.2 | 7339681 |  | 5345279.54 | M/S Khondokear Brothers | 14/06/15 | 21/06/15 | 20/06/16 |  | 100% | 5098903 | 100% |  | Final
3 | BDRIDP/BAR/BAK/UN-Rd(R)/01 | Rehabilitation of Road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 00-1000m. (Salvage Cost Tk. 9,46,801.00) e-ID : 22666 | 506073023 |  | 1 |  |  |  |  | 4566907 |  | 3523866.83 | M/S Khondokear Brothers | 21/07/15 | 28/07/15 | 27/04/16 |  | 75% | 1150000 | 32.63% |  | Prepared for Cancelled
4 | BDRIDP/BAR/BAK/UN-Rd(R)/02 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khayaghat via Kumarbari Bridge & Bagdia GPS road By BC from Ch. 1000m-4870m. e-ID : 22667 | 506073023 |  | 3.87 |  |  |  |  | 18093128 |  | 14682769.7 | M/S Khondokear Brothers | 14/06/15 | 2015-06-08 | 2016-06-05 |  | 100% | 14478871 | 100% |  | Final
5 | BDRIDP/BAR/BAK/CCA-Rd(R)/02 | Rehabilitation of road from Gavikola Mannan Sikder Bari Foot Bridge to West side of Nilganj Foot Bridge via Moksad Khan,Kumarghudi & Kaptain Saye Bari by BC from Ch.00-810m [Salvaged Value Tk.10,53,654.00] e-ID : 29366 | 506075079 |  | 0.81 |  |  |  |  | 3553958 |  | 2619513.44 | Md. Nasir Uddin | 2015-05-11 | 2015-12-11 | 2016-11-05 |  | 100% | 2549020 | 100% |  | Final
6 | BDRIDP/BAR/BAK/CCA-Rd/03 | Improvement of Dudhalmou Ferryghat(RHD) to Kanki Govt.Pry.School Road by Earth Work and HBB under Bakergonj Upazila, District -Barisal. | 506074120 | [6 empty] | 17641663 |  | 16139041.07 | Md. Sumsudhoa Mollick | 21/12/16 | 28/12/16 | 27/06/17 |  | 100% | 13912533 | 100% |  | Final
7 | BDRIDP/BAR/BAK/UN-Rd/03 | Improvement of road from Faridpur Hat Kheya Ghat Durgapasa UP office Gobindapur Bothtala via Kakordha Bazar Road, a Earth Work from Ch. 4860m 7320m.b Bituminus Carpeting from Ch. 4860m 7470m.c Construction of 1 No. 1.60mx1.60m RCC Box Culvert at Ch. 7435m. under Bakergonj upazila Barisal District. Salvage Cost Tk. 3733841.00 | 506073020 |  | 2.46 | 2.61 |  |  | 1.6 | 16459779.83 |  | 14813801.84 | Md Mafuz Khan | 2018-04-01 |  | 30/11/18 |  | 100% | 14808294 | 99.96% |  | Final
8 | BDRIDP/BAR/BAK/CCA-Rd/04 | Improvement of road from west Faridpur Ajgor Sikder Bari to DC road Ferry-ghat via H/O Rahim Mrida Road, a Earth Work from Ch. 0.0 - 1300.00m. b Bituminus Carpeting from Ch. 0.0 - 1300m c Construction of 1 No. 4.0m x 4.0m RCC Box Culvert at Ch. 425m. under Bakergonj upazila Barisal District. | 506074151 |  | 1.3 | 1.3 |  |  | 4 | 9994097.44 |  | 8994687.7 | M/S Islam Brothers | 2018-02-01 | 2018-09-01 | 2018-09-10 |  | 100% | 7800000 | 86.72%
9 | BDRIDP/BAR/BAK/CCA-Rd/06 | Improvement of road from Shashi Bazar Bridge-Telani Lunch Ghat Najrul Talukder Bari. under Bakergonj Upazila Dist:Barisal. a) HBB from Ch. 00m-1000m b) Protection Work 108m c) Earth work from Ch. 00m-1000m | 506074100 |  |  | 1 |  |  |  | 4609416.97 |  | 4563267.91 | Md. Zakir Hossain Mia | 17/01/18 | 24/01/18 | 24/07/18 |  | 100% | 4548499 | 99.68%
10 | BDRIDP/BAR/BAK/CCA-Rd(R)/05 | Improvement of road from ATIMKHANA to Bothra Road via Mr. Matiur Rahman (ASP) at Ch. 0.00m-500.00m (Efective Length= 475.00m) (ID No.506074225) under Bakergonj Upazila, Dist : Barisal [Salvaged cost : Tk1049647.00] |  |  | 0.5 |  |  |  |  | 3304868 |  | 2974381.2 | M/S Osin Enterprise | 17/01/18 | 24/01/18 | 24/05/18 |  | 100% | 800000 | 26.9%
11 | BDRIDP/BAR/BAK/CCA-Rd/07 | Improvement of road from Sampur Ray Barir Culvert to Birangal Digirpar Kader Hohlade Bari via Karim Gaji Bari a Earth work 0.0 - 1500m b Bituminous Surfacing - wearing course DC 0.0m - 1500m c 1.5 m x 1.5m RCC Box Culvert at Ch.900m | 506075125 |  | 1.5 |  |  |  | 1.5 | 9125908.56 |  | 8213317.7 | M/S Abul Kalam Azad | 22/01/18 | 29/01/18 | 29/10/18 |  | 60% | 1500000 | 18.26%
12 | BDRIDP/BAR/BAK/CCA-Rd/08 | Improvement of Extended Portion of Dudhalmou Ferryghat (RHD) to Kanki Govt. Pry. School Road (Connecting Road Sheikh Hasina Cantonment). | 506074120 | [6 empty] | 4332834.63 |  | 2878392 | M/S Amir Engineering Corporation | 18/01/18 | 20/01/18 | 15/02/18 |  | 100% | 2878392 | 100% |  | Final
13 | BDRIDP/BAR/BAK/CCA-Rd/09 | Improvement of Aulia DargabariRHD to Shyampur Hat via Dhokati Madrasha & Dhokati Govt.Pry.school Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini to Syampur Hat via Ali Khan Bari a Earth work at Ch.4500-6000m b Carpeting BC at Ch.4500 - 6000m c Construction of 1No. Box culvert1.06m x 1.06m at Ch.85m & 3 nos U-Drain 900mm x 900mm at Ch.4620m4800m & 5135m on the same road d Protective worksSite Facilities& Road Safety works under Bakergonj Upazila Barishal District. Salvaged cost Tk 854269.00 | 506074119 |  | 1.5 |  |  |  | 3.76 | 14791503 |  | 13742664.31 | Md. Nasir Uddin | 26/08/18 | 2018-02-09 | 2019-02-08 |  | 100% | 2800000 | 20.37%
14 | BDRIDP/BAR/BAK/UZ-Rd/01 | Improvement of Rahamgonj RHD via Dhokati GPS & Bakergonj-Sampur Road to BoaliaGC Bakergonj-Sampur Road Mill Ghar to Auliapur Dargabari RHD-Sampur Road Howlader Bari Trimohini a Earth work at Ch.1913-2775mb CarpetingBC at Ch.1913-2775mc Construction of 1No. Box culvert1.06m x 1.06m at Ch.2549m on the same roadd Protective worksSite Facilities& Road Safety works under Bakergonj UpazilaBarishal District.Salvaged cost Tk 921239.00 | 506072014 |  | 0.862 |  |  |  | 1.06 | 8583037 |  | 7995234.286 | M/s Kazi Holdings | 27/08/18 | 2018-04-09 | 2019-04-06 |  | 90% |  | 0%
15 | BDRIDP/BAR/BAK/Gha/01 | Construction of Ghatla at Kaligonj Bazar Khal under Bakergonj Upazila Barisal . | [7 empty] | 1933397.79 |  | 1885106.37 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 40% |  | 0%
16 | BDRIDP/BAR/BAK/UZ-St/01 | Construction of 23.00m Long RCC Girder Bridge over road from Kamarkali GC to Baharchar GC via Sarsi Pollice Farry Patkati L/G Faridpur UP Office & Janota Bajarat at Ch. 5847m Under Bakerganj Upazila District Barisal Road ID 506072012 | [6 empty] | 23 | 13048406.72 |  | 12395986.384 | M/S SUN TRADERS | 23/08/18 | 30/08/18 | 2019-04-08 |  | 80% | 6700000 | 54.05%
17 | BDRIDP/BAR/BAK/CCA-RdR/10 | Improvement of Road from Hanua UP Office Bridge to Sarder Bari Foot Bridge via Jainpuri Khanka Sarif Bari & Khodaboxkati Eshak Member Bari Char a Earth work at Ch.0.0 - 2000m b CarpettingBC Ch.0.0 -2000m c Construction of 1 No Box culvert 1.0m x 1.0m at ch.1310m d Protective worksPalisading 60m under Bakergonj UpazilaBarishal District. Salvaged Cost TK.1943192.00 | 506074199 |  | 2 |  |  |  | 1 | 14520624.67 |  | 13794593.43 | M/S Sikder Enterprise | 19/02/19 | 26/02/19 | 19/08/19 |  | 15% |  | 0%
18 | BDRIDP/BAR/BAK/CCA-Rd/11 | Improvement of Road from Goma Amtala to Chatra Hat via Gajir Hat DKP High School & Sowdakar Bari Road by BC at Ch. 1600m-2100. Effective Length 500m.Under Bakerganj Upazila District- Barishal. | 506074136 |  | 0.5 |  |  |  |  | 3243472.3 | [11 empty] | E-Tender Under Process.
19 | BDRIDP/BAR/BAK/CCA-Rd/12 | Improvement of road from Kabiraj Altaf Chairman Bari near Madrasha to East Dhudal Community Pry School via Shahajahan Howlader & Alomgir Mollik Bari road by BC Ch. 736m-2000m. Under Bakerganj Upazila District- Barishal. | 506074148 |  | 1.264 |  |  |  |  | 8566686.78 | [11 empty] | E-Tender Under Process.
20 | BDRIDP/BAR/BAK/CCA-Rd/13 | Improvement of Road from Kabai Dhola Riazuddin Madrasha to Khodaboxkati Govt. Pry. School by BC work at Ch.00m-500 with 1 No. 900mx900m U-Drain. Under Bakerganj Upazila District- Barishal. | 506075432 |  | 0.5 |  |  |  | 0.9 | 3857006.71 | [11 empty] | E-Tender Under Process.
21 | BDRIDP/BAR/BAK/CCA-Rd/14 | A Improvement of road from Rabipur Ali Hossain Khan Bari UZR to Sharif Bari via Ayeb Boyati Bari i Earthwork Ch.0.0m-500m ii CarpetingDC Ch.0.0 - 500m.iii Palisading work-50m B Improvement of road from S/Side of Kabai HatNear Chunakhali Sluice Get to E/S of Pearpur Iron BridgeUZR via Chunakhali HatDhola Madrasa & Dhola Sluice Get i Earthwork Ch.4000m-5000m ii Carpeting DC Ch.4000m-5000m iii Construction of 2Nos 1.0m x 1.0m Box Culvert at Ch.4666m 4951m & 1No. U-Drain at Ch.4830m iv Palisading work-55m Under Bakergonj Upazila Barishal District | 506075099 506074155 |  | 1.5 |  |  |  | 2.625 | 11940345.81 | [11 empty] | E-Tender Under Process.
22 | BDRIDP/BAR/BAK/CCA-Rd/15 | Improvement of road East Bathsala UZR to Dhulia River Bank via Bathsala Karikornagar GPS infront of Amir Khan Bari Mosque Salvaged Cost Tk 331586.00 i Earthwark Ch.0.00m-1450m. ii Carpeting DC Ch.0.00m-1450m. iii Construction of 01 No U-Drain 0.9mx0.9m at Ch.1250m.iv Palasading 79m. Under Bakergonj Upazila Barishal District. | 506075379 |  | 1.45 |  |  |  | 0.9 | 10466500 | [11 empty] | E-Tender Under Process.
23 | BDRIDP/BAR/BAK/CCA-Rd/16 | Part A Improvement of road from H/O Sujauddin Halta F.H. high School. Halta Mouza Sholoshath to Surath Memorial GPS. i Earthwark Ch.0.00m-850m. ii Carpeting DC Ch.0.00m-850m. iii Construction of 02 Nos RCC Culvert1.6mx1.6m at Ch 4m845m 3 Nos U-Drain 0.9mx0.9m at Ch.120m190m235m.iv Palsading 96mPart B Improvement of road from Mokimabad Bajar S/Side of Culvert to East Side of BIP Siuce Get via Dilip Master Bari.Oza Bari to Thakur Bari via Naboraz Biswas bari i Earthwark Ch.2500m-3250m. ii Carpeting DC Ch. 2500m-3250m. iii Construction of 01 No RCC Culvert 1.6mx1.6m at Ch 3125m.iv Palsading 38m.Under Bakergonj Upazila District Barishal. | 506075180 506075229 |  | 1.575 |  |  |  | 7.5 | 14776000 | [11 empty] | E-Tender Under Process.
24 | BDRIDP/BAR/BAK/CCA-Rd/17 | Part A Improvement of road from Padrishibpur GPSUZR to Bismillah Bazar via Sikder Bari Kowabunia khal & Dhulal sadu Bari Salvaged Cost Tk 921459.76i Earthwark Ch.0.0m-900m. ii Carpeting DC Ch. 0.0 - 900m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert & 1No.U-Drain at Ch 482m.& 28m iv Palsading 59m.Under Bakergonj Upazila District Barishal. Part B Improvement of road from East side of Bangla bazar Box Culvert to Wapder Khal Ghorar Bridge Bothra via Biharipur Madrasha road. i Earthwark Ch.3250m-3850m. ii Carpeting DC Ch.3250m-3850m. iii Construction of 01 No 2.0 m x 2.0m RCC Box Culvert at Ch.3255m & 01 No 1.6 m x 1.6m RCC Box Culvert at Ch.3716m iv Palsading 28m.Under Bakergonj Upazila District Barishal.Part C Improvement of road from Padrishibpur Sunddartala Baily Bridge UZR to Aowal Sikderbari i Earthwark Ch.0.0m-500m. ii Carpeting DC Ch. 0.0 - 500m. Under Bakergonj Upazila District Barishal. | 506074057 506074182 506075155 |  | 2 |  |  |  | 6.225 | 16443000 | [11 empty] | E-Tender Under Process.
25 | BDRIDP/ BAR/BAK/ CCA-Rd/18 | Improvement of Road UZR Rabipur GPS UNR Younous Sharif Bari Via Rabipur. Salvaged Cost Tk 641271.00i Earthwark Ch.0.00m-500m. ii Carpeting DC Ch.0.00m-500m. iii Palsading 50m. Under Bakergonj Upazila Barishal District. | 506074267 |  | 0.5 |  |  |  |  | 3691293.53 | [11 empty] | E-Tender Under Process.
25 |  |  |  | 0 | 25.091 | 5.923 | 0 | 0 | 81.27 | 228442092.74 | 0 | 138547512.53 | [6 empty] | 83001291 |  | 0 |  |  | 8829.82
1 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 0.00m-1000m | 506073023 | [6 empty] | 131861 |  | 131861 | Anwar Hossain LCS No-01 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 118814 | 90.11%
2 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1000m-1400m. | 506073023 | [6 empty] | 256728 |  | 256728 | Md. Babul Howlader LCS No-02 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 226287 | 88.14%
3 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1400m-1900m | 506073023 | [6 empty] | 230734 |  | 230734 | Md. Joynal Abadin LCS No-03 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 203474 | 88.19%
4 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 1900m-2300m | 506073023 | [6 empty] | 224792 |  | 224792 | Md. Royon Mollah LCS No-04 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 198427 | 88.27%
5 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2300m-2800m | 506073023 | [6 empty] | 233429 |  | 233429 | Md. Shahidul Sharif LCS No-05 | 15/04/15 | 16/04/15 | 16/05/15 |  | 95% | 220264 | 94.36%
6 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 2800m-3300m | 506073023 | [6 empty] | 205799 |  | 205799 | H M Shamsul Huda LCS No-06 | 15/04/15 | 16/04/15 | 16/05/15 |  | 95% | 191913 | 93.25%
7 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3300m-3700m | 506073023 | [6 empty] | 243498 |  | 243498 | Md. Hanif LCS No-07 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 238747 | 98.05%
8 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 3700m-4200m | 506073023 | [6 empty] | 230149 |  | 230149 | Md. Amir Ali Khan LCS No-08 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 203332 | 88.35%
9 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4200m-4500m | 506073023 | [6 empty] | 249498 |  | 249498 | Md. Monir Hossain LCS No-09 | 15/04/15 | 16/04/15 | 16/05/15 |  | 90% | 211006 | 84.57%
10 | BDRIDP/BAR/BAK/UN-EW/01 | Improvement of road from Kalaskati UP Office (Vumi Office) to Arshed Khaya Ghat via Kumarbari Bridge & Bagdia Govt. Pry. Schoo. Road by Earth Filling Work at Ch. 4500m-4870m | 506073023 | [6 empty] | 222257 |  | 222257 | Md. Shalim Mridha LCS No-10 | 15/04/15 | 16/04/15 | 16/05/15 |  | 100% | 196192 | 88.27%
10 |  | Sub Total: |  | 0 | 0 | 0 | 0 | 0 | 0 | 2228745 | 0 | 2228745 | [6 empty] | 2008456 |  | 0 |  |  | 0
35 |  | Grand Total: |  | 0 | 25.091 | 5.923 | 0 | 0 | 81.27 | 230670837.74 | 0 | 140776257.53 | [6 empty] | 85009747 |  |  |  |  | 8829.82
Upazila: Gournodi
1 | BDRIDP/BAR/GOR/CCA-Rd/02 | Improvement of road from Gournadi Highway Thana Connecting road under Gournadi Upazila. | 506325047 | [6 empty] | 1544297 |  | 1612193 | M/S Tamim Enterprise | 14/06/15 | 21/06/15 | 20/11/15 |  | 100% | 1612193 | 100% |  | Final | 50% | -806096.5
2 | BDRIDP/BAR /GOU/UN-Rd/01 | (a) Improvement of Road from Sarikal GC to Shaheber char Bazar via Nalchira Bazar ch. 5555m-7055m), (b) Construction of 2 nos U-drain at ch.599m & 6555m on the same road Under Gournadi Upazila, District-Barisal. | 506323013 |  | 1.5 |  |  |  | 1.8 | 9785485 |  | 10357650.8 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 10353584 | 99.96% |  | Final | 60% | -4138993.52
3 | BDRIDP/BAR /GOU/UZ-Rd/01 | (a) Improvement of Road from Gournadi Bandar GC to Muladi GC via Kutubpur Bazar at ch. 0m-630m), (b) Construction of 2 nos U-drain at ch. 205m & 364m on the same road Under Gournadi Upazila, District-Barisal. | 506322016 |  | 0.63 |  |  |  | 1.8 | 5122695 |  | 5399315 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 5356652 | 100% |  | Final | 60% | -2117063
4 | BDRIDP/BAR /GOU/UZ-Rd/02 | Improvement of illah (NHW) to Kalkini Upazila HQ via Tulatala Bazar at ch.2413m-3213m), Under Gournadi Upazila, District-Barisal. | 506322013 |  | 0.8 |  |  |  |  | 4643337 |  | 4898705 | M/S Sadman Builders | 2014-09-11 | 16/11/14 | 15/05/15 |  | 100% | 4667277 | 95.28% |  | Final | 40% | -2707795
5 | BDRIDP/BAR /GOU/UN-Rd/02 | (a) Improvement of Batazore GC to Pinglakathi Bazar via Pachim Chandrahar GPS at ch. 0m-1000m), (b)Construction of 1 nos U-drain at at ch.14m on the same road, (c) Construction 1v-2.3mx2.30m RCC Box Culvert at ch.527m & 1583m on the same road Under Gournadi Upazila, District-Barisal. | 506323001 |  | 1 |  |  |  | 2.2 | 7805159 |  | 8236744 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 100% | 8218516 | 99.78% |  | Final | 50% | -4100144
6 | BDRIDP/BAR/GOR/CCA-Rd/01 | Improvement of road from Maddam Hosnabad Nabarun RPS to Nezamuddin College by HBB at Ch.481-1492m (Nizamuddin Degree College road from freedom fighter Nizamuddin Shaheber Kaborstan via Madha hosnabad UP Member Md.Matiur Rahman Sarif Bari Bridge under Gouranadi upazila, Barisal District. | 506324040 |  |  | 1.011 |  |  |  | 2839204 |  | 2601109.88 | Md. Sirazul Islam Hanif | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 2583729 | 100% |  | Final | 100% | 17380.88
7 | BDRIDP/BAR/GOR/UZ-Rd/03 | Improvement of Barthi Bazar (NHW) to Gournadi GC via Torky GC at ch.2150 - 4150m. | 506322005 |  | 2 |  |  |  |  | 13145679 |  | 13801595 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 100% | 13799645 | 99.99% |  | Final
8 | BDRIDP/BAR/GOR/UN-Rd/03 | Rehabilitation of road from Mahilara UP Office to Chadshi Hat via Bilogram Bazar (A. Rob Chokder House to Chadshi Hat road) road By BC from Ch. 5370-6900m. | 506323019 |  | 1.53 |  |  |  |  | 5834483 |  | 6124969 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 100% | 6121962 | 99.95% |  | Final
9 | BDRIDP/BAR/GOR/UN-Rd(R)/04 | Rehabilitation of road from Mahilara UP office to Chadshi hat via Billogram Bazar road from Ch. 3740-4850m (Salvage Material Cost Tk. 11,01,418.00) | 506323019 |  | 1.11 |  |  |  |  | 5359476 |  | 5623536 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/04/16 |  | 100% | 5623536 | 100%
10 | BDRIDP/BAR/GOR/UN-St/01 | Construction of 2-Vent 4.30mx4.30m RCC Box Culvert on Mahilara UP office to Chadshi hat via Billogram Bazar road at Ch. 4200m. | 506323019 | [5 empty] | 8.6 | 1970942 |  | 2069109 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/12/15 |  | 100% | 2036343 | 100% |  | Final
11 | BDRIDP/BAR/GOR/CCA-St/01 | Construction of 3 Nos Single Vent 4.30mx4.30m RCC Box Culvert & 2 nos U-Drain on Battala Kapali bari Bridge (NHW) to Khanjapur High School road at ch. 95m,270m,1276m564m&970m Under Gournadi Upazila, District-Barisal e-ID : 22284 | 506324136 | [5 empty] | 14.9 | 6680560 |  | 6946789.2 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 100% | 6943287 | 99.95% |  | Final
12 | BDRIDP/BAR/GOR/CCA-Rd/03 | Improvement of road from Battala Kapali bari Bridge (NHW) to Khanjapur High School road by BC from Ch.00 - 1656m Under Gournadi Upazila, District-Barisal e-ID : 22285 | 506324136 |  | 1.656 |  |  |  |  | 7060824 |  | 7343257.29 | M/S Siam Enterprise | 2015-01-07 | 2015-08-07 | 2016-08-04 |  | 100% | 7343257 | 100% |  | Final
13 | BDRIDP/BAR/GOR/UZ-Rd/04 | Improvement of Barthi Bazar (NHW) to Burghata bus Stand (NHW) via Amanagong hat at Ch. 450-2450m. e-ID : 19611 | 506322017 |  | 2 |  |  |  |  | 12874579 |  | 13172831.8 | M/S Howlader Constructure | 2015-07-07 | 2015-08-07 | 2016-06-07 |  | 100% | 13168763 | 99.97% |  | Final
14 | BDRIDP/BAR/GOR/UZ-ST/01 | Construction of 30.00m PSC Girder Bridge on Barti Bazar to Gournadi GC at Ch.5000km over Anandhapur Khal under Gournadi UpazilaDistrict-Barisal | 506322005 | [5 empty] | 30 | 24934266.46 |  | 27173350.5 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 75% | 20600000 | 75.81%
15 | BDRIDP/BAR/GOR/UZ-ST/02 | Construction of 32.00m PSC Girder Bridge on Barti BazarNHW to Gournadi GC via Torky GC at Ch.9340km over Kashba Khal under Gournadi Upazila District-Barisal | 506322005 | [5 empty] | 32 | 24196878.89 |  | 26369588.63 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 60% | 15400000 | 58.4%
16 | BDRIDP/BAR/GOR/UZ-RdR/05 | Periodic Maintenance of Batazore-Agarpur-Sarikal via Hosnabad Nalchira-Miarchar road. a Earthwark from Ch. 8725- 17177m.b Carpeting DC 17361.14 sqm.c 12mm SC-13906.56 sqm. Under Gournadi Upazila District - Barishal. | 506322002 |  | 8.45 |  |  |  |  | 16020946.84 | [11 empty] | E-Tender Under Process.
17 | BDRIDP/BAR/GOR/UZ-RdR/06 | Periodic Maintenance of iIlah Bas stand NHW to Agailjhara H/Q via Bakai & Rajihar Bazar in/c Nutun Bazar Connecting road.a Earthwark from Ch. 0- 3832m.b Carpeting DC 3224.409 sqm.c 12mm SC-11191.1 sqm. Under Gournadi Upazila District - Barishal. | 506322006 |  | 3.832 |  |  |  |  | 5915176.68 | [11 empty] | E-Tender Under Process.
18 | BDRIDP/BAR/GOR/UZ-RdR/07 | Periodic Maintenance of Batazore GCNHW to Dhamura GC via Solak Bazar road.a Earthwark from Ch. 0- 2145m.b Carpeting 40mm-DC 6403.2 sqm.c Palisading Work297.00m. Under Gournadi Upazila District - Barishal. | 506322011 |  | 2.145 |  |  |  |  | 8824294.58 | [11 empty] | E-Tender Under Process.
19 | BDRIDP/BAR/GOR/UN-RdR/05 | Periodic Maintenance of Chadshi UP Office-Goila UP Office Road.a Earthwark from Ch. 0- 830m.b Carpeting DC 322.5 sqm.c 12mm SC-2208.35 sqm. Under Gournadi Upazila District - Barishal. | 506323020 |  | 0.83 |  |  |  |  | 1001243.79 | [11 empty] | E-Tender Under Process.
19 |  |  |  | 0 | 27.483 | 1.011 | 0 | 0 | 91.3 | 165559527.24 | 0 | 141730744.1 | [6 empty] | 123828744 |  | 0 |  |  | -13852711.14
1 | BDRIDP/BAR/GOR/UN-EW/01 | Improvement of road from Mahilara UP Office to Chadshi hat via Billogram Bazar road By Earth Filling Work from Ch. 3740m-4850m. | 506323019 | 1756 | [5 empty] | 349519 |  | 349519 | Anjur Ali Sarder LCS No-1 | 2015-10-11 | 15/11/15 | 30/03/16 |  | 100% | 349399 | 99.97%
2 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Gournadi GC via Torky GC at Ch. 2150m-4150m by earth . | 506322005 | 1603.375 | [5 empty] | 223623 |  | 223623 | Md Shalim Khalifa LCS-1 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 223598 | 99.99%
3 |  |  |  | 501.125 | [5 empty] | 69892 |  | 69892 | Sunil Joydhar LCS-2 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 69822 | 99.9%
4 | BDRIDP/BAR/GOR/UZ-EW/01 | Resectioning of road from Brthi Bazar (NHW) to Burghata Bus Stand (NHW) via Amanothgonj hat at Ch. 450m-2450m by earth. | 506322017 | 2151.655 | [5 empty] | 300092 |  | 300092 | Md Mahabub Khan LCS-1 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 299749 | 99.89%
5 |  |  |  | 1505.375 | [5 empty] | 209955 |  | 209955 | Md Mohasin Sharder LCS-2 | 26/09/16 | 2016-10-10 | 2017-10-01 |  | 100% | 209849 | 99.95%
5 |  |  |  | 7517.53 | 0 | 0 | 0 | 0 | 0 | 1153081 | 0 | 1153081 | [6 empty] | 1152417 |  | 0 |  |  | 0
24 |  |  |  | 7517.53 | 27.483 | 1.011 | 0 | 0 | 91.3 | 166712608.24 | 0 | 142883825.1 | [6 empty] | 124981161 |  | 0 |  |  | -13852711.14
Upazila: Agailjhara
1 | BDRIDP/BAR /AGL/CCA-Rd/01 | Improvement of Road by BC from Rathkhola Bazar-Bhadrapara Road (ch. 0m-1000m) Under Agailjhara Upazila, District-Barisal. | 506024008 |  | 1 |  |  |  |  | 5097636 |  | 5599756.34 | M/S Talukder Enterprise | 23/10/14 | 30/10/14 | 30/04/15 |  | 100% | 5597543 | 99.96% |  | Final
2 | BDRIDP/BAR/AGL/CCA-Rd/02 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 5527014 |  | 4583839 | M/S Mitushi Traders | 27/11/14 | 2014-08-12 | 2015-04-06 |  | 100% |  | 0% |  | W/O Cancel
3 | BDRIDP/BAR/AGL/CCA-Rd(R)/06 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m. | 506025056 |  | 1 |  |  |  | 2.7 | 4914057 | 196459 | 5158284.22 | M/S Sharif Enterprise | 22/04/15 | 29/04/15 | 28/01/16 |  | 100% | 5157868 | 99.99% |  | Final | 50% | -2578725.89
4 | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent 4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. | 506025058 | [5 empty] | 8.9 | 1677674 |  | 1771918.99 | M/S Sharif Enterprise | 28/05/15 | 2015-04-06 | 2015-04-12 |  | 100% | 1693392 | 100% |  | Final
5 | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 506023001 |  | 2.76 |  |  |  |  | 14739342 | 791797 | 15592739.8 | M/S Sharif Enterprise | 25/05/15 | 2015-06-06 | 30/05/15 |  | 100% | 13800000 | 88.5% |  |  | 20% | -10681452.04
6 | BDRIDP/BAR/AGL/UZ-Rd/02 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by BC from Ch. 3800m-5800m. | 506022003 |  | 2 |  |  |  |  | 10771206 |  | 11288255.96 | M/S Sraboni Construction | 27/05/15 | 2015-04-06 | 2016-03-06 |  | 100% | 11286798 | 99.99% |  | Final | 60% | -4513844.424
7 | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m | 506024034 |  | 1.28 |  |  |  |  | 6017149 |  | 6375868.44 | M/S Sarniabad Enterprise | 25/05/15 | 2015-01-06 | 2015-01-12 |  | 100% | 6375048 | 99.99% |  | Final | 60% | -2549526.936
8 | BDRIDP/BAR/AGL/CCA-Rd/04 | Improvement of road from Poiser hat GC-Ramshil Bazar via Trimukhi road by BC from Ch. 0.00m-1000m. | 506024040 |  | 1 |  |  |  |  | 4926273 |  | 5538660.26 | M/S Shafique Brothers | 21/05/15 | 28/05/15 | 28/11/15 |  | 100% | 5554952 | 100.3% |  | Final | 70% | -1677889.818
9 | BDRIDP/BAR/AGL/CCA-Rd(R)/05 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m. | 506025058 |  |  | 1.2 |  |  |  | 4159274 | 288401 | 4400152.34 | M/S Helal Traders | 2015-02-07 | 2015-09-07 | 2016-09-01 |  | 100% | 3950000 | 89.77% |  |  | 30% | -2629954.298
10 | BDRIDP/BAR/AGL/UZ-Rd(R)/01 | Rehabilitation of Barthi - Valukshi - Magura- Ambari-Bakalhat road by BC at ch.5870-7880m. | 506022008 |  | 2.01 |  |  |  |  | 12746908 |  | 13383052 | M/S Santu Traders | 2015-08-07 | 15/07/15 | 14/07/16 |  | 100% | 13383025 | 100% |  | Final
11 | BDRIDP/BAR/AGL/CCA-Rd/07 | Improvement of road from Biplob Serniabad House to Hazi Musa House road By BC from ch.00-400m. | 506025084 |  | 0.4 |  |  |  |  | 1917053 |  | 2012714.3 | M/S Serniabad Enterprise | 2015-07-07 | 2015-08-07 | 2015-08-12 |  | 100% | 2012370 | 99.98% |  | Final
12 | BDRIDP/BAR/AGL/CCA-Rd/ 02 | Improvement of road from Seral - Goila road via Shahid Serniabad House - Tamer Jame Mosjid(Tamer Girls High School-Seral Community Center) by BC (Ch.0.0 - 975m) under Agailjhara Upazila,Barisal. | 506025048 |  | 0.975 |  |  |  |  | 7232587 | 7232587 | 7230073.2 | M/S Serniabad Traders | 2017-09-03 | 16/03/17 | 16/10/17 |  | 100% | 7153140 | 100% |  | Final
13 | BDRIDP/BAR/AGL/CCA-Rd/08 | Improvement of road from Hazi Mokbul Sardar House via Sardar Mohabubul Alom & Sardar Harun - Jainger Gomosta House road. at Ch.00 to 208m under Agailjhara Upazila Barisal. | 506025088 |  | 0.208 |  |  |  |  | 2168362.12 |  | 2276707.38 | M/S Sharif Enterprise | 15/03/18 | 22/03/18 | 22/09/18 |  | 100% | 1634000 | 71.77%
14 | BDRIDP/BAR/AGL/Gha/01 | Construction of Ghat at Paisarhat Paschim par under Agailjhara Upazila Barisal | [7 empty] | 2900067.47 |  | 2958070.38 | M/S Sharif Enterprise | 22/03/18 | 29/03/18 | 29/09/18 |  | 60% | 1700000 | 57.47%
15 | BDRIDP/BAR/AGL/UZ-RdR/03 | Maintenance of Barthi- Valiukshi-Magura Bakal Hat Roada Earthwark from Ch. 9860- 11860m.b Carpeting DC 21.3 sqm.c 12mm SC-5237.7 sqm. d Palisading Work 103.00m. Under Agailjhara Upazila District- Barishal. | 506022008 |  | 2 |  |  |  |  | 2265178.34 | [11 empty] | E-Tender Under Process.
16 | BDRIDP/BAR/AGL/ UZ-RdR/04 | Maintenance of Road From Nimtola RHD-Dhamura GC viaRatnapur UP Road at Ch 5265m-7383m Agailjhara Under Agailjhara Upazila District- Barishal. | 506022010 |  | 2.118 |  |  |  |  | 2649883 | [11 empty] | E-Tender Under Process.
17 | BDRIDP/BAR/AGL/UN-RdR/03 | Maintenance of Road From Goila UP Office to Billogram Bazar via Rajer Bari Road at Ch 00m-2000mm Agailjhara Under Agailjhara Upazila District- Barishal. | 506023008 |  | 2 |  |  |  |  | 2890888.53 | [11 empty] | E-Tender Under Process.
18 | BDRIDP/BAR/AGL/UN-RdR/02 | Maintenance of Road From Basail Hat Rajihar UP-Batra Bazar viiiia Basail Pachchim Para Bazar Road at Ch 00m-1000m Agailjhara Under Agailjhara Upazila District - Barishal. | 506023006 |  | 1 |  |  |  |  | 3511387.07 | [11 empty] | E-Tender Under Process.
19 | BDRIDP/ BAR/AGL/ CCA-Rd/09 | A Improvement of Temar Bastaila Nagar GPS-West Mollapara-Ohchiarmad Bazar. i Earthwark Ch.650m-1865m.ii Carpeting DC Ch. 650m-1865m. iii Palsading 641m.B Choto Basail Kander Bepari House to East Valukshi Bridge.Salvaged Cost Tk 37835.00i Earthwark Ch.0.00m-360m.ii Carpeting DC Ch.0.00m-360m. iii Palsading 120m. Under Agailjhara upazila District Barishal. | 506024009 506025045 |  | 1.575 |  |  |  |  | 15112800 | [11 empty] | E-Tender Under Process.
19 |  |  |  | 0 | 22.301 | 1.2 | 0 | 0 | 11.6 | 111224739.53 | 8509244 | 88170092.61 | [6 empty] | 79298136 |  | 0 |  |  | -24631393.406
1 | BDRIDP/BAR/AGL/CCA-EW/01 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal. | 506024034 | 2209.995 | [5 empty] | 302120 |  | 153224 | Ramesh Chandra Shikari LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 119075 | 77.71%
2 |  |  | 506024034 | 2209.995 | [5 empty] | 302120 |  | 148896 | Md Halim Talukder LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 122647 | 82.37%
3 | BDRIDP/BAR/AGL/CCA-EW/02 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 448658 |  | 216905 | Abdul Hakim Molla LCS No-1 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 140432 | 64.74%
4 |  | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 3613.15 | [5 empty] | 448658 |  | 231753 | Anukul Chandra Barai LCS No-2 | 20/01/15 | 2015-05-02 | 30/04/15 |  | 100% | 185062 | 79.85%
5 | BDRIDP/BAR/AGL/CCA-EW/03 | Resectioning of road from Temar Bastala to Hawla Bridge via Nagar GPS-Talbazar-lichermath Bazar road from Ch. 3840-4840m. | [7 empty] | 344680 |  | 344680 | Nolini Halder LCS No-1 | 2017-11-01 | 15/01/17 | 30/04/17 |  | 100% | 306262 | 100%
6 | [9 empty] | 230350 |  | 230350 | Susen Bala LCS No-2 | 2017-11-01 | 15/01/17 | 30/04/17 |  | 100% | 226669 | 100%
7 | BDRIDP/BAR/AGL/UZ-EW/01 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal. | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 124341 | Md. Sohrab Howlader LCS No-1 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 124340 | 100% |  | Final
8 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 307876 | Md. Mosharef Sheikh LCS No-2 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 307875 | 100% |  | Final
9 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 329106 | Abdul Rashid Howlader LCS No-3 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 329106 | 100% |  | Final
10 |  |  | 506022009 | 6543.5 | [5 empty] | 1091852 |  | 330529 | Matleb Howlader LCS No-4 | 2015-05-02 | 20/02/15 | 30/04/15 |  | 100% | 329457 | 99.68% |  | Final
11 | BDRIDP/BAR/AGL/UN-EW/01 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal. | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 201404 | Mahim Baishnab LCS No-1 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 201396 | 100%
12 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 289300 | Sudhir Kumar Ojha LCS No-2 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 288996 | 99.89%
13 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 288022 | Banendra Nath Panday LCS No-3 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 287780 | 99.92%
14 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 207336 | Rabindranath Sarker LCS No-4 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207335 | 100%
15 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 205837 | Nirmal Ghatak LCS No-5 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205837 | 100%
16 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 207632 | Bebek Pandey LCS No-6 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 207631 | 100%
17 |  |  | 506023001 | 11301.706 | [5 empty] | 1605483 |  | 205952 | Pangkoj Joydhor LCS No-7 | 28/01/15 | 20/02/15 | 30/04/15 |  | 100% | 205952 | 100%
18 | BDRIDP/BAR/AGL/CCA-EW/01 | Resectioning of Road from Seral-Goila road via Shahid Serniabad House-Tamer Jame Mosjid (Tamer Girls High School-Seral Community Center) by Earth at Ch. 0.00m-975m. | 506025048 | [6 empty] | 317636 |  | 317636 | Md. Babul Sikder | 30/03/17 | 30/03/17 | 30/04/17 |  | 100% | 310599 | 100%
18 |  |  |  | 116932.232 | 0 | 0 | 0 | 0 | 0 | 4110429 | 0 | 4340779 | [6 empty] | 4106451 |  | 0 |  |  | 0
37 |  |  |  | 116932.232 | 22.301 | 1.2 | 0 | 0 | 11.6 | 115335168.53 | 8509244 | 92510871.61 | [6 empty] | 83404587 |  | 0 |  |  | -24631393.406
Upazila: Babugonj
1 | BDRIDP/BAR/BABU/CCA-Rd/01 | Improvement of road from Babugonj Agorpur GC to Mr. Younusur Rahman (Divisional Commissioner) house via Clubgonj hat by Carpeting from Ch. 750-1400m & 0.00-1550m. | 506034025 |  | 2.2 |  |  |  |  | 9792326 | 944029 | 10750396.05 | M/S Lutful Kobir | 2014-10-07 | 17/07/14 | 16/04/15 |  | 100% | 10748336 | 100% |  | Final | 90% | -1072979.555
2 | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km. | 506035070 |  | 2.35 |  |  |  |  | 9718891 | 421856 | 10173103.86 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 10173094 | 100% |  | Final | 60% | -4069231.684
3 | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 506034095 |  | 4.32 |  |  |  |  | 18518441 | 1035938 | 19386557.17 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 19386554 | 100% |  | Final | 60% | -7754619.698
4 | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. | 506035006 |  | 2.6 |  |  |  |  | 9959477 |  | 10428682 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 10422370 | 99.94% |  | Final | 60% | -4165160.8
5 | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 506035070 | [5 empty] | 8.3 | 2931768 | 184122 | 3071060.04 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 2500000 | 81.41% |  | 715wgt †PB‡b‡R KvR Kiv hv‡e bv¦ | 60% | -657363.976
6 | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 506034095 | [5 empty] | 18.2 | 4744358 | 199349 | 4968549.43 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 4300000 | 86.54% |  |  | 60% | -1318870.342
7 | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 506035006 | [5 empty] | 7.6 | 2001016 | 62866 | 2095536.41 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 1500000 | 71.58% |  |  | 60% | -242678.154
8 | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 506034024 | [5 empty] | 12 | 1982458 | 150637 | 2076355.09 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 1163749 | 56.05% |  |  | 60% | 82064.054
9 | BDRIDP/BAR/BAB/UN-St/01 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m. | 506033006 | [5 empty] | 7.6 | 1443386 | 41933 | 1029755.17 | M/S Lutful Kobir | 29/04/15 | 2015-06-05 | 25/10/15 |  | 100% | 986117 | 100% |  | Final | 60% | -368263.898
10 | BDRIDP/BAR/BAB/UN-Rd(R)/01 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m. | 506033006 |  | 1.78 |  |  |  |  | 6457205 | 2442317 | 5193526.54 | M/S Alvi Construction | 2015-05-05 | 2015-12-05 | 2016-12-02 |  | 100% | 5024035 | 100% |  | Final | 60% | -1907919.076
11 | BDRIDP/BAR/BAB/CCA-Rd/05 | Improvement of road from Daroger hat to Shandha river bank via Battala bazar road By BC from Ch. 00-3800m under Babuganj Upazila, Barisal District. | 506034024 |  | 3.8 |  |  |  |  | 14308351 |  | 14979470.55 | M/S Atique Construction | 25/03/15 | 2015-01-04 | 2016-01-04 |  | 100% | 14979470 | 100% |  | Final | 60% | -5991787.67
12 | BDRIDP/BAR/BAB/UN-RD/02 | Improvement of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 |  | 2.11 |  |  |  |  | 12421386 |  | 11570042.22 | M/S Hasan Construction | 22/11/16 | 29/11/16 | 28/06/17 |  | 100% | 11570042 | 100% |  | Final
13 | BDRIDP/BAR/BAB/UN-St/02 | Construction of No 6.00m Span OFC, 3 Nos 2.00m×2.00m & 2 Nos 1.60m×1.60m RCC Box Culvert on Road From Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m, 0.00m, 125m, 1101m, 1907m & 708m. | 506033007 | [5 empty] | 15.2 | 4182978 |  | 4179759.25 | M/S Saifuddin Traders | 14/11/16 | 20/11/16 | 19/09/17 |  | 100% | 4095279 | 100% |  | Final
14 | BDRIDP/BAR/BAB/CCA-RdR/06 | Improvement of Road from Telerchar GPS -Najamrari Bari - Jahungirnagar UP road Start ch.1700m Satter Mirar Bari -Thakur. From Ch.0.0m - 550mSalvaged Cost Tk 192766.00 | 506035103 506034109 |  | 1.7 |  |  |  |  | 3507645.29 |  | 3156880.761 | M/S Niaz Traders | 2018-11-01 | 18/01/18 | 18/07/18 |  | 50% | 700000 | 22.17%
15 | BDRIDP/BAR/BAB/CCA-Rd/07 | Improvement of road from Jahapur Shilondia Bridge -Uttor Mujafforpur Peda Master bari under Jahangir Nagar Union a Bituminous Surfacing -wearing courseDC ch.190m -1190m b 1No. 2.0m x 2.0m & 1No.1.0m x1.0m RCC Box Culvert at Ch.273m & 615m under Babuganj Upazila Barisal District. | 506035018 |  | 1.1 |  |  |  | 3 | 6955230.78 |  | 6449870.12 | M/S Amir Engineering Corporation | 27/02/18 | 2018-04-03 | 2018-04-12 |  | 100% | 3350000 | 51.94%
16 | BDRIDP/ BAR/BAB/ CCA-Rd/08 | Improvement of Road from Ramjankathi GPS to Charalgi GPS. a Earthwark from Ch. 0- 1500m.b Carpeting DC from Ch. 0- 1500m.c Construction of 2 Nos 625mmx600mm U-Drain at Ch. 736m & 1285m.d Palisading Work 150.00m. Under Babuganj District- Barishal. | 506035132 |  | 1.5 |  |  |  | 1.25 | 11562581.55 | [11 empty] | E-Tender Under Process.
17 | BDRIDP/ BAR/BAB/ CCA-Rd/09 | Improvement of from Khudrokathi Freedom Fighter Mogibor Rahaman Sikder House to Baige Comander Abdul Mojid Khan house. At Ch. 00m-1100m.Salvaged Cost Tk 285357.00i Earthwark Ch.0.00m-1100m.ii Carpeting DC Ch.0.00m-1100m. iii Construction of 02 Nos 0.625mx0.600m U-Drain. at Ch.110m & 400m.iv Palsading 46m.Under Babuganj Upazila Barishal District. | 506034155 |  | 1.1 |  |  |  | 1.25 | 7945251 | [11 empty] | E-Tender Under Process.
17 |  |  |  | 0 | 24.56 | 0 | 0 | 0 | 74.4 | 128432749.62 | 5483047 | 109509544.661 | [6 empty] | 100899046 |  | 0 |  |  | -27466810.799
1 | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. | 506033006 | [6 empty] | 195850 |  | 195850 | Md. Masum Hossain Gazi LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 185240 | 100% |  | Final
2 | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Earth Work under Dehergothi UP at Ch. 0.00m-2+350km. | 506035070 | [6 empty] | 285121 |  | 285121 | Taslima LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 270738 | 100% |  | Final
3 | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Earth Work under Dehergothi UP at Ch. 0.00m-4+320km. | 506034095 | [6 empty] | 381065 |  | 381065 | Rajib Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 80% | 38100 | 9.998%
4 | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Earth Work under Dehergothi UP at Ch. 0.00m-2+600km. | 506035006 | [6 empty] | 300535 |  | 300535 | Md. Liton Hossain LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 279799 | 100% |  | Final
5 | BDRIDP/BAR/BAB/CCA-EW/04 | Improvement of road From Daroger hat to Shandha river bank via Battala Bazar road by Earth work from Ch. 0.00m-3900m. | 506034024 | [6 empty] | 354810 |  | 354810 | Md. Kabir Sikder LCS No-1 | 15/05/15 | 15/05/15 | 30/09/15 |  | 100% | 203192 | 57.27%
6 | BDRIDP/BAR/BAB/UN-EW/02 | Resectioning of Road from Agorpur UP Office (Chairman Hat) to Miar Hat via Jahapur under Jahangirnagor (Agorpur) UP at Ch. 0.00m-2110m | 506033007 | 2404.83 | [5 empty] | 290672 | 290672 | 290672 | Md. Habibur Rohman LCS No-1 | 16/06/16 | 20/06/16 | 20/10/16 |  | 100% | 290503 | 99.94%
6 |  |  |  | 2404.83 | 0 | 0 | 0 | 0 | 0 | 1808053 | 290672 | 1808053 | [6 empty] | 1267572 |  | 0 |  |  | 0
23 |  |  |  | 2404.83 | 24.56 | 0 | 0 | 0 | 74.4 | 130240802.62 | 5773719 | 111317597.661 | [6 empty] | 102166618 |  |  |  |  | -27466810.799
Upazila: Mehendigonj
1 | BDRIDP/BAR/MHN/UZR(R)-Rd/01 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal. | 506622005 |  | 1.11 |  |  |  |  | 5853739 |  | 4973018 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 100% | 4973018 | 100% |  | Final | 60% | -1989207.2
2 | BDRIDP/BAR/MHN/CCA-Rd/01 | Improvement of Mothertoli Bazar - Uttarchar road via Charekkaria road by BC (Ch.2170-3220m, Road Under Mehendigonj Upazila, District-Barisal. | 506625079 |  | 1.05 |  |  |  |  | 5327472 |  | 4515030 | M/S Nahid Enterprise | 16/11/14 | 23/11/14 | 23/04/15 |  | 100% | 4514924 | 100% |  | Final | 60% | -1805906
3 | BDRIDP/BAR/MHN/CCA-St/01 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal. | 506625079 | [5 empty] | 1 | 222783 |  | 184788 | M/S Hasib Enterprise | 2014-09-11 | 16/11/14 | 15/03/15 |  | 100% | 167876 | 100% |  | Final
4 | BDRIDP/BAR/MHN/CCA-Rd/02 | Improvement of road Purbo Yearbeg (Paloun Bari) - Trimohoni Big Road via Howlader Bari,Jamadder Bari Ebtadi Madrasha from ch.0.00 - 1610m with U-Drain (0.625m x 0.90m) at ch.1051m. | 506624016 |  | 1.61 |  |  |  |  | 6864308 | 6864308 | 6860287.95 | M/S Hasan Construction | 2017-12-01 | 19/01/17 | 19/09/17 |  | 70% | 2525000 | 36.81%
5 | BDRIDP/BAR/MHN/UZ-Rd/02 | Improvement of Ulania GC Aligonj(Hizla) road from Ch.1000-4000m under Mehandigonj Upazila,Barisal. | 506622007 |  | 3 |  |  |  |  | 10545370 |  | 10492643.13 | M/S Lutful Kabir | 2017-07-05 | 14/05/17 | 14/02/18 |  | 100% | 6200000 | 59.09%
6 | BDRIDP/BAR/MHN/CCA-Rd/03 | Improvement of Road from Posshim Yearbeg Dadpur GPS under Mehendiganj Upazila District Barisal aEarthwork Ch.1000 2760m b HBB Ch.1000 -2760m | 506625062 |  |  | 1 |  |  |  | 5960375.56 |  | 5661508 | M/S Amir Engineering Corporation | 28/03/18 | 2018-05-04 | 2019-05-01 |  | 100% | 4000000 | 70.65%
7 | BDRIDP/BAR/MHN/GC/01 | Constructionof Langutia G C (i) Fish Shed (Size : 12m x 6m) (ii) 2 Nos Waste collection Pit (Dustbin) (Size : 1.4m x 1.4m) (iii) Multipurpose Shed (Size : 12m x 6m) (iv) Logistic Support for Langutia Bazar (v) Toilet Block (Size : 5.75m x 3.07m) (vi) 2 Nos Deep Hand Tube well (vii) CC road without side drain : 100m (viii) RCC Ghat at Langutia Bazar Under Mehendigonj, Barishal District | [7 empty] | 4989791 |  | 4740301.45 | M/S Oshin Enterprise | 2019-04-01 | 2019-11-01 | 2019-04-07 |  | 0% |  | 0%
7 |  |  |  | 0 | 6.77 | 1 | 0 | 0 | 1 | 39763838.56 | 6864308 | 37427576.53 | [6 empty] | 22380818 |  | 0 |  |  | -3795113.2
1 | BDRIDP/BAR/MHN/CCA-EW/01 | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 0.00m-600m by Earth. | 506624016 | [6 empty] | 346489 | 346489 | 346489 | Nizam Uddin Talukder LCS No-1 | 2016-06-12 | 18/12/16 | 18/03/17 |  | 100% | 345129 | 99.61%
2 |  | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 600m-1200m by Earth. | [7 empty] | 421652 | 421652 | 421652 | Md. Sadak LCS No-2 | 2016-06-12 | 18/12/16 | 18/03/17 |  | 100% | 352629 | 83.63%
3 |  | Resectioning of Purbo Yearbeg (Paloun Bari)-Trimohoni Big Road via Howlader Bari, Jamadder Bari Ebtadi Madrasha at Ch. 1200m-1610m by Earth. | [7 empty] | 258058 | 258058 | 258058 | Md. Faruk Buiya LCS No-3 | 2016-06-12 | 18/12/16 | 18/03/17 |  | 100% | 256220 | 99.29%
4 | BDRIDP/BAR/MHN/UZ-EW/01 | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1000m-1600m | 506622007 | [6 empty] | 164958 | 164958 | 164958 | LCS No-1 |  |  |  |  | 100% | 159113 | 96.46%
5 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 1600m-2350m | [7 empty] | 379812 | 379812 | 379812 | LCS No-2 |  |  |  |  | 100% | 372997 | 98.21%
6 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 2350m-3250m | [7 empty] | 297385 | 297385 | 297385 | LCS No-3 |  |  |  |  | 100% | 290952 | 97.84%
7 |  | Resectioning of Ulania GC-Aligonj GC (Hizla) Road at Ch. 3250m-4000m | [7 empty] | 254707 | 254707 | 254707 | LCS No-4 |  |  |  |  | 100% | 249233 | 97.85%
7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2123061 | 2123061 | 2123061 | [6 empty] | 2026273
14 |  |  |  | 0 | 6.77 | 1 | 0 | 0 | 1 | 41886899.56 | 8987369 | 39550637.53 | [6 empty] | 24407091 |  | 0
Upazila: Hizla
1 | BDRIDP/BAR/HZL/UZ-Rd(R)/01 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m. | 506362009 |  | 1 |  |  |  |  | 7094634 | 1476772 | 5645230.7 | M/S Oshin Enterprise | 21/05/15 | 28/05/15 | 28/02/16 |  | 100% | 5645230 | 100% |  | Final | 40% | -3387137.72
2 | BDRIDP/BAR/HZL/CCA-Rd/01 | Improvement of Kowria- Moulavirhat UZR Poschim koralia road under Hizla Upazila District Barisal aEarth work from Ch.0.0 -900m b Dense Carpeting Ch.0.0 -900m c Two vent 4m x 4m RCC Box Culvert at Ch.252m | 506364033 |  | 0.9 |  |  |  | 8 |  |  | 7950598.407 | Md. Mahafuz Khan | 2018-04-04 | 2018-11-04 | 2019-01-02 |  | 35% |  | 0%
3 | BDRIDP/BAR/HZL/CCA-Rd/02 | Improvement of Hizla Muladi road to Motiar Dewan Bari via Sergent Dula Bari roadRHD via Surgeant Dulal- Kathal BeganUZR under Hizla Upazila Barisal District.ID No.506364003 Salvaged Cost Tk.2186650.00a Earth work Ch.0.0 - 1500mb Carpetting Ch. 0.0 - 1500mc Construction of 2 nos U-Drain on the same road at Ch.777m & 1275m |  |  | 1.5 |  |  |  | 1.8 | 10053464.17 |  | 9550790.96 | M/S R S Construction | 21/06/18 | 28/06/18 | 28/12/18 |  | 25% |  | 0%
4 | BDRIDP/BAR/HZL/Gha/01 | Construction of RCC Boat land Station at Abupur Ghat under Hizla Upazila Barisal | [7 empty] | 3254666.63 |  | 3146706.64 | M/S S H Enterprise | 2018-05-05 | 2018-12-05 | 2018-12-11 |  | 100% | 3119743 | 100%
5 | BDRIDP/BAR/HZL/CCA-Rd/03 | Improvement of Khunna Hospital RHD via Kawmi Madrasha - Baherchar UZR Barajalia Board GPS CS Connecting road a Earthwork from Ch.850 -1820m b Carpetting BC from Ch.850 -1820m under Hizla Upazila District Barishal Salvaged Cost TK 2343371.00 | 506365049 |  | 0.97 |  |  |  |  | 6797662.78 |  | 6457779.64 | M/S Munny Enterprise |  |  |  |  | 20% |  | 0%
6 | BDRIDP/BAR/HZL/CCA-Rd/04 | Improvement of road from Horinathpur Koshaipotti UZR - Zetighat GPS UZR ID No. a Earthwork from Ch.0.0 -1500m b Carpetting BC from Ch.0.0 -1500m under Hizla Upazila District Barishal Salvaged Cost TK 112128.00 | 506365056 |  | 1.5 |  |  |  |  | 9936759.78 |  | 9439921.79 | M/S Esad & Emad Enterprise |  |  |  |  | 10% |  | 0%
7 | BDRIDP/ BAR/HZL/ CCA-Rd/05 | Improvement of road from UZR -6 Mohishkhola Madrasha to VRA-15 Uttor Guabaria GPS via house of Abdul Gafur Sarder road by BC From Ch. 00m-1760.00m. Salvage Amount TK 296023.00 Under Hizla Upazila District- Barishal. | 506364034 |  | 1.76 |  |  |  |  | 12738507.36 | [11 empty] | E-Tender Under Process.
8 | BDRIDP/BAR/HZL/CCA-Rd/06 | Improvement of Kawria Bazar Danushikder hat road - Noroshingpur road Start Mollah Bari Shop Salvaged Cost Tk.309333.54 i Earth work Ch.0.0 - 760miiCarpeting DC Ch.0.0 - 760m under Hizla Upazila District Barishal. | 506365051 |  | 0.76 |  |  |  |  | 5255934.36 | [11 empty] | E-Tender Under Process.
9 | BDRIDP/BAR/HZL/UZ-St/01 | Dhunusikder Hat to Memania Taker Hat road via Abupur Kheyaghat i Construction of Diuble vent 2 x 4.50 x 6.50m RCC Box Culvert at Ch.2600mii Construction of Diuble vent 2 x 4.00 x 5.00m RCC Box Culvert at Ch.3380mUnder Hizla Upazila Barishal District. | 506362005 | [5 empty] | 17 | 5693472 | [11 empty] | E-Tender Under Process.
10 | BDRIDP/ BAR/HZL/ CCA-Rd/07 | Improvement of Purbo Kandi WDB Embt. Salvaged Cost Tk 257546.00i Earthwark Ch.0.00m-900m. ii Carpeting DC Ch.0.00m-900m. iii Palsading 95m.Under Hizla Upazila Barishal District. | 506365003 |  | 0.9 |  |  |  |  | 6755327.72 | [11 empty] | E-Tender Under Process.
10 |  |  |  | 0 | 9.29 | 0 | 0 | 0 | 26.8 | 67580428.8 | 1476772 | 42191028.137 | [6 empty] | 8764973 |  | 0 |  |  | -3387137.72
1 | BDRIDP/BAR/HZL/UZ-EW/01 | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 0.00m-325m | 506362009 | [6 empty] | 226562 | 226562 | 226562 | Md. Humaun Kabir LCS No-1 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 225780 | 99.65%
2 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 325m-650m | [7 empty] | 220227 | 220227 | 220227 | Md. Monju Noli LCS No-2 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 218498 | 100%
3 |  | Resectioning of road from Dhanusikder Hat to Muladi Upazila Road at Ch. 650m-1000m | [7 empty] | 217087 | 217087 | 217087 | Md. Parvaz LCS No-3 | 2015-04-11 | 15/11/15 | 30/03/16 |  | 100% | 214482 | 100%
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 663876 | 663876 | 663876 | [6 empty] | 658760
13 |  |  |  | 0 | 9.29 | 0 | 0 | 0 | 26.8 | 68244304.8 | 2140648 | 42854904.137 | [6 empty] | 9423733
Upazila: Banaripara
1 | BDRIDP/BAR/BAN/UZ-Rd/01 | Improvement of road from Banaripara - Harta, At Ch.5865 -6865m under Banaripara Upazila, District Barisal. | 506102003 | 0 | 1 | 0 | 0 | 0 | 0 | 7013799 | 7013799 | 5349539.02 | M/S Saleha Enterprise | 29/01/17 | 2017-06-02 | 2017-06-06 |  | 50% | 1300000 | 24.3% |  |  | 40% | 839815.608
2 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m,1 No.3.0m x 3.0m, 2Nos.4.0m x 4.0m, 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 506102003 | 0 | 0 | 0 | 0 | 0 | 11 | 7531517 | 7531517 | 5461652.5 | M/S Soma Enterprise | 25/01/17 | 2017-02-02 | 2017-02-10 |  | 100% | 5200000 | 95.21%
3 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 11850164.61 |  | 10665148 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 90% | 9450000 | 88.61%
4 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 9814374 |  | 8832936 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 70% | 6035000 | 68.32%
5 | BDRIDP/BAR/BAN/Gha/01 | Construction of RCC Ghat at Mohish Katakhali Kheya Ghat under Banaripara Upazila Barisal . | [7 empty] | 2911932.99 |  | 2620739.69 | M/S Amir Engineering Corporation | 2018-03-05 | 2018-10-06 | 2018-10-12 |  | 20% |  | 0%
6 | BDRIDP/ BAR/BAN/ CCA-Rd/01 | Improvement of road by BC Gordder Abu Taher Shop to Kachua Madrasha. Salvaged Cost Tk 448135.00i Earthwark Ch.600m-1600m. ii Carpeting DC Ch.600m-1600m. iii Construction of 03 Nos. 1.5mx1.5m Box Culvert at Ch.667m742m & 938m & U-Drain 0.6mx0.6m at Ch.870m973m & 1550m. under Banaripara UpazilaBarishal District | 506105098 |  | 1 |  |  |  | 5.1 | 8974998.66 | [11 empty] | E-Tender Under Process.
6 |  |  |  | 0 | 2 | 0 | 0 | 0 | 46.1 | 48096786.26 | 14545316 | 32930015.21 | [6 empty] | 21985000 |  | 0 |  |  | 839815.608
1 | BDRIDP/BAR/BAN/UZ-EW/01 | Resectioning of Banaripara-Harta Road at Ch. 4665m-6066m. | 506102003 | 3655.305 | [5 empty] | 441816.72 | 441816.72 | 441816.72 | Zakir Hossain LCS No: 1 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 437075 | 100%
2 |  | Resectioning of Banaripara-Harta Road at Ch. 6066m-7252m. |  | 3440.645 | [5 empty] | 415870.76 | 415870.76 | 415870.76 | Kohinoor Begum LCS No: 2 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 415280 | 99.86%
3 |  | Resectioning of Banaripara-Harta Road at Ch. 7252m-7702m. |  | 3300.95 | [5 empty] | 398985.83 | 398985.83 | 398985.83 | Baschu Forazi LCS No: 3 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 397904 | 99.73%
4 |  | Resectioning of Banaripara-Harta Road at Ch. 7702m-8152m. |  | 3181.47 | [5 empty] | 384544.28 | 384544.28 | 384544.28 | Abdul Karim LCS No: 4 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 382564 | 100%
5 |  | Resectioning of Banaripara-Harta Road at Ch. 8152m-8752m. |  | 3835.515 | [5 empty] | 463598.7 | 463598.7 | 463598.7 | Horolal Mondol LCS No: 5 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 463243 | 99.92%
6 |  | Resectioning of Banaripara-Harta Road at Ch. 8752m-9352m. |  | 3821.705 | [5 empty] | 461929.48 | 461929.48 | 461929.48 | Mithu Howlader LCS No: 6 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 461929 | 100%
7 |  | Resectioning of Banaripara-Harta Road at Ch. 9352m-9760m. |  | 3097.89 | [5 empty] | 374441.97 | 374441.97 | 374441.97 | Md. Khairul Islam LCS No: 7 | 2016-10-11 | 2016-10-11 | 30/03/17 |  | 100% | 373462 | 99.74%
7 |  |  |  | 24333.48 | [5 empty] | 2941187.74 | 2941187.74 | 2941187.74 | [6 empty] | 2931457
13 |  |  |  | 24333.48 | 2 | 0 | 0 | 0 | 46.1 | 51037974 | 17486503.74 | 35871202.95 | [6 empty] | 24916457
267 |  |  |  | 202153.643 | 174.3 | 10.509 | 0 | 0 | 690.99 | 1348453936.18 | 97974535.74 | 1059406949.403 | [6 empty] | 728276982 |  | 0 |  |  | -64116545.26
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal
0

## Earth work
Monthly Progress Report
Implementation Status
Barisal Division Rural Infrastructure Development Project
District: Barisal. | [14 empty] | Upto Month: December/2014
Sl. No | Upazila | Type of Work (E/W, BC, CC, HBB, Brdg, cul, Tree, Mkt, Gc, Ght, La) | Package No. | Scheme Name with Location (Ch. to Ch.) | Road ID No. | Effective Quantity (m3, Km, m, Nos, ha) | Approved Estimate (Tk.) | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract Signing Date | Actual Start Date | Completion Date as Per Contract | Actual Completion Date | Physical Progress (%) | Financial Progress |  | Fund Received With memo Date | Remarks
[15 empty] | Amount Spent (Tk.) | In %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | Sadar | Earth work | BDRIDP/BAR/SDR/CCA-EW/01 | Rehabiliation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 | 0.732km | 238242 | 238242 | LCS
1 | Sub-Total: | [5 empty] | 238242 | 238242 | [5 empty] | 0%
1 | Muladi | Earth work | LCS-1 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 0.00-500m. | 506692004 | 0.500km | 334778 | 334778 | LCS-1 | 18/05/14 | 22/05/14 | 22/10/14 |  | 70% | 219205
2 | Muladi | Earth work | LCS-2 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 500-900m. | 506692004 | 0.400km | 403489 | 403489 | LCS-2 | 18/05/14 | 22/05/14 | 22/10/14 |  | 65% | 257547
3 | Muladi | Earth work | LCS-3 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 900-1150m. | 506692004 | 0.250km | 386512 | 386512 | LCS-3 | 18/05/14 | 22/05/14 | 22/10/14 |  | 75% | 270840
4 | Muladi | Earth work | LCS-4 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1150-1500m. | 506692004 | 0.350km | 371303 | 371303 | LCS-4 | 18/05/14 | 22/05/14 | 22/10/14 |  | 80% | 267959
5 | Muladi | Earth work | LCS-5 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1500-1800m. | 506692004 | 0.300km | 372013 | 372013 | LCS-5 | 18/05/14 | 22/05/14 | 22/10/14 |  | 80% | 260843
6 | Muladi | Earth work | LCS-6 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 1800-2150m. | 506692004 | 0.350km | 374943 | 374943 | LCS-6 | 18/05/14 | 22/05/14 | 22/10/14 |  | 85% | 266409
7 | Muladi | Earth work | LCS-7 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2150-2600m. | 506692004 | 0.450km | 374353 | 374353 | LCS-7 | 18/05/14 | 22/05/14 | 22/10/14 |  | 50% | 133641
8 | Muladi | Earth work | LCS-8 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2600-2900m. | 506692004 | 0.300km | 369858 | 369858 | LCS-8 | 18/05/14 | 22/05/14 | 22/10/14 |  | 55% | 31000
9 | Muladi | Earth work | LCS-9 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 2900-3150m. | 506692004 | 0.250km | 397315 | 397315 | LCS-9 | 18/05/14 | 22/05/14 | 22/10/14 |  | 50% | 31000
10 | Muladi | Earth work | LCS-10 | Improvement of road by earth work from Mirdarhat GC-Nazirpur GCCR via Madrasharhat, Nomorhat & Bangla Bazar Ch. 3150-3450m. | 506692004 | 0.300km | 428100 | 428100 | LCS-10 | 18/05/14 | 22/05/14 | 22/10/14 |  | 45% | 33000
11 | Muladi | Earth work | BDRIDP/BAR/MUL/CCA-EW/01 | Earth work of road Raguya Kazirchar R&H-Joynal Master via H/Q Sahajahan Dafader Ch. 0.00m-1000m under Muladi upazila, Barisal District. | 506695135 | 1.00km | 221909 | 221909 | Md Fazlu Tafader | 17/11/14 | 18/11/14 | 18/02/15 |  | 95% | 22200
12 | Muladi | Earth work | BDRIDP/BAR/MUL/CCA-EW/02 | Earth work of road from Boraiya R&D to Prokas Mondol bari via Boraiya GPS at Ch. 0.00-585m under Muladi upazila, Barisal District. | 506695127 | 0.585km | 239879 | 239879 | Md Kabir Hossain | 17/11/14 | 18/11/14 | 18/02/15 |  | 45% | 23900
13 | Muladi | Earth work | BDRIDP/BAR/MUL/CCA-EW/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road by Earth work from Ch. 00-1250m under Muladi upazila, Barisal District. | 506694063 | 1.250km | 323312 | 323312 | LCS
13 | Sub-Total: | [5 empty] | 4597764 | 4597764 | [5 empty] | 795% | 1817544
1 | Agailjhara | Earth work | BDRIDP/BAR/AGL/CCA-EW/01 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by Earth work from Ch. 00-1000m under Agailjhara Upazila, Barisal. | 506024034 | 1.00km | 302120 | 302120
2 | Agailjhara | Earth work | BDRIDP/BAR/AGL/CCA-EW/02 | Improvement of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas’s House by Earth work from Ch. 00-1200m under Agailjhara Upazila, Barisal. | 506025058 | 1.200km | 448658 | 448658
3 | Agailjhara | Earth work | BDRIDP/BAR/AGL/UZ-EW/01 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by Earth work from Ch. 3800-5800m under Agailjhara Upazila, Barisal. | 506022009 | 2.00km | 1091852 | 1091852
4 | Agailjhara | Earth work | BDRIDP/BAR/AGL/UN-EW/01 | Improvement of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by Earth work form Ch. 11192-13954m under Agailjhara Upazila, Barisal. | 506023001 | 2.762km | 1605483 | 1605483
4 | Sub-Total: | [5 empty] | 3448113 | 3448113 | [5 empty] | 0%
1 | Babugonj | Earth work | BDRIDP/BAR/BAB/UN-Ew/01 | Improvement of road from Dehergothi UP office to Kalir Bazar road by Earth Work from Ch. 1960m-3710m. | 506033006 | 1.750km | 195850 | 195850
2 | Babugonj | Earth work | BDRIDP/BAR/BAB/CCA-Ew/01 | Improvement of road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School By Carpeting under Dehergothi UP at Ch. 0.00m-2+350km. | 506035070 |  | 285121
3 | Babugonj | Earth work | BDRIDP/BAR/BAB/CCA-Ew/02 | Improvement of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergothi UP at Ch. 0.00m-4+320km. | 506034095 |  | 381065
4 | Babugonj | Earth work | BDRIDP/BAR/BAB/CCA-Ew/03 | Improvement of road Jayinpur madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under Dehergothi UP at Ch. 0.00m-2+600km. | 506035006 |  | 300535
4 | Sub-Total: | [5 empty] | 1162571 | 195850 | [5 empty] | 0%
22 | Grand Total: | [5 empty] | 9446690 | 8479969 | [5 empty] | 795% | 1817544
Accountant |  |  | Sub-Assistant Engineer |  |  | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal |  |  | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  |  | LGED, Barisal

## Structure
Monthly Progress Report
Implementation Status
Barisal Division Rural Infrastructure Development Project
District: Barisal. | [15 empty] | Upto Month: December/2014
Sl. No | Upazila | Type of Work (E/W, BC, CC, HBB, Brdg, cul, Tree, Mkt, Gc, Ght, La) | Package No. | Scheme Name with Location (Ch. to Ch.) | Road ID No. | Effective Quantity (m3, Km, m, Nos, ha) | Approved Estimate (Tk.) | Salvage Materials | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract Signing Date | Actual Start Date | Completion Date as Per Contract | Actual Completion Date | Physical Progress (%) | Financial Progress |  | Fund Received With memo Date | Remarks
[16 empty] | Amount Spent (Tk.) | In %
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Sadar | BC | BDRIDP/BAR/SDR/CCA-Rd/01 | Improvement of Bukhainagar Bridge to Abdul Aziz Khan's House via Shaluka GPS Road (Ch. 00-500m). | 506514170 | 0.500km | 2045654 |  | 1613223.41 | M/S Talukder Enterprise | 2014-09-06 | 16/06/14 | 16/09/14 |  | 30%
2 | Sadar | BC | BDRIDP/BAR/SDR/CCA-Rd/02 | Improvement of Chandpura Mojidderhat-Saheberhat via Khontakhali School road from Ch. 1635-3192m. | 506514154 | 1.557km | 7466730 |  | 6279530.87 | M/S S M Construction | 2014-10-08 | 17/08/14 | 16/05/15 |  | 0%
3 | Sadar | BC | BDRIDP/BAR/SDR/CCA-Rd/03 | Improvement of Road form Karnakathi Puraton Hat-Char Aicha Sabuz Memerer Bari By BC Ch. 0.00-513m | 506514148 | 0.513km | 2809559 |  | 2294335.91 | M/S Serajul Islam Hanif | 24/07/14 | 2014-01-08 | 2015-01-02 |  | 0%
4 | Sadar | BC | BDRIDP/BAR/SDR/CCA-Rd/04 | Rehabilitation of road from of Narokati Altaf Mollah Bari-Moslem Howlader Dokan via GPS (Narokati GPS) road by BC from Ch. 0.00m-732m. | 506514059 | 0.732km | 2900881 | 1230068 | [10 empty] | E-Tender under Process
5 | Sadar | Bridge | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | 20.00m | 12772854 | [11 empty] | E-Tender under Process
6 | Sadar | BC & Box Culvert | BDRIDP/BAR/SDR/CCA-Rd/04 | Improvement of road from Chownatha Toabu Chowkider Bari via Clinic road by BC from Ch. 0.00m-1000m with 1 No 1.60m×1.60m Box Culvert at Ch. 366mm. | 506515102 | 1.00km & 1.60m | 4543594 | [11 empty] | E-Tender under Process
7 | Sadar | Box Culvert | BDRIDP/BAR/SDR/CCA-St/04 | Construction of 4 Nos 2.00×1.60m Box Culvert on Jaliabari Pool via Mujaffar Hazi Bari road at Ch. 391m, 910m, 1740, & 1860m. | 506514048 |  | 1333966 | [11 empty] | E-Tender under Process
8 | Sadar | BC | BDRIDP/BAR/SDR/CCA-Rd(R)/05 | Rehabilitation of road from Jaliabari Pool via Mujaffar Hazi Bari road by BC from Ch. 0.00m-2782m. | 506514048 | 2.782km | 10910419 | 207108 | [10 empty] | E-Tender under Process
8 | Sub-Total: | [5 empty] | 44783657 | 1437176 | 10187090.19 | [5 empty] | 30%
1 | Uzirpur | Bridge | BDRIDP/BAR/UZ/CCA-St/01 | Construction of 15.00m RCC Girder Bridge at Ch. 1600m on Daberkul-Dhamura Road over the Thandar Khal infornt of Wazed Ali Sikder GPS. |  | 15.00m | 6544168 |  | 5567698.82 | M/S Safi Enterprise | 2014-11-06 | 18/06/14 | 17/06/15 |  | 0%
2 | Uzirpur | U-Drain & Box Culvert | BDRIDP/BAR/UZP/CCA-St/02 | Construction of 1No.0.625m x 0.600m U-Drain & 1No.2 x 4.0m x 4.0m RCC Box Culvert on Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market ,Nurani Madrasha & H/O Mr.Habibur Rahman road at Ch.650m & 816m. | 506945205 |  | 2586217 |  | 2015457.24 | Md Zakir Hossain Mia | 23/11/14 | 30/11/14 | 30/05/15 |  | 0%
3 | Uzirpur | BC | BDRIDP/BAR/UZP/CCA-Rd/01 | Improvement of road from Goria Natunhat to Fakirbari via Gomostabari Corner, H/O Hazi Makbul Molla, Santu Market, Nurani Madrasha & H/O Mr.Habibur Rahman (Beer Protik) by BC from Ch.0.00-1500m under Uzirpur Upazila, Barisal. | 506945205 | 1.500km | 6378273 |  | 5167677 | Md Sirazul Islam Hanif | 2014-01-12 | 2014-08-12 | 2015-07-06 |  | 0%
4 | Uzirpur | HBB | BDRIDP/BAR/UZP/CCA-Rd/02 | Improvement of road from Paschim Satla WAPDA to Satla Kheyaghat via H/O Fazlul Hoque Hawlader & Mosque By HBB from Ch. 0.00-375m. | 506945204 | 0.375km | 1316117 | [11 empty] | E-Tender under Process
5 | Uzirpur | RCC Box Culvert | BDRIDP/BAR/UZR/CCA-St/03 | Construction of 2 Nos 1 Vent 2.00×2.00m RCC Box Culvert on the Khal on the road from Mosang Bazar South side of river towards the west (Mosang Khal GCCR to Mosang Jamey Mosque road) at Ch 10m & 400m. | 506945129 | 4.00m | 3397103 | [11 empty] | E-Tender under Process
5 | Sub-Total: | [5 empty] | 20221878 | 0 | 12750833.06
1 | Muladi | Box Culvert | BDRIDP/BAR/MUL/UZ-St/01 | Construction of 4 Nos Box Culvert on Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road at Ch. 1020m, 1950m, 2360m & 3435m. | 506692004 | 19.00m | 7798117 |  | 8772459.2 | M/S Misi Construction | 21/07/14 | 28/07/14 | 27/03/15 |  | 0%
2 | Muladi | BC | BDRIDP/BAR/MUL/UZ-Rd/01 | Improvement of road from Mirdarhat GC-Nazirpur GCCR via Madrasharhat Nomorhat & Bangla Bazar road Ch. 0.00-3450m. | 506692004 | 3.450km | 24406349 |  | 20744407.41 | M/S Lutful Kobir | 13/08/14 | 20/08/14 | 20/05/15 |  | 0%
3 | Muladi | HBB | BDRIDP/BAR/MUL/CCA-Rd/01 | Rehabilitation of road Raguya Kazirchar R & H - Joynal Master via H/O Sahajahan Dafader (Ch.0.00- 1000.00m. Road under Muladi upazila, Barisal District. | 506695135 | 1.00km | 4172838 |  | 3545269 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 0%
4 | Muladi | HBB | BDRIDP/BAR/MUL/CCA-Rd/02 | Improvement of Road from Boraiya R & HD to Prokas Mondol bari via Boraiya GPS at Ch.0+00km to 0+585km ,Road under Muladi upazila, Barisal District. | 506695127 | 0.585km | 2763145 |  | 2347546 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 0%
5 | Muladi | RCC Box Culvert | BDRIDP/BAR/MUL/CCA-St/02 | Construction of 1 No 4.00m×4.00m (3 Vent) RCC Box Culvert on Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat Road at ch. 0.00m. | 506694001 | 4.00m | 2543802 | [11 empty] | E-Tender under Process
6 | Muladi | RCC Box Culvert | BDRIDP/BAR/MUL/CCA-St/03 | Construction of 2 Nos 4.00m×4.00m (2 Vent) RCC Box Culvert on Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road at Ch. 750m & 1402m | 506694060 | 8.00m | 5115590 | [11 empty] | E-Tender under Process
7 | Muladi | BC | BDRIDP/BAR/MUL/CCA-Rd(R)/04 | Rehabilitation of road from Madrashar Hat (Start from Char Kalekhan College gate) to Charmalia Beparir Hat road by BC from Ch. 0.00m-2175m. | 506694001 | 2,175km | 8969284 | 1518637 | [10 empty] | E-Tender under Process
8 | Muladi | BC | BDRIDP/BAR/MUL/CCA-Rd/05 | Improvement of road from Kashem Sharder Barir Pool-Kaetmara Kader Mirda Bari road by BC road Ch. 750m-2100m. | 506694060 | 1.350km | 5450114 | [11 empty] | E-Tender under Process
9 | Muladi | HBB | BDRIDP/BAR/MUL/CCA-Rd/03 | Improvement of road from Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road from Ch. 0.00m-1250m. | 506694063 | 1.250km | 3310397 | [11 empty] | E-Tender under Process
10 | Muladi | RCC Box Culvert | BDRIDP/BAR/MUL/CCA-St/01 | Construction of 1 no 1 Vent 2.00m×2.00m RCC Box Culvert on Bepari Bridge to Char Padma hat via Habib noli at Safipur UP (South Side of Amir Sarif Bridge to Madrasha Bazar via Front of Mojibur Rahaman Noli Bari) road at Ch. 750m | 506694063 | 2.00m | 505514 | [11 empty] | E-Tender under Process
10 | Sub-Total: | [5 empty] | 65035150 | 1518637 | 35409681.61 | [6 empty] | 0
1 | Bakergonj | HBB | BDRIDP/BAR/BAK/CCA-Rd/01 | Improvement of road from South side Dhola Sluice Gate to Alim Meridha Bari (Vary) via Sikder Bari, Manik Member Bari, Shatghor & Mannan Princhpal Bari (East side of Hanua Bridge to Shatghor via Shikder Bari) By HBB from Ch. 0.00-1013m. | 506075221 | 1.013km | 3558576 |  | 3985608.82 | M/S Nahid Enterprise | 17/07/14 | 24/07/14 | 24/01/15 |  | 0%
1 | Sub-Total: | [5 empty] | 3558576 |  | 3985608.82
1 | Gournadi | BC | BDRIDP/BAR/GOR/CCA-Rd/02 | Improvement of road from Gournadi Highway Thana Connecting road under Gournadi Upazila. | 506325047 | 0.250km | 1544297 |  | 1264779.02 | M/S Auditi Enterprise | 23/09/14 | 30/09/14 | 30/03/14 |  | 0%
2 | Gournadi | U-drain | BDRIDP/BAR /GOU/UN-Rd/01 | (a) Improvement of Road from Sarikal GC to Shaheber char Bazar via Nalchira Bazar ch. 5555m-7055m), (b) Construction of 2 nos U-drain at ch.599m & 6555m on the same road Under Gournadi Upazila, District-Barisal. | 506323013 | 1.500km | 9785485 |  | 10357650.8 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 0%
3 | Gournadi | U-drain | BDRIDP/BAR /GOU/UZ-Rd/01 | (a) Improvement of Road from Gournadi Bandar GC to Muladi GC via Kutubpur Bazar at ch. 0m-630m), (b) Construction of 2 nos U-drain at ch. 205m & 364m on the same road Under Gournadi Upazila, District-Barisal. | 506322016 | 0.630km | 5122695 |  | 5399315 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 0%
4 | Gournadi | BC | BDRIDP/BAR /GOU/UZ-Rd/02 | Improvement of illah (NHW) to Kalkini Upazila HQ via Tulatala Bazar at ch.2413m-3213m), Under Gournadi Upazila, District-Barisal. | 506322013 | 0.800km | 4643337 |  | 4898705 | M/S Sadman Builders | 2014-09-11 | 16/11/14 | 15/05/15 |  | 0%
5 | Gournadi | U-drain | BDRIDP/BAR /GOU/UN-Rd/02 | (a) Improvement of Batazore GC to Pinglakathi Bazar via Pachim Chandrahar GPS at ch. 0m-1000m), (b)Construction of 1 nos U-drain at at ch.14m on the same road, (c) Construction 1v-2.3mx2.30m RCC Box Culvert at ch.527m & 1583m on the same road Under Gournadi Upazila, District-Barisal. | 506323001 | 1.00km | 7805159 |  | 8236744 | M/S Islam Brothers | 16/11/14 | 23/11/14 | 23/05/15 |  | 0%
6 | Gournadi | HBB | BDRIDP/BAR/GOR/CCA-Rd/01 | Improvement of road from Maddam Hosnabad Nabarun RPS to Nezamuddin College by HBB at Ch.481-1492m (Nizamuddin Degree College road from freedom fighter Nizamuddin Shaheber Kaborstan via Madha hosnabad UP Member Md.Matiur Rahman Sarif Bari Bridge under Gouranadi upazila, Barisal District. | 506324040 | 1.01km | 2839204 |  | 2601109.88 | Md. Sirazul Islam Hanif | 20/11/14 | 27/11/14 | 27/04/15 |  | 0%
6 | Sub-Total: | [5 empty] | 31740177 |  | 32758303.7
1 | Agailjhara | BC | BDRIDP/BAR /AGL/CCA-Rd/01 | Improvement of Road by BC from Rathkhola Bazar-Bhadrapara Road (ch. 0m-1000m) Under Agailjhara Upazila, District-Barisal. | 506024008 | 1.00km | 5097636 |  | 5599756.34 | M/S Talukder Enterprise | 23/10/14 | 30/10/14 | 30/04/15 |  | 15%
2 | Agailjhara | BC | BDRIDP/BAR/AGL/CCA-Rd/02 | Improvement of Road from Seral-Goila road viaShahid Serniabad House- Tamer Jame Mosjid (Tamer Girls High School - Seral Community Center by BC From Ch. 0.0m-975m under Agailjhara Upazila,Barisal. | 506025048 | 0.975km | 5527014 |  | 4583839 | M/S Mitushi Traders | 27/11/14 | 2014-08-12 | 2015-04-06 |  | 0%
3 | Agailjhara | BC | BDRIDP/BAR/AGL/CCA-Rd(R)/06 | Rehabilitation of road from Temar Bastala to Hawla bridge via Nagar GPS-Talbazar-Oichermath bazar road by BC from Ch. 3840m-4840m with 3 Nos U-Drain at Ch. 4410m, 4590m & 4740m. | 506025056 | 1.00km | 4914057 | 196459 | [10 empty] | E-Tender under Process
4 | Agailjhara | Box Culvert | BDRIDP/BAR/AGL/CCA-St/01 | Construction of road from 2 vent ×4.00m×4.00m RCC Box Culvert on Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road at Ch. 841m with Dranage Culvert at Ch. 930m. | 506025058 | 4.00m | 1677674 | [11 empty] | E-Tender under Process
5 | Agailjhara | BC | BDRIDP/BAR/AGL/UN-Rd(R)/01 | Rehabilitation of road from Goila (DR) to Teimukhi via Bakal hat & Kodaldhoa bazar road by BC form Ch. 11192m-13954m. | 506023001 | 2.762km | 14739342 | 791797 | [10 empty] | E-Tender under Process
6 | Agailjhara | BC | BDRIDP/BAR/AGL/UZ-Rd/02 | Improvement of road from Paisharhat GC to Shatla GC via Bagdha GC road by BC from Ch. 3800m-5800m. | 506022003 | 2.00km | 10771206 | [11 empty] | E-Tender under Process
7 | Agailjhara | BC | BDRIDP/BAR/AGL/CCA-Rd/03 | Improvement of road from Boro Magra Sluice to Ramshil Bazar via Kodaldhoa road by BC from Ch. 0.00m-1000m with on Boromagra Stuice to Ramshil Bazar via Dodaldhoa road from Ch. 280m | 506024034 | 1.00km | 6017149 | [11 empty] | E-Tender under Process
8 | Agailjhara | BC | BDRIDP/BAR/AGL/CCA-Rd/04 | Improvement of road from Poiser hat GC-Ramshil Bazar via Trimukhi road by BC from Ch. 0.00m-1000m. | 506024040 | 1.00km | 4926273 | [11 empty] | E-Tender under Process
9 | Agailjhara | HBB | BDRIDP/BAR/AGL/CCA-Rd(R)/05 | Rehabilitation of road from Ashkor Puraton Kalibari Baily Bridge to Kishore Bissas's house road from Ch. 0.00m-1200m. | 506025058 | 1.200km | 4159274 | 288401 | [10 empty] | E-Tender under Process
9 | Sub-Total: | [5 empty] | 57829625 | 1276657 | 10183595.34
1 | Babugonj | BC | BDRIDP/BAR/BABU/CCA-Rd/01 | Improvement of road from Babugonj Agorpur GC to Mr. Younusur Rahman (Divisional Commissioner) house via Clubgonj hat by Carpeting from Ch. 750-1400m & 0.00-1550m. | 506034025 | 2.20km | 9792326 |  | 10750396.05 | M/S Lutful Kobir | 2014-10-07 | 17/07/14 | 16/04/15 |  | 0%
2 | Babugonj | BC | BDRIDP/BAR/BAB/CCA-Rd(R)/02 | Rehabilitation of road Shajahan Sikder Farm to Najam Mridha House via idel Kathi High School by Carpeting under dehergothi UP at Ch 00-2+350km. | 506035070 | 2.350km | 9718891 | 421856 | [10 empty] | E-Tender under Process
3 | Babugonj | BC | BDRIDP/BAR/BAB/CCA-Rd(R)/03 | Rehabilitation of road Dehergothi in High School-Rahamotpur Krishi College via Khalik member's house by Carpeting under Dehergoti UP at Ch. 00m-4+320km | 506034095 | 4.320km | 18518441 | 1035938 | [10 empty] | E-Tender under Process
4 | Babugonj | BC | BDRIDP/BAR/BABU/CCA-Rd/04 | Improvement of road Jayinpur Madrasha to Dhaka Barisal RHD via Molla Bari by Carpeting under dehergoti UP at Ch. 00-2+600km. | 506035006 | 2.600km | 9959477 | [11 empty] | E-Tender under Process
5 | Babugonj | RCC Box Culvert | BDRIDP/BAR/BAB/CCA-St/01 | Construction of 4Nos RCC Box Culvert on road Shajahan Sikder Farm to Najam Mridha House via Idel Kathi High School Under Dehergothi UP at Ch 248m, 715m, 1414m & 1543m. | 506035070 |  | 2931768 | 184122 | [10 empty] | E-Tender under Process
6 | Babugonj | RCC Box Culvert | BDRIDP/BAR/BAB/CCA-St/02 | Construction of 11Nos RCC Box Culvert on road from Dehergothi in High school-Rahamotpur Krishi College via Khalik member's house under Dehergothi UP at Ch. 797m, 1455m, 1602m, 1875m, 1965m, 2362m, 2535m, 2655m, 4140m & Link road 2250m & 380m. | 506034095 |  | 4744358 | 199349 | [10 empty] | E-Tender under Process
7 | Babugonj | RCC Box Culvert | BDRIDP/BAR/BAB/CCA-St/03 | Construction of 5Nos RCC Box Culvert on road Jayipuri Madrasha to Dhaka Barisal RHD via Molla Bari Under Dehergothi UP at Ch. 1135m, 1612m, 2272m, 2375m, 2540m. | 506035006 |  | 2001016 | 62866 | [10 empty] | E-Tender under Process
8 | Babugonj | RCC Box Culvert | BDRIDP/BAR/BAB/CCA-St/04 | Construction of 3.00m×3.00m 3 Nos 1.00m×1.00m 1Nos 2.00m×2.00m RCC Box Culvert on Daroger hat to Shandha river bank via Battala Bazar road at Ch. 33m, 2820m, 2980m, 3155m & 1785m. | 506034024 |  | 1982458 | 150637 | [10 empty] | E-Tender under Process
9 | Babugonj | RCC Box Culvert | BDRIDP/BAR/BAB/UN-St/01 | Construction of 2 Nos 2.00×2.00m 1 No 1.60m×1.60m 1No 1.00m×1.00m RCC Box Culvert on Dehergothi UP office to Kalir Bazar road at Ch. 2475m, 2693m, 2860m & 3035m. | 506033006 |  | 1443386 | 41933 | [10 empty] | E-Tender under Process
10 | Babugonj | BC | BDRIDP/BAR/BAB/UN-Rd(R)/01 | Rehabilitation of road from Dehergothi UP office to Kalir Bazar by BC from Ch. 1930m-3710m. | 506033006 | 1.780km | 6457205 | 2442317 | [10 empty] | E-Tender under Process
10 | Sub-Total: | [5 empty] | 67549326 | 4539018 | 10750396.05
1 | Mehendigonj | BC | BDRIDP/BAR/MHN/UZR(R)-Rd/01 | Rehabilitation of Patherhat GC - Kazirhat GC Road by BC at Ch.1500 - 2610m Under Mehendigonj Upazila, District-Barisal. | 506622005 | 1.11km | 3853739 |  | 4973018 | M/S Santu Traders | 20/11/14 | 27/11/14 | 27/04/15 |  | 0%
2 | Mehendigonj | BC | BDRIDP/BAR/MHN/CCA-Rd/01 | Improvement of Mothertoli Bazar - Uttarchar road via Charekkaria road by BC (Ch.2170-3220m, Road Under Mehendigonj Upazila, District-Barisal. | 506625079 | 1.05km | 5327472 |  | 4515030 | M/S Nahid Enterprise | 16/11/14 | 23/11/14 | 23/04/15 |  | 15%
3 | Mehendigonj | Box Culvert | BDRIDP/BAR/MHN/CCA-St/01 | Construction of 1.0 x 1.0m RCC Box culvert at Ch.3042 on Mothertoli Bazar - Uttarchar road via Charekkaria UP road Under Mehendigonj Upazila, District-Barisal. | 506625079 | 1.00m | 222783 |  | 184788 | M/S Hasib Enterprise | 2014-09-11 | 16/11/14 | 15/03/15 |  | 50%
3 | Sub-Total: | [5 empty] | 9403994 | 0 | 9672836
1 | Hizla | BC | BDRIDP/BAR/HZL/UZ-Rd(R)/01 | Rehabilitation of road from of Dhanusikder Hat-Muladi Upazila road by BC from Ch. 0.00m-1000m. | 506362009 | 1.00km | 7094634 | 1476772 | [10 empty] | E-Tender under Process
1 | Sub-Total: | [5 empty] | 7094634 | 1476772 | 0
53 | Grand Total: | [5 empty] | 307217017 | 10248260 | 125698344.77 | [6 empty] | 0
Accountant |  |  | Sub-Assistant Engineer |  |  | Assistant Engineer |  |  |  |  | Senior Assistant Engineer |  |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal |  |  | LGED, Barisal |  |  |  |  | LGED, Barisal |  |  |  |  | LGED, Barisal

## Sheet2
SCHEME STATUS REPORT
Project Title: Barisal Division Rural Infrastructure Development Project.
Repoting Month: June/2014.
SL. No. | Name of Project (Name of Development Assistant/Partoner) | RADP Fund (GOB+RPA) | No of Schemes/Contracts |  |  | Target |  | Activities | [5 empty] | Phtsical Progress (%) | Total Fund Spent (GOB+RPA) | Remarks
|  |  | New Schemes/Contracts | Carried over Contracts/Excess of Previous year (No) | Total (No) | Last Date for Award | Last Date of works Commencement | Schemes Prepared (No) | Schemes Preparation Under (No) | Tender Called (No) | Tender Evaluation Under | Works going on (No) | Schemes Completed (No)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
56 | Barisal Division Rural Infrastructure Development | 200.00 (160+40) | 19/2 | 0/0 | 19 | 2014-11-06 | 18/06/14 | 43 | 0 | 9 | 7 | 12 | 0 | 15% | 300000 | 10 Nos E/W Scheme going on by LCS.
300000

## Progress (6)
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project
District: Barisal | [18 empty] | Reporting Month: April/19
Sl No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity | [5 empty] | Approved Estimated Cost (Tk) | Salvage Materials | Contract Amount (Tk) | Name of Contractor/LCS Chairman | Contract date | Commencement Date | Completion Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [9 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | BDRIDP/BAR/SDR/UN-St/01 | Construction of 20.00m Long RCC Girder Bridge on Nishatala Tunglbaria UP office-Shaheberhat via Bisharad road at Ch. 136m. | 506513002 | [5 empty] | 20 | 12772854 |  | 10088368.67 | M/S Rupali Construction | 2015-11-03 | 17/03/15 | 17/03/16 |  | 100% | 8800000 | 87.23% |  | 10088368.67
2 | BDRIDP/BAR/MUL/UN-St/02 | Construction of 20.00m long RCC Girder Bridge on Boropatherchar GPS at Ch. 0+650km Over Uttar Dakathia khal under Muladi Upazila, Barisal District. | 506693005 | [5 empty] | 20 | 14312698.5 |  | 12881428.65 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 100% | 11600000 | 90.05%
3 | BDRIDP/BAR/MUL/UZ-St/03 | Construction of 20.00m long RCC Girder Bridge on Mirdhar hat GC-Nazirpur GC at Ch. 4+500km Over Charkalekhan khal under Muladi Upazila, Barisal District. | 506692004 | [5 empty] | 20 | 17924056.31 |  | 16131650.67 | PTSL-MOTREE (PVT) LTD | 2017-09-08 | 16/08/17 | 15/08/18 |  | 100% | 15200000 | 94.22%
4 | BDRIDP/BAR/MUL/UN-St/01 | Construction of 21.00m long RCC Girder Bridge on Boropatherchar GPS at Ch.0900km over Uttar Char Dakatia Khal under Muladi Upazila Barisal District. | 506693005 | [5 empty] | 21 | 15795569.51 |  | 14216012.55 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 97% | 12950000 | 91.09%
5 | BDRIDP/BAR/MUL/UZ-St/02 | Construction of 45.00m long RCC Girder Bridge on Mirdhar hat GC-Harinathpur GC - Muladi Border at Ch.3+596km. Over Char Dumuritala khal under Muladi Upazila,Barisal District. | 506692002 | [5 empty] | 45 | 24434851.86 |  | 21991136.67 | M/S Islam Brothers | 30/07/17 | 2017-07-08 | 2018-06-08 |  | 75% | 15636746 | 71.1%
6 | BDRIDP/BAR/MUL/UZ-St/04 | Construction of 25.00m long PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at ch.8380km over Banimardhan khal under Muladi Upazila Barisal. | 506692004 | [5 empty] | 25 | 23503677 |  | 21153309.3 | Orien Trading & Builders | 2017-03-08 | 2017-10-08 | 2018-10-08 |  | 95% | 19900000 | 94.08%
7 | BDRIDP/BAR/MUL/UZ-St/05 | Construction of 30.00m PC Girder Bridge on Mirdhar Hat GC-Nazirpur GC at Ch.7620km over Banimardhan Khal under Muladi UpazilaDistrict-Barisal | 506692004 | [5 empty] | 30 | 21022197.08 |  | 18919977.37 | M/S Amir Engineering Corporation and M.M Builders & Engineers | 2018-04-02 | 2018-11-02 | 2018-11-12 |  | 96% | 17900000 | 94.61%
8 | BDRIDP/BAR/BAK/UZ-St/01 | Construction of 23.00m Long RCC Girder Bridge over road from Kamarkali GC to Baharchar GC via Sarsi Pollice Farry Patkati L/G Faridpur UP Office & Janota Bajarat at Ch. 5847m Under Bakerganj Upazila District Barisal Road ID 506072012 | [6 empty] | 23 | 13048406.72 |  | 12395986.384 | M/S SUN TRADERS | 23/08/18 | 30/08/18 | 2019-04-08 |  | 92% | 11150000 | 89.95%
9 | BDRIDP/BAR/GOR/UZ-ST/01 | Construction of 30.00m PSC Girder Bridge on Barti Bazar to Gournadi GC at Ch.5000km over Anandhapur Khal under Gournadi UpazilaDistrict-Barisal | 506322005 | [5 empty] | 30 | 24934266.46 |  | 27173350.5 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 97% | 26212000 | 96.46%
10 | BDRIDP/BAR/GOR/UZ-ST/02 | Construction of 32.00m PSC Girder Bridge on Barti BazarNHW to Gournadi GC via Torky GC at Ch.9340km over Kashba Khal under Gournadi Upazila District-Barisal | 506322005 | [5 empty] | 32 | 24196878.89 |  | 26369588.63 | M/S Kohinoor Enterprise | 2018-11-03 | 18/03/18 | 18/03/19 |  | 85% | 21300000 | 80.77%
11 | BDRIDP/BAR/BAN/UZ-St/01 | Construction of 1No.2.0m x 2.0m,1 No.3.0m x 3.0m, 2Nos.4.0m x 4.0m, 1No.1.0m x 1.0m RCC Box Culvert & 3 Nos 0.625m x 0.625m U-Drain at Ch.5950m, 6787m, 6145m, 6230m, 6407m, 5871m, 6555m & 6622m on Banaripara-Harta Road. | 506102003 | 0 | 0 | 0 | 0 | 0 | 11 | 7531517 | 7531517 | 5461652.5 | M/S Soma Enterprise | 25/01/17 | 2017-02-02 | 2017-02-10 |  | 100% | 5200000 | 95.21%
12 | BDRIDP/BAR/BAN/UZ-St/02 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.8642km over B.Bari Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 11850164.61 |  | 10665148 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 90% | 9450000 | 88.61%
13 | BDRIDP/BAR/BAN/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Banaripara to Harta road at ch.7162 km over Onil Ghat Khal under Banaripara UpazilaBarisal District | 506102003 | [5 empty] | 15 | 9814374 |  | 8832936 | Md Mahfuz Khan | 28/09/17 | 2017-05-10 | 2018-05-07 |  | 70% | 6035000 | 68.32%
[10 empty] | 221141511.94 | 7531517 | 206280545.894 | [6 empty] | 181333746 |  |  | #VALUE!
Accountant |  |  | Sub-Assistant Engineer | [5 empty] | Assistant Engineer |  |  |  | Senior Assistant Engineer |  |  |  | Executive Engineer
LGED, Barisal |  |  | LGED, Barisal | [5 empty] | LGED, Barisal |  |  |  | LGED, Barisal |  |  |  | LGED, Barisal
0