## Bhola
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project (BDRIDP)
District: Bhola
[14 empty] | Repoting Date : 31-12-2020 |  |  |  |  | 2020-12-04
SL No | Package No | Scheme Name with Location (Ch to Ch) | Road ID | Effective Quantity |  |  |  |  | Approved Estimated Cost (Tk) | Contract Amount (Tk) | Name of Contractor | Contract date | Commencement Date | Comple Date as per Contract | Actual Completion date | Phy. Prog. (%) | Financial Progress |  | Fund Requried | Remarks | Upazila
|  |  |  | E/W (m3) | BC (Km) | Bridge/Culvert (m) | RCC (Km) | Rehab (Km) | [8 empty] | Amount Spent (Tk) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila -Bhola Sadar (Road Work)
1 | BDRIDP/Bho/Sdr/CCA-Rd/01 | Improvement of road from Bhola Ilisha Bottola- Kalurhat – Nuton (Nadermiar hat) Porangonj road Ch: 00-1000m under Sadar upazila. | 509184073 |  | 1 |  |  |  | 5256034 | 5256034 | Md.Zakir Hossin | 11.05.14 | 18.05.14 | 10.08.14 | 17/15/14 | 100% | 5256034 | 100% |  | FBP | Bhola-S | 0
2 | BDRIDP/Bho/Sdr/Un-Rd/01 | Improvement of road from Pachim Elisha- Malerhat road Ch: 8200-9000m under Sadar upazila. | 509183012 |  | 0.8 |  |  |  | 4996230 | 4993002 | M/s Mahir & Munem | 27.08.14 | 06.09.14 | 26.12.14 | 20/01/15 | 100% | 4991165 | 99.96% |  | FBP | Bhola-S | 1837
3 | BDRIDP/Bho/ SDR/UZ-Rd(R)/03 | Rehabilitation Bangla Bazar-Bagmara-Sharif Khar hat-Velumia-Banker hat Road by BC from ch.2400-4300m. (ID. 509182011). under Bhola Sadar | 509182011 |  | 0 |  |  | 1.9 | 6192063 | 6151913 | M/s Ma Enterprise | 14.08.14 | 27.08.14 | 28.12.14 | 20/2/15 | 100% | 6145694 | 99.9% |  | FBP | Bhola-S | 6219
4 | BDRIDP/Bho/ SDR/UZ-Rd(R)/05 | Rehabilitation of Bhola-Gazaria GC road (Link= Chowmatha-Char Kumary RNGPS- Reba Rahman College-RHD) Road by BC from Ch.00-2500m. (ID No.509182015) under Bhola Sadar Upazila. | 509182015 |  | 0 |  |  | 2.5 | 4442625 | 4422590 | M/s Ma Enterprise | 14.08.14 | 28.08.14 | 28.12.14 | 2016-10-02 | 100% | 4403688 | 99.57% |  | FBP | Bhola-S | 18902
5 | BDRIDP/Bho/ SDR/CCA-Rd/05 | Improvement of Shere Bangla Bazar-Charkali-Luzar hat road by BC from Ch. 0.00-700m (ID No.509185144) under Bhola Sadar | 509185144 |  | 0.7 |  |  |  | 3139853 | 3139682 | M/s Priyonity Construction | 14.04.14 | 27.04.14 | 11.12.14 | 25/11/15 | 100% | 3135447 | 99.87% |  | FBP | Bhola-S | 4235
6 | BDRIDP/Bho/SDR/Uz-Rd(R)/01 | Rehabilitation of RHD Junction (Chader Matha)-Wapda Closer bazar road by BC from Ch.00-3000m. under Bhola Sadar | 509182008 |  | 0 |  |  | 3 | 8171771 | 8171771 | M/s Telmi Interprise | 06.07.14 | 13.07.14 | 06.01.15 | 20/2/15 | 100% | 8011184 | 100% |  | FBP | Bhola-S | 160587
7 | BDRIDP/Bho/ SDR/UZ-Rd(R)/04 | Rehabilitation of RHD Junction (Chader Matha)-Wapda Closer bazar road by BC from Ch.3000-6000m. (ID No.509182008) under Bhola Sadar | 509182008 |  | 0 |  |  | 3 | 7548390 | 7548357 | M/s Mollick Enterprise | 28.12.14 | 04.11.15 | 27.12.15 | 2015-12-03 | 100% | 7333137 | 100% |  | FBP | Bhola-S | 215220
8 | BDRIDP/Bho/ SDR/CCA-Rd(R)/06 | Rehabilitation of Bhola Kheyaghat-Santir hat-Bagmara road by BC from Ch. 00-1200m (ID No.509184070) under Bhola Sadar | 509184070 |  | 0 |  |  | 1.2 | 2525944 | 2525677 | M/s Priyonity Construction | 14.08.14 | 14.08.14 | 11.12.14 | 22/3/15 | 100% | 2525677 | 100% |  | FBP | Bhola-S | 0
9 | BDRIDP/Bho/SDR/CCA-Rd/03 | Improvement of Char Mohammad Ali GPS CUM- Cyclone Shelter Connecting approach road (Closser Bazar Barry Bandh-Char Mohammad Ali GPS) by BC Paved at Ch. 0.00-2000m (5096). Under Sadar | 509185096 |  | 2 |  |  |  | 8956626 | 8593921 | Md Julfiker Ahamed | 30.9.15 | 30.9.15 | 29.9.16 | 18/2/16 | 100% | 8588131 | 100% |  | FBP | Bhola-S | 5790
10 | BDRIDP/Bho/ SDR/CCA-Rd/04 | Rehabilitation of Charkali-Luzarhat-Natun Hat-Nazimazir Kheyaghat road by BC at Ch. 0.00-4330m (ID No. 509184049) under Bhola Sadar | 509184049 |  | 4.43 |  |  |  | 11624958 | 11648452 | M/S Rubel Enterprise | 25.07.14 | 25.07.14 | 10.12.14 | 2014-10-11 | 100% | 11634795 | 99.88% |  | FBP | Bhola-S | 13657
11 | BDRIDP/Bho/ SDR/CCA-Rd/07 | Improvement of road form khayerhat karalia GPS alam Bazar MP Tafael Ahamed Bari road by BC Paved at Ch. 0.00-2000m (ID No.509185406). Under Sadar Upazila. | 509185406 |  | 2 |  |  |  | 8832467 | 8832216 | M/s Saymen Enterprise | 10.12.14 | 10.12.14 | 10.06.15 | 20/3/15 | 100% | 8819716 | 99.86% |  | FBP | Bhola-S | 12500
12 | BDRIDP/Bho/ SDR/UZ-Rd(R)/05 | Rehabilitation of R&H Junction to Closer Bazar Road by BC from Ch.6000-7500m. (ID 509182008) Under Sadar Upazila. | 509182008 |  | 1.5 |  |  | 1 | 3360362 | 3358681 | M/s Mahir & Munam B.T | 24.02.15 | 24.02.15 | 23.10.15 | 27/4/15 | 100% | 3358681 | 100% |  | FBP | Bhola-S | 0
13 | BDRIDP/Bho/ SDR/UZ-Rd(R)/08 | Rehabilitation of Roar from Bhola-Charfession RHD-Kamaruddin -Rarir hat-Battala Bazar road by BC from Ch (1654m-2930m )and (3222m-3800m) under bhola sadar Upazila (ID no. 509182030). | 509182030 |  | 1.854 |  |  |  | 4837912 | 4837912 | M/s Hider Bulders | 23.12.14 | 23.12.14 | 23.06.15 | 20/2/15 | 100% | 4834452 | 99.93% |  | FBP | Bhola-S | 3460
14 | BDRIDP/Bho/ SDR/UZ-Rd(R)/02 | Rehabilitation of Bhola Gazaria GC Roar from Ch. 3500-4500m under bhola sadar Upazila (ID no. 509182015). | 509182015 |  | 0 |  |  | 1 | 3538144 | 3536345 | M/s Siddeque Trade International | 27.8.14 | 27.8.14 | 26.01.15 | 2015-01-03 | 100% | 3530197 | 99.83% |  | FBP | Bhola-S | 6148
15 | BDRIDP/Bho/ SDR/CCA-Rd/08 | Imp. Of road from Sadur Char Jungaliahat munshirhat khayaghat Pacca Brick filed road Brick filed road at Ch. 00-1000m ID 509185154 | 509185154 |  | 1 |  |  |  | 4693575 | 5113997 | M/s Nazimuddin Traders | 24.12.14 | 24.12.14 | 23.06.15 | 2015-08-06 | 100% | 4856532 | 100% |  | FBP | Bhola-S | 257465
16 | BDRIDP/Bho/ SDR/UZ-Rd(R)/07 | Rehabilitation of RHD Junction (Chader Matha)-Wapda Closer bazar road by BC from 7500-8500m. (ID No.509182008) under Kola Sadar Upazila. | 509182008 |  | 1 |  |  |  | 3522362 | 3522337 | M/s Five Star | 28.12.14 | 28.12.14 | 28.6.15 | 25/3/15 | 100% | 3517152 | 100% |  | FBP | Bhola-S | 5185
17 | BDRIDP/BHO/SDR/CCA-Rd/16 | Improvement of Road from Beduria Baro Tarik bazar Farazi Bari Mosque-Shere-Bangla Bazar Road by Bc from Ch.00.00-1350m ( ID No 509185159) | 509185159 |  | 1.35 |  |  |  | 5914829 | 4975497 | M/s Nazemuddin | 22.4.15 | 22.4.15 | 22.10.15 | 20/3/16 | 100% | 4965397 | 99.8% |  | FBP | Bhola-S | 10100
18 | BDRIDP/BHO/SDR/UZ-Rd(R)/09 | Rehabilitation of road from Bhola Khaya ghat -kalinath Ray Bazar Darger road by pass-pondiler pol-Gazaria GC from ch. 8350m-9800m (ID No/ 509182010) | 509182010 |  | 0 |  |  | 1.35 | 6625260 | 6619600 | Md. Rahul Amin | 25.03.15 | 25.03.15 | 29.09.15 | 20/4/15 | 100% | 6227628 | 100% |  | FBP | Bhola-S | 391972
19 | BDRIDP/BHO/SDR/CCA-Rd(R)/10 | Rehabilitation of road from Gazipur road-Mannan Talukder bari to PArhat road at Ch. 00-1700m n(ID No. 50918414) | 50918414 |  | 0 |  |  | 1.7 | 4863602 | 4859028 | Md. Jamaluddin Golder | 31.03.15 | 31.03.15 | 30.09.15 | 2015-10-06 | 100% | 4859028 | 100% |  | FBP | Bhola-S | 0
20 | BDRIDP/BHO/SDR/CCA-Rd(R)/02 | Improvement of Bhola Charfession RHD ( Ilisha Bazar) Madda Ilisha RNGPS cum Cyclone Shelter connectiong road at Ch. 00-1000m (ID No. 509185097) | 509185097 |  | 1 |  |  |  | 5845270 | 5841615 | M/s Subo Construction | 27.08.14 | 27.08.14 | 27.12.14 | 20/5/15 | 100% | 5840883 | 99.99% |  | FBP | Bhola-S | 732
21 | BDRIDP/BHO/SDR/CCA-Rd/11 | Improvement of road from Hazir Hat Porir Hat road By BC from Ch. 900-1900m (ID No. 509184062) | 509184062 |  | 1 |  |  |  | 4754619 | 4754707 | Md Bahalul Karim | 31.03.15 | 31.03.15 | 10.10.15 | 2016-10-01 | 100% | 4744606 | 99.79% |  | FBP | Bhola-S | 10101
22 | BDRIDP/BHO/SDR/CCA-Rd(R)/17 | Rehabilitation of Road from Beduria Baro tarik Bazar-Charkali GPS (Connecting Cold Stores) road By BC from Ch. 00-1200m (ID No 509185179) | 509185179 |  |  |  |  | 1.2 | 3318977 | 2886633 | M/s. Nazim Uddin Traders | 22.08.15 | 22.08.15 | 21.10.16 | 21/1/16 | 100% | 2878297 | 99.71% |  | FBP | Bhola-S | 8336
23 | BDRIDP/BHO/SDR/CCA-Rd(R)/14 | Rehabilitation of Road from Charnoabad Chomohine by pass Auto Brick filed Santer hat road By BC from Ch. 00-3700m (ID No 509184041 | 509184041 |  |  |  |  | 3.7 | 6840361 | 6830100 | M/s Prince Enterprise | 15.4.15 | 15.4.15 | 15.08.15 | 27/10/15 | 100% | 6819640 | 99.85% |  | FBP | Bhola-S | 10460
24 | BDRIDP/BHO/SDR/CCA-Rd(R)/15 | Rehabilitation of road from Shibpur UP (Ratar Pur Bazar)-Munceb Bari- Charpata UP Connecting road By BC from Ch,00-3200m. (ID No. 509184066) under Sadar Upazila. | 509184066 |  |  |  |  | 3.2 | 6036422 | 6024349 | Md. Akter Hossain | 15.04.15 | 15.04.15 | 15.07.15 | 30/3/15 | 100% | 6019128 | 99.91% |  | FBP | Bhola-S
25 | BDRIDP/BHO/SDR/UN--Rd(R)/02 | Rehabilitation of road from Poshim Elisha Up Maler hat road Ch. 2900-5000m Under Bhola Sadar. | 509183012 |  |  |  |  | 2.1 | 4528307 | 4526602 | M/s Siddiki Enterprise | 27.8.14 | 27.8.14 | 27.02.15 | 2015-07-06 | 100% | 4165108 | 100% |  | FBP | Bhola-S
26 | BDRIDP/BHO/SDR/CCA-Rd/18 | Improvement of Rashid Khan shop-Dakkin Koralia Dakil Madrasha via Shah Shikder Bari Road at ch. 00-1650m(ID No.509185169) under Sadar Upazila. | 509185169 |  | 1.65 |  |  |  | 6123354 | 6111107 | M/s Pronty Construction | 21.4.15 | 21.4.15 | 21.7.15 | 20/7/15 | 100% | 6111107 | 100% |  | FBP | Bhola-S
27 | BDRIDP/BHO/SDR/UZ-Rd(R)/10 | Rehabilitation of road from Bhola Khaya ghat - kalinath Ray Bazar Darger road by pass - pondiier pol-Gazaria GC By BC from Ch. 5000-7000m. (ID No.509182010) under Sadar Upazila. | 509182010 |  | 0 |  |  | 2 | 7844323 | 7832556 | Md. Iqbal Hossain | 15.04.15 | 15.04.15 | 14.07.15 | 25/10/15 | 100% | 7827393 | 99.93% |  | FBP | Bhola-S
28 | BDRIDP/BHO/SDR/CCA-Rd(R)/20 | Improvement of Malerhat-Joinal Member House-Mukti camp road, Ch: 00-2000m (ID No.509185143) under Sadar Upazila. | 509185143 |  | 2 |  |  |  | 5070609 | 5057932 | M/s Drim construction | 07.04.15 | 07.04.15 | 07.07.15 | 15/7/15 | 100% | 5052418 | 99.89% |  | FBP | Bhola-S
29 | BDRIDP/Bho/SDR/CCA-D(R)/13 | Improvement of road form Bhola-lllisha RHD Battala Kalur hat(nader miar hat) Parangonj road By BC from Ch.1000- 2375m (ID No.509184073 [Sadar] | 509184073 |  | 1.375 |  |  |  | 6070283 | 6066680 | Md. Jakir Hossain | 22.7.15 | 22.7.15 | 22.7.16 | 2015-07-11 | 100% | 5957932 | 100% |  | FBP | Bhola-S
30 | BDRIDP/BHO/SDR/CCA-Rd/12 | Improvement of road from Dosh Khali Bridge-Char Hossain- Chandra Proshad Jonal Bapari Shop (Mir Bazar) Bisso road by BC from Ch. 00-1500m (ID No. 509185061) [Sadar] | 509185061 |  | 1.5 |  |  |  | 7541633 | 7538447 | M/s Samata Enterprise | 23.7.15 | 23.7.15 | 22.7.16 | 16/2/17 | 100% | 7525947 | 99.83% |  | FBP | Bhola-S
31 | BDRIDP/Bho/SDR/CCA-Rd/19 | Improvement of road from RHD Bapari Bazar-Charpata road (South Ratanpur GPS-Miji Bari- Taltali Bazar road) By Earth work from Ch.00-1450m (ID No.509185082) [Sadar] | 509185082 |  | 1.45 |  |  |  | 4956088 | 4950067 | Md. Jakir Hossain | 22.7.15 | 22.7.15 | 22.7.16 | 25/9/15 | 100% | 4923367 | 100% |  | FBP | Bhola-S
32 | BDRIDP/BHO/SDR/CCA-Rd/21 | Improvement of Road from Charkali-Luzarhat-Natun Hat-Nazir Mazi Kheya Ghat (Dakhakin Pascim Madrasa-Maksud matabbar bari) Road By BC from Ch(.4330-5690m) (ID No4049) Under Sadar | 5091854049 |  | 1.24 |  |  |  | 5722088 | 5602339 | Md. Jakir Hossain | 8.9.15 | 8.9.15 | 8.9.16 | 25/6/16 | 100% | 5601339 | 99.98% |  | FBP | Bhola-S
33 | BDRIDP/Bho/SDR/UZ-Rd(R)-11 | Rehabilitation of road from illisha Colghat-kabiraj bari-Piar khan -Bapta UP-RHD road by BC from Ch. 1000-3400m(ID No-509182014) Under Sadar Upazila. | 509182014 |  | 2.4 |  |  |  | 5909031 | 5905685 | Md. Jakir Hossain | 8.9.15 | 8.9.15 | 8.9.16 | 25/10/15 | 100% | 5842711 | 100% |  | FBP | Bhola-S
34 | BDRIDP/Bho/SDR/CCA-RD-22 | Rehabilitation of Alinagar Taicknago Thmatha-Ponditer Poll Bazar Road-Nekunger Poll Road. Ch. 1000-1740m Construction of 1.50m x1.50m RCC Box culvert & 1 No U-Drain on Alinagar Taicknago Thmatha-Ponditer Poll Bazar Road-Nekunger Poll Road U-Drain at Ch. 366m , 800m 1366m & 470m 509185131 Under Sadar Upazila. | 509185131 |  | 1.74 |  |  |  | 11884351 | 11878384 | Md. Sha Alam | 2.5.17 | 5.7.17 | 4.7.18 | 2018-09-03 | 100% | 11863012 | 99.87% |  | FBP | Bhola-S
35 | BDRIDP/BHO/SDR/CCA-Rd-09 | a Resectioning of Birserreshto Mostafa Kamal Bari-Gazaria GC Cannectiong Road.ID No. 509184082b Improvement of Birserreshto Mostafa Kamal Bari-Gazaria GC Cannectiong Road from Ch. 1000m-1740m. ID No. 509184082c Construction of 1 Nos. 1.50m x 1.50m RCC Box Culvert 2 Nos U-Drain on Birserreshto Mostafa Kamal Bari-Gazaria GC Cannectiong road at Ch. 1242m 1110 & 1738m.ID No. 509184082 | 509184082 |  | 0.74 |  |  |  | 5265625 | 5265525 | M/s Ruble Enterprise | 30.7.17 | 29.4.18 | 25.3.18 | 25/3/18 | 100% | 5257865 | 99.85% |  | FBP | Bhola-S
36 | BDRIDP/Bho/SDR/CCA-rd/23 | Improvement of Purbo Ilisha RHD Jonson -Char Annanda School Bareque Member Bari Road from ch 00-858.00 ID 509185184 bConstruction of 1 No 1.5mx1.5m RCC Box Culvert 4 nos U-Drain on Improvement of Purbo Ilisha RHD Jonson -Char Annanda School Bareque Member Bari Road at Ch. 215m, 183m, 318m, 380m & 436m. [Sadar] | 509185184 |  | 0.858 |  |  |  | 6288953 | 6287778 | M/s Howlader Construction | 2018-11-02 | 10.2.18 | 10.11.18 | 30/5/18 | 100% | 6281406 | 99.9% |  | FBP | Bhola-S
37 | BDRIDP/Bho/SDR/CCA-RDS/24 | Construction Of RCC Road from Komoruddin-Rarir hat joynal abedin joy asst. Director NSI Bari Road Under Bhola Sadar Dist-Bhola ID 509185067 | 509185067 |  |  |  | 0.13 |  | 712379 | 676760 | Md. Javed | 13.02.19 | 21.02.19 | 12.07.19 | 2019-05-07 | 100% | 676760 | 100% |  | FBP | Bhola-S
38 | BDRIDP/BHO/SDR/CCA-Rd/24 | A Improvement of Bhola Hospital Road-Altaf Member Bari-Kalikirti Road. Road ID No.-509184080 B Improvement of Pangshia Ghat-Bissa Road Ghat Nuzu Malmosque-Lokman Hazi Mosjid doctor Bari Pole Road ID No.-509184019 C Improvement of Pangashia launch ghat-Khaye Ghat Road. Road ID No.-509184054 | 509184080 509184054 509184019 |  | 5.18 |  |  |  | 25310324 | 25299131 | MS Jarin & co & Monirzzman (JV) | 21.5.19 | 30.5.19 | 20.5.20 | 25.02.20 | 100% | 22195000 | 87.73% | 3104131 |  | Bhola-S
39 | BDRIDP/BHO/SDR/CCA-Rd/25 | A Improvement of Bapta Illisha RHD Hazir Hat-Sifullah Master Bari Road. Road ID No.-509185258 B Improvement of Sultan Char Annda Register Primary School- Santir Hat Road. Road ID No.-509184007 C Improvement of Bapta UP Illisha RHD- Bapta Boro Bari- Mento Mollah Bari Mokammel Miar Bari Road. Road ID No.-509184088 | 509184007 509184088 509185258 |  | 2.215 |  |  |  | 22089139 | 22083920 | Unos All Mamun & Imded Hossain (JV) | 21.05.19 | 30.5.19 | 20.5.20 | 5.03.20 | 100% | 17750000 | 80.38% | 4310934 |  | Bhola-S
40 | BDRIDP/BHO/SDR/CCA-Rd/26 | A Improvement of Charshamia Natun Hat Madrasha-Molle Hat Road Rarir Hat Road No. 509185166 B Improvement of Junction Bazar. RHD via ICE factory Road Mozumder Bari-Beri Badh High School-Dhaka Launchghat Road No. 509184020 C Improvement of Dhania Master Bari-Khorki Paragonj Road Selim Member Bari-Khandoker Bari GPS-Wapda Beribadh Road No. 509184010 | 509185166 509184020 509184010 |  | 4.23 |  |  |  | 26656782 | 26541860 | MS Priyonti Construction | 21.05.19 | 30.5.19 | 20.5.20 | 25.03.20 | 100% | 20410000 | 76.9% | 6136218 |  | Bhola-S
41 | BDRIDP/BHO/SDR/CCA-Rd/28 | a Improvement of Maler Hat Bridge to Rustun Ali Mia Brick Field Road from Ch 00.00-1920m Maler Hat Ghatla Approach ID No 509185109 b. Improvement of Barishal RHD -Rafique Miar House Road from Ch 00-800m ID 509185118 | 509185109 509185118 |  | 1.92 | 2.25 |  |  | 15602678 | 14084799 | M/s Samata Enterprise | 11.7.19 | 20.7.19 | 10.7.20 |  | 100% | 7630670 | 54.18% | 6440144 |  | Bhola-S
42 | BDRIDP/BHO/SDR/CCA-Rd/29 | a Improvement of Gazaria GC Road -Rarir Hat via Justice Farid Ahmed Bari Road from Ch 2700m-3400m ID No 509185171 b Improvement of Dania Algi Talukdar Bari Badamtala Nasir Maji Road from Ch 00.00-1375m ID no 509185037 | 509185171 509185037 |  | 2.075 | 6 |  |  | 19519542 | 19413522 | m/s Sayem Enterprise | 27.8.19 | 6.9.19 | 26.2.20 |  | 100% | 15282428 | 78.72% | 4131094 |  | Bhola-S
43 | BDRIDP/BHO/SDR/CCA-Rd/30 | Improvement of Char Ananda Part-3-Swdis School-Alhajj Mofijol Haque Talukdar Bari Road from Ch 00-1100m ID no 509184085 | 509184085 |  | 1.1 |  |  |  | 7773479 | 7757931 | M/S Hider Builders | 17/6/19 | 22/6/19 | 16/12/19 | 15.12.19 | 100% | 6352087 | 81.88% | 1401676 |  | Bhola-S
44 | BDRIDP/BHO/SDR/CCA-Rd/32 | Improvement of Illisha Embank ment -Nader Mia Hat Road Ch-00-2050m Road Id no. 509185004 | 5004 |  | 2.05 | 6.5 |  |  | 20725388 | 20700000 | M/S Eli Enterprise | 25/8/19 | 31/8/19 | 24/2/20 |  | 80% | 5385000 | 26.01% | 15315000 |  | Bhola-S
45 | BDRIDP/BHO/SDR/CCA-Rd/31 | a Improvement of Suderhat-Illisha Kachia Union Road Ch-00-732m Road Id no. 509184004b Improvement of Koralia Bangla Bazar Khayerhat Road Ch-00-600m Road Id no. 509185014c Improvement of Khair Hat High School-Horni Bridge via Nipu Chow Bari Road Ch-00-450m Road Id no. 509185046 | 5014 5046 |  | 1.782 | 6.25 |  |  | 18362272 | 15111791 | M/S Lutful Kabir , Dilbag Bagura, Barisal | 17/09/19 | 26/9/19 | 16/03/20 |  | 100% | 6570000 | 43.48% | 8541791 |  | Bhola-S
46 | BDRIDP/BHO/SDR/CCA-Rd/33 | A- Improvement of Ilisha RHD Road panditer Hat-WDB Embk Kalupur road ID No.509184031 a- Earth work at Ch 00-400m b- Carpeting DC Ch. 00-400m c- Palisaiding 70m Salvage value Tk- 0.00 B- Improvement of Kachia Ramdabpur Bazar_Guccagram Road ID No.509185137 a- Earth work at Ch 00-1000m b- Carpeting DC Ch. 00-1000m c-Palisaiding 350m Salvage value Tk-1062034.00 | 4031 5137 |  | 1.4 |  |  |  | 11674110 | 9746724 | Md. Jakir Hossain | 23/12/19 | 28/12/19 | 22/6/2020 |  | 80% | 670000 | 6.874% | 9076724 |  |  | 49380988
46 | Bhola Sadar (Road Work) Sub-Total |  |  |  | 56.539 | 21 | 0.13 | 28.85 | 381469394 | 372883956 | Amount Spent (Tk) 18: 312627839; In (%) 20: 58457712; In (%) 22: Bhola-S
. | Bhola Sadar (Structure Work) | [9 empty] | In (%) 22: Bhola-S
1 | BDRIDP/Bho/ SDR/UZ-St/01 | Construction of 4 Nos 1.50mx1.50m RCC Box Culvert on Bhola-Gazaria GC road (Link=Chowmatha-Char Khumary RNGPS-Reba Rahman College-RHD) road at Ch.200m, 950m, 1700m & 2400m (ID No.509182015) under Bhola Sadar | 509182015 |  |  | 5.6 |  |  | 1681647 | 1689461 | M/s Ma Enterprise | 14.08.14 | 14.08.14 | 28.12.14 | 21/4/15 | 100% | 1674292 | 100% |  | FBP | Bhola-S
2 | BDRIDP/Bho/ SDR/Ghat/01 | Construction of RCC Ghatla at Malar Hat Bazar North Side under Bhola Sadar | [6 empty] | 2447855 | 2792310 | Md. Zakir Hossain |  | 07.12.14 |  | 24/12/14 | 100% | 2792310 | 100% |  | FBP | Bhola-S
3 | BDRIDP/Bho/ SDR/CCA-St/03 | Construction of 3Nos 0.75mx0.75m size 1no 3 vent 3x4.50mx4.50m RCC Box culvert on Shere Bangla Bazar-Charkali-Luzar hat road at Ch. 640m, 76m, 247m & 378m (ID No. 509185144) under Bhola | 509185144 |  |  | 15.75 |  |  | 5349125 | 5007188 | M/s Priyonti Construction | 14.08.14 | 14.08.14 | 11.12.14 | 22/3/15 | 100% | 5007168 | 100% |  | FBP | Bhola-S
4 | BDRIDP/Bho/ SDR/CCA-St/04 | Construction of 3x4.50mx4.50m (W-5.50m Three-vent) RCC Box Culvert on Bhola Barisal New Road- Char Chatkimara Primary School Adarshagram road at ch.710m (ID No. 509185149) under Bhola Sadar | 509185149 |  |  | 13.5 |  |  | 5056874 | 4754282 | M/s Sayem Enterprise | 14.08.14 | 14.08.14 | 28.12.14 | 26/12/14 | 100% | 4754282 | 100% |  | FBP | Bhola-S
5 | BDRIDP/Bho/ SDR/CCA-St/01 | Construction of 1 no 2x4.50mx4.50m, 3 nos 1.50mx1.50m & 1no 2.50mx2.50m size RCC Box culvert at Ch.1406m, Ch.439m, Ch.904m, Ch.1627m & Ch.1170m and 10 nos (0.750mx 0.750m size) U-drain at Ch.68m, Ch. 105m, ch.505m, Ch.536m, ch.641m, Ch778m, Ch.1140m, Ch.1291m Ch.1496m & Ch.1720m respecttively on Char Mohammad Ali GPS CUM- Cyclone Shelter Connecting approach road (Closser Bazar Barry Bandh-Char Mohammad Ali GPS) (ID No.509185096) under Bhola Sadar. | 509185096 |  |  | 23.5 |  |  | 6003575 | 6002040 | Md. Mohasin Nagar | 13.07.14 | 13.07.14 | 11.01.15 | 2015-07-03 | 100% | 5998668 | 99.94% |  | FBP | Bhola-S
6 | BDRIDP/Bho/ SDR/CCA-St/02 | Construction of 1.50mx1.50m RCC Box Culvert on Charkali-Lizarhat-Natun Hat-Nazirmazir Kheyaghat road at Ch. 1553m (ID No.509184049) Under Sadar | 509184049 |  |  | 1.5 |  |  | 1430648 | 1425152 | M/s Rable Enterprise | 14.12.14 | 14.12.14 | 12.01.15 | 2015-01-03 | 100% | 1424162 | 99.93% |  | FBP | Bhola-S
7 | BDRIDP/Bho/ SDR/UZ-St/02 | Construction of 1no 1.50m x 1.50m RCC Box Culvert on R&H Junction to Closer Bazar road at Ch. 7380m. (ID No.509182008) Under Sadar | 509182008 |  |  | 1.5 |  |  | 398764 | 398764 | M/s Msahir & Monir | 12.01.15 | 12.01.15 |  |  | 100% | 362676 | 100% |  | FBP | Bhola-S
8 | BDRIDP/Bho/ SDR/CCA-St/05 | Construction of 4 nos 1.50m* 1.50m RCC Box Culvert, 2 nos 0.75m*0.75m and 1 no 2*4.5*4.5m on khayer hat road-Koralia GPS-Alam bazar -MP Tofael Ahmed Bari(Dokljkhin Koralia *School cum Cyclone Shelter) Road at Ch. 13.00m, 185m 67m,469m, 606m 1970m and 1037m (ID No. 5091854061) Under Bhola Sadar. | 509184061 |  |  | 16.5 |  |  | 4946220 | 4726000 | M/s Rable Enterprise | 19.12.14 | 19.12.14 | 18.6.15 | 15/1/15 | 100% | 4726078 | 100% |  | FBP | Bhola-S
9 | BDRIDP/BHO/SDR/UN-St/13 | Construction of 3x4.50mx4.50m RCC Box Culvert on Dhania up -Shibpur UP Connecting road at Ch. 3750m (ID No. 509183018) | 509183018 |  |  | 13.5 |  |  | 5170477 | 5164444 | Shalaueddin Lincon | 5.4.15 | 5.4.15 | 15.10.15 | 2016-10-09 | 100% | 5164444 | 100% |  | FBP | Bhola-S
10 | BDRIDP/BHO/SDR/UN-St/02 | construction of 2X4.50MX4.50M RCC Box Culvert on RHD-Wapda (BIP-2) Ratanpur Bazar-Santir hat - Chrpata UP road at Ch. 2200m (ID No. 509183005) | 509183005 |  |  | 9 |  |  | 2943480 | 2937055 | Shalaueddin Lincon | 5.4.15 | 5.4.15 | 15.10.15 | 25/9/15 | 100% | 2913046 | 100% |  | FBP | Bhola-S
11 | BDRIDP/BHO/SDR/CCA-St/17 | Construction of 2 nos 1.50mx1.50m Box Culvert on Beduria Baro tarik Bazar-Charkali GPS (Connecting Cold Stores) road at Ch. 210m and 930m (ID No 509185179) | 509185179 |  |  | 3 |  |  | 798422 | 650390 | M/s. Nazim Uddin Traders | 22.4.15 | 22.4.15 | 21.10.15 | 19/11/15 | 100% | 650390 | 100% |  | FBP | Bhola-S
12 | BDRIDP/BHO/SAD/CCA-St/14 | Construction of 2.50mx2.50m RCC Box Culvert on Bhola Ilisha R&H Battala kalur hat (Nader miar hat) Parangonj road at Ch.,1300m ( ID No 509184073) | 509184073 |  |  | 2.5 |  |  | 858059 | 857070 | M/s Singapur Electrnice | 22.07.15 | 23.07.15 | 22.07.16 | 2015-08-10 | 100% | 841293 | 100% |  | FBP | Bhola-S
13 | BDRIDP/BHO/SAD/CCA-St/18 | Construction of 2 nos 1.50mx1.5m RCC Box Culvert and 2 nos 0.75mx0.75m Box Culvert on Improvement of Road from Beduria Baro Tarik bazar Farazi Bari Mosque-Shere-Bangla Bazar Road at Ch. 910m ,1300m , 220m ,1100m ( ID No 509185159) | 509185159 |  |  | 4.5 |  |  | 1020175 | 822120 | Md Nazimuddin Traders | 22.07.15 | 23.07.15 | 22.07.16 | 15/1/16 | 100% | 807908 | 100% |  | FBP
14 | BDRIDP/BHO/SDR/UN-St/01 | Construction 4x5.00mx5.00m (Four vent) RCC Box Culvert on Madrasha Bazar (south side)- NAzimuddin Alam road-Charshemayia UP office road (near Vir Sheresto Mostofa kamal Bari) at ch. 1000m (ID No. 509183007) | 509183007 |  |  | 20 |  |  | 7073113 | 7069374 | Md. Rahul Amin | 24.03.15 | 24.09.15 | 24.09.15 | 20/6/16 | 100% | 7034676 | 99.51% |  | FBP | Bhola-S
15 | BDRIDP/BHO/SDR/CCA-St/12 | Construction of 1 No 2x4.50mx4.50m (W-5.5m double vent) RCC Box Culvert on Pachim llisha Union 1NO Word Dakin Charpata NAziur Rahman School Road at ch. 440m (ID No. 509185107) | 509185107 |  |  | 9 |  |  | 2907583 | 2905447 | M/s Orid Enterprise | 08.04.15 | 09.04.15 | 07.07.15 | 2015-10-05 | 100% | 2905447 | 100% |  | FBP | Bhola-S
16 | BDRIDP/BHO/SDR/UZ-St/05 | Construction of 2 nos 1.50x1.50m (Width 5.50m) RCC Box Culvert on Rehabilitation of road from Bhola khyaghat- kalinath Ray Bazar Darger road by pass-pondiler pol Gazaria GC at ch 9200m, 9400m (ID No. 509182010) | 509182010 |  |  | 3 |  |  | 794622 | 790166 | Md. Rahul Amin | 24.03.15 | 24.03.15 | 24.09.15 | 2015-04-05 | 100% | 790038 | 99.98% |  | FBP | Bhola-S
17 | BDRIDP/BHO/SDR/CCA-St/09 | Construction of road from 1NO 2.50m x 2.50m RCC Box Culvert on Gazipur road-Mannan Talukder bari to PArihat road at Ch. 1315m (ID No. 509184014) | 509184004 |  |  | 2.5 |  |  | 1086930 | 1086574 | Md. Jamaluddin Golder | 31.03.15 | 01.04.15 | 30.09.15 | 2015-10-05 | 100% | 1086574 | 100% |  | FBP | Bhola-S
18 | BDRIDP/BHO/SDR/CCA-St/10 | Construction of road from 1No Double vent 3.00mx3.00m Box Culvert on Hazir Hat-Porir Hat road at Ch. 1510m (ID No. 509184062) | 509184062 |  |  | 3 |  |  | 1591058 | 1589940 | M/s Howlader Construction | 31.03.15 | 01.04.15 | 30.06.15 | 13/5/15 | 100% | 1589940 | 100% |  | FBP | Bhola-S
19 | BDRIDP/BHO/SDR/CCA-St/11 | Construction of road from 1No 2x4.50x4.50m RCC Box Culvert on Ilish RHD (Hazir Hat) Khalifa Bari road at Ch. 5m (ID No. 509185174) | 509185174 |  |  | 9 |  |  | 2907583 | 2901074 | M/s Thaura Enterprise | 01.04.15 | 01.07.15 |  | 2014-10-05 | 100% | 2901074 | 100% |  | FBP | Bhola-S
20 | BDRIDP/BHO/SDR7CCA-St/06 | Construction of 3x4.50mx4.50m (W-5.5m Three-vent) RCC Box Culvert on illsha RHD (Kalam Member Mill Ghor)-Rabarahman RNGPS-Berry Bandh road at Ch. 870m (ID No. 509184040) under Sadar Upazila. | 509184040 |  |  | 13.5 |  |  | 4040560 | 4030458 | M/s Jakir Hossain | 21.4.15 |  | 06.6.15 | 21/5/14 | 100% | 4025470 | 99.88% |  | F.B.P | Bhola-S
21 | BDRIDP/BHO/SDR/CCA-St/07 | Construction of 3x4,50mx4.50m (W-5.50m Three- vent) RCC Box Culvdrt on Shibpur UP-Munceb Bari- Charpata Up Connecting road at Ch. 280m (ID No. 509184066) under Sadar Upazila. | 509184066 |  |  | 13.5 |  |  | 5123957 | 5111147 | M/s Ruble Enterprise | 21.4.15 | 21.4.15 | 20.07.15 | 20/5/15 | 100% | 5098369 | 99.75% |  | F.B.P | Bhola-S
22 | BDRIDP/BHO/SDR/CCA-St/08 | Construction of 3x4.50mx4.50m (W-5.50m Three- vent) RCC Box Culvert on Rajapur Santir hat Bazar- Ali Meji Bari via Sampur Helal Member bari road at Ch. 700m (ID No. 509184075) under Sadar Upazila. | 509184075 |  |  | 13.5 |  |  | 5123957 | 5111147 | M/s Telmi Enternational | 21.4.15 | 21.4.15 | 21.7.15 | 20/6/15 | 100% | 5111129 | 100% |  | F.B.P | Bhola-S
23 | BDRIDP/BHO/SDR/CCA-St/23 | Construction of 3x4.50 x4050 (W-5.50m Four Vent) RCC Box Culvert on Bhala Barisal New road Char Chatkimara Primary School-Adarshgram Road, at Ch. 1045.00m. (ID No. 509185149) under Sadar Upazila. | 509185149 |  |  | 13.5 |  |  | 5170477 | 5157550 | M/s Ruble Enterprise | 1.4.15 | 1.4.15 | 1.7.15 | 22/11/14 | 100% | 5170477 | 100.3% |  | F.B.P | Bhola-S
24 | BDRIDP/BHO/SDR/CCA-St/24 | Construction of 3x4.50 x4050 (W-5.50m Three Vent) RCC Box Culvert on Bhala Barisal RDH Mazkazi Connecting Road (Near -Alhaz sikander ali Bari and Tofazal Howlader Shop) at Ch.05.00m. (ID No. 509185115) under Sadar Upazila. | 509185115 |  |  | 13.58 |  |  | 5170477 | 5157550 | M/s Singapur Electrnice | 2.4.15 | 2.4.15 | 2.7.15 | 2015-10-05 | 100% | 5157240 | 99.99% |  | F.B.P | Bhola-S
25 | BDRIDP/BHO/SDR/CCA-St/15 | Construction of 3 Nos 1.50mx1.50m RCC Box Culvert & 1 No 0.75mx0.75m Box Culvert on Charnoabad Chowmuhane- By Pass-Auto Brick fields-Santir hat road By BC at Ch. 1020m, 2600m, 3200m & 2040m (ID No. 509184041). [Sadar] | 509184041 |  |  | 5.25 |  |  | 1524067 | 1523851 | M/s Mollah Trading & Const. | 22.7.15 | 22.7.15 | 21.7.16 | 20/12/15 | 100% | 1523048 | 99.95% |  | FBP | Bhola-S
26 | BDRIDP/BHO/SDR/CCA-St/16 | Construction of 2 Nos 0.75mx0.75m RCC Box Culvert on Shibpur UP (Ratan Pur Bazar)-Munceb Bari-Charpata UP Connecting road at Ch. 1340m & 1500m. (ID No. 509184066). [Sadar] | 509184066 |  |  | 1.5 |  |  | 488439 | 440587 | M/s Mollah Trading & Const. | 22.7.15 | 22.7.15 | 21.7.16 | 20/12/15 | 100% | 437287 | 100% |  | FBP | Bhola-S
27 | BDRIDP/BHO/SDR/CCA-St/21 | Construction of 2x4.50 mx4.50m (W-5.50m Double Vent) RCC Box Culvert on Pilor R.H.D-West Munshi Kandi- Sufilla Master Bari-Hazir hat Road. (Near Rashid Dafader Bari) at 950.00m. (ID No. 509184023) [Sadar] | 509184023 |  |  | 9 |  |  | 2988469 | 2985052 | Md. Ruhal Aaim | 22.7.15 | 22.7.15 | 22.7.16 | 25/1/17 | 100% | 2966259 | 100% |  | FBP | Bhola-S
28 | BDRIDP/BHO/ SDR/CCA-St/19 | Construction of 2x4.50m x4.50m (W-5.50m Double Vent) RCC Box Culvert on llisha RHD (Mohajan Bari)-West Madupur Chewakhali GPS-porir hat-Tulatali GC road. (Near Matabar bari) at ,00.00m. (ID No. 509184069) [Sadar] | 509184069 |  |  | 9 |  |  | 2988469 | 2986842 | M/s Sayem Enterprise | 22.7.15 | 22.7.15 | 22.7.16 | 25/1/16 | 100% | 2963858 | 100% |  | FBP | Bhola-S
29 | BDRIDP/BHO/SDR/CCA-St/20 | Construction of 2x4.50mx4.50m (W-5.50m Double Vent) RCC Box Culvert on Abohowa office road-Siraj Maker Bari-Killa Bari-Hazir hat Road. (Near Killa Barii) at.1230.00m. (ID No. 509185081) [Sadar] | 509185081 |  |  | 9 |  |  | 2988469 | 2986981 | M/s Prionti Const. | 22.7.15 | 22.7.15 | 22.7.16 | 2016-05-01 | 100% | 2986553 | 99.99% |  | FBP | Bhola-S
30 | BDRIDP/BHO/SDR/UZ-St/08 | Construction of 2x4.50m x4.50m (W-5.50m Double Vent) RCC Box Culvert on Ilisha-Kabiraj Bari-Colghat Bapta Up-R.H.D (Howlader Bari) Road. at. 3800.00m. (id No. 509182014) [Sadar] | 509182014 |  |  | 9 |  |  | 2988469 | 2985077 | M/s Prionti Const. | 22.7.15 | 22.7.15 | 22.7.16 | 2016-06-01 | 100% | 2968705 | 100% |  | FBP | Bhola-S
31 | BDRIDP/BHO/SDR/UZ-St/06 | Construction of 2x4.50mx4.50m (W-5.50m Double Vent) RCC Box Culvert on lllsha-Kabiraj Bari-Colghat Bapta Up-R.H.D. (Near Sharkar Bari) Road at. 2950.00m. (ID No 509182014) [Sadar] | 509182014 |  |  | 9 |  |  | 2988469 | 2985052 | M/s Sayem Enterprise | 22.7.15 | 22.7.15 | 22.7.16 | 2016-05-01 | 100% | 2968664 | 100% |  | FBP | Bhola-S
32 | BDRIDP/BHO/SDR/UZ-St/07 | Const., of 4x5.00mx5.00m (Four Vent) RCC Box Culvert on Ilisha-Kabiraj Bari-Colghat Bapta Up-R H D (Near Kabiraj Bari) at. 2440.00m. (ID No. 509182014) [Sadar] | 509182014 |  |  | 20 |  |  | 6049304 | 6045473 | M/s Kayed Enterprise | 22.7.15 | 22.7.15 | 22.7.16 | 2016-01-05 | 100% | 6043873 | 99.97% |  | FBP | Bhola-S
33 | BDRIDP/Bho/SDR/CCA-St/25 | Construction of 04 Nos 1.50mx1.50m RCC Box Culvert on RHD Bapari Bazar-Charpata road (South Ratanpur GPS-Miji Bari-Taltali Bazar road) By Earth Work from Ch. 00-1450m. (ID No.509185082) [Sadar] | 509185082 |  |  | 6 |  |  | 1768854 | 1767853 | Md. Jakir Hossain | 22.7.15 | 22.7.15 | 22.7.16 | 25/9/15 | 100% | 1767853 | 100% |  | FBP | Bhola-S
34 | BDRIDP/BHO/SDR/CCA-St/13 | Construction of 5 Nos ,750mx.750m & 1No 1.50m x 1.50m on Dosh Khali Bridge-Char Hossain-Chandra Proshad Jonal Bapari Shop (Mir Bazar) Bisso road at Ch. 374m, 421m, 755m, 1254m, 1407m & 634m (ID No, 509185061) [Sadar] | 509185061 |  |  | 5.25 |  |  | 973447 | 969209 | M/s Samata Enterpise | 22.7.15 | 22.7.15 | 23.7.16 | 25/2/16 | 100% | 967256 | 99.8% |  | FBP | Bhola-S
35 | BDRIDP/Bho/SDR/UZ-St/09 | Construction of .75m*.75m(W-5.5M) RCC Box Culvert on illisha Colghat-kabiraj bari-Piar khan -Bapta UP-RHD road at Ch 1200m,1500m, 2700m,2900m and 3150m (ID No-509182014) Under Sadar Upazila. | 509182014 |  |  | 3.75 |  |  | 1287757 | 1284538 | Md. Jakir Hossain | 21.9.15 | 21.9.15 | 20.9.16 | 2015-08-10 | 100% | 1284538 | 100% |  | FBP | Bhola-S
36 | BDRIDP/BHO/SDR/CCA-St/26 (27080) | Construction of 3.00m*3.00m Double vent 1 nos 2.50m*2.50m RCC box Cuvert and 4nos 0.75m*0.75m U Drain Culvert on Charkali-Luzarhat-Natun Hat-Nazir Mazi Kheya Ghat (Dakhakin Pascim Madrasa-Maksud matabbar bari) Road at Ch 4817m ,5630m ,4970m 5130m & 5230m (ID No 509184049) Under Sadar Upazila. | 509182014 |  |  | 8.5 |  |  | 2362884 | 2261121 | M/s Sayem Enterprise | 6.9.15 | 6.9.15 | 6.9.16 | 13/5/15 | 100% | 2258202 | 99.87% |  | FBP | Bhola-S
37 | BDRIDP/BHO/SDR/UZ-St/04 | Construction of 36.05m long RCC Girder Bridge on Bangla bazar Bagmara Sharfkhan hat -Vulumia GC road at Ch. 922m [Sadar] | 509182010 |  |  | 36.05 |  |  | 22015083 | 22006854 | Md. Younus Al Mamun | 9.7.15 | 9.7.15 | 08.01.18 | 26/7/17 | 100% | 21984225 | 99.9% |  | FBP | Bhola-S | 22629
38 | BDRIDP/BHO/SDR/UZ-St/10 (35019) | Construction of 54.00m long RCC Girder Bridge over Darogar Canal at Elisha RHD -Rowder hat Shanterhat Wpada Closser Bazar char Monsaha Rajapur Union at Ch. 1800m [Sadar] | 509182012 |  |  | 54 |  |  | 28372823 | 29790581 | M/s Monir Traders | 26.1.16 | 26.1.16 | 28.12.17 | 28/11/17 | 100% | 29777031 | 99.95% |  | FBP | Bhola-S | 13550
39 | BDRIDP/BHO/SDR/CCA-St/27 (35020) | Construction of 20.00m long RCC Girder Bridge on Diaya Canal at Daiya Natun Hat -Mehen digonj road at Ch. 550m [Sadar] | 509184083 |  |  | 20 |  |  | 14009741 | 14705335 | M/s Eli Enterprise | 28.1.16 | 28.1.16 | 27.1.17 | 2016-10-09 | 100% | 14612684 | 100% |  | FBP | Bhola-S | 92651
40 | BDRIDP/Bho/SDR/CCA-St/22 | Construction of 1.60mx1.60m Box Culvert on the road Rashid Khan shop -Dakkin Koralia Madrasha via Shah sikder bari road (ID No.509185169) [Sadar] | 509185169 |  |  | 1.6 |  |  | 648742 | 647120 | M/s Sayem Enterprise | 15.07.15 | 15.07.15 | 15.08.15 | 21/7/15 | 100% | 647120 | 100% |  | FBP |  | 0
0
40 | Bhola Sadar (Structure Work) Sub-Total |  |  | 0 | 0 | 431.33 | 0 | 0 | 173539124 | 174508229 | Amount Spent (Tk) 18: 174144307; In (%) 20: 0 | 363922
86 | Bhola Sadar Upazila Total |  |  | 0 | 56.539 | 452.33 | 0.13 | 28.85 | 555008518 | 547392185 | Amount Spent (Tk) 18: 486772146; In (%) 20: 58457712; In (%) 21: 0 | 60620039
| Borhanuddin (Road Work) | [9 empty] | In (%) 22: Borhanuddin | 0
1 | BDRIDP/Bho/Brn/CCA-Rd/01 | Improvement of road from Manikarhat RHD- Uttar gongapur road (Kamu bari-Matabbar- Dhani Bhanga school-Khayerhat road) under Borhanuddin | 509215025 |  | 1 |  |  |  | 8506642 | 9405856 | M/S. Sayem Enterprise | 20.04.14 | 20.04.14 | 19.10.14 | 18/11/14 | 100% | 9405856 | 100% |  | FBP | Borhanuddin | 0
2 | BDRIDP/Bho/Brn/UZ-Rd/02 | Improvement of road from Borhangonj- GC- Moazzemhat GC via Talukderhat under Borhanuddin | 509212008 |  | 1.8 |  |  |  | 16422158 | 17910576 | M/S. Sayem Enterprise | 20.04.14 | 20.04.14 | 19.04.15 | 25/11/14 | 100% | 17910576 | 100% |  | FBP | Borhanuddin | 0
3 | BDRIDP/Bho/Brn/UZ-Rd/03 | Improvement of road Borhanuddin RHD - Choto Manika Syed Bepari Bari Road At Ch. 00-300m under Borhanuddin | 50921 |  | 0.3 |  |  |  | 1821296 | 1730231 | M/s Oritro Enterprise | 30.07.14 | 30.07.14 | 29.11.14 | 2014-05-01 | 100% | 1730129 | 99.99% |  | FBP | Borhanuddin | 102
4 | BDRIDP/Bho/ BRN/UN-Rd(R)/01 | Rehabilitation of Pakshia to ranogonj road by CB from Ch. 00-3930m (ID No.509213006) Under Borhanuddin | 509213006 |  | 0 |  |  | 3.93 | 5306596 | 5304654 | Md. Rafiqule Islam | 24.02.15 | 24.02.15 | 23.05.15 | 2015-10-04 | 100% | 5093573 | 100% |  | FBP | Borhanuddin | 211081
5 | BDRIDP/Bho/ BRN/UN-Rd(R)/02 | Rehabilitation of Borhanuddin to Chowmohoni hat road by BC from Ch.4010-7471m (ID No.509213001) Under Borhanuddin Upazila. | 509213001 |  | 3.06 |  |  |  | 8418179 | 9214714 | Md. Iqbal Hossain | 20.08.14 | 20.08.14 | 31.12.14 | 19/2/15 | 100% | 9214714 | 100% |  | FBP | Borhanuddin | 0
6 | BDRIDP/Bho/ BRN/CCA-Rd/04 | Improvement of Borhanuddin-Chowmohanirhat-Matiarmar Pukur-Moller hat, connecting road (Omor hasan mia road) by BC from Ch.00-995m, (ID.509214079) Borhanuddin | 509214079 |  | 0.995 |  |  |  | 6466245 | 6461842 | M/s Howlader Construction | 20.08.14 | 20.08.14 | 11.01.15 | 2015-01-03 | 100% | 6461842 | 100% |  | FBP | Borhanuddin | 0
7 | BDRIDP/Bho/ BRN/CCA-Rd/05 | Improvement of Road from Musalman Pukur-Ful Kachia GPS road By BC from Ch.2500-4730m (ID .509214055) Under Borhanuddin Upazila. | 509214055 |  | 4.73 |  |  |  | 10555796 | 10555825 | Md. Anichul Hoque | 23.12.14 | 23.12.14 | 22.12.15 | 21/10/16 | 100% | 10555824 | 100% | 0 | FBP | Borhanuddin | 1
8 | BDRIDP/BHO/BRN/CCA-Rd/06 | Improvement of road from Ranigonj-Banglabazar road Pirgonj via Darogha Bari (Safizol Mia Bari Road from Ch. 00m -1100m (ID no 509215053) | 509215053 |  | 1.1 |  |  |  | 6839538 | 6838256 | Md. Rafiqule Islam | 22.04.15 | 21.10.15 |  | 2017-03-01 | 100% | 6838256 | 100% | 0 | FBP | Borhanuddin | 0
9 | BDRIDP/BHO/BRN/UZ-Rd(R)/01. | Rehabilitation of road from Borhangonj-Sikderhat-Maniram-Mizakalu road By BC from ch.00-4000m (ID No. 509212005) Under Borhanuddin Upazila. | 509212005 |  | 4 |  |  |  | 10248053 | 9723855 | Md. Abul Khayer Hossain | 14.10.15 | 14.10.15 | 14.10.16 |  | 100% | 9723833 | 100% |  | FBP | Borhanuddin | 22
10 | BDRIDP/BHO/BRN/UZ-Rd(R)/03. (27084) | Rehabilitation of road from Borhangonj-Sikderhat-Maniram-Mizakalu road By BC from ch.4000-8490m (ID No. 509212005) Under Borhanuddin Upazila. | 509212005 |  | 4.49 |  |  |  | 7611190 | 7600298 | Md. Rafiqule Islam | 30.9.15 | 30.9.15 | 30.9.16 | 22/1/16 | 100% | 7597668 | 99.97% |  | FBP | Borhanuddin | 2630
11 | BDRIDP/BHO/BRN/CCA-rd/07 (27084) | A Improvement Ranigonj to Borhangonj Road Ch. 1790-3000m ID No. 509214064 B Improvement of Sikderhat-Maniram-Borhanuddin-Lalmohan Balagon Bari-Bassa Bari road Ch.00-1170m ID No. 509214089 | 509214089 |  | 2.38 |  |  |  | 20118522 | 20112151 | M/s Sayem Enterprise | 01.08.19 | 10.08.19 | 31.7.19 |  | 90% | 9000000 | 44.75% | 11112151 |  |  | 11112151
11 | Borhanuddin (Road Work) Sub-Total |  |  | 0 | 23.855 | 0 | 0 | 3.93 | 102314215 | 104858258 | Amount Spent (Tk) 18: 93532271; In (%) 20: 11112151 | 11325987
| Borhanuddin (Structure Work) | [20 empty] | 0
1 | BDRIDP/BHO/BRN/CCA-St/02 | Construction of 7Nos 1.00m x1. 00m W-4.66m RCC Box Culvert on Musalman pukur-Ful kachia GPS road at Ch. 2805m, 2990m,3415m, 3500m, 3816m and 4565m.(ID No 509214055) | 509214055 |  |  | 7 |  |  | 2162000 | 2159272 | M/s Howlader Construction | 15.4.15 | 15.4.15 | 14.07.15 | 2015-10-09 | 100% | 2159230 | 100% |  | FBP | Borhanuddin | 42
2 | BDRIDP/BHO/BRN/CCA-St/03 | Construction of 4Nos 1.00m x1.00m W-4.66m RCC Box Culvert on Box Culvert on Borhanuddin-Chowmunirhat Matiarmar Pukur Loller hat Connecting Road (Omor Hassan road) at Ch. 92m, 427m, 553m and 800m (ID No 509214079) | 509214079 |  |  | 4 |  |  | 1235434 | 1233870 | M/s Howlader Construction | 15.4.15 | 15.4.15 | 14.10.15 | 15/5/15 | 100% | 1233870 | 100% |  | FBP | Borhanuddin | 0
3 | BDRIDP/BHO/BRN/CCA-St/01. | Construction of 3 Nos 1.00mx1.00mm (4.66w) RCC Box Culvert on road from Ranigonj-Banglabazar road Pirgonj via Darogha Bari (Safizol Mia Bari Road) at Ch. 330m 480mm, 510mm. |  |  |  | 3 |  |  | 832422 | 828562 | M/s Howlader Construction | 15.4.15 | 15.4.15 | 14.07.15 | 2015-10-07 | 100% | 826826 | 99.79% |  | FBP | Borhanuddin | 1736
4 | BDRIDP/BHO/BRN/UZ-St/01 | Construction of 4 Nos 1.0m*1.0m (W7.32) RCC Box Culvert on Borhangonj-Sikdarhat-Maniram-Mirzakalu Road at Ch.150.00m, 1830.00m,6515.0mand 7910m ( ID No 509212005) Under Borhanuddin Upazila. | 509212005 |  |  | 4 |  |  | 1450123 | 1443571 | md kayer Hossain | 14.10.16 | 14.10.16 | 06.07.16 | 2016-06-07 | 100% | 1443571 | 100% |  | FBP | Borhanuddin | 0
4 | (Structure Work) Sub-Total |  |  | 0 | 0 | 18 | 0 | 0 | 5679979 | 5665275 | Amount Spent (Tk) 18: 5663497; In (%) 20: 0 | 1778
15 | Borhanuddin Upazila Total |  |  | 0 | 23.855 | 18 | 0 | 3.93 | 107994194 | 110523533 | Amount Spent (Tk) 18: 99195768; In (%) 20: 11112151; In (%) 21: 0 | 11327765
| Upazila : Daulatkhan (Road Work) | [20 empty] | 0
1 | BDRIDP/Bho/Dau/CCA-Rd/01 | Improvement of road from Munaf bepari Bari- Faruk Miar hat Rd. (Azkar Patowari bari- Nurmiarhat UZR via Eunus member house- Chotto dholi GPS) Ch: 600-1995m under Daulatkhan upazila. | 509295034 | 0 | 1.395 |  |  |  | 6673889 | 6340200 | M/S Hawlader Construction | 15.05.14 | 15.05.14 | 14.11.14 | 20/11/14 | 100% | 6340200 | 100% |  | FBP | Daulatkhan | 0
2 | BDRIDP/BHO/DOU/CCA-Rd/01 | Improvement of road South Joyngar UP Office 9Bhola-Charfession RHD) to Miar hat via Box All Bazar road By BC from Ch. 5595-7500m (ID No 509293003) | 509293003 | 0 | 2.095 |  |  |  | 9425724 | 9421282 | M/s Howlader Construction | 15.04.15 | 14.04.16 | 14.04.16 | 15/06/15 | 100% | 9421258 | 100% |  | FBP | Daulatkhan | 24
3 | BDRIDP/BHO/DOU/CCA-Rd/02 | Improvement of road from chailtatali hat to Otarnddinnn munshir hat road By BC from Ch. 00-2950m (ID No 509294002 | 509294002 | 0 | 2.95 |  |  |  | 10949402 | 10947498 | M/s Roni Const. | 2.4.15 | 01.4.16 | 01.4.16 | 2016-10-08 | 100% | 10947498 | 100% |  | FBP | Daulatkhan | 0
4 | BDRIDP/BHO/DOU/CCA-Rd/03 | Improvement of road from Banglabazar-Daulatkhan R&H to (Jahungir Mias House ) WAPDA Embankmment road By BC from Ch. 00-1280m. (ID No 509295063) | 509295063 | 0 | 1.28 |  |  |  | 4689781 | 4688697 | M/s Roni Const. | 10.05.15 | 10.5.15 | 9.11.15 | 25/04/17 | 100% | 4688697 | 100% | 0 | FBP | Daulatkhan | 0
5 | BDRIDP/BHO/DOU/CCA-Rd/04 | Improvement of road from Mirdharhat Bridge URZ to Guingar hat VAPSA UZR Road by BC from Ch. 00-2190m (ID No 509294018) | 509294018 | 0 | 2.19 |  |  |  | 9331957 | 9329826 | M/s Rani Construction | 15.04.15 | 14.04.15 | 14.04.15 | 2015-12-12 | 100% | 9329804 | 100% | 0 | FBP | Daulatkhan | 22
6 | BDRIDP/BHO/DAU/CCA-Rd/06 | Improvement of road from Purbo Didarulla Cyclone Shelter (Banglabazar-Daulatkhan UZR( East side of mridar hat ) to miar hat , Howladar hat road via west kolakopa RNGPS -Purbo Didarulla Cyclone Shelter road from Ch.00.00-2420m (ID 509295155) Under Daulatkhan | 509295155 | 0 | 2.42 |  |  |  | 14055114 | 14051423 | M/s Priyonti Construction | 2.9.15 | 2.9.16 | 2.9.16 | 23/02/15 | 100% | 14051423 | 100% |  | FBP | Daulatkhan | 0
7 | BDRIDP/BHO/DAU/CCA-Rd/05 | Improvement of road from Medua Cyclone Shelter ( Jalil Bepari Bari to WAPDA Embankment ) road from Ch.00-1084m (ID NO 509295154) Under Daulatkhan Upazila. | 509295154 | 0 | 1.084 |  |  |  | 5394477 |  | 12: M/S Sayem Enterprise; In (%) 21: Cancal; In (%) 22: Daulatkhan | 0
8 | BDRIDP/BHO/DAU/UN-Rd/02 | Improvement of road from South Joynagor UP office ( Bhola-Charfession RHD ) to miar hat via Box Ali Bazar Road From Ch260-660 and 1440-2065m ( Id no 509293003) Under Daulatkhan | 509293003 | 0 | 0.4 |  |  |  | 6108111 | 6103673 | M/s Priyonti Construction | 2.9.15 | 2.9.16 | 2.9.16 | 2016-12-02 | 100% | 6103673 | 100% |  | FBP | Daulatkhan | 0
9 | BDRIDP/BHO/DOU/CCA-Rd-07 | a Re-sectioning of Kalacopa Daroga Bari road Ch.00-1060 509295010b Improvement of Kalacopa Daroga Bari to Chawkidar Bari road Ch.00-1060 509295010 c Construction of 4 nos 1.0m x1.0m RCC Box Culvert on Kalacopa Daroga Bari to Chawkidar Bari road at 161m264m440m and 781m 509295010 | 509295010 |  | 1.06 |  |  |  | 5975442 | 5974158 | Md .Kamal Hossain | 30.7.17 | 29.4.18 |  | 7.11.18 | 100% | 5927837 | 99.22% | 0 | FBP | Daulatkhan | 46321
9 | Daulatkhan (Road Work) Sub-Total |  |  | 0 | 14.874 | 0 | 0 | 0 | 72603897 | 66856757 | Amount Spent (Tk) 18: 66810390; In (%) 20: 0; In (%) 22: Daulatkhan | 46367
| Daulatkhan (Structure Work) | [20 empty] | 0
1 | BDRIDP/BHO/DOU/UN-St/01 | Construction of 2no 1.00mx5.5m Long RCC Box Culvert on South Joynagar UP Office (Bhola Charfession Rhd) to Miar hat via Box Ali Bazar road at ch 6550m and6875m (ID NO 509293003) | 509293003 |  |  | 2 |  |  | 548391 | 544795 | M/s Howlader Construction | 15.4.15 | 15.4.15 | 14.7.15 | 30/04/15 | 100% | 542302 | 99.54% |  | FBP | Daulatkhan | 2493
2 | BDRIDP/BHO/DOU/CCA-St/01 | Construction of road from 4 Nos 1.00mmx1.00mx5.50m RCC Box Culvert on Chailtali hat to Otaruddinnn munshir hat road at Ch. 667m, 970mm, 1928m and 2228m (ID No 509294002) | 509294002 |  |  | 4 |  |  | 1096782 | 1093322 | M/s Howlader Construction | 15.4.15 | 15.4.15 | 14.7.15 | 2015-12-07 | 100% | 1093188 | 99.99% | 0 | FBP | Daulatkhan | 134
3 | BDRIDP/BHO/DOU/CCA-St/02 | Construction of road from 2 Nos 1.00mx1.00mx5.50m RCC Box Culvert on Banglabazar-Daulatkhan R&H to (Jahungir MIas House) WAPDA Embankment road at Ch. 250m & 1130m (ID No. 509295063) | 509295063 |  |  | 2 |  |  | 548391 | 545436 | M/s Howlader Construction | 20.04.15 | 20.06.15 |  | 30.04.15 | 100% | 545360 | 99.99% |  | F.B.P | Daulatkhan | 76
4 | BDRIDP/BHO/DOU/CCA-St/03 | Construction of road from 3 Nos 1.00mx1.00mx5.50m RCC Box Culvert on Mirdharhat Bridge URZ to Guingar hat VAPSA UZR road at Ch. 860m 1585m & 1923m (ID No. 509294018) | 509294018 |  |  | 3 |  |  | 822587 | 802275 | M/s Unons & Sons | 10.11.14 | 20.04.15 | 19.10.15 | 05.07.15 | 100% | 800876 | 99.83% | 0 | F.B.P | Daulatkhan | 1399
5 | BDRIDP/BHO/DAU/CCA-St/04(a) | Construction of 3 nos 1.0m*1.0m*5.5m Box culvert on road from Purbo Didarulla Cyclone Shelter (Banglabazar-Daulatkhan UZR( East side of mridar hat ) to miar hat, Howladar hat road via west kolakopa RNGPS -Purbo Didarulla Cyclone Shelter road at Ch 270m,1715m &2035m (ID 509295155) Under Daulatkhan Upazila. | 509295155 |  |  | 3 |  |  | 778842 | 775635 | M/S Sayem Enterprise | 02.09.15 | 2.9.15 | 01.9.16 | 20/09/15 | 100% | 775464 | 99.98% | 0 | F.B.P | Daulatkhan | 171
6 | BDRIDP/BHO/DAU/CCA-St/04(b) | Construction of 1 No 1.0m*1.0m*5.50m long Box Culvert on Medua Cyclone Shelter ( Jalil Bepari Bari to WAPDA Embankment ) at Ch 475m (ID NO 509295154) Under Daulatkhan Upazila. | 509295154 |  |  | 1 |  |  | 259614 | 258256 | M/s Priyonti Construction | 02.09.15 | 2.9.15 | 01.9.16 | 18/09/15 | 100% | 257790 | 99.82% |  | FBP | Daulatkhan | 466
7 | BDRIDP/BHO/DAU/UN-St/02 | Construction of 4 Nos 1.0m*1.0m*5.50m Box Culvert on South Joynagor UP office ( Bhola-Charfession RHD ) to miar hat via Box Ali Bazar Road at Ch 301m ,1563m,1670mand 1889m ( Id no 509293003) Under Daulatkhan Upazila. | 509293003 |  |  | 4 |  |  | 1038457 | 1058542 | M/s Priyonti Construction | 02.09.15 | 2.9.15 | 01.9.16 | 20/09/15 | 100% | 1053311 | 99.51% |  | FBP | Daulatkhan | 5231
7 | (Structure Work) Sub-Total |  |  | 0 | 0 | 19 | 0 | 0 | 5093064 | 5078261 | Amount Spent (Tk) 18: 5068291; In (%) 20: 0 | 9970
16 | Daulatkhan Upazila Total |  |  |  | 14.874 | 19 | 0 | 0 | 77696961 | 71935018 | Amount Spent (Tk) 18: 71878681; In (%) 20: 0; In (%) 21: 0 | 56337
| Upazila: Lalmohan (Road Work) | [20 empty] | 0
1 | BDRIDP/Bho/ LAl/CCA-Rd/01 | Improvement of Munshir Hawla (H/O/Dulu Miah)-Patowary Bari-Dewan bari via Hazi Solayman RNGPS by BC at Ch: 4475-5000m (ID No. 509545081) Under Lalmohan Upazila. | 509255081 |  | 0.525 |  |  |  | 1951880 | 2039980 | M/s Bhaya Enterprise | 24.07.14 | 01.08.14 | 23.12.14 | 14/12/15 | 100% | 2039980 | 100% | 0 | FBP | Lalmohan | 0
2 | BDRIDP/Bho/ LAl/CCA-Rd/02 | Improvement of Pangashia H/O Iddrish Khalifa-Berribandh (Jobeda road) via Pangasia Bazar road by Earth Work at Ch: 3400-4820m. (ID No. 509544050) Under Lalmohan | 509254050 |  | 1.42 |  |  |  | 5602804 | 5602819 | M/s Bhaya Enterprise | 24.07.14 | 30.07.14 | 23.12.14 | 2015-05-02 | 100% | 5602805 | 100% | 0 | FBP | Lalmohan | 14
3 | BDRIDP/Bho/ LAl/CCA-Rd/03 | Improvement of Alami Madrasha-Hazigonj School UNR road by BC at Ch:00-965m. (ID.509545057) Under Lalmohan | 509255057 |  | 0.96 |  |  |  | 4344730 | 4344742 | M/s Bhaya Enterprise | 24.07.14 | 30.07.14 | 24.12.14 | 21/11/15 | 100% | 4344741 | 100% | 0 | FBP | Lalmohan | 1
4 | BDRIDP/Bho/ LAl/CCA-Rd/04 | Improvement of UZR Lordhardings-Dhaligournagor Border-Hafizuddin Bazer road By BC at Ch:1730-2590m. (ID No.509544055) Under Lalmohan Upazila. | 509254055 |  | 0.86 |  |  |  | 3281655 | 3589969 | Md. Iqbal Hossain | 24.07.14 | 30.07.14 | 9.12.14 | 18/06/15 | 100% | 3589710 | 99.99% | 0 | FBP | Lalmohan | 259
5 | BDRIDP/Bho/ LAl/CCA-Rd/05 | Improvement of Chatla Bazar UZR-Shambhupur (Tazumuddin Border) road by BC at Ch.4070-5270m. (ID No. 509544015) Under Lalmohan Upazila. | 509254015 |  | 1.2 |  |  |  | 5132643 | 4976604 | Md. Zakir Hossain Mia | 24.07.14 | 30.07.14 | 07.01.15 | 17/02/16 | 100% | 4976604 | 100% | 0 | FBP | Lalmohan | 0
6 | BDRIDP/Bho/ LAl/CCA-Rd/06 | Improvement of Chatla Bazar UZR-Shambhupur (Tazumuddin Border) road by BC at Ch.5270-6500m. (ID No. 509544015) Under Lalmohan Upazila. | 509254015 |  | 1.23 |  |  |  | 5482489 | 5482504 | M/s Sirajia Enterprise | 24.7.14 | 30.07.14 | 29.12.14 | 13/05/17 | 100% | 5482208 | 99.99% | 0 | FBP | Lalmohan | 296
7 | BDRIDP/Bho/ LAl/CCA-Rd/07 | Improvement of UNR 3012 (Asrafia C/C)-Dider Mosque (UNR 3003) via Anisol Miar Bazar road by BC at Ch.00-1085m (ID No. 509544045) Under Lalmohan Upazila. | 509254045 |  | 1.085 |  |  |  | 3408918 | 4818363 | Md. Iqbal Hossain | 24.7.14 | 30.07.14 | 31.12.14 | 2015-10-06 | 100% | 4818363 | 100% |  | FBP | Lalmohan | 0
8 | BDRIDP/Bho/ LAl/CCA-Rd/08 | Improvement of UNR 3012 (Asrafia C/C)-Dider Mosque (UNR 3003) via Anisol Miar Bazar road by BC at Ch.1085-2135m (ID No. 509544045) Under Lalmohan | 509254045 |  | 1.05 |  |  |  | 4309553 | 4718983 | Md. Iqbal Hossain | 24.7.14 | 30.07.14 | 31.12.14 | 2016-10-06 | 100% | 4718983 | 100% |  | FBP | Lalmohan | 0
9 | BDRIDP/BHO/LAL/CCA-Rd/10 | Improvement of road From North Side Nazirpur-Janata Bazar (Uttar Char Sakhina GPS Connecting road) road by BC from Ch. 1550-2800 (ID ¦No. 509545043) | 509545043 |  | 1.35 |  |  |  | 5359588 | 5351967 | Md. Iqbal Hossain | 26.4.15 | 25.10.15 |  | 22/03/16 | 100% | 5351636 | 99.99% |  | FBP | Lalmohan | 331
10 | BDRIDP/BHO/LAL/CCA-Rd/09 | Improvement of road from (Emankment Bogirchar DC road (Sona Bazar DC-Wapda) By BC from ch. 00-930m (ID No. 509545041) | 509545041 |  | 0.93 |  |  |  | 4318757 | 4317135 | Md. Nazrul Islam Channu | 20.04.15 | 20.04.15 | 20.07.15 | 2016-12-06 | 100% | 4317135 | 100% |  | FBP | Lalmohan | 0
11 | BDRIDP/BHO/LAL/UN-Rd(R)/01 | Rehabilitation of Road from R&H Dabirchar Bazar UNR By BC with U-Drain on RHD-Debir Char Bazar UNR from ch. 8021-8321m (ID No. 50953014) | 50953014 |  | 2 |  |  |  | 4069427 | 4067214 | M/s Santo Enterprise | 20.04.15 | 20.04.15 | 20.07.15 | 28/12/15 | 100% | 3967098 | 100% |  | FBP | Lalmohan | 100116
12 | BDRIDP/Bho/Lal/UN-Rd/02 | Improvement of road from Nazirpur Bazar -Pachim Char Umed Up via Farajgonj UpRoad from Ch 10395-11542m ( ID 509543012) [Lalmohan] | 509543012 |  | 1.147 |  |  |  | 4358068 | 4348068 | Rashuddzaman Piter | 26.01.16 | 26.01.16 | 26.07.16 | 28/03/17 | 100% | 4268466 | 100% |  | FBP | Lalmohan | 79602
13 | BDRIDP/Bho/Lal/CCA-Rd/11 | Improvement of Road by BC on Middle Char Titia Cyclone shelter cum GPS-Kazirabad Border Road from Ch525.00-1910.00m with 2 nos U-Drain at Ch 530.00m and 1130.00m (ID 509545009) | 509545009 |  | 1.385 |  |  |  | 7689999 | 7685334 | Md. Iqbal Hossain | 26.01.16 | 26.01.16 | 26.07.16 | 26/12/16 | 100% | 7687104 | 100% | 0 | FBP | Lalmohan | -1770
14 | lGED/PD/BDRIDP/BHO/Lal/UN-Rd/(R)-03 | Improvement of Road from Nazirpur Bazar -Paschim Char UmedUP via Farajgonj UP Union Road at Ch.8465.00-9600.00m( ID 509543012) | 509543012 |  | 1.135 |  |  |  | 6835897 | 5700619 | Md. Bahalul Karim |  | 17.11.16 | 16.11.17 | 2018-01-02 | 100% | 5646951 | 100% |  | FBP | Lalmohan | 53668
15 | BDRIDP/BHO/LAL/CCA-Rd/12 | a Improvement of Road from UZR 2002 Ramagang Master Bazar Siddique Miar Pole Bazar-New Muguria UNR 3001 via Bangla Bazar from ch. 0.00m-1305.00m. ID No. 509544014b Construction of 1 No. 1.50mx1.50m W-5.5m Size Box Culvert on same Road at CH. 633mc Construction of 3 Nos 0.75mx0.75m W-5.5m Size Box Culvert on same Road at Ch. 833m 1044m & 1163. | 509544014 |  | 1.305 |  |  |  | 9053288 | 9051000 | Md. Iqbal Hossain | 05.06.17 | 28.9.17 | 27.6.18 | 20/06/18 | 100% | 5560000 | 61.43% | 3469954 |  | Lalmohan | 3491000
16 | BDRIDP/BHO/LAL/CCA-Rd/13 | a Improvement of Road from Noboni Brick field-UNR 3013 via Salim Member Bari & Samsol Haque GPS Noboni Brick field-Pangasia Border via UNR 3013 Pangasia Nuria School College from ch. 0.00m-1000.00m. ID No. 509544034b Construction of 1 No. 1.50mx1.50m W-5.5m Size Box Culvert on same Road at CH. 680mc Construction of 1 No. 0.75mx0.75m W-5.5m Size Box Culvert on same Road at Ch. 882m. | 509544034 |  | 1 |  |  |  | 6641239 | 6641000 | Md. Iqbal Hossain | 05.06.17 | 28.9.17 | 27.6.18 | 15/10/18 | 100% | 6635304 | 99.91% | 0 | FBP | Lalmohan | 5696
17 | BDRIDP/BHO/LAL/CCA-Rd/14 | a Improvement of Road from Bhola Charfession RHD Mohazon Bari Pawra Park road from ch. 0.00m-445.00m. ID No. 509544043b Construction of 3 Nos. 0.75mx0.75m W-5.5m Size Box Culvert on same Road at Ch. 55m 270m & 370m. | 509544043 |  | 0.445 |  |  |  | 3390745 | 3390737 | Md. Iqbal Hossain | 05.06.17 | 28.9.17 | 27.3.18 | 15/09/16 | 100% | 3098526 | 91.38% | 0 | FBP | Lalmohan | 292211
18 | BDRIDP/BHO/LAL/CCA-Rd/15 | Improvement of road from Idris Matubber bari Mosque-Dewtola School Road H/O Idris Matabber Bari Mosque-Towards South Direction Mehergonj-Dewalkandi SchoolID No. 509545263aEarth Work Ch.00-720mbCarpeting DC Ch. 00-720mcU-Drain 01 no. 1.5mx1.5m Box Culvert at Ch.522m & 2 nos. 0.75x0.75m Box Culvert at ch 260m 718m. | 509545263 |  | 0.72 | 3 |  |  | 6367968 | 6365420 | Md. Mohasin Nagar | 01.08.18 | 9.08.18 | 01.08.19 | 30/07/19 | 100% | 6363227 | 99.97% | 0 | FBP | Lalmohan | 2193
19 | BDRIDP/BHO/LAL/UN-Rd (R)/04 | A Maintenance work of Char Betua UPC-Raychand GC Road ID No. 509543001 B Maintenance work of Lalmohan Chowmohoni Karterhat East Road ID No. 509543002 | 509543002 |  | 2.782 | 2.25 |  |  | 11479372 | 11453932 | Md. Asadullah | 8.7.19 | 20.7.19 | 7.7.20 | 20/1019 | 100% | 11432700 | 99.81% |  | FBP |  | 21232
20 | BDRIDP/BHO/LAL/UZ- Rd (R)/01 | A .Improvement of Dowri Bazar Khasherhat GC Road Lalmohan Part Ch 00-700m ID No. 509542005 B Mongol Sikder GC Bazar- Betua RHD via Lordharding UP Road Lalmohan PartCh 130650-14365m ID No. 509542009 | 509542009 |  | 2 |  |  |  | 10031949 | 10016535 | Md. Asadullah | 8.7.19 | 20.7.19 | 7.7.20 | 30.01.20 | 100% | 6200000 | 61.9% | 3804891 |  |  | 3816535
21 | BDRIDP/BHO/LALCCA-Rd/17 | A Improvement of Shada Pole Bazar RHD UZR 2002 Neyamatopur GPS & Balamchar road. Road Id no.509544035 a Earth work Ch. 715-1880m b Carpeting DC Ch. 715-1880m c Constructionof 02 nos. 0.75x0.75m Culvert at Ch.850m & 1685m 01 no. 1.50x1.50m Box Culvert at Ch. 1396m d Palisiding 163mB Improvement of Shikderhat-Gazaria Berri Bandh road H/O Karim uddin Bepari via Janota Bazar road. Road Id no.509544044 a Earth work Ch. 590m-1400m b Carpeting Ch. 590-1400m c Construction of 01 nos. 1.50x1.50m Box Culvert at Ch. 971m & 1 no. 0.75x0.75m Culvert at Ch.1350m d Palisiding 1743m | 4035 4044 |  | 1.941 | 6.25 |  |  | 16822358 | 14638506 | M/S Sayem Enterprise | 27.04.20 | 05.05.20 | 30.06.20 |  | 60% | 1040000 | 7.105% | 13598506 |  |  | 13598506
22 | BDRIDP/BHO/LAL/CCA-Rd/16 | A Improvement of Kartar Hat bhola-Charfession RHD- Chawmohoni Bazer road. Road Id no.509544022 a Earth work Ch. 1200m-1700m b Carpeting DC Ch.1200m-1700m c Palisiding 20mB Improvement of Mozammol Haque road-Farajigonj Nesaria Madrasha via Chan Gazi Hawlader Road Id no.509545140 a Earth work Ch.00m-1003m b Carpeting Ch.00-1003m c Construction of 01 nos. 2.50x2.50m Box Culvert at Ch. 145m & 1 no. 0.75x0.75m Culvert at Ch.5710m d Palisiding 350m | 4022 |  | 1.503 | 3.25 |  |  | 13735642 | 13734672 | M/s Santo Enterprise | 17.9.19 | 25.9.19 | 16.3.20 |  | 100% | 12650880 | 92.11% | 1060213 |  |  | 1083792
23 | BDRIDP/BHO/LAL/CCA-Rd/18 | A Improvement of Karim Gonji Bazar-Shambhupur via Shazi Chomohoni IZR 2003 H/O Moslehuddin- Shambhupur via Karimganj GPS & Master Bazar road. Road Id no.509544053 a Earth work Ch. 500m-1480m b Carpeting DC Ch.500m-1480mm c Construction of 01 nos. 1.50x1.50m Box Culvert at Ch. 0m & 3 nos. 0.75x0.75m Culvert at Ch.1010m1085m & 1428m d Palisiding 75m | 4053 |  | 0.98 | 3.25 |  |  | 8884551 | 8480320 | M/s Alam Trading Corporation | 17.9.19 | 25.9.19 | 16.3.20 |  | 30% | 780000 | 9.198% | 7700320 |  |  | 7700320
24 | BDRIDP/BHO/LAL/UN-RD/05 | Improvement of Parchim Char Umed UPC-Kalir Take Bazar via Balacharkandi GPS Road Id no.509543017 a Earth work Ch. 3627-4627m b Carpeting DC Ch. 3627-4627m c Construction of 06 nos. 0.75x0.75m Box Culvert at Ch.3690m 3990m 4070m 4155m 4247m 4556m d Palisiding152m | 3017 |  | 1 | 4.25 |  |  | 9204918 | 8744672 | M/s Howlader Construction | 10.03.20 | 17.03.20 | 12.06.20 |  | 50% | 650000 | 7.433% | 8094672 |  |  | 8094672
25 | BDRIDP/BHO/LAL/UN-Rd/06 | Maintenance work of Lalmohon Chowmohoni - Balurchar Bazar Road at Ch. 1360m - 1925m. [Road ID No. 509543004] (a) Earth work at Ch. 1360m - 1925m (b) Carpeting (DC) at Ch. 3100m - 4100m (c) Construction of 04 nos. 0.75m x 0.75m RCC Box Culvert at Ch. 1438m, 1670m, 1780m & 1912m. (d) Palisading 74m | 3004 |  | 1.565 | 3 |  |  | 3995763 | 3795975 | M/s Madina Enterprise | 04.03.20 | 13.3.20 | 03.8.20 | 15.05.20 | 100% | 1556989 | 41.02% | 2233256 |  |  | 2238986
25 | Lalmohan (Road Work) Sub-Total |  |  | 0 | 31.518 | 25.25 | 0 | 0 | 165754201 | 163357070 | Amount Spent (Tk) 18: 122779410; In (%) 20: 39961812 | 40577660
| Lalmohan (Structure Work) | [20 empty] | 0
1 | BDRIDP/Bho/ LAl/CCA-St/01 | (a) Construction of 1.50mx1.50m Size RCC Box culvert on Munshir Hawla (H/O Dulu Miah)-Patowary Bari-Dewan bari via Hazi Solyman RNGPS at Ch.4590m (ID No.509545081) (b) Construction of 1.50mx1.50m Size RCC Box culvert on Pangashia H/O Iddris Khalifa-Berri bandh (Jobeda road) via Pangasia Bazar road at Ch.4700m and 04(Four) nos U-drain at Ch.3452m, 5970m, 4040m & 4300m. (ID No.509544050) (c) Construction of 1.50mx1.50m RCC Box culvert on Chatla Bazar UZR-Shambhupur (Tazumuddin Border) road (Ch.5252m and 02(Two) nos U-Drain at Ch.4335m & 5099m (ID No. 509544015) (d) Construction of 1.50mx1.50m RCC Box Culvert and 05(Five) nos U-drain on UnR 3012 (Asrafia C/C)-Dider Mosque (UNR 3003) via Anisol Miar Bazar road at Ch.705, 65m, 206m 450m, 635m & 942m. (ID No.509544045). under Lalmohan upazila. | 509184045 |  |  | 14.25 |  |  | 2215500 | 2214502 | M/s ma money Enterpise | 21.11.14 | 28.11.14 | 19.01.15 | 25/06/15 | 100% | 2213974 | 99.98% |  | F.B.P | Lalmohan | 528
2 | BDRIDP/BHO/LAL/CCA-St/06 | Construction of 2x4.00mx3.50m (W-3.7) RCC Box culver Over Khal infront Radha Gobinda Mondir Under Ramagonj UP road. (ID No. 509545229) | 509545229 |  |  | 8 |  |  | 1742060 | 1733183 | Md. Iqbal Hossain | 26.4.15 | 25.07.15 |  | 22/01/16 | 100% | 1733005 | 99.99% | 0 | FBP | Lalmohan | 178
3 | BDRIDP/Bho/Lal/CCA-St/07 | Construction of 3x4.00mx4.50m (W-3.7) RCC Box culver Over Khal infront of Shabuddin Jomadder Bari and Badarpur GPS at Badarpur UP road. (ID No. 509545233) | 509545233 |  |  | 12 |  |  | 2746479 | 2717207 | Md. Iqbal Hossain | 26.4.15 | 25.10.15 |  | 2015-06-10 | 100% | 2717039 | 99.99% | 0 | FBP | Lalmohan | 168
4 | BDRIDP/Bho/Lal/CCA-St/08 | Construction of 3x4.00mx4.50m RCC Box culver Over Khal infront H/O Golam Rahman at Char Bhuta UP Word No.04 (Four) road. (ID No. 509545227) | 509545227 |  |  | 12 |  |  | 2746479 | 2723954 | M/s Sarazia Enterprise | 08.04.15 | 10.04.15 | 08.10.15 | 27/12/15 | 100% | 2721949 | 99.93% | 0 | FBP | Lalmohan | 2005
5 | BDRIDP/Bho/Lal/CCA-St/09 | Construction of 2x4.00mx3.50m (W-4.26m) RCC Box culver Over Tegasia Khal adjacent H/O Hakkunia at Ramagonj UP road. (ID No. 509545230) | 509545230 |  |  | 8 |  |  | 1569299 | 1560421 | Md. Akter Hossain | 23.4.15 | 23.4.15 | 22.07.15 | 2016-12-02 | 100% | 1559900 | 99.97% |  | FBP | Lalmohan | 521
6 | BDRIDP/Bho/Lal/CCA-St/10 | Construction of 3x4.00mx4.50m(W-3.70m) RCC Box culver Over Khal adjacent North of H/O Humayun Miah at Bawria Under Dhaligournagar UP road.(ID No. 509545234) | 509545234 |  |  | 12 |  | ` | 2746479 | 2717209 | M/s Bhaya Enterprise | 26.4.15 | 26.4.15 | 25.10.15 | 2015-10-10 | 100% | 2694312 | 100% |  | FBP | Lalmohan | 22897
7 | BDRIDP/Bho/Lal/CCA-St/11 | Construction of 2x4.50mx3.50m (W-3.70m) RCC Box culver Over Khal adjacent H/O Rajjak Miah Word No. 05 (Five) at Lalmohan Up road .(ID No. 509545231) | 509545231 |  |  | 9 |  |  | 1662469 | 1644142 | M/s Bhaya Enterprise | 15.4.15 | 15.4.15 | 14.10.15 | 23/07/15 | 100% | 1644062 | 100% | 0 | FBP | Lalmohan | 80
8 | BDRIDP/Bho/Lal/CCA-St/12 | Construction of 2x4.50mx3.50m (W-3.70) RCC Box culver Over khal adjacent H/O Khalek Miah Work No 09 (Nine) at Lalmohan UP road (ID No 509545228) | 509545228 |  |  | 9 |  |  | 1662469 | 1653310 | Md. Akter Hossain | 23.4.15 | 23.4.15 | 22.07.15 | 22/01/16 | 100% | 1638884 | 100% | 0 | FBP | Lalmohan | 14426
9 | BDRIDP/Bho/Lal/CCA-St/13 | Construction of 4x4.50mx5.00m (W-3.70m) RCC Box culver Over Katakhali Khal infront Jugi Bari Word No 06 (six) at Faragonj UP road (ID No. 509545067) | 509545067 |  |  | 18 |  |  | 3369006 | 3346129 | M/s Ma moni Enterprise | 01.04.15 | 01.04.15 | 01.10.15 | 2015-05-07 | 100% | 3321795 | 100% |  | FBP | Lalmohan | 24334
10 | BDRIDP/BHO/LAL/CCA-St/14 | Construction of 4x3.50mx3.50m (W-3.70m) RCC Box culver Over Balur Char Khal infront H/O Julfiker Miah Counsilor Word No 06 (six) at kalma UP road. (ID No. 509545232) | 509545232 |  |  | 14 |  |  | 2151033 | 2077473 | M/s Bhaya Enterprise | 15.4.15 | 15.4.15 | 14.10.15 | 2015-10-05 | 100% | 2073570 | 99.81% | 0 | FBP | Lalmohan | 3903
11 | BDRIDP/Bho/Lal/CCA-St/05 | Construction of 2x4.00mx3.50m (W-3.70m) RCC Box culver Over Arojbaki khal Infront H/O Lakman memver under Dhaligoournagar Up road (ID No. 509545128) | 509545128 |  |  | 8 |  |  | 1742060 | 1733183 | Md. Akter Hossain | 23.4.15 | 23.4.15 | 22.07.15 | 20/03/16 | 100% | 1732680 | 99.97% | 0 | FBP | Lalmohan | 503
12 | BDRIDP/Bho/Lal/CCA-St/04 | Construction of 2x4.50mx3.50m(W-3.7m) RCC Box culver Over khal adjacent West Side H/O Salauddin Member at Nazirpur-Parchim Char Umed via Farajgonj Up road (ID No. 509544006) | 509544006 |  |  | 9 |  |  | 1678642 | 1669483 | Md. Akter Hossain | 23.4.15 | 23.4.15 | 22.07.15 | 2017-12-06 | 100% | 1669335 | 99.99% | 0 | FBP | Lalmohan | 148
13 | BDRIDP/BHO/LAL/CCA-St/03 | Construction of 02 Nos 1.5mx1.5m RCC Box Culvert & 04 Nos U-Drain on North Side Nazirpur-JANata Bazar (Uttar Char Sakhina GPS Connectiong road) at Ch. 1737m, 2414m, 1580m, 2005m, 2160m & 2795m (ID No. 509545043) | 509545043 |  |  | 6 |  |  | 1103062 | 1101067 | Md. Iqbal Hossain | 26.4.15 | 26.4.15 | 25.7.15 | 2018-01-10 | 100% | 1098541 | 99.77% | 0 | FBP | Lalmohan | 2526
14 | BDRIDP/BHO/LAL/CCA-St/02 | Construction of road from 1 no 1.50mx1.50m (3.70m width) RCC Box Culvert & 1no U-Drain on Embankment Bogirchar DC road (Sona Bazar DC-Wapda) at ch. 840m & 575m. (ID No. 509545041) | 509545041 |  |  | 2.5 |  |  | 435114 | 434196 | Md. Nazrul Islam Channu | 20.04.15 | 20.04.15 | 20.07.15 | 25/10/18 | 100% | 434196 | 100% |  | FBP | Lalmohan | 0
15 | (BDRIDP/Bho/Lal/UN-St/01 (31556) | Construction of 1 nos 1.50mx1.50m ( 5.0m) Box Culvert & 3 nos U drain on Nazirpur Bazar-Pachim Char Umed Up via Farajgonj UP Union Road At Ch. 10710m, 10881m,11125m &11413m (ID no 50953012) [Lalmohan] | 50953012 |  |  | 3.75 |  |  | 768999 | 703144 | Md. Rashaduzzman | 26.1.16 | 26.1.16 | 26.3.16 |  | 100% | 702770 | 99.95% |  | FBP | Lalmohan | 374
16 | lGED/PD/BDRIDP/BHO/UN-St /-02 | Construction of 10.00m long RCC Bridge on Nazirpur Bazar -Paschim Char Umed UP via Farajgonj UP Union Road at Ch.8505.00m( ID 509543012) | 509543012 |  |  | 10 |  |  | 8130719 | 6749022 | Md. Bahalul Karim |  | 17.11.16 | 16.11.17 |  | 100% | 6711332 | 100% |  | FBP | Lalmohan | 37690
17 | BDRIDP/BHO/LAL/CCA-ST/15 | Construction of 3.00 x 4.00 x 4.50m W.370m RCC Box Culvert Nurunnavi Chowdhaury Sarak Bounia GPS road Over khal adjacent west side of Humauan mia bari at Ch. 1415m Lalmohan upazila Bhola 509544052 | 509544052 |  |  | 12 |  |  | 3680028 | 3678262 | Md. Jakir Hossain | 2018-03-04 | 2018-10-03 | 2.11.18 |  | 100% | 3485214 | 94.75% | 0 | FBP | Lalmohan | 193048
18 | BDRIDP/BHO/LAL/CCA-ST/16 | Construction of 3.00 x 4.00 x 4.50m W.370m RCC Box Culvert Nurunnavi Chowdhaury Sarak Bounia GPS road Over khal adjacent west side of Abdul Haque mia bari at Ch. 1565m Lalmohan upazila Bhola | 509544052 |  |  | 12 |  |  | 3921376 | 3919490 | Md. Jakir Hossain | 2018-03-04 | 2018-10-03 | 2.11.18 | 30.11.18 | 100% | 3707826 | 94.6% | 0 | FBP | Lalmohan | 211664
18 | Lalmohan(Structure Work) Sub-Total |  |  | 0 | 0 | 179.5 | 0 | 0 | 44071273 | 42375377 | Amount Spent (Tk) 18: 41860384; In (%) 20: 0 | 514993
43 | Lalmohan Upazila Sub-Total |  |  | 0 | 31.518 | 204.75 | 0 | 0 | 209825474 | 205732447 | 15: 0; Amount Spent (Tk) 18: 164639794; In (%) 20: 39961812 | 41092653
| Upazila : Tazumuddin (Road Work) | [20 empty] | 0
1 | BDRIDP/BHO/ TAZ/CCA-Rd/01 | Improvement of Road from Nuria GPS Chandpur cum Cyclone Shelter (Mozammal Member bari to Muchibari-Shibpur Khaserhat UZR) Road from Ch.1200.00-1500.00m (ID 509915032) | 509915032 |  | 0.3 |  |  |  | 2105884 | 2106329 | Md. Iqbal Hossain | 5.6.16 | 5.6.16 | 5.6.17 | 2019-10-06 | 100% | 2078322 | 98.67% |  | FBP | Tazumuddin | 28007
2 | BDRIDP/BHO/ TAZ/ CCA-Rd/02 | Improvement of road From Chandpur karim GPS Cum Cyclone Shelter Tazumuddin College-Mezi Bari via Karim GPS ID No. 509915014.a Earth Filling from Ch. 1000m-2700m.b Bituminous Carpeting from Ch. 1000m-2700m.c Construction for 2 Nos 3m x 3m RCC Box Culvert at Ch. 1420m & 2115m and 1 No 1.5m x 1.5m RCC Box Culvert at Ch. 2320m. [Tazumuddin] | 509915014 |  | 1.7 |  |  |  | 14499711 | 14476264 | Md . Mahasin Nagor | 15.2.18 | 18.2.19 |  |  | 100% | 14422261 | 99.63% | 0 | FBP | Tazumuddin | 54003
3 | BDRIDP/BHO/TAZ/GC/01 | Improvement of Shashigonj Bazar. Garbage Pit Open Sales Platform (RCC), CC Road, RCC, U –Drain, Deep Tube Well and MMC Office | Bazar | [5 empty] | 4950674 | 4703140 | M/s Urmi Traders , Barisal | 17.02.19 | 16.08.19 | 5.3.20 | 2020-10-03 | 100% | 4657616 | 99.03% |  | FBP | Tazumuddin | 45524
4 | BDRIDP/BHO/TAZ/CCA-Rd/03 | A Improvement of Harun Dalal House to taragazi School Feregikandi Road Ch-00-700m ID-59914026 B Improvement of South Kayamulla Road Ch-2200-2965 ID-59915008 | 59914026 59915008 |  | 1.465 |  |  |  | 12792958 | 12125742 | M/s Sarazia Enterprise | 11.7.19 | 21.7.19 | 10.7.20 |  | 90% | 7952137 | 65.58% | 4173605 |  | Tazumuddin | 4173605
5 | BDRIDP/BHO/TAZ/UZ- Rd (R)/01 | Improvement of Tazumuddin Hospital RHD_Dowari GC Via Khaserhat GC & Bangla Bazar Road Ch. 5810-7898m 509912003 | 2003 |  | 2.008 |  |  |  | 7174404 | 7170816 | M/s Bikarampur Enterprise | 17.6.19 | 21.6.19 | 16.12.19 |  | 100% | 7163346 | 99.9% |  | FBP | Tazumuddin | 7470
6 | BDRIDP/BHO/TAZ/CCA-RD/04 | Improvement of Thakur Bazar UZR-Bangla Bazar UZR via Anil Shadur Asram Road. Road Id no.509544015a Earth work Ch. 2300m-3000m b Carpeting DC Ch. 2300m-3000m c Construction of 02 nos. 1.50x1.50m Box Culvert at Ch.2616m2755m d Palisiding179m | 4015 |  | 1 | 3 |  |  | 6685914 | 6351618 | M/S S. B Corporaration bhola | 17.9.19 | 25.919 | 16.03.20 |  | 100% | 4180000 | 65.81% | 2168250 |  | Tazumuddin | 2171618
6 | Tazumuddin (Road Work) Sub-Total |  |  | 0 | 6.173 |  |  |  | 48209545 | 46933909 | Amount Spent (Tk) 18: 40453682; In (%) 20: 6341855 | 6480227
Upazila: Charfession (Road Work) | [21 empty] | 0
1 | BDRIDP/Bho/CF/UN-Rd/02 | Improvement of road from Nilkamal UP (Ghosherhat) Hazir hat (Maya river) road, Ch: 00-3000m. under Charfession | 509253016 |  | 3 |  |  |  | 23470345 | 26125358 | M/S Khan Traders | 22.04.14 | 22.04.14 | 21.04.15 | 2015-06-05 | 100% | 26103819 | 99.92% | 0 | FBP | Charfession | 21539
2 | BDRIDP/Bho/CF/UN-Rd/03 | Improvement of road from Zinnagor UP- Dularhat- Hazirhat via Abdullah pur UP road, Ch: 1100-3100m. under Charfession upazila. | 509253040 |  | 3 |  |  |  | 16551993 | 18017499 | M/S Rubel Enterprise | 22.04.14 | 22.04.14 | 21.04.16 | 2015-12-01 | 100% | 18015435 | 99.99% |  | F.B.P | Charfession | 2064
3 | BDRIDP/Bho/CF/UN-Rd/04 | Improvement of road from RHD- Kaliakandi GPS Jalil road- Dinar Kheyaghat via Bhuyarhat road, Ch: 00-2000m. under Charfession upazila. | 509253026 |  | 2 |  |  |  | 13881822 | 15128965 | M/S. Sayem Enterprise | 22.04.14 | 22.04.14 | 21.01.15 | 28/02/16 | 100% | 15127579 | 99.99% | 0 | FBP | Charfession | 1386
4 | BDRIDP/Bho/CF/CCA-Rd/03 | Improvement of Approach road Kuchia mara 2No. GPS cum Cyclone shelter, Ch: 00-1160m. under Charfession | 509254101 |  | 1.16 |  |  |  | 9637731 | 10790625 | M/S. Jasim Construction | 22.04.14 | 22.04.14 | 21.10.14 | 20/10/15 | 100% | 10784568 | 99.94% | 0 | FBP | Charfession | 6057
5 | BDRIDP/Bho/CF/UN-Rd/01 | Improvement by Earth Filling on Charfession college road- Panirkal via Ginnagor balok rasta, ch: 1450-4450m (ID: 509253054) under Charfession | 509253054 |  | 3 |  |  |  | 21188882 | 24079263 | Md. Unos Al Mamun | 22.4.14 | 21.4.15 |  | 2015-01-01 | 100% | 24075189 | 99.98% |  | FBP | Charfession | 4074
6 | BDRIDP/Bho/CF/CCA-Rd/02 | Improvement of road from adjacent Charfassion upazila reserve Pukur, Ch: 186-238m. under Charfession upazila. |  |  | 0.052 |  |  |  | 2837186 | 2837186 | M/s Jashim Construction | 07.07.14 | 11.01.15 |  | 23/03/14 | 100% | 2837189 | 100% |  | FBP | Charfession | -3
7 | BDRIDP/Bho/ CF/CCA-Rd/04 | Improvement of Samraj-Chairman Bazar old Embk. road to Khajurgachia Bazar (New Embk.) road at Ch. 00-2500m (ID No.509254106) under Charfession Upazila. | 509254106 |  | 2.5 |  |  |  | 12791520 | 12794151 | Md. Iqbal Hossain | 07.07.14 | 11.01.15 |  | 18/09/15 | 100% | 12792990 | 99.99% | 0 | FBP | Charfession | 1161
8 | BDRIDP/Bho/ CF/CCA-Rd/05 | Improvement of Samraj-Chairman Bazar old Embk. road to Khajurgachia Bazar (New Embk.) road at Ch.2500-5050m. (ID No.509254106) under Charfession Upazila. | 509254106 |  | 2.55 |  |  |  | 12174948 | 12174042 | Md. Iqbal Hossain | 11.1.15 | 10.01.16 |  | 15/11/15 | 100% | 12172042 | 99.98% | 0 | FBP | Charfession | 2000
9 | BDRIDP/Bho/CF/CCA-Rd/06 | Improvement of road from Jahanpur Mykel Modhus hondha abason (Asrayan) Connecting road by BC from Ch. 2948-3248m & 4080-4856m. (ID No. 509254108) under Charfession Upazila. | 509254108 |  | 3.776 |  |  |  | 3875188 | 3852744 | M/s Malin Traders | 10.11.14 | 16.11.14 | 10.1.15 | 30/01/15 | 100% | 3849948 | 99.93% |  | FBP | Charfession | 2796
10 | BDRIDP/Bho/CF/UN-Rd(R)/05 | Rehabilitationof road from Dularhat road (Nurabad UP office)- Gachir Khal road By BC from Ch. 1524m from 00-540m (ID No.509253038) Under Charfession Upazila. | 509253038 |  | 0.95 |  |  |  | 990205 | 988027 | Badul kasno Devnath | 17.11.14 | 20.11.14 | 17.01.15 | 2015-08-06 | 100% | 985244 | 99.72% |  | F.B.P | Charfession | 2783
11 | BDRIDP/Bho/CF/CCA-Rd/09 | Improvement of road from Munshir Hat-Kasem Mier hat (Lanch ghat) road by BC from ch.1000-2645m. (ID No. 509254004) Under Charfession Upazila. | 509254004 |  | 1.645 |  |  |  | 7728835 | 7613065 | M/s Jashim Const. | 17.11.14 | 20.11.14 | 17.01.15 | 2015-08-02 | 100% | 7610930 | 99.97% |  | F.B.P | Charfession | 2135
12 | BDRIDP/Bho/CF/UN-Rd/06 | Improvement of road from Nilkomal UP (Ghosherhat) Hazirhat (Maya River) by BC from Ch: 9630-11410m (ID No: 509253016) Under Charfession Upazila. | 509253016 |  | 1.81 |  |  |  | 9687175 | 9648664 | M/s unous Al mamun | 17.11.14 | 20.11.14 | 17.01.15 | 2015-08-02 | 100% | 9645845 | 99.97% |  | FBP | Charfession | 2819
13 | BDRIDP/Bho/CF/CCA-Rd/08 | Improvement of road from Nayber Bridge Bacharkandi-Shashibussion Gazaria road by BC from Ch.3310-4046m with 3Nos 0.75mx0.75m RCC Box Culvert at Ch. 3681m, 3750m & 4016m (ID No. 509254001) Under Charfession Upazila. | 509254001 |  | 0.736 |  |  |  | 4510569 | 4479423 | M/s Bangol Traders | 25.01.15 | 25.06.15 |  | 2015-10-03 | 100% | 4477004 | 99.95% |  | FBP | Charfession | 2419
14 | BDRIDP/Bho/CF/CCA-Rd/07 | Improvement of road from Janata Bazar Bhuierhat road (Nurul Haque Shop)-Osmangonj Aslampur Border road via Aligow CPB (Easin road) by BC from Ch: 00-1570m (ID No. 509254107) under Charfession Upazila. | 509254107 |  | 1.57 |  |  |  | 8585620 | 8543070 | M/s Jashim Const. | 01.12.14 | 01.03.15 |  | 20/10/15 | 100% | 8540698 | 99.97% | 0 | FBP | Charfession | 2372
15 | BDRIDP/Bho/CF/UN-Rd(R)09 | Rehabilitation of road from Charfassion (Kutubhonj)-Char Madraj UP Road) road By BC from Ch.2760-3480m. (IDNo.509253008) | 509253008 |  |  |  |  | 0.72 | 1825805 | 1819415 | M/s Babul Traders | 5.4.15 | 5.6.15 |  | 14/06/15 | 100% | 1752098 | 100% |  | F.B.P | Charfession | 67317
16 | BDRIDP/Bho/CF/UN-Rd(R)10 | Rehabilitation of road from Charfassion Betua Road - Char Madraj UP road By BC from Ch.2410 - 3300m.(ID No.509213029) | 509253029 |  |  |  |  | 0.89 | 1918565 | 1910890 | M/s Monir Enterprise | 5.4.15 | 15.6.15 |  | 16/05/15 | 100% | 1910889 | 100% |  | F.B.P | Charfession | 1
17 | BDRIDP/Bho/CF/CCA-Rd(R)12 | Rehabilitation of road from Madraj UP - (Keramotgonj Natun Moszid)-Shamraj Bazar ( road By BC from Ch.00 - 2265m. (ID No. 509254109) | 509254109 |  |  |  |  | 2.265 | 4753930 | 4744874 | M/s Bangol Traders | 5.4.15 | 5.7.15 | 25/3/18 | 25/03/16 | 100% | 4740758 | 99.91% |  | F.B.P | Charfession | 4116
18 | BDRIDP/BHO/CF/UN-Rd(R)/08 | Rehabilitation of road from Hazarigonj Beribadh - North side of Aslampur road from Ch: 4200-6400m Under Char Madraj Union (ID No.509253057) | 509253057 |  |  |  |  | 2.2 | 5017853 | 5000290 | M/s Boksi Enterprise | 5.4.15 | 5.7.15 |  | 2015-12-05 | 100% | 5000290 | 100% |  | FBP | Charfession | 0
19 | BDRIDP/BHO/CF/UN-Rd(R)/12 | Rehabilitation of road from Madraj UP (Keramotgonj bazar)-Abugonj bazar road (Keramotgonj bazar connecting ) from ch.00m-690m Under Char Madraj Union (ID No.509253060) | 509253060 |  |  |  |  | 0.69 | 2133273 | 2124739 | M/s Milon Traders | 5.4.15 | 20.6.15 |  | 15/06/15 | 100% | 2122742 | 99.91% |  | FBP | Charfession | 1997
20 | BDRIDFVBHO/CF/UN-Rd(R)/07 | Rehabilitation of road from Hazarigonj Beribadh - North side of Aslampur road from Ch: 6400-8690m (ID No.509253057) under Charfession. | 509253057 |  |  |  |  | 2.29 | 3702022 | 3689062 | Md. Fakrul Islam | 5.4.15 | 15.6.15 |  | 2015-10-05 | 100% | 3689055 | 100% |  | F.B,P | Charfession | 7
21 | BDRIDFVBHO/CF/CCA-Rd(R)/10 | Rehabilitation of road from Madraj Shamrajdone road Paterikandi-Hazarigonj Embk road by BC from Ch:00-2700m (ID No. 509254021) under Charfession. | 509255402 |  |  |  |  | 2.7 | 9201845 | 9201145 | Younus Al Mamun | 5.04.15 | 5.07.15 |  | 28/03/16 | 100% | 7652989 | 100% |  | F.B,P | Charfession | 1548156
22 | BDRIDFVBHO/CF/CCA-Rd(R)/11 | Rehabilitation of road from Kashemgonj-East side of Madraj Beribadh road by BC from ch: 1700-3390m (ID No. 509254076). under Charfession. | 509254076 |  |  |  |  | 1.69 | 2884272 | 2875619 | Badul kasno Devnath | 5.4.15 | 20.6.15 |  | 20/05/15 | 100% | 2872477 | 99.89% |  | F.B.P | Charfession | 3142
23 | BDRIDP/Bho/CF/CCA-Rd/17 | Ipmrovement of road from Shashibussion-Anjurhat road nea Chowmouhoni Bazar uttar Mongol GPS road By BC from Ch 00-340m (ID No. 509254113) [Charfession] | 509254113 |  | 0.34 |  |  |  | 2309309 | 2694192 | M/S.Monir Enterprise | 22.07.15 | 22.07.15 | 21.07.16 |  | 100% | 2691225 | 99.89% | 0 | F.B.P | Charfession | 2967
24 | BDRIDP/Bho/CF/CCA-Rd/18 | Improvement of road from Charfession GC-road Kabir shop south Side of Abdullapur (Faruk member house) road By BC frorr Ch.00-1260m. (ID No.509254118) [Charfession] | 509254118 |  | 1.26 |  |  |  | 7769595 | 7767290 | M/s Jashim Const. | 22.07.15 | 22.07.15 | 21.07.16 | 15/06/17 | 100% | 7748162 | 99.75% | 0 | F.B.P | Charfession | 19128
25 | BDRIDP/Bho/CF/CCA-Rd/19 | improvement of road from Charfession GC-road Kabir shop south side of Charfession UZ H/Q Dularhat road near (Haris Dofader Bari Mosjid) By BC from Ch.00-1212m. (ID No.509254119) [Charfession] | 509254119 |  | 1.212 |  |  |  | 6906787 | 6905968 | Ms.Khan Traders | 22.07.15 | 22.07.15 | 21.07.16 | 21/03/16 | 100% | 6903708 | 99.97% | 0 | FBP | Charfession | 2260
26 | BDRIDP/Bho/CF/CCA-Rd/12 | improvement of road from Miagir Khamar RHD road south side of latra khal near of nurul Islammeter hopuse road By BC from Ch.00-785m. (ID No. 509254120) [Charfession] | 509254120 |  | 0.785 |  |  |  | 6264453 | 6264540 | M/S.Monir Enterprise | 22.07.15 | 22.07.15 | 21.07.16 | 2017-06-03 | 100% | 6262136 | 99.96% | 0 | FBP | Charfession | 2404
27 | BDRIDP/Bho/CF/CCA-Rd/21 | Improvement of road from Panirkhal RHD road south side of Kasemgonj .Jahanpur up H/Q road (Zohur Ahammed Jame Mosjid) By BC from Ch.00-1215m. (ID No:509254121) [Charfession] | 509254121 |  | 1.215 |  |  |  | 8231283 | 8221950 | M/S.Jasim Construction | 22.07.15 | 22.07.15 | 21.07.16 | 2016-01-04 | 100% | 8219909 | 99.98% | 0 | FBP | Charfession | 2041
28 | BDRIDP/Bho/CF/CCA-Rd/22 | improvement of road from Farazgonj RHD road Jama Mosjhid Madrasha South side of Kashemgonj Beribadh BC from Ch 00-1045m (ID No.509254122) [Charfession] | 509254122 |  | 1.045 |  |  |  | 6710108 | 6470294 | Ma.Akter Hossain | 22.07.15 | 22.07.15 | 21.07.16 | 25/03/16 | 100% | 6464905 | 99.92% | 0 | FBP | Charfession | 5389
29 | BDRIDP/Bho/CF/CCA-Rd/23 | Improvement of road from RHD road (Slam Patowary house) west side of shashibussion GC Gazaria GC road by BC from 1000- 2115m (ID No. 509254123) [Charfession] | 509254123 |  | 1.69 |  |  |  | 6427932 | 6421181 | M/S.Babul Traders | 22.07.15 | 22.07.15 | 21.07.16 | 18/12/14 | 100% | 6419024 | 99.97% | 0 | FBP | Charfession | 2157
30 | BDRIDP/BHO/CF/UN-Rd/11 | Improvement road from Charfession GC (B.R.D.B.)- Mazirhat (WDB Embak) road By BC from Ch: 650-1960m with 2x4.50mx3.50m RCC Double vent Box culvert at Ch: 650m (ID No. 509253017) [Charfession] | 509253017 |  | 1.31 |  |  |  | 8632746 | 8581096 | Badul kasno Devnath | 22.07.15 | 22.07.15 | 21.07.16 | 2016-02-03 | 100% | 8579030 | 99.98% | 0 | FBP | Charfession | 2066
31 | BDRIDP/BHO/CF/CCA-Rd/13 | Improvement of road from Charfession Dularhat Road-Wapda Embk. Via W-Nurabad GPS road By BC from Ch: 00-920m with 3x4.50x3.50m Three vent RCC Box culvert at Ch: 3.0m and 3Nos 0.75mx0.75m RCC Box culvert at Ch: 240m, 420m, 585m & 810m (ID No. 509254007) [Charfession] | 509254007 |  | 0.92 |  |  |  | 7275478 | 7267813 | M/S.Malin Traders | 22.07.15 | 22.07.15 | 21.07.16 | 2016-05-07 | 100% | 7265560 | 99.97% | 0 | FBP | Charfession | 2253
32 | BDRIDP/BHO/CF/CCA-Rd/14 | Improvement of road from Dularhat Hospital Road-Aminabad Nurabad Barder road By BC from Ch.600- 1210m with 3.00mx3.00m One Vent RCC Box Culvert at ch: 1206m and 1.50mx1.50m RCC Box Culvert at Ch:616m & 0.75mx0.75m RCC Box Culvert at Ch: 904m (ID No.509255077) [Charfession] | 509255077 |  | 0.61 |  |  |  | 4545015 | 4539611 | Md.Bahalul Karim | 22.07.15 | 22.07.15 | 21.07.16 | 2016-02-04 | 100% | 4534242 | 99.88% | 0 | FBP | Charfession | 5369
33 | BDRIDP/BHO/CF/CCA-Rd/15 | Improvement of road from North Aicha Bazar-Embk. via Golkhali Khal road By BC from Ch.00-1300m With 01 no 2x4.50mx3.50m RCC Doulble Vent Box Culvert at Ch.1007 and 4Nos 0.75mx0.75m RCC Box Culvert at Ch.45m, 282m, 540m & 906m. (ID No.509254043) [Charfession] | 509254043 |  | 1.3 |  |  |  | 9103557 | 9103000 | Md.Salauddin Lincon | 22.07.15 | 22.07.15 | 21.07.16 | 2016-03-10 | 100% | 9097498 | 99.94% | 0 | FBP | Charfession | 5502
34 | BDRIDP/BHO/CF/CCA-Rd/16 | Improvement of road from West Side 0 R&H road Vhasanchar Abason Project Via Mowlubi road By BC from Ch.00-1200m With 1no 2x4.50mx3.50m RCC Doulble Vent Box Culvert at Ch.1007m, 1no 3.00mx3.00m One Vent RCC Box Culvert and 3Nos 0.75mx0.75m RCC Box Culvert at Ch.510m, 665m & 804m. (ID No. 509255062) [Charfession] | 509255062 |  | 1.2 |  |  |  | 9821908 | 9816887 | Md.Fakrul Islam | 22.07.15 | 22.07.15 | 21.07.16 | 30/03/17 | 100% | 8186078 | 100% | 0 | FBP | Charfession | 1630809
35 | BDRIDP/BHO/CF/CCA-Rd/24 | Ipmrovement of road from RHD road (Slam Patowary house west side of Shashibussion GC Gazaria GC road By BC from Ch: 00-835m with 4 Nos RCC Box Culvert at Ch.227m, 144m, 480m & 678m (ID No. 509254124) [Charfession] | 509254124 |  | 0.835 |  |  |  | 5901619 | 5892320 | M/s. Sayem Enterprise | 23.07.15 | 23.07.15 | 22.07.16 | 24/09/16 | 100% | 5892227 | 100% | 0 | FBP | Charfession | 93
36 | BDRIDP/BHO/CF/CCA-Rd/25 | Improvement of road from Uttar Aicha RHD road Shashibussion Zaheria Madrasha cum Cyclone selter road By BC from Ch:00-1000m with 4 Nos RCC Box Culvert 104m, 430m, 652m & 918m.(ID No.509254125) [Charfession] | 509254125 |  | 1 |  |  |  | 5979349 | 5978555 | Julfiker Ahamed | 22.07.15 | 22.07.15 | 21.07.16 |  | 100% | 5365999 | 100% | 0 | FBP | Charfession | 612556
37 | BDRIDP/BHO/CF/CCA-Rd/26 | Improvement of road from Kalmi Bridge South side of Uttar Aicha Bazar Rasulpur UP RHD road By BC from Ch.3550-4170m. with 2 Nos RCC Box Culvert at Ch. 4151m & 3585n No.509254126) [Charfession] | 509254126 |  | 0.62 |  |  |  | 6965695 | 6965000 | Md. Unos Al Mamun | 22.07.15 | 22.07.15 | 21.07.16 | 15/07/16 | 100% | 2981776 | 100% | 0 | FBP | Charfession | 3983224
38 | BDRIDP/BHO/CF/CCA-Rd/27 | Improvement of road from Butua R&H road (Dudumia Bridge) South side of uttar Aicha Bazar Pasulpur UP RHD road by BC from Ch. 00-530m with 2 Nos Box Culvert at Ch.510m & 290m.(ID No. 509254127) m[Charfession] | 509254127 |  | 0.53 |  |  |  | 6251338 | 6251338 | M/s Milon Traders | 23.07.15 | 23.07.15 | 22.07.16 | 20/06/17 | 100% | 3844632 | 100% |  | FBP | Charfession | 2406706
39 | BDRIDP/BHO/CF/CCA-Rd/28 | Improvement of road from Batua Keramotgonj Bazar GC Sha GC Gazaria GC road Shazahan Member Rice Mill road By BC From Ch.00- 762m with 2 Nos RCC Box Culvert at Ch. 501m & 704m. (ID No. 509254128) [Charfession] | 509254128 |  | 0.762 |  |  |  | 4726533 | 4725532 | M/s Rubal Enterprise | 22.07.15 | 22.07.15 | 21.07.16 | 24/11/16 | 100% | 4725505 | 100% | 0 | FBP | Charfession | 27
40 | BDRIDP/BHO/CF/CCA-Rd/29 | Improvement of road from Kutubgonj Charman Bazar road (north side of Charman Bazar) Shashibussion road By BC from Ch:00-635m with 1 No RCC Box Culvert at Ch. 412m (ID No.509254129) [Charfession] | 509254129 |  | 0.635 |  |  |  | 3317214 | 3316214 | Md. Jakir Hossain | 22.07.15 | 22.07.15 | 21.07.16 | 24/02/17 | 100% | 3314947 | 99.96% | 0 | FBP | Charfession | 1267
41 | BDRIDP/BHO/CF/CCA-Rd/30 | Improvement of road from Kutubgonj Charman Bazar road hossain Munshi bari Mosjid West side of Jahanpur UP H/Q road By BC from 00-1210m with 2 Nos RCC Box Culvert at Ch.520m. & 796m(ID No. 509254130). [Charfession] | 509254129 |  | 1.21 |  |  |  | 6838015 | 6830979 | Ma.Akter Hossain | 22.07.15 | 22.07.15 | 21.07.16 | 2017-05-01 | 100% | 6830581 | 99.99% | 0 | FBP | Charfession | 398
42 | BDRIDP/Bho/CF/UN-RD/13 | Ipmrovement of road from UZ H/Q-Dularnat GC via Ganimunshir Chowmohoni, Dularhat Adsrsho College & Aminabad UP Office road By BC from Ch.6870-7870m with 1 No :3.00mx3.00m & 02 Nos 0.75mx0.75m RCC Box Culvert at Ch. 7823m, 6912m & 7070m (ID No 509253013) [Charfession] | 509253013 |  | 1 |  |  |  | 6585998 | 6579730 | M/s Khan Traders | 22.07.15 | 22.07.15 | 21.07.16 | 21/03/16 | 100% | 6577679 | 99.97% |  | FBP | Charfession | 2051
43 | BDRIDP/Bho/CF/UN-RD/14 | Improvement of road from UZ H/Q-Dularhat GC via Ganimunshir Chowmohoni, Duiarhat Adarsho College & Aminabad UP Office road By BC from Ch. 7870-8695m with 1 No 3.00mx3.00m RCC Box Culvert at Ch. 8224. (ID No. 509253013) [Charfession] | 509253013 |  | 0.825 |  |  |  | 5461511 | 5458474 | M/s Khan Traders | 22.07.15 | 22.07.15 | 21.07.16 | 21/03/16 | 100% | 5456456 | 99.96% |  | FBP | Charfession | 2018
44 | BDRIDP/Bho/CF/CCA-Rd/31 | Improvement of road from Siddik Howlader Bazar (Rudder Hat)-Bangla Bazar road By BC from Ch.00-1100m with 01 No 3.00mx3.00m & 05 Nos 0.75mx0.75m RCC Box Culvert at Ch. 864m, 280m, 583m 702m 950m & 1038m. (ID No.509255055) [Charfession] | 509255055 |  | 1.1 |  |  |  | 8383018 | 8338369 | Badul kasno Devnath | 22.07.15 | 22.07.15 | 21.07.16 | 20/01/16 | 100% | 8335829 | 99.97% |  | FBP | Charfession | 2540
45 | BDRIDP/Bho/CF/CCA-Rd/32 | Improvement of road from Betua RHD road Asiampur Madraj Border Bridge via Abu Chairman Brick Field road By BC from Ch.00-1365m with 1 No 3.00mx3.00m & 1No 1.50mx1.50m RCC Box Culvert at Ch 207m & 715m. (ID No. 509254135) [Charfession] | 509254135 |  | 1.365 |  |  |  | 8554173 | 8523168 | M/s Babul Traders | 22.07.15 | 22.07.15 | 21.07.16 | 20/04/16 | 100% | 8520910 | 99.97% |  | FBP | Charfession | 2258
46 | BDRIDP/Bho/CF/CCA-Rd/33 | Improvement of road from Betua RHD road -Forest Office (Near Hasem Dewan Shop) road By BC from Ch.00- 600m with 01 No 3x4.50mx3.50m 3Vent RCC Box Culvert; 1 No 3.00mx3.00m & 1 No 0.75mx0.75m RCC Box Culvert at Ch. 351 m. 565m & 90m. (ID No. 509254110) [Charfession] | 509254110 |  | 0.6 |  |  |  | 6903186 | 6899084 | M/s Boksi Enterprise | 22.07.15 | 22.07.15 | 21.07.16 | 2016-08-04 | 100% | 6876946 | 99.68% |  | FBP | Charfession | 22138
47 | BDRIDP/Bho/CF/CCA-Rd/34 | Improvement of road from Betua RHD (Holud Building) - East Side of WDB Embk. road By BC from Ch.00-700m with 1 No 2x4.50mx3.50m 2Vent Box Culvert & 1 No 0.75mx0.75m RCC Box Culvert at Ch 163m & 530m. (ID No. 509254141) [Charfession] | 509254141 |  | 0.7 |  |  |  | 5540158 | 5538267 | M/s Mollah Trading & const: | 22.07.15 | 22.07.15 | 21.07.16 | 25/03/17 | 100% | 5537740 | 99.99% |  | FBP | Charfession | 527
48 | BDRIDP/Bho/CF/CCA-Rd/35 | Improvement of road from Betua RHD from Awaspur 01 No Word Latra Khal (Rohizol Mai Kheya Gnat)-West Awaspur Ko-Aid School road By BC from Ch. 00-950m with 1 No 3x4.50mx3.50m 3Vent RCC Box Culvert; 1 No 1.50mx1.50m & 3 Nos 0.75mx0.75m RCC Box Culvert at Ch. 545m, 646m, 200m, 507m & 910m (ID No. 509254111). [Charfession] | 509254111 |  | 0.95 |  |  |  | 8811263 | 8803529 | M/s.Saymum Traders | 22.07.15 | 22.07.15 | 21.07.16 | 30/04/16 | 100% | 8798431 | 99.94% |  | FBP | Charfession | 5098
49 | BDRIDP/Bho/CF/CCA-Rd/36 | Improvement of road from WFP Katcha Road (Ibrahim Khalil Bari Mosjid)- WDB Embk. Near Fores; Office via Jalii Barari Hat road By BC from Ch. 00-1400m with 4 Nos 0.75mx0.75m RCC Box Cuivert at Ch. 181m, 485m, 800m & 873m. (ID No. 509254112) [Charfession] | 509254112 |  | 1.4 |  |  |  | 8538470 | 8533467 | Badul kasno Devnath | 22.07.15 | 22.07.15 | 21.07.16 | 14/02/17 | 100% | 8514981 | 99.78% | 0 | FBP | Charfession | 18486
50 | BDRIDP/BHO/CF/CCA-Rd/37 | Improvement of road from Karimpara (RHD road) - WDB Embk. Ruhul Amin Chairman Bazar road By BC from Ch. 1200-1890m (ID No. 509254140) [Charfession] | 509254140 |  | 0.69 |  |  |  | 4176221 | 4175193 | Md. Unos Al Mamun | 22.07.15 | 22.07.15 | 30.07.17 | 30/07/17 | 100% | 4173193 | 99.95% |  | FBP | Charfession | 2000
51 | BDRIDP/BHO/CF/CCA-Rd/38 | Improvement of road from Char Kochhopia GPS (RHD road) - South Side of Kochhopia Bazar WDB Embk. road By BC from Ch. 00-915m with 3 Nos 0.75mxO.75m RCC Box Culvert at Ch. 80m, 392m & 598m (ID No. 509254138) [Charfession] | 509254138 |  | 0.915 |  |  |  | 5762029 | 5723778 | M/s Jashim Const. | 22.07.15 | 22.07.15 | 21.07.16 | 2016-02-10 | 100% | 5721736 | 100% |  | FBP | Charfession | 2042
52 | BDRIDP/BHO/CF/CCA-Rd/39 | Improvement of road from Kochhopir RHD road (Paccar Matha) - North Side of Korban Ali Bapari Bari Mosjid road By BC from Ch. 00-1450m with 3 Nos 0.75mx0.75m RCC Box Culvert at Ch. 103m, 570 & 807m. (ID No. 509254136) [Charfession] | 509254136 |  | 1.45 |  |  |  | 8312714 | 8303329 | Badul kasno Devnath | 22.07.15 | 22.07.15 | 21.07.16 | 2016-04-04 | 100% | 8301278 | 99.98% | 0 | FBP | Charfession | 2051
53 | BDRIDP/BHO/CF/CCA-Rd/40 | Improvement of road from Kachhopia Gano Shaisto Hospital (RHD road) - North Side of Kasem Comander Bari road By BC from Ch. 00-1170m with 4 Nos 0.75mx0.75m RCC Box Culvert at Ch. 302m, 533m, 834m & 990m. (ID No. 509254139) [Charfession] | 509254139 |  | 1.17 |  |  |  | 7090595 | 7078903 | M/s Khan Traders | 22.07.15 | 22.07.15 | 21.07.16 | 2016-02-10 | 100% | 7076535 | 99.97% | 0 | FBP | Charfession | 2368
54 | BDRIDP/BHO/CF/CCA-Rd/41 | Improvement of road from Char Kochhopia GPS (RHD road) - North Side of Motahar Munshi Bari Mosjid road By BC from Ch. 00-940m 1 No 1.50mx1.50m & 2 Nos 0.75mx0.75m RCC Box Culvert at Ch. 806m, 408m & 600m. (ID No. 509254137) [Charfession] | 509254137 |  | 0.94 |  |  |  | 5991855 | 5985317 | M/s Saymon Traders | 22.07.15 | 22.07.15 | 21.07.16 | 2017-10-02 | 100% | 5983244 | 100% | 0 | FBP | Charfession | 2073
55 | BDRIDP/BHO/CF/CCA-Rd/42 | Improvement of road from Charfassion Betua RHD road (Near Sharder Bari Bridge) - Shazahan Member Rice Mill road By BC from Ch. 00-785m with 2 Nos 0.75rnx0.75m RCC Box Culvert at Ch. 15m &525m. (ID No. 50254142) [Charfession] | 509254142 |  |  | 0.785 |  |  | 4573005 | 4573000 | Julfiker Ahamed | 22.07.15 | 22.07.15 | 21.07.16 | 2016-08-10 | 100% | 4570930 | 100% | 0 | FBP | Charfession | 2070
56 | BDRIDP/BHO/CF/CCA-Rd/43 | Improvement of road from Sultaner Pacca Road-Brac School road By BC from Ch. 00-295m with 1 No 0.75mx0.75m RCC Box Culvert at Ch. 246m. (ID No. 509254143) [Charfession] | 509254143 |  | 0.295 |  |  |  | 1914205 | 1911457 | Md.Fakrul Islam | 22.07.15 | 22.07.15 | 21.07.16 | 2017-12-03 | 100% | 1903676 | 100% | 0 | FBP | Charfession | 7781
57 | BDRIDP/BHO/CF/CCA-Rd/44 | Improvement of road from Sultaner Kheyaghat road (Mirdha Chowmuhoni) BC (Near Aziz Master Bari) road By BC from Ch. 00-505m with 3 Nos 0.75mx0.75m RCC Box Culvert at Ch. 115m, 250m & 440m (ID No. 509254144) [Charfession] | 509254144 |  | 0.505 |  |  |  | 3268684 | 3164525 | M/s Bokshi Enterprise | 22.07.15 | 22.7.15 | 22.7.16 | 15/02/17 | 100% | 3162218 | 99.93% | 0 | FBP | Charfession | 2307
58 | BDRIDP/BHO/CF/CCA-Rd/45 | Improvement of road from Shashibussion-Anjurhat riad (Ali Ahammed Bari Mosjid)-Sultaner Kheyaghat Bridge road By BC from Ch,00-1150m. (ID No.509254105 Add ID) [Charfession] | 509254105 |  | 1.15 |  |  |  | 6343556 | 6339158 | M/s Jashim Const. | 22.07.15 | 22.07.15 | 21.07.16 | 16/03/17 | 100% | 6335024 | 99.93% | 0 | FBP | Charfession | 4134
59 | BDRIDP/BHO/CF/CCA-Rd/46 | Improvement of road from Shashibussion-Anjurhat riad (Ali Ahammed Bari Mosjid)-Sultaner Kheyaghat Bridge road By BC from Ch.1150-2000m. (ID No.509254105 Add ID) [Charfession] | 509254105 |  | 0.75 |  |  |  | 4452367 | 4451929 | Badul kasno Devnath | 22.07.15 | 22.07.15 | 21.07.16 | 15/03/17 | 100% | 4449929 | 99.96% | 0 | FBP | Charfession | 2000
60 | BDRIDP/BHO/CF/CCA-Rd/47 | Improvement of road from Shashibussion-Anjurhat riad (Ali Ahammed Bari Mosjid)-Sultaner Kheyaghat Bridge road By BC from Ch.2000-2430m. (ID No.509254105 Add ID) [Charfession] | 509254105 |  | 0.43 |  |  |  | 2161379 | 2161379 | M/s Bengol Traders | 22.07.15 | 22.07.15 | 21.07.16 | 19/03/17 | 100% | 2159378 | 99.91% | 0 | FBP | Charfession | 2001
61 | BDRIDP/BHO/CF/CCA-Rd/48 | Improvement of road from Kasemgonj Awaspur 01 No GPS (RHD road)-East Side of Mridha Bari Jame Mosjid road By BC from Ch.00-490m with 01 No 0.75mx0.75m RCC Box Culvert at Ch.247m. (ID No. 509255080 Add ID) [Charfession] | 509255080 |  | 0.49 |  |  |  | 3008926 | 3001431 | M/s Babul Traders | 22.07.15 | 22.07.15 | 21.07.16 | 2016-03-04 | 100% | 2999318 | 99.93% | 0 | FBP | Charfession | 2113
62 | BDRIDP/BHO/CF/UN-RD/15 | Improvement of Road from Charfession College road Panirkal via Zinnagor Balok Road Ch. 4450.00m-5350.00m under Charfessain Bhola. (509253054) | 509253054 |  | 0.9 |  |  |  | 5221101 | 5609730 | Md. Aker Hossain | 6.4.16 | 6.4.16 | 30.9.16 | 30/09/18 | 100% | 5605737 | 99.93% | 0 | FBP | Charfession | 3993
63 | BDRIDP/BHO/CF/UN-RD/16 | Improvement of Road from Jinnaganar UP-Dularhat-Hazirhat via Abdullahpur UP Office Road from Ch. 6200m-9040m under Charfessain Bhola. (509253040) | 509253040 |  | 2.84 |  |  |  | 19428405 | 19216598 | M/s Khan Traders | 06.04.16 | 06.04.16 | 06.04.17 | 17/06/17 | 100% | 19171372 | 99.76% | 0 | FBP | Charfession | 45226
64 | BDRIDP/BHO/CF/UN-RD/17 | Improvement of Road from Nilkamal UP (Ghosherhat)-Hajirhat (Maya river) Road from Ch. 3000m-3575m &4800-8450m under Charfessain Bhola. (509253016) | 509253016 |  | 4.225 |  |  |  | 24559681 | 26947728 | Eunos Al Mamun | 12.04.16 |  | 12.04.17 |  | 100% | 26912257 | 99.87% | 0 | FBP | Charfession | 35471
65 | BDRIDP/BHO/CCA/RD/01 | Approch road Adiacent -Resurve pond road ch. 00-186m unddr Charfession |  |  | 1.86 |  |  |  | 8678309 | 8676830 | M/s Babul Traders | 24.02.14 |  | 24.04.14 | 30/03/18 | 100% | 8668600 | 99.91% |  | FBP | Charfession | 8230
65 | Charfession (Road Work) Sub-Total |  |  | 0 | 72.778 | 0.785 | 0 | 13.445 | 477048327 | 488446249 | Amount Spent (Tk) 18: 477900319; In (%) 20: 0; In (%) 22: Charfession | 10545930
| Charfassion (Structure Work) | [9 empty] | In (%) 22: Charfession | 0
1 | BDRIDP/Bho/ CF/UN--Rd-St/01 | Const. of 99.00m long RCC Girder Bridge over Betua khal on RHD Kaliakandi GPS to jalil road via Bhulyarhat Dinar kheya ghat at Ch. 7230m under Cherfession |  |  |  | 99 |  |  | 67352763 | 79005297 | Md. Unos Al Mamun | 1.12.14 | 8.12.14 | 1.12.16 | 2015-06-01 | 100% | 78974360 | 99.96% |  | FBP | Charfession | 30937
2 | BDRIDP/Bho/CF/CCA-St/01 | Construction of 1No 1.50m x 1.50m size, 4 Nos 0.75mx0.75m RCC Box culvert on Janata Bazar Bhuierhat road (Nurul Haque Shop)- Osmangonj Aslampur Border road via Aligow GPS (Eyachin road) road at Ch.820m, 242m, 663m, 1261m & 1483m (ID No. 509254107) under Charfession Upazila. | 509254107 |  |  | 4.5 |  |  | 1183579 | 1178080 | Manir Enterprise | 23.11.14 | 30.11.14 | 22.01.15 | 30/12/14 | 100% | 1177659 | 99.96% |  | FBP | Charfession | 421
3 | BDRIDP/Bho/CF/CCA-St/02 | Construction of 01 No 3.00mx3.00m RCC Box Culvert on Jahanpur Mykel Modhushudhan Abason (Asrayan) Connecting road at ch. 4192m (ID No. 509254108). Under Charfession Upazila. | 509254108 |  |  | 3 |  |  | 896329 | 891618 | Badul kasno Debonath | 2.11.14 | 14.11.14 | 2.01.15 | 13/04/16 | 100% | 890950 | 99.93% |  | FBP | Charfession | 668
4 | BDRIDP/BHO/CF/CCA-St/04 | Construction of 01 No 1.50mx1.50m; 02 No 0.75m x 0.75m RCC Box Culvert on Shashibussion-Anjurhat riad (Ali Ahammed Bari Mosjid)-Sultaner Kheyaghat Bridge road at Ch.900m, 402m & 1105m. (ID No.509254105 Add ID) [Charfession] | 509254105 |  |  | 3 |  |  | 779629 | 778824 | M/s Boksi Enterprise | 22.7.15 | 22.7.15 | 21.7.16 | 16/03/17 | 100% | 777862 | 99.88% |  | FBP | Charfession | 962
5 | BDRIDP/BHO/CF/CCA-St/05 | Construction of 01 No 1.50mx1.50m & 01 No 0.75mx 0.75m RCC Box Culvert on Shashibussion-Anjurhat riad (Ali Ahammed Bari Mosjid)-Sultaner Kheyaghat Bridge road at Ch.1812m & 1681m. (ID No. 509254105 Add ID) [Charfession] | 509254105 |  |  | 2.25 |  |  | 593358 | 590464 | M/s Milan Traders | 22.7.15 | 22.7.15 | 21.7.16 | 13/08/17 | 100% | 590275 | 100% |  | FBP | Charfession | 189
6 | BDRIDP/BHO/CF/CCA-St/06 | Construction 01 No 3x4.50mx5.00m 3Vent and 01 No 0.75mx0.75m RCC Box Culvert on Shashibussion-Anjurhat riad (Ali Ahammed Bari Mosjid)-Sultaner Kheyaghat Bridge road at Ch. 2126m & 2234m. (ID No.509254105 Add ID) [Charfession] | 509254105 |  |  | 13.5 |  |  | 3279270 | 3239747 | M/s Monir Enterprise | 22.7.15 | 22.7.15 | 21.7.16 |  | 0% | 0 | 0% |  | বাতিলের প্রসতাব প্রেরন করা হয়েছে। | Charfession | 3239747
7 | BDRIDP/BHO/CF/CCA-St/03 | Construction of 54.00m long RCC Gider Bridge on Kochapia Bazar WDB Embankment south side of Alam road at Ch. 30m Under Charfession. | 509254117 |  |  | 54 |  |  | 39775082 | 39774724 | M/s Monir Construction | 19.8.15 | 19.8.15 | 19.8.17 | 2018-10-01 | 100% | 39553320 | 100% |  | FBP | Charfession | 221404
8 | BDRIDP/BHO/CF/CCA-St/07 | Construction of 54.06m long RCC Gider Bridge on Shashibhosaion Anjurhat Road to Babubazar at Ch. 4350 road . Under Charfession Upazila. | 509255039 |  |  | 54.06 |  |  | 30680411 | 30680410 | Younus -Al- Mamun | 19.8.15 | 29.8.15 | 19.8.17 |  | 100% | 30395643 | 100% | 0 | FBP | Charfession | 284767
9 | BDRIDP/BHO/CF/CCA-St/08 | Construction of 45.00m long RCC Gider Bridge over Latakhali khal on Begam Rahima Islam Mohila College approch road at Ch. 393m Under Charfession Upazila. | 509254031 |  |  | 45 |  |  | 38468375 | 38468375 | Younus -Al- Mamun | 27.04.17 | 30.7.17 | 29.7.18 |  | 97% | 36613019 | 95.18% | 1855356 |  | Charfession | 1855356
9 | (Structure Work) Sub-Total |  |  | 0 | 0 | 278.31 | 0 | 0 | 183008796 | 194607539 | Amount Spent (Tk) 18: 188973088; In (%) 20: 1855356
74 | Charfession Upazila Sub-Total |  |  | 0 | 72.778 | 279.095 | 0 | 13.445 | 660057123 | 683053788 | Amount Spent (Tk) 18: 666873407; In (%) 20: 1855356
Upazila : Monpura (Road Work) | [21 empty] | 0
1 | BDRIDP/BHO/Mon/CCA-Rd/09 | Improvement of road from AR Polley Mondir Connecting road Hazir hat Sadar By BC from Ch. 00-500m (ID No. 509654058) | 509654058 |  | 0.5 |  |  |  | 2238346 | 1834095 | M/s Tahura Enterprise | 27.7.15 | 27.7.15 | 26.1.16 | 16/02/16 | 100% | 1813434 | 100% | 0 | FBP | Monpura | 20661
2 | BDRIDP/BHO/MON/CCA-Rd/06 | Improvement of road from Nayeber hat-Chowdhory Bazar- Shonar Char road By BC from Ch.00-1500m. With 2Nos 0.75mx0,750m RCC Single Vent Box Culvert at Ch.130m & 740m (ID No. 509654024) [Monpura] | 509654024 |  | 1.5 |  |  |  | 8535674 | 8535600 | M/s Bokshe Enterprise | 22.7.15 | 22.7.15 | 22.7.16 | 24/02/16 | 100% | 8514132 | 99.75% | 0 | FBP | Monpura | 21468
3 | BDRIDP/BHO/MON/CCA-Rd/07 | Improvement of road from RCC road on Rafiq Maowlana Bari-UZR-Gomatoli GPS-East Beri Bundth road By BC from Ch.1500-2450m With 2Nos 0.750mx0.750m RCC Single Vent Box Culvert at Ch.1650m & 2100m. (ID No.509654045) [Monpura] | 509654045 |  | 1.45 |  |  |  | 5967245 | 5949907 | Md. Unos Al Mamun | 22.07.15 | 22.07.15 | 21.07.16 | 21/04/17 | 100% | 5940065 | 99.83% | 0 | FBP | Monpura | 9842
4 | BDRIDP/BHO/MON/CCA-Rd/08 | Improvement of RCC road on Gagon Member Bari-UZR- West Beri Bundth road from Ch.1000-1930m With 1no 2.50mx2,50m & 1no 0.750mx 0.750m RCC Single Vent Box Culvert at Ch. 1870m & 1200m. (ID No.509654046) [Monpura] | 509654046 |  | 0.9 |  |  |  | 6379767 | 6366267 | M/s Babul Traders | 22.07.15 | 22.07.15 | 21.07.16 | 28/06/16 | 100% | 6357275 | 99.86% | 0 | FBP | Monpura | 8992
5 | BDRIDP/BHO/MON/CCA-Rd/O1 | Improvement of road from on Nayeber Nat-Chowdhory Bazar- Shonar Char road By RCC from Ch-1500 - 3050m with 2.5mx2.5m & 0.75mx0,75m RCC single vent box culvert at Ch- 1550m & Ch-3000m (ID No.509654024) [Monpura] | 509654024 |  | 1.05 |  |  |  | 9633478 | 9628107 | M/s Jasim Construction | 22.07.15 | 22.07.15 | 21.07.16 | 24/03/16 | 100% | 9352560 | 97.14% | 0 | FBP | Monpura | 275547
6 | BDRIDP/BHO/MON/CCA-Rd/02 | Improvement of road from Fakirhat Cyclone Shelter (Alomgir Master Bari) road by RCC from Ch.00-1440m and 2Nos 0.750mx0.750m RCC Single vint Box Culvert at Ch.250 & 710m (ID No.509654007) [Monpura] | 509654007 |  | 1.44 |  |  |  | 8952162 | 8936444 | M/s Bengol Traders | 0 | 22.07.15 | 21.07.16 | 2016-10-04 | 100% | 8927385 | 99.9% | 0 | FBP | Monpura | 9059
7 | BDRIDP/BHO/MON/CCA-Rd/03 | Improvement of road from Rafiq Maowlana Bari-UZR-Gomatoli GPS-East Beri Bundh road By RCC from Ch. 00-1500m and 4 Nos 0.750mx0.750m RCC Single Vent Box Culvert at Ch. 900m, 1020m, 1650m & 2100m (ID No.509654045) [Monpura] | 509654045 |  | 1.5 |  |  |  | 9691257 | 9631309 | M/s Milon Traders | 22.07.15 | 22.07.15 | 21.07.16 | 2016-08-06 | 100% | 9614422 | 99.82% | 0 | FBP | Monpura | 16887
8 | BDRIDP/BHO/MON/CCA-Rd/04 | Improvement of Road from Gagon Member Bari-UZR-West Beri Bundh road from Ch.00-1000m with 2 Nos 0.750m x 0.750m RCC Single Vent Box Culvert at Ch. 400m & 700m (ID No.509654046) [Monpura] | 509654046 |  | 1 |  |  |  | 6344821 | 6335402 | M/s Monir Enterprise | 22.07.15 | 22.07.15 | 21.07.16 | 23/06/15 | 100% | 6327008 | 99.87% | 0 | FBP | Monpura | 8394
9 | BDRIDP/BHO/MON/CCA-Rd/05 | Improvement of road from East Beri to Bhuiar hat UZR road By RCC from Ch. 00-720m. and 1no 0.750mx0.750m RCC Single vent box Culvert at Ch.100m. (ID No.509654048) [Monpura] | 509654048 |  | 0.72 |  |  |  | 4404424 | 4391232 | Md. Younus Al Mamun | 22.07.15 | 22.07.15 | 21.07.16 | 2016-07-03 | 100% | 4381708 | 99.78% | 0 | FBP | Monpura | 9524
9 | Monpura (Road Work) Sub-Total |  |  |  | 10.06 | 0 | 0 | 0 | 62147174 | 61608363 | Amount Spent (Tk) 18: 61227989; In (%) 20: 0
249 | Bhola Dist. Total |  |  |  | 215.797 | 973.175 | 0.13 | c | 1720938989 | 1727179243 | Amount Spent (Tk) 18: 1591041467
[13 empty] | F. Year |  | Fund Received |  | Fund Spent |  | Laps
[13 empty] | 2013-2014 |  | 6000000 |  | 6000000 |  | 0
[13 empty] | 2014-2015 |  | 360900000 |  | 360900000 |  | 0
Accountant |  | Sub Assistant Engineer | Assistant Engineer |  |  |  |  | Sr. Assistant Engineer |  |  | 12: Executive Engineer; 14: 2015-2016; 16: 587700000; Amount Spent (Tk) 18: 587700000; In (%) 20: 0
LGED,Bhola |  | LGED, Bhola. | LGED,Bhola |  |  |  |  | LGED,Bhola |  |  | 12: LGED,Bhola.; 14: 2016-2017; 16: 245600000; Amount Spent (Tk) 18: 245600000; In (%) 20: 0
[13 empty] | 2017-2018 |  | 146800000 |  | 146800000 |  | 0
[13 empty] | 2018-2019 |  | 74000000 |  | 73981700 |  | 18300
[13 empty] | 2019-2020 |  | 116000000 |  | 116000000 |  | _
[11 empty] | 14: 2020-2021; 16: 54460000; Amount Spent (Tk) 18: 54059767 |  | Cash in Hand
[11 empty] | 14: Total Tk.; 16: 1591460000; Amount Spent (Tk) 18: 1591041467; In (%) 20: 18300 |  | 418533
0

## Short work
Barisal Division Rural Infrastructure Development Project (BDRIDP)
District : Bhola
SL No | Upazila Name | Total Scheme (no) | Road (Km)/ Structure (m) | Estimated Cost. | Contract Amount (Tk.) | Payment (Tk.) | Road (km) | Stru. (m) | Completed
1 | Bhola sadar( road) | 46 | 85.389 | 381469394 | 372883956 | 312627839 | 85.389
| Structure | 40 | 431.33 | 173539124 | 174508229 | 174144307 |  | 431.33
2 | Borhanuddin ( road) | 11 | 27.785 | 102314215 | 104858258 | 93532271 | 27.785
| Structure | 4 | 18 | 5679979 | 5665275 | 5663497 |  | 18
3 | Daulatkhan ( road) | 9 | 14.874 | 72603897 | 66856757 | 66810390 | 14.874
| Structure | 7 | 19 | 5093064 | 5078261 | 5068291 |  | 19
4 | Lalmohan ( road) | 25 | 31.518 | 165754201 | 163357070 | 122779410 | 31.518
| Structure | 18 | 179.5 | 44071273 | 42375377 | 41860384 |  | 179.5
5 | Tazumuddin ( road) | 6 | 6.173 | 48209545 | 46933909 | 40453682 | 6.173
| Structure | 0 | ke33 | 0 | 0 | 0 | 0 | ke33
6 | Charfession ( road) | 65 | 86.223 | 477048327 | 488446249 | 477900319 | 86.223
| Structure | 9 | 278.31 | 183008796 | 194607539 | 188973088 |  | 278.31
7 | Monpura ( road) | 9 | 10.06 | 62147174 | 61608363 | 61227989 | 10.06
| Structure | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | 249 | 1188.162 | 1720938989 | 1727179243 | 1591041467 | 262.022 | 926.14 | 0