## December20
Monthly Progress Report of Schemes under Barisal Division Rural Infrastructure Development Project(BDRIDP)
Project Name : Barisal Division Rural Improvement Development Project(BDRIDP)
District : Barguna | [17 empty] | Reporting Month:November/2020
Sl No | Packeg No | Scheme Name of the Location (Ch-ch) | Road ID No | Effective Qtyantity | [5 empty] | Approved Estimate cost (Tk) | Contract Amount (Tk) | Name of contractor/ LCS Chairman | Contract signing date | Actual start Date | Completion date as per contract | Actual Completion date | Physical progress % | Financial progress |  | Fund received with memo date | Remarks
[18 empty] | Amount spent | in %
|  |  |  | E/W (m3) | BC (Km) | HBB (Km) | RCC (Km) | Rehab (Km) | Str. (m)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
1 | BDRIDP/BRG/BET/UZ-Rd/01 | Badnikhali GC- Kazirhat GC via west karuna High school road by BC from ch 0.00m-2500.00m under Betagi. | 504472005 |  | 2.5 |  |  |  |  | 15775672 | 13712087.32 | M/S Khan Enterprise | 01.02.2015 | 07.02.2015 | 06.02.2016 |  | 100% | 13712051 | 100% |  | Final bill paid
2 | BDRIDP/BRG/BET/UZ-Rd/02 | Badnikhali GC- Kazirhat GC via west karuna High school road by BC from ch 2500.00m-3700.00m under Betagi. | 504472005 |  | 1.2 |  |  |  |  | 7373067 | 6339303.15 | M/S Khan Enterprise | 01.02.2015 | 07.02.2015 | 18.04.2016 |  | 100% | 6339259 | 100% |  | Final bill paid
3 | BDRIDP/BRG/BET/UZ-St/01 | Construction of 2Nos 4.00m*3.30m 2Vent Box culvert on Badnikhali GC- Kazirhat GC via west karuna High school road by BC at ch 2621.00m & 2891.00m under Betagi. | 504472005 | [5 empty] | 16 | 3528828 | 2945703.18 | M/S Safi Enterprise | 25.01.2015 | 01.02.2015 | 01.02.2016 |  | 100% | 2909132 | 100% |  | Final bill paid
4 | BDRIDP/BRG/PAT/UN-Rd/01 | Rehabilitation of road from Lemua GC - C&B Bazar(RHD) via Hatempur road by BC from ch 2230.00m-4230.00m(ID NO-504853008) | 504853008 |  |  |  |  | 2 |  | 10504095 | 10496376 | Md.Nizam Uddin | 19.04.2015 | 26.04.2015 | 31.12.2016 |  | 100% | 10496344 | 100% |  | Final bill paid
5 | BDRIDP/BRG/BAM/CCA-St/01 | Construction of 1 No 1.50m*1.50m RCC Box culvert on Madha Kakchira GPS cum Cyclone Shelter- Cotto Bhaijora GPS- Khuchnichora GPS cum Cyclone Shelter road at Ch. 1350m (Road ID-504194011) Upazila: Bamna , District: Barguna. | 504194011 | [5 empty] | 1.5 | 413563 | 334519.63 | M/S Homaira construction | 31.05.2015 | 01.06.2015 | 30.09.2016 |  | 100% | 334290 | 99.93% |  | Final bill paid
6 | BDRIDP/BRG/BAM/UN-Rd(R)/01 | Rehabilitation of road from Bukabunia Head Quarter- Amua GC via Laxmipura Madrasha road by BC from Ch. 1000-3000m with 1.50m*1.50m Box Culvert at Ch. 1400m (Road ID-504193004) Upazila: Bamna , District: Barguna. | 504193004 |  |  |  |  | 2 |  | 10200813 | 8569716 | M/S Ahmed Still Industries | 31.05.2015 | 31.05.2015 | 30.06.2016 |  | 100% | 8569103 | 100% |  | Final bill paid
7 | BDRIDP/BRG/BET/UZ-Rd(R)/03 (Tender ID 25642) | Rehabilitation of road from Niamati- Deshanterkathi via DC Hat by BC Ch. 3900-5363.00 (Road ID-504472002) Upazila: Betagi , District: Barguna. | 504472002 |  |  |  |  | 1.46 |  | 9274495 | 8342124 | M/S Khan Enterprise | 28.07.2015 | 05.08.2015 | 17.10.2016 |  | 100% | 8342124 | 100% |  | Final bill paid
8 | BDRIDP/BRG/BET/UZ-St/02(Tender ID 25643) | Construction of 2 Vent 3.60*4.00m RCC Box Culvert & 1 Nos U-Drain on Niamati -Deshantorkathi via DC Hat road at ch. 4830m & 1020m (Road ID-504472002) Upazila: Betagi , District: Barguna. | 504472002 | [5 empty] | 7.83 | 2960050 | 2346675 | Md.Munibur Rahman | 26.07.2015 | 05.08.2015 | 05.02.2016 |  | 100% | 2339488 | 99.69% |  | Final bill paid
9 | BDRIDP/BRG/PAT/CCA-Rd(R)/01 (Tender ID-27058) | Rehabilitation of road from Jaliaghata Bridge -Apiler Bridge road from Ch. 0.00-1483m (Road ID-504855032) Upazila: Patharghata , District: Barguna. | 504855032 |  |  |  |  | 1.48 |  | 7089953 | 6400115 | M/S Afser & Co. | 12.08.2015 | 20.08.2015 | 20.08.2016 |  | 100% | 6400094 | 100% |  | Final bill paid
10 | BDRIDP/BRG/PAT/CCA-St/01(Tender ID-25645) | Construction of 5 Nos U-Drain and 1 No Box Culvert on Jaliaghata Bridge - Apiler Bridge road at Ch.350m,704m,896m,974m, 1260m,& 528m (Road ID-504855032) Upazila: Patharghata , District: Barguna. | 504855032 | [5 empty] | 4.625 | 968607 | 788563 | M/S Humaira Construction | 28.07.2015 | 05.08.2015 | 05.02.2016 |  | 100% | 788383 | 99.98% |  | Final bill paid
11 | BDRIDP/BRG/BET/CCA-Rd/01(Tender ID25646) | Improvement of road from Betagi-Barguna (UZR/Bango Bandhu Bazar) -Charkhali Wapda Bazar (Bango Bandhu Bazar Paschim Kauna H/S-Kaialghata- Charkhali) road By BC from Ch. 00-1800m(ID No. 504474298) Upazila: Betagi , District: Barguna. | 504474298 |  | 1.8 |  |  |  |  | 7706160 | 6583394 | M/S Humayun Enterprise | 28.07.2015 | 05.08.2015 | 17.10.2016 |  | 100% | 6583337 | 100% |  | Final bill paid
12 | BDRIDP/BRG/BET/CCA-Rd/02(Tender ID-25647) | Improvement of road from Betagi-Barguna (UZR/Bango Bandhu Bazar) -Charkhali Wapda Bazar (Bango Bandhu Bazar Paschim Kauna H/S-Kaialghata- Charkhali) road By BC from Ch. 1800-3425m(ID No. 504474298) Upazila: Betagi , District: Barguna. | 504474298 |  | 1.63 |  |  |  |  | 7793746 | 6771620 | M/S Khan Enterprise | 28.07.2015 | 05.08.2015 | 17.10.2016 |  | 100% | 6771621 | 100% |  | Final bill paid
13 | BDRIDP/BRG/BAT/CCA-St/01(Tender ID25648) | Construction of 4Nos U-Drain & 2Nos 2Vent 3.00X3.50m RCC Box Culvert on Betagi-Barguna (UZR/Bango Bandhu Bazar) -Charkhali Wapda Bazar (Bango Bandhu Bazar Paschim Kauna H/S-Kaialghata- Charkhali) road at ch.55m,638m,2810m,3200m,250m & 3112m (ID No. 504474298) Upazila: Betagi , District: Barguna. | 504474298 | [5 empty] | 14.5 | 2638424 | 2162558 | M/S Khan Enterprise | 28.07.2015 | 05.08.2015 | 05.02.2016 |  | 100% | 1037064 | 100% |  | Final bill paid
14 | BDRIDP/BRG/BAM/CCA-Rd/02(Tender ID-23932) | Improvement of road from Bamna Bukabunia road to gafur Master House with 2Nos U-Drain at ch 10m & 300m. | 504195037 |  | 0.6 |  |  |  | 1.25 | 3417708 | 2836052.7 | M/S Rudra Enterprise | 11.04.2015 | 18.04.2016 | 18.10.2016 |  | 100% | 2828160 | 99.72% |  | Final bill paid
15 | BDRIDP/BRG/SDR/UZ-St/01 | Construction of 72.00n Long RCC Girder Bridge on Barguna - Fuljhuri GC- Kakchira GC road Adjacent to Barguna Fish Market at ch 50.00m under Barguna Sadar Upazila.Barguna. | 504282003 | [5 empty] | 72 | 35991256 | 40392605.47 | MSE-SMS(JV) | 31.08.2016 | 08.09.2016 | 30.01.2018 (30.06.2018) |  | 100% | 39208645 | 100% |  | Final Bill Paid
16 | BDRIDP/BRG/PAT/UZ-Rd/01 (Tender ID 58712) | Improvement of Kalmegha - Charduani GC Road from ch 6944m-8100m(ID No-5048552005) | 504852005 |  | 1.15 |  |  |  |  | 9862112 | 6849647.09 | Md. Golam Kibria | 22.08.2016 | 28.08.2016 | 28.02.2017 (31.12.2018) |  | 100% | 6849647 | 100% |  | Final bill paid
17 | BDRIDP/BRG/PAT/UZ-Rd(R)/02 (Tender ID 58713) | Rehabilitation of Kalmegha - Charduani GC Road from ch 2134m-6944m with construction of 5 Nos U-Drain at ch 2494m,3750m,4090m,6076m & 6176m(ID No-5048552005) | 504852005 |  |  |  |  | 4.81 |  | 35775876 | 31235571.26 | M/S Polly Stors | 05.10.2016 | 12.10.2016 | 17.11.2017 (05.02.2018) |  | 100% | 30880860 | 100% |  | Final bill paid
18 | BDRIDP/BRG/AMT/UZ-Rd/01 | Improvement of road from Amtali Mohiskata RHD -Kalagasia Khasherhat GC via Gulishakhali Bazar at ch 6843m-8843m | 504092010 |  | 2 |  |  |  |  | 11684315 | 9931712.5 | M/S Mithun Traders | 05.09.2016 | 12.09.2016 | 20.07.2017 |  | 100% | 9931711 | 100% |  | Final bill paid
19 | BDRIDP/BRG/PAT/CCA-Rd/02 (Tender ID 62007) | Improvement of road from Chaherabad GPS cum Cyclone Shelter (Chaherabad Dali Bari - Subendra Nath High school) at ch 0m-1435m | 504855093 |  | 1.435 |  |  |  |  | 8082179 | 7193498.62 | M/S Jami Enterprise | 28.08.2016 | 05.09.2016 | 23.07.2017 (30.04.2018) |  | 100% | 7190032 | 99.95% |  | Final bill paid
20 | BDRIDP/BRG/PAT/CCA-Rd/03 (Tender ID 62008) | Improvement of road from Kathal Toli GPS Cum Cyclone shelter Connecting road ( Kathaltoli Bazar -Parighata via Kathaltoli GPS Road )at ch 0m-2230m | 504094009 |  | 2.23 |  |  |  |  | 11733997 | 9798093.32 | M/S Arif & Asif Construction | 26.09.2016 | 03.10.2016 | 19.08.2017 (15.02.2018) |  | 100% | 9759315 | 99.6% |  | Final bill paid
21 | BDRIDP/BRG/AMT/CCA-Rd/01 (Tender ID 72101) | Improvement of road by BC from Angulkata GPS cum cyclone shelter-North Angulkata GPS & Lunch ghat via Khekuani Bazar Road at ch 1900m-4200m.Effective length 2270m and construction of 1 No0.925mx1.20m U-Drain(L=8m) at ch 3250m. | 504094014 |  | 2.27 |  |  |  | 0.925 | 13105957 | 10943307.62 | M/S Mithun Traders | 26.12.2016 | 01.01.2017 | 06.11.2017 |  | 100% | 10943307 | 100% |  | Final bill paid
22 | BDRIDP/BRG/SAD/CCA-Rd/01 (Tender ID 72101) | Improvement of road from Barguna - Lakurtala -Dhupati - Chandukhali GC at ch 8400m-10025m with construction of 2 Nos small structure U-Drain(625mmx900mm) at ch 8625m & 9350m | 504282007 |  | 1.625 |  |  |  | 1.25 | 11488931 | 10121414.92 | M/S Sonali Enterprise | 30.01.2017 | 07.02.2017 | 07.02.2018 (30.06.2018) |  | 100% | 9964635 | 100% |  | Final
23 | BDRIDP/BRG/BAM/CCA-RdR/01 (Tender ID 103724) | Rehabilitation of road from Maidha Kakchira GPS cum Cyclone Shelter- Cotto Bhaijora GPS- Khuchnichora GPS cum Cyclone Shelter road from Ch. 930-2100m (Road ID-504194011 Salvage amount Tk 688913.00) Upazila: Bamna , District: Barguna. | 504194011 |  | 1.17 |  |  |  |  | 6302039 | 5671835 | M/S Poly construction | 17.07.2017 | 01.09.2017 | 28.02.2018 (28.02.2019) |  | 100% | 5671835 | 100% |  | Final bill paid
24 | BDRIDP/BRG/BAM/CCA-Rd/03 | Improvement of Road from Tulatala BC road to Bebazia khal GPS cum Cyclone Shelter via Dhalu Sikder House from Ch. 00-500m under Bamna Upazila District Barguna Road ID-504194051 Salvage amount Tk. 27776 | 504194051 |  | 0.5 |  |  |  |  | 2522537 | 2270283.3 | M/S Kohinoor Enterprise | 24.09.2017 | 27.09.2017 | 27.03.2018 |  | 100% | 2114620 | 100% |  | Final bill paid
25 | BDRIDP/BRG/BAM/CCA-Rd/04 | Improvement of road from Ramna dawatala battala Culvert- Wapda via Poschim Golaghata GPS Cum Cyclone Shelter at ch 0.00-715m and Construction of 05Nos U-Drain on same road at ch 40m,250m450m,593m & 682m under Bamna Barguna | 504854019 |  | 0.715 |  |  |  | 3.75 | 5184525 | 4925975.98 | M/S Atom Enterprise | 01.03.2018 | 07.03.2018 | 07.09.2018 (31.12.2018) |  | 100% | 4918601 | 100% |  | final bill paid
26 | BDRIDP/BRG/PAT/CCA-Rd/04(ID-146855) | Improvement of Amratala GPS Cum Cyclone Shelter Connecting road Kelmegha UP-Mesherpur Bazar via Paschim Amratala GPS road. DPP ID No-504855062 New ID No-504853020 a) Earthwork Ch. 00-1000m. b) Bituminous Carpeting Ch. 00-1000m. c) U-Drain at Ch. 112.00m, 355.00m, 528.00m & 947.00m under Patharghata Upazila, District Barguna. | 504855062 & 504853020 |  | 1 |  |  |  | 2.5 | 6986296.47 | 6892012.88 | M/S KK Enterprise | 08.02.2018 | 25.02.2018 | 10.07.2018 |  | 100% | 6884475 | 99.89% |  | final bill paid
27 | BDRIDP/BRG/ AMT/CCA-Rd/02(ID-162870) | Improvement of road Khaliyan Bus-Stand to H/O Hasem Mridha via Valoybunia GPS & Nilgonj High School Road by BC From Ch. 00m to 1450m Including structure under Amtali Upazila, District: Barguna [Road ID-504094087] | 504094087 |  | 1.45 |  |  |  |  | 9165157 | 8962617.1 | Md. Abul Kalm Azad | 30.04.2018 | 30.10.2018 | 10.03.2019 |  | 100% | 8957147 | 99.94% |  | Final Bill Paid
28 | BDRIDP/BRG/ BAM/UN-Rd/02(ID-162871) | Improvement of Bamna UP Office-Gudhighata Bazar via Kuchnichora GPS Ramna UP Office-Gudhighata Bazar via Kuchinichora GPS Road by BC From Ch. 1370m to 2370m Earthen from CH. 1000m to 2000m & 1 Nos U-Drain at Ch. 1940m under Bamna Upazila, District: Barguna [Road ID-504193006]. | 504193006 |  | 1 |  |  |  | 0.625 | 5985941.34 | 5387347.2 | M/S Khankaker Sahin Ahmed.Paschim Goalchatmot. Faridpur | 06.05.2018 | 14.05.2018 | 14.11.2018 (31.03.2021) |  | 40% | 1576723 | 29.27% |  | AS completed. WBM on going
29 | BDRIDP/BRG/BAM/CCA-Rd/05(ID-162872) | Improvement of Uttar Kakchira Bazar Chalavanga Launch Ghat via Gudhighata Adarsha GPS cum Cyclone Shelter Road by BC From Ch. 00m to 1000m under Bamna Upazila, District: Barguna [Road ID-504194080] | 504194080 |  | 1 |  |  |  |  | 5919275.8 | 5327342.22 | M/S Khankaker Sahin Ahmed.Paschim Goalchatmot. Faridpur | 06.05.2018 | 14.05.2018 | 14.11.2018 (31.03.2021) |  | 60% | 1441618 | 27.06% |  | W BM on Complete
30 | BDRIDP/BRG/ BAM/UN-Rd/03(ID-162873) | Improvement of Dawatala UP Office-Uttar Kakchira Bazar via Nobogram GPS Road by BC From Ch. 00m to 1000m under Bamna Upazila, District: Barguna [Road ID-504193012] (Salvage amount Tk 426251.00). | 504193012 |  | 1 |  |  |  |  | 7378671 | 6640804.52 | M/S Khankaker Sahin Ahmed.Paschim Goalchatmot. Faridpur | 13.05.2018 | 21.05.2018 | 21.11.2018 (31.12.2019) |  | 100% | 6543000 | 100% |  | Final bill paid
31 | BDRIDP/BRG/ PAT/GHT/01 | Construction of Gfhat at Kakchira Bazar(GC) | [6 empty] | 1 | 2915940 | 2864196.44 | M/S Arif & Asif Construction. Sadar road Barguna. | 06.06.2018 | 13.05.2018 | 13.09.2018 |  | 0% |  | 0% |  | Work cancel
32 | BDRIDP/BRG/ BAM/GHT/01 | Construction of Gfhat at Bukabunia Bazar | [6 empty] | 1 | 3029594.82 | 3019058.92 | M/S Arif & Asif Construction. Sadar road Barguna. | 20.05.2018 | 27.05.2018 | 27.09.2018 (31.05.2019) |  | 100% | 3005010 | 99.53% |  | Final bill paid
33 | BDRIDP/BRG/ TAL/GHT/01 | Construction of Gfhat at Taltali Bazar(GC) | [6 empty] | 1 | 3438990 | 3267040.67 | M/S jahanara Islam,College Road,Barguna | 24.06.2018 | 02.07.2018 | 02.11.2018 (17.12.2018) |  | 100% | 2871945 | 87.91%
34 | BDRIDP/BRG/AMT/UZ-St/01 | Construction of 21.00n RCC Girder Bridge on Amtali Mohiskata R&H - Kalagasia Kaserhat GC via Gulishakhali Bazar at ch 3790m under Amtali Upazila.Barguna. | 504092010 | [5 empty] | 21 | 15544813.32 | 14763772.65 | Md.Enayet Hossain | 07.05.2018 | 14.05.2018 | 14.01.2019 (30.11.2019) |  | 100% | 14134746 | 100% |  | Final
35 | BDRIDP/BRG/PAT/CCA-Rd/05 | Improvement of Kamarer Hat- Thakurbari to Katakhali Union road under Patharghata Upazila District Barguna Road ID-504854067a Earthwork Ch. 0.00m-250.00mb Carpeting BC Ch. 0.00m-250.00m | 504854067 |  | 0.25 |  |  |  |  | 1714935 | 1629188.25 | M/S Othoi Enterprise,Dakkhin monosha,Purbo Dhupoti, Barguna Sadar,barguna. | 24.06.2018 | 01.07.2018 | 31.12.2018 |  | 100% | 1529432 | 100% |  | Final
36 | BDRIDP/BRG/PAT/CCA-Rd/06 | Improvement of Gabbaria GPS-Wapda Kamal shop via Tafalbaria Madrasha road under Patharghata Upazila District Barguna Road ID- 504855113a Earthwork Ch. 0.00m-2538.00mb Carpeting BC Ch. 0.00m-2538.00mc U-Drain 04 Nos at Ch. 628m 962m 1538m & 1950m | 504855113 |  | 2.53 |  |  |  |  | 16834834.65 | 16666486.3 | M/S Akon Traders, pathorghata pauroshova, Barguna | 24.06.2018 | 01.07.2018 | 30.12.2018 (31.05.2019) |  | 100% | 16665819 | 100% |  | Final
37 | BDRIDP/BRG/SAD/CCA-Rd/01 (188387) | Improvement of Kumarkhali GPS Connecting Approach Road Bawalker GCCR- Kumarkhali Jame Mosque Road at Ch. 00.00m to 1000.00m under Barguna Sadar Upazila District Barguna Road ID- 504285029 Salvage amount Tk. 605472.00 |  |  | 1 |  |  |  |  | 6349339 | 6031872.53 | M/S RS Buisness Center | 05.07.2018 | 13.07.2018 | 13.01.2019 |  | 100% | 6030189 | 99.97% |  | Final
38 | BDRIDP/BRG/SDR/UZ-St/04 (190364) | Construction of 15.00m Long RCC Girder Bridge on Katherpul RHD-Kadamtala Hat-Baikalin Hat-Ayla GC road at Ch. 4364.00m Road ID- 504282010 under Barguna Sadar Upazila Barguna District. | 504282010 | [5 empty] | 15 | 13779578 | 13090599.45 | M/S RS Buisness Center | 05.07.2018 | 13.07.2018 | 13.01.2019 |  | 100% | 13088611 | 99.98% |  | Final
39 | BDRIDP/BRG/SDR/UZ-St/02(190361) | Construction of 36.00m Long RCC Girder Bridge on Katherpul RHD-Kadamtala Hat-Baikalin Hat-Ayla GC road at Ch. 6455.00m Road ID -504282010 under Barguna Sadar Upazila Barguna District. | [6 empty] | 36..00 | 21799736 | 20906703.75 | M/S Khan Enterprise & M/S Poly Construction | 05.08.2018 | 13.08.2018 | 13.04.2019 (23.11.2019) |  | 95% | 18998549 | 90.87% |  | Approach completed
40 | BDRIDP/BRG/SDR/UZ-St/03(190362) | Construction of 20.00m Long RCC Girder Bridge on Barguna-Lakurtala-Dhapati-Chandukhali GC Road Amtali-Kakchira RHDLakurtala-Chandukhali GC via Andarmanik Road Sadar Part at Ch. 11580.00m Road ID -504282007 under Barguna Sadar Upazila Barguna District. | [6 empty] | 20 | 23059314.24 | 22097987.62 | Quashem Construction & M/S polly Store(JV).Town Kalikapur, patuakhali | 12.08.2018 | 19.08.2018 | 19.08.2019 (01-11-19) |  | 90% | 19479731 | 88.15% |  | Approach completed
41 | BDRIDP/BRG/TAL/UZ-St/02(190363) | Construction of 36.06m Long RCC Girder Bridge on Kathupatra GC-Bogirhat GC via H/O Patoary & Panchakoralia Bazar road at Ch. 9714.00m Road ID -504872005 under Taltali Upazila Barguna District. | [6 empty] | 36.06 | 23278939 | 22320471 | M/S Arif & Asif Construction & M/S Mithun Traders (JV0 | 24.07.2018 | 01.08.2018 |  |  | 100% | 22225780 | 99.58% |  | Final
42 | BDRIDP/BRG/TAL/UZ-St/01(188388) | Construction of 50.06m RCC Girder Bridge on Kachupatra GC- Bogirhat GC via Panchakoralia at Ch. 350.00m under Taltali Upazila District Barguna Road ID- 504872005 | [6 empty] | 50.06 | 29010460 | 27412692 | M/S Arif & Asif Construction & M/S Mithun Traders (JV0 | 24.07.2018 | 01.08.2018 | 30.05.2019 |  | 100% | 27290296 | 99.55% |  | Final
43 | BDRIDP/BRG/BAM/CCA-Rd/06 | Improvement of road Chalitabunia Bazar Bukabunia UP Dr. Lublu House.ID No-504194004 (a) Earth wark from Ch. 1739m-3174m. (b) Carpeting BC from Ch. 1739m-3174m. (c) Construction of 1 Nos 4.00mx3.00m & 1 Nos 1.5mX1.5m Box Culvert at Ch. 2616m & 2424m. 2 Nos 0.625mX0.625m U-drain at Ch 2924m & 3114m under Bamna Upazila, District: Barguna (Estimated Cost : 1,23,35,199.00). | 504473014 |  | 1.44 |  |  |  |  | 12335199 | 11718439.05 | M/S Akon Trading Hospital Road ,Bamna, Barguna | 05.08.2018 | 13.08.2018 | 13.02.2019 |  | 100% | 11698840 | 99.83% |  | Final
44 | BDRIDP/BRG/SAD/CCA-St/05 | Construction of 29.00m PSC Girder Bridge on Katherpol RHD - Kadamtala Hat - Baikalin Hat - Ayla GC road at ch 3215m under Barguna sadar,Barguna. Road ID- 504282010 | 504282010 | [5 empty] | 29 | 22562486.91 | 22045900.26 | M/S Quashem Const. -M/S polly Store(JV) | 24.01.2019 |  | 12.12.2019 (30.12.2020) |  | 60% | 10650000 | 48.31% |  | Abutment Completed
45 | BDRIDP/BRG/SAD/UZ-St/06 (234465) | Construction of Retaining wall & Under pass way of 72.00n Long RCC Girder Bridge Approach on Barguna - Fuljhuri GC- Kakchira GC road Adjacent to Barguna Fish Market at ch 50m ID No-504282003 (a) retaining wall 84.00m (b)guide wall 8.40m (c 2Nos Culvert 3.00mX3.00m 6m under Barguna Sadar Upazila.Barguna. | 504282003 | [5 empty] | 6 | 7594651.03 | 7214918.45 | M/S RS Buisness Center | 24.12.2018 | 01.01.2019 | 30.06.2019 |  | 100% | 6902922 | 100% |  | Final
46 | BDRIDP/BRG/SAD/CCA-Rd/02, (253161) | Improvement of Nazimuddin Bari-Kasem Musuli Bari road. ID No-504285074 a Earth wark from Ch. 00 - 1000m. 9b Carpeting DC from at Ch. 00 - 1000m. c Construction of 3 Nos U - Drain at Ch. 400m 580m 800m. Under sadar Upazila,Barguna. | 504285074 |  | 1 |  |  |  | 1.88 | 7380000.66 | 7011000.62 | M/S Taj Enterprise,Nazrul Islam Road,Barguna. | 28.01.2019 |  | 05.09.2019 |  | 100% | 7009859 | 99.98% |  | final
47 | BDRIDP/BRG/SAD/CCA-Rd/03, (253162) | Improvement of Monosatoli Sluice - Latakata road. ID No-504285078 a Earth wark at Ch. 00 - 1000m. b Carpeting DC from at Ch. 00 - 1000m. c Construction of 2 Nos U - Drain at Ch. 540m 700m. Under sadar Upazila,Barguna. | 504285078 |  | 1 |  |  |  | 1.25 | 7285995.61 | 7174936 | M/S Azad Traders | 28.01.2019 |  | 16.06.2019 |  | 100% | 7174936 | 100% |  | Final
48 | BDRIDP/BRG/AMT/UZ-St/02, (267090) | Construction of 20.00m RCC Girder Bridge on Amtali Moshiskata RHD -Kalagasia Khasher Hat GC Via Gulishakhali bazar at Ch 6085m under Amtali,,Barguna. Road ID- 504092010 | 504092010 | [5 empty] | 20 | 16919025.42 | 14204167 | M/S Amir Engineering corporetion & M/S Khandoker Brothers(JV) | 05.04.2019 | 12.04.2019 | 12.04.20120 |  | 100% | 13770562 | 96.95% |  | B/S abutment & wing wall completed
49 | BDRIDP/BRG/SAD/UN-Rd/01 ,(277654) | Improvement of Gourichanna East Lakurtala-Rodpara Bazar road from Ch. 1185.00m 2685.00m ID No-504283004 (a) Earth wark from Ch.1185 - 2685m. (b) Carpeting Ch.1185-2685m. (c) 2 Nos U - Drain at Ch. 2085m & 2580m | 504283004 |  | 1.5 |  |  |  | 1.25 | 11805558 | 11207240 | M/S Mohiuddin Ahmed. Papuakhali | 01.05.2019 |  | 16.12.2019 (31.12.2020) |  | 60% | 5852663 | 52.22% |  | WBM on going
50 | BDRIDP/BRG/AMT/UN-Rd/01, (278816) | Improvement of Atharogasia UP - Munsir Hat via uttar Garabunia Bazar & GPS road from Ch 0.00-2000.00m under Amtali Upazila. ID No-504093029 | 504093029 |  | 2 |  |  |  |  | 11911911 | 11394729 | M/S Mohiuddin Ahmed. Papuakhali | 08.05.2019 |  | 01.03.2020 (30.12.2020) |  | 65% | 5788900 | 50.8% |  | WBM Completed
51 | BDRIDP/BRG/AMT/UZ-Rd/02 ,(278481) | Improvement of Gazipur GC-Badura GC via Atharogasia UP road from Ch 2850.00-3748.00m & 3877m-3987m. at Amtali Upazila ID No-504092006 | 504092006 |  | 1 |  |  |  |  | 7812226 | 7421615 | M/S Tanha Enterprise.Vill & post:Paschim Chila,Amtali, Barguna | 31.03.2019 | 07.04.2019 | 07.11.2019 (30.05.2020) |  | 100% |  | 0%
52 | BDRIDP/BRG/AMT/GHAT/01,(279781) | Construction of RCC Ghatla at Gazipur Bazar under Amtali Upazila Dist Barguna. | [6 empty] | 1 | 2985902 | 2836607 | M/S Sikder & Sons | 24.04.2019 |  | 30.01.2020 |  | 100% | 1823034 | 64.27%
53 | BDRIDP/BRG/BET/UN-Rd/01, (299697) | Improvement of Hosnabad UPC - Kazirhat GC to Late Asraf Ali Talukder Ex-MUP Bari Mosque Link Road Ch. 00m - 250m (a) Earthwork from Ch oom - 250m. (b) Carpeting DC Ch 00m - 250m. (c) Palisading 83m ID No-504473014 under Betagi Upazila Dist Barguna. Salvage-8,878.00. | 504473014 |  | 0.25 |  |  |  |  | 2237665.46 | 2125782 | M/S Musulli Construction, Boro labongola, Barguna Sadar, Barguna | 16.05.2019 |  | 23.11.2019 |  | 100% | 2125303 | 99.98% |  | Final
54 | BDRIDP/BRG/BET/CCA-Rd/03 ,(299698) | (A) Improvement of Jamir Uddin bridge - RRIPM Bridge near at H/O Ataher Matubber Road by BC Ali Howlader House - Doctor Bari road Ch. 1400m-2100m (a) Earthwork from Ch 1400m-2100m (b) Carpeting DC Ch 1400m-2100m (c) 1 no 2.6m x 2.00m RCC Box Culvert at Ch. 1745 ID No-504474222 under Betagi Upazila Dist Barguna. (B) Improvement of Kazir hat UZR-H/O Hashim member Road by BC Ch. 00m-700m (a) Earthwork from Ch. 00m-700m (b) Carpeting DC Ch. 00m-700m ID No-504474194 Under Betagi Upazila Dist Barguna. Salvage-2,12,137.00 | 504474194 |  | 0.7 |  |  |  | 2.6 | 5231076 | 9213511 | M/S Al Mamun | 11.06.19 |  | 27.02.2020 |  | 50% |  |  |  | WBM ongoing
55 | BDRIDP/BRG/PAT/CCA-Rd/07 (299699) | , Improvement of Battala RHD-Kalmegha High School Abdus Sattar Khan Bari Road Ch. 00m-640m (a) Earth work from Ch. 00m-640m (b) Carpeting DC Ch. 00m - 640m (c) 2 nos U-Drain at Ch. 27m & 251m ID No-504854068 under Patharghata Upazila Dist Barguna. | 504854068 |  | 0.64 |  |  |  | 1.25 | 5188058.36 | 4928655 | M/S Othoi Enterprise, Dakkhin monoshatali, Purbo Dhupoti, Barguna Sadar,barguna. | 16.05.2019 | 23.05.2019 | 23.12.2019 (17.03.2020) |  | 100% | 4895764 | 100% |  | Final
56 | BDRIDP/BRG/AMT/GC/01 (305315), | Improvement of Gazipur Bazar (i) Single Storied Multipurpose Shed Size 12.00mx6.00m. (ii) Interal road (a) CC Road0.54km (b) HBB Road 0.25 km (iii) Toilet Block 5.75mx3.075m (iv) Deep Tube-Well under Amtali Upazila Dist Barguna. | [6 empty] | 1 | 4979196 | 4730236 | Mahi Enterprise, Bawalkor, Barguna Sadar,Barguna | 20.05.2019 |  | 27.11.2019 (30.12.2020) |  | 75% | 1435921 | 30.36% |  | Multipurpose shade & Toilet Block work on going
57 | BDRIDP/BRG/SAD/CCA-Rd/04(397674) | Improvement of Sujauddin Khayagha t- Rodpara Bazar Road.at Ch.3100m-4100m Road ID504284033 | 504284033 |  | 1 |  |  |  |  | 10062601 | 9549471 | M/S Belal Hossain Traders | 02.06.2020 |  | 09.08.2020 |  | 25% |  |  |  | Redy for ISG
58 | BDRIDP/BAR/BET/UZ-St/03 (410433) | Construction of 30.06m Long RCC Girder Bridge on Niamati- Deshanterkati via DC hat Niamati GC-Barguna-Bakergonj RHD Kanki Bazar Road at ch.4551 Km Road ID 504472002 Under Betagi Upazila Dist Barguna. | 504472002 | [5 empty] | 30.06 | 29689957 | 24210105 | M/S lyla Builders & Md Lutful kabir (JV) | 24.05.2020 |  | 11.04.2021 |  | 0% |  |  |  | Preparation for pile casting
LCS
1 | BDRIDP/BRG/BET/UZ-Ew/01 | Badnikhali GC- Kazirhat GC via west karuna High school road by Earth Work from ch 00.00m-900.00m under Betagi. | 504472005 | 2524.25 | [5 empty] | 335624 | 335624 | LCS Kabir | 11.01.2015 | 01.02.2015 | 30.04.2015 |  | 100% | 333922 | 100% | 28.09.2014 | Final
2 | BDRIDP/BRG/BET/UZ-Ew/01 | Badnikhali GC- Kazirhat GC via west karuna High school road by Earth Work from ch 900.00m-1800.00m under Betagi. | 504472005 | 2510.5 | [5 empty] | 333796 | 333796 | LCS Ripon | 11.01.2015 | 01.02.2015 | 30.04.2015 |  | 100% | 332167 | 100% |  | Final
3 | BDRIDP/BRG/BET/UZ-Ew/01 | Badnikhali GC- Kazirhat GC via west karuna High school road by Earth Work from ch 1800.00m-2500.00m under Betagi. | 504472005 | 2717.25 | [5 empty] | 361285 | 361285 | LCS Shapon | 11.01.2015 | 01.02.2015 | 30.04.2015 |  | 100% | 359856 | 99.6% |  | Final
4 | BDRIDP/BRG/BET/UZ-Ew/02 | Badnikhali GC- Kazirhat GC via west karuna High school road by Earth Work from ch 2500.00m-3700.00m under Betagi. | 504472005 | 3155.7 | [5 empty] | 418754 | 418754 | LCS Shanu | 11.01.2015 | 01.02.2015 | 30.04.2015 |  | 100% | 416949 | 100% |  | Final
5 | BDRIDP/BRG/BET/UZ-Ew/03 | Resectioning of road from Niamati - Deshanterkathi via DC Hat Ch. 3900-5363m | 504472002 | 1463 | [5 empty] | 493864 | 493864 | LCS Hemayet | 24.05.2015 | 09.06.2015 | 30.08.2015 |  | 100% | 488911 | 100% |  | Final
6 | BDRIDP/BRG/AMT/CCA-Ew/01 | Angulkata GPS cum cyclone shelter -North Angulkata GPS & Angilkata Launch ghat via Khekuani Bazar road at ch1800.00m-2300.00m under Amtali,Barguna | 504094014 | 3087 | [5 empty] | 388912 | 388912 | LCS Harun | 29.04.2015 | 05.05.2015 | 05.06.2015 |  | 100% | 388151 | 99.8% |  | Final
7 | BDRIDP/BRG/AMT/CCA-Ew/01 | Angulkata GPS cum cyclone shelter -North Angulkata GPS & Angilkata Launch ghat via Khekuani Bazar road at ch2300.00m-2850.00m under Amtali,Barguna | 504094014 | 2395.88 | [5 empty] | 297303 | 297303 | LCS Nurul Islam | 29.04.2015 | 05.05.2015 | 05.06.2015 |  | 100% | 296072 | 99.59% |  | Final
8 | BDRIDP/BRG/AMT/CCA-Ew/01 | Angulkata GPS cum cyclone shelter -North Angulkata GPS & Angilkata Launch ghat via Khekuani Bazar road at ch2850.00m-3250.00m under Amtali,Barguna | 504094014 | 2530.25 | [5 empty] | 310739 | 310739 | LCS Harun Gazi | 29.04.2015 | 05.05.2015 | 05.06.2015 |  | 100% | 308552 | 100% |  | Final
9 | BDRIDP/BRG/AMT/CCA-Ew/01 | Angulkata GPS cum cyclone shelter -North Angulkata GPS & Angilkata Launch ghat via Khekuani Bazar road at ch3250.00m-3650.00m under Amtali,Barguna | 504094014 | 2316 | [5 empty] | 289045 | 289045 | LCS Abdul Aziz | 29.04.2015 | 05.05.2015 | 05.06.2015 |  | 100% | 288327 | 99.75% |  | Final
10 | BDRIDP/BRG/AMT/CCA-Ew/01 | Angulkata GPS cum cyclone shelter -North Angulkata GPS & Angilkata Launch ghat via Khekuani Bazar road at ch 3650.00m-4100.00m under Amtali,Barguna | 504094014 | 2493.75 | [5 empty] | 310627 | 310627 | LCS Al-Amin | 29.04.2015 | 05.05.2015 | 05.06.2015 |  | 100% | 308915 | 100% |  | Final
11 | BDRIDP/BRG/BAT/CCA-Ew/01(a) | Re-section of road from Betagi Barguna(UZR/Bangobandhu Bazar)-Charkhali Wapda Bazar (Bangobandhu Bazar-Paschim Karuna H/S -Kaialghata-Charkhali)road by Earthen at ch 0.00-500.00m under Betagi,Barguna. |  | 3010.35 | [5 empty] | 400256 | 400256 | LCS Nur-E-Alom | 12.11.2015 | 01.01.2016 | 30.05.2016 |  | 100% | 396356 | 100% |  | Final
12 | BDRIDP/BRG/BAT/CCA-Ew/01(b) | Re-section of road from Betagi Barguna(UZR/Bangobandhu Bazar)-Charkhali Wapda Bazar (Bangobandhu Bazar-Paschim Karuna H/S -Kaialghata-Charkhali)road by Earthen at ch 500.00-2200.00m under Betagi,Barguna |  | 3584.2 | [5 empty] | 476555 | 476555 | LCS Forkan Mollik | 12.11.2015 | 01.01.2016 | 30.05.2016 |  | 100% | 474446 | 99.56% |  | Final
13 | BDRIDP/BRG/BAT/CCA-Ew/01(c) | Re-section of road from Betagi Barguna(UZR/Bangobandhu Bazar)-Charkhali Wapda Bazar (Bangobandhu Bazar-Paschim Karuna H/S -Kaialghata-Charkhali)road by Earthen at ch2200.00-3425.00m under Betagi,Barguna |  | 3620.6 | [5 empty] | 481395 | 481395 | LCS Monir Hosain | 12.11.2015 | 01.01.2016 | 30.05.2016 |  | 100% | 478447 | 100% |  | Final
14 | BDRIDP/BRG/BAM/CCA-Ew/01 | Re-section of road from Bamna Bukabunia road-Gafur Master Hiouse at RAPDA road by Earthen at ch 00.00-600.00m under Bamna,Barguna | 504195037 | 1560 | [5 empty] | 181319 | 181319 | LCS Mrs. Bauety Begum | 26.01.2016 | 03.06.2016 | 20.06.2016 |  | 100% | 178296 | 100% |  | Final
15 | BDRIDP/BRG/PAT/CCA-Ew/01 | Re-section of road from Patharghata Jhaliaghata Bridge-Apeler Bridge road by Earthen at ch 00.00-1483.00m under Patharghata,Barguna | 504855032 | 4410 | [5 empty] | 253136 | 253136 | LCS Khadija Begum | 24.05.2016 | 03.06.2016 | 20.06.2016 |  | 100% | 253136 | 100% |  | Final
16 | BDRIDP/BRG/AMT/CCA-Ew/01 | Improvement of road by Earth workfrom Amtali-Moshiskata RHD-Kalagasia Khasher Hat GC via Gulishakhali Bazar at ch 6843m-7500m under Amtali,Barguna. | 504092010 | 1732.29 | [5 empty] | 277323 | 277323 | Md.jamal Hossain | 18.08.2016 | 01.09.2016 | 30.03.2017 |  | 100% | 276022 | 99.53% |  | Final
17 | BDRIDP/BRG/AMT/CCA-Ew/02 | Improvement of road by Earth workfrom Amtali-Moshiskata RHD-Kalagasia Khasher Hat GC via Gulishakhali Bazar at ch 7500m-7900m under Amtali,Barguna. | 504092010 | 2321 | [5 empty] | 370381 | 370381 | Md.Shahidul Islam | 18.08.2016 | 01.09.2016 | 30.03.2017 |  | 100% | 367377 | 100% |  | Final
18 | BDRIDP/BRG/AMT/CCA-Ew/03 | Improvement of road by Earth workfrom Amtali-Moshiskata RHD-Kalagasia Khasher Hat GC via Gulishakhali Bazar at ch 7900m-8400m under Amtali,Barguna. | 504092010 | 1962.75 | [5 empty] | 313752 | 313752 | Md Shohel Musulli |  | 01.09.2016 | 30.03.2017 |  | 100% | 310867 | 100% |  | Final
19 | BDRIDP/BRG/AMT/CCA-Ew/04 | Improvement of road by Earth workfrom Amtali-Moshiskata RHD-Kalagasia Khasher Hat GC via Gulishakhali Bazar at ch 8400m-8843m under Amtali,Barguna. | 504092010 | 2019.99 | [5 empty] | 322799 | 322799 | Md.Shahin Gazi | 18.08.2016 | 01.09.2016 | 30.03.2017 |  | 100% | 317729 | 100% |  | Final
20 | BDRIDP/BRG/AMT/CCA-Ew/01 | Improvement of road from Bamna Bukabunia road to gafur Master House at WAPDA road from ch 0.00-600.00m | 504195037 | 1560 | [5 empty] | 181319 | 181319 | Mrs Beauty Begum | 03.06.2016 | 20.06.2016 | 20.06.2016 |  | 100% | 178296 | 100% |  | Final
21 | BDRIDP/BRG/PAT/UZ-Rd/01 | Improvement of Kalmegha - Charduani GC Road from ch 2134m-4200m(ID No-504852005) | 504852005 | 2066 | [5 empty] | 246244 | 246244 | Md Shah Alom | 08.12.2016 | 30.05.2017 |  |  | 100% | 243133 | 100% |  | Final
22 | BDRIDP/BRG/PAT/UZ-Rd/02 | Improvement of Kalmegha - Charduani GC Road from ch 4200m-5550m(ID No-504852005) | 504852005 | 1350 | [5 empty] | 260519 | 260519 | Md. A.Rahim | 08.12.2016 | 30.05.2017 |  |  | 100% | 260517 | 100% |  | Final
23 | BDRIDP/BRG/PAT/UZ-Rd/03 | Improvement of Kalmegha - Charduani GC Road from ch 5550m-6600m(ID No-504852005) | 504852005 | 900 | [5 empty] | 247212 | 247212 | Monju Rani Adhikay | 08.12.2016 | 30.05.2017 |  |  | 100% | 247211 | 100% |  | Final
24 | BDRIDP/BRG/PAT/UZ-Rd/04 | Improvement of Kalmegha - Charduani GC Road from ch 6600m-6944m(ID No-504852005) | 504852005 | 344 | [5 empty] | 170598 | 170598 | Gonesh Chandra | 08.12.2016 | 30.05.2017 |  |  | 100% | 170598 | 100% |  | Final
25 | BDRIDP/BRG/PAT/UZ-Rd/05 | Improvement of Kalmegha - Charduani GC Road from ch 6944m-7500m(ID No-504852005) | 504852005 | 547 | [5 empty] | 328930 | 328930 | Shibani Rani | 08.12.2016 | 30.05.2017 |  |  | 100% | 328727 | 99.94% |  | Final
26 | BDRIDP/BRG/PAT/UZ-Rd/06 | Improvement of Kalmegha - Charduani GC Road from ch 7500m-8100m(ID No-504852005) | 504852005 | 600 | [5 empty] | 264024 | 264024 | Nikunjo Majhi | 08.12.2016 | 30.05.2017 |  |  | 100% | 264063 | 100% |  | Final
27 | BDRIDP/BRG/PAT/CCA-EW/02 | Improvement of road from Chaherabad GPS cum Cyclone Shelter (Chaherabad Dali Bari - Subendra Nath High school) at ch 0m-1435m | 504855093 | 1424.5 | [5 empty] | 227046 | 227046 | Shyamol | 03.05.2017 | 30.062 |  |  | 100% | 226767 | 99.88% |  | Final
28 | BDRIDP/BRG/PAT/CCA-EW/03 | Improvement of road from Kathal Toli GPS Cum Cyclone shelter Connecting road ( Kathaltoli Bazar -Parighata via Kathaltoli GPS Road )at ch 0m-2230m | 504854009 | 1702.33 | [5 empty] | 301648 | 301648 | Md.Mozibar | 03.05.2017 | 30.062 |  |  | 100% | 301434 | 99.93% |  | Final
29 | BDRIDP/BRG/TAL/UZ-EW/01(Group-1) | Improvement of Kachupatra Gc - bogir Hat GC via Panchakoralia Bazar road by earth at ch 4560m-8150m under Taltali,Barguna | 504872005 | 2896.28 | [5 empty] | 352573 | 352573 | Lucky Begum | 05.02.2017 | 30.06.2017 |  |  | 100% | 349758 | 100% |  | Final
30 | BDRIDP/BRG/TAL/UZ-EW/01(Group-2) | Improvement of Kachupatra Gc - bogir Hat GC via Panchakoralia Bazar road by earth at ch 4560m-8150m under Taltali,Barguna | 504872005 | 2805.9 | [5 empty] | 341649 | 341649 | Rashida Begum | 05.02.2017 | 30.06.2017 |  |  | 100% | 339751 | 100% |  | Final
31 | BDRIDP/BRG/TAL/UZ-EW/01(Group-3) | Improvement of Kachupatra Gc - bogir Hat GC via Panchakoralia Bazar road by earth at ch 4560m-8150m under Taltali,Barguna | 504872005 | 2563.65 | [5 empty] | 312368 | 312368 | Hamida Begum | 05.02.2017 | 30.06.2017 |  |  | 100% | 311401 | 100% |  | Final
32 | BDRIDP/BRG/TAL/UZ-EW/01(Group-4) | Improvement of Kachupatra Gc - bogir Hat GC via Panchakoralia Bazar road by earth at ch 4560m-8150m under Taltali,Barguna | 504872005 | 2145.65 | [5 empty] | 261845 | 261845 | Rahima Begum | 05.02.2017 | 30.06.2017 |  |  | 100% | 260362 | 100% |  | Final
33 | BDRIDP/BRG/TAL/UZ-EW/01(Group-5) | Improvement of Kachupatra Gc - bogir Hat GC via Panchakoralia Bazar road by earth at ch 4560m-8150m under Taltali,Barguna | 504872005 | 2217.88 | [5 empty] | 270575 | 270575 | shahin Patoary | 05.02.2017 | 30.06.2017 |  |  | 100% | 269018 | 100% |  | Final
34 | BDRIDP/BRG/SDR/UZ-Ew/01(Group-1) | Improvement of road from Barguna - Lakurtala -Dhupati - Chandukhali GC at ch 8400m-9350m | 504282007 | 3380.5 | [5 empty] | 484159 | 484159 | Md.Chunnu Miah | 28.05.2017 | 30.06.2017 |  |  | 100% | 479776 | 100% |  | Final
35 | BDRIDP/BRG/SDR/UZ-Ew/01(Group-2) | Improvement of road from Barguna - Lakurtala -Dhupati - Chandukhali GC at ch 9350m-10025m | 504282007 | 2914.32 | [5 empty] | 415841 | 415841 | Abdus salam | 28.05.2017 | 30.06.2017 |  |  | 100% | 411927 | 100% |  | Final
36 | BDRIDP/BRG/AMT/UZ-EW/01 | Resectioning of road from Gazipur GC-Badura GC via Atharogasia UP Ch.3600m-4220m | 504092006 | 3095.87 | [5 empty] | 497877.81 | 497877.81 | Md.Shahajahan Fakir | 02.11.2017 | 21.11.2017 | 21.05.2018 |  | 100% | 496443 | 100% |  | Final
37 | BDRIDP/BRG/AMT/UZ-EW/02 | Resectioning of road from Gazipur GC-Badura GC via Atharogasia UP Ch.4200m-4850m | 504092006 | 2959.9 | [5 empty] | 476011.12 | 476011.12 | Md.Rubel chawkider | 02.11.2017 | 21.11.2017 | 21.05.2018 |  | 100% | 471741 | 100% |  | Final
38 | BDRIDP/BRG/AMT/UZ-EW/03 | Resectioning of road from Gazipur GC-Badura GC via Atharogasia UP Ch.4850m-5475m | 504092006 | 2993.12 | [5 empty] | 481353.56 | 481353.56 | Md.Harun fakir | 02.11.2017 | 21.11.2017 | 21.05.2018 |  | 100% | 476167 | 100% |  | Final
39 | BDRIDP/BRG/AMT/UZ-EW/03 | Resectioning of road from Gazipur GC-Badura GC via Atharogasia UP Ch.5475m-5860.00m | 504092006 | 3063.77 | [5 empty] | 492715 | 492715 | Ahmed Ali | 21.01.2018 | 28.01.2018 | 30.04.2018 |  | 100% | 484513 | 100% |  | Final
40 | BDRIDP/BRG/AMT/UZ-EW/03 | Resectioning of road from Gazipur GC-Badura GC via Atharogasia UP Ch.5860m-6285m | 504092006 | 2810.05 | [5 empty] | 451912 | 451912 | Md.Shahajahan | 21.01.2018 | 28.01.2018 | 30.04.2018 |  | 100% | 449142 | 100% |  | Final
|  |  |  | 93755.48 | 40.585 | 0 | 0 | 11.75 | 367.165 | 617235514.58 | 575913542.43 | [6 empty] | 478330676
|  | Accountant | Sub-Asstt-Engineer | [7 empty] | Asstt-Engineer |  |  |  | Sr.Asstt-Engineer |  |  |  | Executive engineer
|  | LGED,Barguna | LGED,Barguna. | [7 empty] | LGED,Barguna. |  |  |  | LGED,Barguna. |  |  |  | LGED,Barguna.