## On Going
Monthly Progress Report
Implementation Status
Barisal Division Rural Infrastructure Development Project
District: Patuakhali. | [15 empty] | Upto Month: November/2020
Sl No | Package No. | Scheme Name with Location (Ch. To Ch.) | Road ID No. | Effective Quantity (m3,km,m,Nos,ha) | [5 empty] | Approved Estimated Cost (Tk) | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract signing date | Actual start date | Completion date as per contract | Actual completion date | Physical Progress (%) |  | Financial Progress |  | Fund received with memo date | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | str. (m) | [9 empty] | Amount Spent(Tk) | in (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22
| Upazila: Bauphal | [19 empty] | Fy-2014-15 (Road)
21 | BDRIDP/PAT/BAF/CCA-Rd/16 | Improvement of road From Uttar Modonpura Islamia Dakhil Madrasha - Daroga bari -via golam Mostafa Chairman House by BC at Ch. 2000m-3680m including 01 No. 2.00mx2.00m & 01 No. 1.00mx1.00m RCC Box Culvert at ch. 750m and 3660m. (ID No. 578384223) (Salvage Cost: Tk. 413597.00) | 578384223 |  | 1.68 |  |  |  | 3 | 11305924.1 | 10951114.8 | M/S. Tanvir Ahmed | 2018-03-21 | 2018-03-28 | 2018-09-27 |  | 25% | 17.07% | 1868881 |  | Fy-2015-16 (Bridge Culvert) | 28 days final letter
26 | BDRIDP/PAT/BAF/UN-Rd/06 | Improvement of Road from Daspara UPC Moishadi Bazar via Char Alogi GPS Road by BC at Ch. 850m-1500m & 2500m-2850m including 01 No 3.00mX3.00m RCC Box Culvert at Ch. 2050m (ID No. 578383044) (Salvage: BDT: 1432898.00) | 578383044 |  | 1 |  |  |  | 3 | 7394045.61 | 7830472.257 | Md. Nazrul Islam Chunnu | 2018-10-24 | 2018-11-01 | 2019-04-29 |  | 65% | 27.46% | 2150000 |  | Memo No-818 dt.13-11-16 Tk.20,00,000.00
28 | BDRIDP/PAT/BAF/CCA-Rd/21 | Improvement of Madhya Modonpura Bridge RHD-Ramnagar Bazar & GPS Ramnagar Board GPS west Site St. Bridge via Kalu Howlader House/Hazi Bari Jame Mosque Satla Kha Bari at Ch. 00m-1000m including 01 Nos 1.00mX1.00m RCC Box at Ch. 775m & 01 No 0.625mX0.900m U-Drain Length7.00m at Ch. 150m. ID No. 578384046 | 578384046 |  | 1 |  |  |  | 1.625 | 7490969.64 | 7116421.158 | M/S AL MADINA MOTORS | 2019-04-25 | 2019-05-02 | 2020-06-30 |  | 50% | 23.89% | 1700000 |  | Fy-2016-17 (Road) | WBM on going
29 | BDRIDP/PAT/BAF/UN-Rd/ 07 | Improvement of road from Boga UP- Nowmala UP via Shabupura hat Road from Ch.00m-1950m including 02 Nos. 1.00m x 1.00m Box Culvert at Ch. 428m & 1140m. ID No. 578383002 under Bauphal Upazila District Patuakhali [OSTETM] | 578383002 |  | 1.95 |  |  |  | 2 | 15063619.78 | 13728356.438 | Md. Enayet Hossain | 2019-04-25 | 2019-05-02 | 2019-08-29 |  | 70% | 62.71% | 8608405 |  | Memo No-575 dt. 07-08-16 Warth work Tk.23,00,000.00 Road Tk.15,00,000.00 | BC on Going
36 | BDRIDP/PAT/BAF/UZ-St/01 | Construction of 20.00m RCC Girder Bridge on Boga Bauphal RHD (Shaplakhali) to Kalisuri GC via Kanakdia Hat Road at Ch. 12+290km (Road ID No. 578382004) | 578382004 | [5 empty] | 20 | 15035062.58 | 12849606.16 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-01-24 |  | 92% | 87.92% | 11297598 |  | Memo No-372 dt. 24-04-18 Road Tk.3,00,00,000.00 | Main Bridge Completed. Approach on going
37 | BDRIDP/PAT/BAF/UZ-St/02 | Construction of 20.00m RCC Girder Bridge on Mominpur GC - Baherchar GC via Kalisuri GC Road at Ch. 13+680km (Road ID No. 578382005) | 578382005 | [5 empty] | 20 | 16489178.72 | 14840260.848 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-12-31 |  | 90% | 79.91% | 11859262 |  | Memo No-476 dt. 06-06-18 Road Tk.3,50,00,000.00 | Main Bridge Completed. Approach on going
38 | BDRIDP/PAT/BAF/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Boga Bauphal RHD (Shaplakhali) to Kalisuri GC via Kanakdia Hat Road at Ch. 14+990km (Road ID No. 578382004) | 578382004 | [5 empty] | 15 | 12477741.85 | 11229967.655 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-01-24 |  | 90% | 84.62% | 9503330 |  | Memo No-490 dt. 11-06-18 Road Tk.68,50,000.00 | Main Bridge Completed. Approach on going
39 | BDRIDP/PAT/BAF/UZ-St/04 | Construction of 15.00m RCC Girder Bridge on Boga Bauphal RHD (Shaplakhali) to Kalisuri GC via Kanakdia Hat Road at Ch. 15+980km (Road ID No. 578382004) | 578382004 | [5 empty] | 15 | 12406863.41 | 11166177.069 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-12-30 |  | 80% | 74.42% | 8309801 |  | Fy-2018-19 (Road) | Main Bridge Completed. Approach on going
40 | BDRIDP/PAT/BAF/UN-St/05 | Construction of 15.00 m long RCC Girder Bridge on Kalisuri UP ( Kumarkhali Bridge) - Nurainpur Bazar via Kanakdia Bazar at ch 1+500 km. ID no-578383001 under Bauphal, Patuakhali. | 578383001 | [5 empty] | 15 | 11592689.73 | 11013055.244 | Md. Mahabubur Rahaman | 2020-03-19 | 2020-03-26 | 2020-07-03 |  | 30% |  |  |  | Memo No-699 dt. 10-10-18 Road Tk.1,50,00,000.00
41 | BDRIDP/PAT/BAF/UN-St/04 | Construction of 15.00 m long RCC Girder Bridge on Kalisuri UP ( Kumarkhali Bridge) - nurainpur Bazar via kanakdia Bazar at ch 1+600 km. ID no-578383001 | 578383001 | [5 empty] | 15 | 11644343.44 | 11062126.268 | M/S JUI ENTERPRISE | 2020-03-19 | 2020-03-26 | 2020-07-03 |  | 30% |  |  |  | Memo No-855 dt. 11-12-18 Road Tk.2,00,00,000.00
42 | BDRIDP/PAT/BAF/UZ-St/05 | Construction of 15.00 m long RCC Girder Bridge on Boga- Bauphal RHD ( Shaplakhali)- Kalisuri GC via Kanakdia Hat at Ch 13+180 km. (ID no-578382004) | 578382004 | [5 empty] | 15 | 16032937.12 | 13160872.049 | Md. Enayet Hossain | 2020-05-17 | 2020-05-24 | 2020-11-19 |  | 20% | 0% |  |  | Memo No-78 dt. 15-01-19 Road Tk.40,00,000.00
21 | BDRIDP/PAT/SDR/CCA-Rd/ 13 | Improvement of Road from Chottobeghi UP-8ashtala Bazar at Ch. 1000m-2500m.lncluding 02 Nos 1.50m x 1.50m. RCC Box at Ch. 1110.00m s 1350.00m ID No. 578954097 under Sadar Upazila District Patuakhali [OSTETM] | 578954097 |  | 1.5 |  |  |  | 3 | 11702504.42 | 10688183.983 | Md. Enayet Hossain | 2019-04-25 | 2019-05-02 | 2019-08-29 |  | 80% | 70.9% | 7577563 |  | Memo No-977 dt. 19-12-19 road Tk.1,50,00,000.00 | WBM Complete
24 | BDRIDP/PAT/SDR/CCA-Rd/15 (277979) | Improvement of Road from R&H Pairakunza Bazar to RHD Bus Stand Badher Hat from Ch. 00m-2000m including 03 Nos 1.50m x 1.50m RCC Box at Ch. 450.00m840.00m & 990.00m under Sadar Upazila District Patuakhali ID No. 578954060 | 578954060 |  | 2 |  |  |  | 4.5 | 15559650.14 | 14200725.199 | Md. Enayet Hossain | 2019-05-09 | 2019-05-16 | 2019-10-13 |  | 65% | 56.67% | 8047228 |  | Memo No-640 dt. 03-07-19 Tk.20,00,000.00 | WBM on going
35 | BDRIDP/PAT/SAD/UZ-St/04 | Construction of 42.06m RCC Girder Bridge on Patuakhali Barisal RHD (Moukaron Bridge)-Dumki UZHQ via Moukaran GC (Sadar Part) at Ch. 3282m (Road ID: 578952007) | 578952007 | [5 empty] | 42.06 | 26857732.46 | 24171959.214 | M/S. Amir Engineering Corporation-M.M. Builders & Engineers Ltd.-M/S. Niaz Traders-JV | 2018-04-24 | 2018-05-01 | 2019-04-30 |  | 98% | 97.66% | 23607480 |  |  | Main Str. Completed. Approach work on going
36 | BDRIDP/PAT/SDR/UZ-St/05 | Construction of 24.00m Long RCC Girder Bridge at Khasher hat GC to Bottolbunia GC via Hajhir hat.road at Ch. 3487.00m. (ID No-578952006) under Sadar Upazila, District: Patuakhali | 578952006 | [5 empty] | 24 | 27732668.12 | 25657219.712 | M/S. Hamim International Lubna Khanom | 2019-07-18 | 2019-07-25 | 2020-07-24 |  | 80% | 76.35% | 19589462 |  |  | Deck Slab Complete
6 | BDRIDP/PAT/DUM/UZ-Rd/01 | Improvement of road from Muradia UP-Laukathi UP via South Khali GPS & Bhoktobari A Salam Doctor Abari via Mozumder Hat road by BC at Ch.0.00m-2000.00m Old ID No- 578962003 New ID No. 578964015 | 578964015 |  | 2 |  |  |  |  | 11180031.09 | 10062027.981 | M/S. Amir Engineering Corporation | 2017-11-05 | 2017-11-12 | 2018-11-11 |  | 65% | 53.73% | 5406787 |  |  | WBM Complete
11 | BDRIDP/PAT/DUM/CCA-Rd/10 | Improvement of road from Atharogachia Mojibor Sikder Bari-Karthikpasha UZR road by BC at Ch.0.00m-1000.00m Including 1 No 4.00m x 4.00m 2 Nos 1.00m x 1.00m RCC Box Culvert at Ch. 536.00m 155.00m & 900.00m ID No-578964155 | 578964155 |  | 1 |  |  |  | 5 | 8400644.92 | 7560580.428 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2019-12-20 |  | 30% | 0% |  |  |  | ISG Completed. 28 days final letter
12 | BDRIDP/PAT/DUM/CCA-Rd/11 | Improvement of road from Pangasi Noldoani High School & GPS - H/O Jennta Ali Gazi Mosque road by BC at Ch.0.00m-1000.00m Including 1 No 1.50m x 1.50m RCC Box Culvert at Ch. 476.00m ID No-578965071 | 578965071 |  | 1 |  |  |  | 1.5 | 6111741.95 | 5500567.755 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2019-12-30 |  | 65% | 33.12% | 1821696 |  |  | WBM Complete
15 | BDRIDP/PAT/DUM/CCA-Rd/14 | Improvement of Road from East Side of Fokir Bari Upazila Road-Karticpasha Via H/O Akkel Ali Howlader from Ch.0m-1000m. including 02 Nos 1.00m x 1.00m RCC Box at Ch. 52.00m & 715.00m under Dumki Upazila District Patuakhali ID No. 578965070 | 578965070 |  | 1 |  |  |  | 2 | 7921013.58 | 7524962.901 | M/S. Md. Delowar Hossain | 2019-04-18 | 2019-04-25 | 2019-10-24 |  | 45% | 27.25% | 2050643 |  |  | WMB on going
3 | BDRIDP/PAT/RANG/GC/01 | Development of Baherchar Bazar i) Construction of Multipurpose Shed. ii) Construction of Fish Shed. iii) Construction of 2 NOs Open Platform. iv) Construction of Toilet Block. v) Construction of Internal Road. vi) Sinking of Deep Tubewell. vii) Construction of Drain, viii) Construction of Dustbin. ix) Earth Filling Work under Rangabali Upazila, District: Patuakhali. (Tender ID- 360588) | [6 empty] | 1 | 5221850.52 | 4960757.994 | Md. Nasiruddin Ahmed | 2020-01-12 | 2020-01-19 | 2020-06-18 |  | 45% | 10.08% | 500000
4 | BDRIDP/PAT/KAL/CCA-Rd/02 | Improvement of Road from Kathalpara Wapda - Uttar Chakamayia Latif Master House Start Uttar Chakamayia Latif Master Bari to Uttar Chakamayia GPS from Ch. 17500m - 20000.00m including 05 Nos 0.60mx0.60m U-Drain & 01 No 3.30mx3.00rn RCC Box Culvert at Ch.17550m 18130m 18829m 18988m 19333m & 17700m. 1D No. 578664019 under Kalapara Upazila District Patuakhali | 578664019 |  | 2.5 |  |  |  | 6 | 19192522.37 | 18712655.622 | M/S. Najmus Shahadat Traders | 2019-08-22 | : 01-09-2019 | 2020-02-28 |  | 60% | 29.39% | 5500000 |  |  | WBM Complete
5 | BDRIDP/PAT/KAL/UN-Rd/02 | Improvement of Road from Lalua UPC-Tiekhali UPC via Payraport, Chingoria road [ID: 578663009] a. Earthwork From Ch. 3540m-4105m, b. Carpeting (BC) Ch. 3540m-4105m, c. Palasading 05m. under Kalapara Upazila, District: Patuakhali. | 578663009 |  | 0.565 |  |  |  |  | 4032696.86 | 3831062.017 | M/S. Shahidul Enterprise | 2019-08-26 | 2019-09-03 | 2020-03-02 |  | 35% | 24.02% | 920366 |  |  | AS Complete
3 | BDRIDP/PAT/MIR/CCA-Rd/02 | Improvement of Road from UZR near Charkhali GPS at Deuly Bererdon River (Chatra GPS) by BC from Ch. 0.00m-1450.00m. (ID No. 578765080) | 578765080 |  | 1.45 |  |  |  |  | 8039212 | 6742371.579 | Kinnary Construction | 2016-07-18 | 2016-07-25 | 2017-04-21 |  | 30% | 0% |  |  |  | ASS on going 28 days letter need to cancel
5 | BDRIDP/PAT/MIR/UZ-St/01 | Construction of 21.00m long RCC Girder Bridge on Voyang GC-Ayola GC (Habib Bazar) Road at Ch. 3858m. (ID No-578762007) | 578762007 | [5 empty] | 21 | 14844326.61 | 14101982.562 | M/S. Sikder Enterprise (Moyazzem) | 2018-08-14 | 2018-08-21 | 2019-08-20 |  | 90% | 88.52% | 12482579 |  |  | Main Str Complete. Approach to be done
6 | BDRIDP/PAT/MIR/CCA-Rd/03 | Improvement of Road from R&H at East Bazita Club-H/O Bazlu Bayati-Munshirhat Road by BC at Ch. 00m-1000m including 02 Nos 1.50mx1.50m & 01 No 4.00mx3.50m RCC Box Culvert at Ch. 450m, 624m & 90m under Mirjagonj, Patuakhali. (ID No. 578764049) | 578764049 |  | 1 |  |  |  | 7.5 | 9991327.38 | 9491917.011 | M/S. Md. Delowar Hossain | 2018-08-02 | 2018-08-09 | 2019-02-08 |  | 60% | 27.99% | 2656896 |  |  | WBM on going
7 | BDRIDP/PAT/MIR/CCA-Rd/04 | Improvement of Road from Labubunia H/O Wazed Khan-Talukder Bari-H/O Nurmohammad Road by BC at Ch. 00m-1000m including 02 Nos 1.50mx1.50m & 01 No. 4.00mx3.50m RCC Box Culvert at Ch. 183m, 450m & 710m under Mirjagonj, Patuakhali. (ID No. 578765056) | 578765056 |  | 1 |  |  |  | 7.5 | 9636060.99 | 9154257.941 | M/S. Gazi Construction (Ahsan) | 2018-08-14 | 2018-08-21 | 2019-02-20 |  | 60% | 63.45% | 5807923 |  |  | WBM on going
9 | BDRIDP/PAT/MIR/CCA-Rd/06 | A) Improvement of RHD (Monasep Sikdar Bari) - UZR (West Side Bazita Arshed Dr. Bari) road via Karikor Bari at Ch. 700m-738m, 1546m-1915m, 2052m-2320m with 310m link Road. Including 01 No 1.50mx1.50m RCC Box Culvert at Ch. 120m Over link Road (ID No. 578764023) B) Improvement of Mashlskata Muchi Bari Brldge- Bazita High School via Bepari Bari at Ch. 1600m-2500.00m with 250m Extension road Includlng 01 No 3.00mx3.00m RCC Box Culvert at Ch. 2310m. (ID No. 578764058) under Mirzagonj Upazila, District: Patuakhali | 578764023 & 578764058 |  | 2.135 |  |  |  | 4.5 | 17297092.78 | 15197172.336 | M/S. Khan Enterprise | 2019-09-25 | 2019-10-02 | 2020-04-01 |  | 55% | 40.14% | 6100000 |  |  | WBM on going
10 | BDRIDP/PAT/MIR/UZ-St/02 | Construction of 50.06 RCC Girder Bridge on Kathaltoli GC (Trimukhi)- Sailabunia Sluice RHD Road via Shishurhat at Ch.4300m. (ID No. 578762003) under Mirjagonj, Patuakhali. | 578762003 | [5 empty] | 50.06 | 31636038.23 | 31184184.92 | M/S. Abul Kalam Azad | 2019-09-01 | 2019-09-08 | 2020-09-07 |  | 80% | 75.37% | 23503258 |  |  | Deck Slab Complete
11 | BDRIDP/PAT/MIR/UZ-St/03 | Construction of 20.00 RCC Girder Bridge on Kathaltoli GC Trimukhi- Sailabunia Sluice RHD Road via Shishurhat at Ch.3630m. ID No. 578762003 under Mirjagonj, Patuakhali. | 578762003 | [5 empty] | 20 | 19181757.8 | 18083479.852 | M/S. Mohiuddin Ahmed | 2019-08-21 | 2019-08-28 | 2020-08-27 |  | 75% | 70.86% | 12814035 |  |  | Slab complete
12 | BDRIDP/PAT/MIR/UZ-St/04 | Construction of 23.00m long RCC Girder Bridge on Voyang GC- Ayla GC (Habib Bazar) Road at Ch. 1819m under Mirzagonj Upazila, District: Patuakhali [Road ID-578762007] | 578762007 | [5 empty] | 23 | 18048128.55 | 15298728.925 | M/S. Shahil Enterprise- Md. Gius Uddin (JV) | 2019-09-15 | 2019-09-22 | 2020-07-21 |  | 45% | 42.29% | 6469429
2 | BDRIDP/PAT/DAS/CCA-Rd/02 | Improvement of Road from Betagi- Patabunia GC Near Sultan Sarder Bari to Shahalom Member Bari via Mazid Biswas Bari at Ch. 0.00m-560.00m including 01 No 0.625m x 0.600m U-Drain (Length=7.00m) at ch. 330.00m (ID No. 578525209) under Dashmina Upazila, District: Patuakhali | 578525209 |  | 0.56 |  |  |  | 0.625 | 4640453.07 | 4248830.417 | M/S. Dafadar Enterprise | 2019-04-18 | 2019-04-25 | 2019-10-24 |  | 45% | 32.95% | 1400000 |  |  | WBM on going
5 | BDRIDP/PAT/GAL/CCA-Rd/01 | Improvement of road by bothside Widening by Bitumenous Carpeting from Chottosiba UZR-Barosiba Launch Ghat (Ferry Ghat Road) at Ch. 1700m-3905m & 6300m-7100m including 01 No 1.50mX1.50m RCC Box Culvert at Ch. 3850m (ID No. 578574209) | 578574209 |  | 2.205 |  |  |  | 1.5 | 18035713.07 | 16966359.552 | M/S. Palli Stors | 2018-04-24 | 2018-05-01 | 2020-03-10 |  | 75% | 69.48% | 11787637 |  |  | WBM Complete
6 | BDRIDP/PAT/GAL/UN-Rd/01 | Improvement of Both Side Widening from Char Biswas- Nomo Sluice Bazar road at Ch. 00.00m - 3000.00m (ID No. 578573018) under Galachipa Upazila, District: Patuakhali | 578573018 |  | 3 |  |  |  |  | 25867446.35 | 25022256.782 | M/S. Najmus Shahadat Traders | 2019-10-09 | 2019-10-09 | 2020-04-15 |  | 45% | 0% |  |  |  | WBM on going
7 | BDRIDP/PAT/GAL/CCA-Rd/02 | A) Improvement of Road from Jomir Khar Barir Mosjid - Uttar Amkhola GPS at Ch. 00.00m - 1000.00m including 01 No 0.625m x 0.600m U- Drain (Length=7.00m) at Ch. 825.00m (ID No. 578575192) B) Improvement of Both side widening from Chottosiba UZR - Barosiba Launchghat Road from Ch. 00.00m - 1700.00m & 3950.00m - 6300.00m including 02 Nos 1.50m x 1.50m RCC Box at Ch. 614.00m & 1314.00m (ID No. 578574209) under Galachipa Upazila, District: Patuakhali) | 578575192 & 578574209 |  | 3.25 |  |  |  | 3.6 | 35685287.71 | 33338333.528 | M/S. Rupali Construction | 2019-10-14 | 2019-10-21 | 2020-04-20 |  | 30% | 10.61% | 3536209
9 | BDRIDP/PAT/GAL/UZ-St/02 | Construction of 42.06m RCC Girder Bridge on Badura GC-Julakha Bazar RHD Road at Ch. 11283m, [Road ID: 578572005] | 578572005 | [5 empty] | 42.06 | 26858867.95 | 24172981.155 | M/S. Amir Engineering Corporation-M.M. Builders & Engineers Ltd.-M/S. Niaz Traders-JV | 2018-04-24 | 2018-05-01 | 2019-04-30 |  | 95% | 91.84% | 22201313 |  |  | Main structure complete Approach on going
|  | Sub Total Tk= |  |  | 8.455 | 0 | 0 | 0 | 47.16 | 106447315.08 | 99499931.017 | [7 empty] | 37525159
|  | Grand Total Tk= |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | [7 empty] | #VALUE!
| Accountant |  |  | Sub-Assistant Engineer | [6 empty] | Sr. Assistant Engineer |  |  |  |  | Executive Engineer
| LGED, Patuakhali. |  |  | LGED, Patuakhali. | [6 empty] | LGED, Patuakhali. |  |  |  |  | LGED, Patuakhali.

## New Formet Road & Structure
Monthly Progress Report
Implementation Status
Barisal Division Rural Infrastructure Development Project
District: Patuakhali. | [15 empty] | Upto Month: December/2020
Sl No | Package No. | Scheme Name with Location (Ch. To Ch.) | Road ID No. | Effective Quantity (m3,km,m,Nos,ha) | [5 empty] | Approved Estimated Cost (Tk) | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract signing date | Actual start date | Completion date as per contract | Actual completion date | Physical Progress (%) |  | Financial Progress |  | Fund received with memo date | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | str. (m) | [9 empty] | Amount Spent(Tk) | in (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  | 19 | 20 | 21 | 22
| Upazila: Bauphal | [19 empty] | Fy-2014-15 (Road)
1 | BDRIDP/ PAT/BAF/ CCA-RD/01 | Improvement of Nawmala UP-Sabupura Bazar-Bauphal-Patuakhali RHD road (Kaderer Garage) by BC at ch.00-1000m. | 578384082 |  | 1 |  |  |  |  | 4385388 | 3872761.121 | M/S Kabir Traders. | 2014-10-19 | 2014-02-11 | 2015-01-11 | 2014-12-30 | 100% | 89.34% | 3460059 |  | Memo No-617 dt.28-09-14 Tk.5,00,000.00 | FBP
2 | BDRIDP/ PAT/BAF/ CCA-RD/02 | Improvement of Kanakdia UP-Dipasha Bazar-Afsarer Garage-Sabupura Bazar- Nager hat road by BC at ch.0.0m-1000m under Bauphal Upazila. | 578384073 |  | 1 |  |  |  |  | 5028158.4 | 4446664.284 | M/S Tanvir Ahmed. | 2014-10-16 | 2014-02-11 | 2015-01-11 | 2015-01-05 | 100% | 99.64% | 4430525 |  | Memo No-82 dt.29-01-15 Tk.30,00,000.00 | FBP
3 | BDRIDP/ PAT/BAF/ CCA-Rd/03 | Improvement of road from Daspara UP Norer road to Kalaiya-Hosnabad road by BC from ch.00-1150m. | 578384124 |  | 1.15 |  |  |  |  | 4554034 | 4379282 | M/S. K. K. Enterprise | 2015-04-22 | 29.04-15 | 2016-04-28 | 2016-04-20 | 100% | 96.75% | 4236773 |  | Memo No-78 dt.29-01-15 Tk.10,00,000.00 | FBP
4 | BDRIDP/ PAT/BAF/ CCA-Rd(R)/04 | Rehabilitation of road from Madanpura UP (Kagojir Pool) Merdar hat-Chandrapara-Chowrasta Bazar (Dhali Asia Khatun Madrasha) Madanpura Union road by BC from ch.00-1900m. | 578384027 |  |  |  |  | 1.9 |  | 9502581 | 9201118.97 | M/S. K. K. Enterprise | 2015-04-22 | 29.04-15 | 2016-04-28 | 2016-04-25 | 100% | 99.53% | 9158296 |  | Memo No-401 dt.11-05-15 Tk.90,00,000.00 | FBP
5 | BDRIDP/ PAT/BAF/ CCA-Rd/05 | Rehab. Of road from North Soula GPS cum Cyclone Shelter-South Soula GPS cum Cyclone Shelter (UZR Iman Ali Howlader Mosque to Baharampur-WAPDA very Bunth road by BC from ch.1000-2650m | 578384060 |  |  |  |  | 1.65 |  | 6604640 | 5513736.58 | M/S. Tushar Enterprise | 2015-03-22 | 2015-03-29 | 2016-03-28 | 2016-02-28 | 100% | 98.89% | 5452718 |  | Memo No-405 dt.11-05-15 Tk.40,00,000.00 | FBP
6 | BDRIDP/ PAT/BAF/ CCA-Rd(R)/06 | Rehab. Of road from North Soula GPS cum Cyclone Shelter-South Soula GPS cum Cyclone Shelter (UZR Iman Ali Howlader Mosque to Baharampur-WAPDA very Bunth road by BC from ch.2650m-3460m | 578384060 |  |  |  |  | 0.81 |  | 3223257 | 2690388.76 | M/S. Tushar Enterprise | 2015-03-22 | 2015-03-29 | 2016-03-28 | 2016-03-20 | 100% | 98.7% | 2655377 |  | Memo No-510 dt.04-06-15 Tk.35,00,000.00
7 | BDRIDP/ PAT/BAF/ UN-RD/01 | Improvement of Chanropara Chowrasta- Tentulia River road by BC at ch.0.0m-1000m & Const. of 01 No U-Drain at ch.18m under Bauphal Upazila. | 578383039 |  | 1 |  |  |  | 0.625 | 5964730.79 | 5114689.781 | M/S Khandakar Brothers. | 2014-10-20 | 2014-10-28 | 2015-03-05 | 2015-02-26 | 100% | 99.97% | 5113033 |  | Memo No-513 dt.04-06-15 Tk.30,00,000.00 | FBP
8 | BDRIDP/ PAT/BAF/ UN-Rd/02 | Improvement of road from Kalisuri UP (Kumarkhali Bridge)-Kanakdia Bazar (Kalisuri UP-Shibpur Hazar-Sattar Fakir House-Shibpur Satalight School road) by BC from ch.00-1750m | 578383001 |  | 1.75 |  |  |  |  | 9671480 | 7800041 | M/S. Y.A Khan | 2015-04-16 | 2015-04-23 | 2016-06-30 | 2016-05-31 | 100% | 99.96% | 7796926 |  | Memo No-617 dt.28-0-14 Tk.500000.00 | FBP
9 | BDRIDP/ PAT/BAF/ UN-Rd/03 | Imp. Of road from Daspara UP-Char Alogi GPS-Moishadi Bazar road by BC from ch.1500-2500m | 578383044 |  | 1 |  |  |  |  | 5557653 | 5512568 | M/S. K. K. Enterprise | 2015-03-12 | 2015-03-19 | 2016-03-18 | 2016-03-10 | 100% | 97.57% | 5378504 |  | Fy-2014-15 (Bridge Culvert) | FBP
10 | BDRIDP/ PAT/BAF/ UN-Rd/04 | Imp. Of road from Kanakdia UP Baultali Bazar- Jhilna Bazar road by BC from 3500m-5100m | 578383045 |  | 1.6 |  |  |  |  | 8742133 | 7168551.37 | M/S. Y.A Khan | 2015-03-05 | 2015-03-12 | 2016-06-30 | 2016-06-10 | 100% | 99.46% | 7130122 |  | Memo No-84 dt.29-01-15 Tk.20,00,000.00 | FBP
11 | BDRIDP/ PAT/BAF/ CCA-Rd/08 | Improvement of road from East Side of Dr. Shahalom Talukder House Jame Mosque-Nogorer Hat Yuasub Member House via Nowmala High School road by BC from Ch. 00-510m (ID No. 578384274) under Bauphal, Patuakhali. | 578384274 |  | 0.51 |  |  |  |  | 3259126 | 2553344.49 | Dr. A. Khaleq Bishwas | 2015-11-02 | 2015-11-09 | 2016-08-08 | 2016-06-20 | 100% | 97.42% | 2487456 |  | Memo No-396 dt.11-05-15 Tk.2,00,000.00 | FBP
12 | BDRIDP/ PAT/BAF/ CCA-Rd/09 | Improvement of road from Shabupura Tulatola Bor Sikder Bari-Dasher Howla UZR Connecting road by BC from Ch. 2750-4100m with 02(Two) Nos. U-Drain at Ch. 2860m & 3275m (ID No. 578385057) under Bauphal, Patuakhali. | 578385057 |  | 1.35 |  |  |  | 1.3 | 7726972 | 6876951.823 | Md. Akhtaruzzaman | 2015-08-30 | 2015-09-07 | 2016-09-07 |  | 50% | 24.72% | 1700000 |  | Memo No-520 dt.04-06-15 Tk.12,00,000.00 | Cancle
13 | BDRIDP/PAT/BAF/CCA-Rd/07 | Improvement of road from Jamalkhati road-Oytizobahi Dighir Ghat & Kobor Stan via Advocate Nazrul Islam House road by CC work from Ch. 00-100m under Bauphal, Patuakhali. | 578385109 |  |  |  | 0.1 |  |  | 313539 | 187120.98 | M/S. Munia Enterprise | 2015-08-09 | 2015-08-16 | 2016-02-28 | 2016-02-20 | 100% | 100% | 187120 | 100 | Fy-2015-16 (Warth work, Road & Bridge) | FBP
14 | BDRIDP/PAT/BAF/CCA-Rd(R)/10 | Rehabilitation of road from Bauphal UPC (Sher-E-Bangla Road)-Naomala BDC Bazar Road via Olipura Bazar East Side (Bilbilash Miah Bari Mr. M. K Raman's House) road By BC from Ch. 00-300m (ID No.578383021) | 578383021 |  |  |  |  | 0.3 |  | 1759578 | 1497622.709 | Md. Azaher Uddin | 2016-03-03 | 2016-03-10 | 2016-06-09 | 2016-06-05 | 100% | 99.85% | 1495305 |  | Warth work, Memo No-696 dt.30-07-15 Tk.25,00,000.00 | FBP
15 | BDRIDP/PAT/BAF/UN-Rd/05 | Improvement of Road from Kalisuri UPC Kumarkhali Bridge-Nurainpur Bazar via Kanakdia Bazar by BC at Ch. 1750m-2750m and including 3 Nos 1.60mX1.60m RCC Box Culvert at Ch. 1945.00m 2260.00m & 2530.00m ID No 578383001 | 578383001 | 1 | 4.8 |  |  |  |  | 6704240 | 6033816 | Md. Firoz | 2017-04-25 | 2017-04-25 | 2018-01-19 | 2018-01-10 | 100% | 99.94% | 6029924 |  | Road Memo No-701 dt.30-07-15 Tk.90,00,000.00 | FBP
16 | BDRIDP/PAT/BAF/CCA-Rd/11 | Improvement of Road from Karkhana Launch Ghat-Karkhana Manik Gazi Bari Karkhana High School West side Fourkan Munshi Shop To Karkhana Seniour Madrsha via Previous Poura Chairman Abdul Haque Mia Bari & Karkhana Launch Ghat from Ch. 0.00m-860.00m including 1.60mX1.60m RCC Box Culvert at Ch. 483m ID No 578385041 Salvage Cost Tk. 48257.00 | 578385041 |  | 0.86 |  |  |  | 1.6 | 5843445.72 | 5446734.041 | Suresh Chandra Biswas | 2017-08-17 | 2017-08-24 | 2018-05-23 |  |  | 0% |  |  | Warth work, Memo No-770 dt. 19-08-15 Tk.15,00,000.00 | Dropped
17 | BDRIDP/PAT/BAF/CCA-Rd/12 | Improvement of road from Mominpur Biswas Bari-Saber Howlader Bari- Sikder Bazar road from Ch. 600.00-1600.00m including 1No. 1.00mx1.00m RCC Box Culvert at Ch. 1510.00m & 2 Nos. U-drain at Ch. 785.00m & 915.00 ( ID No. 578385150) | 578385150 |  | 1 |  |  |  | 2.3 | 6518346.28 | 6780580.273 | Md. Khair Hossain | 2018-04-04 | 2018-04-11 | 2019-02-19 | 2019-02-15 | 100% | 99.82% | 6768565 |  | Road Memo No-771 dt.19-08-15 Tk.1,00,00,000.00 | FBP
18 | BDRIDP/PAT/BAF/CCA-Rd/13 | Improvement of road From Kalishuri-Chandkati H/School Kasobpur Bazar by BC at Ch. 1000m-1770m including 01 Nos. 1.00mx1.00m RCC Box Culvert at ch. 1175m & 1 No. U-Drain at Ch. 1308m. (ID No. 578384033) | 578384033 |  | 0.77 |  |  |  | 1.625 | 6046619.25 | 5441957.325 | M/S. Islam Brothers | 2018-03-29 | 2018-04-05 | 2018-10-04 | 2018-10-02 | 100% | 99.92% | 5437766 |  | Memo No-996 dt. 26-11-15 Warth work Tk.15,00,000.00 Road Tk. 60,00,000.00 | FBP
19 | BDRIDP/PAT/BAF/CCA-Rd/14 | Improvement of road From Kanakdia Kachipara (Bader hat) - Hisbullah Bazar (Mohosin Sepahi Bari) by BC at Ch. 00m-1500m including 03 Nos. 1.00mx1.00m RCC Box Culvert at ch. 437m, 732m & 831m and 04 Nos U-Drain at Ch. 250m, 510m, 1221m, 1450m. (ID No. 578384079) | 578384079 |  | 1.5 |  |  |  | 3.5 | 10940064.85 | 10274075.362 | M/S. Mohiuddin Ahmed | 2018-03-29 | 2018-04-05 | 2018-09-04 |  | 100% | 81.8% | 8403858 |  | Memo No-215 dt. 05-04-16 Warth work Tk.20,00,000.00 Road Tk.1,00,00,000.00 | Complete
20 | BDRIDP/PAT/BAF/CCA-Rd/15 | Improvement of road From gonsinga (RHD) - Rasidea Madrasha - Bilbilash Molla Bari Bridge by BC at Ch. 00m-1215m including 02 Nos. 1.00mx1.00m RCC Box Culvert at ch. 20m, 676m and 03 Nos U-Drain at Ch. 145m, 380m, 1155m. (ID No. 578384103) | 578384103 |  | 1.215 |  |  |  | 3.875 | 8797854.41 | 8787946.353 | M/S. Najmus Shahadat Traders | 2018-05-29 | 2018-06-05 | 2018-12-04 | 2018-12-01 | 100% | 99% | 8700407 |  | Memo No-320 dt. 15-05-16 Warth work Tk.75,00,000.00 Road Tk.4,50,00,000.00 | FBP
21 | BDRIDP/PAT/BAF/CCA-Rd/16 | Improvement of road From Uttar Modonpura Islamia Dakhil Madrasha - Daroga bari -via golam Mostafa Chairman House by BC at Ch. 2000m-3680m including 01 No. 2.00mx2.00m & 01 No. 1.00mx1.00m RCC Box Culvert at ch. 750m and 3660m. (ID No. 578384223) (Salvage Cost: Tk. 413597.00) | 578384223 |  | 1.68 |  |  |  | 3 | 11305924.1 | 10951114.8 | M/S. Tanvir Ahmed | 2018-03-21 | 2018-03-28 | 2020-12-31 |  | 50% | 17.07% | 1868881 |  | Fy-2015-16 (Bridge Culvert) | 28 days final letter
22 | BDRIDP/PAT/BAF/CCA-Rd/17 | Improvement of road From Madonpura Kanakdia UNr road (Shader bari Jame Mosque) -Kanakdia UPC - Chandrapara Bazar UNR Road connecting via Engr. Atikur Rahman House by BC at Ch. 500m-2110m including 02 Nos. 1.00mx1.00m RCC Box Culvert at Ch. 745m, 1325m & 01 No U-Drain at Ch. 1160m. (ID No. 578384290) | 578384290 |  | 1.61 |  |  |  | 2.625 | 10589027.67 | 10491461.329 | M/S. K. K. Enterprise | 2018-03-21 | 2018-03-28 | 2018-09-27 | 2018-09-26 | 100% | 79.64% | 8355103 |  | Memo No-700 dt.30-07-15 Tk.10,00,000.00
23 | BDRIDP/PAT/BAF/CCA-Rd/11 | Improvement of Road from Karkhana Lanch Ghat -Karkhana Manik Gazi Bari (Karkhana High School West side of Fouekan Munsi Shop to Karkhana Senior Madrasha via previous Poura Chairmain Abdul Haque Mia Bari & Karkhana Lunch Ghat From Ch.0.00m-550.00m By HBB including 02 Nos 1.00mX1.00m Box Culvert at Ch. 220.00m & 435.00m. | 578385041 |  |  | 0.55 |  |  | 2 | 5012682.08 | 4762047.976 | Brothers Treding | 2018-10-24 | 2018-11-01 | 2019-03-31 |  | 100% | 63% | 3000000 |  | Memo No-772 dt.19-08-15 Tk.10,00,000.00 | Complete
24 | BDRIDP/PAT/BAF/CCA-Rd/18 (222892) | Improvement of road From Boga Sabupura BC road to Sabupura GPS Via Sabupura Mother & Child Hospital by BC at Ch. 950m-1678m including 01 No. 1.00mx1.00m RCC Box Culvert at Ch. 1165m. (ID No. 578384352) | 578384352 |  | 0.728 |  |  |  | 1 | 5418905.9 | 5656496.635 | Md. Azaher Uddin | 2018-12-23 | 2019-01-29 | 2019-12-30 | 2020-05-30 | 100% | 55.41% | 3134000 |  | Memo No-996 dt.26-11-15 Tk.30,00,000.00 | Complete
25 | BDRIDP/PAT/BAF/CCA-Rd/19 (222893) | Improvement of road From Boga UP Chairman Ahmmed Hpuse Mosque to Sabupura GPS - North side of Serjen Ali Mridha House by BC at Ch. 810m-1200m including 01 No. 2.00mx2.00m RCC Box Culvert at Ch. 1140m. (ID No. 578385103) | 578385103 |  | 0.39 |  |  |  | 2 | 4080491.12 | 4258212.555 | Md. Azaher Uddin | 2019-01-31 | 2019-02-07 | 2020-03-28 | 2020-03-28 | 100% | 98.4% | 4190101 |  | Fy-2016-17 (Bridge Culvert) | FBP
26 | BDRIDP/PAT/BAF/UN-Rd/06 | Improvement of Road from Daspara UPC Moishadi Bazar via Char Alogi GPS Road by BC at Ch. 850m-1500m & 2500m-2850m including 01 No 3.00mX3.00m RCC Box Culvert at Ch. 2050m (ID No. 578383044) (Salvage: BDT: 1432898.00) | 578383044 |  | 1 |  |  |  | 3 | 7394045.61 | 7830472.257 | Md. Nazrul Islam Chunnu | 2018-10-24 | 2018-11-01 | 2019-04-29 |  | 65% | 27.46% | 2150000 |  | Memo No-818 dt.13-11-16 Tk.20,00,000.00 | Time Ex. Send to H/Q up to 30-12-20
27 | BDRIDP/PAT/BAF/CCA-Rd/20 | Improvement o Road from Alogi River-Sultanabad Bazar-Dandi GPS Road By BC at ch. 00.00m-1860.00m including 01 No 1.00mx1.00m, 01 No 3.00mx3.00m RCC Box Culvert at Ch. 1036.00m, 1860.00m & 2Nos U- Drain at Ch 1248.00m, 1570.00m. (ID No. 578384123) | 578384123 |  | 1.86 |  |  |  | 5.25 | 13986181.2 | 13286872.14 | M/S. Gazi Construction (Ahsan) | 2018-10-24 | 2018-11-01 | 2019-04-30 | 2019-04-30 | 100% | 99.91% | 13274276 |  | Memo No-414 dt.17-05-17 Tk.30,00,000.00 | FBP
28 | BDRIDP/PAT/BAF/CCA-Rd/21 | Improvement of Madhya Modonpura Bridge RHD-Ramnagar Bazar & GPS Ramnagar Board GPS west Site St. Bridge via Kalu Howlader House/Hazi Bari Jame Mosque Satla Kha Bari at Ch. 00m-1000m including 01 Nos 1.00mX1.00m RCC Box at Ch. 775m & 01 No 0.625mX0.900m U-Drain Length7.00m at Ch. 150m. ID No. 578384046 | 578384046 |  | 1 |  |  |  | 1.625 | 7490969.64 | 7116421.158 | M/S AL MADINA MOTORS | 2019-04-25 | 2019-05-02 | 2021-01-31 |  | 50% | 23.89% | 1700000 |  | Fy-2016-17 (Road) | WBM on going
29 | BDRIDP/PAT/BAF/UN-Rd/ 07 | Improvement of road from Boga UP- Nowmala UP via Shabupura hat Road from Ch.00m-1950m including 02 Nos. 1.00m x 1.00m Box Culvert at Ch. 428m & 1140m. ID No. 578383002 under Bauphal Upazila District Patuakhali [OSTETM] | 578383002 |  | 1.95 |  |  |  | 2 | 15063619.78 | 13728356.438 | Md. Enayet Hossain | 2019-04-25 | 2019-05-02 | 2020-05-30 |  | 100% | 62.71% | 8608405 |  | Memo No-575 dt. 07-08-16 Warth work Tk.23,00,000.00 Road Tk.15,00,000.00
30 | BDRIDP/ PAT/BAF/ UN-St/01 | Const. of 02 Nos (1.60mX1.60) RCC Box Culvert on the road from Chanropara Chowrasta Tentulia River road at ch.1360m & 2030m. | 578383039 | [5 empty] | 3.2 | 606892.53 | 471153.721 | M/S Khandakar Brothers. | 13/10/14 | 2014-02-11 | 2015-03-05 | 2015-02-28 | 100% | 99.93% | 470835 |  | Memo No-818 dt. 13-11-16 Warth work Tk.30,00,000.00 Road Tk.3,00,00,000.00 | FBP
31 | BDRIDP/ PAT/BAF/ UN-St/02 | Const. of 1 No. 1.60mX1.60m Box culvert and 1No U-Drain Kalisuri UP (Kumarkhali Bridge)-Kanakdia Bazar-Nurainpur Bazar (Kalisuri UP-Shibpur Hazar-Sattar Fakir House-Shibpur Satalight school road) at ch.1100m & 1650m. | 578383001 | [5 empty] | 1.6 | 395873 | 372202.808 | M/S. K. K. Enterprise | 2015-04-22 | 2015-04-29 | 2015-10-28 | 2015-10-20 | 100% | 99.42% | 370043 |  | Memo No-414 dt. 17-05-17 Road Tk.1,00,00,000.00 | FBP
32 | BDRIDP/ PAT/BAF/ UN-St/03 | Const. of road from 3 Nos 1.60mx1.60m Box culvert on Kanakdia UP Baultali Bazar-Jhilna Bazar road at ch.313m, 815m & 1153m. | 578383045 | [5 empty] | 4.8 | 962383 | 749807 | Suresh Chandra Bishwas | 2015-02-25 | 2015-03-04 | 2015-09-03 | 2015-08-30 | 100% | 99.81% | 748361 |  | Fy-2017-18 (Road) | FBP
33 | BDRIDP/ PAT/BAF/ CCA-St/01 | Const.of road from 1No 1.60mX1.60m Box Culvert and 1 No U-Drain on Daspara UP Norer road to Kalaiya-Hosnabad road at ch.750m & 1095m | 578384124 | [5 empty] | 1.6 | 395873 | 373351 | M/S. K. K. Enterprise | 2015-05-27 | 2015-06-03 | 2015-12-02 | 2015-12-02 | 100% | 99.94% | 373144 |  | Memo No-678 dt. 20-08-17 Road Tk.1,15,00,000.00 | FBP
34 | BDRIDP/ PAT/BAF/ CCA-St/02 | Const. of road from 3 Nos 1.60mX1.60m Box culvert and 1No U-Drain on Madanpura UP (Kagojir Pool) Merdar hat-Chandrapara-Chowrasta bazar (Dhali Asia Khatun Madrasha) Union road at ch.235m, 1205m, 1620m & 944m. | 578384027 | [5 empty] | 1.8 | 950258 | 765023.771 | M/S. Auditi Enterprise | 2015-04-07 | 2015-04-14 | 2015-10-13 | 2015-10-10 | 100% | 92.25% | 705722 |  | Memo No-1014 dt. 31-12-17 Road Tk.20,00,000.00 | FBP
35 | BDRIDP/ PAT/BAF/ CCA-St/03 | Const. of 1No 1.60mx1.60m Box culvert & 1No U-Drain on North Soula GPS cum cyclone shelter-South Soula GPS cum Cyclone shelter (UZR Iman Ali Howlader Mosque to Baharampur-WAPDA very Bunth) road at ch.2202m & 2112m | 578384060 | [5 empty] | 1.6 | 395873 | 301028 | M/S. Munia Enterprise | 2015-03-22 | 2015-03-29 | 2015-09-28 | 2015-09-20 | 100% | 99.89% | 300682 |  | Memo No-119 dt. 30-01-18 Road Tk.3,00,00,000.00 | FBP
36 | BDRIDP/PAT/BAF/UZ-St/01 | Construction of 20.00m RCC Girder Bridge on Boga Bauphal RHD (Shaplakhali) to Kalisuri GC via Kanakdia Hat Road at Ch. 12+290km (Road ID No. 578382004) | 578382004 | [5 empty] | 20 | 15035062.58 | 12849606.16 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-01-24 |  | 92% | 87.92% | 11297598 |  | Memo No-372 dt. 24-04-18 Road Tk.3,00,00,000.00 | Main Bridge Completed. Approach on going & Time Ex. Send to H/Q up to 30-11-20
37 | BDRIDP/PAT/BAF/UZ-St/02 | Construction of 20.00m RCC Girder Bridge on Mominpur GC - Baherchar GC via Kalisuri GC Road at Ch. 13+680km (Road ID No. 578382005) | 578382005 | [5 empty] | 20 | 16489178.72 | 14840260.848 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-12-31 |  | 90% | 79.91% | 11859262 |  | Memo No-476 dt. 06-06-18 Road Tk.3,50,00,000.00 | Main Bridge Completed. Approach on going
38 | BDRIDP/PAT/BAF/UZ-St/03 | Construction of 15.00m RCC Girder Bridge on Boga Bauphal RHD (Shaplakhali) to Kalisuri GC via Kanakdia Hat Road at Ch. 14+990km (Road ID No. 578382004) | 578382004 | [5 empty] | 15 | 12477741.85 | 11229967.655 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-01-24 |  | 90% | 84.62% | 9503330 |  | Memo No-490 dt. 11-06-18 Road Tk.68,50,000.00 | Main Bridge Completed. Approach on going & Time Ex. Send to H/Q up to 30-11-20
39 | BDRIDP/PAT/BAF/UZ-St/04 | Construction of 15.00m RCC Girder Bridge on Boga Bauphal RHD (Shaplakhali) to Kalisuri GC via Kanakdia Hat Road at Ch. 15+980km (Road ID No. 578382004) | 578382004 | [5 empty] | 15 | 12406863.41 | 11166177.069 | M.M. Builders & Engineers Ltd. | 2018-01-18 | 2018-01-25 | 2019-12-30 |  | 80% | 74.42% | 8309801 |  | Fy-2018-19 (Road) | Main Bridge Completed. Approach on going
40 | BDRIDP/PAT/BAF/UN-St/05 | Construction of 15.00 m long RCC Girder Bridge on Kalisuri UP ( Kumarkhali Bridge) - Nurainpur Bazar via Kanakdia Bazar at ch 1+500 km. ID no-578383001 under Bauphal, Patuakhali. | 578383001 | [5 empty] | 15 | 11592689.73 | 11013055.244 | Md. Mahabubur Rahaman | 2020-03-19 | 2020-03-26 | 2021-04-30 |  | 60% | 27.07% | 2981000 |  | Memo No-699 dt. 10-10-18 Road Tk.1,50,00,000.00
41 | BDRIDP/PAT/BAF/UN-St/04 | Construction of 15.00 m long RCC Girder Bridge on Kalisuri UP ( Kumarkhali Bridge) - nurainpur Bazar via kanakdia Bazar at ch 1+600 km. ID no-578383001 | 578383001 | [5 empty] | 15 | 11644343.44 | 11062126.268 | M/S JUI ENTERPRISE | 2020-03-19 | 2020-03-26 | 2021-04-30 |  | 55% | 45.78% | 5063799 |  | Memo No-855 dt. 11-12-18 Road Tk.2,00,00,000.00
42 | BDRIDP/PAT/BAF/UZ-St/05 | Construction of 15.00 m long RCC Girder Bridge on Boga- Bauphal RHD ( Shaplakhali)- Kalisuri GC via Kanakdia Hat at Ch 13+180 km. (ID no-578382004) | 578382004 | [5 empty] | 15 | 16032937.12 | 13160872.049 | Md. Enayet Hossain | 2020-05-17 | 2020-05-24 | 2020-11-19 |  | 30% | 0% |  |  | Memo No-78 dt. 15-01-19 Road Tk.40,00,000.00 | Time Ex. Send to H/Q up to 30-06-21
|  | Sub Total Tk= |  |  | 30.723 | 0.55 | 0.1 | 4.66 | 166.925 | 300871657.18 | 276016038.103 | [7 empty] | 194287077 | 0 | 0
Upazila: Sadar
1 | BDRIDP/ PAT/SAD/ CCA-Rd/01 | Imp. Of road from Moukaran UNR road start Purbo Talikhali Mazibar dokan-North side Kafulabunia khal-Daritaluk P/S & H/S road via Abdul Latif Howlader bari road by HBB from ch.00-1500m. | 578954134 |  |  | 1.5 |  |  |  | 3499645 | 3079703.747 | Md. Shafiqur Rahman | 2015-03-01 | 2015-03-08 | 2016-03-07 | 2016-02-28 | 100% | 100% | 3079552 |  | Memo No-228 dt. 07-03-19 Road Tk.1,00,00,000.00 | FBP
2 | BDRIDP/ PAT/SDR/ CCA-RD/02 | Improvement of road from Pangashia UP-Gazipur R&H (Bus Stand)-Jamla road upto Sreerampur Sluice Gate road by BC from ch.4228-5724m | 578954053 |  | 1.496 |  |  |  |  | 7641141 | 7183010.328 | M/S. Selim Stores | 2015-03-04 | 2015-03-11 | 2016-04-24 | 2016-04-20 | 100% | 100% | 7182989 |  | Memo No-241 dt. 15-03-19 Road Tk.20,00,000.00 | FBP
3 | BDRIDP/ PAT/SAD/ CCA-Rd/03 | Imp. Of road from Low Kathi Officer hat to Kaler hat via Kismat Moukarn Primary School road by BC from ch.1400-3116m | 578954082 |  | 1.716 |  |  |  |  | 7996232 | 7184088.1 | Md. Jasim Uddin Khan | 2015-03-03 | 2015-03-10 | 2016-03-09 | 2016-03-05 | 100% | 100% | 7184066 |  | Memo No-316 dt. 16-04-19 Road Tk.1,50,00,000.00 | FBP
4 | BDRIDP/ PAT/SAD/ CCA-Rd/04 | Imp. Of road from Moukaran UZR road via Jabber Sikder bari via Fakir Bari-Rashid Kazi Bari via Muktijodda Yousuf Kazi bari-Moukarn Bazar Gazipur road by HBB from ch.00-1215m | 578954140 |  |  | 1.215 |  |  |  | 3464371 | 2980967.667 | M/S. Hima Bricks | 2015-03-01 | 2015-03-08 | 2016-03-07 | 2016-03-05 | 100% | 99.99% | 2980693 |  | Memo No-602 dt. 23-06-19 Road Tk.2.19,00,000.00 | FBP
5 | BDRIDP/PAT/SAD/CCA-Rd/07 | Improvement of road from Showla Baily Bridge-Full Sharif Bazar via Mazi Bari-pachim Vaila Madrasha-Vaila RNGPS road By HBB from Ch.3000-4200m with 1 No U-Drain (625mmx625mm) at Ch.4200m (ID No. 578954111) | 578954111 |  |  | 1.2 |  |  | 0.625 | 4009113 | 3996722.853 | M/S. Hima Bricks | 2015-05-24 | 2015-06-03 | 2016-05-30 | 2016-05-30 | 100% | 99.99% | 3996515 |  | Fy-2018-19 (Bridge) | FBP
6 | BDRIDP/PAT/SAD/CCA-Rd/05 | Improvement of road from Jainkati UP-Bhuria Bazar UNR to Pathan Bari Mosque via Abdul Malek Mredha Bari by HBB form ch. 00-550m (ID No. 578955341) | 578955341 |  |  | 0.55 |  |  |  | 1106046 | 1011784.331 | M/S. Hima Bricks | 2015-05-13 | 2015-05-20 | 2015-11-19 | 2015-11-15 | 100% | 92.57% | 936587 |  | Memo No-699 dt. 10-10-18 Bridge Tk.3.51,60,000.00 | FBP
7 | BDRIDP/PAT/SAD/CCA-Rd/06 | Improvement of road from Islampur Madrasha to BWDB Embankment via Rafiqul Islam Moulana Bari by HBB form ch. 00-600m (ID No. 578955342) | 578955342 |  |  | 0.6 |  |  |  | 1474728 | 1269113.775 | M/S. Hima Bricks | 2015-05-13 | 2015-05-20 | 2015-11-19 | 2015-11-18 | 100% | 100% | 1269108 |  | Memo No-855 dt. 11-12-18 Bridge Tk.33,00,000.00 | FBP
8 | BDRIDP/ PAT/SAD/ UN-Rd/01 | Imp. Of road from Badarpur UP-Lowkati UP via Skandar Rari Bari road by HBB from ch.4955-5990m with 1No U-Drain at ch.5779m | 578953019 |  |  | 1.035 |  |  |  | 3199605 | 2761692 | M/S. Hima Bricks | 2015-03-01 | 2015-03-08 | 2016-03-07 | 2016-03-05 | 100% | 97.31% | 2687430 |  | Memo No-228 dt. 07-03-19 Bridge Tk.50,00,000.00 | FBP
9 | BDRIDP/ PAT/SAD/ UZR-Rd/01 | Imp. Of road Patuakhali-Brisal R&H to Dumki Upazila via Moukaran GC (Sadar part) road by BC from ch.3255-5035m | 578952007 |  | 1.78 |  |  |  |  | 12666819 | 11077439.432 | M/S. Nazmul Shahdat Traders | 2015-03-11 | 2015-03-18 | 2016-03-17 | 2016-03-10 | 100% | 100% | 11077043 |  | Memo No-316 dt. 16-04-19 Bridge Tk.1,00,00,000.00 | FBP
10 | BDRIDP/ PAT/SDR/ UN-Rd/02 | Improvement of road from Auliapur UP-Badura GC via Dhakkin Badura GPS (Dhakkin Badura GPS cum Cyclone Center) road (ID No. 578953035) by BC from Ch. 3500m-4500m under Patuakhali Sadar, Patuakhali. | 578953035 |  | 1 |  |  |  |  | 11422601 | 9301690.981 | M/S. Lutfa Construction | 2015-09-09 | 2015-09-16 | 2016-09-16 | 2016-09-15 | 100% | 100% | 9301658 |  | Memo No-602 dt. 23-06-19 Bridge Tk.75,00,000.00 | FBP
11 | BDRIDP/ PAT/SAD/ UZ-Rd/02 | Improvement of road from Khaser hat GC to Bottolbunia GC via Hazikhali Bazar road by Earth work (Ch. 3805-4805m) | 578952006 | 1 | [5 empty] | 6652678 | 5880338.913 | M/S. Mohiuddin Ahmed | 2015-05-27 | 2015-06-03 | 2016-06-02 | 2016-05-30 | 100% | 99.12% | 5828631 |  | Fy-2018-19 (Village road) | FBP
12 | BDRIDP/PAT/SAD/UZ-Rd/03 | Improvement of road from Patuakhali Barisal R&H (Moukaran Bridge)-Dumki UZHQ via Moukaran GC Road (Sadar Part) from Ch. 5035m-6965m (Road ID No. 578952007) | 578952007 |  | 1.93 |  |  |  |  | 13169432 | 10492112 | M/S. Shakil Enterprise | 2017-02-08 | 2017-02-15 | 2017-11-14 | 2017-11-10 | 100% | 56.23% | 5900000 |  | Memo No-699 dt. 10-10-18 Village road Tk.75,00,000.00
13 | BDRIDP/PAT/SDR/UZ-Rd/04 | Improvement of Road from Patuakhali-Betagi R&H Pairakunja Bazar Kakrabunia GC via Officer hat Sadar Part from Ch. 3200m-5200m including 3 Nos 1.50mx1.50m RCC Box Culvert at Ch. 3615m 3700m & 4840m ID No. 578952011 | 578952011 |  | 2 |  |  |  | 4.5 | 15582689 | 15435761.202 | M/S. Nazmus Shahdat Traders | 2017-08-30 | 2017-09-07 | 2018-06-08 | 2018-06-05 | 100% | 99.97% | 15431240 |  | Fy-2018-19 (Bhaban, Groth shelter, Ghat) | FBP
14 | BDRIDP/PAT/SDR/CCA-Rd/08 | Improvement of road From Khejurtala Bazar-Dhankhali Bazar via Dakurbunia GPS at Ch. 0.00-1000.00m including 2Nos. 1.50mX1.50m RCC Box Culvert at Ch. 220.00m & 415.00m (ID No. 578954096) | 578954096 |  | 1 |  |  |  | 3 | 6865304 | 6178773 | Md. Gius Uddin | 2018-01-18 | 2018-01-25 | 2018-10-21 | 2018-10-20 | 100% | 99.99% | 6178004 |  | Memo No-699 dt. 10-10-18 Tk.50,00,000.00 | FBP
15 | BDRIDP/PAT/SDR/CCA-Rd/09 | Improvement of road From Sreerapur Bazar-Munshir hat via Parkartikpasha GPS at ch. 765.00m-2300.00m including 1No. 1.50mX1.50m RCC Box Culvert at Ch. 1250.00m (ID No. 578954052) | 578954052 |  | 1.535 |  |  |  | 1.5 | 9680810.34 | 9100919 | Md. Firoz | 2018-02-15 | 2018-02-22 | 2018-11-21 | 2018-11-15 | 100% | 99.58% | 9062495 |  | Fy-2019-20 (Road) | FBP
16 | BDRIDP/PAT/SDR/CCA-Rd/10 | Improvement of road From (UZR) Fadea Bazar-(UNR) Gadur Bazar ch. 0.00-1300.00m including 1No. 1.50mX1.50m RCC Box Culvert at Ch. 1000.00m (ID No. 578954156) | 578954156 |  | 1.3 |  |  |  | 1.5 | 8518694.58 | 7746839.693 | M/S. Soma Enterprise | 2018-01-18 | 2018-01-25 | 2019-01-24 | 2019-01-24 | 100% | 99.98% | 7745217 |  | Memo No-640 dt. 03-07-19 road Tk.2,00,00,000.00 | FBP
17 | BDRIDP/PAT/SAD/UZ-Rd/05 | Improvement of BC road From Khasher Hat GC - Bottlebunia GC via Hazikhali Hat at Ch. 2450m-3805m including 01 No. 1.00mx1.00m RCC Box Culvert at ch. 3053m. (ID No. 578952006) | 578952006 |  | 1.355 |  |  |  | 1 | 10933122.12 | 10376509.476 | Abdul Kader Khan | 2018-04-24 | 2018-05-01 | 2019-12-31 |  | 100% | 97.33% | 10099062 |  | Memo No-667 dt. 05-05-19 road Tk.1,00,00,000.00 | FB Not Submitted
18 | BDRIDP/PAT/SAD/CCA-Rd/11 | Improvement of BC road From UZR (Hazikhali Mohammadia Madrasha) to UNR (Atahar Pada bari) - Iron Bridge road at Ch. 00m-1830m including 02 Nos. 1.50mx1.50m RCC Box Culvert at ch. 510m & 1380m. (ID No. 578954168) | 578954168 |  | 1.83 |  |  |  | 3 | 11616041.31 | 11605828.513 | Md. Bashir Uddin | 2018-03-29 | 2018-04-05 | 2018-10-04 | 2018-10-04 | 100% | 99.98% | 11602942 |  | Memo No-754 dt. 15-09-19 road Tk.12,50,000.00 | FBP
19 | BDRIDP/PAT/SAD/UZ-Rd/06 | Improvement of Patuakhali UZHQ-Muradia GC via Sreerampur Bazar (Sadar Part) at Ch. 6785m-8785m. Including 04 Nos 1.50mX1.50m, 01 No. 3.00mX3.00m (2-vent) RCC Box Culvert at Ch. 6945m, 7565m 7835m, 8495m & 7357m | 578952009 |  | 2 |  |  |  | 12 | 15934940.87 | 15445371.515 | Md. Manebur Rahman | 2018-03-20 | 2018-03-27 | 2018-09-26 |  | 100% | 70.73% | 10923758 |  | Memo No-809 dt. 06-10-19 road Tk.1,50,00,000.00 | FB Not Submitted
20 | BDRIDP/PAT/SDR/CCA-Rd/ 12 (269595) | Improvement of Road from Patukhali GPS to Hazi Asmotail Junior High School at Ch. 1730m- 3430m. including 01 No 3.00m x 3.00m & 01 No 1.50m x 1.50m. RCC Box at Ch. 1013.00m & 1490.00m ID No. 578955001 under Sadar Upszila District Patuakhali [OSTETM] | 578955001 |  | 1.7 |  |  |  | 4.5 | 14206023.05 | 15509943 | M/S. Najmus Shahadat Traders | 2019-04-25 | 2019-05-02 | 2020-02-28 |  | 100% | 93.5% | 14501289 |  | Memo No-882 dt. 12-11-19 road Tk.1,50,00,000.00 | Complete
21 | BDRIDP/PAT/SDR/CCA-Rd/ 13 | Improvement of Road from Chottobeghi UP-8ashtala Bazar at Ch. 1000m-2500m.lncluding 02 Nos 1.50m x 1.50m. RCC Box at Ch. 1110.00m s 1350.00m ID No. 578954097 under Sadar Upazila District Patuakhali [OSTETM] | 578954097 |  | 1.5 |  |  |  | 3 | 11702504.42 | 10688183.983 | Md. Enayet Hossain | 2019-04-25 | 2019-05-02 | 2020-05-30 |  | 80% | 70.9% | 7577563 |  | Memo No-977 dt. 19-12-19 road Tk.1,50,00,000.00 | WBM Complete
22 | BDRIDP/PAT/SDR/UN-Rd/03 (277980) | Improvement of Road from Pangashia UPC Iron Bridge Sreerampur Bazar via Moukaran GPS & H/S from Ch 5730m-6730m. Including 01 No 1.50m x 1.50m. RCC Box at Ch. 586000m under Sadar Upazila District Patuakhali ID No.578953057 | 578953057 |  | 1 |  |  |  | 1.5 | 6858656.99 | 6515724.141 | Md Delower Hossain | 2019-04-18 | 2019-04-25 | 2019-11-15 | 2019-11-29 | 100% | 99.93% | 6511202 |  | Memo No-985 dt. 22-12-19 road Tk.35,00,000.00 | FBP
23 | BDRIDP/PAT/SDR/CCA-Rd/14 (277981) | Improvement of Road from Itbaria UP Dakurbunia Culvert to WAPDA via Sultan Mredha Bari from Ch. 00m-700m. Including 01 No 1.50m x 1.50m RCC Box at Ch. 250.00m under Sadar Upazila District Patuakhali ID No. 578955453 | 578955453 |  | 0.7 |  |  |  | 1.5 | 5679365.07 | 5395396.817 | M/S. Shaharia Enterprise | 2019-04-18 | 2019-04-25 | 2020-02-28 | 2020-02-24 | 100% | 99.79% | 5383962 |  | Fy-2019-20 (Bhaban, Groth shelter, Ghat) | FBP
24 | BDRIDP/PAT/SDR/CCA-Rd/15 (277979) | Improvement of Road from R&H Pairakunza Bazar to RHD Bus Stand Badher Hat from Ch. 00m-2000m including 03 Nos 1.50m x 1.50m RCC Box at Ch. 450.00m840.00m & 990.00m under Sadar Upazila District Patuakhali ID No. 578954060 | 578954060 |  | 2 |  |  |  | 4.5 | 15559650.14 | 14200725.199 | Md. Enayet Hossain | 2019-05-09 | 2019-05-16 | 2019-10-13 |  | 65% | 56.67% | 8047228 |  | Memo No-640 dt. 03-07-19 Tk.20,00,000.00 | Time Ex. Send to H/Q up to 28-02-21
25 | BDRIDP/PAT/SDR/CCA-Rd/16 (285036) | Improvement of Road from Dholkhali Sluice- Katakhali Bazar via Dhopa Bari Bridge at Ch. 0.00m - 500.00m including 01 No 1.5mx1.5m at Ch.450.00m (ID No. 578954171) under Sadar Upazila, District: Patuakhali | 578954171 |  | 0.5 |  |  |  | 1.5 | 4344350.62 | 4127133.089 | M/S AL MADINA MOTORS | 2019-04-18 | 2019-04-25 | 2019-10-24 | 2019-10-20 | 100% | 99.68% | 4114037 |  | Memo No-809 dt. 06-10-19 Tk.20,00,000.00 | FBP
26 | BDRIDP/ PAT/SAD/ UZR-ST/01 | Const.of 1No 4.00mx4.00m RCC Box Culvert on Patuakhali-Barisal R&H to Dumki Upazila via Moukaran GC (Sadar part) road at ch.4715m. | 578952007 | [5 empty] | 4 | 2231307 | 1751536.082 | M/S. Gazi Enterprise | 2015-03-08 | 2015-03-15 | 2015-09-14 | 2015-06-20 | 100% | 99.93% | 1750257 |  | Fy-2019-20 (Bridge) | FBP
27 | BDRIDP/ PAT/SAD/ CCA-ST/01 | Const. of 3.00mx3.00m RCC Box culvert on Moukarn UNR road start Purbo Talikhali Mazibar dokan-North side Kafulabunia khal-daritaluk P/S & H/S road via Abdul Latif Howlader bari road at ch.1140m | 578894134 | [5 empty] | 3 | 1061680 | 777640.23 | M/S. Masud & Brothers | 2015-03-11 | 2015-03-18 | 2015-09-17 | 2015-06-10 | 100% | 100% | 777635 |  | Memo No-640 dt. 03-07-19 Tk.2,50,00,000.00 | FBP
28 | BDRIDP/ PAT/SDR/ CCA-St/02 | Const. of 1 No. 3.00mX1.00m Box culvert on Pangasha UP-Gazipur R&H (Bus Stand)-Jamla road upto Sreerampur Sluice Gate road at ch.4380m. | 578954053 | [5 empty] | 3 | 979058 | 729368.5 | M/S. Gazi Enterprise | 2015-03-08 | 2015-03-15 | 2015-09-14 | 2015-06-10 | 100% | 100% | 729363 |  | Memo No-809 dt. 06-10-19 Tk.1,50,00,000.00 | FBP
29 | BDRIDP/ PAT/SAD/ CCA-St/03 | Const. of 1 No 3.00mx3.00m Box Culvert & 03 Nos U-Drain on Low Kathi Officer hat to Kaler hat via Kismat Moukaran Primary School road at ch.2630m, 1792m,2309m & 2976m. | 578954082 | [5 empty] | 4.8 | 1268691 | 983193.51 | M/S. Gazi Enterprise | 2015-03-08 | 2015-03-15 | 2015-09-14 | 2015-06-30 | 100% | 99.27% | 975990 |  | Memo No-106 dt. 08-03-2020 Tk.1,00,00,000.00 | FBP
30 | BDRIDP/ PAT/SDR/ UN-St/01 | Construction of 02 Nos. 3.00mx3.00m RCC Box Culvert on Auliapur UP-Badura GC via Dhakkin Badura GPS (Dhakkin Badura GPS cum Cyclone Center) road at Ch. 3600m & 4150m (ID No. 578953035) under Patuakhali Sadar, Patuakhali. | 578953035 | [5 empty] | 6 | 2799670 | 1928137.795 | Siful Enterprise | 2015-08-20 | 2015-08-27 | 2016-06-30 |  | 0% | 0% |  |  |  | Cancle
31 | BDRIDP/PAT/SAD/UZ-St/02 | Construction of 2Nos 1.00mX1.00m RCC Box Culvert on Khaser Hat GC via Hazikhali Bazar road at Ch. 4285m & 4450m (ID No. 578952006) | 578952006 | [5 empty] | 1 |  | 437060.015 | M/S. Talukder Enterprise | 2015-05-27 | 2015-06-03 | 2015-12-02 | 2015-12-02 | 100% | 99.74% | 435928 |  |  | FBP
32 | BDRIDP/ PAT/SDR/ UN-St/01 | Construction of 02 Nos. 3.00mx3.00m RCC Box Culvert on Auliapur UP-Badura GC via Dhakkin Badura GPS (Dhakkin Badura GPS cum Cyclone Center) road at Ch. 3600m & 4150m (ID No. 578953035) under Patuakhali Sadar, Patuakhali. | 578953035 | [5 empty] | 6 | 2839359 | 1942450.81 | M/S. Soma Enterprise | 2016-08-17 | 2016-09-25 | 2017-03-24 | 2017-03-20 | 100% | 99.51% | 1932895
33 | BDRIDP/PAT/SAD/UZ/St-03 | Construction of 2 Nos. 3.00mx3.00m, 2 Nos. 2.00mx2.00m & 2 Nos. 1.50mx1.50m RCC Box Culvert on Patuakhali Barisal R&H (Moukaran Bridge)-Dumki UZHQ via Moukaran GC Road (Sadar Part) at Ch. 5865m, 6135m, 6592m, 6435m, 5185m & 5499m. (Road ID No. 578952007) | 578952007 | [5 empty] | 13 | 5298141 | 3596319.056 | Md. Gius Uddin | 2017-02-08 | 2017-02-15 | 2018-02-14 | 2018-02-10 | 100% | 99.51% | 3578776 |  |  | FBP
34 | BDRIDP/PAT/SAD/CCA-St/04 | Construction of 2-Vent 3.00mx3.00m RCC Box Culvert on Auliapur UP-Badura GC via Dakkhin Badura GPS at Ch. 6500m (Auliapur UP-H/O Bonda Ali Miah South Badura Bazar) | 578953035 | [5 empty] | 6 | 1937544.41 | 1743789.969 | Md. Mahafuz Khan | 2018-06-18 | 2018-06-25 | 2018-12-24 |  | 0% | 0% |  |  |  | Neet to Cancel
35 | BDRIDP/PAT/SAD/UZ-St/04 | Construction of 42.06m RCC Girder Bridge on Patuakhali Barisal RHD (Moukaron Bridge)-Dumki UZHQ via Moukaran GC (Sadar Part) at Ch. 3282m (Road ID: 578952007) | 578952007 | [5 empty] | 42.06 | 26857732.46 | 24171959.214 | M/S. Amir Engineering Corporation-M.M. Builders & Engineers Ltd.-M/S. Niaz Traders-JV | 2018-04-24 | 2018-05-01 | 2019-04-30 |  | 98% | 97.66% | 23607480 |  |  | Main Str. Completed. Approach work on going
36 | BDRIDP/PAT/SDR/UZ-St/05 | Construction of 24.00m Long RCC Girder Bridge at Khasher hat GC to Bottolbunia GC via Hajhir hat.road at Ch. 3487.00m. (ID No-578952006) under Sadar Upazila, District: Patuakhali | 578952006 | [5 empty] | 24 | 27732668.12 | 25657219.712 | M/S. Hamim International Lubna Khanom | 2019-07-18 | 2019-07-25 | 2020-07-24 |  | 80% | 76.35% | 19589462 |  |  | Deck Slab Complete & Time Ex. Send to H/Q
|  | Sub Total Tk= |  |  | 26.342 | 6.1 | 0 | 0 | 156.485 | 286790414.5 | 262264447.648 | [7 empty] | 231980057 |  | 0 | 0
Upazila: Dumki
1 | BDRIDP/ PAT/DUM/ CCA-Rd/01 | Improvement of road from Angaria (RHD Baherchar Ferry Ghat Janab Rubul Amin Howlader Honarable MP)-Old Patabunia Bazar road by BC from ch.00-600m. | 578964158 |  | 0.6 |  |  |  |  | 2876468 | 2854634.994 | M/S. K. K. Enterprise | 2015-05-13 | 2015-05-20 | 2016-05-19 | 2016-05-18 | 100% | 87.32% | 2492706 |  |  | FBP
2 | BDRIDP/ PAT/DUM/ CCA-Rd(R)/02 | Rehabilitation of road from Angaria (RHD Baherchar Ferry ghat Janab Ruhul Amin Howlader Honorable MP)-Clinic road by BC from ch.00-258m. | 578965085 |  |  |  |  | 0.258 |  | 1274241 | 1242834 | M/S. K. K. Enterprise | 2015-04-20 | 2015-04-27 | 2015-10-26 | 2015-10-20 | 100% | 60.71% | 754508 |  |  | FBP Salvage 486814
3 | BDRIDP/PAT/DUM/CCA-Rd/03 | Improvement of Utter Muradia Cyclone Shelter connecting road under Dumki Upazila. (Ch. 0.00-400.00m) (Salvage amount Tk. 264289.00 (Fixed)) | 578964157 |  | 0.4 |  |  |  |  | 2379982 | 1838692.316 | M/S. Melanium Traders | 2016-04-20 | 2016-04-27 | 2016-10-27 | 2016-10-22 | 100% | 99.95% | 1837729 |  |  | FBP
4 | BDRIDP/PAT/DUM/CCA-Rd/04 | Improvement of Dumki Satani GPS cum Cyclone Shelter connecting road.. (Ch. 0.00-450.00m) (Salvage amount Tk. 196726.00 (Fixed)) | 578965081 |  | 0.45 |  |  |  |  | 2557907 | 1983093.317 | M/S. Melanium Traders | 2016-04-20 | 2016-04-27 | 2016-10-27 | 2016-10-25 | 100% | 99.99% | 1982954 |  |  | FBP
5 | BDRIDP/PAT/DUM/CCA-Rd/05 | Improvement of Muradia Santos Member Bari-Uttar Wapda Verry Bandh via Razzak Pada House Road by BC at Ch. 00m-850m & Link Road Ch. 00m-150m Including 2 nos 1.00mX1.00m RCC Box Culvert at Ch. 343.00m & 750.00m ID No. 578964123 Salvage Cost BDT219430.00 | 578964123 |  | 1 |  |  |  | 2 | 6374482.07 | 5737033.863 | Lutfa Construction | 2017-11-08 | 2017-11-15 | 2018-08-15 |  | 100% | 58.72% | 3368685
6 | BDRIDP/PAT/DUM/UZ-Rd/01 | Improvement of road from Muradia UP-Laukathi UP via South Khali GPS & Bhoktobari A Salam Doctor Abari via Mozumder Hat road by BC at Ch.0.00m-2000.00m Old ID No- 578962003 New ID No. 578964015 | 578964015 |  | 2 |  |  |  |  | 11180031.09 | 10062027.981 | M/S. Amir Engineering Corporation | 2017-11-05 | 2017-11-12 | 2020-12-30 |  | 65% | 62.18% | 6256787 |  |  | WBM Complete
7 | BDRIDP/PAT/DUM/CCA-Rd/06 | Improvement of road from Labukhali-Boga RHD Chorgorobdi Free Ghat-Amir Hossain Howlader Bazar launch Ghat via A. Kashem High School by BC at Ch.0.00.m-2000.00m Including 3 Nos 1.50m x 1.50m RCC Box Culvert at Ch. 1458.00m 1798.00m & 1918.00m Old ID No-578963007 New ID No. 578964162 Salvage Cost 531968.00 | 578964162 |  | 2 |  |  |  | 4.5 | 13979628.43 | 12581665.587 | Md. Enayet Hossain | 2017-11-08 | 2017-11-15 | 2018-11-14 | 2018-11-12 | 100% | 99.97% | 12578512 |  |  | FBP
8 | BDRIDP/PAT/DUM/CCA-Rd/07 | Improvement of road from Jamla Bazar-Kalbari Bazar Gabtali Bazar-Sreerampur Dakatia Khalgora via Talukder Hat road by BC at Ch.0.00m-1000.00m ID No-578964135 | 578964135 |  | 1 |  |  |  |  | 5836020.28 | 5252418.252 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2019-12-20 |  | 100% | 99.44% | 5222763
9 | BDRIDP/PAT/DUM/CCA-Rd/08 | Improvement of road from Board Office Bridge-Gabtoli Bazar via H/O Salam Mridha West side of Bridge- Gabtoli Hat via Salampur Fazil Madrasha by BC at CH.0.00m-1000.00m ID No-578964041 | 578964041 |  | 1 |  |  |  |  | 5994897.26 | 5395407.535 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2018-08-14 | 2018-08-10 | 100% | 99.89% | 5389501 |  |  | FBP
10 | BDRIDP/PAT/DUM/CCA-Rd/09 | Improvement of road from Labukhali Bauphal RHD Taltali Chowrasta-Char Boyra High School road by BC at Ch.0.00m-500.00m Including 1 No 1.00 x 1.00m RCC Box Culvert at Ch. 135.00m ID No-578964047Salvage Cost 349064.00 | 578964047 |  | 0.5 |  |  |  | 1 | 3480965.41 | 3132868.869 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2018-05-14 |  | 100% | 79.73% | 2497891
11 | BDRIDP/PAT/DUM/CCA-Rd/10 | Improvement of road from Atharogachia Mojibor Sikder Bari-Karthikpasha UZR road by BC at Ch.0.00m-1000.00m Including 1 No 4.00m x 4.00m 2 Nos 1.00m x 1.00m RCC Box Culvert at Ch. 536.00m 155.00m & 900.00m ID No-578964155 | 578964155 |  | 1 |  |  |  | 5 | 8400644.92 | 7560580.428 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2019-12-20 |  | 30% | 0% |  |  |  | ISG Completed. 28 days final letter & Time Ex. Send to H/Q up to 30-12-20
12 | BDRIDP/PAT/DUM/CCA-Rd/11 | Improvement of road from Pangasi Noldoani High School & GPS - H/O Jennta Ali Gazi Mosque road by BC at Ch.0.00m-1000.00m Including 1 No 1.50m x 1.50m RCC Box Culvert at Ch. 476.00m ID No-578965071 | 578965071 |  | 1 |  |  |  | 1.5 | 6111741.95 | 5500567.755 | M/S. Niaz Traders | 2017-11-08 | 2017-11-15 | 2019-12-30 |  | 65% | 33.12% | 1821696 |  |  | WBM Complete
13 | BDRIDP/PAT/DUM/CCA-Rd/12 | Improvement of Road from United Mohila College-Wazed Ali Howlader Jum-E-Mosque (Uttar Sreerampur H/S, GPS-Rajakhali Bazar at Ch. 00m-414m by BC & Ch. 414m-1000m by HBB including 3 Nos 1.00mx1.00m RCC Box Culvert at Ch. 4.00m, 330.00m & 842.00m (ID No. 578964145) under Dumki, Patuakhali. | 578964145 |  | 0.414 | 0.586 |  |  | 3 | 6348374.02 | 6030955.319 | M/S. Md. Delowar Hossain | 2018-08-02 | 2018-08-09 | 2020-04-30 |  | 100% | 77.04% | 4646049 |  |  | Complete
14 | BDRIDP/ PAT/DUM/CCA-Rd/13 | Improvement of Road from Labukhali Bauphal RHD-Rajakhali Bazar Rajakhali Forkania Madrasha via Eman Ali Howlader Abul Kashen Master at Ch.0m-1000m under Dumki Upazila District Patuakhali ID No. 578964062 Salvage cost Tk. 2168832.00 | 578964062 |  | 1 |  |  |  |  | 7221930.98 | 6860834.431 | A.K.M Moniruzzaman | 2019-04-18 | 2019-04-25 | 2020-02-28 | 2020-02-26 | 100% | 45.57% | 3126320 |  |  | Work Complete
15 | BDRIDP/PAT/DUM/CCA-Rd/14 | Improvement of Road from East Side of Fokir Bari Upazila Road-Karticpasha Via H/O Akkel Ali Howlader from Ch.0m-1000m. including 02 Nos 1.00m x 1.00m RCC Box at Ch. 52.00m & 715.00m under Dumki Upazila District Patuakhali ID No. 578965070 | 578965070 |  | 1 |  |  |  | 2 | 7921013.58 | 7524962.901 | M/S. Md. Delowar Hossain | 2019-04-18 | 2019-04-25 | 2020-12-30 |  | 45% | 27.25% | 2050643 |  |  | WMB on going
|  | Sub Total Tk= |  |  | 13.364 | 0.586 | 0 | 0.258 | 19 | 91938327.99 | 83558577.548 | [7 empty] | 54026744
Upazila: Rangabali
1 | BDRIDP/ PAT/RANG/ UN-Rd(R)/01 | Rehabilitation of road from Chottobaisdia UP-Rangabali UP (Upto Samudafath) road from Ch. 00-1595m (ID No. 578583016) under Rangabali, Patuakhali. | 578583016 |  |  |  |  | 1.595 |  | 10075034 | 9308911.137 | M/S. Palli Strores | 2015-09-09 | 2015-09-16 | 2016-09-16 | 2016-08-10 | 100% | 100% | 9308874 |  |  | FBP
2 | BDRIDP/PAT/RAG/GHT/01 | Construction of RCC Ghat at Khalgor Bazar (Kachibunia Bazar) | [6 empty] | 1 | 3053023 | 3052163.625 | M/S. Deip Enterprise | 2018-07-05 | 2018-07-12 | 2019-01-11 | 2019-01-10 | 100% | 99.54% | 3038229 |  |  | FBP
3 | BDRIDP/PAT/RANG/GC/01 | Development of Baherchar Bazar i) Construction of Multipurpose Shed. ii) Construction of Fish Shed. iii) Construction of 2 NOs Open Platform. iv) Construction of Toilet Block. v) Construction of Internal Road. vi) Sinking of Deep Tubewell. vii) Construction of Drain, viii) Construction of Dustbin. ix) Earth Filling Work under Rangabali Upazila, District: Patuakhali. (Tender ID- 360588) | [6 empty] | 1 | 5221850.52 | 4960757.994 | Md. Nasiruddin Ahmed | 2020-01-12 | 2020-01-19 | 2020-09-30 |  | 60% | 10.08% | 500000
|  | Sub Total Tk= |  |  | 0 | 0 | 0 | 1.595 | 2 | 18349907.52 | 17321832.756 | [7 empty] | 12847103
Upazila: Kalapara
1 | BDRIDP/PAT/KAL/UN-Rd/01 | Improvement of road from Kalapara-Teakhali Bazar-Madhaya Teakhali Ghat bazar road by BC form ch. 5050-7300m with 3 Nos U-Drain at Ch. 6430m, 6573m & 6950m under Kalapara, Patuakhali. | 578663001 |  | 2.25 |  |  |  | 1.95 | 12903418 | 11288141.273 | Md. Bashir Uddin | 2015-08-09 | 2015-08-16 | 2016-08-16 | 2016-07-30 | 100% | 99.98% | 11285463 |  |  | FBP
2 | BDRIDP/PAT/KAL/CCA-Rd/01 | Improvement of road by 25mm dense Carpeting on Omedpur GPS cum Cyclone Shelter road from ch. 0.00m-1500.00m with 01 No. U-Drain (0.600mx0.600m) at ch. 720.00m | 578665088 |  | 1.5 |  |  |  | 0.6 | 8957232 | 7892374.074 | M/S. Yousuf Ali | 2016-04-28 | 2016-05-05 | 2017-01-28 | 2017-01-20 | 100% | 100% | 7892374 |  |  | FBP
3 | BDRIDP/PAT/KAL/GC/01 | Improvement of Alipur Bazar at Latachapli Union, Kalapara, Patuakhali. | [6 empty] | 1 | 5093059.35 | 4583753.415 | S. Ananta Bikash Tripura | 2018-05-29 | 2018-06-05 | 2018-12-04 |  | 100% | 74.19% | 3400880 |  |  | Complete
4 | BDRIDP/PAT/KAL/CCA-Rd/02 | Improvement of Road from Kathalpara Wapda - Uttar Chakamayia Latif Master House Start Uttar Chakamayia Latif Master Bari to Uttar Chakamayia GPS from Ch. 17500m - 20000.00m including 05 Nos 0.60mx0.60m U-Drain & 01 No 3.30mx3.00rn RCC Box Culvert at Ch.17550m 18130m 18829m 18988m 19333m & 17700m. 1D No. 578664019 under Kalapara Upazila District Patuakhali | 578664019 |  | 2.5 |  |  |  | 6 | 19192522.37 | 18712655.622 | M/S. Najmus Shahadat Traders | 2019-08-22 | : 01-09-2019 | 2021-04-30 |  | 60% | 56.11% | 10500000 |  |  | WBM Complete
5 | BDRIDP/PAT/KAL/UN-Rd/02 | Improvement of Road from Lalua UPC-Tiekhali UPC via Payraport, Chingoria road [ID: 578663009] a. Earthwork From Ch. 3540m-4105m, b. Carpeting (BC) Ch. 3540m-4105m, c. Palasading 05m. under Kalapara Upazila, District: Patuakhali. | 578663009 |  | 0.565 |  |  |  |  | 4032696.86 | 3831062.017 | M/S. Shahidul Enterprise | 2019-08-26 | 2019-09-03 | 2020-12-30 |  | 35% | 24.02% | 920366 |  |  | AS Complete
|  | Sub Total Tk= |  |  | 6.815 | 0 | 0 | 0 | 9.55 | 50178928.58 | 46307986.401 | [7 empty] | 33999083
Upazila: Mirjagonj
1 | BDRIDP/PAT/MIR/UZ-Rd/02 | Improvement of road from Voyang GC - Ayla GC (Habib Bazar) by BC from Ch. 1850.00m-2850.00m. (ID No. 578762007) | 578762007 |  | 1 |  |  |  |  | 6941645 | 6069844.573 | Sayed Md. Sohel | 2016-07-18 | 2016-07-25 | 2017-04-21 | 2017-04-20 | 100% | 27.74% | 1683500
2 | BDRIDP/PAT/MIR/UZ-Rd(R)/01 | Rehabilitation of road from Voyang GC-Ayla GC (Habib Bazar) by BC from Ch. 0.00m-1850.00m including 3 nos. 2.00mx2.00m RCC Box Culvert at Ch. 509m, 1248m & 1641m. (Salvage Cost: Tk. 3056224.00) (ID No. 578762007) | 578762007 |  |  |  |  | 1.85 | 6 | 15418640 | 12508713.977 | Kinnary Construction | 2016-07-18 | 2016-07-25 | 2017-04-21 | 2017-04-10 | 100% | 97.15% | 12152399 |  |  | FBP
3 | BDRIDP/PAT/MIR/CCA-Rd/02 | Improvement of Road from UZR near Charkhali GPS at Deuly Bererdon River (Chatra GPS) by BC from Ch. 0.00m-1450.00m. (ID No. 578765080) | 578765080 |  | 1.45 |  |  |  |  | 8039212 | 6742371.579 | Kinnary Construction | 2016-07-18 | 2016-07-25 | 2017-04-21 |  | 30% | 0% |  |  |  | ASS on going 28 days letter need to cancel
4 | BDRIDP/PAT/MIR/CCA-St/01 | Construction of 9.15m OFC bridge on UZR near Chairkhali GPS at Deuly UP - Barrardone River (Chatra GPS) road at Ch:0.00m (Road ID No. 578765080) | 578765080 | [5 empty] | 9.15 | 2549594 | 1950799.469 | M/S. Soma Enterprise | 2016-07-18 | 2017-07-25 | 2017-01-23 | 2017-01-20 | 100% | 92.03% | 1795356
5 | BDRIDP/PAT/MIR/UZ-St/01 | Construction of 21.00m long RCC Girder Bridge on Voyang GC-Ayola GC (Habib Bazar) Road at Ch. 3858m. (ID No-578762007) | 578762007 | [5 empty] | 21 | 14844326.61 | 14101982.562 | M/S. Sikder Enterprise (Moyazzem) | 2018-08-14 | 2018-08-21 | 2019-08-20 |  | 90% | 88.52% | 12482579 |  |  | Main Str Complete. Approach to be done Revised Approved.
6 | BDRIDP/PAT/MIR/CCA-Rd/03 | Improvement of Road from R&H at East Bazita Club-H/O Bazlu Bayati-Munshirhat Road by BC at Ch. 00m-1000m including 02 Nos 1.50mx1.50m & 01 No 4.00mx3.50m RCC Box Culvert at Ch. 450m, 624m & 90m under Mirjagonj, Patuakhali. (ID No. 578764049) | 578764049 |  | 1 |  |  |  | 7.5 | 9991327.38 | 9491917.011 | M/S. Md. Delowar Hossain | 2018-08-02 | 2018-08-09 | 2020-05-30 |  | 60% | 27.99% | 2656896 |  |  | WBM on going
7 | BDRIDP/PAT/MIR/CCA-Rd/04 | Improvement of Road from Labubunia H/O Wazed Khan-Talukder Bari-H/O Nurmohammad Road by BC at Ch. 00m-1000m including 02 Nos 1.50mx1.50m & 01 No. 4.00mx3.50m RCC Box Culvert at Ch. 183m, 450m & 710m under Mirjagonj, Patuakhali. (ID No. 578765056) | 578765056 |  | 1 |  |  |  | 7.5 | 9636060.99 | 9154257.941 | M/S. Gazi Construction (Ahsan) | 2018-08-14 | 2018-08-21 | 2019-02-20 |  | 60% | 63.45% | 5807923 |  |  | WBM on going & Time Ex. Send to H/Q up to 28-02-21
8 | BDRIDP/PAT/MIR/CCA-Rd/05 | Improvement of Road from RHD at Humraibunia UZR Saylabunia road via south Jatibunia GPS-H/Q Kader Sikder Road by BC at Ch. 660m-1920m including 03 Nos 1.50mx1.50m & 01 No 2.00mx2.00m RCC Box Culvert at Ch. 77m, 171m 480m & 708m (ID No. 578765012) under Mirjagonj, Patuakhali. | 578765012 |  | 1.26 |  |  |  | 6.5 | 10337392.88 | 11463923.68 | M/S. Jannatul Ferdous Traders | 2018-08-14 | 2018-08-21 | 2019-02-08 |  | 100% | 100% | 11463893 |  |  | FBP
9 | BDRIDP/PAT/MIR/CCA-Rd/06 | A) Improvement of RHD (Monasep Sikdar Bari) - UZR (West Side Bazita Arshed Dr. Bari) road via Karikor Bari at Ch. 700m-738m, 1546m-1915m, 2052m-2320m with 310m link Road. Including 01 No 1.50mx1.50m RCC Box Culvert at Ch. 120m Over link Road (ID No. 578764023) B) Improvement of Mashlskata Muchi Bari Brldge- Bazita High School via Bepari Bari at Ch. 1600m-2500.00m with 250m Extension road Includlng 01 No 3.00mx3.00m RCC Box Culvert at Ch. 2310m. (ID No. 578764058) under Mirzagonj Upazila, District: Patuakhali | 578764023 & 578764058 |  | 2.135 |  |  |  | 4.5 | 17297092.78 | 15197172.336 | M/S. Khan Enterprise | 2019-09-25 | 2019-10-02 | 2020-04-01 |  | 55% | 40.14% | 6100000 |  |  | WBM on going
10 | BDRIDP/PAT/MIR/UZ-St/02 | Construction of 50.06 RCC Girder Bridge on Kathaltoli GC (Trimukhi)- Sailabunia Sluice RHD Road via Shishurhat at Ch.4300m. (ID No. 578762003) under Mirjagonj, Patuakhali. | 578762003 | [5 empty] | 50.06 | 31636038.23 | 31184184.92 | M/S. Abul Kalam Azad | 2019-09-01 | 2019-09-08 | 2020-09-07 |  | 80% | 75.37% | 23503258 |  |  | Deck Slab Complete
11 | BDRIDP/PAT/MIR/UZ-St/03 | Construction of 20.00 RCC Girder Bridge on Kathaltoli GC Trimukhi- Sailabunia Sluice RHD Road via Shishurhat at Ch.3630m. ID No. 578762003 under Mirjagonj, Patuakhali. | 578762003 | [5 empty] | 20 | 19181757.8 | 18083479.852 | M/S. Mohiuddin Ahmed | 2019-08-21 | 2019-08-28 | 2020-08-27 |  | 75% | 70.86% | 12814035 |  |  | Slab complete
12 | BDRIDP/PAT/MIR/UZ-St/04 | Construction of 23.00m long RCC Girder Bridge on Voyang GC- Ayla GC (Habib Bazar) Road at Ch. 1819m under Mirzagonj Upazila, District: Patuakhali [Road ID-578762007] | 578762007 | [5 empty] | 23 | 18048128.55 | 15298728.925 | M/S. Shahil Enterprise- Md. Gius Uddin (JV) | 2019-09-15 | 2019-09-22 | 2020-07-21 |  | 60% | 55.09% | 8428004
|  | Sub Total Tk= |  |  | 7.845 | 0 | 0 | 1.85 | 155.21 | 163921216.22 | 151247376.825 | [7 empty] | 98887843
Upazila: Dashmina
1 | BDRIDP/PAT/DAS/CCA-Rd/01 | Improvement of road from Rabibaria Hat RHD to Alipur GC-Ulania GC UZR road near Rangopaldi High School by BC from Ch: 0.00m-1315.00m under Dashmina Upazila. (ID No. 578525156) | 578525156 |  | 1.315 |  |  |  |  | 6471115 | 6206840 | Md. Asadur Rahman | 2016-08-24 | 2016-09-01 | 2017-05-31 |  | 100% | 100% | 6206840 |  |  | FBP
2 | BDRIDP/PAT/DAS/CCA-Rd/02 | Improvement of Road from Betagi- Patabunia GC Near Sultan Sarder Bari to Shahalom Member Bari via Mazid Biswas Bari at Ch. 0.00m-560.00m including 01 No 0.625m x 0.600m U-Drain (Length=7.00m) at ch. 330.00m (ID No. 578525209) under Dashmina Upazila, District: Patuakhali | 578525209 |  | 0.56 |  |  |  | 0.625 | 4640453.07 | 4248830.417 | M/S. Dafadar Enterprise | 2019-04-18 | 2019-04-25 | 2019-10-24 |  | 45% | 32.95% | 1400000 |  |  | WBM on going & Time Send to H/Q up to 30-12-20
3 | BDRIDP/PAT/DAS/Ghat/01 | Construction of Arojbagi Ghat by RCC frame structure. | [6 empty] | 1 | 2694017.35 | 2424615.615 | M/S. Kohinoor Enterprise | 2018-03-29 | 2018-04-04 | 2018-10-03 |  | 100% | 0% |  |  |  | FB Submitted
|  | Sub Total Tk= |  |  | 1.875 | 0 | 0 | 0 | 1.625 | 13805585.42 | 12880286.032 | [7 empty] | 7606840
Upazila: Galachipa
1 | BDRIDP/PAT/GAL/UZ-Rd/01 | Improvement of road from Kalagachia GC-Patabunia GC (Kharizzama-Bazar UZR-Patabunia GC) Road by BC at Ch. 0.00-2000 m (Old ID no: 578572003),(New ID no: 578574201) | 578574201 |  | 2 |  |  |  |  | 11410363 | 9182532.517 | Shafiqur Rahman | 2016-10-24 | 2016-11-01 | 2017-10-31 | 2017-10-30 | 100% | 100% | 9182350 |  |  | FBP
2 | BDRIDP/PAT/GAL/UZ-Rd/02 | Improvement of road from Badura GC- Gazipur Gc ( Badhura GC-Julakha Bazar RHD) road by BC at Ch. 200-3200m (ID no. 578572005) (Salvage: BDT: 26,85,106.00) | 578572005 |  | 3 |  |  |  |  | 21346322 | 16999920.991 | Md. Firoz | 2016-11-15 | 2016-11-22 | 2017-11-21 |  | 100% | 99.26% | 16874002 |  |  | FBP
3 | BDRIDP/PAT/GAL/UZ-Rd/03 | Improvement of Kalagachia GC-Patabunia GC Kharizzama Bazar UZR-Patabunia GC road by BC from ch.2000.00m-4000.00m. ID No. Old 578572003 New 578574201 Salvage Cost Tk. 434417.00 | 578574201 |  | 2 |  |  |  |  | 13044140.34 | 11739726.306 | Shafiqur Rahman | 2017-08-30 | 2017-09-07 | 2018-06-06 | 2018-05-30 | 100% | 100% | 11739689 |  |  | FBP
4 | BDRIDP/PAT/GAL/UZ-Rd/04 | Improvement of Badura GC-Gazipur GC Badura GC - Julakha Bazar RHD road by BC from ch. 5200.00m-7750.00m including 3 Nos 2.00mx2.00m RCC Box Culvert at ch. 6260m 6470m & 7070m. ID No. 578572005 | 578572005 |  | 2.55 |  |  |  | 6 | 20566985.61 | 18704863.8 | Md. Firoz & Abdul Satter Howlader (JV) | 2017-08-21 | 2018-05-27 | 2018-05-27 |  | 100% | 70% | 17925729 |  |  | Complete
5 | BDRIDP/PAT/GAL/CCA-Rd/01 | Improvement of road by bothside Widening by Bitumenous Carpeting from Chottosiba UZR-Barosiba Launch Ghat (Ferry Ghat Road) at Ch. 1700m-3905m & 6300m-7100m including 01 No 1.50mX1.50m RCC Box Culvert at Ch. 3850m (ID No. 578574209) | 578574209 |  | 2.205 |  |  |  | 1.5 | 18035713.07 | 16966359.552 | M/S. Palli Stors | 2018-04-24 | 2018-05-01 | 2020-03-10 |  | 75% | 69.48% | 11787637 |  |  | WBM Complete
6 | BDRIDP/PAT/GAL/UN-Rd/01 | Improvement of Both Side Widening from Char Biswas- Nomo Sluice Bazar road at Ch. 00.00m - 3000.00m (ID No. 578573018) under Galachipa Upazila, District: Patuakhali | 578573018 |  | 3 |  |  |  |  | 25867446.35 | 25022256.782 | M/S. Najmus Shahadat Traders | 2019-10-09 | 2019-10-09 | 2020-04-15 |  | 45% | 0% |  |  |  | WBM on going
7 | BDRIDP/PAT/GAL/CCA-Rd/02 | A) Improvement of Road from Jomir Khar Barir Mosjid - Uttar Amkhola GPS at Ch. 00.00m - 1000.00m including 01 No 0.625m x 0.600m U- Drain (Length=7.00m) at Ch. 825.00m (ID No. 578575192) B) Improvement of Both side widening from Chottosiba UZR - Barosiba Launchghat Road from Ch. 00.00m - 1700.00m & 3950.00m - 6300.00m including 02 Nos 1.50m x 1.50m RCC Box at Ch. 614.00m & 1314.00m (ID No. 578574209) under Galachipa Upazila, District: Patuakhali) | 578575192 & 578574209 |  | 3.25 |  |  |  | 3.6 | 35685287.71 | 33338333.528 | M/S. Rupali Construction | 2019-10-14 | 2019-10-21 | 2020-04-20 |  | 30% | 10.61% | 3536209 |  |  | Time Ex. Send to H/Q up to 30-12-20
8 | BDRIDP/PAT/GAL/UZ-St/01 | Construction of 4.00mX4.00m 2-Vent RCC Box Culvert on Badura GC-Gazipur GC (Badura GC-Julakha Bazar RHD) Road At Ch. 3240.00m (ID No: 578572005) | 578572005 | [5 empty] | 8 | 2915061 | 2099172.373 | M/S. Talukder Enterprise | 2016-11-17 | 2016-11-24 | 2017-05-22 |  | 0% | 0% |  |  |  | Termination for convenience
9 | BDRIDP/PAT/GAL/UZ-St/02 | Construction of 42.06m RCC Girder Bridge on Badura GC-Julakha Bazar RHD Road at Ch. 11283m, [Road ID: 578572005] | 578572005 | [5 empty] | 42.06 | 26858867.95 | 24172981.155 | M/S. Amir Engineering Corporation-M.M. Builders & Engineers Ltd.-M/S. Niaz Traders-JV | 2018-04-24 | 2018-05-01 | 2019-04-30 |  | 95% | 91.84% | 22201313 |  |  | Main structure complete Approach on going
|  | Sub Total Tk= |  |  | 18.005 | 0 | 0 | 0 | 61.16 | 175730187.03 | 158226147.004 | [7 empty] | 93246929
|  | Grand Total Tk= |  |  | 104.969 | 7.236 | 0.1 | 8.363 | 571.955 | 1101586224.44 | 1007822692.317 | [7 empty] | 726881676
| Accountant |  |  | Sub-Assistant Engineer | [6 empty] | Sr. Assistant Engineer |  |  |  |  | Executive Engineer
| LGED, Patuakhali. |  |  | LGED, Patuakhali. | [6 empty] | LGED, Patuakhali. |  |  |  |  | LGED, Patuakhali.