## Perojpur
Monthly Progress Report
Implementation Status
Barisal Division Rural Infrastructure Development Project
District: Pirojpur | [20 empty] | Reporting Month: November-2020
Sl.No. | Package No. | Scheme Name with Location (Ch. to Ch.) | Road ID No. | Effective Quantity (m3, km, m, Nos, ha) | [5 empty] | Approved Estimate Cost (Tk.) | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract signing date | Actual start date | Completion date as per contract | Actual completion date | Physical Progress (%) | Financial Progress |  | Demand upto June | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | Str. (m) | [8 empty] | Amount Spent(Tk.) | In (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Upazila : Pirojpur Sadar District: Perojpur
1 | BDRIDP/PRJ/ SDR/U-Ew/01 | Improvement of road from R&H road to Pantadubi Mazibar Dakuyar Bari via Bala Bari Mohsiner Bari, Syfuler Bari & Clab & Madrasha, School road by Earth work from ch. 00-375m | 579803018 | 0.375 | [5 empty] | 377041 | 377041 | Md. Saiful Islam | 25.01.15 | 01.02.15 | 01.08.15 |  | 100% | 374348 |  |  | Final
2 | BDRIDP/PRJ/ SDR/U-Ew/01 | Improvement of road from R&H road to Pantadubi Mazibar Dakuyar Bari via Bala Bari Mohsiner Bari, Syfuler Bari & Clab & Madrasha, School road by Earth work from ch. 375-690m | 579803018 | 0.315 | [5 empty] | 389514 | 389514 | Md. Gias uddin | 25.01.15 | 01.02.15 | 01.08.15 |  | 100% | 388668 |  |  | Final
3 | BDRIDP/PRJ/ SDR/U-Ew/01 | Improvement of road from R&H road to Pantadubi Mazibar Dakuyar Bari via Bala Bari Mohsiner Bari, Syfuler Bari & Clab & Madrasha, School road by Earth work from ch. 690-1050m | 579803018 | 0.36 | [5 empty] | 373950 | 373950 | Md. Moshin | 25.01.15 | 01.02.15 | 01.08.15 |  | 100% | 363012 |  |  | Final
4 | BDRIDP/PRJ/ SDR/U-Ew/01 | Improvement of road from R&H road to Pantadubi Mazibar Dakuyar Bari via Bala Bari Mohsiner Bari, Syfuler Bari & Clab & Madrasha, School road by Earth work from ch.1050-1300m | 579803018 | 0.25 | [5 empty] | 367550 | 367550 | Md. Mizan | 25.01.15 | 01.02.15 | 01.08.15 |  | 100% | 360866 |  |  | Final
5 | BDRIDP/PRJ/ SDR/U-Ew/01 | Improvement of road from R&H road to Pantadubi Mazibar Dakuyar Bari via Bala Bari Mohsiner Bari, Syfuler Bari & Clab & Madrasha, School road by Earth work from ch.1300-1550m | 579803018 | 0.25 | [5 empty] | 429362 | 429362 | Md. Gias uddin | 25.01.15 | 01.02.15 | 01.08.15 |  | 100% | 415050 |  |  | Final
6 | BDRIDP/PRJ/ SAD/UE-Ew/02 | Improvement of road from Sikder Mallik UP-Panchpara GC road By Earth work from Ch. 00-1029m | 579803004 | 1.029 | [5 empty] | 456518 | 456518 | Md. Golam Rabbani Pintu | 21.07.15 | 28.07.15 |  |  | 100% | 440400 |  |  | Final
7 | BDRIDP/PRJ/ SAD/UE-Ew/03 | Improvement of road from Sikder Mallik UP-Durgapur UP via Panchpara GC road By Earth work from Ch. 00-1000m | 579803003 | 1 | [5 empty] | 396635 | 396635 | Md. Sabuj Howlader | 21.07.15 | 28.07.15 |  |  | 100% | 386267 |  |  | Final
8 | BDRIDP/PRJ/ SAD/UE-Ew/01 | Improvement of road from Daudpur house of Idris Sardar to Rajarkati via Udaykati Jam-e-Mosque road by Earth work from Ch. 00-1500m u | 579805099 | 1.5 | [5 empty] | 383751 | 383751 | Md. Asad Khan | 19.08.15 | 25.08.15 | 30.06.16 |  | 100% | 382411 |  |  | Final
9 | BDRIDP/PRJ/ SAD/UZ-Ew/01 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 2090-2765m | 579802001 | 0.675 | [5 empty] | 399846 | 399846 | Md. Waeach Ali |  |  |  |  | 100% | 399846
10 | BDRIDP/PRJ/ SAD/UZ-Ew/01 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 2765-3115m | 579802001 | 0.35 | [5 empty] | 303237 | 303237 | Md. Alamgir |  |  |  |  | 100% | 303237
11 | BDRIDP/PRJ/ SAD/UZ-Ew/01 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 3515-4415m | 579802001 | 0.9 | [5 empty] | 347530 | 347530 | Md. Nurul Islam |  |  |  |  | 100% | 347530
12 | BDRIDP/PRJ/ SAD/UZ-Ew/01 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 4415-5165m | 579802001 | 0.75 | [5 empty] | 262020 | 262020 | Md. Delwar Hossain |  |  |  |  | 100% | 262020
13 | BDRIDP/PRJ/ SAD/UZ-Ew/02 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 5165-6065m | 579802001 | 0.9 | [5 empty] | 317472 | 317472 | Md. Omar Faruk Sheikh |  |  |  |  | 100% | 315000
14 | BDRIDP/PRJ/ SAD/UZ-Ew/02 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 6065-7515m | 579802001 | 1.45 | [5 empty] | 370367 | 370367 | Mrs. Piara Begum |  |  |  |  | 100% | 370000
15 | BDRIDP/PRJ/ SAD/UZ-Ew/02 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 7515-8265m | 579802001 | 0.75 | [5 empty] | 346689 | 346689 | Md. Jahidul Islam |  |  |  |  | 100% | 346689
16 | BDRIDP/PRJ/ SAD/UZ-Ew/02 | Improvement of road from Parerhat GC-Hularhat GC road by Earth work from Ch. 8265-8900m | 579802001 | 0.653 | [5 empty] | 402063 | 402063 | Md. Faizul Islam |  |  |  |  | 100% | 400000
|  | Earth work Sub-Total = |  | 11.507 | 0 | 0 | 0 | 0 | 0 | 5923545 | 5923545 | [6 empty] | 5855344
17 | BDRIDP/PRJ/ SAD/UN-Rd/02 | Improvement of road from Sikder Mallik UP-Panchpara GC road By BC from Ch. 00-1029m under sadar upazila [ID No: 579803004] | 579803004 |  | 1.02 |  |  |  |  | 5821916 | 15820000 | M/S. Ruma Bricks Prop. Md. Rustum Mollah Banaripara, Barisal. |  | 22.03.15 | 22.09.15 |  | 100% | 15820000 |  |  | Final
18 | BDRIDP/PRJ/ SAD/UN-Rd/03 | Improvement of road from Sikder Mallik UP-Durgapur UP via Panchpara GC road By BC from Ch. 00-1000m under sadar upazila [ID No: 579803003]. | 579803003 |  | 1 |  |  |  |  | 9668845 | 9665000 | M/S. Reazon Enterprise Prop. Md. Kazi Jaman Nesarabad, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 9665000 |  |  | Final
19 | BDRIDP/PRJ/ SAD/CCA-Rd/01 | Improvement of road from Daudpur house of Idris Sardar to Rajarkati via Udaykati Jam-e-Mosque road by HBB from Ch. 00-1500m under Sadar Upazila. | 579805099 |  | 1.5 |  |  |  |  | 4493946 | 4224429.563 | M/S. Abir & Brothers Prop. Salma Rahman Amlapara, Pirojpur |  | 01.02.16 | 01.02.17 |  | 100% | 4222873 |  |  | Final
20 | BDRIDP/PRJ/ SAD/UN-Rd/01 | Improvement of road from R&H to Pantadubi Mazibar Dakuyar Bari via Bala Bari Mohsiner Bari, Syfuler Bari & Clab & Madrasha, School road By BC from Ch. 00-1550m. | 579803018 |  | 1.55 |  |  |  |  | 9518495 | 9512694.886 | M/S. Ziaul & Brothers Prop. Khandakar Ziaul Hossain Bhandaria, Pirojpur |  | 06.05.15 | 06.11.15 |  | 100% | 9500034 |  |  | Final
21 | BDRIDP/PRJ/SDR/UZ-RdR/01 | A Rehabilitation of Parerhat GC - Hularhat GC Road by BC at Ch. 2090-5140ID No.579802001B Construction of 9 Nos. 1.00mx1.00m 6 Nos. 2.00mx2.00m 2 Nos 3.00mx3.00m 2 Nos. 4.00mx4.00m Singale vent & 1 No. 4.00mx4.00m Double vent RCC Box culvert on Parerhat GC - Hularhat GC road at Ch. 2228m 2258m 2321m 2357m 2516m 2824m 2931m 2975m 3230m 3280m 3332m 3406m 3501m 3534m 3585m 3728m 3810m4507m 4826m & 5040m ID No.579802001 | 579802001 |  | 3.05 |  |  |  |  | 39642726 | 35678425.95 | PTSL-MAITREE (PVT) LTD 39, Mojumder House, Level-04, Suite-F, Purana Paltan, Dhaka-1000 | 26.07.17 | 01.10.17 | 01.10.18 |  | 100% | 35642152
22 | BDRIDP/PRJ/SDR/UZ-RdR/02 | a Rehabilitation of Parerhat GC-Hulurhat GC road by BC at Ch. 5140m-8640m ID No 5789802001 Salvage Materials Tk. 4404583.00 b Construction of 3nos 1.00mx1.00m 2nos 2.00mx2.00m & 1no 3.00mx3.00m RCC Box Culvert on Parerhat GC-Hularhat GC road at Ch. 5475m 5509m 5745m 6880m 6940m & 7630m ID No 579802001 | 579802001 |  | 3.5 |  |  |  |  | 25416511.44 | 22874860.296 | PTSL-MAITREE (PVT) LTD 39, Mojumder House, Level-04, Suite-F, Purana Paltan, Dhaka-1000 | 04.10.17 | 14.10.17 | 13.10.18 |  | 95% | 21000000
23 | BDRIDP/PRJ/SAD/UN-Rd/04 | Improvement of Road from Sikder Mollik UP S.K Krishi College Sikder Mallik Bazar Road Up to Sikder Mallik RHD by HBB at Ch.600m-2880m. Including 1 Nos 2.00mx2.00m & 2 Nos 1.00mx1.00m RCC Box Culvert at Ch.640m1460m 1730m. Id No. 579803019 | 579803019 |  | 2.88 |  |  |  |  | 12066788.88 | 10860109.992 | ISLAM BROTHERS & ENGINEER LTD Sonartori Toer, 4-5 Th Floor , 132 Sonargan Road, Dhaka-1000 | 07.05.18 | 15.05.18 | 15.11.18 |  | 100% | 10832369
24 | BDRIDP/PRJ/SDR/CCA-Rd/02 | A Improvement of road from Udaykati H/S-Razarkati Kheyaghat By BC at Ch. 0.00-500.00m. including 01 No 3.00mX3.00m 03 Nos 2.00mX2.00m &01 No 1.00mX1.00m RCC Box Culvert at Ch. 165.00m90.00m 290.00m. 480.00m& 75.00m. ID No-579805001 Salvage Cost TK. 274029.00B Improvement of road from Bazarkati Bazar-Kalakhali Bazar Via LGED Road at Ch. 0.00-800.00m. including 01 No 4.00mX4.00m RCC Box Culvert at Ch.780.00m. ID No-Salvage Cost 1444286.00 | 579805080 | [6 empty] | 15360444 | 13523352.955 | M/S. Ziaul Traders 37 Toot para Cross road-2, Khulna | 09.07.19 | 16.07.19 | 16.01.20 |  | 90% | 11900000
25 | BDRIDP/PRJ/SDR/CCA-Rd/05 | A Improvement of Sikdermolok UP-Kalakhali UP Upto Gojaliya Launch Ghat Via Ghophat & Chalisha Hat Road at Ch. 0.00-600.00m. including 01 No 3.00mX3.00m & 01 No1.00mX1.00m RCC BOx Culvert at Ch. 297.00m& 428.00m. ID No-579803009 Salvage Cost TK. 902396.00B Improvement of Kadomtola UP Sikdermolok UP Via Nikarirhat & Porgola Nutanhat Road at Ch 1770.00-2770.00m. ID No-579803005 Salvage Cost TK. 2583897.00 | 579803005 | [17 empty] | Cancelled
26 | BDRIDP/PRJ/SDR/CCA-Rd/03 | A Improvement of Perojpur-Nazirpur Barobari Bus Stand to Porgola Nikarihat Road By BC at Ch. 0.00m-900.00m. including 03 Nos 2.00mX2.00m RCC Box Culvert at Ch. 165.00m445.00m & 692.00m. ID No-579805096 Salvage Cost- 535266.00 B Improvement of Road From Tona Baily Bridge to Chalisha Via Tona GPS Dakhin Jibogram FRB - Uttar Bajukati GPS road at Ch.0.00m-1305.00m. including 01 No 2.00mX2.00m RCC Box Culvert at Ch. 1305.00m. ID No-579805091. Salvage Cost TK. 2948460.00 | 579805096 579805091 | [6 empty] | 17893065 | 16354862.149 | M/S. Lutful Kabir Dill Bag, Bagura, Alekanda Road, Barisal-8200 | 09.07.19 | 16.07.19 | 16.01.20 |  | 85% | 13000000
|  | Road work Sub-Total = |  | 0 | 8.12 | 0 | 0 | 0 | 0 | 139882737.32 | 138513735.791 | [6 empty] | 131582428
27 | BDRIDP/PRJ/ SAD/UN-St/02 | Construction of 1No 2.00x2.00m & 1No 4.00x4.00m RCC Box Culvert on Sikder Mallik UP-Panchpara GC road at Ch. 847m and 970m under Sadar Upazila. [ID No: 579803004] | 579803004 | [5 empty] | 6 | 3074778 | 3068000 | M/S. Reazon Enterprise Prop. Md. Kazi Jaman Nesarabad, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 3065595 |  |  | Final
28 | BDRIDP/PRJ/ SAD/UN-St/03 | Construction of 3Nos 3.00x3.00m RCC Box Culvert & 3Nos U-Drain (1.00x1.20m) on Sikder Mallik UP-Durgapur UP via Panchpara GC road at Ch. 530m, 840m, 970m, 150m, 180m & 360m under Sadar Upazila [ID No: 579803003]. | 579803003 | [5 empty] | 12 | 14803419 | 14800000 | M/S. Ruma Bricks Prop. Md. Rustum Mollah Banaripara, Barisal. |  | 22.03.15 | 22.09.15 |  | 100% | 14799821 |  |  | Final
29 | BDRIDP/PRJ/ SAD/CCA-St/01 | Construction of 4Nos 0.625mx0.60m U-Drain & 2nos 2.00x2.00m RCC Box Culvert on Daudpur house of Idris Sardar to Rajarkati via Udaykati Jam-e-Mosque road at ch. 75m, 110m, 295m, 1305m, 365 & 945m under Sadar Upazila. | 579805099 | [5 empty] | 6.5 | 1148546 | 1134493.88 | M/S. Mudasser Ali Mallik, Sagardi, Barisal. |  | 20.01.16 | 20.07.16 |  | 100% | 1129328 |  |  | Final
30 | BDRIDP/PRJ/ NSB/UN-St/01 | Construction of 2Nos 4.00x4.00m , 2nos 3.00x3.00m 3nos 2.00x2.00m, 1no 3vent 4.00x4.00m RCC Box Culvert & 3nos U-Drain on R&H road to Pantadubi Mazibar Dakuyar bari via Bala bari Mohsiner Bari & Madrasha , School road at ch. 378m, 1158m, 900m, 1072m, 313m, 1020m, 1360m, 1175m, 470m, 610m & 1230m Ch. 00-1550m. | 579803018 | [5 empty] | 27.5 | 2653663 | 12634273.604 | M/S. Gazi Construction Prop. Md. Ziaul Ahasan Gazi Badura Parerhat road, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 12625914 |  |  | Final
31 | BDRIDP/PRJ/SDR/UZ-/St-02 | Construction of 30.00m P.S.C Girder Bridge on Parerhat GC to Hularhat GC Road At Ch. 9+350m Over Sariktala Khal under Pirojpur Sadar Upazila (ID No: 579802001) | 579802001 | [5 empty] | 30 | 22522642 | 22291661.166 | abir_mkhan (JV) Prop. Salma Rahman Parerhat road, Pirojpur |  | 12.03.17 | 11.03.18 |  | 100% | 20573731
32 | BDRIDP/PRJ/SDR/UZ-/St-01 | Construction of 30.00m P.S.C Girder Bridge on Parerhat GC to Hularhat GC Road At Ch. 8+415m over Kalikati Khal under Pirojpur Sadar Upazila (ID No: 579802001) | 579802001 | [5 empty] | 30 | 29163849 | 26247464.316 | PTSL-MAITREE (PVT) LTD 39, Mojumder House, Level-04, Suite-F, Purana Paltan, Dhaka-1000 | 05.07.17 | 12.07.17 | 11.07.18 |  | 100% | 26186471 |  |  | final
33 | BDRIDP/PRJ/SDR/UZ-st/03 | Construction of 99.10m Long PC Girder Bridge on Parerhat GC to Hularhat GC road at Ch-0300km over Chami Khal including aproach road at ch.0.00m-1155.00m & 1 no. 2.00mx2.00m 1 no. 1.00mx1.00m & 1 no. 4.00mx4.00m Two vent RCC box culvert at ch. 870.00m1080.00m & 1117.00m. under Upazila Pirojpur Sadar District Pirojpur | [6 empty] | 99.1 | 94287679.53 | 84858911.577 | Toma Construction & Co. Limited, Toma Tower, 77/1, Kakrail, Ramna, Dhaka-1000 | 31.01.18 | 10.02.18 | 09.02.19 |  | 90% | 74500000
|  | Structure work Sub-Total = |  | 0 | 0 | 0 | 0 | 0 | 211.1 | 167654576.53 | 165034804.543 | [6 empty] | 152880860
|  | Upazila Total = |  | 11.507 | 8.12 | 0 | 0 | 0 | 211.1 | 313460858.85 | 309472085.334 | [6 empty] | 290318632
Upazila : Indurkani
34 | BDRIDP/PRJ/ZIA/ CCA-Ew/01 | Improvement by Earth Filling on Talukder bari Masque-Care Road via Doari Bari (Ch. 0.00-340m). | 579885059 | 0.34 | [5 empty] | 319600 | 319600 | Md. Kamruzzaman Shawon | 11.09.14 | 18.09.14 | 18.03.15 |  | 100% | 318722 | 100% |  | Final
35 | BDRIDP/PRJ/ZIA/ CCA-Ew/02 | Improvement by Earth Filling on LGED road - Mollik Bari road via Rahman Shake house (Laxmidia GPS) (Ch. 756-944m). | 579885058 | 0.188 | [5 empty] | 195370 | 195370 | Md. Lablu | 11.09.14 | 18.09.14 | 18.03.15 |  | 100% | 191360 | 100% |  | Final
36 | BDRIDP/PRJ/ ZIA/UN-Ew/01 | Improvement of road from Parerhat UP-Batazor hat via Natunhat road by Earth work from Ch. 1680-4342m | 579883003 | 2.662 | [5 empty] | 266168 | 266168 | Abu Bakar Siddik | 20.05.15 |  |  |  | 100% | 133800 | 100%
37 | BDRIDP/PRJ/ ZIA/UN-Ew/02 | Improvement of road from Balipara UP (Kholputua)-Munshirhat-Jamadderhat-Uttar Kolaron RNGPS road by Earth work from Ch.2429-3445m | 579883009 | 1.265 | [5 empty] | 417575 | 417575 | Abdul Karim | 27.04.15 |  |  |  | 100% | 348806 | 100% |  | Final
38 | BDRIDP/PRJ/ ZIA/UN-Ew/02 | Improvement of road from Balipara UP (Kholputua)-Munshirhat-Jamadderhat-Uttar Kolaron RNGPS road by Earth work from Ch. 5445-6010m | 579883009 | 1.265 | [5 empty] | 324175 | 324175 | Md. Masud Talukder | 27.04.15 |  |  |  | 100% | 324175 | 100% |  | Final
|  | Earth work Sub-Total = |  | 5.72 | 0 | 0 | 0 | 0 | 0 | 1522888 | 1522888 | [6 empty] | 1316863
39 | BDRIDP/PRJ/ZIA/CCA-Rd/01 | Improvement of Road by HBB from Talukder Bari Masjid-Care Road Via Doari Bari (Ch.0.00-340m). | 579885059 |  |  | 0.34 |  |  |  | 958642 | 949061.95 | M/S. Matubber Enterprise Prop. Md. Nazrul Islam Matubber Shankarpasha, Pirojpur | 20.07.14 | 27.07.14 | 27.12.14 |  | 100% | 948978 | 100% |  | Final
40 | BDRIDP/PRJ/ZIA/CCA-Rd/02 | Improvement of Road by HBB from LGED road via Rahman Shehk house (Laxmiadia GPS).(Ch.756-944m) | 579885058 |  |  | 0.188 |  |  |  | 1177275 | 1114879.24 | M/S. Matubber Enterprise Prop. Md. Nazrul Islam Matubber Shankarpasha, Pirojpur | 20.07.14 | 27.07.14 | 27.12.14 |  | 100% | 1100466 | 100% |  | Final
41 | BDRIDP/PRJ/ ZIA/UN-Rd(R)/02 | Improvement of road Balipara UP (Kholputua)-Munshirhat-Jamadderhat-Uttar Kolaron RNGPS road By BC from ch. 2945-3445m By HBB from Ch. 3693-4051m & 5039-6020m with 5 Nos 0.625x0.600m U-Drain at Ch. 3938m, 5280m, 5565m, 5555m & 5775m under Zianagar Upazila.[ID No: 579883009] . | 579883009 |  |  | 1.33 |  |  |  | 27435361 | 27425000 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 27424988 | 100% |  | Final
42 | BDRIDP/PRJ/ ZIA/UN-Rd(R)/01 | Improvement of road from Parerhat UP-Batazorhat via Natunhat road By BC from Ch. 1680-4342m with 4Nois U-Drain at Ch. 1460m, 2720m, 3513m & 4112m under Zianagar Upazila [ID No: 579883003] | 579883003 |  | 2.66 |  |  |  |  | 24912189 | 24908000 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Piropur |  | 22.03.15 | 22.03.16 |  | 100% | 24903375 | 100% |  | Final
43 | BDRIDP/PRJ/ IDK/CCA-Rd/04 | Improvement of road from Kalibari-Dorichar Ekor Bunia road at Ch. 00m-704m & 825m-890m. including 01 No 4.00m x 4.00m & 01 No 1.00 x 1.00m RCC Box at Ch. 270.00m & 320.00m. ID No-579885023 | 579885023 |  | 1.35 |  |  |  |  | 8219701.25 | 7808716.188 | M/S. Sourov Construction Prop. Md. Badiuzzaman Saurov Machimpur, Pirojpur |  | 30.01.19 | 29.07.19 |  | 100% | 7800000 | 0%
44 | BDRIDP/PRJ/ IDK/CCA-Rd/03 | Improvement of road from Balipara Bottola-Patherhat road via Nuria Dakhil Madrasha at Ch. 0.00m-1000.00m. ID No-579884039 | 579884039 |  | 1 |  |  |  |  | 7234604.68 | 6872874.446 | M/S. Jiaul and Brothers Prop. Khandakar Jiaul Hossain, Bhandaria, Pirojpur | 13.03.19 | 08.04.19 | 08.10.19 |  | 70% | 4660000 | 0%
45 | BDRIDP/ PRJ/ IND/ GHAT/01 | Construction of indurkani Bazar RCC Ghat Boat Landing | [7 empty] | 2962600.31 | 2814470 | M/S Alamgir & Sons Baheratala Road, Mathbaria, Pirojpur | 15.05.19 | 22.05.19 | 22.11.19 |  | 100% | 2814225 | 0%
|  | Road work Sub-Total = |  | 0 | 2.66 | 1.858 | 0 | 0 | 0 | 72900373.24 | 71893001.824 | [6 empty] | 69652032
|  | Upazila Total = |  | 5.72 | 2.66 | 1.858 | 0 | 0 | 0 | 74423261.24 | 73415889.824 | [6 empty] | 70968895
Upazila : Mathbaria
46 | BDRIDP/PRJ/ MAT/CCA-Ew/01 | Improvement by Earth Filling on Mirukhali RHD to dhoudkhali Nutan hat Via Kalibari GPS road (Ch. 00-1000m) (Srart from Mirukhali Amua RHD to Shahadad Hossain khan house via Dhoudkhali Board GPS cum Cyclone Shelter) | 579584090 | 1 | [5 empty] | 433744 | 433744 | Md. Jahangir | 07.04.14 | 10.04.14 | 15.05.14 |  | 100% | 433700 | 100% |  | Final
47 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch. 15750-16600m | 579582004 | 0.85 | [5 empty] | 345460 | 345460 | Nurul Islam Gazi | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 345460 |  |  | Final
48 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch. 16600-17150m | 579582004 | 1.15 | [5 empty] | 341778 | 341778 | Md. Shorab Sikder | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 246082
49 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch. 17150-17750m | 579582004 | 0.6 | [5 empty] | 325613 | 325613 | Md. Bepul Mistry | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 312286 |  |  | Final
50 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch. 17750-18200m | 579582004 | 0.45 | [5 empty] | 317713 | 317713 | Md. Shahajan Khalifa | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 228780
51 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch.18200-18595m | 579582004 | 0.395 | [5 empty] | 354612 | 354612 | Md. Ruhul Amin Howlader | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 348021 |  |  | Final
52 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch.18595-19030m | 579582004 | 0.435 | [5 empty] | 352875 | 352875 | Md. Juel Howlader | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 344220 |  |  | Final
53 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch.19030-19550m | 579582004 | 0.52 | [5 empty] | 334320 | 334320 | Md. Siddique Khan | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 333926 |  |  | Final
54 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of Mathbaria GC-Musulli Bari RHD via Mirukhali Bazar-Vogirothpur Bazar road by Earth ch.19550-20050m | 579582004 | 0.5 | [5 empty] | 312173 | 312173 | Mr. Ram krishan | 08.09.14 | 15.09.14 | 15.03.15 |  | 100% | 298372 |  |  | Final
55 | BDRIDP/PRJ/ MAT/UN-Ew/01 | Improvement of road from Amragachia UP to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work form ch. 6100-6950m [ID No: 579583010] | 579583010 | 0.85 | [5 empty] | 259366 | 259366 | Md. Monir Talukder | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 259000 |  |  | Final
56 | BDRIDP/PRJ/ MAT/UN-Ew/01 | Improvement of road from Amragachia UP to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work form ch. 6950-7330m [ID No: 579583010] | 579583010 | 0.38 | [5 empty] | 294154 | 294154 | Mrs. Rehana Begum | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 290600 |  |  | Final
57 | BDRIDP/PRJ/ MAT/UN-Ew/01 | Improvement of road from Amragachia UP to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work form ch. 7330-7690m [ID No: 579583010] | 579583010 | 0.36 | [5 empty] | 256333 | 256333 | Md. Yeakub | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 251600 |  |  | Final
58 | BDRIDP/PRJ/ MAT/UN-Ew/01 | Improvement of road from Amragachia UP to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work form ch. 7690-8100m [ID No: 579583010] | 579583010 | 0.41 | [5 empty] | 271567 | 271567 | Md. Halim | 14.12.14 | 21.02.14 | 21.06.15 |  | 100% | 267000 |  |  | Final
59 | BDRIDP/PRJ/ MAT/UZ-Ew/01 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 2490-2750m. | 579582005 | 0.26 | [5 empty] | 331666 | 335500 | Md. Zakir Hossain | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 335500 |  |  | Final
60 | BDRIDP/PRJ/ MAT/UZ-Ew/01 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 2750-2950m. | 579582005 | 0.2 | [5 empty] | 297635 | 297635 | Md. Walid | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 283000 |  |  | Final
61 | BDRIDP/PRJ/ MAT/UZ-Ew/01 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 2950m-3400m. | 579582005 | 0.45 | [5 empty] | 289748 | 289748 | Md. Afzal | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 280400 |  |  | Final
62 | BDRIDP/PRJ/ MAT/UZ-Ew/01 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 3400-3850m. | 579582005 | 0.45 | [5 empty] | 268437 | 268437 | Mrs. Khursida | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 258000 |  |  | Final
63 | BDRIDP/PRJ/ MAT/UZ-Ew/01 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 3850-4150m. | 579582005 | 0.3 | [5 empty] | 201135 | 201135 | Mrs. Dulia Begum | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 190900 |  |  | Final
64 | BDRIDP/PRJ/ MAT/UZ-Ew/01 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 4150-4950m. | 579582005 | 0.8 | [5 empty] | 241003 | 241003 | Mrs. Shefaly Begum | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 228900 |  |  | Final
65 | BDRIDP/PRJ/ MAT/UZ-Ew/02 | Improvement of road from Gulishakhali GC-Dowatala GC via Tearkhali Bazar & Kumirmara Bazar road by Earth work form ch. 2400-2850m | 579582006 | 0.45 | [5 empty] | 324189 | 324189 | Abdul Halim Khan | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 300900 |  |  | Final
66 | BDRIDP/PRJ/ MAT/UZ-Ew/02 | Improvement of road from Gulishakhali GC-Dowatala GC via Tearkhali Bazar & Kumirmara Bazar road by Earth work form ch.2850-3500m | 579582006 | 0.65 | [5 empty] | 334128 | 334128 | Mrs. Runu | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 320500 |  |  | Final
67 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch. 5853-6200m | 579582002 | 0.347 | [5 empty] | 325210 | 325210 | Md. Sumon | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 323874 |  |  | Final
68 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch.6200-6600m | 579582002 | 0.4 | [5 empty] | 325718 | 325718 | Mirza Sagir | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 320871 |  |  | Final
69 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch.6600-7500m | 579582002 | 0.9 | [5 empty] | 280183 | 280183 | Mrs. Masuma | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 277270 |  |  | Final
70 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch.7500-8100m | 579582002 | 0.6 | [5 empty] | 277039 | 277039 | Md. Sagir Howlader | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 270098 |  |  | Final
71 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch.8100-8700m | 579582002 | 0.6 | [5 empty] | 288157 | 288157 | Md. Nazrul | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 280638 |  |  | Final
72 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch.8700-9400m | 579582002 | 0.7 | [5 empty] | 317940 | 317940 | Md. Sukur | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 311566 |  |  | Final
73 | BDRIDP/PRJ/ MAT/UZ-Ew/04 | Improvement of road from Masua RHD Mathbaria GC-Safa Amua RHD via Algi Hat road by Earth work from ch.9400-9900m | 579582002 | 0.5 | [5 empty] | 199317 | 199317 | Md. Sumon | 14.12.14 | 21.12.14 | 21.06.15 |  | 100% | 167296 |  |  | Final
74 | BDRIDP/PRJ/ MAT/UZ-Ew/05 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 4490-4800m. | 579582005 | 0.31 | [5 empty] | 301141 | 301141 | Md. Habibur Rahman | 15.02.15 | 22.02.15 | 22.08.15 |  | 100% | 281395 |  |  | Final
75 | BDRIDP/PRJ/ MAT/UZ-Ew/05 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch. 4800-5100m. | 579582005 | 0.31 | [5 empty] | 300855 | 300855 | Md. Al-Amin | 15.02.15 | 22.02.15 | 22.08.15 |  | 100% | 293631 |  |  | Final
76 | BDRIDP/PRJ/ MAT/UZ-Ew/05 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch.5100-5550m. | 579582005 | 0.45 | [5 empty] | 310661 | 310661 | Md. Merazul Islam | 15.02.15 | 22.02.15 | 22.08.15 |  | 100% | 303844 |  |  | Final
77 | BDRIDP/PRJ/ MAT/UZ-Ew/05 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch.5550-6150m. | 579582005 | 0.6 | [5 empty] | 207969 | 207969 | Md. Swapon | 15.02.15 | 22.02.15 | 22.08.15 |  | 100% | 196066 |  |  | Final
78 | BDRIDP/PRJ/ MAT/UZ-Ew/05 | Improvement of road from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by Earth work from ch.6150-6630m. | 579582005 | 0.48 | [5 empty] | 193598 | 193598 | Mrs. Khadija Begum | 15.02.15 | 22.02.15 | 22.08.15 |  | 100% | 186290 |  |  | Final
79 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of road from Dhanisafa Launchghat-Safa Bazar road by Earth work from Ch. 00-1000m | 579584006 | 2 | [5 empty] | 284300 | 353360 | Md. Ismail | 15.03.15 |  |  |  | 100% | 353360 |  |  | Final
80 | BDRIDP/PRJ/ MAT/CCA-Ew/03 | Improvement of road from Dhanisafa Launchghat-Safa Bazar road by Earth work from Ch. 1000-2000m | 579584006 | 2 | [5 empty] | 284303 | 284303 | Md. Masud | 15.03.15 |  |  |  | 100% | 210000 |  |  | Final
81 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 8100-8525m | 579583010 | 0.452 | [5 empty] | 306135 | 306135 | Mrs. Jaida Afroz Nina | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 304253 |  |  | Final
82 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 8525-8900m | 579583010 | 0.4 | [5 empty] | 303448 | 303448 | Md. Raisul Arefin | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 303148 |  |  | Final
83 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 8900-9250m | 579583010 | 0.925 | [5 empty] | 315813 | 315813 | Tamanna Nustrat | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 315015 |  |  | Final
84 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 9250-9650m | 579583010 | 0.4 | [5 empty] | 316711 | 316711 | Hasina Begum | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 316245 |  |  | Final
85 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 9650-10350m | 579583010 | 0.7 | [5 empty] | 289578 | 289578 | Md. Imran Hasan | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 288969 |  |  | Final
86 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 10350-11125m | 579583010 | 0.775 | [5 empty] | 241429 | 241429 | Md. Bellal Hossain | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 240069 |  |  | Final
87 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 11125-11750m | 579583010 | 0.625 | [5 empty] | 179129 | 179129 | Md. Ibrahim Khalil | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 179097 |  |  | Final
88 | BDRIDP/PRJ/ MAT/UN-Ew/02 | Improvement of Earthern road from Amagachia Union Parisahad to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road by Earth work from Ch. 11750-12100m | 579583010 | 0.35 | [5 empty] | 211063 | 211063 | Md. Siddique Mia | 25.02.15 | 04.03.15 | 04.09.15 |  | 100% | 206856 |  |  | Final
89 | BDRIDP/PRJ/ MAT/UN-Ew/03 | Improvement of road from Mathbaria GC-Betmore ajpara Union Parisahad road by Earth work from Ch. 4000-5000m. | 579883003 | 1 | [5 empty] | 410692 | 410692 | Mithun Mazumder | 30.04.15 |  |  |  | 100% | 352000
90 | BDRIDP/PRJ/ MAT/CCA-Ew/02 | Improvement of road from Tuskhali UNR road-Sotto Masua Wapdha Mosaraf House road by Earth work at Ch. 00-1000m. | 5795855021 | 1 | [5 empty] | 303531 | 303531 | Md. Abdus Salam | 15.03.15 | 22.03.15 | 22.06.15 |  | 100% | 300100 |  |  | Final
91 | BDRIDP/PRJ/ MAT/CCA-Ew/02 | Improvement of road from Tuskhali UNR road-Sotto Masua Wapdha Mosaraf House road by Earth work at Ch. 00-1000m. | 5795855021 | 1 | [5 empty] | 303531 | 303531 | Md. Sohag | 15.03.15 | 22.03.15 | 22.06.15 |  | 100% | 300100 |  |  | Final
92 | BDRIDP/PRJ/ MAT/UN-Ew/04 | Improvement of road from Amragachia Union Parisad-Manikkhali Bazar via Sonakhali Bazar & Tulata Bazar road Ch. 12100-12700m | 579583010 | 0.6 | [5 empty] | 466091 | 466091 | Md. Nur Islam | 07.06.15 | 13.06.15 |  |  | 100% | 465000 |  |  | Final
93 | BDRIDP/PRJ/ MAT/UN-Ew/04 | Improvement of road from Amragachia Union Parisad-Manikkhali Bazar via Sonakhali Bazar & Tulata Bazar road Ch. 12700-13300m | 579583010 | 0.6 | [5 empty] | 467687 | 467687 | Md. Anwar Hossain | 07.06.15 | 13.06.15 |  |  | 100% | 465000 |  |  | Final
94 | BDRIDP/PRJ/ MAT/UN-Ew/04 | Improvement of road from Amragachia Union Parisad-Manikkhali Bazar via Sonakhali Bazar & Tulata Bazar road Ch. 13300-14100m | 579583010 | 0.8 | [5 empty] | 453294 | 453294 | Md. Siddiqur Rahman | 07.06.15 | 13.06.15 |  |  | 100% | 449670 |  |  | Final
95 | BDRIDP/PRJ/ MAT/UN-Ew/05 | Improvement of road from Amragachia Union Parisad-Manikkhali Bazar via Sonakhali Bazar & Tulata Bazar road Ch. 14100-15100m | 579583010 | 1 | [5 empty] | 339191 | 339191 | Mr. Mithun Mogumder | 07.06.15 | 13.06.15 |  |  | 100% | 335050 |  |  | Final
96 | BDRIDP/PRJ/ MAT/CCA-Ew/04 | Resectioning of road from Sonakhali Collage UZR-Sonakhali Manikkhali road Ch. 00-600m | 579584042 | 0.6 | [5 empty] | 428052 | 428052 | Md. Shafiqul | 07.06.15 |  |  |  | 100% | 427998 |  |  | Final
97 | BDRIDP/PRJ/ MAT/CCA-Ew/04 | Resectioning of road from Sonakhali Collage UZR-Sonakhali Manikkhali road Ch. 600-1550m | 579584042 | 0.95 | [5 empty] | 472378 | 472378 | Md. Nizam Akon | 07.06.15 |  |  |  | 100% | 472378 |  |  | Final
98 | BDRIDP/PRJ/ MAT/CCA-Ew/05 | Resectioning of road from Gulishakhali Bazar road-Tttar Sonakhali Chan Miah house via Talukder Bari road from Ch. 1850-2850m | 579584103 | 1 | [5 empty] | 473980 | 473980 | Md. Helal Hawlader | 07.06.15 |  |  |  | 100% | 472272 |  |  | Final
99 | BDRIDP/PRJ/ MAT/CCA-Ew/06 | Improvement of road from Sahid Noor Hossain bari road (Sapleza Nali road-Sapleza Bondoppara road via East Sapleza GPS road) by earth work at Ch. 0.00-2000m | 579585036 | 2 | [5 empty] | 461542 | 461542 | Md. Habibur Rahman |  | 13.06.16 | 13.09.16 |  | 100% | 461179 |  |  | Final
100 | BDRIDP/PRJ/ MAT/UZ-Ew/06 | Resectioning of road from Pirojpur Patharghata RHD Road (Gudighata)-Rayenda GC (Machua Rocket Ghat) at Ch. 1100m-2400m | 579582007 | 1.3 | [5 empty] | 292521 | 292521 | Md. Altaf Hossain | 07.05.17 | 15.05.17 | 15.08.17 |  | 100% | 286978 |  |  | Final
101 | BDRIDP/PRJ/ MAT/UZ-Ew/06 | Resectioning of road from Pirojpur Patharghata RHD Road (Gudighata)-Rayenda GC (Machua Rocket Ghat) at Ch. 2400m-3050m | 579582007 | 0.65 | [5 empty] | 235092 | 235092 | Md. Sogir Howlader | 07.05.17 | 15.05.17 | 15.08.17 |  | 100% | 233913 |  |  | Final
102 | BDRIDP/PRJ/ MAT/UZ-Ew/06 | Resectioning of road from Pirojpur Patharghata RHD Road (Gudighata)-Rayenda GC (Machua Rocket Ghat) at Ch.3050m-3650m | 579582007 | 0.6 | [5 empty] | 283168 | 283168 | Md. Ayub Ali | 07.05.17 | 15.05.17 | 15.08.17 |  | 100% | 281204 |  |  | Final
103 | BDRIDP/PRJ/ MAT/CCA-Ew/07 | Earth filling of road from Panchyet Bari-Sapleza Nali road via Tomazia High School at Ch. 2900-3800m | 579584007 | 0.9 | [5 empty] | 358143 | 358143 | Md. Farid Uddin | 06.04.17 | 13.04.17 | 30.06.17 |  | 100% | 356203 |  |  | Final
104 | BDRIDP/PRJ/ MAT/CCA-Ew/07 | Earth filling of road from Panchyet Bari-Sapleza Nali road via Tomazia High School at Ch. 3800-4700m | 579584007 | 0.9 | [5 empty] | 354112 | 354112 | Md. Mostafa Dulal | 06.04.17 | 13.04.17 | 30.06.17 |  | 100% | 352170 |  |  | Final
105 | BDRIDP/PRJ/ MAT/UZ-Ew/07 | Earth filling of road from Gulishakhali GC-Dwatala GC (Kumirmara & Tearkhali Bazar) road Ch. 4500-5000m | 579582006 | 0.5 | [5 empty] | 364758 | 364758 | Md. Monir Talukder | 06.04.17 | 13.04.17 | 30.06.17 |  | 100% | 364142 |  |  | Final
106 | BDRIDP/PRJ/ MAT/UZ-Ew/07 | Earth filling of road from Gulishakhali GC-Dwatala GC (Kumirmara & Tearkhali Bazar) road Ch. 5000-5600m | 579582006 | 0.6 | [5 empty] | 452447 | 452447 | Ziauddin Mahmud | 06.04.17 | 13.04.17 | 30.06.17 |  | 100% | 451993 |  |  | Final
|  | Earth work Sub-Total = |  | 42.284 | 0 | 0 | 0 | 0 | 0 | 19467556 | 19540450 | [6 empty] | 18914348
107 | BDRIDP/PRJ/ MAT/CCA-Rd/01 | Improvement of road from Mirukhali RHD to dhaudkhali Nutan hat Via Kalibari GPS road by BC (Ch. 00-1000m) (Srart from Mirukhali Amua RHD to Shahadad Hossain khan house via Dhoudkhali Board GPS cum Cyclone Shelter) | 579584090 |  | 1 |  |  |  |  | 5949036 | 5938941.05 | Md. Tahidul Basher Kabir Mathbria, Pirojpur | 08.07.14 | 15.07.14 | 14.11.14 |  | 100% | 5938784 |  |  | Final
108 | BDRIDP/PRJ/ MAT/UZR®-Rd/01 | Rehabilitation of Gulishakhali GC-Dowatala GC via Tearkhali Bazar & Kumirmara Bazar road by Flexible Pavement at ch. 2400-3500m. | 579582006 |  | 0.9 |  |  |  |  | 6919580 | 5805551.489 | RM JVCA Mathbaria, Pirojpur | 14.09.14 | 01.10.14 | 31.03.15 30.06.16 |  | 100% | 5805538 |  |  | Final
109 | BDRIDP/PRJ/ MAT/UZR®-Rd/02 | Rehabilitation of Masua R&H road-Mathbaria GC-Safa Amua RHD via Algi Bazar road by Flexible Pavement ch. 5853-7853m | 579582002 |  | 2 |  |  |  |  | 11362513 | 9537859.425 | RM JVCA Mathbaria, Pirojpur | 14.09.14 | 01.10.14 | 31.03.15 |  | 100% | 9385368 |  |  | Final
110 | BDRIDP/PRJ/ MAT/CCA-Rd/02 | Improvemen of road from Sapleza Varani to Hazigang Bazar road by HBB (start from Howlader bari corner-Jalal Matubbar bari-Hazigang Bazar HBB road) from 00-990m and 3nos U-Drain at Ch. 378m, 485m & 676m | 579584008 |  | 0.99 |  |  |  |  | 2821178 | 2680119 | M/S. Ahmed Steel Industries Prop. Md. Rafiuddin Ahmed Mathbaria, Pirojpur | 30.11.14 | 10.12.14 | 24.05.15 |  | 100% | 2679788 |  |  | Final
111 | BDRIDP/PRJ/ MAT/UZ-Rd (R)/05 | Rehabilitation of road from Mathbaria GC (Dack Bangla)-Amua GC road via Dhaudkhali Union Porishad road by BC from Ch. 4490-6630m | 579582005 |  | 2.14 |  |  |  |  | 13770633 | 13765957.14 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur |  | 05.04.15 | 05.10.15 |  | 100% | 13755291 |  |  | Final
112 | BDRIDP/PRJ/ MAT/UN-Rd (R)/01 | Rehabilitation of road from Amragachia Union Parishad-Manikkhali Bazar via Sonakhali Bazar, Tulatalahat road by BC from Ch. 8100-12100m | 579583010 |  | 4 |  |  |  |  | 20709592 | 20705637.79 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Pirojpur |  | 05.04.15 | 05.02.16 |  | 100% | 20701388 |  |  | Final
113 | BDRIDP/PRJ/ MAT/UZ-Rd (R)/06 | Rehabilitation of road from Masua R&H Mathbaria GC-Safa Amua RHD via Algihat road by BC ch. 7853-9900m | 579582002 |  | 2.04 |  |  |  |  | 21087322 | 21081460.75 | M/S. Eashan Enterprise Prop. Md. Salauddin Bhandaria, Pirojpur |  | 05.04.15 | 05.10.15 |  | 100% | 21077946 |  |  | Final
114 | BDRIDP/PRJ/ MAT/UN-Rd/02 | Improvement of road Mathbaria GC- Betmore Rajpara Union Parishad road by BC from Ch. 4000-5000m (ID No: 579883003) | 579883003 |  | 1 |  |  |  |  | 5445011 | 4512125.802 | M/S. Selim Enterprise Prop. Md. Azizul Haque Selim Mathbaria, Pirojpur |  | 17.08.15 | 16.08.16 |  | 100% | 4511549 |  |  | Final
115 | BDRIDP/PRJ/ MAT/CCA-Rd/03 | Improvement of road from Tushkhali UNR road-Sotto Masua Wapdha via Mosaraf House road By HBB at Ch. 00m-2000m [ ID No: 5795855021] | 5795855021 |  |  | 2 |  |  |  | 4701483 | 4673274 | M/S. Laskar Enterprise Prop. Md. Shohel Laskar Mathbaria, Pirojpur | 14.07.15 | 21.07.15 | 21.01.16 |  | 100% | 4596750 |  |  | Final
116 | BDRIDP/PRJ/ MAT/CCA-Rd/04 | Improvement of road from Dhanisaf Launchghat-Safa Bazar road By HBB from Ch. 00-2000m [ ID No: 579584006] | 579584006 |  |  | 2 |  |  |  | 4701483 | 4665751 | M/S. Laskar Enterprise Prop. Md. Shohel Laskar Mathbaria, Pirojpur | 14.07.15 | 21.07.15 | 21.01.16 |  | 100% | 4533756 |  |  | Final
117 | BDRIDP/PRJ/ MAT/CCA-Rd/06 | Improvement of road from Gulishakhali Bazar-Uttar Sonakhali Chan Miah house via Talukder Bari road from Ch. 1850-2850m. | 579584103 |  |  | 1 |  |  |  | 5723969 | 4784984.019 | M/S. Saifuddin Traders Prop. M.M.A Wahab Nesarabad, Pirojpur | 19.10.15 | 26.10.15 | 26.04.16 |  | 100% | 4784731 |  |  | Final
118 | BDRIDP/PRJ/ MAT/CCA-Rd(R)/05 | Improvement of road from Sonakhali Collage UZR-Sonakhali Manikkhali road from ch. 00-1550m. | 579584042 |  |  | 1.55 |  |  |  | 10069841 | 8148553.649 | Md. Manebur Rahman Sabujbag 6th Lene, Patuakhali. | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 8148526 |  |  | Final
119 | BDRIDP/PRJ/ MAT/UZR®-Rd/03 | Rehabilitation of road by Flexible Pavement from Amragachia UP to Manikkhali Bazar Sonakhali Bazar & Tulatala Bazar road by BC at ch. 6100-8100m. | 579583010 |  |  | 2 |  |  |  | 9863551 | 9860018.893 | ASI-TBK (JV) Kapuriapatty, Mathbaria, Pirojpur | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 9860018 |  |  | Final
120 | BDRIDP/PRJ/ MAT/UN-Rd®/03 | Rehabilitation of road from Amragachia Union Parishad-Manikkhali Bazar via Sonakhali Bazar, Tulatala Bazar road from Ch. 12100-14100m. | 579583010 |  |  | 2 |  |  |  | 11510584 | 10587536.35 | ASI-TBK (JV) Kapuriapatty, Mathbaria, Pirojpur | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 10587536 |  |  | Final
121 | BDRIDP/PRJ/ MAT/UZR®-Rd/04 | Rehabilitation of road by Flexible Pavement from Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali Union Parishad road by BC at ch. 2490-4490m. | 579582005 |  |  | 2 |  |  |  | 12826948 | 12824011.682 | RE-TT (JV) New Mrket 22 viti, Mathbaria Pirojpur | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 12824000 |  |  | Final
122 | BDRIDP/PRJ/MAT/UZ-Rd®/07 | Rehabilitation of road from Pirojpur Patharghata RHD Road (Gudighata)-Ryendha GC (Machua Rocketghat) by BC at Ch. 1100-3650m inclding construction of 02nos 1.50x1.50m and 2nos 1.00x1.00m RCC Box Culvert at ch. 1050m, 2323m, 2749m & 3185m (ID No: 579582007) | 579582007 |  |  | 2.55 |  |  |  | 18978134 | 18933808.63 | M/S. Telikhali Construction Prop. Md. Samsuddin Howlader Bhandaria, Pirojpur | 26.10.16 | 09.11.16 | 09.11.17 |  | 100% | 18920225 |  |  | Final
123 | BDRIDP/PRJ/MAT/UN-RdR/04 | Rehabilitation of road from Amragachia UP Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar by BC At Ch. 14100m-16100m including 3no U-Drain At Ch. 14500m 14750m & 15560m ID No 579583010 Salvage Materials Tk. 1258343.00 | 579583010 |  |  | 2 |  |  |  | 12523929 | 12504758.7 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 16.04.17 | 26.04.17 | 25.04.18 |  | 100% | 12504700 |  |  | Final
124 | BDRIDP/PRJ/MAT/UZ-RdR/08 | Rehabilitation of road from Gulishakhali GC-Dhawatala GC Kumirmara Bazar via Tearkhali Bazarby BC At Ch. 3510m-6260m ID No 579582006 Salvage Materials Tk. 4046601.00 | 579582006 |  |  | 2.75 |  |  |  | 20387749 | 18348974.1 | M/S. Abir & Brothers Prop. Salma Rahman Amlapara, Pirojpur | 16.04.17 | 26.04.17 | 25.04.18 |  | 100% | 18345122 |  |  | Final
125 | BDRIDP/PRJ/ MAT/CCA-Rd/07 | Improvement of road from Sahid Noor Hossain bari road (Sapleza Nali road-Sapleza Bondoppara road via East Sapleza GPS road) by HBB at Ch. 0.00-2000m including 6nos U-Drain at Ch. 07m, 505m, 650m, 704m, 1050m & 1350m under Mathbaria Upazila. | 579585036 |  | 2 |  |  |  |  | 6951884 | 6950557.954 | M/S. Ahmed Steel Industries Prop. Md. Rafiuddin Ahmed Mathbaria, Pirojpur | 10.08.16 | 19.09.16 | 19.03.17 |  | 100% | 6950557 |  |  | Final
126 | BDRIDP/PRJ/MAT/UN-Rd/05 | Improvement of road from Matbaria GC-Betmore Rajpara Union Parishad via Taltala Bazar Road by BC from Ch. 5000m-6000m including 1 No. 1.00x1.00m RCC Box Culvert at ch. 5256m ID No 579583003 Salvage Materials Tk. 1495720.00 | 579583003 |  | 1 |  |  |  | 1 | 6055896 | 5455706.4 | M/S. Islam Brothers Prop. Md. Monirul Islam Talukder, 7, Court Road, Jhalakati. | 06.07.17 | 13.07.17 | 13.07.18 |  | 100% | 5451114
127 | BDRIDP/PRJ/MAT/CCA-Rd/08 | Improvement of road from Panchyet Bari-Sapleza Nali road via Tomezia High School by BC at Ch.2900-4700m including 5nos U-Drain 3100m3515m3865m3945m& 3985m.ID No. Salvage Materials Tk. 1401751.00 | 579584007 |  | 1.6 |  |  |  |  | 10263127 | 9236813.724 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 06.07.17 | 13.07.17 | 13.07.18 |  | 100% | 9221562
128 | BDRIDP/PRJ/MAT/UN-RdR/06 | Rehabilitation of Road from Mathbaria Amragachia UP-Manikkhali Bazar via Sonakhali bazar & Tulatola bazar road by BC from Ch. 625m-1500m including 1No. 1.00x1.00m RCC Box Culvert at Ch. 927m ID No 579583010 Salvage Materials Tk. 507828.00 | 579583010 |  | 0.85 |  |  |  | 1 | 5224005 | 4701604.833 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 06.07.17 | 13.07.17 | 13.07.18 |  | 100% | 4687258
129 | BDRIDP/PRJ/MAT/UN-Rd/07 | Improvement of road from Dhaudkhali UP-Mirukhali UP road by HBB at Ch. 0.00-2925m under Mathbaria Upazila ID No 579583001 Salvage Materials Tk. 344829.00 | 579583001 |  | 2.9 |  |  |  |  | 9241827 | 8317643.958 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 04.10.17 | 14.10.17 | 13.10.17 |  | 100% | 8317000
130 | BDRIDP/PRJ/MAT/UZ-RdR/09 | Rehabilitation of Mathbaria GC-Pirojpur Patharghata RHD road Musulle Bari via Mirukhali Bazar & Vogirathpur Bazar road from Ch. 16260m-20060m under Mathbaria Upazila ID No 579582004 Salvage Materials Tk. 435458.00 | 579582004 |  | 3.8 |  |  |  |  | 24343446.98 | 23812451 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 04.10.17 | 14.10.17 | 13.10.17 |  | 100% | 23800000
131 | BDRIDP/PRJ/ MAT/ CCA-Rd/11 | Improvement of road from Panchayet bari to Sapleza Nali road via Tomezia high school road by BC from Ch.00m-1500m &2350m-2770m. including 01 No U-Drain 7.00m Long at Ch. 2420m. ID No-579584007 | 579584007 |  | 1.9 |  |  |  |  | 12939509.58 | 12292534.5 | M/S. Sher-E-Bangla Traders, Prop. Md. Khalilur R ahman, Mothbaria, Pirojpur | 30.01.19 | 26.02.19 | 26.08.19 |  | 100% | 12288300
132 | BDRIDP/PRJ /MAT/ CCA-Rd/10 | Improvement of road from Safa Boyratala road-Tulatala road via Wahab Jomadder house at Ch.00m-2000m. including 01 No 1.50 x 1.50m RCC Box at Ch. 299.00m & 06 Nos 0.625m x 0.90 U-Drain 7.00m Long. at Ch. 441m530m 960m 1208m 1500m & 1700m. ID No-579585027 | 579585027 |  | 2 |  |  |  |  | 15176632.21 | 14417800.6 | M/S. Selim Enterprise Prop. Md. Azizul Haque Selim Mathbaria, Pirojpur | 25.03.19 | 08.04.19 | 08.10.19 |  | 100% | 14411412
133 | BDRIDP/PRJ/ MAT/ CCA-Rd/09 | Improvement of road from Baromachua Bazar to Khejurbaria UZR via Khejurbaria GPSCycolone Shelter by BC at Ch. 1000.00- 2220.00m. ID No-579584049 | 579584049 |  | 2.22 |  |  |  |  | 8145181.72 | 7737922.634 | M/S. Talukder Enterprise Prop. Md. Harun Talukder Mothbaria, Pirojpur | 27.02.19 | 18.02.19 | 17.08.19 |  | 100% | 7737720 |  |  | Final
|  | Road work Sub-Total = |  | 0 | #VALUE! | 19.85 | 0 | 0 | 2 | 297694045.49 | 282282359.072 | [6 empty] | 281825939
134 | BDRIDP/PRJ/ MAT/CCA-St/01 | Construction of 3 Nos Box Culvert on Mirukhali RHD to Dhaudkhali Nutan hat via Kalibari GPS road at Ch. 75m, 480m & 600m (Srart from Mirukhali Amua RHD to Shahadad Hossain khan house via Dhoudkhali Board GPS cum Cyclone Shelter) | 579584090 | [5 empty] | 7.5 | 2929722 | 2919441.64 | Md. Tohidul Bashar Kabir Mathbaria, Pirojpur | 07.04.14 | 10.04.14 | 15.05.14 |  | 100% | 2819263 |  |  | Final
135 | BDRIDP/PRJ/ MAT/UZR-St/02 | Construction of RCC Box Culverts 4.00x4.00m at ch. 7391m & 1.5mx1.5m at ch. 6756m on Masua R&H road-Mathbaria GC-Safa Amua RHD via Algi Bazar road (ID No: 579582002) | 579582002 | [5 empty] | 4 | 2654776 | 2070307.983 | M/S. Tuhin Enterprise Prop. Md. Liton Paskar Bhandaria, Pirojpur | 14.09.14 | 01.10.14 | 31.03.15 |  | 100% | 2069618 |  |  | Final
136 | BDRIDP/PRJ/ MAT/UZR-St/01 | Construction of 2Nos 1.0mx1.0m Box Culverts on Gulishakhali GC-Dowatala GC via Terkhali Bazar & Kumirmara Bazar road at ch. 3200m & 3320m | 579582006 | [5 empty] | 2 | 11690213 | 11562164.48 | M/S. Laskar Enterprise Prop. Md. Shohel Laskar Mathbaria, Pirojpur | 14.09.14 | 01.10.14 | 31.03.15 |  | 100% | 11562100 |  |  | Final
137 | BDRIDP/PRJ/ MAT/UZR-St/03 | Construction of 12Nos 1.0mx1.0m Box Culverts on Amragachia UP to Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road at ch. 6146m, 6257m, 6306m, 6368m, 6689m, 6895m, 7020m, 7099m, 7415m, 7525m, 7640m & 8030m. | 579583010 | [5 empty] | 12 | 13706925 | 13013663.92 | M/S. Laskar Enterprise Prop. Md. Shohel Laskar Mathbaria, Pirojpur | 14.09.14 | 01.10.14 | 31.03.15 |  | 100% | 13012277 |  |  | Final
138 | BDRIDP/PRJ/ MAT/UZR-St/04 | Construction of 7Nos RCC Box Culvert on 1.0mx1.0m at ch. 2670m, 1.50x1.50m at ch. 2755m, 2994m, 3270m, 3920m & 4.00mx4.00m at ch. 2490m, 3606m Mathbaria GC (Dack Banglo)-Amua GC via Dhaudkhali union Parishad road by BC at ch. 2490-6630m | 579582005 | [5 empty] | 14 | 17221913 | 16092882.578 | ASI-TBK (JV) Kapauriapatti, Mathbaria, Pirojpur. | 14.09.14 | 01.10.14 | 31.03.15 |  | 100% | 16084917 |  |  | Final
139 | BDRIDP/PRJ/ MAT/UZ-St/05 | Construction of 1No 4.00x4.00m (3Vent) RCC Box Culvert; 1No. 4.00mx4.00m (2 Vent) RCC Box Culvert; 1No 1.50mx1.50m RCC Box Culvert & 4Nos 1.00mx1.00m RCC Box Culvert on Mathbaria GC (Dack Bangla)-Amua GC road via Dhaudkhali Union Porishad road at Ch. 6602m, 4780m, 5903m, 4590m, 4680m, 5296m & 5570m | 579582005 | [5 empty] | 10.5 | 18019435 | 18011861.65 | M/S. Simu Enterprise Prop. Mrs. Shamima Akter Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 18009849 |  |  | Final
140 | BDRIDP/PRJ/ MAT/UN-St/01 | Construction of 1No 3.00x3.00m RCC Box Culvert; 4Nos 1.50mx1.50m Box Culvert & 2Nos 1.00mx1.00m Box Culvert on Amragachia Union Parishad-Manikkhali Bazar via Sonakhali Bazar, Tulatalahat road at Ch. 11893m, 8645m, 10866m, 11134m, 11395m, 9810m & 11960m | 579583010 | [5 empty] | 11 | 13152124 | 13151160.37 | M/S. Eashan Enterprise Prop. Md. Salauddin Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 13148197 |  |  | Final
141 | BDRIDP/PRJ/ MAT/UZ-St/06 | Construction of 1No 4.00mx4.00m (3Vent) RCC Box Culvert; 1No 4.50mx4.0m RCC Box Culvert; 1No 2.00mx2.00m RCC Box Culvert & 2Nos 1.00mx1.00m RCC Box Culvert on Masua R&H Mathbaria GC-Safa Amua RHD via Algi hat road at Ch. 8851m, 7906m, 9283m, 8068m & 9636m | 579582002 | [5 empty] | 11 | 17070804 | 17060295.77 | M/S. Simu Enterprise Prop. Mrs. Shamima Akter Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 17056114 |  |  | Final
142 | BDRIDP/PRJ/ MAT/UZ-St/07 | (a) Construction of 3 nos 1.50x1.50m, 1No. 2.00x2.00m, 1No. 3.00x3.00m, 2Nos 4.00x3 2Vent , 1Nos 4.00x4.00m 2Vetn & 1No. 4.50x4.00m RCC Box Culvert on Mothbaria GC-Musulle Bari R&H road via Mirukhali Bazar-Vogirathpur Bazar road at Ch. 16590m, 16836m, 17410m, 16534m, 18926mm, 17823m, 18093m, 2005m, & 17085m (ID No: 579582004) (b) Extension work of Existin 1No. 3.00x3.00m & 1No. 1.50mx1.50m RCC Box Culvert on Mothbaria GC-Musulle Bri R&H road via Mirukhali Bazar-Vogirathpur Bazar road at ch. 16759m & 17329m under Mathbaria Upazila. | 579582004 | [5 empty] | 31.5 | 14296565 | 10864526.34 | M/S. Saifuddin Traders Prop. M.A Wahab Nesarabad, Pirojpur |  | 17.08.15 | 17.08.16 |  | 100% | 10748670 |  |  | Final
143 | BDRIDP/PRJ/ MAT/CCA-St/02 | Construction of 1No 1.50mx1.50m and 8nos 1.00mx1.00m RCC Box Culvert on Tushkhali UNR road-Sotto Masua Wapdha via Mosaraf House road at Ch. 1800m, 280m, 490m, 670m, 1200m, 1340m, 1480m, 1540m & 1700m [ID No: 5795855021] | 5795855021 | [5 empty] | 9.1 | 2475328 | 2455523.37 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 14.07.15 | 21.07.15 | 21.01.16 |  | 100% | 2452991 |  |  | Final
144 | BDRIDP/PRJ/ MAT/CCA-St/03 | Construction of 4Nos 1.50x1.50m RCC Box Culvert on Dhanisafa Launchghat-Safa Bazar road at Ch. 1180m, 1490m, 1700m & 1800m [ ID No: 579584006] | 579584006 | [5 empty] | 9 | 11559723 | 11534767.43 | M/S. H.S Engineers Prop. Md. Nurul Haq Machimpur, Pirojpur | 14.07.15 | 21.07.15 | 21.01.16 |  | 100% | 11533595 |  |  | Final
145 | BDRIDP/PRJ/ MAT/UZ-St/08 | Construction of 22.00m Long RCC Girder Bridge on Mathbaria GC-Musulle Bari R&H road via Mirukhali Bazar & Vogirathpur Bazar road at ch. 17705m | 579582004 | [5 empty] | 22 | 15041239 | 12985794.646 | M/S. Gazi Construction Prop. Md. Ziaul Ahasan Gazi Badura Parerhat road, Pirojpur | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 12967732 |  |  | Final
146 | BDRIDP/PRJ/ MAT/CCA-St/04 | Construction of 2nos 4.00x4.00m RCC Box Culvert on Sonakhali Collage UZR-Sonakhali Manikkhali Road at ch. 1297m & 1350m. | 579584042 | [5 empty] | 8 | 3496353 | 2651000.676 | M/S. Saifuddin Traders Prop. M.A Wahab Nesarabad, Pirojpur | 19.10.15 | 26.10.15 | 26.04.16 |  | 100% | 2648651 |  |  | Final
147 | BDRIDP/PRJ/ MAT/UN-St/02 | Construction of 4Nos 1.00x1.00m RCC Box Culvert on Amragachia Union parisad-Manikkhali Bazar via Sonakhali Bazar & Tulatala Bazar road at ch. 12390m, 12750m, 13120m & 13350m. | 579583010 | [5 empty] | 4 | 986847 | 722029.525 | M/S. Sakil Enterprise Prop. Md. Shahin Jamaddar Mathbaria, Pirojpur | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 716374 |  |  | Final
148 | BDRIDP/PRJ/ MAT/CCA-St/05 | Construction of 2Nos U-Drain & 1No 3.00x3.00m RCC Box Culvert on Gulishakhali Bazar road Uttar Sonakhali Chan Miah house via Talukder Bri road at ch. 2030m, 2532m & 1940m. | 579584103 | [5 empty] | 4 | 11200643 | 1882805.727 | M/S. Sakil Enterprise Prop. Md. Shahin Jamaddar Mathbaria, Pirojpur | 19.10.15 | 26.10.15 | 26.10.16 |  | 100% | 1881616 |  |  | Final
149 | BDRIDP/PRJ/ MAT/UZ-St/09 | Construction of 2.00x2.00m Box Culvert & 30.00m Long RCC Slab Bridge on Mathbaria GC-Masulle Bari R&H road via Mirukhali Bazar Vogirathpur Bazar at Ch. 15775m & 16175m. | 579582004 | [5 empty] | 32 | 23197041 | 23189962.907 | M/S. Rahima Enterprise Prop. Abu Hanif Khan Mathbaria, Pirojpur | 19.11.15 | 26.11.15 | 30.11.16 |  | 100% | 23188185 |  |  | Final
150 | BDRIDP/PRJ/MAT/UZ-St/10 | Construction of 6nos 1.50mx1.50m RCC Box Culvert & 1No. U-Drain on Gulishakhali GC-Dhawatala GC Kumirmara Bazar via Tearkhali Bazar at Ch. 3792m 4428m 4720m 5040m 5165m 5325m & 5945m ID No 579582006 | 579582006 | [5 empty] | 9 | 2977223 | 2679500.7 | M/S. Abir & Brothers Prop. Salma Rahman Amlapara, Pirojpur | 18.04.17 | 28.04.17 | 27.10.17 |  | 100% | 2650000 |  |  | Final
151 | BDRIDP/PRJ/MAT/UN-St/03 | Construction of 2Nos.3.00mx3.00m & 5 Nos.1.50mx1.50m RCC Box Culvert on Dhaudkhali UP-Mirukhali UP road at Ch. 505m 850m 913m 1445m 1954m 2812m & 2920m | 579583001 | [5 empty] | 14 | 3933042 | 3539738.493 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur | 04.10.17 | 14.10.17 | 14.08.18 |  | 100% | 3539700 |  |  | Final
152 | BDRIDP/PRJ/ MAT/CCA-St/06 | Construction of 2-Vent 6.00m x6.00m RCC Box Culvert on North side of Daudkhali Board GPS on Mirukhali Amur R&H -Daudkhali Natun Hat via Kalibari GPS road at Ch.0480km Id No-579584090 | 579584090 | [5 empty] | 6 | 5852247.48 | 5267022.732 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 06.05.18 | 15.05.18 | 15.11.18 |  | 100% | 5267000 |  |  | Final
|  | Structusre work Sub-Total = |  | 0 | 0 | 0 | 0 | 0 | 220.6 | 191462163.48 | 171654450.937 | [6 empty] | 171356849
|  | Upazila Total = |  | 42.284 | #VALUE! | 19.85 | 0 | 0 | 222.6 | 508623764.97 | 473477260.009 | [6 empty] | 472097136
Upazila : Bhandaria
153 | BDRIDP/PRJ/ BAN/CCA-Ew/01 | Improvement of Bhitabaria Board GPS Connecting (Improvement of Kapalirhat GC-Board School-Chinguria Bazar-Nadmulla R&H from ch. 00-700m) road by Earth work | 579144012 | 0.7 | [5 empty] | 382409 | 382409 | Md. Kalam Khalifa | 02.03.15 | 09.03.15 | 09.07.15 |  | 100% | 372765 |  |  | Final
154 | BDRIDP/PRJ/ BAN/CCA-Ew/02 | Improvement of Bhitabaria Board GPS Connecting (Improvement of Kapalirhat GC-Board School-Chinguria Bazar-Nadmulla R&H from ch.700-1350m) road by Earth work | 579144012 | 0.65 | [5 empty] | 362859 | 362859 | Md. Shujan Sharif | 02.03.15 | 09.03.15 | 09.07.15 |  | 100% | 350908 |  |  | Final
155 | BDRIDP/PRJ/ BAN/CCA-Ew/03 | Improvement of GC Bhandaria Ghat to Telikhali (Improvement of Nadmullah UP-Nadmullah Madrasha Hat via Chinguria and Collony Bazar road) by Earth Work at ch. 1200-2200m. | 579143010 | 1 | [5 empty] | 373621 | 373621 | Md. Salam Howlader | 15.02.15 | 22.02.15 | 24.06.15 |  | 100% | 224550
156 | BDRIDP/PRJ/ BAN/UZ-Ew/01 | Improvement of From Telikhali GC-Tushkhali GC in/c Harinpala-Kotcha Connecting Approach road by Earth work from Ch. 12000m-13200m | 579142005 | 1.32 | [5 empty] | 417710 | 417710 | Fatima | 12.02.15 | 19.02.15 | 19.08.15 |  | 100% | 417710 |  |  | Final
157 | BDRIDP/PRJ/ BAN/UZ-Ew/01 | Improvement of From Telikhali GC-Tushkhali GC in/c Harinpala-Kotcha Connecting Approach road by Earth work from Ch. 13200m-14400m | 579142005 | 1.2 | [5 empty] | 460575 | 460575 | Zahangir | 12.02.15 | 19.02.15 | 19.08.15 |  | 100% | 460575 |  |  | Final
158 | BDRIDP/PRJ/ BAN/UN-Ew/03 | Improvement of road from Telikhali UP Complex-Junia Community Pry. School-Serajuddin Market-Abason-Harinpala Lanchghat -Tushkhali GC road By Earth work from Ch. 3300-4600m | 579143017 | 1.3 | [5 empty] | 432360 | 432360 | Md. Nasir | 01.02.15 | 07.02.15 | 07.08.15 |  | 100% | 311202
159 | BDRIDP/PRJ/ BAN/UN-Ew/03 | Improvement of road from Telikhali UP Complex-Junia Community Pry. School-Serajuddin Market-Abason-Harinpala Lanchghat -Tushkhali GC road By Earth work from Ch. 4600-6000m | 579143017 | 1.4 | [5 empty] | 463568 | 463568 | Zahirul | 01.02.15 | 07.02.15 | 07.08.15 |  | 100% | 455125
160 | BDRIDP/PRJ/ BAN/UN-Ew-01 | Recsectioning of Road by Earth work on Nadmullah to Dhawa UP Office via Nadmullah High School at Ch. 00-1200m | 579143011 | 1.2 | [5 empty] | 458779 | 458779 | Md. Razzak | 17.02.15 | 24.02.15 | 24.08.15 |  | 100% | 447705 |  |  | Final
161 | BDRIDP/PRJ/ BAN/UN-Ew-01 | Recsectioning of Road by Earth work on Nadmullah to Dhawa UP Office via Nadmullah High School at Ch.1200-2100m | 579143011 | 0.9 | [5 empty] | 369284 | 369284 | Md. Shahabuddin | 17.02.15 | 24.02.15 | 24.08.15 |  | 100% | 345188 |  |  | Final
162 | BDRIDP/PRJ/ BAN/UN-Ew-01 | Recsectioning of Road by Earth work on Nadmullah to Dhawa UP Office via Nadmullah High School at Ch.2100-3500m | 579143011 | 1.4 | [5 empty] | 395095 | 395095 | Md. Shahidul Alam Swapon | 17.02.15 | 24.02.15 | 24.08.15 |  | 100% | 365087 |  |  | Final
163 | BDRIDP/PRJ/ BAN/CCA-Ew-03 | Improvement of road from Batagi Shingkhali GPS (Moidda Atorkhali UZR-Banai Bhagiratpur UZR via Ponchaet Bari River Bazar) road By BC from Ch. 00-1000m | 579144079 | 1 | [5 empty] | 373980 | 373980 | Md. Kabir Farazi |  |  |  |  | 100% | 214420
164 | BDRIDP/PRJ/ BAN/CCA-Ew-06 | Improvement of road from Dhawa Poddarkhal to Dhawa Bazar (Aysha Siddika Madhamik Balika Biddalaya) via Dhawa Health Sub-Center road by Earth work form Ch. 1850-2600m | 579144058 | 0.85 | [5 empty] | 384620 | 384620 | Md. Habibur Rahman | 03.03.15 | 10.03.15 | 10.06.15 |  | 100% | 371157 |  |  | Final
165 | BDRIDP/PRJ/ BAN/CCA-Ew-04 | Improvement of road from Dhakhin Ikree GPS (Charkhali-Mathbaria RHD road to H/O Moti Talukder via Miraj Hawlader Bari by e road by Earth work form Ch. 1500-2300m | 579144112 | 0.8 | [5 empty] | 371488 | 371488 | Juyal Akon |  |  |  |  | 100% | 346312 |  |  | Final
166 | BDRIDP/PRJ/ BAN/CCA-Ew-04 | Improvement of road from Dhakhin Ikree GPS (Charkhali-Mathbaria RHD road to H/O Moti Talukder via Miraj Hawlader Bari by e road by Earth work form Ch. 2300-3000m | 579144112 | 0.7 | [5 empty] | 331745 | 331745 | Giash Uddin |  |  |  |  | 100% | 311447 |  |  | Final
167 | BDRIDP/PRJ/ BAN/UN-Ew-01 | Improvement of road from Ikree UP-Bagirothpur Bazar road by Earth filling work from Ch. 1000-1850m. | 579143006 | 0.85 | [5 empty] | 351245 | 351245 | Sultan Kazi | 15.04.15 | 22.04.15 | 22.07.15 |  | 100% | 330113 |  |  | Final
168 | BDRIDP/PRJ/ BAN/UN-Ew-01 | Improvement of road from Ikree UP-Bagirothpur Bazar road by Earth filling work from Ch. 1850-2586m. | 579143006 | 0.736 | [5 empty] | 497353 | 497353 | Monirul Islam | 15.04.15 | 22.04.15 | 22.07.15 |  | 100% | 430113 |  |  | Final
169 | BDRIDP/PRJ/ BAN/CCA-Ew/03 | Improvement of road from North Bhitabaria R&H-Kapalirhat GC via Enaytkhar hat, Sarder hat (Mohshinar Chow Rasta-H/O Hamid Howlader & Jomaddar Bari) road By Earth work from Ch. 00-900m. | 579144040 | 0.9 | [5 empty] | 349911 | 349911 | Md. Shahiduzzaman | 02.03.15 | 09.03.15 | 09.09.15 |  | 100% | 339855 |  |  | Final
170 | BDRIDP/PRJ/ BAN/CCA-Ew/03 | Improvement of road from North Bhitabaria R&H-Kapalirhat GC via Enaytkhar hat, Sarder hat (Mohshinar Chow Rasta-H/O Hamid Howlader & Jomaddar Bari) road By Earth work from Ch. 900-1800m. | 579144040 | 0.9 | [5 empty] | 420551 | 420551 | Md. Abul Kasem | 02.03.15 | 09.03.15 | 09.09.15 |  | 100% | 394439 |  |  | Final
|  | Earth work Sub-Total = |  | 17.806 | 0 | 0 | 0 | 0 | 0 | 7197153 | 7197153 | [6 empty] | 6488671
171 | BDRIDP/PRJ/ BAN/UN-Rd/03 | Improvement of GC Bhandaria Ghat to Telikhali (Improvement of Nadmullah UP-Nadmullah Madrasha Hat via Chinguria and Collony Bazar road) by BC from ch. 1200-2200m. | 579144010 |  | 1 |  |  |  |  | 24582044 | 25436892.5 | M/S. Rezvi Enterprise Prop. Md. Rezaul Haq Bhandaria, Pirojpur. | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 25436892 |  |  | Final
172 | BDRIDP/PRJ/ BAN/UZ-Rd (R)/01 | Rehabilitation of Telikhali GC-Tushkhali GC road (With Horinpala Cotcha Connected) road by BC. | 579142005 | [6 empty] | 1768606 | 1917705.36 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Piropur | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 1917705 |  |  | Final
173 | BDRIDP/PRJ/ BAN/CCA-Rd/01 | Improvement of Bhitabaria Board GPS connecting (Improvement of Kapalirhat GC-Board School-Chinguria Bazar-Nadmulla R&H from ch. 700-1350m) road by BC | 579144012 |  | 0.65 |  |  |  |  | 18658054 | 18317077.5 | M/S. Mallik Enterprise Prop. Md. Anwar Mallik Mathbaria, Pirojpur | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 18298250 |  |  | Final
174 | BDRIDP/PRJ/ BAN/UN-Rd (R)/01 | Rehabilitation of road by Flexible pavement from Nadmullahat to Dhawa UP Office via Nadmullah High School at ch. 0.00-3500m. | 579143011 |  | 3.5 |  |  |  |  | 25449029 | 28456079.42 | M/S. Esili Enterprise Prop. Md. Faizur Rashid Bhandaria, Pirojpur. | 10.01.15 | 17.01.15 | 17.07.15 |  | 100% | 28454879 |  |  | Final
175 | BDRIDP/PRJ/ BAN/UN-Rd-02 | Improvement of road by BC Paved from Ikree UP Bagirothpur Bazar road ch. 1000m-2600m. | 579143006 |  | 2.6 |  |  |  |  | 18238595 | 19873203.4 | M/S. Lemon Enterprise Prop. Md. Nasiruddin Dulal Bhandaria, Pirojpur | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 19873203 |  |  | Final
176 | BDRIDP/PRJ/ BAN/GC/01 | a) Rehabilitation of Rice Shed (b) Construction of Toilet & Urinal Shed with Other's Facilities © Construction of Internal RCC Paved Road (d) Improvement of Truck Bay in Loading and Unloading Place (e) Construction of Internal RCC Drain With Footpath. | [7 empty] | 20661745.83 | 24680718.83 | M/S. Oishi Construction Prop. Sabina Yeasmin Mathbaria, Pirojpur | 10.01.15 | 17.01.15 | 16.01.16 |  | 100% | 24679925
177 | BDRIDP/PRJ/BAN/UZ-Rd(R)/02 | a) Rehabilitation of road from Bhandaria Bandar Bazer Bhubaneshwar Bridge to Bhandaria Colage R&D Junction via Sadar Union Parishad, Post Office, Govt. Girls School, Bhandaria Govt. Collage and Upazila Parishad at ch. 00-1100m. (b) Construction of RCC Drain with Footparth different ch. (Two side) of the Road at from Bhandaria Bandar Bazar Bhubaneshwar Bridge to Bhandaria Collage R&D Junction via Sadar Union Parishad, Post Office Govt. Girls School-Bhandaria Govt. Collage and Upazila Parishad at ch. 00-1100m. | 579142017 |  | 1.1 |  |  |  |  | 30546987.69 | 36314839.77 | M/S. Eashan Enterprise Prop. Md. Salauddin Bhandaria, Pirojpur | 10.01.15 | 17.01.15 | 16.01.16 |  | 100% | 36312529 |  |  | final
178 | BDRIDP/PRJ/BAN/ UZ-Rd(R)/03 | (a) Rehabilitation of road from Bhandaria Bandar Bazer Bhubaneshwar Bridge to Bhandaria Colage R&D Junction via Sadar Union Parishad, Post Office, Govt. Girls School, Bhandaria Govt. Collage and Upazila Parishad at ch. 1100-1650m. (b) Construction of RCC Drain with Footparth different ch. (Two side) of the Road at from Bhandaria Bandar Bazar Bhubaneshwar Bridge to Bhandaria Collage R&D Junction via Sadar Union Parishad, Post Office Govt. Girls School-Bhandaria Govt. Collage and Upazila Parishad at ch. 1100-1650m. | 579142017 |  | 0.55 |  |  |  |  | 15191360.69 | 18122680.39 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Pirojpur | 10.01.15 | 17.01.15 | 17.11.15 |  | 100% | 18119197 |  |  | final
179 | BDRIDP/PRJ/ BAN/UZ-Rd(R)/04 | Rehabilitation of road from Widening (Both Side) Telikhali GC-Tushkhali GC in/c Harinpala-Kotcha Connecting Approach road by HBB from Ch. 12000-14400m | 579142005 |  | 2.4 |  |  |  |  | 14442850 | 14441024 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 14441000 |  |  | Final
180 | BDRIDP/PRJ/ BAN/UN-Rd/04 | Improvement of road from (Both Side Widenign) Telikhali UP-Complex-Junia Community Pry. School-Serajuddin Market-Abason-Harinpala Launchghat-Tushkhali GC road by HBB from Ch. 3300-6000m. | 579143017 |  | 2.7 |  |  |  |  | 16912813 | 16909580 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 16909580 |  |  | Final
181 | BDRIDP/PRJ/ BAN/CCA-Rd(R)/02 | Rehabilitation of road from North Bhitabaria R&H to Kapalirhat GC via Enaytkhar hat, Sarder hat (Mohshinar Chow Rasta-H/O Hamid Howlader & Jomaddar Bari) road by BC from Ch. 00-1800m under Bhandaria Upazila. [ID No: 579144040] | 579144040 |  | 1.8 |  |  |  |  | 19543326 | 19535000 | M/S. Upokar Enterprise Prop. Md. Shahin Talukder Khamkata, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 19534896 |  |  | Final
182 | BDRIDP/PRJ/ BAN/CCA-Rd(R)/03 | Improvement of road from Batagi Shingkhali GPS (Moidda Atorkhali UZR-Banai Bhagiratpur UZR via Ponchaet Bari River Bazar) road By BC from Ch. 00-1000m under Bhandaria Upazila. [ID No: 579144079]. | 579144079 |  | 1 |  |  |  |  | 14002964 | 13990000 | M/S. Simu Enterprise Prop. Mrs. Shamima Akter Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 13988246 |  |  | Final
183 | BDRIDP/PRJ/ BAN/CCA-Rd(R)/04 | Improvement of road from Dhakkhin Ikree GPS (Charkhali-Mathbaria RHD road to H/O Moti Talukder via Miraj Hawlader Bari) road By BC from Ch. 1500-3000m under Bhandaria Upazila. [ID No: 579144112] . | 579144112 |  | 1.5 |  |  |  |  | 16380827 | 16375000 | M/S. Eashan Enterprise Prop. Md. Salauddin Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 16374450 |  |  | Final
184 | BDRIDP/PRJ/ BAN/CCA-Rd/05 | Improvement of roaf from Dhawa Poddar Khal to Dhawa Bazar (Aysha Siddika Madhamik Balika Biddalaya) via Dhawa Helath Sub-Center road by BC Ch. 1850-2600m ( | 579144058 |  | 0.65 |  |  |  |  | 12910372 | 12908960.435 | M/S. Silpi Enterprise Prop. Md. Sakil Howlader Machimpur, Pirojpur |  | 26.05.15 | 25.11.15 |  | 100% | 12908960 |  |  | Final
185 | BDRIDP/PRJ/BAN/UN-Rd/05 | A Improvement of road from Telikhali UP Complex-South Junia Noyarhat-Tuskhali GC road by BC at Ch 1000.00m-3000.00m. including 01 No 2.00mX2.00m RCC Box Culvert at Ch.1200.00m. ID No-579143015 B Improvement of road from Madarshi Bazar RHD-Telikhali GC road by BC atCh. 0.00m-1000.00m. including 01 No 2.00mX2.00m RCC Box Culvert atCh.885.00m. ID No-579143009 Clmprovement of road from Dhawa UP-Bothla Bazar via Binapani Bazarroad by BC from Ch. 0.00-600m. including 02 Nos 2.00mX2.00m & 1 No2- vent 4.00mX3.60m RCC Box Culvert at Ch.100.00300.00 & 600.00m. ID No-579143005 Salvage Cost 1983248.00 | 579143015 579143005 | [6 empty] | 29251896.32 | 24865163.428 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 24862147
186 | BDRIDP/PRJ/BAN/CCA-Rd/17 | A Improvement of road from Bhitabaria Ershad Bridge-11 No. GPS Golpatarhat road by BC from Ch. 1820m-2600m. 1 No 2.00mX2.00m RCC Box Culvert at Ch.2500.00m. ID No-579144017B Improvement of road from Nadmulla UP-Qashemia Madrasha-Dhawa Bazar via -Dhawa RNGPS road by BC from Ch. 2500-2950m. including 02 Nos 2.00mX2.00m & 1 No 2- vent 4.00mX3.60m RCC Box Culvert at Ch.2608.002758.00 & 2508.00m.ID No-579144088 C Improvement of road from Charkhali-Mothbaria RHD road to 44no. Modhy Bothla GPS via H/Q Md. Humaun Kabir road by BC from Ch. 0.00-750m.including 01 No 1.30mx1.30m & 02 Nos 2.00mX2.00m RCC Box Culvert at Ch.426.00337.00 &580.00m. ID No-579144109 Salvage Cost 1775930.00 | 579144017 579144088 579144109 | [6 empty] | 21873013.81 | 19248448.037 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 19245635
187 | BDRIDP/PRJ/BAN/CCA-Rd/15 | Improvement of road from West Goulbunia Dholu Talukder Bari- Hindupara Reg.Pry. School-Shafa- Telikhali UZR road by BC at Ch. 0.00-3000.00m. including 02 Nos 2.00mX2.00m. RCC Box Culvert at Ch. 10.00m & 1505.00m ID No-579144153 | 579144153 | [6 empty] | 22294074.23 | 19288244.069 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 19286658
188 | BDRIDP/PRJ/ BAN/CCA-Rd/11 | A Improvement of road from Goulbunia Talukder Bari Bridge-Charghata Bari Debipur RHD road by BC at Ch. 0.00m-3000.00m including 02 Nos 2.00mx2.00m RCC Box Culvert at Ch. 10.00m & 1505.00m ID No 579144145 B Improvement of road from Junia Korashia Khal Bridge-Fajlu Jamadder bari-Hashem Khan Bari-30 No-Junia Board Govt. Pry. School road by BC at Ch. 0.00-1000m ID No 579144142 | 579144145 579144142 | [6 empty] | 29307659.17 | 27695125.848 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 27692768
189 | BDRIDP/PRJ/ BAN/CCA-Rd/14 | A Improvement of road from Horinpala UZR -Harinpala UZR via Barek Boyatee road by BC at Ch. 0.00m-2000.00m including 02 Nos 2.00mx2.00m RCC Box Culvert at Ch. 830m & 1055m ID No 579145054 B Improvement of road from Bhandaria-Charkhali RHD road to West Nodmulla RNGPS via Charkhali Jomadder Bari road by BC at Ch. 0.00m-1000.00m including 05 Nos 1.30mx1.30m & 01 Nos 2.00mx2.00m RCC Box Culvert at Ch. 46m 172m 447m 561m 970m & 485m ID No 579144097 Salvage Cost. Tk. 2159427.00 | 579145054 579144097 | [6 empty] | 25770000 | 24412665.796 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 24407457
190 | BDRIDP/PRJ/BAN/CCA-Rd/13 | A Improvement of road from Telikhali UP Complex-Huzzat Ali Bazar road by BC at Ch. 0.00m-2000m ID No 579144087 B Improvement of road from Telikhali Bazar-Ikree Bazar via 42No GPS road by BC at Ch. 0.00m-1500.00m. including 03 Nos 2.00x2.00m RCC Box Culvert at Ch. 250.00m 900.00m & 1200.00. ID No-579144078 Salvage Cost-TK.1410681.00 | 579144087 579144078 | [6 empty] | 25820000 | 24528007.779 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 24528000
191 | BDRIDP/PRJ/BAN/CCA-Rd/16 | A Improvement of road from Horinpala RHD road-Serajuddin Market road by BC at Ch. 0.00m-2000.00m. ID No-579144068 B Improvement of road from Telikhali UP Complex-Uttar Junia Bazar via Shahajan Member House road by BC at Ch. 0.00-2000.00m. ID No-579144069 C Improvement of road from Jalals Shop of R1/3-House of Rashid Mridha road by BC at Ch. 0.00-1800.00m. including 02 Nos 2.00mX2.00m& 01 No 2-vent 4.00mX3.60m RCC Box Culvert at Ch. 320.00m1200.00m& 120.00m. ID No-579144009 Salvage Cost 976625.00 | 579144068 579144069 579144009 | [6 empty] | 22086973.9 | 20760749.405 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 20756794
192 | BDRIDP/PRJ/BAN/CCA-Rd/06 | A Improvement of road from Junia Noyerhat to Md. Anshar Khan house road by BC at Ch. 0.00-2000m. including 02 Nos 2.00x2.00m RCC Box Culvert at Ch. 480.00m & 850m ID No 579144105 B Improvement of road from Telikhali Safa road to Md. Ali House via Panchaet Bari road by BC at Ch. 0.00-2000m . including 02 Nos 2.00x2.00m RCC Box Culvert at Ch. 400m & 1836m ID No 579145042 Salvage Tk. 1669209.00 | 579144105 579145042 | [6 empty] | 29970000 | 26675549.749 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 26672988
193 | BDRIDP/PRJ/BAN/CCA-Rd/10 | Improvement of road from Huzzat Ali Hat-Telikhali Embanment road by BC at Ch. 0.00-3500m . including 05 Nos 2.00x2.00m RCC Box Culvert at Ch. 100m 330m 800m 2125m & 3380.00m ID No 579144041 Salvage Tk. 1291315.00 | 579144041 | [6 empty] | 27330000 | 24427031.865 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 24423989
194 | BDRIDP/PRJ/BAN/CCA-Rd/09 | A Improvement of road from Bhandaria-Charkhali RHD road to Mostofa Sharif bari via Abdul Sattar shops Road by BC at Ch. 0.00m-1130m . including 04 Nos 2.00mx2.00m RCC Box Culvert at Ch. 355.00m 457m 956m & 1070m ID No 579144101 B Improvement of road from Telikhali A. Satter Rari Bari to Koncha River Embankment road by BC at Ch. 0.00m-1500m. including 03 Nos 2.00x2.00m RCC Box Culvert at Ch. 380m 900m & 1450m ID No 579145078 C Improvement of road from Rajpasha Sadnarhat-Posharibunia Aziz Khan Bari by BC at Ch. 0.00-800m. including 04 Nos 2.00x2.00m RCC Box Culvert at Ch. 280m 375m 550m & 622m ID No 579144074 Salvage Tk. 3300525.00 | 579144101 579145078 579144074 | [6 empty] | 29800000 | 25500244.587 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 25500000
195 | BDRIDP/PRJ/BAN/CCA-Rd/12 | A Improvement of road from Goulbunia-Gera Vanga Khal Bridge-Azahar Chowkeder Bari-Pona River road by BC at Ch. 0.00-2500m including 02 Nos 2.00x2.00m RCC Box Culvert at Ch. 10.00m & 1255m ID No 579144152 B Improvement of road from Bhandaria-Charkhali RHD rod to Coloni Bazar via Dhawa Boader road by BC at Ch. 1105m-1800m. including 01 Noi 4.00x4.00m RCC Box Culvert at Ch. 1642.00m ID No 579144100 | 579144152 579144100 | [6 empty] | 26705000 | 23803725.001 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 23801693
196 | BDRIDP/PRJ/BAN/CCA-Rd/08 | Improvement- of road from Telikhali-Tushkhali UZR Kazirkanda 31 No GPS-Horinpala Abason road by BC at Ch. 1500-5000m including 02 Nos 2.00x2.00m RCC Box Culvert at Ch. 2400m & 4950m ID No 579144086 | 579144086 | [6 empty] | 24713092.54 | 21994224.054 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 21990132
197 | BDRIDP/PRJ/BAN/CCA-Rd/07 | A Improvemen tof road from Telikhali Safa UZR road to Md. Emadul Hoque house via Huzzat Ali Bazar road by BC at Ch. 0.00-2000m ID No 579144102 B Improvement of road from Horinpala UZR Mal bari-Mohabbat Ali Bari UZR road by BC at Ch. 0.00-2000m . including 02 Nos 2.00x2.00m RCC Box Culvert at Ch. 10m & 1005m ID No 579144161 | 579144102 579144161 | [6 empty] | 29278833.42 | 26277679.61 | EFTE.ETCL(PVT.) LIMITED MANAGING DIRECTOR MD. MERAZUL ISLAM BHANDARIA, PIROJPUR | 12.05.19 | 19.05.19 | 19.12.19 |  | 100% | 26275482
|  | Improvement of road from Dhawa UP-Bothla Bazar via Binapani Bazar Road by BC at Ch. 3800-5800m under Upazila-Bhandaria [Road ID: 579143005] | 579143005 |  | 2 |  |  |  |  | 17501668 | 15751501.2
|  | Improvement of road from Junia Korashia khal Bridge-Fajlu Jamadder Bari-Hashem Khan Bari-30No Junia Board Govt. Pry School road by BC at Ch. 1000m-2000m under Upazila-Bhandaria [Road ID: 579144142] | 579144142 |  | 1 |  |  |  |  | 9614651 | 8653185.9
|  | Rehabilitation of road from Telikhali UP Complex-Uttar Junai Bazar via Shahajan Member House by BC at Ch. 2000-4500m under Upazila-Bhandaria [Road ID: 579144069] | 579144069 |  | 2.5 |  |  |  |  | 12712178 | 11440960.2
|  | Improvement of road from Nadmulla UP-Qashemia Madrasha-Dhawa Bazar via C-Dhawa RNGPS road by BC at Ch. 1000m-2500m under Dhawa Union, Upazila-Bhandaria [Road ID: 579144088] | 579144088 |  | 1.5 |  |  |  |  | 15462245 | 13916020.5
|  | Improvement of road from Telikhali Safa Road-MD. Ali house via Panchaet Bari by BC at Ch. 2000-3000m (Including small Structure) under Bhandaria Upazila [Road ID: 579145042] | 579145042 |  | 1 |  |  |  |  | 16689737 | 15020763.3
|  | Road work Sub-Total = |  | 0 | 19.45 | 0 | 0 | 0 | 0 | 665470596.6 | 641538051.933 | [6 empty] | 576693455
198 | BDRIDP/PRJ/ BAN/CCA-St/01 | Construction of 1no 3Vent 4.00x4.00x7.32m and 2nos 2.00x2.00x7.01m RCC Box Culvert on Bhitabaria Board GPS Connecting (Kapalirhat GC-Board School-Chinguria Bazar-Nadmulla R&H) at ch. 0.00m, 1220m & 1300m. | 579144012 | [5 empty] | 6 | 15197108 | 16184943.37 | M/S. Rumi Enterprise Prop. Md. Khalilur Rahman Block-C, Banani, Dhaka. | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 16100000 |  |  | Final
199 | BDRIDP/PRJ/ BAN/CCA-St/02 | Construction of 3nos 2.00x2.00x5.50m RCC Box Culvert on Improvement of GC Bhandaria Ghat to Telikhali (Nadmullah UP-Nadmullah Madrasha Hat via Chinguria and Collony Bazar road) at ch. 1230m, 1600m & 1900m. | 579144010 | [5 empty] | 6 | 1831917 | 2167539.7 | M/S. Tuhin Enterprise Prop. Md. Liton Paskar Bhandaria, Pirojpur | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 2153050 |  |  | Final
200 | BDRIDP/PRJ/ BAN/UNR-St/01 | Construction of 02Nos 4.00x4.00x3.66m size Double Vent RCC Box Culvert on Ikree UP- Bagirothpur Bazar Road at ch. 880m & 2300m, 03Nos 2.00x2.00x6.10m RCC Box Culvert at ch. 1060m, 1250m & 2475m & 02Nos 1.30x1.30x5.01m RCC Box Culvert at ch. 2050m & 2100m. | 579143006 | [5 empty] | 16.3 | 6734469 | 17906814.02 | M/S. H.M Faisal Enterprise Prop. Md. Khalilur Rahman Bhandaria, Pirojpur | 28.12.14 | 04.01.15 | 04.07.15 | 0 | 100% | 17834088 |  |  | Final
201 | BDRIDP/PRJ/ BAN/UZ-St/01 | Construction of 36.00m Long RCC Girder Bridge on Bhandaria-Telikhali GC road at Ch. 1400m. | 579142001 | [5 empty] | 36 | 23201687 | 23195879.26 | M/S. Telikhali Construction Prop. Md. Samsuddin Bhandaria, Pirojpur |  | 05.04.15 | 05.02.16 |  | 100% | 23191872 |  |  | Final
202 | BDRIDP/PRJ/ BAN/CCA-St/02 | Construction of 3Nos 2.00x2.00m RCC Box Culvert & 06Nos 1.30mx1.30m RCC Box Culvert on North Bhitabaria R&H to Kapalirhat GC via Enaytkhar Hat, Sarder hat (Mohshinar Chow Rasta-H/O. Hamid Howlader & Jomaddar Bari) road at ch. 480m, 1078m, 1655m, 410m, 450m, 522m, 742m, 1450m & 1795m under Bhandaria Upazila. [ID No: 579144040] | 579144040 | [5 empty] | 13.8 | 3246262 | 3235000 | M/S. Upokar Enterprise Prop. Md. Shahin Talukder Khamkata, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 3227781 |  |  | Final
203 | BDRIDP/PRJ/ BAN/CCA-St/03 | Construction of 1No 1.30x1.30m & 1No 4.00x4.00m (2Vent RCC Box Culvert on Batagi Shingkhali GPS (Modda Atorkhali UZR-Banai Bhagirathpur UZR via Ponchaet Bari River Bazar) Road at Ch. 630m & 1000m. [ID No: 579144079] | 579144079 | [5 empty] | 5.3 | 12516623 | 12512000 | M/S. Efte Enterprise Prop. Md. Merazul Islam Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 12510065 |  |  | Final
204 | BDRIDP/PRJ/ BAN/CCA-St/04 | Construction of 1No 4.00x4.00m (3Vent) & 1No 1.30x1.30m RCC Box Culvert on Dhakhhin Ikree GPS (Charkhali-Mathbaria RHD road to H/O Moti Talukder via Miraj Hawlader Bari) road at ch. 2450m & 1730m under Bhandaria Upazila [ID No: 579144112]. . | 579144112 | [5 empty] | 5.3 | 13074010 | 13070000 | M/S. Simu Enterprise Prop. Mrs. Shamima Akter Bhandaria, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 13069238 |  |  | Final
205 | BDRIDP/PRJ/ BAN/CCA-St/05 | Construction of 01No. 1.30x1.30; 01 No. 2.00x2.00m RCC Bo xCulvert on Dhawa Poddar Khal to Dhawa Bazar (Aysha Siddika Madhamik Balika Biddalaya) via Dhawa Health Sub-Center road at ch. 1880m & 2290m | 579144058 | [5 empty] | 3.3 | 703270 | 557125.51 | M/S. Fahim Enterprise Prop. Md. Saiful Islam Rajapur, Jhalakati. |  | 26.05.15 | 27.09.15 |  | 100% | 553160 |  |  | Final
206 | BDRIDP/PRJ/ BAN/Ghat/01 | Construction of a Ghat Beside Poona river near Horinpala 2nos GPS cum Cyclone Center. | 579142005 | [6 empty] | 12731286 | 13265571.49 | M/S. Eashan Enterprise Prop. Md. Salauddin Bhandaria, Pirojpur | 28.12.14 | 04.01.15 | 04.07.15 |  | 100% | 13265571 |  |  | Final
207 | BDRIDP/PRJ/BAN/UZ-ST/02. | Construction of 39.06m RCC Girder Bridge on Telikhali GC-Tushkhali GC road with Horinpala Kotcha Connected Ch.2250m. ID No-579142005 | 579142005 | [5 empty] | 39.06 | 35360213 | 31824192.24 | PMPL-KSA-LA (JV), C/O: Tajwar Trade Systems Ltd. Akram Tower (4thl floor), Room No: 504, 199 Shahid Sayed Nazrul Islam Sawrani, Bijoynagar, Dhaka-1000 | 24.09.17 | 14.10.17 | 13.10.18 |  | 100% | 31798251
208 | BDRIDP/PRJ/BAN/UZ-St/03. | Construction of 54.06m RCC Girder Bridge on Telikhali GC-Tushkhali GC road with Horinpala Kotcha Connected Ch.5000m. ID NO-579142005 | 579142005 | [5 empty] | 54.06 | 40953933.65 | 36858540.285 | PMPL-KSA-LA (JV), C/O: Tajwar Trade Systems Ltd. Akram Tower (4thl floor), Room No: 504, 199 Shahid Sayed Nazrul Islam Sawrani, Bijoynagar, Dhaka-1001 | 24.09.17 | 14.10.17 | 13.10.18 |  | 100% | 36812451
209 | BDRIDP/PRJ/BAN/ UZ-St-04 | Construction of 22.00m Long RCC Girder Bridge on Bhandaria-Kathalia RHD Purbo Bhandaria Basher Pool to Maliarhat GC road at Ch. 39.00m ID No 579142002 | 579142002 | [5 empty] | 22 | 14713553.31 | 13977875.35 | M/S. Busra Trade International Prop. Layla Parvin Parerhat road, Pirojpur | 25.06.18 | 03.07.18 | 02.07.19 |  | 100% | 11258678
|  | Structusre work Sub-Total = |  | 0 | 0 | 0 | 0 | 0 | 207.12 | 180264331.96 | 184755481.225 | [6 empty] | 181774205
|  | Upazila Total = |  | 17.806 | 19.45 | 0 | 0 | 0 | 207.12 | 852932081.56 | 833490686.158 | [6 empty] | 764956331
Upazila : Nesarabad
210 | BDRIDP/PRJ/ NSB/UN-Ew-01 | Improvement of road fromUttar Bastokati GPS to Beshkati Surbojanin Debashram via H/O Freedom Fighter Mr. Nittanandan Sutar road by Earth work form Ch. 00-1000m | 579583001 | 1 | [5 empty] | 432685 | 432685 | Sawpan Howlader | 01.04.15 | 07.04.15 | 30.06.15 |  | 100% | 427994 |  |  | Final
211 | BDRIDP/PRJ/ NSB/CCA-Ew-01 | Improvement of road fromKuriana Argo Sommoliny School to Rajapur H/O Anil Mistry via Adamkati (Bastakati-Rajapur road) road by Earth work form Ch. 2050-4535m | 579584004 | 2.48 | [5 empty] | 345407 | 345407 | Mr. Niranjon Roy | 17.02.15 | 24.02.15 | 24.05.15 |  | 100% | 344734 |  |  | Final
212 | BDRIDP/PRJ/ NSB/UZ-Ew-01 | Improvement of road from Jagannathkati-Baithakata via Miarhat Nanduhar Ekota Bazar road by Earth work form Ch. 4932-5650m | 579582005 | 0.718 | [5 empty] | 412471 | 412471 | Md. Tayabur Rahman | 18.12.14 | 25.12.14 | 25.04.15 |  | 100% | 410590 |  |  | Final
213 | BDRIDP/PRJ/ NSB/UZ-Ew-01 | Improvement of road from Jagannathkati-Baithakata via Miarhat Nanduhar Ekota Bazar road by Earth work form Ch. 5650-6370m | 579582005 | 0.72 | [5 empty] | 242908 | 242908 | Md. Abul Kalam Azad | 18.12.14 | 25.12.14 | 25.04.15 |  | 100% | 242907 |  |  | Final
214 | BDRIDP/PRJ/ NSB/UZ-Ew-01 | Improvement of road from Jagannathkati-Baithakata via Miarhat Nanduhar Ekota Bazar road by Earth work form Ch. 6370-6949m | 579582005 | 0.579 | [5 empty] | 335561 | 335561 | Md. Sultan Ahmed | 18.12.14 | 25.12.14 | 25.04.15 |  | 100% | 334739 |  |  | Final
|  | Earth work Sub-Total = |  | 5.497 | 0 | 0 | 0 | 0 | 0 | 1769032 | 1769032 | [6 empty] | 1760964
215 | BDRIDP/PRJ/ NSB/UN-Rd/01 | Improvemen of road from Uttar Beshkati GPS to Beshkati Surbojanin Debashram via H/O Freedom Fighter Mr. Nittanandan Sutar road by HBB from Ch 00-1000m [ID No: 579873001] | 579873001 |  |  | 1 |  |  |  | 12418203 | 12416000 | M/S. Sikder Traders Prop. Md. Abdur Rob Sikder Nesarabad, Piropur |  | 22.03.15 | 22.09.15 |  | 100% | 12355444 |  |  | Final
216 | BDRIDP/PRJ/ NSB/UZR(R)/ Rd/01 | Improvement of road from Jagonathkati-Baithakata via Miarhat Nanduhar Ekota Bazar road by BC at ch. 4932-6949m under Nesarabad Upazila [ID No: 579582005] | 579582005 |  | 2.01 |  |  |  |  | 13536599 | 13531000 | M/S. Rayan Enterprise Prop. Md. Mahmud Kabir Nesarabad, Pirojpur |  | 22.03.15 | 22.03.16 |  | 100% | 13526859 |  |  | Final
217 | BDRIDP/PRJ/ NSB/CCA-Rd/01 | Improvemen of road from Kuriana Arjo Sommoliny School to Rajapur H/O Anil Mistry via Adamkati (Bastakati-Rajapur road) road by BC from Ch. 2050-4535m [ ID No: 579874004] | 579874004 |  | 2.48 |  |  |  |  | 9777474 | 18397736.144 | M/S. Sharif & Co Prop. Sharif Nurul Islam Nesarabad, Pirojpur |  | 06.05.15 | 06.11.15 |  | 100% | 18394771 |  |  | Final
218 | BDRIDP/PRJ/ NSB/CCA-Rd/02 | Improvement of road from Daihary Bazar to Gonakpara R&H via Solibunia High School road by BC from Ch. 00-1500m (ID No: 579874127) under Nesarabad Upazila . | 579874127 |  | 1.5 |  |  |  |  | 17610435 | 15989696.668 | M/S. Sikder Traders Prop. Md. Abdur Rob Sikder Nesarabad, Piropur |  | 17.08.15 | 16.08.16 |  | 100% | 15989645 |  |  | Final
219 | BDRIDP/PRJ/NSB/CCA-Rd-03 | a) Improvement of road from Akota Bazar-Sarengkathi UZR road at Ch. 0.00-1500.00m ID No 579874090 (b) Resectioning of Akota Bazar-0Sarengkathi UZR road at Ch. 0.00-1500.00m ID No 579874090 (c) Construction of 3Nos 1.50mx1.50m 1No. 2.00mx2.00m & 1No. 4.00mx4.00m RCC Box Culvert on Akota Bazar-Sarengkathi UZR road at Ch. 190m 815m 1438m 542m & 635m ID No 579874090 under Nesarabad Upazila. Salvage Materials Tk. 1432147.00 | 579874090 |  | 3 |  |  |  |  | 12605238.78 | 11344714.902 | PTSL-MAITREE (PVT) LTD 39, Mojumder House, Level-04, Suite-F, Purana Paltan, Dhaka-1000 |  | 01.11.17 | 30.10.18 |  | 100% | 11321300
220 | BDRIDP/PRJ/NSB/CCA-Rd/04 | a) Improvement of road from Shohagdal GPS-West Shohagdalk Shahid Sreeti H/School road from Ch. 0.00m-592.00m 792m-1500m & 3500m-3800m ID No 579874044 (b) Re-sectioning of Shohagdal GPS-West Shohagdal Shahid Sreeti H/School road from Ch. 0.00m-592.00m 792m-1500m & 3500m-3800m ID No 579874044 (c) Construction of 2Nos 1.50mx1.50m RCC Box Culvert on Shohagdal GPS-West Shohagdal Shahid Sreeti H/School road at Ch. 310m & 501m ID No 579874044 Salvage Materials Tk. 2795473.00 | 579874044 |  | 1.34 |  |  |  |  | 10485209.28 | 9436688.352 | PTSL-MAITREE (PVT) LTD 39, Mojumder House, Level-04, Suite-F, Purana Paltan, Dhaka-1001 |  | 01.11.17 | 30.07.2018 |  | 100% | 9432849 |  |  | Final
221 | BDRIDP/PRJ/NSB/CCA-Rd/05 | Improvement of Road from Alkirhat Bazar Uttar Karfa RHD road by BC at Ch.2000m-2940m including 02 nos 3.00mx3.00m02 nos 2.00mx2.00m & 4 nos 1.00mx1.00m RCC Box Culvert at Ch.2195m2445m 2320m2345m 2025m2100m2275m & 2777ID No.579874132. Salvaged alImprovement of Road from Alkirhat Bazar Uttar Karfa RHD road by BC at Ch.2000m-2940m including 02 nos 3.00mx3.00m02 nos 2.00mx2.00m & 4 nos 1.00mx1.00m RCC Box Culvert at Ch.2195m2445m2320m2345m2025m2100m2275m & 2777ID No.579874132. Salvaged Materials Tk 550453.00ue Tk 550453.00 | 579874132 |  | 0.94 |  |  |  |  | 10507087.08 | 10180863.893 | M/S. Shilpi Enterprise Prop. Md. Sakil Howlader Machimpur, Pirojpur | 25.06.18 | 03.07.18 | 03.01.19 |  | 100% | 10164200
222 | BDRIDP/PRJ/NSB/ CCA-Rd/06 | Improvement of road From Guarekha Govt Primary school-Hiramon House via Kalibari High School & Govt Primary School at Ch. 1650.00-2650.00m. including 04Nos 1.00m x 1.00m RCC Box at Ch. 1871m 2070m 2220m &2450m. ID No-579874049 | 579874049 |  | 1 |  |  |  |  | 8037917.31 | 7636021.444 | M/S. Sourov Construction Prop. Md. Badiuzzaman Saurov Machimpur, Pirojpur | 06.02.19 | 15.02.19 | 14.08.19 |  | 100% | 6552000
223 | BDRIDP/ PRJ/ NSB/CCA-Rd/07 | Improvement of road from Atghor Bazar North side bridge to jhalokato boarder road via Chowdury Bari road from Ch. 0.00m-800.00m. including 01No 3.00mX3.00m RCC Box Culvert at Ch. 347.00m. ID No-579874043 Salvage Cost TK. 641142.00 | 579874043 |  | 0.8 |  |  |  |  | 6957344 | 6609476.8 | M/S. M.R.S Enterprise Machimpur Mashidbari road, Pirojpur Sadar, Pirojpur | 15.05.19 | 22.05.19 | 22.11.19 |  | 90% | 5620000
|  | Road work Sub-Total = |  | 0 | 5.99 | 1 | 0 | 0 | 0 | 101935507.45 | 105542198.203 | [6 empty] | 103357068
224 | BDRIDP/PRJ/ NSB/UZR-St/01 | Construction of 02 nos 4.00mx2.50m, 1Nos 2Vent 3.00x3.00m & 1No 2.00x2.00m size RCC Box Culvert at ch. 5063m, ch. 5363m, ch. 5187m, & ch. 6100m and 3Nos U-drain at ch. 4992m, ch. 5105m & Ch. 5274m respecttively on Jagonathkati-Baithakata via Miarhat Nanduhar Ekota Bazar road under Nesarabad Upazila. [ID No: 579582005] | 579582005 | [5 empty] | 8 | 5892852 | 5885000 | M/S. Rayan Enterprise Prop. Md. Mahmud Kabir Nesarabad, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 5878120 |  |  | Final
225 | BDRIDP/PRJ/ NSB/UN-St/01 | Construction of 2Nos 2.00x2.00m RCC Box Culvert on Uttar Beshkati GPS to Beshkati Surbojanin Debashram via H/O Freedom Fighter Mr. Nittanandan Sutar road at ch. 183m & 518m with 4Nos U-Drain 580m, 700m, 748m & 995m [ID No: 579873001] | 579873001 | [5 empty] | 4 | 1244712 | 1242000 | M/S. Sikder Traders Prop. Md. Abdur Rob Sikder Nesarabad, Piropur |  | 22.03.15 | 22.09.15 |  | 100% | 1163282 |  |  | Final
226 | BDRIDP/PRJ/ NSB/CCA-St/01 | Construction of 2nos U-Drain, 4nos 2.00x2.00m RCC Box Culvert, 2nos 3.00x3.00m RCC Box Culvert, 1no 4.50mx4.00m Box Culvert & 3 Vent 4.50x4.50m RCC Box Culvert on Kuriana Arjo Sommoliny School to Rajapur H/O Anilk Mistry via Adamkati (Bastakati-Rajapur road) at Ch. 2138m, 4000m, 2290m, 3904m, 4165m, 4281m, 3310m, 3830m, 4082m & 2900m. | 579874004 | [5 empty] | 33.25 | 6734624 | 5264146.668 | Md. Zakir Hossain Mia B 4/7, Raptali Housing, Barisla. |  | 22.03.15 | 22.09.15 |  | 100% | 5254071 |  |  | Final
227 | BDRIDP/PRJ/ NSB/CCA-St/02 | Construction of 6nos D-Drain 1No, 2vent 4.50x4.00m , 1No. 2.00x 2.00m RCC Box Culvert on Daihary Bazar to Gonakpara R&H via Solibunia High School road at ch. 60m, 120m, 300m, 1000m, 1220m, 1300m, 683m & 1460m (ID No: 579874127) under Nesarabad Upazila . | 579874127 | [5 empty] | 6.5 | 13014820 | 12298805.708 | M/S. Sikder Traders Prop. Md. Abdur Rob Sikder Nesarabad, Piropur |  | 17.08.15 | 16.08.16 |  | 100% | 12292269 |  |  | Final
228 | BDRIDP/PRJ/NSB/UZ-St/04 | Construction of 25.00m PSC Girder Bridge on Jagannathkati Plan Ghat-Baitakata GC Road At Ch. 8700m Over Chami Khal ID No 579872005 under Nesarabad Upazila. | 579872005 | [5 empty] | 25 | 23556432 | 21200788.8 | M.M Builders & Engineers Ltd. House No-127 (6th floor), Road-10, Block-C, Niketon, Gulshan-1, Dhaka-1212 | 16.04.17 | 23.04.17 | 22.04.18 |  | 100% | 21188151
229 | BDRIDP/PRJ/NSB/UZ-St/03 | Construction of 32.00m P.S.C Girder Bridge on Jagannathkati Plan Ghat-Baitakata GC via Miar Hat Nanduhar Akoita Bazar Road At Ch. 2541m Over Kustakhati Khal under Nesarabad Upazila ID No | 579872005 | [5 empty] | 32 | 10656166 | 26057490.3 | M.M Builders & Engineers Ltd. House No-127 (6th floor), Road-10, Block-C, Niketon, Gulshan-1, Dhaka-1212 | 16.04.17 | 23.04.17 | 22.04.18 |  | 100% | 26010798
230 | BDRIDP/PRJ/NSB/UZ-St/02 | Construction of 25.00m P.S.C Girder Bridge on Jagannathkati Plan Ghat-Baitakata GC via Miar Hat Nanduhar Akota Bazar Road At Ch. 10416m Over Gagan Khal under Nesarabad Upazila ID No | 579872005 | [5 empty] | 25 | 20049789 | 18044810.1 | M.M Builders & Engineers Ltd. House No-127 (6th floor), Road-10, Block-C, Niketon, Gulshan-1, Dhaka-1212 | 16.04.17 | 23.04.17 | 22.04.18 |  | 100% | 18023111
231 | BDRIDP/PRJ/NSB/CCA-St/03 | Construction of 12.00m RCC Slab Bridge on Zindakathi GPS Connecting Road Over Andharkul Khal Ch of 0425m of Zindakathi to Kirtipasha Road under Nesarabad Upazila ID No | 579875057 | [5 empty] | 12 | 10656166 | 10534990.284 | M/S. Raj & Brothers Prop. Md. Habibur Rahman, Parherhat road, Pirojpur | 13.04.17 | 20.04.17 | 19.04.18 |  | 100% | 10522155
232 | BDRIDP/PRJ/NSB/UZ-St/05 | Construction of 49.00m Long PC Girder Bridge on Jagannathkati Plan Ghat- Baitakata GC via Miarhat Nanduhar Aktota Bazar road.at Ch. 7685Km Over Tarabunia Khal. ID No-579872005 | 579872005 | [5 empty] | 49 | 95577032 | 84657893.527 | M/S. Kohinoor Enterprise Kawnia 1st Lane, Barisal. |  | 17.11.19 | 17.08.20 |  | 80% | 66000000
|  | Structusre work Sub-Total = |  | 0 | 0 | 0 | 0 | 0 | 194.75 | 187382593 | 185185925.387 | [6 empty] | 166331957
|  | Upazila Total = |  | 5.497 | 5.99 | 1 | 0 | 0 | 194.75 | 291087132.45 | 292497155.59 | [6 empty] | 271449989
Upazila : Kawkhali
232 | BDRIDP/PRJ/ Kaw/CCA-Ew-01 | Improvement of road from Chot Birajpur GPS cum Cyclone Shelter road by earth work Ch. 00-400m | 579475020 | 0.4 | [5 empty] | 304076 | 304076 | Md. Jahirul Islam | 16.02.15 | 23.02.15 | 23.08.15 |  | 100% | 242199
233 | BDRIDP/PRJ/ Kaw/CCA-Ew-01 | Improvement of road from Chot Birajpur GPS cum Cyclone Shelter road by earth work Ch. 400-700m | 579475020 | 0.3 | [5 empty] | 283304 | 283304 | Md. Samsul Haque | 16.02.15 | 23.02.15 | 23.08.15 |  | 100% | 245550
234 | BDRIDP/PRJ/ Kaw/CCA-Ew-01 | Improvement of road from Chot Birajpur GPS cum Cyclone Shelter road by earth work Ch. 700-1250m | 579475020 | 0.55 | [5 empty] | 238563 | 238563 | Juboraj | 16.02.15 | 23.02.15 | 23.08.15 |  | 100% | 225965
235 | BDRIDP/PRJ/ Kaw/CCA-Ew-01 | Improvement of road from Chot Birajpur GPS cum Cyclone Shelter road by earth work Ch. 1250-1500m | 579475020 | 0.25 | [5 empty] | 152060 | 152060 | Marufa Akter | 16.02.15 | 23.02.15 | 23.08.15 |  | 100% | 98523
236 | BDRIDP/PRJ/ Kaw/UZ-Ew-01 | Improvement of road from Hogla -Ragunathpur-Sayna-Hularhat Kheyaghat road Ch.1512-1925m | 579472007 | 0.413 | [5 empty] | 270015 | 270015 | Md. Moniruzzaman | 19.02.15 | 26.02.15 | 26.08.15 |  | 100% | 234009
237 | BDRIDP/PRJ/ Kaw/UZ-Ew-01 | Improvement of road from Hogla -Ragunathpur-Sayna-Hularhat Kheyaghat road Ch.1925-2285m | 579472007 | 0.36 | [5 empty] | 279929 | 279929 | Md. Rasel Hossain | 19.02.15 | 26.02.15 | 26.08.15 |  | 100% | 224835
238 | BDRIDP/PRJ/ Kaw/UZ-Ew-01 | Improvement of road from Hogla -Ragunathpur-Sayna-Hularhat Kheyaghat road Ch.2285-2925m | 579472007 | 0.64 | [5 empty] | 203583 | 203583 | Md. Alim | 19.02.15 | 26.02.15 | 26.08.15 |  | 100% | 183947
239 | BDRIDP/PRJ/ Kaw/UZ-Ew-01 | Improvement of road from Hogla -Ragunathpur-Sayna-Hularhat Kheyaghat road Ch.2925-3325m | 579472007 | 0.4 | [5 empty] | 190664 | 190664 | Md. Sakil Ahmed | 19.02.15 | 26.02.15 | 26.08.15 |  | 100% | 153386
240 | BDRIDP/PRJ/ Kaw/UZ-Ew-01 | Improvement of road from Hogla -Ragunathpur-Sayna-Hularhat Kheyaghat road Ch.3325-3600m | 579472007 | 0.27 | [5 empty] | 269650 | 269650 | Ruma Begum | 19.02.15 | 26.02.15 | 26.08.15 |  | 100% | 180991
|  | Earth work Sub-Total = |  | 3.583 | 0 | 0 | 0 | 0 | 0 | 2191844 | 2191844 | [6 empty] | 1789405
241 | BDRIDP/PRJ/ KAW/CCA-Rd/01 | Improvement of road from Choto Biraljuri GPS cumCyclone Shelter road by BC from Ch. 00-1500m under Kawkhali Upzila [ID No: 579475020]. | 579475020 |  | 1.5 |  |  |  |  | 16101934 | 16095000 | M/S. Raj & Brothers Prop. Md. Habibur Rahman Parerhat road, Pirojpur |  | 22.03.15 | 22.09.15 21.12.16 |  | 100% | 16091243 |  |  | Final
242 | BDRIDP/PRJ/ Kaw/UZ-Rd (R) /01 | Rehabilitation of road from Hogla-Raghunathpur-Sayna-Hularhat Kheyaghat road By BC from Ch. 1512-3600m under Kawkhali Upazila [ID No: 579472007] | 579472007 |  | 2.08 |  |  |  |  | 14412592 | 14408000 | M/S. Urmi Enterprise Prop. Md. Maniruzzaman Kawkhali, Pirojpur |  | 22.03.15 | 22.03.16 15.09.16 |  | 100% | 14271369
243 | BDRIDP/PRJ/KAW/CCA-Rd/ 02 | Improvement of Road from Kawkhali Collage Moor R&H road to Dasherkati Rafique Master house via Aspordi Govt. Primary School at Ch.00m-500m.Including 01 No 2.00m x 2.00m 01 No 2-vent 3.00m x 3.00m. RCC Box at Ch. 444.00m & 232.00m & 02 Nos 0.60m x 0.60m U- Drain 9.50m Long At Ch.381.00m & 483.00m.ID No. 579474047 | 579474047 |  | 0.5 |  |  |  |  | 6919191.05 | 6573231.498 | M/S SUMAIYA ENTERPRISE Hularhat, Pirojpur | 17.04.19 | 01.05.19 | 01.08.19 |  | 100% | 6540000
244 | BDRIDP/PRJ/KAW/UN-Rd/01 | Improvement of Road from Kawkhali GC Uttar Bazar Bridge- Kawkhali-Swarupkati RHD road via Amrajuri UP at Ch. 566m-1611m. including 01 No 2- vent 4.50m x 4.00m. 02 Nos 1.50m x 1.50m & 01 No 2.00m x 2.00m. RCC Box at Ch. 1100.00m 220.00m 1008.00m & 970.00m.ID No. 579473002 salvage Cost-1865217.00 TK | 579473002 | [6 empty] | 12830500 | 11591226.686 | Abir-Sarder Consortium (JV), Sikerpur, Pirojpur | 25.06.19 | 01.07.19 | 01.01.20 |  | 95% | 10400000
245 | BDRIDP/PRJ/KAW/UZ-Rd/02 | Improvement of Hogla -Hogla Betka bazar -Polerhat Sirsa GPS Rogunathpur H/S Killa-Saina-Hularhat Khyaghat road at Ch. 3600m-3955m.including of 02 Nos-1.0mX1.0m & 02 Nos 2.0mX2.0m RCC Box Culvert at Ch.3684m 3716m 3786m & 3902m. Salvage Cost-99994.00TK | [7 empty] | 6999452 | 6649479.4 | M/S. Sadia Constructio Prop. Matiur Rahman Doctor Patti Road, Jhalokati | 27.10.19 | 03.11.19 | 02.05.20 |  | 100% | 6649400
|  | Road work Sub-Total = |  | 0 | 3.58 | 0 | 0 | 0 | 0 | 50264217.05 | 48667458.184 | [6 empty] | 53952012
246 | BDRIDP/PRJ/ KAW/UZ-St/01 | Construction of 6Nos 1.00x1.00m, 2Nos 2.00x2.00m, 1No 3.00x3.00m & 1No 4.00x4.00m RCC Box Culvert on Hogla-Raghunathpur-Sayna-Hularhat Kheyaghat road at Ch. 1665m, 1694m, 2088m, 2945m, 3056m, 3362m, 2097m, 2233m, 3096m & 1512m under Kawkhali Upazila [ID No: 579472007]. | 579472007 | [5 empty] | 17 | 7877356 | 7870000 | M/S. Firoza Enterprise Prop. Md. Jashim Uddin Kawkhali, Piropur |  | 22.03.15 | 22.09.15 30.05.16 |  | 100% | 7797554 |  |  | Final
247 | BDRIDP/PRJ/ KAW/CCA-St/01 | Construction of 5Nos 1.00x1.00m & 2Nos 2.00x2.00m RCC Box Culvert on Choto Biraljuri GPS cum Cyclone Shelter road at Ch. 241m, 466m, 646m, 1080m, 1170m, 1051m & 1490m under Kawkhali Upazila. [ID No: 579475020] | 579475020 | [5 empty] | 9 | 3325753 | 3315000 | M/S. Raj & Brothers Prop. Md. Habibur Rahman Parerhat road, Pirojpur |  | 22.03.15 | 22.09.15 |  | 100% | 3309508 |  |  | Final
248 | BDRIDP/PRJ/ KAW/GHAT/01 | Construction of Kawkhali Ghat including Connecting road | 579474064 | [6 empty] | 4459349 | 3520981.258 | M/S. Amin Brothers Prop. Md. Nurul Amin Kawkhali, Pirojpur |  | 04.07.16 | 04.01.17 |  | 100% | 3507148
249 | BDRIDP/PRJ/ KAW/UZ-St/02 | Construction of 12.00m RCC Girder Bridge on Hogla-Polerhat-Sirsha-Saina Ragunathpur to Hularhat Kheyaghat road at Ch. 8+482m over Sayna Khal under Kawkhali Upazila. | 579472007 | [5 empty] | 12 | 13270287 | 10238624.399 | M/S. Saifuddin Traders Prop. M.M.A Wahab Nesarabad, Pirojpur |  | 16.02.17 | 16.02.18 |  | 100% | 10238000
250 | BDRIDP/PRJ/ KAW/UZ-St/03 | Construction of 12.00m RCC Girder Bridge on Hogla-Polerhat-Sirsha-Saina Ragunathpur to Hularhat Kheyaghat road at Ch. 8+347m over Sayna Khal under Kawkhali Upazila. | 579472007 | [5 empty] | 12 | 13268609 | 9903145.412 | M/S. Soma Enterprise Prop. Khondokar Imam Hossain, Old Bass Terminal Road, Patuakhali |  | 20.02.17 | 19.02.18 |  | 100% | 9888425
251 | BDRIDP/PRJ/ KAW/UZ-St/04 | Construction of 12.00m RCC Girder Bridge on Hogla-Polerhat-Sirsha-Saina Ragunathpur to Hularhat Kheyaghat road at Ch. 3+825m over Sayna Khal under Kawkhali Upazila. | 579472007 | [5 empty] | 12 | 11012279 | 8113892.713 | M/S. Kalai Mollah Construction Prop. Md. Billal Mollah Purbo Rasti, Puran Bazar Madaripur |  | 20.02.17 | 19.02.18 |  | 100% | 8092340 |  |  | Final
|  | Structusre work Sub-Total = |  | 0 | 0 | 0 | 0 | 0 | 62 | 53213633 | 42961643.782 | [6 empty] | 42832975
|  | Upazila Total = |  | 3.583 | 3.58 | 0 | 0 | 0 | 62 | 105669694.05 | 93820945.966 | [6 empty] | 98574392
Upazila : Nazirpur
252 | BDRIDP/PRJ/ NZP/UN-Ew/03 | Improvement of road from Malikhali UP to Chandkati bazar road by earth work Ch. 1200-2250m | 579763005 | 1.05 | [5 empty] | 282120 | 282120 | Tapan Mondon |  |  |  |  | 100% | 282120
253 | BDRIDP/PRJ/ NZP/UN-Ew/01 | Improvement of road from Malikhali UP to Chandkati bazar road by earth work Ch. 2250-3200m | 579763005 | 1 | [5 empty] | 202477 | 202477 | Asraf Mollah |  |  |  |  | 100% | 202477
254 | BDRIDP/PRJ/ NZP/UN-Ew/01 | Improvement of road from Malikhali UP to Basbaria GC road by earth work Ch. 00-210m & 1210-3425m | 579763018 | 2.425 | [5 empty] | 440184 | 440184 | Milon Mondol |  |  |  |  | 100% | 440184
255 | BDRIDP/PRJ/ NZP/UN-Ew/02 | Improvement of road from Malikhali UP to Gaokhali hat road by earth work Ch. 2010-2610m | 579763009 | 0.5 | [5 empty] | 237763 | 237763 | [5 empty] | 100% | 237763
256 | BDRIDP/PRJ/ NZP/UN-Ew/02 | Improvement of road from Malikhali UP to Gaokhali hat road by earth work Ch. 2610-2900m | 579763009 | 0.29 | [5 empty] | 295718 | 295718 | Sunil Malakar |  |  |  |  | 100% | 295718
257 | BDRIDP/PRJ/ NZP/UN-Ew/02 | Improvement of road from Malikhali UP to Gaokhali hat road by earth work Ch. 2900-3200m | 579763009 | 0.3 | [5 empty] | 328870 | 328870 | Mrs. Helena |  |  |  |  | 100% | 328870
258 | BDRIDP/PRJ/ NZP/UN-Ew/02 | Improvement of road from Malikhali UP to Gaokhali hat road by earth work Ch. 3200-3500m | 579763009 | 0.3 | [5 empty] | 292992 | 292992 | Rasmoy Ray |  |  |  |  | 100% | 289478
|  | Earth work Sub-Total = |  | 5.865 | 0 | 0 | 0 | 0 | 0 | 2080124 | 2080124 | [6 empty] | 2076610
259 | BDRIDP/PRJ/NZP/UN-Rd/03 | Improvement of road from Malikhali UP-Chandkati Bazar by BC at Ch. 1200.00-3200m (ID No: 579763005) under Nazirpur Upazila. | 579763005 | 2 | [5 empty] | 12192040 | 9558031.46 | M/S. Swagata Enterprise, Prop. Chancal Kanti Biswas Nazirpur, Pirojpur |  | 12.03.17 | 11.03.18 |  | 100% | 9545000
260 | BDRIDP/PRJ/NZP/UN-Rd/02 | Improvement of road from Malikhali UP-Gowkhali Hat by HBB at Ch. 2000-3500m (ID No: 579763009) under Nazirpur Upazila. | 579763009 | 1.5 | [5 empty] | 5054000 | 4114941.709 | M/S. Saifuddin Traders Prop. M.M.A Wahab Nesarabad, Pirojpur | 05.03.17 | 12.03.17 | 12.09.17 |  | 100% | 4114941 |  |  | Final
261 | BDRIDP/PRJ/NZP/UN-Rd/01 | Improvement of road from Malikhali UP-Basbaria GC by BC from Ch. 00-210m & 1210m-4700m including 2 nos 1.00x1.00m Box Culvert at Ch. 4055m & 4395m (ID No: 579763018) under Nazirpur Upazila [Salvage Materials Tk. 4,73,199.00] | 579763018 | 3.28 |  |  |  |  | 2 | 23828602 | 18973110.469 | M/S. Saifuddin Traders Prop. M.M.A Wahab Nesarabad, Pirojpur | 05.03.17 | 12.03.17 | 11.03.18 |  | 100% | 18973110 |  |  | Final
262 | BDRIDP/PRJ/NZP/CCA-Rd/01 | Improvement of Pirojpur-Gopalgonj RHD Chithalia-Kumarkhali Hat Road from Ch. 0.00m-2000m including 2Nos 4.50mx4.00m 1No 2x4.00mx4.50m & 1No. 3x4.00x4.50m RCC Box Culvert at Ch. 510m 1493m 285m & 1178m ID No 579764027 Salvage Materials Tk. 2873645.00 | 579764027 | 2 |  |  |  |  | 24.5 | 17927293.99 | 16134564.591 | PTSL-MAITREE (PVT) LTD 39, Mojumder House, Level-04, Suite-F, Purana Paltan, Dhaka-1000 | 04.10.17 | 14.10.17 | 14.10.18 |  | 100% | 16134314 |  |  | Final
263 | BDRIDP/PRJ/NZP/UN-Rd/04 | Improvement of Matibhanga UP to Chalitabari hat road by BC from Ch.0.00-1950m Including 01No 4.00x4.50m2-Vent & 04 Nos 1.50mx1.50m RCC Box Culvert at Ch.1300.00m 320.00m 680.00m 940.00m & 1615.00m ID No.579763016 Salvage Amount Tk.3511066.00 | 579763016 |  | 1.95 |  |  |  | 14 | 16015168.43 | 14413651.587 | M/S. Kohinoor Enterprise Prop. Mehedi Hasan Dadpur Lodge Kawnia 1st Lane Barisal. | 25.03.18 | 01.04.18 | 01.04.19 |  | 100% | 14400000
264 | BDRIDP/PRJ/NZP/CCA-Rd/02 | a Improvement of road from Balua Mugarjor Rice Mill- Golam Rahaman House road at Ch. 2000.00m-2600.00m. including 02 Nos 2.00X2.00m 01 No 4.00X4.50m RCC Box Culvert 01 No 2-vent 4.00mX4.50m RCC Box Culvert at Ch.2431m 2590m2481m & 2533m. ID No-579756026 b Improvement of road from Boithakata GC-Bisharkandi Border road by BC a Ch. 1000.00m-1450.00m. including 01 No 2-Vent 4.00mX4.50m Box Culvert at Ch. 1356.00m. ID No-579764024 | 579756026 579764024 | [6 empty] | 15668337.81 | 14524077.795 | M/S. Oishi Construction Prop. Sabina Yeasmin Mathbaria, Pirojpur | 25.03.18 | 01.04.18 | 01.04.19 |  | 100% | 14523115
265 | BDRIDP/PRJ/NZP/UN-Rd/05 | Improvement work of Kalardoania UP-Chandkathi Hat Road Ch. 7190-8330m. including 02 Nos 2-vent 4.00x4.50m 01 No 2.00x2.00m & 05 Nos 1.500x1.500m RCC Box Culvert at Ch. 7333m 7530m 7625m 6937m 7190m 7430m 7685m & 7998m ID No 579763007 Salvage Tk. 2293520.00 | 579763007 | [6 empty] | 16062063.39 | 14778115.267 | M/S. Lutful Kabir Dill Bag, Bagura, Alekanda Road, Barisal-8200 | 09.07.19 | 16.07.19 | 16.01.20 |  | 80% | 11600000
|  | Road work Sub-Total = |  | 8.78 | 0 | 0 | 0 | 0 | 26.5 | 106747505.62 | 92496492.878 | [5 empty] | 6.8 | 89290480 | 0 | 0
266 | BDRIDP/PRJ/NZP/UN-/St-01 | Construction of 30.00m P.S.C Girder Bridge on Malikhali UP to Bashbaria GC Road At Ch. 4610m over Jhanjhonia Khal under Nazirpur Upazila (ID No: 579763018) | 579763018 | [5 empty] | 30 | 20130269 | 17084116.696 | M/S. Raj & Brothers Prop. Md. Habibur Rahman Parerhat road, Pirojpur | 05.03.17 | 12.03.17 | 11.03.18 |  | 100% | 17039872 |  | 0 | Final
267 | BDRIDP/PRJ/NZP/UN-St/02 | Construction of 21.00m RCC Girder Bridge on Malikhali UP to Bashbaria GC Road Over Mithakul Khal At Ch. 4226m under Nazirpur Upazila ID No 579763018 | 579763018 | [5 empty] | 21 | 11271391 | 10144251.9 | M/S. Abir & Brothers Prop. Salma Rahman Amlapara, Pirojpur | 18.04.17 | 26.04.17 | 25.04.18 |  | 100% | 10122000
268 | BDRIDP/PRJ/NZP/CCA-St/01 | Construction of 2x4.00x4.50m RCC Box Culvert on Nazirpur UPC-Patuakhali Village Road via H/O Narayon Bepari at Ch. 70.00m ID No 579765025 | 579765025 | [5 empty] | 8 | 2155823.41 | 1940241.069 | M/S. Niaz Traders Prop. Niaz Ahmed 154, Motijheel C/A, Masjid Market (2nd floor), Room No. 301-303, Dhaka-1000. | 04.10.17 | 14.10.17 | 14.04.18 |  | 100% | 1938147
269 | BDRIDP/PRJ/NZP/GHT/01 | Construction of RCC Ghat at Sachia Bazar | [7 empty] | 3316569.74 | 2984912.766 | ISLAM BROTHERS & ENGINEER LTD Sonartori Toer, 4-5 Th Floor , 132 Sonargan Road,Dhaka-1000 | 07.05.18 | 15.05.18 | 15.11.18 |  | 100% | 2983120
270 | BDRIDP/PRJ/NZP/CCA-St/02 | Construction of 12.00m RCC Slab Bridge on Barobari Chithulia Bridge to Amtola Road at Ch.0505Km.ID No-579764045 | [7 empty] | 15598973 | 12646871.269 | Md. Mahfug Khan Ltd-M/S. Abir and Brothers (JV) Amlapara, Parerhat road, Pirojpur | 05.09.19 | 12.09.19 | 11.09.20 |  | 90% | 10700000
|  | Structusre work Sub-Total = |  | 0 | 0 | 0 | 0 | 0 | 59 | 52473026.15 | 44800393.7 | [6 empty] | 42783139
|  | Upazila Total = |  | 8.78 | 0 | 0 | 0 | 0 | 85.5 | 159220531.77 | 139377010.578 | [6 empty] | 134150229
Earth work Total = |  |  |  | 92.262 | 0 | 0 | 0 | 0 | 0 | 40152142 | 40225036 | [6 empty] | 38202205
Road work Total = |  |  |  | 0 | #VALUE! | 22.708 | 0 | 0 | 2 | 1434894982.77 | 1380933297.885 | [6 empty] | 1306353414 |  |  |  | Year | Total Spent
Structusre work Total = |  |  |  | 0 | 0 | 0 | 0 | 0 | 895.57 | 832450324.12 | 794392699.574 | [6 empty] | 757959985 |  |  |  | 2013-2014 | 3.5
District Total : |  |  |  | 92.262 | #VALUE! | 22.708 | 0 | 0 | 897.57 | 2307497448.89 | 2215551033.459 | [6 empty] | 2102515604 |  |  |  | 2014-2015 | 1606.5
[22 empty] | 2015-2016 | 3575.12
[22 empty] | 2016-2017 | 2957
[22 empty] | 2017-2018 | 6122.34
[22 empty] | 2018-2019 | 3770
[22 empty] | 2019-20 | 3725
21759.46
|  | Accountant |  |  |  |  | Sub-Assistant Engineer | [5 empty] | Sr.Assistant Engineer |  |  |  |  | Executive Engineer
|  | LGED, Pirojpur |  |  |  |  | LGED, Pirojpur | [5 empty] | LGED, Pirojpur |  |  |  |  | LGED, Pirojpur