## Progress
Monthly Progress Report
Implementation Status
Barisal Division Rural Infrastructure Development Project
District: Jhalakathi. | [12 empty] | Upto Month: October/2015
Sl No | Upazila | Type of work (E/W,BC,CC,HBB,Brdg,Cul, Tree, Mkt, GC, Ghat, LA) | Package No. | Scheme Name with Location (Ch. To Ch.) | Road ID No. | Effective Quantity (m3,km,m,Nos,ha) | Approved Estimated Cost (Tk) | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract signing date | Actual start date | Completion date as per contract | Actual completion date | Physical Progress (%) | Financial Progress |  | Fund received with memo date | Remarks
[15 empty] | Amount Spent(Tk) | in (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
1 | Rajapur | BC | BDRIDP/JHL/RJP/CCA-Rd/01 | Improvement of road from South side of Sultan Mia's House to Galua Pir Shaheb House via Abdul Malek Master Bari road (Ch.00-800m) by BC Including a culvert. | 542845090 | 0.800km | 5405281 | 5121236.04 | M/s. Sarna Construction | 21-07-2014 | 28-07-14 | 21-05-15 |  | 55% | 1325800
2 | Rajapur | BC | BDRIDP/JHL/RJP/CCA-Rd/02 | Improvement of road from Rajapur-Bekutia R&H at H/O Mannan Master to Monoherpur H/S (Ch.00-790m). | 542845032 | 0.790km | 4029652 | 4510602.26 | M/s. Sarna Construction | 20-07-14 | 27-07-14 | 23-07-15 |  | 100% | 3300000
3 | Rajapur | BC | BDRIP/JHL/RJP/CCA-Rd/03 | Rehabilitation by flexible pavement of Rajapur Kathalia C&B Road-Purbo Agria Ather Khan Bari via Khan Bari GPS road at ch00.00-1000.00m (ID NO:542844097) (salavage amount BDT 1065783.00) | 542844097 | 1.00km | 4662347 | 3303721.476 | M/S Syed Enterprise | 18/01/15 | 28/1/15 | 13/07/15 |  | 70% | 1385949
4 | Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/01 | Construction of 3 Nos1.83mx1.83m RCC Box culvert at ch.325m, 880.00m, and 6.10m at 1000.00m on Rajapur Kathalia C&B road Purbo Angria Ather Khan Bari via Khan Bari GPS road (ID No:542844097) | 542844097 | 5.49m | 1897132 | 1254680.52 | M/S Shafiqul Islam | 28/01/15 | 2015-03-02 | 2015-02-08 |  | 50% | 0
5 | Rajapur | HBB | BDRIDP/JHL/RJP/CCA-Rd/06 | Improvement of road from Amena Khtun GPS via Imam uddin Baitul Jame Mosque-Galua Charakhali LGED road by HBB from ch.1238-2319m (ID:542844096) | 542844096 | 1.081km | 3333337 | 3304391.757 | M/S Syed Enterprise | 2015-02-02 | 2015-09-02 | 2015-08-08 |  | 100% | 2170601
6 | Rajapur | BC | BDRIDP/JHL/RJP/CCA-Rd/07 | Improvement of road from Bashtala R&H to Napiterhat via Char Indropasha Ashraon road from ch.1024-2330m by BC with & Connecting road at ch.1524m from 00-250m with Jame Mosque, Madrasha (ID No.542844077) (Salvaged Cost Tk.2604590) | 542844077 | 1.306km | 6835202 | 6771834.153 | M/S Syed Enterprise | 2015-02-02 | 2015-09-02 | 2015-08-08 |  | 20% | 0
7 | Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/04 | Construction of 3Nos 1.83mx.183m RCC Box culvert on Rampur-Bekutia R&H at H/O Mannan Master to Monoharpur H/S road at ch.370m, 570m & 676m (ID No.542845032) | 542845032 | 5.49m | 645143 | 418201.615 | M/S Arafat Traders | 29/01/15 | 2015-05-02 | 2015-04-05 |  | 100% | 0
8 | Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/05 | Construction of 5Nos 1.83mx.183m RCC Box culvert on Amena Khatun GPS via Imam uddin Baitul Jame Mosque-Galua Charakhali LGED road at ch. 1294m, 1569m, 1789m, 1904m & 2115m (ID No.542844096) | 542844096 | 9.15m | 1075238 | 725758.723 | M/S Syed Enterprise | 2015-02-02 | 2015-09-02 | 2015-08-07 |  | 100% | 725758
9 | Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/06 | Construction of 5Nos 1.83mx.183m RCC Box culvert on Bashtala R&H to Napiterhat via Char Indropasha Ashraon road at ch. 1205m, 1404m, 1650m, 1863m & 2018m (ID No.542844077) | 542844077 | 9.15m | 1075990 | 697488.683 | M/S Arafat Traders | 29/01/15 | 2015-05-02 | 2015-04-08 |  | 100% | 418201
10 | Rajapur | Road | BDRIDP/JHL/RJP/UZ-Rd(R)/04 | Rehabilitation of road from Mirerhat GC to Lebubunia GC via Galua UP (Rajapur-Kathalia RHD-Lebubunia GC via Galua UP) road by BC from ch.5357-7357m. | 579582002 | 2.00km | 12392337 | 12390215.21 | M/S Badol Construction | 15-05-15 | 17-05-15 | 16-05-16 |  | 70% | 0
11 | Rajapur | culvert | BDRIDP/JHL/RJP/UZ-St/04 | Construction of 2Nos. 4.00mx4.00m (2vent)/ 4Nos. 2.00mx2.00m; 2Nos. 2.60mx2.60m & 7Nos. 1.83mx1.83m RCC Box Culvert on Mirerhat GC to Lebubunia GC via Galua UP (Rajapur-Kathalia RHD-Lebubunia GC via Galua UP) road at ch.5606m, 5769m,6166m, 6288m, 6479m, 7103m, 6757m,6972m,5902m, 5957m, 6227m,5420m,6522m,6710m & 7307m with Connecting road 2.00mx2.00m RCC box culvert at ch.95.00m | 579582002 | 42.01m | 14580135 | 14573165.47 | M/S Badol Construction | 2015-07-05 | 14-05-15 | 15-05-16 |  | 80% | 4000000
12 | Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/07 | Construction of 1 No 6.10m;1 No 2.0mx2.0m & 3 Nos 1.83mx1.83m RCC Box Culvert on Alamgir Chowdhury Bari-South Pur at 328m,290m,26m,172m & 213m (ID NO.542844114) | 542844114 | 13.59m | 2545513 | 1620238.19 | M/S M. M Enterprise | 27-05-2015 | 2015-04-06 | 2015-04-12 |  | 0% | 0
13 | Rajapur | Road | BDRIDP/JHL/RJP/CCA-Rd/08 | Improvement of Road from Alamgir Chowdhury Bari-South Pur road by BC from ch. 00-635m (ID NO 542844114) | 542844114 | 0.635km | 3073568 | 3085641.12 | M/S M. M Enterprise | 2015-01-07 | 2015-08-06 | 2015-07-12 |  | 0% | 0
| Rajapur | culvert | BDRIDP/JHL/RJP/UZ-St/01 | Construction of 2nos 1.83mx1.83m & 1no. 4.00mx4.00m RCC box culvert on Nolkathi-Talukder hat (Jhalokathi part) from ch.275m, 584m & 796m (ID No.542842007) | 542842007 | 7.66m | 2543127 | 2543115.54 | M/s. Prince & Co.
| Rajapur | Road | BDRIDP/JHL/RJP/UZ-Rd/01 | Improvement of Noikathi-Talukder hat (Jhalokathi part) road by BC from ch.3000-3796m (ID No.542842007) | 542842007 | 0.796km | 3540425 | 3538291.43 | M/s. Prince & Co.
| Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/02 | Construction of 4Nos. 1.83mx1.83m size, 1no. 9.00m RCC Girder Birdge & 2Nos. 2.00mx2.00m RCC Box culvert on Akoner hat-Hawladerhat via A. Rahim Khan house road at ch.2817m,2975m,3410m,3440m,3080m,3200m & 3330m. (ID No.542844032) | 542844032 | 20.32m | 4042949 | 4038992.25 | M/s. Islam Brothers
| Rajapur | culvert | BDRIDP/JHL/RJP/CCA-St/03 | Construction of 1no. 6.10m Span open Foundation Culvert on road Hazirhat-M. Fuluher Junior High School via Rola hat road at ch.2840m (ID No.542844033) | 542844033 | 6.10m | 1572367 | 1571148.29 | M/s. Islam Brothers
| Rajapur | Road | BDRIDP/JHL/RJP/CCA-Rd/04 | Improvement of road from Akoner hat-Hawladerhat via A. Rahim Khan house road by BC from ch.2250-3500m (ID No.542844032). | 542844032 | 1.25km | 5765111 | 57,62,945.38 | M/s. Islam Brothers
| Rajapur | Road | BDRIDP/JHL/RJP/CCA-Rd/05 | Improvement of road from Hazirhat-M.Fuluher Junior high School via Rola hat road by BC rom ch.2580-3000m. (ID No.542844033) | 542844033 | 0.420km | 2080393 | 2078697.38 | M/s. Islam Brothers
| Rajapur | culvert | BDRIDP/JHL/RJP/UZ-St/02 | Construction of 2Nos. 2.00mx2.00m RCC Box culvert on Mollar hat R&H-Sreemontokathi-N. Pingri via Balarjore hat GC from ch.206m & 328m. | 542842004 | 4.00m | 1612762 | 1611324.23 | M/s. Prince & Co.
| Rajapur | culvert | BDRIDP/JHL/RJP/UZ-St/03 | Construction of 2Nos. 1.83mx1.83m & 1no. 2.60mx2.60m RCC Box culvert on Nizamia high School to North palot LG via Baroia high School from ch.469m, 780m & 944m. | 542842010 | 6.26m | 1634222 | 1632794.82 | M/s. Prince & Co.
| Rajapur | Road | BDRIDP/JHL/RJP/UZ-Rd/02 | Improvement of Mollar hat R&H-Sreemontokathi-N. Pingri via Balarjore hat GC road by BC from ch.4800-5862m. (ID No.542842004) | 542842004 | 1.062km | 6629410 | 6627929.05 | M/s. Prince & Co.
| Rajapur | Road | BDRIDP/JHL/RJP/UZ-Rd/03 | Improvement of Nizamia high School to North palot LG via Baroia high School by BC from ch.5700-6700m (ID No.542842010) | 542842010 | 1.00km | 6350109 | 6348690.19 | M/s. Prince & Co.
| Rajapur | culvert | BDRIDP/JHL/RJP/UZ-st/05 | (a) Construction of 1 no 2.00m*2.00m RCC Box culvert on Mirer hat-Nizamia -Baroia-Niamoti ( included kacharibari hat connection from Jiza road ch. 6050m) road at ch. 490m (ID no. 542842009) (b) Construction of 1 no RCC Box culvert on Al-Madina Zame Mosque connecting road connect with Nizamia High School Baroia High School road at ch. 2410m connecting road from ch. 00-90m at ch. 5.00m ( ID no 542842010) | 542842010 |  | 1918662 | 1702549.71 | M/s. H. R Enterprise
| Rajapur | culvert | BDRIDP/JHL/RJP/CCA-Rd/09. | Improvement of road from Naykathi Bhandaria RHD Amtola Bazar to Farazi Bari via in front side of Hamej Uddin Memorial H/S road by BC from ch 1350-2450m (ID NO 542844103) | 542844103 |  | 4718479 | 3775161.38 | M/s. Arafat Traders
| Rajapur | culvert | BDRIDP/JHL/RJP/UZ-Rd(R0/05 | (a) Rehabilitation of road from Mirerhat-Nizamia-Bproia-Niamoti (included kacharibari hat connection ) ( From Jica road ch. 6050m) road by BC from ch. 00-690m with 2.00m*2.00m Box culvert at ch. 490m (ID No. 542842009) (b) Improvement of road from Al-Madina Zame Mosque connecting road connect with Nizamia High School Baroia High School road at ch. 2410m connecting road from ch. 00-90m (ID.542842010) | 542842010 |  | 3661898 | 2747898.28 | M/s. Arafat Traders
|  |  |  | Sub Total Tk= |  |  | 97321750 | 87768158.397 |  |  |  |  | 0 |  | 13326309 | 0 | 0
1 | Sadar | HBB | BDRIDP/JHL/SAD/CCA-Rd-01 | Improvement of road by HBB from Rahmatpur Gorkhay Bridge-Khajuria via Mirakati School from ch.00-1000m under Sadar Upazila. | 542404061 | 1.00km | 2530318 | 1954251.17 | Md. Feroj Alam | 17-09-14 | 24-09-14 | 15-01-15 |  | 40% | 0
2 | Sadar | culvert | BDRIDP/JHL/SAD/CCA-St-01 | Construction of 1 No. 6.00m RCC Girder Bridge on Ramanathpur Gorkhay Bridge-Khajuria via Mirakathi via Mirakathi School road at ch.574m under Sadar Upazila | 542404061 | 6.00m | 1998982 | 1296767.19 | M/s. Syed Enterprise | 14-09-14 | 2014-04-12 | 20/03/2015 |  | 100% | 1288393
3 | Sadar | BC | BDRIDP/JHL/SDR/UZ-Rd(R)/02 | Rehabilitation of Atghar GC-Baligona R&H via Ramjankathi Krishi College road by BC at ch.00-1500m (ID542402006) Jhalakathi-S.( salvage amount=BDT1987269.00) | 542402006 | 1.50km | 8465134 | 6062898.904 | M/S Rashedul Enterprise | 25/12/14 | 2015-02-01 | 19/11/15 |  | 60% | 2117650
4 | Sadar | culvert | BDRIDP/JHL/SDR/UZ-St/03 | Construction of 6 Nos 1.60mx1.60m RCC Box Culvert Atghor GC-Baligona R&H via Ramjankathi Krishi College road at ch.40m, 300m,505m 700m,800m 1350m (ID 542402006) Jhalakathi-S | 542402006 | 9.60m | 5161558 | 3264210.725 | M/S Shafiqul Islam | 28/1/15 | 2015-03-02 | 2016-01-02 |  | 100% | 1870160
5 | Sadar | culvert | BDRIDP/JHL/SDR/CCA-St/02 | Construction of 3 Nos. 9.00m Span RCC Girder Bridge at ch.259m, 918m & 1045m; 1No. box culvert 1.60mx1.60m at ch.860m; 2Nos. 1.22mx1.22m Box Culvert at ch.590m & 820m 1No. 12.00m Span RCC Girder Birdge at ch.1700m. (ID No.542404034) under Sadar Upazila, District: Jhalakathi. | 542404034 | 45.04m | 11217654 | 11211324.98 | M/S Sifat Enterprise | 2015-10-05 | 17-05-15 | 16-05-16 |  | 40% | 0
6 | Sadar | HBB | BDRIDP/JHL/SDR/CCA-Rd/02 | (a) Improvement of HBB road from Goalkanda Harun or Rashid Talukder Bari to Betra road HBB rom ch.00-100m. (ID No.542405313) (b) Construction of RCC Ghatla Goalkanda Harun of Rashid Talukder Bari to Betra road. (ID No.542405313) | 542405313 | 0.100km | 496934 | 410303.93 | M/S M.M Enterprise | 27-05-2015 | 2015-04-06 | 2015-04-09 |  | 70% | 0
7 | Sadar | culvert | BDRIDP/JHL/SDR/UZ-St/02 | Construction of 1Nos. 4.00mx4.00m RCC Box culvert Gabkhan-Guaton via Sekerhat UP including Amrajhuri Road at ch.750m. (ID No.542402005) | 542402005 | 4.00m | 3780497 | 3776277.51 | M/s. Prince & Co.
8 | Sadar | Road | BDRIDP/JHL/SDR/UZ-Rd(R)/01 | Rehabilitation of Gabkhan-Guaton via Sekerhat UP including Amrajhuri Road BY BC at ch.400-1400m. (ID No.542402005) | 542402005 | 1.00km | 1745202 | 1744138.04 | M/s. Prince & Co.
| Sadar | Road | BDRIDP/JHL/SAD/CCA-Rd/03. | Improvement of road from Tarpasha LGED HBB to Kubirkati via Bottala (Tarapasha R& H- Jhalakati Swarupkati R&H road via Kubirkati)road by HBB from ch:00-1370m (ID No.542404150) | 542404150 | 1.370km | 4564723 | 3716578.18 | Md. Zakir Hossain Mia
|  |  |  | Sub Total Tk= |  |  | 39961002 | 33436750.629 |  |  |  |  | 0 |  | 5276203 | 0 | 0 | 0
1 | Kathalia | Ghat | BDRIDP/PRJ/KTH/Ghat/01 | Construction of RCC Ghatla Kachua Bazar & Connecting road. |  |  | 2970893 | 2968261.99 | M/S Syed Enterprise | 2015-10-05 | 17-05-15 | 16-11-15 |  | 0%
| Kathalia | Bridge | BDRIDP/JHL/KTH/UN-BH/01 | Construction of 15.00m Girder Bridge over Jugirkhal under Checrirampur Union Parishad at ch.1250m on Tasserer Kheyaghat-Ghosherhat via Tarabunia Bazar road.(ID No.542433019) | 542433019 | 15.00m | 12221793 | 12217013.32 | M/s. Islam Brothers
| Kathalia | Culvert | BDRIDP/JHL/KTH/UZ-St/01 | Construction of 1no. 2.00mx2.00m RCC Box Culvert on Citky R&H Road-Awrabunia GC road at ch.3686m. (ID No.542432004) | 542432004 | 2.00m | 638564 | 638686.52 | M/s. Islam Brothers
| Kathalia | Culvert | BDRIDP/JHL/KTH/CCA-St/02 | Construction of 4Nos. 1.50mx1.50m and 1no. 2.50mx2.50m RCC Box Culvert on Uttar Talgachia Cyclone Shelter Connecting Road at ch.175m, 260m 470m, 675m & 626m. (ID No.542435157) | 542435157 | 8.50m | 2543444 | 2541783.81 | M/s. Islam Brothers
| Kathalia | Road | BDRIDP/JHL/KTH/UZ-Rd/01 | Improvement of road form citky R&H Road-Awrabunia GC road by BC from Ch.3000-4000m. (ID No.542432004) | 542432004 | 1.00km | 5856260 | 5855701.2 | M/s. Islam Brothers
| Kathalia | Road | BDRIDP/JHL/KTH/CCA-Rd/01 | Improvement of road from Uttar Talgachia Cyclone Shelter Connecting Road by BC from ch.00-1000m. (ID No.542435157) | 542435157 | 1.00km | 5000355 | 49,99,453.50 | M/s. Islam Brothers
|  |  |  | Sub Total Tk= |  |  | 29231309 | 2968261.99 | 0 |  | 0 | 0 | 0 | 0 | 0
|  |  |  | Grand Total Tk= |  |  | 166514061 | 124173171.016 | [6 empty] | 18602512
|  |  | Accountant |  | Sub-Assistant Engineer |  |  |  | Sr. Assistant Engineer |  |  |  |  | Executive Engineer
|  |  | LGED, Jhalakati |  | LGED, Jhalakathi |  |  |  | LGED, Jhalakathi |  |  |  |  | LGED, Jhalakati

## Progress Original
Implementation Status
Barisal Division Rural Infrastructure Development Project
Month: December/2020
Sl No | Package No. | Scheme Name with Location (Ch. To Ch.) | Road ID No. | Effective Quantity (m3,km,m,Nos,ha) | [5 empty] | Approved Estimated Cost (Tk) | Contract Amount (Tk.) | Name of Contractor/LCS Chairman | Contract signing date | Actual start date | Completion date as per contract | Actual completion date | Physical Progress (%) | Financial Progress |  | Demand | BG/PO | Remarks
|  |  |  | E/W (m3) | BC (km) | HBB (km) | RCC (km) | Rehab (km) | str. (m) | [8 empty] | Amount Spent(Tk) | (%)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |  | 22
Upazila: Rajapur
1 | BDRIDP/JHL/RJP/CCA-Rd/01 | Improvement of road from South side of Sultan Mia's House to Galua Pir Shaheb House via Abdul Malek Master Bari road (Ch.00-800m) by BC Including a culvert. | 542845090 |  | 0.8 |  |  |  |  | 5405281 | 5121236.04 | M/s. Sarna Construction | 21-07-14 | 28-07-14 | 21-05-15 | 21-05-2015 | 100% | 5072249 | 100% |  |  | Final
2 | BDRIDP/JHL/RJP/CCA-Rd/02 | Improvement of road from Rajapur-Bekutia R&H at H/O Mannan Master to Monoherpur H/S (Ch.00-790m). | 542845032 |  | 0.79 |  |  |  |  | 4029652 | 4510602.26 | M/s. Sarna Construction | 20-07-14 | 27-07-14 | 23-07-15 | 20/5/2015 | 100% | 4310356 | 100% |  |  | Final
3 | BDRIP/JHL/RJP/CCA-Rd/03 | Rehabilitation by flexible pavement of Rajapur Kathalia C&B Road-Purbo Agria Ather Khan Bari via Khan Bari GPS road at ch00.00-1000.00m (ID NO:542844097) (salavage amount BDT 1065783.00) | 542844097 |  | 1 |  |  |  |  | 4662347 | 3303721.476 | M/S Syed Enterprise | 18/01/15 | 28/1/15 | 13/07/15 | 21-3-16 | 100% | 3241466 | 100% |  |  | Final
4 | BDRIDP/JHL/RJP/CCA-St/01 | Construction of 3 Nos1.83mx1.83m RCC Box culvert at ch.325m, 880.00m, and 6.10m at 1000.00m on Rajapur Kathalia C&B road Purbo Angria Ather Khan Bari via Khan Bari GPS road (ID No:542844097) | 542844097 | [5 empty] | 11.59 | 1897132 | 1254680.52 | M/S Shafiqul Islam | 28/01/15 | 2015-03-02 | 2015-02-08 | 17-10-15 | 100% | 1254679 | 100% |  |  | Final
5 | BDRIDP/JHL/RJP/CCA-Rd/06 | Improvement of road from Amena Khtun GPS via Imam uddin Baitul Jame Mosque-Galua Charakhali LGED road by HBB from ch.1238-2319m (ID:542844096) | 542844096 |  | 1.08 |  |  |  |  | 3333337 | 3304391.757 | M/S Syed Enterprise | 2015-02-02 | 2015-09-02 | 2015-08-08 | 2015-08-06 | 100% | 3304391 | 100% |  |  | Final
6 | BDRIDP/JHL/RJP/CCA-Rd/07 | Improvement of road from Bashtala R&H to Napiterhat via Char Indropasha Ashraon road from ch.1024-2330m by BC with & Connecting road at ch.1524m from 00-250m with Jame Mosque, Madrasha (ID No.542844077) (Salvaged Cost Tk.2604590) | 542844077 |  | 1.556 |  |  |  |  | 6835202 | 6771834.153 | M/S Syed Enterprise | 2015-02-02 | 2015-09-02 | 2015-08-08 | 2016-08-02 | 100% | 6771834 | 100% |  |  | Final
7 | BDRIDP/JHL/RJP/CCA-St/04 | Construction of 3Nos 1.83mx.183m RCC Box culvert on Rampur-Bekutia R&H at H/O Mannan Master to Monoharpur H/S road at ch.370m, 570m & 676m (ID No.542845032) | 542845032 | [5 empty] | 5.49 | 645143 | 418201.615 | M/S Arafat Traders | 29/01/15 | 2015-05-02 | 2015-04-05 | 26/2/2015 | 100% | 418201 | 100% |  |  | Final
8 | BDRIDP/JHL/RJP/CCA-St/05 | Construction of 5Nos 1.83mx.183m RCC Box culvert on Amena Khatun GPS via Imam uddin Baitul Jame Mosque-Galua Charakhali LGED road at ch. 1294m, 1569m, 1789m, 1904m & 2115m (ID No.542844096) | 542844096 | [5 empty] | 9.15 | 1075238 | 725758.723 | M/S Syed Enterprise | 2015-02-02 | 2015-09-02 | 2015-08-07 | 2015-04-06 | 100% | 725758 | 100% |  |  | Final
9 | BDRIDP/JHL/RJP/CCA-St/06 | Construction of 5Nos 1.83mx.183m RCC Box culvert on Bashtala R&H to Napiterhat via Char Indropasha Ashraon road at ch. 1205m, 1404m, 1650m, 1863m & 2018m (ID No.542844077) | 542844077 | [5 empty] | 9.15 | 1075990 | 697488.683 | M/S Arafat Traders | 29/01/15 | 2015-05-02 | 2015-04-08 | 2015-08-03 | 100% | 697488 | 100% |  |  | Final
10 | BDRIDP/JHL/RJP/UZ-Rd(R)/04 | Rehabilitation of road from Mirerhat GC to Lebubunia GC via Galua UP (Rajapur-Kathalia RHD-Lebubunia GC via Galua UP) road by BC from ch.5357-7357m. | 579582002 |  | 2 |  |  |  |  | 12392337 | 12390215.21 | M/S Badol Construction | 15-05-15 | 17-05-15 | 16-05-16 | 25/1/2016 | 100% | 12390215 | 100% |  |  | Final
11 | BDRIDP/JHL/RJP/UZ-St/04 | Construction of 2Nos. 4.00mx4.00m (2vent)/ 4Nos. 2.00mx2.00m; 2Nos. 2.60mx2.60m & 7Nos. 1.83mx1.83m RCC Box Culvert on Mirerhat GC to Lebubunia GC via Galua UP (Rajapur-Kathalia RHD-Lebubunia GC via Galua UP) road at ch.5606m, 5769m,6166m, 6288m, 6479m, 7103m, 6757m,6972m,5902m, 5957m, 6227m,5420m,6522m,6710m & 7307m with Connecting road 2.00mx2.00m RCC box culvert at ch.95.00m | 579582002 | [5 empty] | 36.81 | 14580135 | 14573165.47 | M/S Badol Construction | 2015-07-05 | 14-05-15 | 15-05-16 | 16-11-15 | 100% | 14573165 | 100% |  |  | Final
12 | BDRIDP/JHL/RJP/CCA-St/07 | Construction of 1 No 6.10m;1 No 2.0mx2.0m & 3 Nos 1.83mx1.83m RCC Box Culvert on Alamgir Chowdhury Bari-South Pur at 328m,290m,26m,172m & 213m (ID NO.542844114) | 542844114 | [5 empty] | 13.59 | 2545513 | 1620238.19 | M/S M. M Enterprise | 27-05-2015 | 2015-04-06 | 2015-04-12 | 2015-02-12 | 100% | 1620237 | 100% |  |  | Final
13 | BDRIDP/JHL/RJP/CCA-Rd/08 | Improvement of Road from Alamgir Chowdhury Bari-South Pur road by BC from ch. 00-635m (ID NO 542844114) | 542844114 |  | 0.64 |  |  |  |  | 3073568 | 3085641.12 | M/S M. M Enterprise | 2015-01-07 | 2015-08-06 | 2015-07-12 | 2016-07-01 | 100% | 3085641 | 100% |  |  | Final
14 | BDRIDP/JHL/RJP/UZ-St/01 | Construction of 2nos 1.83mx1.83m & 1no. 4.00mx4.00m RCC box culvert on Noikathi-Talukder hat (Jhalokathi part) from ch.275m, 584m & 796m (ID No.542842007) | 542842007 | [5 empty] | 7.66 | 2543127 | 2543115.54 | M/s. Prince & Co. | 28-9-15 | 2015-05-10 | 2016-04-04 | 2016-03-04 | 100% | 2543115 | 100% |  |  | Final
15 | BDRIDP/JHL/RJP/UZ-Rd/01 | Improvement of Noikathi-Talukder hat (Jhalokathi part) road by BC from ch.3000-3796m (ID No.542842007) | 542842007 |  | 0.8 |  |  |  |  | 3540425 | 3538291.43 | M/s. Prince & Co. | 28-9-15 | 2015-05-10 | 2016-04-04 | 2016-04-04 | 100% | 3538281 | 100% |  |  | Final
16 | BDRIDP/JHL/RJP/CCA-St/02 | Construction of 4Nos. 1.83mx1.83m size, 1no. 9.00m RCC Girder Birdge & 2Nos. 2.00mx2.00m RCC Box culvert on Akoner hat-Hawladerhat via A. Rahim Khan house road at ch.2817m,2975m,3410m,3440m,3080m,3200m & 3330m. (ID No.542844032) | 542844032 | [5 empty] | 20.32 | 4042949 | 4038992.25 | M/s. Islam Brothers | 2015-07-10 | 14-10-15 | 13-10-16 | 2016-12-03 | 100% | 4038915 | 100% |  |  | Final
17 | BDRIDP/JHL/RJP/CCA-St/03 | Construction of 1no. 6.10m Span open Foundation Culvert on road Hazirhat-M. Fuluher Junior High School via Rola hat road at ch.2840m (ID No.542844033) | 542844033 | [5 empty] | 6.1 | 1572367 | 1571148.29 | M/s. Islam Brothers | 2015-07-10 | 14-10-15 | 13-04-16 | 23/3/2016 | 100% | 1571038 | 100% |  |  | Final
18 | BDRIDP/JHL/RJP/CCA-Rd/04 | Improvement of road from Akoner hat-Hawladerhat via A. Rahim Khan house road by BC from ch.2250-3500m (ID No.542844032). | 542844032 |  | 1.25 |  |  |  |  | 5765111 | 57,62,945.38 | M/s. Islam Brothers | 2015-07-10 | 14-10-15 | 13-10-16 | 2016-12-08 | 100% | 5762945 | 100% |  |  | Final
19 | BDRIDP/JHL/RJP/CCA-Rd/05 | Improvement of road from Hazirhat-M.Fuluher Junior high School via Rola hat road by BC rom ch.2580-3000m. (ID No.542844033) | 542844033 |  | 0.42 |  |  |  |  | 2080393 | 2078697.38 | M/s. Islam Brothers | 16-10-15 | 13-10-15 | 14-10-16 | 13-8-16 | 100% | 2078697 | 100% |  |  | Final
20 | BDRIDP/JHL/RJP/UZ-St/02 | Construction of 2Nos. 2.00mx2.00m RCC Box culvert on Mollar hat R&H-Sreemontokathi-N. Pingri via Balarjore hat GC from ch.206m & 328m. | 542842004 | [5 empty] | 4 | 1612762 | 1611324.23 | M/s. Prince & Co. | 2015-08-10 | 15-10-15 | 14-10-16 | 20-3-16 | 100% | 1611324 | 100% |  |  | Final
21 | BDRIDP/JHL/RJP/UZ-St/03 | Construction of 2Nos. 1.83mx1.83m & 1no. 2.60mx2.60m RCC Box culvert on Nizamia high School to North palot LG via Baroia high School from ch.469m, 780m & 944m. | 542842010 | [5 empty] | 6.26 | 1634222 | 1632794.82 | M/s. Prince & Co. | 2015-07-10 | 14-10-15 | 13-10-16 | 2016-10-03 | 100% | 1632594 | 100% |  |  | Final
22 | BDRIDP/JHL/RJP/UZ-Rd/02 | Improvement of Mollar hat R&H-Sreemontokathi-N. Pingri via Balarjore hat GC road by BC from ch.4800-5862m. (ID No.542842004) | 542842004 |  | 1.06 |  |  |  |  | 6629410 | 6627929.05 | M/s. Prince & Co. | 2015-11-10 | 17-10-15 | 16-10-16 | 16-8-16 | 100% | 6371268 | 100% |  |  | Final
23 | BDRIDP/JHL/RJP/UZ-Rd/03 | Improvement of Nizamia high School to North palot LG via Baroia high School by BC from ch.5700-6700m (ID No.542842010) | 542842010 |  | 1 |  |  |  |  | 6350109 | 6348690.19 | M/s. Prince & Co. | 2015-12-10 | 19-10-15 | 18-10-16 | 17-8-16 | 100% | 6348690 | 100% |  |  | Final
24 | BDRIDP/JHL/RJP/UZ-st/05 | (a) Construction of 1 no 2.00m*2.00m RCC Box culvert on Mirer hat-Nizamia -Baroia-Niamoti ( included kacharibari hat connection from Jiza road ch. 6050m) road at ch. 490m (ID no. 542842009) (b) Construction of 1 no RCC Box culvert on Al-Madina Zame Mosque connecting road connect with Nizamia High School Baroia High School road at ch. 2410m connecting road from ch. 00-90m at ch. 5.00m ( ID no 542842010) | 542842010 |  | 0.09 |  |  |  | 6 | 1918662 | 1702549.71 | M/s. H. R Enterprise | 2015-07-10 | 14-10-15 | 13-04-16 | 24/4/2016 | 100% | 1702549 | 100% |  |  | Final
25 | BDRIDP/JHL/RJP/CCA-Rd/09. | Improvement of road from Naykathi Bhandaria RHD Amtola Bazar to Farazi Bari via in front side of Hamej Uddin Memorial H/S road by BC from ch 1350-2450m (ID NO 542844103) | 542844103 |  | 1.1 |  |  |  |  | 4718479 | 3775161.38 | M/s. Arafat Traders | 22/05/16 | 13-10-15 | 14-10-16 | 13-4-16 | 100% | 3775160 | 100% |  |  | Final
26 | BDRIDP/JHL/RJP/UZ-Rd(R0/05 | (a) Rehabilitation of road from Mirerhat-Nizamia-Bproia-Niamoti (included kacharibari hat connection ) ( From Jica road ch. 6050m) road by BC from ch. 00-690m with 2.00m*2.00m Box culvert at ch. 490m (ID No. 542842009) (b) Improvement of road from Al-Madina Zame Mosque connecting road connect with Nizamia High School Baroia High School road at ch. 2410m connecting road from ch. 00-90m (ID.542842010) | 542842010 |  | 0.69 |  |  |  | 2 | 3661898 | 2747898.28 | M/s. Arafat Traders | 22/05/16 | 19-10-15 | 18-10-16 | 28-6-16 | 100% | 2747897 | 100% |  |  | Final
27 | BDRIDP/JHL/RJP/CCA-St/09 | Construction of 1 No 6.10m span RCC OFC; 1 No 2.50xm2.50m & 4 Nos 1.83mx1.83m RCC Box culvert on Rajapur-Vandaria Highway road side Moulana Nurul Islam Howlader bari to Moulana Sekander Ali Hawlader bari road at ch.89m, 950m,318m,523m,615m & 825m (ID No. 542845120) under Rajapur, District: Jhalakathi | 542845120 | [5 empty] | 15.92 | 3256782 | 2301620.52 | M/S Badol Construction | 20/01/2016 | 2016-01-04 | 2016-09-11 | 2016-05-07 | 100% | 2294744 | 100% |  |  | Final
28 | BDRIDP/JHL/RJP/CCA-Rd/10 | Improvement of road at Rajapur-Vandaria Highway roadside Moulana nurul islam Howlader bari road by HBB from ch.00-1000m (ID: No:542845120) under Rajapur, District: Jhalakathi | 542845120 |  | 1 |  |  |  |  | 2618960 | 2410939.64 | M/S Badol Construction | 2018-10-06 | 2016-01-04 | 2016-09-11 | 2016-05-07 | 100% | 2331587 | 100% |  |  | Final
29 | BDRIDP/JHL/RJP-UN-Rd(r)/01 | Rehabilitation of Rajapur Bazar Napiter hat-Sunder-Badurtala hat. from ch.5835.00-7885.00m By BC with 2Nos. 1.83mx1.83m & 1 Nos. 2.00mx2.00m RCC Box Culvert at ch.6431.00m, 7583.00m & 6594.00m (ID No.542843003)under Rajapur Upazila, District: Jhalakathi | 542843003 |  | 2.05 |  |  |  | 5.66 | 7151740 | 7149545 | M/S Islam Brothers | 21/5/2018 | 29-5-16 | 28-05-17 | 28-5-17 | 100% | 7149479 | 100% |  |  | Final
30 | BDRIDP/JHL/RJP-UN-Rd(R)/06 | Rehabilitation of Rajapur Saturia Miarhat-Pangasia-Haldarkhali R&H via Libubunia GC from ch.18890.00m-20150.00m by BC. with 2 Nos. 1.83mX1.83m RCC Box Culvert at ch.19026.00m & 20096.00m (ID No.542842003) under Rajapur Upazila, District: Jhalakathi | 542842003 |  | 1.26 | 1.26 |  |  | 1.83 | 8051826 | 8050211 | M/S Islam Brothers | 21/5/18 | 29-5-16 | 28-05-17 |  | 70% | 7245485 | 90% | 804726 | BG 17-8-17 | 2nd R/A
31 | BDRIDP/JHL/RJP-UZ-St/06 | Construction of 23.00m Long RCC Girder Bridge on Road from Mollar hat R&H-Sreemontokathi-N.Pingri via Balarjore hat GC at ch.5400.00m. (ID No.542842004) under Rajapur Upazila, District: Jhalakathi | 542842004 | [5 empty] | 23 | 34885014 | 34880069.95 | M/S Islam Brothers | 2018-04-06 | 29-5-16 | 28-05-17 | 30-6-18 | 100% | 33880621 | 100% |  |  | Final
32 | BDRIDP/JHL/RJP/CCA-St/08 | Construction of 2 Nos 6.10m;2 Nos 2.0mx2.0m and 2 Nos 1.83mx1.83m RCC Box Culvert on Naykathi Bhandaria RHD Amtola Bazar to Farazi Bari via in front side of Hamej Uddin Memorial H/S road at ch.1368m, 1974m, 1538m, 1700m, 1494m & 1600m (ID NO:542844103) | 542844103 | [5 empty] | 17.86 | 4293302 | 3080912.94 | M/S Sayed Enterprise | 2018-04-04 | 27/01/2016 | 27/07/2016 | 28-02-16 | 100% | 3080889 | 100% |  |  | Final
33 | BDRIDP/JHL/RJP/CCA-Rd/15 | Improvement of Bishwas Bari Baily Bridge to Altef Choukider via Isahakia S.Md. Road by BC at ch.00-1140m Including 5 Nos U-Drain at ch.210m 310m 442m 850m & 1068m.ID No. 542845031. Salvage Amount-854101.00 BDT | 542845031 |  | 1.14 |  |  |  | 3.125 | 7514094 | 7478455.01 | M/S Arafat Traders | 2018-03-14 | 17/6/2018 | 2018-10-12 | 26-11-18 | 100% | 7408547 | 100% |  |  | Final
34 | BDRIDP/JHL/RJP/CCA-Rd/14 | Improvement of Jhalokathi Bhandaria R&H Road Galua Bazar khalek shop-Naikathi Bhandaria R&H Road Tarabunia Afsaruddin High School-Galua Durgapur Junior High School by BC at ch.2213m-3020m. Including 1N0 2.00m2.00m RCC Culvert & 2 Nos 0.625m0.6m U-Drain at ch.2587m2563m &2903m. ID N.542844089 | 542844089 |  | 0.807 |  |  |  | 3.25 | 5947290.001 | 6005761.57 | SHAMIM ENTERPRISE (PVT) LTD | 2019-09-18 | 28/5/2018 | 27/11/2018 | 2019-07-03 | 100% | 5974812 | 100% |  | BG 17-5-21 | Final
35 | BDRIDP/JHL/RJP/CCA-Rd/13 | Improvement of Samoby R&H- Akhonerhat via Mir Amzad Hossain house Road by BC at ch.00-1100m. including 1NO U-Drain at ch.423m. ID No. 542844035. Salvage Amount-409797.00BDT | 542844035 |  | 1.1 |  |  |  | 0.625 | 6494995 | 5845495.86 | SHAMIM ENTERPRISE (PVT) LTD | 16-10-2019 | 28/5/18 | 27/11/18 | 26-06-19 | 100% | 5818215 | 100% |  | BG 21-5-18 | Final
36 | BDRIDP/JHL/RJP/CCA-Rd/12 | Improvement of road from Hazirhat-M. Fuluher-Junior high school via Roia hat at ch.1666m-2580m including 1No. 4.00mx4.00m two vent and 1no.1.50mx1.50m RCC box culvert at ch.1906 & 2538m. | 542844033 |  | 0.914 |  |  |  | 5.5 | 9026189 | 9025202 | M/S Arafat Traders |  | 2018-11-06 | 2018-10-12 | 16-12-18 | 100% | 9024852 | 100% |  | BG 2-12-18 | Final
37 | BDRIDP/JHL/RJP/CCA-St/10 | Construction of 20m long RCC girder bridge on Galua UP Complex-Kathakhali Bazar via Galua D. Islamic Madrasha Road at ch.1188.00m (road ID: 542844090) | 542844090 | [5 empty] | 20 | 14438073.68 | 12994266.312 | M/S Abul Kalam Azad | 2019-06-16 | 2018-11-04 | 2019-10-04 | 2019-10-04 | 100% | 12991715 | 100% |  | BG 19-6-19 | Final
38 | BDRIDP/JHL/RJP/CCA-Rd/11 | Improvement of road from Somobay (RHD)to natun Hat road at ch.00m-1000m including 1 No4.00mx4.00m (two vent) and 1 No2.00mx2.00m RCC box culvert at ch.555.00m and 863.00m (ID No: 542845042) | 542845042 |  | 1 | 1 |  |  | 6 | 9792318.21 | 8813086.38 | SHAMIM ENTERPRISE (PVT) LTD |  | 2018-03-21 | 2019-03-20 |  | 70% | 2502049 | 28% | 6311037.38 | BG 21-4-19 | Ist R/A
39 | BDRIDP/JHL/RJP/UN-Rd(R)/02 | (a) Rehabilitation Work Rajapur Bazar-Napter Hat via Mathbari UP Office Road at Ch. 00-1200m including 225 m Bazar Link Road & 530m RCC Drain (Road ID 542843003) [Salvage Cost-55496.00 Taka] | 542843003 |  | 1.2 | 1.2 |  |  |  | 25142789.72 | 25137152.018 | M/S Mohiuddin Ahmed & M/S Sayed Enterprise (JV) Address: Post office road, Madho Chandkathi, Jhalakathi |  | 2019-09-25 | 2020-03-24 |  | 100% | 17919859 | 71% | 7217293.018 |  | R/A
40 | BDRIDP/JHL/RJP/CCA-St/11 | Construction of 35.00m PSC Girder on Tarabunia Afsaruddin High School - Galua Durgapur Junior High School Road (Road ID-502844089) | [6 empty] | 35 | 35155356.6 | 33872186.083 | M/S Rupali Construction, Head office: 166/147, Kalibari Road, Barisal; Branch Office: Alam Brothers Building (2nd floor), Hospital Road, Barisal. | 17-09-14 | 23/10/2019 | 22-10-2019 |  | 95% | 31824092 | 86% | 2048094.083 |  | 2nd R/A
41 | BDRIDP/JHL/RAJ/CCA-Rd/16 | Improvement of Road from Barishal Khulna R&H - Sangor at Ch. 00m-1275m including 03 Nos. 1.0m x 1.0m 01 No 1.50m x 1.50m & 2.50m x 2.50m RCC Box culvert at Ch. 60m 245m 1071m 128m & 382m ( Road ID No. 542845009, Salvage Cost 697773 Taka) | 542845009 |  | 1.275 | 1.275 |  |  | 7 | 11219492.32 | 10377879.233 | M/S Mother Engineering, Munni Nibash, Battala, Barisal. | 14-09-14 |  |  |  | 100% | 7966013 | 76% | 2411866.233 |  | R/A
42 | BDRIDP/JHL/RAJ/Ghat/01 | Rajapur West Galua Durgapur GPS Ghat |  | 1 | [5 empty] | 2636489.65 | 2504665.16 | M/S Tahasin Enterprise,Pro: Aslam Hossain,Maluhar,Banaripara,Barisal. | 25/12/14 | 2019-06-23 | 2019-12-22 |  | 15% | 0 | 100% | 2504665.16
42 |  | Sub Total Tk= |  |  | 26.022 | 4.735 | 0 | 0 | 282.89 | 295245501.181 | 275921216.443 |  | 28/1/15 |  |  |  |  | 258601112 |  | 21297681.874
| Upazila: Sadar | [11 empty] | 2015-10-05
1 | BDRIDP/JHL/SAD/CCA-Rd-01 | Improvement of road by HBB from Rahmatpur Gorkhay Bridge-Khajuria via Mirakati School from ch.00-1000m under Sadar Upazila. | 542404061 |  | 1 |  |  |  |  | 2530318 | 1954251.17 | Md. Feroj Alam | 27-05-2015 | 24-09-14 | 15-01-15 | 27/2/2015 | 100% | 1954251 | 100% |  |  | Final
2 | BDRIDP/JHL/SAD/CCA-St-01 | Construction of 1 No. 6.00m RCC Girder Bridge on Ramanathpur Gorkhay Bridge-Khajuria via Mirakathi via Mirakathi School road at ch.574m under Sadar Upazila | 542404061 | [5 empty] | 6 | 1998982 | 1296767.19 | M/s. Syed Enterprise | 2015-05-10 | 2014-04-12 | 20/03/2015 | 2015-10-03 | 100% | 1288393 | 100% |  |  | Final
3 | BDRIDP/JHL/SDR/UZ-Rd(R)/02 | Rehabilitation of Atghar GC-Baligona R&H via Ramjankathi Krishi College road by BC at ch.00-1500m (ID542402006) Jhalakathi-S.( salvage amount=BDT1987269.00) | 542402006 |  | 1.5 |  |  |  |  | 8465134 | 6062898.904 | M/S Rashedul Enterprise | 2015-05-10 | 2015-02-01 | 19/11/15 | 25-11-15 | 100% | 6061298 | 100% |  |  | Final
4 | BDRIDP/JHL/SDR/UZ-St/03 | Construction of 6 Nos 1.60mx1.60m RCC Box Culvert Atghor GC-Baligona R&H via Ramjankathi Krishi College road at ch.40m, 300m,505m 700m,800m 1350m (ID 542402006) Jhalakathi-S | 542402006 | [5 empty] | 9.6 | 5161558 | 3264210.725 | M/S Shafiqul Islam | 2015-05-10 | 2015-03-02 | 2016-02-01 | 2016-01-02 | 100% | 2406322 | 74% | 857888.725
5 | BDRIDP/JHL/SDR/CCA-St/02 | Construction of 3 Nos. 9.00m Span RCC Girder Bridge at ch.259m, 918m & 1045m; 1No. box culvert 1.60mx1.60m at ch.860m; 2Nos. 1.22mx1.22m Box Culvert at ch.590m & 820m 1No. 12.00m Span RCC Girder Birdge at ch.1700m. (ID No.542404034) under Sadar Upazila, District: Jhalakathi. | 542404034 | [5 empty] | 45.04 | 11217654 | 11211324.98 | M/S Sifat Enterprise | 28-01-2016 | 17-05-15 | 16-05-16 | 15-5-16 | 100% | 11205749 | 100% |  |  | Final
6 | BDRIDP/JHL/SDR/CCA-Rd/02 | (a) Improvement of HBB road from Goalkanda Harun or Rashid Talukder Bari to Betra road HBB rom ch.00-100m. (ID No.542405313) (b) Construction of RCC Ghatla Goalkanda Harun of Rashid Talukder Bari to Betra road. (ID No.542405313) | 542405313 |  | 0.1 |  |  |  |  | 496934 | 410303.93 | M/S M.M Enterprise | 2019-03-24 | 2015-04-06 | 2015-04-09 | 2015-03-09 | 100% | 408634 | 100% |  |  | Final
7 | BDRIDP/JHL/SDR/UZ-St/02 | Construction of 1Nos. 4.00mx4.00m RCC Box culvert Gabkhan-Guaton via Sekerhat UP including Amrajhuri Road at ch.750m. (ID No.542402005) | 542402005 | [5 empty] | 4 | 3780497 | 3776277.51 | M/s. Prince & Co. | 2019-04-21 | 2015-12-10 | 2016-11-04 | 25/5/2016 | 100% | 3635040 | 100% |  |  | Final
8 | BDRIDP/JHL/SDR/UZ-Rd(R)/01 | Rehabilitation of Gabkhan-Guaton via Sekerhat UP including Amrajhuri Road BY BC at ch.400-1400m. (ID No.542402005) | 542402005 |  | 1 |  |  |  |  | 1745202 | 1744138.04 | M/s. Prince & Co. | 2019-04-29 | 2015-12-10 | 2016-11-04 | 2016-10-04 | 100% | 1744138 | 100% |  |  | Final
9 | BDRIDP/JHL/SAD/CCA-Rd/03. | Improvement of road from Tarpasha LGED HBB to Kubirkati via Bottala (Tarapasha R& H- Jhalakati Swarupkati R&H road via Kubirkati)road by HBB from ch:00-1370m (ID No.542404150) | 542404150 |  | 1.37 |  |  |  |  | 4564723 | 3716578.18 | Md. Zakir Hossain Mia | 2019-06-16 | 2015-12-10 | 2016-11-04 | 28-4-16 | 100% | 3716578 | 100% |  |  | Final
10 | BDRIDP/JHL/SAD/CCA-St/03 | Construction of 04 Nos 1.22mx1.22m Drainage culvert and 2 Nos 2.5mx2.50m RCC Box Culvert & 1 No 6.00m RCC Girder Bridge on Tarapasha LGED HBB to Kubirkati via Bottala (Tarapasha R &H- Jhalokathi Swarupkathi R&H road via Kubirkati) road ch.520m 640m,885m,1100m,1210m, 1350m & 820m (ID No.542404150) | 542404150 | [5 empty] | 15.88 | 4908364 | 3494073 | M/S Sayed Enterprise | 18/09/.2019 | 2016-04-02 | 2016-03-08 | 25/4/2016 | 100% | 3494036 | 100% |  |  | Final
11 | BDRIDP/JHL/SDR/CCA-St/04 | Construction of 36.06m RCC Girder Bridge on Kirtipasha R&H - Shahid Hat Road at Ch 2410m ID No 542404147 (a) Bridge Construction (b) Approach Road (c) Social Safe Guard (d) Site Facilities | [6 empty] | 36 | 24200000 | 21807005 | M/S Mt Builders |  |  | 2020-03-30 |  | 100% | 21807004 | 98% | 1 |  | Final
12 | BDRIDP/JHL/SDR/CCA-Rd/04 | Improvement of Road from Gabindodhabol R&H South Ramanathpur Govt Pry School via Azaharia Madrasha Road Ch. 00-700m including 03 Nos 2X2 m RCC Box Culvert at Ch. 351m 529m and 642m (Road ID No 542404145) [Salvage Cost-1150931 Taka] |  |  | 0.7 |  |  |  | 6 | 7607013.29 | 7226662 | M/S Merry Suppliers | 2020-01-06 | 2019-05-05 | 2019-10-27 |  | 100% | 7221316 | 100% | 5346 | NOA Issued | Final
13 | BDRIDP/JHL/SDR/CCA-Rd/05 | Improvement of road from Kanchabalia Khalpar-Baro Mollik Bari Sayjuddin Master Bari Road at Ch 00-740 m (Road ID-542405160) including 02 Nos 1.22 X 1.22m RCC Box Culvert at Ch 150 m & Ch 450 m |  |  | 0.74 |  |  |  | 2.44 | 5438643.87 | 5166711 | M/S HR Enterprise | 2019-12-12 | 2019-05-11 | 2019-11-05 |  | 60% | 1300000 |  | 3866711 | NOA Issued
14 | BDRIDP/JHL/SDR/UN-RdR/02 | Maintenance of Road on Sekherhat UP-Pwonechayana bazar RHD Road at Ch 00 - 1000m including 01 No 1.60m X 1.60m RCC Box Culvert at Ch 173m ( Road ID - 542403012) |  |  | 1 |  |  | 1 | 1.6 | 3471906.66 | 3301161.32 | M/S Uday Enterprise | 2020-01-06 | 2019-06-23 | 2019-12-22 |  | 100% | 3296880 | 100% |  |  | Final
15 | BDRIDP/JHL/SDR/UN-Rd/01 | (a) Improvement of Road on Ponabalia UP Office-Mohadebpur Bazar at Ch 6260-7110m including 02 Nos 1.22mX1.22m RCC Box Culvert at Ch 6820 & 7108m under Sadar Upazila, District: Jhalokathi under Sadar Upazila, District: Jhalokathi (Road ID-542403001) (b) Improvement of Road on Keora UPC-Kirtipasha Bazar at Ch 00-1013m including 03 Nos 1.22mX1.22m RCC Box Culvert at Ch 367m, 596m & 703m under Sadar Upazila, District: Jhalokathi (Road ID-542403004) | Road ID-542403001& Road ID-542403004 |  | 1.863 |  |  |  | 6.1 | 14560973.12 | 13090294.233 | M/S Abul Kalam Azad,Azad Bhaban, Muslimpara, Patuakhali Sadar, Patuakhali. | 2019-11-18 | 2019-09-25 | 2019-03-24 |  | 60% | 3300000 | 100% | 9790294.233
16 | BDRIDP/JHL/SDR/CCA-Rd/06 | a) Improvement of Road from Barisal-Jhalokathi Road Chreerampur to Sugandia RHD Khowkhir Mill Gar-Sugandia RHD Road via Dibakorkathi High School road from Ch.0.00m-1200m & H/S. GPS Extended UP to Kalizira river via Hazi Bari road at Ch.0.00m-332m including 05 Nos 0.90mX0.90m U-Draion at ch.510m610m950m1010 & Dibakorkathi High School Road at Ch.50m under Sadar Upazila District Jhalakathi ( Road ID 542404035, Salvage Cost: 286148 Taka ) |  |  | 1.532 |  |  |  | 4.5 | 11658876.54 | 10451929.118 | M/S S H Enterprise ,Amirgonj, Mehendigonj, Barishal | 2019-09-09 | 2019-09-16 | 2020-03-15 |  | 40% | 1200000 | 100% | 9251929.118
17 | BDRIDP/JHL/SDR/CCA--Rd/07 | a Improvement of Road Pipolita School-Masud Howlader Bari South Pipolita Nehal Pur via Mazi Bari Road at Ch 0.00m-1000m Road ID-542404123 Salvage Cost 1080282 Taka b Improvement of Road from Rajpasha Board School-South Rajpasha Pry. School via Mazba Miah Bari at Ch 00-600m including 01 No 4.57 Span RCC slab Culvert & 02 Nos 2X2 RCC Box Culvert at Ch 293m & 523m Road ID-542404090 Salvage Cost 713467 Taka |  |  | 1.6 |  |  |  | 8.57 | 13993111.6 | 13976090.57 | Ithuwan & MM JV |  | 2020-01-13 | 2020-06-18 |  | 60% | 2900000 | 100% | 11076090.57 |  | 346482
18 | BDRIDP/JHL/SDR/CCA-Rd/08 | Improvement of Road from Kirtipasha Upazila Road - Mirakati Sultan Hossain Khan High School via Khajura Pry School Road at Ch.00-1400m including 4 Nos 1.5m X 1.5m RCC Box Culvert & 1 No 9.00m Span RCC Girder Bridge at Ch. 229m 419m 769 1055m & 1344m respectively (Road ID 542404148) (Salvage Cost : 275194 Taka) |  |  | 1.4 |  |  |  | 15 | 15387631.81 | 15368697.94 | M/s Sifat Enterprise |  | 2019-12-19 | 2020-06-18 |  | 60% | 5000000 | 100% | 10368697.94 |  | 331921
19 | BDRIDP/JHL/SDR/CCA-Rd/09 | Improvement of Road from Gabindodhabol R&H - Pipolita Hat at Ch. 00-1000m including 1 No 9.00m Span RCC Girder Bridge & 2 Nos 2mX 2m RCC Box Culverts at Ch. 945m 593m 754m respectively Road ID 542404164 Salvage Cost1823479 Taka |  |  | 1 |  |  |  | 13 | 11990623.57 | 11979314.65 | M/S Sayed Enterprise |  | 2020-01-13 | 2020-06-17 |  | 50% | 1002567 | 8% | 10976747.65 |  | R/A
20 | BDRIDP/JHL/SDR/UN-RdR/03 | Periodic Maintenance of road on Kirtipasha UP Office-Panjiputhipara GC at Ch. 3150m-3500m including of 01 No 2.0m x 2.0m RCC Box Culvert at Ch 3300m Road ID542403021 Salvage Cost 249426 Taka |  |  | 0.35 |  |  |  | 2 | 3264359.32 | 3101141.35 | M/S Monoara Enterprise | 2019-11-06 | 2019-11-12 | 2020-05-11 |  | 100% | 1000000 | 100% | 2101141.35 |  | 331920
21 | BDRIDP/JHL/SDR/UZ-RdR/03 | (a) Periodic Maintenance of Jhalokathi RHD-Bermohal via Himanandakati RHD Road from at ch.250m-989m & ch.1160m-1923m. ID No.542402001 b Periodic Maintenance of Jhalokathi HQ-Gagonhat via Manpasha GC Road from ch.2000m-3500m [Road ID No.542402002] |  |  | 3.002 |  |  |  |  | 7186396.29 | 6827076.47 | M/S Monoara Enterprise | 2015-10-05 |  |  |  | 100% |  | 100% | 6827076.47 |  | 389418 Evaluation on goning
22 | BDRIDP/JHL/SDR/UZ-Rd/04 | Improvement of Road from Jhalokathi RHD-Bermohal via Himanandi Road from at Ch. 1923m-2900m including 02 No 1.6mX1.6m RCC Box Culvert at Ch. 2758m and 2800m respectively Sadar Road ID-542402001 (Salvage Cost: 643753.00) |  |  | 0.977 |  |  |  | 3.2 | 7619549.83 | 7238572.33 | M/S H.N Builders | 2015-04-10 |  |  |  | 30% |  | 100% | 7238572.33 |  | 394681 Evaluation on going
23 | BDRIDP/JHL/SDR/UN-Rd/04 | Improvement of Road from Jhalokathi-Choupala Hat via Basonda UP Road at Ch. 3069m-3800m including 01 No 2.0mX2.0m RCC Box Culvert at Ch. 3579m Sadar Road ID-542403002 (Salvage Cost: 1923746.00) |  |  | 0.731 |  |  |  | 2 | 7005121.96 | 6654865.82 | M/S Monoara Enterprise | 2015-04-10 |  |  |  | 10% |  | 100% | 6654865.82 |  | 394682 Evaluation on going
23 |  | Sub Total Tk= |  |  | 19.865 | 0 | 0 | 1 | 180.93 | 178253573.86 | 163120345.43 |  | 2015-04-10 |  |  |  |  | 83942206 |  | 79015362.206 | 0
Upazila: Kathalia | [12 empty] | 2015-06-10
1 | BDRIDP/PRJ/KTH/Ghat/01 | Construction of RCC Ghatla Kachua Bazar & Connecting road. | [7 empty] | 2970893 | 2968261.99 | M/S Syed Enterprise | 2015-07-10 | 17-05-15 | 16-11-15 | 23-4-15 | 100% | 2393365 | 81% | 574896.99 |  | RCC Road & salasing
2 | BDRIDP/JHL/KTH/UN-BH/01 | Construction of 15.00m Girder Bridge over Jugirkhal under Checrirampur Union Parishad at ch.1250m on Tasserer Kheyaghat-Ghosherhat via Tarabunia Bazar road.(ID No.542433019) | 542433019 | [5 empty] | 15 | 12221793 | 12217013.32 | M/s. Islam Brothers | 2016-01-12 | 2015-11-10 | 2016-10-04 | 17-11-17 | 100% | 12215010 | 100% | 0 |  | Final
3 | BDRIDP/JHL/KTH/UZ-St/01 | Construction of 1no. 2.00mx2.00m RCC Box Culvert on Citky R&H Road-Awrabunia GC road at ch.3686m. (ID No.542432004) | 542432004 | [5 empty] | 2 | 638564 | 638686.52 | M/s. Islam Brothers | 19-6-17 | 2015-11-10 | 2016-10-04 | 2016-10-04 | 100% | 632624 | 100% | 0 |  | Final
4 | BDRIDP/JHL/KTH/CCA-St/02 | Construction of 4Nos. 1.50mx1.50m and 1no. 2.50mx2.50m RCC Box Culvert on Uttar Talgachia Cyclone Shelter Connecting Road at ch.175m, 260m 470m, 675m & 626m. (ID No.542435157) | 542435157 | [5 empty] | 8.5 | 2543444 | 2541783.81 | M/s. Islam Brothers | 19-6-17 | 2015-11-10 | 2016-10-04 | 22-6-16 | 100% | 2522089 | 100% | 0 |  | Final
5 | BDRIDP/JHL/KTH/UZ-Rd/01 | Improvement of road form citky R&H Road-Awrabunia GC road by BC from Ch.3000-4000m. (ID No.542432004) | 542432004 |  | 1 |  |  |  |  | 5856260 | 5855701.2 | M/s. Islam Brothers | 20-6-17 | 13-10-15 | 2016-12-10 |  | 100% | 2385271 | 44% | 3470430.2 | BG 14-10-16 | R/A
6 | BDRIDP/JHL/KTH/CCA-Rd/01 | Improvement of road from Uttar Talgachia Cyclone Shelter Connecting Road by BC from ch.00-1000m. (ID No.542435157) | 542435157 |  | 1 |  |  |  |  | 5000355 | 4999453.5 | M/s. Islam Brothers | 2017-03-07 | 14-10-15 | 13-10-16 |  | 100% | 2000000 | 40% | 2999453.5 | BG 19-12-17 | R/A
7 | BDRIDP/JHL/KAT/UZ-Rd/ 02 | Improvement of road from Aurabunia GC to Mativanga via Satany Bazar. by BC at Ch. 1400.00m-2900.00m.(ID-542432007) Salvage cost-194710.00BDT | 542432007 |  | 1.5 |  |  |  |  | 7268757 | 7265447.47 | M/S Salim Enterprise | 2018-05-06 | 2016-07-12 | 2017-06-09 | 2017-05-09 | 100% | 7262130 | 100% | 0 |  | Final
8 | BDRIDP/JHL/KTH/UZ-St/02 | Construction of 3 nos 1.0mx1.0m & 2 Nos 2.00mx2.00m RCC Box Culvert on Kaikhali GC-Amua GC via Goserhat Road at ch.725m915.00m 1073m669.00m & 1345.00m | 542432005 | [5 empty] | 5 | 2311047 | 2979942 | M/S Ziaual & Brothers | 2018-02-07 | 26-6-17 | 2017-12-25 |  | 100% | 1552300 | 0% | 1427642 |  | R/A
9 | BDRIDP/JHL/KTH/UZ-St/03 | Construction of 1 No 4.00mx4.00m 6 Nos 1.00mx1.00m & 4 Nos 2.00mx2.00m RCC Box Culvert on Kaikhali GC-Amua GC via Goserhat Road at Ch. 5042.00m 2670.00m3178.00m3305.00m3580.00m3720.00m5485.00m2340.00m4003.00m4735.00m & 5690.00m | 542432005 | [5 empty] | 10 | 6895815 | 6206233.5 | M/S Ziaual & Brothers |  | 26-6-17 | 25-6-18 |  | 100% | 2917545 | 47% | 3288688.5 |  | R/A
10 | BDRIDP/JHL/KTH/UZ-Rd/03 | Improvement of Road from Kaikhali GC-Amua GC via Gosherhat by BC at ch0-00m-1600m | 542432005 |  | 1.6 |  |  |  |  | 11050182 | 10829158.79 | M/S Sayed Enterprise | 2019-06-24 | 27-6-17 | 25-6-18 | 2019-02-03 | 100% | 10829158 | 100% | 0 | BG 7-12-18 | Final
11 | BDRIDP/JHL/KTH/UZ-RdR/04 | Rehabilitation of Road by BC Kaikhali GC-Amua GC via Goserhat at Ch.1600.00m-5884.0m | 542432005 |  | 4.286 |  |  |  |  | 29478960 | 29474249 | M/S Santo Enterprise |  | 2017-10-07 | 2018-08-07 |  | 100% | 23163813 | 79% | 6310436 | BG 18-6-18 | R/A
12 | BDRIDP/JHL/KTH/UN-St/03 | Construction of 12.00m Long RCC Girder Bridge on Aurabunia UP office -Munshirabad-Chaighar Madrasha-Mollaharhat to Binapani Bazar at ch.2218.00mRoad ID-542433007 | [6 empty] | 12 | 14484962.06 | 13036465.854 | M. M. Builders & Engineers Ltd. |  | 2018-12-06 | 2018-11-06 | 2019-06-11 | 100% | 13036460 | 100% | 0 | PO | Final
13 | BDRIDP/JHL/KTH/UN-St/02 | Construction of 32.00m Long PC Girder Bridge over Binapani River on Chechrirampur UP office-Binapani Bazar at ch.3300.00m.Road ID-542433004 | [6 empty] | 32 | 21770095.07 | 19593085.563 | M/S. Amir Engineering Corporation- M.M. Builders & Engineers Ltd. (JV) |  | 2018-09-07 | 2019-08-07 |  | 100% | 19279228 | 98% | 313857.563 | BG 23-06-19 | R/A
14 | BDRIDP/JHL/KTH/UZ-St/04 | Construction of 60.06m RCC Girder Bridge on Aworabunia GC to mativanga Road via satany bazarover Aworabunia khal at ch.5950m ID No- 542432007 | 542432007 | [5 empty] | 60.06 | 37458851.78 | 33422158.66 | M/S Selim Sifat JV | 17/11/2016 | 2019-11-11 | 2020-11-10 |  | 35% |  |  | 37458851.78
15 | BDRIDP/JHL/KTH/CCA-Rd/02 | Improvement of Road by BC Choudda Boalia Khal East P/B of Naboyan House Road from Ch 00-500m including 02 Nos 1mX1m RCC Box Culvert at Ch 190m & 420m under Kathalia Upazila District Jhalokathi [ Road ID-542434028 ] | 542434028 |  | 0.5 |  | 2 |  |  | 4404077.98 | 4183874.08 | M/S Lucky Enterprise | 17/11/2016 | 2019-07-01 | 2019-12-30 | 25/12/2019 | 100% | 4178438 | 44% | 5436.08 |  | Final
|  | Earth Work | [7 empty] | 8857674 | 8169836 |  | 2017-03-07 |  |  |  | 100% | 7234416 | 100%
15 |  | Sub Total Tk= |  |  | 9.886 | 0 | 2 | 0 | 144.56 | 173211730.89 | 164381351.257 |  | 15-6-17 |  |  |  |  | 111601847 |  | 55849692.613
Upazila: Nalchity | [12 empty] | 29-8-17
1 | BDRIDP/JHL/NAL/UN-Rd/01 | Improvement of road from Simultala-Manpasa at ch. 00-2030.00m (ID No. 54233006) under Nalchity Upazila. |  |  | 2.03 |  |  |  |  | 11816000 | 11814930.58 | M/s. Ithuwan Builders | 28/3/2018 | 24/11/2016 | 23/11/17 | 2018-09-23 | 100% | 11582462 | 100% | 0 |  | Final
2 | BDRIDP/JHL/NAL/UN-St/ 01 | Construction of 2 Nos 9.15m, 1 No. 6.10m & 2 Nos 4.57m span OFC on Simultala-Manpasa road at ch. 15.00m, 2304.00m, 594.00m, 950.00m, & 1720.00m. ( ID N0. 54233006) under Nalchity Upazila | [6 empty] | 33.54 | 9405000 | 9402370.09 | M/s. Ithuwan Builders | 2018-03-08 | 24/11/2016 | 23/11/17 | 2017-09-15 | 100% | 9394068 | 100% | 0 |  | Final
3 | BDRIDP/JHL/NAL/UN-St/02 | Construction of 21m span RCC Girder Bridge on Nachanmohal Nachanmahal Up to Kulkathi UP road at ch.4855.00m road id | 542733007 | [5 empty] | 21 | 15592528 | 14033275.2 | M/S M. M Enterprise | 23/5/2018 | 2017-10-07 | 2018-09-07 | 2018-06-25 | 100% | 14033275 | 100% | 0 |  | Final
4 | BDRIDP/JHL/NAL/CCA-St/01 | Construction of 15.00m span RCC Girder Bridge on Kumarkhali Bazar-Dapdapia UP Kumarkhali GPS cum CS Connecting Approach Road via Timirkathi H/S Road at ch.570.00 Road. | 512734102 | [5 empty] | 15 | 15592528 | 14080510.8 | M/S Sifat Enterprise | 2019-03-17 | 22-6-17 | 21-6-17 | 2018-04-14 | 100% | 14080510 | 100% | 0 |  | Final
5 | BDRIDP/JHL/NAL/UN-St/04 | Construction of 23m Long RCC Girder Bridge on Simultala to Manpasa road at Ch. 3100m. under Nalchity Upazila Jhalokathi. | 542733006 | [5 empty] | 23 | 14150438 | 15614084 | SE & BC (JV) |  | 2017-05-09 | 2018-04-09 | 2018-06-15 | 100% | 15614083 | 100% | 0 |  | Final
6 | BDRIDP/JHL/NAL/UN-RD/02 | Improvement of road from Kusangal UP-Seota Bazar road by BC at Ch.1508m-2910m under Nalchity Upazila Jhalokathi. 107982 | 542733005 |  | 1.402 |  |  |  |  | 9383348 | 8445013.2 | M/s SHAMIM ENTERPRISE (PVT) LTD 4. K.B. Ismail road, Mymensingh | 2019-02-10 | 2018-04-04 | 2019-03-04 |  | 100% | 8445013 | 62% | 0.2 |  | Final
7 | BDRIDP/JHL/NAL/UN-St/03 | Construction of 1no 1.5m RCC Culvert & 1no 9.00m span RCC Girder Bridge on Kusangal UP-Seota Bazar road at Ch.2420m & 2080m. under Nalchity Upazila Jhalokathi. 139187 | 542733006 | [5 empty] | 10.5 | 2334946 | 2101451.4 | M/s SHAMIM ENTERPRISE (PVT) LTD 4. K.B. Ismail road, Mymensingh | 2019-09-18 | 2018-03-22 | 2019-03-14 | 2018-06-21 | 100% | 2101461 | 100% | 0 |  | Final
8 | BDRIDP/JHL/NAL/Ghat/01 | Construction of RCC Ghatla of K.M hat in Nalchity Upazila. | [7 empty] | 3062823.35 | 2909682.18 | M/S Jamal & Brothers | 2019-09-18 | 30/5/2018 | 30/11/2018 | 2018-11-15 | 100% | 2707105 | 100% | - |  | Final
9 | BDRIDP/JHL/NAL/CCA-Rd/02 | Improvement of Road from Saitpakia Bazar-Promoher Extended Road UP to Sharif House at Ch 00-300m including 01 No 3-Vent 4.00m X4.00m RCC Box Culvert at Ch 15.00m [ ID No 542734069 ] |  |  | 0.3 |  |  |  | 12 | 4868134.41 | 4624727.69 | M/S M.T Builders, Pro: Kamal Sharif, 201, Palbari Road,Jhalakathoi |  | 2019-03-24 | 2019-09-23 |  | 60% | 1652057 |  | 2972670.69 | Evaluation on Going
10 | BDRIDP/JHL/NAL/CCA-Rd/03 | (a) Improvement of road from Baro Premhar (Mallick Bari Jame Mosque)-Bhairabpasa via Gonjur Bari, Sharif Bari & Soto Premhar GPS Road at Ch. 00-800 m including 03 Nos 1.5 X 1.5 m RCC Box Culvert at Ch 358m 378m & 557m (Road ID 542735088) [ Salvage Cost 715960 Taka ] (b) Improvement of road from East Dapdhapia UP Office Nilkhola Dapdapia Chowmatha Borobari dapdapia UP at Ch 2400-3000m including 01 No 1.5 X 1.5 m RCC Box Culvert at Ch 2850m (Road ID 542734029) [Salvage Cost 613475 Taka] | 542735088 542734029 |  | 1.4 |  |  |  | 6 | 13044466.88 | 12999141.229 | Selim & Sifat JV,364, Middle Chandkati, Jhalokati | 2020-03-24 |  |  |  | 80% | 3009722 |  | 9989419.229
11 | BDRIDP/JHL/NAL/CCA-Rd/01 | Improvement of Road from Dorgabari - Jurkati UZR South Dudharia Ponchaet khal Bridge to Kodamtala Bazar at Ch 00m-1000m including 01 No 2mX2m & 02 No 1.5mX1.5m RCC Box Culvert at Ch 220m 521m & 807m ID No 502734135 | 542734135 |  | 1 |  |  |  | 5 | 9207399.79 | 8747029.8 | M/S Shampa Construction |  | 2019-02-17 | 2019-08-16 | 22/09/2019 | 100% | 8747029 | 100% | 0 |  | final
12 | BDRIDP/JHL/NAL/CCA-Rd/04 | a) Improvement of Kumarkhali Bazar to Dapdapia UP via Timirkathi H/S form Ch 00-600m including 02 Nos 2.0 X 2.0m & 02 Nos 1.50 X 1.50m RCC Box Culvert at Ch 164m 238m 370m & 520m respectively Road ID 542734102 Salvage Cost NIL b) Improvement of Taltala Dopabari-Mara Bishkhali form Ch. 1000-2000m including 01 Nos 4.57m Span RCC Slab Culvert at Ch 1968m 01 No 2.0 X 2.0m & 02 Nos 1.50 X 1.50m RCC Box Culvert at Ch. 1880m 1150m & 1840m respectively Road ID 542734044 Salvage Cost 1145251.00 Taka | Road ID 542734102&Road ID 542734044 |  | 1.6 |  |  |  | 16.57 | 17813627.59 | 16382049.869 | M/S Abul Kalam Azad,Azad Bhaban, Muslimpara, Patuakhali Sadar, Patuakhali. | 0 | 2019-09-25 | 2020-03-24 | 2.4444 | 65% | 3700000 |  | 12682049.869 |  | Salvage Cost : 1145251.00
13 | BDRIDP/JHL/NAL/UN-Rd/03 | Improvement of Sher-E-Bangla Bazar-Mollahat UP via Amtali GPS at Ch. 2000m-3300m Under Nalchity Upazila District Jhalakathi ( Road ID 542733008, Salvage Cost: 803136 Taka) |  |  | 1.3 |  |  |  |  | 10106700.15 | 10090364.902 | M/S Mohiuddin Ahmed & M/S Sayed Enterprise (JV),Post office road, Madho Chandkathi, Jhalakathi |  | 2019-09-25 | 2020-03-24 |  | 60% |  |  | 10090364.902
14 | BDRIDP/JHL/NAL/UN-Rd/04 | Improvement of Road from Nachanmohal UP-Takerhat Bazar-Kulkathi UP at Ch. 5230m-5970m including 01 No 1.5mX1.50m RCC Box Culvert at Ch. 5420m Nalcity Road ID-542403012 (Salvage Cost: 695471.00) |  |  | 0.74 |  |  |  | 1.5 | 6953844.29 | 6606152.07 | M/S Tuba Enterprise |  |  |  |  | 50% |  |  |  |  | 394679 Evaluation on going
15 | BDRIDP/JHL/NAL/CCA-Rd/05 | Improvement of Road from Manpasha Bazar-Shampur Bazar at Ch. 0.00m-1250m including 01 No 1.5mX1.50m RCC Box Culvert at Ch. 430m Nalcity Road ID-542404039 (Salvage Cost 1032956.00) |  |  | 1.25 |  |  |  | 1.5 | 10455542.78 | 9932765.64 | M/S Sakin Enterprise, Prop.Md.Shafiqul Islam,Nyare,Birkathi,Jhalakathi. |  | 2020-04-01 | 2020-07-30 |  | 100% | 6802486 |  |  |  | 394680 Evaluation on going
15 |  | Sub Total Tk= |  |  | 11.022 | 0 | 0 | 0 | 145.61 | 153787327.24 | 147783548.65 | [6 empty] | 101869271 |  | 35734504.89
95 |  | Grand Total Tk= |  |  | 66.795 | 4.735 | 2 | 1 | 753.99 | 800498133.171 | 751206461.78 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 556014436 | 0 | 191897241.583
[12 empty] | cÖKí ïiæ †_‡K Ryb/2020 ch©šÍ - cÖvß I LiP |  |  | 5433.38
| Accountant |  | Sub-Assistant Engineer | [8 empty] | Sr. Assistant Engineer |  |  |  |  | Executive Engineer
| LGED, Jhalakati |  | LGED, Jhalakathi | [8 empty] | LGED, Jhalakathi |  |  |  |  | LGED, Jhalakati

## Earth Work
ÒQKÓ
Òewikvj wefvM cjøx AeKvVv‡gv Dbœqb (2q ms‡kvwaZ)Ó kxl©K cÖK‡íi AvIZvq ev¯ÍevwqZ/ev¯Íevqbvaxb ¯‹xgmg~‡ni Z_¨vw`
Upto Month: February/2020
µwgK bs | ¯‹x‡gi bvg (AvBwW I c¨v‡KR mn) | wVKv`v‡ii bvg/ LCS Gi bvg | ¯‹xg Aby‡gv`b ¯§viK I ZvwiL | Pzw³g~j¨ | ms‡kvwaZ Pzw³g~j¨ | KvR ïiæi ZvwiL | KvR mgvwßi ZvwiL (cÖK…Z) | nvjbvMv` cwi‡kvwaZ UvKv | ‡fŠZ AMÖMwZ | Avw_©K AMÖMwZ | gšÍe¨
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 22
1 | Improvement of Atghor GC-Baligona R&H via Ramjankati Krishi Collage road By Earth Work at ch.00-1500m. (ID No.542402006) BDRIDP/JHL/SDR/UZ-Ew/02 | Md. Monjur Alam |  | 350979 |  | 2015-01-02 | 21-5-2015 | 350979 | 100%
2 | Improvement of road from South side of Sultan Mia's House to Galua Pir Shaheb House via Abdul Malek Master Bari road (Ch.00-800m) by BC Including a culvert. | Abul Kalam |  | 136225 |  | 20/04/14 |  | 136225 | 100%
3 | Improvement of road from Amena Khatun GPS via Imam uddin Baitul Jame Mosque-Galua Charakhali LGED road by Earth work from ch.1238-2319m (ID No.542844096) BDRIDP/JHL/RJP/CCA-Ew/03 | Md. Nasiruddin |  | 304209 |  | 28/12/2014 |  | 303591 | 100%
4 | Imprvement of road from Bashtala R&H to Napiterhat via Char Indropasha Ashraon road from ch.1024-2330m by Earth work with Connecting road at ch.1524m from 00-250m with Jame Mosque, Madrasha. BDRIDP/JHL/RJP/CCA-Ew/04 | Taslima Abida |  | 500000 |  | 28/12/2014 |  | 499333 | 100%
5 | Imprvement of road from Alamgir Chowdhuri Bari-South Pur road by Earth work form ch.00-635m (ID No. 542844114) BDRIDP/JHL/RJP/CCA-Ew/05 | Md. Alamgir Chowdhuri |  | 124529 |  | 23/02/2015 |  | 124158 | 100%
6 | Improvement of road from Mirerhat GC to Lebubunia GC via Galua UP (Rajapur-Kathalia RHD-Lebubunia GC via Galua UP) road by Earth work from ch.5357-7357m. BDRIDP/JHL/RJP/CCA-Ew/04 | Md. Fakrul Islam Khan |  | 500000 |  | 30/02/2015 |  | 499388 | 100%
7 | Improvement of road from Mirerhat-Nizamia-Boroia-Niamoti (Included Kacharibari hat Connection) From Jica Road ch.6050) road by Earth work from ch.00-690m. BDRIDP/JHL/RJP/CCA-Ew/04 | Md. Ahashan Karim |  | 159567 |  | 27/04/2015 |  | 158258 | 100%
8 | Improvement of Mollar hat R&H-Sreemontokathi-N. Pingri via Balarjore hat GC road by BC from ch.4800-5862m. BDRIDP/JHL/RJP/UZ-EW/02 | Md. Kamal Hossain |  | 391495 |  | 2015-12-01 |  | 390044 | 100%
9 | Improvement of Nizamia high School to North palot LG via Baroia high School by BC from ch.5700-6700m BDRIDP/JHL/RJP/UZ-Ew/03 | Md. Ahashan Karim |  | 450293 |  | 2015-12-02 |  | 449104 | 100%
10 | Improvement of Rajapur-Vandaria Highway road side Moulana Nurul Islam Howlader bari to Moulana Sekander ali howlader bari road from ch.00-1000m. BDRIDP/JHL/RJP/CCA-ew/06 | Moulana Nurul Islam |  | 291295 |  | 2015-11-28 |  | 290742 | 100%
11 | Improvement of Noikathi-Talukder hat (Jhalokathi part) road by BC from ch.3000-3796m BDRIDP/JHL/RJP/CCA-ew/01 BDRIDP/JHL/RJP/CCA-ew/01 | Md. Altaf Hossain H. |  | 202909 |  | 2015-12-03 |  | 201503 | 100%
12 | Improvement of road from Akoner hat-Hawladerhat via A. Rahim Khan house road by BC from ch.2250-3500m BDRIDP/JHL/RJP/CCA-ew/02 | Md. Nasir sikder |  | 249057 |  | 2015-12-10 |  | 247982 | 100%
13 | Rehabilitation of Gabkhan-Guaton via Sekerhat UP including Amrajhuri Road BY BC at ch.400-1400m. BDRIDP/JHL/SDR/UZ-ew/01 | Md. Sabur Khan |  | 291534 |  | 2016-01-05 |  | 291533 | 100%
14 | Improvement of road form citky R&H Road-Awrabunia GC road by BC from Ch.3000-4000m. BDRIDP/JHL/KTH/UZ-ew/01 | Md. Dalowear Hossain |  | 423733 |  | 20/02/16 |  | 423467 | 100%
15 | Improvement of road from Uttar Talgachia Cyclone Shelter Connecting Road by BC from ch.00-500m. 542435157 BDRIDP/JHL/KTH/CCA-ew/01 | Abdul Jalil |  | 329533 |  | 17/02/16 |  | 328738 | 100%
16 | Improvement of road from Uttar Talgachia Cyclone Shelter Connecting Road by BC from ch.500-1000m. 542435157 BDRIDP/JHL/KTH/CCA-ew/01 | Md. Faruk |  | 329533 |  | 17/02/16 |  | 326923 | 100%
17 | Resectiontion of Road from Rajapur Saturia Miarhat-Pangasia-Haldarkhali R&H via Lebubunia GC Road at ch.18890.00m-20150.00m (ID No-542842003) BDRIDP/JHL/RJP/UZ-ew/06 | Md. Nachar |  | 318417 |  | 18/04/16 |  | 317046 | 100%
18 | Resectiontion of Road from Rajapur Bazar Napiterhat-Sunder-Badurtala hat at ch.5835.00m-7885.00m (ID No-542843003) BDRIDP/JHL/RJP/UN-ew/01 | Md. Wazrul Islam |  | 400336 |  | 19/04/16 |  | 399227 | 100%
19 | Resectioning of road from Aurabunia GC to Mativanga via Satany Bazar Road at ch.1400m-2150m (ID No.542432007) BDRIDP/JHL/KAT/.UZ-Ew02 | Md. Yousuf Ali |  | 305118 |  | 18/04/2017 |  | 122047 | 100%
20 | Resectioning of road from Aurabunia GC to Mativanga via Satany Bazar Road at ch2150m-2900m (ID No.542432007) BDRIDP/JHL/KAT/.UZ-Ew03 | Md. Hasina Begom |  | 305117 |  | 18/04/2017 |  | 122046 | 100%
21 | Resectioning of road from Kailkhali GC- Amua GC Via Gosherhat Road at ch.1600m-2400m (ID No.542432005) BDRIDP/JHL/KTH/.UZ-Ew/03 | Jasmin |  | 222293 |  | 2017-12-03 |  | 88917 | 100%
22 | Resectioning of road from Kailkhali GC- Amua GC Via Gosherhat Road at ch.2400m-3200m (ID No.542432005) BDRIDP/JHL/KTH/.UZ-Ew/03 | Fathima Bagum |  | 229814 |  | 2017-12-04 |  | 91925 | 100%
23 | Resectioning of road from Kailkhali GC- Amua GC Via Gosherhat Road at ch.3200m-4500m (ID No.542432005) BDRIDP/JHL/KTH/.UZ-Ew/04 | Moreum Bagum |  | 140279 |  | 2017-12-05 |  | 56111 | 100%
24 | Resectioning of road from Kailkhali GC- Amua GC Via Gosherhat Road at ch.4500m-5844m (ID No.542432005) BDRIDP/JHL/KTH/.UZ-Ew/04 | Khohenur Bagum |  | 197496 |  | 2017-12-06 |  | 78998 | 100%
25 | Resectioning of road from Kailkhali GC- Amua GC Via Gosherhat Road at ch.00m-1600m (ID No.542432005) BDRIDP/JHL/KTH/.UZ-Ew/03 | Taslima |  | 145913 |  | 2017-12-03 |  | 58365 | 100%
26 | Resectioning of Simultala-Manpasa road at ch. 00-1200.00m (ID No. 54233006) under Nalchity Upazila. BDRIDP/JHL/Nal/UN-Ew01 | Auib Ali Howlader |  | 476494 |  | 2017-05-03 |  | 476494 | 100%
27 | Resectioning of Simultala-Manpasa road at ch. 1200-2030.00m (ID No. 54233006) under Nalchity Upazila. BDRIDP/JHL/Nal/UN-Ew02 | Rokon Uddin Howlader |  | 393669 |  | 2017-05-04 |  | 393669 | 100%
|  |  |  | 8169837 |  |  |  | 7226813
| wnmve iÿK |  |  | wmwbqvi mnKvix cÖ‡KŠkjx |  |  |  | wbe©vnx cÖ‡KŠkjx
| GjwRBwW, SvjKvVx |  |  | GjwRBwW, SvjKvVx |  |  |  | GjwRBwW, SvjKvVx